Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol

UNDP Annual Progress and Financial Report Narrative: 1991-2015

77th Meeting, 28 November – 2 December 2016, Montreal

I. INTRODUCTION

The following narrative is based on a database of 2,391 projects funded by the Multilateral Fund, which contains basic information on their status of implementation as of 31 December 2015.  However, some updates of activities which took place during the first quarters of 2016 are also included for information purposes.  The database results in 11 summary tables which can be found at the end of this report, and which are referred to throughout this narrative.

As can be seen in the following sections, UNDP has disbursed US$ 648,874,275 of the US$ 713,136,381 worth of projects that were approved under the Multilateral Fund since its inception in 1991. These programmes were supposed to eliminate 67,743 ODP T/year, of which 67,076 (99%) were phased out as of 31 December 2015. This demonstrates UNDP’s important role in the success of MLF’s assistance towards the elimination of Ozone Depleting Substances.

As of the end of 2016, UNDP was active in 46 countries, of which 21 are low volume consuming (LVCs). The vast majority of ongoing projects are implemented using the National Implementation modality, providing countries with larger country ownership.

A large portion of the current ongoing programmes consist of HCFC phase-out management plans (HPMPs).  For these, UNDP is the lead agency in 29 countries.  In addition, UNDP also acts as the cooperating agency for 18 countries.  In 2015, there were are only two remaining HPMPs (Mauritania and South Sudan), which were a part of UNDP’s business plan and which have not been submitted yet. However, the Stage I HPMP for South Sudan has been submitted for consideration of the Executive Committee at the 77th meeting.  While actions are being taken to allow submission of the remaining Stage I HPMP for Mauritania, it should be noted that the reason why this HPMP cannot be submitted lies beyond UNDP’s control.

There is a surge of workload for UNDP to meet the needs of so many HPMPs that are currently under implementation. This significant workload comes at a time that preparation of Stage II HPMPs is under way.  Most countries, for which UNDP is the lead agency, have submitted their requests for Stage II HPMP full proposals in 2015/2016 and five countries (Angola, Bangladesh, Democratic Republic of Congo, Nigeria, and Peru) are expected to submit their requests in 2017 and beyond.  Despite this challenging situation, UNDP, with its network of country offices, remains fully committed to meet the increased workload and ensure that countries receive the assistance needed to be in compliance with all requirements of the Montreal Protocol.

UNDP has also been at the forefront of technical assessments and demonstration projects for potentially cost-effective alternatives to HCFCs that minimize environmental impacts, particularly for those specific applications where such alternatives are not presently available and applicable.  Pursuant to ExCom decision 72/40, UNDP has submitted seven funding requests for the preparation of projects to demonstrate climate-friendly and energy-efficient alternative technologies to HCFCs, and feasibility studies on district cooling. All these projects were approved in 2015.

Finally, pursuant to the decision of XXVI/9 of the Twenty-Sixth Meeting of the Parties to the Montreal Protocol on Substances that Deplete the Ozone Layer, UNDP is also conducting twelve surveys of ODS alternatives, prioritizing the Foams, Refrigeration and Air Conditioning sectors in selected developing countries representing a balance of size and regional spread in order to: establish the market penetration of current commercially available alternatives, in terms of supply chain and costs, performance and environmental impact; and identify emerging alternatives, in terms of their expected market introduction and availability, performance and projected costs.  ODS alternative surveys have been approved for Bangladesh, Costa Rica, Cuba, Dominican Republic, El Salvador, India, Iran, Lebanon, Moldova, Panama, Paraguay, and Peru.

II. PROJECT APPROVALS AND DISBURSEMENTS

A.	Annual Summary Data (See table 1)

Table 1: “Annual Summary” shows the important summary data on the number of project approvals, corresponding budgets, ODP, and disbursement figures.  The table highlights that, cumulatively, as of 31 December 2015, UNDP had a total of 2,391 approved projects under the Multilateral Fund, of which 93 had been canceled or transferred. Of the 2,297 remaining projects, 2,121, or 92% have been completed.  They are set to eliminate 67,072 ODP T/year, of which 66,440 ODP T (99%) have already been eliminated.

As of 31 December 2015, UNDP had received cumulative net project approvals of US$ 713,136,381 (excluding support costs). Of these, UNDP, as of end-2015, had disbursed US$ 648,874,275 excluding all obligations.  This translates to 91% of approved funding.  This is the same as last year’s disbursement rate of 91%.  Furthermore, an additional US$ 557,166 of obligations were outstanding as of end-December 2015, representing orders placed but final payments not yet made

B.	Interest and Adjustments

Interest income earned on MLF resources in 2015 is US$ 505,346. Once the financial statements are submitted to the MLF Treasurer by the agreed deadline of 30 September, the difference between the provisional and final 2015 interest income can be adjusted against UNDP project approvals in 2016.

C.         Summary Data By Type and Chemical [CPG, DEM, INS, INV, PRP, TAS, TRA] (See table 2)

Table 2: Summary Data by Project Type presents an overview of the approvals by the type of project.  It demonstrates that of the total amounts approved, 82.2% of the budgets were dedicated to investment projects, 5.2% to technical assistance projects, 5.7% to institutional strengthening and 3.5% to project preparation activities. The remaining 3.3% was dedicated to country programmes and demonstration/training activities.

III. PROJECT COMPLETIONS SINCE LAST REPORT

A	ODP Phased Out from Completed Investment Projects

A total of 46 investment projects phasing out 802.00 ODP tonnes, comprising 1in aerosols, 1 in destruction, and 1 in phase-out plans were completed between 1 January and 31 December 2015.  The corresponding ODP tonnes phased out for these projects are 111.80 in aerosols, 45.3 in destruction, and 40.2 in phase-out plans.

B.	Non-Investment Project Completions Since The Last Report

A total of 23 non-investment projects, comprising 12 institutional strengthening phases, and 11 other activities were completed between 1 Jan and 31 Dec 2015.

IV. GLOBAL AND REGIONAL PROJECT HIGHLIGHTS

- Global Projects: There is one on-going global programmes under implementation by UNDP:

GLO/SEV/71/TAS/322, the Core unit support (2016) programme approved at the 75th meeting of  the Executive Committee, that covers the administrative costs of UNDP’s Montreal Protocol Unit; and

continuation of Core Unit support at a level that allows UNDP to provide the oversight, reporting and assistance needed to sustain the large programmer is critical.

- Regional Projects:  There are no ongoing regional projects at this time.

V. PERFORMANCE INDICATORS

A. 	Results in 2015

Decision 41/93 of the Executive Committee approved the following indicators to allow for the evaluation of performance of implementing agencies, with the weightings indicated in the table below.  Annex V of the report of the 73rd meeting of the Executive Committee contained UNDP’s 2015 targets. One can see from the table below that UNDP fully met 5 out of 9 of its targets and that its score amounts to 91%.

| Category of performance indicator | Item | Weight | UNDP’s target for 2015 | Result achieved in 2015 | Score |
| --- | --- | --- | --- | --- | --- |
| 1. Approval | Number of tranches approved vs. those planned* | 10 | 36 | 29 ( 81% (see annex 2, 1) | 8.1 |
| 2. Approval | Number of projects/activities approved vs. those planned (including project preparation activities)** | 10 | 19 | 39 ( 100% (see annex 2, 2) | 10.0 |
| 3. Implementation | Funds disbursed | 15 | $19 million | $32 million ( 100% (see annex 2, 3) | 15.0 |
| 4. Implementation | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans | 25 | 500.5 | 418.2( 84% (see annex 2, 4) | 20.1 |
| 5. Implementation | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 20 | 71 | 60( 85% (see annex 2, 5 ) | 16.9 |
| 6. Administrative | The extent to which projects are financially completed 12 months after project completion | 10 | 70% of those due | 32 finrevs out of 32 100% (see annex 2, 7) | 10.0 |
| 7. Administrative | Timely submission of project completion reports vs. those agreed | 5 | 70% of those due | 100% achieved (1 individual PCR submitted out of 1 planned -- see annex 2, 8) | 5.0 |
| 8. Administrative | Timely submission of progress reports and responses unless otherwise agreed | 5 | On-time | 100% achieved (see annex 2, 9) | 5.0 |
| TOTAL |  | 100 |  |  | 90.1 |

*The target of an agency would be reduced if it could not submit a tranche owing to another cooperating or lead agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

B.	Cumulative completed investment projects (Table 4)

As Table 4: Cumulative completed investment projects shows, a total of 1,134 investment projects have been completed, with a corresponding elimination of 61,052 ODP T.  Of the US$ 504,519,000 in their approved budgets in the sectors of Foam, Refrigeration, Phase-out Plan, Aerosol, Solvents, Fumigants, Halon, Process Agents, and Sterilants, 100% has already been disbursed.  It took an average of 13 months from approval to first disbursement and 33 months from approval to completion.  The overall cost-effectiveness of the projects to the Fund was $7.56 /kg. A breakdown of this group of projects is given by region, sector, implementation modality, etc.

C.	Cumulative completed non-investment projects (Table 5)

As Table 5 shows, UNDP has completed 513 non-investment projects excluding project preparation assistance.  Of the US$ 87,466,639 in their approved budgets, 100% has been disbursed. It took an average of 13 months from approval to first disbursement and 40 months from approval to completion. A breakdown of this group of projects is given by region, type, sector, implementation modality, etc.

D.	Cumulative ongoing investment projects (Table 6)

As can be seen in Table 6, UNDP has 68 ongoing investment projects in the sectors of Phase-out Plans, Foam

Aerosol, and Fumigants with corresponding budgets of US$ 76,396,577.  Of this amount, 40% has already been disbursed.   It takes an average of 13 months from approval to first disbursement and an average of 41 months from approval to the estimated project completion.  The overall cost-effectiveness of the projects to the Fund was $65.37 /kg. A breakdown of this group of projects is given by region, sector, implementation modality, etc.

E.	Cumulative ongoing non-investment projects (Table 7)

Table 7 shows that UNDP has 63 ongoing non-investment projects excluding project preparation assistance.  Of the US$ 15,646,280 in approved budgets, 16% has been disbursed.  It takes an average of 13 months from approval to first disbursement and 32 months from approval to the estimated project completion. A breakdown of this group of projects is given by region, type, sector, implementation modality, etc.

VI. STATUS OF AGREEMENTS AND PROJECT PREPARATION BY COUNTRY

- Agreements To Be Signed/Executed/Finalized

Since UNDP has a standard legal agreement in place in each developing country that covers UNDP activities in that country, no additional legal agreement is required.  There were no specific issues related to this in 2014.

- Project Preparation By Country, Approved Amount And Amount Disbursed (Table 8)

Table 8: Project Preparation by Country, Approved Amount and Amount Disbursed, indicates active project preparation accounts.  Of the ongoing 45 PRP projects listed with US$ 3,207,000 in associated approvals, 26% has been disbursed.

VII.	DESCRIPTION OF KEY ONGOING ACTIVITIES

This section contains a narrative description of the following key ongoing activities:

A. Technology demonstration projects

B. ODS destruction demonstration projects

C. Country Highlights

- Technology demonstration projects

UNDP has been at the forefront of developing and implementing demonstration projects in various regions and sectors to assess relatively new technological developments for which little or no experience or data exists on technical performance and costs since 1996.  The major objectives of such types of demonstrations were to find alternative solutions and cost-saving methods to the Multilateral Fund for the Implementation of the Montreal Protocol in order to carry out HCFC-investment activities in the future years, bearing in mind the impact on the climate. The results of the demonstrations of emerging technologies in various industrial processes under local conditions in the following countries are described below:

A1. Demonstrations related to Stage I HPMPs

Brazil and Mexico

Pilot projects for the assessment of alternative technologies in PU Foam Applications were approved in Brazil and Mexico to develop, optimize and assess the use of methyl formate and methylal as blowing agents in PU applications. As a result of the demonstration projects, methyl formate was selected as an alternative technology in Egypt, Mexico, Nigeria, Brazil, Jamaica, Trinidad and Tobago, Cameroon, and some other countries. System houses in both Mexico and Brazil have adopted methylal technology in their HPMPs as a result of the successful pilot project.

China

Foam Sector

The Executive Committee approved a demonstration project to convert HCFC-22/HCFC-142b technology to CO2 with methyl formate co-blowing technology in the manufacture of extruded polystyrene foam at Feininger (Nanjing) Energy Saving Technology Co. Ltd.  It can be concluded that the CO2 and methyl formate formulation tested can be applied to XPS manufacturing given that thermal conductivity, compression strength and limited oxygen index are acceptable. It was also determined that using methyl formate as the co-blowing agent of CO2 had no significant influence on the processing process of XPS board.

Refrigeration and Air Conditioning

### Demonstration project for conversion from HCFC-22 to HFC-32 in the manufacture of commercial air-source chillers/heat pumps at Tsinghua Tong Fang Artificial Environment Co. Ltd.: The project is the first in China to adopt HFC-32 in place of HCFC-22 in the production of small-sized commercial air-source chillers/heat pumps. The demonstration project has directly led to the use of HFC-32 as a major alternative to HCFC-22 in the industrial and commercial refrigeration sector plan of stage I of the HPMP for China. Further conversion activities to HFC-32 technology have been approved for the HPMP in Indonesia, Algeria and Thailand.

### Demonstration project for conversion from HCFC-22 technology to ammonia/CO2 technology in the manufacture of two-stage refrigeration systems for cold storage and freezing applications at Yantai Moon Group Co. Ltd: The capacity of the production line has been converted to use substitute refrigerants and is capable of manufacture the converted products. The project has passed the national acceptance verification. The converted products have been put into use by users in Yantai, Weihai and Dalian. The market has expressed interest. The technology route is innovative, the resulting product has significant advantages in terms of environment friendliness and energy efficiency, and the safety performance is greatly improved.

Solvents

The Executive Committee approved a demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd.  The project carried out an assessment of more than 15 solvents widely used in the medical devices sector globally. The project tested the use of KC-6 as an alternative to HCFC-141b.  With necessary equipment modifications for needle assembly lines and silicification tooling cleaning line KC-3 presents itself as a viable alternative to HCFC-141b for cleaning in the manufacture of medical devices.

Colombia

The Executive Committee approved the assessment project for supercritical CO2 technology in the manufacture of sprayed polyurethane rigid foams in Colombia. The project was designed to evaluate in developing countries the performance of super-critical CO2, a relatively new technology currently used in Japan for polyurethane (PU) spray rigid foam. Results from this project showed that supercritical CO2 technology is a non-flammable, zero ODP and low GWP technology and it shouldn’t create any additional industrial hygiene and safety hazards for the use as a replacement for HCFC-141b technology.

Egypt
Low cost options for the use of Hydrocarbons (HC) as foaming agents in the manufacture of PU Foam were considered as part of a demonstration project in Egypt. The objective of this project was to develop, optimize, and disseminate low-cost systems for the use of hydrocarbons in the manufacture of PU rigid insulation and integral skin foams. Both options that are emerging from the project—pre-blended cyclopentane systems and direct HC injection—have been selected for ODS phase-out projects in Brazil and Egypt. The findings of the demonstration project show that further mixing head optimization would be beneficial and might enhance the foam densities and reduce operational costs.  This optimization was finalized at a system house in Egypt with the complementary report with additional findings submitted in 2015.

Nigeria

The hydrocarbon production demonstration project, being implemented at Pamaque Ltd as part of the HPMP in Nigeria (Stage 1), has been completed in its pilot phase in 2015, and the pilot plant commissioned on 19 November 2015. The establishment of the distillation and bottling unit has proved to be functional and safe. The commercial production is linked to private sector’s further involvement and investment and work and consultations are still ongoing in this regard. Replication abroad is also being considered. A side event on the project was organized by UNDP and the Government of Nigeria at the 27th MOP in Dubai (1-5 November 2015) and a final report of this pilot demonstration project was submitted as an Annex to the request for the 5th tranche of the first stage of the HPMP, approved at the 75th ExCom Meeting.

Turkey

A pilot project validating the use of HFO-1234ze as Blowing Agent in the Manufacture of Extruded Polystyrene (XPS) Foam Boardstock in Turkey was designed to assess the use of HFO-1234ze in a developing country context. All planned production trials have been completed in 2011 and early 2012 and a final assessment was submitted to the 67th ExCom.  The current findings show that there is a need for further trials as this will help obtain better assessment of the feasibility of the technology for developing countries. Unfortunately, funding for these additional activities was not approved so that no final conclusions about the technical feasibility of this technology could be arrived at.

A2. Demonstrations related to Stage II HPMPs

Pursuant to ExCom decision 72/40, UNDP is preparing additional projects to demonstrate climate-friendly and energy-efficient alternative technologies to HCFCs, and feasibility studies on district cooling. UNDP has prepared and received approval for eight demonstration projects for the following seven countries:

- China: demonstrating ammonia semi-hermetic frequency convertible screw refrigeration compression unit in the industrial and commercial refrigeration industry;

- Colombia: HC-290 (propane) is being tested as an alternative refrigerant in commercial air-conditioning manufacturing; and validation of the use of hydrofluoro-olefins for discontinuous panels in Article 5 parties through the development of cost-effective formulations;

- Costa Rica: testing the application of an ammonia/carbon dioxide refrigeration system in replacement of HCFC-22 for the medium-sized producer and retail store of Premezclas Industriales S.A.

- Dominican Republic: feasibility study for district cooling in Punta Cana;

- Egypt: demonstrating low-cost options for the conversion to non-ODS technologies in polyurethane foams at very small users;

- Kuwait: demonstrating HCFC-free low-global warming potential technology performance in air-conditioning applications; and

- Maldives: testing HCFC-free low-global warming potential alternatives in refrigeration in fisheries sector are being tested.

- ODS destruction demonstration projects

The UNDP Montreal Protocol & Chemicals Unit has been supporting countries to assist them to manage their stocks of ODS, which cannot be reused in a sound way. The potential for recovery, proper management and final disposal of such unwanted ODS and ODS containing appliances/equipment banked, have been proven as being possible in developed countries if the proper legislation and price incentives, as well as business opportunities, exist. However, the applicability of banks management schemes in developed countries needs to also be demonstrated in Article 5 countries. The Executive Committee has approved preparation activities for Brazil, Colombia, Cuba, Georgia, Ghana and India, to address ODS waste management leading to ODS destruction. Five such projects (Brazil, Colombia, Cuba, Georgia, and Ghana) have been submitted and approved by the Executive Committee in prior years.  Progress is still ongoing in these projects and it is still too early to determine conclusive results at this stage.  Nonetheless, an important conclusion from Ghana and Georgia is that for LVCs, in particular, the least cost option is export in combination with other hazardous waste (i.e. POPs), thus calling for integrated action with other chemical conventions.

C.  	Country Highlights (January – December 2015)

UNDP has been at the forefront of innovative solutions for countries to address their Montreal Protocol compliance obligations. UNDP’s work has resulted in market transformation for the introduction of environment-friendly products and corresponding policy and technological advances and has bought to countries access to emerging technologies, reduced energy bills for consumers, fostered innovation, and created a more equitable market for greener products, allowing indigenous manufacturers to maintain competitiveness.

The next section showcases several prominent examples showing the impact of UNDP’s support at the country level.

Colombia

The demonstration project for Industrias Thermotar Ltda. in Colombia was approved at the 75th meeting of the ExCom under the $10 million funding window that was set up to demonstrate low GWP alternatives, especially in the RAC manufacturing sector. This is a demonstration project for the use of R-290 (propane) as an alternative refrigerant in the commercial air conditioning manufacturing with ranges between 3.5 kW (1 ton of refrigeration) and 17.5 kW (5 tons of refrigeration), contributing to the elimination of HCFC-22 use in this RAC subsector. This project seeks to demonstrate the safe use of HC as a low GWP option for the manufacturing of commercial air-conditioning equipment that will be used in tropical areas of the Article 5 parties. Modifications in different production operations, such as refrigerant storage stations, HC feed lines, vacuum stations, HC charging station and the design modifications that will be undertaken as well as unit testing, will be considered. Moreover, training for operators and technical assistance to end users will be introduced to improve the complete framework of risk management. This project is expected to generate significant new knowledge about the safe use of HCs in the commercial AC sector in tropical climates in A5 countries.

Dominican Republic

At the 74th meeting of the ExCom in May 2015, funds were approved for the business case/feasibility study for establishing a district cooling solution in the area owned by the Puntacana Foundation. The area includes two airport terminals, a shopping mall, 3 hotels and a new supermarket, and has the potential to be further expanded in the future. District Energy Venture (DEVCCO) from Sweden has been hired by UNDP to assist with the preparation of the business case study, and will hopefully trigger a large investment from the Puntacana Foundation for the benefit of the environment.  A side event on district cooling was organized on the sidelines of the OEWG in Aprl 2016 in Geneva.

Egypt

As a part of the Stage 1 HPMP, the Government of Egypt and UNDP have successfully completed all approved individual PU foam programmes – 6 enterprises have transitioned to non-ODP/low GWP technologies such as methyl formate and hydrocarbons (HC). The results of previous low-cost HC demonstration programme were useful in addressing HCFC-141b consumption in PU foam companies with lower HCFC use, where otherwise HC technologies would not be implemented due to higher capital costs. At this moment, activities are focused on the system house level with polyol blending enterprises participating and initiating chemical formula preparation with methyl formate, methylal and other technologies to transfer them to downstream users. Uniform advances with system houses are the current objective to attempt a market-wide shift towards non-ODP/low GWP alternatives.

Kyrgyzstan

In 2015, the Government of Kyrgyzstan and UNDP/UNEP jointly formulated an accelerated HCFC phase-out programme to achieve by 2020 a 97.5% reduction in the servicing sector with a service tail of 2.5% remaining until 2025. This HCFC reduction ahead of usual phase-out time was a decision of the Government based on its accession to the Customs Union’s framework constituted by Art 2 group of countries in the former Soviet Union where HCFCs use is controlled by accelerated schedules and this recommendation was adopted by Kyrgyzstan for its own context. The Stage II HPMP programme was approved in May 2015 and is now in its first implementation phase on the ambitious path towards substantive HCFC phase-out by 2020. The programme had its inception round of workshops, and plans for an initial R&R tool procurement round to further strengthen the country’s capability to address its dependence on HCFCs are underway.

India

UNDP worked closely with India Government on the completion of systems house project.  This project was a part of the HPMP and would assist the enterprises in developing HCFC free, low GWP formulations.  During Q4 of 2015, detailed consultations were held with systems houses in the country who were beneficiaries to this project.  During the discussion, besides completion of systems house project elements, UNDP shared experiences on how systems house phase-out is progressing in different countries in the region and also highlighted the importance of policies/regulations to eliminate use of HCFC-141b in polyol systems produced and sold in the domestic market.  There were various questions discussed relating to technology evolution, costs and assistance that could be offered by the large systems houses in the process of developing low GWP HCFC polyol systems.  With full support from the Government, the larger systems house agreed to support technology transfer though the specifics need to be discussed individually with the respective systems houses on a case-by-case basis.  There was also agreement on considering phase-out of HCFC-141b in new polyol systems during the period 2017-2019.  The systems houses also agreed to this accelerated phase-out related consultations during HPMP Stage-II discussions that are currently underway.

Dubai side event on RAC technology adoption in India

This was an important side event organized during the MOP in Dubai in November 2015.  The side event was primarily designed to show actual experiences of Indian industry in adoption of HCFC free technologies in residential air-conditioning applications.  The side event was organized in close consultation with the industry association in India, industrial enterprises producing R-290 and HFC-32 based air-conditioners and National Ozone Unit which supports technology adoption in the country.  This side event was well attended by a range of stakeholders and had over 70 participants.  Information on adoption of low GWP flammable technologies and their use in Indian market was shared by the respective manufacturers.  The side event, which mainly presented the India case, provided an opportunity for other NOUs to understand the key parameters relating to the adoption of low GWP technologies and network with industry players so that the countries could move forward on adopting low GWP technologies.

VIII. ADMINISTRATIVE ISSUES (OPERATIONAL, POLICY, FINANCIAL, OTHER)

##### Meetings Attended by UNDP in 2015

| From | To | Location | Description |
| --- | --- | --- | --- |
| 26-Jan-15 | 2-Feb-15 | India | Policy Support and Programme Oversight |
| 8-Feb-15 | 14-Feb-15 | Kyrgyzstan | Policy Support and Programme Oversight |
| 9-Feb-15 | 13-Feb-15 | Brazil | Policy Support and Programme Oversight |
| 18-Feb-15 | 20-Feb-15 | Cuba | Policy Support and Programme Oversight |
| 25-Feb-15 | 27-Mar-15 | Bahamas | Regional Network meeting for English speaking LAC |
| 26-Feb-15 | 27-Feb-15 | Canada | MPU Interagency coordination meeting |
| 10-Feb-15 | 13-Feb-15 | Ghana | Policy Support and Programme Oversight |
| 15-Feb-15 | 19-Feb-15 | Indonesia | Policy Support and Programme Oversight |
| 23-Feb-15 | 27-Feb-15 | Brunei | Policy Support and Programme Oversight |
| 9-Mar-15 | 14-Mar-15 | Korea | Joint Network Meeting of SA and SEAP |
| 14-Mar-15 | 19-Mar-15 | Angola | Policy Support and Programme Oversight |
| 15-Mar-15 | 20-Mar-15 | Iran | Policy Support and Programme Oversight |
| 18-Mar-15 | 19-Mar-15 | Brazil | Policy Support and Programme Oversight |
| 22-Mar-15 | 27-Mar-15 | Bahrain | Inter-agency & coordination meeting |
| 22-Mar-15 | 28-Mar-15 | China | Policy Support and Programme Oversight |
| 11-Apr-15 | 14-Apr-15 | Bangladesh | Policy Support and Programme Oversight |
| 14-Apr-15 | 22-Apr-15 | Egypt | Policy Support and Programme Oversight |
| 20-Apr-15 | 24-Apr-15 | Thailand | OEWG meeting and HFC workshop |
| 16-May-15 | 23-May-15 | Canada | 74th Executive Committee Meeting |
| 21-May-15 | 22-May-15 | Peru | Policy Support and Programme Oversight |
| 25-May-15 | 27-May-15 | Mexico | Policy Support and Programme Oversight |
| 1-Jun-15 | 3-Jun-15 | Chile | Policy Support and Programme Oversight |
| 8-Jun-15 | 12-Jun-15 | Venezuela | Policy Support and Programme Oversight |
| 11-Jun-15 | 15-Jun-15 | Brussels | Resource Mobilization |
| 18-Jun-15 | 19-Jun-15 | Costa Rica | Policy Support and Programme Oversight |
| 24-Jun-15 | 26-Jun-15 | Colombia | Policy Support and Programme Oversight |
| 30-Jun-15 | 2-Jul-15 | Uruguay | Policy Support and Programme Oversight |
| 30-Jun-15 | 1-Jul-15 | Ghana | Policy Support and Programme Oversight |
| 1-Jul-15 | 9-Jul-15 | China | Policy Support and Programme Oversight |
| 6-Jul-15 | 10-Jul-15 | Moldova | Policy Support and Programme Oversight |
| 10-Jul-15 | 11-Jul-15 | India | Policy Support and Programme Oversight |
| 22-Jul-15 | 26-Jul-15 | France | 36th OEWG Meeting |
| 29-Jul-15 | 30-Jul-15 | Brazil | Policy Support and Programme Oversight |
| 29-Jul-15 | 6-Aug-15 | Lebanon | Policy Support and Programme Oversight |
| 17-Aug-15 | 21-Aug-15 | Indonesia | Policy Support and Programme Oversight |
| 24-Aug-15 | 25-Aug-15 | Peru | Policy Support and Programme Oversight |
| 31-Aug-15 | 1-Sep-15 | Canada | Montreal Protocol interagency coordination meeting |
| 8-Sep-15 | 10-Sep-15 | Costa Rica | Policy Support and Programme Oversight |
| 14-Sep-15 | 16-Sep-15 | Dominican Republic | Policy Support and Programme Oversight |
| 21-Sep-15 | 25-Sep-15 | Brazil | Febrava and Conbrava conferences |
| 13-Sep-15 | 19-Sep-15 | China | Policy Support and Programme Oversight |
| 26-Sep-15 | 28-Sep-15 | Germany | Resource Mobilization |
| 4-Oct-15 | 16-Oct-15 | Delhi | Policy Support and Programme Oversight |
| 13-Oct-15 | 15-Oct-15 | Belarus | Policy Support and Programme Oversight |
| 12-Oct-15 | 16-Oct-15 | Senegal | Regional Ozone Network meeting for Africa |
| 28-Oct-15 | 4-Nov-15 | UAE | 55th Implementation Committee, 36th OEWG and 27th Meeting of Parties on Montreal Protoco |
| 8-Nov-15 | 14-Nov-15 | Timor Leste | Policy Support and Programme Oversight |
| 16-Nov-15 | 21-Nov-15 | Nigeria | Policy Support and Programme Oversight |
| 11-Nov-15 | 12-Nov-15 | Colombia | Policy Support and Programme Oversight |
| 16-Nov-15 | 21-Nov-15 | Canada | 75th Meeting of the Executive Committee and the Climate and Clean Air Coalition (CCAC) Workshop |
| 23-Nov-15 | 27-Nov-15 | Chile | Policy Support and Programme Oversight |
| 23-Nov-15 | 25-Nov-15 | Peru | Policy Support and Programme Oversight |
| 27-Nov-15 | 30-Nov-15 | Iran | Policy Support and Programme Oversight |
| 30-Nov-15 | 4-Dec-15 | Brunei | Policy Support and Programme Oversight |
| 1-Dec-15 | 4-Dec-15 | Malaysia | Policy Support and Programme Oversight |

##### Other Issues.

There were no specific issues in 2015 that need to be addressed

ANNEX 1: Tables related to the Performance Indicators

- Performance Indicator 1: MYAs

Approvals for multi-year agreements are listed in the following table.

| Country | Short Title |
| --- | --- |
| Angola | Stage I HPMP |
| Brazil | Stage I HPMP |
| Brazil | Stage II HPMP |
| Brunei Darussalam | Stage I HPMP |
| China | Stage I HPMP (Solvents) |
| China | Stage I HPMP (ICR) |
| Colombia | Stage II HPMP |
| Costa Rica | Stage I HPMP |
| Dominican R | Stage I HPMP |
| El Salvador | Stage I HPMP |
| Guyana | Stage II HPMP |
| India | Stage I HPMP |
| India | Accelerated CFC production phase-out (second tranche) |
| India | Accelerated CFC production phase-out (remaining of the second tranche) |
| India | CTC phase-out plan for the consumption and production sectors: 2009 annual programme |
| Iran | Stage I HPMP |
| Kyrgyzstan | Stage II HPMP |
| Lebanon | Stage I HPMP |
| Lebanon | Stage II HPMP |
| Malaysia | Stage I HPMP |
| Mexico | Stage I HPMP |
| Moldova | Stage I HPMP |
| Nepal | Stage I HPMP |
| Nigeria | Stage I HPMP |
| Panama | Stage I HPMP |
| Paraguay | Stage I HPMP |
| Peru | Stage I HPMP |
| Trin/Tobago | Stage I HPMP |

- Performance Indicator 2: Individual Projects

The number of individual projects approved in 2015 are listed in the following table.

| Country | Short Title |
| --- | --- |
| ¦¦Global | Core unit budget (2016) |
| Angola | Stage II HPMP Preparation |
| Bangladesh | Stage II HPMP Preparation |
| Bangladesh | Stage II HPMP Preparation (refrigeration and air-conditioning sector) |
| Bangladesh | Survey of ODS alternatives at the national level |
| Brazil | Several Ozone unit support |
| Chile | Several Ozone unit support |
| China | PRP for demo for ammonia semi-hermetic frequency convertible screw refrigeration system in industrial and commercial refr |
| Colombia | Several Ozone unit support |
| Colombia | Demonstration of HC-290 (propane) as an alternative refrigerant in commercial air-conditioning manufacturing at Industrias Thermotar ltda |
| Costa Rica | Several Ozone unit support |
| Costa Rica | PRP for demo for transition of HCFC-22-based refrigerant unit to NH3 system in cold chambers |
| Costa Rica | ODS alternatives survey |
| Costa Rica | Verification report for HPMP Stage I |
| Cuba | Several Ozone unit support |
| Cuba | Survey of ODS alternatives at the national level |
| Dominican R | Feasibility study for district cooling in Punta Cana |
| Dominican R | Survey of ODS alternatives at the national level |
| Egypt | Stage II HPMP Prep |
| Egypt | Stage II HPMP Prep (foam) |
| Egypt | Stage II HPMP Prep (XPS) |
| El Salvador | ODS alternatives survey |
| Georgia | Several Ozone unit support |
| Georgia | Verification report for HPMP Stage I |
| India | PRP for demo for development and evaluation of spray foam polyol systems for buildings using HFOs as blowing agent |
| India | ODS alternatives survey |
| Indonesia | Several Ozone unit support |
| Iran | ODS alternatives survey |
| Kuwait | PRP for demo for low- GWP alternatives in high ambient temperature conditions in air-conditioning applications |
| Lebanon | ODS alternatives survey |
| Malaysia | Several Ozone unit support |
| Maldives | PRP for demo for low-GWP alternatives for HCFC phase-out in refrigeration applications in fishing industry |
| Moldova | Survey of ODS alternatives at the national level |
| Panama | Several Ozone unit support |
| Panama | ODS alternatives survey |
| Paraguay | Survey of ODS alternatives at the national level |
| Peru | Stage II HPMP Preparation |
| Peru | Survey of ODS alternatives at the national level |
| Uruguay | Several Ozone unit support |

- Performance Indicator 3: Funds disbursed

| 2015 Disbursements | 32,005,542 |
| --- | --- |

- Performance Indicator 4: 2015 ODS phase-out

| MLF Number | Short Title | ODP to be Phased Out |
| --- | --- | --- |
| ANG/PHA/75/INV/16 | Stage I HPMP (third tranche) | 1.6 |
| BRA/PHA/74/INV/307 | Stage I HPMP (4th tranche, foam) | 32.9 |
| BRA/PHA/75/INV/312 | Stage II HPMP (first tranche) (foam sector) | 40.8 |
| BRA/PHA/75/INV/315 | Stage I HPMP (fifth tranche) (foam sector) | 54.5 |
| BRA/PHA/75/TAS/313 | Stage II HPMP (first tranche) (refrigeration servicing, regulatory actions and project monitoring) | 4.4 |
| BRU/PHA/74/INV/17 | Stage I HPMP (2nd tranche, foam) | 0 |
| COL/PHA/75/INV/96 | Stage II HPMP (first tranche) (refrigeration servicing sector) | 6.9 |
| COL/PHA/75/INV/98 | Stage II HPMP (first tranche) (foam sector) | 48.2 |
| COL/PHA/75/TAS/91 | Stage II HPMP (first tranche) (project management, monitoring and coordination) | 0 |
| COL/PHA/75/TAS/92 | Stage II HPMP (first tranche) (technical assistance in policies formulation and implementation) | 1.6 |
| COL/PHA/75/TAS/94 | Stage II HPMP (first tranche) (technical assistance for fire protection sector) | 6.8 |
| COS/PHA/74/INV/50 | Stage I HPMP (3rd tranche) | 1.4 |
| CPR/PHA/75/INV/567 | Stage I HPMP (fifth tranche) (industrial and commercial refrigeration and air conditioning sector plan) | 38.2 |
| CPR/PHA/75/INV/569 | Stage I HPMP (third tranche) (solvent sector) | 0 |
| DOM/PHA/74/INV/58 | Stage I HPMP (3rd tranche, servicing) | 0 |
| EGY/PHA/74/PRP/126 | Stage II HPMP Prep | 0 |
| ELS/PHA/74/INV/31 | Stage I HPMP (2nd tranche) | 0 |
| GUY/PHA/75/INV/28 | Stage II HPMP (first tranche) | 0.2 |
| IND/PHA/75/INV/463 | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | 0 |
| IND/PHA/75/INV/464 | Stage I HPMP (third tranche) (polyurethane foam sector plan and project monitoring) | 47.8 |
| IND/PRO/75/INV/462 | Accelerated CFC production phase-out (second tranche) | 0 |
| IRA/PHA/74/INV/219 | Stage I HPMP (4th tranche, ac and pmu) | 0 |
| KYR/PHA/74/INV/34 | Stage II HPMP (1st tranche) | 1.3 |
| LEB/PHA/74/INV/84 | Stage I HPMP (3rd tranche) | 0 |
| LEB/PHA/75/INV/85 | Stage II HPMP (first tranche) (foam sector) | 19.1 |
| LEB/PHA/75/INV/86 | Stage II HPMP (first tranche) (air conditioning sector) | 5 |
| LEB/PHA/75/INV/87 | Stage II HPMP (first tranche) (refrigeration servicing sector) | 5.7 |
| LEB/PHA/75/TAS/88 | Stage II HPMP (first tranche) (project management and coordination) | 0 |
| MAL/PHA/75/TAS/179 | Stage I HPMP (third tranche) (refrigeration servicing, management and coordination) | 9.5 |
| MEX/PHA/75/INV/178 | Stage I HPMP (fifth tranche) (foam sector plan for systems houses and local customers) | 30 |
| MOL/PHA/74/INV/31 | Stage I HPMP (2nd tranche) | 0 |
| NEP/PHA/75/INV/35 | Stage I HPMP (second tranche) | 0.1 |
| NIR/PHA/75/INV/143 | Stage I HPMP (fifth tranche) (foam sector and refrigeration servicing) | 56 |
| PAN/PHA/74/INV/39 | Stage I HPMP (3rd tranche) | 0 |
| PAR/PHA/74/INV/34 | Stage I HPMP (2nd tranche) | 2.1 |
| PER/PHA/75/INV/48 | Stage I HPMP (second tranche) (refrigeration servicing sector) | 2.2 |
| TRI/PHA/75/INV/33 | Stage I HPMP (third tranche) | 0 |
| URU/PHA/75/INV/66 | Stage I HPMP (fifth tranche) | 1.9 |

- Performance Indicator 5: Projects completed in 2015.

The following 60 projects were completed in 2015:

| MLF Number | Actual Completion Date |
| --- | --- |
| ANG/PHA/65/INV/10 | Dec-15 |
| ANG/PHA/73/TAS/13 | Dec-15 |
| ARM/PHA/73/TAS/13 | Nov-15 |
| BHU/PHA/70/INV/19 | Sep-15 |
| BRA/PHA/64/INV/295 | Jul-15 |
| BRA/PHA/68/INV/298 | Dec-15 |
| BRU/PHA/66/INV/13 | May-15 |
| BZE/PHA/62/INV/26 | Jan-15 |
| CHI/PHA/63/INV/174 | Nov-15 |
| CHI/SEV/69/INS/177 | Mar-15 |
| COL/PHA/66/INV/81 | Jan-15 |
| COL/REF/47/DEM/65 | Dec-15 |
| COS/SEV/71/INS/49 | Dec-15 |
| CPR/PHA/64/INV/515 | May-15 |
| CPR/PHA/65/INV/519 | May-15 |
| CPR/PHA/68/INV/525 | Dec-15 |
| CPR/PHA/71/INV/537 | Dec-15 |
| CUB/DES/62/DEM/46 | Oct-15 |
| CUB/PHA/65/INV/49 | Jul-15 |
| DOM/PHA/65/INV/49 | Dec-15 |
| DOM/PHA/69/INV/53 | Sep-15 |
| DOM/PHA/69/INV/54 | Sep-15 |
| EGY/FOA/58/DEM/100 | Dec-15 |
| ELS/PHA/65/INV/29 | Nov-15 |
| ELS/PHA/65/INV/30 | Nov-15 |
| GEO/DES/69/DEM/33 | Dec-15 |
| GEO/PHA/63/INV/30 | Mar-15 |
| GEO/SEV/69/INS/34 | Dec-15 |
| GLO/SEV/73/TAS/324 | Dec-15 |
| IDS/PHA/64/INV/195 | May-15 |
| IDS/PHA/64/TAS/192 | May-15 |
| IDS/SEV/71/INS/201 | Dec-15 |
| IND/ARS/56/INV/423 | Dec-15 |
| IND/PHA/66/INV/441 | May-15 |
| IND/PHA/66/TAS/440 | Nov-15 |
| IND/SEV/66/INS/444 | Dec-15 |
| IRA/PHA/68/INV/208 | Apr-15 |
| IRA/PHA/72/INV/211 | Dec-15 |
| IRA/SEV/67/INS/206 | Jun-15 |
| JAM/PHA/64/INV/29 | May-15 |
| KAM/PHA/61/INV/24 | Dec-15 |
| KYR/PHA/72/INV/29 | Oct-15 |
| LEB/PHA/70/INV/78 | Dec-15 |
| LEB/SEV/68/INS/77 | Sep-15 |
| MAL/PHA/65/TAS/170 | Apr-15 |
| MAL/SEV/64/INS/167 | Jun-15 |
| MAL/SEV/70/INS/171 | Dec-15 |
| MDV/PHA/53/INV/15 | May-15 |
| MEX/PHA/68/INV/165 | Dec-15 |
| MOL/PHA/63/INV/25 | Nov-15 |
| PAK/SEV/68/INS/82 | Sep-15 |
| PAN/PHA/70/INV/34 | Nov-15 |
| PAN/PHA/74/INV/39 | Dec-15 |
| PAR/PHA/63/INV/29 | Aug-15 |
| SRL/PHA/62/INV/40 | Dec-15 |
| TRI/PHA/64/INV/27 | Jun-15 |
| TRI/SEV/68/INS/29 | Dec-15 |
| URU/PHA/71/INV/59 | Dec-15 |
| URU/PHA/73/INV/63 | Apr-15 |
| URU/SEV/71/INS/60 | Dec-15 |

7.  Performance Indicator 7:  Final Revisions

Last year’s database counted 46 projects operationally completed before 1 Jan 2015, which could have been financially completed in 2015.  This year’s database counts 32 projects for which a final revision was issued in 2015, which equals 70% of our target.

8.  Performance Indicator 8:  PCRs

100% achieved (2 multi-year PCRs and 1 individual PCR submitted out of 3 PCRs scheduled for submission in 2015).

9.  Performance Indicator 9

Progress Report produced on 5 September 2016 as required.