|  |  |  |
| --- | --- | --- |
| **UNITED NATIONS** | | **EP** |
| UNEP | **United Nations**  **Environment**  **Programme** | Distr.  GENERAL  UNEP/OzL.Pro/ExCom/82/24/Corr.1  30 November 2018  ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF  
 THE MULTILATERAL FUND FOR THE  
 IMPLEMENTATION OF THE MONTREAL PROTOCOL  
Eighty-second Meeting

Montreal, 3-7 December 2018

Corrigendum

TRANCHE SUBMISSION DELAYS

# This corrigendum is being issued to standardize the recommendations in Annex I for Algeria, Antigua and Barbuda and the Central African Republic to be consistent with the recommendations contained in relevant progress reports as at 31 December 2017 as follows:

| **Country** | **Agency** | **Tranche** | **Amount (with support costs)**  **(US $)** | **Reason for delay/withdrawal** | **Recommendations** |
| --- | --- | --- | --- | --- | --- |
| Algeria (Stage I) | UNIDO | 2014 | 154,800 | Government decisions/endorsements/ changes in the national ozone unit (NOU)/structural change | Noting the ongoing difficult circumstances in the country and to request the Secretariat to send a letter to the Government of Algeria seeking its agreement to cancel stage I of the HPMP at the 83rd meeting and to return the remaining balances to the 84th meeting so that a proposal for stage II of the HPMP could be submitted when conditions permit. |
| Antigua and Barbuda (Stage I) | UNEP | 2015 | 6,610 | Government decisions/endorsements/ changes in the NOU/structural change/ submission of progress and financial reports/internal or external difficulties | Noting that the second (2015) tranche of stage I of the HPMP for Antigua and Barbuda had not been submitted due to structural changes within the Government and to cancel stage I of the HPMP at the 82nd meeting and to return the remaining balances to the 83rd meeting, noting that stage II of the HPMP would take into consideration decision XXIX/19 on special considerations for the Caribbean islands affected by hurricanes. |
| Central African Republic (the)  (Stage I) | UNEP | 2013 | 62,150 | Internal or external difficulties/securities issues/20 per cent disbursement threshold | Noting the ongoing difficult circumstances in the country and to cancel stage I of the HPMP for the Central African Republic at the 82nd meeting and to return the remaining balances to the 83rd meeting so that a proposal for stage II of the HPMP could be submitted when conditions permit. |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |