## Delays
Code | Agency | Project Title | Category of Delays | Progress Report to the 44th Meeting | Final Assessment | Milestones and Deadlines | Category of Delay
CHI/REF/35/TAS/147 | Canada | Implementation of the RMP: recovery and recycling programme | Status Report | This component of the Chile RMP was approved by the Executive Committee on the understanding that the project will not commence until the legislation controlling CFC import will be in place and the price of CFCs increase to a level equivalent to the local market price of non-ODS refrigerants. As Chile has not yet put this legislation into place, the component can not be initiated. However, progress has been made in the implementation of other components of the RMP, including training of 800 refrigeration technicians, development of a code of good practice and equipping 7 training centres across the country with tools and equipment for ongoing technician training. | No additional status report required
STK/REF/24/TAS/04 | Canada | Refrigerant Management Plan (RMP) for St.Kitts and Nevis | Status Report | Implementation of the Training of Customs Officers and Recovery and Recycling (R&R) components of this RMP were awaiting the adoption by the Government of appropriate legislation to control CFC imports. This legislation was adopted during the first half of 2004 and activities are now being planned to complete the RMP. A shipment of R&R equipment to St.Kitts and Nevis has been arranged and an R&R training workshop is scheduled for October 28-29, 2004. The training of customs officers will be held subsequently and is expected to be completed by approximately April 2005. | No additional status report required
IRA/SEV/26/TAS/36 | France | Small and medium enterprises study | 18 months delays | This project was interrupted because the Islamic Republic of Iran considered it unnecessary when the NPP was approved. A report has been requested in order to proceed with the cancellation of the project. | No Progress | Request report at the Meeting on possible canellation | D
LEB/REF/28/TAS/29 | France | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers | 12 months delays | FFEM/AfD is waiting for the Lebanese government to start with the R&R project (23/TAS/21) in order to implement this project. There has been some progress regarding the financial agreement in between Lebanon and France. This document should be signed very soon. | Some Progress |  | D
MOR/FUM/29/INV/37 | France | Phase-out of methyl bromide use in the cut flower and banana production | 18 months delays | The first project results show a decrease in MB use, mainly in the cut flower sector. The equipment has been bought and adapted. An evaluation is scheduled for October 2004 by UNIDO, which implements the proejct on behalf AfD. Additional Comments: Date of completion per proposal is Dec 03, and Planned date of completion is April 05, therefore 18 months delay in neither case. | Some Progress |  | C
MOR/REF/32/TAS/42 | France | Technical assistance for cold storage – Training and demonstration project | 12 months delays | April 2004: Official launch in Casablanca of the Awareness part of the project: 50 participants. May 2004: Local Technical Assistance Facility (TAF) established a detailed operating plan. 6 training sessions were carried out June 03, September 03, Nov 03, Jan 04 and Feb 04. The project should be completed by Dec 04. | Some Progress |  | D
SYR/REF/29/INV/48 | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarkisian Refrigerators | 12 months delays | The company has sent the financial agreement back to FFEM/AfD and informed the ozone office of its intention to complete the project by the 45th ExCom. | Some Progress |  | A
SYR/REF/29/INV/53 | France | Conversion from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Shoukairi and Co. | 12 months delays | The company has informed the ozone office of its intention to complete the proejct by the 45th ExCom. | Some Progress |  | C
SYR/REF/29/INV/54 | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Bashar Refrigerators | 12 months delays | A contract was signed with a local supplier. The equipment was bought and delivered. The project should be completed before the 45th ExCom. | Some Progress |  | B
SYR/REF/29/INV/56 | France | CFC emission reduction in central air conditioning | 12 months delays | Situation is blocked due to prices considered too high by Elba Cham hotel. Last attempt is been carried out to proceed. France suggests waiting until 35th ExCom. | No Progress | Letter of Possible Cancellation | C
ALG/FOA/31/INV/44 | Germany | Conversion of Algeria Mousse Polyrethane (AMP) | 12 months delays | Training and test trials have been finalised and according to the supplier CFC free production has started. Final site visit and completion report is due in November 2004 | Some Progress
ALG/FOA/32/INV/45 | Germany | Conversion of SOFTPM, Choupot Oran, to LCD technology | 12 months delays | Training and test trials have been finalised and according to the supplier CFC free production has started. Final site visit and completion report is due November 2004 | Some Progress
ALG/FOA/32/INV/46 | Germany | Conversion of Matelas Souf to LCD technology | 12 months delays | Training and test trials have been finalised and according to the supplier CFC free production has started. Final site visit and completion report is due in November 2004 | Some Progress
CPR/REF/27/INV/282 | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at China Aerospace Industry Corp. Kunming Refrigerator Factory | 12 months delays | Installation accomplished in spite of some damage caused by a recent taifun. Handing over, TÜV approval and destruction of old equipment are scheduled for second week of December 2004 | Some Progress
EGY/REF/29/TAS/75 | Germany | Implementation of the RMP: establishing a national recovery and recycling network | Status Report | Deliberations have started with the NOU in July 2004 about the re-start of the R&R project, after the price for CFC now exceeds the minimum level as stipulated by ExCom. A re-evaluation of equipment and training needs will be done as a first step, followed by equipment purchase, distribution and training. | Additional status report required
IND/FOA/36/INV/350 | Germany | Conversion from CFC-11 to water-based technology at Precision Engineering Tools and Components | 12 months delays | Installation finished early September 2004. Training and test trials have been finalised and according to the supplier CFC free production has started. Final site visit and completion report is due in Decemebr 2004 | Progress
IND/FOA/36/INV/351 | Germany | Conversion from CFC-11 to water-based technology at Pramukh Poly-Products | 12 months delays | Installation finished early September 2004. Training and test trials have been finalised and according to supplier CFC free production has started, enterprise is acquiring some additional parts for molding. Final site visit and completion report is due in December 2004 | Progress
IND/REF/32/TAS/288 | Germany | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | 12 months delays | Project proposal submitted in time. ExCom approval process lasted rather long. Project finally approved and thereby the preparation process completed at the 42nd ExCom. | Completed
IRA/FOA/34/INV/114 | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Iranogharb | 12 months delays | All equipment on site. Installation and trials were delayed several times by the supplier. Installation and commissioning of the plant is now agreed for end of October 2004. Enterprise has accomplished all preparatory works. | Some Progress
IRA/FOA/35/INV/116 | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Esfanj Jajerood foam company | 12 months delays | Training and test trials have been finalised and according to the supplier CFC free production has started. Final site visit and completion report is due in November 2004 | Some Progress
KEN/FUM/39/INV/33 | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (first tranche) | 12 months delays | It is not clear to Germany why the first tranche of this project is considered delayed, when the second tranche was already approved at the 42nd ExCom. | Completed
KEN/REF/36/TAS/27 | Germany | Project preparation for the RMP update | 12 months delays | TPMP proposal submitted for consideration at the 44th ExCom | Completed
ARG/FUM/29/DEM/93 | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Status Report | The project is under full implementation since the change of the local implementing agency. About 30% of the funds have been allocated. Protocols to test alternatives on citrus and cotton have been developed. Test for alternatives to MB are taking place based on the season of the crops. First results are expected to be completed by Dec.04. | No additional status report required |  | c,d
ARG/HAL/26/TAS/80 | IBRD | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Status Report | Civil works to install gas chromatograph and management facilities completed. Gas chromatograph, cylinders to take halon samples, hardware and software, and gases for calibrating the chromatograph are at INTI facilities. Portable gas chromatographs and recovery and recycling equipment were already procured and are being delivered. Five courses on halon management have been taught. Halon Bank is expected to start operations by Dec. 04. R&R equipment will be delivered by Oct. Time between arrival of equipment and start-up of the bank is due to the legal coordination between the operators and INTI. | No additional status report required |  | b,d
ARG/REF/18/INV/39 | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba S.A. | 12 and 18 months delays | Neba S.A. presented a new ownership. Currently the new owners are in the process of completing the legal paperwork. An updated version of the implementing schedule will be reported before the end of Nov. 04. | Some Progress |  | b, e
ARG/SOL/28/INV/91 | IBRD | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. | 12 and 18 months delays | Grimoldi, Heliodino, Integral Metalurgíca and Trosh showed no progress and July 2004 milestone was not met. According to the last mission Aid Memoire, the GOA agreed to the inclusion of these projects in the list of cancellations at the 44th ExCom. | Automatic cancellation |  | b, e
CHI/FUM/25/DEM/35 | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment applications for tomatoes and peppers | Status Report | Project is in its final stage. All field activities completed. The only remaining activity is the completion of a consumption survey agreed between CONAMA and the MInistry of Agriculture/SAG. The results of this activity are expected to be completed by the end of Dec. 04. | No additional status report required |  | d
CHI/MUS/19/INV/14 | IBRD | Montreal Protocol implementation programme - phase II | 12 and 18 months delays | PCR for this project is being prepared by CONAMA. Once the balance of the program is established, any remaining funds will be returned. Physical completion for TECFIN was reached Aug. 04. | Completed |  | d,e
CHI/MUS/26/INV/37 | IBRD | Montreal Protocol implementation programme (Phase II, second tranche) | 12 and 18 months delays | Sindelen did not finish its project and funds will not be allocated to the enterprise. Physical completion for TECFIN was reached Aug. 04. PCR is being prepared by CONAMA. Once the balance of the program is established, any remaining funds will be returned. | Completed |  | d,e
COL/SOL/31/INV/45 | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | 12 and 18 months delays | Project has been physically completed: full ODS-free production, at full capacity, started in July 2004. No equipment disposal was required, as per project proposal, but silicone-based coating equipment was retrofitted. | Completed |  | c
CPR/FOA/20/INV/179 | IBRD | Conversion to CFC-free technology in the manufacture of flexibe (slabstock) polyurethane foam at Chengdu Plastics No. 7 | 12 and 18 months delays | Plant has rented a CO2 storage tank. Installation will begin on 28 Sep. 04 when Hennecke's engineers arrive at the enterprise. | Milestones Achieved - Some Progress |  | b, c
CPR/FOA/26/INV/267 | IBRD | Conversion of refrigerator manufacture from CFC-11 to pentane foam blowing agent in the production of PU insulation panels at Foshan Refrigeration Equipment General Factory | 12 and 18 months delays | Trial run completed. Before starting commercial production, a safety certificate from the local safety authorities for the storage and use of pentane is required. Local FB has been requested to certify the safety of the pentane installation and foam operations. Certification and equipment disposal expected by Dec. 04. | Some Progress |  | b, c
CPR/FOA/27/INV/274 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shenyin Polyurethane Xinzhuang Plant | 12 and 18 months delays | Installation was done Sep. 04. Trial runs will be completed in Oct. 04. | Some Progress |  | a,b,e
CPR/FOA/27/INV/277 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jiangsu Haimen Foam plant | 12 and 18 months delays | Installation was done in May and trial run completed in Sep. 04. Baseline equipment disposal certificate expected by end Oct. 04. | Some Progress |  | a,b,e
CPR/FOA/27/INV/281 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Putuo Zhujiajian Rubber and Plastic Plant | 12 and 18 months delays | Trial production completed and baseline equipment destroyed. Project completed. | Completed |  | a,b,e
CPR/FOA/27/INV/284 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shanghai Shenyin Polyurethane Baoshan Plant | 12 and 18 months delays | Installation was done in Aug. 04. Trial runs will be completed in Oct. 04. | Some Progress |  | a,b,e
CPR/FOA/27/INV/285 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Chengdu Jinjiang Foam General Plant | 12 and 18 months delays | Installation done and trials completed in Aug. 04. Baseline equipment disposal certificate expected by Oct. 04. | Some Progress |  | a,b,e
CPR/FOA/28/INV/293 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Changzhou Huangfa Co. Ltd., Foam Plant | 12 months delays | Baseline equipment dismantled. New production for high density foam has been undertaken since Nov. 03. Outcome of September 2004 trials not yet reported to WB. | Some Progress |  | b,e
CPR/FOA/29/INV/311 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to methylene chloride and vertifoam from CFC-11 to liquid carbon dioxide technology at Shenzhou Foam Plant | 12 and 18 months delays | Installation of MC foam machine completed in July and will be calibrated and adjusted in Sep. 04. Second trial for vertical foaming machine conductes in Aug. 04 but was not successful, athough the result was better than that of the first trial. Enterprise itself continues the testing, and will request Beamech, if necessary, to do the third trial. | Some Progress |  | b
CPR/FOA/29/INV/322 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Fuxing Jiahe Foam Plant | 12 and 18 months delays | Storage tank and cooling system arrived at the enterprise. LCD equipment was installed by Cannon in Aug. 04. Trials will start in Oct. 04. | Some Progress |  | a
CPR/FOA/31/INV/358 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Qujing Plastic No. 2 Plant | 12 and 18 months delays | Trial production was completed in Jul. 04. Completion expected by Oct. 04. | Some Progress |  | a
CPR/FOA/31/INV/361 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Wuxian Polyurethane Foam Plant | 12 and 18 months delays | SEPA issued Letter of Credit for the purchase of pumps and valves in Aug. 04. Pumps and valves to be delivered to the enterprise in Nov. 04 and trials to be completed by end of Jan. 05 | Some Progress |  | a,e
CPR/FOA/31/INV/362 | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Nantong Xinyuan Foam Plant | 12 and 18 months delays | CO2 tank was purchased and delivered to the enterprise in Jul. 04 and installation completed. Trial runs are ongoing and will be completed in Oct. 04. | Some Progress |  | a,e
CPR/REF/28/INV/298 | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | 12 months delays | Domestic equipment was delivered to the plant. Trial production was completed in Sep. 04 and completion expected Nov. 04. | Some Progress |  | b
CPR/REF/28/INV/300 | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium sized open type compressors at Zhejiang Commercial Machinery Factory | 12 months delays | Domestic equipment was delivered to the enterprise. Trial production completed in Sep. 04. Completion expected Oct. 04. | Some Progress |  | b
CPR/REF/28/INV/303 | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of semi-hermetic compressors at Yueyang Hengli Air-Cool Equipment Co. Ltd. | 12 months delays | Domestic equipment was delivered to the enterprise. Trial production completed Sep. 04 and completion expected Oct. 04. | Some Progress |  | b
CPR/REF/34/INV/378 | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | 18 months delays | Shangling was sold to Yangzhou Kelon in Dec. 03. Existing equipment of the three production lines was moved to Yangzhou Kelon, including one electric motor purchased by the grant. The Bank has agreed on the transfer of this project from Shangling to Kelon. The subgrant agreement for transfer was signed on April 26, 2004. CEB (financial agent) is discussing with the Bank’s procurement officer to solve equipment procurement issues. | Some Progress |  | b
ECU/FUM/26/TAS/23 | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | 18 months delays | Soil characterization and biological studies have been completed and results of trials with chemical alternatives show 75% progress. With regards to studies on organic matter, the research phase completed and data is currently being compiled for the final report. As per the steam vaporization trials, samples of the soil have been collected and the lab test completed; the steam unit will be ready to start physical trials in two weeks. Solarization and combined studies are expected to start early Oct. in the farm Coteg in Guayllabamba. A workshop to report on the results from the trials obtained up to date will be carried out Oct. 04. | Some Progress |  | e
IDS/ARS/22/INV/61 | IBRD | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | 12 and 18 months delays | Four lines (2 semi-automatic and 2 automatic) have been installed at the aerosol filling center, and 1 line installed at PT. Candi’s own aerosol plant. Installation of the molecular-sieve columns, pumps, gas meters and LPG pipelines to the machines completed. Trials and production have started in 3 lines at the aerosol filling center. A technical audit is expected in early Oct. 04 upon which project will be declared technically completed. | Some Progress |  | b,e
IDS/FOA/23/INV/77 | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | 12 and 18 months delays | A total of 30 units of equipment are expected to arrive in three ports by Oct. 30 (5 units of equipment have already arrived in the Medan port in Sep. 04. Port clearance and delivery to recipients is expected by Oct. 04). The plan to have 30 units of equipment delivered 6 months after L/C was opened (opened on 27 Feb. 04) was delayed because: (i) L/C was opened late and (ii) some parts to build machines were not delivered by parts supplier to Sunkist (e.g. pumps and other equipment parts). Trials will commence in mid Oct. 04 and be completed by mid-Jan. 05. AFI provided KLH and the Bank with a work plan and schedule for commissioning of the equipment at enterprises. The L/C for the 2nd batch of 24 enterprises opened Aug. 04 and delivery of equipment is expected Feb. 05. A training workshop will be conducted Oct. 04 for the 2nd batch of enterprises. | Some Progress |  | c,a,e,b
IDS/FOA/23/INV/78 | IBRD | Technical assistance programme for SMEs for flexible polyurethane foam at Indonesian Foam Association (AFI) | 12 and 18 months delays | Molded equipment arrived at the ports in April and distribution completed by Jun. 04. A training and beneficiary awareness workshop was already conducted. Chemical procurement and delivery was completed by the end of Jun. 04. A comprehensive review of readiness of the individual recipients to do start-up commissioning before delivery of equipment was found to be a key success of commissioning. AFI conducteded site visits to review readiness of beneficiaries (such as reliable electricity, site layout, etc.). Installation, commissioning and trial of 16 foam equipment pieces completed Aug. 04. Completion of commissioning will be signified by the signing of a receipt of a certificate of satisfactory completion by supplier and foam recipients. One enterprise is still pending commissioning due to incomplete receipt of parts of machine and expects commissioning by early Oct. 04. Project will be ready for a technical audit by Nov. 04. | Some Progress |  | c,a,e,b
IDS/FOA/35/INV/129 | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | 18 months delays | Supplier has supplied, installed and commissioned individual retrofitted parts and retrofit already completed. PLC system (control panel) in place but final system adjustments are required to synchronize between the PLC and machine. Trials to synchronize the work of dry parts (retrofitted parts of pumps etc.) and wet parts for moulds and mixing heads will start by end of Sep. 04 and are expected to be completed by Oct. 04. | Some Progress |  | b
IND/REF/22/INV/110 | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigeration Components and Accessories | 12 and 18 months delays | Project completed, new equipment received and old equipment rendered unusable. PCR submitted by enterprise and being reviewed by FI. Final dibursement to be done after PCR satisfactorily completed. | Completed |  | b
IND/REF/22/INV/123 | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Hindustan Refrigeration Industries | 12 and 18 months delays | Project completed, new equipment received and old equipment rendered unusable. PCR submitted by enterprise and being reviewed by FI. Final dibursement to be done after PCR satisfactorily completed. | Completed |  | b,a
IND/REF/22/INV/124 | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | 12 and 18 months delays | Project completed, new equipment received and old equipment rendered unusable. PCR submitted by enterprise and being reviewed by FI. Final dibursement to be done after PCR satisfactorily completed. | Completed |  | b
IND/REF/22/INV/126 | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HCF-134a refrigerant at Voltas Ltd. | 12 and 18 months delays | Voltas II: Project completed. PCR submitted by enterprise and being reviewed by WB. Final disbursements completed. EKL Warora: Project completed. PCR submitted by enterprise and being reviewed by WB. Final disbursements completed. EKL Nandalur: Component has been cancelled and official notification received from the enterprise. Funds to be returned to the MLF. | Completed |  | b
JOR/ARS/31/INV/63 | IBRD | Substitution of CFC-12 for HAPs for perfumes and cosmetics at the aerosol plant Abu Shakra Factory | 12 and 18 months delays | Project physically completed. | Completed |  | d,a
JOR/ARS/31/INV/64 | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | 18 months delays | Project technically completed but not completed per Dec. 28/2. Disposal of baseline equipment has commenced. Planned date of equipment disposal certification is Oct. 04. | No Progress | Request report at the Meeting on possible canellation | d,a
JOR/HAL/29/TAS/53 | IBRD | Halon management programme, halon recovery, recycling and banking | Status Report | Delay caused by late opening of LC. LC opened, PO issued and shipment expected in Oct. 04. | No additional status report required |  | e
JOR/HAL/32/INV/69 | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | 12 and 18 months delays | Remaining fire extinguishing company has converted operations. | Some Progress |  | b
OMA/HAL/41/TAS/08 | IBRD | Halon consumption phase-out through a technical assistance programme and a halon recycling | Status Report | Pending confirmation whether Government wants to cancel this project. | Possible cancellation by mutual agreement | Request report at the Meeting on possible canellation
PAK/FOA/17/INV/06 | IBRD | Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group: (Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Industries Ltd., Procon En) | 12 and 18 months delays | Conveyors have been manufactured and received in the Azad Kashmir location and are being installed. They are expected to be ready by end Oct 04 and operational in Nov 04. | No Progress | Letter of Possible Cancellation | b
PAK/FOA/23/INV/20 | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | 12 and 18 months delays | The local representative of the machinery supplier plans to resolve the after-sale service issue once he inspects the thermoware units in Oct 04. Installation of two remaining machines will be done by the supplier by Dec. 04. | No Progress | Letter of Possible Cancellation | b,a
PAK/FOA/23/INV/22 | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible moulded, rigid foam) at Diamond Group of Industries | 12 and 18 months delays | Cannon Viking promised to send another technician but this has not yet taken place. The CV manager promised a visit by a software engineer in mid-Oct. 04. | No Progress | Letter of Possible Cancellation | b
PAK/FOA/25/INV/25 | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | 12 and 18 months delays | The local representative of the machinery supplier plans to resolve the after-sale service issue once he inspects the thermoware units in Oct 04. Installation of two remaining machines will be done by the supplier by Dec. 04. | No Progress | Letter of Possible Cancellation | b,a
PAK/FOA/29/INV/34 | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | 12 months delays | Foam equipment delivered Aug. 04. Installation of machinery expected Nov 04. | Some Progress |  | a,e
PAK/REF/23/INV/19 | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | 12 months delays | The PO and related LC have been issued. Equipment is expected to be shipped by Nov. 04 which would allow for installation by Feb. 05. Payment made to the enterprise for ref. component in Jun. 04. | Some Progress |  | b, e
PAK/REF/23/INV/21 | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Singer Pakistan Ltd. | 12 and 18 months delays | Project completed per Dec. 28/2 July 2004. | Completed |  | a
THA/FOA/31/INV/131 | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | 18 months delays | Project completed per Dec. 28/2 May 2004. | Completed |  | b
THA/FUM/33/TAS/135 | IBRD | Preparation of a methyl bromide phaseout strategy | 12 and 18 months delays | Final proposal for the National Methyl Bromide Phaseout Strategy was submitted to the ExCom Secretariat in Sep. 04. | Completed |  | d,e
THA/HAL/29/TAS/121 | IBRD | Halon management programme, halon recovery, recycling and banking | Status Report | Data analysis complete. According to the Halon National Consultant's survey and report, it is not feasible to establish a physical halon bank in Thailand. The Halon Steering Committee has proposed that an Electronic Clearing House be established. A WB mission is planned for Oct. 04 to determine next steps with the Government. | Additional status report required |  | d,a,e
THA/HAL/32/INV/134 | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | 18 months delays/Status Report | Five enterprises are implementing projects under the Terminal Halon Conversion Project. Three enterprises have completed the PCR. For the remaining enterprises, the appraisal report for one was approved by DIW and planned completion is end 2004. For the second enterprise, the conversion is expected to be completed in Oct. 04. | Some Progress |  | b
THA/REF/25/INV/92 | IBRD | Terminal umbrella project to convert CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at 224 small and medium sized enterprises | 12 months delays | All equipment distributed to enterprises. Last site visits to the enterprises are on-going. A wrap-up seminar will be conducted to refresh the knowledge of the enterprises after the training on how to use the equipment and on the Government's new regulation on commercial refrigeration and CFC and is expected to end in Dec. 04. | Some Progress |  | e,b,d,a
TUN/FOA/26/INV/33 | IBRD | Phaseout of CFC-11 by conversion to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Supermousse | 12 months delays | Non-CFC production has started. Waiting for confirmation whether Dec. 28/2 regarding equipment disposal has been fulfilled. | Completed |  | c,b
TUR/FUM/31/INV/69 | IBRD | Phase-out methyl bromide in the dried fig sector | 12 months delays | Taris will move its dried fig facilities to Aydin Industrial Zone delaying the planned installation of the repaired tanks. Beneficiary plans to install tanks by May 2005. | No Progress | Letter of Possible Cancellation | e
TUR/HAL/38/TAS/80 | IBRD | Halon management programme, halon recovery, recycling and banking | Status Report | Negotiations continued into Q2 of 2004. In early July, MoEF & TTGV met with Turk Telekom (TT) and TT expressed its concerns as to why it cannot implement this project. At the end of July, meetings were held with Technopark authorities in Bilkent and Chemical Department of Bilkent University who also did not have interest in the project. In early August, the Environmental Engineering Department of Middle East Technical University (METU) expressed interest in the project and will carry out the project under the Environmental Research Center (ERC) which a part of the department. | Additional status report required |  | e
TUR/SOL/35/INV/76 | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | 18 months delays | Only 16 enterprises are taking part in the project and now 14 enterprises have completed their sub-projects. Two enterprises's plan to finalize their sub-projects by the end of 2004. The sub-projects were delayed because required technical modifications on the cleaning machines could not be completed on time. | Some Progress |  | c
NIR/SEV/38/TAS/104 | Japan/UNEP | Assistance for a national information, education and communication campaign for compliance with the Montreal Protocol | Status Report | The key preparatory and consultative process have been completed. Agreement has been reached by all Partners on the implementation schedule and stakeholder responsibilities. The main progress made to date is summarised below: 1) Concept note prepared, finalized and agreed to by all Partners. 2) Project implementation schedule prepared and agreed to by all Partners. 3) National consultant retained by the NOU. 4) International consultant identified and UNEP proceeded with contractual arrangements. 5) MOU drafted by UNEP and submitted to Nigeria for approval. 6) TORs for consultants finalized and approved. 7) Travel arrangements finalized for consultations in Paris and Tokyo. | No additional status report required
ARG/FUM/36/INV/129 | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (2001 and 2002 tranches) | 12 months delays | This project approval represented the first year implementation of a MY MB Phaseout project. Year I activities were completed and Tranche II of the MY project was approved at ExCom 40. As per understanding for MY, performance-based projects, balance of funds rolled over to Year II ongoing implementation. As a result, no implementation delays to be recorded. Project on track. | Progress |  | G
BAH/REF/29/INV/09 | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | 12 months delays | Final mission had to be post-poned but now scheduled for end-Oct/early-Nov 2004. | Some Progress |  | A, E
BAH/REF/29/INV/10 | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | 12 months delays | Final mission had to be post-poned but now scheduled for end-Oct/early-Nov 2004. | Some Progress |  | A, E
COS/FUM/35/INV/25 | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (first tranche) | 12 months delays | This project approval represented the first year implementation of a MY MB Phaseout project. Year I activities were completed and Tranche II of the MY project was approved at ExCom 43. As per understanding for MY, performance-based projects, balance of funds rolled over to Year II ongoing implementation. As a result, no implementation delays to be recorded. Project on track. | Progress |  | G
COS/REF/32/TAS/23 | UNDP | Technical assistance for RMP survey and preparation | 18 months delays | Final payments still to be made. Delays due to new financial system. | Completed |  | A
CPR/REF/25/INV/249 | UNDP | Conversion to cyclopentane and isobutane in the manufacture of domestic refrigerators at Hangzhou Household Electrical Appliance Industrial Corporation (HHEAIC) | 12 months delays | Foam operation converted in April 2004. TUV safety certification on refrigeration to take place 4Q 2004 but CFC-12 no longer consumed. Full phase out achieved | Some Progress |  | C
CPR/REF/32/INV/367 | UNDP | Phaseout of CFC-11 by conversion to cyclopentane technology and CFC-12 by conversion to isobutane (600a) technology in the manufacture of domestic freezers at Qingdao Haier No. 2 Freezer Plant | 18 months delays | Completed. COC/HOP took place April 2004. Installation and trial successful completed. Disbursement to be completed in 2004 | Completed |  | G
CPR/SOL/33/INV/373 | UNDP | ODS phaseout in China solvent sector: 2000-2001 annual programme | 18 months delays | Equipment delivered and installed, contributing 336.3 ODP tonnes of CFC-113 and 7.3 ODP tonnes of TCA to 2003 phase-out targets, and 205.3 ODP tonnes of CFC-113, 3.3 ODP tonnes of TCA to 2004 phase-out targets. Disbursements will be reflected in 2004 | Completed |  | G
CPR/SOL/36/INV/390 | UNDP | ODS phase-out in China solvent sector: 2002 annual programme | 12 months delays | Equipment delivered and installed at 18 of 32 enterprises, remaining 14 enterprises will complete project activities by end 2004, Project completion at these 32 will contribute 535.8 ODP tonnes of CFC-113 and 43.2 ODP tonnes of TCA to 2004 phase-out targets. | Progress |  | B, C
CUB/ARS/34/INV/18 | UNDP | Phaseout of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | 12 months delays | Training visit to Mexico planned for June unable to take place due to visa difficulties. Local works still ongoing. Communication ver difficult after hurricane Ivan. | Some Progress |  | B, E
DOM/HAL/38/TAS/32 | UNDP | National halon bank management plan development | Status Report | NOU, in cooperation with UNDP, established a plan of action to complete the activities programmed under this project. Fire department was assigned as recycling body for halons. National workshop to halon users held on 28th June 2004 with the participation of a UNDP international expert. During this workshop the project was presented to halons users previously identified, and the modalities of implementation were discussed with them. Some of the subjects discussed in the workshop were: 1. The results of previous consultations with Canada and Venezuela (possibility to send halons to different countries in the regions and costs). 2. Decision on the characteristics of the halon bank in Dom Rep. (it will be a virtual bank and not physical because of the low volume of consumption, the bank will be integrated in the regional halon bank of the Caribbean). 3. Exchange price of halons will be determined as per economic policies of the country. 4. Awareness will be focused on the halon users and not to the general public. Currently, the local consultant is preparing more detailed inventory of halons in order to ensure the most accurate monitoring and total phase out. The legal framework still to be prepared. | No additional status report required |  | B
EGY/HAL/32/TAS/81 | UNDP | Halon management bank programme | Status Report | Change in management at the national level (National Ozone Officer changed) resulted in some delays. National Halon Bank Management team organised, equipment in process of distribution and workshops planned for Q4 2004. Project on track for completion. | No additional status report required |  | D
IDS/REF/37/INV/148 | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (first tranche) | 12 months delays | Equipment arrived and delivered to enterprises sites. Full activities completed at 15 enterprises, 15-20 more enterprises have equipment installed pending completion formality. Completion at remaining enterprises will take place end 2004.contributing over 347 ODP tonnes to the 2004 phase-out target. | Progress |  | B, C
IND/ARS/28/INV/221 | UNDP | Phaseout of CFC by substituting HAPs at Syncaps | 12 and 18 months delays | Follow-up visits took place mid-September 2004. Local works still not finished by enterprise. Equipment still not installed. MOEF is aware of the situation but suggests to give enterprise until March 2005 to complete the project. | No Progress | Project Completion by March 2005 | B
IND/ARS/29/TAS/244 | UNDP | Technical assistance for safety and technical programme to assist SME's manufacturing aerosol products (Phase I) | 12 months delays | Hindi manual completed. Project will be closed by UNOPS. | No Progress | Project Completion by March 2005 | G
IND/HAL/29/TAS/243 | UNDP | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | 12 months delays | Steering Committee scheduled for end-September 04. Standards to be distributed at this time and final workshops will take place thereafter. | Some Progress |  | B
IND/SEV/36/CPG/349 | UNDP | Country programme update | 12 months delays | State-level surveys in progress and compensation mechanism for assisting the local environment units being finalized. Final survey report expected 4Q 04. Draft CPU targeted for Dec. 2004 for subsequent endorsement by the Empowered Steering Committee for MP and formal approval by Indian Cabinet | Progress |  | C
IRA/FOA/35/INV/117 | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sandalisazi Esfanje Ghalebi Iran | 18 months delays | Verification mission took place and project completed. Final completion documents being prepared. | Completed |  | G
IRA/REF/35/INV/131 | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Alireza Abdolrezazadeh Co. | 18 months delays | Verification mission took place and project completed. Final completion documents being prepared. | Completed |  | G
IRA/REF/35/INV/132 | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Garm Iran Co. | 18 months delays | Verification mission took place and project completed. Final completion documents being prepared. | Completed |  | G
IRA/REF/35/INV/137 | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Sain Electric Co. | 18 months delays | Verification mission took place and project completed. Final completion documents being prepared. | Completed |  | G
IRA/REF/35/INV/140 | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Tehran Sardsazi Industrial Co. | 18 months delays | Verification mission took place and project completed. Final completion documents being prepared. | Completed |  | G
LEB/ARS/28/INV/30 | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at International Cosmetic Manufacturing Co. (Incoma), SAL | 12 and 18 months delays | NOU confirmed full completion. However, formal documentation still pending. | Completed |  | D
LEB/ARS/28/INV/35 | UNDP | Conversion to CFC-free technology in the manufacture of aerosols at Societe Nougeaim PMOSAL | 12 and 18 months delays | NOU confirmed full completion. However, formal documentation still pending. | Completed |  | D
LEB/ARS/29/INV/32 | UNDP | Group SME's project for the conversion to CFC-free technology in manufacturer of aerosol at Zahdreddine Trade and Manufacturing Sarl (ZTME), at Societe Nouvelle pour le Commerce et l'Industrie (SNCI) | 12 months delays | NOU confirmed full completion. However, formal documentation still pending. | Completed |  | D
LEB/FUM/34/INV/46 | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (first tranche) | 12 months delays | This project approval represented the first year implementation of a MY MB Phaseout project. Year I activities were completed and Tranche II of the MY project was approved at ExCom 38. As per understanding for MY, performance-based projects, balance of funds rolled over to Year II ongoing implementation. As a result, no implementation delays to be recorded. Project on track. | Completed |  | G
LIB/FOA/32/INV/05 | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Sebha Unit | 18 months delays | Despite numerous attempts to get Ozone office to follow-up, no response has been forthcoming. | No Progress | Letter of Possible Cancellation | D
LIB/FOA/32/INV/08 | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Ben Ghazi Unit | 18 months delays | Despite numerous attempts to get Ozone office to follow-up, no response has been forthcoming. | No Progress | Letter of Possible Cancellation | D
MAL/ARS/19/INV/85 | UNDP | Umbrella project to phase out ODS at SMEs in the aerosol sector | 12 months delays | Local works completed and equipment installed at 3 remaining enterprises. Government arranging safety audit of all companies for final project completion formalities | Some Progress |  | B
MEX/HAL/35/TAS/104 | UNDP | National halon management and banking programme | Status Report | Further to pro-active follow-up, defective parts have been replaced and bank is now operational. Awareness workshops and steering committee are being planned with Government for final stages and completion of the project. | No additional status report required |  | C
MLI/REF/32/TAS/10 | UNDP | Implementation of the RMP: monitoring the activities in the refrigerant management plan | Status Report | NOU requested for the recruitment of an alternative national consultant. New candidate now recruited and monitoring phase started. International consultants visited Bamako in July 2004. | No additional status report required |  | D
MLW/FOA/26/INV/12 | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Robry Ltd. | 12 months delays | Final inspection visit conducted in June 2004. Project operationally completed. Final financial documentation/review pending. | Completed |  | C
MLW/FUM/34/INV/16 | UNDP | Second payment under the national programme for the phaseout of all non-essential and non-quarantine and pre-shipment applications of methyl bromide | 12 months delays | This project approval represented the ongoing implementation of a MY MB Phaseout project. Activities were completed and Tranche III of the MY project was approved at ExCom 40. As per understanding for MY, performance-based projects, balance of funds rolled over to ongoing MY implementation. As a result, no implementation delays to be recorded. Project on track. | Completed |  | G
MOR/FOA/23/INV/12 | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Sodiflex and Tiznit Plastic S.A. | 12 months delays | Conditions to resume activites in all LCD projects in Morocco were not met and 43rd ExCom confirmed that therefore all six were canceled, including this project. | Automatic cancellation | per Decision 42/15 | B
NEP/REF/28/TAS/07 | UNDP | Implementation of the RMP: monitoring activities included in the RMP | Status Report | Monitoring consultant now recruited and we are waiting for monitroring period to end and receive final report. | No additional status report required |  | D
NIR/FOA/26/INV/32 | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Olufoam and Plastic Industries Ltd. | 18 months delays | The project is technically completed. Awaiting Handover Protocol (HOP) to be signed. National Consultant is following up and official completion will definetely take place before year-end. | Completed |  | B
NIR/FOA/26/INV/35 | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Confidence Products and Services Ltd. | 12 months delays | The project is technically completed. Awaiting Handover Protocol (HOP) to be signed. National Consultant is following up and official completion will definetely take place before year-end. | Completed |  | B
NIR/FOA/34/INV/89 | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Harmony Foam Nigeria Ltd. | Status Report | Some additional trials are still outstanding. Then Handover Protocol (HOP) to be signed. National Consultant is following up and official completion will definetely take place before year-end. | Additional status report required |  | B
NIR/FOA/34/INV/91 | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Global Plastic Industries, Ltd. | Status Report | Enterprise has declared bankruptcy and all equipment (including equipment supplied under the project) have been seized by the bank. UNOPS is working with the Government to resolve the issue. As the company is currently not producing, there is technically no ODS use. | Possible cancellation by mutual agreement | Request report at the Meeting on possible canellation | B
NIR/SEV/36/CPG/102 | UNDP | Country programme update | 12 months delays | Activity progressing slowly as results of the regional surveys are being awaited for. CP-Update expected to be completed for the 45th ExCom meeting. | Some Progress |  | D
SYR/REF/35/INV/81 | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Saad Refrigeration | Status Report | Equipment installed, trials done. Project completed. Final documents being prepared. | No additional status report required |  | B
TRI/ARS/25/INV/12 | UNDP | Project to phaseout use of CFCs in aerosol filling at Hand Arnold Industries Limited (HAIL) | 12 months delays | Extraction system installed satisfactorily., Final payment to be made upon endorsement by expert. Project completed. | Some Progress |  | B
VIE/ARS/31/INV/28 | UNDP | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | 18 months delays | Manufacturer informs that addiitional part to be delivered in Oct. 04 Project to be completed thereafter. | Some Progress |  | B, C
VIE/REF/34/TAS/38 | UNDP | Implementation of the RMP: monitoring the activities in the RMP | Status Report | Monitoring phase still on-going. Report received and sent to consultant for comments. | Additional status report required |  | D
VIE/REF/35/TAS/39 | UNDP | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | Status Report | Jointlry implemented with VIE-38. Monitoring phase still on-going. Report received and sent to consultant for comments. | Additional status report required |  | D
AFR/SEV/32/TAS/28 | UNEP | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | 12 months delays | The Sub programme with CEMAC was launched on 9 August 2004 in Douala. This subprogramme is planned to end on 30 October 2004. Two payments have been made under this subprogramme. The other sub programme with UEMOA started in May 2004 and a draft report is available. The experts' meeting and the Ministers' meeting for the adoption of the recommendations will be held on 11-14 October 2004. Two payments have been done under that sub programme. We plan to close the programme by December 2004. | Some Progress
ALB/PHA/39/TRA/07 | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | 12 months delays | Training of trainers in good practices in refrigeration completed on 12 March 2004. | Completed
ARG/SEV/30/TAS/104 | UNEP | Policy assistance for the design and implementation of an ODS import/export licensing system for Argentina | 12 and 18 months delays | Final draft of licensing system was extensively reviewed by national stakeholders in a consultative process. The Ministries of Environment and Foreign Affairs have recommended some formal adjustments to the legislation. National expert is being contracted to carry out these adjustments. The NOU and the Ministry have used the consultative process to raise awareness amongst key stakeholders including different institutions of Government, as well as the private sector and NGOs. | Some Progress
ASP/SEV/36/TAS/46 | UNEP | Implementation of the PIC Strategy: Policy assistance and guidance to countries for development of regulations | 12 months delays | SPREP has been actively following up on this issue. This was also discussed during the 15th SPREP Environment Ministers Meeting in September. As a specific example, Tonga's draft Ozone Layer Protection Bill revised in September 2004 and submitted to the Crown Law Office for clearance before being submitted to the Minister for Environment for approval. | Progress
COL/REF/17/TRA/18 | UNEP | Training programme in good practices in refrigeration | 12 months delays | Project completed in Mar-04. PCR being finalised. | Completed
CPR/FUM/35/TAS/381 | UNEP | Awareness raising workshop to support ratification of the Copenhagen Amendment | 12 months delays | Most activities under the project have been completed, financial reports need to be finalised. Project to be closed during last quarter of 2004. | Progress
CPR/FUM/35/TAS/382 | UNEP | Techno-economic evaluation of methyl bromide alternatives | 12 months delays | Most activities under the project have been completed, financial reports need to be finalised. Project to be closed during last quarter of 2004. | Progress
FIJ/SEV/37/INS/08 | UNEP | Renewal of institutional strengthening project (Phase III) | Status Report | IS Renewal request is being submitted to the 44th ExCom meeting. | No additional status report required
GLO/SEV/19/TAS/112 | UNEP | Training modules on management of ODS phase-out in SMEs | 12 and 18 months delays | Contract with consultant (ICF Incorporated) signed in August 2004. First disbursement made in September 2004. Project schedule with milestones submitted by consultant. Data collection and research underway. Expected completion is by 1 April 2004 as per ExCom 42/15. | Milestone established by Decisin 42/15
GLO/SEV/29/TAS/198 | UNEP | Complement for translation and printing of four guidelines and training modules into Arabic, Chinese, French and Spanish | 12 months delays | Translation completed. Printing to be done by UNON Printshop in December 2004. Completion of project by December 2004 | Some Progress
GLO/SEV/32/TAS/224 | UNEP | Regional awareness raising and South-South assistance | 12 months delays | The funding was apportioned to each Region and the Network members as a group decided how to use the funds, with guidance provided by UNEP. As such, there are multiple sub-components to this project, most of which (but not all) are completed. | No Progress | Request report at the Meeting on possible canellation
GLO/SEV/34/TAS/230 | UNEP | Study on development of ODS phase-out strategy for SMEs | 12 months delays | Contract with consultant (ICF Incorporated) signed in August 2004. First disbursement made in September 2004. Project schedule with milestones submitted by consultant. Data collection and research underway. | Some Progress
GLO/SEV/34/TAS/232 | UNEP | Development of tracking system for ODS and ODS-based equipment | 12 months delays | UNEP contacted Data Mining International, Inc. (DMI) and the EU to request for their data tracking system in order to not invest unnecessarily in developing such a system. As a result DMI made a presentation on to the Asia and Pacific networks on their system (which analyses past data). UNEP will discuss with the regions the existing tracking systems such as the EC licensing and quota system and the Data Mining International, Inc. (DMI) system to see if they can be adapted for use in Article 5 countries. | Cancellation by mutal agreement
GLO/SEV/37/TAS/241 | UNEP | Assistance for regional awareness raising | 12 months delays | The funding was apportioned to each Region and the Network members as a group decided how to use the funds, with guidance provided by UNEP. As such, there are multiple sub-components to this project, most of which (but not all) are completed. | Some Progress
MDV/SEV/37/INS/04 | UNEP | Renewal of institutional strengthening project (Phase 2) | Status Report | CAP team has been in touch with the country between the 43rd and the 44th meeting. The NOU was on sabbatical and has resumed duties in August 2004. As a result some activities were delayed. RMP training for refrigeration technicians and customs officers have been held on 13-17 June 2004 and 16-18 August 2004 respectively. The country organised a very successful Ozone day on 16 September 2004. The IS renewal project is being submitted to the 44th meeting of the ExCom. | No additional status report required
OMA/SEV/37/TAS/07 | UNEP | Policy and technical assistance | 12 months delays | Oman nominated a legal expert who reviewed and amended the existing regulations to meet the country requirements to fulfill the obligations of MP. The draft of new legislation was reviewed by both NOU of Oman & CAP. In addition, the draft was reviewed by the key stakeholders and their comments were incorporated in the final draft and now the proposed legislation is ready to be submitted to the Minister for his signature and enacted. The second payment will be released in the end of this month upon CAP receiving Oman's progress report on this regard. | Some Progress
STP/SEV/36/CPG/01 | UNEP | Preparation of country programme and refrigerant management plan | 12 months delays | CP/RMP to be submitted at the 44th ExCom. Project to be completed by December 2004. | Completed
STP/SEV/38/INS/02 | UNEP | Establishment of the Ozone Unit | Status Report | Project to be completed by December 2004. Additional 2 years for the project will be requested at the 44th ExCom. | No additional status report required
VEN/SEV/34/TAS/90 | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | 12 months delays | In early 2004, the Ministry of Environment submitted the Revised Decree to the Attorney General's office for authorisation before submission to the President for approval. The Attorney General's office requested revisions to the proposed Decree. The Ministry of Environment has complied with these and is waiting for the final authorisation from the Attorney General's office. This is expected in the near future, and after this the proposed Decree will be submitted to the President for approval. | Some Progress
CPR/FOA/32/INV/369 | UNIDO | Replacement of CFC-11 with HCFC-141b in manufacturing of PU rigid spray foam for insulation at 26 enterprises | 12 months delays | The project site is prepared for the remaining one company for installation and commissioning of equipment , which is partially delivered. The rest of equipment will be delivered by mid October 2004 and commissioning will start beginning 11/2004. The completion is planned for 12/2004. | Some Progress |  | B
CPR/FOA/34/INV/376 | UNIDO | Phase out of CFC-12 in the manufacture of extruded polystyrene foams to butane at 9 enterprises (umbrella) | 12 months delays | The project sites of the remaining enterprises are prepared for installation and commissioning of equipment which is partially delivered; the rest of equipment will be delivered by mid October 2004 and commissioning will start beginning Nov. 2004. The completion is planned for December 2004. | Some Progress |  | B
CPR/FOA/35/INV/379 | UNIDO | Phase out of CFC-12 in the manufacturing of extruded polystyrene foams through the use of butane as a blowing agent at 7 enterprises (terminal umbrella project) | 12 months delays | The first round of bidding exercise was completed in June 2004 without expected results. Therefore, the scope of supply was modified and re-bidding will be announced in October 2004. The project completion is planned for June 2005. | Some Progress |  | C
CPR/REF/29/INV/336 | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Zhejiang Electrical Equipment Co. | 12 months delays | The project will be completed latest by December 2004. All equipment are installed, a training component and the final TUV visit and certification is to be carried out this year. | Some Progress |  | B
IND/PAG/34/INV/303 | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at M/S Benzo Chemical Industries, Tarapore | 18 months delays | The company is delayed in the site preparation, thus the installation is still outstanding. | No Progress | Letter of Possible Cancellation | B
IND/PAG/34/INV/314 | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at FDC Limited, Roha | 12 months delays | All equipment procured and are being installed. Estimated project completion is December 2004. | Some Progress |  | C
IND/REF/32/INV/290 | UNIDO | Umbrella project for the conversion of three commercial refrigeration enterprises in New Delhi (Gaurav Controls, Thermoking and Western Engineering) | 12 months delays | Project completed in August 2004. | Completed |  | G
IRA/FOA/28/INV/50 | UNIDO | Phasing out ODS in manufacturing of flexible PU slabstock foam through the use of liquid CO2 blowing technology at Bahman Plastic Co. | 12 months delays | Due to the labour problem, the company could not move to the new site. The Government agreed to install the equipment at the current site. Installation is foreseen for December 2004. | Some Progress |  | B
IRA/FOA/31/INV/73 | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Rashestan Co. | 12 months delays | Equipment was installed but not yet commissioned due to absence of one press to be procured by the counterpart. Safety certification is pending due to the above mentioned reason and it was classified as incomplete installation from the safety point of view. | Some Progress |  | B
IRA/FOA/37/INV/149 | UNIDO | Phasing out of ODS in the manufacture of flexible slabstock foam through the use of LCD blowing technology at Esfanj Shirvan Co. | 12 months delays | The fund provided was not sufficient to cover all the equipment required for the conversion. The counterpart has to provide equipment such as the LCD tank. The equipment to be provided by the counterpart is in process. The foaming equipment is delivered and installation will take place in December 2004. | Progress |  | C
IRA/FUM/29/INV/57 | UNIDO | Phasing out of the important non critical, non-essential use of methyl bromide for post-harvest treatment | 12 months delays | The result of the assessment showed that seven chambers should be modified in order to increase the efficiency of the alternative proposed. Precise list of items to be modified is to be determined before the end of the year and then UNIDO will proceed with the procurement activities. | Some Progress |  | C, D
IRA/REF/28/INV/51 | UNIDO | Replacement of CFC-12 refrigerant by HFC-134a at Iran Compressor Manufacturing Company (ICMC) | 12 months delays | The project is at completion stages. During inspection of the equipment for installation, the supplier found out that the damaged equipment cannot be repaired on site and it has to be shipped back to the UK for repair. | Some Progress |  | E
MDN/ARS/32/INV/17 | UNIDO | Phase-out of CFC 11/12 in the manufacture of aerosols by conversion to HFC and hydrocarbon propellants at Alkaloid A.D. | 12 months delays | Permission on the civil work from the Ministry of Transport obtained. Preparation of the project site for equipment installation and commissioning is on the way. Completion of civil work is expected for end of October 2004. | Some Progress |  | B
MOR/FUM/34/INV/44 | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (first tranche) | 12 months delays | The Agreement has been signed with the tomato producers. The reviewed project document is being submitted to the 44th ExCom Meeting. | Some Progress |  | D
SYR/ARS/32/INV/71 | UNIDO | Phase-out o fCFC-11 and 12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Badran and Co. | 12 months delays | Project completed in June 2004 | Completed |  | G
SYR/ARS/32/INV/72 | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Mahmoud Hamida | 12 months delays | Project completed in June 2004 | Completed |  | G
SYR/ARS/32/INV/73 | UNIDO | Phase-out of CFC-11 and 12 in the manufacture of hair sprays by conversion to hydrocarbon propellant at Khadji and Zahka | 12 months delays | Project completed in June 2004 | Completed |  | G
SYR/ARS/32/INV/74 | UNIDO | Phase-out of CFC-12 in the manufacture of insecticides by conversion to hydrocarbon propellant at Cheikh Ghazal Insecticide Plant | 12 months delays | Project completed in June 2004 | Completed |  | G
SYR/FOA/32/INV/68 | UNIDO | Conversion from CFC-11 to HCFC-141b in the production of rigid foam panels at Bassam Baghdan | 12 months delays | There was a delay in the civil works and site preparation. However, it was now confirmed by the Ozone Officer that the company has advanced its civil works and the new building structure was ready. All remaining works necessary for installation and commissioning will be completed in two months time. Project completion is estimated for the first quarter of 2005. | Some Progress |  | B
VEN/FOA/36/INV/94 | UNIDO | Phasing out CFC-11 by conversion to water system as a blowing agent in the manufacture of flexible polyurethane foams at Manufacturas Enveta, C.A. Cumana | 18 months delays | Project completed in June 2004. | Completed |  | G
VEN/REF/32/INV/88 | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at seven commercial refrigeration companies (umbrella project) | 12 months delays | 1) Eterna, Indartelca and Vikingo received refrigeration equipment only, which were installed. Indartelca stopped its production; Eterna and Vikingo are still using CFCs with a reduced production level. 2) J.R. Refrigeracion and Couttenye have received refrigeration and foaming equipment, which have not yet been installed. These companies cannot be contacted. 3) Refrinaza received foaming equipment, which is installed and commissioned. The company is producing CFC-free. Refrinaza is now working on the mould heating system. 4) The foaming and refrigeration equipment at Inelmem were installed and commissioned and CFC-related equipment were destroyed. Inelmem has stopped its production, but they showed interests to restart production. | No Progress | Letter of Possible Cancellation | B, E
YUG/FOA/35/INV/14 | UNIDO | Phase out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim Co. | 18 months delays | Equipment was delivered in July 2004. On-site preparatory works are in progress. As soon as the project site is prepared, equipment installation will start. | Some Progress |  | B