## Delays
Code | Agency | Project Title | Category of Delays | Progress Report to the 47th Meeting | Progress Report to the 47th Meeting (Continued) | Progress Report to the 47th Meeting (Continued) | Progress Report to the 47th Meeting (Continued) | Final Assessment | Category of Delay
AFR/HAL/35/TAS/29 | Germany | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | Status Report | A new implementation plan for the Regional Halon Project in Southern and Eastern Africa is available and has been approved by all but two countries which to date could not be reached for comments. Germany has submitted this revised plan for consideration at the 47th ExCom. |  |  |  | Request additional status report.
AFR/HAL/37/TAS/31 | UNDP | Sectoral phase out programme: establishing a regional halon bank for West and Central Africa (Benin, Burkina Faso, Cameroon, Congo, Congo DR, and Guinea) | Status Report | Persistent delays on activities with non-consuming countries caused by request for change in implementation at April 2005 Regional Network Meeting in Mauritania. Discussions with regional spokesperson on ExCom (Niger) led to revised proposal and return to regional workshop modality. Higher value national contracts now issued and pending signature. Technical missions for the 5 20% countries proceeding as planned. Project completion target now June 2006. |  |  |  | Request additional status report. | D
ALB/PHA/39/TAS/05 | UNIDO | National ozone depleting substances phase-out plan: refrigerant recovery and recycling network | 18 months delays | The second tranche of the project was approved by the 46th ExCom. Since the legislation has been approved, expenditures can be made on the recovery and recycling component . A joint UNIDO/UNEP mission took place in August 2005 in order to accelerate the pace of implementation of the project. The resurvey of the service market was finished. The eligible enterprises are being selected by the NOU. As a first step, the 10-20 biggest CFC consumers will be selected for assistance and potential enterprises will be identified by the NOU for the establishment of a recovery and recycling centre. |  |  |  | Progress | D, F
ALB/PHA/39/TRA/07 | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | 12 months delays | Release of 2nd payment to organize Phase II of training project was authorized by UNEP Nairobi in May 2004. Apparently, the NOU failed to follow-up with UNDP Tirana and informed UNEP only a year later that they still do not have the funds to prepare the workshops. UNEP therefore re-issued a fresh payment authorization requested by UNDP Tirana in order to release the funds. Another obstacle was the release of the training equipment from Customs Authority which insisted on VAT payment. This has been resolved by NOU and training equipment was sent to the training center. Phase II training in 13 cities for approx 270 technicians is scheduled to begin end of September 2005. |  |  |  | Some Progress | D
ALG/HAL/35/TAS/51 | Germany | Sectoral phase out programme: establishment of a halon bank | Status Report | Germany received that a total of 427 kg halon 1301 and 7kg Halon 1211 had been recovered. |  |  |  | No further status report needed.
ARG/ARS/38/INV/131 | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | 18 months delays | Project physically completed and awaiting financial completion. Servex presented its final report to the PIU in Aug 05. Financial closure expected in Oct. 05. PCR under preparation. |  |  |  | Completed
ARG/FOA/32/INV/113 | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constuctora Vimac; Gaspar Adragna; Placido Sandoval) | 12 months delays | Confirmation received in April 2005 that new pouring gun working satisfactorily. CFC-stocks depleted and project technically completed. HOP dated April 2005. |  |  |  | Completed | G
ARG/FUM/29/DEM/93 | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Status Report | Project is being implemented satisfactorily, however as the project relies on planting seasons, this operation is expected to be completed in Aug. 06. Contract with executing agency (INTA) was extended for a maximum of 18 months. Project was delayed because of a change in the executing agency, compounded by the need for respecting the planting seasons. |  |  |  | No further status report needed. | c,d,e
ARG/FUM/40/INV/136 | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (third tranche) | 12 months delays | Phase I and II of project operationally complete and the Progress Report on activities conducted and results achieved during Phase IV was presented to ExCom 46. Procurement, distribution of materials and training on-going. Project is meeting targets and is on schedule. |  |  |  | Progress | G
ARG/REF/18/INV/39 | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba S.A. | 12 and 18 months delays | 1) The legal process to find new ownership for NEBA S.A. has stopped, as potential parties are no longer interested. NEBA S.A. has been declared bankrupt by the local judge. World Bank has started process to recover the funds disbursed to the project. 2) We are reporting the cancellation of this project. The process to find new ownership has been terminated snf yhr Government of Argentina and the World Bank mutually agree to the cancellation. The balance of funds will be returned to the MLF and attempt are being made to recuperate funds from the equipment purchased with the grant. |  |  |  | Cancellation by Mutual Agreement | b, e
ARG/REF/32/TRA/115 | UNEP | Training programme for the refrigeration servicing sector (Phase III) | 12 months delays | Last MOU will be signed in SEP-05 and project expected to be completed in Dec-05 |  |  |  | Some Progress
ARG/SEV/30/TAS/104 | UNEP | Policy assistance for the design and implementation of an ODS import/export licensing system for Argentina | 12 and 18 months delays | Country is selecting consulting firm to carry out complementary activities as of SEP-05 |  |  |  | Some Progress | D
ASP/HAL/30/TAS/36 | Germany | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) | Status Report | As reported to the 46th ExCom, the activities required under the Regional Halon Project for West Asia had been completed and the available funds exhausted. Germany has prepared a detailed Draft Project Completion Report which is being reviewed by the countries concerned. Germany may report again on this issue during the 47th ExCom. In the meantime, Germany has submitted the current working document for information to the Secretariat. |  |  |  | No further status report needed.
ASP/SEV/34/TAS/42 | Sweden | Regional cooperation for monitoring and control of ODS consumption | 12 months delays | At the 39th ExCom meeting in 2003, the project on “Regional cooperation for monitoring and control of ODS consumption” approved at 34th ExCom meeting in 2001 for the SEAP region, was expanded to include also the countries in the South Asia (SA) region through the project “Preventing Illegal Trade of ODS in the SA Region – Extension of SEAP project”. The reasons for delay incorporate also the SA part of the project. The original project time frame for the SEAP part of the project was September 2001 to March 2004 with two meetings every year during the 3 year period. With the SA extension, completion date was changed to the last quarter 2004 with four joint meetings during a 2 year period. The reasons for delay in this project (referred to as the customs network) are as follows: | 1) To have the inception meeting back to back with the ODSONET/SEAP meeting in September 2001 proved to be too optimistic given that the project was approved in July 2001 only. Instead the inception meeting was held back to back with the ODSONET/SEAP meeting in April 2002. The second meeting of the customs network was held in October 2002. 2) Due to the unfortunate outbreak of the SARS disease in the spring of 2003, it was impossible to organise international conferences in the Asia Region. The third meeting for the SEAP customs network and the first joint workshop for the SEAP and SA customs networks therefore had to be postponed and was held in October 2003. 3) The second joint workshop was organised in April 2004. The Officers attending the 2004 workshop proposed to organise the next workshop in the spring of 2005 as they felt that not enough time was otherwise available before the next workshop to make progress to agreed recommendations and to undertake the planned desk study on illegal ODS trade. | 4) At the third joint workshop in Beijing in April 2005, there was discussion on the possibilities for and benefits of introducing electronic management tools for monitoring and control of ODS trade at the national level. It was agreed that some countries would pilot the implementation of such a tool and that the result of this pilot study should be presented at the next workshop. To allow sufficient time for the pilot study to be undertaken, the forth workshop was decided to be held in the spring 2006. | 5) Another reason for postponing the forth, and in this project last, joint workshop until spring 2006 was that the countries at that period in time would be better informed about their status of compliance with the 2005 phase-out target and that this would be an important topic for consideration and discussion between customs and ozone officers. Providing more time between the workshops of the customs network has also allowed for additional bilateral and small group meetings to be organised by UNEP CAP discussing specific problems on illegal trade between countries. Currently UNEP/ROAP is preparing an interim progress report with details about the positive outputs from this important pilot project. This report could be forwarded to the Fund Secretariat if so requested. | Some Progress
ASP/SEV/38/TAS/49 | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region (phase 2) | 12 months delays | PCR Submitted |  |  |  | Completed
BGD/PHA/42/TAS/18 | UNEP | National ODS phase-out plan: public awareness and information dissemination to main stakeholders (2004 work programme) | 12 months delays | The Project Document for the transfer of funding has been reviewed by the Government. |  |  |  | Some Progress | D
BGD/PHA/42/TRA/16 | UNEP | National ODS phase-out plan: training and certification programme for refrigeration service technicians, including development of a code of good practices (2004 work programme) | 12 months delays | The Project Document for the transfer of funding has been reviewed by the Government. |  |  |  | Some Progress | D
BGD/SEV/36/CPG/14 | UNDP | Country programme update | 12 months delays | Project was implemented jointly with Formulation of Sector Phase Out Plan. Latter was approved at 42nd ExCom meeting, but experts were unaware that separate CP-document needed to be produced. UNDP will finalize latter in first half of 2006. |  |  |  | Report at 47th Meeting | A
BHE/FOA/35/INV/08 | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Inga Co. | 12 months delays | Contract for the supply of equipment and services has been awarded and finalization of entire installations is in progress. Certificate on occupational safety to be issued subsequently by local authorities concerned. |  |  |  | Some Progress | B
BHE/FOA/39/INV/15 | UNIDO | Phase-out of CFC-11 by conversion to n-pentane in the manufacture of rigid foam products for insulating purposes at Stirokart Co. | 12 months delays | Missing press has been delivered. Project site preparatory works including engineering safety-related works are being finalized. Final installations should take place in October 2005. Safety certification to be issued subsequently. |  |  |  | Some Progress | B
BHE/REF/35/INV/09 | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with cyclopentane in the manufacture of commercial refrigeration equipment at Bira, Bihac | 12 months delays | Site preparation was delayed by the counterpart. However, the site had already been prepared, equipment was installed and final commissioning is planned for September 2005. |  |  |  | Some Progress | B
BRA/FOA/36/INV/244 | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Decorfrio | 12 months delays | Confirmed in August 2005 that machine successfully installed, trials done and project is now completed. HOP dated August 2005. |  |  |  | Completed | G
BRA/FUM/38/TAS/263 | UNIDO | Assistance for the preparation of a survey on the consumption of methyl bromide | 12 months delays | The project was completed in September 2005. |  |  |  | Completed | G
BRA/PHA/37/INV/262 | UNDP | National CFC phase-out plan (first tranche) | 12 months delays | National Phase Out Plan of Brazil ongoing until 2009. Annual Report for the year 2005 and Action Plan 2006 submitted to 47th Excom Meeting. |  |  |  | Some Progress | G
CBI/SEV/36/INS/02 | UNEP | Establishment of the Ozone Unit | Status Report | The French RNC visited the country and the National Ozone Unit has been settled down. |  |  |  | No further status report needed.
COL/FOA/29/INV/39 | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises | 12 and 18 months delays | Project is physically and financially completed. Last disbursement to GMP Quimicos, the Group Coordinator, took place in Aug. 05. NOU is completing PCR, which will be submitted to the Bank during Q4 05. |  |  |  | Completed
COL/REF/38/INV/57 | IBRD | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 enterprises | 12 months delays | Contracts signed between Cabarria y Cia. S.A., the project's Group Coordinator, and nine beneficiary enterprises. Equipment ordered and delivery expected to occur in Q4 05. Total number of beneficiaries for the project will be 10 and not 17, as initially expected. Various reasons including bankrupcy and reluctance to participate in the project account for the decrease in the number of beneficiaries. Delays were due to difficulties obtaining insurance certificates for enterprises (which are v. small with insufficient documentation). Project expected to be completed by the end of 05. |  |  |  | Some Progress | b,e
COS/REF/32/TAS/23 | UNDP | Technical assistance for RMP survey and preparation | 12 and 18 months delays | Project completed. |  |  |  | Completed | G
CPR/FOA/35/INV/379 | UNIDO | Phase out of CFC-12 in the manufacturing of extruded polystyrene foams through the use of butane as a blowing agent at 7 enterprises (terminal umbrella project) | 12 months delays | The contract for provision of equipment for the 7th enterprise was awarded in May 2005. The project site under preparation for installation of the new equipment, which is planned to be delivered end November 2005. |  |  |  | Some Progress | C
CPR/REF/34/INV/378 | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | 18 months delays | Equipment procured (including 3rd c-pentane foaming machine), cyclopentane tank installed, one foam line installed and two other lines under installation. Due to a financial investigation of its parent company, Shangling/Yangzhou Kelong accounts have been frozen resulting in a cash shortage. This will delay completion of the installation due to the requirement of counterpart funds for project completion. It is now expected that the project will be completed by Dec. 05. |  |  |  | Some Progress | b
CPR/SEV/37/TRA/392 | UNEP | Policy training for local authorities (second tranche) | 12 months delays | All activities finalised, including the training workshops for local EPB. Launch of the on-line training on 16th September 2005 |  |  |  | Completed
CPR/SOL/33/INV/373 | UNDP | ODS phaseout in China solvent sector: 2000-2001 annual programme | 12 and 18 months delays | Completed. Of the 541.6 ODP tonnes CFC-113 and 10.6 ODP tonnes TCA signed under 21 ODS Reduction Contracts, phase out of these two quantities were achieved in 2003 and 2004 |  |  |  | Completed | B
CPR/SOL/40/INV/403 | UNDP | ODS phase-out in China solvent sector: 2003 annual programme | 12 months delays | Equipment delivered and commissioned at 7 of 12 enterprises. Equipment for 35 SMEs under the Voucher System has been delivered by August 2005 commission to be completed by end September. All enterprises under 2003 AIP will complete their phase out by Dec. 2005 |  |  |  | Progress | C
CUB/ARS/34/INV/18 | UNDP | Phaseout of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | 12 months delays | Local works completed. Two representatives from company attended aerosol safety workshop in Mexico in Sept. 2005. Awaiting installation visit by supplier. Scheduled for October 2005. Project completion delayed until December 2005. |  |  |  | Some Progress | C
DOM/SEV/37/TAS/31 | UNEP | Policy and technical assistance | 12 months delays | Goverment has changed and MOU was amended, and final activities are under completion by the country. Closure of the project is awaited for end of 2006 |  |  |  | Some Progress | D
ECU/FUM/26/TAS/23 | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | 12 and 18 months delays | With the vaporization trials at Gypso farm, field studies were completed by 30 Jun 05. The results of the tests with seven alternatives to MB were presented at the international workshop held in Quito 20-22 Jul 05, with the participation of international and regional experts. Final reports on alternatives are being currently completed and are expected to be ready for print by the end of Oct. 05. |  |  |  | Some Progress | e
EGY/FOA/22/INV/64 | UNDP | Phaseout of the remaining ODS consumption in the foam sector (11 enterprises) | 12 months delays | Spare delivered and project completed. HOP dated Jan. 2005 |  |  |  | Completed | B
EGY/HAL/32/TAS/81 | UNDP | Halon management bank programme | Status Report | Mission to Cairo was undertaken in August 2005. Discussions were held with the Armed Forces to take on the implementation of the Halon Bank as it appeared they had the most critical uses for Halons. Indications received from Egypt are that the Armed Forces are interested but the official letter is still awaited. Meanwhile, Egypt Ozone office has written to the equipment supplier in September to obtain some details about the layout, area requirement, water, air, electrical requirements and when they can come to commission, indicating that some activity is taking place. Full details about the awareness component and the collection of decommissioned Halons in the civilian sector need to be finalised. |  |  |  | No further status report needed. | D
EUR/SEV/39/TAS/05 | UNEP | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and the Slovak Republic) | 12 months delays | The project was completed in February 2005. A report on the implementation of this project was submitted to ExCom 45. The PCR is currently being prepared. |  |  |  | Completed
GLO/ARS/39/TAS/246 | UNEP | Development of guidelines to promote safety an aerosol conversions | 12 months delays/Status Report | English version printed. Translations into Arabic, Chinese, Russsian, French, Spanish underway. |  |  |  | Some Progress
GLO/SEV/19/TAS/112 | UNEP | Training modules on management of ODS phase-out in SMEs | 12 and 18 months delays/Status Report | Completed. Document translated and printed. |  |  |  | Completed
GLO/SEV/34/TAS/230 | UNEP | Study on development of ODS phase-out strategy for SMEs | 12 months delays | Completed. Document translated and printed. |  |  |  | Completed
GLO/SEV/39/TAS/247 | UNEP | Assistance for regional awareness raising | 12 months delays | Regional awareness products developed and finalised in several regions. |  |  |  | Some Progress
GLO/SEV/39/TAS/248 | UNEP | Production of OzonAction Newsletter in Russian, translation of 4 refrigeration/customs training modules into Russian, and reprinting and updating existing publications | 12 months delays | Project was approved by ExCom 39 on condition that 50% of funds were to come from CAP budget. Thus, disbursements for translation of 4 training manuals were made from the CAP budget. UNEP signed MOU with Georgia NOU for printing of the translated documents. The translation of the manuals was arranged through a consultancy contract. The following training manuals were translated from English to Russian: "Training Manual for Customs Offices: Saving the Ozone Layer – Phasing out Ozone Depleting Substances in Developing Countries", "Recovery and Recycling Systems: Guidelines", "National Training Programmes on Good Practices in Refrigeration" and "Planning, Designing and Implementing Policies to Control Ozone Depleting Substances under the Montreal Protocol: A Handbook of Policy Setting at the National Level". | The "Training Manual for Customs Officers" was proofread and reviewed. Layout and design of the manual was prepared by Georgia NOU. Printing will be done in Oct2005. The proof-reading of the 3 remaining training manuals is in process. Printing is planned to be completed by end 2005. Translation and printing of 3 issues of the Russian version of OzonAction Newsletter in 2005 are covered from the project. The first issue was published in spring 2005, the second issue is being translated and the third one will be prepared in late 2005. |  |  | Some Progress
GRN/SEV/30/INS/02 | UNEP | Creation of a National Ozone Unit | Status Report | The NOO has fufullied all the MP compliance requirements. NOO is contracted under the IS project. The delay is in getting the IS audit reports completed and signed off by the relevant departmental head. |  |  |  | No further status report needed. | D
GRN/SEV/44/INS/07 | UNEP | Institutional strengthening project | Status Report | The NOO has fufullied all the MP compliance requirements. NOO is contracted under the IS project. The delays is in getting the present IS audit reports completed and signed off by the relevant departmental head. |  |  |  | No further status report needed. | D
IDS/FOA/23/INV/77 | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | 12 and 18 months delays | All 30 units of first batch commissioned. Second and last batch of equipment (24 units) delivered, installed and commisioned except for one company. Commissioning started on 28 April and was completed by Aug. 05. One enterprise (PT Cipta Megah Foamindo, Pasuruan) was hit by a fire which caused damage to the equipment before installation took place. A visit to the plant was conducted Apr. 05 by AFI, the FI and KLH staff to confirm the accident. Documentation, including police-report letter was submitted to the government. Solution still pending. WB has given a deadline of Oct. 30, 05 for finding a solution. |  |  |  | Some Progress | c,a,e,b
IDS/FOA/35/INV/129 | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | 18 months delays | Project physically completed and confirmed by KLH May 20, 05. Disbursement of IOC pending receipt of documentation from enterprise. Financial completion is expected by Oct 05. |  |  |  | Completed
IDS/FOA/37/INV/145 | Japan | Phase-out of CFC-11 by conversion to HCFC-14 b in the manufacture of rigid polyurethane foam for insulating purpose at Aneka Citra Refrigeratama Co. | 18 months delays | Due to delayed transfer of funds, PAD was issued only only on 24 December 2002. As UNIDO's rule allows a donor country to limit the bidder to the corporations of its country, the Government of Japan has requested bidder only to Japanese corporations. The requisition For Purchase of equipment was issued on 4 February 2003, and a Japanese bidder won the bidding. The offering from the bidder was satisfactory from commercial and technical viewpoints, and acceptable to both the Government of Indonesia and beneficiary company as well. | UNIDO offered to make a contract with that company. However, due to the terrorist bombing incident in Indonesia, the possible winning company became unable, according to its company's security rule, to dispactch their technical experts for installation of equipment and training of local staff to Indonesia. That company had to withdraw its offer before entering into contract. Another bidding tool place without limitation in nationality, and was successfully completed. As a result, the first disbursement was effected only in 2004. Current Status: Equipment was delivered, installed, commissioned and start up trial was executed accordingly. Project is operationally completed. PCR will be submitted in six months time. |  |  | Completed
IDS/REF/38/INV/151 | UNDP | Refrigeration sector phase-out plan: refrigeration servicing | 12 months delays | Equipment delivered to about 360 servicing and training establishments. Training of trainers completed and training of technicians initiated and in good progress |  |  |  | Some Progress | E
IDS/SEV/37/TAS/149 | IBRD | Strengthening of import/export control | 12 months delays | Indonesia has now ratified the MP amendment making import/export control mandatory. A revised draft regulation was prepared which will be enacted once agreement is reached amongst all involved ministries. Standard Operating Procedure drafted for import licensing and quota system and circulated to various government stakeholders. Meetings are now regularly being held with Ministry of Trade, the legal importer (PPI), the Indonesian Department of Statistics, Ministry of Finance, Ministry of Industry, and KLH to discuss the amendment of the Decree No. 789/MPP/KEP/12/2002. Training and workshop for customs officers completed. Hence, project is completed as planned, but can only be closed once the draft is agreed and adopted by all ministries (expected in 2006). |  |  |  | Some Progress | d
IND/ARS/28/INV/221 | UNDP | Phaseout of CFC by substituting HAPs at Syncaps | 12 and 18 months delays | Completed. Visit in March 2005 confirmed machine correctly installed, CFC stocks depleted and project declared technically completed. HOP signed March 2005 |  |  |  | Completed | G
IND/HAL/29/TAS/243 | UNDP | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | 12 months delays/Status Report | 15 new standards developed and published during 2005. All standards are now finalized and are being distributed to public. Two workshops already took place and final two scheduled for Sept. 2005. Project completion report scheduled for Oct. 2005 |  |  |  | Some Progress | D
IND/HAL/32/TAS/278 | Canada | National halon management and banking programme | Status Report | (A) Project Status - The following provides a status on the principal project activities: 1) a) Project Element: Establish National Halon Bank facility; b) Status: The facility was established and officially inaugurated in September 2004. However, it appears that the facility is not fully in use. No information on amounts of recovered, recycled and reclaimed halon has been received; c) Outstanding Actions: Ensure that the facility becomes fully operational and reports regularly through the ozone cell on quantities of halon recovered, recycled and reclaimed. 2) a) Project Element: Legislation to ban import and production of new halon; b) Status: In process. Ozone cell indicated that draft legislation has been drafted, but is not sure of when it will be approved; c) Outstanding Actions: Approval and provision of legislation. | 3) a) Project Element: Establish National Halon Essential Uses Panel; b) Status: Panel constituted, objectives and functions agreed; c) Outstanding Actions: Nil. 4) a) Project Element: Establish Halon Management Group; b) Status: Group constituted, objectives and functions agreed; c) Outstanding Actions: Nil. 5) a) Project Element: Establish Critical use database; b) Status: Database developed, data collection and entry underway; c) Outstanding Actions: Awaiting status report. 6) a) Project Element: Develop and implement a National program for collection, storage and transportation; b) Status: Development and implementation underway; c) Outstanding Actions: Awaiting status report. | 7) a) Project Element: Provide training coursed for fire system management; b) Status: Initial series of courses completed as per Project Document; c) Outstanding Actions: Assess if further courses are required. 8) a) Project Element: Develop business-specific halon phaseout plans for critical users; b) Status: Completed as per Project Document; c) Outstanding Actions: Nil. 9) a) Project Element: Developing public education and awareness; b) Status: Project requirements completed; c) Outstanding Actions: Nil. | (B) Next Step: There has been very little progress with respect to the implementation of activities still requiring completion since the halon banking facility was inaugurated in September 2004. In order to stimulate further progress, Environment Canada will be undertaking a mission to India during the week of October 10, in order to meet with key project stakeholders, assess the situation of the halon banking facility and obtain agreement from stakeholders on a new plan of action to finalize the project within a six-month period. Information on the results of this mission can be provided to the Secretariat prior to the 47th Meeting of the Executive Committee. | Report at 47th Meeting
IND/HAL/32/TAS/281 | Australia | National halon management and banking programme | Status Report | (A) Project Status - The following provides a status on the principal project activities: 1) a) Project Element: Establish National Halon Bank facility; b) Status: The facility was established and officially inaugurated in September 2004. However, it appears that the facility is not fully in use. No information on amounts of recovered, recycled and reclaimed halon has been received; c) Outstanding Actions: Ensure that the facility becomes fully operational and reports regularly through the ozone cell on quantities of halon recovered, recycled and reclaimed. 2) a) Project Element: Legislation to ban import and production of new halon; b) Status: In process. Ozone cell indicated that draft legislation has been drafted, but is not sure of when it will be approved; c) Outstanding Actions: Approval and provision of legislation. | 3) a) Project Element: Establish National Halon Essential Uses Panel; b) Status: Panel constituted, objectives and functions agreed; c) Outstanding Actions: Nil. 4) a) Project Element: Establish Halon Management Group; b) Status: Group constituted, objectives and functions agreed; c) Outstanding Actions: Nil. 5) a) Project Element: Establish Critical use database; b) Status: Database developed, data collection and entry underway; c) Outstanding Actions: Awaiting status report. 6) a) Project Element: Develop and implement a National program for collection, storage and transportation; b) Status: Development and implementation underway; c) Outstanding Actions: Awaiting status report. | 7) a) Project Element: Provide training coursed for fire system management; b) Status: Initial series of courses completed as per Project Document; c) Outstanding Actions: Assess if further courses are required. 8) a) Project Element: Develop business-specific halon phaseout plans for critical users; b) Status: Completed as per Project Document; c) Outstanding Actions: Nil. 9) a) Project Element: Developing public education and awareness; b) Status: Project requirements completed; c) Outstanding Actions: Nil. | (B) Next Step: There has been very little progress with respect to the implementation of activities still requiring completion since the halon banking facility was inaugurated in September 2004. In order to stimulate further progress, Environment Canada will be undertaking a mission to India during the week of October 10, in order to meet with key project stakeholders, assess the situation of the halon banking facility and obtain agreement from stakeholders on a new plan of action to finalize the project within a six-month period. Information on the results of this mission can be provided to the Secretariat prior to the 47th Meeting of the Executive Committee. | Report at 47th Meeting
IND/REF/38/INV/359 | UNIDO | Plan for phase-out of CFCs in the refrigeration (manufacturing) sector | 12 months delays | Sub agreements with the companies signed. After verification of NOU 25 companies were listed eligible for technical assistance. 10 other companies are being verified by the NOU for eligibility for the inclusion in the project. Bidding for the supply of equipment and services has started. |  |  |  | Some Progress | B
IND/SEV/36/CPG/349 | UNDP | Country programme update | 18 months delays | Draft Update being circulated to other government departments for review, follow by stakeholders workshop early December 2005. Upon final approval CP Update to be submitted to 48th ExCom Meeting |  |  |  | Some Progress | D
IND/SOL/35/TAS/343 | UNEP | Overall strategy for the solvent sector to support the phaseout of ODS in SMEs | 12 months delays | During the last 12 months, awareness raising activities were undertaken to promote non-ODS technology options for the SMEs and on regulatory and legal aspects related to the phase out of ODS solvents. Preparatory work has been carried out to organise the visit of a group of Indian experts to China as part of South-South cooperation that will enhance efforts to phase out ozone depleting solvents. |  |  |  | Completed | C
IRA/FOA/28/INV/50 | UNIDO | Phasing out ODS in manufacturing of flexible PU slabstock foam through the use of liquid CO2 blowing technology at Bahman Plastic Co. | 12 months delays | The Government is still trying solve the labor and management problem. |  |  |  | Some Progress - Milestones Achieved | B
IRA/FOA/31/INV/73 | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Rashestan Co. | 12 months delays | The project was completed. Operational and financial completion is being requested. |  |  |  | Completed | G
IRA/FOA/37/INV/152 | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded PU foam at Sanayeh Dashboard Iran | 12 months delays | Please be advised that the company had recieved one foaming machine which is in operation since last year. A second foaming machine of the company, however, was to be retrofitted for which arrangement with supplier representative has been made. As soon as the retrofitting job is done and the machine inters into production, we will inform you accordingly. |  |  |  | Some Progress
IRA/FUM/29/INV/57 | UNIDO | Phasing out of the important non critical, non-essential use of methyl bromide for post-harvest treatment | 12 months delays | None of the proposals received were technically acceptable. Thus, new offers will be requested. |  |  |  | Some Progress | C
IRA/REF/28/INV/51 | UNIDO | Replacement of CFC-12 refrigerant by HFC-134a at Iran Compressor Manufacturing Company (ICMC) | 12 months delays | Arrangement is made for repair. Upon arrival of the equipment, repair will take around 3 months. |  |  |  | Some Progress | C
IRA/REF/34/INV/111 | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Arjah Boroudat Co. | 12 months delays | The project was completed |  |  |  | Completed | G
IRA/REF/35/INV/133 | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Ghotb Jonoub Industrial Group | 18 months delays | Due to difficulties in admitting a US expert for final verification mission, HOP unable to be issued. Visit foreseen to take place in Oct. 2005 |  |  |  | No Progress--Letter of Possible Cancellation | D
JOR/ARS/31/INV/64 | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | 12 and 18 months delays | Baseline equipment destroyed in Feb. 05. Project completed. |  |  |  | Completed
JOR/HAL/32/INV/69 | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | 12 and 18 months delays | Training course to be implemented in Feb. 06, due to the delay in finalizing the training arrangement in Oman. Contract with the National Training Centre signed Jul. 05. Training is expected to be completed in Feb. 06. |  |  |  | Some Progress | b
KEN/FUM/38/INV/31 | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flower component (first tranche) | 18 months delays | Budget 2005 prepared and endorsed. Flower sector activities underway: procurement, training, installation and adoption of alternatives. Metham sodium application machine operational (required modifications result of soil quality). Identification of nationally owned MB using flower farms in process. |  |  |  | Progress | G
KEN/SEV/37/TAS/29 | UNEP | Policy and technical assistance | 12 months delays | The NOU was assisted to draft and finalise the ODS regulations in 2004. Several reviews and consultations were made and all the comments by different stakeholders were considered. The regulations were submitted to government for approval and gazettement. The process of approval and gazettement has been delayed. It is expected that before the end of this year the regulations would be approved and gazetted. |  |  |  | No Progress--Letter of Possible Cancellation | D
LAO/REF/34/TAS/07 | UNEP | Implementation of the RMP: monitoring the activities contained in the RMP | Status Report | The technican training programme was started in Feb 2005 and customs training has not yet started. Consequently the monitoring activities were delayed. After starting the technicians training proprogramme in 2005, the local consultant under this project was recurited by the country and the first monitoring report was submitted. The second payment is being processed. |  |  |  | No further status report needed. | D
LEB/REF/28/TAS/29 | France | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers | 12 months delays | As already mentioned in the Delays List for the 45th Excom, this project is completed. |  |  |  | Completed | G
LIB/FOA/32/INV/06 | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Garabouli Unit | 12 months delays | Visit in March 2005 confirmed that machine correctly installed, CFC sotcks depleted and project declared technically completed. Safety process workshop held in May 2005. HOP dated May 2005. |  |  |  | Completed | D
LIB/FOA/32/INV/07 | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Electrical Household Appliance-Tajura by conversion to a combination of water and HCFC-141b based systems | 12 months delays | Visit in March 2005 confirmed that machine correctly installed, CFC sotcks depleted and project declared technically completed. Safety process workshop held in May 2005. HOP dated May 2005. |  |  |  | Completed | D
LIB/FOA/32/INV/08 | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Ben Ghazi Unit | 12 and 18 months delays | During visit in March 2005, company indicated wanted to buy a new machine but needed authorization from state head. In May, company received goahead and Purchase Order issued. Delivery scheduled for October 2005. |  |  |  | Some Progress | D
MAL/ARS/19/INV/85 | UNDP | Umbrella project to phase out ODS at SMEs in the aerosol sector | 12 months delays | Project technically completed. Safety audit conducted and certified. Final safety workshop will take place in 3Q05. Final bills to be paid |  |  |  | Some Progress | E
MEX/PRO/40/INV/115 | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (first tranche) | 12 months delays | The project was completed. Operational and financial completion is being requested. |  |  |  | Completed | G
MEX/STE/40/INV/115 | IBRD | Sterilization group project to replace CFC-12 technology-based sterilization equipment by alternative technologies in the hospital medical sterilization sector | 12 months delays | Delays occured prior to SGA signing due to a verification process covering the entire sector. Five of seven SGAs have been signed. Once formal procedures are completed, the other 2 SGAs will be signed by Sep. 05. Three institutions have almost completed their subprojects and entire project is expected to be completed by June 2006. |  |  |  | Some Progress | d
MOR/FUM/29/INV/37 | France | Phase-out of methyl bromide use in the cut flower and banana production | 18 months delays | Regarding the cut flower sector, fumigants 1,3 D (1,3 Dichloropropene) and chloropicrin have been used as alternatives. Consumption of MBR has decreased from 24T in 2004 (35ha) to 7 T in 2005 (10ha), but it is also due to a reduction in the cultivated areas. For the banana sector, quite a lot of complications occurred. All technologies proposed by the project were used in the North of the country without substantial success. MBR consumption has however decreased, due to alternative technologies and also to the high price of MBR. | A one day awareness workshop was organised in May 2005 in Agadir on the need for alternatives. About 300 people took part. 1,3 D in a concentrated emulsifier (approved for tomatoes) had never been used before on banana in Morocco. It was used in 2005. The results are promising and the Ministry of Agriculture, Rural Development and Fishing would like to extend its use to wider areas in three different regions. The Ministry intends to request a further delay of the project in order to cover two agricultural campaign". _ Progress _ " |  |  | Some Progress | C
MOR/FUM/34/INV/44 | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (first tranche) | 12 months delays | Procurement of nursery equipment completed, purchase order issued. Expected delivery time December 2005. Signed subcontract with APEFEL for the provision of various services for the implementation of the project. Recruited the National Project Coordinator and the field expert. 65 ha of tomato have been treated with MB alternative (solarization plus low dosage of nematicide plus grafted seedling) for the crop season 2005/2006. Technical evaluation of offers for the procurement of greenhouses for tomato production completed, the purchase order will be issued in December 2005 as soon as the ExCom approves the next funding tranche. This tranche is operationally completed. |  |  |  | Completed | G
MOR/REF/32/TAS/42 | France | Technical assistance for cold storage equipment (training and demonstration project) | 12 and 18 months delays | This project is completed |  |  |  | Completed | G
NIR/HAL/37/TAS/103 | Germany | Sectoral phase-out programme: establishing a halon bank | Status Report | Germany received information that a total of 5000kg halon 1301 and 9000kg Halon 1211 had been recovered. |  |  |  | No further status report needed.
NIR/PHA/38/INV/106 | UNDP | National CFC phase-out plan: foam sector and refrigeration servicing sector (first tranche) | 12 and 18 months delays | Foam equipment ordered, arrived and distribution to Recipients is ongoing. Order for R&R equipment being finalised. Refrigeration Trainer contracted. Customs Trainer being contracted. – Detailed report will be submitted at 48th ExCom. |  |  |  | Progress | D
NIR/SEV/36/CPG/102 | UNDP | Country programme update | 12 months delays/Status Report | Government is in the process of putting together the complete documentation which will be followed by a National stakeholders workshop before finalising the document. Should be ready for 48th Excom. |  |  |  | Some Progress | D
NIR/SEV/38/TAS/104 | Japan | Assistance for a national information, education and communication campaign for compliance with the Montreal Protocol | 12 and 18 months delays | The consultative process have been completed. Agreement has been reached by all Partners on the implementation schedule and stakeholder responsibilities. The study tour to Tokyo was held in December 2004. The main progress made to date is summarised below: 1) Concept note prepared, finalized and agreed to by all Partners. 2) Project Implementation schedule prepared and agreed to be all Partners. 3) Nigerian consultant retained by the NOU. 4) Japanese consultant retained by UNEP. 5) MOU established between UNEP and Nigeria. 6) TORs for consultants finalized and approved. 7) Consultations with communication experts were held in Tokyo from 9 to 15 December 2004 (phase I). 8) Draft strategy prepared for the workshop in Nigeria. |  |  |  | Completed
OMA/SEV/37/TAS/07 | UNEP | Policy and technical assistance | 12 months delays | The proposed legislation was completed by NOU and submitted to the minister for his approval. CAP is in close contact with NOU to expedite the enactment of the legislation and organized the national workshop of stakeholders on enforcement of the legislation as per the MOU between UNEP and Oman. |  |  |  | No Progress--Letter of Possible Cancellation | D
PAK/FOA/23/INV/20 | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | 12 months delays | Local technician appointed by Hennecke in Jun. 05. 22 enterprises have converted operations and destroyed baseline equipment. One enterprise remains which will be visited by the technical mission in November 2005 to close it. One enterprise has had a fire and will not complete the project as planned - enterprise has lodged insurance claim and is expecting 50 % of the claim. Regarding two machines at the port, the customs department has informed that no date for an auction has been fixed as yet. |  |  |  | Some Progress | b,a
PAK/FOA/25/INV/25 | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | 12 months delays | Same as above |  |  |  | Some Progress | b,a
PAK/FOA/29/INV/34 | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | 12 months delays | Installation completed in July and project is physically completed with the destruction of old machinery Production started Jul. 05. |  |  |  | Completed - Milestones Achieved | a,e
PAK/PAG/35/INV/42 | UNIDO | Conversion of carbon tetrachloride as process solvent to 1,2-dichloroethane at Himont Chemicals Ltd. | 12 months delays | For complete installation some more technological components are required. Procurement of these components has been initiated. We expect delivery of these components by the end of 2005. |  |  |  | Some Progress | B, Other (supplier)
PAK/REF/23/INV/19 | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | 12 months delays | Refrigerant component completed. L/c for the safety equipment for the freezer line opened. Supplier has asked Cool if it has completed the local works as decided in the month of June and OMS has confirmed that it wants to start the installation by mid-Sep 05. National consultant visited Cool in early Sep. 05 to check status of the local works. |  |  |  | Some Progress | b, e
PAK/REF/32/INV/39 | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | 12 and 18 months delays | Refrigeration equipment and one foaming machine (Gusmer) installed. Enterprise has invited the technician of the supplier Cannon, Italy to install the machine, who is awaited. Enterprise is manufacturing some additional equipment to synchronise it with the imported machines. |  |  |  | Some Progress | b,e,a
PAK/REF/32/INV/40 | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Mumtaz Engineers | 13 and 18 months delays | All machinery related to refrigeration and foam are with the enterprise. Installation of foaming machine is done and is in production. Certificate of completion issued. Disposal of the CFC machine to be done in Oct 05. |  |  |  | Some Progress | b,d
PAK/SOL/37/INV/47 | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Riaz Electric Ltd., Lahore | 18 months delays | The project could not be completed as scheduled, since installation of some ancillary equipment and additional ventilation was delayed by the counterpart. This is being now completed. Commissioning and trials will be carried out in October 2005. |  |  |  | Some Progress | B
PAN/PHA/44/TAS/23 | UNEP | National phase-out plan for Annex A (Group I) substances (first tranche) | 12 months delays | Mission planned for SEP-05 in order to discuss and agree text of a MOU with NEW customs authorities. |  |  |  | Some Progress | E
PAR/REF/32/TAS/06 | UNEP | Implementation of the RMP: monitoring and control of ODS and ODS based equipment, and training of customs officers and other inspection officers | Status Report | Local UNDP will open an account in order to release funds and finalize implementation. |  |  |  | Additional status report | E
PAR/REF/32/TAS/10 | UNEP | Implementation of the RMP: policy dialogue programme on complementary policy and enforcement | Status Report | Local UNDP will open an account in order to release funds and finalize implementation. |  |  |  | Additional status report | E
PAR/REF/32/TRA/07 | UNEP | Implementation of the RMP: train of trainers and training of refrigeration service technicians | Status Report | Local UNDP will open an account in order to release funds and finalize implementation. |  |  |  | Additional status report | E
PAR/SEV/39/INS/13 | UNEP | Extension of institutional strengthening project (phase 3) | Status Report | Due to Audit's comments, the ISP should be managed through the local UNDP office. Administrative arrangements are in progress. |  |  |  | Additional status report | E
RWA/REF/41/TAS/09 | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Status Report | A new NOO is contracted and we agreed to start the activities by December 2005. Then we will start the monitoring activities |  |  |  | No further status report needed. | D
RWA/REF/41/TRA/06 | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Status Report | The equipement was ordered and a date for the training of trainers will be set as soon as the equipment is available |  |  |  | No further status report needed. | D
RWA/REF/41/TRA/07 | UNEP | Implementation of the RMP: training programme for customs officers | Status Report | The training of trainers is set for 17-19 November 2005 |  |  |  | No further status report needed. | D
RWA/SEV/36/INS/03 | UNEP | Establishment of the Ozone Unit | Status Report | This phase of the IS project is now completed by the new ODS Officer. |  |  |  | No further status report needed.
RWA/SEV/41/INS/05 | UNEP | Establishment of the Ozone Unit | Status Report | This phase is actively implemented by the NOU that is now fully established and completion of the project is planned for end of 2006. |  |  |  | No further status report needed.
SOM/SEV/35/TAS/01 | UNEP | Formulation of national phase out strategy | 12 months delays | UNEP prepared the CP for submission. Political situation still not stable. |  |  |  | Some Progress | E
SRL/FUM/38/TAS/21 | UNDP | Methyl bromide phase-out for all remaining uses excluding QPS applications | 18 months delays | Implementation of project activities is on-going. Project team is organizing visit for UNDP technical expert during the last week of September 2005. UNDP is coordinating with UNEP so that a joint mission can take place. Project on track. |  |  |  | Progress | B
SYR/FOA/32/INV/68 | UNIDO | Conversion from CFC-11 to HCFC-141b in the production of rigid foam panels at Bassam Baghdan | 12 months delays | The commissioning was completed in July 2005. Verification mission by UNIDO is planned for December 2005. |  |  |  | Some Progress | B
SYR/FUM/41/INV/89 | UNIDO | Phase-out of methyl bromide in grain storage (second tranche) | 12 months delays | All equipment delivered and installed. The second series of training was completed. The third training will be organized in November 2005. |  |  |  | Progress | C, Other (Supplier)
SYR/HAL/34/TAS/77 | Germany | Establishing a halon bank and umbrella project for 63 manufacturers | Status Report | Germany received infomation that a total of 120kg halon 1301 and 150kg Halon 1211 had been recovered. |  |  |  | No further status report needed.
SYR/REF/29/INV/48 | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarkisian Refrigerators | 12 months delays | No activities have been carried out. |  |  |  | No Progress--Letter of Possible Cancellation | B
SYR/REF/29/INV/53 | France | Conversion from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Shoukairi and Co. | 12 months delays | No activities have been carried out. |  |  |  | No Progress--Letter of Possible Cancellation | B
SYR/REF/29/INV/54 | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Bashar Refrigerators | 12 months delays | The company has received equipment, preparation for installation is completed and the project will be commissioned end of October. |  |  |  | Some Progress | B
SYR/REF/29/INV/56 | France | CFC emission reduction in central air conditioning | 12 months delays | The hotel prepared the requested action plan and is very interested in completing the project soonest. It is reflected in the Quotations document which includes prices and timeframe that has been received from Carrier (chiller brand). Further quotations to be submitted. Decision to be taken by mid-October. Delivery 18 weeks later, customs, transport and installation 4 weeks later. |  |  |  | Some Progress - Milestones Achieved | B
THA/HAL/32/INV/134 | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | 18 months delays | Nippon Chemical Co., Ltd. project physically completed. Financial completion is pending approval of PCR, which has been submitted to the Bank for review. Some delays have occurred for Antifire Co., Ltd. Equipment is scheduled to be delivered Oct. 05 and enterprise has committed to completing the project by Nov. 05. |  |  |  | No Progress--Letter of Possible Cancellation | b
TUR/FUM/31/INV/69 | IBRD | Phase-out methyl bromide in the dried fig sector | 12 months delays | Project is nearly physically completed. CO2 tanks installed and trial runs carried out in Jun 05. System will be used in the new season. Expenses in last period are expected from the company for disbursement of remaining funds. |  |  |  | Some Progress | e
TUR/HAL/38/TAS/80 | IBRD | Halon management programme, halon recovery, recycling and banking | Status Report | Delays were due to the time needed to select a suitable and willing executing agency. Energy Systems and Environmental Research Institute (ESERI) under the Marmara Research Center (MRC) of TUBITAK has agreed to implement the halon project. A World Bank mission visited the institute and endorsed the institute as executing agency. The halon project action plan was prepared in Aug. 05 and approved by the World Bank. Project start is expected by Sep. 05 after the subgrant agreement is signed with the executing agency. |  |  |  | No further status report needed. | e
TUR/SOL/35/INV/76 | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | 18 months delays | Project completed physically. Cleaning machine installed and used by the beneficiary. Project will be financially completed after invoices covering last period are sent by the beneficiary. Trial runs completed and old equipment disposed of Jun 05. |  |  |  | Completed | c
VEN/SEV/34/TAS/90 | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | 12 months delays | Project completed in FEB-05. Last disbursement pending financial report from country. |  |  |  | Completed
YUG/FOA/35/INV/14 | UNIDO | Phase out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim Co. | 12 and 18 months delays | The contract for the project site preparatory works including some safety related local works has been concluded. Works are in progress. Final installations of equipment to be executed by the supplier of foaming equipment is envisaged in October 2005. |  |  |  | Some Progress | B,F
YUG/REF/34/INV/13 | Italy | Replacement of CFC-11 with cyclopentane foam blowing agent and CFC-12 with HFC-134a refrigerant in the manufacture of domestic refrigerators and freezers at Obod Elektroindustrija | 12 months delays |  |  |  |  | Report at 47th Meeting