## DataBase
Status | Agency | Project Title | Multi-Year/Multi-Year Partial Phase-out/One-off Phase-Out/Individual/RMP/RMP Update/RMP for Non-LVC/Halon Banking | Region | Country | Sector | Mtg | Type | Num | A/N | O/T | IRD | Chemical | Consumption ODP to be Phased Out per Proposal | Consumption ODP Phased Out | Production ODP to be Phased Out per Proposal | Production ODP Phased Out | Date Approved | First Disbursment Date | Date of Compl per Proposal | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Funds Disbursed (US$) | Per Cent of Funds Disbursed | Balance (US$) | Funds Obligated (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Cost Disbursed (US$) | Support Cost Balance (US$) | Support Cost Obligated (US$) | Remarks (Specify milestone achieved, remedial actions, and issues of relevance to ExCom | Remarks (continued) (for Multi-Year, One-off address provisions of agreement, RMPs; and implementation of conditions of agreements). | Year of Contribution | 22nd Mtg Planned Date of Completion | 28th Mtg Planned Date of Completion | 31st Mtg Planned Date of Completion | 34th Mtg Planned Date of Completion | 37th Mtg Planned Date of Completion | 40th Mtg Planned Date of Completion | 43rd Mtg Planned Date of Completion | 46th Mtg Planned Date of Completion | Year of Business Plan | Business Plan Allocation (Investment/Non-Investment) | Multi-Year Current Tranche - Consumption Performance Target (ODP Tonnes) | Multi-Year Current Tranche - Actual Consumption (ODP Tonnes) | Multi-Year Current Tranche - Production Performance Target (Odp Tonnes) | Multi-Year Current Tranche - Actual Production (ODP Tonnes) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Annual Target Met as Reported by Country (Yes/No) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Verification Completed (Yes/No) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Verification Report to ExCom (Yes/No)
FIN | Australia | Replacement of methyl bromide with non-ozone depleting alternative in grain storage | Individual | AFR | AFR | FUM | 17 | TAS | 14 | A | O | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-10-01 | 1995-11-01 | 38896 | 0 | 38896 | 38896 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | Australia | Provision of training in leak reduction, emission control and recycling and management of non-CFC refrigerants in domestic and commercial refrigeration and air conditioning | Individual | LAC | ARG | REF | 17 | TAS | 24 | A | O | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1996-02-01 | 1996-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | Australia | Support for delegates from six Asian countries to participate in regional workshop on alternatives to CFC | Individual | ASP | ASP | SEV | 07 | TRA | 06 | A | O | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-07-01 | 39394 | -4420 | 34974 | 34974 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1992
FIN | Australia | Support to ASEAN regional conference on CFC and halons | Individual | ASP | ASP | SEV | 08 | TRA | 08 | A | O | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 4420 | -103 | 4317 | 4317 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1993
FIN | Australia | Support to participants to the regional workshop on refrigeration and air conditioning training programme | Individual | ASP | ASP | REF | 12 | TRA | 14 | A | O | D |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-04-01 | 1994-05-01 | 66800 | 0 | 66800 | 66800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1994
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | FSM | REF | 36 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 | 2005-04-01 |  |  | 10000 | 0 | 10000 | 2983 | 29.83% | 7017 | 0 | 7017 | 1300 | 0 |  | 1300 | 1300 | Participated in 2 regional meetings on development of ODS regulations. Little progress made to date in developing regulations. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | FSM | REF | 36 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 | 2005-04-01 |  |  | 26000 | 0 | 26000 | 21083 | 81.09% | 4917 | 0 | 4917 | 3380 | 0 |  | 3380 | 3380 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. |  | 2002
FIN | Australia | Indonesian ODS control policy | Individual | ASP | IDS | SEV | 17 | TAS | 33 | A | O | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-05-01 | 1996-01-01 |  | 1996-01-01 | 1996-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
ONG | Australia | National halon management and banking programme | Individual | ASP | IND | HAL | 32 | TAS | 281 | A | O | I | HAL | 197.2 | 0 | 0 | 0 | 2000-12-01 | 2002-02-01 | 2004-01-01 | 2005-10-01 |  |  | 245700 | 0 | 245700 | 207600 | 84.49% | 38100 | 19400 | 38100 | 0 | 0 |  | 0 |  | The following activities have been completed as planned in 2004: Fire engineering & system maintenance training courses for large halon owners/users: initial series of courses completed; Technical assistance/consultancy services to critical halon users: commenced and ongoing;Public education and awareness activities: project requirements completed. See narrative for activities planned for completion in 2005 |  | 2000
CLO | Australia | Replacement of methyl bromide with non ozone depleting substances in grain storage | Individual | AFR | KEN | FUM | 21 | DEM | 12 | A | O | D |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-07-01 |  |  | 2000-06-01 | 232834 | -91869 | 140965 | 140965 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | 1996
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | KIR | REF | 36 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 | 2005-04-01 |  |  | 10000 | 0 | 10000 | 2983 | 29.83% | 7017 | 0 | 7016.7017 | 1300 | 0 | 0 | 1300 | 1300 | Participated in 2 regional meetings on development of ODS regulations. Little progress made to date in developing regulations. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | KIR | REF | 36 | TAS | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 | 2005-04-01 |  |  | 18000 | 0 | 18000 | 13456 | 74.76% | 4544 | 0 | 4544 | 2340 | 0 | 0 | 2340 | 2340 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | MAS | REF | 36 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 9905 | 3380 | 0 | 0 | 3380 | 3380 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | MAS | REF | 36 | TAS | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | MAS regulations have been approved. Customs training workshop held April 2005. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | SOI | REF | 36 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | Participated in 2 regional meetings on development of ODS regulations. Little progress made to date in developing regulations. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | SOI | REF | 36 | TAS | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 34000 | 0 | 34000 | 23351 | 68.68% | 10649 | 0 | 10649 | 4420 | 0 | 0 | 4420 | 4420 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration” . |  | 2002
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TON | REF | 36 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | Participated in 2 regional meetings on development of ODS regulations. Some progress made to date in developing regulations. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TON | REF | 36 | TAS | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 30000 | 0 | 30000 | 20080 | 66.93% | 9920 | 0 | 9920 | 3900 | 0 | 0 | 3900 | 3900 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TTR | REF | 36 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | Participated in 2 regional meetings on development of ODS regulations. Some progress made to date in developing regulations. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TTR | REF | 36 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2005-04-01 |  |  | 30000 | 0 | 30000 | 17484 | 58.28% | 12516 | 0 | 12516 | 3900 | 0 | 0 | 3900 | 3900 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration” . |  | 2002
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TUV | REF | 36 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 | 2005-04-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | Participated in 2 regional meetings on development of ODS regulations. Some progress made to date in developing regulations. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TUV | REF | 36 | TAS | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 | 2005-04-01 |  |  | 18000 | 0 | 18000 | 13375 | 74.31% | 4625 | 0 | 4624 | 2340 | 0 | 0 | 2340 | 2340 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration” . |  | 2002
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | VAN | REF | 36 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 | 2005-04-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5016 | 1040 | 0 | 0 | 1040 | 1040 | Participated in 2 regional meetings on development of ODS regulations. Little progress made to date in developing regulations. |  | 2002
ONG | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | VAN | REF | 36 | TAS | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 | 2005-04-01 |  |  | 26000 | 0 | 26000 | 14970 | 57.58% | 11030 | 0 | 11030 | 3380 | 0 | 0 | 3380 | 3380 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration” . |  | 2002
COM | Australia | Demonstration project CFC recycling and emissions reduction in the commercial refrigeration sector | Individual | ASP | VIE | REF | 20 | DEM | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1997-12-01 |  | 2001-12-01 |  | 282687 | 0 | 282687 | 208004 | 73.58% | 74683 | 74683 | 0 | 0 | 0 |  | 0 |  | Monitoring phase completed Dec. 2001. Project and final report completed. Australia awaiting UNOPS advice as to the remaining funds from Australia's contribution including interest and confirmation from MLFS that unspent balance including accrued interest should be returned to the MLF. |  | 1996 | 1997-12-01
TRF | Australia | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | Individual | ASP | VIE | REF | 34 | TAS | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 290413 | -290413 | 0 | 0 |  | 0 | 0 | 0 | 37754 | -37754 | 0 | 0 | 0 | Transferred to UNDP at 35th ExCom, December 2001. |  | 2001
FIN | Austria | Establishment of a training centre for commercial refrigeration service technicians at Comservice S.A. |  | EUR | ROM | REF | 20 | TRA | 11 | A | O | I |  | 10 |  |  |  | 1996-10-01 |  | 1997-10-01 |  | 1999-02-01 | 1999-05-01 | 116628 | 0 | 116628 | 116628 | 100% | 0 |  | 0 | [7 empty] | 1996
CLO | Belgium | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Quimica Andina |  | LAC | BOL | FOA | 28 | INV | 10 | A | O | I |  | 5 | 0 |  |  | 1999-07-01 | 0 | 2002-02-01 |  |  |  | 108480 | 0 | 108480 | 0 | 0% | 108480 |  | 60000 | 0 |  |  |  |  | Agreement between UNDP and the Belgian Government finally signed in September 2000. However, funds not yet received as of 31 December 2000. Info as of 31 May 2001: funds received in Feb. 2001. Project document not yet signed by Bolivian Govt. However, invitations to bid were sent out and bid analysi was done. However, we had to re-bid because offers did not meet specs for one machine. New bid analysis on-going. Info as of 31 December 2001: New ministry was undergoing some verification of the enterprises which were being considered for MLF funding since according to some new regulations, in order for Quimica Andina to qualify it needed to be one of the higher national consumers of CFC-11. Only if this was the case would the project be approved and the PRODOC signed. |  | 2001-02-01
FIN | Canada | Implementation of the RMP: training of customs | RMP | LAC | ANT | REF | 26 | TRA | 04 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2002-10-01 | 2002-12-01 | 42940 | 0 | 42940 | 42940 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Complete. PCR submitted. |  | 1998 | [8 empty] | 1998 | Non-Inv.
FIN | Canada | Implementation of the RMP: training the trainers in good refrigerant management practices | RMP | LAC | ANT | REF | 26 | TRA | 05 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 47460 | 0 | 47460 | 47460 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed PCR submitted. |  | 1998 | [8 empty] | 1998 | Non-Inv.
FIN | Canada | Implementation of the RMP: national recovery and recycling | RMP | LAC | ANT | REF | 26 | TAS | 06 | A | O | I | CFC | 1 |  | 0 |  | 1998-11-01 | 2000-06-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. PCR submitted. |  | 1998 | [8 empty] | 1998 | Non-Inv.
ONG | Canada | Implementation of the RMP: training of custom officials | RMP Update | AFR | BEN | REF | 32 | TRA | 08 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2003-01-01 | 2003-06-01 | 2006-06-01 |  |  | 59900 | 0 | 59900 | 59900 | 100% | 0 |  |  | 7787 | 0 | 7787 | 0 |  | Project delayed until ODS import/export legislation was passed in April 2002. Train-the-Trainer Worshop held August 2003 and training of 60 more customs officers followed in 2004. Country considers project finished but Canada has asked that more customs officers be trained, as results are lower than under other comparable projects. Discussions with country and UNEP on when to close project still ongoing. |  | 2000 | [8 empty] | 2000 | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practices | RMP Update | AFR | BEN | REF | 32 | TRA | 09 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-10-01 | 2002-12-01 |  | 2003-12-01 | 2004-12-01 | 144000 | 0 | 144000 | 144000 | 100% | 0 |  | 0 | 18720 | 0 | 18720 | 0 |  | Train-the-Trainer workshop held in Jan. 2002. Phase II training and monitoring completed in 2003. |  | 2000 | [8 empty] | 2000 | Non-Inv.
FIN | Canada | Implementation of the RMP: development of code of good practice for technicians | RMP Update | AFR | BEN | REF | 32 | TAS | 10 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2003-01-01 | 2002-12-01 |  | 2004-06-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 1300 | 0 | 1300 | 0 |  | Final copies of Code of Good Practice received by Canada. |  | 2000 | [8 empty] | 2000 | Non-Inv.
ONG | Canada | Implementation of the RMP: training of environmental inspectors and investigators | RMP Update | AFR | BEN | REF | 32 | TRA | 11 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2005-01-01 | 2003-12-01 | 2006-06-01 |  |  | 57000 | 0 | 57000 | 52000 | 91.23% | 5000 |  | 5000 | 7410 | 0 | 6743 | 667 |  | Train-the-Trainer workshop for 25 environmental inspectors completed in March 2005 and report received. Country was supposed to train additional inspectors but has not done so yet. Canada and UNEP are in discussion with country to ensure completion of the project as agreed. |  | 2000 | [8 empty] | 2000 | Non-Inv.
FIN | Canada | Implementation of the RMP: training of customs officers programme | RMP | AFR | BKF | REF | 29 | TRA | 09 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2002-08-01 | 2003-01-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 |  | 0 | 5525 | 0 | 5525 | 0 |  | Project Complete. PCR submitted. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers and technicians in good refrigeration management practices | RMP | AFR | BKF | REF | 29 | TRA | 10 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-03-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 5200 | 0 | 5200 | 0 |  | Training of technicians is completed as of March 2002. PCR submitted. |  | 1999 | [8 empty] | 1999 | Non-Inv.
ONG | Canada | Project preparation for the terminal phase-out management plan |  | AFR | BKF | PHA | 47 | PRP | 19 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 | 2006-11-01 |  |  | 10000 | 0 | 10000 | 0 | 0% | 10000 |  | 10000 | 1300 | 0 | 0 | 1300 |  | Project preparation initiated in April 2006 |  | 2005
FIN | Canada | Implementation of the RMP: assistance in preparation of regulations and technical norms | RMP | LAC | BOL | REF | 36 | TAS | 17 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2003-11-01 | 2003-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  | 0 | 1690 | 0 | 1690 | 0 |  | Funds disbursed for legal consultant and workshops to develop legislation. Legislation approved in March 2004. Project completed. PCR submitted. |  | 2002 | [8 empty] | 2002 | Investment
COM | Canada | Implementation of the RMP: training programme for customs officers and technical staff in municipalities | RMP | LAC | BOL | REF | 36 | TRA | 19 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2005-04-01 | 2005-04-01 | 48000 | 0 | 48000 | 34028 | 70.89% | 13972 |  | 13972 | 6240 | 0 | 6240 | 0 |  | Train-the-trainers workshop completed in 2004. Phase II customs officers training completed in March 2005 with 83 officers trained. A total of $13,972 remains in funding and will be disbursed in 2006 for use in other RMP components, based on Decision 41/100 which allows for flexibility in use of RMP funds. |  | 2002 | [8 empty] | 2002 | Investment
ONG | Canada | Implementation of the RMP: public awareness programme on issues related to the ozone layer | RMP | LAC | BOL | REF | 36 | TAS | 20 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 | 2006-08-01 |  |  | 52000 | 0 | 52000 | 35664 | 68.58% | 16336 |  | 16336 | 6760 | 0 | 6760 | 0 |  | Public awareness activities have commenced. Posters, hats, 2 videos, public teachers' textbook, radio spots have been produced and distributed. In 2006, a text for training public school teachers will be produced, awareness-raising seminars for importers will be organized, and additional radio spots will be broadcasted. |  | 2002 | [8 empty] | 2002 | Investment
COM | Canada | Implementation of the RMP: training programme for refrigeration technicians | RMP | LAC | BOL | REF | 36 | TRA | 21 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2005-06-01 | 2005-06-01 | 55000 | 0 | 55000 | 53039 | 96.43% | 1961 |  | 1961 | 7150 | 0 | 7150 | 0 |  | Train-the Trainers workshop held in Sept. 2004. Training equipment purchased and distributed. Phase II training completed in May 2005 with 265 technicians trained. A total of $1,961 remains in funding and will be disbursed in 2006 for use in other RMP components, based on Decision 41/100 which allows for flexibility in use of RMP funds. |  | 2002 | [8 empty] | 2002 | Investment
ONG | Canada | Implementation of the RMP: monitoring the activities in the RMP project | RMP | LAC | BOL | REF | 36 | TAS | 22 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-09-01 | 2005-12-01 | 2006-12-01 |  |  | 57000 | 0 | 57000 | 53515 | 93.89% | 3485 |  | 3485 | 7410 | 0 | 7410 | 0 |  | Monitoring database and information system installed and working, as well as ODS monitoring and reporting activities. 2003 data indicates that Bolivia consumed 32.29 ODP tones of CFCs; 2004: 42.37 ODP tonnes. Preliminary data indicates that a total of 575 kg of R-12 was recovered in Bolivia in 2005. |  | 2002 | [8 empty] | 2002 | Investment
ONG | Canada | Implementation of the RMP: recovery and recycling | RMP | LAC | BOL | REF | 39 | TAS | 23 | A | O | I | CFC | 14 |  | 0 |  | 2003-04-01 | 2005-01-01 | 2005-12-01 | 2006-08-01 |  |  | 292000 | 0 | 292000 | 163330 | 55.93% | 128670 | 124915.96 | 3754.04 | 37960 | 0 | 37960 | 0 |  | Project began in the fall of 2004. 1st Phase of R&R equipment was shipped to Bolivia in April 2005 and 2nd Phase in Dec. 2005. ODS import controls in place; NOU reports that CFC-12 imports decreased by 30% in 2004, while prices have increased by approximately 80%. Preliminary data indicates that a total of 575 kg of R-12 was recovered in Bolivia in 2005. |  | 2003 | [8 empty] | 2002 | Investment
ONG | Canada | Project preparation for the terminal phase-out management plan |  | LAC | BOL | PHA | 47 | PRP | 27 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 |  | 30000 | 3900 | 0 | 0 | 3900 |  | Project preparation to be initiated in May 2006 |  | 2005
FIN | Canada | Refrigeration training workshop in the state of Sao Paulo | Individual | LAC | BRA | REF | 11 | TRA | 11 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-09-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project held in September 1993 and approved in retroactive funding in November 1993. |  | 1993 | 2000-01-01 | [7 empty] | 1993 | Non-Inv.
FIN | Canada | Montreal Protocol Technology Transfer Workshop on ODS (Phase II) | Individual | LAC | BRA | SEV | 15 | TRA | 17 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1994-09-01 | 1995-12-01 | 58390 | 0 | 58390 | 58390 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project held in September 1994 and approved in retroactive funding in December 1994 |  | 1994 | 2000-01-01 | [7 empty] | 1994 | Non-Inv.
FIN | Canada | Ozone depleting solvents workshop in Brazil | Individual | LAC | BRA | SOL | 17 | TRA | 25 | A | O | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1994-05-01 | 1996-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project held in May 1994 and approved by retroactive funding in August 1995 |  | 1995 | 2000-01-01 | [7 empty] | 1995 | Non-Inv.
FIN | Canada | Halon recycling and bank management | Halon Banking | LAC | BRA | HAL | 19 | TAS | 47 | A | O | I |  | 0 |  | 0 |  | 1996-05-01 | 1996-10-01 | 1998-05-01 |  | 1999-05-01 | 1999-05-01 | 499360 | -20031 | 479329 | 479329 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project successfully implemented although one year later than planned. Adjustment results of exchange rate fluctuations |  | 1996 | 1998-09-01 | [7 empty] | 1996 | Non-Inv.
FIN | Canada | Implementation of the RMP: training of trainers and refrigeration technicians in good servicing practices | RMP | LAC | BZE | REF | 29 | TRA | 02 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Train the trainers workshop held in April 2001. Subsequent training took place in 2002 and finalized in 2003. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: monitoring and control of ODS and ODS based equipment and training programme for customs and other inspection officers | RMP | LAC | BZE | REF | 29 | TAS | 03 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 3640 | 0 | 3640 | 0 |  | Train-the-trainer customs workshop held in March 2002. Phase II training completed in 2003. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: policy dialogue programme and regulatory framework for phasing out ODSs | RMP | LAC | BZE | REF | 29 | TAS | 04 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2000-09-01 |  | 2001-11-01 | 2002-12-01 | 15500 | 0 | 15500 | 15500 | 100% | 0 |  | 0 | 2015 | 0 | 2015 | 0 |  | Planning and Policy Dialogue component completed Nov. 2001. Regulatory framework developed and adopted by Government. PCR submitted |  | 1999 |  |  |  | 2001-12-01 |  |  |  |  | 1999 | Non-Inv.
FIN | Canada | Bromosorb technology in commodity fumigation | Individual | LAC | CHI | FUM | 15 | DEM | 06 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1997-04-01 | 1997-04-01 | 300000 | 17000 | 317000 | 317000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 1994 | 1996-12-01 | [7 empty] | 1994 | Non-Inv.
FIN | Canada | Refrigerant management plan formulation project | Individual | LAC | CHI | REF | 27 | TAS | 138 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-10-01 | 2001-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. RMP was submitted to the 35th EXCOM and has been approved. |  | 1999 | [8 empty] | 1999 | Non-Inv.
ONG | Canada | Implementation of the RMP: recovery and recycling programme | RMP | LAC | CHI | REF | 35 | TAS | 147 | A | O | I | CFC | 40 |  | 0 |  | 2001-12-01 |  | 2005-04-01 | 2007-12-01 |  |  | 531620 | 0 | 531620 | 0 | 0% | 531620 |  | 212000 | 53162 | 0 | 10000 | 43162 |  | ODS legislation was adopted in January 2006. Some support costs disbursed to design R&R plan and identify equipment options. Project to commence in mid 2006. Work plan to be agreed upon and agreement in place by June 2006. |  | 2001 | [8 empty] | 2001 | Non-Inv.
ONG | Canada | Implementation of the RMP: training programme for technicians and establishment of refrigeration standards | RMP | LAC | CHI | REF | 35 | TRA | 150 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-09-01 | 2004-12-01 | 2006-11-01 |  |  | 260000 | 0 | 260000 | 260000 | 100% | 0 |  | 0 | 33800 | 0 | 33800 | 0 |  | Refrigeration equipment purchased and distributed. Over 800 technicians trained thus far. 800 were to be trained in 2005; final report to be submitted in April 2006. Development of code/standard of good practices completed in July 2005. Retrofit demo strategy developed and demos will be completed before end of 2006. |  | 2001 | [8 empty] | 2001 | Non-Inv.
COM | Canada | Training programme for customs officers | Individual | LAC | COL | REF | 35 | TRA | 52 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2004-07-01 |  | 2005-06-01 |  | 106150 | 0 | 106150 | 106150 | 100% | 0 |  | 0 | 13799 | 0 | 13799 | 0 |  | Project completed. 300 cusotms officers trained and monitoring and evaluation completed. Final reports and financial closure expected by April 2006 |  | 2000 | [8 empty] | 2001 | Non-Inv.
FIN | Canada | Activities in Sichuan Province | Individual | ASP | CPR | SEV | 11 | TRA | 52 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-10-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Workshop held in October 1993 and approved by retroactive funding in September 1994. |  | 1993 | 2000-01-01 | [7 empty] | 1993 | Non-Inv.
CLO | Canada | Feasibility study to establish a refrigerant conservation programme in Sichuan Province | Individual | ASP | CPR | REF | 14 | TAS | 81 | A | O | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  |  | 1997-06-01 | 58400 | -58400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | [7 empty] | 1994 | Non-Inv.
FIN | Canada | No-clean technology programme | Individual | ASP | CPR | SOL | 14 | TAS | 82 | A | O | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  | 1994-11-01 | 1995-09-01 | 51100 | 0 | 51100 | 51100 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | [7 empty] | 1994 | Non-Inv.
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | ASP | CPR | FUM | 22 | DEM | 199 | A | O | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-06-01 | 1999-06-01 |  | 1998-10-01 | 1998-10-01 | 145000 | 0 | 145000 | 145000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project Completed |  | 1997 | [8 empty] | 1997 | Non-Inv.
FIN | Canada | Project preparation for development of a refrigerant management plan | Individual | LAC | CUB | REF | 25 | PRP | 09 | A | O | I |  | 0 |  | 0 |  | 1998-07-01 | 1999-06-01 | 1999-01-01 |  | 1999-09-01 | 2000-09-01 | 22600 | 0 | 22600 | 22600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Although previous reports indicated all funds had been disbursed in 2002, US $2,600 were found to be left-over and were returned to the MLF. See letter to Sectretariat. |  | 1998 | [8 empty] | 1998 | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practice | RMP | LAC | CUB | REF | 29 | TRA | 12 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 10400 | 0 | 10400 | 0 |  | 2650 technicians trained. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: training programme for customs officers | RMP | LAC | CUB | REF | 29 | TRA | 13 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | 667 customs officers trained. ODS Import database system established. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation and enforcement of regulations on ODSs | RMP | LAC | CUB | REF | 29 | TAS | 14 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  | 0 | 2600 | 0 | 2600 | 0 |  | Policy workshop held May 2002. ODS regulations updated. Project errouneously reported as completed in 2003. Completion officially reported by Cuba in 2004 |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: recovery and recycling of CFC-12 in the MAC sector (amendment to the RMP) | RMP | LAC | CUB | REF | 30 | TAS | 15 | A | O | I | CFC | 8 |  | 0 |  | 2000-03-01 | 2001-11-01 | 2002-04-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project erroneously reported as completed in 2003. Additional (final) training took place in 2004. Insufficient data to determine ODP phase-out. However, RMP as a whole is deemed to have contributed to a reduction in the servicing sector of about 90 ODP T between 2000 and 2004. |  | 2000 | [8 empty] | 2000 | Non-Inv.
ONG | Canada | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 26 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 | 2006-12-01 |  |  | 400000 | 0 | 400000 | 149778 | 37.44% | 250222 |  | 250222 | 52000 | 0 | 30000 | 22000 |  | First phase of R&R equipment shipped in May 2005. Public awareness activities initiated in 2005; R&R and retrofitting posters and pamphlets developed, television commercials, updating of ozone webpage, stickers for retrofitted equipment. 2nd and last phase of R&R to be completed by end 2006. |  | 2004
ONG | Canada | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 32 | A | O | I | CFC | 30 |  | 0 |  | 2005-04-01 |  | 2007-04-01 | 2007-12-01 |  |  | 62000 | 0 | 62000 | 0 | 0% | 62000 |  | 40000 | 8060 | 0 | 0 | 8060 |  | Project scheduled to initiate activities at end of 2006. |  | 2005
ONG | Canada | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 35 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 196871 | 0 | 196871 | 0 | 0% | 196871 |  | 50000 | 25593 | 0 | 0 | 25593 |  | External counterpart funding for the project will be secured in 2006 and it is estimated that project activities will initiate during the second semester of 2006. |  | 2005
FIN | Canada | Promoting compliance with the Montreal Protocol in countries with economies in transition (CEITs) | Individual | EUR | GEO | SEV | 27 | TAS | 06 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-03-01 |  | 2001-10-01 | 2002-06-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | GEO | FUM | 30 | TAS | 07 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-01-01 | 2004-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 2000 | [8 empty] | 2000 | Non-Inv.
FIN | Canada | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 180 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-02-01 | 2000-04-01 |  | 2001-07-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | English version of manual completed in April 2001. Printing and dissemination has been completed. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Translation, in French and Spanish, of the approved manual on Customs Officer Training on Substances that Deplete the Ozone Layer | Individual | GLO | GLO | SEV | 32 | TAS | 213 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2001-07-01 |  | 2002-02-01 | 2002-03-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 |  | 0 | 1440 | 0 | 1440 | 0 |  | Translation of manual into Spanish and French completed in early 2002. Both manuals were printed and disseminated in 2002. Project Completed. |  | 2000 | [8 empty] | 2000 | Non-Inv.
FIN | Canada | Implementation of the RMP: national recovery and recycling programme | RMP | LAC | GUY | REF | 23 | TAS | 08 | A | O | I | CFC | 6.5 |  | 0 |  | 1997-11-01 | 1998-04-01 | 2000-12-01 |  | 2003-05-01 | 2003-05-01 | 73450 | 0 | 73450 | 73450 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completion Report submitted. |  | 1997 | [8 empty] | 1997 | Non-Inv.
TRF | Canada | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 41 | INV | 158 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 |  | 2007-12-01 |  |  | 2004-12-01 | 350000 | -350000 | 0 | 0 |  | 0 |  | 0 | 45500 | -45500 | 0 | 0 |  | Project transferred to UNIDO. |  | 2003 | [8 empty] | 2003 | Non-Inv.
FIN | Canada | Initiative to help phase out the release of ODS by Asian SMEs | Individual | ASP | IND | SEV | 15 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1996-02-01 | 1996-02-01 | 109780 | 0 | 109780 | 109780 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | [7 empty] | 1994 | Non-Inv.
ONG | Canada | National halon management and banking programme | Halon Banking | ASP | IND | HAL | 32 | TAS | 278 | A | O | I | HAL | 197.2 |  | 0 |  | 2000-12-01 | 2002-10-02 | 2004-01-01 | 2006-12-01 |  |  | 245700 | 0 | 245700 | 245700 | 100% | 0 |  | 0 | 24570 | 0 | 24570 | 0 |  | Halon reclamation facility established in 2003. Canadian component of project completed. Australian component still ongoing. As reported at ExCom 48, NOU had committed to complete pending work by March 2006. However, since then, NOU requested and was granted extension until the Meeting of the Parties (October 2006). |  | 2000 | [8 empty] | 2000 | Investment
FIN | Canada | Implementation of the RMP: training of trainers in refrigeration and certification of technicians | RMP | LAC | JAM | REF | 27 | TRA | 11 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-10-01 |  | 2000-08-01 | 2001-03-02 | 50850 | 0 | 50850 | 50850 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Phase 1 (train-the trainer) completed 7-11 June 1999. Phase 2 completed in June 2000. Monitoring and evaluation completed August 2000. | PCR submitted to Secretariat | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: customs officers training programme | RMP | LAC | JAM | REF | 27 | TRA | 12 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-10-01 |  | 2001-11-01 | 2001-12-01 | 54240 | 0 | 54240 | 54240 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Legislation finalized in July 99. Phase 1 -train-the-trainer- completed June 2000, Phase 2 completed in Nov. 2000, Monitoring and evaluation completed in Nov. 2001. | PCR submitted to Secretariat. | 1999 |  |  |  | 2001-12-01 |  |  |  |  | 1999 | Non-Inv.
ONG | Canada | Terminal phase-out management plan for CFCs: training and recovery and recycling | One-off Phase-out | LAC | JAM | PHA | 37 | TAS | 16 | A | O | I | CFC | 57.5 |  | 0 |  | 2002-07-01 | 2002-09-01 | 2006-01-01 | 2006-03-01 |  |  | 240000 | 0 | 240000 | 235000 | 97.92% | 5000 |  | 5000 | 31200 | 0 | 31200 | 0 |  | All activities completed by end of 2005. Final monitoring reports received in March 2006. Project technically and financially completed by March 2006. |  | 2002 | [8 empty] | 2002 | Non-Inv.
FIN | Canada | Project preparation for the phase-out of methyl bromide |  | LAC | JAM | FUM | 43 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2005-09-01 | 2005-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 1125 | 0 | 1125 | 0 |  | Project proposal completed in September 2005, submitted and approved at ExCom 47. |  | 2004
ONG | Canada | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | JAM | FUM | 47 | TAS | 22 | A | O | I | MBR | 1.2 |  | 0 |  | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 55530 | 0 | 55530 | 0 | 0% | 55530 |  | 36030 | 7219 | 0 | 0 | 7219 |  | Project contribution agreement drafted. Project to be initiated in May 2006 |  | 2005
ONG | Canada | Methyl bromide replacement demonstration programme | Individual | AFR | KEN | FUM | 26 | DEM | 20 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-05-01 | 1999-12-01 | 2006-06-01 |  |  | 100000 | 0 | 100000 | 90000 | 90% | 10000 |  | 10000 | 0 | 0 | 0 | 0 |  | Worskhops on IPM and other MB alternatives were held in April 2005. Report of workshops received. Project consultant to prepare final report and IPM manual by June 1st 2006 to complete project. |  | 1998 | [8 empty] | 1998 | Non-Inv.
COM | Canada | Development of a regional halon bank management plan for the English-speaking Caribbean (Bahamas, Barbados, Grenda, Guyana, Jamaica, and Trinidad and Tobago) | Halon Banking | LAC | LAC | HAL | 26 | TAS | 28 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-10-01 | 2000-06-01 |  | 2005-12-01 |  | 177410 | 0 | 177410 | 167612 | 94.48% | 9798 | 9798 | 9798 | 0 | 0 | 0 | 0 |  | Establishment of halon clearing house in Trinidad and promotional brochure completed in 2005. All 6 countries finished their halon surveys. All project activities completed. One last payment to UNEP to reimburse University of West Indies for halon clearing house was sent in March 2006. |  | 1998 | [8 empty] | 1998 | Non-Inv.
ONG | Canada | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 122 | A | O | I | MBR | 18.2 |  | 0 |  | 2004-04-01 |  | 2006-10-01 | 2007-10-01 |  |  | 190000 | 0 | 190000 | 0 | 0% | 190000 |  | 129000 | 24700 | 0 | 0 | 24700 |  | Initiation of this project was delayed at request of country, as Mexico preferred to wait until the final results of the UNDP demonstration project. Implementation expected to begin in Jan. 2006. |  | 2004
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | MOL | FUM | 30 | TAS | 06 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-04-01 | 2004-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed in April 2004. PCR submitted |  | 2000 | [8 empty] | 2000 | Non-Inv.
ONG | Canada | Implementation of the RMP including training programmes for refrigeration technicians and customs officers, assistance in the design of policies and regulations and recovery and recycling | RMP | LAC | STK | REF | 24 | TAS | 04 | A | O | I | CFC | 2 |  | 0 |  | 1998-03-01 | 1999-05-01 | 2001-03-01 | 2006-09-01 |  |  | 124300 | 0 | 124300 | 123300 | 99.2% | 1000 |  | 1000 | 0 | 0 | 0 | 0 |  | R&R workshop and customs training were delayed because legislation not yet place. However legislation was adopted in early 2004 and R&R project was completed. Phase I Customs Training also implemented. Final reports by country received in February 2006, essentially completing the project. Final payment of US $1,000 made to UNEP in March 2006, financially completing the project. |  | 1998 | [8 empty] | 1998 | Non-Inv.
FIN | Canada | Implementation of the RMP | RMP | LAC | STL | REF | 23 | TAS | 04 | A | O | I | CFC | 3 |  | 0 |  | 1997-11-01 | 1998-03-01 | 2000-12-01 |  | 2003-12-01 | 2003-12-01 | 146900 | 0 | 146900 | 146900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | All activities completed. Project Completion Report is currently being drafted. |  | 1997 | [8 empty] | 1997 | Non-Inv.
FIN | Canada | Preparation of update of refrigerant management plan | Individual | LAC | STL | REF | 35 | PRP | 06 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-07-01 |  | 2003-11-01 | 2003-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 |  | 0 | 975 | 0 | 975 | 0 |  | RMP Update was completed and project was submitted in Nov. 2003. |  | 2000 | [8 empty] | 2001 | Non-Inv.
ONG | Canada | Implementation of the RMP update | RMP Update | LAC | STL | REF | 41 | TAS | 08 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 | 2006-12-01 |  |  | 73450 | 0 | 73450 | 60327.4 | 82.13% | 13122.6 |  | 13122.6 | 9549 | 0 | 6000 | 3549 |  | Project began in May 2004. Good Practices Training module completed. R&R was purchased and delivered in 2005. Training of technicians to begin in April 2005. Remaining R&R training, retrofit demos to be completed by August 2006. |  | 2003 | [8 empty] | 2003 | Non-Inv.
FIN | Canada | Implementation of the RMP: custom officers training programme | RMP | LAC | URU | REF | 27 | TRA | 29 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2003-06-01 | 2004-05-01 | 71190 | 0 | 71190 | 71190 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers programme in the refrigeration sector | RMP | LAC | URU | REF | 27 | TRA | 30 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2001-06-01 | 2002-03-01 | 63280 | 0 | 63280 | 63280 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Train-the-technicians workshop complete, 150 technicians trained. PCR submitted to Sect. |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation of a license/quota system for ODS | RMP | LAC | URU | REF | 27 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2001-03-01 |  | 2001-11-01 | 2002-04-01 | 11300 | 0 | 11300 | 11300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed and licensing developed as planned. PCR Submitted to Sect |  | 1999 | [8 empty] | 1999 | Non-Inv.
FIN | Canada | Technical assistance in halon sector | Halon Banking | LAC | VEN | HAL | 11 | TAS | 18 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1997-11-01 |  | 1996-05-01 | 1996-05-01 | 414000 | -109500 | 304500 | 304500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1993 | 2000-01-01 | [7 empty] | 1993 | Non-Inv.
FIN | Canada | Halon recycling and bank management (Phase II) | Halon Banking | LAC | VEN | HAL | 19 | TAS | 47 | A | O | I |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1998-05-01 |  | 1998-05-01 | 1998-09-01 | 352220 | -69864 | 282356 | 282356 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented. Adjustment results from lower equipment prices and exchange rate fluctuations. |  | 1996 | 1997-06-01 | [7 empty] | 1996 | Non-Inv.
FIN | Canada | Implementation of a centralized reclamation plant for recovered refrigerants in the commercial refrigeration and air-conditioning sector | Individual | LAC | VEN | REF | 22 | TAS | 55 | A | O | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-06-01 | 1999-06-01 | 495285 | -6685 | 488600 | 488600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997 | [8 empty] | 1997 | Non-Inv.
FIN | Czech Republic | Regional network for 10 article 5 countries in Eastern Europe and Central Asia (jointly implemented with Hungary, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 04 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 58487 | 0 | 58487 | 58487 | 100% | 0 |  |  | 7603 | 0 | 7603 | 0
FIN | Denmark | Establishment of a CFC recycling centre at Zhejiang Donggyang Chemical Factory |  | ASP | CPR | REF | 17 | TAS | 130 | N | O | I |  | 20 |  |  |  | 1995-07-01 | 1996-10-01 | 1996-07-01 | 1998-12-01 | 1998-12-01 |  | 205000 | 0 | 205000 | 161053.25 | 78.56% | 43946.75 |  | 0 | [5 empty] | Completed. Project Document signed in March 1996. Procurement comtract initialed in August 1996 but contract was not signed until 1997. Major delay caused by disagreement on contractual terms. Building modification work completed by enterprise in May 1998 and equipment delivered and installed in June 1998. A seminar for evaluation and dissemination of work experience was held 15-16 December 1998. All project activities were completed in December 1998. More than 50 tons of CFC has been recovered. A few tons of CFC had further been recycled at the reclaim station. |  |  | 1996-12-01
TRF | Finland | Implementation of a training programme for recovery and recycling of refrigerants |  | AFR | ETH | REF | 23 | TRA | 04 | A | O | I | CFC | 0 |  |  |  | 1997-11-01 | 1998-01-01 | 1999-12-01 |  |  | 2000-03-01 | 93490 | -93490 | 0 |  |  |  |  | 0 | [5 empty] | Project transferred to UNEP at ExCom 30 |  | N.a.
FIN | Finland | Customs training manual |  | GLO | GLO | SEV | 27 | TRA | 184 | A | O | I |  | 0 |  |  |  | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2001-11-01 | 2002-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1999 |  |  |  | 2001-06-01
FIN | Finland | Implementation of a training programme for recovery and recycling of refrigerants |  | AFR | NAM | REF | 20 | TRA | 03 | A | O | I | CFC | 5.4 | 5.4 |  |  | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-10-01 | 1999-10-01 | 103440 | 0 | 103440 | 103440 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1997
COM | Finland | Implementation of the RMP: Assistance in the design of policies and regulations |  | LAC | NIC | REF | 25 | TAS | 06 | A | O | I | CFC | 12.8 |  |  |  | 1998-07-01 | 2001-09-01 | 2000-07-01 |  | 2005-12-01 |  | 225430 | 0 | 225430 | 148699.54 | 67.77% | 76730.46 | 76730 | 76730.46 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2005. Licensing system is being enforced by the Ministry of Agriculture. Disbursement of balance is tied to completion of customs training activities under a unique MOU. |  | 1998
ONG | Finland | Implementation of the RMP: Monitoring and evaluation of the RMP | Individual | LAC | PAN | REF | 29 | TAS | 11 | A | O | I | CFC | 0 |  |  |  | 1999-11-01 | 2002-02-01 | 2002-12-01 | 2006-12-02 |  |  | 33000 | 0 | 33000 | 6800 | 20.61% | 26200 | 0 | 29200 | 0 | 0 | 0 | 0 | 0 | Progress report submitted by national consultant in Dec-05 and last disbursement processed under this contract. Phase II training in customs and refrigeration have progressed significantly. Complementary training activities will be completed in 2006 together with the final monitoring activities and report. |  | 2001
ONG | Finland | Implementation of the RMP: Training programme for custom officers | Individual | LAC | PAN | REF | 29 | TRA | 12 | A | O | I | CFC | 0 |  |  |  | 1999-11-01 | 2003-05-01 | 2001-06-01 | 2006-12-02 |  |  | 70000 | 0 | 70000 | 23086 | 37.27% | 46914 | 0 | 43914 | 0 | 0 | 0 | 0 | 0 | Refreshing train the trainers workshop was carried out in Aug-05. Up to Dec-05, 101 customs officers have been trained in 6 workshops around the country. Complementary training to be carried out and completed in 2006. |  | 2001 |  |  |  | 2002-12-01
FIN | France | Technology transfer workshop for African countries on practical implementation of the Montreal Protocol |  | AFR | AFR | SEV | 17 | TRA | 11 | A | O | D |  | 0 |  | 0 |  | 1995-07-01 | 1995-12-01 | 1996-01-01 |  | 1996-02-01 | 1996-02-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Exécuté en février 1996 en coopération ave le PNUE.
FIN | France | Refrigeration and global environment evaluation of equipment modernization study |  | AFR | AFR | REF | 32 | TAS | 26 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-07-23 | 2002-07-01 |  | 2002-12-01 | 2002-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Final report sent to the Secretariat in Mai 2003.
FIN | France | Survey for halon banking management plan in West Asia (Bahrain, Lebanon, Qatar and Yemen) |  | ASP | ASP | HAL | 28 | TAS | 29 | N | O | D |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2000-02-01 |  | 2000-02-01 | 2002-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed.
COM | France | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with Germany) |  | ASP | ASP | HAL | 30 | TAS | 37 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2004-04-21 | 2001-10-01 |  | 2004-12-07 |  | 117500 | 0 | 117500 | 117500 | 100% | 0 |  | 0 | 5875 | 0 | 0 | 5875 |  | Project completed. Final payment to GTZ in 2004.
ONG | France | Implementation of the RMP: training programme for customs officers | Individual | AFR | CAF | REF | 34 | TRA | 08 | N | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 | 2006-11-01 |  |  | 77440 | 0 | 77440 | 50393 | 65.07% | 27047 |  | 27000 | 10067 | 0 | 5838.86 | 4228.14 |  | The Ministry decided to appoint a new ozone officer. Recruitment through the university was unfruitful. Expenses have been explained, but not sufficiently documented. France sent a letter to the Minister in August.
ONG | France | Implementation of the RMP: train the trainers programme for refrigeration technicians in good management practices and a training programme to address technicians in the informal sector | Individual | AFR | CAF | REF | 34 | TRA | 09 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 | 2006-11-01 |  |  | 60900 | 0 | 60900 | 43050 | 70.69% | 17850 |  | 17500 | 7917 | 0 | 4987.71 | 2929.29 |  | The Ministry decided to appoint a new ozone officer. Recruitment through the university was unfruitful. Expenses have been explained, but not sufficiently documented. France sent a letter to the Minister in August.
ONG | France | Implementation of the RMP: development and implementation of a tax/incentive programme | Individual | AFR | CAF | REF | 34 | TAS | 10 | N | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 | 2006-11-01 |  |  | 5500 | 0 | 5500 | 1592 | 28.95% | 3908 |  | 3900 | 715 | 0 | 185.9 | 529.1 |  | The Ministry decided to appoint a new ozone officer. Recruitment through the university was unfruitful. Expenses have been explained, but not sufficiently documented. France sent a letter to the Minister in August.
ONG | France | Implementation of the RMP: monitoring the activities of the RMP project, including registration of refrigeration service technicians, distributors and importers of CFCs | Individual | AFR | CAF | REF | 34 | TAS | 11 | N | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 | 2006-11-01 |  |  | 26250 | 0 | 26250 | 15286.776 | 58.24% | 10963.224 |  | 10900 | 3413 | 0 | 1979.54 | 1433.46 |  | The Ministry decided to appoint a new ozone officer. Recruitment through the university was unfruitful. Expenses have been explained, but not sufficiently documented. France sent a letter to the Minister in August.
FIN | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | 0 | 30000 | 10743.0998 | 35.81% | 19256.9002 |  | 0 | 1500 | 0 | 537.155 | 962.845 |  | une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
FIN | France | Project preparation of phase out of use of ODS solvent in production of parts working in high voltage conditions |  | ASP | CPR | SOL | 29 | PRP | 327 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-07-26 | 2000-12-01 |  | 2002-09-01 | 2002-09-01 | 27500 | 0 | 27500 | 27500 | 100% | 0 |  | 0 | 1375 | 0 | 1375 | 0 |  | Completed project. AFD is waiting for the Chinese Gvt's approval for submission.
ONG | France | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 27 | A | O | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 | 2006-12-01 |  |  | 200000 | 0 | 200000 | 80319 | 40.16% | 119681 |  | 0 | 26000 | 0 | 10441.47 | 15558.53 |  | The French contribution is implemented by GTZ-Proklima. Financial agreement between AFD and GTZ was drafted for this purpose. Technicians studied retrofit systems and potentials and prepared a syllabus on emission reduction; conversion of one cold room to R409; Preparation to retrofit 15 commercial refrigeration systems; development and printing of 1000 retrofit manuals and emission reduction manuals; development of training programme on emission reduction; Training courses in retrofit and emission reduction conducted for 20 trainers and 500 technicians; Preparation of a manual on R409a. - Cuba requested to change Lead Agency Germany and Cooperating Agency France.
ONG | France | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 31 | A | O | I | CFC | 60 |  | 0 |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 |  | 0 | 26000 | 0 | 0 | 26000 |  | The French contribution is implemented by GTZ-Proklima. Financial agreement between AFD and GTZ was drafted for this purpose. Technicians studied retrofit systems and potentials and prepared a syllabus on emission reduction; conversion of one cold room to R409; Preparation to retrofit 15 commercial refrigeration systems; development and printing of 1000 retrofit manuals and emission reduction manuals; development of training programme on emission reduction; Training courses in retrofit and emission reduction conducted for 20 trainers and 500 technicians; Preparation of a manual on R409a. - Cuba requested to change Lead Agency Germany and Cooperating Agency France.
ONG | France | Implementation of the RMP update | Individual | AFR | ETH | REF | 44 | TAS | 14 | A | O | I | CFC | 0 |  | 0 |  | 2004-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 91300 | 0 | 91300 | 0 | 0% | 91300 |  | 55000 | 11869 | 0 |  | 11869 |  | The French contribution is implemented by GTZ-Proklima. Financial agreement between AFD and GTZ was drafted for this purpose. There was a change of personnel at the NOU which led to a delay in the start of implementation, however activities were initiated only late in 2005 and expenditures will be accounted to 2006.
FIN | France | Technical assistance in air conditioning |  | AFR | GHA | REF | 27 | TAS | 11 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-01-18 | 2000-04-01 |  | 2001-04-02 | 2001-04-01 | 31500 | 0 | 31500 | 26379.2079 | 83.74% | 5120.7921 |  | 0 | 0 | 0 | 0 | 0 |  | le Ghana a présenté avec l'aide du PNUD un projet utilisant les 50% restant dans le cadre du Plan de Gestion des Réfrigérants. Il n'est donc plus possible de présenter de projets avant 2007 dans ce pays.
ONG | France | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 374 | A | O | I | CTC | 0 |  | 0 |  | 2004-04-01 |  | 2005-04-01 | 2007-04-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 |  | 657333 | 85000 | 0 |  | 85000 |  | The French contribution is implemented by GTZ-Proklima. The MOU between India, France and Germany was signed in August 2005. The financial agreement between AFD and GTZ was prepared afterwards. Various surveys are being conducted in the sector identifying the different applications of CTC as well as identifying and testing several locally available alternative substances and processes. Preliminary results were presented and discussed in a stakeholder workshop in cooperation with the Indian Textiles Committee. Costs will be accounted for in 2006.
ONG | France | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 387 | A | O | I | CTC | 1385 |  | 0 |  | 2005-04-01 |  | 2006-04-01 | 2008-04-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 |  | 0 | 85000 | 0 | 0 | 85000 |  | The French contribution is implemented by GTZ-Proklima. The MOU between India, France and Germany was signed in August 2005. The financial agreement between AFD and GTZ was prepared afterwards. Various surveys are being conducted in the sector identifying the different applications of CTC as well as identifying and testing several locally available alternative substances and processes. Preliminary results were presented and discussed in a stakeholder workshop in cooperation with the Indian Textiles Committee. Costs will be accounted for in 2006.
FIN | France | Project preparation/technical assistance for MAC recycling and training in good servicing practices |  | ASP | IRA | REF | 20 | PRP | 18 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1997-08-01 | 1997-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet approuvé à la 23ème Réunion
FIN | France | Project preparation and technical assistance in the solvent sector |  | ASP | IRA | SOL | 23 | PRP | 23 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | L'enquête est temrinée. Le projet finalisé a été soumis au Comité Exécutif.
COM | France | Set up of a national programme of recovery and recycling CFC-12 (pilot project in Tehran) |  | ASP | IRA | REF | 23 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1999-10-12 | 1998-12-01 |  | 2004-12-01 |  | 345923 | 0 | 345923 | 242768.0348 | 70.18% | 103154.9652 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Billing issues cleared with IIF and Ozone Office. Final balance to be calculated and unused amount returned to the MF in 2005.
FIN | France | Projects preparation and technical assistance in the halon sector |  | ASP | IRA | HAL | 23 | PRP | 32 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 1999-07-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet sera soumis à la 28ème réunion du Comité Exécutif
COM | France | Conversion to non-CFC facilities of 4 companies producing cars and wagons equipped with MAC-umbrella project |  | ASP | IRA | REF | 24 | INV | 34 | A | O | I |  | 0 |  | 0 |  | 1998-03-01 | 2000-02-22 | 1999-04-01 |  | 2002-06-01 |  | 138600 | 0 | 138600 | 103129.2625 | 74.41% | 35470.7375 |  | 13766.7388 | 0 | 0 | 0 | 0 |  | Waiting for the documents of 1 company for last disbursement and completion. | [6 empty] | 2002-06-01
CLO | France | Small and medium enterprises study |  | ASP | IRA | SEV | 26 | TAS | 36 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 2002-05-01 | 1999-12-01 |  |  |  | 75000 | 0 | 75000 | 20000 | 26.67% | 55000 |  | 0 | 0 | 0 | 0 | 0 |  | A draft report exists on the study. Iran and France have agreed to proceed with the project cancellation in 2005. | [6 empty] | 2002-12-01
COM | France | Conversion to ODS-free technology at Dorcharkh Company |  | ASP | IRA | SOL | 28 | INV | 48 | A | O | I | CTC | 11 |  | 0 |  | 1999-07-01 | 2001-08-22 | 2001-08-01 |  | 2002-12-01 |  | 165140 | 0 | 165140 | 161218.3652 | 97.63% | 3921.6348 | 0 | 0 | 0 | 0 | 0 | 0 |  | This project is completed. Documents of the company to be provided. Remaining balance will be returned once final accounting is carried out in 2005.
ONG | France | Halon management programme | Individual | ASP | IRA | HAL | 28 | TAS | 49 | A | O | I |  | 0 |  | 0 |  | 1999-07-01 | 2002-06-18 | 2003-08-01 | 2006-12-01 |  |  | 511175 | 0 | 511175 | 32943.9362 | 6.445% | 478231.0638 |  | 402660.4434 | 0 | 0 | 0 | 0 |  | Iran and France agreed to retrieve project from Tarbiat Modarres University (TMU) as this institution did not proceed with the implementation. Public bidding was prepared through local press in order to hire a new project co-ordinator.
ONG | France | National CFC phase-out plan: first tranche | Multi-Year | ASP | IRA | PHA | 41 | INV | 163 | A | O | I | CFC | 0 | 59.4 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 | 2006-12-01 |  |  | 1006620 | 0 | 1006620 | 697980 | 69.34% | 308640 |  | 308640 | 110728 | 0 | 76777.6613 | 33950.3387 |  | The French contribution is implemented by GTZ-Proklima based on an agreement concluded in 2004. Distribution of the first 220 pieces of equipment has taken place. Training workshops have been implemented together with the National Training Institute for Vocational Training. Two Train the Trainer Workshops had been organised with the National TVTO. Manual and handouts were provided. The national Vocational Training Organisation (TVTO) has integrated the best practices in their regular training courses, from which several hundred new technicians are certified per year.
ONG | France | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 171 | A | O | I | CFC | 91.4 |  | 0 |  | 2005-04-01 |  | 2007-04-01 | 2008-04-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 |  | 250000 | 55000 | 0 | 0 | 55000 |  | The French contribution is implemented by GTZ-Proklima based on an agreement concluded in 2004. Distribution of the first 220 pieces of equipment has taken place. Training workshops have been implemented together with the National Training Institute for Vocational Training. Two Train the Trainer Workshops had been organised with the National TVTO. Manual and handouts were provided. The national Vocational Training Organisation (TVTO) has integrated the best practices in their regular training courses, from which several hundred new technicians are certified per year.
FIN | France | Refrigeration management plan preparation |  | AFR | IVC | REF | 21 | PRP | 09 | A | O | I |  | 0 |  | 0 |  | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1998-03-01 | 1998-03-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet approuvé à la 24ème réunion du Comité Exécutif
ONG | France | Implementation of the RMP | Individual | AFR | IVC | REF | 24 | TAS | 10 | A | O | I | CFC | 24.8 |  | 0 |  | 1998-03-01 | 1999-10-16 | 2000-04-01 | 2006-12-01 |  |  | 227650 | 0 | 227650 | 31436.2872 | 13.81% | 196213.7128 |  | 160000 | 0 | 0 | 0 | 0 |  | The limited progress of this project is linked to the prevailing political instability. ToRs and tender were sent to companies for the R&R equipment.
FIN | France | Documentary on traffic in second-hand refrigerators |  | AFR | IVC | REF | 27 | TAS | 14 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-04-01 | 2000-06-01 |  | 1999-07-01 | 1999-07-01 | 12000 | 0 | 12000 | 9619 | 80.16% | 2381 |  | 0 | 0 | 0 | 0 | 0 |  | projet achevé
COM | France | Project preparation for projects in commercial refrigeration production facilities |  | AFR | IVC | REF | 37 | PRP | 15 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 1999-12-16 | 2003-08-01 |  | 2004-12-01 |  | 15000 | 0 | 15000 | 13364 | 89.09% | 1636 |  | 0 | 750 | 0 | 750 | 0 |  | This project is completed. A study on a replacement programme for centrifugal chillers was completed in 2002. It was followed by a proposal on the phase out of CFC emissions in centrifugal chillers through energy related activities.
ONG | France | Implementation of the refrigerant management plan: monitoring the activities of the RMP and set up of an import/export licensing system | Individual | AFR | IVC | REF | 37 | TAS | 16 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 |  | 2004-08-01 | 2006-12-01 |  |  | 49500 | 0 | 49500 | 0 | 0% | 49500 |  | 15000 | 4950 | 0 | 0 | 4950 |  | Project on hold due to unstable political environment.
ONG | France | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 37 | INV | 17 | A | O | I | CFC | 18 |  | 0 |  | 2002-07-01 |  | 2006-08-01 | 2006-12-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 |  | 100000 | 100000 | 0 | 0 | 100000 |  | Project on hold due to unstable political environment. Reactivation to be sought by linking it to the chiller demonstration project.
FIN | France | Technical assistance in air-conditioning |  | ASP | JOR | REF | 27 | TAS | 46 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-23 | 2000-04-01 |  | 2002-06-01 | 2002-06-01 | 42000 | 0 | 42000 | 10424.9065 | 24.82% | 31575.0935 |  | 0 | 0 | 0 | 0 | 0 |  | le rapport d'enquête a été achevé. D'un commun accord avec le Gouvernement jordanien, le projet sera transféré à la Banque Mondiale. | [5 empty] | 2001-11-01
ONG | France | Terminal CFCs phase-out management plan (first tranche) | Multi-Year | AFR | KEN | PHA | 44 | INV | 37 | A | O | I | CFC | 45.1 |  | 0 |  | 2004-12-01 |  | 2005-12-01 | 2007-06-01 |  |  | 215914 | 0 | 215914 | 0 | 0% | 215914 |  | 194300 | 28069 | 0 | 0 | 28069 |  | The French contribution is implemented by GTZ-Proklima. Financial agreement between AFD and GTZ is being drafted for this purpose. Kenya is still struggling with the approval of the ODS regualtions which was the condition set by the ExCom for the disbursement of funds. Continuous effort is being made to encourage the Kenyan government to approve the ODS regulations which are prepared and only awaiting formal approval.
ONG | France | Implementation of the RMP: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II) | Individual | ASP | LAO | REF | 34 | TRA | 03 | N | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2005-01-04 | 2004-08-01 | 2006-06-01 |  |  | 78750 | 0 | 78750 | 69750 | 88.57% | 9000 |  | 9000 | 10237 | 0 | 9067.0571 | 1169.9429 |  | Financial agreement signed between Lao and AFD includes the 3 projects. Asia Consultants was selected in Sept 04 to organise and carry out the training over a 2 months period. Necessary training material was bought and training was carried out.
ONG | France | Implementation of the RMP: customs training programme | Individual | ASP | LAO | REF | 34 | TRA | 04 | N | O | I |  | 0 |  | 0 |  | 2001-07-01 |  | 2003-08-01 | 2006-12-01 |  |  | 81542 | 0 | 81542 | 0 | 0% | 81542 |  | 80000 | 10600 | 0 | 0 | 10600 |  | Decree on the Control of the Import, Export and Use of ODSs signed 13 oct 2003. Regulation on Control of Imports, Exports and Consumption of ODSs signed 16 Nov 2004. These were conditions for the training of customs officers to be organised. Tender has then been prepared.
ONG | France | Implementation of the RMP: recovery and recycling, training and demonstration project (complement) | Individual | ASP | LAO | REF | 34 | TAS | 06 | N | O | I |  | 0 |  | 0 |  | 2001-07-01 |  | 2004-08-01 | 2006-12-01 |  |  | 40800 | 0 | 40800 | 18950 | 46.45% | 21850 |  | 35000 | 2040 | 0 | 947.5 | 1092.5 |  | R&R activities will begin in 2006.
FIN | France | Technical assistance for country programme and refrigerant management plan preparation |  | ASP | LAO | SEV | 27 | CPG | 09 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-07 | 2000-12-01 |  | 2001-02-01 | 2001-02-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | le Plan de gestion des réfriférants a été approuvé en même temps que le Programme de pays à la 34ème réunion du Comité Exécutif.
FIN | France | Projects preparation and technical assistance in the foam sector |  | ASP | LEB | FOA | 19 | TAS | 07 | A | O | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-08-01 | 1996-09-01 | 20000 | 0 | 20000 | 19505 | 97.52% | 495 |  |  | 0 | 0 | 0 | 0 |  | Projets d'investissements soumis et approuvés à la 20ème
FIN | France | Conversion to non-CFC technology in the manufacture of polyurethane flexible molded foam at Meuble Mode Sarl |  | ASP | LEB | FOA | 20 | INV | 10 | A | O | I | CFC | 9 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-03-01 | 55700 | 0 | 55700 | 55465 | 99.58% | 235 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en mars 2000
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Furniture and Plastic Sarl (FAP) |  | ASP | LEB | FOA | 20 | INV | 11 | A | O | I | CFC | 28 | 28 | 0 |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 2000-09-01 | 2000-12-01 | 128700 | 0 | 128700 | 128700 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en septembre 2000 |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Plastiflex Sarl |  | ASP | LEB | FOA | 20 | INV | 12 | A | O | I | CFC | 42 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-03-01 | 1999-08-01 | 154000 | 0 | 154000 | 146776 | 95.31% | 7224 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. Rapport d'achèvement soumis |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Merza Foam Sarl |  | ASP | LEB | FOA | 20 | INV | 13 | A | O | I | CFC | 45 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-04-01 | 108172 | 0 | 108172 | 107222 | 99.12% | 950 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en mars 2000
FIN | France | Conversion to non-CFC technology in the manufacture of rigid foam (sandwich panels) at Kilzi and Co. Sarl |  | ASP | LEB | FOA | 20 | INV | 14 | A | O | I | CFC | 22.5 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-11-01 | 1999-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. Rapport d'achèvement soumis, |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Fomaco Sarl |  | ASP | LEB | FOA | 20 | INV | 15 | A | O | I | CFC | 26 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-09-01 | 1999-12-01 | 154000 | 0 | 154000 | 151742 | 98.53% | 2258 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. Rapport d'achèvement soumis
FIN | France | Project preparation for the commercial refrigeration sector |  | ASP | LEB | REF | 20 | PRP | 16 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet approuvé à la 23ème Réunion
FIN | France | Project preparation to establish a CFC and HCFC recovery and recycling centre |  | ASP | LEB | REF | 20 | PRP | 17 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet approuvé à la 23ème Réunion
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | ASP | LEB | REF | 23 | TRA | 20 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1999-06-01 |  | 2000-10-01 | 2000-12-01 | 52668 | 0 | 52668 | 52668 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en octobre 2000
ONG | France | Implementation of an ODS recovery and recycling network | Individual | ASP | LEB | REF | 23 | TAS | 21 | A | O | I | CFC | 62 |  | 0 |  | 1997-11-01 |  | 1998-12-01 | 2006-12-01 |  |  | 425289 | 0 | 425289 | 0 | 0% | 425289 |  | 200000 | 0 | 0 | 0 | 0 |  | The implementation of this project was delayed as Lebanon decided to update its country program first. It was then logical to consider implementing this project at the same time as the NPP. New disagreements occurred on the terms of the financial agreement in between Lebanon and AFD, which further delayed project implementation. |  |  |  |  | 2002-11-01
FIN | France | Conversion of refrigeration industrial facilities |  | ASP | LEB | REF | 23 | INV | 22 | A | O | I | CFC | 10.4 |  | 0 |  | 1997-11-01 | 1999-01-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 166605 | 0 | 166605 | 153162 | 91.93% | 13443 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé
COM | France | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers |  | ASP | LEB | REF | 28 | TAS | 29 | A | O | I |  | 0 |  | 0 |  | 1999-07-01 | 2000-03-23 | 2002-02-01 | 2005-12-01 | 2005-12-01 |  | 45750 | 0 | 45750 | 24784 | 54.17% | 20966 |  | 0 | 0 | 0 | 0 | 0 |  | The study was completed and a draft report was handed over to the NOU (08/2001). Remaining activities could be carried out at the same time than the R&R project. As Lebanon has not expressed any further interest to continue, this project is considered completed.
FIN | France | Country programme preparation |  | AFR | MAG | SEV | 21 | CPG | 01 | A | O | D |  | 0 |  | 0 |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-09-01 | 1999-12-01 | 40000 | 0 | 40000 | 36981 | 92.45% | 3019 |  | 0 | 0 | 0 | 0 | 0 |  | Programme de pays achevé et soumis au Comité Exécutif. Rapport d'achèvement soumis
COM | France | Implementation of the RMP: training of personnel in charge of control and monitoring of imports of ODS |  | AFR | MAG | REF | 29 | TRA | 02 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2003-06-01 |  | 26000 | 0 | 26000 | 25148.9362 | 96.73% | 851.0638 |  | 0 | 1300 | 0 | 1261 | 39 |  | Training of 17 custom's officers and 4 representatives of the ozone office carried out in Antananarivo and Toamasina (Tamatave). Regulations drafted (Décret 2003 / 170). Remaining balance will be returned in 2005.
COM | France | Implementation of the RMP: training of trainers and refrigeration technicians in good service practices |  | AFR | MAG | REF | 29 | TRA | 03 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2004-08-01 |  | 46200 | 0 | 46200 | 44680.8511 | 96.71% | 1519.1489 |  | 0 | 2310 | 0 | 2240.7 | 69.3 |  | Training of 89 trainers and technicians carried out. Remaining balance will be returned in 2005.
COM | France | Implementation of the RMP: set up a national recovery and recycling network |  | AFR | MAG | REF | 29 | TAS | 05 | A | O | I | CFC | 12 |  | 0 |  | 1999-11-01 | 2002-05-30 | 2002-12-01 |  | 2004-08-01 |  | 82700 | 0 | 82700 | 70804.8191 | 85.62% | 11895.1809 |  | 0 | 4135 | 0 | 3556.1 | 578.9 |  | Analysis of best R&R set up given the bad transport/road conditions. A minimum of 7 R&R centres needed, but only 3 identified. Invitation to tender carried out re. equipment. Equipment bought.
ONG | France | Implementation of the RMP: recovery and recycling component | Individual | AFR | MAG | REF | 47 | TAS | 12 | A | O | I | CFC | 7.1 |  | 0 |  | 2005-11-01 |  | 2007-06-01 | 2007-07-01 |  |  | 40500 | 0 | 40500 |  | 0% | 40500 |  | 20000 | 5265 | 0 | 0 | 5265 |  | This project is new.
CLO | France | Phasing out the use of CFC-113 in the electronics industry through the technical promotion of no clean processes |  | ASP | MAL | SOL | 18 | INV | 78 | A | O | D |  | 0 |  | 0 |  | 1995-11-01 |  | 1996-11-01 |  |  | 1997-11-01 | 226600 | -226600 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet annulé
FIN | France | No clean process improvement training for electronic assemblers who phased out the use of CFC-113 |  | ASP | MAL | SOL | 22 | TRA | 97 | A | O | D |  | 0 |  | 0 |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-04-01 | 1999-04-01 | 192423 | 30000 | 222423 | 217885 | 97.96% | 4538 |  |  | 0 | 1500 | 1469.3962 | 30.6038 |  | Projet achevé en avril 1999. Rapport d'achèvement soumis.
FIN | France | Country programme preparation |  | AFR | MAU | SEV | 13 | CPG | 01 | A | O | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-07-01 | 1995-07-01 |  | 1995-07-01 | 1995-09-01 | 44000 | -2580 | 41420 | 39771 | 96.02% | 1649 |  | 0 | 0 | 0 | 0 | 0 |  | Approuvé à la 14ème Réunion
FIN | France | Institutional strengthening project proposal |  | AFR | MAU | SEV | 14 | INS | 02 | A | T | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 1999-12-01 | 1999-12-01 | 38874 | 0 | 38874 | 25983 | 66.84% | 12891 |  | 0 | 0 | 0 | 0 | 0 |  | D'un commun accord entre le Gouvernement et l'AFD le projet sera transféré au PNUE. Rapport d'achèvement soumis.
FIN | France | Training and awareness of personnel involved in the task of codifying and identifying ODS and ODS-containing material |  | AFR | MAU | SEV | 14 | TRA | 03 | A | O | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-10-01 | 1995-09-01 |  | 1996-11-01 | 1996-12-01 | 10000 | 0 | 10000 | 9456 | 94.56% | 544 |  | 0 | 0 | 0 | 0 | 0 |  | La formation a eu lieu du 02 au 04 novembre 1996
FIN | France | Training of refrigeration technicians |  | AFR | MAU | REF | 14 | TRA | 04 | A | O | D |  | 0 |  | 0 |  | 1994-09-01 | 1997-07-01 | 1995-09-01 |  | 1999-06-01 | 1999-08-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. Rapport d'achèvement soumis |  |  | 1997-05-01
FIN | France | Conversion of CFC-based commercial refrigeration installations in the fishing industry |  | AFR | MAU | REF | 14 | TAS | 05 | A | O | D | CFC | 2 |  | 0 |  | 1994-09-01 | 1999-07-01 | 1996-09-01 |  | 2000-11-01 | 2000-12-01 | 106900 | -7378 | 99522 | 99521.8666 | 100% | 0.13336 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé en Novembre 2000. Rapport d'achèvement soumis |  |  |  |  | 2000-06-01
FIN | France | Project preparation in the foam sector (Fofy) |  | AFR | MLI | FOA | 25 | PRP | 04 | A | O | I |  | 0 |  | 0 |  | 1998-07-01 | 1998-08-01 | 1999-01-01 |  | 1998-09-01 | 1998-11-01 | 15000 | 0 | 15000 | 14000 | 93.33% | 1000 |  | 0 | 0 | 0 | 0 | 0 |  | Projet présenté à la 26ème réunion du Comité Exécutif
FIN | France | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Fofy Industrie |  | AFR | MLI | FOA | 26 | INV | 05 | A | O | I | CFC | 19.5 | 19.5 | 0 |  | 1998-11-01 | 2000-01-27 | 2000-12-01 |  | 2001-12-18 | 2001-12-18 | 151000 | 0 | 151000 | 150999.9781 | 100% | 0.021858 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. Rapport d'achèvement en cours d'approbation par Fofy
FIN | France | Project preparation for the formulation of a project to implement a recycling network for CFC-11, CFC-12 and HCFC-22 |  | AFR | MOR | REF | 19 | PRP | 02 | A | O | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1996-11-01 |  | 1997-04-01 | 1997-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet approuvé à la 23ème réunion
FIN | France | Technical assistance on alternative technologies for cold storage facilities |  | AFR | MOR | REF | 20 | TAS | 05 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1999-10-01 | 1999-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | le projet devrait être présenté à la 32ème Réunion du Comité Exécutif
ONG | France | Implementation of an ODS recovery and recycling network | Individual | AFR | MOR | REF | 23 | TAS | 17 | A | O | I | CFC | 22 |  | 0 |  | 1997-11-01 |  | 1998-12-01 | 2006-12-01 |  |  | 355867 | 0 | 355867 | 4398.3921 | 1.236% | 351468.6079 |  | 250000 | 0 | 0 | 0 | 0 |  | Tender was prepared by the CNPP for the R&R operator. Data was updated concerning service workshops. However, Ministry decided to make a public bidding, which further delayed the process. |  |  |  |  | 2002-11-01
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | AFR | MOR | REF | 23 | TRA | 18 | A | O | D |  | 0 |  | 0 |  | 1997-11-01 | 1999-02-01 | 1998-06-01 |  | 2000-12-01 | 2000-12-01 | 53361 | 0 | 53361 | 53361 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en décembre 2000
ONG | France | Phase-out of methyl bromide use in the cut flower and banana production | Individual | AFR | MOR | FUM | 29 | INV | 37 | A | O | I | MBR | 61 |  | 0 |  | 1999-11-01 | 2001-05-29 | 2003-12-01 | 2007-06-01 |  |  | 1006652 | 0 | 1006652 | 928212.3142 | 92.21% | 78439.6858 |  | 78400 | 120732 | 0 | 111324.3992 | 9407.6008 |  | This project is implemented through UNIDO. The activities have been completed in the cut flower sector. The project in the banana sector has encountered delays due to administrative issues first and then through technical complications. A reorientation is being considered, and an evaluation is to be carried out by UNIDO and France in 2006. | [6 empty] | 2005-04-01
COM | France | Technical assistance for cold storage equipment (training and demonstration project) |  | AFR | MOR | REF | 32 | TAS | 42 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2004-01-16 | 2003-01-01 | 2005-08-01 | 2005-08-01 |  | 114337 | 0 | 114337 | 114405.1702 | 100.1% | -68.1702 |  | 0 | 5717 | 0 | 4679 | 1038 |  | Project compleated
ONG | France | Refrigerant management plan update | Individual | AFR | MOZ | REF | 44 | TAS | 12 | A | O | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2005-12-13 | 2007-12-01 | 2007-12-01 |  |  | 104512 | 0 | 104512 | 6073 | 5.811% | 98439 |  | 50000 | 13587 | 0 | 789.5156 | 12797.4844 |  | The French contribution is implemented by GTZ-Proklima. Mozambique lacks ODS regulations so a national legal expert has been hired to assist the NOU make a final draft for approval. Additioanlly Technician trainings are taking place in the regions.
FIN | France | Project preparation for projects in the hotel and fisheries industries and recycling |  | AFR | SEN | REF | 19 | PRP | 06 | A | O | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1996-12-01 | 10000 | 0 | 10000 | 9752 | 97.52% | 248 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. Le projet a été soumis comme à la 30ème réunion du Comité Exécutif comme partie du plan de gestion des réfriégérants.
FIN | France | Training of technicians in domestic refrigeration and air conditioning |  | AFR | SEN | REF | 21 | TRA | 07 | A | O | I |  | 0 |  | 0 |  | 1997-02-01 | 1998-01-01 | 1997-08-01 |  | 1998-03-01 | 1998-06-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Rapport d'achèvement soumis au Comité Exécutif
FIN | France | Project preparation in the commercial refrigeration sector |  | ASP | SYR | REF | 26 | PRP | 35 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 25000 | 0 | 25000 | 16172 | 64.69% | 8828 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | France | Technical assistance in the air-conditioning sector |  | ASP | SYR | REF | 26 | TAS | 37 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 30000 | 0 | 30000 | 25982 | 86.61% | 4018 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
ONG | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarkisian Refrigerators | Individual | ASP | SYR | REF | 29 | INV | 48 | A | O | I | CFC | 3.8 |  | 0 |  | 1999-11-01 |  | 2002-12-01 | 2006-08-01 |  |  | 57783 | 0 | 57783 | 0 | 0% | 57783 |  | 55000 | 2889 | 0 | 0 | 2889 |  | Local company has been selected and is preparing the conversion in the same way as in the Bashar case (29/INV54).
COM | France | Development of a halon banking management plan |  | ASP | SYR | HAL | 29 | TAS | 50 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 |  | 2000-05-01 |  | 2001-05-01 | 2004-04-21 | 10736 | 0 | 10736 | 10736 | 100% | 0 |  |  | 536 | 0 | 536 | 0 |  | Project completed.
ONG | France | Conversion from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Shoukairi and Co. | Individual | ASP | SYR | REF | 29 | INV | 53 | A | O | I | CFC | 2.5 |  | 0 |  | 1999-11-01 |  | 2002-12-01 | 2006-08-01 |  |  | 33359 | 0 | 33359 | 0 | 0% | 33359 |  | 33000 | 1668 | 0 | 0 | 1668 |  | Local company has been selected and is preparing the conversion in the same way as in the Bashar case (29/INV54).
COM | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Bashar Refrigerators |  | ASP | SYR | REF | 29 | INV | 54 | A | O | I | CFC | 3.2 | 3.2 | 0 |  | 1999-11-01 | 2005-02-15 | 2002-12-01 | 2005-12-01 | 2005-12-01 |  | 49113 | 0 | 49113 | 47497.8723 | 96.71% | 1615.1277 |  | 0 | 2456 | 0 | 2375.2321 | 80.7679 |  | Project completed.
ONG | France | CFC emission reduction in central air conditioning | Individual | ASP | SYR | REF | 29 | INV | 56 | A | O | I | CFC | 0.9 |  | 0 |  | 1999-11-01 | 2001-04-06 | 2002-06-01 | 2006-08-01 |  |  | 143000 | 0 | 143000 | 8250.8251 | 5.77% | 134749.1749 |  | 100000 | 7150 | 0 | 412.5413 | 6737.4587 |  | Hotel management indicated preference for a new chiller before accepting containment of its 4 chillers. Explanations were given and quotations were seeked. Request for payment submitted to AFD in December.
COM | France | Establishing a halon bank and umbrella project for 63 manufacturers |  | ASP | SYR | HAL | 34 | TAS | 78 | A | O | I | HAL | 205 |  | 0 |  | 2001-07-01 | 2004-04-21 | 2004-08-01 |  | 2004-04-21 |  | 161000 | 0 | 161000 | 161000 | 100% | 0 |  | 0 | 8050 | 0 | 8050 | 0 |  | Project completed.
FIN | France | No clean process improvement training for electronic assemblers |  | ASP | THA | SOL | 29 | TRA | 124 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-01-18 | 2001-12-01 |  | 2002-12-01 | 2002-12-01 | 118140 | 0 | 118140 | 116000 | 98.19% | 2140 |  | 0 | 5907 | 0 | 5800 | 107 |  | Projet achevé
ONG | France | Implementation of the RMP update | Individual | AFR | UGA | REF | 44 | TAS | 11 | A | O | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2005-07-01 | 2007-12-01 | 2007-12-01 |  |  | 75000 | 0 | 75000 | 12183.9 | 16.25% | 62816.1 |  | 52000 | 9750 | 0 | 1583.907 | 8166.093 |  | The French contribution is implemented by GTZ-Proklima. Uganda requested the purchase of 12 idenitfiers for their border posts. These have been purchased and delivered. Customs training is planned for 2006.
ONG | France | Refrigerant management plan update | Individual | AFR | URT | REF | 46 | TAS | 18 | A | O | I | CFC | 0 |  | 0 |  | 2005-07-01 | 2005-09-05 | 2008-07-01 | 2008-07-01 |  |  | 157252 | 0 | 157252 | 18562 | 11.8% | 138690 |  | 55000 | 20443 | 0 | 2413.0883 | 18029.9117 |  | The French contribution is implemented by GTZ-Proklima. An awareness workshop on RMP Update activities as well as a workshop to finalise the draft regulations have been organised. Each workshop was attended by over 30 persons indicating successful participation.
FIN | France | Country programme preparation |  | ASP | VIE | SEV | 13 | CPG | 03 | A | O | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-08-01 | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 30000 | -8965 | 21035 | 21035 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Le Programme de Pays du Vietnam a été soumis et approuvé pendant la 19ème Réunion du Comité Exécutif.
FIN | France | Technical assistance on alternative technologies for cold storage facilities and project preparation |  | ASP | VIE | REF | 20 | TAS | 12 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-09-01 | 1999-05-01 | 40000 | 0 | 40000 | 34500 | 86.25% | 5500 |  |  | 0 | 0 | 0 | 0 |  | Projet soumis au Comité (29ème réunion)
FIN | France | CFC emission reductions in spinning halls air conditioning systems chillers (pilot project) |  | ASP | VIE | REF | 28 | INV | 22 | A | O | I | CFC | 3.6 |  | 0 |  | 1999-07-01 | 2001-06-12 | 2001-08-01 |  | 2002-12-31 | 2002-12-01 | 197340 | 0 | 197340 | 197340 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé | [6 empty] | 2002-12-01
ONG | Germany | National ODS Phase Out Plan | Multi-Year | ASP | AFG | PHA | 47 | INV | 06 | A | O | I | CFC | 28 |  | 0 |  | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 118438 | 0 | 118438 | 0 | 0% | 118438 | 0 | 118438 | 15397 | 0 | 0 | 15397 | 0 | Project has only been approved in Nov. 05. Implementation to start in 2006.
ONG | Germany | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | Individual | AFR | AFR | HAL | 35 | TAS | 29 | A | O | I | HAL | 27 |  | 0 |  | 2001-12-01 | 2002-08-01 | 2005-01-01 | 2007-12-01 |  |  | 350000 | 0 | 350000 | 240841 | 68.81% | 109159 | 0 | 52000 | 45500 | 0 | 31309.33 | 14190.67 | 0 | Drafted new strategy for regional halon management. New stragey approved by the participating countries. MOU discussions on Halon recovery and recycling ongoing with Afrox. | [10 empty] | 2001
FIN | Germany | Project preparation, technical assistance in the halon sector |  | AFR | ALG | HAL | 31 | PRP | 42 | A | O | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-01-01 | 2002-01-01 |  | 2001-06-01 | 2002-03-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 |  | 1368 | 0 | 1368 | 0 | 0 | Project preparation lead to Halon bank project approved at 35th ExCom | [10 empty] | 1999
COM | Germany | Conversion of Algeria Mousse Polyurethane (AMP) |  | AFR | ALG | FOA | 31 | INV | 44 | A | O | I | CFC | 152 |  | 0 |  | 2000-07-01 | 2000-08-01 | 2003-08-01 |  | 2004-12-01 |  | 565728 | 0 | 565728 | 565728 | 100% | 0 | 0 | 0 | 73545 | 0 | 73545 | 0 | 0 | Project completed. PCR has been submitted to the country | [10 empty] | 2002
COM | Germany | Conversion of SOFTPM, Choupot Oran, to LCD technology |  | AFR | ALG | FOA | 32 | INV | 45 | A | O | I | CFC | 80 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 |  | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 | 0 | 64792 | 0 | 64792 | 0 | 0 | Project completed. PCR has been submitted to the country | [10 empty] | 2002
COM | Germany | Conversion of Matelas Souf to LCD technology |  | AFR | ALG | FOA | 32 | INV | 46 | A | O | I | CFC | 95 |  | 0 |  | 2000-12-01 | 2001-01-11 | 2002-01-01 |  | 2004-12-01 |  | 561379 | 0 | 561379 | 561379 | 100% | 0 | 0 | 0 | 72979 | 0 | 72979 | 0 | 0 | Project completed. PCR has been submitted to the country | [10 empty] | 2002
COM | Germany | Project preparation in the solvent sector |  | AFR | ALG | SOL | 33 | PRP | 48 | A | O | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed. Strategy will be included in NPP. | [10 empty] | 2002
COM | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector |  | AFR | ALG | FOA | 33 | PRP | 49 | A | O | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 |  | 30900 | 0 | 30900 | 30900 | 100% | 0 | 0 | 0 | 4017 | 0 | 4017 | 0 | 0 | Project completed. A report has been prepared and will be used in preparation of the terminal phase out plan. | [10 empty] | 2002
ONG | Germany | Sectoral phase out programme: establishment of a halon bank | Individual | AFR | ALG | HAL | 35 | TAS | 51 | A | O | I | HAL | 195 |  | 0 |  | 2001-12-01 | 2002-10-01 | 2005-01-01 | 2006-12-01 |  |  | 259500 | 0 | 259500 | 259500 | 100% | 0 | 0 | 0 | 33735 | 0 | 33735 | 0 | 0 | Training of 130 engineers in Hassi Messaoud. Training in how to set up non-halon fire protection systems based on existing standards and norms.
ONG | Germany | Project preparation for terminal ODS phase out management plan, excluding the refrigeration sector |  | AFR | ALG | PHA | 37 | PRP | 57 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 | 2006-12-01 |  |  | 42000 | 0 | 42000 | 38500 | 91.67% | 3500 | 0 | 3500 | 5460 | 0 | 5005 | 455 | 0 | Terminal phase out plan to be submitted to 50th Excom meeting.
ONG | Germany | Development of a country programme update |  | AFR | ALG | SEV | 43 | CPG | 60 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-09-01 | 2005-07-01 | 2006-12-01 |  |  | 13500 | 0 | 13500 | 13500 | 100% | 0 | 0 | 0 | 1215 | 0 | 1215 | 0 | 0 | CPU is finalised and awaits approval of the governjment. To be submitted at the 49th meeting.
FIN | Germany | Country programme preparation |  | AFR | ANG | SEV | 34 | CPG | 02 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | National consultants contracted, survey on ODS consump finalized, Country Programme prepared and submitted together with prop. for I.S. Angola. Aproved at 38th ExCom. (1st instalment of 1st tranche of IS funding of 81000) Request for 2nd instalment of IS funding will be submitted at 42nd ExCom. Furthermore a prop. for RMP Angola was prepared in the framework of CP preparation and approved at the 39th ExCom. | [10 empty] | 1998
ONG | Germany | Establishment of the Ozone Unit |  | AFR | ANG | SEV | 38 | INS | 03 | N | O | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-04-01 | 2005-12-01 | 2006-11-01 |  |  | 71682 | 141618 | 213300 | 152940 | 71.7% | 60360 | 0 | 60360 | 9319 | 18411 | 19882.917 | 7847.083 | 0 | Installation of NOU-office in Luanda has been completed, with internet and telepone /fax connection. Regionals support groups have been created in serveral of Angolas provinces in order to assist NOU in the fields of data collection, public awareness activities, etc. ODS data for 2004 has been submitted to both Ozone Secretariat and Multilateral Fund Secretariat. | [10 empty] | 1998
ONG | Germany | Implementation of the RMP: enforcement of regulations, training of customs officers, training of refrigeration service technicians, recovery and recycling, incentive programme for end-users, and public awareness | Individual | AFR | ANG | REF | 39 | TAS | 04 | A | O | I | CFC | 103 | 51 | 0 |  | 2003-04-01 | 2003-11-01 | 2008-04-01 | 2008-04-01 |  |  | 700000 | 0 | 700000 | 212203 | 30.31% | 487797 | 0 | 150000 | 87000 | 0 | 26373.8014 | 60626.1986 | 0 | Training courses were conducted in the towns of Namibe, Benguela and Cabinda. A public awareness campagne has been launched, including the southern provinces (Cuando Cubango, Namibe) as well as the provinces of Cabinda and Luanda. A working group has been created within the Ministry of Urbanism and Environment in order to acellerate preparation and presentation of draft on ODS related legislation and regulations. | [10 empty] | 1998
COM | Germany | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) |  | ASP | ASP | HAL | 30 | TAS | 36 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-02-01 | 2001-10-01 |  | 2005-04-01 |  | 117500 | 0 | 117500 | 117500 | 100% | 0 | 0 | 0 | 15275 | 0 | 15275 | 0 | 0 | Evaluation meeting Beirut 31.5.-4.6.2004; Comment on Terms, Comment on evaluation report; Calculation of operational costs of halon R&R equipment; contact addresses and quotations received for storage cylinders; discussion of alternative strategies. Project completed. | [10 empty] | 1997
FIN | Germany | Survey for halon banking management plan in West Asia: Bahrain, Lebanon, Qatar and Yemen |  | ASP | ASP | HAL | 28 | TAS | 39 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-02-01 |  | 2000-03-01 | 2000-09-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project approved at 30th ExCom. | [10 empty] | 2001
COM | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | BOT | REF | 26 | TAS | 06 | A | O | I | CFC | 1.5 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2005-06-05 |  | 70375 | 0 | 70375 | 70375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR to be submitted in 2006 | [10 empty] | 2000
COM | Germany | Project preparation for an RMP update |  | AFR | BOT | REF | 39 | PRP | 07 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-12-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project preparation completetd. RMP update to be submitted for approval at 45th Excom | [10 empty] | 2002
ONG | Germany | RMP Update | Individual | AFR | BOT | REF | 45 | TAS | 09 | A | O | I | CFC | 0 |  | 0 |  | 2005-11-01 | 2005-11-01 | 2007-03-06 | 2007-06-05 |  |  | 64295 | 0 | 64295 | 6280 | 9.767% | 58015 | 0 | 40000 | 8358 | 0 | 816.3658 | 7541.6342 | 0 | Only 1 technician training has been conducted. The issue of regulations is dragging all other activities.
COM | Germany | Pilot project: training programme for the refrigeration maintenance sector |  | LAC | BRA | REF | 34 | TRA | 228 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2004-08-01 |  | 247400 | 0 | 247400 | 247400 | 100% | 0 | 0 | 0 | 32162 | 0 | 32162 | 0 | 0 | Project completed. Strategy derived from the demonstration project has been subvmitted with the National Phase Out Plan or Brazil | [10 empty] | 2002
ONG | Germany | National CFC phase out plan: training of customs officers | Multi-Year | LAC | BRA | PHA | 37 | TRA | 260 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 | 2006-12-01 |  |  | 141200 | 0 | 141200 | 80331.08 | 56.89% | 60868.92 | 0 | 60868.92 | 18356 | 0 | 10443.0404 | 7912.9596 | 0 | Training activities completed. Refrigerant identifiers need still to be distributed to Customs officers.
ONG | Germany | National CFC phase-out plan: training of refrigeration mechanics in domestic and commercial refrigeration service sub-sectors (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | TRA | 261 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 | 2006-12-01 |  |  | 435937 | 1062863 | 1498800 | 1032148.55 | 68.86% | 466651.45 | 0 | 466651.45 | 56672 | 95658 | 104902.0474 | 47427.9526 | 0 | Training programme has been conducted in Sao Paolo region, where more than 2000 Trainees have been trained by end of 2004. Training has also been extended to 6 other regions and has started there as well.
ONG | Germany | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 265 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2005-04-01 | 2005-12-01 | 2006-12-01 |  |  | 700000 | 0 | 700000 | 105000 | 15% | 595000 | 0 | 595000 | 63000 | 0 | 9450 | 53550 | 0 | Project (2nd tranche) approved in April 2004 (Excom 42). For project progress see comments on BRA/PHA/37/TRA/261
FIN | Germany | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) | Individual | ASP | CPR | REF | 16 | INV | 115 | N | O | I | CFC | 174 | 174 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 1336918 | 0 | 1336918 | 1336918 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completion report submitted Oct 99 |  |  | 2000-01-01 | [7 empty] | 2002
COM | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at China Aerospace Industry Corp. Kunming Refrigerator Factory |  | ASP | CPR | REF | 27 | INV | 282 | A | O | I | CFC | 95.5 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-04-01 |  | 2004-12-01 |  | 1451137 | 0 | 1451137 | 1451137 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR ready for submission, seen and commented by NOU (April 2006). | [10 empty] | 2002
FIN | Germany | Project preparation/technical assistance in the refrigeration sector (thermostat) |  | ASP | CPR | SEV | 33 | PRP | 372 | A | O | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2001-12-01 |  | 2002-01-02 | 2002-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 |  | 650 | 0 | 650 | 0 | 0 | Completed; no PCR due to project preparation only | [10 empty] | 2002
COM | Germany | Conversion of the use of CFC-12 to HC in the manufacture of thermostats at Foshan Tongbao Co., Ltd. |  | ASP | CPR | REF | 35 | INV | 384 | A | O | I | CFC | 11.5 |  | 0 |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 |  | 213271 | 0 | 213271 | 213271 | 100% | 0 | 0 | 0 | 27725 | 0 | 27725 | 0 | 0 | Project completed. PCR seen and commented by NOU (April 2006). | [10 empty] | 2002
ONG | Germany | Development of a suitable strategy for the long term management of HCFCs, in particular HCFC-22 | Individual | ASP | CPR | REF | 43 | TAS | 414 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-11-01 | 2005-12-01 | 2006-12-01 |  |  | 300300 | 0 | 300300 | 224014.73 | 74.6% | 76285.27 | 0 | 76285.27 | 39039 | 0 | 29121.9149 | 9917.0851 | 0 | R22 Enduser survey has been finalised. Project enters phase of data processing, analysis and synthesis of alternative strategies. Preliminary draft has been completed and is waiting authorisation from chinese authorities.
TRF | Germany | Project preparation for phasing out ODS use in Pliva Pharmaceuticals |  | EUR | CRO | ARS | 36 | PRP | 16 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-04-01 | 16500 | -16500 | 0 |  |  | 0 | 0 |  | 2145 | -2145 | 0 | 0 | 0 | Project was offset against Germany contributions at the 39th meeting. Project funds have been transferred to the Croatia Halon project preparation project.
FIN | Germany | Project preparation/technical assistance for the halon sector |  | EUR | CRO | HAL | 39 | PRP | 19 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2004-07-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 | 0 |  | 2145 | 0 | 2145 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
ONG | Germany | Sectoral phase-out programme: establishment of a halon bank | Individual | EUR | CRO | HAL | 43 | TAS | 24 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2007-07-01 | 2007-07-01 |  |  | 60000 | 0 | 60000 | 5000 | 8.333% | 55000 | 0 | 25000 | 7800 | 0 | 650 | 7150 | 0 | The largest halon system is installed in the National Library. Activities were so far limited to assisting Croatia in finding a suitable setting for the R&R Center. Up to now no suitable place could be identified. 2005: Recovery and Recycling Refresher Course conducted. 24 technicians got training in R&R of CFCs. Equipment was handed over.
FIN | Germany | Preparation of a CFC phase out management plan |  | LAC | CUB | PHA | 37 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-07-01 | 2004-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Project preparation lead to project approval at 43rd Excom | [10 empty] | 2002
ONG | Germany | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 25 | A | O | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 | 2006-12-01 |  |  | 120000 | 0 | 120000 | 43453 | 36.21% | 76547 | 0 | 0 | 15600 | 0 | 5648.89 | 9951.11 | 0 | Technicians studied retrofit systems and potentials and prepared a syllabus on emission reduction; conversion of one cold room to R409; Preparation to retrofit 15 commercial refrigeration systems; development and printing of 1000 retrofit manuals and emission reduction manuals; development of training programme on emission reduction; Training courses in retrofit and emission reduction conducted for 20 trainers and 500 technicians; Preparation of a manual on R409a. Cuba requested the change of implementation agencies.
ONG | Germany | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 30 | A | O | I | CFC | 19.7 |  | 0 |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 116000 | 0 | 116000 | 0 | 0% | 116000 | 0 | 0 | 15080 | 0 | 0 | 15080 | 0 | see remarks under MLF No. CUB/PHA/43/TAS/25
FIN | Germany | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and cucurbits) | Individual | AFR | EGY | FUM | 25 | PRP | 68 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1998-12-01 |  | 1998-08-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Implementation of the demonstration | [10 empty] | 1998
FIN | Germany | Four alternatives to the use of methyl bromide in horticulture (strawberries, tomatoes, cucurbits) | Individual | AFR | EGY | FUM | 26 | DEM | 69 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-12-01 | 2001-03-01 | 308000 | -81000 | 227000 | 227000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completion report submitted. Balance was offset against German contribution at the 40th Meeting.
FIN | Germany | Application of methyl bromide alternatives in grain storage | Individual | AFR | EGY | FUM | 26 | DEM | 70 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completion report submitted. | [10 empty] | 1995
FIN | Germany | Development of a refrigerant management plan |  | AFR | EGY | REF | 27 | PRP | 71 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 1999-09-01 | 2002-01-01 | 28700 | 0 | 28700 | 28700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
COM | Germany | Implementation of the RMP: modification of legal provisions and information system |  | AFR | EGY | REF | 29 | TAS | 74 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2002-12-01 |  | 2004-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | UNIDO was subcontracted. Project completed. Draft PCR prepared. Submission will be after completion of and together with EGY/REF/29/TAS/75 (R&R). | [10 empty] | 1997
ONG | Germany | Implementation of the RMP: establishing a national recovery and recycling network | Individual | AFR | EGY | REF | 29 | TAS | 75 | A | O | I | CFC | 100 |  | 0 |  | 1999-11-01 | 2000-04-01 | 2002-12-01 | 2006-12-01 |  |  | 599500 | 0 | 599500 | 563601 | 94.01% | 35899 | 0 | 35899 | 77935 | 0 | 73268.13 | 4666.87 | 0 | The price of CFC increased to US$ 4 during 2004 as required by ExCom. A MOU and workplan were agreed between the Government of Egypt and GTZ in Nov-04. Project implementation will proceed in 2005. R&R equipment has been purchased and delivered to Egypt. It is ready for distributed to the different regions. Training courses have been prepared and will be conducted in 2006.
COM | Germany | Implementation of the RMP: implementation of measures to address the informal sector |  | AFR | EGY | REF | 29 | TAS | 76 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2002-12-01 |  | 2004-12-01 |  | 252500 | 0 | 252500 | 252500 | 100% | 0 | 0 | 0 | 32825 | 0 | 32825 | 0 | 0 | Unido was subcontracted, training courses have been carried out successfully. Project completed. Draft PCR prepared. Submission will be after completion of and together with EGY/REF/29/TAS/75 (R&R). | [10 empty] | 1997
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ETH | REF | 23 | PRP | 05 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 1999-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation | [10 empty] | 1998
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | ETH | REF | 26 | TAS | 06 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-10-01 | 2005-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. RMP update approved in dec 2004 | [10 empty] | 2000
FIN | Germany | Project preparation for a refrigerant management plan update |  | AFR | ETH | REF | 37 | PRP | 10 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom | [10 empty] | 1998
FIN | Germany | Promoting compliance with the Montreal Protocol in countries with economies in transition (Croatia and Romania) |  | EUR | EUR | SEV | 28 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2001-08-01 | 2003-10-01 | 67800 | -6900 | 60900 | 60900 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [11 empty] | 2002
FIN | Germany | Project preparation for additional activities for Gambia RMP |  | AFR | GAM | REF | 32 | PRP | 11 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2004-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project completed and resultant RMP update is being implemented. | [10 empty] | 1998
ONG | Germany | Implementation of the RMP: phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | GAM | REF | 37 | TAS | 12 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-03-01 | 2005-01-01 | 2007-01-01 |  |  | 76700 | 0 | 76700 | 48352 | 63.04% | 28348 | 0 | 28348 | 9971 | 0 | 6285.76 | 3685.24 | 0 | 3 additional technician training (49 technicians trained) and a further customs training has been conducted (24 officers trained). | [10 empty] | 1998
FIN | Germany | Support to attend the Alternatives to CFC and Halons Technologies and Substances conference | Individual | GLO | GLO | SEV | 07 | TRA | 26 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-10-01 | 1992-10-01 |  | 1992-10-01 | 1994-10-01 | 18378 | 0 | 18378 | 18378 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | Germany | Information video: working safely with hydrocarbons in domestic and small scale commercial refrigeration |  | GLO | GLO | REF | 23 | TRA | 138 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1998-08-01 |  | 2001-01-01 | 2002-12-01 | 322050 | 0 | 322050 | 322050 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completion report submitted Dec 2003 | [10 empty] | 2002
FIN | Germany | Travel expenses for participants to attend a regional workshop on methyl bromide alternatives for North African countries (Algeria, Egypt, Jordan, Lebanon, Morocco, Syria, Tunisia) | Individual | GLO | GLO | FUM | 25 | TRA | 161 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-05-01 | 1999-06-01 |  | 1998-06-01 | 1999-07-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | Germany | Implementation of RMPs for 14 low volume consuming countries in eastern and southern Africa |  | GLO | GLO | REF | 26 | TAS | 172 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-11-01 | 2005-09-01 | 815000 | 0 | 815000 | 815000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All countries completed the activities under this project. PCR is to be submitted | [10 empty] | 2000
FIN | Germany | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector |  | ASP | IND | REF | 32 | TAS | 288 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2004-04-05 | 2004-04-01 | 240200 | 0 | 240200 | 240200 | 100% | 0 | 0 |  | 31226 | 0 | 31226 | 0 | 0 | India's National CFC consumption Phase-Out Plan with special refeence to the Refrigeration Service Sector was approved at the 42nd ExCom (IND/REF/42/INV/369). | [10 empty] | 2002
FIN | Germany | Project preparation for the phase out of ODS use in the flexible molded foam sub-sector in 5 enterprises |  | ASP | IND | FOA | 34 | PRP | 309 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-10-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 |  | 3088 | 0 | 3088 | 0 | 0 | 2 resultant investment projects were submitted and approved in Mar-02 | [10 empty] | 2002
COM | Germany | Conversion from CFC-11 to water-based technology at Precision Engineering Tools and Components |  | ASP | IND | FOA | 36 | INV | 350 | A | O | I | CFC | 22 |  | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-05 |  | 200282 | 0 | 200282 | 200256 | 99.99% | 26 | 0 | 0 | 26037 | 0 | 26033.62 | 3.38 | 0 | Project has been completed. PCR is being drafted to be submitted in 2006. | [8 empty] | 2004-12-01 |  | 1998
COM | Germany | Conversion from CFC-11 to water-based technology at Pramukh Poly-Products |  | ASP | IND | FOA | 36 | INV | 351 | A | O | I | CFC | 27 |  | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-05 |  | 224812 | 0 | 224812 | 224803 | 100% | 9 | 0 | 0 | 29226 | 0 | 29224.83 | 1.17 | 0 | Project has been completed. PCR is being drafted to be submitted in 2006 | [8 empty] | 2004-12-01 |  | 1998
ONG | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector (first tranche) | Multi-Year | ASP | IND | REF | 42 | INV | 369 | A | O | I |  | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 | 2006-04-01 |  |  | 414370 | 0 | 414370 | 391556 | 94.49% | 22814 | 0 | 22814 | 53868 | 0 | 50902.1855 | 2965.8145 | 0 | Overall, the project is well on track with minor delays with regard to ESS. Decisions taken in the last core group meeting will further improve the equipment distribution under the scheme. Customs&Policy training component activities of AWP 2004-05 have been implemented in AWP 2005-06 or will be implemented in AWP 2006-07.
ONG | Germany | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 375 | A | O | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 | 2006-04-01 |  |  | 700000 | 0 | 700000 | 273906 | 39.13% | 426094 | 0 | 426094 | 57500 | 0 | 22499.4214 | 35000.5786 | 0 | Overall, the project is well on track. Based on efforts in South India, alternatives have been identified and a training package for capacity building has been developed. Further mapping of clusters has been initiated in collaboration with Textiles Committee. Synergies with the metal cleaning activities (France) have been worked out.
ONG | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 3rd tranche | Multi-Year | ASP | IND | REF | 44 | INV | 380 | A | O | I |  | 0 |  | 0 |  | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 100000 | 13000 | 0 | 0 | 13000 | 0 | A total of 1715 technicians have been trained in 67 programs in the course of the operational year April 2005 to March 2006 against an assigned target of 1270 technicians as per planning. Procurement and contractual arrangements for Equipment Support Scheme are under process. Awareness activities as planned.
ONG | Germany | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 388 | A | O | I | CTC | 970 |  | 0 |  | 2005-04-01 |  | 2006-07-01 | 2007-12-01 |  |  | 700000 | 0 | 700000 | 0 | 0% | 700000 | 0 | 46079 | 57500 | 0 | 0 | 57500 | 0 | see remarks under MLF No. IND/PHA/42/INV/375
ONG | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 393 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 | 2007-12-01 |  |  | 105090 | 0 | 105090 | 0 | 0% | 105090 | 0 | 105090 | 13662 | 0 | 0 | 13662 | 0 | Project (3rd tranche) just approved in Dec. 2005 (Excom 47). For project progress see also UNEP/OzL.Pro/ExCom/47/29
COM | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Iranogharb |  | ASP | IRA | FOA | 34 | INV | 114 | A | O | I | CFC | 62 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-12-01 |  | 2004-12-01 |  | 386260 | 0 | 386260 | 386260 | 100% | 0 | 0 | 0 | 50214 | 0 | 50214 | 0 | 0 | Project completed. PCR has been submitted to the country | [10 empty] | 2002
COM | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Esfanj Jajerood foam company |  | ASP | IRA | FOA | 35 | INV | 116 | A | O | I | CFC | 89 |  | 0 |  | 2001-12-01 | 2001-01-01 | 2003-05-01 |  | 2004-12-01 |  | 499299 | 0 | 499299 | 499299 | 100% | 0 | 0 | 0 | 64909 | 0 | 64909 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector in 5 companies |  | ASP | IRA | FOA | 35 | PRP | 118 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2001-01-01 | 2003-01-01 |  | 2002-09-01 | 2002-12-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 |  | 3088 | 0 | 3088 | 0 | 0 | 5 projects submitted and approved in Jul-02.
COM | Germany | Conversion from CFC-11 to pentane technology in the manufacture of integral skin PU foam at Jahad Tahghihat Group |  | ASP | IRA | FOA | 37 | INV | 150 | A | O | I | CFC | 23 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2004-03-01 |  | 2004-09-01 |  | 335249 | 0 | 335249 | 335249 | 100% | 0 | 0 | 0 | 43582 | 0 | 43582 | 0 | 0 | Project completed. PCR has been submitted to the country
COM | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Abre Baspar foam company |  | ASP | IRA | FOA | 37 | INV | 151 | A | O | I | CFC | 77 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 |  | 387174 | 0 | 387174 | 387174 | 100% | 0 | 0 | 0 | 50333 | 0 | 50333 | 0 | 0 | Equipment has been delivered onsite and installation is under way.
ONG | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded PU foam at Sanayeh Dashboard Iran | Individual | ASP | IRA | FOA | 37 | INV | 152 | A | O | I | CFC | 22 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 | 2006-12-01 |  |  | 185632 | 0 | 185632 | 133889.88 | 72.13% | 51742.12 | 0 | 51742.12 | 24132 | 0 | 17405.569 | 6726.431 | 0 | Equipment was procured and installed in 2004.
COM | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Nikou Esfandj |  | ASP | IRA | FOA | 37 | INV | 153 | A | O | I | CFC | 18.6 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2004-09-01 |  | 228310 | 0 | 228310 | 228310 | 100% | 0 | 0 | 0 | 29680 | 0 | 29680 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Project preparation for the development of a foam sector strategy |  | ASP | IRA | FOA | 37 | PRP | 154 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  | 2002-12-01 | 2003-12-01 | 51850 | 0 | 51850 | 51850 | 100% | 0 | 0 |  | 6741 | 0 | 6741 | 0 | 0 | Project preparation lead to sector phase out strategy, included in NPOP approved at 41st ExCom.
COM | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Phira Khodro |  | ASP | IRA | FOA | 37 | INV | 156 | A | O | I | CFC | 20.2 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 |  | 158166 | 0 | 158166 | 124586.71 | 78.77% | 33579.29 | 0 | 33579.29 | 20562 | 0 | 16196.6031 | 4365.3969 | 0 | Project technically completed. Payment of incremental operational costs continues.
FIN | Germany | Preparation of a national CFC phase-out plan |  | ASP | IRA | PHA | 39 | PRP | 159 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-04-01 | 2004-04-01 |  | 2003-11-01 | 2003-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 | National Phase Out Plan has been submitted and appproved at the 41th meeting
ONG | Germany | National CFC phase-out plan: 1st and 2nd tranche | Multi-Year | ASP | IRA | PHA | 41 | INV | 160 | A | O | I | CFC | 0 |  | 0 |  | 2003-12-01 | 2004-03-01 | 2004-12-01 | 2006-12-01 |  |  | 694124 | 946405 | 1640529 | 1640529 | 100% | 0 | 0 | 0 | 76354 | 104105 | 180459 | 0 | 0 | Activity progressed according to plan. So far, a total of 1500 ODP tons have been replaced with CFC-free technology.
ONG | Germany | National CFC phase-out plan: 3rd tranche | Multi-Year | ASP | IRA | PHA | 45 | INV | 169 | A | O | I | CFC | 214 |  | 0 |  | 2005-04-01 | 2005-05-01 | 2007-12-01 | 2007-12-01 |  |  | 479044 | 0 | 479044 | 185782 | 38.78% | 293262 | 0 | 293262 | 52695 | 0 | 20436.0821 | 32258.9179 | 0 | Funds have been all obligated for the conversion of additional manufacturers in the foam sector.
FIN | Germany | Comprehensive approach to disseminate soil solarization technology for methyl bromide substitution |  | ASP | JOR | FUM | 26 | DEM | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-08-01 | 2002-01-01 | 232789 | 0 | 232789 | 232789 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completion report submitted | [10 empty] | 1998
ONG | Germany | Complete phase-out of the use of methyl bromide in Jordan | Individual | ASP | JOR | FUM | 29 | INV | 54 | A | O | I | MBR | 180 | 101.4 | 0 |  | 1999-11-01 | 2000-03-01 | 2008-12-01 | 2015-12-01 |  |  | 3063000 | 0 | 3063000 | 1603634 | 52.36% | 1459366 | 0 | 198168 | 398190 | 0 | 208472.42 | 189717.58 | 0 | Jordan imported 79.8 ODP tonnes MB in 2003, 78.6 ODP tonnes in 2004 and 60 ODP tonnes in 2005. The reduction did not progress as fast as anticipated because lower importation targets could not politically be enforced in view of the critical use exemptions granted to A2 parties. The planned date of completion should also be corrected from Dec-08 (as stated in the Inventory) to Dec-15 as stated in the agreement between the Government of Jordan and the MLF. Jordan is, however, still aiming at an earlier phase out. in 2005 importation of small cans was discontinued. This will discourage small farmers from using MB. It was noticed that expenditures reported in the progress reports for 2000 and 2001 included unrelated cost items. After corrections, the accumulated total for the end of 2005 will now be reported to be US$ 1'603'634. | [10 empty] | No bus plan
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | KEN | REF | 23 | PRP | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1998
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | KEN | REF | 26 | TAS | 19 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. TPMP approved in Dec 2004 | [10 empty] | 2000
FIN | Germany | Development of an investment project for the phase out of methyl bromide in vegetable production |  | AFR | KEN | FUM | 30 | PRP | 23 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-08-01 | 2000-12-01 |  | 2002-11-01 | 2003-09-01 | 13360 | 0 | 13360 | 13360 | 100% | 0 | 0 |  | 1737 | 0 | 1737 | 0 | 0 | Project initially blocked by 30th ExCom Decision on Kenya. Work completed November 2002. Investtment project approved at 39th ExCom. | [10 empty] | 1997
FIN | Germany | Recovery and recycling project |  | AFR | KEN | REF | 28 | TAS | 24 | A | O | I | CFC | 8.5 | 5 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2001-08-01 |  | 2004-05-01 | 2004-10-01 | 98725 | 0 | 98725 | 98725 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PCR submitted to the 44th Excom. | [10 empty] | 2001
FIN | Germany | Project preparation for the solvent sector |  | AFR | KEN | SOL | 35 | PRP | 26 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-05-02 | 2003-07-01 |  | 2002-11-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project completed , investment project being implemented | [10 empty] | 1998
FIN | Germany | Project preparation for the RMP update |  | AFR | KEN | REF | 36 | TAS | 27 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2003-06-01 | 2003-03-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | A TPMP developed through the preparation process was approved at the 44th ExCom | [10 empty] | 1998
ONG | Germany | Conversion of TCA based cleaning process to non-ODS alternatives at the Kenya Power and Lighting Company | Individual | AFR | KEN | SOL | 39 | INV | 32 | A | O | I | TCA | 1.9 | 1 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2004-10-01 | 2006-09-06 |  |  | 85800 | 0 | 85800 | 41200 | 48.02% | 44600 | 0 | 44600 | 11154 | 0 | 5356 | 5798 | 0 | KPLC has successfully converted to alternatives, however discussions are ongoing about need for supplementary equipment to ensure successful long term conversion | [10 empty] | 2002
COM | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (first tranche) |  | AFR | KEN | FUM | 39 | INV | 33 | A | O | I | MBR | 5 | 8 | 0 |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-04-01 |  | 287247 | 0 | 287247 | 287247 | 100% | 0 | 0 | 0 | 37342 | 0 | 37342 | 0 | 0 | During 2004 the project staff was completed, a demonstration facility was set up in cooperation with the University of Nairobi, a very successful demonstration of substrates as alternative to MB was held at this facility. In sectors and areas where viable alternatives have already been identified, the project is assisting MB using farms with equipment, materials, training and technical assistance in the installation and use of alternatives. In sectors where the suitable alternatives have not yet been identified, the project identifyed farms to carry out pilot technology transfers – relevant techniques are being transferred from other regions, piloted on Kenyan farms and adopted as necessary. Following this, a training programme is being carried out to disseminate the most appropriate techniques in the areas. During 2005 technology transfer activities continued through agreements with small and large scale farms on the use of various activities ranging from drip irrigation systems to soil less culture and the use of alternative chemicals like Basamid, Telone and Metham sodium. Demonstration and training activities were held at the Kabete campus in Nairobi for farmers and also for students. | [10 empty] | 1997
ONG | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (second tranche) | Multi-Year | AFR | KEN | FUM | 42 | INV | 35 | A | O | I | MBR | 12 |  | 0 |  | 2004-04-01 | 2005-05-01 | 2006-04-01 | 2006-04-01 |  |  | 172347 | 0 | 172347 | 50369 | 29.23% | 121978 | 0 | 121978 | 22405 | 0 | 6547.9379 | 15857.0621 | 0 | Second tranche approved at 42nd ExCom. Progress as described under KEN/FUM/41/TAS/21.
FIN | Germany | Training in improved operations, service and maintenance for refrigeration technicians in using hydrocarbons |  | ASP | LEB | REF | 26 | TRA | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-09-01 | 2002-01-01 | 49500 | -8197 | 41303 | 41303 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | [10 empty] | 1999
CLO | Germany | Project preparation and technical assistance at Arnatoury S.A.R.L., Sin-El-Fil | Individual | ASP | LEB | ARS | 26 | PRP | 26 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project will not be implemented | Funds to be offset against future german approvals | [9 empty] | 2000
FIN | Germany | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers |  | ASP | LEB | REF | 28 | TAS | 31 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2001-11-01 | 2003-10-01 | 37550 | -3 | 37547 | 37547 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | [10 empty] | 2001
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | LES | REF | 26 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-11-01 | 2004-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted TPMP submitted and approved at 41st Excom | [10 empty] | 1999
FIN | Germany | Project preparation for an RMP update |  | AFR | LES | REF | 37 | PRP | 07 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project completed, TPMP approved at 41st Excom | [10 empty] | 1998
COM | Germany | Terminal CFC phase-out management plan (first tranche) |  | AFR | LES | PHA | 41 | INV | 08 | A | O | I | CFC | 0.6 | 0.8 | 0 |  | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2005-03-05 |  | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Second tranche was requested for the TPMP. | [10 empty] | 2002
ONG | Germany | Terminal CFC phase-out management plan (2nd tranche) | Multi-Year | AFR | LES | PHA | 45 | INV | 09 | A | O | I | CFC | 0.6 |  | 0 |  | 2005-04-01 | 2005-04-01 | 2006-04-01 | 2006-12-06 |  |  | 35000 | 0 | 35000 | 5600 | 16% | 29400 | 0 | 29400 | 4550 | 0 | 728 | 3822 | 0 | There has been a delay in the implmentation of the 2nd tranche due to delay in enforcement of the permit system. Lesotho is presently trying to address the issue prior to moving ahead with the project
ONG | Germany | Implementation of the RMP: training of trainers in code of good refrigeration practices and establishment of national refrigeration demonstration centre | Individual | AFR | LIR | REF | 41 | TRA | 03 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-03-01 | 2006-12-01 | 2007-12-01 |  |  | 119460 | 0 | 119460 | 95500 | 79.94% | 23960 | 0 | 10000 | 15530 | 0 | 12415.1599 | 3114.8401 | 0 | Technician trainigns have been ongoing. 8 courses have been conducted in Monrovia and another 8 are planned for other towns. | [10 empty] | 2002
ONG | Germany | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector and recovery and recycling | Individual | AFR | LIR | REF | 41 | TAS | 04 | A | O | I | CFC | 21 |  | 0 |  | 2003-12-01 | 2005-06-01 | 2006-12-01 | 2007-12-01 |  |  | 92400 | 0 | 92400 | 36400 | 39.39% | 56000 | 0 | 20000 | 12012 | 0 | 4732 | 7280 | 0 | Approximately 150 technicians have so far benefitted from the best practices course held in the country | [10 empty] | 2002
ONG | Germany | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | Individual | AFR | LIR | REF | 41 | TAS | 05 | A | O | I | CFC | 2 |  | 0 |  | 2003-12-01 | 2005-04-01 | 2008-12-01 | 2007-12-01 |  |  | 107350 | 0 | 107350 | 25700 | 23.94% | 81650 | 0 | 40000 | 13996 | 0 | 3350.6959 | 10645.3041 | 0 | As part of the incentive scheme some funds have been used for purchasing basic tools fo r technicians. Given that the customs training has still not been conducted, the NOU feels that incentive scheme might not be useful yet. | [10 empty] | 2002
ONG | Germany | Implementation of the RMP: MAC recovery/recycling of CFC-12 | Individual | AFR | LIR | REF | 41 | TAS | 06 | A | O | I | CFC | 8.6 |  | 0 |  | 2003-12-01 | 2005-04-01 | 2006-12-01 | 2007-12-01 |  |  | 61858 | 0 | 61858 | 23000 | 37.18% | 38858 | 0 | 20000 | 8042 | 0 | 2990.171 | 5051.829 | 0 | Recovery and recycling were purchased on request from the NOU, to ensure that the technicians trained on how ot use the equipment also had access to the equipment. 10 recovery units were purchased and distributed through out the country.
ONG | Germany | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | LIR | REF | 41 | TAS | 08 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2003-12-01 | 2006-12-01 | 2007-12-01 |  |  | 15455 | 0 | 15455 | 7300 | 47.23% | 8155 | 0 | 3800 | 2009 | 0 | 948.9291 | 1060.0709 | 0 | NOU has requested a national consultant to be hired ot assist with the monitoring of the project activities. | [10 empty] | 2002
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MAR | REF | 23 | PRP | 08 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1998-03-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1998
FIN | Germany | Project preparation and technical assistance at Chem Tech | Individual | AFR | MAR | ARS | 26 | PRP | 09 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2001-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | MAR | REF | 26 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted TPMP approved at 41st Excom | [10 empty] | 1999
FIN | Germany | Investment project for phasing out CFCs at Chem Tech-Stella Industries, Port Louis |  | AFR | MAR | ARS | 27 | INV | 11 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1999-03-01 | 1999-03-01 | 1999-11-01 |  | 2001-06-01 | 2002-01-01 | 90400 | 0 | 90400 | 90400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | Funds to be offset against future german approvals |  |  |  | 2000-12-01 | [5 empty] | 2000
COM | Germany | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration |  | AFR | MAR | REF | 28 | TAS | 12 | A | O | I | CFC | 8 | 5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-06-01 |  | 2005-12-01 |  | 183377 | 0 | 183377 | 179730.3 | 98.01% | 3646.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Certification of R&R center. Follow-up evaluation of the performance of recycling center. Recommendation that the training institue should cooperate with the local gas dealer in utilizing the facility. PCR to be submitted in 2006.
FIN | Germany | Project preparation for the phase out of methyl bromide use |  | AFR | MAR | FUM | 37 | PRP | 13 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2002-10-01 | 2003-12-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 | 0 |  | 1430 | 0 | 1430 | 0 | 0 | A project proposal was prepared but not accepted by the beneficiary. Assistance of beneficiary will now be unter the TPMP approved at 41st ExCom. | [10 empty] | 1997
FIN | Germany | Project preparation for a CFC terminal phase out management plan |  | AFR | MAR | REF | 37 | PRP | 14 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project completed. TPMP approved at 41st Excom
COM | Germany | Implementation of an ODS terminal phase out management plan (first tranche) |  | AFR | MAR | PHA | 41 | INV | 15 | A | O | I | CFC | 2 | 2.6 | 0 |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-10-05 |  | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | 2 Hydrocarbon trainings have been conducted. NOU has finally started the process of converting the New Court House through a subsidy scheme provided under the project. The conversion is to be completed by end of 2006. | [10 empty] | 2002
ONG | Germany | Implementation of an ODS terminal phase out management plan (2nd tranche) | Multi-Year | AFR | MAR | PHA | 45 | INV | 16 | A | O | I | CFC | 2 |  | 0 |  | 2005-04-01 | 2005-11-01 | 2006-12-01 | 2006-12-06 |  |  | 62030 | 0 | 62030 | 25000 | 40.3% | 37030 | 0 | 37030 | 8064 | 0 | 3250.0403 | 4813.9597 | 0 | The MB conversion of the flour is still pending. The Flour mill has indicated and instrest to convert to SF however an official MOU is still to be signed between the flour mill and the NOU
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MLW | REF | 23 | PRP | 08 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1998
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | MLW | REF | 26 | TAS | 11 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted | [10 empty] | 2000
FIN | Germany | Project preparation for a refrigerant management update |  | AFR | MLW | REF | 37 | PRP | 17 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2004-05-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | RMP approved in June 04
ONG | Germany | Implementation of the RMP update: refrigeration and air-conditioning sector | Individual | AFR | MLW | REF | 43 | TAS | 20 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2007-07-01 | 2007-04-07 |  |  | 100000 | 0 | 100000 | 43433 | 43.43% | 56567 | 0 | 40000 | 13000 | 0 | 5646.29 | 7353.71 | 0 | 3 technician trainings have been conducted , 65 technicians participated.
FIN | Germany | Three alternatives to the use of methyl bromide: enemy plants, organic amendments and grafting on resistant rootstocks in combination with an integrated pest management system in tomatoes and curcubits |  | AFR | MOR | FUM | 26 | DEM | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 2001-10-10 | 2003-10-01 | 229523 | 0 | 229523 | 229523 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PCR submitted to 41st ExCom | [10 empty] | 1997
COM | Germany | Project preparation/technical assistance in the halon sector |  | AFR | MOR | HAL | 31 | PRP | 40 | A | O | I |  | 0 |  | 0 |  | 2000-07-01 | 2000-08-01 | 2001-01-01 |  | 2004-12-04 |  | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project proposal completed and with consent of NOU transferred to UNIDO for implementation. | [10 empty] | 1998
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | MOZ | REF | 26 | TAS | 07 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved. | [10 empty] | 2000
FIN | Germany | Project preparation for a refrigerant management plan update |  | AFR | MOZ | REF | 37 | PRP | 09 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | NAM | REF | 23 | PRP | 04 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1999
FIN | Germany | Recuperation and recycling of CFC-12 integrated with the introduction of hydrocarbon technology in the service sector | Individual | AFR | NAM | REF | 24 | TAS | 05 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-06-01 |  | 1998-06-01 | 2000-01-01 | 34400 | -244 | 34156 | 34156 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | [10 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | NAM | REF | 26 | TAS | 06 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. TPMP approved in Dec 2003 | [10 empty] | 2001
FIN | Germany | Project preparation for a terminal ODS phase-out management plan |  | AFR | NAM | PHA | 37 | PRP | 08 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-09-01 | 2004-08-01 | 50250 | 0 | 50250 | 50250 | 100% | 0 | 0 |  | 6533 | 0 | 6533 | 0 | 0 | Project completed and TPMP approved at 41st Excom | [10 empty] | 1998
ONG | Germany | Terminal phase-out management plan for CFCs | Multi-Year | AFR | NAM | PHA | 41 | INV | 10 | A | O | I | CFC | 10.5 |  | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 | 2006-12-06 |  |  | 160000 | 0 | 160000 | 65000 | 40.62% | 95000 | 0 | 95000 | 20800 | 0 | 8450 | 12350 | 0 | The incentive scheem for the conversion of commercial end users is slowly picking up. However the progress has been slow with limited requests being recceived by the NOU. | [10 empty] | 2002
FIN | Germany | Project preparation/technical assistance for the halon sector |  | AFR | NIR | HAL | 34 | PRP | 87 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 19420 | 0 | 19420 | 19420 | 100% | 0 | 0 |  | 2525 | 0 | 2525 | 0 | 0 | Project proposal submitted and approved by MF (37th ExCom). | [10 empty] | 1998
ONG | Germany | Sectoral phase-out program: establishing a halon bank | Individual | AFR | NIR | HAL | 37 | TAS | 103 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2005-08-01 | 2006-12-01 |  |  | 499000 | 0 | 499000 | 490000 | 98.2% | 9000 | 0 | 9000 | 64870 | 0 | 63700 | 1170 | 0 | Contracting legal expert; Contracting PA expert; Installation of equipment and training, OMOT will process halon in Nigeria and is offering its services for the region; Voluntary agreement on halon R&R between halon user and Omot; Preparation for cross border traffic of halon; Preparation for a regional conference in 2005 | [10 empty] | No bus plan
FIN | Germany | Project preparation/technical assistance for the halon sector |  | ASP | OMA | HAL | 34 | PRP | 03 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-09-01 | 2002-01-01 |  | 2003-07-03 | 2003-12-01 | 17000 | 0 | 17000 | 17000 | 100% | 0 | 0 |  | 2210 | 0 | 2210 | 0 | 0 | Int.consultant visited Oman, nat. consultants identified, Implemenation of the projects will be done by World Bank on request of Oman, results transferred to WB Jul-03. WB TAS-Project approved 41st ExCom. | [10 empty] | 1998
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Azkcon Refrigeration Industries, Inc. |  | ASP | PHI | REF | 23 | INV | 53 | A | O | I | CFC | 18.9 | 18.9 | 0 |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2005-04-01 | 370258 | -75353 | 294905 | 294905 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project is completed, PCR drafted by UNDP for completion and submission by GTZ. Remaining balance and interest (USD 75.353) has been returned in Dec-04 to GTZ to be reported and returned to MLF at the 45th ExCom. | [10 empty] | 1992
FIN | Germany | Project preparation for the development of an ODS phase out action plan |  | ASP | PNG | PHA | 36 | PRP | 04 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | TPMP for PNG has been approved at the 39th ExCom | [10 empty] | 1998
ONG | Germany | Terminal phase-out management plan for ODS (1st tranche) | Multi-Year | ASP | PNG | PHA | 39 | INV | 05 | A | O | I | CFC | 30.8 |  | 0 |  | 2003-04-01 | 2003-08-01 | 2005-12-01 | 2006-04-06 |  |  | 480000 | 0 | 480000 | 396415 | 82.59% | 83585 | 0 | 83585 | 59700 | 0 | 49304.1156 | 10395.8844 | 0 | PNG is successfully implementing its permit system and maintaining consumption within the target established by the TPMP. PNG is starting to implmnet its incentive scheme for end users, additional customs, technician, MAC and hydrocarbon trainings have been completed in 2005. Request for 2nd tranche submitted in 2006. | [10 empty] | 2002
ONG | Germany | Extension of institutional strengthening project |  | ASP | PNG | SEV | 41 | INS | 06 | N | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-06-01 | 2005-12-01 | 2006-03-06 |  |  | 39693 | 0 | 39693 | 30000 | 75.58% | 9693 | 0 | 9693 | 5160 | 0 | 3899.932 | 1260.068 | 0 | NOU conducted a very successful ozone day where Hydrocarbon refriergants were promoted and MACs were converted from CFC to HC. | [10 empty] | 2002
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SEY | REF | 23 | PRP | 04 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-03-01 | 2001-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | SEY | REF | 26 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. RMP Update ongoing | [10 empty] | 1999
FIN | Germany | Project preparation for a refrigerant management plan update |  | AFR | SEY | REF | 37 | PRP | 07 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-07-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | RMP update approved | [10 empty] | 2001
ONG | Germany | Phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | SEY | REF | 40 | TAS | 08 | A | O | I |  | 0 |  | 0 |  | 2003-07-01 | 2003-10-01 | 2006-12-01 | 2006-12-01 |  |  | 41607 | 0 | 41607 | 27329 | 65.68% | 14278 | 0 | 14278 | 5409 | 0 | 3552.8291 | 1856.1709 | 0 | 2 Hydrocarbon technician training was successfully completed. | [10 empty] | 2002
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SWA | REF | 23 | PRP | 04 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | SWA | REF | 26 | TAS | 05 | A | O | I | CFC | 4 | 1.5 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 90375 | 0 | 90375 | 90375 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted. RMP update ongoing | [10 empty] | 2001
FIN | Germany | Project preparation for a refrigerant management plan update |  | AFR | SWA | REF | 37 | PRP | 06 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2003-08-03 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project completed. RMP update approved at 41st Excom
ONG | Germany | Implementation of the RMP update | Individual | AFR | SWA | REF | 41 | TAS | 08 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 | 2006-12-01 |  |  | 74295 | 0 | 74295 | 36500 | 49.13% | 37795 | 0 | 37795 | 9658 | 0 | 4744.8281 | 4913.1719 | 0 | NOU was concentrating on ratification this year. Emphasis was also on establishing and enforcement of the permit system for imports of ODS. | [10 empty] | 2002
FIN | Germany | Development of halon banking management plan |  | ASP | SYR | HAL | 29 | TAS | 55 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2000-05-01 |  | 2000-05-01 | 2002-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 | 0 |  | 1396 | 0 | 1396 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 2001
ONG | Germany | Implementation of the RMP: national recovery and recycling network | Individual | ASP | SYR | REF | 30 | TAS | 59 | A | O | I | CFC | 120 |  | 0 |  | 2000-03-01 | 2000-11-01 | 2002-04-01 | 2006-05-01 |  |  | 742146 | 0 | 742146 | 742146 | 100% | 0 | 0 | 0 | 96479 | 0 | 96479 | 0 | 0 | R&R center and network revived. Contract to draft legislation for mandatory R&R and adoption of European technical norms. 24 more trainings for 683 technicians in R&R of refrigerants conducted.
FIN | Germany | Project preparation/technical assistance in soil fumigants (methyl bromide) |  | ASP | SYR | FUM | 32 | PRP | 70 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2001-09-01 | 2002-03-01 | 37200 | 0 | 37200 | 37200 | 100% | 0 | 0 |  | 4836 | 0 | 4836 | 0 | 0 | Project preparation led to project proposal for implementation, which was not accepted because of quantities of illegal MB. Syria is currently complying with its obligations. Only 8 ODP tons will still be eligeable in the future. | [10 empty] | 1997
ONG | Germany | Establishing a halon bank and umbrella project for 63 manufacturers | Individual | ASP | SYR | HAL | 34 | TAS | 77 | A | O | I | HAL | 205 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 | 2006-08-01 |  |  | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 | 0 | 20930 | 0 | 20930 | 0 | 0 | Training for trainers in fire protection, implementation of a country wide training program for companies with a total of about 200 fire protection experts, an intermediary vessel was installed at the reclamation center, the halon center continues to operate and recylce halon. | [10 empty] | 1998
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | UGA | REF | 23 | PRP | 06 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | UGA | REF | 26 | TAS | 07 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved in Dec 2004
FIN | Germany | Project preparation for a refrigerant management plan update |  | AFR | UGA | REF | 37 | PRP | 09 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Project completetd. RMP update approved at 44th ExCom | [10 empty] | 2002
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | URT | REF | 26 | TAS | 12 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
ONG | Germany | Recovery and recycling of CFCs | Individual | AFR | URT | REF | 36 | TAS | 14 | A | O | I | CFC | 11.7 |  | 0 |  | 2002-03-01 | 2002-12-01 | 2004-04-01 | 2006-05-01 |  |  | 164223 | 0 | 164223 | 156862 | 95.52% | 7361 | 0 | 7361 | 21349 | 0 | 20392.0696 | 956.9304 | 0 | One training conducted for MAC as well as commercial refridgeration with 24 participants; one recovery and recycling center installed in Dar-es-Salam and training conducted for 9 participants.
COM | Germany | Project preparation for a refrigerant management update |  | AFR | URT | REF | 37 | PRP | 15 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-06-05 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A RMP update was submitted by Tanzania in 2005
FIN | Germany | Preparation for phase-out investment project for methyl bromide sector |  | ASP | YEM | FUM | 34 | PRP | 09 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-05-01 | 2002-01-01 |  | 2003-12-01 | 2004-04-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0 | Project to reduce MB consumtion by 9.1 ODP tonnes approved at 41st ExCom.
ONG | Germany | Technical assistance programme for the phase-out of methyl bromide in agriculture | Individual | ASP | YEM | FUM | 41 | TAS | 21 | A | O | I | MBR | 9.1 |  | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 | 2006-12-01 |  |  | 250000 | 0 | 250000 | 84490 | 33.8% | 165510 | 0 | 165510 | 32500 | 0 | 10983.7 | 21516.3 | 0 | A MOU and workplan have been agreed between the Government of Yemen and GTZ. Information visits were conducted to the main MB consuming areas. Working relations between the various stakeholders (Ministry of Environment and farmers, pesticide traders, Ministry of Agriculture, General Department of Plant Protection, Customs, etc.) have been established. First extension activities were conducted to create awareness on the phase out of MB in the medium term. Appropriate regulations to limit import of MB is under preparation. The MB traders agreed to cooperate with the Government even in the absence of approved legislation. During 2005 2 expert workshops and 3 on-site training courses were held to transfer technology on soil solarization and bio-fumigation technology. Legislation to control MB was passed and executive measures to enforce the legislation are under way. Initial data show that a further 4 ODP tons of MB were reduced ensuring Yemen's over-compliance with the ExCom agreement. | [10 empty] | 1997
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZAM | REF | 23 | PRP | 07 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-05-02 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | ZAM | REF | 26 | TAS | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-05-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | RMP completed, RMP update approved in 42nd Excom | [10 empty] | 2000
FIN | Germany | Project preparation for a refrigerant management plan update |  | AFR | ZAM | REF | 37 | PRP | 12 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-01-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | RMP update approved at the 42nd meeting | [10 empty] | 2002
ONG | Germany | Refrigerant management plan update: refrigeration and air conditioning sector | Individual | AFR | ZAM | REF | 42 | TAS | 13 | A | O | I |  | 0 |  | 0 |  | 2004-04-01 | 2004-07-01 | 2007-04-01 | 2007-12-06 |  |  | 136000 | 0 | 136000 | 66319 | 48.76% | 69681 | 0 | 50000 | 17680 | 0 | 8621.47 | 9058.53 | 0 | 3 technician trainings with 60 participants mainly involving informal sector was conducted. Also workshops were conducted on data management where the improters and users were brought together to find ways of controlling illegal trade.
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZIM | REF | 23 | PRP | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [10 empty] | 1998
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations |  | AFR | ZIM | REF | 26 | TAS | 15 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-03 | 2004-07-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
CLO | Germany | Project preparation for phasing out of ODS at the domestic refrigeration factory Fridgemaster | Individual | AFR | ZIM | REF | 26 | PRP | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project will not be implemented. | Funds to be offset against future german approvals
FIN | Germany | Project preparation for a terminal ODS phase-out management plan |  | AFR | ZIM | PHA | 37 | PRP | 25 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-09-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 62760 | 0 | 62760 | 62760 | 100% | 0 | 0 |  | 8159 | 0 | 8159 | 0 | 0 | TPMP first tranche approved at 44th ExCom
ONG | Germany | Terminal phase-out management plan for CFCs (first tranche) | Individual | AFR | ZIM | PHA | 44 | INV | 29 | A | O | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-03-01 | 2006-12-01 | 2007-04-07 |  |  | 280000 | 0 | 280000 | 180000 | 64.29% | 100000 | 0 | 80000 | 36400 | 0 | 23400 | 13000 | 0 | Ongoing technician and customs training. Also the R&R project has been restarted.
FIN | Hungary | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 02 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 41145 | 0 | 41145 | 41145 | 100% | 0 |  |  | 5349 | 0 | 5349 | 0
FIN | IBRD | Preparation of investment projects |  | AFR | ALG | SEV | 12 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -93039 | 6961 | 6961 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a national CFC phase-out plan |  | LAC | ANT | PHA | 39 | PRP | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-09-01 | 2004-09-01 |  | 2004-09-01 | 2004-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | Project prepared, submitted and then approved at the 44th ExCom. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | CFC phase-out management plan | Multiyear | LAC | ANT | PHA | 44 | INV | 10 | N | O | I | CFC | 2 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 69400 | 0 | 69400 | 0 | 0% | 69400 | 69400 | 40000 | 6246 | 0 | 0 | 6246 | 6246 | Preparation of grant agreement is in the final stage. Pending final clearance, GA package will be submitted to Antigua and Barbuda for its consideration. To allow implementation of the Terminal Phase-out Plan and move forward without delays, consideration has been made to include provisions for retroactive reimbursement in the GA. | [10 empty] | 2004 | INV | 1.8 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 06 | CPG | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 149337 | -59619 | 89718 | 89718 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ARG | SEV | 09 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 63000 | -29084 | 33916 | 33916 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector project identification and preparation (1993) |  | LAC | ARG | SEV | 10 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 100000 | 65560 | 165560 | 165560 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and foam sectors (1994) |  | LAC | ARG | SEV | 12 | PRP | 06 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 192929 | 4741 | 197670 | 197670 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
TRF | IBRD | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | O | D |  | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1997-07-01 |  |  | 1994-07-01 | 359500 | -359500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transfered to UNDP | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of heat exchangers for mobile air conditioning at Interclima, S.A. | Individual | LAC | ARG | REF | 15 | INV | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-07-01 | 1995-12-01 |  | 1999-06-01 | 1999-11-01 | 1983430 | -314039 | 1669391 | 1669391 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. PCR was sent to ExCom. |  |  | 1997-07-01 | 1999-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of condensers for mobile air conditioning at Simon Cachan, S.A. | Individual | LAC | ARG | REF | 15 | INV | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-12-01 |  | 2001-01-01 | 2002-03-01 | 2738217 | -459396 | 2278821 | 2278821 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  | 1997-07-01 | 1999-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of complete mobile air conditioning systems at Mirgor, S.A. | Individual | LAC | ARG | REF | 15 | INV | 17 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-06-01 | 1995-12-01 |  | 1999-06-01 | 1999-06-01 | 35632 | -4082 | 31550 | 31550 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-07-01 | 1999-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of ODP in the production of household refrigerators at the Fribe La Rioja Plant | Individual | LAC | ARG | REF | 15 | INV | 18 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1488127 | -1444783 | 43344 | 43344 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned at 27th meeting. |  |  | 1999-03-01 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in two manufacturing plants of domestic refrigerators at Helametal S.A., and Helametal Catamarca S.A. | Individual | LAC | ARG | REF | 15 | INV | 19 | N | O | I | CFC | 62 | 62 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1996-12-01 |  | 2003-10-01 | 2004-07-01 | 2959085 | -59591.29 | 2899493.71 | 2899493.71 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-03-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of ODS in the production of domestic refrigerators in the Fribe, S.A. plant | Individual | LAC | ARG | REF | 15 | INV | 20 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1822750 | -1769660 | 53090 | 53090 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned to 27th meeting. |  |  | 1999-03-01 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in the domestic refrigerator manufacturing plant of McLean | Individual | LAC | ARG | REF | 15 | INV | 21 | N | O | I | CFC | 74 | 74 | 0 | 0 | 1994-12-01 | 1998-02-01 | 1996-12-01 |  | 2001-01-01 | 2001-05-01 | 2440570 | -1567990 | 872580 | 872580 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | All pending payments were effected by May 2001. The project is complete and the PCR has been submitted to EXCOM. |  |  | 1999-03-01 | 2000-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ARG | SEV | 16 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 185000 | -4503 | 180497 | 180497 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in domestic refrigerator production plants in Aurora S.A. | Individual | LAC | ARG | REF | 18 | INV | 35 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 567590 | -567590 | 0 | 0 |  | 0 | 0 |  | 73786.7 | -73786.7 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in 2 domestic refrigerator manufacturing plants at Piragua S.A., and Piragua San Luis | Individual | LAC | ARG | REF | 18 | INV | 36 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 1040264 | -1040264 | 0 | 0 |  | 0 | 0 |  | 135234.32 | -135234.32 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in domestic refrigerator production plant in Autosal, S.A. | Individual | LAC | ARG | REF | 18 | INV | 37 | N | O | I | CFC | 22 | 22 | 0 | 0 | 1995-11-01 | 1998-11-01 | 1997-11-01 |  | 2003-06-01 | 2004-03-01 | 797390 | 0 | 797390 | 797390 | 100% | 0 | 0 |  | 103660.7 | 0 | 103660.7 | 0 | 0 | Project completed. |  |  | 1998-05-01 | 1999-11-01 |  | 2001-09-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Briket, S.A. | Individual | LAC | ARG | REF | 18 | INV | 38 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1998-02-01 | 1997-11-01 |  | 2001-10-01 | 2001-11-08 | 726400 | 0 | 726400 | 726400 | 100% | 0 | 0 |  | 94432 | 0 | 94432 | 0 | 0 | The company has been producing without CFCs since Aug. 2001. Destruction of old equipment was completed Oct. 2001. |  |  | 1998-05-01 | 1999-10-01 | [7 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba, S.A. | Individual | LAC | ARG | REF | 18 | INV | 39 | N | O | I | CFC | 29 | 0 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1997-11-01 | 2007-12-01 |  |  | 686370 | 0 | 686370 | 398318.4 | 58.03% | 288051.6 | 288051.6 |  | 89228.1 | 0 | 51781.39 | 37446.71 | 37446.71 | New ownership was found for NEBA S.A. IKALA S.A. in Nov. 05: an important producer of kitchens in Argentina acquired the company. Production is expected to restart in Feb. 06. Representatives of IKALA S.A. are interested in carrying out the project and have started meetings with the Project Implementation Unit to define a work plan and finalize the acquisition of new equipment from IMPIANTI S.A. |  |  | 1998-05-01 | 1999-10-01 |  | 2001-09-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of mobile air conditioning systems at Sistemaire, S.A. | Individual | LAC | ARG | REF | 18 | INV | 40 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-11-01 |  | 2000-09-01 | 2000-12-01 | 2370550 | -1400728 | 969822 | 969822 | 100% | 0 | 0 |  | 308171.5 | -182094.64 | 126076.5 | 0.36 | 0.36 | Completed. PCR submitted to ExCom. Savings returned to 34th ExCom. |  |  | 1998-05-01 | 1999-08-01 | 2000-11-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 18 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators at Adzen S.A. C.I.F. | Individual | LAC | ARG | REF | 19 | INV | 43 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 2003-12-01 | 356970 | -356970 | 0 | 0 |  | 0 | 0 |  | 46406 | -41051.45 | 5354.55 | 0 | 0 | Project cancelled at the 40th ExCom. |  |  | 1997-11-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators of Frimetal, Rosario | Individual | LAC | ARG | REF | 19 | INV | 44 | N | O | I | CFC | 89.7 | 89.7 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1998-05-01 |  | 2004-09-01 | 2004-10-01 | 1855000 | 0 | 1855000 | 1855000 | 100% | 0 | 0 |  | 241150 | 0 | 241150 | 0 | 0 | Project financially and physically completed. |  |  | 1998-11-01 | 2000-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 21 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 12 | CPG | 59 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program was completed and presented at the 13th E.C. meeting. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in 1 manufacturing plant of domestic refrigerators of enterprise Whirlpool Argentina S.A. | Individual | LAC | ARG | REF | 23 | INV | 68 | N | O | I | CFC | 90.55 | 90.55 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-04-26 | 863879 | -99292 | 764587 | 764587 | 100% | 0 | 0 |  | 112304 | -12907.69 | 99396.31 | 0 | 0 | Project completed and funding disbursed. PCR submitted Dec. 01. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators at Lobato San Luis S.A. | Individual | LAC | ARG | REF | 23 | INV | 69 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 2002-11-01 | 410683 | -410683 | 0 | 0 |  | 0 | 0 |  | 53389 | -47229 | 6160 | 0 | 0 | Cancelled - 37th ExCom | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators at Gepasa S.A. and Gesal S.R.L. | Individual | LAC | ARG | REF | 23 | INV | 70 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2000-12-01 | 550400 | -550400 | 0 | 0 |  | 0 | 0 |  | 71552 | -71552 | 0 | 0 | 0 | Project cancelled at 31st ExCom. Funds returnd at 32nd ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration, halon and MAC sectors |  | LAC | ARG | SEV | 24 | PRP | 72 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for methyl bromide (citrus and cotton) demonstration project |  | LAC | ARG | FUM | 25 | PRP | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-30 | 1999-08-01 |  | 1999-06-30 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Substituting CFCs by HCFC-141b and HFC-134a in manufacturing of domestic and commercial refrigerators at El Dorado, S.A. | Individual | LAC | ARG | REF | 25 | INV | 77 | N | O | I | CFC | 12.8 | 12.8 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-09-01 | 2000-06-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 22880 | 0 | 22880 | 0 | 0 | Completed. PCR has been sent | [11 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Individual | LAC | ARG | HAL | 26 | TAS | 80 | N | O | I | HAL | 200 | 0 | 0 | 0 | 1998-11-01 | 2002-02-01 | 2000-12-01 | 2006-12-01 |  |  | 290620 | 0 | 290620 | 136899.54 | 47.11% | 153720.46 | 153720.46 | 153720 | 37780.6 | 0 | 17796.94 | 19983.66 | 19983.66 | All scheduled courses completed. Halon bank not yet fully operational as R&R equipment not yet delivered. Order for equipment has been placed but changes in government have prevented disbursement of funds to acquire equipment. Only other activity remaining is construction of storage facility but it is also delayed due to Government changes. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam in panels for thermal insulation at Arneg Raffo | Individual | LAC | ARG | FOA | 27 | INV | 81 | N | O | I | CFC | 67 | 67 | 0 | 0 | 1999-03-01 | 2001-02-20 | 2001-04-01 |  | 2002-07-01 | 2004-03-01 | 177960 | 0 | 177960 | 177960 | 100% | 0 | 0 |  | 23134.8 | 0 | 23134.8 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in sterilization via ETO at Asisthos SRL | Individual | LAC | ARG | STE | 27 | INV | 82 | N | O | I | CFC | 20.69 | 20.69 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2001-04-01 |  | 2000-09-01 | 2001-03-01 | 395095 | 0 | 395095 | 395095 | 100% | 0 | 0 |  | 51362.35 | 0 | 51362.35 | 0 | 0 | Completed. PCR submitted Feb. 01. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and solvent cleaning sectors |  | LAC | ARG | SEV | 27 | PRP | 86 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-30 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of 1,1,1-trichloethane sheet steel cleaning system on the steel sheet-cutting table with an aqueous-mechanical system in the steel enterprise Siderar, SAIC | Individual | LAC | ARG | SOL | 28 | INV | 90 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2001-08-01 |  |  | 2003-04-01 | 105147 | -105147 | 0 | 0 |  | 0 | 0 |  | 13669.11 | -11566 | 2103 | 0.11 | 0.11 | Cancelled - 38th ExCom | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. | Individual | LAC | ARG | SOL | 28 | INV | 91 | N | O | I | TCA | 7.1 | 2.3 | 0 | 0 | 1999-07-01 | 2001-02-20 | 2000-08-01 |  | 2004-03-01 | 2004-03-01 | 272157 | -183607 | 88550 | 88550 | 100% | 0 | 0 |  | 35380.41 | -23868.91 | 11511.5 | 0 | 0 | Orbis and Buffalo have completed conversion. Argelite, Unisol and Cincam cancelled at the 39th ExCom. Grimoldi, Integral Metalurgica, Heliodino and Trosh were cancelled at the 44th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Individual | LAC | ARG | FUM | 29 | DEM | 93 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-08-01 | 2001-12-01 | 2006-07-01 |  |  | 375000 | 0 | 375000 | 110509 | 29.47% | 264491 | 264491 | 264491 | 48750 | 0 | 14366.17 | 34383.83 | 34383.83 | All necessary equipment purchased. First draft results received in 2005. Experiments will re-start Mar 06 once cotton and citrus seasons begin. No disb. in '05 because of changes in the Gov. Project expected to be finished Jul 06. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of an investment project in methyl bromide sector |  | LAC | ARG | FUM | 30 | PRP | 100 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | ARG | REF | 30 | PRP | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | LAC | ARG | FOA | 30 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2000-12-01 | 2000-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the solvent (TCA) sub-sector |  | LAC | ARG | SOL | 30 | PRP | 109 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-03-01 |  | 2001-12-01 | 2001-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the CFC production sector |  | LAC | ARG | PRO | 31 | PRP | 112 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 by HCFC-141b in the manufacture of rigid polyurethane foam for domestic refrigerators and sandwich panels at MTH S.R.L. | Individual | LAC | ARG | REF | 32 | INV | 116 | N | O | I | CFC | 8 | 8 | 0 | 0 | 2000-12-01 | 2001-05-30 | 2002-12-01 |  | 2002-10-01 | 2004-03-01 | 82695 | 0 | 82695 | 82695 | 100% | 0 | 0 |  | 10750.35 | 0 | 10750.35 | 0 | 0 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Electroquimica Delta | Individual | LAC | ARG | ARS | 36 | INV | 128 | N | O | I | CFC | 60 | 60 | 0 | 0 | 2002-03-01 | 2004-08-01 | 2005-04-01 |  | 2004-12-01 |  | 264000 | 0 | 264000 | 190080 | 72% | 73920 | 73920 | 73920 | 34320 | 0 | 24710.4 | 9609.6 | 9609.6 | Project physically completed. Financial completion expected Jun. 06. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | Individual | LAC | ARG | ARS | 38 | INV | 131 | N | O | I | CFC | 36.4 | 36.4 | 0 | 0 | 2002-11-01 | 2004-08-01 | 2005-11-01 |  | 2005-02-01 |  | 160160 | 0 | 160160 | 143240 | 89.44% | 16920 | 16920 | 16920 | 20820.8 | 0 | 18621.2 | 2199.6 | 2199.6 | Project physically completed. Financial completion expected Jun. 06. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production closure plan (first tranche) | Multiyear | LAC | ARG | PRO | 38 | INV | 133 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-12-01 | 2003-12-01 |  | 2003-12-01 |  | 500000 | 0 | 500000 | 53548 | 10.71% | 446452 | 446452 | 218000 | 20000 | 0 | 2141.92 | 17858.08 | 17858.08 | Activities for current year include TA for alternatives to CFC, audit of the plant, development of environmental guidelines for equipment dismantling, development of a framework to address work compensation schedules and monitoring of the closure of FIASA. | [10 empty] | 2002 | INV | 0 | 0 | 3020 | 3018 | Yes | Yes | Yes
CLO | IBRD | Preparation of one investment project in the aerosol filling industry |  | LAC | ARG | ARS | 39 | PRP | 135 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2003-12-01 |  |  | 2005-11-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 750 | -750 | 0 | 0 | 0 | Funds returned to the 47th ExCom. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2004 annual programme | Multiyear | LAC | ARG | PRO | 44 | INV | 141 | N | O | I | CFC | 0 | 0 | 1373 | 1373 | 2004-12-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 |  | 3500000 | 0 | 3500000 | 1012000 | 28.91% | 2488000 | 2488000 | 2488000 | 200000 | 0 | 57828.57 | 142171.43 | 142171.43 | New disbursement schedule agreed between FIASA and Gov. of Argentina in which all funds approved to FIASA to date ($3.8 million) will be disbursed by end 2006/early 2007. (Delay in disb. due to Gov. changes.) | [10 empty] | 2003 | INV | 0 | 0 | 3020 | 3016 | Yes | Yes | Yes
ONG | IBRD | Preparation of MDI phase-out plan |  | LAC | ARG | ARS | 45 | PRP | 142 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-12-01 | 2006-11-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 50000 | 50000 | 3750 | 0 | 0 | 3750 | 3750 | Project prep. has suffered delays due to recent changes in the Government (Secretary of Industry). Plan of action will be discussed during WB's next mission in Apr. 06. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2005 annual programme | Multiyear | LAC | ARG | PRO | 45 | INV | 143 | N | O | I | CFC | 0 | 0 | 1373 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 300000 | 0 | 300000 | 0 | 0% | 300000 | 300000 | 300000 | 120000 | 0 | 0 | 120000 | 120000 | New schedule of disbursements agreed between GoA and FIASA in which all funds for FIASA approved to date will be disbursed by the end of 2006/early 2007. | [10 empty] | 2005 | INV | 0 | 0 | 1647 | 1645 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2006 work programme | Multiyear | LAC | ARG | PHA | 47 | INV | 148 | N | O | I | CFC | 1.5 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 | 500000 | 500000 | 37500 | 0 | 0 | 37500 | 37500 | Study of chiller sector completed in mid-2005. Argentina & WB have identified a list of potential chillers to replace. | [10 empty] | 2005 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation |  | ASP | BGD | SEV | 04 | PRP | 07 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 25564 | -25564 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Terminal phaseout management plan | Multiyear | LAC | BHA | PHA | 35 | INV | 08 | N | O | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2004-11-01 | 2003-12-01 |  | 2003-12-01 |  | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 |  | 31200 | 0 | 31200 | 0 | 0 | Grant Agreement between the Bank and the Bahamas became effective Jun. 04. WB mission conducted to confirm progress of TPMP implementation. Disbursement of funds from first tranche made, on a retroactive basis, upon approval of Progress Report and CFC consumption verification report. Audited account of expenditures and verification report confirmed that the Bahamas met all commitments, as per Excom agreement. | [10 empty] | 2001 | INV | 48 | 48 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Terminal phase-out management plan: 2004-2005 biennial programme | Multiyear | LAC | BHA | PHA | 44 | INV | 12 | N | O | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 200000 | 200000 | 26000 | 0 | 0 | 26000 | 26000 | CFC demand declined faster than anticipated and a number of activities proposed in the 2004-2005 Biennial Action Plan became unnecessary. The Plan therefore emphasized more public awareness and training of customs and other relevant stakeholders to ensure that ODS consumption reduction achievement thus far would be sustainable. The Bahamas is preparing the next Biennial Action Plan along with the 2005 Verfication and financial audit for 2004-2005. | [10 empty] | 2003 | INV | 25 | 23 | 0 | 0 | Yes | No | No
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | BRA | SEV | 04 | PRP | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 114583 | -73761 | 40822 | 40822 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 06 | CPG | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 123788 | -122316 | 1472 | 1472 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | BRA | SEV | 06 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -89419 | 102459 | 102459 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation on converting CFC-11 central air conditioning units with HCFC-123 or HFC-134a |  | LAC | BRA | REF | 07 | PRP | 05 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-12-01 | 1993-06-01 |  | 1995-12-01 | 1995-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Assembly line refitting for HFC-134a refrigerator compressor, commercial production | Individual | LAC | BRA | REF | 07 | INV | 06 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 530000 | -530000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1995-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC-12 collection, recycling and conservation programme for household refrigerator maintenance and repair shops | Individual | LAC | BRA | REF | 07 | TAS | 07 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1999-06-01 | 1995-06-01 |  |  | 2001-07-01 | 2000000 | -1980000 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1995-06-01 | 1999-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | BRA | SEV | 09 | PRP | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112000 | -20388 | 91612 | 91612 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the refrigeration sector (1994) |  | LAC | BRA | REF | 12 | PRP | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 164380 | -53297 | 111083 | 111083 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | System for storage and charging of ester oils used in the manufacture of HFC-134a compressors at Embraco | Individual | LAC | BRA | REF | 13 | INV | 15 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1994-09-01 |  | 1994-07-01 | 1995-07-01 | 221200 | 0 | 221200 | 221200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully implemented resulting in savings of 270 tons per year ODP. Project completed. |  |  | 1994-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to reduced CFC technology in the manufacture of Refrigerators at Refrigeracao Parana S.A., Unidade Sao Carlos | Individual | LAC | BRA | FOA | 15 | INV | 16 | N | O | I | CFC | 96 | 96 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-12-01 |  | 1999-06-01 | 1999-05-01 | 162603 | -12710 | 149893 | 149893 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11/12 to cyclopentane/HFC-134a foaming agent/refrigerant factory conversion at Metalfrio S.A. | Individual | LAC | BRA | REF | 15 | INV | 18 | N | O | I |  | 205.5 | 205.5 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1998-07-01 | 1999-05-01 | 2360360 | -776471 | 1583889 | 1583889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Foaming process began operation in July 98 and refrigeration process in June 98. Final disbursement to Metalfrio was made on May 99. |  |  | 1997-12-01 | 1999-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | BRA | SEV | 16 | PRP | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 235906 | 0 | 235906 | 235906 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Sao Rafael Ind. Com. | Individual | LAC | BRA | FOA | 18 | INV | 30 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-10-01 |  | 1999-09-01 | 1998-02-01 | 82676 | -2016 | 80660 | 80660 | 100% | 0 | 0 |  | 10748 | -262.08 | 10485.8 | 0.12 | 0.12 | Complete. |  |  | 1998-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Randon Implementos S.A. | Individual | LAC | BRA | FOA | 18 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-09-01 |  |  | 1999-07-01 | 92180 | -92180 | 0 | 0 |  | 0 | 0 |  | 11983 | -11983 | 0 | 0 | 0 | Cancelled. |  |  | 1998-06-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Recrusul SEA | Individual | LAC | BRA | FOA | 18 | INV | 32 | N | O | I | CFC | 201 | 201 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1999-06-01 | 1999-08-01 | 1075650 | -121339 | 954311 | 954311 | 100% | 0 | 0 |  | 139835 | -15774.5 | 124060.5 | 0 | 0 | Complete. |  |  | 1997-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at M. Agostini, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 33 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1996-08-01 |  | 1999-09-01 | 1999-02-01 | 85217 | -2078 | 83139 | 83139 | 100% | 0 | 0 |  | 11078 | -269.93 | 10808.07 | 0 | 0 | All three foaming machines now installed and in routine operation. |  |  | 1998-06-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Termolar, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 34 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-08-01 |  |  | 1996-09-01 | 61716 | -61716 | 0 | 0 |  | 0 | 0 |  | 8023 | -8023 | 0 | 0 | 0 | Cancelled. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the manufacture of commercial chest freezers at Refrigeracao Parana S.A. Curitiba | Individual | LAC | BRA | REF | 18 | INV | 35 | N | O | I | CFC | 363 | 363 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1998-11-01 | 1999-08-01 | 1557613 | -210305.8 | 1347307.2 | 1347307 | 100% | 0.2 | 0.2 |  | 202490 | -27340.31 | 175149.69 | 0 | 0 | The firm went ahead with its own funds and completed one line (vertical freezers) in July 97; and the other line (horizontal freezers) in Nov. 98. FINEP reimbursed the firm retroactively for capital and operating costs. Final reimbursement made on August 2, 1999. |  |  | 1997-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC-113 and of MCF used in vapor degreasers to clean aircraft parts at Embraer | Individual | LAC | BRA | SOL | 18 | INV | 38 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1998-07-01 | 308215 | -308215 | 0 | 0 |  | 0 | 0 |  | 40068 | -40068 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1998-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | BRA | SEV | 18 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Reubli, S.A. | Individual | LAC | BRA | REF | 19 | INV | 48 | N | O | I | CFC | 89.9 | 89.9 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 1999-06-01 | 901270 | -200188 | 701082 | 701082 | 100% | 0 | 0 |  | 117165 | -26024.34 | 91140.66 | 0 | 0 | Complete. |  |  | 1997-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Geltec Comercio e Industria S.A. | Individual | LAC | BRA | REF | 19 | INV | 49 | N | O | I | CFC | 18.3 | 18.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-02-01 | 1998-02-01 | 228250 | -93750 | 134500 | 134500 | 100% | 0 | 0 |  | 29673 | -12188 | 17485 | 0 | 0 | Refrigeration equipment installed and operating. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-11 to cyclopentane foam blowing agent and CFC-12 to HFC-134a refrigerant at Tecnomecanica Esmaltec Ltda. | Individual | LAC | BRA | REF | 19 | INV | 50 | N | O | I | CFC | 68.7 | 68.7 | 0 | 0 | 1996-05-01 | 1998-08-01 | 1997-11-01 |  | 2000-03-01 | 1999-06-01 | 924040 | 0 | 924040 | 924040 | 100% | 0 | 0 |  | 120125 | 0 | 120125 | 0 | 0 |  |  |  | 1998-06-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Everest Refrigeracao Ind. e Comercio Ltda. | Individual | LAC | BRA | REF | 19 | INV | 51 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 149050 | -149050 | 0 | 0 |  | 0 | 0 |  | 19377 | -19377 | 0 | 0 | 0 | Cancelled. |  |  | 1998-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-113 in medical parts cleaning and silicone deposition, and CFC-12 used in sterilization at Tecnobio | Individual | LAC | BRA | SOL | 19 | INV | 52 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 1997-11-01 | 317492 | -317492 | 0 | 0 |  | 0 | 0 |  | 41274 | -41274 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Gelopar | Individual | LAC | BRA | REF | 20 | INV | 55 | N | O | I | CFC | 13.14 | 13.14 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-05-01 | 1998-05-01 | 200200 | -145442 | 54758 | 54758 | 100% | 0 | 0 |  | 26026 | -18907.46 | 7118.54 | 0 | 0 | Refrigeration equipment acquired and installed. 134a production began May 98. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the production of refrigeration equipment (drinking water fountains and coolers) at Industria Brasileira de Bebedouros Ltda. (IBBL) | Individual | LAC | BRA | REF | 20 | INV | 56 | N | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-07-01 | 1998-05-01 | 82500 | -23113 | 59387 | 59387 | 100% | 0 | 0 |  | 10725 | -3004.69 | 7720.31 | 0 | 0 |  |  |  |  | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam sector |  | LAC | BRA | FOA | 22 | PRP | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1999-03-31 | 1997-12-01 |  | 1999-12-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 |  |  |  |  | 1999-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 12 | CPG | 76 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 49000 | -45000 | 4000 | 4000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brazil Country Program was completed, presented and approved at the 13th Meeting of the Executive Committee. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the process agent sub-sector |  | LAC | BRA | PAG | 36 | PRP | 242 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-12-01 | 50000 | -14819 | 35181 | 35181 | 100% | 0 | 0 |  | 6500 | -1926 | 4573.53 | 0.47 | 0.47 | Upon confirmation of very low national CTC consumption, arrangements with Ministry of Environment are being made to transfer project to UNDP. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | CHI | SEV | 04 | CPG | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 121166 | -115333 | 5833 | 5833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | CHI | SEV | 06 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -134385 | 57493 | 57493 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of the Technology Conversion Financing Programme (Tecfin) | Individual | LAC | CHI | MUS | 07 | INV | 04 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  | 1998-07-01 | 2000-03-01 | 69548 | -69548 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Part of $1,206,000 line-of-grant project. Funding returnd at the 30th ExCom. |  |  | 1997-04-30 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (approved at the 7th ExCom meeting) |  | LAC | CHI | SEV | 12 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30208 | 2849 | 33057 | 33057 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | CHI | SEV | 09 | PRP | 07 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 82890 | -10881 | 72009 | 72009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Establishment of the Ozone Team | Individual | LAC | CHI | SEV | 07 | INS | 08 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-10-01 | 1996-11-01 | 213000.03 | -2093 | 210907.03 | 210906.86 | 100% | 0.17 | 0.17 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-31 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Ozone seal programme | Individual | LAC | CHI | SEV | 07 | TAS | 09 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1993-06-01 |  | 1996-06-01 | 1996-06-01 | 8000 | -600 | 7400 | 7400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-06-30 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Public awareness programme | Individual | LAC | CHI | SEV | 07 | TAS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-06-01 | 1996-07-01 | 378000 | -5932 | 372068 | 372067.8 | 100% | 0.2 | 0.2 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-07-31 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of a sector specific training programme | Individual | LAC | CHI | SEV | 07 | TRA | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1996-01-01 | 1996-06-01 |  | 1997-10-01 | 1998-12-01 | 111000 | -14033 | 96967 | 96967 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-06-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | CHI | SEV | 16 | PRP | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-12-01 |  | 1995-12-31 | 1995-12-31 | 130312 | 0 | 130312 | 130312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | CHI | SEV | 18 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-03-01 | 1997-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Funds committed in CY96 were disbursed in CY97. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Montreal Protocol implementation programme - phase II | Individual | LAC | CHI | MUS | 19 | INV | 14 | N | O | I | CFC | 400 | 216 | 0 | 0 | 1996-05-01 | 1998-12-01 | 2000-05-01 |  | 2004-12-01 |  | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 130000 | 0 | 130000 | 0 | 0 | There was a change in the NOU since the project was completed and the PCR for the entire Tecfin Project has not been completed. The PCR will be completed by Jun 06 at which time financial completion will occur. |  |  | 1997-12-31 | 2000-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening II | Individual | LAC | CHI | SEV | 20 | INS | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-10-01 |  | 1998-10-01 | 1998-10-01 | 113500 | 0 | 113500 | 113500 | 100% | 0 | 0 |  | 14755 | 0 | 14755 | 0 | 0 | Completed |  |  | 1998-10-31 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | CHI | SEV | 04 | PRP | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 162736 | -134936 | 27800 | 27800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Retrofit of freezing chambers at Frigorent Frigorifico Sociedad Limitada | Individual | LAC | CHI | REF | 07 | INV | 18 | N | O | I | CFC | 0.03 | 0.03 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-09-01 |  | 1996-10-01 | 1996-10-01 | 20166.36 | 0 | 20166.36 | 20166.36 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-31 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Frigocar | Individual | LAC | CHI | FOA | 07 | INV | 19 | N | O | I | CFC | 0.6 | 0.6 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-10-01 |  | 1996-10-01 | 1996-10-01 | 15784 | 0 | 15784 | 15784 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Foam project |  |  | 1996-10-31 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Kifafi | Individual | LAC | CHI | FOA | 07 | INV | 20 | N | O | I | CFC | 0.9 | 0.8 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFCs at Mimet | Individual | LAC | CHI | REF | 07 | INV | 21 | N | O | I | CFC | 47.8 | 47.8 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1996-12-01 |  | 1996-12-01 | 1997-01-01 | 93671.85 | 0 | 93671.85 | 93671.85 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-23 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and recycling programme at Central De Servicios Tecnicos (CST) | Individual | LAC | CHI | REF | 07 | TAS | 22 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1997-03-01 |  | 1996-11-01 | 1997-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Polimin | Individual | LAC | CHI | FOA | 07 | INV | 23 | N | O | I | CFC | 0.3 | 0.28 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 9120 | 0 | 9120 | 9120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of ODS at Supermercado Gran Avenida | Individual | LAC | CHI | REF | 07 | INV | 24 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Vicuna McKenna | Individual | LAC | CHI | REF | 07 | INV | 25 | N | O | I | CFC | 0.64 | 0.05 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 5558 | 0 | 5558 | 5558 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Macul | Individual | LAC | CHI | REF | 07 | INV | 26 | N | O | I | CFC | 0.4 | 0.08 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 2505 | 0 | 2505 | 2505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Plaza Egana | Individual | LAC | CHI | REF | 07 | INV | 27 | N | O | I | CFC | 0.32 | 0.03 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 3300 | 0 | 3300 | 3300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC phase out at Himmer & Himmer | Individual | LAC | CHI | FOA | 07 | INV | 28 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC phase out at SAAM, S.A. | Individual | LAC | CHI | FOA | 07 | INV | 29 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from Inventory |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Instapanel (IPAC) | Individual | LAC | CHI | FOA | 07 | INV | 30 | N | O | I | CFC | 64.2 | 64.2 | 0 | 0 | 1992-06-01 | 1997-02-01 | 1997-03-01 |  | 1996-12-01 | 1997-02-01 | 131606.92 | 0 | 131606.92 | 131606.92 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-16 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Inversiones Overjuna (Metalcargo) | Individual | LAC | CHI | FOA | 07 | INV | 31 | N | O | I | CFC | 0.2 | 0.2 | 0 | 0 | 1992-06-01 | 1996-12-01 | 1997-03-01 |  | 1996-12-01 | 1996-12-01 | 4740 | 0 | 4740 | 4740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-01-31 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector for tomatoes |  | LAC | CHI | FUM | 24 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the Phase II auction scheme |  | LAC | CHI | SEV | 25 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-30 | 1999-08-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Newly approved. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment applications for tomatoes and peppers | Individual | LAC | CHI | FUM | 25 | DEM | 35 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 | 2006-12-31 |  |  | 348130 | 0 | 348130 | 330231 | 94.86% | 17899 | 17899 | 17899 | 45256.9 | 0 | 42930.03 | 2326.87 | 2326.87 | Project is in its final stage. All field activities completed. The consumption survey agreed between CONAMA and the Ministry of Agriculture/SAG was completed in 2005. Remaiining activity is to further develop a tracking system. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Ozone protection and institutional strengthening project (renewal) | Individual | LAC | CHI | SEV | 25 | INS | 36 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-12-01 | 2000-12-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Montreal Protocol implementation programme (Phase II, second tranche) | Individual | LAC | CHI | MUS | 26 | INV | 37 | N | O | I | CFC | 270 | 202.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2004-12-01 |  | 2800000 | -1000000 | 1800000 | 1605995 | 89.22% | 194005 | 0 |  | 318000 | -95000 | 186659.45 | 36340.55 | 0 | There was a change in the NOU since the project was completed and the PCR for the entire Tecfin Project has not been completed. The PCR will be completed by Jun 06 at which time financial completion will occur. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Extension of institutional strengthening project |  | LAC | CHI | SEV | 38 | INS | 52 | N | T | I | CFC | 15.42 | 15.42 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 | 186550 | 0 | 186550 | 186550 | 100% | 0 | 0 |  | 46800 | 0 | 46800 | 0 | 0 | Phase V of the IS project completed. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment project in the methyl bromide sector |  | LAC | CHI | FUM | 30 | PRP | 139 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening |  | LAC | CHI | SEV | 32 | INS | 142 | N | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2003-01-01 | 2003-01-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | NOU completed the IS tranche with work on several activities: the RMP, methyl bromide demo. project, sterilization project, and methyl bromide phase out in the tree sub-sector. New IS approved at the 38th ExCom. | [10 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for 2 projects in the methyl bromide sector |  | LAC | CHI | FUM | 33 | PRP | 145 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2002-09-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | The proposal is being prepare by the Bank and the INIA | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a national halon bank |  | LAC | CHI | HAL | 39 | PRP | 152 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Proposal will be submitted to the 42nd ExCom Meeting. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Halon Banking | LAC | CHI | HAL | 42 | TAS | 156 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2006-10-01 | 2006-10-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 4500 | 0 | 0 | 4500 | 4500 | As per ExCom approval, disbursement can only take place when import restrictions for halon is in place in the country. A law for regulating ODS use and import quotas in Chile was passed by Congress in 2005. This law only comes into effect when regulatory limits are put in place by Presidential Decree, expected Q2 2006. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of the institutional strengthening project (phase VI, second year) | Individual | LAC | CHI | SEV | 45 | INS | 157 | N | T | I | CFC | 7.7 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 | 2006-04-01 |  |  | 93275 | 0 | 93275 | 67347 | 72.2% | 25928 | 25928 | 25928 | 6996 | 0 | 5051.29 | 1944.71 | 1944.71 | Combined funds of two tranches for IS(this one and CHI/SEV/47/INS/159) will be used to cover personnel salary at the NOU, admin. charges and consulting needed in order to advance in the development of the law on the mechanisms for the protection of the ozone layer approved by congress, IS, including wages for personnel at the ozone unit, admin. expenses and expenses for the consolidation of the regulatory framework. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase-out of all the remaining uses of methyl bromide in soil application pest control (first tranche) | Multiyear | LAC | CHI | FUM | 45 | INV | 158 | N | O | I | MBR | 1.3 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 691703 | 0 | 691703 | 0 | 0% | 691703 | 0 |  | 51878 | 0 | 0 | 51878 | 0 | Project will be cancelled (as per request by the Gov. of Chile) at the 48th ExCom. Funds will be returned to the MPMF. | [10 empty] | 2005 | INV | 170 | 168.2 | 0 | 0 | Yes | No | No
ONG | IBRD | Extension of institutional strengthening (phase VI, year 2) | Individual | LAC | CHI | SEV | 47 | INS | 159 | N | T | D | CFC | 7.7 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 93275 | 0 | 93275 | 0 | 0% | 93275 | 93275 | 93275 | 6996 | 0 | 0 | 6996 | 6996 | Combined funds of two tranches for IS (this one and CHI/SEV/45/INS/157) will be used to cover personnel salary at the NOU, admin. charges and consulting needed in order to advance in the development of the law on the mechanisms for the protection of the ozone layer approved by congress, IS, including wages for personnel at the ozone unit, admin. expenses and expenses for the consolidation of the regulatory framework. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation identification |  | LAC | COL | SEV | 21 | PRP | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | COL | REF | 24 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Daniel J. Fernandez and Cia. Ltd. | Individual | LAC | COL | FOA | 26 | INV | 28 | N | O | I | CFC | 22.2 | 22.2 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2002-02-01 | 2002-05-01 | 173822 | 0 | 173822 | 173822 | 100% | 0 | 0 |  | 22596.86 | 0 | 22596.86 | 0 | 0 | Project has been fully executed. PCR is being revised for submission. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Friotermica S.A. | Individual | LAC | COL | FOA | 26 | INV | 29 | N | O | I | CFC | 8.6 | 8.6 | 0 | 0 | 1998-11-01 | 2001-12-01 | 2000-12-01 |  | 2002-09-01 | 2002-12-01 | 67338 | 0 | 67338 | 67338 | 100% | 0 | 0 |  | 8753.94 | 0 | 8753.94 | 0 | 0 | Project fully completed during the last trimester of 2002. PCR is being prepared. | [5 empty] | 2002-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Indufrio | Individual | LAC | COL | FOA | 26 | INV | 30 | N | O | I | CFC | 9.65 | 9.65 | 0 | 0 | 1998-11-01 | 2002-12-01 | 2000-12-01 |  | 2003-10-01 | 2003-12-01 | 75548 | 0 | 75548 | 75548 | 100% | 0 | 0 |  | 9821.24 | 0 | 9821.24 | 0 | 0 | Project has been financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-22 technology at Master Cooler and Cia Ltd. | Individual | LAC | COL | FOA | 26 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70862 | -70862 | 0 | 0 |  | 0 | 0 |  | 9212.06 | -9212 | 0 | 0.06 | 0.06 | Project cancelled and funds returned at the 35th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and solvent sectors |  | LAC | COL | SEV | 27 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Polares Ltda. | Individual | LAC | COL | REF | 28 | INV | 34 | N | O | I | CFC | 4.64 | 4.64 | 0 | 0 | 1999-07-01 | 2001-09-11 | 2001-08-01 |  | 2002-03-01 | 2002-06-01 | 58109 | 0 | 58109 | 58109 | 100% | 0 | 0 |  | 7554.17 | 0 | 7554.17 | 0 | 0 | Project has been fully executed. PCR being prepared. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Rojas Hnos., Ltda. | Individual | LAC | COL | FOA | 28 | INV | 35 | N | O | R | CFC | 8.2 | 8.2 | 0 | 0 | 1999-07-01 | 2001-08-30 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 64206 | 0 | 64206 | 64206 | 100% | 0 | 0 |  | 8346.78 | 0 | 8346.78 | 0 | 0 | The project is completed, equipment destroyed and funding disbursed. PCR is expected May 2002. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises | Individual | LAC | COL | FOA | 29 | INV | 39 | N | O | I | CFC | 56.6 | 37.6 | 0 | 0 | 1999-11-01 | 2002-09-01 | 2002-06-01 |  | 2005-01-01 | 2005-08-01 | 584727 | 0 | 584727 | 414170 | 70.83% | 170557 | 0 |  | 74319.97 | 0 | 52641.83 | 21678.14 | 0 | Project is physically and financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration subsector |  | LAC | COL | REF | 30 | PRP | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [11 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in MACs and compressors project category |  | LAC | COL | REF | 30 | PRP | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [11 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Industrias Supernórdico | Individual | LAC | COL | REF | 28 | INV | 44 | N | O | I | CFC | 9.6 | 9.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-02-01 | 2002-06-01 | 128381 | 0 | 128381 | 128381 | 100% | 0 | 0 |  | 16689.53 | 0 | 16689.53 | 0 | 0 | Project has been fully executed. PCR has been prepared and is being evaluated. Actual phaseout as reported in the PCR and confirmed with enterprise, country and revised proposal. | [5 empty] | 2002-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 100% | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | Project is physically and financially completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Thermo-coil, Calaires, Auto Aires, and Servi Aires | Individual | LAC | COL | REF | 34 | INV | 51 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-11-01 | 2003-12-01 | 1358647 | -13905 | 1344742 | 1344742.18 | 100% | -0.18 | -0.18 |  | 159451.17 | -1632 | 157819.3 | -0.13 | -0.13 | Project physically and financially completed. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 100% | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 enterprises | Individual | LAC | COL | REF | 38 | INV | 57 | N | O | I | CFC | 25.8 | 7.85 | 0 | 0 | 2002-11-01 | 2005-12-01 | 2004-12-01 |  | 2005-10-01 | 2005-12-01 | 211636 | 0 | 211636 | 81565 | 38.54% | 130071 | 0 |  | 27512.68 | 0 | 10603.44 | 16909.24 | 0 | Project is physically and financially completed. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 47 | INV | 64 | N | O | I | CTC | 2 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 114480 | 0 | 114480 | 0 | 0% | 114480 | 0 |  | 10303 | 0 | 0 | 10303 | 0 | The Government of Colombia, the World Bank and UNDP have agreed to transfer implementation of this project to UNDP. A request will be made to the Excom, at its 48th Meeting, to approve the transfer of all funds approved, including Agency support costs, to UNDP. No disbursement of funds approved at the 47th Excom Meeting has taken place. | [10 empty] | 2005 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | CPR | SEV | 04 | PRP | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 184000 | -167746 | 16254 | 16254 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme studies | Individual | ASP | CPR | SEV | 06 | CPG | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 180000 | -73841 | 106159 | 106159 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Shanghai CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 14 | N | O | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-09-01 | 1997-06-01 | 1900000 | 409000 | 2309000 | 2309000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhejiang foam plant conversion to butane | Individual | ASP | CPR | FOA | 07 | INV | 15 | N | O | I | CFC | 400 | 400 | 0 | 0 | 1992-06-01 | 1994-04-01 | 1994-06-01 |  | 1995-09-01 | 1996-09-01 | 1042000 | -49000 | 993000 | 993000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. ODP phaseout target reached. |  |  | 1995-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project I: 50% CFC foam | Individual | ASP | CPR | FOA | 07 | INV | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1994-06-01 |  | 1996-06-01 | 1996-06-01 | 645000 | 0 | 645000 | 645000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Fully disbursed and distributed to 50% foam projects that were approved a year after this approval. Disbursed amount appeared to exceed grant by $1000. Thru Dec. 37/14, the Bank was able to return the $1,000 to the MLF in the context of the reconciliation of the Accounts of the Fund at the 38th ExCom (Dec. 38/9). |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhejiang halon extinguisher conversion | Individual | ASP | CPR | HAL | 07 | INV | 17 | N | O | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1993-12-01 |  | 1996-11-01 | 1996-01-01 | 797000 | -67000 | 730000 | 730000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and ODP phaseout target reached. The project was commissioned in May 97. |  |  | 1996-11-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Beijing ABC powder production project | Individual | ASP | CPR | HAL | 07 | INV | 18 | N | O | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1996-04-01 | 1996-08-01 | 403000 | 527000 | 930000 | 930000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation advance for developing components of Project I (1992) |  | ASP | CPR | SEV | 07 | PRP | 21 | N | O | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PPA I is complete. These funds were used to support implementation of the China ODS Projects I and II. No money was allocated, however $600,000 from ODS II and $900,000 from ODS I was used. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Tianjin CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 23 | N | O | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-03-01 | 1997-06-01 | 2500000 | 270000 | 2770000 | 2770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Pre-investment activities for Nanjing compressor and four refrigeration projects |  | ASP | CPR | REF | 08 | PRP | 24 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. In addition, a sector-wide phaseout strategy for the commercial refrigeration and air-conditioning sector was prepared (12,500 tons of CFCs). | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Financial agent fee for the implementation of approved projects (two aerosols, two foams, two halons) | Individual | ASP | CPR | SEV | 09 | TAS | 29 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1996-12-01 | 1996-12-01 | 185000 | 0 | 185000 | 185000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The FA completed appraisal reports for all subprojects and all have been cleared by the Bank. PPA I has been fully disbursed. ODS II was disbursed, and its accounts closed in 1997. Project completion report for ODS I& II completed. |  |  | 1996-12-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | CPR | SEV | 09 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 326000 | -133667 | 192333 | 192333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Production-sector pre-investment studies |  | ASP | CPR | PRO | 10 | PRP | 34 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-06-28 | 1994-06-01 |  | 1996-03-01 | 1996-03-01 | 240000 | 80000 | 320000 | 320000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete, including many proposals and six sector phaseout strategies. 26 foam projects, to be implemented by UNDP and the Bank, were prepared following first two workshops. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | CPR | SEV | 10 | PRP | 35 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 280000 | -131872 | 148128 | 148128 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Liming Research and development of polyol and blended polyol production techniques for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 42 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-01-01 | 1996-09-01 | 457000 | 0 | 457000 | 457000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1996-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Wuxi production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 43 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1995-06-01 |  | 1995-09-01 | 1997-05-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1995-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Chengde conversion to 50% reduced CFC foam in insulation panel and in-situ foaming formulations | Individual | ASP | CPR | FOA | 10 | INV | 44 | N | O | D | CFC | 32 | 50 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1997-06-01 |  | 1994-10-01 | 1996-09-01 | 163000 | 0 | 163000 | 163000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1995-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Dalian conversion to 50% CFC reduced foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 45 | N | O | D | CFC | 14 | 30 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1996-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Tianjin conversion to 50% reduced CFC foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 46 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 443000 | -443000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Transferred to UNDP. $443,000 credited to the MLF at 17th Meeting. |  |  | 1995-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Qindao Haier conversion to 50% reduced CFC foam in freezer cabinets | Individual | ASP | CPR | FOA | 10 | INV | 47 | N | O | D | CFC | 120 | 232 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1994-06-01 | 1997-06-01 | 476000 | 0 | 476000 | 476000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1994-08-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Henan Xinfei conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 48 | N | O | D | CFC | 103 | 250 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1994-10-01 | 1997-06-01 | 1042000 | 0 | 1042000 | 1042000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. Funding approved for final conversion to non-ODS. |  |  | 1996-11-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shangling conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 49 | N | O | I | CFC | 103 | 244.1 | 0 | 0 | 1993-06-01 | 1995-12-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 958000 | 0 | 958000 | 958000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1996-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shuangyan conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 50 | N | O | D | CFC | 28 | 63 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1993-06-01 | 1997-03-01 | 485000 | 0 | 485000 | 485000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1994-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shenyang production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 51 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-09-01 | 1997-06-01 |  | 1994-08-01 | 1996-12-01 | 165000 | 0 | 165000 | 165000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. By using the contingency fund, the factory went one step ahead to develop 100% CFC-free technology. |  |  | 1995-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects ODS III (1994) |  | ASP | CPR | SEV | 12 | PRP | 62 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 660000 | -138768 | 521232 | 521232 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation of China ODS I (1994) |  | ASP | CPR | SEV | 12 | PRP | 63 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 79000 | -35235 | 43765 | 43765 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation of China ODS II (1994) |  | ASP | CPR | SEV | 12 | PRP | 64 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 110000 | 10949 | 120949 | 120949 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-134a refrigerant with Tecumseh designed compressors at Hua Yi Electrical Appliances General Co. | Individual | ASP | CPR | REF | 13 | INV | 68 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-09-01 | 1368000 | 0 | 1368000 | 1368000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-152a refrigerant in conventional compressors at Wanbao Electrical Appliances Industrial Corporation | Individual | ASP | CPR | REF | 13 | INV | 69 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 1999-07-01 | 2002-09-01 | 1360000 | 0 | 1360000 | 1360000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1997-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Engineering assistance for conversion of refrigerator manufacture to a ternary blend refrigerant (MP-39) in conventional compressors at Shanghai Shuanglu Electrical Appliances Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 70 | N | O | I | CFC | 70 | 64.3 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1996-07-01 |  |  | 1998-09-01 | 1010000 | -82008 | 927992 | 927992 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to financial difficulties. Undisbursed balance of $82,007.65 has been returned to MLF at the 30th ExCom Meeting. Four charging machines are proposed to be transferred to the new Shanghai Shangling project. PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-152a/HCFC-22 blended refrigerant in conventional compressors at Chang Ling Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 71 | N | O | I | CFC | 70 | 70 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-09-01 | 1997-03-01 | 853000 | -10 | 852990 | 852990 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 26th ExCom. |  |  | 1997-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam at Shanghai No. 18 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 72 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-07-01 | 1996-09-01 | 1995-07-01 |  | 1998-09-01 | 1998-09-01 | 450000 | 0 | 450000 | 450000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 27th ExCom. |  |  | 1997-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Shanghai No. 6 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 75 | N | O | I | CFC | 105 | 105 | 0 | 0 | 1994-07-01 | 1996-10-01 | 1995-07-01 |  | 1998-06-01 | 1998-12-01 | 687000 | -1292 | 685708 | 685708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 31th ExCom. |  |  | 1997-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Halon 1211 production closure at Tongxiang Chemical Fertilizer Factory | Individual | ASP | CPR | PRO | 13 | INV | 76 | N | O | I | HAL | 0 | 0 | 1200 | 1200 | 1994-07-01 | 1996-08-01 | 1995-01-01 |  | 1994-12-01 | 1996-08-01 | 838000 | -730880 | 107120 | 107120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom. |  |  | 1994-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for conversion of compressor manufacturing to HFC-134a rotary compressor designs at Shanghai Refrigerator Compressor Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 77 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-05-01 | 1997-06-01 | 1280000 | 0 | 1280000 | 1280000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCOM. |  |  | 1998-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-134a with rotary compressor at Shanghai Shangling General Refrigerator Factory | Individual | ASP | CPR | REF | 13 | INV | 78 | N | O | I | CFC | 108 | 108 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 2000-06-01 | 2002-09-01 | 1327000 | 0 | 1327000 | 1327000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998-01-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhongshan Fine Chemical Aerosol Filling Center CFC-12 substitution project | Individual | ASP | CPR | ARS | 13 | INV | 79 | N | O | I | CFC | 4067 | 4067 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-05-01 | 1998-10-01 | 1351360 | -319 | 1351041 | 1351041 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 29th ExCom. |  |  | 1998-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Lanzhou Plastic Packing Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 83 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1997-08-01 | 1997-11-01 | 222100 | -37 | 222063 | 222063 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom in January 1999. |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Cangzhou No. 2 Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 84 | N | O | I | CFC | 140 | 140 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1998-11-01 | 1999-04-01 | 394000 | 0 | 394000 | 394000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the 30th ExCom. |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Beijing Foam Plastic General Factory | Individual | ASP | CPR | FOA | 15 | INV | 85 | N | O | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-11-01 | 1999-11-01 | 720000 | 0 | 720000 | 720000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted December 2000. |  |  | 1997-06-01 | 1999-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in manufacture of extruded polyethylene and polystyrene foam sheet at Zhengzhou Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 86 | N | O | I | CFC | 260 | 260 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 2003-04-01 | 2004-05-01 | 267100 | 0 | 267100 | 267100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 1997-03-01 | 1999-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium sized semi-hermetic CFC-12 air conditioning compressor production to HCFC-22 at Beijing Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 15 | INV | 107 | N | O | I | CFC | 233 | 233 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1997-12-01 |  | 2000-08-01 | 2002-04-01 | 3098000 | -1000 | 3097000 | 3097000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-06-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) in Gaofeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 108 | N | O | I | CFC | 180 | 180 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-01-01 | 2002-09-01 | 458400 | 0 | 458400 | 458400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997-12-01 | 1999-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Hebei Dongfeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 109 | N | O | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  | 1999-05-01 | 1999-03-01 | 268600 | 0 | 268600 | 268600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to 30th ExCom. |  |  | 1997-12-01 | 1999-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium sized open-type CFC-12 refrigeration compressor production to HCFC-22 at Shanghai Refrigerating Machine Works (SRMW) | Individual | ASP | CPR | REF | 16 | INV | 110 | N | O | I | CFC | 162 | 162 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 1998-09-01 | 1999-09-01 | 2710000 | 0 | 2710000 | 2710000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the ExCom March 2000. |  |  | 1999-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small open-type CFC-12 refrigeration compressor production to HCFC-22 at Anhui Provincial Refrigerating Machinery Factory (APRMF) | Individual | ASP | CPR | REF | 16 | INV | 111 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 2002-07-01 | 2004-04-01 | 2224000 | 0 | 2224000 | 2224000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 1999-06-01 |  |  | 2001-06-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Jiangsu Taizhou Commercial Machinery Factory (JTCMF) | Individual | ASP | CPR | REF | 16 | INV | 112 | N | O | I | CFC | 285 | 285 | 0 | 0 | 1995-03-01 | 1996-10-01 | 1998-03-01 |  | 1999-12-01 | 2002-09-01 | 2797500 | 0 | 2797500 | 2797500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Nanjing Refrigerator General Works (NRGW) | Individual | ASP | CPR | REF | 16 | INV | 113 | N | O | I | CFC | 242 | 242 | 0 | 0 | 1995-03-01 | 1996-04-01 | 1998-03-01 |  | 1999-05-01 | 2002-04-01 | 2890000 | -27 | 2889973 | 2889973 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Production of small ammonia refrigerating compressor at Yantai Refrigerating Machinery Works (YRMW) | Individual | ASP | CPR | REF | 16 | INV | 114 | N | O | I | CFC | 240 | 240 | 0 | 0 | 1995-03-01 | 1996-12-01 | 1998-03-01 |  | 1999-05-01 | 2000-06-01 | 2874000 | 0 | 2874000 | 2874000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed.PCR and certificates were submitted to 30th ExCom Meeting. |  |  | 1999-06-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | CPR | SEV | 16 | PRP | 120 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 103131 | 0 | 103131 | 103131 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Yifeng Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 17 | INV | 122 | N | O | I | CFC | 90 | 60 | 0 | 0 | 1995-07-01 | 1998-01-01 | 1997-01-01 |  | 1998-04-01 | 1998-08-01 | 214600 | 0 | 214600 | 214600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1998-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Shanghai Ek Chor General Machinery Co. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 129 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1996-01-01 | 1998-06-01 | 961000 | 0 | 961000 | 961000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1998-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Development of a cost effective sector based ODS phase out approach | Individual | ASP | CPR | SEV | 17 | TAS | 136 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-10-31 | 1996-12-01 |  | 1996-12-01 | 1996-12-01 | 350000 | -150000 | 200000 | 200000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | $100,000 transferred to PPA-V. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Liangzhu | Individual | ASP | CPR | FOA | 17 | INV | 137 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-08-01 | 2002-09-01 | 167800 | 0 | 167800 | 167800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted to ExCom. |  |  | 1997-12-01 | 1999-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zhenjiang No. 5 Plastic Factory | Individual | ASP | CPR | FOA | 17 | INV | 138 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  |  | 2001-03-01 | 276800 | -60003 | 216797 | 216797 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. Remaining amount of $60,000 has been returned to ExCom. |  |  | 1998-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS III (1995) |  | ASP | CPR | SEV | 16 | PRP | 139 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Processing of the third ODS Phaseout project for China has been completed. Grant agreement was signed in June 1995. $50,000 was transferred from PPA-IV (China) (CPR/SEV/16/PRP/217) to this project preparation (ODS III - China). Thus, $700,000 was disbursed under this activity. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Penglai Polyurethane Plastic Factory | Individual | ASP | CPR | FOA | 18 | INV | 140 | N | O | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-01-01 | 320583 | -83 | 320500 | 320500 | 100% | 0 | 0 |  | 41675.79 | -11 | 41665 | -0.21 | -0.21 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 foaming agent to cyclopentane at Chang Ling (Group) Co. Ltd. | Individual | ASP | CPR | FOA | 18 | INV | 146 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-12-01 | 1999-01-01 | 2062000 | 0 | 2062000 | 2062000 | 100% | 0 | 0 |  | 268060 | 0 | 268060 | 0 | 0 | Project completed; PCR submitted December 2000. |  |  | 1998-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Yueyang Hengli Air Conditioning Equipment Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 148 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 2000-02-01 | 1767961 | 0 | 1767961 | 1767961 | 100% | 0 | 0 |  | 229834.93 | 0 | 229834.93 | 0 | 0 | Project completed; PCR submitted to the 31th ExCom. |  |  | 1998-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Guangzhou Haohua Automobile Parts Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 149 | N | O | I |  | 0.65 | 0.65 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 2001-03-01 | 2001-07-08 | 2212039 | -202829 | 2009210 | 2009210.43 | 100% | -0.43 | -0.43 |  | 287565.07 | -25353.62 | 262211.45 | 0 | 0 | Project completed; Draft PCR is under review. |  |  | 1998-06-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Shanghai Automobile Air Conditioner Co. (SAAC) | Individual | ASP | CPR | REF | 18 | INV | 150 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1996-12-01 | 1997-03-01 | 1642330 | -30 | 1642300 | 1642300 | 100% | 0 | 0 |  | 213502.9 | -3.9 | 213499.15 | -0.15 | -0.15 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 18 | PRP | 154 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Hangzhou Plastic Foam Factory | Individual | ASP | CPR | FOA | 19 | INV | 156 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1997-11-01 |  | 1999-03-01 | 1999-08-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 41210 | 0 | 41210 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-06-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qingyang Chemical Corp. | Individual | ASP | CPR | FOA | 19 | INV | 157 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1996-05-01 | 1999-08-01 | 1997-11-01 |  | 2001-09-01 | 2002-10-01 | 362000 | 0 | 362000 | 362000 | 100% | 0 | 0 |  | 47060 | 0 | 47060 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-06-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Yinguang Chemical Group | Individual | ASP | CPR | FOA | 19 | INV | 158 | N | O | I | CFC | 85 | 85 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1999-05-01 | 2000-10-01 | 376000 | 0 | 376000 | 376000 | 100% | 0 | 0 |  | 48880 | 0 | 48880 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qinhuangdao No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 159 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-08-01 | 1998-10-01 | 370000 | 0 | 370000 | 370000 | 100% | 0 | 0 |  | 48100 | 0 | 48100 | 0 | 0 | Project completed. PCR will be submitted in January 2001. |  |  | 1999-06-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFCs in the manufacture of flexible slabstock PUF at Jinan Shiyan Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 160 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1996-05-01 | 1998-04-01 | 1997-05-01 |  | 1999-01-01 | 2001-11-23 | 209300 | 0 | 209300 | 209300.29 | 100% | -0.29 | -0.29 |  | 27209 | 0 | 27209.03 | -0.03 | -0.03 | Project completed; PCR submitted. |  |  | 1998-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zibo No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 162 | N | O | I | CFC | 100 | 55 | 0 | 0 | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1999-01-01 | 2000-12-01 | 249000 | 0 | 249000 | 249000 | 100% | 0 | 0 |  | 32370 | 0 | 32370 | 0 | 0 | Project complete; PCR submitted to 29th ExCOM. |  |  | 1999-06-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Hua Yi Electrical Appliance General Company | Individual | ASP | CPR | FOA | 19 | INV | 166 | N | O | I | CFC | 170 | 170 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-02-01 |  | 1998-05-01 | 1998-09-01 | 972490 | 0 | 972490 | 972490 | 100% | 0 | 0 |  | 126423.7 | 0 | 126423.7 | 0 | 0 | Project completed; PCR submitted to 29th ExCOM. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Shanghai Shuanglu Electrical Appliance Co. Ltd. | Individual | ASP | CPR | FOA | 20 | INV | 174 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-07-01 |  |  | 1999-07-01 | 1899230 | -1899230 | 0 | 0 |  | 0 | 0 |  | 246899.9 | -246900 | 0 | -0.1 | -0.1 | Project cancelled. Company bankrupt. Funds returned at 27th meeting. |  |  | 1998-06-01 | 1998-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium-sized semi-hermetic CFC-12 refrigerating compressor production to HCFC-22 production at Tianjin Tian Shan Refrigeration Equipment Co. | Individual | ASP | CPR | REF | 20 | INV | 175 | N | O | I | CFC | 275.5 | 275.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2003-05-01 | 2004-09-01 | 2256000 | 0 | 2256000 | 2256000 | 100% | 0 | 0 |  | 293280 | 0 | 293280 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane and CFC-12 refrigerant to HFC-134a at Gansu Changfeng Baoan Industry Co. Ltd. | Individual | ASP | CPR | REF | 20 | INV | 176 | N | O | I | CFC | 65.2 | 65.2 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1998-10-01 |  | 2002-04-01 | 2004-07-01 | 634150 | 260000 | 894150 | 894150 | 100% | 0 | 0 |  | 82439.5 | 33800 | 116239.5 | 0 | 0 | Project financially completed. |  |  | 1999-06-01 |  | 2000-08-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of rigid PUF products at Handan Plastics No. 8 | Individual | ASP | CPR | FOA | 20 | INV | 177 | N | O | I | CFC | 101.64 | 101.64 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1997-10-01 |  | 1999-05-01 | 2002-07-01 | 265000 | 0 | 265000 | 265000 | 100% | 0 | 0 |  | 34450 | 0 | 34450 | 0 | 0 |  |  |  | 1997-12-01 | 1999-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexibe (slabstock) polyurethane foam at Chengdu Plastics No. 7 | Individual | ASP | CPR | FOA | 20 | INV | 179 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1996-10-01 | 2001-01-01 | 1998-04-01 |  | 2005-04-01 | 2005-01-01 | 301000 | 0 | 301000 | 301000 | 100% | 0 | 0 |  | 39130 | 0 | 39130 | 0 | 0 | Project completed. |  |  | 1998-04-01 | 2000-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigerating compressor production at Shanghai General Machinery (Group) Corp. (SGMC) | Individual | ASP | CPR | REF | 20 | INV | 180 | N | O | I | CFC | 209 | 209 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 2039800 | 0 | 2039800 | 2039800 | 100% | 0 | 0 |  | 265174 | 0 | 265174 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-11 and CFC-12 centrifugal refrigerating compressor to HFC-134a centrifugal technology at Chongqing General Machinery Factory (CGMF) | Individual | ASP | CPR | REF | 20 | INV | 182 | N | O | I | CFC | 220 | 220 | 0 | 0 | 1996-10-01 | 1998-01-01 | 2000-04-01 |  | 2000-08-01 | 2002-03-01 | 2632000 | 0 | 2632000 | 2632000 | 100% | 0 | 0 |  | 342160 | 0 | 342160 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  | 2000-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 20 | INV | 183 | N | O | I | CFC | 108.5 | 108.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 1974000 | 0 | 1974000 | 1974000 | 100% | 0 | 0 |  | 256620 | 0 | 256620 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Additional preparation of halon sector approach |  | ASP | CPR | HAL | 20 | PRP | 184 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-31 | 1997-08-01 |  | 1997-09-30 | 1997-09-30 | 132500 | 0 | 132500 | 132500 | 100% | 0 | 0 |  | 17225 | 0 | 17225 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the halon sector |  | ASP | CPR | HAL | 21 | PRP | 187 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 133000 | -500 | 132500 | 132500 | 100% | 0 | 0 |  | 17290 | -65 | 17225 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 21 | PRP | 189 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 32500 | 0 | 32500 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 medium open-type refrigerating compressor to HCFC-22 compressor at Guangzhou Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 198 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-04-01 | 2004-09-01 | 1904769 | 0 | 1904769 | 1904769 | 100% | 0 | 0 |  | 247619.97 | 0 | 247619.97 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 |  | 2002-06-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type refrigerating compressor to HCFC-22 refrigerating compressor at Subei Refrigeration Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 200 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-01-01 | 2004-04-01 | 1806908 | 0 | 1806908 | 1806908 | 100% | 0 | 0 |  | 234898.04 | 0 | 234898.04 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the production sector for 1998 submission |  | ASP | CPR | PRO | 22 | PRP | 205 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Wuhan New World Refrigeration Industrial Co. Ltd. | Individual | ASP | CPR | REF | 22 | INV | 208 | N | O | I | CFC | 209 | 209 | 0 | 0 | 1997-05-01 | 1999-09-01 | 2000-06-01 |  | 2003-08-01 | 2004-12-01 | 1459871 | 0 | 1459871 | 1459871 | 100% | 0 | 0 |  | 189783.23 | 0 | 189783.23 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 22 | INV | 209 | N | O | I | CFC | 186 | 186 | 0 | 0 | 1997-05-01 | 2001-12-31 | 2000-11-01 |  | 2002-12-01 | 2004-04-01 | 1048286 | 0 | 1048286 | 1048286 | 100% | 0 | 0 |  | 136277.18 | 0 | 136277.18 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small and medium open type refrigerating compressor production at Zhejiang Chunhui Company (Group) (ZCC) | Individual | ASP | CPR | REF | 22 | INV | 210 | N | O | I | CFC | 361 | 361 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-02-01 | 2004-05-01 | 3200394 | 0 | 3200394 | 3200394 | 100% | 0 | 0 |  | 416051.22 | 0 | 416051.22 | 0 | 0 | Project is financially completed. |  |  |  | 2000-06-01 |  | 2002-06-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Chongqing Bingyang Refrigerating Machine Co. | Individual | ASP | CPR | REF | 22 | INV | 214 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-12-01 | 2004-05-01 | 1805370 | 0 | 1805370 | 1805370 | 100% | 0 | 0 |  | 234698.1 | 0 | 234698.1 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open type refrigerating compressor production at Ningbo Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 215 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2002-10-01 | 2004-04-01 | 1786949 | 0 | 1786949 | 1786949 | 100% | 0 | 0 |  | 232303.37 | 0 | 232303.37 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (1995) |  | ASP | CPR | SEV | 16 | PRP | 217 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-12-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. Actual disbursement for PPA IV was $200,000. and the balance of $50,000 was utilized for project preparation under ODS III (CPR/SEV/16/PRP/139). | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Hefei General Machinery Research Institute (HGMRI): four technical assistance projects to support conversion of commercial refrigeration compressors | Individual | ASP | CPR | REF | 23 | INV | 218 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-06-01 | 2001-11-01 |  | 2002-11-01 | 2002-11-01 | 692400 | -39141 | 653259 | 653259 | 100% | 0 | 0 |  | 90012 | -4892.63 | 85119.37 | 0 | 0 | Project completed. Draft PCR underway. Savings to be returned to the MLF. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 227 | N | O | I | CFC | 462.6 | 462.6 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2001-12-01 | 2002-11-01 | 1132682 | -2956 | 1129726 | 1129726 | 100% | 0 | 0 |  | 147249 | -370 | 146879 | 0 | 0 | Project completed. PCR submitted to ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Shanghai General Machinery Company (SGMC) | Individual | ASP | CPR | FOA | 23 | INV | 230 | N | O | I | CFC | 88.3 | 88.3 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2002-12-01 | 2004-09-01 | 380300 | -1711.2 | 378588.8 | 378588.8 | 100% | 0 | 0 |  | 49439 | -171.12 | 49267.88 | 0 | 0 | Financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 1998 Annual Programme | Individual | ASP | CPR | HAL | 23 | INV | 231 | N | O | I | HAL | 9939 | 9939 | 11739 | 11739 | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 |  | 12400000 | 0 | 12400000 | 12400000 | 100% | 0 | 0 |  | 1240000 | 0 | 1240000 | 0 | 0 | 1998 Annual Plan was successfully completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Henan Xinfei Electric Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 234 | N | O | I | CFC | 375 | 375 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-12-01 |  | 1998-12-01 | 2000-09-01 | 1556490 | 0 | 1556490 | 1556490 | 100% | 0 | 0 |  | 202344 | 0 | 202344 | 0 | 0 | Project was completed; PCR submitted to 30th ExCOM. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Shanghai Shangling Chang-An Refrigerator Co., Ltd (former Shanghai Yuandong Refrigerator Co. Ltd.) | Individual | ASP | CPR | REF | 23 | INV | 235 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 2000-11-01 |  |  | 2000-12-01 | 1237663 | -1237663 | 0 | 0 |  | 0 | 0 |  | 160896 | -158482.56 | 2413.44 | 0 | 0 | Project cancelled due to financial difficulties. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the aerosol, foam, MAC and commercial refrigeration sectors |  | ASP | CPR | SEV | 24 | PRP | 243 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 78000 | 0 | 78000 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project to complete CFC phaseout in general purpose aerosols at NCLI and Fujiang Light Industry Co. | Individual | ASP | CPR | ARS | 24 | INV | 244 | N | O | I | CFC | 1224 | 1224 | 0 | 0 | 1998-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-12-01 | 2004-05-01 | 547675 | 0 | 547675 | 547675 | 100% | 0 | 0 |  | 71197.75 | 0 | 71197.75 | 0 | 0 | Project financially completed. | [5 empty] | 2002-06-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | CPR | SEV | 16 | PRP | 246 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 68017 | 0 | 68017 | 68017 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of refrigerator manufacture in Changhe Group to HFC-134a as refrigerant and cyclopentane as foam blowing agent | Individual | ASP | CPR | REF | 25 | INV | 251 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2001-08-01 |  |  | 2001-12-31 | 1267638 | -1267638 | 0 | 0 |  | 0 | 0 |  | 164792.94 | -162321.05 | 2471.89 | 0 | 0 | Project has been cancelled. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture to forced cooling and methylene chloride at Wuxi New Type Raw Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 252 | N | O | I | CFC | 231 | 231 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-08-01 |  | 1999-10-01 | 2002-08-01 | 488150 | 0 | 488150 | 488150 | 100% | 0 | 0 |  | 63459.5 | 0 | 63459.5 | 0 | 0 | [12 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | MAC ODS phaseout sector plan | One off phaseout | ASP | CPR | REF | 26 | INV | 255 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-04-01 | 7700000 | 0 | 7700000 | 7700000 | 100% | 0 | 0 |  | 820000 | 0 | 820000 | 0 | 0 | Project completed. Completion report submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 1999 Annual Programme | Multiyear | ASP | CPR | HAL | 26 | INV | 261 | N | O | I | HAL | 5370 | 5370 | 5826 | 5826 | 1998-11-01 | 1999-03-31 | 1999-12-01 |  | 1999-12-01 |  | 9700000 | 0 | 9700000 | 9700000 | 100% | 0 | 0 |  | 970000 | 0 | 970000 | 0 | 0 | 1999 annual plan completed successfully. | [11 empty] | INV | 19110 | 18880 | 24090 | 22735 | Yes | Yes | Yes
FIN | IBRD | Conversion of refrigerator manufacture from CFC-11 to pentane foam blowing agent in the production of PU insulation panels at Foshan Refrigeration Equipment General Factory | Individual | ASP | CPR | FOA | 26 | INV | 267 | N | O | I | CFC | 120.3 | 120.3 | 0 | 0 | 1998-11-01 | 2000-09-01 | 2001-12-01 |  | 2005-03-01 | 2005-08-01 | 743500 | 0 | 743500 | 743500 | 100% | 0 | 0 |  | 91785 | 0 | 91785 | 0 | 0 | Completed. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Handan Fuyang Chemical Corporation | Individual | ASP | CPR | FOA | 27 | INV | 269 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2002-10-01 |  |  | 2001-12-01 | 436100 | -436100 | 0 | 0 |  | 0 | 0 |  | 56693 | -55842.6 | 850.4 | 0 | 0 | Project cancelled at the 35th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Qingdao Changlong Commercial Machinery Co. Ltd. | Individual | ASP | CPR | FOA | 27 | INV | 270 | N | O | I | CFC | 57.7 | 57.7 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-02-01 | 2003-10-01 | 451791 | -3921.96 | 447869.04 | 447869.04 | 100% | 0 | 0 |  | 58732.83 | -490.25 | 58242.58 | 0 | 0 | Physically and financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Xiaoshan Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 27 | INV | 271 | N | O | I | CFC | 111 | 111 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 603058 | 0 | 603058 | 603058 | 100% | 0 | 0 |  | 76336.38 | 0 | 76336.38 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and CFC production sectors |  | ASP | CPR | SEV | 27 | PRP | 273 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-31 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shenyin Polyurethane Xinzhuang Plant | Individual | ASP | CPR | FOA | 27 | INV | 274 | N | O | I | CFC | 86.1 | 86.1 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-11-01 | 2005-04-01 | 536403 | 0 | 536403 | 536403 | 100% | 0 | 0 |  | 69004.33 | 0 | 69004.33 | 0 | 0 | Completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Henan Huojia Huashi Co. | Individual | ASP | CPR | FOA | 27 | INV | 275 | N | O | I | CFC | 109.5 | 109.5 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 583186 | 0 | 583186 | 583186 | 100% | 0 | 0 |  | 74150.46 | 0 | 74150.46 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Zhenjiang Commercial Refrigeration Equipment General Plant | Individual | ASP | CPR | FOA | 27 | INV | 276 | N | O | I | CFC | 30.81 | 30.81 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 145376 | -4908 | 140468 | 140468 | 100% | 0 | 0 |  | 18899 | -490.8 | 18408.2 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jiangsu Haimen Foam plant | Individual | ASP | CPR | FOA | 27 | INV | 277 | N | O | I | CFC | 73 | 73 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-08-01 | 2004-12-01 | 454790 | 0 | 454790 | 454790 | 100% | 0 | 0 |  | 59122.7 | 0 | 59122.7 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Shanghai Haiou Electric Appliance General Factory | Individual | ASP | CPR | FOA | 27 | INV | 280 | N | O | I | CFC | 33.34 | 33.34 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-09-01 | 2004-04-01 | 261052 | 0 | 261052 | 261052 | 100% | 0 | 0 |  | 33936.76 | 0 | 33936.76 | 0 | 0 | Financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Putuo Zhujiajian Rubber and Plastic Plant | Individual | ASP | CPR | FOA | 27 | INV | 281 | N | O | I | CFC | 112 | 112 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-07-01 | 2005-03-01 | 525483 | 0 | 525483 | 525483 | 100% | 0 | 0 |  | 67803.13 | 0 | 67803.13 | 0 | 0 | Completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shanghai Shenyin Polyurethane Baoshan Plant | Individual | ASP | CPR | FOA | 27 | INV | 284 | N | O | I | CFC | 76 | 76 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-10-01 | 2005-04-01 | 473480 | 0 | 473480 | 473480 | 100% | 0 | 0 |  | 61552.4 | 0 | 61552.4 | 0 | 0 | Completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Chengdu Jinjiang Foam General Plant | Individual | ASP | CPR | FOA | 27 | INV | 285 | N | O | I | CFC | 89 | 89 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-08-01 | 2004-11-01 | 554470 | 0 | 554470 | 554470 | 100% | 0 | 0 |  | 70991.7 | 0 | 70991.7 | 0 | 0 | Financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | FOA | 28 | INV | 288 | N | O | I | CFC | 29.3 | 29.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-11-01 | 2004-11-01 | 149195 | 0 | 149195 | 149195 | 100% | 0 | 0 |  | 19395.35 | 0 | 19395.35 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Heilongjiang Commercial Installation Corporation | Individual | ASP | CPR | FOA | 28 | INV | 292 | N | O | I | CFC | 52.6 | 52.6 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2001-11-01 | 2003-02-01 | 411858 | 0 | 411858 | 411858 | 100% | 0 | 0 |  | 53541.54 | 0 | 53541.54 | 0 | 0 | Project physically and financially completed and PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Changzhou Huangfa Co. Ltd., Foam Plant | Individual | ASP | CPR | FOA | 28 | INV | 293 | N | O | I | CFC | 70.7 | 70.7 | 0 | 0 | 1999-07-01 | 2001-01-01 | 2002-08-01 |  | 2004-06-01 | 2005-04-01 | 440461 | 0 | 440461 | 440461 | 100% | 0 | 0 |  | 57259.93 | 0 | 57259.93 | 0 | 0 | Completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiangsu Taizhou Commercial Machiner General Factory | Individual | ASP | CPR | FOA | 28 | INV | 294 | N | O | I | CFC | 28.3 | 28.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 192890 | -106.2 | 192783.8 | 192783.8 | 100% | 0 | 0 |  | 25075.7 | -10.62 | 25065.08 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane foam sandwich panels at Chengde Commercial Machinery Group Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 295 | N | O | I | CFC | 106 | 106 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-07-01 | 829980 | 0 | 829980 | 829980 | 100% | 0 | 0 |  | 101297.8 | 0 | 101297.8 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Shandong Tianhua (Group) Plastic Plant | Individual | ASP | CPR | FOA | 28 | INV | 296 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2002-08-01 |  |  | 2001-12-01 | 534534 | -534534 | 0 | 0 |  | 0 | 0 |  | 68798.74 | -67766.76 | 1031.98 | 0 | 0 | Project cancelled at the 35 th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 298 | N | O | I | CFC | 104.2 | 104.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1457583 | 0 | 1457583 | 1457583 | 100% | 0 | 0 |  | 170334.13 | 0 | 170334.13 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Guangdong Zhujiang Refrigeration and Air Conditioning Co. | Individual | ASP | CPR | FOA | 28 | INV | 299 | N | O | I | CFC | 87.7 | 87.7 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2002-02-01 | 2003-06-01 | 581230 | 0 | 581230 | 581230 | 100% | 0 | 0 |  | 73935.3 | 0 | 73935.3 | 0 | 0 | Project completed. PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium sized open type compressors at Zhejiang Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 300 | N | O | I | CFC | 251.7 | 251.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1710295 | 0 | 1710295 | 1710295 | 100% | 0 | 0 |  | 198132.45 | 0 | 198132.45 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of semi-hermetic compressors at Yueyang Hengli Air-Cool Equipment Co. Ltd. | Individual | ASP | CPR | REF | 28 | INV | 303 | N | O | I | CFC | 220.2 | 220.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1951757 | -291.22 | 1951465.78 | 1951465.78 | 100% | 0 | 0 |  | 224693.27 | -33.53 | 224659.74 | 0 | 0 | Financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 2000 Annual Programme | Multiyear | ASP | CPR | HAL | 29 | INV | 309 | N | O | I | HAL | 3712 | 3712 | 5970 | 5970 | 1999-11-01 | 2000-08-01 | 2000-12-01 |  | 2000-12-01 |  | 10600000 | 0 | 10600000 | 10600000 | 100% | 0 | 0 |  | 1060000 | 0 | 1060000 | 0 | 0 | Annual Program fully completed and disbursed. | [11 empty] | INV | 13740 | 14720 | 18120 | 16214 | Yes | Yes | Yes
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Chengde Machinery Installation Co. Qinghuangdao Branch | Individual | ASP | CPR | FOA | 29 | INV | 310 | N | O | I | CFC | 19.99 | 19.99 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2004-04-01 | 156600 | -5284 | 151316 | 151316 | 100% | 0 | 0 |  | 20358 | -660.5 | 19697.5 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to methylene chloride and vertifoam from CFC-11 to liquid carbon dioxide technology at Shenzhou Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 311 | N | O | I | CFC | 134.9 | 134.9 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2005-05-01 | 2005-12-01 | 609616 | 0 | 609616 | 609616 | 100% | 0 | 0 |  | 77057.76 | 0 | 77057.76 | 0 | 0 | Completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Qianjin Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 317 | N | O | I | CFC | 64.77 | 64.77 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-08-01 | 2003-11-01 | 507109 | -79316 | 427793 | 427793 | 100% | 0 | 0 |  | 65781.99 | -10169 | 55613 | -0.01 | -0.01 | Project physically and financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hangxing Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 320 | N | O | I | CFC | 60.6 | 60.6 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-09-01 | 2004-09-01 | 471217 | -85471 | 385746 | 385746 | 100% | 0 | 0 |  | 61258.21 | -11111 | 50147.21 | 0 | 0 | Project financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Yangzhou Tongli Refrigeration Container Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 321 | N | O | I | CFC | 14.63 | 14.63 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-11-01 | 2003-06-01 | 114513 | 0 | 114513 | 114513 | 100% | 0 | 0 |  | 14886.69 | 0 | 14886.69 | 0 | 0 | Project physically and financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Fuxing Jiahe Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 322 | N | O | I | CFC | 136.67 | 136.67 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2005-03-01 | 2005-07-01 | 515970 | 0 | 515970 | 515970 | 100% | 0 | 0 |  | 66756.7 | 0 | 66756.7 | 0 | 0 | Completed. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Huisheng Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 323 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-12-01 | 522207 | -522207 | 0 | 0 |  | 0 | 0 |  | 67442.77 | -67443 | 0 | -0.23 | -0.23 | Project cancelled at the 40th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane vertifoam manufacture from CFC-11 to liquid carbon dioxide technology in Tonxiang Shule Plastic Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 324 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2001-12-01 | 498400 | -498400 | 0 | 0 |  | 0 | 0 |  | 64792 | -63820.12 | 971.88 | 0 | 0 | Project cancelled at the 35th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shanghai Furong Food Machinery Factory | Individual | ASP | CPR | FOA | 29 | INV | 335 | N | O | I | CFC | 23.1 | 23.1 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2002-06-01 | 2003-09-01 | 139379 | 0 | 139379 | 139379 | 100% | 0 | 0 |  | 18119.27 | 0 | 18119.27 | 0 | 0 | Physically completed. Draft PCR under review. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the flexible polyurethane foam subsector |  | ASP | CPR | FOA | 30 | PRP | 342 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for CFC production phaseout: 2000 annual programme | Multiyear | ASP | CPR | PRO | 30 | INV | 347 | N | O | I | CFC | 0 | 0 | 4931 | 4931 | 2000-03-01 | 2000-08-07 | 2000-12-01 |  | 2000-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 1170000 | 0 | 1170000 | 0 | 0 | Annual Program fully completed and disbursed. | [10 empty] | 2000 | INV | 0 | 0 | 40000 | 39990.5 | Yes | Yes | Yes
FIN | IBRD | Project preparation in the foam flexible subsector |  | ASP | CPR | FOA | 30 | PRP | 349 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam (general) sector |  | ASP | CPR | FOA | 30 | PRP | 350 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration sub-sector |  | ASP | CPR | REF | 30 | PRP | 351 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the domestic refrigeration subsector |  | ASP | CPR | REF | 30 | PRP | 352 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | ASP | CPR | FOA | 30 | PRP | 353 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed | [10 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the solvent (process agent) sector |  | ASP | CPR | PAG | 30 | PRP | 354 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed | [10 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for CFC production phaseout: 1999 annual programme | Multiyear | ASP | CPR | PRO | 27 | INV | 356 | N | O | I | CFC | 0 | 0 | 5497.6 | 5497.6 | 1999-03-01 | 1999-09-30 | 1999-12-01 |  | 1999-12-01 |  | 10000000 | 10000000 | 20000000 | 20000000 | 100% | 0 | 0 |  | 900000 | 900000 | 1800000 | 0 | 0 | 1999 annual plan successfully completed. | [11 empty] | INV | 0 | 0 | 44931 | 44793 | Yes | Yes | Yes
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Qujing Plastic No. 2 Plant | Individual | ASP | CPR | FOA | 31 | INV | 358 | N | O | I | CFC | 99 | 99 | 0 | 0 | 2000-07-01 | 2003-04-01 | 2003-08-01 |  | 2004-09-01 | 2005-12-01 | 600066 | 0 | 600066 | 600066 | 100% | 0 | 0 |  | 76007.26 | 0 | 76007.26 | 0 | 0 | Completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Wuxian Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 361 | N | O | I | CFC | 80 | 80 | 0 | 0 | 2000-07-01 | 2003-12-01 | 2003-08-01 |  | 2004-10-01 | 2005-04-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 |  | 64792 | 0 | 64792 | 0 | 0 | Completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Nantong Xinyuan Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 362 | N | O | I | CFC | 82 | 82 | 0 | 0 | 2000-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 510860 | 0 | 510860 | 510860 | 100% | 0 | 0 |  | 66194.6 | 0 | 66194.6 | 0 | 0 | Financially completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jintan Tiaoxi Shuya Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 363 | N | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 420525 | -420525 | 0 | 0 |  | 0 | 0 |  | 54668.25 | -53848.23 | 820.02 | 0 | 0 | Project cancelled at the 35th ExCom. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 2001 Annual Programme | Multiyear | ASP | CPR | HAL | 32 | INV | 364 | N | O | I | HAL | 1389 | 1389 | 1980 | 1980 | 2000-12-01 | 2002-12-01 | 2001-12-01 |  | 2001-12-01 |  | 4500000 | 0 | 4500000 | 4500000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Completed and fully disbursed. | [10 empty] | 2000 | INV | 12351 | 10296 | 16131 | 11484 | Yes | Yes | Yes
COM | IBRD | Sector plan for CFC production phaseout: 2001 annual programme | Multiyear | ASP | CPR | PRO | 33 | INV | 370 | N | O | I | CFC | 0 | 0 | 3800 | 3804 | 2001-03-01 | 2001-07-19 | 2001-12-01 |  | 2001-12-31 |  | 6500000 | 6500000 | 13000000 | 13000000 | 100% | 0 | 0 |  | 585000 | 585000 | 1170000 | 0 | 0 | Annual Program fully completed and disbursed. | [10 empty] | 2001 | INV | 0 | 0 | 36200 | 36196 | Yes | Yes | Yes
FIN | IBRD | Project preparation for the process agent sector plan |  | ASP | CPR | PAG | 34 | PRP | 374 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-06-01 |  | 2001-12-01 | 2001-12-01 | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 |  | 15860 | 0 | 15860 | 0 | 0 | [11 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | Individual | ASP | CPR | REF | 34 | INV | 378 | N | O | I | CFC | 174.2 | 174.2 | 0 | 0 | 2001-07-01 | 2003-05-01 | 2004-08-01 |  | 2005-12-01 |  | 1400000 | 0 | 1400000 | 1194036.68 | 85.29% | 205963.32 | 205963.32 | 205963.32 | 164000 | 0 | 139872.86 | 24127.14 | 24127.14 | Equipment delivered in Apr. 05 and commissioning and trial runs, as well as equipment disposal done in Dec. 05. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2002 annual programme | Multiyear | ASP | CPR | FOA | 35 | INV | 380 | N | O | I | CFC | 2000 | 2000 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 9940000 | 0 | 9940000 | 9940000 | 100% | 0 | 0 |  | 886600 | 0 | 886600 | 0 | 0 | One remaining conversion project expected to be completed Jul 06. All TA activities have completed. | [10 empty] | 2000 | INV | 14143 | 14143 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phaseout in China, 2002 Annual Programme | Multiyear | ASP | CPR | HAL | 35 | INV | 383 | N | O | I | HAL | 2889 | 2889 | 2160 | 2160 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 3700000 | 0 | 3700000 | 3700000 | 100% | 0 | 0 |  | 370000 | 0 | 370000 | 0 | 0 | Annual Program completed and final disbursement for the tranche made. | [10 empty] | 2001 | INV | 9462 | 6492 | 13962 | 7408 | Yes | Yes | Yes
ONG | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium open compressors at 5 enterprises (Dalian No.2, Shanghai Minhang, Zhejiang Beifeng, Zhejiang Chunlian, Zhejiang Yuhuan) | One off phaseout | ASP | CPR | REF | 36 | INV | 389 | N | O | I | CFC | 764.9 | 764.9 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-03-01 | 2006-06-01 |  |  | 5250852 | 0 | 5250852 | 2950852 | 56.2% | 2300000 | 2300000 | 2000000 | 587593.72 | 0 | 330213.47 | 257380.25 | 257380.25 | Delivery of equipment was delayed. The two conversion projects for Dalian and Chunhui are now expected to be completed by Jun 06 (pending one last piece of equipment delivery for one enterprise and baseline equipment disposal. No more CFC in use. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for CFC production phase-out: 2002 annual programme | Multiyear | ASP | CPR | PRO | 36 | INV | 391 | N | O | I | CFC | 0 | 0 | 3298 | 3300 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 910000 | 0 | 910000 | 0 | 0 | Annual program completed. CFC production verified and confirmed to be within target. | [10 empty] | 2002 | INV | 0 | 0 | 32900 | 32896 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phaseout in China: 2003 annual programme | Multiyear | ASP | CPR | HAL | 38 | INV | 395 | N | O | I | HAL | 2292 | 2292 | 1992 | 1992 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 5900000 | 0 | 5900000 | 5900000 | 100% | 0 | 0 |  | 442500 | 0 | 442500 | 0 | 0 | Annual Program completed and final disbursement for tranche made. | [10 empty] | 2002 | INV | 7170 | 4945 | 11970 | 5654 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2003 annual programme | Multiyear | ASP | CPR | FOA | 38 | INV | 396 | N | O | I | CFC | 2500 | 2721 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2003-12-01 |  | 2003-12-01 |  | 12570000 | 0 | 12570000 | 10104000 | 80.38% | 2466000 | 2466000 | 2466000 | 1115300 | 0 | 896498.9 | 218801.1 | 218801.1 | One remaining conversion project expected to be completed Jun. 06. | [10 empty] | 2002 | INV | 13830 | 13830 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): First tranche | Multiyear | ASP | CPR | PAG | 38 | INV | 397 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-10-01 | 2003-12-01 |  | 2003-12-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | First tranche completed. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation funds for CTC and TCA production closure plan |  | ASP | CPR | PRO | 38 | PRP | 399 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | TCA Sector Plan will be submitted to the 43rd ExCom. CTC sector plan will be submitted for information purpose to the 42nd ExCom. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector: 2003 annual programme | Multiyear | ASP | CPR | PRO | 39 | INV | 401 | N | O | I | CFC | 0 | 0 | 2900 | 2900 | 2003-04-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Annual Program completed and fully disbursed. | [10 empty] | 2003 | INV | 0 | 0 | 30000 | 29986 | Yes | Yes | Yes
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2003 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 39 | INV | 402 | N | O | I | CTC | 0 | 0 | 2638 | 2638 | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 |  | 20000000 | 0 | 20000000 | 20000000 | 100% | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Annual Program completed. | [10 empty] | 2003 | INV | 5066.2 | 5066.2 | 61514 | 61199 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phase-out in China: 2004 annual programme | Multiyear | ASP | CPR | HAL | 41 | INV | 404 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2004-12-01 |  | 1200000 | 0 | 1200000 | 660000 | 55% | 540000 | 540000 | 540000 | 90000 | 0 | 49500 | 40500 | 40500 | Annual Program successfully completed. Last tranche to be disbursed Jan 06. | [10 empty] | 2003 | INV | 7170 | 4433 | 11970 | 5053 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2004 annual programme | Multiyear | ASP | CPR | FOA | 41 | INV | 405 | N | O | I | CFC | 2500 | 2500 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 10903000 | 0 | 10903000 | 5606500 | 51.42% | 5296500 | 5296500 | 5296500 | 961270 | 0 | 494300.67 | 466969.33 | 466969.33 | 2004 AP has completed according to general obligations and with approval of the 2005 AP and second tranche disbursed. | [10 empty] | 2003 | INV | 11666 | 11666 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Project preparation for the second phase of process agents phase-out plan |  | ASP | CPR | PAG | 42 | PRP | 408 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2004-12-01 | 2006-04-01 |  |  | 125000 | 0 | 125000 | 56250 | 45% | 68750 | 68750 | 68750 | 9375 | 0 | 4218.75 | 5156.25 | 5156.25 | Sector plan was approved in principle at the 47th ExCom meeting. Agreement with ExCom will be submitted to the 48th ExCom. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for CFC production phase-out: 2004 annual programme | Multiyear | ASP | CPR | PRO | 42 | INV | 411 | N | O | I | CFC | 0 | 0 | 4700 | 4700 | 2004-04-01 | 2005-11-01 | 2004-12-01 |  | 2005-04-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Annual Program completed and fully disbursed. | [10 empty] | 2004 | INV | 0 | 0 | 25300 | 25285 | Yes | Yes | Yes
ONG | IBRD | Project preparation for pharmaceutical aerosol |  | ASP | CPR | ARS | 43 | PRP | 415 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2005-07-01 | 2006-11-01 |  |  | 135500 | 0 | 135500 | 0 | 0% | 135500 | 135500 | 135500 | 10163 | 0 | 0 | 10163 | 10163 | Sector Plan preparation now expected to be completed in Nov 06 due to time needed to agree on the consultant selection by SEPA and the State Food and Drug Administration. First disbursement expected in Feb. 06. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2004 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 43 | INV | 416 | N | O | I | CTC | 0 | 0 | 6657 | 6657 | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 |  | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 |  | 1200000 | 0 | 1200000 | 0 | 0 | Implemented as planned and fully disbursed. | [10 empty] | 2004 | INV | 5063 | 5063 | 54857 | 52353 | Yes | Yes | Yes
ONG | IBRD | Strategy for gradual phase-out of 1,1,1-trichlorethane (TCA) production (first stage programme) | Multiyear | ASP | CPR | PRO | 43 | INV | 417 | N | O | I | TCA | 0 | 0 | 33.8 | 0 | 2004-07-01 | 2005-12-01 | 2008-07-01 | 2008-07-01 |  |  | 1400000 | 0 | 1400000 | 750000 | 53.57% | 650000 | 650000 | 390000 | 105000 | 0 | 56250 | 48750 | 48750 | Implementation of AP is underway. | [10 empty] | 2003 | INV | 0 | 0 | 113 | 78 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phase-out in China: 2005 annual programme | Multiyear | ASP | CPR | HAL | 44 | INV | 423 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-11-01 |  | 1800000 | 0 | 1800000 | 0 | 0% | 1800000 | 1800000 | 900000 | 135000 | 0 | 0 | 135000 | 135000 | Annual program targets accomplished disbursement to be done in 2006. | [10 empty] | 2004 | INV | 7170 | 0 | 7970 | 0 |  | No | No
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2005 annual programme | Multiyear | ASP | CPR | FOA | 44 | INV | 424 | N | O | I | CFC | 2500 | 1335 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 |  | 10903000 | 0 | 10903000 | 0 | 0% | 10903000 | 10903000 | 5659500 | 961270 | 0 | 0 | 961270 | 961270 | Two projects were found ineligible and were cancelled. New conversion contracts are under preparation to cover remaining planned phaseout. | [10 empty] | 2004 | INV | 9000 | 0 | 0 | 0 | Yes | No | No
ONG | IBRD | Sector plan for CFC production phase-out: 2005 annual programme | Multiyear | ASP | CPR | PRO | 45 | INV | 428 | N | O | I | CFC | 0 | 0 | 6500 | 6500 | 2005-04-01 | 2005-12-01 | 2005-12-01 | 2006-04-01 |  |  | 13000000 | 0 | 13000000 | 6500000 | 50% | 6500000 | 6500000 | 6500000 | 975000 | 0 | 487500 | 487500 | 487500 | Implementation of AP is underway. | [10 empty] | 2005 | INV | 0 | 0 | 18750 | 18720.49 | Yes | Yes | Yes
ONG | IBRD | Process agent sector plan (phase I): 2005 annual programme | Multiyear | ASP | CPR | PAG | 46 | INV | 432 | N | O | I | CTC | 4556 | 4556 | 16171 | 16171 | 2005-07-01 | 2005-12-01 | 2006-07-01 | 2006-07-01 |  |  | 2000000 | 0 | 2000000 | 1400000 | 70% | 600000 | 600000 | 600000 | 150000 | 0 | 105000 | 45000 | 45000 | Implementation of AP is underway. China indicates that 2005 AP targets have been met. | [10 empty] | 2005 | INV | 1454 | 1397.85 | 38686 | 33080 | Yes | Yes | Yes
ONG | IBRD | Sector plan for halon phase-out in China: 2006 annual programme | Multiyear | ASP | CPR | HAL | 47 | INV | 433 | N | O | I | HAL | 6170 | 0 | 10470 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 11400000 | 0 | 11400000 | 0 | 0% | 11400000 | 11400000 | 400000 | 855000 | 0 | 0 | 855000 | 855000 | Implementation of AP is underway. | [10 empty] | 2005 | INV | 1000 | 0 | 1500 | 0 |  | No | No
ONG | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2006 annual programme | Multiyear | ASP | CPR | FOA | 47 | INV | 434 | N | O | I | CFC | 600 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 3320000 | 0 | 3320000 | 0 | 0% | 3320000 | 3320000 | 360000 | 282800 | 0 | 0 | 282800 | 282800 | Implementation of AP is underway. | [10 empty] | 2005 | INV | 7000 | 0 | 0 | 0 |  | No | No
ONG | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production (first tranche) | Multiyear | ASP | CPR | PAG | 47 | INV | 437 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2010-12-01 | 2010-12-01 |  |  | 15000000 | 0 | 15000000 | 0 | 0% | 15000000 | 15000000 | 8000000 | 1125000 | 0 | 0 | 1125000 | 1125000 | First Annual Plan is under preparation. Agreement for Phase II will be completed by the 48th ExCom. | [10 empty] | 2005 | INV | 0 | 0 | 0 | 0 | n/a | n/a | n/a
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | ECU | SEV | 04 | PRP | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 92031 | -5365 | 86666 | 86666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation for the conversion of six aerosol plants from CFC-12 to LPG |  | LAC | ECU | ARS | 06 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 300000 | -300000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation | Individual | LAC | ECU | SEV | 06 | CPG | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 76100 | -76100 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | ECU | SEV | 06 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 95026 | 76203 | 171229 | 171229 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation for the reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants (Indurama, Durex, Ecasa) |  | LAC | ECU | FOA | 06 | PRP | 06 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants: Indurama, Durex, and Ecasa | Individual | LAC | ECU | FOA | 09 | INV | 10 | N | O | I | CFC | 51 | 126.4 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1994-03-01 |  | 1995-11-01 | 1997-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprises have used funds to completely phaseout CFC-11 through adoption of HCFC-141b. PCR completed. |  |  | 1995-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening | Individual | LAC | ECU | SEV | 09 | INS | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1997-05-01 | 1997-08-01 | 204000 | -33327 | 170673 | 170673 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Public awareness campaign has been successfully carried out. Ozone Team actively supporting project implementation. |  |  | 1997-06-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of 18 aerosol plants to hydrocarbon propellants (Laboratorios Windsor (60 ton CFC/year), Pro Quim (6 ton), Jabonería Nacional (50 ton), Camposa (5 ton) and 14 other plants (169 ton) | Individual | LAC | ECU | ARS | 09 | INV | 12 | N | O | I | CFC | 290 | 82 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-09-01 | 1995-10-01 | 697000 | -365172 | 331828 | 331828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A complete phaseout in the aerosol sector has been achieved through this project component. All small aerosol producers have agreed to have their cans filled by Windsor Laboratories, Ecuador's largest aerosol filler. Balance to be returned to MF by Nov/99. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ECU | SEV | 09 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 68000 | 13231 | 81231 | 81231 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (approved at the 9th ExCom Meeting) |  | LAC | ECU | SEV | 12 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 15197 | 45197 | 45197 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY95. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ECU | SEV | 16 | PRP | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 56745 | 0 | 56745 | 56745 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY97. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | ECU | SEV | 21 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Ongoing. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | LAC | ECU | SEV | 04 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 40386 | -22201 | 18185 | 18185 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector for cut flowers and tobacco |  | LAC | ECU | FUM | 24 | PRP | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam, refrigeration and halon sectors |  | LAC | ECU | SEV | 24 | PRP | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-31 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 49000 | 0 | 49000 | 49000 | 100% | 0 | 0 |  | 6370 | 0 | 6370 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | Individual | LAC | ECU | FUM | 26 | TAS | 23 | N | O | I | MBR | 15 | 0 | 0 | 0 | 1998-11-01 | 2003-12-01 | 2005-11-01 | 2006-11-01 |  |  | 244244 | 0 | 244244 | 161075.75 | 65.95% | 83168.25 | 83168.25 | 83168.25 | 31751.72 | 0 | 20939.84 | 10811.88 | 10811.88 | Main activity remaining is development of a compendium of MB alternatives currently available. Publication will include results of field tests and lab results analyzed at ESPE, results of an intl seminar carried out in Jul. 05 and intl experience with MB alternatives. Gov. is also interested in carrying out additional field tests in crops other than summer flowers that have been identified as MB consumers. Results from additional testing would also be included in the compendium which is expected to be finalized Nov. 06. Finally, GoE is developing a small booklet summarizing main results for summer flowers which would be distributed to unions and MB users nationwide which is expected to be completed Jun 06. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the fabrication of flexible foams by replacement with methylene chloride at an automobile and furniture component manufacturing plant belonging to Elasto S.A. | Individual | LAC | ECU | FOA | 26 | INV | 24 | N | O | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-06-01 |  | 2002-10-01 | 2002-11-01 | 187286 | 0 | 187286 | 187286 | 100% | 0 | 0 |  | 24347.18 | 0 | 24347.18 | 0 | 0 | Project successfully completed in both physical and financial terms, and total funding disbursed. PCR under preparation. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacing CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Indurama S.A. | Individual | LAC | ECU | REF | 26 | INV | 25 | N | O | I | CFC | 28.38 | 28.38 | 0 | 0 | 1998-11-01 | 2002-09-01 | 2001-06-01 |  | 2002-09-01 | 2002-09-01 | 174792 | 0 | 174792 | 174792 | 100% | 0 | 0 |  | 22722.96 | 0 | 22722.96 | 0 | 0 | ODS free production started Jun. 02. Project successfully completed in both physical and financial terms and all funds disbursed. PCR is under preparation. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Ecuatoriana de Artefactos S.A. (ECASA) | Individual | LAC | ECU | REF | 26 | INV | 26 | N | O | I | CFC | 15.73 | 15.73 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-02-01 |  | 2001-11-30 | 2002-03-01 | 188545 | 0 | 188545 | 188545 | 100% | 0 | 0 |  | 24510.85 | 0 | 24510.85 | 0 | 0 | Project successfully completed both in physical and financial terms, and all funding disbursed. PCR under preparation. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the foam and commercial refrigeration sectors |  | LAC | ECU | SEV | 27 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | LAC | ECU | SEV | 28 | INS | 28 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2001-12-01 | 2001-08-01 |  | 2004-04-01 | 2004-04-01 | 97300 | 0 | 97300 | 97300 | 100% | 0 | 0 |  | 12649 | 0 | 12649 | 0 | 0 | NOU (MICIP) activities included work on the regulatory side, seeing thru a resolution that sets up import quotas for ODS in order to comply with the Protocol's control measures and additional agreed targets with ExCom. Public awareness activities included a series of seminars in schools in different regions of the country. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector |  | LAC | ECU | FUM | 33 | PRP | 29 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-11-01 | 2001-12-01 |  | 2002-11-01 | 2002-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | MeBr phaseout plan for the rose plant nursery sector approved at the 38th ExCom. | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation of a national CFC phase-out plan |  | LAC | ECU | SEV | 36 | PRP | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | NCPP submitted and approved at the 41st ExCom. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technology change for the phase-out of methyl bromide in the rose plant nursery sector | Individual | LAC | ECU | FUM | 38 | INV | 31 | N | O | I | MBR | 37.2 | 37.2 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2005-11-01 |  | 2005-01-01 | 2005-02-01 | 597945 | 0 | 597945 | 597945 | 100% | 0 | 0 |  | 75774 | 0 | 75774 | 0 | 0 | Project completed. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: first tranche | Multiyear | LAC | ECU | PHA | 41 | INV | 32 | N | O | I | CFC | 11 | 11 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2005-04-01 |  | 777326 | 0 | 777326 | 301297.34 | 38.76% | 476028.66 | 476028.66 | 410000 | 58299.45 | 0 | 22597.3 | 35702.15 | 35702.15 | All subprojects in the NCPP are underway. During 2005, 48 refrigeration workshops from all over the country were trained on good practices in refrigeration. Equipment (2R and 3R) for each of these workshops is being procured. Customs training program started this year. Equipment for customs also being procured. A total of $280,000 in equipment have been committed. Training (chiller sector) for $70,000 and additional equipment for a CFC bank for $60,000 are in this year's plan. | [10 empty] | 2003 | INV | 235 | 143 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Extension of institutional strengthening project (phase III) | Individual | LAC | ECU | SEV | 42 | INS | 33 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2006-04-01 | 2006-04-01 |  |  | 176800 | 0 | 176800 | 72554.37 | 41.04% | 104245.63 | 104245.63 | 104245 | 13260 | 0 | 5441.57 | 7818.43 | 7818.43 | Public awareness campaigns still underway, including participation in Ozone Day, the children's 2nd National Paint Contest (children from all 22 provinces participated), seminars in highschools in Quito, as well as the release of brochures and technical sheets on ozone depletion. In addition, a training course on ozone depletion was carried out for the 22 Provincial Environmental and Road Education Chiefs. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of a methyl bromide project |  | LAC | ECU | FUM | 45 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-12-01 | 2006-11-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 25000 | 25000 | 1875 | 0 | 0 | 1875 | 1875 | A report on MB use in Ecuador will be finished in Jan 06. It will be the basis for the new MB project which is expected to be presented to the 49 ExCom. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of a TCA phase-out project |  | LAC | ECU | SOL | 45 | PRP | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-12-01 | 2006-07-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 20000 | 1500 | 0 | 0 | 1500 | 1500 | Seminar on solvents will be carried out Jan 06 which will be the basis of the TCA phase-out project. Results will be evaluated thereafter. TCA phase-out project is expected to be presented at the 49th ExCom. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | LAC | ECU | PHA | 45 | INV | 36 | N | O | I | CFC | 85 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-11-01 |  |  | 439319 | 0 | 439319 | 0 | 0% | 439319 | 439319 | 300000 | 32349 | 0 | 0 | 32349 | 32349 | Second phase of Training and Certification of refrigeration technicians started and expected to be completed in 2006 as well as the subcomponent on chillers and IS and monitoring. 2006 AP will be presented to the 49th ExCom. | [10 empty] | 2005 | INV | 150 | 133 | 0 | 0 | Yes | No | No
FIN | IBRD | Country programme preparation | Individual | AFR | EGY | SEV | 04 | CPG | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 68981 | 28539 | 97520 | 97520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | EGY | SEV | 06 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 227827 | -219155 | 8672 | 8672 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of refrigeration compressor manufacturing to HFC-134a at MISR Compressors Manufacturing Co. (MCMC) | Individual | AFR | EGY | REF | 08 | INV | 08 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1994-03-01 |  | 1997-07-01 | 2000-11-01 | 2800000 | -950000 | 1850000 | 1850000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Savings of $250,000 to be returned to the 36th ExCom. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | EGY | SEV | 09 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112200 | -69976 | 42224 | 42224 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the commercial and industrial refrigeration (1994) |  | AFR | EGY | REF | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | -18884 | 6116 | 6116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | AFR | EGY | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1995) |  | AFR | EGY | SEV | 16 | PRP | 47 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 65623 | 0 | 65623 | 65623 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The reconnaissance mission reported that the scope of refrigeration-sector projects would be limited to recovery and recycling activities. Project identification was then undertaken. This activity is now completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | EGY | SEV | 04 | PRP | 65 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 131065 | -51944 | 79121 | 79121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | AFR | GHA | SEV | 04 | PRP | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 29362 | -11448 | 17914 | 17914 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 320000 | -34564 | 285436 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1347550 | -396573 | 950977 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Global refrigeration project | Individual | GLO | GLO | REF | 08 | TAS | 29 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 60000 | -6681 | 53319 | 53319 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The original Global Refrigeration project is completed. The final activity, the preparation of a template for the domestic refrigeration sector utilizing hydrocarbon refrigerant, has been completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Global solvent project |  | GLO | GLO | SOL | 08 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 260000 | 21754 | 281754 | 281754 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is completed Final report to be issued shortly. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1993) |  | GLO | GLO | SEV | 09 | PRP | 38 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1995-03-01 |  |  | 1993-12-01 | 455000 | -455000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 43 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1179000 | -309745 | 869355 | -100 | -100 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Global aerosol project | Individual | GLO | GLO | ARS | 10 | TAS | 44 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-12-01 |  | 1995-12-01 | 1995-12-01 | 350000 | -196423 | 153577 | 153577 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Global Aerosol Phase I report has been received and is under consideration. It is most likely that the Phase II component will be implemented by UNEP. Discussions have been initiated. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 52 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1418963 | -47607 | 1371356 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | SOL | 12 | PRP | 64 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | REF | 12 | PRP | 65 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | ARS | 12 | PRP | 66 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 349931 | -349931 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | OORG workshops and meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 92 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 183399 | 0 | 183399 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | IFC concessional financing study |  | GLO | GLO | SEV | 21 | PRP | 117 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Initial work programme for 1991 | Individual | GLO | GLO | SEV | 04 | TAS | 135 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 500000 | -500000 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Advance for project preparation as indicated in the 1998 business plan |  | GLO | GLO | SEV | 23 | PRP | 149 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 1998-12-01 | 275600 | -275600 | 0 | 0 |  | 0 | 0 |  | 35828 | -35828 | 0 | 0 | 0 | The resources allocated for this project were granted to The World Bank as an advance for project preparation for the Year 1998. During the 24th meeting the resources were taken out of the total project prepartion approvals. To indicate this transaction a negative entry with the same ID is created in 24th meeting. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation advance |  | GLO | GLO | SEV | 26 | PRP | 177 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-03-31 | 1999-12-01 |  | 2000-12-01 | 1999-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Unallocated project preparation funds |  | GLO | GLO | SEV | 27 | PRP | 185 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 162000 | 0 | 162000 | 162000 | 100% | 0 | 0 |  | 21060 | 0 | 21060 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation advance for 2000 |  | GLO | GLO | SEV | 29 | PRP | 191 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2000-03-01 | 357450 | -357450 | 0 | 0 |  | 0 | 0 |  | 46468.5 | -46468.5 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation (unallocated) |  | GLO | GLO | SEV | 30 | PRP | 203 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 212 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1450646 | 0 | 1450646 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation advance (2002) |  | GLO | GLO | SEV | 35 | PRP | 235 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2001-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 | [11 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Unallocated project preparation |  | GLO | GLO | SEV | 36 | PRP | 239 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2002-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 | [11 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Core unit (2003) |  | GLO | GLO | SEV | 38 | TAS | 245 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included support/travel of core staff; annual FI workshop and OORG meeting; attendance at ExCom and interagency mtgs; 15th MOP and UNEP regional meetings; and publication of MP case study and flyer. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Core unit (2004) |  | GLO | GLO | SEV | 41 | TAS | 251 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of three MP events and development of select knowledge material. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Core unit (2005) |  | GLO | GLO | SEV | 44 | TAS | 261 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the chiller sector and organization of a workshop |  | GLO | GLO | REF | 46 | PRP | 267 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2005-11-01 | 2005-11-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Chiller Workshop held Sep 05. Findings were used as a basis for development of IA chiller projects, including the Bank's Global Chiller Project. The Global Chiller Project was submitted for ExCom consideration in Nov 05 and US$6.88 million was approved out of the $15 million window. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Global chiller replacement project (China, India, Indonesia, Malaysia and Philippines) | Individual | GLO | GLO | REF | 47 | DEM | 268 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2013-12-01 | 2013-12-01 |  |  | 6884612 | 0 | 6884612 | 0 | 0% | 6884612 | 6884612 | 200000 | 516346 | 0 | 0 | 516346 | 516346 | Newly approved project at the end of 2005. Efforts to mobilize additional resources from GEF and carbon finance are planned for 2006. Country-specific implementation arrangements in priority countries (China, India, Malaysia, Philippines, Indonesia, Jordan & Tunisia) will commence in 2006. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Core unit budget (2006) |  | GLO | GLO | SEV | 47 | TAS | 273 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 0 | 1500000 | 1500000 | Activities will include travel to MP-related meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | GUA | SEV | 08 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 25000 | -13641 | 11359 | 11359 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | GUA | SEV | 09 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 47000 | -13488 | 33512 | 33512 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | GUA | SEV | 12 | PRP | 06 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 55000 | -47098 | 7902 | 7902 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 54000 | -12931 | 41069 | 41069 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation advance I (1993) |  | ASP | IDS | SEV | 09 | PRP | 03 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. 14 subproject proposals were prepared. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | IDS | SEV | 09 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 206000 | 1805 | 207805 | 207805 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11/12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Tulus Bakti Sempurna | Individual | ASP | IDS | FOA | 11 | INV | 07 | N | O | I | CFC | 95 | 95 | 0 | 0 | 1993-11-01 | 1997-01-01 | 1994-11-01 |  | 1998-09-01 | 1998-12-01 | 416000 | -22725 | 393275 | 393275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Intitri Muliatama | Individual | ASP | IDS | FOA | 11 | INV | 08 | N | O | I | CFC | 119 | 119 | 0 | 0 | 1993-11-01 | 1996-12-01 | 1994-11-01 |  | 1998-09-01 | 1998-09-01 | 387000 | -62963 | 324037 | 324037 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Dasa Windu Agung | Individual | ASP | IDS | FOA | 11 | INV | 09 | N | O | I | CFC | 122 | 122 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1995-04-01 |  | 1998-08-01 | 1998-08-01 | 1733000 | 0 | 1733000 | 1733000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Run commercially. Technical audit had been completed and equipment disposal had been carried out. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Safety and technical programme to assist manufacturers of hydrocarbon propelled aerosol products | Individual | ASP | IDS | ARS | 11 | TAS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-07-01 | 1995-11-01 |  | 1998-11-01 | 1998-11-01 | 238000 | -18915 | 219085 | 219085 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities on Work program had been completed. Technical audit has been carried out. Draft PCR has been submitted. Remaining grant returned to trust fund. Project completed and closed. 3% agency fee incl. |  |  | 1997-06-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance programme for small CFC users in the flexible polyurethane foam sector | Individual | ASP | IDS | FOA | 11 | TAS | 11 | N | O | I | CFC | 100 | 286 | 0 | 0 | 1993-11-01 | 1996-11-01 | 1995-11-01 |  | 1998-05-01 | 1998-05-01 | 1600000 | -1987 | 1598013 | 1598013 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project technically and financial completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Foamindo Industri Uretan | Individual | ASP | IDS | FOA | 11 | INV | 12 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1993-11-01 | 1998-01-01 | 1994-11-01 |  | 2002-04-01 | 2002-04-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in Apr. 02. Draft PCR submitted to WB for review. |  |  | 1997-12-01 |  | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Completion of processing of investment projects approved at the 11th ExCom Meeting |  | ASP | IDS | SEV | 12 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 128899 | 43396 | 172295 | 172295 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation and processing complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IDS | SEV | 12 | TRA | 14 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-07-01 | 1995-03-01 |  | 1998-08-01 | 1998-08-01 | 50000 | -701 | 49299 | 49299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TA Uppindo project is closed. PCR submitted. 3% agency fee incl. |  |  | 1997-12-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IDS | SEV | 12 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-30 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 117312 | -81569 | 35743 | 35743 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Erlangga Trimanunggal Kusumah | Individual | ASP | IDS | FOA | 13 | INV | 16 | N | O | I | CFC | 100 | 100 | 0 | 0 | 1994-07-01 | 1997-10-01 | 1995-07-01 |  | 2002-04-01 | 2002-04-01 | 379000 | 0 | 379000 | 379000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project was completed in April 2002. Draft PCR has been submitted to WB for review. |  |  | 1997-12-01 |  | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out investment project preparation (1994) |  | ASP | IDS | SEV | 13 | PRP | 17 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-08 | 1996-08-01 |  | 1996-08-01 | 1996-08-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Royal Abadi Sejahtera | Individual | ASP | IDS | FOA | 13 | INV | 18 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-06-01 | 1997-06-01 | 237500 | -3846 | 233654 | 233654 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Positive Foam Industry | Individual | ASP | IDS | FOA | 15 | INV | 19 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1994-12-01 | 1997-10-01 | 1995-12-01 |  | 2002-04-01 | 2002-04-01 | 449000 | 0 | 449000 | 449000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in April 2002. Draft PCR had been submitted to WB for review. |  |  | 1997-12-01 |  | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Multi Karya Makmur | Individual | ASP | IDS | FOA | 15 | INV | 20 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 2003-06-01 | 2003-07-01 | 123700 | -768 | 122932 | 122932.14 | 100% | -0.14 | -0.14 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1997-12-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene and polystyrene foam sheet at PT Inter Foamindosentra | Individual | ASP | IDS | FOA | 15 | INV | 21 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 1998-09-01 | 2000-10-01 | 390000 | -154145 | 235855 | 235855 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. Balance returned to the MLF at the 33rd ExCom. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Sharp Yasonta, Indonesia | Individual | ASP | IDS | REF | 15 | INV | 22 | N | O | I | CFC | 172.7 | 172.7 | 0 | 0 | 1994-12-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 1998-05-01 | 346000 | 502910 | 848910 | 848910.25 | 100% | -0.25 | -0.25 |  | 0 | 78000 | 78000 | 0 | 0 | PCR has been submitted. Project is physically and financially completed. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Lippo Melco Manufacturing | Individual | ASP | IDS | REF | 15 | INV | 23 | N | O | I | CFC | 47.02 | 47.02 | 0 | 0 | 1994-12-01 | 1996-12-01 | 1998-10-01 |  | 1998-06-01 | 1999-03-01 | 382000 | 234452.23 | 616452.23 | 616452.23 | 100% | 0 | 0 |  | 0 | 32455.02 | 32455.42 | -0.4 | -0.4 | Conversion of refrigerant to 134a is finished. Technical audit done on Feb. '98. Completed ODS phaseout in Jun. '98. Disposal plan was carried out in Nov. 19, '98. IOC has been disbursed. Project is technically and financially closed. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the manufacturing of household refrigerators at P.T. Sanyo Industries Indonesia, Jakarta | Individual | ASP | IDS | REF | 15 | INV | 26 | N | O | I | CFC | 72.3 | 72.3 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1998-12-01 |  | 1998-03-01 | 1998-12-01 | 558000 | -30847.24 | 527152.76 | 527152.76 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project is completed. PCR had been submitted, project is closed. Unused funds returned to 32nd meeting. 3% agency fee incl. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination in production of halon-1211 fire protection extinguishers at Dahlia Cahaya, Bayu Sentosa Agung and Chubb Lips | Individual | ASP | IDS | HAL | 15 | INV | 27 | N | O | I | HAL | 465 | 682.4 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1995-12-01 |  | 1997-11-01 | 1997-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PCR has been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Reduction of CFC-12 emission during service of MAC by use of recycling equipment | Individual | ASP | IDS | REF | 15 | TAS | 29 | N | O | I | CFC | 41 | 41 | 0 | 0 | 1994-12-01 | 2000-03-01 | 1996-12-01 |  | 2002-04-01 | 2002-04-01 | 327000 | -51593.01 | 275406.99 | 275406.99 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Draft PCR submitted to the Bank. Savings are to be returned to the MLF. |  |  | 1997-12-01 | 2000-01-01 | 2001-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Musimassejahtera Abadi | Individual | ASP | IDS | FOA | 15 | INV | 30 | N | O | I | CFC | 114 | 50 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  |  | 2000-12-01 | 390000 | -356351 | 33649 | 33649 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled at 31st meeting and $154,145 returned at the 32nd meeting. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IDS | SEV | 16 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 108824 | 0 | 108824 | 108824 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. Topjaya Antariksa Electronics | Individual | ASP | IDS | REF | 18 | INV | 36 | N | O | I | CFC | 51 | 69 | 0 | 0 | 1995-11-01 | 1996-11-01 | 2002-12-02 |  | 1998-05-01 | 2000-02-01 | 702000 | -2674 | 699326 | 699326 | 100% | 0 | 0 |  | 91260 | -347 | 90913 | 0 | 0 | Project is completed. PCR has been submitted. Unused fund is returned to 32nd Ex.Com. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. National Gobel (Nabel) | Individual | ASP | IDS | REF | 18 | INV | 37 | N | O | I | CFC | 90 | 100.57 | 0 | 0 | 1995-11-01 | 1996-07-01 | 2000-12-01 |  | 1998-03-01 | 2000-03-01 | 856500 | 0 | 856500 | 856500 | 100% | 0 | 0 |  | 111345 | 0 | 111345 | 0 | 0 | Project is completed. PCR has been submitted. |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning processes from 1.1.1 TCA to aqueous cleaning at PT INTI (Industri Telekomunikasi Indonesia) | Individual | ASP | IDS | SOL | 18 | INV | 38 | N | O | I | TCA | 0.97 | 1 | 0 | 0 | 1995-11-01 | 1996-07-01 | 1996-11-01 |  | 1996-06-01 | 1996-08-01 | 37380 | 0 | 37380 | 37380 | 100% | 0 | 0 |  | 4859.4 | 0 | 4859.4 | 0 | 0 | Project is completed and closed. PCR submitted. |  |  | 1996-08-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Garuda Indonesia | Individual | ASP | IDS | SOL | 18 | INV | 39 | N | O | I | TCA | 0.86 | 2.67 | 0 | 0 | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-11-01 | 1998-11-01 | 33264 | -169 | 33095 | 33095 | 100% | 0 | 0 |  | 4324.32 | -21.97 | 4302.35 | 0 | 0 | The project is completed. Technical audit has been done with satisfactory result. PCR had been submitted. Project is closed. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Markindo Theco | Individual | ASP | IDS | SOL | 18 | INV | 40 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 1999-03-01 | 83200 | -83200 | 0 | 0 |  | 0 | 0 |  | 10816 | -10816 | 0 | 0 | 0 | CANCELLED. Funds returned to 27th meeting. |  |  | 1997-12-01 | 1996-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 18 | PRP | 42 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene foam sheet at PT. Toha Kencana Mas | Individual | ASP | IDS | FOA | 20 | INV | 45 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-10-01 |  |  | 1999-07-01 | 109930 | -109930 | 0 | 0 |  | 0 | 0 |  | 14290.9 | -14291 | 0 | -0.1 | -0.1 | Project is cancelled. Funds returned to 28th meeting. |  |  | 1997-12-01 | 1997-10-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Goldstar Astra Electronics (GSA) | Individual | ASP | IDS | REF | 20 | INV | 48 | N | O | I | CFC | 38.1 | 35.04 | 0 | 0 | 1996-10-01 | 1998-02-01 | 1999-04-01 |  | 1999-12-01 | 2001-03-01 | 512730 | -163820 | 348910 | 348910.32 | 100% | -0.32 | -0.32 |  | 66654.9 | -21297 | 45358 | -0.1 | -0.1 | Project is technically and financially closed. IOC has been disbursed. Balance returned to the MLF at the 35th ExCom. |  |  | 1999-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at PT Cahaya Biru Sakti | Individual | ASP | IDS | SOL | 20 | INV | 50 | N | O | I | TCA | 18.2 | 18.2 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1998-06-01 | 2000-10-01 | 700700 | -125383 | 575317 | 575317 | 100% | 0 | 0 |  | 91091 | -16299.79 | 74791.21 | 0 | 0 | Project completed and PCR submitted Jan. 01. |  |  | 1997-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of tobacco expansion process from CFC-11 to carbon dioxide at PT Hanjaya Mandal Sampoerna and P.T. Djarum | Individual | ASP | IDS | OTH | 21 | INV | 51 | N | O | I | CFC | 90 | 54 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1999-02-01 |  | 1997-06-01 | 1998-08-01 | 1214000 | -607000 | 607000 | 607000 | 100% | 0 | 0 |  | 157820 | -78910 | 78910 | 0 | 0 | PT Sampoerna - grant was fully disbursed. Completed technical audit and disposal plan. PCR has been submitted and project is closed. PT Djarum - steam-based technology proposed was refused, project cancelled. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Samsung Maspion Indonesia (SMI) | Individual | ASP | IDS | REF | 21 | INV | 52 | N | O | I | CFC | 104.3 | 98.24 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1999-08-01 |  | 2001-10-01 | 2001-11-01 | 537226 | -320243 | 216983 | 216983 | 100% | 0 | 0 |  | 69839.38 | -41632 | 28206.97 | 0.41 | 0.41 | Enterprise decided not to proceed to c-pentane due to current unfavorable economic conditions causing a high upfront investment costs for technology, and stopped at HCFC-141b. Disposal of old equipment done and IOC disbursed. Unused funds returned to the MLF at 35th and 36th Meetings. PCR under preparation. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 21 | PRP | 55 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 179000 | -150000 | 29000 | 29000 | 100% | 0 | 0 |  | 23270 | -19500 | 3770 | 0 | 0 | For IDS/SEV/21/PRP/55 $179,000 was approved of which $29,000 was expensed, and the remaining $150,000 was transferred to Indonesia PPA III. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | Individual | ASP | IDS | ARS | 22 | INV | 61 | N | O | I | CFC | 460 | 460 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1999-06-01 |  | 2005-05-01 | 2004-10-01 | 1175340 | 0 | 1175340 | 1175340 | 100% | 0 | 0 |  | 152794 | 0 | 152794 | 0 | 0 | Project financially and physically completed. |  |  |  | 2000-06-01 |  | 2002-06-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IDS | SEV | 16 | PRP | 62 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 50000 | -32695 | 17305 | 17305 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Maspion | Individual | ASP | IDS | REF | 23 | INV | 72 | N | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2000-11-01 | 136890 | -11703 | 125187 | 125187.38 | 100% | -0.38 | -0.38 |  | 17796 | -1521.39 | 16274.31 | 0.3 | 0.3 | Project completed. Disposal of old equipment has been carried out. PCR will be submitted January 2001. Project is closed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polethylene foam sheet at PT. Tara Guna Foam | Individual | ASP | IDS | FOA | 23 | INV | 73 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1997-11-01 | 2001-10-01 | 1999-12-01 |  | 2001-12-01 | 2002-10-01 | 287700 | -34630.97 | 253069.03 | 253069.03 | 100% | 0 | 0 |  | 37401 | -4502.03 | 32898.97 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  |  | 2001-02-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Porkka Indonesia | Individual | ASP | IDS | REF | 23 | INV | 74 | N | O | I | CFC | 3.96 | 3.96 | 0 | 0 | 1997-11-01 | 2000-10-01 | 1999-12-01 |  | 1998-08-01 | 2001-03-01 | 58517 | -9377 | 49140 | 49140 | 100% | 0 | 0 |  | 7607 | -1219.01 | 6387.99 | 0 | 0 | Project completed and PCR to be submitted Mar. 02. Savings returned to the 35th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT. Irc Inoac Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 75 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2003-04-01 | 412900 | -412900 | 0 | 0 |  | 0 | 0 |  | 53677 | -53677 | 0 | 0 | 0 | Cancelled - 38th ExCom | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT Sea Horse Maspion Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 76 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 532200 | -532200 | 0 | 0 |  | 0 | 0 |  | 69186 | -63864 | 5322 | 0 | 0 | Project cancelled at the 35th ExCom and funds to be returned at the 36th ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 77 | N | O | I | CFC | 954 | 954 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 | 2006-05-01 |  |  | 4060640 | 0 | 4060640 | 3578955.28 | 88.14% | 481684.72 | 481684.72 | 10000 | 527883 | 0 | 465264.01 | 62618.99 | 62618.99 | IOC receipts submitted by enterprises to State Ministry of the Environment(KLH)and FI. 2nd and last batch of equipment (24 units) delivered, installed and commissioned with exception of one company. Commissioning started Apr 05 and completed Aug 05. One enterprise had a fire which caused damage to equipment before installation. Issue will be addressed by KLH by Apr. 06. WB technical audit in progress. Disposal of baseline equipment is on-going with 28 beneficiaries completing equipment disposal. 100% completion of equipment disposal is planned by Apr 06. No more CFC in use. |  |  |  |  | 2001-02-01 | 2002-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance programme for SMEs for flexible polyurethane foam at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 78 | N | O | I | CFC | 370 | 370 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2005-04-01 | 2005-12-01 | 3538400 | 0 | 3538400 | 1554876.04 | 43.94% | 1983523.96 | 0 |  | 459992 | 0 | 202133.88 | 257858.12 | 0 | Project completed. |  |  |  |  | 2001-02-01 | 2002-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of commercial refrigeration units at PT Wahana Derby Sejati | Individual | ASP | IDS | REF | 23 | INV | 79 | N | O | I | CFC | 10.28 | 10.28 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1997-11-01 | 1998-07-01 | 139233 | -77613 | 61620 | 61620 | 100% | 0 | 0 |  | 18100 | -10089.69 | 8010.31 | 0 | 0 | Project completed, PCR submitted Mar. 99 and balance returned to the 32nd ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the halon recycling sector |  | ASP | IDS | HAL | 24 | PRP | 85 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | IDS | HAL | 27 | TAS | 107 | N | O | I | HAL | 972 | 0 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2003-04-01 | 2006-12-01 |  |  | 486200 | 0 | 486200 | 360414.42 | 74.13% | 125785.58 | 125785.58 | 112670 | 63206 | 0 | 46853.87 | 16352.13 | 16352.13 | Focus of activities are on addressing essential users, fire authorities and fire equipment industry. Process for hiring consultant to develop Standard Operating and Procedures and mapping /db system on Halon Banking operations completed but SOP not in place. Only one quotation received for digital balance procurement although 4 companies invited to bid. Balance is needed to handle lager cylinders and meet accuracy requirements for the aviation sector. Retendering scheduled for Apr 06. Halon Advisory Panel meeting held Oct 05 to discuss among others, categorizing halon for essential/ critical use, listing of interim critical use and strategizing on halon mgmt, including to develop a halon regulation. Bank has not recieved more halon due to insufficient storage facilities which are being upgraded and procurement of new storage cylinder completed. GMF and KLH to commence prepararation of regulation mandating use of recycled halon in 2006. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam sector |  | ASP | IDS | FOA | 27 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at CV Sumber Logam | Individual | ASP | IDS | FOA | 29 | INV | 111 | N | O | I | CFC | 12.1 | 12.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2001-12-01 | 2002-05-01 | 56118 | -30157 | 25961 | 25961 | 100% | 0 | 0 |  | 7295.34 | -3920.41 | 3374.93 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at PT Sentra Sukses Selalu | Individual | ASP | IDS | FOA | 29 | INV | 115 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-04-01 | 539579 | -539579 | 0 | 0 |  | 0 | 0 |  | 69353.69 | -69353.69 | 0 | 0 | 0 | Cancelled - 38th ExCom | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (boxfoam and sprayfoam) at PT Intimas Chemindo | Individual | ASP | IDS | FOA | 29 | INV | 116 | N | O | I | CFC | 74.3 | 74.3 | 0 | 0 | 1999-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-03-01 | 2004-09-01 | 290294 | -163063.56 | 127230.44 | 127230.44 | 100% | 0 | 0 |  | 37738.22 | -21198.04 | 16539.96 | 0.22 | 0.22 | Project technically and financially completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at PT Dawamiba Engineering | Individual | ASP | IDS | FOA | 29 | INV | 117 | N | O | I | CFC | 31.6 | 31.6 | 0 | 0 | 1999-11-01 | 2001-11-01 | 2002-12-01 |  | 2003-06-01 | 2003-10-01 | 156500 | -2750 | 153750 | 153750 | 100% | 0 | 0 |  | 20345 | -357.5 | 19987.5 | 0 | 0 | Project technically and financially completed. PCR draft being finalized. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at Kimura Fiberglass | Individual | ASP | IDS | FOA | 29 | INV | 118 | N | O | I | CFC | 21.1 | 21.1 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2001-12-01 | 2002-07-01 | 69385 | -36556.41 | 32828.59 | 32828.59 | 100% | 0 | 0 |  | 9020.05 | -4752.34 | 4267.71 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to water based technology and LCD technology in the manufacture of flexible moulded foam and to HCFC-141b in the manufacture of molded integral skin polyurethane foam at Anto Indo Foam | Individual | ASP | IDS | FOA | 31 | INV | 120 | N | O | I | CFC | 51.75 | 51.75 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-03-01 | 2003-10-01 | 249645 | -244 | 249401 | 249400.86 | 100% | 0.14 | 0.14 |  | 32453.85 | -32 | 32422.11 | -0.26 | -0.26 | Project technically and financially completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for 3 projects in the foam sector and one in the refrigeration sector |  | ASP | IDS | SEV | 33 | PRP | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (steel door) at PT Bostinco | Individual | ASP | IDS | FOA | 35 | INV | 127 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-01-01 |  | 2003-10-01 | 2004-05-01 | 88479 | 0 | 88479 | 88479 | 100% | 0 | 0 |  | 11502.27 | 0 | 11502.27 | 0 | 0 | Project physically and financially completed. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (cooler box products) at Dua Roda Industrial Co. | Individual | ASP | IDS | FOA | 35 | INV | 128 | N | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-05-01 | 2003-10-01 | 52457 | -5800 | 46657 | 46657 | 100% | 0 | 0 |  | 6819.41 | -754 | 6065.41 | 0 | 0 | Project physically and financially completed. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | Individual | ASP | IDS | FOA | 35 | INV | 129 | N | O | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2004-10-01 |  | 2005-12-01 | 2005-12-01 | 165201 | 0 | 165201 | 144690.56 | 87.58% | 20510.44 | 0 |  | 21476.13 | 0 | 18809.77 | 2666.36 | 0 | Project financially and technically completed. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (house ware products) at PT Maspion Plastic and Metal Industry | Individual | ASP | IDS | FOA | 35 | INV | 130 | N | O | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-11-01 | 2004-09-01 | 141723 | 0 | 141723 | 141723 | 100% | 0 | 0 |  | 18423.99 | 0 | 18423.99 | 0 | 0 | Project physically and financially completed | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of two sector plans in the aerosol sector and in the foam sector |  | ASP | IDS | SEV | 36 | PRP | 142 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Foam and aerosol proposals prepared and submitted to Excom. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Strengthening of import/export control | Individual | ASP | IDS | SEV | 37 | TAS | 149 | N | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2004-08-01 | 2006-12-01 |  |  | 110000 | 0 | 110000 | 106000 | 96.36% | 4000 | 4000 | 4000 | 14300 | 0 | 13780 | 520 | 520 | An MOU between Ministry of Environment and Customs was signed Dec 05 aiming at strengthening control of ODS arriving in the country. Advance draft of regulation on ODS control to amend Decree 789/MPP/KEP/12/2002 will be submitted to Ministry of Industry at inter-agency meeting to be held Feb 06. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | IBRD | Refrigeration sector phase-out plan: MAC servicing sector | Multiyear | ASP | IDS | REF | 38 | INV | 153 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 1369800 | 0 | 1369800 | 1369800 | 100% | 0 | 0 |  | 121962 | 0 | 121962 | 0 | 0 | 2003 annual plan completed successfully. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector phase-out plan for elimination of CFCs in the refrigeration (MAC servicing) sector: 2004 annual programme | Multiyear | ASP | IDS | REF | 41 | INV | 156 | N | O | I | CFC | 110 | 110 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 |  | 1347300 | 0 | 1347300 | 955240.91 | 70.9% | 392059.09 | 392059.09 | 392059.09 | 119937 | 0 | 85035.79 | 34901.21 | 34901.21 | 2004 annual plan completed sucessfully. | [10 empty] | 2003 | INV | 695 | 695 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Phase-out of residual CFCs in the foam sector (advancement) | Multiyear | ASP | IDS | FOA | 42 | INV | 160 | N | O | I | CFC | 130 | 130 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 |  | 100000 | 1625000 | 1725000 | 744060.38 | 43.13% | 980939.62 | 980939.62 | 980939.62 | 7500 | 121875 | 856 | 128519 | 128519 | 2005 consumption reduction target has been met. | [10 empty] | 2003 | INV | 222.2 | 222 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (third tranche) | Multiyear | ASP | IDS | REF | 44 | INV | 165 | N | O | I | CFC | 110 | 110 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 |  | 1347300 | 0 | 1347300 | 0 | 0% | 1347300 | 1347300 | 400000 | 119937 | 0 | 0 | 119937 | 119937 | 2005 consumption reduction target was achieved. | [10 empty] | 2004 | INV | 585 | 585 | 0 | 0 | Yes | No | No
ONG | IBRD | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives | Individual | ASP | IDS | ARS | 44 | INV | 166 | N | O | I | CFC | 70 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-05-01 | 2008-05-01 |  |  | 371910 | 0 | 371910 | 2000 | 0.5378% | 369910 | 369910 | 89600 | 27893 | 0 | 149.99 | 27743.01 | 27743.01 | Work plan and procurement plan completed. Local consultant has been hired to revalidate information provided by the enterprises in the project document. Revalidation work is on-going. | [10 empty] | 2003 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Project preparation funds for the development of a phase-out plan for the MDI sector |  | ASP | IDS | PHA | 46 | PRP | 170 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 |  | 2006-07-01 | 2006-07-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 45000 | 45000 | 3375 | 0 | 0 | 3375 | 3375 | Project preparation activities underway to meet targeted submission date (49th ExCom). | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies |  | ASP | IND | SEV | 09 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 400000 | 11292 | 411292 | 411292 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 refrigerant by HCFC-123 in centrifugal chillers (Blue Star) | Individual | ASP | IND | REF | 10 | INV | 08 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1993-06-01 | 1995-07-01 | 1996-06-01 |  | 1997-12-01 | 1997-12-01 | 567000 | -146504 | 420496 | 420496 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Shriram Industries | Individual | ASP | IND | REF | 10 | INV | 09 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 1997-07-01 | 685000 | -309549 | 375451 | 375451 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aero Pharma aerosol conversion | Individual | ASP | IND | ARS | 11 | INV | 10 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1993-11-01 | 1996-08-01 | 1994-11-01 |  | 2000-10-01 | 1998-06-01 | 62520 | 0 | 62520 | 62520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | No change in previous status |  |  | 1997-03-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Modification of CFC-12 MAC manufacturing for HFC-134a at Subros Ltd. | Individual | ASP | IND | REF | 11 | INV | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1995-11-01 |  | 1998-11-01 | 2003-05-01 | 1710000 | -55496 | 1654504 | 1654504 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at UB Petroproducts Ltd. | Individual | ASP | IND | FOA | 11 | INV | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1999-02-01 | 1996-11-01 |  | 1999-08-01 | 2000-08-01 | 200000 | 291817 | 491817 | 491817.37 | 100% | -0.37 | -0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-04-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at Manali Petrochemical Ltd. | Individual | ASP | IND | FOA | 11 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1997-02-01 | 1996-11-01 |  | 1998-01-01 | 2000-08-01 | 219000 | 211348 | 430348 | 430347.63 | 100% | 0.37 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-04-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor designs for refrigeration and appliances from CFC-12 to HFC-134a at Kirloskar Copeland Ltd. | Individual | ASP | IND | REF | 12 | INV | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1998-03-01 |  | 1999-03-01 | 1999-11-01 | 547900 | -16905 | 530995 | 530994.85 | 100% | 0.15 | 0.15 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-03-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IND | SEV | 12 | PRP | 20 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-12-31 | 1994-12-01 |  | 1996-12-01 | 1996-12-01 | 430000 | -241165 | 188835 | 188835 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects for India ODS II (1994) |  | ASP | IND | SEV | 12 | PRP | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 70837 | -6037 | 64800 | 64800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IND | SEV | 12 | TRA | 22 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-03-01 | 1995-03-01 | 345000 | -239292 | 105708 | 105708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation advance of $345,000 to IDBI has been cleared by the Bank to support the preparation of subprojects to be processed thru the umbrella grant agreement. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 as blowing agent in polyurethane foam systems with low and non-ODS materials at Expanded Incorporation | Individual | ASP | IND | FOA | 13 | INV | 23 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1997-04-01 | 1998-07-01 |  | 2000-09-01 | 2000-09-01 | 502130 | -8064 | 494066 | 494066 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 open-type compressor designs for use with HCFC-22 refrigerant at Freezeking Industries Pvt., Ltd. | Individual | ASP | IND | REF | 13 | INV | 24 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1997-07-01 |  | 1999-11-01 | 2000-12-01 | 240500 | -25806 | 214694 | 214694.04 | 100% | -0.04 | -0.04 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase-out in sterilization and siliconisation of disposable syringes and needle at Hindustan Syringes and Medical Devices Private Ltd., Haryana | Individual | ASP | IND | SOL | 13 | INV | 26 | N | O | I | CFC | 53.2 | 56 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1996-12-01 | 1998-09-01 | 481000 | -22298 | 458702 | 458702 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | IND | SEV | 16 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 24065 | 0 | 24065 | 24065 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IND | SEV | 16 | PRP | 33 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 355246 | 0 | 355246 | 355246 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible slabstock PUF at Duroflex Coir Industries P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 34 | N | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1997-01-01 |  | 1997-08-01 | 1998-03-01 | 100800 | -7422 | 93378 | 93378 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF at Industrial Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 35 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1997-08-01 | 1997-06-01 | 320000 | -9500 | 310500 | 310500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Arts (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 36 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-05-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Ashish Plastics P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 37 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible polyurtehane foams at Karnataka Consumer Products Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 38 | N | O | I | CFC | 27 | 27 | 0 | 0 | 1995-07-01 | 1999-06-01 | 1997-01-01 |  | 2000-03-01 | 2001-07-01 | 253200 | -103341 | 149859 | 149859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1998-12-01 | 1999-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of moulded PUF at Madras Polymoulds (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 39 | N | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1997-10-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 167700 | -57255 | 110445 | 110445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-12-01 | 1999-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Plastics Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 40 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 456500 | -81683 | 374817 | 374817 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Polyplas (India) Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 41 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 236000 | -52332 | 183668 | 183668 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Panorama Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 42 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Polynate Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 43 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-02-01 | 2001-10-01 | 278000 | -1057 | 276943 | 276943 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | 1999-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Sree Precoated Steels Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 44 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1997-01-01 |  |  | 1999-11-01 | 224000 | -224000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled |  |  | 1998-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Vikram Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 45 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 236000 | -52312 | 183688 | 183688 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Tranquil Rubber Sales Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 46 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1998-04-01 | 2000-07-01 | 215250 | -79521 | 135729 | 135729 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Real Polymers | Individual | ASP | IND | FOA | 17 | INV | 47 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  | 1998-09-01 | 1998-07-01 | 276200 | -51275 | 224925 | 224925 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of PUF moldings at Vijayjyot Seats Ltd. | Individual | ASP | IND | FOA | 17 | INV | 48 | N | O | I | CFC | 49 | 49 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1998-09-01 | 1999-12-01 | 335500 | -25979 | 309521 | 309521 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF automotive seats at Polyflex (India) P. Ltd. | Individual | ASP | IND | FOA | 17 | INV | 49 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1998-03-01 | 1997-01-01 |  | 1998-09-01 | 2002-01-01 | 222400 | -6000 | 216400 | 216400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 17 | DEM | 50 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1995-07-01 | 181550 | -181550 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project implementation has been transferred to UNDP. |  |  | 1996-06-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Alfa Foams (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 51 | N | O | I | CFC | 19 | 19 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1997-10-01 | 2000-11-01 | 219900 | -27875 | 192025 | 192025.49 | 100% | -0.49 | -0.49 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Blue Star Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 52 | N | O | I | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1998-06-01 | 2000-12-01 | 224000 | -55898 | 168102 | 168102 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of integral skin PUF moldings at Pfeda Synthetics (P) Ltd. | Individual | ASP | IND | FOA | 18 | INV | 54 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-05-01 |  | 1998-04-01 | 1999-09-01 | 335728 | -14893 | 320835 | 320834.93 | 100% | 0.07 | 0.07 |  | 43644.64 | -1936.09 | 41708.55 | 0 | 0 | Complete. |  |  | 1997-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at Bharat Seats Ltd. | Individual | ASP | IND | FOA | 18 | INV | 55 | N | O | R | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-03-01 |  | 1993-07-01 | 1996-12-01 | 514563 | -563 | 514000 | 514000 | 100% | 0 | 0 |  | 66893.19 | -73.19 | 66820 | 0 | 0 | Complete. |  |  | 1993-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at PUR Polyurethane Products P. Ltd. | Individual | ASP | IND | FOA | 18 | INV | 56 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2002-03-01 | 2005-01-01 | 187864 | -41523 | 146341 | 146341 | 100% | 0 | 0 |  | 24422.32 | -5397.99 | 19024.33 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 1997-12-01 | 1999-02-01 | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFCs in the manufacture of extruded polyethylene foam at Kunstoff Polymers Ltd. | Individual | ASP | IND | FOA | 18 | INV | 57 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1997-02-01 | 239320 | -239320 | 0 | 0 |  | 0 | 0 |  | 31111.6 | -31111.6 | 0 | 0 | 0 | Cancelled |  |  | 1997-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Shroff Textiles Ltd. | Individual | ASP | IND | FOA | 18 | INV | 58 | N | O | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1998-05-01 | 1997-05-01 |  | 2000-06-01 | 2001-01-01 | 197200 | 0 | 197200 | 197200 | 100% | 0 | 0 |  | 25636 | 0 | 25636 | 0 | 0 | Project completed and PCR submitted |  |  | 1997-12-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of rigid PUF products at SDC Polyurethane Products Ltd. | Individual | ASP | IND | FOA | 18 | INV | 59 | N | O | I | CFC | 24 | 24 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1997-05-01 |  | 1998-06-01 | 2000-07-01 | 160971 | 0 | 160971 | 160970.73 | 100% | 0.27 | 0.27 |  | 20926.23 | 0 | 20926.19 | 0.04 | 0.04 | Project completed and PCR submitted. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from halon-1211 to ABC dry chemical power (ABC-DCP) and carbon dioxide (CO2) in portable extinguishers at Real Value Appliances Ltd. | Individual | ASP | IND | HAL | 18 | INV | 60 | N | O | I | HAL | 462 | 462 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 2003-07-01 | 251736 | -251736 | 0 | 0 |  | 0 | 0 |  | 32725.68 | -32725.68 | 0 | 0 | 0 | Project cancelled at the 39th ExCom. |  |  | 1998-06-01 |  | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Meghdoot Refrigeration Industries | Individual | ASP | IND | REF | 18 | INV | 61 | N | O | I | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-01-01 | 2000-07-01 | 164590 | -5660 | 158930 | 158929.9 | 100% | 0.1 | 0.1 |  | 21396.7 | -735.8 | 20660.9 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-08-01 | 1999-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna & Co. | Individual | ASP | IND | REF | 18 | INV | 62 | N | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-06-01 | 2001-06-01 | 147020 | -11574 | 135446 | 135446 | 100% | 0 | 0 |  | 19112.6 | -1504.62 | 17607.98 | 0 | 0 | Project completed and PCR submitted |  |  | 1997-08-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna Engineers P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 63 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2001-04-01 | 2003-10-01 | 202790 | -81830 | 120960 | 120960 | 100% | 0 | 0 |  | 26362.7 | -10637.87 | 15725.13 | -0.3 | -0.3 | Project completed. |  |  | 1997-08-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Friz-Tech P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 64 | N | O | I | CFC | 12 | 11.5 | 0 | 0 | 1995-11-01 | 1997-11-01 | 1997-05-01 |  | 2000-03-01 | 2002-07-01 | 132920 | 0 | 132920 | 132920 | 100% | 0 | 0 |  | 17279.6 | 0 | 17279.6 | 0 | 0 |  |  |  | 1997-08-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | IND | SEV | 18 | PRP | 68 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of molded PUF automotive seat cushions at Roloforms Polymer Ltd. | Individual | ASP | IND | FOA | 19 | INV | 77 | N | O | I | CFC | 26 | 26 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-03-01 | 162400 | -38657 | 123743 | 123743 | 100% | 0 | 0 |  | 21112 | -5025.41 | 16086.59 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-01-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF products at Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 84 | N | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2001-03-01 | 140190 | -26 | 140164 | 140164 | 100% | 0 | 0 |  | 18224.7 | -3.38 | 18221.32 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF for insulated thermoware at Arihant Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 85 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 146450 | -146450 | 0 | 0 |  | 0 | 0 |  | 19038.5 | -19038.5 | 0 | 0 | 0 | Cancelled. |  |  | 1998-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Plast | Individual | ASP | IND | FOA | 19 | INV | 86 | N | O | I | CFC | 21 | 21 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 141320 | -546 | 140774 | 140773.84 | 100% | 0.16 | 0.16 |  | 18372 | -70.98 | 18301.02 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 87 | N | O | I | CFC | 17.4 | 17.4 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 129420 | 0 | 129420 | 129420 | 100% | 0 | 0 |  | 16824.6 | 0 | 16824.6 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Wimco Pen Co. | Individual | ASP | IND | FOA | 19 | INV | 88 | N | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 119290 | -4225 | 115065 | 115065 | 100% | 0 | 0 |  | 15507.7 | -549.25 | 14958.45 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | 1999-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rabi-Run Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 89 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 2001-01-01 | 2002-09-01 | 142622 | -2428 | 140194 | 140194.28 | 100% | -0.28 | -0.28 |  | 18541 | -315.64 | 18225.36 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 1998-02-01 |  | 2000-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Seepra Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 90 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1998-08-01 | 1999-12-01 | 171910 | -10400 | 161510 | 161510 | 100% | 0 | 0 |  | 22348 | -1352 | 20996 | 0 | 0 | Complete. |  |  | 1998-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Shakti Fabricators | Individual | ASP | IND | REF | 19 | INV | 91 | N | O | I | CFC | 13.5 | 13.5 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 2001-11-01 | 2003-10-01 | 159230 | -926 | 158304 | 158304 | 100% | 0 | 0 |  | 20699.9 | -120.42 | 20579.58 | -0.1 | -0.1 | Project completed. |  |  | 1998-02-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Chandra Frig Co. P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 92 | N | O | I | CFC | 9.4 | 4.8 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  |  | 2004-04-01 | 130984 | -64197 | 66787 | 66787.07 | 100% | -0.07 | -0.07 |  | 17028 | -8346 | 8682.32 | -0.32 | -0.32 | Project cancelled at the 42nd ExCom and balance returned at the 43rd ExCom. Bank has requested FI to examine the SGA to find out appropriate course of action for recuperation of equipment. Process underway. |  |  | 1998-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rockwell Devices P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 93 | N | O | I | CFC | 18 | 18 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-07-01 | 2000-09-01 | 181004 | -9611 | 171393 | 171392.74 | 100% | 0.26 | 0.26 |  | 23530.52 | -1249.43 | 22281.09 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sethia Appliances P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 94 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 2000-08-01 | 173384 | -6586 | 166798 | 166798.3 | 100% | -0.3 | -0.3 |  | 22540 | -856.18 | 21683.82 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | FOA | 20 | INV | 104 | N | O | I | CFC | 568 | 568 | 0 | 0 | 1996-10-01 | 1999-01-01 | 1999-02-01 |  | 1999-07-01 | 2003-10-01 | 2691570 | -27265 | 2664305 | 2664305 | 100% | 0 | 0 |  | 349904.1 | -3544.45 | 346359.55 | 0.1 | 0.1 | Project completed. |  |  |  | 2000-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Supercold Refrigeration Systems P. Ltd. | Individual | ASP | IND | REF | 20 | INV | 105 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1996-10-01 | 2000-12-01 | 1998-04-01 |  | 2001-04-01 | 2002-05-01 | 133770 | -3495 | 130275 | 130275 | 100% | 0 | 0 |  | 17390.1 | -454.35 | 16935.75 | 0 | 0 | Enterprise has submitted the draft PCR which will be sent to the Bank by April 15, 2003. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Murali Refrigeration and Engineering Co. | Individual | ASP | IND | REF | 20 | INV | 106 | N | O | I | CFC | 9 | 9 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-04-01 |  | 1999-06-01 | 2000-10-01 | 126485 | -1539 | 124946 | 124945.52 | 100% | 0.48 | 0.48 |  | 16443.05 | -200.07 | 16242.98 | 0 | 0 | Project completed and PCR submitted | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration sector |  | ASP | IND | REF | 21 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1998-06-01 | 1998-06-01 | 243000 | 0 | 243000 | 243000 | 100% | 0 | 0 |  | 31590 | 0 | 31590 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigeration Components and Accessories | Individual | ASP | IND | REF | 22 | INV | 110 | N | O | I | CFC | 9.5 | 9.5 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 125370 | -75182.45 | 50187.55 | 50187.55 | 100% | 0 | 0 |  | 16298.1 | -9773.72 | 6524.38 | 0 | 0 | Project financially completed and balance funds returned. |  |  |  |  | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of 1,1,1 TCA from the precision cleaning processes at Modi Xerox | Individual | ASP | IND | SOL | 22 | INV | 112 | N | O | I | TCA | 6.07 | 6.07 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1998-06-01 | 1998-01-01 | 130819 | -25985 | 104834 | 104834 | 100% | 0 | 0 |  | 17006.47 | -3378.05 | 13628.42 | 0 | 0 | Complete. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Stella Industries aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 113 | N | O | I | CFC | 105 | 105 | 0 | 0 | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-09-01 | 1998-09-01 | 269175 | 0 | 269175 | 269175 | 100% | 0 | 0 |  | 34992.75 | 0 | 34992.75 | 0 | 0 | Project completed. PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Accra Pack India Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 114 | N | O | I | CFC | 52 | 52 | 0 | 0 | 1997-05-01 | 1999-02-01 | 1998-06-01 |  | 2001-07-01 | 2002-04-01 | 129690 | -7545 | 122145 | 122145 | 100% | 0 | 0 |  | 16859.7 | -980.85 | 15878.85 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  |  | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Pranav Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 116 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 2002-03-01 | 2002-12-01 | 944914 | -90669 | 854245 | 854245 | 100% | 0 | 0 |  | 122838.82 | -11786.97 | 111051.85 | 0 | 0 | Draft PCR submitted to ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | My Fair Lady aerosol conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 119 | N | O | I | CFC | 59.4 | 59.4 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1998-06-01 |  | 2000-12-01 | 2002-09-01 | 113975 | -16195 | 97780 | 97780.37 | 100% | -0.37 | -0.37 |  | 14816.75 | -2105.35 | 12711.4 | 0 | 0 | PCR finalized and submitted to ExCom. |  |  |  | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Standard Refrigeration Appliances | Individual | ASP | IND | REF | 22 | INV | 120 | N | O | I | CFC | 18.8 | 18.8 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-11-01 |  | 2000-08-01 | 2000-12-01 | 170180 | -166 | 170014 | 170014 | 100% | 0 | 0 |  | 22123.4 | -21.58 | 22101.82 | 0 | 0 | Project completed and PCR submitted | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Sanden Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 121 | N | O | I | CFC | 8.36 | 8.36 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2002-03-01 | 2002-04-01 | 490820 | -111557 | 379263 | 379263 | 100% | 0 | 0 |  | 63806.6 | -14502.41 | 49304.19 | 0 | 0 | Draft PCR submitted to the ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sheetal Engineering Works P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 122 | N | O | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-02-01 | 2001-06-01 | 127630 | -28297 | 99333 | 99333 | 100% | 0 | 0 |  | 16591.9 | -3678.61 | 12913.29 | 0 | 0 | Project completed. PCR will be submitted January 2001. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Hindustan Refrigeration Industries | Individual | ASP | IND | REF | 22 | INV | 123 | N | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 132320 | -81327 | 50993 | 50993 | 100% | 0 | 0 |  | 17201.6 | -10572.51 | 6629.09 | 0 | 0 | Project financially completed and balance funds returned. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 124 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 147300 | -95904.45 | 51395.55 | 51395.55 | 100% | 0 | 0 |  | 19149 | -12467.58 | 6681.42 | 0 | 0 | Project financially completed and balance funds returned. |  |  |  |  | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Maharaja International Ltd. | Individual | ASP | IND | REF | 22 | INV | 125 | N | O | I | CFC | 59.8 | 59.8 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-11-01 |  | 2004-01-01 | 2005-01-01 | 510000 | -261775.31 | 248224.69 | 248224.69 | 100% | 0 | 0 |  | 66300 | -34030.79 | 32269.21 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [5 empty] | 2001-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HCF-134a refrigerant at Voltas Ltd. | Individual | ASP | IND | REF | 22 | INV | 126 | N | O | I | CFC | 379.83 | 379.83 | 0 | 0 | 1997-05-01 | 2000-07-01 | 2001-12-01 |  | 2003-11-01 | 2005-01-01 | 2724378 | -1093985 | 1630393 | 1630393 | 100% | 0 | 0 |  | 354169.14 | -142218 | 211951 | 0.14 | 0.14 | Project financially completed and balance funds returned. |  |  |  | 1999-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects for submission in 1997 and 1998 |  | ASP | IND | REF | 22 | PRP | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Polar Enterprises | Individual | ASP | IND | REF | 22 | INV | 131 | N | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1999-09-01 | 2001-07-01 | 138190 | -189 | 138001 | 138001 | 100% | 0 | 0 |  | 17964.7 | -24.57 | 17940.13 | 0 | 0 | Project completed and PCR submitted | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of refrigerator manufacture to cyclopentane foam blowing agent and to HCF-134a refrigerant at Videocon Appliances Ltd. | Individual | ASP | IND | REF | 22 | INV | 134 | N | O | I | CFC | 351.7 | 351.7 | 0 | 0 | 1997-05-01 | 1999-10-01 | 1999-11-01 |  | 2001-12-01 | 2002-08-01 | 1835115 | 524053.41 | 2359168.41 | 2359168.41 | 100% | 0 | 0 |  | 238564.95 | 61500.14 | 300065.09 | 0 | 0 | Project physically completed in 2001, however, was not reported as such by FI in time for the 2001 progress report. Subsequent draft PCR has confirmed correct date of completion. |  |  |  | 1999-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Attarwala and Co. Pvt. Ltd. aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 137 | N | O | I | CFC | 30.6 | 30.6 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2002-12-01 | 2005-01-01 | 134250 | -12102 | 122148 | 122148 | 100% | 0 | 0 |  | 17452.5 | -1573.26 | 15879.24 | 0 | 0 | Project financially completed and balance funds returned to ExCom. PCR submitted. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aero Industries aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 139 | N | O | I | CFC | 27.6 | 27.6 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 1999-05-01 | 121735 | -3903 | 117832 | 117832 | 100% | 0 | 0 |  | 15825.55 | -507.39 | 15318.16 | 0 | 0 | Project completed and PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aeropres aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 141 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 2000-10-01 | 146860 | -4040 | 142820 | 142819.81 | 100% | 0.19 | 0.19 |  | 19091.8 | -525.2 | 18566.6 | 0 | 0 | Project completed and PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IND | SEV | 16 | PRP | 142 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Aarkay Industries | Individual | ASP | IND | REF | 23 | INV | 144 | N | O | I | CFC | 19.8 | 19.8 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 135798 | 15128 | 150926 | 150926 | 100% | 0 | 0 |  | 17654 | 1967 | 19621 | 0 | 0 | PCR is being finalized for submission in 2003. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Saikrupa Industries | Individual | ASP | IND | REF | 23 | INV | 145 | N | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 125618 | 10524 | 136142 | 136142 | 100% | 0 | 0 |  | 16330.34 | 1368.12 | 17698.46 | 0 | 0 | PCR is being finalized for submission in 2003. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sarkar Refrigeration Industries | Individual | ASP | IND | REF | 23 | INV | 152 | N | O | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-06-01 |  | 2000-11-01 | 2002-06-01 | 117100 | -1955 | 115145 | 115145 | 100% | 0 | 0 |  | 15223 | -287 | 14936 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  |  | 2000-09-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Sidwal Refrigeration Industries P. Ltd. | Individual | ASP | IND | REF | 23 | INV | 160 | N | O | I | CFC | 11.7 | 14.1 | 0 | 0 | 1997-11-01 | 1999-10-01 | 1999-06-01 |  | 2000-09-01 | 2002-05-01 | 169744 | 5038 | 174782 | 174782 | 100% | 0 | 0 |  | 22067 | 655.32 | 22722.32 | 0 | 0 | [12 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration, solvent and halon production sectors |  | ASP | IND | SEV | 24 | PRP | 178 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sandeep Refrigeration | Individual | ASP | IND | REF | 25 | INV | 180 | N | O | I | CFC | 9.9 | 9.9 | 0 | 0 | 1998-07-01 | 1999-08-01 | 2000-08-01 |  | 2000-08-01 | 2001-04-01 | 107684 | -773 | 106911 | 106911 | 100% | 0 | 0 |  | 13998.92 | -100.49 | 13898.43 | 0 | 0 | Project completed and PCR submitted | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Prashant Refrigeration Appliances | Individual | ASP | IND | REF | 25 | INV | 182 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 1999-12-01 | 104058 | -104058 | 0 | 0 |  | 0 | 0 |  | 13527.54 | -13528 | 0 | -0.46 | -0.46 | Project has been cancelled. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of domestic refrigerators at BPL Refrigeration Ltd. | Individual | ASP | IND | REF | 25 | INV | 183 | N | O | I | CFC | 136 | 136 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2001-08-01 |  | 2002-12-01 | 2005-01-01 | 722906 | 302123 | 1025029 | 1025029 | 100% | 0 | 0 |  | 93977.78 | 35611.19 | 129588.97 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the refrigeration, solvent and CFC-halon production sectors |  | ASP | IND | SEV | 27 | PRP | 203 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Whirlpool of India Ltd. | Individual | ASP | IND | REF | 27 | INV | 204 | N | O | I | CFC | 200.6 | 200.6 | 0 | 0 | 1999-03-01 | 2002-12-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 675165 | -276756 | 398409 | 398409 | 100% | 0 | 0 |  | 84268.15 | -39407.54 | 44860.61 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of use of carbon tetrachloride as process agent in the production of endosulphan by Excel Industries Limited | Individual | ASP | IND | PAG | 28 | INV | 217 | N | O | I | CTC | 375 | 375 | 0 | 0 | 1999-07-01 | 2000-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-03-01 | 366000 | 0 | 366000 | 366000 | 100% | 0 | 0 |  | 47580 | 0 | 47580 | 0 | 0 | PCR to be finalized and submitted in 2003. | [11 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out project: 1999 annual programme | Multiyear | ASP | IND | PRO | 29 | INV | 238 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2000-11-01 |  | 2000-11-01 |  | 12000000 | 0 | 12000000 | 12000000 | 100% | 0 | 0 |  | 960000 | 0 | 960000 | 0 | 0 | Implemented | [11 empty] | INV | 0 | 0 | 22588 | 22411 | Yes | Yes | Yes
FIN | IBRD | Preparation of projects in the solvent general sector |  | ASP | IND | SOL | 30 | PRP | 247 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in halon production sector |  | ASP | IND | PRO | 30 | PRP | 249 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the industrial and chiller refrigeration subsectors |  | ASP | IND | REF | 30 | PRP | 255 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out project: 2000 annual programme | Multiyear | ASP | IND | PRO | 31 | INV | 262 | N | O | I | CFC | 0 | 0 | 1882 | 1882 | 2000-07-01 | 2000-09-01 | 2000-12-01 |  | 2000-12-01 |  | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Annual Programme satisfactorily implemented with achievement of CY2000 CFC production reduction and disbursement targets. ODS (regulation & control) rules established along with quota order for production quota licenses for CFC-producing enterprises. | [10 empty] | 2000 | INV | 0 | 0 | 20706 | 20407 | Yes | Yes | Yes
COM | IBRD | CFC production sector gradual phase-out project: 2001 annual programme | Multiyear | ASP | IND | PRO | 33 | INV | 295 | N | O | I | CFC | 0 | 0 | 1583 | 1583 | 2001-03-01 | 2001-04-30 | 2001-12-01 |  | 2001-12-01 |  | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Annual Programme satisfactorily implemented. | [10 empty] | 2001 | INV | 0 | 0 | 18824 | 18693 | Yes | Yes | Yes
FIN | IBRD | Project preparation in the MAC sector |  | ASP | IND | REF | 33 | PRP | 300 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-09-01 | 2001-12-01 |  | 2002-09-01 | 2002-09-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project submitted to and approved at the 38th ExCom. | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a sector plan for the process agent sector |  | ASP | IND | PAG | 33 | PRP | 301 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-31 | 2001-12-01 |  | 2003-04-01 | 2003-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Sector Plan completed and project document prepared for submission to the ExCom. | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Halon production and consumption sector phase out plan | One off phaseout | ASP | IND | HAL | 34 | INV | 315 | N | O | I | HAL | 556 | 556 | 321 | 321 | 2001-07-01 | 2003-08-01 | 2002-08-01 |  | 2003-10-01 |  | 2600000 | 0 | 2600000 | 2300000 | 88.46% | 300000 | 300000 |  | 234000 | 0 | 207000 | 27000 | 27000 | Agreement signed with UNDP for transfer of balance funds, which is expected in early 06. Project will be financially completed after UNDP has completed its project activities. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of chlorinated rubber manufacture from carbon tetrachloride to non-ODS process at Rishiroop Organics Pvt. Ltd. | Individual | ASP | IND | PAG | 34 | INV | 320 | N | O | I | CTC | 248.8 | 248.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-10-01 | 2005-01-01 | 2074300 | -109984 | 1964316 | 1964315.95 | 100% | 0.05 | 0.05 |  | 238173 | -12098.24 | 226074.76 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to either R600a or HFC-134a refrigerant at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | REF | 30 | INV | 337 | N | O | I | CFC | 71.7 | 71.7 | 0 | 0 | 2000-03-01 | 2003-07-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 2050000 | -330954 | 1719046 | 1799315.36 | 104.7% | -80269.36 | -80269.36 |  | 235500 | -36404.94 | 206701.84 | -7606.78 | -7606.78 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [10 empty] | 1999 | INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out project: 2002 annual programme | Multiyear | ASP | IND | PRO | 36 | INV | 352 | N | O | I | CFC | 0 | 0 | 1883 | 1883 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 480000 | 0 | 480000 | 0 | 0 | Completed. | [10 empty] | 2002 | INV | 0 | 0 | 16941 | 16890 | Yes | Yes | Yes
FIN | IBRD | Project preparation funds for CTC production closure plan |  | ASP | IND | PRO | 38 | PRP | 355 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed and submitted to ExCom. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Complete phase out of CFC-12 to non-ODS technology (HFC-134a) for manufacturing of mobile air-conditioners (MACs) at Subros Limited (phase II) | Individual | ASP | IND | REF | 38 | INV | 357 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-11-01 |  | 2003-11-01 | 2005-01-01 | 1181693 | -83277 | 1098416 | 1098416 | 100% | 0 | 0 |  | 222895 | -15708 | 207187.01 | -0.01 | -0.01 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out: 2003 annual programme | Multiyear | ASP | IND | PRO | 39 | INV | 361 | N | O | I | CFC | 0 | 0 | 1883 | 1883 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-04-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Implemented. | [10 empty] | 2003 | INV | 0 | 0 | 15058 | 15014 | Yes | Yes | Yes
COM | IBRD | CTC phase-out plan for the consumption and production sectors (first tranche) | Multiyear | ASP | IND | PHA | 40 | INV | 363 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-07-01 |  | 5000000 | 3520843 | 8520843 | 8520843 | 100% | 0 | 0 |  | 375000 | 264063 | 0 | 639063 | 639063 | Tranche is completed. | [10 empty] | 2003 | INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out: 2004 annual programme | Multiyear | ASP | IND | PRO | 42 | INV | 372 | N | O | I | CFC | 0 | 0 | 1832 | 1832 | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2005-01-01 |  | 6000000 | 0 | 6000000 | 5933054 | 98.88% | 66946 | 66946 | 66946 | 450000 | 0 | 444979.05 | 5020.95 | 5020.95 | Completed. | [10 empty] | 2004 | INV | 0 | 0 | 13176 | 13069 | Yes | Yes | Yes
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multiyear | ASP | IND | PHA | 42 | INV | 373 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 |  | 9180112 | 0 | 9180112 | 1479157 | 16.11% | 7700955 | 7700955 | 7700955 | 688508 | 0 | 110936.71 | 577571.29 | 577571.29 | Verification protocol was finalized in 2005. Additional payments will be made once the verification of 2005 production and consumption is completed. It is expected that full disbursement of this tranche will be made by end of 2006. | [10 empty] | 2003 | INV | 0 | 0 | 0 | 0
ONG | IBRD | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multiyear | ASP | IND | PHA | 45 | INV | 386 | N | O | I | CTC | 6158 | 0 | 9827 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 399045 | 0 | 399045 | 0 | 0% | 399045 | 399045 | 339045 | 29928 | 0 | 0 | 29928 | 29928 | Verification of 2005 production and consumption will be undertaken during the first qtr of 2006. Disbursement for this tranche will be made after the verification is completed. | [11 empty] | INV | 1726 | 1726 | 1726 | 1726 | n/a | No | No
ONG | IBRD | CFC production sector gradual phase-out: 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 45 | INV | 390 | N | O | I | CFC | 0 | 0 | 1882 | 1882 | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2006-04-01 |  |  | 5850000 | 0 | 5850000 | 5265000 | 90% | 585000 | 585000 | 585000 | 438750 | 0 | 394875 | 43875 | 43875 | Annual Program satisfactorily implemented. Reduction of CFC production proceeded in accordance with the planned schedule, as agreed between India and ExCom. National CFC production in '05 - to be verified by the verification audit in early 2006 - was 11,264 MT. TA activities including training and awareness have been implemented by PMU with support from UNEP. | [10 empty] | 2005 | INV | 0 | 0 | 11294 | 11263.48 | Yes | Yes | Yes
CLO | IBRD | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1992) |  | ASP | IRA | SEV | 06 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  |  | 1992-12-01 | 40000 | -39579 | 421 | 421 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | JOR | SEV | 04 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 24464 | -21052 | 3412 | 3412 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | JOR | SEV | 06 | CPG | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 70000 | -17005 | 52995 | 52995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
TRF | IBRD | Reduction of CFC-11 in rigid insulation foams in domestic and commercial refrigerators | Individual | ASP | JOR | FOA | 07 | INV | 05 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transferred project to UNIDO. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  | 1994-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC use in flexible foam at International Foam Industries Co. Ltd. | Individual | ASP | JOR | FOA | 07 | INV | 06 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Company moved to the Sudan. |  |  | 1994-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technology transfer and engineering support | Individual | ASP | JOR | FOA | 07 | TAS | 07 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1995-01-01 | 1994-06-01 |  | 1996-06-01 | 1998-05-01 | 73000 | 0 | 73000 | 73000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed for Phase-1 ODS projects. It is part of a line-of-grant approval. The project was carried out as part of IS project. To avoid double counting, disbursement was claimed under the IS project approved at the 7th Meeting. |  |  | 1994-06-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in flexible foam at Kolaghassi Foam and Mattress Factory Co. | Individual | ASP | JOR | FOA | 07 | INV | 08 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-12-01 | 1998-05-01 | 172800 | -3904.84 | 168895.16 | 168895.16 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in air conditioning, commercial and domestic refrigeration (1992) |  | ASP | JOR | REF | 07 | PRP | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-06-30 | 1996-06-01 |  | 1992-12-01 | 1992-12-01 | 500000 | -445139 | 54861 | 54861 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Recovery and recycling of CFC-12 in refrigeration equipment and maintenance procedures and recycling in halon systems | Individual | ASP | JOR | REF | 07 | DEM | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. UNIDO took over. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Policy and monitoring measures | Individual | ASP | JOR | SEV | 07 | INS | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1995-12-01 |  | 1997-06-01 | 1997-06-01 | 100000 | 70000 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PIU fully operational. Total funding of $170,000 was disbursed. |  |  | 1997-06-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | LPG purification at Jordan Refinery Company | Individual | ASP | JOR | ARS | 07 | INV | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1995-06-01 |  | 1998-01-01 | 1998-05-01 | 805000 | 0 | 805000 | 805000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in aerosol at Household and Toiletries | Individual | ASP | JOR | ARS | 07 | INV | 13 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1995-06-01 |  | 1998-04-01 | 1998-05-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in aerosol at Haddad and Sons Inc. | Individual | ASP | JOR | ARS | 07 | INV | 14 | N | O | I | CFC | 85 | 85 | 0 | 0 | 1992-06-01 | 1995-08-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 214200 | 0 | 214200 | 214200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | JOR | SEV | 09 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123200 | -38647 | 84553 | 84553 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | JOR | SEV | 12 | PRP | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 72900 | 6579 | 79479 | 79479 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at three flexible polyurethane foam factories at Arab Foam, Jordan Plastics, National Foam | Individual | ASP | JOR | FOA | 15 | INV | 22 | N | O | I | CFC | 114 | 114 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-09-01 |  | 2002-12-01 | 2003-12-01 | 368500 | 0 | 368500 | 368500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-10-01 | 1999-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | JOR | SEV | 16 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 64680 | 0 | 64680 | 64680 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at Five Star Polyurethane Foam Factory | Individual | ASP | JOR | FOA | 17 | INV | 24 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-02-01 | 1996-04-01 |  | 1998-03-01 | 1998-05-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | JOR | SEV | 18 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project preparation is completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Industrial Petrochemical Co. Ltd. (JIPCO) | Individual | ASP | JOR | ARS | 20 | INV | 26 | N | O | I | CFC | 98 | 98 | 0 | 0 | 1996-10-01 | 2002-12-01 | 1997-10-01 |  | 2003-10-01 | 2003-12-01 | 102855 | 0 | 102855 | 102855 | 100% | 0 | 0 |  | 13371.15 | 0 | 13371.15 | 0 | 0 | Project completed. |  |  |  | 2000-12-01 |  | 2002-03-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Antiseptics and Detergents Ind. Co. Ltd. (JADICO) | Individual | ASP | JOR | ARS | 20 | INV | 27 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1996-10-01 | 1999-03-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 65720 | 0 | 65720 | 65720 | 100% | 0 | 0 |  | 8543.6 | 0 | 8543.6 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Chemical Products Co. Ltd. (JCPCO) | Individual | ASP | JOR | ARS | 20 | INV | 28 | N | O | I | CFC | 61 | 61 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 203328 | 0 | 203328 | 203328 | 100% | 0 | 0 |  | 26432.64 | 0 | 26432.64 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening | Individual | ASP | JOR | SEV | 22 | INS | 30 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1999-05-01 |  | 1999-05-01 | 1999-06-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | PIU fully operational. Funds were fully disbursed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polysterene at Al Hussam | Individual | ASP | JOR | FOA | 22 | INV | 31 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1999-12-01 | 1999-06-01 |  | 2001-02-01 | 2002-01-01 | 347855 | 0 | 347855 | 347855 | 100% | 0 | 0 |  | 45221.15 | 0 | 45221.15 | 0 | 0 | Project completed. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF (box foam) at Baybars | Individual | ASP | JOR | FOA | 22 | INV | 32 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1997-05-01 | 2001-12-01 | 1998-11-01 |  | 2002-12-01 | 2003-12-01 | 112500 | 0 | 112500 | 112500 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Project completed. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the original country programme |  | ASP | JOR | SEV | 22 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-31 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | 1999-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | ASP | JOR | SEV | 04 | PRP | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 25079 | 47196 | 72275 | 72275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (miscellaneous applications) at Fathei Abu Arja | Individual | ASP | JOR | FOA | 23 | INV | 37 | N | O | I | CFC | 105.4 | 105.4 | 0 | 0 | 1997-11-01 | 1999-12-01 | 2000-12-01 |  | 1999-12-01 | 2004-08-01 | 824869 | -7968 | 816901 | 816901 | 100% | 0 | 0 |  | 107233 | -1035.84 | 106197.13 | 0.03 | 0.03 | FAA project is technically and financially completed. There is no more ODS used in production. Baseline equipment modified so as to fit the new alternative of 141-b. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and halon recycling sectors |  | ASP | JOR | SEV | 24 | PRP | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of project in the aerosol and halon recycling sectors |  | ASP | JOR | SEV | 27 | PRP | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2000-01-01 |  | 1999-12-01 | 1999-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 |  | 650 | 0 | 650 | 0 | 0 | Completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | ASP | JOR | SEV | 28 | INS | 51 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-08-01 | 1999-08-01 |  | 2001-07-01 | 2001-07-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | IS tranche completed and full funding dibursed. |  |  |  |  | 2000-12-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | JOR | HAL | 29 | TAS | 53 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2003-12-01 | 2006-02-01 |  |  | 382250 | 0 | 382250 | 311945.22 | 81.61% | 70304.78 | 70304.78 | 14844.39 | 49693 | 0 | 40553.28 | 9139.72 | 9139.72 | Delay due to difficulty in opening of Letter of Credit, which took 15 months. Equipment delivered Jan. 05 and trial runs commenced in Mar. 05. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation of projects in the aerosol sector |  | ASP | JOR | ARS | 30 | PRP | 59 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam general sector |  | ASP | JOR | FOA | 30 | PRP | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the halon non-recycling |  | ASP | JOR | HAL | 30 | PRP | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-12 for HAPs for perfumes and cosmetics at the aerosol plant Abu Shakra Factory | Individual | ASP | JOR | ARS | 31 | INV | 63 | N | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-08-01 | 2003-11-01 | 76676 | 0 | 76676 | 76676 | 100% | 0 | 0 |  | 9967.88 | 0 | 9967.88 | 0 | 0 | Enterprise has ceased using CFCs. Project conversion is completed. Remaining amount of the grant has been requested and payment process initiated. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | Individual | ASP | JOR | ARS | 31 | INV | 64 | N | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2005-02-01 | 2005-02-01 | 49539 | 0 | 49539 | 49539 | 100% | 0 | 0 |  | 6440.07 | 0 | 6440.07 | 0 | 0 | Project completed. | [7 empty] | 2003-06-01 |  |  | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme update | Individual | ASP | JOR | SEV | 31 | CPG | 67 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-09-01 | 2001-04-01 |  | 2002-09-01 | 2002-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | CP update submitted to the 38th ExCom. | [10 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | Individual | ASP | JOR | HAL | 32 | INV | 69 | N | O | I | HAL | 421.8 | 421.8 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-03-01 | 2006-10-01 |  |  | 563000 | 0 | 563000 | 535416.95 | 95.1% | 27583.05 | 27583.05 | 27583.05 | 71930 | 0 | 68405.93 | 3524.07 | 3524.07 | All contracts signed. All halon fire extinguishing companies completed conversion. NOU is trying to complete workshops for different concerned trainees and parties. The required number of workshops is 8 and Jordan has completed 6 workshops in the fall of 2005. Remaining 2 workshops to be completed in 2006. For the study tour to either Oman, Bharain or Malaysia, Jordan is still contacting authorized personnel to finalize arrangements. | [7 empty] | 2003-06-01 |  |  | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of the institutional strengthening project |  | ASP | JOR | SEV | 34 | INS | 73 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 133333 | -20000 | 113333 | 113333 | 100% | 0 | 0 |  | 17333.29 | -2600 | 14733.29 | 0 | 0 | Final activities of this IS tranche completed. NOU supervised ongoing projects, organized Ozone Day and conducted public awareness. | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National ODS phase out plan: aerosol, foam, MAC service and solvent sectors | One off phaseout | ASP | JOR | PHA | 38 | INV | 77 | N | O | I |  | 157.4 | 32 | 0 | 0 | 2002-11-01 | 2005-11-01 | 2009-11-01 | 2009-11-01 |  |  | 590000 | 0 | 590000 | 84886 | 14.39% | 505114 | 505114 | 140000 | 74900 | 0 | 10776.2 | 64123.8 | 64123.8 | MDI component: Arab center for pharmaceutical products awarded contract. Equipment delivered May 05 and commissioning was Nov. 05. ODS phaseout expected in 06. Foam subsector component under implemenation with six companies identified. MAC component - Contract award expected in 2006. | [10 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | JOR | SEV | 40 | INS | 79 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-06-01 | 2005-07-01 |  | 2005-06-01 | 2005-06-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | Phase 6 of the IS project completed. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Renewal of institutional strengthening project (phase VI) | Individual | ASP | JOR | SEV | 46 | INS | 80 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 | 2007-07-01 |  |  | 147320 | 0 | 147320 | 32541 | 22.09% | 114779 | 114779 | 85000 | 11049 | 0 | 2440.57 | 8608.43 | 8608.43 | Phase 7 of the IS project focuses primarily on meeting Jordan's 85% CFC/halon consumption reduction targets in 2007 thru targeted activities, including in the aerosol, com. ref and servicing sectors, and coordination of IAs active in the country. Ongoing supervision and public awareness activies included. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | AFR | KEN | SEV | 04 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 31498 | -22816 | 8682 | 8682 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | MAL | SEV | 04 | CPG | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 16294 | -8287 | 8007 | 8007 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | MAL | SEV | 04 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 38289 | 5307 | 43596 | 43596 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Servicing, maintenance and recovery of portable extinguishers (halon-1211) and training programme | Individual | ASP | MAL | HAL | 06 | INV | 04 | N | O | I | HAL | 900 | 900 | 0 | 0 | 1992-02-01 | 1996-03-01 | 1993-02-01 |  | 1998-09-01 | 2002-04-01 | 720000 | -1150 | 718850 | 718850 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conservation, leakage control and recycling of CFC-12 and demonstration project in MAC sector | Individual | ASP | MAL | REF | 06 | TAS | 05 | N | O | D | CFC | 370 | 370 | 0 | 0 | 1992-02-01 | 1994-03-01 | 1992-12-01 |  | 1997-06-01 | 1997-07-01 | 910000 | -1845 | 908155 | 908155 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-08-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | MAL | SEV | 06 | PRP | 06 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | -65592 | 54408 | 54408 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $54,408 and expenditure of $35,201 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $89,609 and entry for country program removed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | MAL | SEV | 09 | PRP | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 28200 | 916 | 29116 | 29116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | MAL | SEV | 10 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 75000 | -58343 | 16657 | 16657 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | MAL | SEV | 12 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 35815 | 12744 | 48559 | 48559 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Up-date country programme | Individual | ASP | MAL | SEV | 12 | CPG | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program up-date is complete. Final document submitted to the Bank and the Government on 4/30/95. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | MAL | SEV | 12 | PRP | 36 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 66610 | 2803 | 69413 | 69413 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-12 and CFC-11 with HFC-134a and HCFC-141b respectively and elimination of the use of 1.1.1. TCA in household refrigerator manufacturing at Matsuchita Electric Co. (Melcom) | Individual | ASP | MAL | REF | 15 | INV | 51 | N | O | D |  | 99.73 | 99.73 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1997-12-01 |  | 1996-01-01 | 1997-08-01 | 1276500 | -4307 | 1272193 | 1272193 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. $5,096.82 will be returned. |  |  | 1996-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion project at Argon Malaysia, Sdn. Bhd | Individual | ASP | MAL | ARS | 15 | INV | 53 | N | O | I | CFC | 38 | 38 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-12-01 |  | 1997-08-01 | 1997-08-01 | 131200 | 0 | 131200 | 131200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of the aerosol filling plant Kontrak Manufacturing Services Sdn. Bhd. | Individual | ASP | MAL | ARS | 15 | INV | 55 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-12-01 |  | 1998-10-01 | 1998-11-01 | 618000 | 0 | 618000 | 618000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | MAL | SEV | 16 | PRP | 57 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 206488 | 0 | 206488 | 206488 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation of subprojects which was initiated in 1994 is complete resulting in 11 proposals. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | MAL | SEV | 16 | PRP | 58 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 12258 | 0 | 12258 | 12258 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This budget is being utilized to supervise the MACs and halon Recover and Recycling projects approved for Malaysia in 1993. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS in the process of EPE/EPS foam sheet at Star Foam Paper Products Sdn. Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 59 | N | O | I | CFC | 66 | 66 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-07-01 |  | 2000-10-01 | 2002-03-01 | 295000 | -43111 | 251889 | 251889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Safety audit cannot be performed as enterprise out of business due to economic slowdown. Given this subproject was physically completed many years ago and the enterprise cannot recover its business, DOE and the Bank decided safety audit cannot be done and PCR should be sent to ExCom after receiving endorsement letter from the Government. |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to non-ozone depleting organic solvents in Ban Seng Lee Industries Sdn. Bhd. | Individual | ASP | MAL | SOL | 17 | INV | 62 | N | O | D | TCA | 3.36 | 3.36 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1996-07-01 | 1996-09-01 | 108400 | 0 | 108400 | 108400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1996-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Tenco Industries Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 63 | N | O | D | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-11-01 |  | 1996-03-01 | 1997-03-01 | 79200 | 0 | 79200 | 79200 | 100% | 0 | 0 |  | 10296 | 0 | 10296 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-12 MAC system production equipment and conversion to HFC-134a MAC system manufacturing in Nippondenso Capital Sdn. Bhd. | Individual | ASP | MAL | REF | 18 | INV | 75 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-03-01 | 1999-11-01 |  | 1998-11-01 | 1998-12-01 | 2232718 | -420628.19 | 1812089.81 | 1812089.81 | 100% | 0 | 0 |  | 290253.34 | -30624.23 | 259629.11 | 0 | 0 | Project completed. Disbursement figure in 1999 and 2000 progress reports is incorrect. Additional balance to be returned to 37th ExCom. |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-12 MAC manufacturing equipment and conversion to HFC-134a MAC system manufacturing at APM Air Conditioners Sdn., Bhd. | Individual | ASP | MAL | REF | 18 | INV | 76 | N | O | I |  | 5 | 5 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1999-11-01 |  | 2001-12-01 | 2002-10-01 | 1181553 | -150254.79 | 1031298.21 | 1031298.21 | 100% | 0 | 0 |  | 153601.89 | -19533.15 | 134068.74 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Balance to be returned at the 39th ExCom. |  |  | 1997-12-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Reduction of the consumption of ODSs in the commercial air-conditioning sector via training, recovery and recycling of CFC-11 and CFC-12 in chillers at Mashrae | Individual | ASP | MAL | REF | 18 | TAS | 77 | N | O | I | CFC | 105 | 4.45 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1996-11-01 |  | 2000-11-01 | 2002-10-01 | 824078 | -118061 | 706017 | 706017 | 100% | 0 | 0 |  | 107130.14 | -15347.93 | 91782.21 | 0 | 0 | Final PCR not submitted to ExCom as DOE and the Bank requested MASHRAE and CETEC to revise PCR to ensure that information accurately reflects the actual nature of this project including lessons learned. Actual ODP phaseout low because many chiller owners decided to replace the CFC unit with the new non-CFC unit instead of using the facility. |  |  | 1997-12-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at AE Technology Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 79 | N | O | R | TCA | 17 | 16.8 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1995-08-01 | 1996-09-01 | 56893 | 0 | 56893 | 56893.2 | 100% | -0.4 | -0.4 |  | 7396.09 | 0 | 7396.11 | -0.02 | -0.02 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Mondial Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 80 | N | O | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 2001-03-01 | 144447 | -144447 | 0 | 0 |  | 0 | 0 |  | 18778.11 | -18778.11 | 0 | 0 | 0 | Project cancelled. |  |  | 1997-07-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Widetech | Individual | ASP | MAL | SOL | 18 | INV | 81 | N | O | I | TCA | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-09-01 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 398418 | 0 | 398418 | 398418 | 100% | 0 | 0 |  | 51794.34 | 0 | 51794.34 | 0 | 0 | Project completed. |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at Eng Teknologi Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 82 | N | O | I | TCA | 3.4 | 3.36 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-11-01 |  | 1998-09-01 | 1999-02-01 | 117379 | 0 | 117379 | 117378.6 | 100% | 0.4 | 0.4 |  | 15259.27 | 0 | 15259.21 | 0.06 | 0.06 | Project completed. |  |  | 1997-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 18 | PRP | 84 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane refrigerator panels at Penang Trading Co. | Individual | ASP | MAL | FOA | 19 | INV | 86 | N | O | I | CFC | 10.5 | 10.5 | 0 | 0 | 1996-05-01 | 2000-02-01 | 2000-05-01 |  | 2001-12-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents since Nov. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank in 02. The Bank is waiting for certificate of destruction from DOE before issuing an approval letter |  |  | 1997-05-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufactue of polyurethane cold-room insulation panels/truck container panels at Kejuruteraan Transfreeze Sdn Bhd | Individual | ASP | MAL | FOA | 19 | INV | 87 | N | O | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 2000-02-01 | 1997-05-01 |  | 2001-11-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phrase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents as of Dec. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank Mar. 02. These both projects has two funding parts that are ICC and contingency. |  |  | 1997-05-01 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-12 MAC manufacturing equipment and conversion of HFC-134a MAC manufacturing equipment at UCM Industrial Corporation Berhad | Individual | ASP | MAL | REF | 19 | INV | 90 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-05-01 | 2000-05-01 |  | 2000-08-01 | 2002-10-01 | 1468797 | -263251 | 1205546 | 1205546 | 100% | 0 | 0 |  | 190943.61 | -34222.63 | 156720.98 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Savings to be returned at the 39th ExCom. |  |  | 1997-12-01 |  | 2000-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 21 | PRP | 92 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0 | Completed. |  |  |  | 1999-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for MACs and compressors project category |  | ASP | MAL | REF | 30 | PRP | 132 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent sector and a national CFC phase out programme |  | ASP | MAL | SEV | 27 | PRP | 135 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0 | Ongoing | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC 134a in the manufacturing of MAC system at Sanden International (M) Sdn., Bhd. | Individual | ASP | MAL | REF | 34 | INV | 144 | N | O | R | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-02-01 | 2003-01-01 |  | 2002-08-01 | 2003-02-01 | 807280 | -15079 | 792201 | 792201 | 100% | 0 | 0 |  | 48440 | -904.74 | 47535.26 | 0 | 0 | Project fully completed. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | MAL | PHA | 35 | INV | 145 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 1799940 | 0 | 1799940 | 1396210.57 | 77.57% | 403729.43 | 403729.43 | 403729.43 | 140395 | 0 | 108904.17 | 31490.83 | 31490.83 | 2002 phaseout targets achieved. Verification report confirming phaseout was submitted to ExCom in advance. Implementation of project activities under this tranche completed since Dec 03. There is a balance of $403,729 which country intends to re-allocate for MAC sector. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | MAL | PHA | 37 | INV | 147 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-12-01 | 2003-08-01 |  | 2003-08-01 |  | 2969065 | 0 | 2969065 | 2342766 | 78.91% | 626299 | 626299 | 626299 | 259216 | 0 | 204536.59 | 54679.41 | 54679.41 | Annual tranche allocated to: i)TA for MDIs ii)Solvent iii) Foam & CRSS iv)investment project (CFC113) v)MAC Inspection requirement vi)Train-the-Trainer (MAC) vii)PMU Cost viii)Customs training. Implementation of MAC Inspection requirement and Train-the-Trainer (MAC) completed Apr 04. Implementation of Foam & CRSS, Solvent, TA for MDIs and Customs Training are in progress. For foam sector: Phase 1 Group project completed Jul 04; Phase 2 for individual sub-projects - 22 completed Dec. 05; Phase 3,last 4 individual sub-projects started end 05. Foam sector will be closed Jun 06. Implementation of final project under solvent sector underway with planned completion of Apr 06. | [10 empty] | 2002 | INV | 1910.51 | 1671.38 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | National CFC phase-out plan: 2003 annual work programme | Multiyear | ASP | MAL | PHA | 40 | INV | 149 | N | O | I | CFC | 292 | 292 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-12-01 |  | 2013100 | 0 | 2013100 | 1409346 | 70.01% | 603754 | 603754 | 603754 | 169179 | 0 | 118440.09 | 50738.91 | 50738.91 | Funding approved under this tranche was allocated to: i)MAC Inspection requirement ii)Train-the-Trainer(MAC). iii)Subsidy for MAC basic tools iv) Subsidy for MAC R&R machines v)PMU Cost. Implementation of MAC Inspection requirement and Train-the-Trainer(MAC)completed Apr 04. Implementation of subsidy for MAC basic tools and MAC R&R machines in progress. As of Dec 05, total of 2,529 workshops registered as part of the Cetification of Service Technician Program. 2,511 vouchers for MAC basic service tools issued and 424 vouchers issued for R&R machines. There was a slight deficit of funds for MAC basic tools & R&R machines and country will employ flexibility mechanism to use savings from the 1st Tranche to support this AP. | [10 empty] | 2003 | INV | 1618.51 | 1471.94 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | MAL | PHA | 44 | INV | 154 | N | O | I | CFC | 430 | 430 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 |  | 1688300 | 0 | 1688300 | 466800 | 27.65% | 1221500 | 1221500 | 1221500 | 143947 | 0 | 39800.07 | 104146.93 | 104146.93 | Annual tranche funding allocated to: i)Subsidy for MAC basic tools ii)Subsidy for MAC R&R machines iii)PMU Cost. Implementation of subsidy for MAC basic tools and MAC R&R machines in progress. As of Dec 05, a total of 2,529 workshops have registered as part of the Certification of Service Technician Program. 2,511 vouchers for MAC basic service tools and 424 vouchers for R&R machines issued. | [10 empty] | 2004 | INV | 1188.51 | 1139.9 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | MAL | PHA | 47 | INV | 156 | N | O | I | CFC | 470.8 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 1208300 | 0 | 1208300 | 0 | 0% | 1208300 | 1208300 | 871894 | 100747 | 0 | 0 | 100747 | 100747 | AP funding allocated to: i)Train-the-Trainer (RAC) ii)Subsidy for MAC basic tools iii)Subsidy for MAC R&R machines iv) PMU Cost. Implementation of MAC servicing sector has progressed. Total of 2,529 workshops out of the anticipated 3,000 workshops registered. Total of 2,511 and 424 vouchers for MAC basic tools and R&R machines, repectively distributed to workshops. Implementation of Refrigeration Servicing component begun. Group Coordinator will be confirmed by DOE in Jan 06. | [10 empty] | 2005 | INV | 717.68 | 667.37 | 0 | 0 | Yes | No | No
FIN | IBRD | Country programme preparation | Individual | LAC | MEX | SEV | 04 | CPG | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 36061 | 26194 | 62255 | 62255 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | MEX | SEV | 04 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 68164 | 35178 | 103342 | 103342 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Safety programme in aerosol plant and recycling training and demonstration project in MAC | Individual | LAC | MEX | MUS | 04 | TRA | 04 | N | O | I | CFC | 0 | 36 | 0 | 0 | 1991-06-01 | 1996-02-01 | 1992-11-01 |  | 1996-04-01 | 1996-04-01 | 180000 | -126208 | 53792 | 53792 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-05-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of projects identified in the country programme | Individual | LAC | MEX | MUS | 05 | INV | 05 | N | O | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1996-11-01 |  | 1996-12-01 | 1997-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Demonstration programme in CFC recovery and recycling of the Instituto Mexicano del Seguro Social (IMSS) refrigeration equipment | Individual | LAC | MEX | REF | 05 | DEM | 06 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-12-01 | 1992-11-01 |  | 1996-12-01 | 1996-12-01 | 499918 | 0 | 499918 | 499918 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Training of Quimobasicos personnel in the use of CFC recovery and recycling equipment | Individual | LAC | MEX | REF | 05 | TRA | 07 | N | O | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1992-11-01 |  |  | 1996-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. |  |  | 1996-12-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recovery and recycling of refrigeration equipment in Monterrey City (Climas Jiménez) | Individual | LAC | MEX | REF | 05 | TAS | 08 | N | O | I | CFC | 4 | 0.3 | 0 | 0 | 1991-11-01 | 1995-10-01 | 1992-11-01 |  | 1994-06-01 | 1995-12-01 | 29328 | 0 | 29328 | 29328 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 with HFC-134a refrigerant in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | REF | 05 | INV | 09 | N | O | I | CFC | 13 | 13 | 0 | 0 | 1991-11-01 | 1995-08-01 | 1992-11-01 |  | 1995-12-01 | 1995-12-01 | 211543 | 0 | 211543 | 211543 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b foam blowing in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 10 | N | O | I | CFC | 25 | 25 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-09-01 | 494500 | 0 | 494500 | 494500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-113 used as a cleaning agent in the manufacturing of optical frames at Styloptic, S.A. | Individual | LAC | MEX | SOL | 05 | INV | 11 | N | O | I | CFC | 3.2 | 0.72 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-06-01 | 79299 | 0 | 79299 | 79299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery, reclaim and recycling of CFC-113 and methylchloroform through Química Omega S.A. plant | Individual | LAC | MEX | SOL | 05 | INV | 12 | N | O | I |  | 183.3 | 183.3 | 0 | 0 | 1991-11-01 | 1995-02-01 | 1992-11-01 |  | 1995-11-01 | 1995-11-01 | 295302 | 0 | 295302 | 295302 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-11-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recovery and recycling programme through Quimobasicos, S.A. | Individual | LAC | MEX | REF | 05 | TAS | 13 | N | O | I | CFC | 140 | 260 | 0 | 0 | 1991-11-01 | 1994-10-01 | 1992-11-01 |  | 1994-07-01 | 1994-12-01 | 222540 | 0 | 222540 | 222540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The annual rate of ODS phaseout has been determined and has exceeded phaseout expectations, resulting in a phase out of 260 tons of CFC phaseout. Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | MEX | SEV | 06 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 292076 | -223980 | 68096 | 68096 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $60,082 and expenditure of $8,014 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $68,096 and entry for country program removed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | MEX | SEV | 09 | PRP | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123400 | -65386 | 58014 | 58014 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | LAC | MEX | SEV | 12 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -35085 | 64915 | 64915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | MEX | SEV | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 52286 | -44858 | 7428 | 7428 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Bank is evaluating its activities in the country. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | MEX | SEV | 16 | PRP | 38 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 71744 | 0 | 71744 | 71744 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | MEX | SEV | 21 | PRP | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC-11 phase out at Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 60 | N | O | I | CFC | 15.6 | 13 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-12-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Gigante 1 | Individual | LAC | MEX | REF | 05 | INV | 61 | N | O | I | CFC | 38 | 5 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1997-09-01 | 1997-09-01 | 496380 | 0 | 496380 | 496380 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Aurrera 1 | Individual | LAC | MEX | REF | 05 | INV | 62 | N | O | I | CFC | 44 | 22.2 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Gigante 2 | Individual | LAC | MEX | REF | 05 | INV | 63 | N | O | I | CFC | 18 | 0 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1997-06-01 |  | 1998-10-01 | 1998-10-01 | 278070 | 0 | 278070 | 278070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Chedraui stores | Individual | LAC | MEX | REF | 05 | INV | 64 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1996-08-01 | 1996-08-01 | 228120 | 0 | 228120 | 228120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Aurrera 2 | Individual | LAC | MEX | REF | 05 | INV | 65 | N | O | I | CFC | 22 | 11.8 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration (end users) conversion projects |  | LAC | MEX | REF | 24 | PRP | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Manufacture of complete heat exchanger systems for air conditioning equipment that use HFC-134a at Climas de Mexico | Individual | LAC | MEX | REF | 24 | INV | 78 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 2000-05-01 | 2000-05-01 | 2359812 | 0 | 2359812 | 2359812 | 100% | 0 | 0 |  | 306775.56 | 0 | 306775.56 | 0 | 0 | Project completed. Indirect phaseout of 110.5 MT. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration sector |  | LAC | MEX | REF | 30 | PRP | 93 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Airtemp | Individual | LAC | MEX | REF | 34 | INV | 102 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-01-01 |  | 2001-11-30 | 2002-03-01 | 1651430 | 0 | 1651430 | 1651430 | 100% | 0 | 0 |  | 191657.3 | 0 | 191657.3 | 0 | 0 | Project successfully completed both physically and financially and all funding disbursed. PCR is under preparation and expected to be submitted in early 2003. Planned and indirect phaseout should be 60 tons on the basis of 1.1 kg installed per unit plus 2 kg of additional service charges (adding up to 3.1 kg per unit). | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the MAC sector |  | LAC | MEX | REF | 36 | PRP | 106 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-04-01 | 2003-07-01 | 25000 | -20000 | 5000 | 5000 | 100% | 0 | 0 |  | 3250 | -2600 | 650 | 0 | 0 | Project preparation commenced, however, upon further inspection at the enterprise, enterprise was determined ineligible. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Sterilization group project to replace CFC-12 technology-based sterilization equipment by alternative technologies in the hospital medical sterilization sector | Individual | LAC | MEX | STE | 40 | INV | 115 | N | O | I | CFC | 14.5 | 4.8 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2005-07-01 | 2006-12-01 |  |  | 288700 | 0 | 288700 | 121044 | 41.93% | 167656 | 167656 | 167656 | 21653 | 0 | 9078.5 | 12574.5 | 12574.5 | Four subprojects completed, one SGA signed & process of procuring equipment started. Two subproject SGA still not signed due to enterprise delays in submitting required documentation needed. Final two SGAs expected to be signed by end of Mar. 06 (equipment replacement and destruction is expected to happen within a week of signing SGAs). | [10 empty] | 2003 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Umbrella project for the conversion of CFC-11, CFC-12 and CFC-113 into HFC, HCFC, HFE for technical aerosols at Tecnosol, Envatec and Dimmex | Individual | LAC | MEX | ARS | 41 | INV | 116 | N | O | I | CFC | 57.3 | 0 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2006-12-01 | 2006-12-01 |  |  | 252340 | 0 | 252340 | 118696 | 47.04% | 133644 | 133644 | 133644 | 18925.5 | 0 | 8902.2 | 10023.3 | 10023.3 | TECNOSOL project now completed. DIMMEX will cease production using CFCs by Feb 06. An audit will be carried out in Mar 06 to verify that both DIMMEX and TECNOSOL have ceased using CFCs. Final disbursement will be done after audit. | [10 empty] | 2003 | INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2005 work programme | Multiyear | LAC | MEX | PHA | 45 | INV | 124 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 | 500000 | 500000 | 37500 | 0 | 2883.75 | 34616.25 | 34616.25 | Funds for the 2005 programme will be disbursed to FIDE in Feb 06. Analysis of interested parties for chiller replacement to start during Q2 2006 (this includes credit checks and status of current equipment). | [10 empty] | 2005 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1991) | Individual | AFR | NIR | SEV | 04 | CPG | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-02-01 |  | 1991-12-01 | 1991-12-01 | 129981 | -44959 | 85022 | 85022 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1992) | Individual | AFR | NIR | SEV | 06 | CPG | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 271255 | -214838 | 56417 | 56417 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1992) |  | AFR | NIR | SEV | 06 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 144078 | -144078 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1993) |  | AFR | NIR | SEV | 09 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1994-03-01 |  |  | 1993-12-01 | 62500 | -62500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1994) |  | AFR | NIR | SEV | 12 | PRP | 08 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1993) | Individual | AFR | NIR | SEV | 09 | CPG | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 35100 | -11028 | 24072 | 24072 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1994) | Individual | AFR | NIR | SEV | 12 | CPG | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 150000 | -143520 | 6480 | 6480 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1995) | Individual | AFR | NIR | SEV | 16 | CPG | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1997-06-01 | 1997-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | AFR | NIR | SEV | 04 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 82821 | -82821 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
TRF | IBRD | Halon consumption phase-out through a technical assistance programme and a halon recycling | Halon Banking | ASP | OMA | HAL | 41 | TAS | 08 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 |  |  | 2005-07-01 | 64600 | -64600 | 0 | 0 |  | 0 | 0 |  | 5814 | -5814 | 0 | 0 | 0 | Project transferred to UNIDO at the 46th ExCom. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project identification and preparation (1993) |  | ASP | PAK | SEV | 11 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 100000 | -91044 | 8956 | 8956 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | PAK | SEV | 12 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 133191 | -38871 | 94320 | 94320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group: (Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Industries Ltd., Procon En) | Individual | ASP | PAK | FOA | 17 | INV | 06 | N | O | I | CFC | 205 | 205 | 0 | 0 | 1995-07-01 | 1999-08-01 | 1997-01-01 |  | 2005-02-01 |  | 1247330 | 0 | 1247330 | 1246300 | 99.92% | 1030 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-05-01 | 1999-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded and rigid PUF at Razi Sons | Individual | ASP | PAK | FOA | 18 | INV | 07 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1995-11-01 | 1999-04-01 | 1997-05-01 |  | 2002-11-01 | 2003-08-01 | 493262 | 0 | 493262 | 493262 | 100% | 0 | 0 |  | 64124.06 | 0 | 64124.06 | 0 | 0 | Project and draft PCR completed. |  |  | 1998-12-01 | 1999-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1995) |  | ASP | PAK | SEV | 16 | PRP | 08 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 143009 | 0 | 143009 | 143009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agenct and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | Individual | ASP | PAK | REF | 19 | INV | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1999-11-01 | 257650 | -257650 | 0 | 0 |  | 0 | 0 |  | 33494.5 | -33494.5 | 0 | 0 | 0 | Subproject cancelled. |  |  | 1998-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 21 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the country programme |  | ASP | PAK | FOA | 22 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-30 | 1998-05-01 |  | 1997-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Synthetic Products Enterprises (Pvt) Ltd. (SPEL) | Individual | ASP | PAK | FOA | 23 | INV | 16 | N | O | I | CFC | 13.6 | 13.6 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-01-01 | 2003-10-01 | 160625 | -23796.5 | 136828.5 | 136828.5 | 100% | 0 | 0 |  | 20881 | -3093.5 | 17787.5 | 0 | 0 | Project completed and PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kold Kraft Ltd. | Individual | ASP | PAK | REF | 23 | INV | 18 | N | O | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-12-01 | 2003-02-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0 | Project completed and PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | Individual | ASP | PAK | REF | 23 | INV | 19 | N | O | I | CFC | 117.6 | 27 | 0 | 0 | 1997-11-01 | 2004-07-01 | 2000-03-01 | 2006-07-01 |  |  | 841750 | 0 | 841750 | 696426.92 | 82.74% | 145323.08 | 145323.08 | 145323.08 | 109428 | 0 | 90535.91 | 18892.09 | 18892.09 | Supplier technicians visited Cool in Dec. 05 and installed machines for refrigerator foaming line. Delay in installation due to enterprise postponing supplier visit and not completing local works. C-pentane storage area and pre-mixing station now completed. Ducting of exhaust system & fabrication of foaming room completed. Local works to be done end Jan. 06. Supplier has retrofitted one machine for freezer line. Supplier will complete retrofitting of remaining machine Feb 06. Training expected in Mar. 06. | [11 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 23 | INV | 20 | N | O | I | CFC | 239.6 | 239.6 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 | 2006-03-01 |  |  | 1600000 | 0 | 1600000 | 1330864 | 83.18% | 269136 | 269136 | 269106 | 208000 | 0 | 173012.32 | 34987.68 | 34987.68 | Project technically completed with the last completion occurring in Nov. 05. Enterprise that suffered the fire is negotiating with another Thermoware producer to contract services/ equipment for production until insurance issues settled. Two units (Sanson and Efasco) machines are still at port. FI approached customs collector for auction date which is awaited. IOC for eligible units is being assessed. Disbursement expected by Mar. 06. | [5 empty] | 2001-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Singer Pakistan Ltd. | Individual | ASP | PAK | REF | 23 | INV | 21 | N | O | I | CFC | 17.8 | 17.8 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2004-07-01 | 2005-02-01 | 205893 | 0 | 205893 | 205893 | 100% | 0 | 0 |  | 26766 | 0 | 26766 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible moulded, rigid foam) at Diamond Group of Industries | Individual | ASP | PAK | FOA | 23 | INV | 22 | N | O | I | CFC | 64.1 | 64.1 | 0 | 0 | 1997-11-01 | 2001-09-01 | 2000-03-01 |  | 2005-02-01 |  | 563339 | 0 | 563339 | 506935 | 89.99% | 56404 | 56404 | 56404 | 73234 | 0 | 65901.48 | 7332.52 | 7332.52 | Project completed. 10% cost of machinery held up because computer control software is still not functioning. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 24 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 |  | 8190 | 0 | 8190 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 25 | INV | 25 | N | O | I | CFC | 105.65 | 105.65 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2000-08-01 | 2006-03-01 |  |  | 718900 | 0 | 718900 | 548587 | 76.31% | 170313 | 170313 | 170313 | 93457 | 0 | 71316.31 | 22140.69 | 22140.69 | Project technically completed with last completion occurring in Nov. 05. Enterprise that suffered the fire is negotiating with another Thermoware producer to contract services/ equipment for production until insurance issues settled. Two units (Sanson and Efasco) machines are still at port. FI approached customs collector for auction date which is awaited. IOC for eligible units is being assessed. Disbursement expected by Mar. 06. | [5 empty] | 2001-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Dawlance P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 26 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 477894 | -477894 | 0 | 0 |  | 0 | 0 |  | 62126.22 | -62126.33 | 0 | -0.11 | -0.11 | Project cancelled at the 33rd ExCom Meeting. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of refrigeration equipment at United Refrigeration Industries Ltd. | Individual | ASP | PAK | REF | 25 | INV | 27 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 457815 | -457815 | 0 | 0 |  | 0 | 0 |  | 59515.95 | -59515.95 | 0 | 0 | 0 | Project cancelled at the 33rd ExCom Meeting. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC134a in the manufacture of commercial refrigeration equipment at Shadman Electronic Industries P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 28 | N | O | I | CFC | 15.53 | 15.53 | 0 | 0 | 1998-07-01 | 2000-10-01 | 2000-08-01 |  | 2002-11-01 | 2003-02-01 | 236936 | 0 | 236936 | 236936 | 100% | 0 | 0 |  | 30801.68 | 0 | 30801.68 | 0 | 0 | Project completed and PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 through conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane slabstock foam at United Foam Industries | Individual | ASP | PAK | FOA | 26 | INV | 29 | N | O | I | CFC | 28.6 | 28.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-12-01 | 2002-01-01 | 178200 | 0 | 178200 | 178200 | 100% | 0 | 0 |  | 23166 | 0 | 23166 | 0 | 0 | Project completed and PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 through conversion to water based technology in the manufacture of flexible molded polyurethane foam at Saleem Automotive Industries Ltd. | Individual | ASP | PAK | FOA | 26 | INV | 30 | N | O | I | CFC | 2.5 | 2.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-06-01 |  | 1999-03-01 | 2000-12-01 | 33875 | -2272 | 31603 | 31603 | 100% | 0 | 0 |  | 4403.75 | -295.35 | 4108.4 | 0 | 0 | Project completed, PCR submitted June 2000. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a in the manufacture of domestic refrigeration equipment at Refrigerators Manufacturing Company Pakistan Ltd. | Individual | ASP | PAK | REF | 26 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-31 | 127804 | -127804 | 0 | 0 |  | 0 | 0 |  | 16614.52 | -16614.52 | 0 | 0 | 0 | Project cancelled at the 35th ExCom Meeting. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam and refrigeration sectors |  | ASP | PAK | SEV | 27 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | Individual | ASP | PAK | FOA | 29 | INV | 34 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1999-11-01 | 2004-09-01 | 2001-12-01 |  | 2005-06-01 | 2005-09-01 | 279280 | 0 | 279280 | 273667.14 | 97.99% | 5612.86 | 0 |  | 36306.4 | 0 | 35576.72 | 729.68 | 0 | Project completed. | [6 empty] | 2003-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam flexible sub-sector |  | ASP | PAK | REF | 30 | PRP | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration sector (railway) |  | ASP | PAK | REF | 30 | PRP | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam |  | ASP | PAK | FOA | 30 | PRP | 37 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 |  | 1560 | 0 | 1560 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | PAK | SEV | 18 | PRP | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | Individual | ASP | PAK | REF | 32 | INV | 39 | N | O | I | CFC | 19.7 | 19.7 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-08-01 |  | 176681 | 0 | 176681 | 174382.26 | 98.7% | 2298.74 | 2298.74 | 2298.74 | 22968.53 | 0 | 22669.69 | 298.84 | 298.84 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Mumtaz Engineers | Individual | ASP | PAK | REF | 32 | INV | 40 | N | O | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-11-01 |  | 204736 | 0 | 204736 | 97690 | 47.72% | 107046 | 107046 | 107046 | 26615.68 | 0 | 12699.7 | 13915.98 | 13915.98 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Assistance for the country programme update | Individual | ASP | PAK | SEV | 36 | CPG | 46 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | CPU submitted and approved at the 41st ExCom Meeting. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase-out of the use of CFCs in remaining foam enterprises: Pakistan Insulation, Simpson Wire, HEPCO, Indus Plastic, Workman and Thermocraft Engineering | Individual | ASP | PAK | FOA | 41 | INV | 58 | N | O | I | CFC | 106.9 | 45 | 0 | 0 | 2003-12-01 | 2005-11-01 | 2006-01-01 | 2006-06-01 |  |  | 658973 | 0 | 658973 | 440285 | 66.81% | 218688 | 218688 | 218688 | 49423 | 0 | 33021.39 | 16401.61 | 16401.61 | Pakistan Insulation: Machinery installed; Simpson: Machinery to be installed in Jan 06; Hepco: Machinery expected to arrive in Feb 06; Indus: Project completed; Thermocraft: Mahinery to be installed in Jan 06; Workman: Machinery under clearance. | [10 empty] | 2003 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phaseout of the use of CFC-11 and CFC-12 in the manufacture of refrigeration equipment at Dawlance, United Refrigeration, Ice Age and at 29 small enterprises | Individual | ASP | PAK | REF | 42 | INV | 59 | N | O | I | CFC | 181.3 | 0 | 0 | 0 | 2004-04-01 | 2005-08-01 | 2007-04-01 | 2007-04-01 |  |  | 1126855 | 0 | 1126855 | 152582.65 | 13.54% | 974272.35 | 974272.35 | 940488 | 84514 | 0 | 11443.68 | 73070.32 | 73070.32 | SGAs signed for 3 lg manufacturers in Feb 05 and equipment ordered. As of end Dec. 05 - Dawlance: Machinery under customs clearance; United Ref: Machinery under customs clearance; Ice Age: Machinery expected to arrive in Feb 06; SME: Request for proposal for a Group Coordinator is in progress. | [10 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | PHI | SEV | 04 | CPG | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 19952 | 17415 | 37367 | 37367 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | PHI | SEV | 04 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 10826 | 39489 | 50315 | 50315 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | PHI | SEV | 06 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-08-12 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 400000 | -6325 | 393675 | 393675 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. Balance of funds returned to Multilateral Fund. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | PHI | SEV | 06 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 100000 | -57260 | 42740 | 42740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Concepcion Industries | Individual | ASP | PHI | REF | 09 | INV | 07 | N | O | I | CFC | 40.8 | 78.3 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-05-01 |  | 1998-10-01 | 1999-02-01 | 790000 | -46000 | 744000 | 744000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Full-production with C-pentane - Oct. 21, 1998. PCR was endorsed to WB on 01/12/99. Grant fund fully disbursed. No ODS eqpt. Dismantled - High pressure foam machine was used even at the start of operation. |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Sanyo Philippines | Individual | ASP | PHI | REF | 09 | INV | 08 | N | O | D | CFC | 12.6 | 23.9 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-03-01 |  | 1996-11-01 | 1999-01-01 | 660000 | -37061 | 622939 | 622939 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Phase 2 completed 11/96 - adoption of HCFC 141b foam. PCR was endorsed to WB on 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 12/19/95 |  |  | 1997-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Transunion (formerly called Federal Electric Company) | Individual | ASP | PHI | REF | 09 | INV | 09 | N | O | I | CFC | 6.6 | 26.4 | 0 | 0 | 1993-03-01 | 1997-09-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 770000 | -204218.75 | 565781.25 | 565781.34 | 100% | -0.09 | -0.09 |  | 0 | 0 | 0 | 0 | 0 | Full production with C-pentane - Oct.1, 1998. PCR was endorsed to WB on 2/2/99. Date ODS Eqpt. Dismantled - 12/02/98. All safety equipmpent and other items are installed and operational. Total grant fund disbursed is $547,732.15 only (excluding FI fees). Completed revision of PCR's Table 5. Revised PCR submitted to WB on 10 Jan |  |  | 1997-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Instititional strengthening for Ozone Desk Operations | Individual | ASP | PHI | SEV | 09 | INS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-12-01 | 2002-05-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed physically and financially. |  |  | 1998-06-01 | 1999-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to semi-aqueous and aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 11 | N | O | D |  | 85.7 | 85.7 | 0 | 0 | 1993-03-01 | 1996-08-01 | 1993-09-01 |  | 1995-09-01 | 1998-07-01 | 790000 | 0 | 790000 | 790000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 8/16/96 |  |  | 1995-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to low-emission processing and organic solvents at Pacific Semiconductors, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1996-10-01 | 710000 | -710000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise decided not to proceed with project. Project cancelled. |  |  | 1993-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at Electronic Assemblies, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 13 | N | O | I | CFC | 4 | 4.16 | 0 | 0 | 1993-03-01 | 1996-04-01 | 1993-09-01 |  | 1997-02-01 | 1998-07-01 | 710000 | -34141 | 675859 | 675859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 6/11/96 |  |  | 1997-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at Integrated Microelectronic, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 14 | N | O | D | CFC | 14.6 | 14.6 | 0 | 0 | 1993-03-01 | 1997-08-01 | 1993-09-01 |  | 1997-12-01 | 1998-12-01 | 430000 | -72997.88 | 357002.12 | 357002.12 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/20/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 5/19/98 |  |  | 1996-07-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to semi-aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 15 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1997-02-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise is no longer eligible for grant funding. Project cancelled. | [11 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Information exchange programme | Individual | ASP | PHI | SEV | 09 | TAS | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-11-01 |  |  | 1993-11-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Funds transferred to UNEP for its implementation at the request of the Govt. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance for the financial institution | Individual | ASP | PHI | SEV | 09 | TAS | 17 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-08-01 | 1994-03-01 |  | 2000-04-01 | 2000-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project and PCR completed. |  |  | 1998-06-01 | 1999-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of tobacco fluffing process to carbon dioxide at Fortune Tobacco corporation | Individual | ASP | PHI | OTH | 09 | INV | 18 | N | O | I | CFC | 350 | 350 | 0 | 0 | 1993-03-01 | 1996-05-01 | 1995-03-01 |  | 1999-08-01 | 2000-08-01 | 4720000 | -267640 | 4452360 | 4452360 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully completed on Dec. 30, 1999. Decommissioning of the G -13 Plant was done from Jan. 10 to May 7, 2000. PCR was endorsed to WB on August 2, 2000. Grant fund fully disbursed. |  |  | 1997-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Philippines Appliance Corporation (Philacor) | Individual | ASP | PHI | REF | 09 | INV | 19 | N | O | I | CFC | 240 | 240 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1997-05-01 |  | 1998-04-01 | 1999-02-01 | 1770000 | 0 | 1770000 | 1770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR was endorsed to WB on 10/20/98. Date ODS Eqpt. Dismantled - 12/19/95. Grant fund fully disbursed. |  |  | 1998-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | PHI | SEV | 09 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 194550 | -129221 | 65329 | 65329 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | User-sector project identification and preparation (1993) |  | ASP | PHI | SEV | 11 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  |  | 1994-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | PHI | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 136027 | -93678 | 42349 | 42349 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1994) |  | ASP | PHI | SEV | 12 | PRP | 29 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 94900 | -94900 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | PHI | SEV | 16 | PRP | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-12-31 | 1996-12-01 | 169937 | -70000 | 99937 | 99937 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Philacor, Concepcion, Sanyo and Transunion -- Engineering Design and Assistance for the Use of HFC-134a Refrigerant in Household Refrigerators | Individual | ASP | PHI | REF | 19 | INV | 45 | N | O | I | CFC | 91.9 | 27.1 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1998-01-01 |  | 1998-05-01 | 1999-03-01 | 952000 | -485520 | 466480 | 466480 | 100% | 0 | 0 |  | 123760 | -58262.73 | 65497.27 | 0 | 0 | Project completed - HFC 134a refrigeration systems. PCRs endorsed to WB on 12/1/99. Grant fund fully disbursed. Philacor's Calamba Plant is not covered with grant funding. |  |  | 1998-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening |  | ASP | PHI | SEV | 28 | INS | 63 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-05-01 | 2002-05-01 | 139333 | 0 | 139333 | 139333 | 100% | 0 | 0 |  | 18113 | 0 | 18113 | 0 | 0 | Phase II completed and IS renewal approved at the 36th ExCom. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a national CFC phaseout plan |  | ASP | PHI | PHA | 35 | PRP | 65 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2001-12-31 | 2002-12-01 |  | 2002-11-01 | 2002-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Completed. NCPP approved at the 38th ExCom. | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening project (Phase III) |  | ASP | PHI | SEV | 36 | INS | 67 | N | O | I | CFC | 14.97 | 14.97 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2004-12-01 | 2005-01-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 23547.29 | 0 | 23547.29 | 0 | 0 | Phase III completed and IS renewal approved at the 42nd ExCom. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase out plan: manufacturing sector (first tranche) | Multiyear | ASP | PHI | PHA | 38 | INV | 69 | N | O | I |  | 89.3 | 89.3 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 2858473 | 0 | 2858473 | 634497.04 | 22.2% | 2223975.96 | 2223975.96 | 444795 | 248663 | 0 | 55195.88 | 193467.12 | 193467.12 | PMU established Sep. 03 and staffed in 2004. NCPP announced & CFC import quota and phaseout schedule reaffirmed; MDI strategy finalized Apr. 04 & corresponding Admin. Order signed Jun. 04. Technical specs for servicing sector equipment identified. Evaluation Committee for Equipment Supplier Acceditation created thru a DENR-EMB Special Order. TA to aerosol sector pending submission by enterprise of amended proposal. As of Dec. 05, project funds distributed to 3 enterprises. Train-the-trainers completed. Criteria for subsidies to the service sector revised and announced in Dec. 05. | [10 empty] | 2002 | INV | 1960 | 1422.4 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Preparation of a methyl bromide phase-out plan |  | ASP | PHI | FUM | 39 | PRP | 70 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | Meetings and workshops with Fertilizer and Pesticide Authority, a TWG and affected groups prior conducted. MBr consumption survey forwarded to Ozone Secretariat to support countrys request to lift potential non-compliance status. Proposed National MBr Strategy approved at the 45th ExCom. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan (manufacturing sector): 2004 annual programme | Multiyear | ASP | PHI | PHA | 41 | INV | 71 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 |  | 1877418 | 0 | 1877418 | 705043.2 | 37.55% | 1172374.8 | 1172374.8 | 234475 | 160968 | 0 | 60449.72 | 100518.28 | 100518.28 | Activities underway. For manufacturing, 3 projects under implementation and 3 project proposals under review by PMU prior to endorsing project appraisal as of end 2005. For servicing, Code of Practice finalized. In 2005, training equipment procured and distributed to training centers; 34 vouchers issues and 21 technicians trained in the pilot implementation of the voucher system. 2003 audit results show that actual CFC imports were 1,422.4 MT (537.6 MT less than NCPP max. allowable consumption level). | [10 empty] | 2003 | INV | 1810 | 1389.81 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | PHI | SEV | 42 | INS | 73 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2005-05-01 | 90566 | 0 | 90566 | 90566 | 100% | 0 | 0 |  | 6792 | 0 | 6792 | 0 | 0 | First half of Phase IV of the IS project completed. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | PHI | PHA | 44 | INV | 75 | N | O | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 |  | 2160071 | 0 | 2160071 | 76435.65 | 3.539% | 2083635.35 | 2083635.35 | 416727 | 186006 | 0 | 6581.95 | 179424.05 | 179424.05 | Three suppliers of tools and equipment for voucher system qualified. "Catch-up" plan adopted which includes utilization of EMB Regional Offices and hiring of additonal man-power to expedite national implementation of voucher system. 52 technicians trained by training centers. Policy on MAC Inspection endorsed for approval to Department Secretaries & procurement process for identifiers on-going. Training of LTO Regional Offices on mandatory MAC inspection conducted Nov-Dec 2005. Additional 3000 copies of Code of Practice printed. Meetings with PARII representatives undertaken to discuss concerns regarding operation of reclamation facility and procurement process for facility initiated. | [10 empty] | 2004 | INV | 1509 | 0 | 0 | 0 | Yes | No | No
ONG | IBRD | Technical assistance for a national methyl bromide phase-out strategy | One off phaseout | ASP | PHI | FUM | 44 | TAS | 76 | N | O | I | MBR | 9 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-12-01 | 2008-12-01 |  |  | 330000 | 0 | 330000 | 25227.22 | 7.645% | 304772.78 | 304772.78 | 95773 | 24750 | 0 | 1892.04 | 22857.96 | 22857.96 | Activities include issuance of policies/guidelines to control MB consumption, monitoring of fumigators, consultation with the Bureau of Plant Industries (BPI) on QPS applications of MB, consultation with stakeholders (exporters, fumigators and pest control operators) and 3 regional orientation workshops to concerned government agencies (BPI, Fertilizer and Pesticide Authority and Customs). | [10 empty] | 2004 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of the institutional strengthening project (phase IV, second year) | Individual | ASP | PHI | SEV | 45 | INS | 78 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 | 2006-04-01 |  |  | 90567 | 0 | 90567 | 64418.57 | 71.13% | 26148.43 | 26148.43 | 26148.43 | 6793 | 0 | 4831.73 | 1961.27 | 1961.27 | 2nd part of Phase IV under implementation. 2005 accomplishments include 4 halon orientation seminars for Bureau of Fire Protection; monitoring of 14 manufacturers, the halon bank and 14 service shops; coordination of hearings with senate on ratification of MP amendments; monitoring & enforcement of ODS import policies and regulation on ODS trade; continuation of info., education & communication campaign targeting various stakeholders and launching of storybooks on ozone protection. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | PHI | PHA | 47 | INV | 79 | N | O | I | CFC | 149 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 2873197 | 0 | 2873197 | 0 | 0% | 2873197 | 2873197 | 143660 | 248588 | 0 | 0 | 248588 | 248588 | Newly approved. 2006 AP targets include the operationalization of MAC inspection and adherence to the max. allowable ceiling of 1,360 MT of CFC consumption. Full implementation of the voucher scheme will also be the focus of the this tranche, considering the significant reductions of CFC imports in 2007. | [10 empty] | 2005 | INV | 1360 | 0 | 0 | 0 |  | No | No
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1993) | Individual | EUR | SLO | SEV | 11 | CPG | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  | 1994-12-01 | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | SLO | SEV | 11 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-03-01 |  | 1994-03-01 | 1994-03-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | SLO | SEV | 12 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -22085 | 77915 | 77915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A workshop held on project preparation and processing procedures earlier in the year has helped the preparation of 8 subprojects in the refrigeration, foam, aerosol and solvents sectors. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1994) | Individual | EUR | SLO | SEV | 12 | CPG | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation |  | ASP | SRL | SEV | 04 | PRP | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 23339 | -23339 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | THA | SEV | 04 | CPG | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 30909 | 220344 | 251253 | 251253 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | THA | SEV | 04 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 32476 | 11678 | 44154 | 44154 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | THA | SEV | 06 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-08 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 390000 | -40 | 389960 | 389960 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed and closed. Balance returned to Multilateral Fund. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | THA | SEV | 06 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | 12195 | 132195 | 132195 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Thai-Airways non-ODS metal cleaning |  | ASP | THA | SOL | 07 | PRP | 06 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-12-01 | 1994-06-01 |  | 1994-12-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1994-12-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recycling in MAC | Individual | ASP | THA | REF | 07 | TAS | 07 | N | O | I | CFC | 250 | 86.93 | 0 | 0 | 1992-06-01 | 1999-01-01 | 1994-12-01 |  | 2003-12-01 | 2004-03-01 | 900000 | 0 | 900000 | 801085.63 | 89.01% | 98914.37 | 24033.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-05-01 | 1999-12-01 | 2001-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | THA | SEV | 09 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 190000 | -10781 | 179219 | 179219 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to wet media blasting and aqueous cleaning solvents at Hana (BKK) Co., Ltd. | Individual | ASP | THA | SOL | 10 | INV | 12 | N | O | D |  | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-03-01 |  | 1993-12-01 | 1997-08-01 | 1010000 | -232835 | 777165 | 777165 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at GSS Array | Individual | ASP | THA | SOL | 10 | INV | 13 | N | O | D | CFC | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1994-03-01 |  | 1993-12-01 | 1997-05-01 | 316000 | -41204 | 274796 | 274796 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at Saha Union's Sriracha facility | Individual | ASP | THA | SOL | 10 | INV | 14 | N | O | R | CFC | 27.2 | 21.76 | 0 | 0 | 1993-06-01 | 1996-06-01 | 1994-03-01 |  | 1993-05-01 | 1997-05-01 | 2573000 | -472605 | 2100395 | 2100395 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at Thai Heat Exchange Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 15 | N | O | I | TCA | 11 | 11 | 0 | 0 | 1993-06-01 | 1998-08-01 | 1994-03-01 |  | 1998-08-01 | 1998-08-01 | 268000 | -14000 | 254000 | 254000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-08-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at C.I. Group Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 16 | N | O | R | TCA | 12.7 | 12.7 | 0 | 0 | 1993-06-01 | 1998-05-01 | 1994-03-01 |  | 1995-12-01 | 1998-05-01 | 277000 | 0 | 277000 | 277000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 17 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-02-01 | 823000 | -131273 | 691727 | 691727 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Kang Yong Electric Co. Ltd. (Kye) | Individual | ASP | THA | REF | 10 | INV | 18 | N | O | R | CFC | 109 | 109 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1997-12-01 | 1140000 | -256628 | 883372 | 883372 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 19 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-01-01 | 1864000 | -1269071 | 594929 | 594929 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Hitachi Consumer Products Co. Ltd. | Individual | ASP | THA | REF | 10 | INV | 20 | N | O | D | CFC | 132 | 132 | 0 | 0 | 1993-06-01 | 1997-08-01 | 1996-06-01 |  | 1996-12-01 | 1998-10-01 | 553000 | 128861 | 681861 | 681861 | 100% | 0 | 0 |  | 0 | 32939.53 | 32939.53 | 0 | 0 | Project completed. Phase I was financially completed in Aug '97. Phase II was financially completed in Oct. '98. |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 21 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-09-01 | 1996-06-01 |  | 1997-01-01 | 1996-11-01 | 989000 | -330207 | 658793 | 658793 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 22 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-01-01 | 1996-06-01 |  | 1995-12-01 | 1997-01-01 | 686000 | -85630 | 600370 | 600370 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b as a foam blowing agent at Technic Foam, Ltd. | Individual | ASP | THA | FOA | 10 | INV | 23 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1993-06-01 | 1999-09-01 | 1993-12-01 |  | 2000-01-01 | 2000-06-01 | 174000 | 0 | 174000 | 174000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR approved by the WB in Jun/2000. |  |  | 1997-12-01 | 1999-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | THA | SEV | 10 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 150000 | -104309 | 45691 | 45691 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | THA | SEV | 12 | PRP | 28 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 129433 | 3256 | 132689 | 132689 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Umbrella Grant Agreement signed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | THA | SEV | 12 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 81302 | -68062 | 13240 | 13240 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of electronic cleaning processes from CFC-113 to high-purity water cleaning at Team Tronics, Co. Ltd. | Individual | ASP | THA | SOL | 13 | INV | 34 | N | O | I | CFC | 12 | 11.5 | 0 | 0 | 1994-07-01 | 1998-05-01 | 1995-01-01 |  | 1999-08-01 | 1999-09-01 | 221760 | 0 | 221760 | 221760 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-12-01 | 1999-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Production of HFC-134a MAC parts at Nippodenso | Individual | ASP | THA | REF | 13 | INV | 37 | N | O | R | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1997-03-01 | 1995-07-01 |  | 1993-12-01 | 1997-03-01 | 141500 | 0 | 141500 | 141500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of ODS solvents at Thai Airways | Individual | ASP | THA | SOL | 15 | INV | 40 | N | O | I | CFC | 6 | 0 | 0 | 0 | 1994-12-01 | 1998-12-01 | 1996-06-01 |  | 1999-12-01 | 1999-12-01 | 463900 | -32600 | 431300 | 431300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-12-01 | 1999-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | THA | SEV | 16 | PRP | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1997-12-01 | 1997-12-01 | 267138 | 0 | 267138 | 267138 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of plastic lens cleaning processes from CFC-113 and 1,1,1 TCA to aqueous cleaning at Crystal Lens Corporation Ltd. | Individual | ASP | THA | SOL | 18 | INV | 48 | N | O | R |  | 1.86 | 1.86 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-05-01 |  | 1996-12-01 | 1998-08-01 | 39830 | 0 | 39830 | 39830 | 100% | 0 | 0 |  | 5177.9 | 0 | 5177.9 | 0 | 0 | Project completed. |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 18 | PRP | 50 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC-11 in the manufacturing of equipment for the food and beverage industry at Siam Stainless Steel Co. Ltd. | Individual | ASP | THA | REF | 19 | INV | 52 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-09-01 |  |  | 1999-03-01 | 212900 | -212900 | 0 | 0 |  | 0 | 0 |  | 27677 | -27677 | 0 | 0 | 0 | Project cancelled. Funds returned to 27th meeting. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at BKJ Engineering Co. Ltd. (BKJ) | Individual | ASP | THA | SOL | 19 | INV | 53 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-02-01 |  |  | 1998-07-01 | 186487 | -186487 | 0 | 0 |  | 0 | 0 |  | 24243.31 | -24243 | 0 | 0.31 | 0.31 | Project cancellation |  |  | 1997-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of precision cleaning processes from CFC-113 to aqueous and alternative solvent cleaning and conversion of insulator applications from CFC-113 to perfluorocarbons at Thai CRT Co. Ltd. | Individual | ASP | THA | SOL | 19 | INV | 54 | N | O | R | CFC | 5 | 5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1996-05-01 |  | 1995-09-01 | 1997-05-01 | 99440 | 0 | 99440 | 99440 | 100% | 0 | 0 |  | 12927.2 | 0 | 12927.2 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ozone depleting substances used in the production of household refrigerators at A.P. National Co. Ltd. | Individual | ASP | THA | REF | 21 | INV | 57 | N | O | R | CFC | 54 | 54 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1998-02-01 |  | 1997-01-01 | 1997-12-01 | 311150 | 0 | 311150 | 311150 | 100% | 0 | 0 |  | 40449.5 | 0 | 40449.5 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 58 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1997-04-01 |  | 1997-01-01 | 1998-05-01 | 673680 | 224477 | 898157 | 898157 | 100% | 0 | 0 |  | 87578.4 | 29181.85 | 116760.25 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 60 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1997-01-01 | 1997-10-01 | 808234 | -94003 | 714231 | 714231 | 100% | 0 | 0 |  | 105070.42 | 10323.11 | 115393.53 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 61 | N | O | R | CFC | 436 | 436 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1997-08-01 |  | 1997-01-01 | 1998-08-01 | 1467055 | -84285 | 1382770 | 1382770 | 100% | 0 | 0 |  | 190717.15 | -5722.05 | 184995.1 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 62 | N | O | R | CFC | 89 | 89 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1998-02-01 |  | 1997-01-01 | 1998-05-01 | 316957 | -19224 | 297733 | 297733 | 100% | 0 | 0 |  | 41204.41 | -1236.1 | 39968.31 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (panels) at Alcan Nikkei Thai Aluminum Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 72 | N | O | R |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-11-01 |  |  | 1999-11-01 | 36500 | -36500 | 0 | 0 |  | 0 | 0 |  | 4745 | -4745 | 0 | 0 | 0 | Project cancelled. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Can Asia Products Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 73 | N | O | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-11-01 |  | 1999-10-01 | 2000-06-01 | 84300 | 0 | 84300 | 84300 | 100% | 0 | 0 |  | 10959 | 0 | 10959 | 0 | 0 | Project completed. PCR submitted to the WB in May/2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in rigid sprayfoam applications at Thermobond Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 74 | N | O | I | CFC | 10.4 | 10.4 | 0 | 0 | 1997-11-01 | 1999-04-01 | 1999-11-01 |  | 1999-07-01 | 2000-04-01 | 81400 | -4613 | 76787 | 76787 | 100% | 0 | 0 |  | 10582 | -599.69 | 9982.31 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Siam Chaicharoen Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 76 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 2000-04-01 | 2000-06-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat 30 June 2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at General Injection Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 77 | N | O | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-11-01 |  | 2000-06-01 | 2000-07-01 | 120580 | 0 | 120580 | 120580 | 100% | 0 | 0 |  | 15675 | 0 | 15675 | 0 | 0 | Project Completed. PCR submitted to the WB in Jun/2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Viriyakit Plastic Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 78 | N | O | I | CFC | 27.5 | 27.5 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-11-01 |  | 1999-02-01 | 1999-06-01 | 142700 | 0 | 142700 | 142700 | 100% | 0 | 0 |  | 18551 | 0 | 18551 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in rigid spray foam applications at P.U. Foam Insulation and Trading Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 79 | N | O | I | CFC | 58.1 | 58.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 1999-08-01 | 1999-09-01 | 225400 | 0 | 225400 | 225400 | 100% | 0 | 0 |  | 29302 | 0 | 29302 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of water coolers at Sirithana | Individual | ASP | THA | REF | 23 | INV | 80 | N | O | I | CFC | 8.06 | 8.06 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-05-01 |  | 1999-08-01 | 1999-12-01 | 122593 | 0 | 122593 | 122593 | 100% | 0 | 0 |  | 15937 | 0 | 15937 | 0 | 0 | Project completed. PCR submitted to the WB in Dec/1999. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Padriew Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 81 | N | O | I | CFC | 10.24 | 10.24 | 0 | 0 | 1997-11-01 | 1999-05-01 | 1999-05-01 |  | 1999-07-01 | 1999-08-01 | 135954 | 0 | 135954 | 135954 | 100% | 0 | 0 |  | 17674 | 0 | 17674 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of Water Coolers at Siam Cooler | Individual | ASP | THA | REF | 23 | INV | 82 | N | O | I | CFC | 26.38 | 12.38 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-05-01 |  | 2000-08-01 | 2000-09-01 | 186545 | -8258 | 178287 | 178286.83 | 100% | 0.17 | 0.17 |  | 24251 | -1073.54 | 23177.46 | 0 | 0 | Project completed. PCR submitted to the World Bank 4 September 2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Sahakarn Intercool Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 85 | N | O | I | CFC | 5.7 | 5.7 | 0 | 0 | 1997-11-01 | 2000-03-01 | 1999-05-01 |  | 2000-07-01 | 2001-12-31 | 86697 | 0 | 86697 | 86697 | 100% | 0 | 0 |  | 11271 | 0 | 11271 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Treathaboon Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 86 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 1999-02-01 | 1999-12-01 | 177750 | -20563 | 157187 | 157187 | 100% | 0 | 0 |  | 23108 | -2673.19 | 20434.81 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam, halon, commercial refrigeration (end users), and solvent sectors |  | ASP | THA | SEV | 24 | PRP | 88 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Terminal umbrella project to convert CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at 224 small and medium sized enterprises | Individual | ASP | THA | REF | 25 | INV | 92 | N | O | I | CFC | 173 | 186.1 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2002-12-01 |  | 2004-12-01 |  | 750000 | 1881486 | 2631486 | 2265174.37 | 86.08% | 366311.63 | 202140.63 | 202140.63 | 97500 | 226963 | 279296.67 | 45166.33 | 27107.33 | PCR preparation, which has undergone significant delays, is almost complete. Project activities completed in 2004 but given large number of beneficiaries, data collection for the PCR has been slow and complex. All data needed to complete the PCR was provided by Kulthorn Engineering by end 2005. TMB committed to finalizing the PCR by Mar 06. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of cold store polyurethane panels at Somerville | Individual | ASP | THA | FOA | 25 | INV | 95 | N | O | I | CFC | 18.1 | 18.13 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2001-08-01 |  | 2000-03-01 | 2000-04-01 | 141957 | -21957 | 120000 | 120000 | 100% | 0 | 0 |  | 18454.41 | -2854.41 | 15600 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Programme to reduce the usage of CFC-11 and CFC-12 in chiller servicing by replacing CFC-based chillers with HFC-134a and HCFC-123 chillers at Electricity Generating Authority (EGAT) | Individual | ASP | THA | REF | 26 | INV | 104 | N | O | I | CFC | 13.2 | 13.2 | 0 | 0 | 1998-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-09-01 | 2005-04-01 | 2475000 | -1276053.07 | 1198946.93 | 1198946.93 | 100% | 0 | 0 |  | 282250 | -145520.83 | 136729.17 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam, halon, commercial refrigeration end-use and solvent sectors |  | ASP | THA | SEV | 27 | PRP | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 | 0 |  | 18330 | 0 | 18330 | 0 | 0 | Ongoing | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.E. Containers Supply Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 108 | N | O | I | CFC | 29 | 29 | 0 | 0 | 1999-03-01 | 2000-06-01 | 1999-04-01 |  | 2000-09-01 | 2000-10-01 | 181883 | -8750 | 173133 | 173133 | 100% | 0 | 0 |  | 23644.79 | -1137.5 | 22507.29 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from CFC-11 to water blown and HCFC-141b technology in the manufacture of rigid foam (spray) at Bangkok Integrated Trading Co. | Individual | ASP | THA | FOA | 27 | INV | 109 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-04-01 |  |  | 2001-12-31 | 117923 | -117923 | 0 | 0 |  | 0 | 0 |  | 15329.99 | -15329.99 | 0 | 0 | 0 | Project cancelled July 2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam M.P. Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 110 | N | O | I | CFC | 25.4 | 25.4 | 0 | 0 | 1999-03-01 | 2000-09-01 | 1999-04-01 |  | 2000-08-01 | 2000-10-01 | 164366 | -12500 | 151866 | 151866 | 100% | 0 | 0 |  | 21367.58 | -1625 | 19742.58 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat Nov. 2000. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam Steel International PLC | Individual | ASP | THA | FOA | 27 | INV | 111 | N | O | I | CFC | 27.1 | 27.1 | 0 | 0 | 1999-03-01 | 2001-08-01 | 2001-03-01 |  | 2001-05-01 | 2002-03-01 | 196981 | -200 | 196781 | 196781 | 100% | 0 | 0 |  | 25607.53 | -26 | 25581.53 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  |  |  | 2001-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid foam at Willich Sales & Contracting Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 112 | N | O | I | CFC | 16.05 | 16.05 | 0 | 0 | 1999-03-01 | 2001-03-01 | 1999-04-01 |  | 2001-08-01 | 2002-11-01 | 58630 | 0 | 58630 | 58630 | 100% | 0 | 0 |  | 7621.9 | 0 | 7621.9 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  |  |  | 2000-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of integral skin polyurethane foam and rigid moulded foam at Jennings Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 113 | N | O | I | CFC | 14.35 | 14.35 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-02-01 | 2001-10-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282.37 | 0 | 16282.37 | 0 | 0 | Project completed. PCR submitted to the WB in Sep. 01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Plastmate Industry Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 115 | N | O | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 2000-08-01 | 1999-04-01 |  | 2000-11-01 | 2000-11-01 | 80649 | -6500 | 74149 | 74149 | 100% | 0 | 0 |  | 10484.37 | -845 | 9639.37 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to HCFC-141b technology in the manufacture of commercial refrigerator and display cabinets at Makassan Metal Works | Individual | ASP | THA | FOA | 28 | INV | 116 | N | O | I | CFC | 9.3 | 9.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2001-05-01 | 2002-07-01 | 72819 | 0 | 72819 | 72819 | 100% | 0 | 0 |  | 9466.47 | 0 | 9466.47 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. | [5 empty] | 2004-02-01 | [5 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | THA | HAL | 29 | TAS | 121 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2003-12-01 | 2008-07-01 |  |  | 220750 | 0 | 220750 | 0 | 0% | 220750 | 220750 | 50000 | 28697.5 | 0 | 0 | 28697.5 | 28697.5 | As a result of various evaluations and feasibility studies conducted with the Swedish counterpart, Government concluded that it was not feasible to develop a physical halon banking facility in Thailand. 47th ExCom therefore approved a revised proposal for the banking project with partial reallocation of the balances from the Terminal Halon Conversion project to finance proposed demo activities. Halon projects will remain open until revised Halon Mgmt and Banking project completed. US$200,000 for TA approved for this project under Sweden, in addition to funds for this project. All disbursements to date made from TA component. 2005 was spent partly in revising the project, including extensive consultations with stakeholders. In 2006, DIW and the Bank will work on TORs and selection criteria for the Halon Management Team that will assist NOU in implementating revised project. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in halon non-recycling |  | ASP | THA | HAL | 30 | PRP | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane subsector |  | ASP | THA | FOA | 30 | PRP | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | ASP | THA | SOL | 30 | PRP | 128 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 21 | PRP | 129 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 16250 | 0 | 16250 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of commercial refrigeration equipment at Arco Industry Co., Ltd | Individual | ASP | THA | FOA | 28 | INV | 130 | N | O | I | CFC | 16.8 | 16.32 | 0 | 0 | 1999-07-01 | 2001-12-31 | 2002-02-01 |  | 2001-09-01 | 2002-02-01 | 131544 | -3759 | 127785 | 127785 | 100% | 0 | 0 |  | 17100.72 | -488.67 | 16612.05 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. | [5 empty] | 2004-02-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | Individual | ASP | THA | FOA | 31 | INV | 131 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-05-01 | 2005-02-01 | 51795 | -14902 | 36893 | 36893 | 100% | 0 | 0 |  | 6733.35 | -1936.91 | 4796.09 | 0.35 | 0.35 | Project completed and PCR under review. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Siam Cargo Containers | Individual | ASP | THA | FOA | 31 | INV | 132 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-07-01 | 2005-03-01 | 2003-08-01 |  | 2004-08-01 | 2005-03-01 | 177741 | -79622 | 98119 | 98119 | 100% | 0 | 0 |  | 23106.33 | -10350.86 | 12755.47 | 0 | 0 | Project physically and financially completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (sprayfoam and blocks) at Isotech | Individual | ASP | THA | FOA | 32 | INV | 133 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2004-01-01 |  | 2001-11-01 | 2002-01-01 | 144943 | 0 | 144943 | 144943 | 100% | 0 | 0 |  | 18842.59 | 0 | 18842.59 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/World Bank. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | Individual | ASP | THA | HAL | 32 | INV | 134 | N | O | I | HAL | 436 | 717.4 | 0 | 0 | 2000-12-01 | 2003-10-01 | 2004-02-01 | 2008-07-01 |  |  | 568000 | 0 | 568000 | 145771 | 25.66% | 422229 | 422229 | 68360 | 72480 | 0 | 18601.2 | 53878.8 | 53878.8 | Project included 5 subprojects. First 4 subprojects physically & financially completed. Antifire Co. Ltd. completed and will be financially completed by Q1 2006. Overall project will remain open because 47th ExCom approved a revised version of the Halon Management and Banking project. Excom approved partial reallocation of balances ($164,100) from Terminal Halon Conversion projects to finance demo activities proposed under revised project. Both halon projects will remain open until objectives of revised halon banking poroject are achieved. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a methyl bromide phaseout strategy | Individual | ASP | THA | FUM | 33 | TAS | 135 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2003-12-01 | 2002-09-01 |  | 2004-12-01 | 2005-03-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Project preparation completed. Strategy approved at the 44th ExCom. | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol |  | ASP | THA | SEV | 35 | INS | 136 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-12-31 | 2003-07-01 |  | 2003-07-01 | 2004-12-01 | 0 | 225128 | 225128 | 225128 | 100% | 0 | 0 |  | 0 | 29267 | 29267 | 0 | 0 | Project was completed and a terminal report and extension request was submitted to ExCom in Jul. 03. Funding was advanced to cover costs which was not received until 43rd ExCom. | [10 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | THA | PHA | 35 | INV | 137 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2002-12-01 |  | 2002-12-01 |  | 540000 | 0 | 540000 | 540000 | 100% | 0 | 0 |  | 27000 | 0 | 27000 | 0 | 0 | Implementation of project activities under this tranche completed since 2004. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | THA | PHA | 37 | INV | 138 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2003-12-01 |  | 5194380 | 0 | 5194380 | 1347515 | 25.94% | 3846865 | 3846865 | 2815536.36 | 459494 | 0 | 119200.95 | 340293.05 | 340293.05 | Funding under this AP allocated to aerosol, foam, solvent, MDI, textile and garment project(THTI), MAC inspection requirement, train-the-trainer for MAC, custom training and PMU. As of Dec 05, implementation of investment activities in aerosol completed, while some projects in foam and solvent sectors ongoing until end 2006. Implementation of THTI sub-project experienced progress as voucher was finalized and db of textile and garment factories developed. For TA components, MDI activity, training equipment procurement to DSD under Train-the-Trainer for MAC, dev. of inspection manual and specs of refrigerant identifier for MAC inspection completed in 2005. Activities implemented under PMU in 2005 comprise of project implementation and policy activities. | [10 empty] | 2002 | INV | 3107.52 | 2180 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | THA | SEV | 40 | INS | 139 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-08-01 | 2005-08-01 | 346667 | 0 | 346667 | 346667 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Remaining budget was used for public awareness activities e.g. ozone road show, publications, etc. These PR activities were conducted to promote and ensure sustainable ODS phaseout. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: 2003 annual programme | Multiyear | ASP | THA | PHA | 41 | INV | 140 | N | O | I | CFC | 486 | 486 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-03-01 |  | 4011846 | 0 | 4011846 | 930991.33 | 23.21% | 3080854.67 | 3080854.67 | 500000 | 353066 | 0 | 81932.7 | 271133.3 | 271133.3 | Funding under AP also allocated to foam, textile and garment project, MAC inspection requirement, Train-the-Trainer for MAC, custom training, and PMU. In addition, AP funding also allocated for MAC service equipment and R&R machine. For basic equipment, as of Dec 05, 2,073 vouchers released to certified MAC service shops of which 80% already have equipment. For R&R machines, there was difficulty in securing docs from MAC service shops to verify consumption. Therefore distribution of voucher for R&R machines will be done in 2006. | [10 empty] | 2003 | INV | 2818.52 | 1848.53 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | THA | PHA | 42 | INV | 141 | N | O | I | CFC | 486 | 486 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 |  | 1315400 | 0 | 1315400 | 69747.46 | 5.302% | 1245652.54 | 1245652.54 | 500000 | 118386 | 0 | 6277.27 | 112108.73 | 112108.73 | Funding under AP for MAC service equipment, R&R machines and PMU operation. In addition, AP allocated savings from manufacturing to cover cost of GC's fee and certification of MAC service technicians. Contract between FI and 3 GCs for MAC service program signed Mar 05. As of Mar 05, 68 training workshops conducted throughout Thailand for MAC servicing certification. Approximately 2,547 MAC service shops certified. In Dec 05, additional 7 workshops organized. Eight workshops will be organized in Jan 06 to meet NCPP target. | [10 empty] | 2004 | INV | 2332.52 | 1320.06 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National methyl bromide phase-out plan (first tranche) | Multiyear | ASP | THA | FUM | 44 | INV | 143 | N | O | I | MBR | 58.7 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 546991 | 0 | 546991 | 0 | 0% | 546991 | 546991 | 200000 | 41024 | 0 | 0 | 41024 | 41024 | Consultation workshop held Feb 05 to present strategy to stakeholders. Grant Agreement between WB and Thailand amended to incorporate the Department of Agriculture (DOA) as the executing agency. Ministry of Finance countersigned GA Oct 05. Signature of MOA between DOA and GSB(FI) will take place in Feb 06. DOA has designated in 2005 a temporary PMU that will be responsible for carrying out the initial activities under the plan. A selection committee also set up to select permanent staff of the PMU. | [10 empty] | 2004 | INV | 183.1 | 103.91 | 0 | 0 | Yes | No | No
ONG | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | THA | PHA | 45 | INV | 144 | N | O | I | CFC | 962.9 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 1330400 | 0 | 1330400 | 0 | 0% | 1330400 | 1330400 | 200000 | 111736 | 0 | 0 | 111736 | 111736 | Funding for activities covered MAC service equipment and R&R machines, operaton of PMU and new activity (Train-the-Trainer for refrigeration). In addition, AWP also included allocation of savings to certification of MAC service technician and procurement of Refrigerant Identifiers. However, procurement of RIs could not be carried out in 2005 and was postponed to 2006 as a proposal to grant approval for duty exemption for these RIs was in the process of consideration and approval by the Cabinet. | [10 empty] | 2005 | INV | 1370 | 1002.54 | 0 | 0 | Yes | No | No
ONG | IBRD | Renewal of institutional strengthening project (phase IV) | Individual | ASP | THA | SEV | 46 | INS | 145 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 | 2007-07-01 |  |  | 346668 | 0 | 346668 | 112959.13 | 32.58% | 233708.87 | 233708.87 | 116854.43 | 26000 | 0 | 8471.9 | 17528.1 | 17528.1 | NOU used IS funds to ensure effective implementation of existing import control system, maintain cooperation with chemical suppliers, relevant industries and international bodies to prevent any illegal trade, fulfill the country's obligations under the MP, assist PMU/DIW to implement the NCPP, coordinate with DOA to implement MB phaseout strategy, follow-up and monitor CFC use in the servicing sector and to finalize the national strategy for mgmnt of halons. | [10 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | LAC | TRI | SEV | 04 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 86843 | -86843 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation |  | LAC | TRI | SEV | 04 | PRP | 06 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 107561 | -107561 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | TUN | SEV | 04 | PRP | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 64748 | -33533 | 31215 | 31215 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 04 | CPG | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 58363 | 105240 | 163603 | 163603 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | TUN | SEV | 06 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 50000 | -27623 | 22377 | 22377 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical seminar and conversion to non-CFC technology in aerosol sector | Individual | AFR | TUN | ARS | 07 | INV | 04 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1993-06-01 |  | 1998-03-01 | 1998-06-01 | 239995 | 50000 | 289995 | 289995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998 |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance and demonstration of non-CFC technology in rigid and flexible foam production | Individual | AFR | TUN | FOA | 07 | INV | 05 | N | O | I | CFC | 45 | 45 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-02-01 |  | 1998-03-01 | 1998-06-01 | 218354.28 | 0 | 218354.28 | 218354.28 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of low-CFC and non-CFC in rigid foams in refrigeration insulation at Tabrid | Individual | AFR | TUN | FOA | 07 | INV | 06 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-06-01 |  | 1997-07-01 | 1998-06-01 | 258844 | 0 | 258844 | 258844 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final PCR provided in June 1998 |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Maintenance of domestic, commercial and industrial refrigeration systems | Individual | AFR | TUN | REF | 07 | TAS | 07 | N | O | I | CFC | 42 | 42 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1997-06-01 |  | 1997-12-01 | 1998-06-01 | 32836 | 300000 | 332836 | 332836 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR provided in June 1998 |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance for development of HFC-134a-based domestic refrigerators | Individual | AFR | TUN | REF | 08 | TAS | 08 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1995-04-01 |  | 1997-06-01 | 1998-06-01 | 404658.6 | 0 | 404658.6 | 404658.6 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of Governmnet actions (institutional strengthening) | Individual | AFR | TUN | SEV | 08 | INS | 09 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-07-01 | 1995-10-01 |  | 1998-06-01 | 1998-06-01 | 285312 | 0 | 285312 | 285312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | TUN | SEV | 09 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 165800 | -3866 | 161934 | 161934 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | AFR | TUN | SEV | 12 | PRP | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 76296 | -26955 | 49341 | 49341 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | AFR | TUN | SEV | 16 | PRP | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 35000 | -3418 | 31582 | 31582 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 09 | CPG | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 8200 | 0 | 8200 | 8200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 24 | PRP | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of ozone depleting substances (renewal of institutional strengthening) | Individual | AFR | TUN | SEV | 25 | INS | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-07-01 | 2000-07-01 |  | 2003-12-01 | 2003-12-01 | 186700 | 0 | 186700 | 186700 | 100% | 0 | 0 |  | 24271 | 0 | 24271 | 0 | 0 | Legislation was drafted, ongoing and completed projects monitored and public awareness campaign was continued. IS renewal requested and approved at the 39th ExCom. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion to LCD technology in the manufacture of polyurethane flexible foam and HCFC-141b with water in polyurethane rigid foam at Sotim | Individual | AFR | TUN | FOA | 25 | INV | 32 | N | O | I | CFC | 95.3 | 95.3 | 0 | 0 | 1998-07-01 | 2000-11-01 | 2000-08-01 |  | 2004-12-01 |  | 553400 | 0 | 553400 | 422036.9 | 76.26% | 131363.1 | 131363.1 |  | 71942 | 0 | 54864.79 | 17077.21 | 17077.21 | Project is completed. | [11 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Phaseout of CFC-11 by conversion to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Supermousse | Individual | AFR | TUN | FOA | 26 | INV | 33 | N | O | I | CFC | 93.5 | 93.5 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 |  | 529490 | 0 | 529490 | 422036.9 | 79.71% | 107453.1 | 107453.1 |  | 68243.9 | 0 | 54394.68 | 13849.22 | 13849.22 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a project in the solvent sector |  | AFR | TUN | SOL | 27 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Coldeq by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 36 | N | O | I | CFC | 8.8 | 8.8 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 |  | 68917 | 0 | 68917 | 64525 | 93.63% | 4392 | 4392 |  | 8959.21 | 0 | 8388.25 | 570.96 | 570.96 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Bafes by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 37 | N | O | I | CFC | 11.7 | 11.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 |  | 91477 | 0 | 91477 | 86329 | 94.37% | 5148 | 5148 |  | 11892.01 | 0 | 11222.77 | 669.24 | 669.24 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe de Construction Industrialisee (SCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 38 | N | O | I | CFC | 8.3 | 8.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 |  | 64700 | 0 | 64700 | 58730 | 90.77% | 5970 | 5970 |  | 8411 | 0 | 7634.9 | 776.1 | 776.1 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe Nouvelle de Coupe Industrielle (SNCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 39 | N | O | I | CFC | 20.3 | 20.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 |  | 156235 | 0 | 156235 | 140611.5 | 90% | 15623.5 | 15623.5 |  | 20310.55 | 0 | 18279.49 | 2031.06 | 2031.06 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Soften by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 40 | N | O | I | CFC | 7.5 | 7.5 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 |  | 59079 | 0 | 59079 | 58083.1 | 98.31% | 995.9 | 995.9 |  | 7680.27 | 0 | 7550.8 | 129.47 | 129.47 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 36 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2003-07-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 1300 | -1300 | 0 | 0 | 0 | Project prep. cancelled at the 41st ExCom. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Renewal of institutional strengthening project | Individual | AFR | TUN | SEV | 39 | INS | 43 | N | T | I | CFC | 20.2 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2005-04-01 | 2006-04-01 |  |  | 242667 | 0 | 242667 | 237000 | 97.66% | 5667 | 5667 | 5667 | 18200.03 | 0 | 17775 | 425.03 | 425.03 | IS activities in this tranche devoted to consolidate actions by the NOU, reinforce the regulatory framework for controlling ODS imports and consumption; capacity building and diffusing information on new technologies. 2005 activities included supervision of 45 completed projects; public awareness campaigns; collection and reporting of consumption data; and, leading and contributing to the CPU and national ODS phaseout plan preparation. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of the country programme update | Individual | AFR | TUN | SEV | 42 | CPG | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2004-12-01 | 2006-07-01 |  |  | 80000 | 0 | 80000 | 40000 | 50% | 40000 | 40000 | 40000 | 7200 | 0 | 3600 | 3600 | 3600 | Country Program Update submitted to and accepted at the 47th ExCom. Remaining funds to be utilized for finalizing the National ODS Phaseout Plan addressing the issues raised by the Secretariat. Revised proposal to be submitted to the 49th ExCom. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | EUR | TUR | SEV | 06 | CPG | 01 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1991-06-30 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 13515 | 55074 | 68589 | 68589 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | EUR | TUR | SEV | 06 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 217687 | -67459 | 150228 | 150228 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and recycling of CFC-12 at a refrigeration production plant | Individual | EUR | TUR | REF | 07 | TAS | 03 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1994-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and reclamation of CFC-12 from household refrigerators | Individual | EUR | TUR | REF | 07 | TAS | 04 | N | O | I | CFC | 1 | 0 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1994-06-01 |  | 1996-12-01 | 1997-03-01 | 400000 | -82919.94 | 317080.06 | 317080.06 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Demonstration activities in several sectors |  | EUR | TUR | SEV | 07 | PRP | 05 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-10-01 | 1993-06-01 |  | 1999-12-01 | 2000-03-01 | 500000 | -18877 | 481123 | 481123 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3 demo projects in solvent sector are implemented. 8 demo projects in refrigeration sector completed as of December 31, 1998. 6 demo projects in foam sector is completed as of March 31, 1999. Individual PCRs submitted separately per project code. |  |  | 1997-07-01 | 1999-03-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening | Individual | EUR | TUR | SEV | 08 | INS | 06 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-06-01 | 1997-06-01 |  | 2000-04-01 | 2000-04-01 | 300000 | -33157 | 266843 | 266843 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IS project extended to accommodate additional work program of ozone unit. |  |  | 1997-06-01 | 1999-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of non-ODS technologies in the production of domestic refrigerators at Arcelik A.S. | Individual | EUR | TUR | REF | 08 | INV | 07 | N | O | I | CFC | 750 | 750 | 0 | 0 | 1992-10-01 | 1994-05-01 | 1995-10-01 |  | 1996-06-01 | 1997-03-01 | 4900000 | -10484 | 4889516 | 4889516.31 | 100% | -0.62 | -0.62 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | TUR | SEV | 09 | PRP | 08 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 140400 | 42164 | 182564 | 182564 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | EUR | TUR | SEV | 12 | PRP | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | -8823 | 21177 | 21177 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for supervision on project implementation. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | TUR | SEV | 13 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-30 | 1995-07-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -79142 | 20858 | 20858 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers and coolers at Klimasan Klima Sanayi ve Ticaret A.S. | Individual | EUR | TUR | REF | 15 | INV | 12 | N | O | I |  | 36.9 | 36.9 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1997-01-01 | 1996-12-01 | 690903 | 110665 | 801568 | 801568 | 100% | 0 | 0 |  | 0 | 16669.9 | 16669.9 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the world Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($128,230). |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PEG Profilo Elektrikli Gerecler Sanayii A.S. | Individual | EUR | TUR | REF | 15 | INV | 13 | N | O | I | CFC | 290 | 290 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1996-04-01 | 1996-03-01 | 1578000 | 257747 | 1835747 | 1835747.02 | 100% | -0.02 | -0.02 |  | 0 | 34340.02 | 34340 | 0.02 | 0.02 | The company has achieved 100% non-ODS production. The project is completed and the final report has been submitted to the World Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($264,154). |  |  | 1996-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Assan Demir ve Sac Sanayi A.S., Tuzla-Istanbul | Individual | EUR | TUR | FOA | 15 | INV | 14 | N | O | I | CFC | 180 | 250 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1998-04-01 | 1998-12-01 | 925000 | 0 | 925000 | 925000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | EUR | TUR | SEV | 16 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 43966 | 0 | 43966 | 43966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | EUR | TUR | SEV | 16 | PRP | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 80000 | -7373 | 72627 | 72627 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the mnufacture of rigid polyurethane foam isulation panels at Tek-iz Izolasyon ve Yapi Elemanlari Sanayii, Umnariye-Istanbul | Individual | EUR | TUR | FOA | 18 | INV | 17 | N | O | I | CFC | 155 | 177 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1996-11-01 |  | 1998-04-01 | 1998-07-01 | 729650 | 0 | 729650 | 729650 | 100% | 0 | 0 |  | 94854.5 | 0 | 94854.5 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of the use of CFCs in the manufacture of domestic refrigerators at Pekel Teknik Sanyi ve Ticaret A.S. | Individual | EUR | TUR | REF | 18 | INV | 19 | N | O | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-05-01 |  |  | 1996-10-01 | 500664 | -500664 | 0 | 0 |  | 0 | 0 |  | 65086.32 | -65086.32 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. |  |  | 1996-05-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 18 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Project preparation completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers, coolers, ice makers, and ice cream machines at UGUR Makinalari Sanayi ve Ticaret, A.S. | Individual | EUR | TUR | REF | 19 | INV | 21 | N | O | I | CFC | 64.3 | 64.3 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1999-03-01 | 1999-07-01 | 1166455 | 0 | 1166455 | 1166455 | 100% | 0 | 0 |  | 151639.15 | 0 | 151639.15 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  | 1998-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 21 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project preparation completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into carbon dioxide and water for flexible molded foam at Suntas Foam and Mattress Industry and Commerce, Inc. | Individual | EUR | TUR | FOA | 22 | INV | 24 | N | O | I | CFC | 9.05 | 12.06 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1996-09-01 | 1998-07-01 | 148613 | -5177 | 143436 | 143436 | 100% | 0 | 0 |  | 19319.69 | -579.54 | 18740.15 | 0 | 0 | The project (retroactive) was fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11, CFC-12 into cyclopentane and HFC-134a for commercial refrigeration at S.F.A. Sogutma Urunleri Sanayi Ve Tekstil Pazariama Ltd. Sti. | Individual | EUR | TUR | REF | 22 | INV | 25 | N | O | I |  | 25.9 | 25.9 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-02-01 |  | 1999-03-01 | 1999-12-01 | 389832 | 0 | 389832 | 389832 | 100% | 0 | 0 |  | 50678.16 | 0 | 50678.16 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Gumaksan | Individual | EUR | TUR | REF | 22 | INV | 26 | N | O | I | CFC | 2.3 | 2.3 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1998-06-01 |  | 1998-11-01 | 1999-01-01 | 35195 | 0 | 35195 | 35195 | 100% | 0 | 0 |  | 4575.35 | 0 | 4575.35 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Kulahcioglu | Individual | EUR | TUR | REF | 22 | INV | 27 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 1999-03-01 | 1999-06-01 | 60840 | 0 | 60840 | 60840 | 100% | 0 | 0 |  | 7909.2 | 0 | 7909.2 | 0 | 0 | The project is completed 100% non-CFC production started. Waiting for PCR. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into HCFC-141b at Teba | Individual | EUR | TUR | FOA | 22 | INV | 28 | N | O | I | CFC | 3.51 | 3.51 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1998-06-01 |  | 1998-11-01 | 1999-02-01 | 27468 | -104 | 27364 | 27364 | 100% | 0 | 0 |  | 3570.84 | -13.52 | 3557.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible slabstock foam at Safas | Individual | EUR | TUR | FOA | 23 | INV | 29 | N | O | I | CFC | 93.83 | 93.83 | 0 | 0 | 1997-11-01 | 1998-05-01 | 1999-03-01 |  | 1999-09-01 | 1999-12-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 68900 | 0 | 68900 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from CFC-11 into all-water and HCFC-141b for integral skin foam at Polifleks Sentetik Maddeler Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 33 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 |  | 2000-04-01 |  |  | 1999-11-01 | 252558 | -252558 | 0 | 0 |  | 0 | 0 |  | 32832.54 | -32832.54 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. Funds will be returned at 34th Meeting. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the aerosol, foam and recycling sectors |  | EUR | TUR | SEV | 24 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible slabstock foam at IDAS | Individual | EUR | TUR | FOA | 24 | INV | 38 | N | O | I | CFC | 37 | 37 | 0 | 0 | 1998-03-01 | 1999-02-01 | 2000-04-01 |  | 1998-11-01 | 1999-07-01 | 230510 | -373 | 230137 | 230137 | 100% | 0 | 0 |  | 29966.3 | -48.49 | 29917.81 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 for flexible molded, integral skin and rigid foam at Purplast | Individual | EUR | TUR | FOA | 24 | INV | 39 | N | O | I | CFC | 54 | 54 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2000-11-01 | 551101 | 0 | 551101 | 551101 | 100% | 0 | 0 |  | 71643.13 | 0 | 71643.13 | 0 | 0 | Project fully implemented, 100% non-CFC production started. PCR submitted Jan. 01. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible moulded foam at Elele Doseme Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 40 | N | O | I | CFC | 41.36 | 41.36 | 0 | 0 | 1998-03-01 | 1999-04-01 | 2000-10-01 |  | 1999-04-01 | 1999-07-01 | 311768 | 0 | 311768 | 311768 | 100% | 0 | 0 |  | 40529.84 | 0 | 40529.84 | 0 | 0 | 100% non-CFC production started. Draft PCR prepared. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC foam blowing agents in the production of polyurethane (PU) insulation panels, spray/in situ foam and one component foams at Izopoli Yapi Elemantari Taahhuet Sanayii ve Ticaret Lt | Individual | EUR | TUR | FOA | 24 | INV | 41 | N | O | I | CFC | 274 | 274 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2001-04-01 |  | 2000-05-01 | 2000-05-01 | 1141500 | 0 | 1141500 | 1141500 | 100% | 0 | 0 |  | 148395 | 0 | 148395 | 0 | 0 | Project completed. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible moulded and HCFC-141b for integral skin foam at EPS Entegre Poliuretan Sunger Ve Koltuk San Tic. Ltd. Sti. | Individual | EUR | TUR | FOA | 24 | INV | 42 | N | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 1998-03-01 | 1999-01-01 | 2000-04-01 |  | 1999-12-01 | 1999-12-01 | 188280 | -270 | 188010 | 188010 | 100% | 0 | 0 |  | 24476.4 | -35.12 | 24441.28 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 for flexible moulded, integral skin and rigid foam at Pimsa Poliuretan Imalat Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 43 | N | O | I | CFC | 57.9 | 57.9 | 0 | 0 | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 1999-07-01 | 2000-11-01 | 551501 | 0 | 551501 | 551501 | 100% | 0 | 0 |  | 71695.13 | 0 | 71695.13 | 0 | 0 | Installation completed. 100% non-CFC production started. PCR submitted. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into methylene chloride and dop for flexible molded hot cured foam at Teknik Malzeme | Individual | EUR | TUR | FOA | 24 | INV | 44 | N | O | I | CFC | 17.2 | 17.2 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 1998-06-01 | 1999-08-01 | 122443 | -22079 | 100364 | 100364 | 100% | 0 | 0 |  | 15917.59 | -2870.27 | 13047.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for commercial refrigeration terminal umbrella project |  | EUR | TUR | REF | 25 | PRP | 45 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0 | Completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for methy bromide |  | EUR | TUR | FUM | 25 | PRP | 48 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for 17 enterprises for phaseout of ODS used as solvents | Individual | EUR | TUR | SOL | 25 | INV | 49 | N | O | I |  | 11.97 | 11.97 | 0 | 0 | 1998-07-01 | 2000-03-01 | 1999-08-01 |  | 2000-10-01 | 2000-10-01 | 415312 | -20098 | 395214 | 395214 | 100% | 0 | 0 |  | 53990.56 | -2612.77 | 51377.79 | 0 | 0 | Project implemented and 100% non-CFC production started. Awaiting PCR. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of an electronic defluxing process from ODS-solvent cleaning to hydrocarbon/surfactant (semi-aqueous) cleaning at Aselsan AS | Individual | EUR | TUR | SOL | 25 | INV | 50 | N | O | R | CFC | 3.9 | 3.9 | 0 | 0 | 1998-07-01 | 1999-02-01 | 1999-08-01 |  | 1995-10-01 | 1999-02-01 | 58517 | 0 | 58517 | 58517 | 100% | 0 | 0 |  | 7607.21 | 0 | 7607.21 | 0 | 0 | Company has achieved 100% non-ODS production. Project is completed and draft report submitted to the Bank. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 to isobutane in the manufacture of polyethylene foam tubing at Thermaflex-Form | Individual | EUR | TUR | FOA | 26 | INV | 51 | N | O | R | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1996-08-01 | 1999-06-01 | 124219 | 0 | 124219 | 124219 | 100% | 0 | 0 |  | 16148.47 | 0 | 16148.47 | 0 | 0 | Company started non-CFC production in mid-1996. Subgrant agreement signed in Feb/99. PCR submitted Jan. 01. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the foam, commercial refrigeration, refrigeration/ recycling, halon, methyl bromide and a demonstration project for a national phase-out. |  | EUR | TUR | SEV | 27 | PRP | 54 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | Completed | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into low index additive (LIA) technology for flexible slabstock foam at Elta | Individual | EUR | TUR | FOA | 28 | INV | 55 | N | O | I | CFC | 21.3 | 21.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2001-08-01 |  | 2001-06-01 | 2001-10-01 | 130597 | -20000 | 110597 | 110597 | 100% | 0 | 0 |  | 16977.61 | -2600 | 14377.61 | 0 | 0 | Project fully implemented. 100% non-CFC production started. Awaiting PCR. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of alternatives to methyl bromide in protected strawberry, pepper and eggplant in East Mediterranean region and in strawberry in Aydm province of Turkey | Individual | EUR | TUR | FUM | 29 | INV | 56 | N | O | I | MBR | 50 | 50 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2003-07-01 | 2003-08-01 | 366440 | 0 | 366440 | 366440 | 100% | 0 | 0 |  | 47637.2 | 0 | 47637.2 | 0 | 0 | Project fully implemented. Alternatives to MeBr use in strawberry, pepper and eggplant production determined and results published. | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the aerosol sector |  | EUR | TUR | ARS | 30 | PRP | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of project proposal in the foam general sector |  | EUR | TUR | FOA | 30 | PRP | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects for the halon recycling |  | EUR | TUR | HAL | 30 | PRP | 62 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 15000 | -5000 | 10000 | 10000 | 100% | 0 | 0 |  | 1950 | -650 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane foam subsector |  | EUR | TUR | FOA | 30 | PRP | 63 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | EUR | TUR | SOL | 30 | PRP | 64 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFCs and MCF into HAPs and CO2 for technical aerosols at Beta | Individual | EUR | TUR | ARS | 31 | INV | 66 | N | O | I |  | 31.2 | 31.2 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2002-01-01 |  | 2001-01-01 | 2001-10-01 | 137456 | 0 | 137456 | 137456 | 100% | 0 | 0 |  | 8247 | 0 | 8247 | 0 | 0 | Project fully implemented and 100% non-CFC production started. Awaiting PCR. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase-out methyl bromide in the dried fig sector | Individual | EUR | TUR | FUM | 31 | INV | 69 | N | O | I | MBR | 30 | 0 | 0 | 0 | 2000-07-01 | 2001-06-02 | 2002-10-01 | 2006-12-01 |  |  | 479040 | 0 | 479040 | 477059.26 | 99.59% | 1980.74 | 1980.74 | 1980.74 | 62275.2 | 0 | 62017.7 | 257.5 | 257.5 | New pressure tank equipment installed, commissioned Jun 05 and began operational use in the harvest processing period, Sep. 05. However, TARIS' present installation location is temporary and equipment will be moved to TARIS' new plant by end '06 at which time MeBr use will terminate and remaining MeBr will be phased out. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and integral skin foams at Urosan | Individual | EUR | TUR | FOA | 32 | INV | 70 | N | O | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-03-01 | 2004-12-01 | 291641 | -815.56 | 290825.44 | 290825.44 | 100% | 0 | 0 |  | 37913.33 | -106.02 | 37807.31 | 0 | 0 | Project completed. | [7 empty] | 2004-01-01 |  |  | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and HCFC-141b for integral skin foams at 11 enterprises (Erdogan Rurmenler; KarakayaCelik; Una Polyuretan; Iksan Ltd; Ak-Kom; Karsan; Goldsit; Buoflex; Gervener; Yaris Kabin; Hisarlar) | Individual | EUR | TUR | FOA | 32 | INV | 71 | N | O | I | CFC | 48.5 | 48.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-06-01 | 2005-07-01 | 398378 | -277445.52 | 120932.48 | 120932.48 | 100% | 0 | 0 |  | 51789.14 | -36067.98 | 15721.22 | -0.06 | -0.06 | Project completed and non-ODS production at all 5 participating companies underway. | [7 empty] | 2004-01-01 |  |  | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Renewal of institutional strengthening | Individual | EUR | TUR | SEV | 32 | INS | 73 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 | 2006-04-01 |  |  | 200000 | 0 | 200000 | 143418.59 | 71.71% | 56581.41 | 56581.41 | 56581.41 | 26000 | 0 | 18644.41 | 7355.59 | 7355.59 | Remaining funds will be used for MeBr Resource group studies under MARA. A respective Action Plan has been prepared and approved by MARA. Upon review of the Action Plan and no objection by the WB (expected Mar. 06), the last disbursement from the 2nd IS will be made to MARA. | [10 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Total phase out of CFCs plan: 2001 and 2002 annual programmes | Multiyear | EUR | TUR | PHA | 35 | INV | 75 | N | O | I | CFC | 97 | 97 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 |  | 295000 | 0 | 295000 | 0 | 0 | Conversion 61 SMEs, first and second phase of training and 2 companies' chiller conversion completed. SME site visits ongoing. | [10 empty] | 2001 | INV | 977 | 699 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | Individual | EUR | TUR | SOL | 35 | INV | 76 | N | O | I | TCA | 15.4 | 15.4 | 0 | 0 | 2001-12-01 | 2003-11-01 | 2004-01-01 |  | 2005-02-01 | 2005-12-01 | 518693 | 0 | 518693 | 473213.84 | 91.23% | 45479.16 | 0 |  | 67056.23 | 0 | 61517.82 | 5538.41 | 0 | All 16 projects completed. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation in the methyl bromide sector (storage of hazelnut) |  | EUR | TUR | FUM | 36 | PRP | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2004-12-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 |  | 5200 | -5200 | 0 | 0 | 0 | Due to reorganization of MARA and personnel changes following a newly elected government funding is returned while Gov. weighs its options on a way forward. | [10 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Total phase out of CFCs plan: 2003 annual programme | Multiyear | EUR | TUR | PHA | 38 | INV | 79 | N | O | I | CFC | 375 | 375 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 2500000 | 0 | 2500000 | 1809088.61 | 72.36% | 690911.39 | 690911.39 | 690911.39 | 175000 | 0 | 126636.2 | 48363.8 | 48363.8 | Conversion of 13 SMEs completed. 1st and 2nd phase of training completed. 3rd phase of training will be started by MoEdu as explained in the annual report. Customs training completed and program will be continued. R&R component continues. Chillers component continues with conversion of 5 companies as of end '05. | [10 empty] | 2002 | INV | 534 | 457.16 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | EUR | TUR | HAL | 38 | TAS | 80 | N | O | I | HAL | 118 | 0 | 0 | 0 | 2002-11-01 |  | 2005-11-01 | 2007-12-01 |  |  | 439250 | 0 | 439250 | 0 | 0% | 439250 | 439250 | 220000 | 57102.5 | 0 | 0 | 57102.5 | 57102.5 | Delays due to time needed to select a suitable and willing executing agency. METU, in the end, could not find a suitable location for operating the facility. Energy Systems and Environmental Research Institute under Marmara Research Center of TUBITAK then agreed to implement the project. A WB mission visited the institute and endorsed it as an acceptable executing agency. MRC was also unable to do the project due to legal barriers. Another executing agency (ASO-Ankara Chamber of Industry) was identified and has agreed to execute project. Halon project action plan prepared in Aug. 05 and approved by WB. Contract signing with ASO-Ankara Chamber of Industry will be in Jan. 06. | [10 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | Total phase-out of CFCs plan: 2004 annual programme | Multiyear | EUR | TUR | PHA | 41 | INV | 81 | N | O | I | CFC | 218 | 218 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 1000000 | 0 | 1000000 | 636757.85 | 63.68% | 363242.15 | 363242.15 | 363242.15 | 150000 | 0 | 95513.67 | 54486.33 | 54486.33 | Conversion of 3 SMEs completed. Implementation of chillers, R&R and management components of the project continues with the conversion of 2 of 4 chiller companies. | [10 empty] | 2003 | INV | 316 | 258.16 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Total phase-out of CFCs plan: 2005 annual programme | Multiyear | EUR | TUR | PHA | 44 | INV | 85 | N | O | I | CFC | 150 | 166 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 |  | 750000 | 0 | 750000 | 105277.39 | 14.04% | 644722.61 | 644722.61 | 300000 | 45000 | 0 | 6316.64 | 38683.36 | 38683.36 | For activities under this AP, 2 chiller contracts and 1 end-user contract signed in 2005. Chiller, R&R, end-user and management components continue. | [10 empty] | 2004 | INV | 150 | 132 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Extension of institutional strengthening project (phase III) | Individual | EUR | TUR | SEV | 44 | INS | 86 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 | 2007-06-01 |  |  | 260000 | 0 | 260000 | 29663.38 | 11.41% | 230336.62 | 230336.62 | 115168.31 | 19500 | 0 | 2224.75 | 17275.25 | 17275.25 | Project has been started by both MoEF and MARA in 2005 and is continuing. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Total phase-out of CFCs plan: 2006 annual programme | Multiyear | EUR | TUR | REF | 47 | INV | 87 | N | O | I | CFC | 150 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 750000 | 0 | 750000 | 0 | 0% | 750000 | 750000 | 350000 | 30000 | 0 | 0 | 30000 | 30000 | Tranche newly approved and implementation underway. | [10 empty] | 2005 | INV | 0 | 0 | 0 | 0 |  | No | No
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | URU | SEV | 12 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -41688 | 58312 | 58312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in thermal tanks at Tem, S.A. | Individual | LAC | URU | FOA | 15 | INV | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-08-01 |  |  | 1996-04-01 | 220300 | -220300 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Tem S.A. has closed down. The project was cancelled by the government on 4/29/96. Funds returned to Multilateral Fund 20th Meeting. |  |  | 1997-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in cold storage and substitution of CFC-12 used as refrigerant with HFC-134a at Colder S.R.L. | Individual | LAC | URU | REF | 15 | INV | 11 | N | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-08-01 |  | 1997-09-01 | 1998-08-01 | 325070 | 0 | 325070 | 325070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Company signed Subgrant Agreement in November '96. Implementation began in Fall /96. Product testing started in Fall /97. The project was completed in August 98. |  |  | 1997-12-01 | 1999-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foams used as insulation for refrigerators and substitution of CFC-12 used as refrigerant at Indurnor S.A. | Individual | LAC | URU | REF | 15 | INV | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-12-01 |  |  | 1999-07-01 | 448140 | -448140 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Indunor S.A. has closed down. The funds were returned to the Multilateral Fund on July 99 at the 28th Ex Com meeting |  |  | 1998-06-01 | 2000-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foam used as insulation in thermal tanks at Etchepare-Gil S.A. | Individual | LAC | URU | FOA | 15 | INV | 14 | N | O | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-08-01 |  | 1999-09-01 | 2000-01-01 | 235050 | 0 | 235050 | 235050 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project was technically completed by September 99 and financially completed in January 00. |  |  | 1997-09-01 | 1999-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | URU | SEV | 16 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 81278 | 0 | 81278 | 81278 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation is complete. Project is now under supervision. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and recycling of CFC-12 in maintenance workshops for industrial refrigeration equipment | Individual | LAC | URU | REF | 18 | TAS | 19 | N | O | I | CFC | 4 | 0 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-05-01 |  | 1999-10-01 | 2000-01-01 | 87647 | 0 | 87647 | 87647 | 100% | 0 | 0 |  | 11394.11 | 0 | 11394.11 | 0 | 0 | Implementation began in Fall'96. The funds were transferred to local UNDP office in September'97. During 1998 the equipment was purchased and the consultantwas paid. The equipment were distributed on March 99 . The project was completed by October 99. |  |  | 1997-06-01 | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 18 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project preparation completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Completing the elimination of CFC use in domestic refrigeration manufacturing by adoption of HCFC-141b as blowing agent and HFC-134a as refrigerant at Nevol S.A. | Individual | LAC | URU | REF | 19 | INV | 21 | N | O | I | CFC | 4.62 | 4.62 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-07-01 |  | 2000-02-01 | 1999-07-01 | 141512 | 0 | 141512 | 141512 | 100% | 0 | 0 |  | 18396.56 | 0 | 18396.56 | 0 | 0 | The project was completed in July 99 |  |  | 1997-07-01 | 1999-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 21 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project preparation completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Market survey to develop a country-wide scheme to phase out remaining ODS | Individual | LAC | URU | SEV | 22 | TAS | 24 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1998-07-01 | 1998-07-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0 | Time required for collecting and verifying consumption data was longer than originally anticipated. All disbursements have been made (US$ 23,000). Project completed. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of an investment project in the domestic refrigeration sector |  | LAC | URU | REF | 30 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [11 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Terminal programme for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | Individual | LAC | URU | FOA | 31 | INV | 34 | N | O | I | CFC | 4.35 | 4.35 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2002-01-01 |  | 2003-05-01 | 2003-05-01 | 91300 | -80 | 91220 | 91220 | 100% | 0 | 0 |  | 11869 | -10 | 11858.6 | 0.4 | 0.4 | Project completed. | [10 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | VEN | SEV | 04 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 70419 | -57546 | 12873 | 12873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 06 | CPG | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 61591 | -36591 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | VEN | SEV | 06 | PRP | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 107058 | 69729 | 176787 | 176787 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of a CFC-12 polystyrene foam production facility to use hydrocarbons as blowing agent at Plásticos Molanca | Individual | LAC | VEN | FOA | 07 | INV | 05 | N | O | I | CFC | 259 | 259 | 0 | 0 | 1992-06-01 | 1993-06-01 | 1993-06-01 |  | 1995-12-01 | 1996-04-01 | 1300000 | -38322 | 1261678 | 1261678.18 | 100% | -0.36 | -0.36 |  | 0 | 0 | 0 | 0 | 0 | ICR issued in May/96. The final project cost amounted to about US$2 million. The overrun was absorbed by enterprise. |  |  | 1995-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto Venezolano de los Seguros Sociales | Individual | LAC | VEN | REF | 08 | INV | 08 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1995-07-01 | 851000 | -851000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Cancelled. |  |  | 1994-04-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Clínica Atias, Hospitalización y Servicios | Individual | LAC | VEN | REF | 08 | INV | 09 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-10-01 | 1996-12-01 | 1994-04-01 |  | 1997-01-01 | 1997-02-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-01-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto de Prevencion Social del Médico | Individual | LAC | VEN | REF | 08 | INV | 10 | N | O | D | CFC | 2 | 2 | 0 | 0 | 1992-10-01 | 1995-12-01 | 1994-04-01 |  | 1995-09-01 | 1997-02-01 | 69000 | 0 | 69000 | 69000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Congreso de la Republica | Individual | LAC | VEN | REF | 08 | INV | 11 | N | O | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1998-05-01 | 65000 | -65000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Retroactive project physically completed, but enterprise chose not to utilize MLF funds. Funds returned to MLF. |  |  | 1995-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | VEN | SEV | 09 | PRP | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 156200 | 23305 | 179505 | 179505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a heat exchangers at Fabrica de Aparatos de Aire Acondicionado, S.A. (Faaca) | Individual | LAC | VEN | REF | 11 | INV | 19 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1995-11-01 |  | 1998-02-01 | 1998-02-01 | 3480000 | -380000 | 3100000 | 3100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a compressors and heat exchangers at Aire Acondicionado Integral, S.A. (Aaisa) | Individual | LAC | VEN | REF | 11 | INV | 20 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1996-09-01 |  | 1998-06-01 | 1998-10-01 | 620000 | 3800000 | 4420000 | 4420000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Faaca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -26845 | 20345 | 20345 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Aaisa project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -28772 | 18418 | 18418 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Plásticos Molanca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 83236 | 9685 | 92921 | 92921 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for finalizing project preparation and for project supervision. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of air conditioners project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 28665 | -22792 | 5873 | 5873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS V (Aaisa) (1995) |  | LAC | VEN | SEV | 16 | PRP | 33 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 22455 | 0 | 22455 | 22455 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is now complete. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (Faaca) (1995) |  | LAC | VEN | SEV | 16 | PRP | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 19121 | 0 | 19121 | 19121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I and II (1995) |  | LAC | VEN | SEV | 16 | PRP | 35 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 36430 | 0 | 36430 | 36430 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (central air chillers) (1995) |  | LAC | VEN | SEV | 16 | PRP | 36 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 23966 | 0 | 23966 | 23966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 18 | PRP | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-12-31 |  | 1996-12-31 | 1996-12-31 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project has been dropped in FY97. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 21 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project has been dropped in FY97. | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 04 | CPG | 59 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 30313 | -27612 | 2701 | 2701 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the CFC production phase out project |  | LAC | VEN | PRO | 41 | PRP | 97 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2004-04-01 | 2004-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Project was prepared and subsequently approved at the 44th ExCom in Dec. 04. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Phased reduction and closure of the entire CFC production: 2004 annual programme | Multiyear | LAC | VEN | PRO | 44 | INV | 101 | N | O | I | CFC | 0 | 0 | 1487 | 1487 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 |  | 3300000 | 0 | 3300000 | 3295000 | 99.85% | 5000 | 5000 | 5000 | 247500 | 0 | 247125 | 375 | 375 | A total of $3.2 million was disbursed to PRODUVEN and $95,000 was disbursed to FONDOIN for TA activites. Remaining $5,000 under this tranche is expected to be disbursed by Jun 06 as activities advance. | [10 empty] | 2004 | INV | 0 | 0 | 4400 | 3564.73 | Yes | Yes | Yes
ONG | IBRD | National CFC production closure plan (second tranche) | Multiyear | LAC | VEN | PRO | 46 | INV | 106 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 | 2006-07-01 |  |  | 8100000 | 0 | 8100000 | 8000000 | 98.77% | 100000 | 100000 | 100000 | 607500 | 0 | 600000 | 7500 | 7500 | 2004 audit took place in Feb 05. Production was 19% below the quota for that year (4,400 MT). $8 million were approved for PRODUVEN, and $100k for FOINDOIN for TA activities (2005 AP). To date, $8 million were disbursed to PRODUVEN. Remaining funds ($100k) are expected to be used during the course of 2006. | [10 empty] | 2005 | INV | 0 | 0 | 2913 | 2451.4 | Yes | Yes | Yes
FIN | IBRD | Preparation of a national CFC phase-out plan |  | ASP | VIE | PHA | 39 | PRP | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Project preparation completed and project approved at the 45th ExCom. | [10 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Project preparation for methyl bromide phase-out plan |  | ASP | VIE | FUM | 44 | PRP | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 | 2006-11-01 |  |  | 65000 | 0 | 65000 | 12000 | 18.46% | 53000 | 53000 | 53000 | 4875 | 0 | 900 | 3975 | 3975 | National consulting team was appointed in Oct. 05. Data collection process initiated immediately after the contract signing. Draft data collection report will be available by end of Apr 06. Stakeholders workshops are scheduled for May 06 with draft final project proposal to be ready by Aug 06. | [10 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC and halon phase-out plan (first tranche) | Multiyear | ASP | VIE | PHA | 45 | INV | 45 | N | O | I | CFC | 40 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 495537 | 0 | 495537 | 0 | 0% | 495537 | 495537 | 400000 | 37165 | 0 | 0 | 37165 | 37165 | Government of Vietnam established an import/export licensing system, which is one of the policy recommendations of the Plan, in Jul 05. Import/export licensing system in operations since then. Ban on imports of CFC containing equipment will be issued Jan 06. PMU established Oct. 05. PMU fully staffed since Q3 05. Grant Agreement between Vietnam and WB will be signed Jan 06 allowing approved funds to be used for implementing the Plan and also to retroactively cover the cost of PMU operations in 2005. Other activities conducted in 2005 were the establishment of a quota system, development of specs for refrigeration servicing tool kits as well as for refrigerant identifiers. | [10 empty] | 2004 | INV | 258.5 | 241 | 0 | 0 |  | No | No
FIN | IBRD | Country programme preparation |  | EUR | YUG | SEV | 04 | PRP | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 20302 | -14877 | 5425 | 5425 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | EUR | YUG | SEV | 04 | PRP | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 21432 | -21432 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | AFR | ZIM | SEV | 18 | PRP | 05 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-31 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | [12 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ref-air Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 06 | N | O | I | CFC | 5.3 | 5.3 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2000-11-01 | 2000-11-01 | 43382 | 0 | 43382 | 43382 | 100% | 0 | 0 |  | 5639.66 | 0 | 5639.66 | 0 | 0 | Because of economic difficulties in Zimbabwe (including significant local currency devaluation and unavailability of forex), not much progress was made until CY00 and the project was completed by 11/00. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Commercial Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 07 | N | O | I | CFC | 6.9 | 6.9 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2001-08-01 | 2001-08-01 | 156636 | -15061 | 141575 | 141575 | 100% | 0 | 0 |  | 20363 | -1957.93 | 18405.07 | 0 | 0 | Project completed. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Capri Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 08 | N | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-10-01 |  | 1999-11-01 | 1999-11-01 | 106695 | 0 | 106695 | 106695 | 100% | 0 | 0 |  | 13870 | 0 | 13870 | 0 | 0 | CFC-11 portion completed 2/97 and CFC-12 portion completed 6/99, but because of the economic difficulties in Zimbabwe (including significant local currency devaluation) and the change of ownership of the company, not much progress was made during CY98. The project was completed in 08/99. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to cyclopentane as the blowing agent for foam insulation at Imperial Derby Refrigeration Ltd. | Individual | AFR | ZIM | REF | 20 | INV | 09 | N | O | I | CFC | 14 | 12.85 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-12-01 |  | 1996-03-01 | 2001-05-01 | 310000 | -88275 | 221725 | 221725 | 100% | 0 | 0 |  | 40300 | -11476 | 28824.25 | -0.25 | -0.25 | Project completed. Funds returned at the 35th ExCom. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ajax Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 10 | N | O | I | CFC | 3.5 | 3.5 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2001-10-01 |  | 1997-01-01 | 2001-08-01 | 61966 | 0 | 61966 | 61966 | 100% | 0 | 0 |  | 8056 | 0 | 8056 | 0 | 0 | Company taken over by Commercial Refrigeration and now treated as 2nd production line at Commercial. Project combined with that of Commercial Refrigeration as approved. Financial completion date is the same as Commercial. |  |  |  | 1999-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | Israel | International methyl bromide compliance assistance workshop (Bahamas, Barbados, Bosnia, Congo, Ecuador, Ethiopia, Moldova, Mexico, and Zambia) | Individual | GLO | GLO | FUM | 37 | TRA | 240 | N | O | D |  | 0 |  | 0 |  | 2002-07-01 |  | 2003-03-01 |  | 2002-12-01 |  | 98300 | -64177 | 34123 | 34123 | 100% | 0 | 0 | 0 | 9830 | -5847 | 3983 | 0 | 0 | The workshop was completed as planned. The goals were achieved and feedback from participants was very positive. The numbers of participants were lower than the maximum potential cited in the proposal. Costs were lower than expected. Two countries, Bahamas and Barbados, did not send participants. Participants from Ethiopia did not arrive due to logistical problems. Please see extended summary for further details of workshop content and outputs. * In addition to estimated disbursement stated, there will be support costs at 10%. |  | 2002 | [8 empty] | 2002 | Non-Investment
FIN | Italy | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors | Multi-year | ASP | CPR | REF | 38 | INV | 393 | A | O | I | CFC | 181 | 181 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2005-11-01 |  | 2005-10-01 | 2005-12-01 | 1788991 | 0 | 1788991 | 1788991 | 100% | 0 | 0 | 0 | 161009 | 0 | 161009 | 0 | 0 | Project completed in Oct 2005. Financial completion internally in Dec 2005. |  | 2003 | [8 empty] | 2002 | Investment | 0 | 0 |  |  | n.a. | n.a. | n.a.
ONG | Italy | National phase-out of methyl bromide (phase II) | Multi-year | ASP | CPR | FUM | 46 | INV | 431 | A | O | I | MBR | 534 | 0 | 0 | 0 | 2005-07-01 |  | 2015-07-01 | 2015-07-01 |  |  | 4000000 | 0 | 4000000 | 0 | 0% | 4000000 | 0 | 900000 | 470000 | 0 | 0 | 470000 | 0 | Funds have been transferred to the implementing agency in 2006. In 2006, equipment will be purchased for the tobacco sector and action plans will be prepared for the strawberry, vegetable and flower sectors. Equipment procurement will be set according to SEPA's priorities. |  | 2005 | [8 empty] | 2005 | Investment | 880 | 880 |  |  | n.a. | n.a. | n.a.
COM | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Flexo Foam P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 307 | A | O | I | CFC | 19.4 | 19.4 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-04 |  | 185241 | 0 | 185241 | 183881.2567 | 99.27% | 1359.7433 | 1460.41 | 0 | 24081 | 0 | 23904.2358 | 176.7642 | 189.8507 | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. |  | 2001 | [8 empty] | 2001 | Investment
COM | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sutlej Coach Products P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 318 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-04 |  | 187400 | 0 | 187400 | 185518.1596 | 99% | 1881.8404 | 1911.47 | 0 | 24362 | 0 | 24117.3608 | 244.6392 | 248.4911 | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in June 04. |  | 2001 | [8 empty] | 2001 | Investment
COM | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Malvika Polymers | Individual | ASP | IND | FOA | 34 | INV | 319 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-04 |  | 196610 | 0 | 196610 | 194477.5685 | 98.92% | 2132.4315 | 1690.95 | 0 | 25559 | 0 | 25281.7872 | 277.2128 | 219.8209 | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. |  | 2001 | [8 empty] | 2001 | Investment
COM | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Oto Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 336 | A | O | I | CFC | 12.7 | 12.7 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-04 |  | 139716 | 0 | 139716 | 137141.7089 | 98.16% | 2574.2911 | 1297.18 | 0 | 18163 | 0 | 17828.3436 | 334.6564 | 168.6327 | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. |  | 2001 | [8 empty] | 2001 | Investment
ONG | Italy | Phase out of methyl bromide in horticulture | Individual | EUR | ROM | FUM | 34 | INV | 19 | A | O | I | MBR | 93.9 | 93.9 | 0 | 0 | 2001-07-01 | 2002-02-26 | 2005-08-01 | 2006-12-01 |  |  | 630517 | 0 | 630517 | 580925 | 92.13% | 49592 | 21989 | 49592 | 79357 | 0 | 42318.64 | 37038.36 | 17401.67 | Equipment installation was completed in 2005. A final regional workshop will be held in Bucharest in June 2006. The monitoring of the 2006 crop season will continue. The project will be completed in December 2006. |  | 2001 | [8 empty] | 2001 | Investment
ONG | Italy | Replacement of CFC-11 with cyclopentane foam blowing agent and CFC-12 with HFC-134a refrigerant in the manufacture of domestic refrigerators and freezers at Obod Elektroindustria | Individual | EUR | YUG | REF | 34 | INV | 13 | A | O | I | CFC | 94.9 | 0 | 0 | 0 | 2001-07-01 | 2002-09-01 | 2003-10-01 | 2006-12-01 |  |  | 1683135 | 0 | 1683135 | 1401807 | 83.29% | 281328 | 199474 | 280000 | 180348 | 0 | 149402 | 30946 | 21942 | There was big snow fall in February 2005 with accumulation of 3 meters, and the factory roof and a part of already installed cyclopentane foaming system were broken due to this natural disaster. The repair work of the infrastructure has progressed in cooperation with the Government. It is estimated that the new foaming system will be commissioned by December 2006. It is to be noted that the enterprise banned the use of CFCs in the manufacture of appliances from the end 2003. |  | 2001 | [8 empty] | 2001 | Investment
FIN | Japan | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 33 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-02-01 | 2002-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Regional workshop on monitoring and control of ODS consumption for the South Asia region | Individual | ASP | ASP | SEV | 29 | TRA | 34 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-07-01 | 2001-06-01 |  | 2001-08-01 | 2002-06-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region | Individual | ASP | ASP | SEV | 34 | TAS | 41 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2003-05-01 |  | 148500 | 0 | 148500 | 148500 | 100% | 0 | 0 | 0 | 19305 | 0 | 19305 | 0 | 0 | Project completed in May 2003. Balance of 25,000 USD transferred to Phase II for partly covering activities in Mongolia |  | 2001 | [9 empty] | Non-Investment
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region (phase 2) | Individual | ASP | ASP | SEV | 38 | TAS | 49 | A | O | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-06-01 | 2003-11-01 |  | 2004-03-01 |  | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 | 0 | 16250 | 0 | 16250 | 0 | 0 | Mongolia: Public awareness and IEC activities; Task Force Meeting China/Mongolia August 2003 / Iran: 15-02-04 National Consultation Meeting. Some funds were also used for building urgent capacity in the two new Parties Afghanistan and Bhutan as part of UNEP-Japan expedited assistance approach. |  | 2002 | [9 empty] | Non-Investment
FIN | Japan | Phasing out ODS in the production of compressors at Changshu Refrigerating Equipment Works |  | ASP | CPR | REF | 28 | INV | 302 | A | O | I | CFC | 75 | 75 | 0 |  | 1999-07-01 | 2001-11-01 | 2002-12-01 |  | 2004-10-01 | 2005-12-01 | 2250000 | 0 | 2250000 | 2246858 | 99.86% | 3142 | 0 | 0 | 257500 | 0 | 248026 | 9474 | 9128 | The project was succesfully completed in October 2004. |  | 1999
FIN | Japan | Project preparation assistance for enterprises in the city of Shenzhen for the elimination of CFC-113 and TCA in the production lines of LC display and TV picture tube |  | ASP | CPR | SOL | 29 | PRP | 307 | A | O | I | CFC-113andCTA | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2003-07-01 | 50000 | 0 | 50000 | 19084 | 38% | 30916 |  | 0 | 6500 | 0 | 2481 | 4019 | 0 | Completed. Project proposal prepared but activities incorporated into China Solvent Sector Plan |  | 1999
FIN | Japan | Develop a strategy for the refrigeration servicing sector | Individual | ASP | CPR | REF | 31 | TAS | 359 | A | O | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-07-01 | 2001-12-01 |  | 2003-12-01 | 2005-06-01 | 350000 | 0 | 350000 | 348624 | 99.61% | 1376 | 0 | 0 | 45500 | 0 | 45500 | 0 | 0 | Completed the data survey for the four sub-sectors and developed the first draft strategy. The national workshop was organized in July 2002 to review the draft. The second draft is being prepared as per comments received from the workshop and other sources. |  | 2000
COM | Japan | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 420 | A | O | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2005-12-01 |  | 1000000 | 0 | 1000000 | 413600 | 41.36% | 586400 | 586400 | 586400 | 130000 | 0 | 53768 | 76232 | 76232 | Revised annual implementation plan was approved by 45th ExCom in Apr 2005. Contract was signed for support services and purchase of recovery and recycling equipment for disposal centre. Equipment was delivered. 511 ODP tonnes were phased out in 2005 as a result of UNIDO's and Japan's activities. However, phase-out will be reflected under Japanese component to follow inventory. The second tranche (Japanese contribution) was approved by 47th ExCom in Nov 2005. Institution and trainers were selected for training of trainers workshops. In 2006, training of trainers and technicians training programme was continued. In Apr 2006, study tour to equipment suppliers was undertaken to finalize equipment specifications for servicing workshops and automobile disposal stations. Awareness campaign will be made and service R&R equipment will be purchased (under Japanese component). |  | 2004 | [9 empty] | investment | 5083 | 4868 | not applicable | not applicable | Yes | Yes | Yes
ONG | Japan | Refrigeration servicing sector CFC phase-out plan: second tranche | Multi-Year | ASP | CPR | REF | 47 | INV | 438 | A | O | I | CFC | 511 | 511 | 0 |  | 2005-11-01 |  | 2006-12-01 | 2007-12-01 |  |  | 3000000 | 0 | 3000000 |  | 0% | 3000000 | 2300 | 1000000 | 390000 | 0 | 0 | 390000 | 299 | Revised annual implementation plan was approved by 45th ExCom in Apr 2005. Contract was signed for support services and purchase of recovery and recycling equipment for disposal centre. Equipment was delivered. 511 ODP tonnes were phased out in 2005 as a result of UNIDO's and Japan's activities. However, phase-out will be reflected under Japanese component to follow inventory. The second tranche (Japanese contribution) was approved by 47th ExCom in Nov 2005. Institution and trainers were selected for training of trainers workshops. In 2006, training of trainers and technicians training programme was continued. In Apr 2006, study tour to equipment suppliers was undertaken to finalize equipment specifications for servicing workshops and automobile disposal stations. Awareness campaign will be made and service R&R equipment will be purchased (under Japanese component). |  | 2005 | [9 empty] | investment
COM | Japan | Workshop on concessional lending | Individual | GLO | GLO | SEV | 35 | TRA | 233 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-02 | 2002-12-01 |  | 2003-03-01 |  | 75000 | 0 | 75000 | 57705.86 | 76.94% | 17294.14 | 0 | 0 | 9750 | 0 | 7501.7618 | 2248.2382 | 0 | Project completed in March 2003 |  | 2001
FIN | Japan | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances |  | GLO | GLO | SEV | 41 | TAS | 254 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2006-02-01 | 2004-11-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 |  |  | 2003
COM | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Aneka Citra Refrigeratama Co. |  | ASP | IDS | FOA | 37 | INV | 145 | A | O | I | CFC-11 | 18.2 |  | 0 |  | 2002-07-01 | 2004-11-01 | 2004-09-01 |  | 2005-09-01 |  | 142506 | 0 | 142506 | 142129 | 99.74% | 377 | 12 | 12 | 18525.78 | 0 | 18476.77 | 49.01 | 1.56 | Foaming equipment has been delivered commisioned and full operation of the plant resumed. The last payment of the IOC will be executed upon signature of the draft PCR. The project completed in March 2006. |  | 2002 | [9 empty] | investment
ONG | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Bina Teknik Co. | Individual | ASP | IDS | FOA | 37 | INV | 146 | A | O | I | CFC-11 | 22.8 |  | 0 |  | 2002-07-01 | 2003-12-01 | 2005-03-01 | 2006-03-01 |  |  | 117889 | 0 | 117889 | 117348 | 99.54% | 541 | 0 | 500 | 15325.57 | 0 | 15255.24 | 70.33 | 0 | Foaming equipment has been delivered commisioned and full operation of the plant resumed. The last payment of the IOC will be executed upon signature of the draft PCR. The project completed in March 2006. |  | 2002 | [9 empty] | investment
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year Partial | ASP | IND | PHA | 42 | INV | 376 | N | O | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2005-11-01 | 2005-04-01 | 2006-11-01 |  |  | 2500000 | 0 | 2500000 | 1797457 | 72% | 702543 |  | 702543 | 280000 | 0 | 233669 | 46331 |  | Bid evaluation initiated early 2006, due to technical clarifications between end-user enterprises and equipment supplier and internal UNDP procurement procedures, PO was issued only in November 2005
ONG | Japan | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 389 | N | O | I | CTC | 533 |  | 0 |  | 2005-04-01 |  | 2008-04-01 | 2006-11-01 |  |  | 2500000 | 0 | 2500000 |  | 0% | 2500000 |  | 1500000 | 280000 | 0 |  | 280000 |  | PO issued, manufacture of equipment in progress. Expected delivery first quarter 2006, to be followed by installation/commissioning. Project to be completed November 2006
COM | Japan | Preparation of a terminal phase-out management plan |  | ASP | MON | PHA | 45 | PRP | 09 | A | O | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2005-10-01 |  | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 4407 | 0 | 4407 | 0 | 0
ONG | Japan | Terminal phase-out management plan: first tranche | Multi-Year | ASP | MON | PHA | 47 | INV | 10 | N | O | I | CFC | 0.7 |  | 0 |  | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 19500 | 0 | 0 | 19500 | 19500
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Eastern Wrought Iron Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 73 | A | O | I | CFC-11 | 27.1 | 27.1 | 0 |  | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2004-11-01 | 2006-05-01 | 109345 | 0 | 109345 | 106138 | 97.07% | 3207 | 0 | 0 | 14215 | 0 | 13798 | 417 | 390 | Operationally completed November 2004. COC issued |  | 2000 | [9 empty] | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Mac-Vico (Nig.) Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 74 | A | O | I | CFC-11 | 28.4 | 28.4 | 0 |  | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-07-01 | 2003-10-01 | 105209 | 0 | 105209 | 105209 | 100% | 0 | 0 | 0 | 13677 | 0 | 13677 | 0 | 0 | Operationally completed July 2003, financially completed October 2003 |  | 2000 | [9 empty] | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Martchem Industries Limited (at 2 plants) by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 75 | A | O | I | CFC-11 | 38.4 | 38.4 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2003-03-01 | 2003-10-01 | 175121 | 0 | 175121 | 175121 | 100% | 0 | 0 | 0 | 22766 | 0 | 22766 | 0 | 0 | Operationally and financially completed 2003 |  | 2000 | [9 empty] | investment
ONG | Japan | Assistance for a national information, education and communication campaign for compliance with the Montreal Protocol | Individual | AFR | NIR | SEV | 38 | TAS | 104 | A | O | I | CFC | 5.6 |  | 0 |  | 2002-11-01 | 2004-12-01 | 2003-11-01 | 2006-12-01 |  |  | 68000 | 0 | 68000 | 7100 | 10.44% | 60900 | 25000 | 60900 | 8840 | 0 | 923 | 7917 | 3250 | Preparation for a stakeholders’ workshop which had been scheduled for March 2006 has been made. |  | 2002
ONG | Japan | National compliance action plan: incentive programme for commercial and industrial refrigeration end-users | Individual | ASP | SRL | PHA | 43 | TAS | 26 | A | O | I | CFC | 5 |  | 0 |  | 2004-07-01 |  | 2005-12-01 | 2007-12-01 |  |  | 144000 | 0 | 144000 |  | 0% | 144000 |  | 8000 | 18720 | 0 |  | 18720 |  | The national consultant has been selected, whose CV is being reviewed within the UNOPS and the necessary TORs and MOUs are being prepared. For UNEP-implemented components, the MOU has been signed. |  | 2004
ONG | Japan | National compliance action plan: MAC recovery/recycling and retrofit | Individual | ASP | SRL | PHA | 43 | TAS | 27 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 |  | 2005-12-01 | 2006-12-01 |  |  | 123000 | 0 | 123000 |  | 0% | 123000 |  | 123000 | 15990 | 0 |  | 15990 |  | The national consultant has been selected, whose CV is being reviewed within the UNOPS and the necessary TORs and MOUs are being prepared. For UNEP-implemented components, the MOU has been signed. |  | 2004
ONG | Japan | National compliance action plan: recovery and recycling programme | Individual | ASP | SRL | PHA | 43 | TAS | 28 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 |  | 2006-12-01 | 2006-12-01 |  |  | 290400 | 0 | 290400 |  | 0% | 290400 |  | 290400 | 37752 | 0 |  | 37752 |  | The national consultant has been selected, whose CV is being reviewed within the UNOPS and the necessary TORs and MOUs are being prepared. For UNEP-implemented components, the MOU has been signed. |  | 2004
ONG | Japan | National compliance action plan: monitoring the activities proposed in the plan | Individual | ASP | SRL | PHA | 43 | TAS | 29 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 |  | 2009-12-01 | 2009-12-01 |  |  | 108000 | 0 | 108000 | 3667.36 | 3.39% | 104333 | 0 | 8000 | 14040 | 0 |  | 14040 |  | The national consultant has been selected, whose CV is being reviewed within the UNOPS and the necessary TORs and MOUs are being prepared. For UNEP-implemented components, the MOU has been signed. |  | 2004
FIN | Poland | Implementation of the RMP: Customs training programme | RMP Update | ASP | VIE | REF | 34 | TAS | 37 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-01-01 |  | 2003-01-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Reason for delays in completion of Phase I of the Project was a delay in the payment of Polish contribution covering a cost of the project because of problems with national budget. Payment of outstanding contribution was confirmed through a letter of 21 March 2002 from the UN Office in Nairobi (CP/4040-01-71).
ONG | Portugal | Communication and cooperation support to Portuguese speaking countries (Angola, Cape Verde, East Timor, Guinea Bissau, Mozambique and Sao Tome and Principe) | Individual | GLO | GLO | SEV | 47 | TAS | 269 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 90000 | 0 | 90000 |  | 0% | 90000 |  |  | 11700 | 0 |  | 11700
FIN | Singapore | Regional methyl chloroform elimination programme for ASEAN countries |  | ASP | ASP | SOL | 11 | TAS | 12 | A | O | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 |  | 1995-03-01 |  | 31976 | 0 | 31976 | 31976 | 100% | 0 | [9 empty] | 93
FIN | Singapore | Training workshop on CFC-113 and methyl chloroform substitutes and alternative technologies in ASEAN countries |  | ASP | ASP | REF | 13 | TRA | 15 | A | O | D |  | 0 |  |  |  | 1994-07-01 |  | 1995-07-01 |  | 1995-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | [9 empty] | 94
FIN | Slovak Republic | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 03 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 14622 | 0 | 14622 | 14622 | 100% | 0 |  |  | 1901 | 0 | 1901 | 0
FIN | South Africa | Industry workshop on the practical implementation of the Protocol for English-speaking countries |  | AFR | AFR | SEV | 11 | TRA | 07 | A | O | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 | 1994-09-01 | 1994-09-01 | 1994-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | [9 empty] | 94
ONG | Spain | Total phase-out of MB used in tobacco, flowers, ornamental plants, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 272 | A | O | I | MBR | 65.4 |  | 0 |  | 2005-07-01 |  | 2007-07-01 | 2007-07-01 |  |  | 580390 | 0 | 580390 |  | 0% | 580390 |  | 200000 | 75451 | 0 |  | 75451 |  | The funds for the project were approved in January 2006. Expected date of completion: Jul 2007. |  | 2005 | [8 empty] | 2005 | Investment
ONG | Spain | Policy assistance to support the methyl bromide phase-out with special focus in Guatemala and Honduras | Individual | LAC | LAC | FUM | 47 | TAS | 37 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  |  |  | 80000 | 0 | 80000 |  | 0% | 80000 |  |  | 10400 | 0 |  | 10400 |  | This Project was approved on ExCom 47th, December 2005. First contacts for money transfer were initiated on December 2005
ONG | Spain | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 118 | A | O | I | MBR | 107.2 | 0 | 0 |  | 2004-04-01 | 2005-10-01 | 2006-10-01 | 2006-12-01 |  |  | 707965 | 0 | 707965 | 45380 | 6.41% | 662585 | 125900 | 200000 | 87876 | 0 | 5899.4 | 81976.6 | 16367 | The project is being implemented as planned. A number of workshops have been organized in Mexico. According with prelimianary data the 20% reducttion of mehtyl bromide has been achieved. Expected date of completion: Dec 2006. |  | 2004 | [8 empty] | 2004 | Investment
ONG | Spain | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | PAR | FUM | 47 | TAS | 15 | A | O | I | MBR | 0.2 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  |  |  | 40000 | 0 | 40000 |  | 0% | 40000 |  |  | 5200 | 0 |  | 5200 |  | This Project was approved on ExCom 47th, December 2005. First contacts for money transfer were initiated on December 2005
FIN | Sweden | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 31 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2001-02-01 | 2002-05-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | Regional Workshop on Control and Monitoring of ODS Consumption for the Southeast Asia/Pacific Region (funded with equal bilateral contributions from Sweden and Japan and implemented through UNEP) was held 22-27 May 2000 and was attended by ozone and customs officers from ten countries in the region. The participating countries developed a joint set of declarations and drafted national action plans for further work in their respective country. The report from the workshop was prepared by Sweden in February 2001. The project completion report prepared in coordination with UNEP was submitted 1 May 2002. The project was financially completed 27 May 2002. |  | 1999 | [8 empty] | 1999
ONG | Sweden | Regional cooperation for monitoring and control of ODS consumption | Individual | ASP | ASP | SEV | 34 | TAS | 42 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-03-01 | 2005-04-01 | 2006-06-01 |  |  | 250000 | 200000 | 450000 | 402562 | 89% | 47438 | 47438 | 47438 | 0 | 26000 | 26000 | 0 | 0 | At the 34th Meeting of the Executive Committee, the Government of Sweden received approval for establishing a customs cooperation network in the SEAP region. At the 39th ExCom Sweden got approval for extending the project to the South Asia region. UNEP/ROAP has been contracted as implementing agency in collaboration with Sweden. A steering group is appointed for each meeting. Five successful meetings have been held for the SEAP participants and three of these meetings have been held jointly with the SA participants. The final meeting will be held in Thailand in May 2006. Meetings and work tasks in between meetings have allowed for substantial capacity building of the officers involved. Some of the practical achievements so far are improved national cooperation between ozone and customs officers; improved regional information exchange such as an agreement to share information on licensed ODS importers and exporters regionally and annually. A desk study on imports and exports between the countries in the region have also been undertaken which highlighted the discrepancies between the reported i/e figures and demonstrated the need to improve the monitoring and control of ODS further. |  | 2001/2002 | [8 empty] | 2001
FIN | Sweden | Assistance to prepare an RMP update | Individual | EUR | CRO | REF | 36 | PRP | 15 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2004-03-04 | 2004-04-04 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0 | At the 36th meeting in March 2002 Sweden received approval for assisting the Government of Croatia in updating their Refrigerant Management Plan (RMP Update). International and National consultants were contracted in June 2002. A survey of current ODS consumption and use in the servicing sector has been conducted followed by a desk study and sector review. A mission to Croatia to discuss proposed activities was held in November 2002. Due to ExCom decision regarding Terminal Phase-out Management Plans (TPMP) the Update was in January 2003 submitted as a TPMP, with Sweden as co-implementing agency and UNIDO as lead Implementing Agency, for approval at the 39th ExCom meeting. |  | 2002 | [8 empty] | 2002
FIN | Sweden | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | TAS | 18 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-09-03 | 2004-12-01 |  | 2005-06-01 | 2005-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 |  |  | 3450 | 0 | 3450 | 0 | 0 | Annual report submitted and approved at the 42nd ExCom meeting |  | 2003 | [8 empty] | 2003 | [5 empty] | yes
FIN | Sweden | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | CRO | PHA | 42 | TAS | 23 | A | O | I |  | 0 |  | 0 |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-12-01 | 2005-12-01 | 24700 | 0 | 24700 | 24700 | 100% | 0 |  |  | 1853 | 0 | 1853 | 0 | 0 | Annual report submitted and approved at the 46th ExCom meeting. |  | 2004 | [8 empty] | 2004 | [5 empty] | yes
ONG | Sweden | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 27 | A | O | I | CFC | 13 | 13 | 0 |  | 2005-07-01 | 2005-09-01 | 2006-07-01 | 2006-06-01 |  |  | 21500 | 0 | 21500 | 15749 | 73% | 5751 | 5751 | 5751 | 1613 | 0 | 1613 | 0 | 0 | The assistance to Croatia in the implementation of the TPMP is jointly implemented by UNIDO and Sweden, with UNIDO as the lead implementing agency. In May 2003, Sweden met UNIDO and a representative from the Ministry at a meeting in Vienna to discuss the implementation of the TPMP. Terms of Reference for the international and national consultants were prepared during May 2003. Two international and one national consultant are contracted. The first mission to Croatia was conducted in September 2003. During 2004 and 2005, the national ODS regulation (By-law) was revised and adopted. The reclamation equipment was delivered during autumn 2004. A mission took place in March 2005. The IC participated in the training of the reclamation facilities in October 2005. The SEI and the IC met with UNIDO in Vienna in September 2005 to discuss some outstanding issues. In March 2006 SEI received the final report from the national consultant |  | 2005 | [8 empty] | 2005
ONG | Sweden | Assistance to prepare a terminal phase-out management plan | Individual | EUR | GEO | PHA | 47 | PRP | 19 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 30000 | 3900 | 0 | 0 | 3900 | 3900 | In December 2005 at the 47th Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a Terminal phase-out management plan in Georgia. A national and an international consultant have been contracted and the first mission was undertaken in the beginning of February 2006. The national consultant is currently collecting additional data. A second mission is scheduled for early June to discuss the draft TPMP. The final TPMP will be submitted to the 50th ExCom meeting for consideration. |  | 2005 | [8 empty] | 2005
ONG | Sweden | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 253 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-10-01 |  | 2006-02-01 |  | 33874 | 0 | 33874 | 8972 | 26% | 24902 | 24902 | 24902 | 4404 | 0 | 4404 | 0 | 0 | At the 41st meeting of the Executive Committee, the Government of Sweden in collaboration with Japan received approval for developing a Handbook related to the servicing sector. A Draft outline of the Handbook with a broader perspective in accordance with the ExCom decision was developed in March 04. Two consultants were recruited and a first full Draft was developed in Feb. 2005. The Draft was revised substantially twice before the text was sent for a review by UNEP/DTIE, Japan and the NOUs of Croatia and the Philippines in June 2005. Responses were received in Aug-Sept 2005. After takning into account the comments received, the layout and printing was organised. The printed version was received in February 2006 and the distribution to all NOUs and relevant agencies was organised by UNEP. The Handbook is available at the UNEP and SEI web pages for down load. The Handbook has been presented at the workshop in Pakistan in February and at the Network meeting in Georgia in April 2006. |  | 2003 | [8 empty] | 2003
COM | Sweden | Implementation of the RMP: development of import/export licensing system | Individual | ASP | LAO | REF | 34 | TAS | 05 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-11-01 | 2002-09-01 |  | 2005-12-01 |  | 55000 | 0 | 55000 | 54358 | 99% | 642 | 642 | 642 | 0 | 0 | 0 | 0 | 0 | The Swedish contribution in Lao PDR consists of technical assistance to prepare an import/export licensing system. International and national consultants were contracted in April 2002. After an initial delay in the signing of agreement and data collection the project is completed, we are only awaiting Lao PDR’s approval of the final report. The Decree for the "Control of the Import-Export and Consumption of ODS" was signed late 2003. A regulation for how the new Decree shall be implemented has been developed and the regulation was signed by the Minister in November 2004. SEI and the IC gave a number of suggestions on drafts on the regulation during 2004. An information brochure to all importers informing them about the licensing system has been finalized during 2005. |  | 2001 | [8 empty] | 2001
FIN | Sweden | Preparation of a government strategy to reduce and eliminate the use of CFC refrigerants for servicing and installations on-site | Individual | ASP | PHI | REF | 29 | PRP | 59 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2002-08-01 | 2002-11-01 | 141400 | 0 | 141400 | 141400 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Detailed discussions with the Philippine authority in charge, Department of Environment and Natural Resources (DENR), on the implementation took place May 2000. International and local consultants were contracted and in November 2000, the first meeting with the involved authorities and the private sector was conducted. The political situation in the Philippines during 2001 caused the project a delay. A RMP outline was adopted in October 2001. During 2002 the project was merged into a NCPP together with the WB. The NCPP was submitted jointly and approved in December 2002 with Sweden as co-implementing agency for TA activities related to the servicing sector. |  | 1999 | [8 empty] | 1999
FIN | Sweden | National CFC phase out plan: servicing sector (first tranche) | Multi-Year | ASP | PHI | PHA | 38 | TAS | 68 | A | O | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-02-03 | 2003-12-01 |  | 2005-12-01 | 2006-04-01 | 152400 | 0 | 152400 | 152400 | 100% | 0 |  |  | 11316 | 0 | 11316 | 0 | 0 | In November 2002 ExCom approved the NCPP for the Philippines. Sweden is co-implementing agency for technical assistance activities in the servicing sector. WB is lead agency. In October 2002 a mission was conducted in order to coordinate the scheduled activities in the NCPP with the DENR and relevant authorities in the Philippines. During 2003 Sweden has assisted the Philippines in revising their national ODS legislation that was approved in March 2004. In December 2004 the next funding tranche was approved by the ExCom based on achieved milestones and reduced consumption of CFC. Four missions to assist in relation to training of trainers, equipment requirements, Code of Practice, re-use scheme and technician certification have been conducted. The Swedish funding for 2004 mainly aimed to support establishment of a reclamation capacity, the establishment of a Code of Good Practice and to support the work of the Project Management Unit. The mission in January 2004 was a joint mission with the WB. Sweden has commented on several versions of the Philippine Code of Practice that was adopted in April 2004. The second mission during 2004 was held in June 2004 and invited at the mission were the Technical work group, relevant authorities, WB and Swedish Embassy for a formal acceptance of the first Philippine Code of Practice. As of December 2004, seventy one trainers were trained under the train the trainers Program. In Feb 2005 a mission was conducted mainly in order to finalize details of plan for re-use of CFC including reclamation facility operated by PARII and present it to all refrigerant importers and also to discuss the Evaluation Officer comments resulting from an evaluation mission to Manila in Dec. 2004. |  | 2002 | [8 empty] | 2002
ONG | Sweden | National CFC phase-out plan servicing sector: 2004 annual programme | Multi-Year | ASP | PHI | PHA | 41 | TAS | 72 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-07-01 | 2004-12-01 | 2006-12-01 |  |  | 166134 | 0 | 166134 | 51286 | 31% | 114848 | 114848 | 114848 | 12952 | 0 | 12952 | 0 | 0 | As of Dec 2005, the following activities were conducted: Train-the-trainers Program completed in 2004; Memorandum of Agreement between the DENR-EMB and PARII (delineate the roles and responsibilities of concerned sectors and authorize PARII to collect fees from refrigerant importers) reviewed and revised; PARII selected as the operator of the facility (to be confirmed in 2006); Meetings with PARII held to discuss and update proposal initially submitted to the PMU; PMU initiated procurement of the reclamation facility in Dec. 05; Code of Good Practice (CoP) for RAC and MAC finalized and presented to stakeholders; Eight-thousand copies of CoP printed and disseminated to different service shops; and Notice to All Concerned Stakeholders on the Code of Practice published in a major daily. In March 2006 a mission was conducted jointly with the WB. |  | 2003 | [8 empty] | 2003 | [5 empty] | Yes
ONG | Sweden | National CFC phase-out plan servicing sector: 2005 annual programme | Multi-Year | ASP | PHI | PHA | 44 | TAS | 77 | A | O | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-12-01 | 2007-12-01 | 2007-12-01 |  |  | 40000 | 0 | 40000 | 23207 | 58% | 16793 | 16793 | 16793 | 2000 | 0 | 2000 | 0 | 0 | See remarks above. |  | 2004 | [8 empty] | 2004 | [5 empty] | yes
FIN | Sweden | Assistance to prepare the national CFC phase-out plan (refrigeration servicing sector) | Individual | EUR | ROM | PHA | 43 | PRP | 24 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-04-01 | 2005-07-01 | 59400 | 0 | 59400 | 59400 | 100% | 0 |  |  | 7722 | 0 | 7722 | 0 | 0 | In July 2004, at the 43rd Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a national CFC phase-out plan for the servicing sector in Romania. After recruitment of consultants a mission was held in November 2004. The NCPP was prepared during the autumn 2004 and was approved at the 45th ExCom meeting in April 2005. |  | 2004 | [8 empty] | 2004 | [5 empty] | yes
ONG | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-11-01 | 2007-04-01 | 2008-12-31 |  |  | 119500 | 0 | 119500 | 2741 | 2% | 116759 | 40123 | 30000 | 15535 | 0 | 0 | 15535 | 15535 | The NCPP for Romania was approved at the 45th ExCom meeting in April 2005. Two International consultants were recruited in June 2005. A first meeting with the NOU and UNIDO took place in Vienna in September 2005 and the first meeting in Bucharest took place in February 2006. The PMU was thereafter established. Terms of Reference for a national consultant to develop the Code of Practice has been agreed and will be recruited in May 2006. |  | 2005 | [8 empty] | 2005
ONG | Sweden | Halon management programme, halon recovery, recycling and banking | Halon banking | ASP | THA | HAL | 29 | TAS | 120 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2004-11-01 | 2003-12-01 | 2007-10-01 |  |  | 200000 | 0 | 200000 | 104981 | 52% | 95019 | 95019 | 54992 | 26000 | 0 | 26000 | 0 | 0 | The Swedish contribution to the Thai Halon Management Programme consists of technical assistance. The project is being implemented by the World Bank. Sweden disbursed 100% of the Swedish contribution to the WB in May 2001. The project has been substantially delayed. This has been mainly due to turnover of personnel at DIW and problems with finding qualified national consultants. During the autumn 2003 the project got started. After establishing the regulatory framework necessary to control consumption of halons in the country, and after completing a detailed analysis of the long-term sustainability of central halon reclamation and recycling facility, the Royal Thai Government (RTG) in 2004 concluded that a physical halon bank is not economically feasible for Thailand in the current national context. The technical assistance activities approved under the original project have more or less been finalized with a smaller balance from the Swedish part, but none of the approved investment funds have been disbursed (WB part). Following this, Thailand and the WB has, as requested by the ExCom, submitted a revised project proposal together with a request for reallocating unspent resources to implement a revised Halon Management Program that was approved in Nov. 2005. Sweden provided input to the proposal before submission. Following comments from the MLFS on the proposal, some of the activities were decided to be covered by the balance of another ongoing halon investment project in Thailand - aiming at the phase-out of halon for fire equipment manufacturers and suppliers. This result in that USD 164.000 from the WB part of the Thai Halon Management Plan project is to be returned to the MLF. The new halon program aim at providing enforcement of regulatory measures, training and technical assistance, demonstration of currently available alternatives for conversion of halon-based fixed fire fighting systems, and public awareness activities. The balance from the Swedish part will be used for additional training and technical assistance. |  | 1999 | [8 empty] | 1999
FIN | Sweden | Assistance to prepare a national CFC phase-out plan (servicing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 2003-07-01 | 2003-12-03 | 2004-07-01 |  | 2004-07-01 | 2004-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | The assistance to Serbia and Montenegro (SEM) to develop a NCPP for the servicing sector was completed in a joint undertaking with UNIDO during the spring 2004 and the plan was approved in July 2004. |  | 2003 | [8 empty] | 2003 | [5 empty] | yes
ONG | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 22 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2005-03-01 | 2006-12-01 |  |  | 148000 | 0 | 148000 | 6669 | 5% | 141331 | 122300 | 80000 | 19240 | 0 | 0 | 19240 | 19240 | Annual report submitted and approved at the 47nd ExCom meeting. UNIDO is he lead implementing agency for assisting in the implementation of the NCPP while Sweden is co-implementing agency with technical assistance projects in the servicing sector. The NCPP activities were further discussed at and after a stakeholder meeting in December 2004. Term of references for an international consultant was developed and a consultant was recruited in June 2005. Two missions were held during October and November 2005 in order to involve the stakeholders and to discuss the activities to be implemented. Representatives from both Serbia and Montenegro have been involved. A survey of vocational schools was initiated during 2005 as well as the recruitment of two PMU managers. |  | 2004 | [8 empty] | 2003
ONG | Sweden | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | TAS | 29 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 | 2007-12-01 |  |  | 134000 | 0 | 134000 | 0 | 0% | 134000 | 50000 | 50000 | 17420 | 0 | 0 | 17420 | 17420 | Term of reference for an international consultant was developed and a international consultant was recruited in June 2005. Two missions were held during October and November 2005 in order to involve the stakeholders and to discuss the activities to be implemented. Representatives from both ministeries in Serbia and Montenegro have been involved. A survey of vocational schools was initiated during 2005 as well as the recruitment of two PMU managers. |  | 2005 | [8 empty] | 2005
FIN | Switzerland | Technical assistance and training on safe designs of hydrocarbon based domestic and commercial refrigeration appliances | Individual | LAC | ARG | REF | 19 | TRA | 46 | A | O | D |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-08-01 | 1997-10-01 |  | 1997-08-01 | 1997-10-01 | 242600 | 0 | 242600 | 244854 | 100.9% | -2254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Balance has been compensated with separate Swiss funding |  | 1996
FIN | Switzerland | International workshop on potential for hydrocarbon-based refrigerant as replacements in existing domestic and small commercial refrigeration appliances | Individual | GLO | GLO | REF | 23 | TRA | 137 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1997-12-01 |  | 1997-09-01 | 1997-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1997
FIN | Switzerland | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 292 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 | 2003-04-01 | 2003-04-01 | 2003-04-01 | 70796 | 0 | 70796 | 70796 | 100% | 0 | 0 | 0 | 9204 | 0 | 9204 | 0 | 0 |  |  | 2000
ONG | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 370 | A | O | I |  |  |  | 0 | 0 | 2004-04-01 | 2004-09-01 | 2005-04-01 | 2005-03-01 |  |  | 353020 | 0 | 353020 | 153089 | 43.37% | 199931 | 203020 | 203020 | 45893 | 0 | 32854 | 13039 | 15893 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2004: Four new training cells have been established and a Training of Trainers Wokshop was held for 12 particpants. With this, 13 training cells provided in 2004 standard training programs for refrigeration service technicians. The training cells were managed by two Regional Management organisations. In the operational year 04-05 1610 technicians were trained in standard programs, which is well above the original target of 1500 participants. 7 out of the total of 64 training programs were externally monitored for quality control purposes.The training materials for standard training were updated for NCCOPP requirements and a new manual on MAC was develped and is available as draft. 29 participants were covered in two specialised programs for Mobile Air-Conditioning technicians. The implementation of training programs for institutional users such as Railways and operators of Open Type Compressors has faced delay and no significant activity has developed in 2004. This is due to weak response from and difficult access to the target group. These activities will only be completed in the upcoming operational year. | 2004 | [8 empty] | 2004
ONG | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 381 | A | O | I |  |  |  | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-03-01 |  |  | 256650 | 0 | 256650 | 0 | 0% | 256650 | 0 | 256650 | 33365 | 0 | 0 | 33365 |  | * Consumption reporting by Lead Agency (GTZ) | Outlook on annual work plan 2005: It is planned to cover 1240 participants in standard training programs for refrigeration service technicians. In specialised MAC trainings additional 64 participants will be covered. In this 11 training cells will be involved and 3 industry training partners. For institutional users from the open type compressor market and railways 32 participants are targeted. Out of these trainings 10 programs are earmarked for external monitoring to assure quality of the trainings. A selected number of training programs will be assisted through hand helding of the trainers. The training materials will be further updated to the requirements of the project. INFRAS on behalf of Switzerland will continue to facilitate the selection process of beneficiaries under the equipment support scheme implemented by UNDP. | 2005 | [8 empty] | 2005
ONG | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 394 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 256650 | 0 | 256650 |  | 0% | 256650 |  |  | 33365 | 0 |  | 33365
FIN | Switzerland | Implementation of the RMP: demonstration project to retrofit domestic refrigerators for the use of hydrocarbon refrigerant | RMP | AFR | SEN | REF | 33 | TAS | 14 | A | O | I |  | 0 |  | 0 | 0 | 2001-03-01 | 2003-07-01 | 2001-11-01 | 2003-08-01 | 2004-03-01 | 2004-06-01 | 71230 | 0 | 71230 | 71230 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2001
FIN | UK | Chiller concessional lending pilot project | Individual | LAC | MEX | REF | 28 | INV | 95 | N | O | I | CFC | 5 | 7.8 | 0 |  | 1999-07-01 | 2001-02-22 | 2004-02-01 |  | 2004-03-01 |  | 565000 | 0 | 565000 | 565000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Phase I is completed and accomplished its objectives improving expected results: Twelve chillers were financed instead of the ten expected, with an additional two chillers financed from accumulated funds. 7.8 ODP tons were eliminated instead of 5 tons as expected. Disbursements have been made on schedule with 100% disbursement achieved in August 2002. 100% of building owners that participated in the program have made their monthly repayment on time. Energy savings were 36% higher than proposed. The project will be completed in March 2004. | [11 empty] | Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 06 | TRA | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [10 empty] | 1992 | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 06 | TRA | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Methyl bromide data collection for Africa | Individual | AFR | AFR | FUM | 17 | TAS | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-01-01 |  | 1998-04-01 | 2000-12-01 | 179850 | 0 | 179850 | 179850 | 100% | 0 | 0 | 0 | 23381 | 0 | 23381 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Non-Investment
FIN | UNDP | Regional surveys in halon and methyl bromide sector | Individual | AFR | AFR | SEV | 36 | TAS | 30 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-11-01 | 2005-10-01 | 30000 | 0 | 30000 | 29854 | 99.51% | 146 | 0 | 0 | 3900 | 0 | 3881.02 | 18.98 | 0 | Completed in 2002. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Sectoral phase out programme: establishing a regional halon bank for West and Central Africa (Benin, Burkina Faso, Cameroon, Congo, Congo DR, and Guinea) | Individual | AFR | AFR | HAL | 37 | TAS | 31 | A | O | I | Halon | 61 | 0 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 | 2006-12-01 |  |  | 300000 | 0 | 300000 | 169892 | 56.63% | 130108 | 0 | 45537.8 | 39000 | 0 | 22085.96 | 16914.04 | 0 | Mission to visit Nigerian halon bank completed. Ongoing communication with some partners difficult. Not clear whether countries wish to contract Nigerian Bank. Bilateral discussions ongoing to try to address issue and complete project. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Technical assistance for methyl bromide reductions and formulation of regional phase-out strategies for low-volume consuming countries | Individual | AFR | AFR | FUM | 38 | TAS | 32 | A | O | I | MeBr | 2 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-02-01 | 2006-12-01 |  |  | 550000 | 0 | 550000 | 317789 | 57.78% | 232211 | 0 | 81273.85 | 70500 | 0 | 40734.7718 | 29765.2282 | 0 | 20% countries - Prep of missions (+ tech specs for PRC) and WPs completed. Swaziland mission in Sept. Procurement of equipment for PRC launched. Zero consumers - requested shift in execution strategy. New, higher value, contracts issued. | [10 empty] | 2002 | Non-Investment
FIN | UNDP | Tecnical assistance for country programme preparation | Individual | LAC | ARG | SEV | 04 | CPG | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-07-01 | 1993-02-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Technical assistance to prepare a national halon programme | Individual | LAC | ARG | HAL | 13 | TAS | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-01-01 |  | 1996-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1997-07-01 |  | 1999-12-01 | 2000-12-01 | 359500 | 0 | 359500 | 359500 | 100% | 0 | 0 | 0 | 46735 | 0 | 46735 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance (1994) | Individual | LAC | ARG | SEV | 14 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-09-01 | 1995-09-01 |  | 1995-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Prensiplast | Individual | LAC | ARG | FOA | 14 | INV | 13 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-09-01 | 1995-12-01 | 1995-09-01 |  | 1999-11-01 | 2001-12-01 | 345000 | -5021 | 339979 | 339979 | 100% | 0 | 0 | 0 | 44850 | -653 | 44197 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of sandwich polyurethane panels at Cinter, S.R.L. | Individual | LAC | ARG | FOA | 15 | INV | 14 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 2001-12-01 | 2003-09-01 | 725000 | -32679 | 692321 | 692321 | 100% | 0 | 0 | 0 | 94250 | -4248 | 90002 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1997-12-01 | [7 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 17 | PRP | 25 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-03-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Belmo Buenos Aires and Belmo San Luis | Individual | LAC | ARG | FOA | 18 | INV | 26 | A | O | I | CFC | 145 | 145 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2001-08-01 | 715000 | -10 | 714990 | 714990 | 100% | 0 | 0 | 0 | 92950 | -1 | 92949 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Nuvel Corp. S.A. | Individual | LAC | ARG | FOA | 18 | INV | 27 | A | O | I | CFC | 53 | 53 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 313500 | 0 | 313500 | 313500 | 100% | 0 | 0 | 0 | 40755 | 0 | 40755 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  |  | 1999-06-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Mentvil S.A. | Individual | LAC | ARG | FOA | 18 | INV | 28 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1997-04-01 | 2001-12-01 | 115000 | -12796 | 102204 | 102204 | 100% | 0 | 0 | 0 | 14950 | -1663 | 13287 | 0 | 0 | Completed in 1997. Financially completed in 2001. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Limansky | Individual | LAC | ARG | FOA | 18 | INV | 29 | A | O | I | CFC | 95 | 95 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 473000 | -364 | 472636 | 472636 | 100% | 0 | 0 | 0 | 61490 | -47 | 61443 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Piero SAIC | Individual | LAC | ARG | FOA | 18 | INV | 30 | A | O | I | CFC | 64 | 64 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 341000 | -1708 | 339292 | 339292 | 100% | 0 | 0 | 0 | 44330 | -222 | 44108 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  |  | 1999-06-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstock) at Sueño Estelar S.A. and Estelar San Luis S.A. | Individual | LAC | ARG | FOA | 18 | INV | 31 | A | O | I | CFC | 129 | 129 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 690000 | -2837 | 687163 | 687163 | 100% | 0 | 0 | 0 | 89700 | -369 | 89331 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of the use of CFC's in the manufacture of sandwich panels and spray foams at Montisol Argentina S.A. and Art Nouveau Puntana, S.A. | Individual | LAC | ARG | FOA | 18 | INV | 33 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1995-11-01 | 1997-07-01 | 1996-11-01 |  | 2001-12-01 | 2003-04-01 | 285000 | -631 | 284369 | 284369 | 100% | 0 | 0 | 0 | 37050 | -82 | 36968 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-01-01 | [7 empty] | 1995 | Investment
CLO | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores at Market Costan S.A. | Individual | LAC | ARG | REF | 18 | INV | 34 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1997-05-01 |  |  | 1998-07-01 | 423000 | -421642 | 1358 | 1358 | 100% | 0 | 0 | 0 | 54990 | -54813 | 177 | 0 | 0 | Canceled in 1998. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 18 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of the use of CFC's in the manufacture of display cabinet and walk-in freezers at Disthel | Individual | LAC | ARG | REF | 19 | INV | 45 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 196000 | -5726 | 190274 | 190274 | 100% | 0 | 0 | 0 | 25480 | -744 | 24736 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstocks) at Suavestar S.A. | Individual | LAC | ARG | FOA | 20 | INV | 48 | A | O | I | CFC | 92 | 92 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2002-11-01 | 2004-01-01 | 561000 | 0 | 561000 | 561000 | 100% | 0 | 0 | 0 | 72930 | 0 | 72930 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  | 1998-01-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 21 | PRP | 50 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | LAC | ARG | SEV | 22 | PRP | 54 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Eliminations of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Rheem S.A. | Individual | LAC | ARG | FOA | 22 | INV | 55 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-12-01 | 2001-12-01 | 76650 | 0 | 76650 | 76650 | 100% | 0 | 0 | 0 | 9965 | 0 | 9965 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstocks) at FPV S.A. | Individual | LAC | ARG | FOA | 22 | INV | 56 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-05-01 | 2004-01-01 | 118000 | -34528 | 83472 | 83472 | 100% | 0 | 0 | 0 | 15340 | -4489 | 10851 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Calofrig Asilaciones Jacobi S.A.I.C. | Individual | LAC | ARG | FOA | 22 | INV | 57 | A | O | I | CFC | 72 | 72 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1999-06-01 |  | 2001-12-01 | 2003-04-01 | 563750 | 0 | 563750 | 563750 | 100% | 0 | 0 | 0 | 73288 | 0 | 73288 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of commercial refrigerators and display cabinets at Trevi | Individual | LAC | ARG | REF | 23 | INV | 60 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-11-01 | 2001-08-01 | 53850 | -4409 | 49441 | 49441 | 100% | 0 | 0 | 0 | 7001 | -573 | 6428 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Bonano | Individual | LAC | ARG | FOA | 23 | INV | 61 | A | O | I | CFC | 72 | 72 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 456500 | 0 | 456500 | 456500 | 100% | 0 | 0 | 0 | 59345 | 0 | 59345 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
CLO | UNDP | Conversion to non CFC technology in the manufacture of integral skin and flexible moulded foam at Strapur | Individual | LAC | ARG | FOA | 23 | INV | 62 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2001-08-01 | 212500 | -162380 | 50120 | 50120 | 100% | 0 | 0 | 0 | 27625 | -21109 | 6516 | 0 | 0 | Canceled in 2002. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of moulded foam at Cifor S.A. | Individual | LAC | ARG | FOA | 23 | INV | 63 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-03-01 | 2001-12-01 | 132000 | -9838 | 122162 | 122162 | 100% | 0 | 0 | 0 | 17160 | -1279 | 15881 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
CLO | UNDP | Elimination of the use of CFCs in the manufacture of rigid foam blocks for insulated trailers at Fruehauf | Individual | LAC | ARG | FOA | 23 | INV | 65 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2003-11-01 | 175000 | -40597 | 134403 | 134403 | 100% | 0 | 0 | 0 | 22750 | -5278 | 17472 | 0 | 0 | Canceled in 2002. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores and walk-in coolers at Eurofrio | Individual | LAC | ARG | REF | 23 | INV | 66 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2002-11-01 | 2004-01-01 | 377350 | 0 | 377350 | 377350 | 100% | 0 | 0 | 0 | 49056 | 0 | 49056 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [5 empty] | 2001-05-01 |  |  |  |  | 1997 | Investment
FIN | UNDP | Project preparation for methyl bromide (tobacco) demonstration project | Individual | LAC | ARG | FUM | 24 | PRP | 73 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 24 | PRP | 74 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to low index additive technology in the manufacture of flexible boxfoam at Rozen S.R.L. | Individual | LAC | ARG | FOA | 25 | INV | 76 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1998-07-01 | 2000-08-01 | 2000-08-01 |  | 2002-11-01 | 2004-01-01 | 122100 | 0 | 122100 | 122100 | 100% | 0 | 0 | 0 | 15873 | 0 | 15873 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Comenco | Individual | LAC | ARG | FOA | 26 | INV | 78 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-08-01 | 2001-12-01 | 210150 | -3022 | 207128 | 207128 | 100% | 0 | 0 | 0 | 27320 | -393 | 26927 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Demonstration and training in viable alternatives, information dissemination and development of a national plan for phasing out methyl bromide in the tobacco sector | Individual | LAC | ARG | FUM | 26 | DEM | 79 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-04-01 | 2003-11-01 | 273350 | -1493 | 271857 | 271857 | 100% | 0 | 0 | 0 | 35536 | -194 | 35342 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of two projects in the integral skin foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of an umbrella project and three other projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 87 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 27 | PRP | 88 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and of CFC-12 by conversion to HFC-134a in the manufacture of commercial refrigeration display cabinets and polyurethane panels for cold stores AT Perito Moreno Ref. | Individual | LAC | ARG | REF | 28 | INV | 92 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1999-07-01 | 1999-09-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 379605 | 0 | 379605 | 379605 | 100% | 0 | 0 | 0 | 49349 | 0 | 49349 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at OSIR (Organización de Servicios Integrales Rosario) | Individual | LAC | ARG | FOA | 29 | INV | 94 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 127392 | 0 | 127392 | 127392 | 100% | 0 | 0 | 0 | 16561 | 0 | 16561 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Obras de Ingenieria | Individual | LAC | ARG | FOA | 29 | INV | 95 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2000-12-01 | 2003-04-01 | 124025 | -221 | 123804 | 123804 | 100% | 0 | 0 | 0 | 16123 | -29 | 16094 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and boxfoam) at Mendoza de Poliuretanos | Individual | LAC | ARG | FOA | 29 | INV | 96 | A | O | I | CFC | 44 | 44 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-11-01 | 2004-01-01 | 234409 | 0 | 234409 | 234409 | 100% | 0 | 0 | 0 | 30473 | 0 | 30473 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
COM | UNDP | Renewal of the institutional strengthening under the Montreal Protocol (Phase II) | Individual | LAC | ARG | SEV | 29 | INS | 98 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2003-05-01 |  | 239700 | 0 | 239700 | 236948 | 98.85% | 2752 | 0 | 1376 | 31161 | 0 | 30803.24 | 357.76 | 0 | Completed in 2003. | [10 empty] | 1999 | Non-Investment
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 101 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 102 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of one project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 30 | PRP | 103 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Fasax | Individual | LAC | ARG | FOA | 30 | INV | 106 | A | O | I | CFC | 50 | 50 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2003-04-01 |  | 2002-11-01 | 2004-01-01 | 252000 | 0 | 252000 | 252000 | 100% | 0 | 0 | 0 | 32760 | 0 | 32760 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam at four enterprises: Cosmos; La Cardeuse; Jovis; and Micropore | Individual | LAC | ARG | FOA | 31 | INV | 111 | A | O | I | CFC | 49 | 49 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2003-12-01 | 2005-09-01 | 295300 | -97042 | 198258 | 198258 | 100% | 0 | 0 | 0 | 38389 | -12615 | 25774 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
COM | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constuctora Vimac; Gaspar Adragna; Placido Sandoval) | Individual | LAC | ARG | FOA | 32 | INV | 113 | A | O | I | CFC | 50 | 50 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2005-01-01 |  | 320332 | 0 | 320332 | 315912 | 98.62% | 4420 | 0 | 2210 | 41643 | 0 | 41068.4022 | 574.5978 | 0 | Completed in 2005. Adramet - new gun delivered and installed. Trial period was successful and HOP was issued Jan. 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | ARG | REF | 33 | PRP | 119 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in soil fumigation (tobacco) | Individual | LAC | ARG | FUM | 33 | PRP | 120 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 121 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 4 foam manufacturers (Artestamp, Paissan, Forever, Termica) | Individual | LAC | ARG | FOA | 34 | INV | 122 | A | O | I | CFC | 55 | 55 | 0 | 0 | 2001-07-01 | 2002-09-01 | 2004-08-01 |  | 2005-01-01 |  | 352896 | 0 | 352896 | 339927 | 96.32% | 12969 | 0 | 6484.5 | 45876 | 0 | 44190.0476 | 1685.9524 | 0 | Completed in 2005. Artestamp - new gun delivered and installed. Trial period was successful and HOP issued Jan. 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam insulation panels at Frio Star | Individual | LAC | ARG | FOA | 34 | INV | 123 | A | O | I | CFC | 19 | 19 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-12-01 | 2005-09-01 | 147987 | -53810 | 94177 | 94177 | 100% | 0 | 0 | 0 | 19238 | -6995 | 12243 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | ARG | FOA | 36 | PRP | 126 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 2002. Financially closed in 2005. | [10 empty] | 2002 | Investment
COM | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (2001 and 2002 tranches) | Multi-Year | LAC | ARG | FUM | 36 | INV | 129 | N | O | I | MeBr | 29 | 29 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2002-12-01 |  | 2004-12-01 |  | 1720000 | 0 | 1720000 | 1720000 | 100% | 0 | 0 | 0 | 199200 | 0 | 199200 | 0 | 0 | Completed in 2004. | [8 empty] | 2004-03-01 |  | 2001 | Investment | 156 | 156 |  |  | Yes | N/A | yes
COM | UNDP | Extension of institutional strengthening project | Individual | LAC | ARG | SEV | 38 | INS | 130 | N | T | I | CFC | 26 | 26 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 |  | 311610 | 0 | 311610 | 274878 | 88.21% | 36732 | 0 | 18366 | 40509 | 0 | 35734.14 | 4775.16 | 0 | Completed in 2005. National Ozone Unit continued implementation of terminal umbrella project on foams, investment projects for MeBr and CFC Ref Phase out plan and continued public awareness and ODS regulations related activities. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | ARG | FOA | 38 | INV | 132 | A | O | I | CFC | 192 | 162 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 | 2006-06-01 |  |  | 1324843 | 0 | 1324843 | 896396 | 67.66% | 428447 | 0 | 149956.45 | 155733 | 0 | 105369.5942 | 50363.1058 | 0 | Equipment delivered and installed for Group I. Group II participants identified and purchase orders issued. Compensation was made for companies that would not receive equipment. Group III to be identified early 2006. | [10 empty] | 2002 | Investment
COM | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (third tranche) | Multi-Year | LAC | ARG | FUM | 40 | INV | 136 | N | O | I | MeBr | 21 | 21 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-03-01 |  | 2005-12-01 |  | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Completed in 2005. Phase-out targets being met. Refer to Yearly Progress Report for MY-Plan submitted to ExCom 46 for more detailed information and update on overall project implementation status. | [9 empty] | 2005-07-01 | 2003 | Investment | 90 | 90 |  |  | Yes | N/A | yes
ONG | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fourth tranche) | Multi-Year | LAC | ARG | FUM | 43 | INV | 139 | N | O | I | MeBr | 16 | 16 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-07-01 | 2006-07-01 |  |  | 467000 | 0 | 467000 | 357824 | 76.62% | 109176 | 0 | 38211.6 | 35025 | 0 | 26836.8 | 8188.2 | 0 | Project on track. Phase-out targets being met. See Progress Report submitted to ExCom 46 for more detailed information. | [10 empty] | 2004 | Investment | 56.5 | 56.5 |  |  | Yes | Yes | yes
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | ARG | SEV | 45 | TAS | 144 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 68807 | 0 | 68807 | 0 | 0% | 68807 | 0 | 24082.45 | 6193 | 0 | 0 | 6193 | 0 | Preparatory work to initiate surveys and recruit consultants started. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Extension for institutional strengthening project (phase IV) | Individual | LAC | ARG | SEV | 46 | INS | 145 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 | 2007-07-01 |  |  | 311567 | 0 | 311567 | 10445 | 3.352% | 301122 | 0 | 60224.4 | 23368 | 0 | 783.3909 | 22584.6091 | 0 | During 2005 the NOU continued successfully providing the legislative and managerial support to the ongoing ODS phase out activities. The NOU also continued monitoring of the country’s compliance status with the Montreal Protocol through data collection and monitoring of ODS consumption. The license system to control ODS imports and exports continued to be successfully enforced. Concerning the implementation of projects, significant progress was achieved in the Foam sector finalizing two umbrella projects and progressing on the Terminal Umbrella Project to phase-out Foams in the remaining medium size and small enterprises. This project will be completed in 2006. Significant progress was also achieved in implementation of MB phase out projects in soil fumigation. The NOU is also coordinating the implementation of the National Phase out plan, including among other activities, the provision of equipment to a number of workshops identified through an extensive survey comprising more than 4,000 workshops. Furthermore, Argentina organized an Ozone Protection Awareness Campaign in Radio, Newspaper and Television, in order to keep the phase-out momentum of the different ODS consuming sectors, as well as to identify the remaining ODS users in the country. Argentina also participated actively in Executive Committee Meetings, Meeting of the Parties as well as Regional Meetings for Ozone Officers. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fifth tranche) | Multi-Year | LAC | ARG | FUM | 46 | INV | 146 | N | O | I | MeBr | 33 | 33 | 0 | 0 | 2005-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 467000 | 0 | 467000 | 0 | 0% | 467000 | 0 | 163450 | 35025 | 0 | 0 | 35025 | 0 | Phase-out targets being met. M&E mission conducted Nov. 2005. Stakeholders in sector engaged and committed to sustainable phase-out in sector. Project on track. | [10 empty] | 2005 | Investment | 0 |  |  |  | Latest | Latest | Latest
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 06 | TRA | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Asia | RMP-Component | ASP | ASP | REF | 06 | TRA | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1994-07-01 |  | 1996-08-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 06 | TRA | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in Asia | Individual | ASP | ASP | FOA | 06 | TRA | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -15672 | 36828 | 36828 | 100% | 0 | 0 | 0 | 6825 | -2037 | 4788 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Methyl bromide data collection for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TAS | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 2000-12-01 | 102000 | -64974 | 37026 | 37026 | 100% | 0 | 0 | 0 | 13260 | -8447 | 4813 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1995 | Non-Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BAH | REF | 21 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | ASP | BAH | REF | 22 | TAS | 04 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 242000 | -2849 | 239151 | 239151 | 100% | 0 | 0 | 0 | 31460 | -370 | 31090 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Preparation of two project proposals in the commercial refrigeration subsector | Individual | ASP | BAH | REF | 27 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | Individual | ASP | BAH | REF | 29 | INV | 09 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 |  | 173835 | 0 | 173835 | 190444 | 109.6% | -16609 | 0 | 0 | 22599 | 0 | 24758.213 | -2159.213 | 0 | Completed in 2004. Apparent overrun to be resolved in 2006. | [10 empty] | 1999 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | Individual | ASP | BAH | REF | 29 | INV | 10 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 |  | 224478 | 0 | 224478 | 173371 | 77.23% | 51107 | 0 | 25553.5 | 29182 | 0 | 22538.1219 | 6643.8781 | 0 | Completed in 2004. | [10 empty] | 1999 | Investment
ONG | UNDP | Project preparation for a refrigerant management plan update | Individual | ASP | BAH | REF | 43 | PRP | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-03-01 | 2006-12-01 |  |  | 24000 | 0 | 24000 | 20000 | 83.33% | 4000 | 0 | 4000 | 1800 | 0 | 1500 | 300 | 0 | Project preparation activities initiated. National cosnultant to undertake survey contracted. Joint UNDP/UNEP Project to be submitted for 49th ExCom. | [10 empty] | 2004 | Investment
COM | UNDP | Formulation of investment components of the RMP | Individual | LAC | BAR | REF | 39 | PRP | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Project preparation completed. Project submitted to and approved at ExCom 43. | [10 empty] | 2003 | Investment
COM | UNDP | Project preparation for the formulation of refrigerant management plan for end-users | Individual | LAC | BAR | REF | 42 | PRP | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 |  | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | Completed in 2005. Project preparation completed. Project submitted to and approved by ExCom. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance project to the MAC and end-users sectors | RMP-Component | LAC | BAR | REF | 43 | TAS | 11 | N | O | I | CFC | 6 | 0 | 0 | 0 | 2004-07-01 |  | 2006-12-01 | 2006-12-01 |  |  | 172611 | 0 | 172611 | 0 | 0% | 172611 | 0 | 60413.85 | 15535 | 0 | 0 | 15535 | 0 | ProDoc signed. PRP R&R workplan mission conducted March 05. Provision of assistance to prepare ntl inventory of workshops, detailed AWP, TORs for local consultant, budget breakdown and review equipment specs. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | LAC | BAR | REF | 43 | TAS | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-12-01 | 2006-12-01 |  |  | 26150 | 0 | 26150 | 0 | 0% | 26150 | 0 | 9152.5 | 2354 | 0 | 0 | 2354 | 0 | ProDoc signed. Activity linked to R&R project. On track. | [10 empty] | 2004 | Non-Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities included in the RMP | RMP-Component | AFR | BDI | REF | 26 | TAS | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2001-07-01 | 2000-12-01 |  | 2003-11-01 | 2003-11-01 | 10450 | -415 | 10035 | 10035 | 100% | 0 | 0 | 0 | 1359 | -54 | 1305 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 26 | TAS | 05 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1998-11-01 | 2001-05-01 | 2000-12-01 |  | 2003-11-01 | 2004-01-01 | 119577 | -3603 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15545 | -468 | 15077 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | AFR | BDI | ARS | 33 | PRP | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | BDI | FOA | 33 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Phase-out of CFC-11 and CFC-12 mixture in the manufacture of insecticides by conversion to hydrocarbon propellant at Fadi, S.A. (Fabrication d'insecticide et de product chimique) | Individual | AFR | BDI | ARS | 35 | INV | 09 | A | O | I | CFC | 9 | 9 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2004-12-01 |  | 2003-12-01 |  | 128900 | 0 | 128900 | 128720 | 99.86% | 180 | 0 | 90 | 16757 | 0 | 16733.6 | 23.4 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Exim, S.A. | Individual | AFR | BDI | FOA | 35 | INV | 10 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2005-01-01 |  | 2003-12-01 |  | 78262 | 0 | 78262 | 69927 | 89.35% | 8335 | 0 | 4167.5 | 10174 | 0 | 9090.4564 | 1083.5436 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation for update of refrigerant management plan | Individual | AFR | BDI | REF | 40 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2004-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Update-Comp | AFR | BDI | REF | 41 | TAS | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2006-12-01 | 2006-12-01 |  |  | 32500 | 0 | 32500 | 29156 | 89.71% | 3344 | 0 | 1170.4 | 2925 | 0 | 2624.04 | 300.96 | 0 | Equipment ordered and workshops took place. Spares distributed to recipients. Remaining budget will be spent in 2006. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Update-Comp | AFR | BDI | REF | 41 | TAS | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2006-12-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 14019 | 70.09% | 5981 | 0 | 2093.35 | 1800 | 0 | 1261.71 | 538.29 | 0 | See remark for BDI-13 as activities are jointly implemented. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | BDI | PHA | 47 | PRP | 20 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2250 | 0 | 0 | 2250 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
FIN | UNDP | Preparation of two projects in the general foam subsector | Individual | AFR | BEN | FOA | 27 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Plastique Elastomeres du Benin (P.E.B.) | Individual | AFR | BEN | FOA | 32 | INV | 12 | A | O | I | CFC | 27 | 27 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2003-07-01 |  | 2003-08-01 | 2005-09-01 | 143027 | -6481 | 136546 | 136546 | 100% | 0 | 0 | 0 | 18594 | -843 | 17751 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Reconnaissance survey and training | Individual | ASP | BGD | SEV | 04 | TAS | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1993-06-01 | 1997-12-01 | 55000 | -1150 | 53850 | 53850 | 100% | 0 | 0 | 0 | 7150 | -150 | 7000 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | BGD | SEV | 06 | CPG | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-06-01 |  | 1994-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | BGD | SEV | 14 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | BGD | SEV | 14 | INS | 04 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-09-01 | 1997-09-01 |  | 1999-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at Advanced Chemical Industries Ltd. (ACI) | Individual | ASP | BGD | ARS | 17 | INV | 05 | N | O | I | CFC | 124 | 124 | 0 | 0 | 1995-07-01 | 1998-12-01 | 1996-07-01 |  | 2002-08-01 | 2003-10-01 | 322920 | -343 | 322577 | 322577 | 100% | 0 | 0 | 0 | 41980 | -45 | 41935 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  |  | 1999-12-01 |  | 2001-05-01 |  |  |  |  | 1995 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BGD | REF | 21 | PRP | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-01-01 |  | 1999-09-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Investment
COM | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase II) | Individual | ASP | BGD | SEV | 29 | INS | 09 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2001-12-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2001. | [10 empty] | 1999 | Non-Investment
COM | UNDP | Implementation of the RMP: Implementation of a national recovery and recycling project | RMP-Component | ASP | BGD | REF | 29 | TAS | 10 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2005-07-01 |  | 298270 | 0 | 298270 | 298661 | 100.1% | -391 | 0 | 0 | 38775 | 0 | 38825.8299 | -50.8299 | 0 | Completed in 2005. Additional equipment delivered and project declared completed. Apparent overrun to be resolved in 2006. | [10 empty] | 1999 | Investment
COM | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | ASP | BGD | REF | 29 | TAS | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2005-12-01 |  | 15455 | 0 | 15455 | 15386 | 99.55% | 69 | 0 | 34.5 | 2009 | 0 | 2000.0307 | 8.9693 | 0 | Completed in 2005. Monitoring completed. Final report received from government. | [10 empty] | 1999 | Non-Investment
COM | UNDP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | BGD | SEV | 35 | INS | 13 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-01-01 |  | 2004-12-01 |  | 100000 | 0 | 100000 | 97813 | 97.81% | 2187 | 0 | 1093.5 | 13000 | 0 | 12715.69 | 284.31 | 0 | Completed in 2004. | [10 empty] | 2001 | Non-Investment
ONG | UNDP | Country programme update | Individual | ASP | BGD | SEV | 36 | CPG | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-10-01 | 2006-04-01 |  |  | 18750 | 0 | 18750 | 18156 | 96.83% | 594 | 0 | 207.9 | 2438 | 0 | 2360.28 | 77.22 | 0 | CP-document to be finalized in eatrly 2006 and submitted at 48th ExCom. | [10 empty] | 2002 | Non-Investment
FIN | UNDP | Formulation of a national phase out plan | Individual | ASP | BGD | PHA | 39 | PRP | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | National ODS phase-out plan: technical assistance programme for the refrigeration servicing sub-sector (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 19 | N | O | I | CFC | 36 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 |  |  | 96000 | 0 | 96000 | 0 | 0% | 96000 | 0 | 33600 | 7200 | 0 | 0 | 7200 | 0 | Project document submitted to Government. Awaiting signature. | [10 empty] | 2004 | Investment | 267.6 |  |  |  | No | No | No
ONG | UNDP | National ODS phase-out plan: technical assistance for the phase-out of ODS solvents (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 20 | N | O | I | CTC | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 8750 | 1875 | 0 | 0 | 1875 | 0 | Project document submitted to Government. Activity will start immediately on signature. | [10 empty] | 2004 | Investment | see BGD-19 |  |  |  | No | No | No
ONG | UNDP | National ODS phase-out plan: monitoring and management unit (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 21 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 |  |  | 34000 | 0 | 34000 | 0 | 0% | 34000 | 0 | 11900 | 2550 | 0 | 0 | 2550 | 0 | Project document submitted to Government. Awaiting signature. | [10 empty] | 2004 | Non-Investment | see BGD-19 |  |  |  | No | No | No
ONG | UNDP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | BGD | SEV | 44 | INS | 23 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 130000 | 0 | 130000 | 0 | 0% | 130000 | 0 | 45500 | 9750 | 0 | 0 | 9750 | 0 | The NOU of Bangladesh continued implementation of its planned activities for 2005, including close monitoring of RMP implementation activities, coordination of awareness activities, participation in regional meetings, organization of IAs missions and development of new projects. | [10 empty] | 2004 | Non-Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | BHA | REF | 21 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2543 | 12457 | 12457 | 100% | 0 | 0 | 0 | 1950 | -331 | 1619 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BHA | REF | 23 | TAS | 05 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1997-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-05-01 | 151400 | -12625 | 138775 | 138775 | 100% | 0 | 0 | 0 | 19682 | -1641 | 18041 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
COM | UNDP | Preparation of investment component of the refrigerant management plan | Individual | ASP | BHU | REF | 43 | PRP | 02 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Project submitted and approved at 45th ExCom Meeting | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance in the refrigeration servicing sector | RMP-Component | ASP | BHU | REF | 45 | TAS | 06 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 | 2007-04-01 |  |  | 45000 | 0 | 45000 | 17930 | 39.84% | 27070 | 0 | 5414 | 4050 | 0 | 1613.7 | 2436.3 | 0 | Signature of project document initiated. Coordinated with NOU to initiate project activities | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Implementation of the RMP: Incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | BKF | REF | 32 | TAS | 11 | N | O | I | CFC | 3 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2006-01-01 | 2006-12-01 |  |  | 132250 | 0 | 132250 | 118177 | 89.36% | 14073 | 0 | 4925.55 | 17193 | 0 | 15363.4568 | 1829.5432 | 0 | Repeated efforts made to obtain report from NOU to clarify past activities and to specify how to use remaining funds. Response finally received in Dec 05 but proposed activities unrelated to RMP. Situation difficult as it is difficult to get response. | [10 empty] | 2000 | Non-Investment
ONG | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Update-Comp | AFR | BKF | REF | 34 | TAS | 13 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2007-08-01 | 2007-08-01 |  |  | 16350 | 0 | 16350 | 0 | 0% | 16350 | 0 | 3270 | 2126 | 0 | 0 | 2126 | 0 | See remark for BKF-11 as activities are jointly implemented. | [10 empty] | 2001 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BOL | SEV | 18 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-05-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BOL | REF | 20 | TAS | 04 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 146000 | -691 | 145309 | 145309 | 100% | 0 | 0 | 0 | 18980 | -90 | 18890 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BOL | FOA | 21 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | -2187 | 22813 | 22813 | 100% | 0 | 0 | 0 | 3250 | -284 | 2966 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration and one in domestic refrigeration sub-sectors | Individual | LAC | BOL | REF | 24 | PRP | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (cotton and soy) | Individual | LAC | BOL | FUM | 27 | PRP | 09 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | BOL | FUM | 33 | PRP | 11 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BOL | REF | 33 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BOL | FOA | 33 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Foam sector ODS phaseout (two enterprises: Isolcruz and Teplo) | Individual | LAC | BOL | FOA | 35 | INV | 15 | A | O | I | CFC | 5 | 5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-05-01 |  | 161211 | 0 | 161211 | 155336 | 96.36% | 5875 | 0 | 2937.5 | 20957 | 0 | 20193.2657 | 763.7343 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
ONG | UNDP | Terminal methyl bromide phase-out, excluding QPS applications | One-off-Phaseout | LAC | BOL | FUM | 35 | INV | 16 | N | O | I | MeBr | 2 | 2 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-12-01 | 2006-11-01 |  |  | 221032 | 0 | 221032 | 179883 | 81.38% | 41149 | 0 | 14402.15 | 28734 | 0 | 23384.6598 | 5349.3402 | 0 | Gov’t reports phaseout impact of 1.5 MT. Ntl team developing a monitoring plan + preparing handbook on Bolivia’s MeBr phaseout experience. Completion expected in Nov 06 once monitoring activities completed. Refer to progress report submitted to ExCom 48. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration (terminal phase-out) sector | Individual | LAC | BOL | REF | 36 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-09-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Terminal umbrella project for the commercial refrigeration manufacturing sector | Individual | LAC | BOL | REF | 42 | INV | 25 | N | O | I | CFC | 6 | 0 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2007-04-01 | 2007-04-01 |  |  | 88840 | 0 | 88840 | 37586 | 42.31% | 51254 | 0 | 10250.8 | 7995 | 0 | 3382.4862 | 4612.5138 | 0 | Local consultant on board. Further information on the assited companies collected and equipment to be purchased decided. Equipment purchase process started. | [10 empty] | 2004 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | BOT | REF | 21 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -8880 | 11120 | 11120 | 100% | 0 | 0 | 0 | 2600 | -1154 | 1446 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Demonstration programme to improve domestic refrigerator servicing and CFC recycling in service shops | Individual | LAC | BRA | REF | 06 | DEM | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-02-01 | 1993-12-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening support for the implementation of the Montreal Protocol | Individual | LAC | BRA | SEV | 10 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-03-01 | 1999-12-01 | 403100 | 0 | 403100 | 403100 | 100% | 0 | 0 | 0 | 52403 | 0 | 52403 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 11 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1994-11-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Therm-Jet (Belo Horizonte), Zenimont and Lavale (Sao Paulo) | Individual | LAC | BRA | FOA | 12 | INV | 13 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1994-03-01 | 1996-02-01 | 1995-03-01 |  | 1997-07-01 | 2000-12-01 | 370000 | -15282 | 354718 | 354718 | 100% | 0 | 0 | 0 | 48100 | -1987 | 46113 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam for steering wheels at Plascar | Individual | LAC | BRA | FOA | 17 | INV | 21 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-12-01 |  | 1997-10-01 | 2000-07-01 | 119400 | -25268 | 94132 | 94132 | 100% | 0 | 0 | 0 | 15522 | -3285 | 12237 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 17 | PRP | 22 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-07-01 |  | 1996-01-01 | 1997-12-01 | 75000 | -2 | 74998 | 74998 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic chest freezers at Multibras, S.A. Electrodomésticos | Individual | LAC | BRA | REF | 17 | INV | 24 | N | O | I | CFC | 166 | 166 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-12-01 |  | 1997-12-01 | 1999-12-01 | 598499 | 0 | 598499 | 598499 | 100% | 0 | 0 | 0 | 77805 | 0 | 77805 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Macform | Individual | LAC | BRA | FOA | 18 | INV | 27 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 243500 | -8086 | 235414 | 235414 | 100% | 0 | 0 | 0 | 31655 | -1051 | 30604 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Nacra | Individual | LAC | BRA | FOA | 18 | INV | 28 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 254500 | -47523 | 206977 | 206977 | 100% | 0 | 0 | 0 | 33085 | -6178 | 26907 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at MBR | Individual | LAC | BRA | FOA | 18 | INV | 29 | A | O | I | CFC | 40 | 40 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 338500 | -44421 | 294079 | 294079 | 100% | 0 | 0 | 0 | 44005 | -5775 | 38230 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Phase out of CFC-113 at DMG used in medical equipment parts cleaning | Individual | LAC | BRA | SOL | 18 | INV | 36 | N | O | I | CFC | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1997-11-01 | 2000-12-01 | 38000 | -6 | 37994 | 37994 | 100% | 0 | 0 | 0 | 4940 | -1 | 4939 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-113 from the precision cleaning and drying process at Brasimet | Individual | LAC | BRA | SOL | 18 | INV | 37 | N | O | I | CFC | 2 | 2 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1996-11-01 |  | 1999-12-01 | 2000-09-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-07-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 18 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-08-01 | 1997-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Madef/Isoltec | Individual | LAC | BRA | FOA | 19 | INV | 43 | A | O | I | CFC | 65 | 65 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-12-01 | 2001-12-01 | 346000 | -64202 | 281798 | 281798 | 100% | 0 | 0 | 0 | 44980 | -8346 | 36634 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at three enterprises: Brafer, Invicta and Therm-Jet | Individual | LAC | BRA | FOA | 19 | INV | 44 | A | O | I | CFC | 38 | 38 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-07-01 | 1999-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1996 | Investment
FIN | UNDP | Umbrella project covering 6 companies for the conversion to CFC-free technology in the manufacture of integral rigid skin and flexible molded polyurethane foam (Rorispuma, Indek, Flexfom, Walrod, Rigi | Individual | LAC | BRA | FOA | 19 | INV | 45 | A | O | I | CFC | 52 | 52 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-11-01 | 2000-07-01 | 746000 | 2 | 746002 | 746002 | 100% | 0 | 0 | 0 | 96980 | 0 | 96980 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free techcnology in the manufacture of polyurethane foam at Blitz Ind. Com. de Plasticos | Individual | LAC | BRA | FOA | 19 | INV | 46 | A | O | I | TCA/CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-07-01 | 2000-07-01 | 120000 | -36822 | 83178 | 83178 | 100% | 0 | 0 | 0 | 15600 | -4787 | 10813 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Panisol, S.A. (Paineis Isolantes) | Individual | LAC | BRA | FOA | 20 | INV | 53 | A | O | I | CFC | 54 | 54 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 1999-12-01 | 2003-11-01 | 315958 | -41 | 315917 | 315917 | 100% | 0 | 0 | 0 | 41075 | -5 | 41070 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [6 empty] | 1996 | Investment
COM | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Multibras, S.A. | Individual | LAC | BRA | REF | 20 | INV | 57 | N | O | I | CFC | 1069 | 1069 | 0 | 0 | 1996-10-01 | 1997-07-01 | 1999-09-01 |  | 2001-12-01 |  | 4899790 | 0 | 4899790 | 4899790 | 100% | 0 | 0 | 0 | 636973 | 0 | 636973 | 0 | 0 | Completed in 2001. |  |  | 1999-12-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 21 | PRP | 62 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Giroflex | Individual | LAC | BRA | FOA | 22 | INV | 64 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-08-01 | 2002-11-01 | 177500 | 0 | 177500 | 177500 | 100% | 0 | 0 | 0 | 23075 | 0 | 23075 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyethylene foam tubing at Polipex | Individual | LAC | BRA | FOA | 22 | INV | 65 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2002-01-01 | 2002-12-01 | 191000 | 0 | 191000 | 191000 | 100% | 0 | 0 | 0 | 24830 | 0 | 24830 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Trambusti Naue | Individual | LAC | BRA | FOA | 22 | INV | 66 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2000-11-01 | 2001-11-01 | 763600 | -2355 | 761245 | 761245 | 100% | 0 | 0 | 0 | 99268 | -306 | 98962 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Industrias Facchini, Ldta. | Individual | LAC | BRA | FOA | 22 | INV | 67 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-03-01 | 2001-11-01 | 258000 | -85574 | 172426 | 172426 | 100% | 0 | 0 | 0 | 33540 | -11125 | 22415 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Dalla Rosa E Cia | Individual | LAC | BRA | FOA | 22 | INV | 68 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-05-01 |  | 1999-12-01 | 2001-12-01 | 71600 | 0 | 71600 | 71600 | 100% | 0 | 0 | 0 | 9308 | 0 | 9308 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Aquedores Cumulus S.A. | Individual | LAC | BRA | FOA | 22 | INV | 69 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 86000 | -49 | 85951 | 85951 | 100% | 0 | 0 | 0 | 11180 | -6 | 11174 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Tekcor Utilidades Domesticas Ltd. | Individual | LAC | BRA | FOA | 22 | INV | 70 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1998-07-01 | 2003-05-01 | 71600 | -2957 | 68643 | 68643 | 100% | 0 | 0 | 0 | 9308 | -384 | 8924 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Metallurgica Barra | Individual | LAC | BRA | FOA | 22 | INV | 71 | A | O | I | CFC | 36 | 36 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1997-07-01 | 2000-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Isolenge | Individual | LAC | BRA | FOA | 22 | INV | 72 | A | O | I | CFC | 66 | 66 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-04-01 | 2000-12-01 | 516000 | -84186 | 431814 | 431814 | 100% | 0 | 0 | 0 | 67080 | -10944 | 56136 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | LAC | BRA | SEV | 22 | PRP | 74 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technlogy in the manufacture of polyurethane foam at Plasmold | Individual | LAC | BRA | FOA | 23 | INV | 77 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 161500 | -737 | 160763 | 160763 | 100% | 0 | 0 | 0 | 20995 | -96 | 20899 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bulltrade | Individual | LAC | BRA | FOA | 23 | INV | 78 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 223000 | -358 | 222642 | 222642 | 100% | 0 | 0 | 0 | 28990 | -47 | 28943 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CMZ Poliuretanos | Individual | LAC | BRA | FOA | 23 | INV | 79 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 92750 | -305 | 92445 | 92445 | 100% | 0 | 0 | 0 | 12058 | -40 | 12018 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bruzze | Individual | LAC | BRA | FOA | 23 | INV | 80 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-11-01 |  | 2000-11-01 | 2002-03-01 | 278190 | -456 | 277734 | 277734 | 100% | 0 | 0 | 0 | 36165 | -59 | 36106 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Artico | Individual | LAC | BRA | REF | 23 | INV | 81 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 225100 | -927 | 224173 | 224173 | 100% | 0 | 0 | 0 | 29263 | -120 | 29143 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Bernini | Individual | LAC | BRA | FOA | 23 | INV | 82 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-11-01 | 135150 | 0 | 135150 | 135150 | 100% | 0 | 0 | 0 | 17570 | 0 | 17570 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Polistecom | Individual | LAC | BRA | FOA | 23 | INV | 84 | A | O | I | CFC | 43 | 43 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 303000 | 0 | 303000 | 303000 | 100% | 0 | 0 | 0 | 39390 | 0 | 39390 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
COM | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | BRA | SEV | 23 | TAS | 85 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1999-05-01 |  | 2000-07-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2000. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Niju Ind. Com Implem Rodov Ltda. | Individual | LAC | BRA | REF | 23 | INV | 86 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 111600 | 0 | 111600 | 111600 | 100% | 0 | 0 | 0 | 14508 | 0 | 14508 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mikawa & Cia | Individual | LAC | BRA | FOA | 23 | INV | 87 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 80600 | 0 | 80600 | 80600 | 100% | 0 | 0 | 0 | 10478 | 0 | 10478 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mais Frio | Individual | LAC | BRA | REF | 23 | INV | 88 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 154400 | -25 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20072 | -3 | 20069 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kalf Calcados | Individual | LAC | BRA | FOA | 23 | INV | 89 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-11-01 | 2003-11-01 | 101100 | 0 | 101100 | 101100 | 100% | 0 | 0 | 0 | 13143 | 0 | 13143 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Increal Ltda. | Individual | LAC | BRA | REF | 23 | INV | 90 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 418000 | -4 | 417996 | 417996 | 100% | 0 | 0 | 0 | 54340 | -1 | 54339 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Friar | Individual | LAC | BRA | REF | 23 | INV | 91 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2003-04-01 | 185726 | -1023 | 184703 | 184703 | 100% | 0 | 0 | 0 | 24144 | -133 | 24011 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Fast Frio | Individual | LAC | BRA | FOA | 23 | INV | 92 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at FJ Polymers | Individual | LAC | BRA | FOA | 23 | INV | 93 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 89500 | -992 | 88508 | 88508 | 100% | 0 | 0 | 0 | 11635 | -129 | 11506 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Espumatec | Individual | LAC | BRA | FOA | 23 | INV | 94 | A | O | I | CFC | 65 | 65 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-04-01 | 2003-04-01 | 372000 | -271 | 371729 | 371729 | 100% | 0 | 0 | 0 | 48360 | -35 | 48325 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Zenimont | Individual | LAC | BRA | FOA | 23 | INV | 95 | A | O | I | CFC | 38 | 38 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2001-04-01 | 2002-03-01 | 298300 | 0 | 298300 | 298300 | 100% | 0 | 0 | 0 | 38779 | 0 | 38779 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1997 | Investment
CLO | UNDP | Project preparation for two methyl bromide demonstration projects (soil fumigation for flowers, tomatoes, cucumbers and strawberries) | Individual | LAC | BRA | FUM | 24 | PRP | 96 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  |  | 2000-12-01 | 40000 | -31187 | 8813 | 8813 | 100% | 0 | 0 | 0 | 5200 | -4054 | 1146 | 0 | 0 | Canceled in 2000. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation to prepare 16 projects in the foam sector | Individual | LAC | BRA | FOA | 24 | PRP | 98 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 70000 | -12756 | 57244 | 57244 | 100% | 0 | 0 | 0 | 9100 | -1658 | 7442 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 4 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 24 | PRP | 99 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-07-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1998 | Investment
COM | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | BRA | SEV | 24 | INS | 100 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 2000-04-01 |  | 2000-11-01 |  | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 2000. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Injebank | Individual | LAC | BRA | FOA | 25 | INV | 101 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-04-01 | 86300 | -10846 | 75454 | 75454 | 100% | 0 | 0 | 0 | 11219 | -1410 | 9809 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to hexane and LCD technology in the manufacture of polyurethane foam at Herval | Individual | LAC | BRA | FOA | 25 | INV | 102 | A | O | I | CFC | 64 | 64 | 0 | 0 | 1998-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 637335 | 0 | 637335 | 637335 | 100% | 0 | 0 | 0 | 82854 | 0 | 82854 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to water based technology in the manufacture of polyurethane foam at Refratarios Isolamentos e Pinturas (RIP) | Individual | LAC | BRA | FOA | 25 | INV | 104 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-07-01 | 2003-04-01 | 94000 | -945 | 93055 | 93055 | 100% | 0 | 0 | 0 | 12220 | -123 | 12097 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Panther | Individual | LAC | BRA | FOA | 25 | INV | 105 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2000-11-01 | 2003-05-01 | 275805 | 0 | 275805 | 275805 | 100% | 0 | 0 | 0 | 35855 | 0 | 35855 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Gnatus | Individual | LAC | BRA | FOA | 25 | INV | 107 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-04-01 | 207225 | -488 | 206737 | 206737 | 100% | 0 | 0 | 0 | 26939 | -63 | 26876 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Cougar | Individual | LAC | BRA | FOA | 25 | INV | 108 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 154375 | 0 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20069 | 0 | 20069 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of polyurethane foam at SSM Tecnologia | Individual | LAC | BRA | FOA | 25 | INV | 109 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2003-11-01 | 106500 | 0 | 106500 | 106500 | 100% | 0 | 0 | 0 | 13845 | 0 | 13845 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of polyurethane foam at Delta Pack | Individual | LAC | BRA | FOA | 25 | INV | 110 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 202500 | 0 | 202500 | 202500 | 100% | 0 | 0 | 0 | 26325 | 0 | 26325 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b (foam) and HFC-134a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at Termisa | Individual | LAC | BRA | REF | 25 | INV | 111 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2001-12-01 | 322205 | 0 | 322205 | 322205 | 100% | 0 | 0 | 0 | 41887 | 0 | 41887 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at Isoblock | Individual | LAC | BRA | FOA | 26 | INV | 112 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-04-01 | 106500 | -132 | 106368 | 106368 | 100% | 0 | 0 | 0 | 13845 | -17 | 13828 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at C.A. Cunha | Individual | LAC | BRA | FOA | 26 | INV | 113 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-11-01 | 70100 | 0 | 70100 | 70100 | 100% | 0 | 0 | 0 | 9113 | 0 | 9113 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at P.F.I. Ind. E Com. Refrigeracao Ltd. (P.F.I.) | Individual | LAC | BRA | FOA | 26 | INV | 114 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-11-01 | 64200 | 0 | 64200 | 64200 | 100% | 0 | 0 | 0 | 8346 | 0 | 8346 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and CFC-12 by conversion to HFC-134a in the manufacture of small commercial freezers and coolers at Bebber | Individual | LAC | BRA | REF | 26 | INV | 115 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2002-04-01 | 144500 | -3024 | 141476 | 141476 | 100% | 0 | 0 | 0 | 18785 | -393 | 18392 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by HCFC-141b in the manufacture of integral skin foam furniture and conversion from CFC-11 to methylene chloride in the manufacture of polyurethane boxfoam at Cantegril | Individual | LAC | BRA | FOA | 26 | INV | 116 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-05-01 | 154740 | -4476 | 150264 | 150264 | 100% | 0 | 0 | 0 | 20116 | -582 | 19534 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams (microcellular) at Bicicletos Caloi, S.A. | Individual | LAC | BRA | FOA | 27 | INV | 117 | A | O | I | CFC | 41 | 41 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 227600 | -4765 | 222835 | 222835 | 100% | 0 | 0 | 0 | 29588 | -619 | 28969 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b technology (foam) and HFC-134a -134a technology (refrigerant) in the manufacture of refrigerated truck trailers at Artica | Individual | LAC | BRA | REF | 27 | INV | 118 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-11-01 | 2003-10-01 | 183623 | -7277 | 176346 | 176346 | 100% | 0 | 0 | 0 | 23871 | -946 | 22925 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Conter Ind. e Isolantes Termocos, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 120 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 85347 | 0 | 85347 | 85347 | 100% | 0 | 0 | 0 | 11095 | 0 | 11095 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of four projects in the foam sector | Individual | LAC | BRA | FOA | 27 | PRP | 121 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration sector | Individual | LAC | BRA | REF | 27 | PRP | 122 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of six projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 123 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of five projects in integral skin foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 124 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of integral skin foams at Spandy Peças em Poliuretano, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 125 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 261400 | -4032 | 257368 | 257368 | 100% | 0 | 0 | 0 | 33982 | -524 | 33458 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 27 | PRP | 128 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fabrica De Carrocerias Farage, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 129 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 52770 | 0 | 52770 | 52770 | 100% | 0 | 0 | 0 | 6860 | 0 | 6860 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Posto de Molas Vivian, Ltda. (Posmovil) | Individual | LAC | BRA | FOA | 27 | INV | 130 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 44700 | 0 | 44700 | 44700 | 100% | 0 | 0 | 0 | 5811 | 0 | 5811 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane sprayfoam at Isotherm Tratamento Thermo Acoustico Ltda. | Individual | LAC | BRA | FOA | 28 | INV | 131 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 116768 | 0 | 116768 | 116768 | 100% | 0 | 0 | 0 | 15180 | 0 | 15180 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Phase-out of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers by conversion to cyclo-pentane and HCF-134a at Metalurgica Venan Ltda. | Individual | LAC | BRA | REF | 28 | INV | 132 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-02-01 |  | 2004-03-01 |  | 741800 | 0 | 741800 | 713564 | 96.19% | 28236 | 0 | 14118 | 91598 | 0 | 88111.3983 | 3486.6017 | 0 | Completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11, CFC-12 and R-502 by conversion to HCFC-141b technology (foam) and HFC-134a and R-404a technology (refrigerant) in the manufacture of milk coolers and display cabinets at Incomar | Individual | LAC | BRA | REF | 28 | INV | 133 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 74529 | 0 | 74529 | 74529 | 100% | 0 | 0 | 0 | 9689 | 0 | 9689 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-402a in the manufacture of commercial refrigeration products at General Icy | Individual | LAC | BRA | REF | 28 | INV | 134 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 411139 | 0 | 411139 | 411139 | 100% | 0 | 0 | 0 | 53448 | 0 | 53448 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam at Polsul Group | Individual | LAC | BRA | FOA | 28 | INV | 135 | A | O | I | CFC | 55 | 55 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2002-11-01 |  | 536892 | 0 | 536892 | 512502 | 95.46% | 24390 | 0 | 12195 | 69058 | 0 | 65920.8241 | 3137.1759 | 0 | Completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible integral skin at Moldepol | Individual | LAC | BRA | FOA | 28 | INV | 136 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 421444 | -2 | 421442 | 421442 | 100% | 0 | 0 | 0 | 54788 | 0 | 54788 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ananda | Individual | LAC | BRA | FOA | 28 | INV | 137 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2002-04-01 | 37380 | -14147 | 23233 | 23233 | 100% | 0 | 0 | 0 | 4859 | -1839 | 3020 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in flexible molded foam, to water and methylene chloride technology in semi-rigid packaging foam, and to HCFC-141b in flexible integral skin foams at Espuma Oeste | Individual | LAC | BRA | FOA | 28 | INV | 138 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 181616 | -5766 | 175850 | 175850 | 100% | 0 | 0 | 0 | 23610 | -750 | 22860 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and integral skin foam at JNP Group | Individual | LAC | BRA | FOA | 28 | INV | 140 | A | O | I | CFC | 80 | 80 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2002-12-01 |  | 823867 | 0 | 823867 | 801810 | 97.32% | 22057 | 0 | 11028.5 | 100625 | 0 | 97931.0146 | 2693.9853 | 0 | Completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in rigid polyurethane foam (spray and pour in place) at SIFC | Individual | LAC | BRA | FOA | 28 | INV | 143 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2000-11-01 | 2003-05-01 | 74385 | 0 | 74385 | 74385 | 100% | 0 | 0 | 0 | 9670 | 0 | 9670 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibrart | Individual | LAC | BRA | FOA | 29 | INV | 144 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 111838 | 0 | 111838 | 111838 | 100% | 0 | 0 | 0 | 14539 | 0 | 14539 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Durothan | Individual | LAC | BRA | FOA | 29 | INV | 145 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 228625 | 0 | 228625 | 228625 | 100% | 0 | 0 | 0 | 29721 | 0 | 29721 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at ACS Fibra | Individual | LAC | BRA | FOA | 29 | INV | 146 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 119336 | -2316 | 117020 | 117020 | 100% | 0 | 0 | 0 | 15514 | -301 | 15213 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam for packaging and to HCFC-141b technology for insulation applications at World Pack da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 147 | A | O | I | CFC | 87 | 87 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-10-01 | 405610 | 0 | 405610 | 405610 | 100% | 0 | 0 | 0 | 52729 | 0 | 52729 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for display cabinets at Vacuum Systems | Individual | LAC | BRA | FOA | 29 | INV | 148 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2001-12-01 | 2003-09-01 | 117450 | -1 | 117449 | 117449 | 100% | 0 | 0 | 0 | 15269 | 0 | 15269 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Plastwork Embalagens da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 149 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 144855 | -1757 | 143098 | 143098 | 100% | 0 | 0 | 0 | 18831 | -228 | 18603 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Intertelhas | Individual | LAC | BRA | FOA | 29 | INV | 150 | A | O | I | CFC | 49 | 49 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2000-12-01 | 2002-11-01 | 170074 | -62845 | 107229 | 107229 | 100% | 0 | 0 | 0 | 22110 | -8170 | 13940 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of rigid integral skin foam at Spray | Individual | LAC | BRA | FOA | 29 | INV | 151 | A | O | I | CFC | 32 | 32 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 211080 | -4717 | 206363 | 206363 | 100% | 0 | 0 | 0 | 27440 | -613 | 26827 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams at Nicos do Brasil | Individual | LAC | BRA | FOA | 29 | INV | 152 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Brasinj Ind. E Comm. | Individual | LAC | BRA | FOA | 29 | INV | 153 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 71253 | 0 | 71253 | 71253 | 100% | 0 | 0 | 0 | 9263 | 0 | 9263 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam and sprayfoam at Calorisol | Individual | LAC | BRA | FOA | 29 | INV | 154 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 91477 | -33 | 91444 | 91444 | 100% | 0 | 0 | 0 | 11892 | -4 | 11888 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at ELV TEC Industria e Commercio Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 155 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 134265 | 0 | 134265 | 134265 | 100% | 0 | 0 | 0 | 17454 | 0 | 17454 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin and flexible molded foams at Purtec | Individual | LAC | BRA | FOA | 29 | INV | 156 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2005-10-01 | 140769 | 0 | 140769 | 137595 | 97.75% | 3174 | 0 | 0 | 18300 | 0 | 17887.3793 | 412.6207 | 0 | Completed in 2001. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isolamento Termico Brasfoam Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 157 | A | O | I | CFC | 62 | 62 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 110200 | -2358 | 107842 | 107842 | 100% | 0 | 0 | 0 | 14326 | -307 | 14019 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Fibrasil Ind. Commercio de Carroceria Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 158 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-05-01 | 2003-09-01 | 93425 | -32890 | 60535 | 60535 | 100% | 0 | 0 | 0 | 12145 | -4275 | 7870 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of 10 projects in the integral skin foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 160 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 161 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 3 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 30 | PRP | 162 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector (SMEs) | Individual | LAC | BRA | FOA | 30 | PRP | 163 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
CLO | UNDP | Preparation of 5 projects in the foam sector | Individual | LAC | BRA | FOA | 30 | PRP | 164 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2004-02-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-404a in the manufacture of freezer rooms and panels, and rigid foam at Schmit | Individual | LAC | BRA | REF | 31 | INV | 166 | A | O | I | CFC | 43 | 43 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2002-10-01 | 2003-11-01 | 288764 | -29918 | 258846 | 258846 | 100% | 0 | 0 | 0 | 37539 | -3889 | 33650 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and flexible molded foam at Fabbrini | Individual | LAC | BRA | FOA | 31 | INV | 167 | A | O | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 124887 | -17316 | 107571 | 107571 | 100% | 0 | 0 | 0 | 16235 | -2251 | 13984 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Menaf | Individual | LAC | BRA | FOA | 31 | INV | 168 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 80994 | -11239 | 69755 | 69755 | 100% | 0 | 0 | 0 | 10529 | -1461 | 9068 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water-based technology in the manufacture of rigid polyurethane foam at Polyfoam | Individual | LAC | BRA | FOA | 31 | INV | 169 | A | O | I | CFC | 42 | 42 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2003-10-01 | 2005-09-01 | 178873 | 0 | 178873 | 155221 | 86.78% | 23652 | 0 | 0 | 23253 | 0 | 20178.3048 | 3074.6952 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Massimo | Individual | LAC | BRA | FOA | 31 | INV | 173 | A | O | I | CFC | 8 | 8 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-09-01 | 2003-09-01 | 52279 | -5260 | 47019 | 47019 | 100% | 0 | 0 | 0 | 6796 | -684 | 6112 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and rigid foam at Injepol | Individual | LAC | BRA | FOA | 31 | INV | 175 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 107678 | -9727 | 97951 | 97951 | 100% | 0 | 0 | 0 | 13998 | -1265 | 12733 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin and flexible molded foam at PPU | Individual | LAC | BRA | FOA | 31 | INV | 178 | A | O | I | CFC | 9 | 9 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2003-09-01 | 64568 | -5159 | 59409 | 59409 | 100% | 0 | 0 | 0 | 8394 | -671 | 7723 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Packo Plurinox | Individual | LAC | BRA | FOA | 31 | INV | 179 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2000-12-01 | 2001-12-01 | 39750 | 0 | 39750 | 39750 | 100% | 0 | 0 | 0 | 5168 | 0 | 5168 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at Mach-Plast | Individual | LAC | BRA | FOA | 31 | INV | 180 | A | O | I | CFC | 30 | 30 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 188951 | -12871 | 176080 | 176080 | 100% | 0 | 0 | 0 | 24564 | -1673 | 22891 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin and rigid foam at Montreal | Individual | LAC | BRA | FOA | 31 | INV | 181 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2003-08-01 |  | 2002-08-01 | 2003-09-01 | 83117 | 0 | 83117 | 83117 | 100% | 0 | 0 | 0 | 10805 | 0 | 10805 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Politermo | Individual | LAC | BRA | FOA | 31 | INV | 182 | A | O | I | CFC | 50 | 50 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 219136 | -2808 | 216328 | 216328 | 100% | 0 | 0 | 0 | 28488 | -365 | 28123 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin foam, flexible molded foam and rigid foam at Jetpol | Individual | LAC | BRA | FOA | 31 | INV | 183 | A | O | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-12-01 | 2003-08-01 |  | 2002-05-01 | 2003-09-01 | 214600 | -9772 | 204828 | 204828 | 100% | 0 | 0 | 0 | 27898 | -1270 | 26628 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam and rigid foam at Trantor | Individual | LAC | BRA | FOA | 31 | INV | 184 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 102234 | -5218 | 97016 | 97016 | 100% | 0 | 0 | 0 | 13290 | -679 | 12611 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refripor | Individual | LAC | BRA | FOA | 31 | INV | 185 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2001-12-01 | 2004-01-01 | 85350 | -16916 | 68434 | 68434 | 100% | 0 | 0 | 0 | 11096 | -2199 | 8897 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam, from CFC-11 to water-blown foam in flexible molded foam, and from CFC-11 to HCFC-141b in flexible integral skin foam at Multispuma | Individual | LAC | BRA | FOA | 31 | INV | 187 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 123929 | 0 | 123929 | 123929 | 100% | 0 | 0 | 0 | 16111 | 0 | 16111 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
COM | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin (shoesoles) at Prosola | Individual | LAC | BRA | FOA | 31 | INV | 188 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2003-08-01 |  | 2004-12-01 |  | 214118 | 0 | 214118 | 213953 | 99.92% | 165 | 0 | 82.5 | 27835 | 0 | 27813.5503 | 21.4497 | 0 | Completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and flexible molded/integral skin foam at 50 small enterprises centered around their systems house Plastquim | Individual | LAC | BRA | FOA | 31 | INV | 189 | A | O | I | CFC | 153 | 153 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-12-01 | 931599 | 0 | 931599 | 890119 | 95.55% | 41480 | 0 | 0 | 112476 | 0 | 107467.9391 | 5008.0608 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Rytpak | Individual | LAC | BRA | FOA | 32 | INV | 190 | A | O | I | CFC | 27 | 27 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-03-01 | 2003-04-01 | 211410 | -22300 | 189110 | 189110 | 100% | 0 | 0 | 0 | 27483 | -2899 | 24584 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams (shoesoles) at Megaflex | Individual | LAC | BRA | FOA | 32 | INV | 191 | A | O | I | CFC | 42 | 42 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-04-01 | 2003-05-01 | 205568 | -4726 | 200842 | 200842 | 100% | 0 | 0 | 0 | 26724 | -614 | 26110 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Plastiron | Individual | LAC | BRA | FOA | 32 | INV | 192 | A | O | I | CFC | 32 | 32 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 131768 | -5277 | 126491 | 126491 | 100% | 0 | 0 | 0 | 17130 | -686 | 16444 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refri-Leste | Individual | LAC | BRA | FOA | 32 | INV | 193 | A | O | I | CFC | 30 | 30 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-09-01 | 2003-04-01 | 136840 | -232 | 136608 | 136608 | 100% | 0 | 0 | 0 | 17789 | -30 | 17759 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam and to HCFC-141b for rigid polyurethane foam at Poliumetka | Individual | LAC | BRA | FOA | 32 | INV | 194 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-05-01 | 2003-09-01 | 136183 | -10263 | 125920 | 125920 | 100% | 0 | 0 | 0 | 17704 | -1334 | 16370 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Termobras | Individual | LAC | BRA | FOA | 32 | INV | 195 | A | O | I | CFC | 77 | 77 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2003-08-01 | 2005-09-01 | 294590 | -39496 | 255094 | 255094 | 100% | 0 | 0 | 0 | 38297 | -5135 | 33162 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-12 to isobutane technology in the manufacture of extruded polyethylene foam at Thermo-flex | Individual | LAC | BRA | FOA | 32 | INV | 196 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-10-01 | 123300 | 0 | 123300 | 123300 | 100% | 0 | 0 | 0 | 16029 | 0 | 16029 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water technology in the manufacture of rigid polyurethane foam at Ser Therm | Individual | LAC | BRA | FOA | 32 | INV | 197 | A | O | I | CFC | 72 | 72 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 359791 | -76117 | 283674 | 283674 | 100% | 0 | 0 | 0 | 46773 | -9895 | 36878 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manfuacture of rigid polyurethane foam at Jose Sola | Individual | LAC | BRA | FOA | 32 | INV | 198 | A | O | I | CFC | 39 | 39 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2002-11-01 | 2005-09-01 | 150369 | -24740 | 125629 | 125629 | 100% | 0 | 0 | 0 | 19548 | -3216 | 16332 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 2000 | Investment
ONG | UNDP | Renewal of institutional strengthening (Phase III) | Individual | LAC | BRA | SEV | 32 | INS | 199 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 | 2006-03-01 |  |  | 270000 | 0 | 270000 | 240792 | 89.18% | 29208 | 0 | 10222.8 | 35100 | 0 | 31302.96 | 3797.04 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | BRA | REF | 32 | TAS | 200 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2003-07-01 | 100000 | -1 | 99999 | 99999 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Frigs | Individual | LAC | BRA | FOA | 32 | INV | 201 | A | O | I | CFC | 90 | 90 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 311056 | -73855 | 237201 | 237201 | 100% | 0 | 0 | 0 | 40437 | -9601 | 30836 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 202 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 207 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 208 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 209 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-12-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 210 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Juntafacil | Individual | LAC | BRA | FOA | 34 | INV | 211 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2004-01-01 | 55204 | -3500 | 51704 | 51704 | 100% | 0 | 0 | 0 | 7177 | -455 | 6722 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Ornati-Luce | Individual | LAC | BRA | FOA | 34 | INV | 212 | A | O | I | CFC | 14 | 14 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2003-11-01 | 46292 | -1550 | 44742 | 44742 | 100% | 0 | 0 | 0 | 6018 | -202 | 5816 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam at Paranoa | Individual | LAC | BRA | FOA | 34 | INV | 213 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-05-01 | 2004-01-01 | 84660 | -1 | 84659 | 84659 | 100% | 0 | 0 | 0 | 11006 | 0 | 11006 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam and rigid integral skin foam at Piatex | Individual | LAC | BRA | FOA | 34 | INV | 214 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-11-01 | 83075 | 0 | 83075 | 83075 | 100% | 0 | 0 | 0 | 10800 | 0 | 10800 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of flexible molded foam and to HCFC-141b for flexible integral skin foam at Rosil | Individual | LAC | BRA | FOA | 34 | INV | 215 | A | O | I | CFC | 5 | 5 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 87672 | -2545 | 85127 | 85127 | 100% | 0 | 0 | 0 | 11397 | -331 | 11066 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible integral skin and flexible molded foams at Royal Rubber | Individual | LAC | BRA | FOA | 34 | INV | 216 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 120795 | -3396 | 117399 | 117399 | 100% | 0 | 0 | 0 | 15703 | -442 | 15261 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for electrical resistance floats at Taurus | Individual | LAC | BRA | FOA | 34 | INV | 217 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 88075 | 0 | 88075 | 88075 | 100% | 0 | 0 | 0 | 11450 | 0 | 11450 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Thermoblock | Individual | LAC | BRA | FOA | 34 | INV | 218 | A | O | I | CFC | 41 | 41 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 260592 | -36386 | 224206 | 224206 | 100% | 0 | 0 | 0 | 33877 | -4730 | 29147 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based and HCFC-141b technology in the manufacture of rigid and flexible integral skin foam at VM | Individual | LAC | BRA | FOA | 34 | INV | 220 | A | O | I | CFC | 14 | 14 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-11-01 | 83902 | 0 | 83902 | 83902 | 100% | 0 | 0 | 0 | 10907 | 0 | 10907 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for surfboards at Jedda | Individual | LAC | BRA | FOA | 34 | INV | 221 | A | O | I | CFC | 54 | 54 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 148272 | -32257 | 116015 | 116015 | 100% | 0 | 0 | 0 | 19275 | -4193 | 15082 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Transen | Individual | LAC | BRA | FOA | 34 | INV | 224 | A | O | I | CFC | 19 | 19 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 61940 | -1800 | 60140 | 60140 | 100% | 0 | 0 | 0 | 8052 | -234 | 7818 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam for cold room panels, freezers and coolers at Central Equipment | Individual | LAC | BRA | FOA | 34 | INV | 225 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 118233 | -8399 | 109834 | 109834 | 100% | 0 | 0 | 0 | 15370 | -1092 | 14278 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isar | Individual | LAC | BRA | FOA | 34 | INV | 226 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 174320 | -12870 | 161450 | 161450 | 100% | 0 | 0 | 0 | 22662 | -1673 | 20989 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoeste | Individual | LAC | BRA | FOA | 34 | INV | 227 | A | O | I | CFC | 65 | 65 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 |  | 237296 | 0 | 237296 | 204068 | 86% | 33228 | 0 | 16614 | 30848 | 0 | 26528.4272 | 4319.5728 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid and flexible integral skin foams at Air Micro | Individual | LAC | BRA | FOA | 34 | INV | 229 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2004-01-01 | 56490 | -2984 | 53506 | 53506 | 100% | 0 | 0 | 0 | 7344 | -388 | 6956 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Beneplast | Individual | LAC | BRA | FOA | 34 | INV | 230 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 135176 | -12534 | 122642 | 122642 | 100% | 0 | 0 | 0 | 17573 | -1629 | 15944 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Korta Calhas | Individual | LAC | BRA | FOA | 34 | INV | 231 | A | O | I | CFC | 76 | 76 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 151812 | 0 | 151812 | 151812 | 100% | 0 | 0 | 0 | 19736 | 0 | 19736 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam, rigid foam and flexible molded foam at Carolinas | Individual | LAC | BRA | FOA | 34 | INV | 232 | A | O | I | CFC | 50 | 50 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 237597 | -80 | 237517 | 237517 | 100% | 0 | 0 | 0 | 30888 | -10 | 30878 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam and rigid integral skin foam, and to HCFC-141b for rigid, flexible integral skin and phenolic foams at J. Dal Ponte | Individual | LAC | BRA | FOA | 34 | INV | 233 | A | O | I | CFC | 98 | 98 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 384134 | 0 | 384134 | 384134 | 100% | 0 | 0 | 0 | 49937 | 0 | 49937 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HFC-141b in the manufacture of rigid polyurethane foam at Danko | Individual | LAC | BRA | FOA | 34 | INV | 234 | A | O | I | CFC | 41 | 41 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 199684 | 0 | 199684 | 196355 | 98.33% | 3329 | 0 | 0 | 25959 | 0 | 25526.2287 | 432.7713 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for truck bodies and panels at 9 enterprises (ABC Furgoes, Fricam Refri, Junges, Rafaeli, Refri Santos, Rondofrio, Tresmaiense, Trevosul Refrig, Verde Lago Furgoes) | Individual | LAC | BRA | FOA | 34 | INV | 235 | A | O | I | CFC | 65 | 65 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-12-01 | 450479 | -41321 | 409158 | 380877 | 93.09% | 28281 | 0 | 0 | 58562 | -5372 | 49513.5073 | 3676.4927 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Grupo ACO | Individual | LAC | BRA | FOA | 34 | INV | 236 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2004-08-01 |  |  | 2002-07-01 | 174139 | -174139 | 0 | 0 |  | 0 | 0 | 0 | 22638 | -22638 | 0 | 0 | 0 | Canceled in 2002. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoprice | Individual | LAC | BRA | FOA | 34 | INV | 237 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-12-01 |  | 126846 | 0 | 126846 | 117172 | 92.37% | 9674 | 0 | 4837 | 16490 | 0 | 15232.3785 | 1257.6215 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible microcellular foams at Hidroplas | Individual | LAC | BRA | FOA | 34 | INV | 238 | A | O | I | CFC | 33 | 33 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2002-11-01 | 2004-01-01 | 166211 | -5537 | 160674 | 160674 | 100% | 0 | 0 | 0 | 21607 | -720 | 20887 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam for ice cream makers and coolers at three enterprises (A.V. Bertollo, Citrocar, Systherm) | Individual | LAC | BRA | FOA | 34 | INV | 239 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-10-01 | 2005-12-01 | 135345 | -2457 | 132888 | 132888 | 100% | 0 | 0 | 0 | 17595 | -319 | 17276 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Injetec | Individual | LAC | BRA | FOA | 34 | INV | 240 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 43334 | -2371 | 40963 | 40963 | 100% | 0 | 0 | 0 | 5633 | -308 | 5325 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Pretty Glass | Individual | LAC | BRA | FOA | 36 | INV | 243 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 91508 | 0 | 91508 | 85043 | 92.94% | 6465 | 0 | 0 | 11896 | 0 | 11055.59 | 840.45 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Decorfrio | Individual | LAC | BRA | FOA | 36 | INV | 244 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2005-12-01 |  | 98416 | 0 | 98416 | 98663 | 100.3% | -247 | 0 | 0 | 12794 | 0 | 12826.19 | -32.11 | 0 | Completed in 2005. Equipment installed at new location, trials successful , local works completed. HOP issued Dec. 2005. Apparent overrun to be resolved in 2006. | [10 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Simonaggio | Individual | LAC | BRA | FOA | 36 | INV | 245 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-09-01 | 120383 | 0 | 120383 | 109743 | 91.16% | 10640 | 0 | 0 | 15650 | 0 | 14266.59 | 1383.2 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Heliotek | Individual | LAC | BRA | FOA | 36 | INV | 246 | A | O | I | CFC | 27 | 27 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 127133 | 0 | 127133 | 114912 | 90.39% | 12221 | 0 | 0 | 16527 | 0 | 14938.56 | 1588.73 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isojet | Individual | LAC | BRA | FOA | 36 | INV | 247 | A | O | I | CFC | 47 | 47 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 130427 | 0 | 130427 | 130427 | 100% | 0 | 0 | 0 | 16956 | 0 | 16955.51 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Tecnosono | Individual | LAC | BRA | FOA | 36 | INV | 248 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2003-07-01 | 2004-01-01 | 134718 | -4512 | 130206 | 130206 | 100% | 0 | 0 | 0 | 17513 | -587 | 16926.34 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Tolling Quimica | Individual | LAC | BRA | FOA | 36 | INV | 249 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-08-01 | 2005-10-01 | 159662 | 0 | 159662 | 158306 | 99.15% | 1356 | 0 | 0 | 20756 | 0 | 20579.78 | 176.28 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
COM | UNDP | Phase-out of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibral | Individual | LAC | BRA | FOA | 36 | INV | 250 | A | O | I | CFC | 48 | 48 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 |  | 197613 | 0 | 197613 | 196760 | 99.57% | 853 | 0 | 426.5 | 25690 | 0 | 25578.8 | 110.89 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Preparation of a CFC terminal phase-out programme | Individual | LAC | BRA | PHA | 36 | PRP | 251 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 2002. Financially closed in 2005. | [10 empty] | 2002 | Investment
COM | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam, and water-blown technology for flexible moulded foam at Arquespuma | Individual | LAC | BRA | FOA | 36 | INV | 252 | A | O | I | CFC | 56 | 56 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 |  | 207741 | 0 | 207741 | 207789 | 100% | -48 | 0 | 0 | 27006 | 0 | 27012.57 | -6.24 | 0 | Completed in 2003. Apparent overrun to be resolved in 2006. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isosister | Individual | LAC | BRA | FOA | 36 | INV | 254 | A | O | I | CFC | 82 | 82 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 |  | 277668 | 0 | 277668 | 261860 | 94.31% | 15808 | 0 | 7904 | 36097 | 0 | 34041.8 | 2055.04 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water/methylene chloride/hydrocarbon-blown technology in the manufacture of rigid and flexible foam at Toro | Individual | LAC | BRA | FOA | 36 | INV | 255 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2004-12-01 | 2005-10-01 | 279477 | 0 | 279477 | 279477 | 100% | 0 | 0 | 0 | 36332 | 0 | 36332.01 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Repor | Individual | LAC | BRA | FOA | 36 | INV | 256 | A | O | I | CFC | 51 | 51 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 |  | 323201 | 0 | 323201 | 265892 | 82.27% | 57309 | 0 | 28654.5 | 42016 | 0 | 34565.96 | 7450.17 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid foam and flexible integral skin foam and water-blown technology for flexible moulded foam and rigid integral skin foam at Ariston Polimeros | Individual | LAC | BRA | FOA | 36 | INV | 257 | A | O | I | CFC | 75 | 75 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-08-01 | 2005-09-01 | 369242 | 0 | 369242 | 356493 | 96.55% | 12749 | 0 | 0 | 48001 | 0 | 46344.09 | 1657.37 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Indaru | Individual | LAC | BRA | FOA | 36 | INV | 258 | A | O | I | CFC | 94 | 94 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2004-06-01 |  | 423121 | 0 | 423121 | 428886 | 101.4% | -5765 | 0 | 0 | 55006 | 0 | 55755.18 | -749.45 | 0 | Completed in 2004. Apparent overrun to be resolved in 2006. | [10 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam, elastomers and integral skin foam for automotive applications and to HCFC-141b for furniture integral skin foam applications at Steel Plastik | Individual | LAC | BRA | FOA | 36 | INV | 259 | A | O | I | CFC | 47 | 47 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-12-01 | 2005-11-01 | 247882 | 0 | 247882 | 247882 | 100% | 0 | 0 | 0 | 32225 | 0 | 32224.66 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | INV | 262 | N | O | I | CFC | 1251 | 1251 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2003-12-01 |  | 2005-12-01 |  | 7860000 | 0 | 7860000 | 7860000 | 100% | 0 | 0 | 0 | 687700 | 0 | 687700 | 0 | 0 | Completed in 2005. R&R equipment purchased, 2 reclaim centers identified, purchase order issued. Database on chillers prepared , MAC companies identified and workshop for first 50 companies done. | [10 empty] | 2002 | Investment | 5801 | 5801 |  |  | Yes | Yes | yes
ONG | UNDP | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 264 | N | O | I | CFC | 737 | 737 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 | 2006-12-01 |  |  | 5720000 | 0 | 5720000 | 337291 | 5.897% | 5382709 | 0 | 1883948.15 | 500000 | 0 | 29483.479 | 470516.521 | 0 | Consumption targets accomplished, NPP publicity campaign undertaken, 1st reclaim center established (other 2 being prpared), 33 foam companies converted, other 32 completing their conversion and additional 18 being assisted by a new project. | [10 empty] | 2003 | Investment | 3813 | 3813 |  |  | Yes | Yes | Yes
COM | UNDP | Project preparation for the formulation of CTC as a process agent | Individual | LAC | BRA | SOL | 42 | PRP | 266 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-12-01 |  | 32000 | 0 | 32000 | 32000 | 100% | 0 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | Project prepared to assist two plants consuming CTC as process agent. One of the applications identified not in Dec. X/14, application sent to Ozone Secretariat. More information still to be collected to address MOP decision. | [10 empty] | 2004 | Investment
ONG | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BRA | SEV | 43 | INS | 267 | N | T | I | CFC | 29 | 14 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 351000 | 0 | 351000 | 0 | 0% | 351000 | 0 | 122850 | 26325 | 0 | 0 | 26325 | 0 | During 2005 Brazil continued in compliance with all control measures under the Montreal Protocol and the NOU continued successfully providing the legislative and managerial support to the ongoing ODS phase out activities The implementation of the ODS import licensing system allowed the country to maintain the reductions in the consumption of CFC while through the National Phase Out Plan all the conditions are being set for the consumer sectors to confront the transition to alternative technologies. Specific activities under the National Plan included the completion of 71 companies conversions in the foam sector and the almost completion of activities in this sector. The legislation including criteria and conditions to distribute equipment was established and the first workshop for training/distribution of MAC recovery and recycling equipment was completed. Reclaiming activities started in the reclaiming center of Sao Paulo. The NOU also continued cooperating with UNDP in the preparation of a CTC phase Out plan to be submitted in 2006. Other activities include the celebration of the Ozone Day with country wide media coverage and active participation in the Executive Committee, Meeting of the Parties and Regional Meetings for Ozone Officers. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | National CFC phase-out plan: third tranche | Multi-Year | LAC | BRA | PHA | 45 | INV | 270 | N | O | I | CFC | 743 | 743 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 3970000 | 0 | 3970000 | 0 | 0% | 3970000 | 0 | 1389500 | 342500 | 0 | 0 | 342500 | 0 | Consumption targets accomplished. 1st workshop for training/distribution of MAC R&R equipment completed. Additional 71 foams companies converted. Legislation to distribute recovery machines established. Reclaiming of CFC 12 in Sao Paulo started. | [10 empty] | 2005 | Investment | 3070 | 3070 |  |  | Yes | Yes | Yes
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | BRA | SEV | 45 | TAS | 271 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 183486 | 0 | 183486 | 0 | 0% | 183486 | 0 | 64220.1 | 16514 | 0 | 0 | 16514 | 0 | Preparatory work to initiate surveys and recruit consultants started. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | National CFC phase-out plan: fourth tranche | Multi-Year | LAC | BRA | PHA | 47 | INV | 274 | N | O | I | CFC | 1020 | 1020 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 2856400 | 0 | 2856400 | 0 | 0% | 2856400 | 0 | 999740 | 242276 | 0 | 0 | 242276 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment | 2050 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | BRA | REF | 47 | DEM | 275 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 0 | 200000 | 75000 | 0 | 0 | 75000 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | BRU | REF | 39 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration service and MAC sectors | RMP-Component | ASP | BRU | REF | 44 | TAS | 10 | N | O | I | No_ODP | 16 | 0 | 0 | 0 | 2004-12-01 |  | 2007-05-01 | 2007-05-01 |  |  | 390000 | 0 | 390000 | 0 | 0% | 390000 | 0 | 78000 | 29250 | 0 | 0 | 29250 | 0 | NOU contacted but still no response to initiate project inception mission. Effort intensified to contact NOU to get project started first half 2006 | [10 empty] | 2004 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | BZE | REF | 29 | TAS | 05 | A | O | I | CFC | 2 | 2 | 0 | 0 | 1999-11-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2003-09-01 | 61125 | 0 | 61125 | 61125 | 100% | 0 | 0 | 0 | 7946 | 0 | 7946 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Project preparation for the formulation of refrigerant management plan update (investment component) | Individual | LAC | BZE | REF | 42 | PRP | 09 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 |  | 20000 | 0 | 20000 | 14294 | 71.47% | 5706 | 0 | 5706 | 1500 | 0 | 1072.05 | 427.95 | 0 | Project preparation completed. Project submitted to and approved at ExCom 44. Some payments and final budget revision pending. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | LAC | BZE | REF | 44 | TAS | 12 | N | O | I | No_ODP | 4 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 44879 | 0 | 44879 | 0 | 0% | 44879 | 0 | 8975.8 | 4039 | 0 | 0 | 4039 | 0 | ProDoc signed and project under implementation. UNDP asked to wait for signing of MOU between Government and UNEP (lead agency). | [10 empty] | 2004 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | CAF | SEV | 18 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
CLO | UNDP | Continuation of conversion to CFC-free technology in manufacturing of flexible polyurethane foam at Vita-Centrafrique | Individual | AFR | CAF | FOA | 19 | INV | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1997-05-01 |  |  | 2001-12-01 | 62000 | -30537 | 31463 | 31463 | 100% | 0 | 0 | 0 | 8060 | -3970 | 4090 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  |  | 1998-04-01 | [7 empty] | 1996 | Investment
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | CAF | REF | 20 | TAS | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-09-01 |  |  | 2001-12-01 | 66441 | -923 | 65518 | 65518 | 100% | 0 | 0 | 0 | 8637 | -120 | 8517 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  |  |  | 1999-06-01 | [6 empty] | 1996 | Investment
COM | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | AFR | CBI | REF | 42 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 |  | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2005. Final payments done. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | CBI | REF | 44 | TAS | 08 | N | O | I | No_ODP | 1 | 0 | 0 | 0 | 2004-12-01 |  | 2007-06-01 | 2007-12-01 |  |  | 75400 | 0 | 75400 | 0 | 0% | 75400 | 0 | 15080 | 6786 | 0 | 0 | 6786 | 0 | Approved in Dec 2004. Awaiting legislation before initiating project as per ExCom condition. | [10 empty] | 2004 | Investment
FIN | UNDP | Preparation of a project in refrigerant recovery/recycling and RMP preparation | Individual | AFR | CHD | REF | 27 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | CHD | REF | 29 | TAS | 04 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 198252 | -36260 | 161992 | 161992 | 100% | 0 | 0 | 0 | 25773 | -4714 | 21059 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | CHD | REF | 29 | TAS | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-07-01 | 2005-10-01 | 15455 | 0 | 15455 | 10786 | 69.79% | 4669 | 0 | 0 | 2009 | 0 | 1402.0753 | 606.9247 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1999 | Non-Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | CHD | REF | 37 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-07-01 |  | 2002-12-01 | 2005-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Incentive programme for commercial/industrial end-user sector | RMP-Update-Comp | AFR | CHD | REF | 38 | TAS | 09 | N | O | I | CFC | 6 | 0 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 | 2007-12-01 |  |  | 184416 | 0 | 184416 | 9274 | 5.029% | 175142 | 0 | 35028.4 | 23974 | 0 | 1205.62 | 22768.46 | 0 | Nat.Cons. on board and workshop for awareness raising for end-users was held in N'Djamena in May 05. Questionnaires for applications were harmonized, translated and distributed to some potential applicants. First applications expected in 2006. | [10 empty] | 2002 | Non-Investment
FIN | UNDP | Demonstration programme for service centre technicians on CFC-11 venting and leakage from refrigerators during operation and servicing | Individual | LAC | CHI | REF | 06 | DEM | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project for soil fumigation in nurseries and seed beds for apples and kiwis | Individual | LAC | CHI | FUM | 24 | PRP | 32 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 2000-07-01 | 2003-12-01 | 25000 | -11504 | 13496 | 13496 | 100% | 0 | 0 | 0 | 3250 | -1496 | 1754 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of a project in the aerosol (sterilants) subsector | Individual | LAC | CHI | ARS | 30 | PRP | 140 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
ONG | UNDP | Demonstration and phase-out project for methyl bromide soil fumigation for fruit tree production and replant | One-off-Phaseout | LAC | CHI | FUM | 32 | INV | 143 | N | O | I | MeBr | 76 | 40 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2006-06-01 | 2006-12-01 |  |  | 805000 | 0 | 805000 | 741893 | 92.16% | 63107 | 0 | 22087.45 | 98550 | 0 | 90824.2921 | 7725.7079 | 0 | Strategic ntl WP change suggested at ntl level in order to allow project objectives to be modified so that 20% compliance target maintained. New ntl strategy to be submitted in Q1 06. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the sterilants sector | Individual | LAC | CHI | STE | 33 | PRP | 144 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Terminal conversion of ethylene oxide/CFC-12 mixtures to alternative non-ozone depleting technologies in 26 hospitals | Individual | LAC | CHI | STE | 35 | INV | 151 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2005-12-01 |  | 412741 | 0 | 412741 | 417020 | 101% | -4279 | 0 | 0 | 53656 | 0 | 54212.2666 | -556.2666 | 0 | Completed in 2005. Project visits took longer than originally foreseen. HOP issued and sent to NOU and UNDP for signature. Finalization expected early 2006. Apparent overrun to be resolved in 2006. | [10 empty] | 2001 | Investment
FIN | UNDP | Formulation of solvent sectoral phase-out plan | Individual | LAC | CHI | SOL | 39 | PRP | 153 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Technical assistance to phase-out ozone depleting solvents | Individual | LAC | CHI | SOL | 41 | TAS | 154 | N | O | I | CFC/TCA/CTC | 17 | 0 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2005-12-01 | 2006-12-01 |  |  | 245690 | 0 | 245690 | 37326 | 15.19% | 208364 | 0 | 72927.4 | 22112 | 0 | 3359.3248 | 18752.6752 | 0 | Project on track. Visit of Int.Expert, Workshop to companies using ODS and TAS to determine possible substitutes int heir formulations provided. Formulations with Non-ODS to be tested and companies to be converted to non-ODS in 2006 | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Project preparation for the formulation of commercial refrigeration project | Individual | LAC | CHI | REF | 42 | PRP | 155 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2005-04-01 | 2006-04-01 |  |  | 32000 | 0 | 32000 | 14704 | 45.95% | 17296 | 0 | 17296 | 2400 | 0 | 1102.8 | 1297.2 | 0 | Project preparation activities close to completion at 31 December 2005. Project to be submitted to 48th Excom Meeting. | [10 empty] | 2004 | Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COL | SEV | 12 | CPG | 01 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-03-01 |  | 1994-03-01 | 1994-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1994. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Institutional strengthening for implementation of the Montreal Protocol in Colombia | Individual | LAC | COL | SEV | 12 | INS | 02 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1997-03-01 |  | 1998-03-01 | 1999-12-01 | 317790 | 0 | 317790 | 317790 | 100% | 0 | 0 | 0 | 41313 | 0 | 41313 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 12 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Polarix Electrodomesticos, S.A. | Individual | LAC | COL | REF | 13 | INV | 04 | A | O | I | CFC | 63 | 63 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 844824 | -205206 | 639618 | 639618 | 100% | 0 | 0 | 0 | 109827 | -26677 | 83150 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Haceb, S.A. | Individual | LAC | COL | REF | 13 | INV | 05 | A | O | I | CFC | 69 | 69 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1386314 | -340578 | 1045736 | 1045736 | 100% | 0 | 0 | 0 | 180221 | -44275 | 135946 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Icasa, S.A. | Individual | LAC | COL | REF | 13 | INV | 06 | A | O | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1410680 | -358123 | 1052557 | 1052557 | 100% | 0 | 0 | 0 | 183388 | -46556 | 136832 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion of CFC-12 to HFC-134a compresors at Compresores Andinos, S.A. | Individual | LAC | COL | REF | 13 | INV | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 313650 | -23379 | 290271 | 290271 | 100% | 0 | 0 | 0 | 40774 | -3039 | 37735 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Corporacion de Electrodomesticos, S.A. (Corelsa) | Individual | LAC | COL | REF | 13 | INV | 08 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1999-07-01 | 2000-12-01 | 853432 | -166101 | 687331 | 687331 | 100% | 0 | 0 | 0 | 110946 | -21593 | 89353 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-02-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Manufacturas Ajover Ltda. | Individual | LAC | COL | FOA | 13 | INV | 09 | A | O | I | CFC | 190 | 190 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  | 1998-12-01 | 2001-12-01 | 691500 | -22425 | 669075 | 669075 | 100% | 0 | 0 | 0 | 89895 | -2915 | 86980 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1994 | Investment
CLO | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Industria Nacional de Desechables (Inaldes) | Individual | LAC | COL | FOA | 13 | INV | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  |  | 2001-12-01 | 380500 | -373255 | 7245 | 7245 | 100% | 0 | 0 | 0 | 49465 | -48523 | 942 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  |  |  | 2000-03-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industrias de Refrigeracion Comercial S.A. (Indufrial) | Individual | LAC | COL | REF | 15 | INV | 11 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-10-01 | 2000-12-01 | 442644 | -8866 | 433778 | 433778 | 100% | 0 | 0 | 0 | 57544 | -1153 | 56391 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Wonder S.A. | Individual | LAC | COL | REF | 15 | INV | 12 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-12-01 | 1999-12-01 | 251315 | 0 | 251315 | 251315 | 100% | 0 | 0 | 0 | 32671 | 0 | 32671 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrial Colombia S.A. (Inducol) | Individual | LAC | COL | REF | 15 | INV | 14 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2001-12-01 | 381548 | -36480 | 345068 | 345068 | 100% | 0 | 0 | 0 | 49601 | -4743 | 44858 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-02-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Friomix, S.A. | Individual | LAC | COL | REF | 17 | INV | 15 | A | O | D | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1999-01-01 | 1996-07-01 |  | 1999-02-01 | 2000-12-01 | 11146 | 0 | 11146 | 11146 | 100% | 0 | 0 | 0 | 1449 | 0 | 1449 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-02-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Westell Ltd. | Individual | LAC | COL | REF | 17 | INV | 16 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 227602 | -2 | 227600 | 227600 | 100% | 0 | 0 | 0 | 29588 | 0 | 29588 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 17 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-04-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1995 | Investment
COM | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COL | REF | 17 | TAS | 19 | N | O | I | CFC | 111 | 111 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-07-01 |  | 1999-07-01 |  | 787030 | -5 | 787025 | 787025 | 100% | 0 | 0 | 0 | 102314 | -1 | 102313 | 0 | 0 | Completed in 1999. |  |  |  | 1999-06-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 18 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Unilemh Ltd. (Challenger) | Individual | LAC | COL | REF | 18 | INV | 21 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-07-01 | 155350 | -1561 | 153789 | 153789 | 100% | 0 | 0 | 0 | 20196 | -203 | 19993 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refrigeracion Supernordico Ltda. | Individual | LAC | COL | REF | 19 | INV | 22 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2004-01-01 | 162500 | -1243 | 161257 | 161257 | 100% | 0 | 0 | 0 | 21125 | -162 | 20963 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1996 | Investment
COM | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | COL | SEV | 24 | INS | 25 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 2000-03-01 |  | 2000-03-01 |  | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2000. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | COL | FOA | 24 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-07-01 | 1998-12-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Manilit, S.A. | Individual | LAC | COL | FOA | 29 | INV | 36 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2004-01-01 | 62230 | -679 | 61551 | 61551 | 100% | 0 | 0 | 0 | 8090 | -88 | 8002 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Industrias Refridcol, Ltda. | Individual | LAC | COL | FOA | 29 | INV | 37 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-09-01 | 117450 | 0 | 117450 | 117450 | 100% | 0 | 0 | 0 | 15268 | 0 | 15268 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Dinalsa | Individual | LAC | COL | FOA | 29 | INV | 38 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78625 | 0 | 78625 | 78625 | 100% | 0 | 0 | 0 | 10221 | 0 | 10221 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | COL | FOA | 30 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
COM | UNDP | Renewal of institutional strengthening: Phase 3 | Individual | LAC | COL | SEV | 30 | INS | 42 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2002-04-01 |  | 2003-05-01 |  | 212000 | 0 | 212000 | 211582 | 99.8% | 418 | 0 | 209 | 27560 | 0 | 27505.66 | 54.34 | 0 | Completed in 2003. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COL | REF | 32 | TAS | 46 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2003-12-01 | 2005-10-01 | 40000 | 0 | 40000 | 37422 | 93.55% | 2578 | 0 | 0 | 5200 | 0 | 4864.86 | 335.14 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [7 empty] | 2003-01-01 |  |  | 2000 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at Olaflex with a technical assistance programme covering 10 small customers | Individual | LAC | COL | FOA | 32 | INV | 47 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2001-12-01 | 2003-10-01 | 191833 | 0 | 191833 | 191833 | 100% | 0 | 0 | 0 | 24938 | 0 | 24938 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion rom CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at 25 small enterprises centered around their systems house Espumlatex | Individual | LAC | COL | FOA | 32 | INV | 48 | A | O | I | CFC | 38 | 38 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2004-12-01 | 2004-12-01 | 332768 | 0 | 332768 | 332768 | 100% | 0 | 0 | 0 | 43260 | 0 | 43260 | 0 | 0 | Completed in 2004. Financially completed in 2004. | [10 empty] | 2000 | Investment
COM | UNDP | Retroactive funding for the conversion from CFC-11 to water-based technology in the manufacture of flexible molded and integral skin foam at Espumlatex-Promicolda | Individual | LAC | COL | FOA | 32 | INV | 49 | N | O | R | CFC | 12 | 12 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2001-05-01 |  | 82020 | 0 | 82020 | 82020 | 100% | 0 | 0 | 0 | 4921 | 0 | 4921 | 0 | 0 | Completed in 2001. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | COL | FOA | 33 | PRP | 50 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | COL | REF | 36 | PRP | 54 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2004-06-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | COL | FOA | 36 | PRP | 55 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially closed in 2005. | [10 empty] | 2002 | Investment
FIN | UNDP | Country programme update | Individual | LAC | COL | SEV | 36 | CPG | 56 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-10-01 |  | 2004-06-01 | 2005-11-01 | 30000 | 0 | 30000 | 29585 | 98.62% | 415 | 0 | 0 | 3900 | 0 | 3846.05 | 53.95 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | COL | FOA | 38 | INV | 58 | A | O | I | CFC | 123 | 111 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 | 2006-07-01 |  |  | 840170 | 0 | 840170 | 783474 | 93.25% | 56696 | 0 | 19843.6 | 102419 | 0 | 95507.3242 | 6911.3758 | 0 | ISF segment- equipment deilvered and installed. Trials completed. RPF segment - equipment installed and test trials ongoing. Workshops took place in September. Final activities to take place 1st half of 2006. | [10 empty] | 2002 | Investment
COM | UNDP | Renewal of the institutional strengthening (phase 4) | Individual | LAC | COL | SEV | 38 | INS | 59 | N | T | I | CFC | 23 | 23 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 |  | 275600 | 0 | 275600 | 261307 | 94.81% | 14293 | 0 | 7146.5 | 35828 | 0 | 33969.91 | 1858.09 | 0 | Completed in 2005. Main focus on national phase out plan related matters. Regionalization through the NPP has increased coverage of IS public awareness activities. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | National phase-out plan for Annex A (Group I and II) substances: first implementation programme | Multi-Year | LAC | COL | PHA | 41 | INV | 60 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 | 2006-07-01 |  |  | 2146820 | 0 | 2146820 | 242570 | 11.3% | 1904250 | 3289 | 666487.5 | 161011 | 0 | 18192.6935 | 142818.3065 | 246.6742 | Commercial equipment being purchased, 1st phase of technicians certification completed, regional technicians databases being prepared, first batch of R&R equipment being purchased, halon plan defined, regionalization and NPP national coverage achieved. | [10 empty] | 2003 | Investment | 805.9 | 805.9 |  |  | Yes | Yes | yes
ONG | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | COL | SEV | 45 | INS | 61 | N | T | I | CFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 | 2007-04-01 |  |  | 275600 | 0 | 275600 | 45493 | 16.51% | 230107 | 0 | 46021.4 | 20670 | 0 | 3411.975 | 17258.025 | 0 | During 2005 Colombia maintained compliance with the control measures under the Montreal Protocol and the NOU continued successfully implementing the remaining individual and umbrella ODS phase Out projects, improving and updating the ODS related legislation and monitoring national compliance with the Montreal Protocol through data collection and monitoring of consumption. Special efforts have been made in the implementation of the National Phase Out Plan. Some of the activities done in 2005 included the initiation of the purchase process for the first batch of equipment for the servicing sector and the commercial refrigeration companies, the completion of the first phase of the technicians certification programme, and the establishment of the regional centers to increase coverage and improve monitoring. The NOU also participated in the preparation of a project to phase out CTC , approved at the 47th ExCom Meeting. In addition, participation in the Montreal Protocol and the Latin America Ozone Officer’s network meetings continued to be provided, and public awareness activities continued to be implemented, including the celebration of the ozone day, the publication of a periodic newsletter and the production of a mail stamp related to ozone protection, among other activities. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | COL | SEV | 45 | TAS | 62 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 68807 | 0 | 68807 | 0 | 0% | 68807 | 0 | 24082.45 | 6193 | 0 | 0 | 6193 | 0 | Preparatory work to initiate surveys and recruit consultants started. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | National phase-out plan for Annex A (Group I and II) substances: second implementation programme | Multi-Year | LAC | COL | PHA | 47 | INV | 63 | N | O | I | CFC | 801 | 37 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 2353180 | 0 | 2353180 | 0 | 0% | 2353180 | 0 | 823613 | 176488 | 0 | 0 | 176488 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment | 768.9 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | COL | REF | 47 | DEM | 65 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 0 | 200000 | 75000 | 0 | 0 | 75000 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | ODS reconnaissance study | Individual | LAC | COS | SEV | 04 | TAS | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 20000 | 3422 | 23422 | 23422 | 100% | 0 | 0 | 0 | 2600 | 445 | 3045 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COS | SEV | 06 | CPG | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1992-09-01 |  | 1992-09-01 | 1997-12-01 | 20000 | 2909 | 22909 | 22909 | 100% | 0 | 0 | 0 | 2600 | 378 | 2978 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | COS | SEV | 08 | INS | 03 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-08-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 213160 | 0 | 213160 | 213160 | 100% | 0 | 0 | 0 | 27711 | 0 | 27711 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COS | REF | 08 | TAS | 04 | A | O | I | CFC | 37 | 18 | 0 | 0 | 1992-10-01 | 1997-01-01 | 1998-09-01 |  | 2000-06-01 | 2004-03-01 | 88000 | 233693 | 321693 | 321693 | 100% | 0 | 0 | 0 | 11440 | 30380 | 41820 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  |  |  | 1999-08-01 | [6 empty] | 1992 | Investment
FIN | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 08 | TRA | 05 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 100% | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Seminar/workshop in the solvent sector | Individual | LAC | COS | SOL | 08 | TRA | 06 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | -3219 | 17901 | 17901 | 100% | 0 | 0 | 0 | 2746 | -418 | 2328 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Assistance in project preparation | Individual | LAC | COS | SEV | 08 | PRP | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-05-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [10 empty] | 1992 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Atlas Eléctrica S.A. | Individual | LAC | COS | REF | 18 | INV | 08 | A | O | D | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-04-01 |  | 1998-05-01 | 1999-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase II) | Individual | LAC | COS | SEV | 21 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1999-02-01 |  | 1999-02-01 | 2000-12-01 | 108087 | 0 | 108087 | 108087 | 100% | 0 | 0 | 0 | 14051 | 0 | 14051 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | LAC | COS | SEV | 21 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-04-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration subsector | Individual | LAC | COS | REF | 24 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 100% | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 100% | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol (Phase III) | Individual | LAC | COS | SEV | 27 | INS | 16 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-04-01 |  | 2001-12-01 | 2005-11-01 | 108087 | 0 | 108087 | 105568 | 97.67% | 2519 | 0 | 0 | 14051 | 0 | 13723.5372 | 327.4628 | 0 | Completed in 2001. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Omega, S.A. | Individual | LAC | COS | REF | 27 | INV | 17 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 159883 | 0 | 159883 | 159883 | 100% | 0 | 0 | 0 | 20785 | 0 | 20785 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Wimmer Hnos., S.A. | Individual | LAC | COS | REF | 27 | INV | 18 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 186217 | 0 | 186217 | 186217 | 100% | 0 | 0 | 0 | 24208 | 0 | 24208 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Hermanos González, S.A. | Individual | LAC | COS | REF | 27 | INV | 19 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-04-01 | 185168 | 0 | 185168 | 185168 | 100% | 0 | 0 | 0 | 24072 | 0 | 24072 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
CLO | UNDP | Phaseout of CFC-11and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Quena S.A. | Individual | LAC | COS | REF | 27 | INV | 20 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  |  | 2002-11-01 | 219430 | -111322 | 108108 | 108108 | 100% | 0 | 0 | 0 | 28526 | -14472 | 14054 | 0 | 0 | Canceled in 2002. Financially completed in 2002. | [10 empty] | 1999 | Investment
COM | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COS | REF | 32 | TAS | 23 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2005-12-01 |  | 40000 | 0 | 40000 | 31000 | 77.5% | 9000 | 0 | 4500 | 5200 | 0 | 4030 | 1170 | 0 | Completed in 2005. RMP submitted. Payment issues settled. | [7 empty] | 2003-01-01 |  |  | 2000 | Non-Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | COS | FUM | 33 | PRP | 24 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (first tranche) | Multi-Year | LAC | COS | FUM | 35 | INV | 25 | N | O | I | MeBr | 84 | 84 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2002-12-01 |  | 2005-07-01 |  | 1211321 | 0 | 1211321 | 1211321 | 100% | 0 | 0 | 0 | 143245 | 0 | 143245 | 0 | 0 | Completed in 2005. Phase I of project operationally complete. Progress Report for MY-Plan submitted to ExCom 43 outlines in detail activities undertaken during implementation. | [8 empty] | 2004-07-01 |  | 2001 | Investment | 426.9 | 426.9 |  |  | Yes | Yes | yes
COM | UNDP | Renewal of the institutional strengthening project | Individual | LAC | COS | SEV | 35 | INS | 26 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2004-12-01 |  | 108087 | 0 | 108087 | 104193 | 96.4% | 3894 | 0 | 1947 | 14051 | 0 | 13544.7912 | 506.2088 | 0 | Completed in 2004. | [10 empty] | 2001 | Non-Investment
ONG | UNDP | Implementation of the RMP: incentive programme for the commercial, industrial, and fishing fleet refrigeration end-user sub-sector | RMP-Update-Comp | LAC | COS | REF | 41 | TAS | 27 | N | O | I | CFC | 36 | 9 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 | 2006-12-01 |  |  | 200000 | 0 | 200000 | 41016 | 20.51% | 158984 | 0 | 55644.4 | 18000 | 0 | 3691.44 | 14308.56 | 0 | RMP ongoing satisfactorily. Pilot phase with conversion of 3 ships completed. Incentive scheme developed. 17 additional ships signed up for next round of conversions. Technical assistance to 3 supermarket chains and Dos Pinos (diary cooperative). | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sub-sector | RMP-Update-Comp | LAC | COS | REF | 41 | TAS | 28 | N | O | I | CFC | 46 | 15 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 | 2006-12-01 |  |  | 180000 | 0 | 180000 | 59786 | 33.21% | 120214 | 0 | 42074.9 | 16200 | 0 | 5380.74 | 10819.26 | 0 | RMP ongoing satisfactorily. 16 R&R machines purchased and delivered to MAC workshops (MAC II). Re-activation of MAC I project. Technical assistance given to MAC workshops. Needs assessment exercise carried out in Domestic, commercial and MAC sectors. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: technical assistance for certification and licensing of refrigeration technicians | RMP-Update-Comp | LAC | COS | REF | 41 | TRA | 29 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 | 2007-12-01 |  |  | 100000 | 0 | 100000 | 10439 | 10.44% | 89561 | 0 | 17912.2 | 9000 | 0 | 939.51 | 8060.49 | 0 | RMP ongoing satisfactorily. Assisted in the creation of five associations of refrigeration technicians. MOU established with National Learning Institute (INA) about training and certification of Refrigeration technicians on a national level in 2006. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: technical assistance for training of customs officers | RMP-Update-Comp | LAC | COS | REF | 41 | TRA | 30 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2005-12-01 | 2006-12-01 |  |  | 90000 | 0 | 90000 | 7139 | 7.932% | 82861 | 0 | 29001.35 | 8100 | 0 | 642.51 | 7457.49 | 0 | RMP ongoing satisfactorily. Close coordination with custom officials to get to know the system. Programme for training of custom officials elaborated, and will be executed in 2006. Needs assessment of identification equipment carried out. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: ensuring the effectiveness of all the project proposed with the RMP project | RMP-Update-Comp | LAC | COS | REF | 41 | TAS | 31 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 | 2007-12-01 |  |  | 60000 | 0 | 60000 | 15436 | 25.73% | 44564 | 0 | 8912.8 | 5400 | 0 | 1389.24 | 4010.76 | 0 | RMP ongoing satisfactorily. Monitoring Unit established. Project progress is satisfactorily. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Extension of institutional strengthening project | Individual | LAC | COS | SEV | 41 | INS | 32 | N | T | I | No-ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 | 2006-12-01 |  |  | 140513 | 0 | 140513 | 83640 | 59.52% | 56873 | 0 | 19905.55 | 10538 | 0 | 6272.7173 | 4265.2827 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranches II and III) | Multi-Year | LAC | COS | FUM | 43 | INV | 33 | N | O | I | MeBr | 131 | 69 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-12-01 | 2006-12-01 |  |  | 1938114 | 0 | 1938114 | 351371 | 18.13% | 1586743 | 0 | 555360.05 | 145359 | 0 | 26352.9066 | 119006.0934 | 0 | Project on track and phaseout targets being achieved. Ntl PM resigned in mid-05. New PM selected August 05 and endorsed by all stakeholders. Request for change in Agreed Conditions expected in early 06. | [10 empty] | 2004 | Investment | 253.5 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COS | SEV | 47 | INS | 34 | N | T | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 140513 | 0 | 140513 | 0 | 0% | 140513 | 0 | 28102.6 | 10538 | 0 | 0 | 10538 | 0 | During 2005, the NOU in Costa Rica focused its work on the implementation of the RMP and the accelerated phase out of Methyl Bromide project, including the hiring of a new project coordinator for the MB-project. The ODS licensing system was working well, and quotas for 2006 and 2007 were negotiated with ODS importers. Several awareness-raising activities were carried out, including the celebration of the International Ozone Day. A new training programme with customs officials has been set up, and will be carried out in 2006. Costa Rica is in compliance with its consumption, reporting and other obligations to the Montreal Protocol. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Technical assistance for Guandong aerosols investment project and investigation of non-ODS filling technology and LPG purification | Individual | ASP | CPR | ARS | 06 | TAS | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1996-12-01 | 1998-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Feasibility study on the application of HFC-134a technology in MACs and CFC recycling | RMP-Component | ASP | CPR | REF | 06 | TAS | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-09-01 |  | 1993-12-01 | 1997-12-01 | 40000 | -15164 | 24836 | 24836 | 100% | 0 | 0 | 0 | 5200 | -1971 | 3229 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Establishment of a training programme for centrifugal chillers and domestic refrigeration service managers and technicians | RMP-Component | ASP | CPR | REF | 06 | TRA | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Establishment of a quality control testing plant for using CFC-12 substitute technology in refrigeration and rigid foams | Individual | ASP | CPR | REF | 06 | TAS | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-12-01 | 1993-12-01 |  | 1998-06-01 | 1998-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1998. Financially completed in 1998. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 06 | TAS | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 100% | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Pre-feasibility study to phase-out CFC-113 in electronic cleaning in four production lines | Individual | ASP | CPR | SOL | 06 | TAS | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-10-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 40000 | 1829 | 41829 | 41829 | 100% | 0 | 0 | 0 | 5200 | 238 | 5438 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical study on halons usage and applications of halons substitutes | Individual | ASP | CPR | HAL | 06 | TAS | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 40000 | 3345 | 43345 | 43345 | 100% | 0 | 0 | 0 | 5200 | 435 | 5635 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening, including establishment of the Information Clearing-house at NEPA | Individual | ASP | CPR | SEV | 06 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-04-01 | 1995-02-01 |  | 1996-12-01 | 1998-12-01 | 150000 | 299997 | 449997 | 449997 | 100% | 0 | 0 | 0 | 19500 | 39000 | 58500 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | CPR | SEV | 06 | CPG | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in rigid polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Dalian precision parts cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 19 | N | O | I | CFC | 69 | 69 | 0 | 0 | 1992-06-01 | 1996-04-01 | 1994-06-01 |  | 1996-09-01 | 1998-12-01 | 495000 | -34191 | 460809 | 460809 | 100% | 0 | 0 | 0 | 64350 | -4445 | 59905 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1992 | Investment
FIN | UNDP | Dandong electronic tuner aqueous cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 20 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1992-06-01 | 1995-07-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 495000 | -663 | 494337 | 494337 | 100% | 0 | 0 | 0 | 64350 | -86 | 64264 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1992 | Investment
FIN | UNDP | Technical assistance for the Beijing Household Electric Appliances Research Institute (Bheari) | Individual | ASP | CPR | FOA | 09 | TAS | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-10-01 | 1995-06-01 |  | 1998-10-01 | 2003-07-01 | 0 | 444945 | 444945 | 444945 | 100% | 0 | 0 | 0 | 0 | 57843 | 57843 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Survey and assessment of small CFC plant conversion possibilities | Individual | ASP | CPR | SEV | 09 | TAS | 26 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-05-01 | 1994-03-01 |  | 1998-10-01 | 2001-12-01 | 90000 | -701 | 89299 | 89299 | 100% | 0 | 0 | 0 | 11700 | -91 | 11609 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Import and promotion of applications for CFC substitute chemicals in the refrigeration sector in Southern China | RMP-Component | ASP | CPR | REF | 09 | TAS | 27 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1994-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | CPR | SEV | 09 | PRP | 30 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Tianjin conversion to CFC-free technology in the manufacture of flexible polyurethane foam | Individual | ASP | CPR | FOA | 10 | INV | 32 | N | O | I | CFC | 180 | 180 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1994-09-01 |  | 1995-04-01 | 1998-12-01 | 1080000 | -41407 | 1038593 | 1038593 | 100% | 0 | 0 | 0 | 140400 | -5383 | 135017 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at Nanjing Wire Works | Individual | ASP | CPR | SOL | 10 | INV | 36 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1993-06-01 | 1996-08-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 409000 | -511 | 408489 | 408489 | 100% | 0 | 0 | 0 | 53170 | -66 | 53104 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at the Chengdu Qianfeng Radio Instrument Factory | Individual | ASP | CPR | SOL | 10 | INV | 37 | N | O | I | CFC | 7 | 7 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1995-12-01 |  | 1997-12-01 | 1999-12-01 | 394700 | -13224 | 381476 | 381476 | 100% | 0 | 0 | 0 | 51311 | -1719 | 49592 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1993 | Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | CPR | FOA | 10 | TAS | 38 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-05-01 | 1994-06-01 |  | 1997-07-01 | 2000-06-01 | 200000 | -574 | 199426 | 199426 | 100% | 0 | 0 | 0 | 26000 | -75 | 25925 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Revision of design standards for cold storage | RMP-Component | ASP | CPR | REF | 10 | TAS | 39 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-01-01 | 1994-09-01 |  | 1999-03-01 | 2000-12-01 | 200000 | -18764 | 181236 | 181236 | 100% | 0 | 0 | 0 | 26000 | -2439 | 23561 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-03-01 | [6 empty] | 1993 | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: current situation, revision of national codes, and education and training | Individual | ASP | CPR | HAL | 10 | TAS | 40 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1996-06-01 |  | 1998-09-01 | 2000-12-01 | 280000 | -24125 | 255875 | 255875 | 100% | 0 | 0 | 0 | 36400 | -3136 | 33264 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: transfer of technology on alternatives to halon fire protection systems | Individual | ASP | CPR | HAL | 10 | TAS | 41 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-11-01 | 1996-06-01 |  | 1999-06-01 | 2000-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-06-01 | [6 empty] | 1993 | Non-Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of rigid PUF (spray) at Beijing Commercial Machinery Factory (BCMF) | Individual | ASP | CPR | FOA | 11 | INV | 54 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1998-12-01 | 2000-12-01 | 435000 | -91690 | 343310 | 343310 | 100% | 0 | 0 | 0 | 56550 | -11920 | 44630 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1993 | Investment
FIN | UNDP | Survey on policy and planning measures to promote recycling of CFC | RMP-Component | ASP | CPR | REF | 11 | TAS | 55 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-05-01 | 1994-11-01 |  | 1997-12-01 | 2000-12-01 | 100000 | -19358 | 80642 | 80642 | 100% | 0 | 0 | 0 | 13000 | -2517 | 10483 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1993 | Investment
FIN | UNDP | National product qualification and standards evaluation for non-ODS alternatives to CFC applications | Individual | ASP | CPR | SEV | 11 | TAS | 56 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-11-01 |  | 1998-03-01 | 2000-12-01 | 362500 | -29055 | 333445 | 333445 | 100% | 0 | 0 | 0 | 47125 | -3777 | 43348 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 11 | PRP | 58 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Survey of production and consumption of methyl bromide in China | Individual | ASP | CPR | FUM | 12 | TAS | 60 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-03-01 |  | 1998-10-01 | 2001-12-01 | 87000 | -1791 | 85209 | 85209 | 100% | 0 | 0 | 0 | 11310 | -232 | 11078 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Cleaning applications deployment center for replication of ODS-free process across China | Individual | ASP | CPR | SOL | 12 | TAS | 61 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-03-01 | 1995-03-01 |  | 1998-05-01 | 2000-12-01 | 489400 | -66345 | 423055 | 423055 | 100% | 0 | 0 | 0 | 63622 | -8625 | 54997 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | ODS-free cleaning equipment manufacturing center for phasing out ODS consuming solvents across China | Individual | ASP | CPR | SOL | 12 | INV | 65 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1997-06-01 | 1996-03-01 |  | 1999-11-01 | 2002-07-01 | 524734 | -50707 | 474027 | 474027 | 100% | 0 | 0 | 0 | 68215 | -6592 | 61623 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Acquisition of local air compressors for halon recycling machines | Individual | ASP | CPR | HAL | 12 | INV | 66 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-12-01 | 1998-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
CLO | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Yanfeng | Individual | ASP | CPR | FOA | 13 | INV | 67 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1995-07-01 |  |  | 1995-07-01 | 670000 | -670000 | 0 | 0 |  | 0 | 0 | 0 | 87100 | -87100 | 0 | 0 | 0 | Canceled in 1995. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 used in the manufacture of EPE foam sheet at Danshui Huaya Plastics Industries Co. Ltd. | Individual | ASP | CPR | FOA | 13 | INV | 73 | A | O | R | CFC | 160 | 160 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1995-04-01 | 1997-12-01 | 241000 | 0 | 241000 | 241000 | 100% | 0 | 0 | 0 | 31330 | 0 | 31330 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 used in the manufacture of rigid polyurethane foam at Tianjin Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 13 | INV | 74 | N | O | I | CFC | 130 | 130 | 0 | 0 | 1994-07-01 | 1998-11-01 | 1995-07-01 |  | 2001-08-01 | 2003-07-01 | 690000 | -431333 | 258667 | 258667 | 100% | 0 | 0 | 0 | 89700 | -56073 | 33627 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shijiazhuang Plastic Cement General Factory | Individual | ASP | CPR | FOA | 15 | INV | 87 | A | O | I | CFC | 160 | 160 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 621000 | 0 | 621000 | 621000 | 100% | 0 | 0 | 0 | 80730 | 0 | 80730 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE foam tubing at Suzhou Plastic Works No. 7 | Individual | ASP | CPR | FOA | 15 | INV | 88 | A | O | I | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 358000 | -36690 | 321310 | 321310 | 100% | 0 | 0 | 0 | 46540 | -4770 | 41770 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Sino-Foreign Joint Stock Shenyang Shenrong Co. | Individual | ASP | CPR | FOA | 15 | INV | 89 | A | O | I | CFC | 48 | 48 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-05-01 | 2002-04-01 | 166700 | -1 | 166699 | 166699 | 100% | 0 | 0 | 0 | 21671 | 0 | 21671 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-06-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE foam sheet and netting at Feicheng Plastic Products Factory | Individual | ASP | CPR | FOA | 15 | INV | 90 | A | O | I | CFC | 150 | 150 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-04-01 | 2002-04-01 | 388000 | 0 | 388000 | 388000 | 100% | 0 | 0 | 0 | 50440 | 0 | 50440 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-04-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guangxing Plastics Products Co., Hubei | Individual | ASP | CPR | FOA | 15 | INV | 91 | A | O | I | CFC | 36 | 36 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shenzhen Shentie Plastics Tableware Products Company, Shenzhen | Individual | ASP | CPR | FOA | 15 | INV | 92 | A | O | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 345000 | 0 | 345000 | 345000 | 100% | 0 | 0 | 0 | 44850 | 0 | 44850 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE netting at Hebei Sixing Polypack Products Co. Ltd., Shijiazhuang | Individual | ASP | CPR | FOA | 15 | INV | 93 | A | O | I | CFC | 65 | 65 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 436000 | -183121 | 252879 | 252879 | 100% | 0 | 0 | 0 | 56680 | -23806 | 32874 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Beijing Yanxi | Individual | ASP | CPR | FOA | 15 | INV | 94 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 125000 | -31250 | 93750 | 93750 | 100% | 0 | 0 | 0 | 16250 | -4063 | 12187 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Faw-Trim | Individual | ASP | CPR | FOA | 15 | INV | 95 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of integral skin polyurethane foam at Hubei Auto Engineering | Individual | ASP | CPR | FOA | 15 | INV | 96 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Dalian No. 1 | Individual | ASP | CPR | FOA | 15 | INV | 97 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1998-12-01 |  |  | 2000-07-01 | 490000 | -457910 | 32090 | 32090 | 100% | 0 | 0 | 0 | 63700 | -59528 | 4172 | 0 | 0 | Canceled in 1999. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinfeng | Individual | ASP | CPR | FOA | 15 | INV | 98 | A | O | R | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 235340 | 0 | 235340 | 235340 | 100% | 0 | 0 | 0 | 30594 | 0 | 30594 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinan | Individual | ASP | CPR | FOA | 15 | INV | 99 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 337000 | 0 | 337000 | 337000 | 100% | 0 | 0 | 0 | 43810 | 0 | 43810 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guizhou Jinchang Plastics Products Co. Ltd. | Individual | ASP | CPR | FOA | 15 | INV | 100 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 390000 | -117155 | 272845 | 272845 | 100% | 0 | 0 | 0 | 50700 | -15230 | 35470 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Hailun Plastic Packaging Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 101 | A | O | I | CFC | 95 | 95 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 321000 | -2 | 320998 | 320998 | 100% | 0 | 0 | 0 | 41730 | 0 | 41730 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE/PS foam sheet at Shanghai Jianhua Electro-Mechanical and Mechanical Company | Individual | ASP | CPR | FOA | 15 | INV | 102 | A | O | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-11-01 | 2002-04-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-04-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Foshan No. 3 Plastic Factory | Individual | ASP | CPR | FOA | 15 | INV | 103 | A | O | I | CFC | 360 | 360 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 1065000 | -1 | 1064999 | 1064999 | 100% | 0 | 0 | 0 | 138450 | 0 | 138450 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 15 | PRP | 106 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Guangdong Kelon Electrical Holding Company Ltd. | Individual | ASP | CPR | REF | 17 | INV | 123 | N | O | I | CFC | 767 | 767 | 0 | 0 | 1995-07-01 | 1997-04-01 | 1997-01-01 |  | 1999-06-01 | 2003-07-01 | 4483050 | -6913 | 4476137 | 4476137 | 100% | 0 | 0 | 0 | 582797 | -899 | 581898 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-06-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Changsha Zhongyi Group Corp. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 124 | A | O | I | CFC | 360 | 360 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 2000-09-01 | 2004-01-01 | 2961000 | -2311 | 2958689 | 2958689 | 100% | 0 | 0 | 0 | 384930 | -300 | 384630 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Cangzhou Foreign Trade Packaging Co. | Individual | ASP | CPR | FOA | 17 | INV | 125 | N | O | I | CFC | 75 | 75 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 450800 | -445 | 450355 | 450355 | 100% | 0 | 0 | 0 | 58604 | -58 | 58546 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Handan No. 7 | Individual | ASP | CPR | FOA | 17 | INV | 126 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 400950 | -446 | 400504 | 400504 | 100% | 0 | 0 | 0 | 52124 | -58 | 52066 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Joint Industrial Plastic Corporation, Buotou | Individual | ASP | CPR | FOA | 17 | INV | 127 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2001-05-01 | 604450 | -446 | 604004 | 604004 | 100% | 0 | 0 | 0 | 78579 | -58 | 78521 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 17 | PRP | 128 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-04-01 |  | 1996-03-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Demonstration project (refrigeration - large food stores) | RMP-Component | ASP | CPR | REF | 17 | DEM | 131 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1997-06-01 | 2002-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1995 | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane products at Daimei | Individual | ASP | CPR | FOA | 17 | INV | 134 | N | O | I | CFC | 77 | 77 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-12-01 |  | 1998-12-01 | 2001-12-01 | 362600 | -43425 | 319175 | 319175 | 100% | 0 | 0 | 0 | 47138 | -5645 | 41493 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Tianjin Daqui Foam Plant | Individual | ASP | CPR | FOA | 18 | INV | 141 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 160000 | -60 | 159940 | 159940 | 100% | 0 | 0 | 0 | 20800 | -8 | 20792 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin and cold cured PUF moldings at Jiangxi Auto Engineering Plastic Plant | Individual | ASP | CPR | FOA | 18 | INV | 142 | N | O | I | CFC | 39 | 39 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 2001-03-01 | 2003-07-01 | 170000 | -6784 | 163216 | 163216 | 100% | 0 | 0 | 0 | 22100 | -882 | 21218 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Tianjin Gangda | Individual | ASP | CPR | FOA | 18 | INV | 143 | N | O | I | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1997-05-01 |  | 2000-10-01 | 2003-07-01 | 404250 | -1033 | 403217 | 403217 | 100% | 0 | 0 | 0 | 52553 | -134 | 52419 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Hunan Computer Factory | Individual | ASP | CPR | SOL | 18 | INV | 152 | A | O | R | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 1997-12-01 | 2000-12-01 | 104700 | -18343 | 86357 | 86357 | 100% | 0 | 0 | 0 | 13611 | -2385 | 11226 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 18 | PRP | 153 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Jiangsu Jintan Insulation Material Plant | Individual | ASP | CPR | FOA | 19 | INV | 161 | N | O | I | CFC | 12 | 12 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 66000 | -5638 | 60362 | 60362 | 100% | 0 | 0 | 0 | 8580 | -733 | 7847 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Guingdao Haier General Freezer Company | Individual | ASP | CPR | REF | 19 | INV | 167 | N | O | I | CFC | 279 | 279 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2000-04-01 | 2003-07-01 | 2548280 | -22910 | 2525370 | 2525370 | 100% | 0 | 0 | 0 | 331276 | -2978 | 328298 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  | 1998-05-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Henan Freezer Factory | Individual | ASP | CPR | REF | 19 | INV | 168 | N | O | I | CFC | 168 | 168 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2001-06-01 | 2003-09-01 | 2550605 | -54725 | 2495880 | 2495880 | 100% | 0 | 0 | 0 | 331579 | -7114 | 324465 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Sixth Radio Factory | Individual | ASP | CPR | SOL | 19 | INV | 169 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1996-05-01 | 1999-09-01 | 1998-04-01 |  | 2001-08-01 | 2003-09-01 | 138400 | -14098 | 124302 | 124302 | 100% | 0 | 0 | 0 | 17992 | -1833 | 16159 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-05-01 | [7 empty] | 1996 | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the electron gun final cleaning processes at the Tianjin Picture Tube Factory | Individual | ASP | CPR | SOL | 19 | INV | 170 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1998-04-01 |  |  | 1999-03-01 | 132600 | -132600 | 0 | 0 |  | 0 | 0 | 0 | 17238 | -17238 | 0 | 0 | 0 | Canceled in 1999. | [10 empty] | 1996 | Investment
COM | UNDP | Elimination of the use of CFC-113 and methyl chloroform in the color picture tube cleaning processes at the Shanghai Novel CPT. Corp. Factory | Individual | ASP | CPR | SOL | 19 | INV | 171 | N | O | I | CFC | 75 | 75 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1998-04-01 |  | 2002-11-01 |  | 849950 | -150442 | 699508 | 699508 | 100% | 0 | 0 | 0 | 110494 | -19558 | 90936 | 0 | 0 | Completed in 2002. |  |  | 1998-05-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Elimination of the use of TCA in the Baoshi Electronics Corporation Shijazhuang Manufacturing Operations | Individual | ASP | CPR | SOL | 19 | INV | 172 | N | O | I | TCA | 7 | 7 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1998-04-01 |  | 2000-07-01 | 2003-03-01 | 284900 | -7138 | 277762 | 277762 | 100% | 0 | 0 | 0 | 37037 | -928 | 36109 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  | 1998-05-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai Automation Instrumentation Factory | Individual | ASP | CPR | SOL | 20 | INV | 178 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1996-10-01 | 1999-08-01 | 1998-09-01 |  | 2001-03-01 | 2003-03-01 | 325000 | -5336 | 319664 | 319664 | 100% | 0 | 0 | 0 | 42250 | -694 | 41556 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol - Phase II | Individual | ASP | CPR | SEV | 20 | INS | 181 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 300000 | -1 | 299999 | 299999 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1996 | Non-Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai No 8 Radio Factory | Individual | ASP | CPR | SOL | 20 | INV | 186 | N | O | I | CFC | 19 | 19 | 0 | 0 | 1996-10-01 | 2000-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-09-01 | 378000 | -81073 | 296927 | 296927 | 100% | 0 | 0 | 0 | 49140 | -10539 | 38601 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Update of the country programme and policy workshop | Individual | ASP | CPR | SEV | 21 | CPG | 188 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-03-01 |  | 1998-12-01 | 2002-06-01 | 225000 | -17054 | 207946 | 207946 | 100% | 0 | 0 | 0 | 29250 | -2217 | 27033 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 21 | PRP | 191 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1997 | Investment
FIN | UNDP | Preparation of a sectoral financing plan for the solvents sector | Individual | ASP | CPR | SOL | 21 | TAS | 192 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2003-07-01 | 200000 | -19236 | 180764 | 180764 | 100% | 0 | 0 | 0 | 26000 | -2501 | 23499 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Railway Communication Equipment Factory | Individual | ASP | CPR | SOL | 22 | INV | 195 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1997-05-01 | 1999-09-01 | 1999-06-01 |  | 2001-03-01 | 2003-03-01 | 276287 | -1 | 276286 | 276286 | 100% | 0 | 0 | 0 | 35917 | 0 | 35917 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 22 | PRP | 197 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhejiang Wanpeng Clique Co., Ltd. | Individual | ASP | CPR | FOA | 22 | INV | 202 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 412666 | -10472 | 402194 | 402194 | 100% | 0 | 0 | 0 | 53647 | -1362 | 52285 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhoushan Fuchuan Plastic Products Factory | Individual | ASP | CPR | FOA | 22 | INV | 206 | N | O | I | CFC | 61 | 61 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 403711 | -9045 | 394666 | 394666 | 100% | 0 | 0 | 0 | 52482 | -1175 | 51307 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Computer Factory | Individual | ASP | CPR | SOL | 22 | INV | 216 | N | O | I | CFC | 6 | 6 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-11-01 | 2003-08-01 | 116767 | -1 | 116766 | 116766 | 100% | 0 | 0 | 0 | 15180 | 0 | 15180 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Investment
COM | UNDP | Elimination of ODS (CFC-113) used in the production line at Fujian Putian Vikay Electronics Co. Ltd. | Individual | ASP | CPR | SOL | 23 | INV | 224 | N | O | I | CFC | 56 | 56 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2002-11-01 |  | 619780 | 0 | 619780 | 617424 | 99.62% | 2356 | 0 | 1178 | 80571 | 0 | 80264.7215 | 306.2785 | 0 | Completed in 2002. | [10 empty] | 1997 | Investment
CLO | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Jilin Jinouer Electric Appliances Group Co. | Individual | ASP | CPR | REF | 23 | INV | 225 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-12-01 |  |  | 2003-09-01 | 2548360 | -1223403 | 1324957 | 1324957 | 100% | 0 | 0 | 0 | 331287 | -159042 | 172245 | 0 | 0 | Canceled in 2002. Financially completed in 2003. |  |  |  |  | 2000-12-01 | [5 empty] | 1997 | Investment
COM | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Wanbao Electrical Appliance Industries Co. | Individual | ASP | CPR | REF | 23 | INV | 226 | N | O | I | CFC | 574 | 574 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2003-12-01 |  | 4566985 | 0 | 4566985 | 4566985 | 100% | 0 | 0 | 0 | 593708 | 0 | 593708 | 0 | 0 | Completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels, pipes and spray foams at Baoding Oil Depot & Storage Engineering Company | Individual | ASP | CPR | FOA | 23 | INV | 228 | N | O | I | CFC | 76 | 76 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-09-01 | 400960 | -34986 | 365974 | 365974 | 100% | 0 | 0 | 0 | 52125 | -4549 | 47576 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid and spray polyurethane foams at Xinjiang Tianye Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 229 | N | O | I | CFC | 92 | 92 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 2001-01-01 | 2004-01-01 | 300620 | -15937 | 284683 | 284683 | 100% | 0 | 0 | 0 | 39081 | -2072 | 37009 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Honxiang Group, Laizhou Freezer Plant | Individual | ASP | CPR | REF | 23 | INV | 232 | N | O | I | CFC | 302 | 302 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2003-09-01 | 2005-03-01 | 1339203 | -6776 | 1332427 | 1332427 | 100% | 0 | 0 | 0 | 174096 | -881 | 173215 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1997 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic freezers at DeBao Refrigeration Equipment Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 233 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-06-01 | 1208176 | -683628 | 524548 | 524548 | 100% | 0 | 0 | 0 | 157063 | -88872 | 68191 | 0 | 0 | Canceled in 2002. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels at Luoyang Refrigeration Machinery Factory | Individual | ASP | CPR | FOA | 23 | INV | 236 | N | O | I | CFC | 118 | 118 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-01-01 | 2003-07-01 | 698595 | -41580 | 657015 | 657015 | 100% | 0 | 0 | 0 | 90817 | -5405 | 85412 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 2 projects in the domestic refrigeration (hydrocarbon) subsector | Individual | ASP | CPR | REF | 24 | PRP | 239 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 10 projects in the rigid and integral skin foam sub-sectors | Individual | ASP | CPR | FOA | 24 | PRP | 241 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to cylopentane and R-134a in the manufacture of domestic freezers at Wanbao Freezer Industrial Corporation | Individual | ASP | CPR | REF | 24 | INV | 242 | N | O | I | CFC | 138 | 138 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-08-01 | 2004-06-01 | 1402370 | -52248 | 1350122 | 1350122 | 100% | 0 | 0 | 0 | 182308 | -6792 | 175516 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1998 | Investment
COM | UNDP | Conversion to cyclopentane in the manufacture of heating pipes at Jixi City Thermal Power Company | Individual | ASP | CPR | FOA | 24 | INV | 245 | N | O | I | CFC | 86 | 86 | 0 | 0 | 1998-03-01 | 2000-12-01 | 2000-04-01 |  | 2003-12-01 |  | 673380 | 0 | 673380 | 673380 | 100% | 0 | 0 | 0 | 87539 | 0 | 87539 | 0 | 0 | Completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to LCD technology int he manufacture of flexible (slabstock) polyurethane foam at Jinling Petrochemical Co. Plastics Factory | Individual | ASP | CPR | FOA | 25 | INV | 247 | N | O | I | CFC | 81 | 81 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2000-08-01 |  | 2003-05-01 | 2005-02-01 | 504630 | -4472 | 500158 | 500158 | 100% | 0 | 0 | 0 | 65602 | -581 | 65021 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1998 | Investment
COM | UNDP | Conversion to cyclopentane and isobutane in the manufacture of domestic refrigerators at Hangzhou Household Electrical Appliance Industrial Corporation (HHEAIC) | Individual | ASP | CPR | REF | 25 | INV | 249 | N | O | I | CFC | 248 | 248 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2004-11-01 |  | 2238580 | 0 | 2238580 | 2237518 | 99.95% | 1062 | 0 | 531 | 291015 | 0 | 290876.9402 | 138.0598 | 0 | Completed in 2004. | [5 empty] | 2001-12-01 |  |  |  |  | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride and forced cooling system in the manufacture of flexible polyurethane foam (slabstock) at Cangzhou New-Type Foam Decoration Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 250 | N | O | I | CFC | 67 | 67 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2001-05-01 | 2003-09-01 | 417410 | -17009 | 400401 | 400401 | 100% | 0 | 0 | 0 | 54263 | -2211 | 52052 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
COM | UNDP | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Victory Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 25 | INV | 254 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1998-07-01 | 2001-11-01 | 2000-08-01 |  | 2003-11-01 |  | 563760 | 0 | 563760 | 563487 | 99.95% | 273 | 0 | 136.5 | 73289 | 0 | 73253.5099 | 35.4901 | 0 | Completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to cyclopentane in the manufacture of PU-insulated heating pipes at Tianjin Pipeline Engineering Group Co. Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 257 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-09-01 | 2005-03-01 | 626400 | -346 | 626054 | 626054 | 100% | 0 | 0 | 0 | 78904 | -44 | 78860 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Guangdong Commercial Refrigeration Equipment Co. (GCREC) | Individual | ASP | CPR | FOA | 26 | INV | 258 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-10-01 | 2003-07-01 | 472150 | -18041 | 454109 | 454109 | 100% | 0 | 0 | 0 | 61380 | -2345 | 59035 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Kaifeng Air Separation Group Ltd. (KFAS) | Individual | ASP | CPR | FOA | 26 | INV | 260 | N | O | I | CFC | 68 | 68 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-04-01 | 2001-11-01 | 534090 | -14357 | 519733 | 519733 | 100% | 0 | 0 | 0 | 68750 | -1579 | 67171 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol (Phase III) | Individual | ASP | CPR | SEV | 26 | INS | 262 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and pour-in-place polyurethane foams at Corrosionproof and Insulation Co., Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 263 | N | O | I | CFC | 99 | 99 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-04-01 | 2004-01-01 | 776110 | -13913 | 762197 | 762197 | 100% | 0 | 0 | 0 | 95372 | -1530 | 93842 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of refrigerator manufacture in Zhenjiang Radio Factory from CFC-11 to N-pentane foam blowing agent in the production of PU insulation panels | Individual | ASP | CPR | FOA | 26 | INV | 264 | N | O | I | CFC | 121 | 121 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-09-01 | 2005-02-01 | 617860 | -4968 | 612892 | 612892 | 100% | 0 | 0 | 0 | 77965 | -627 | 77338 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1998 | Investment
COM | UNDP | Conversion to HCFC-141b in the manufacture of rigid and spray polyurethane foams at Daqing Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 26 | INV | 265 | N | O | I | CFC | 168 | 168 | 0 | 0 | 1998-11-01 | 2001-11-01 | 2001-06-01 |  | 2003-11-01 |  | 1124560 | 0 | 1124560 | 1123942 | 99.95% | 618 | 0 | 309 | 133702 | 0 | 133628.5243 | 73.4757 | 0 | Completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of flexible slabstock polyurethane foam at Ningbo Yongling Rubber and Plastic Co. | Individual | ASP | CPR | FOA | 26 | INV | 266 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 448560 | -20224 | 428336 | 428336 | 100% | 0 | 0 | 0 | 58313 | -2629 | 55684 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of 16 projects in general foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 272 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of ten projects in the integral skin foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 278 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2005-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 2000. Financially closed in 2005. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Nanjing Kanglian Industrial Corporation | Individual | ASP | CPR | FOA | 27 | INV | 279 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1999-03-01 | 2000-04-01 | 2001-10-01 |  | 2001-04-01 | 2002-06-01 | 234900 | -14525 | 220375 | 220375 | 100% | 0 | 0 | 0 | 30537 | -1888 | 28649 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Hengfeng Polyurethane Spray Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 286 | N | O | I | CFC | 154 | 154 | 0 | 0 | 1999-07-01 | 2001-06-01 | 2002-02-01 |  | 2003-09-01 | 2005-02-01 | 1206600 | 0 | 1206600 | 1105564 | 91.63% | 101036 | 0 | 0 | 142726 | 0 | 130774.6788 | 11951.3212 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Elimination of ODS used in the production lines at Irico (Caihong) Color Picture Tube Factory | Individual | ASP | CPR | SOL | 28 | INV | 287 | N | O | I | TCA/CFC | 202 | 202 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2003-08-01 |  | 2002-10-01 | 2004-06-01 | 2853200 | -38805 | 2814395 | 2814395 | 100% | 0 | 0 | 0 | 323852 | -4405 | 319447 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Jiangsu Chemical Research Institute | Individual | ASP | CPR | FOA | 28 | INV | 289 | N | O | I | CFC | 32 | 32 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2001-12-01 | 2004-06-01 | 253690 | -9289 | 244401 | 244401 | 100% | 0 | 0 | 0 | 32980 | -1208 | 31772 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiaxing Anti-Corrosion Factory | Individual | ASP | CPR | FOA | 28 | INV | 290 | N | O | I | CFC | 19 | 19 | 0 | 0 | 1999-07-01 | 2000-10-01 | 2002-02-01 |  | 2002-05-01 | 2004-06-01 | 151590 | -6492 | 145098 | 145098 | 100% | 0 | 0 | 0 | 19707 | -844 | 18863 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
CLO | UNDP | Phase-out of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane insulation foam at Suzhou Purification Equipment Factory | Individual | ASP | CPR | FOA | 28 | INV | 291 | N | O | I | CFC | 66 | 66 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  |  | 2005-12-01 | 516780 | -259990 | 256790.16 | 256790 | 100% | 0.16 | 0 | 0 | 66846 | -33463 | 33382.9792 | 0.0208 | 0 | Canceled in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Penglai Polyurethane Industry Co. | Individual | ASP | CPR | FOA | 28 | INV | 297 | N | O | I | CFC | 64 | 64 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2001-04-01 | 2003-07-01 | 497200 | -50527 | 446673 | 446673 | 100% | 0 | 0 | 0 | 64636 | -6569 | 58067 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Phaseout of CFC-11 by conversion to water blown and HCFC-141b in the manufacture of ISF at 4 SMEs (Ningbo Yongling Rubber & Plastic, Sichuan Mianyang Jinpan Automobile Parts, Zhenjiang Xingda Auto Par | Individual | ASP | CPR | FOA | 29 | INV | 304 | N | O | I | CFC | 18 | 18 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 |  | 245710 | 0 | 245710 | 226714 | 92.27% | 18996 | 0 | 9498 | 31942 | 0 | 29472.5432 | 2469.4568 | 0 | Completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Hangzhou Fanlong Steering Wheel, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 305 | N | O | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 176520 | -4703 | 171817 | 171817 | 100% | 0 | 0 | 0 | 22948 | -612 | 22336 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hanfeng Polyurethane Company | Individual | ASP | CPR | FOA | 29 | INV | 312 | N | O | I | CFC | 56 | 56 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 440830 | 0 | 440830 | 431885 | 97.97% | 8945 | 0 | 0 | 57308 | 0 | 56145.148 | 1162.852 | 0 | Completed in 2003. Financially completed in 2005. | [6 empty] | 2002-12-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Henan Bingxiong Refrigeration Truck Plant | Individual | ASP | CPR | FOA | 29 | INV | 313 | N | O | I | CFC | 56 | 56 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2004-06-01 | 440780 | -97118 | 343662 | 343662 | 100% | 0 | 0 | 0 | 57301 | -12626 | 44675 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [6 empty] | 2003-07-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Tianjin Relong Insulation Pipe Plant | Individual | ASP | CPR | FOA | 29 | INV | 314 | N | O | I | CFC | 12 | 12 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 93190 | 0 | 93190 | 87233 | 93.61% | 5957 | 0 | 0 | 12115 | 0 | 11340.5708 | 774.4292 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [6 empty] | 2002-12-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Zhenjiang Feichi Automobile Group, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 315 | N | O | I | CFC | 32 | 32 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 223900 | -11388 | 212512 | 212512 | 100% | 0 | 0 | 0 | 29107 | -1481 | 27626 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [6 empty] | 2002-12-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Taiyuan No. 2 Plastic Factory | Individual | ASP | CPR | FOA | 29 | INV | 316 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1999-11-01 | 2002-10-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 127790 | 0 | 127790 | 120842 | 94.56% | 6948 | 0 | 0 | 16613 | 0 | 15709.7437 | 903.2563 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Harbin Dongguang Machinery Plant | Individual | ASP | CPR | FOA | 29 | INV | 318 | N | O | I | CFC | 57 | 57 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 447170 | -23616 | 423554 | 423554 | 100% | 0 | 0 | 0 | 58132 | -3070 | 55062 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [6 empty] | 2002-12-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Dongfeng Automobile Body Company | Individual | ASP | CPR | FOA | 29 | INV | 319 | N | O | I | CFC | 7 | 7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 111120 | 0 | 111120 | 101865 | 91.67% | 9255 | 0 | 0 | 14446 | 0 | 13242.8167 | 1203.1833 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Zhifu Zhenxing Polyurethane Materials Plant | Individual | ASP | CPR | FOA | 29 | INV | 325 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 261480 | -24023 | 237457 | 237457 | 100% | 0 | 0 | 0 | 33992 | -3123 | 30869 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Hebei Tianye Automobile Group Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 326 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 98800 | -21298 | 77502 | 77502 | 100% | 0 | 0 | 0 | 12844 | -2769 | 10075 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of integral skin foam at Guangzhou Haohua Automobile Carpet Plant | Individual | ASP | CPR | FOA | 29 | INV | 328 | N | O | I | CFC | 7 | 7 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-09-01 | 2004-06-01 | 119540 | -8640 | 110900 | 110900 | 100% | 0 | 0 | 0 | 15540 | -1124 | 14416 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Ningxian Oriental Auto Parts Plant | Individual | ASP | CPR | FOA | 29 | INV | 329 | N | O | I | CFC | 7 | 7 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 122235 | 0 | 122235 | 116085 | 94.97% | 6150 | 0 | 0 | 15891 | 0 | 15091.4774 | 799.5226 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [6 empty] | 2002-12-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Fushan Anti-Corrosion Insulation Engineering Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 330 | N | O | I | CFC | 54 | 54 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2002-08-01 | 2004-06-01 | 425950 | -15465 | 410485 | 410485 | 100% | 0 | 0 | 0 | 55374 | -2010 | 53364 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam and flexible molded foam at Zhongqi Jinan Auto Parts Factory | Individual | ASP | CPR | FOA | 29 | INV | 331 | N | O | I | CFC | 22 | 22 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 236130 | -8780 | 227350 | 227350 | 100% | 0 | 0 | 0 | 30697 | -1141 | 29556 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Anqiu Polyurethane Materials Factory | Individual | ASP | CPR | FOA | 29 | INV | 332 | N | O | I | CFC | 64 | 64 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 497200 | -9710 | 487490 | 487490 | 100% | 0 | 0 | 0 | 64636 | -1262 | 63374 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Jizhou Beinei Automobile Cushion Plant | Individual | ASP | CPR | FOA | 29 | INV | 333 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-05-01 | 2005-03-01 | 484040 | 0 | 484040 | 466263 | 96.33% | 17777 | 0 | 0 | 62925 | 0 | 60613.9973 | 2311.0027 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [6 empty] | 2002-12-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Qingdao No. 10 Plastic Plant | Individual | ASP | CPR | FOA | 29 | INV | 334 | N | O | I | CFC | 38 | 38 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 298480 | -30327 | 268153 | 268153 | 100% | 0 | 0 | 0 | 38802 | -3943 | 34859 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1999 | Investment
CLO | UNDP | Preparation of 7 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 343 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 35000 | -35000 | 0 | 0 |  | 0 | 0 | 0 | 4550 | -4550 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration subsector (hydrocarbons) | Individual | ASP | CPR | REF | 30 | PRP | 344 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 35000 | -7212 | 27788 | 27788 | 100% | 0 | 0 | 0 | 4550 | -938 | 3612 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
CLO | UNDP | Preparation of 4 projects in the foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 345 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
CLO | UNDP | Preparation of 8 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 348 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
COM | UNDP | ODS phaseout in China solvent sector: 2000 annual programme | Multi-Year | ASP | CPR | SOL | 30 | INV | 355 | N | O | I | TCA/CTC/CFC | 383 | 383 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-03-01 |  | 2003-05-01 |  | 6750000 | 0 | 6750000 | 6750000 | 100% | 0 | 0 | 0 | 675000 | 0 | 675000 | 0 | 0 | Completed in 2003. | [10 empty] | 2000 | Investment | 3396 | 3396 |  |  | yes | yes | yes
COM | UNDP | Phaseout of CFC-11 by conversion to cyclopentane technology and CFC-12 by conversion to isobutane (600a) technology in the manufacture of domestic freezers at Qingdao Haier No. 2 Freezer Plant | Individual | ASP | CPR | REF | 32 | INV | 367 | N | O | I | CFC | 181 | 181 | 0 | 0 | 2000-12-01 | 2003-06-01 | 2004-01-01 |  | 2004-11-01 |  | 788359 | 0 | 788359 | 779066 | 98.82% | 9293 | 0 | 4646.5 | 96720 | 0 | 95579.8862 | 1140.1138 | 0 | Completed in 2004. | [10 empty] | 2000 | Investment
COM | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | ASP | CPR | SEV | 32 | INS | 368 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2003-01-01 |  | 2003-06-01 |  | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2003. | [10 empty] | 2000 | Non-Investment
COM | UNDP | ODS phaseout in China solvent sector: 2000-2001 annual programme | Multi-Year | ASP | CPR | SOL | 33 | INV | 373 | N | O | I | TCA/CTC/CFC | 534 | 534 | 0 | 0 | 2001-03-01 | 2003-03-01 | 2002-03-01 |  | 2005-01-01 |  | 6955000 | 0 | 6955000 | 6955000 | 100% | 0 | 0 | 0 | 695500 | 0 | 695500 | 0 | 0 | Completed in 2005. Activities at sub-project levels completed. 2001 phase out targets met | [7 empty] | 2003-09-01 |  |  | 2001 | Investment | 2788 | 2788 |  |  | yes | yes | yes
COM | UNDP | ODS phase-out in China solvent sector: 2002 annual programme | Multi-Year | ASP | CPR | SOL | 36 | INV | 390 | N | O | I | TCA/CTC/CFC | 580 | 580 | 0 | 0 | 2002-03-01 | 2005-01-01 | 2003-03-01 |  | 2005-09-01 |  | 6330000 | 0 | 6330000 | 5243903 | 82.84% | 1086097 | 30 | 1086097 | 633000 | 0 | 524390.3 | 108609.7 | 3 | Completed. All sub-project phase out activities completed. 16 of the 32 enterprises successfully completed installation and commissioning and submitted Project Completion Report in 2004. One enterprise switched to undertake phase out activities at its own and opted for reimbursement mechanism. The remaining 15 enterprises had equipment installed, adjusted and completed commissioning in September 2005. | [8 empty] | 2004-06-01 |  | 2002 | Investment | 2280 | 2280 |  |  | yes | yes | yes
COM | UNDP | Extension of institutional strengthening (phase 5) | Individual | ASP | CPR | SEV | 38 | INS | 398 | N | T | I | CFC | 32 | 32 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2005-09-01 |  | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 50700 | 0 | 50700 | 0 | 0 | Completed in 2005. NOU continued to interact actively with IAs on the implementation of sector phase out plans and necessary regulatory measures | [10 empty] | 2002 | Non-Investment
COM | UNDP | ODS phase-out in China solvent sector: 2003 annual programme | Multi-Year | ASP | CPR | SOL | 40 | INV | 403 | N | O | I | CFC/TCA/CTC | 580 | 580 | 0 | 0 | 2003-07-01 |  | 2004-03-01 |  | 2005-12-01 |  | 5755000 | 0 | 5755000 | 0 | 0% | 5755000 | 0 | 2877500 | 431625 | 0 | 0 | 431625 | 0 | Completed. Due to SARS situation, contracts for phase out activities were signed late in November 2003. Phase out activities at these 12 enterprises with ODS contracts were completed in September 2005. 71 SMEs participated in the voucher system organized by three Intermediate Execution Agents. Equipment was delivered to all and most have their equipment installed, commissioned and trial conducted in 2005 with remaining to be completed in 2006. Phase out was also achieved through agreement signed with 143 enterprises undertaking gradual phase out in 2004 and 2005 consumption. Project completed December 2005. | [9 empty] | 2005-06-01 | 2003 | Investment | 1700 | 1700 |  |  | yes | yes | yes
ONG | UNDP | ODS phase-out in China solvent sector: 2004 annual programme | Multi-Year | ASP | CPR | SOL | 42 | INV | 410 | N | O | I | CFC | 733 | 733 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 |  |  | 5555000 | 0 | 5555000 | 0 | 0% | 5555000 | 0 | 1944250 | 416625 | 0 | 0 | 416625 | 0 | Project activities at enterprises in progress for completion June 2006. Retroactive reimbursement and Voucher System being conducted. 2004 Phase out targets achieved | [10 empty] | 2004 | Investment | 967 | 967 |  |  | yes | yes | yes
ONG | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | CPR | SEV | 44 | INS | 421 | N | T | I | CFC | 32 | 16 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 390000 | 0 | 390000 | 184541 | 47.32% | 205459 | 0 | 71910.65 | 29250 | 0 | 13840.575 | 15409.425 | 0 | During 2005, the Programme Management Office of FECO/SEPA continued effective supervision and management of its sector phase out plans. The PMO intensified its effort and concluded an agreement with MLF and committed to early CFC and halons phase out by July 2007, two years ahead of MP schedule. Under the Solvent Sector Plan, CFC-113 was phased out end 2005. PMO continued its effort in improving policy formulation and intensified its monitoring effort, including illegal ODS activities. The PMO and UNDP also jointly organized activities for 12 provinces/cities to achieve ODS free city status by June 2006 through policies and control measures. High profile public awareness activities and workshops were also implemented. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | ODS phase-out in China solvent sector: 2005 annual programme | Multi-Year | ASP | CPR | SOL | 45 | INV | 429 | N | O | I | TCA/CTC | 635 | 635 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 5680000 | 0 | 5680000 | 0 | 0% | 5680000 | 0 | 1988000 | 426000 | 0 | 0 | 426000 | 0 | Solvent Special Working Group interacted with industries to identify participants in Voucher System and Retroactive Reimbursement to achieve phase-out | [10 empty] | 2005 | Investment | 339 | 339 |  |  | yes | yes | yes
ONG | UNDP | ODS phase-out in China solvent sector: 2006 annual programme | Multi-Year | ASP | CPR | SOL | 47 | INV | 435 | N | O | I | TCA/CTC | 85 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 5055000 | 0 | 5055000 | 0 | 0% | 5055000 | 0 | 1769250 | 379125 | 0 | 0 | 379125 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment | 253 |  |  |  | Latest | Latest | Latest
FIN | UNDP | Country programme preparation | Individual | LAC | CUB | SEV | 08 | CPG | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 20000 | -5000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 2600 | -650 | 1950 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of OTOZ | Individual | LAC | CUB | SEV | 10 | INS | 02 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-10-01 | 2000-12-01 | 172000 | -5 | 171995 | 171995 | 100% | 0 | 0 | 0 | 22360 | -1 | 22359 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Development of an ODS phase out strategy in the refrigeration sector | RMP-Component | LAC | CUB | REF | 13 | TAS | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-07-01 |  | 1997-09-01 | 1998-12-01 | 30000 | -10000 | 20000 | 20000 | 100% | 0 | 0 | 0 | 3900 | -1300 | 2600 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | CUB | REF | 15 | TAS | 04 | A | O | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-12-01 |  | 1997-09-01 | 1998-12-01 | 169000 | -5167 | 163833 | 163833 | 100% | 0 | 0 | 0 | 21970 | -672 | 21298 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 22 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Umbrella project for elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Empco-Mincin and Segere-Sime "Dionisio Rodrigues" | Individual | LAC | CUB | REF | 23 | INV | 06 | A | O | I | CFC | 3 | 3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-06-01 | 2002-03-01 | 119505 | -9086 | 110419 | 110419 | 100% | 0 | 0 | 0 | 15536 | -1181 | 14355 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | CUB | SEV | 26 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14907 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 33 | PRP | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Renewal of the institutional strengthening under Montreal Protocol (phase III) | Individual | LAC | CUB | SEV | 34 | INS | 17 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2003-08-01 |  | 2003-09-01 | 2004-12-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14907 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2001 | Non-Investment
ONG | UNDP | Phaseout of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | Individual | LAC | CUB | ARS | 34 | INV | 18 | A | O | I | CFC | 28 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-05-01 | 2006-07-01 |  |  | 124220 | 0 | 124220 | 122388 | 98.53% | 1832 | 0 | 641.2 | 16149 | 0 | 15910.8341 | 238.1659 | 0 | Inclement weather delayed local works again. Installation visit scheduled in Nov. 2005 and engineer passed away. New visit foreseen for early 2006. | [10 empty] | 2001 | Investment
COM | UNDP | Development of MDI transition strategies | Individual | LAC | CUB | ARS | 36 | TAS | 19 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2004-03-01 |  | 30000 | 0 | 30000 | 22528 | 75.09% | 7472 | 0 | 3736 | 3900 | 0 | 2928.64 | 971.36 | 0 | Completed in 2004. | [10 empty] | 2002 | Non-Investment
FIN | UNDP | Project preparation in the MDI sector | Individual | LAC | CUB | ARS | 36 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 30000 | 20000 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3900 | 1500 | 5400 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Extension of the institutional strengthening project (phase 4) | Individual | LAC | CUB | SEV | 40 | INS | 22 | N | T | I | CFC | 12 | 6 | 0 | 0 | 2003-07-01 | 2003-10-01 | 2005-07-01 | 2006-03-01 |  |  | 149066 | 0 | 149066 | 148564 | 99.66% | 502 | 0 | 175.7 | 11180 | 0 | 11142.3498 | 37.6502 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | CUB | ARS | 41 | INV | 23 | N | O | I | CFC | 109 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2006-09-01 | 2008-03-01 |  |  | 5960000 | 0 | 5960000 | 671465 | 11.27% | 5288535 | 0 | 1057707 | 447000 | 0 | 50359.875 | 396640.125 | 0 | 45th Excom approved change of technology provider by product developer. Commercial agreement signed and 1st visit completed. Layouts for local engineering works prepared. Adaptation of plant and installation of equipment expected in 2006. | [10 empty] | 2003 | Investment
ONG | UNDP | National ODS phase-out plan for CFCs: 2005 annual implementation plan - UNDP Portion | Multi-Year | LAC | CUB | PHA | 45 | INV | 33 | N | O | I | CFC | 30 | 30 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 0 | 87500 | 18750 | 0 | 0 | 18750 | 0 | Approved in Apr 05. Activities initiated. | [10 empty] | 2005 | Investment | 30 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | CUB | SEV | 47 | INS | 34 | N | T | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 149066 | 0 | 149066 | 0 | 0% | 149066 | 0 | 29813.2 | 11180 | 0 | 0 | 11180 | 0 | The Institutional Strengthening project for Cuba has enabled the Government to continue the successful implementation of Montreal Protocol in the country. During 2005 the NOU continued its monitoring of the country’s compliance status with the Montreal Protocol through data collection and monitoring of ODS consumption. The NOU also continued its efforts towards strengthening the legal framework by proposing new resolutions. Implementation of projects has continued progressing and significant progress has been achieved in the MDI conversion project. Cuba has hosted a series of workshops, meetings and events including MeBr alternatives workshop, meeting of the English speaking Caribbean officers on usage of hydrocarbons etc… Furthermore, Cuba continued public awareness activities through TV spots, newspaper clips, posters, calendars, and regular public presentations. Cuba has also participated in the Executive Committee and other Montreal Protocol meetings at the international level. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 36 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 787482 | 0 | 787482 | 0 | 0% | 787482 | 0 | 157496.4 | 59061 | 0 | 0 | 59061 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | DJI | REF | 36 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Update-Comp | AFR | DJI | REF | 37 | TAS | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 9662 | 38.65% | 15338 | 0 | 5368.3 | 3250 | 0 | 1256.06 | 1993.94 | 0 | National consultant to be identified early 2006 for monitoring | [10 empty] | 2002 | Investment
ONG | UNDP | Implementation of the RMP: recovery and recycling | RMP-Update-Comp | AFR | DJI | REF | 37 | TAS | 07 | A | O | I | CFC | 6 | 1 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 | 2006-07-01 |  |  | 136463 | 0 | 136463 | 87855 | 64.38% | 48608 | 0 | 17012.8 | 17740 | 0 | 11421.15 | 6319.04 | 0 | Equipment delivered and workshops held in November. Monitoring phase to start early 2006 after recruitment of National Consultant | [10 empty] | 2002 | Investment
FIN | UNDP | Demonstration project in commercial refrigeration (food storage, distribution and retailing) | RMP-Component | LAC | DOM | REF | 18 | TAS | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-04-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1995 | Non-Investment
FIN | UNDP | Project preparation assistance in foams and refrigeration | Individual | LAC | DOM | SEV | 18 | PRP | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | DOM | REF | 21 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Fabrica de Refrigeradores Comerciales, C.A. (Farco) | Individual | LAC | DOM | REF | 22 | INV | 09 | A | O | I | CFC | 32 | 32 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-11-01 | 2000-07-01 | 423209 | -2883 | 420326 | 420326 | 100% | 0 | 0 | 0 | 55017 | -375 | 54642 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sub-sector | Individual | LAC | DOM | REF | 22 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Metalgas S.A. by replacement with HCFC-141b and HFC-134a respectively | Individual | LAC | DOM | REF | 24 | INV | 11 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 1999-12-01 | 2001-12-01 | 316368 | -3741 | 312627 | 312627 | 100% | 0 | 0 | 0 | 41128 | -486 | 40642 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for one project in commercial refrigeration subsector | Individual | LAC | DOM | REF | 24 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | DOM | REF | 25 | TAS | 13 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 441482 | -49014 | 392468 | 392468 | 100% | 0 | 0 | 0 | 57393 | -6372 | 51021 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | DOM | REF | 25 | TAS | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-01-01 | 2000-08-01 |  | 2003-09-01 | 2003-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Industria Continental, C.A. by replacement with HCFC-141b and HFC 134a respectively | Individual | LAC | DOM | REF | 25 | INV | 16 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-03-01 | 303200 | -2802 | 300398 | 300398 | 100% | 0 | 0 | 0 | 39416 | -364 | 39052 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of a project in the general foam subsector | Individual | LAC | DOM | FOA | 27 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Paredomi (Paneles Refrigerados Dominicanos, C.A.) | Individual | LAC | DOM | FOA | 29 | INV | 21 | A | O | I | CFC | 61 | 61 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-04-01 | 2003-09-01 | 177670 | 0 | 177670 | 177670 | 100% | 0 | 0 | 0 | 23097 | 0 | 23097 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Espumas del Cibao | Individual | LAC | DOM | FOA | 29 | INV | 22 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2002-11-01 | 89712 | -1048 | 88664 | 88664 | 100% | 0 | 0 | 0 | 11663 | -136 | 11527 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Poquinsa (Poliuretano Químico Indutrial, S.A.) | Individual | LAC | DOM | FOA | 29 | INV | 24 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 24920 | 0 | 24920 | 24920 | 100% | 0 | 0 | 0 | 3240 | 0 | 3240 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | DOM | FOA | 33 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | DOM | FOA | 36 | PRP | 27 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2005-07-01 |  | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 975 | 0 | 975 | 0 | 0 | Completed in 2005. National Phase Out Plan submitted and approved at 45th Excom Meeting in April 2005. Expenditures completed. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the solvent sector | Individual | LAC | DOM | SOL | 36 | PRP | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of investment activities of the RMP | Individual | LAC | DOM | REF | 36 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | National halon bank management plan development | Individual | LAC | DOM | HAL | 38 | TAS | 32 | N | O | I | Halon | 3 | 0 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 28391 | 70.98% | 11609 | 0 | 4063.15 | 5200 | 0 | 3690.83 | 1509.17 | 0 | Bidding process to purchase halon recovery equipment ongoing. A Memorandum of Understanding with the Fire departmnet to run the Halon Centerwas prepared with UNDP assistance and sent to the parties for signature. | [10 empty] | 2002 | Investment
COM | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | DOM | PHA | 42 | PRP | 35 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-05-01 |  | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 563 | 0 | 563 | 0 | 0 | Completed in 2005. Project was completed with submission of National Plan. | [10 empty] | 2004 | Investment
ONG | UNDP | Terminal phase-out plan for Annex A (Group I) substances: 2005 annual implementation programme | Multi-Year | LAC | DOM | PHA | 45 | INV | 36 | N | O | I | CFC | 41 | 41 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 | 0 | 175000 | 37500 | 0 | 0 | 37500 | 0 | Approved in Apr 05. Project Document signed and workplan established. | [10 empty] | 2005 | Investment | 311.2 |  |  |  | Latest | Latest | Latest
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | DRC | FOA | 33 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
ONG | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Complast SPRL | Individual | AFR | DRC | FOA | 35 | INV | 06 | A | O | I | CFC | 38 | 10 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 | 2006-07-01 |  |  | 190820 | 0 | 190820 | 181549 | 95.14% | 9271 | 0 | 3244.85 | 24807 | 0 | 23601.7506 | 1205.2494 | 0 | Equipment finally cleared from customs and delivered to end-user. Installation at Kinshasa plant Installation at Mbuji-Myi to take place early 2006. Final verification visit will be scheduled soon thereafter. | [10 empty] | 2001 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slastock foam by conversion to methylene chloride at M.K. SPRL | Individual | AFR | DRC | FOA | 35 | INV | 07 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 |  | 149800 | 0 | 149800 | 96298 | 64.28% | 53502 | 0 | 26751 | 19474 | 0 | 12518.74 | 6955.26 | 0 | Completed in 2005. Installation took place Feb.05. Local works completed, test trials successful and project completed Dec. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in recovery and recycling refrigeration sector | Individual | AFR | DRC | REF | 36 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock sector | Individual | AFR | DRC | FOA | 36 | PRP | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 2002 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Bek SPRL by convesion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 10 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-09-01 |  | 2005-12-01 |  | 165670 | 0 | 165670 | 163376 | 98.62% | 2294 | 0 | 1147 | 21537 | 0 | 21238.88 | 298.22 | 0 | Completed in 2005. Local works completed and formulations finalized and converted. Project completed. | [10 empty] | 2002 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Ekanawe SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 11 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 |  | 75490 | 0 | 75490 | 69735 | 92.38% | 5755 | 0 | 2877.5 | 9814 | 0 | 9065.55 | 748.15 | 0 | Completed in 2005. Local works finalized and equipment installed. Test trials commenced and formulations finetuned. Project completed during last visit in Dec. | [10 empty] | 2002 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Sokamo SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 12 | A | O | I | CFC | 21 | 21 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 |  | 69920 | 0 | 69920 | 68459 | 97.91% | 1461 | 0 | 730.5 | 9090 | 0 | 8899.67 | 189.93 | 0 | Completed in 2005. Local works finalized and equipment installed. Test trials commenced and formulations finetuned. Project completed during last visit in Dec. | [10 empty] | 2002 | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | DRC | REF | 39 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
FIN | UNDP | Formulation of terminal project in the foam sector | Individual | AFR | DRC | FOA | 39 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Update-Comp | AFR | DRC | REF | 41 | TAS | 16 | N | O | I | CFC | 13 | 0 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 437102 | 0 | 437102 | 13767 | 3.15% | 423335 | 454000 | 148167.25 | 32783 | 0 | 1032.536 | 31750.464 | 34050.3635 | Equipm. ordered and subcontract with centralised centers established. Workhop to be organized mid-2006. Overrun due to charge that should have been made to DRC-16. Will be corrected in 2006. | [10 empty] | 2003 | Investment
ONG | UNDP | Terminal umbrella project for the foam sector | Individual | AFR | DRC | FOA | 41 | INV | 19 | N | O | I | CFC | 123 | 0 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 640820 | 0 | 640820 | 7113 | 1.11% | 633707 | 108826 | 221797.45 | 48062 | 0 | 533.4805 | 47528.5194 | 8162.0349 | Equipm. ordered and should arrive in May 06. Meetings held with 8 enterprises to ensure they prepare local works. Trials and closure scheduled by end 2006. | [10 empty] | 2003 | Investment
ONG | UNDP | Project preparation for refrigeration end-user | Individual | AFR | DRC | REF | 45 | PRP | 21 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-05-01 | 2006-04-01 | 2006-07-01 |  |  | 16870 | 0 | 16870 | 13335 | 79.05% | 3535 | 0 | 3535 | 1265 | 0 | 999.9274 | 265.0726 | 0 | Missions undertaken in Jun, Aug and Dec to formulate TPMP in lieu of end-user project. Will be submitted at 49th ExCom. | [10 empty] | 2005 | Investment
FIN | UNDP | Training programme for the Montreal Protocol Project Implementation Unit | Individual | LAC | ECU | SEV | 06 | TRA | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-12-01 |  | 1994-06-01 | 1997-12-01 | 100000 | 40000 | 140000 | 140000 | 100% | 0 | 0 | 0 | 13000 | 5200 | 18200 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Study tours for officials from the Ministry of the Environment, and pre-feasibility study | Individual | AFR | EGY | SEV | 04 | TRA | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-02-01 |  | 1992-06-01 | 1997-12-01 | 51000 | -6910 | 44090 | 44090 | 100% | 0 | 0 | 0 | 6630 | -898 | 5732 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | AFR | EGY | SEV | 06 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1993-09-01 | 2003-04-01 | 100000 | 319 | 100319 | 100319 | 100% | 0 | 0 | 0 | 13000 | 41 | 13041 | 0 | 0 | Completed in 1993. Financially completed in 2003. | [10 empty] | 1992 | Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of flexible polyurethane foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 08 | INV | 05 | A | O | I | CFC | 121 | 121 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1993-10-01 |  | 1994-01-01 | 2003-04-01 | 497000 | 3489 | 500489 | 500489 | 100% | 0 | 0 | 0 | 64610 | 454 | 65064 | 0 | 0 | Completed in 1994. Financially completed in 2003. | [10 empty] | 1992 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacturing of moulded, flexible, semi-rigid and rigid polyurethane foam at Taki-Vita factory | Individual | AFR | EGY | FOA | 08 | INV | 06 | A | O | I | CFC | 50 | 86 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1995-04-01 | 2003-04-01 | 293950 | 58550 | 352500 | 352500 | 100% | 0 | 0 | 0 | 38214 | 7612 | 45826 | 0 | 0 | Completed in 1995. Financially completed in 2003. | [10 empty] | 1992 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of moulded polyurethane foams at Technopol Egypt SAE | Individual | AFR | EGY | FOA | 08 | INV | 07 | A | O | I | CFC | 55 | 55 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-04-01 | 2003-04-01 | 645000 | 31211 | 676211 | 676211 | 100% | 0 | 0 | 0 | 83850 | 4057 | 87907 | 0 | 0 | Completed in 1994. Financially completed in 2003. | [10 empty] | 1992 | Investment
FIN | UNDP | Phase-out of CFC in refrigeration at Koldair Company | Individual | AFR | EGY | REF | 08 | INV | 09 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-01-01 | 2003-04-01 | 272000 | -21979 | 250021 | 250021 | 100% | 0 | 0 | 0 | 35360 | -2857 | 32503 | 0 | 0 | Completed in 1994. Financially completed in 2003. | [10 empty] | 1992 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at Al-Sharif Plastic Factories | Individual | AFR | EGY | FOA | 09 | INV | 10 | A | O | I | CFC | 75 | 75 | 0 | 0 | 1993-03-01 | 1998-12-01 | 1994-06-01 |  | 2001-12-01 | 2003-04-01 | 498000 | -22472 | 475528 | 475528 | 100% | 0 | 0 | 0 | 64740 | -2921 | 61819 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1993 | Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of molded foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 09 | INV | 12 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1993-11-01 | 2003-04-01 | 275000 | 9431 | 284431 | 284431 | 100% | 0 | 0 | 0 | 35750 | 1226 | 36976 | 0 | 0 | Completed in 1993. Financially completed in 2003. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded flexible polyurethane foam at Modern Building Carpentry Co. (Mobica) | Individual | AFR | EGY | FOA | 10 | INV | 15 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 434000 | 0 | 434000 | 434000 | 100% | 0 | 0 | 0 | 56420 | 0 | 56420 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded rigid polyurethane foam at Cairo Light Industries Co. (Olympic Electric) | Individual | AFR | EGY | FOA | 10 | INV | 17 | A | O | I | CFC | 75 | 75 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-12-01 |  | 1995-11-01 | 2000-12-01 | 940000 | -28084 | 911916 | 911916 | 100% | 0 | 0 | 0 | 122200 | -3651 | 118549 | 0 | 0 | Completed in 1995. Financially completed in 2000. | [10 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of rigid polyurethane foam (PUF) at Specialized Engineering Contracting Co. | Individual | AFR | EGY | FOA | 11 | INV | 18 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1994-12-01 | 1998-12-01 | 85000 | -5398 | 79602 | 79602 | 100% | 0 | 0 | 0 | 11050 | -702 | 10348 | 0 | 0 | Completed in 1994. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam at Alex Foam (formerly Dekheila Chemical Industries Co.) | Individual | AFR | EGY | FOA | 11 | INV | 19 | A | O | I | CFC | 130 | 130 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1995-11-01 | 1998-12-01 | 650000 | -82388 | 567612 | 567612 | 100% | 0 | 0 | 0 | 84500 | -10710 | 73790 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam (PUF) at Horse Foam Co. | Individual | AFR | EGY | FOA | 11 | INV | 20 | A | O | I | CFC | 120 | 120 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-08-01 |  | 1997-03-01 | 2000-07-01 | 385000 | -107636 | 277364 | 277364 | 100% | 0 | 0 | 0 | 50050 | -13993 | 36057 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1993 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | FOA | 11 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-01-01 |  | 1994-12-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of flexible polyurethane foam at Foam Industrial and Hyma | Individual | AFR | EGY | FOA | 12 | INV | 22 | A | O | I | CFC | 170 | 170 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-06-01 |  | 1997-03-01 | 2000-07-01 | 525000 | -11898 | 513102 | 513102 | 100% | 0 | 0 | 0 | 68250 | -1547 | 66703 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Technical assistance to prepare a national halon action plan and project development | Individual | AFR | EGY | HAL | 12 | TAS | 23 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-01-01 |  | 1997-03-01 | 1998-12-01 | 25000 | 1730 | 26730 | 26730 | 100% | 0 | 0 | 0 | 3250 | 225 | 3475 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of rigid molded and miscellaneous PUF at 5 plants: Tiba Air, Egat Company, Solar Energy Company, Ismailia Aluminum Company, and Fu Tech Company | Individual | AFR | EGY | FOA | 12 | INV | 26 | A | O | I | CFC | 44 | 44 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-03-01 | 1997-11-01 | 870000 | -107668 | 762332 | 762332 | 100% | 0 | 0 | 0 | 113100 | -13997 | 99103 | 0 | 0 | Completed in 1997. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at Scib Chemical Company | Individual | AFR | EGY | FOA | 12 | INV | 27 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1995-11-01 | 2003-02-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 2003. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at El Fateh | Individual | AFR | EGY | FOA | 12 | INV | 28 | A | O | I | CFC | 59 | 59 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2002-03-01 | 2003-01-01 | 496000 | -1 | 495999 | 495999 | 100% | 0 | 0 | 0 | 64480 | 0 | 64480 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  | 1997-09-01 | [7 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at Industrial Engineering Company for Construction and Development (Icon) | Individual | AFR | EGY | FOA | 12 | INV | 29 | A | O | I | CFC | 51 | 51 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1999-10-01 | 2001-12-01 | 498000 | 0 | 498000 | 498000 | 100% | 0 | 0 | 0 | 64740 | 0 | 64740 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology Reftruck Company | Individual | AFR | EGY | REF | 12 | INV | 30 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1998-09-01 | 2002-11-01 | 385000 | -2692 | 382308 | 382308 | 100% | 0 | 0 | 0 | 50050 | -350 | 49700 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at Misr Panel (Egyptian Company for Cold Storage Industries) | Individual | AFR | EGY | REF | 12 | INV | 31 | A | O | I | CFC | 74 | 74 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2001-03-01 | 2002-03-01 | 636000 | 0 | 636000 | 636000 | 100% | 0 | 0 | 0 | 82680 | 0 | 82680 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  |  | 1997-09-01 | [7 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacturing of rigid PUF at seven enterprises: GMC, Petrojet, Modern Products, Cairo General Contractors Co., Egyptian Solar Energy, Tawifika, Helwan | Individual | AFR | EGY | FOA | 15 | INV | 36 | A | O | I | CFC | 69 | 51 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 2000-12-01 | 2002-11-01 | 780000 | -292655 | 487345 | 487345 | 100% | 0 | 0 | 0 | 101400 | -38045 | 63355 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-07-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Royal Engineering, Co. | Individual | AFR | EGY | REF | 15 | INV | 44 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 539000 | -1790 | 537210 | 537210 | 100% | 0 | 0 | 0 | 70070 | -233 | 69837 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Port Said Metal Work, Co. (MOG) | Individual | AFR | EGY | REF | 15 | INV | 45 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1999-10-01 | 2003-02-01 | 484000 | 0 | 484000 | 484000 | 100% | 0 | 0 | 0 | 62920 | 0 | 62920 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [6 empty] | 1994 | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF at El-Tawil Manufacturing Company | Individual | AFR | EGY | FOA | 15 | INV | 46 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-12-01 |  |  | 2000-12-01 | 121000 | -91977 | 29023 | 29023 | 100% | 0 | 0 | 0 | 15730 | -11957 | 3773 | 0 | 0 | Canceled in 1999. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible molded PUF and integral skin foam at El Shabrawi | Individual | AFR | EGY | FOA | 18 | INV | 48 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 1999-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at United Investment Corporation Inc. | Individual | AFR | EGY | REF | 18 | INV | 49 | A | O | I | CFC | 49 | 49 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1999-11-01 | 2003-11-01 | 493350 | -32495 | 460855 | 460855 | 100% | 0 | 0 | 0 | 64136 | -4224 | 59912 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refcat Compnay Inc. | Individual | AFR | EGY | REF | 18 | INV | 50 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 2000-12-01 | 409000 | -19 | 408981 | 408981 | 100% | 0 | 0 | 0 | 53170 | -3 | 53167 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | SEV | 18 | PRP | 55 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at El-Mohandes | Individual | AFR | EGY | REF | 20 | INV | 58 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 |  | 2000-06-01 | [5 empty] | 1996 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Amiral | Individual | AFR | EGY | REF | 20 | INV | 59 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-06-01 | 1998-09-01 |  |  | 2003-11-01 | 160000 | -70081 | 89919 | 89919 | 100% | 0 | 0 | 0 | 20800 | -9111 | 11689 | 0 | 0 | Canceled in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | EGY | FOA | 21 | PRP | 60 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 40000 | -7520 | 32480 | 32480 | 100% | 0 | 0 | 0 | 5200 | -978 | 4222 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
COM | UNDP | Phaseout of the remaining ODS consumption in the foam sector (11 enterprises) | Individual | AFR | EGY | FOA | 22 | INV | 64 | A | O | I | CFC | 319 | 319 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 2005-01-01 |  | 1672000 | 0 | 1672000 | 1634046 | 97.73% | 37954 | 0 | 18977 | 217360 | 0 | 212425.98 | 4934.02 | 0 | Completed in 2005. Spares delivered and project officially completed. |  |  |  |  | 2000-12-01 | [5 empty] | 1997 | Investment
CLO | UNDP | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and curcubits) | Individual | AFR | EGY | FUM | 24 | PRP | 66 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 1998-07-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 1998. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation to prepare one halon sector programme | Individual | AFR | EGY | HAL | 24 | PRP | 67 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 2000-10-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
ONG | UNDP | Halon management bank programme | Individual | AFR | EGY | HAL | 32 | TAS | 81 | N | O | I | Halon | 756 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2004-01-01 | 2006-12-01 |  |  | 405000 | 0 | 405000 | 258415 | 63.81% | 146585 | 0 | 51304.75 | 52650 | 0 | 33593.95 | 19056.05 | 0 | Equipment procured. Arrived in EGY July 2003. Final negotiations ongoing with Army company to manage halon bank. | [10 empty] | 2000 | Investment
TRF | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | AFR | EGY | REF | 36 | PRP | 84 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 0 | 2600 | 0 | 0 | 2600 | 0 | Transferred in 2003. Balance to be returned. | [10 empty] | 2002 | Investment
FIN | UNDP | Project preparation in the refrigeration sectors | Individual | LAC | ELS | REF | 21 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 45000 | -3239 | 41761 | 41761 | 100% | 0 | 0 | 0 | 5850 | -421 | 5429 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Prado, S.A. de C.V. | Individual | LAC | ELS | REF | 22 | INV | 03 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-06-01 | 2001-12-01 | 306229 | 0 | 306229 | 306229 | 100% | 0 | 0 | 0 | 39810 | 0 | 39810 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
CLO | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | ELS | FOA | 24 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | ELS | REF | 25 | TAS | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2002-01-01 | 2000-08-01 |  | 2003-06-01 | 2005-10-01 | 10500 | 0 | 10500 | 9465 | 90.14% | 1035 | 0 | 0 | 1365 | 0 | 1230.45 | 134.55 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | ELS | REF | 25 | TAS | 09 | A | O | I | CFC | 36 | 36 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-05-01 | 403925 | -26048 | 377877 | 377877 | 100% | 0 | 0 | 0 | 52510 | -3386 | 49124 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | LAC | ELS | REF | 37 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-11-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 2275 | 0 | 2275 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | RMP update: technical assistance for the refrigeration sector | Individual | LAC | ELS | REF | 42 | TAS | 13 | N | O | I | CFC | 56 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 | 2008-04-01 |  |  | 231700 | 0 | 231700 | 47 | 0.02028% | 231653 | 0 | 46330.6 | 20853 | 0 | 4.23 | 20848.77 | 0 | Extraordinary delay to sign Project Document. Finally signed but there are problems in NOU. RMP lead consultant has not been appointed yet. UNDP CO very active trying to help expedite process. Expected mission early 2006 | [10 empty] | 2004 | Investment
ONG | UNDP | RMP update: technical assistance for certification and licensing of refrigeration technicians | Individual | LAC | ELS | REF | 42 | TRA | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 | 2008-04-01 |  |  | 77300 | 0 | 77300 | 47 | 0.0608% | 77253 | 0 | 15450.6 | 6957 | 0 | 4.23 | 6952.77 | 0 | RMP update: Same input as for project ELS/REF/42/TAS/13 | [10 empty] | 2004 | Investment
ONG | UNDP | RMP update: monitoring programme | Individual | LAC | ELS | REF | 42 | TAS | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 | 2008-04-01 |  |  | 41000 | 0 | 41000 | 50 | 0.122% | 40950 | 0 | 8190 | 3690 | 0 | 4.5 | 3685.5 | 0 | RMP update: Same input as for project ELS/REF/42/TAS/13 | [10 empty] | 2004 | Investment
ONG | UNDP | Project preparation of the investment components of the RMP | Individual | AFR | ERI | REF | 47 | PRP | 01 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 1500 | 0 | 0 | 1500 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
CLO | UNDP | Project preparation assistance | Individual | AFR | ETH | SEV | 17 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1997-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1997. | [10 empty] | 1995 | Investment
COM | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | ASP | FIJ | REF | 29 | TAS | 04 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 |  | 96755 | 0 | 96755 | 96256 | 99.48% | 499 | 0 | 249.5 | 12578 | 0 | 12513.1308 | 64.8692 | 0 | Completed in 2003. | [10 empty] | 1999 | Investment
ONG | UNDP | Project preparation for complete ODS phase-out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 16870 | 0 | 16870 | 0 | 0% | 16870 | 0 | 16870 | 1265 | 0 | 0 | 1265 | 0 | Project proposal prepared, submitted and approved at the 47th ExCom Meeting. Invoices to be settled in 2006. | [10 empty] | 2005 | Investment
ONG | UNDP | Implementation of the TPMP (investment component) | One-Off | ASP | FIJ | PHA | 47 | TAS | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 8000 | 3600 | 0 | 0 | 3600 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
ONG | UNDP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 17 | N | O | I | MeBr | 2 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 10000 | 4500 | 0 | 0 | 4500 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | GAB | REF | 21 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-11-01 | 2002-03-01 | 20000 | -5395 | 14605 | 14605 | 100% | 0 | 0 | 0 | 2600 | -701 | 1899 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 26 | TAS | 06 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1998-11-01 | 2001-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 232470 | -36306 | 196164 | 196164 | 100% | 0 | 0 | 0 | 30221 | -4720 | 25501 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GAB | REF | 26 | TAS | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2002-01-01 | 2000-12-01 |  | 2003-07-01 | 2003-08-01 | 12100 | -1600 | 10500 | 10500 | 100% | 0 | 0 | 0 | 1573 | -208 | 1365 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | GAB | REF | 37 | PRP | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Update-Comp | AFR | GAB | REF | 41 | TAS | 11 | N | O | I | CFC | 2 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 60277 | 0 | 60277 | 0 | 0% | 60277 | 0 | 21096.95 | 5425 | 0 | 0 | 5425 | 0 | Lack of response from potential bidders caused delay in purchasing equipm. Purchase Orders to be placed Mar 06 and workshop to be organized soon thereafter. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Update-Comp | AFR | GAB | REF | 41 | TAS | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 5250 | 1350 | 0 | 0 | 1350 | 0 | Project wil start after the R&R workshop conducted. | [10 empty] | 2003 | Non-Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | GAM | FOA | 21 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-05-01 | 2002-03-01 | 20000 | -6548 | 13452 | 13452 | 100% | 0 | 0 | 0 | 2600 | -851 | 1749 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Karan Foam Manufacturing Ltd. | Individual | AFR | GAM | FOA | 22 | INV | 06 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 63500 | -2619 | 60881 | 60881 | 100% | 0 | 0 | 0 | 8255 | -340 | 7915 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Investment
COM | UNDP | Formulation of the investment components of the RMP | Individual | AFR | GBS | REF | 39 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-04-01 |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2005. Final payments done. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance project for MAC and refrigeration service and end-user sub-sectors | RMP-Component | AFR | GBS | REF | 43 | TAS | 07 | N | O | I | CFC | 9 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 282900 | 0 | 282900 | 0 | 0% | 282900 | 0 | 99015 | 21218 | 0 | 0 | 21218 | 0 | Approved in Jul 04. Awaiting legislation to implement as per ExCom condition. | [10 empty] | 2004 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | EUR | GEO | REF | 23 | TAS | 04 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1997-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 106750 | -2348 | 104402 | 104402 | 100% | 0 | 0 | 0 | 13878 | -305 | 13573 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
COM | UNDP | Implementation of the RMP: incentive programme for the end-users in the commercial/industrial refrigeration and refrigerated transport sub-sectors | RMP-Update-Comp | EUR | GEO | REF | 35 | TAS | 10 | N | O | I | CFC | 2 | 2 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2005-01-01 |  | 2005-01-01 |  | 101000 | 0 | 101000 | 94666 | 93.73% | 6334 | 0 | 3167 | 13130 | 0 | 12306.58 | 823.42 | 0 | Completed in 2005. Operationally completed apart from some final admin issues. | [10 empty] | 2001 | Non-Investment
COM | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Update-Comp | EUR | GEO | REF | 35 | TAS | 11 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2007-12-01 |  | 2005-12-01 |  | 16350 | 0 | 16350 | 16350 | 100% | 0 | 0 | 0 | 2126 | 0 | 2126 | 0 | 0 | Completed in 2005. See remark for GEO-10 as activities are jointly implemented. | [10 empty] | 2001 | Non-Investment
TRF | UNDP | Refrigeration training programme for servicing technicians | RMP-Component | AFR | GHA | REF | 04 | TRA | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-06-01 |  |  | 1993-06-01 | 99000 | -93800 | 5200 | 5200 | 100% | 0 | 0 | 0 | 12870 | -12194 | 676 | 0 | 0 | Transferred in 1993. Financially completed in 1993. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Technical assistance for technology transfer for phase-out of CFC-11 in flexible foam | Individual | AFR | GHA | FOA | 08 | TAS | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1994-10-01 |  | 1995-06-01 | 1997-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Improved servicing and maintenance within the refrigeration sector | RMP-Component | AFR | GHA | REF | 08 | TAS | 04 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-04-01 | 1998-12-01 | 328000 | 0 | 328000 | 328000 | 100% | 0 | 0 | 0 | 42640 | 0 | 42640 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [10 empty] | 1992 | Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | GHA | SEV | 08 | INS | 05 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 160000 | 23200 | 183200 | 183200 | 100% | 0 | 0 | 0 | 20800 | 3016 | 23816 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Umbrella project for continuation of CFC free-technology in the manufacture of flexible polyurethane foam at Ashanti, Latex Foam, Nsawam and Prestige Foam | Individual | AFR | GHA | FOA | 12 | INV | 07 | A | O | I | CFC | 316 | 304 | 0 | 0 | 1994-03-01 | 1997-12-01 | 1994-12-01 |  | 2000-06-01 | 2001-12-01 | 345000 | -53650 | 291350 | 291350 | 100% | 0 | 0 | 0 | 44850 | -6974 | 37876 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-08-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | GHA | SEV | 20 | INS | 08 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-12-01 | 1999-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1996 | Non-Investment
COM | UNDP | Renewal of the institutional strengthening project | Individual | AFR | GHA | SEV | 26 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 |  | 107000 | -7725 | 99275 | 99275 | 100% | 0 | 0 | 0 | 13910 | -1004 | 12906 | 0 | 0 | Completed in 2000. | [10 empty] | 1998 | Non-Investment
COM | UNDP | Implementation of the RMP: Mobile air conditioning recovery and recycling of CFC-12 | RMP-Component | AFR | GHA | REF | 32 | TAS | 12 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-12-01 |  | 98902 | 0 | 98902 | 98857 | 99.95% | 45 | 0 | 22.5 | 12857 | 0 | 12851.1501 | 5.8499 | 0 | Completed in 2003. | [10 empty] | 2000 | Investment
ONG | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | AFR | GHA | REF | 32 | TAS | 14 | N | O | I | CFC | 4 | 2 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2006-01-01 | 2006-12-01 |  |  | 198000 | 0 | 198000 | 163146 | 82.4% | 34854 | 0 | 12198.9 | 25740 | 0 | 21208.98 | 4531.02 | 0 | Incentive Programme extremely successful, and 34 applications were approved and have been implemented. Further applications are expected. | [10 empty] | 2000 | Non-Investment
COM | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | AFR | GHA | SEV | 32 | INS | 15 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2003-02-01 |  | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 2003. | [10 empty] | 2000 | Non-Investment
ONG | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GHA | REF | 32 | TAS | 16 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-01-01 | 2006-12-01 |  |  | 15455 | 0 | 15455 | 4198 | 27.16% | 11257 | 0 | 3939.95 | 2009 | 0 | 545.6993 | 1463.3007 | 0 | See remark for GHA-14 as activities are jointly implemented. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation in soil fumigation (curcubits) | Individual | AFR | GHA | FUM | 33 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
ONG | UNDP | Training programme for terminal phase-out of methyl bromide use, excluding QPS applications | One-off-Phaseout | AFR | GHA | FUM | 37 | TRA | 18 | N | O | I | MeBr | 6 | 3 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 | 2006-12-01 |  |  | 101550 | 0 | 101550 | 78117 | 76.92% | 23433 | 0 | 8201.55 | 13202 | 0 | 10155.21 | 3046.79 | 0 | MB regs in place. Technical training mission planning for Q2 05 not implemented. Ntl MB Technical Comm and NOU unresponsive to requests for execution and monitoring updates. | [10 empty] | 2002 | Non-Investment
COM | UNDP | Renewal of institutional strengthening (phase 5) | Individual | AFR | GHA | SEV | 38 | INS | 19 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 |  | 139100 | 0 | 139100 | 136693 | 98.27% | 2407 | 0 | 1203.5 | 18083 | 0 | 17770.09 | 312.91 | 0 | Completed in 2004. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GHA | SEV | 43 | INS | 20 | N | T | I | CFC | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2006-07-01 | 2006-07-01 |  |  | 139100 | 0 | 139100 | 107794 | 77.49% | 31306 | 0 | 10957.1 | 10433 | 0 | 8084.9375 | 2348.0625 | 0 | During 2005, the NOU continued its efforts to ensure compliance with Montreal Protocol. In order to ensure successful implementation of projects that contribute to Ghana’s meeting compliance targets, the NOU has continued its coordination efforts through: training workshops for beneficiaries in the refrigeration and MB sectors, and monitoring of sectors in which projects were previously implemented in order to ensure sustainability of phase out efforts. In addition it has continued monitoring of the implementation of Regulations and Fiscal policies on ODS importation and use. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Technical assistance for the CTC sector | Individual | AFR | GHA | SOL | 44 | TAS | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 11907 | 59.54% | 8093 | 0 | 2832.55 | 1800 | 0 | 1071.63 | 728.37 | 0 | Approved in Dec 2004. National expert appointed to carry out survey. Following survey completion, workshop will be conducted by International expert to provide information on options to CTC and MCF for the applications identified. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | GHA | PHA | 47 | PRP | 23 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2250 | 0 | 0 | 2250 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in the Middle East | RMP-Component | GLO | GLO | REF | 06 | TRA | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1992-12-01 |  | 1996-06-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in MAC | RMP-Component | GLO | GLO | REF | 06 | TAS | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1998-01-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in refrigeration sector | RMP-Component | GLO | GLO | REF | 06 | TAS | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1994-02-01 |  | 1994-09-01 | 1997-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in flexible polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in solvents | Individual | GLO | GLO | SOL | 06 | TAS | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in halons | Individual | GLO | GLO | HAL | 06 | TAS | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-01-01 |  | 1994-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Three national policy workshops | Individual | GLO | GLO | SEV | 06 | TRA | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1996-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Two study-tours for officials and industry representatives | Individual | GLO | GLO | SEV | 06 | TRA | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1998-04-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Participation at workshops and key metings | Individual | GLO | GLO | SEV | 06 | TRA | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-10-01 |  | 1995-09-01 | 1997-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in the Middle East | Individual | GLO | GLO | HAL | 06 | TRA | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-02-01 |  | 1993-12-01 | 1997-12-01 | 60000 | -20988 | 39012 | 39012 | 100% | 0 | 0 | 0 | 7800 | -2728 | 5072 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in the Middle East/Africa | Individual | GLO | GLO | FOA | 06 | TRA | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-12-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -14413 | 38087 | 38087 | 100% | 0 | 0 | 0 | 6825 | -1874 | 4951 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial and industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 06 | TRA | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in rigid polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-01-01 |  | 1993-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in aerosol sector | Individual | GLO | GLO | ARS | 06 | TAS | 24 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-02-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Procurement of 40 halon recycling machines for demonstration | Individual | GLO | GLO | HAL | 07 | DEM | 25 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-09-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Global halon project | Individual | GLO | GLO | HAL | 08 | TAS | 27 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1995-10-01 |  | 1997-12-01 | 1999-05-01 | 345133 | 0 | 345133 | 345133 | 100% | 0 | 0 | 0 | 44867 | 0 | 44867 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Global MAC project | RMP-Component | GLO | GLO | REF | 08 | TAS | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1995-10-01 |  | 1995-12-01 | 1997-12-01 | 318584 | 0 | 318584 | 318584 | 100% | 0 | 0 | 0 | 41416 | 0 | 41416 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Safety pre-assessment and post-assessment of foam and solvent projects implemented by UNDP | Individual | GLO | GLO | FOA | 12 | TAS | 63 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 3000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3250 | 390 | 3640 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Analysis and formulation of a halon action plan and phase out strategy for small consuming countries | Individual | GLO | GLO | HAL | 13 | TAS | 69 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Determination of cost-effective phase-out approaches for enterprises with relatively small ODS use in foams | Individual | GLO | GLO | FOA | 14 | TAS | 71 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-09-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Global MACs project: Phase 2 | RMP-Component | GLO | GLO | REF | 18 | TAS | 90 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1997-11-01 |  | 1999-05-01 | 2004-01-01 | 500000 | -1 | 499999 | 499999 | 100% | 0 | 0 | 0 | 65000 | 0 | 65000 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  |  |  | 1999-07-01 | [6 empty] | 1995 | Non-Investment
FIN | UNDP | Preparation of refrigerant management plans (Bahamas, Bangladesh, Botswana, Dominican Republic, El Salvador, Gabon, Mozambique, Niger, Lesotho, Trinidad and Tobago) | Individual | GLO | GLO | REF | 22 | PRP | 133 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 140000 | -2 | 139998 | 139998 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
CLO | UNDP | Advance for project preparation as indicated in the 1998 business plan | Individual | GLO | GLO | SEV | 23 | PRP | 154 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-03-01 |  |  | 1998-03-01 | 256000 | -256000 | 0 | 0 |  | 0 | 0 | 0 | 33280 | -33280 | 0 | 0 | 0 | Canceled in 1998. | [10 empty] | 1998 | Investment
FIN | UNDP | Global MAC project: Phase III | RMP-Component | GLO | GLO | REF | 24 | TAS | 159 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2002-12-01 | 2003-12-01 | 250000 | -63356 | 186644 | 186644 | 100% | 0 | 0 | 0 | 32500 | -8236 | 24264 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
CLO | UNDP | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 176 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-03-01 |  |  | 1999-03-01 | 299000 | -299000 | 0 | 0 |  | 0 | 0 | 0 | 38870 | -38870 | 0 | 0 | 0 | Canceled in 1999. | [10 empty] | 1998 | Investment
CLO | UNDP | Project preparation advance for the year 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 190 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2003-09-01 | 250000 | -250000 | 0 | 0 |  | 0 | 0 | 0 | 32500 | -32500 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 6 projects in the recovery/recycling refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 204 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 6 projects in the end-user commercial refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 205 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
CLO | UNDP | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 227 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2001-12-01 |  |  | 2001-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2001. | [10 empty] | 2001 | Investment
CLO | UNDP | Project preparation advance (2002) | Individual | GLO | GLO | SEV | 35 | PRP | 236 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2002-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2002. | [10 empty] | 2002 | Investment
COM | UNDP | Core Unit Support (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 243 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2003. | [10 empty] | 2002 | Non-Investment
COM | UNDP | Core Unit Support (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 249 | N | O | I | No-ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2004. | [10 empty] | 2003 | Non-Investment
FIN | UNDP | Initial start-up costs | Individual | GLO | GLO | SEV | 04 | TAS | 256 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1991-12-01 |  | 1992-12-01 | 2004-07-01 | 596500 | 0 | 596500 | 596500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1992. Financially completed in 2004. | [10 empty] | 2004 | Investment
COM | UNDP | Core unit (2005) | Individual | GLO | GLO | SEV | 44 | TAS | 259 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2005. Core Unit Operational. | [10 empty] | 2004 | Non-Investment
COM | UNDP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 266 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2005-11-01 |  | 2005-12-01 |  | 122000 | 0 | 122000 | 96439 | 79.05% | 25561 | 0 | 9561 | 9150 | 0 | 7232.925 | 1917.075 | 0 | Completed in 2005. Demonstration projects prepared for Brazil, Colombia, Cuba and regional Caribbean. All 4 approved at ExCom 47. Payments still pending. | [10 empty] | 2005 | Investment
ONG | UNDP | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 271 | N | O | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1700000 | 0 | 0 | 1700000 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Implementation of the RMP: National recovery recycling project | RMP-Component | LAC | GRN | REF | 30 | TAS | 05 | A | O | I | CFC | 1 | 1 | 0 | 0 | 2000-03-01 | 2002-06-01 | 2001-10-01 |  | 2002-12-01 | 2003-11-01 | 33400 | 0 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4342 | 0 | 4342 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | GUA | SEV | 11 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 30000 | 257 | 30257 | 30257 | 100% | 0 | 0 | 0 | 3900 | 34 | 3934 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industria Metalurgica Centroamericana S.A. (Imca) | Individual | LAC | GUA | REF | 15 | INV | 07 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-07-01 | 2000-07-01 | 155017 | -5823 | 149194 | 149194 | 100% | 0 | 0 | 0 | 20152 | -757 | 19395 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Refrigeradores de Guatemala S.A. (Refrigua) | Individual | LAC | GUA | REF | 15 | INV | 08 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1996-10-01 | 1999-12-01 | 194866 | 0 | 194866 | 194866 | 100% | 0 | 0 | 0 | 25333 | 0 | 25333 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1994 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | GUA | REF | 18 | TAS | 09 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-12-01 | 2002-03-01 | 256780 | -19649 | 237131 | 237131 | 100% | 0 | 0 | 0 | 33381 | -2554 | 30827 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | GUA | FOA | 21 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at four enterprises (Exea S.A., Productos American Vitas S.A., Termomecanica S.A., Unirefri S.A.) | Individual | LAC | GUA | REF | 23 | INV | 16 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2002-03-01 | 212000 | -24132 | 187868 | 187868 | 100% | 0 | 0 | 0 | 27560 | -3137 | 24423 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Construservicios, Aplitex, and Fiberglas & Plasticos | Individual | LAC | GUA | FOA | 23 | INV | 17 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 128500 | -15778 | 112722 | 112722 | 100% | 0 | 0 | 0 | 16705 | -2051 | 14654 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Investment
COM | UNDP | Project preparation for the formulation of refrigerant management plan update (investment components) | Individual | AFR | GUI | REF | 42 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Consultant visited and RMP Investment Component approved at 45th ExCom. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: recovery and recycling programme (phase II) | RMP-Component | AFR | GUI | REF | 45 | TAS | 15 | N | O | I | CFC | 5 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 49890 | 0 | 49890 | 0 | 0% | 49890 | 0 | 9978 | 4490 | 0 | 0 | 4490 | 0 | Project signed and Int.cons. recruited. Equipm. Specs prepared. | [10 empty] | 2005 | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | HAI | REF | 36 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially closed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Implementation of the refrigerant management plan: recovery and recycling of CFC-12 refrigerant | RMP-Update | LAC | HAI | REF | 39 | TAS | 04 | A | O | I | CFC | 14 | 0 | 0 | 0 | 2003-04-01 | 2004-07-01 | 2006-04-01 | 2007-12-01 |  |  | 220256 | 0 | 220256 | 17936 | 8.143% | 202320 | 0 | 40464 | 19823 | 0 | 1614.2367 | 18208.7633 | 0 | Ongoing political instability in 05 continued to delay leg-reg adoption + mid-05 mission cancelled due to hurricane. R&R activities stalled as result. Ongoing monitoring (with UNEP) to asses feasibility of moving implementation forward ongoing. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the refrigerant management plan: monitoring the activities in the RMP | RMP-Update | LAC | HAI | REF | 39 | TAS | 06 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 29400 | 0 | 29400 | 0 | 0% | 29400 | 0 | 10290 | 2646 | 0 | 0 | 2646 | 0 | Project may not begin until R&R project under implementation. Ongoing political instability in 05 continued to delay leg-reg adoption + mid-05 mission cancelled due to hurricane. R&R activities stalled as result. Ongoing monitoring (with UNEP) in place. | [10 empty] | 2003 | Non-Investment
COM | UNDP | Preparation of the RMP update proposal | RMP-Update-Comp | LAC | HON | REF | 41 | PRP | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 13000 | 86.67% | 2000 | 0 | 2000 | 1125 | 0 | 975 | 150 | 0 | Completed in 2005. Project submitted and approved at the 44th Excom Meeting. Pending payments to consultant as of December 2004. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: technical assistance programme for the promotion of good practices and recovery and recycling | RMP-Component | LAC | HON | REF | 44 | TAS | 15 | N | O | I | No_ODP | 16 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2008-07-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 30000 | 13500 | 0 | 0 | 13500 | 0 | NOU changed in October. UNDP as coopeating agency provided asistance to NOUs to start activities. Local RMP consultant identified. Mission to start activities was not possible in 2005 due to numerous trips by NOU. Expected mission early 2006. | [10 empty] | 2004 | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection and Ozone Depleting Substances Phase-out Unit | Individual | ASP | IDS | SEV | 10 | INS | 05 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 1997-06-01 | 2003-04-01 | 314780 | 0 | 314780 | 314780 | 100% | 0 | 0 | 0 | 40921 | 0 | 40921 | 0 | 0 | Completed in 1997. Financially completed in 2003. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 11 | PRP | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1994-11-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
CLO | UNDP | Elimination of the use of 111 TCA and CFC-113 in the manufacture of metal and plastic motorcycle parts at PT KGD Indonesia, Inc. | Individual | ASP | IDS | SOL | 15 | INV | 25 | A | O | R | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1996-02-01 |  |  | 1997-05-01 | 88000 | -88000 | 0 | 0 |  | 0 | 0 | 0 | 11440 | -11440 | 0 | 0 | 0 | Canceled in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance in solvent, halon and refrigeration sectors | Individual | ASP | IDS | SEV | 15 | PRP | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-03-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF foam for cold storage at P.T. Fibrindo Carsa Pratama | Individual | ASP | IDS | FOA | 17 | INV | 32 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1995-07-01 | 1997-03-01 | 1996-06-01 |  | 1997-12-01 | 2000-07-01 | 55000 | -5382 | 49618 | 49618 | 100% | 0 | 0 | 0 | 7150 | -700 | 6450 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for coolers/thermoware at P.T. Perdana Merah Delima | Individual | ASP | IDS | FOA | 18 | INV | 34 | A | O | R | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 1999-12-01 | 173000 | -1 | 172999 | 172999 | 100% | 0 | 0 | 0 | 22490 | 0 | 22490 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 18 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Alpine Cool | Individual | ASP | IDS | FOA | 20 | INV | 44 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 84000 | -268 | 83732 | 83732 | 100% | 0 | 0 | 0 | 10920 | -35 | 10885 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at PT Dithon Urethane | Individual | ASP | IDS | FOA | 20 | INV | 46 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-02-01 | 2000-07-01 | 184000 | -295 | 183705 | 183705 | 100% | 0 | 0 | 0 | 23920 | -38 | 23882 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Mentari Metal Pratama | Individual | ASP | IDS | FOA | 20 | INV | 47 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-09-01 |  | 1999-11-01 | 2001-12-01 | 47000 | -693 | 46307 | 46307 | 100% | 0 | 0 | 0 | 6110 | -90 | 6020 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | IDS | REF | 21 | PRP | 53 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at Plysindo Inter Mouldi (PIM) | Individual | ASP | IDS | FOA | 22 | INV | 60 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1997-09-01 | 2001-12-01 | 75870 | -1848 | 74022 | 74022 | 100% | 0 | 0 | 0 | 9863 | -240 | 9623 | 0 | 0 | Completed in 1997. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF insulated products at UD Samrow Foam | Individual | ASP | IDS | FOA | 23 | INV | 63 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-10-01 | 2001-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC -free technology in the manufacture of rigid polyurethane foam (panels, blocks) at PT Aneka Cool Citratama | Individual | ASP | IDS | FOA | 23 | INV | 65 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 232225 | -10678 | 221547 | 221547 | 100% | 0 | 0 | 0 | 30189 | -1388 | 28801 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at C.V. Kulkasindo | Individual | ASP | IDS | REF | 23 | INV | 66 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 136000 | -18594 | 117406 | 117406 | 100% | 0 | 0 | 0 | 17680 | -2417 | 15263 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at PT Dilihan Glory | Individual | ASP | IDS | FOA | 23 | INV | 67 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 102200 | -14362 | 87838 | 87838 | 100% | 0 | 0 | 0 | 13286 | -1867 | 11419 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray foam) at PT Ferrarindo Multi Sarana | Individual | ASP | IDS | FOA | 23 | INV | 68 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-07-01 | 32900 | -316 | 32584 | 32584 | 100% | 0 | 0 | 0 | 4277 | -41 | 4236 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
CLO | UNDP | Conversion to CFC-free techology in the manufacture of rigid PUF insulated thermoware at PT Langgeng Makmur Plastic Industry Ltd. | Individual | ASP | IDS | FOA | 23 | INV | 70 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 142000 | -142000 | 0 | 0 |  | 0 | 0 | 0 | 18460 | -18460 | 0 | 0 | 0 | Canceled in 1999. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded and integral skin PUF at PT Archigramma | Individual | ASP | IDS | FOA | 23 | INV | 71 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 106625 | -14881 | 91744 | 91744 | 100% | 0 | 0 | 0 | 13861 | -1935 | 11926 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IDS | SEV | 23 | INS | 80 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 208650 | -265 | 208385 | 208385 | 100% | 0 | 0 | 0 | 27125 | -34 | 27091 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF spray insulation at Karya Cipta Semesta | Individual | ASP | IDS | FOA | 23 | INV | 81 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-12-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 8840 | 0 | 8840 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded PUF at Ciptaindah Jokindo | Individual | ASP | IDS | FOA | 23 | INV | 82 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 77125 | -58 | 77067 | 77067 | 100% | 0 | 0 | 0 | 10026 | -7 | 10019 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IDS | REF | 24 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | IDS | FOA | 24 | PRP | 84 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray foam) at PT Sentras Varitima | Individual | ASP | IDS | FOA | 25 | INV | 86 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-07-01 | 2000-08-01 |  | 2000-07-01 | 2002-03-01 | 125000 | -5780 | 119220 | 119220 | 100% | 0 | 0 | 0 | 16250 | -751 | 15499 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Supply conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Gaya Teknik | Individual | ASP | IDS | REF | 25 | INV | 88 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-12-01 | 147880 | -2358 | 145522 | 145522 | 100% | 0 | 0 | 0 | 19224 | -306 | 18918 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Converstion to CFC-free technology in the manufacture of rigid polyurethane spray foam at Metal Tunggal Prakarsamandiri | Individual | ASP | IDS | FOA | 25 | INV | 89 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2002-10-01 | 43330 | 0 | 43330 | 43330 | 100% | 0 | 0 | 0 | 5633 | 0 | 5633 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Aneka Froze Citratama | Individual | ASP | IDS | REF | 25 | INV | 90 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 174255 | -17790 | 156465 | 156465 | 100% | 0 | 0 | 0 | 22653 | -2313 | 20340 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Converstion to CFC-free technolgoy in the manufacture of rigid polyurethane spray foam at Karya Sempati Sarana | Individual | ASP | IDS | FOA | 25 | INV | 91 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2004-01-01 | 45550 | 0 | 45550 | 45550 | 100% | 0 | 0 | 0 | 5922 | 0 | 5922 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of CFC-11 and CFC-12/R-502 to HCFC-141b (foam) and HFC-134a/R404a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at P.T. Intermas Pacific | Individual | ASP | IDS | REF | 25 | INV | 92 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 209300 | -20993 | 188307 | 188307 | 100% | 0 | 0 | 0 | 27209 | -2729 | 24480 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at PT Hanaria Indah | Individual | ASP | IDS | FOA | 26 | INV | 93 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 101352 | -18169 | 83183 | 83183 | 100% | 0 | 0 | 0 | 13176 | -2362 | 10814 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated panels at P.T. Panendra Sejati | Individual | ASP | IDS | FOA | 26 | INV | 95 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 156600 | -46830 | 109770 | 109770 | 100% | 0 | 0 | 0 | 20358 | -6088 | 14270 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Indoklima Sarana Engineering | Individual | ASP | IDS | FOA | 26 | INV | 96 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 212193 | -43243 | 168950 | 168950 | 100% | 0 | 0 | 0 | 27585 | -5622 | 21963 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Laksana | Individual | ASP | IDS | FOA | 26 | INV | 97 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-11-01 | 2004-01-01 | 122885 | -3 | 122882 | 122882 | 100% | 0 | 0 | 0 | 15975 | 0 | 15975 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Mekar Armada Jaya | Individual | ASP | IDS | FOA | 26 | INV | 98 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 149357 | -6055 | 143302 | 143302 | 100% | 0 | 0 | 0 | 19416 | -787 | 18629 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Tesaguna Sejati | Individual | ASP | IDS | REF | 26 | INV | 99 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 147900 | 0 | 147900 | 147900 | 100% | 0 | 0 | 0 | 19227 | 0 | 19227 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Trisakti | Individual | ASP | IDS | FOA | 26 | INV | 100 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2003-03-01 | 80037 | -6557 | 73480 | 73480 | 100% | 0 | 0 | 0 | 10405 | -852 | 9553 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Mentari Adi Fayar | Individual | ASP | IDS | FOA | 26 | INV | 101 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-01-01 | 2004-01-01 | 111517 | 0 | 111517 | 111517 | 100% | 0 | 0 | 0 | 14497 | 0 | 14497 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Herry Alter's | Individual | ASP | IDS | REF | 26 | INV | 102 | A | O | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 438060 | -15658 | 422402 | 422402 | 100% | 0 | 0 | 0 | 56948 | -2036 | 54912 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at Irama Sejuk Santosa | Individual | ASP | IDS | FOA | 26 | INV | 103 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 54800 | -4604 | 50196 | 50196 | 100% | 0 | 0 | 0 | 7124 | -599 | 6525 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 3 enterprises: Bali Cool, Centrum Cool and Ever Cool | Individual | ASP | IDS | REF | 26 | INV | 104 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 231800 | -1729 | 230071 | 230071 | 100% | 0 | 0 | 0 | 30134 | -225 | 29909 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, CFC-12 to HFC-134a and R-502 to R-404A technology in the manufacture of commercial refrigeration equipment at PT Algron | Individual | ASP | IDS | REF | 26 | INV | 105 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-11-01 | 158210 | 0 | 158210 | 158210 | 100% | 0 | 0 | 0 | 20567 | 0 | 20567 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated boxes at P.T. Polidaya Fiberindo Indah | Individual | ASP | IDS | FOA | 26 | INV | 106 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 72800 | -8363 | 64437 | 64437 | 100% | 0 | 0 | 0 | 9464 | -1087 | 8377 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam, panels, blocks) at Tansri Gani | Individual | ASP | IDS | FOA | 29 | INV | 112 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2003-03-01 | 2005-09-01 | 354700 | -5045 | 349655 | 349655 | 100% | 0 | 0 | 0 | 46111 | -656 | 45455 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [6 empty] | 2003-07-01 |  |  |  | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based systems and HCFC-141b in the manufacture of polyurethane foam for automotive and furniture applications at P.T. Yoska Prima Inti | Individual | ASP | IDS | FOA | 29 | INV | 114 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 368868 | -221866 | 147002 | 147002 | 100% | 0 | 0 | 0 | 47953 | -28843 | 19110 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Extension of institutional strengthening project (Phase III) | Individual | ASP | IDS | SEV | 32 | INS | 121 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2003-01-01 |  | 2004-09-01 |  | 208650 | 0 | 208650 | 208323 | 99.84% | 327 | 0 | 163.5 | 27125 | 0 | 27082.4892 | 42.5108 | 0 | Completed in 2004. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IDS | REF | 33 | PRP | 123 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 124 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at PT Kemenangan | Individual | ASP | IDS | FOA | 35 | INV | 126 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 104817 | 0 | 104817 | 102719 | 98% | 2098 | 0 | 0 | 13626 | 0 | 13353.2642 | 272.7358 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Nikoteknik | Individual | ASP | IDS | REF | 35 | INV | 131 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 238903 | 0 | 238903 | 219589 | 91.92% | 19314 | 0 | 0 | 31057 | 0 | 28546.2115 | 2510.7885 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Sapporo Mestika | Individual | ASP | IDS | REF | 35 | INV | 132 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 153768 | 0 | 153768 | 149165 | 97.01% | 4603 | 0 | 0 | 19990 | 0 | 19391.6052 | 598.3948 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Hatindo Metal Utama | Individual | ASP | IDS | REF | 35 | INV | 133 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 |  | 145894 | 0 | 145894 | 145894 | 100% | 0 | 0 | 0 | 18966 | 0 | 18966 | 0 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Leoindo Kreasi | Individual | ASP | IDS | REF | 35 | INV | 134 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 119394 | 0 | 119394 | 114556 | 95.95% | 4838 | 0 | 0 | 15521 | 0 | 14892.0689 | 628.9311 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Alfa Metalindo Agra | Individual | ASP | IDS | REF | 35 | INV | 135 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 146960 | 0 | 146960 | 143460 | 97.62% | 3500 | 0 | 0 | 19105 | 0 | 18649.9952 | 455.0048 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Gastro Gizi Sarana | Individual | ASP | IDS | REF | 35 | INV | 136 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 221049 | 0 | 221049 | 214994 | 97.26% | 6055 | 0 | 0 | 28736 | 0 | 27948.8601 | 787.1399 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | IDS | REF | 36 | PRP | 137 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | 0 | 20000 | 17254 | 86.27% | 2746 | 0 | 0 | 2600 | 0 | 2243.02 | 356.98 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | ASP | IDS | REF | 36 | PRP | 138 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 35000 | 0 | 35000 | 29776 | 85.07% | 5224 | 0 | 0 | 4550 | 0 | 3870.88 | 679.12 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (first tranche) | Multi-Year | ASP | IDS | REF | 37 | INV | 148 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-10-01 | 2002-12-01 |  | 2004-12-01 |  | 1288000 | 0 | 1288000 | 1288000 | 100% | 0 | 0 | 0 | 111920 | 0 | 111920 | 0 | 0 | Completed in 2004. | [8 empty] | 2004-12-01 |  | 2002 | Investment | 1141 | 1141 |  |  | Yes | N/A | yes
COM | UNDP | Refrigeration sector phase-out plan: refrigeration servicing | Multi-Year | ASP | IDS | REF | 38 | INV | 151 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2005-12-01 |  | 2196758 | 0 | 2196758 | 1540080 | 70.11% | 656678 | 0 | 656678 | 195708 | 0 | 137204.9068 | 58503.0932 | 0 | Completed. R&R equipment for first batch of 188 servicing established and 60 training establishments delivered in 2004 was installed and commissioned. Training was conducted and COC/HOP signed. Project completed in December 2005. | [10 empty] | 2002 | Investment | 1072 | 1072 |  |  | Yes | N/A | yes
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector ( 2nd tranche) | Multi-Year | ASP | IDS | REF | 40 | INV | 154 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2003-07-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 52900 | 0 | 52900 | 0 | 0 | Completed in 2004. | [10 empty] | 2003 | Investment | 841 | 841 |  |  | Yes | N/A | yes
ONG | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (balance of second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 155 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 | 2006-06-01 |  |  | 1600000 | 0 | 1600000 | 1057558 | 66.1% | 542442 | 2404 | 189854.7 | 141100 | 0 | 93263.3961 | 47836.6039 | 212.0027 | 14 remaining of the 45 first batch enterprises completed the project. Equipment for 34 second batch enterprises were delivered. Verification report shows targets met and approved by ExCom. | [10 empty] | 2003 | Investment | 541 | 541 |  |  | Yes | N/A | yes
ONG | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (servicing) sector (second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 157 | N | O | I | CFC | 200 | 200 | 0 | 0 | 2003-12-01 |  | 2004-12-01 | 2006-12-01 |  |  | 1805987 | 0 | 1805987 | 0 | 0% | 1805987 | 0 | 632095.45 | 160939 | 0 | 0 | 160939 | 0 | Equipment delivered to 59 second batch servicing establishments. 37 end-users identified for pilot retrofit programme. Demonstration equipment provided to 60 additional training establishments | [10 empty] | 2003 | Investment | 872 | 872 |  |  | Yes | N/A | yes
ONG | UNDP | Extension of institutional strengthening project | Individual | ASP | IDS | SEV | 41 | INS | 159 | N | T | I | No-ODP | 22 | 15 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 | 2006-06-01 |  |  | 271245 | 0 | 271245 | 224468 | 82.75% | 46777 | 0 | 16371.95 | 20343 | 0 | 16834.7897 | 3508.2103 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 163 | N | O | I | CFC | 300 | 300 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 1762000 | 0 | 1762000 | 0 | 0% | 1762000 | 0 | 616700 | 156900 | 0 | 0 | 156900 | 0 | 29 of the 34 second batch enterprises completed the project. Activities initiated for the third batch of enterprises endorsed. Over 300 ODP tonnes were phased out in 2005. Verification report approved. Disbursements pending legislation in place. | [10 empty] | 2004 | Investment | 241 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 164 | N | O | I | CFC | 300 | 300 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 | 0 | 175000 | 43400 | 0 | 0 | 43400 | 0 | SPMCU identified servicing establishments assisted by Univ. of Trisakti. 60 additional Masters Trainer trained. NOU and Ministry continue to interact with Min. of Trade to improve existing licensing system. Verification rep apprvd. Disb pending legisl. | [10 empty] | 2004 | Investment | 572 |  |  |  | Latest | Latest | Latest
ONG | UNDP | National strategy for phasing out the use of CFC in the aerosol: conversion from CFC to hydrocarbon aerosol propellants at P.T Yulia | Individual | ASP | IDS | ARS | 44 | INV | 167 | N | O | I | CFC | 80 | 40 | 0 | 0 | 2004-12-01 | 2005-11-01 | 2005-12-01 | 2006-06-01 |  |  | 224000 | 0 | 224000 | 125076 | 55.84% | 98924 | 0 | 34623.4 | 13440 | 0 | 7504.56 | 5935.44 | 0 | Project activities initiated, Retroactive activities evaluated and remaining actions discussed with enterprises and procurement action initiated | [10 empty] | 2004 | Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IDS | SEV | 45 | TAS | 169 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 114679 | 0 | 114679 | 0 | 0% | 114679 | 0 | 40137.65 | 10321 | 0 | 0 | 10321 | 0 | TORs for national and intl consultants defined for recruitment. Surveys and data collection to be initiated 1Q 2006 under supervision and guidance of national consultant | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IDS | SEV | 47 | INS | 171 | N | T | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 271245 | 0 | 271245 | 0 | 0% | 271245 | 0 | 54249 | 20343 | 0 | 0 | 20343 | 0 | The Ozone Unit continued its effort in the supervision and management of timely and effective implementation of NPP and individual projects, working in close coordination with IAs. Intensive efforts were spent in policy formulation and enforcement, including special attention and effort to coordinate with Ministry of Trade in revising existing licensing system for effective control and monitoring of ODS supplies. The Beijing and Montreal Amendments were ratified in 2005. Public awareness activities, stakeholders workshops and a Regional International Ozone Day were organized to promote and ensure sustainability of ODS phase-out. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Assistance in project preparation in all sectors | Individual | ASP | IND | SEV | 08 | PRP | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 100000 | -18339 | 81661 | 81661 | 100% | 0 | 0 | 0 | 13000 | -2384 | 10616 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IND | SEV | 08 | INS | 02 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-06-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 430600 | -1671 | 428929 | 428929 | 100% | 0 | 0 | 0 | 55978 | -217 | 55761 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IND | SEV | 09 | CPG | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1993-11-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Survey of ODS use in the small scale (including tiny) and informal sectors, data base generation and ODS transition management planning | Individual | ASP | IND | SEV | 11 | TAS | 11 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-11-01 | 1994-05-01 |  | 1996-12-01 | 2001-12-01 | 120000 | -11230 | 108770 | 108770 | 100% | 0 | 0 | 0 | 15600 | -1460 | 14140 | 0 | 0 | Completed in 1996. Financially completed in 2001. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of extruded polyethylene foam sheet at Camphor and Allied Products Ltd. | Individual | ASP | IND | FOA | 12 | INV | 16 | A | O | R | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1995-12-01 | 1994-09-01 |  | 1995-12-01 | 1997-12-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF panels at Sunpra Ltd. | Individual | ASP | IND | FOA | 12 | INV | 17 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 414000 | -43773 | 370227 | 370227 | 100% | 0 | 0 | 0 | 53820 | -5690 | 48130 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Eagle Flasks Industries Ltd. | Individual | ASP | IND | FOA | 12 | INV | 18 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1995-03-01 |  | 1996-09-01 | 2000-12-01 | 365000 | -3745 | 361255 | 361255 | 100% | 0 | 0 | 0 | 47450 | -487 | 46963 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 12 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of phenolic foam at Bakelite Hylam Ltd. | Individual | ASP | IND | FOA | 13 | INV | 27 | A | O | I | CFC | 58 | 58 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1998-11-01 | 1999-12-01 | 367000 | 0 | 367000 | 367000 | 100% | 0 | 0 | 0 | 47710 | 0 | 47710 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1994 | Investment
FIN | UNDP | Demonstration and evaluation of alternative technology for halon fire protection system and technical assistance for sectoral strategy for ODS phase out | Individual | ASP | IND | HAL | 13 | DEM | 28 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-01 | 1997-07-01 |  | 1999-12-01 | 2003-02-01 | 309000 | -44111 | 264889 | 264889 | 100% | 0 | 0 | 0 | 40170 | -5734 | 34436 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-06-01 | [6 empty] | 1994 | Non-Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | IND | FOA | 13 | TAS | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1998-07-01 | 1995-07-01 |  | 1999-12-01 | 2003-05-01 | 200000 | -1396 | 198604 | 198604 | 100% | 0 | 0 | 0 | 26000 | -182 | 25818 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non-Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of polyurethane foam at U-Foam Private Ltd. | Individual | ASP | IND | FOA | 13 | INV | 30 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1997-11-01 | 2000-12-01 | 328500 | -77822 | 250678 | 250678 | 100% | 0 | 0 | 0 | 42705 | -10117 | 32588 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 18 | PRP | 67 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 19 | DEM | 69 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-09-01 | 1997-06-01 |  | 2001-11-01 | 2002-03-01 | 0 | 168783 | 168783 | 168783 | 100% | 0 | 0 | 0 | 0 | 21942 | 21942 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  |  | 1998-04-01 | [7 empty] | 1996 | Non-Investment
CLO | UNDP | Phase out of CFCs in the manufacture of cold cured molded PUF products at Autofit P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 70 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 103125 | -103125 | 0 | 0 |  | 0 | 0 | 0 | 13406 | -13406 | 0 | 0 | 0 | Canceled in 1998. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plastic Products | Individual | ASP | IND | FOA | 19 | INV | 71 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2000-12-01 | 2002-03-01 | 96000 | -889 | 95111 | 95111 | 100% | 0 | 0 | 0 | 12480 | -116 | 12364 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-06-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products in Inalsa Ltd. | Individual | ASP | IND | FOA | 19 | INV | 72 | A | O | I | CFC | 29 | 29 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2000-12-01 | 123000 | -4222 | 118778 | 118778 | 100% | 0 | 0 | 0 | 15990 | -549 | 15441 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products at Omkar PUF Insulation | Individual | ASP | IND | FOA | 19 | INV | 73 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 59000 | -151 | 58849 | 58849 | 100% | 0 | 0 | 0 | 7670 | -20 | 7650 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of cold cured molded and integral skin PUF products at Kaygee Foams P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 74 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 217250 | -1198 | 216052 | 216052 | 100% | 0 | 0 | 0 | 28243 | -156 | 28087 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Mahavir Enterprises | Individual | ASP | IND | FOA | 19 | INV | 75 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 2000-08-01 | 2001-12-01 | 94500 | -220 | 94280 | 94280 | 100% | 0 | 0 | 0 | 12285 | -28 | 12257 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-07-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Phase out of the CFCs in the manufacture of cold cured molded and integral skin PUF products at Preto Foams | Individual | ASP | IND | FOA | 19 | INV | 76 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-11-01 | 2000-12-01 | 167100 | -17268 | 149832 | 149832 | 100% | 0 | 0 | 0 | 21723 | -2245 | 19478 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF insulated thermoware at Asha Handicrafts (formerly Asian Advertisers) | Individual | ASP | IND | FOA | 19 | INV | 78 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 122500 | -6656 | 115844 | 115844 | 100% | 0 | 0 | 0 | 15925 | -865 | 15060 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured and integral skin PUF moldings at Amit Polyseats Ltd. | Individual | ASP | IND | FOA | 19 | INV | 79 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1996-05-01 | 1996-10-01 | 1997-11-01 |  | 1997-06-01 | 2000-07-01 | 243000 | -28744 | 214256 | 214256 | 100% | 0 | 0 | 0 | 31590 | -3737 | 27853 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF spray insulation at Beardsell Ltd. | Individual | ASP | IND | FOA | 19 | INV | 80 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1996-05-01 | 2000-05-01 | 1997-11-01 |  | 2000-11-01 | 2002-03-01 | 129000 | -19305 | 109695 | 109695 | 100% | 0 | 0 | 0 | 16770 | -2510 | 14260 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF products at Lloyd Insulations and Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 81 | A | O | I | CFC | 77 | 77 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-09-01 | 2000-12-01 | 500000 | -35883 | 464117 | 464117 | 100% | 0 | 0 | 0 | 65000 | -4665 | 60335 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Meenakshi Polymers Pvt. Ltd. | Individual | ASP | IND | FOA | 19 | INV | 82 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1996-11-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 214000 | -38836 | 175164 | 175164 | 100% | 0 | 0 | 0 | 27820 | -5049 | 22771 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Punjab Scooters Ltd. | Individual | ASP | IND | FOA | 19 | INV | 83 | A | O | I | CFC | 39 | 39 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 312200 | -23972 | 288228 | 288228 | 100% | 0 | 0 | 0 | 40586 | -3116 | 37470 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Amar Enterprises | Individual | ASP | IND | FOA | 20 | INV | 96 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 120000 | -57 | 119943 | 119943 | 100% | 0 | 0 | 0 | 15600 | -7 | 15593 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plast | Individual | ASP | IND | FOA | 20 | INV | 97 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 71000 | -104 | 70896 | 70896 | 100% | 0 | 0 | 0 | 9230 | -13 | 9217 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Cottage Industries | Individual | ASP | IND | FOA | 20 | INV | 98 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 61000 | -2047 | 58953 | 58953 | 100% | 0 | 0 | 0 | 7930 | -266 | 7664 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at K.B. Poly Industries P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 99 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 149000 | -19595 | 129405 | 129405 | 100% | 0 | 0 | 0 | 19370 | -2547 | 16823 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Deccan Engineering Enterprises | Individual | ASP | IND | FOA | 20 | INV | 100 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 64000 | -3303 | 60697 | 60697 | 100% | 0 | 0 | 0 | 8320 | -429 | 7891 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of EPE foam products at Vora Cork Industries | Individual | ASP | IND | FOA | 20 | INV | 101 | A | O | I | CFC | 40 | 40 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 2003-07-01 | 2005-09-01 | 264500 | -52153 | 212347 | 212347 | 100% | 0 | 0 | 0 | 34385 | -6780 | 27605 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  |  |  | 1999-09-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Best Plastronics P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 102 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 129000 | -35002 | 93998 | 93998 | 100% | 0 | 0 | 0 | 16770 | -4550 | 12220 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at Krishna Fabrications Ltd. | Individual | ASP | IND | FOA | 20 | INV | 103 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 164000 | -21543 | 142457 | 142457 | 100% | 0 | 0 | 0 | 21320 | -2801 | 18519 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Institutional strengthening project for the phaseout of ODSs under the Montreal Protocol: Phase II | Individual | ASP | IND | SEV | 20 | INS | 107 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1999-03-01 | 1999-12-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 1999. Financially completed in 1999. | [10 empty] | 1996 | Non-Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | IND | SEV | 21 | PRP | 109 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-11-01 | 2000-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam chemical systems at Polymermann (Asia) P.Ltd. | Individual | ASP | IND | FOA | 22 | INV | 111 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2003-11-01 | 385000 | -4930 | 380070 | 380070 | 100% | 0 | 0 | 0 | 50050 | -641 | 49409 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-07-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Ultra Tech Specialty Chemicals Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 115 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-09-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Texas Enterprises aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 117 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 70000 | -4903 | 65097 | 65097 | 100% | 0 | 0 | 0 | 9100 | -637 | 8463 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Aerol Formulations aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 118 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -791 | 68659 | 68659 | 100% | 0 | 0 | 0 | 9029 | -103 | 8926 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Blowkings | Individual | ASP | IND | FOA | 22 | INV | 128 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 132000 | -14394 | 117606 | 117606 | 100% | 0 | 0 | 0 | 17160 | -1871 | 15289 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | ASP | IND | SEV | 22 | PRP | 129 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Delta Foams Engineering Co. | Individual | ASP | IND | FOA | 22 | INV | 130 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 2001-12-01 | 85000 | -15226 | 69774 | 69774 | 100% | 0 | 0 | 0 | 11050 | -1979 | 9071 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Super Urethane Products P. Ltd. | Individual | ASP | IND | FOA | 22 | INV | 132 | A | O | I | CFC | 39 | 39 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 284000 | -36532 | 247468 | 247468 | 100% | 0 | 0 | 0 | 36920 | -4749 | 32171 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam in small and medium-sized enterprises (SMEs) | Individual | ASP | IND | FOA | 22 | INV | 133 | A | O | I | CFC | 290 | 290 | 0 | 0 | 1997-05-01 | 1997-12-01 | 2000-06-01 |  | 2001-12-01 | 2003-03-01 | 1404000 | -79 | 1403921 | 1403921 | 100% | 0 | 0 | 0 | 182520 | -10 | 182510 | 0 | 0 | Completed in 2001. Financially completed in 2003. Issues resolved in 2005. |  |  |  | 2000-06-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Aerosols D'Asia Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 135 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -2379 | 67071 | 67071 | 100% | 0 | 0 | 0 | 9029 | -309 | 8720 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Asian Aerosols Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 136 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 90890 | -7767 | 83123 | 83123 | 100% | 0 | 0 | 0 | 11816 | -1010 | 10806 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Aero Pack Products aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 138 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-04-01 | 69450 | 0 | 69450 | 69450 | 100% | 0 | 0 | 0 | 9029 | 0 | 9029 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-09-01 | [6 empty] | 1997 | Investment
CLO | UNDP | Meenakshi aerosol and cosmetics conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 140 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1998-06-01 |  |  | 1998-07-01 | 98940 | -98940 | 0 | 0 |  | 0 | 0 | 0 | 12862 | -12862 | 0 | 0 | 0 | Canceled in 1998. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Nissan Thermoware P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 143 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 111000 | -706 | 110294 | 110294 | 100% | 0 | 0 | 0 | 14430 | -92 | 14338 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Viral Corporation | Individual | ASP | IND | FOA | 23 | INV | 146 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 84000 | -2736 | 81264 | 81264 | 100% | 0 | 0 | 0 | 10920 | -356 | 10564 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible moulded cold-cured and integral skin PU foam at Venus Auto P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 147 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 137250 | -1155 | 136095 | 136095 | 100% | 0 | 0 | 0 | 17843 | -150 | 17693 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at Siddhi Polymer P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 148 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 75250 | -737 | 74513 | 74513 | 100% | 0 | 0 | 0 | 9783 | -96 | 9687 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured moulded and integral skin at Shri Krishna Polyurethane Industries P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 149 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-08-01 | 2002-11-01 | 192875 | -486 | 192389 | 192389 | 100% | 0 | 0 | 0 | 25074 | -63 | 25011 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Reliable Rotomoulders P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 150 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 63000 | -769 | 62231 | 62231 | 100% | 0 | 0 | 0 | 8190 | -100 | 8090 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Panna International | Individual | ASP | IND | FOA | 23 | INV | 151 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1998-12-01 | 2000-12-01 | 48000 | -19370 | 28630 | 28630 | 100% | 0 | 0 | 0 | 6240 | -2518 | 3722 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Malanpur Entech P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 153 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 148000 | -12388 | 135612 | 135612 | 100% | 0 | 0 | 0 | 19240 | -1610 | 17630 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of integral skin PUF products at Legend Interiors | Individual | ASP | IND | FOA | 23 | INV | 154 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 124000 | -14125 | 109875 | 109875 | 100% | 0 | 0 | 0 | 16120 | -1836 | 14284 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at K. J. Polymers P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 155 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 127550 | -353 | 127197 | 127197 | 100% | 0 | 0 | 0 | 16582 | -46 | 16536 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bluplast Corporation | Individual | ASP | IND | FOA | 23 | INV | 156 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Alaska Industries | Individual | ASP | IND | FOA | 23 | INV | 157 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 128000 | -18370 | 109630 | 109630 | 100% | 0 | 0 | 0 | 16640 | -2388 | 14252 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at Ras Polybuild Products P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 158 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 128000 | -136 | 127864 | 127864 | 100% | 0 | 0 | 0 | 16640 | -18 | 16622 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 3 projects in the aerosol sector | Individual | ASP | IND | ARS | 24 | PRP | 161 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-06-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Steelage Industries Limited Minimax Division/ Chennai | Individual | ASP | IND | HAL | 24 | INV | 163 | A | O | I | Halon | 116 | 116 | 0 | 0 | 1998-03-01 | 2000-05-01 | 2000-04-01 |  | 2002-01-01 | 2003-04-01 | 131915 | -41454 | 90461 | 90461 | 100% | 0 | 0 | 0 | 17149 | -5389 | 11760 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation to prepare 10 projects in the foam sector | Individual | ASP | IND | FOA | 24 | PRP | 164 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vijay Fire Protection Systems Ltd. | Individual | ASP | IND | HAL | 24 | INV | 165 | A | O | I | Halon | 292 | 292 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 219152 | 0 | 219152 | 219152 | 100% | 0 | 0 | 0 | 28490 | 0 | 28490 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 5 halon extinguisher projects | Individual | ASP | IND | HAL | 24 | PRP | 166 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Sunder Chemical | Individual | ASP | IND | ARS | 24 | INV | 167 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 59892 | -3617 | 56275 | 56275 | 100% | 0 | 0 | 0 | 7786 | -470 | 7316 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Nitin Fire Protection Industries Ltd., Bombay | Individual | ASP | IND | HAL | 24 | INV | 168 | A | O | I | Halon | 212 | 212 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 165818 | 0 | 165818 | 165818 | 100% | 0 | 0 | 0 | 21556 | 0 | 21556 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IND | REF | 24 | PRP | 169 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of production halon-1211 fire extinguishers at Atkins, New Delhi | Individual | ASP | IND | HAL | 24 | INV | 170 | A | O | I | Halon | 37 | 37 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2001-05-01 | 2002-03-01 | 54760 | -739 | 54021 | 54021 | 100% | 0 | 0 | 0 | 7119 | -96 | 7023 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Sara-Chem Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 171 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 89164 | -29723 | 59441 | 59441 | 100% | 0 | 0 | 0 | 11591 | -3864 | 7727 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Maja Cosmetics Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 172 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 125240 | -705 | 124535 | 124535 | 100% | 0 | 0 | 0 | 16281 | -92 | 16189 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Spray Products | Individual | ASP | IND | ARS | 24 | INV | 173 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 65486 | -2975 | 62511 | 62511 | 100% | 0 | 0 | 0 | 8513 | -387 | 8126 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Chem-Verse Consultants | Individual | ASP | IND | ARS | 24 | INV | 174 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 67324 | -1872 | 65452 | 65452 | 100% | 0 | 0 | 0 | 8752 | -243 | 8509 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at New Age Industries, Bombay | Individual | ASP | IND | HAL | 24 | INV | 175 | A | O | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 132248 | -292 | 131956 | 131956 | 100% | 0 | 0 | 0 | 17192 | -38 | 17154 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vimal Industrial Safety Equipment Corporation Baroda, Gujrat | Individual | ASP | IND | HAL | 24 | INV | 176 | A | O | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 186152 | 0 | 186152 | 186152 | 100% | 0 | 0 | 0 | 24200 | 0 | 24200 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Ashoka Engineering Co., New Delhi | Individual | ASP | IND | HAL | 24 | INV | 177 | A | O | I | Halon | 34 | 34 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 50320 | 0 | 50320 | 50320 | 100% | 0 | 0 | 0 | 6542 | 0 | 6542 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Aerosol Conversion at Midas Care Pharmaceuticals | Individual | ASP | IND | ARS | 24 | INV | 179 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 110880 | -2729 | 108151 | 108151 | 100% | 0 | 0 | 0 | 14414 | -355 | 14059 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam at Puff Insulators | Individual | ASP | IND | FOA | 26 | INV | 184 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-11-01 | 2002-03-01 | 83150 | 0 | 83150 | 83150 | 100% | 0 | 0 | 0 | 10810 | 0 | 10810 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and integral skin foam products to water blown systems in flexible molded polyurethane foam at Joti Foam Pr | Individual | ASP | IND | FOA | 26 | INV | 185 | A | O | I | CFC | 38 | 38 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 174290 | -287 | 174003 | 174003 | 100% | 0 | 0 | 0 | 22658 | -37 | 22621 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated termoware at Jaypee Technoplast P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 186 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 139860 | -966 | 138894 | 138894 | 100% | 0 | 0 | 0 | 18182 | -126 | 18056 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Sintex Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 187 | A | O | D | CFC | 11 | 11 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-11-01 | 2003-04-01 | 62980 | -1589 | 61391 | 61391 | 100% | 0 | 0 | 0 | 8187 | -207 | 7980 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at National Flask Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 188 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-08-01 | 2002-03-01 | 203870 | -16186 | 187684 | 187684 | 100% | 0 | 0 | 0 | 26503 | -2104 | 24399 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at Jayson Industries | Individual | ASP | IND | FOA | 26 | INV | 189 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 88900 | -840 | 88060 | 88060 | 100% | 0 | 0 | 0 | 11557 | -109 | 11448 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC -141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Duab International | Individual | ASP | IND | FOA | 26 | INV | 190 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-12-01 | 2001-12-01 | 104490 | 0 | 104490 | 104490 | 100% | 0 | 0 | 0 | 13584 | 0 | 13584 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Galaxy FRP P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 192 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 144808 | -1805 | 143003 | 143003 | 100% | 0 | 0 | 0 | 18825 | -235 | 18590 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam insulated thermoware at Ajay Corrugating and Plastics P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 193 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 80805 | 0 | 80805 | 80805 | 100% | 0 | 0 | 0 | 10505 | 0 | 10505 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of ten projects in general foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 194 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam in situ and spray insulation at P.K. Construction Co. | Individual | ASP | IND | FOA | 27 | INV | 196 | A | O | D | CFC | 11 | 11 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 1999-12-01 | 2001-12-01 | 74172 | -3275 | 70897 | 70897 | 100% | 0 | 0 | 0 | 9642 | -426 | 9216 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ganga Thermoware | Individual | ASP | IND | FOA | 27 | INV | 197 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 78864 | -5388 | 73476 | 73476 | 100% | 0 | 0 | 0 | 10252 | -700 | 9552 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bansal Plastic Industries | Individual | ASP | IND | FOA | 27 | INV | 198 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 68829 | -6240 | 62589 | 62589 | 100% | 0 | 0 | 0 | 8948 | -811 | 8137 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Renewal of Institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol : Phase 3 | Individual | ASP | IND | SEV | 27 | INS | 199 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2001-04-01 |  | 2001-08-01 | 2002-01-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Non-Investment
FIN | UNDP | Preparation of five projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 27 | PRP | 200 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of two projects in aerosol sector | Individual | ASP | IND | ARS | 27 | PRP | 201 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Baba Insulator | Individual | ASP | IND | FOA | 27 | INV | 202 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 59096 | -10468 | 48628 | 48628 | 100% | 0 | 0 | 0 | 7682 | -1361 | 6321 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at R.S. Insulators | Individual | ASP | IND | FOA | 27 | INV | 205 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 54800 | -10912 | 43888 | 43888 | 100% | 0 | 0 | 0 | 7124 | -1419 | 5705 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of seven projects in rigid foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 206 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Shree Nath Plastics | Individual | ASP | IND | FOA | 27 | INV | 207 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 61370 | -7114 | 54256 | 54256 | 100% | 0 | 0 | 0 | 7978 | -925 | 7053 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Cascade Counsel Ltd. New Delhi | Individual | ASP | IND | HAL | 28 | INV | 208 | A | O | I | Halon | 54 | 54 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79920 | 0 | 79920 | 79920 | 100% | 0 | 0 | 0 | 10390 | 0 | 10390 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Bharat Engineering Works, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 209 | A | O | I | Halon | 50 | 50 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 73260 | -7751 | 65509 | 65509 | 100% | 0 | 0 | 0 | 9524 | -1008 | 8516 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Varivar Plast Products P., Ltd. | Individual | ASP | IND | FOA | 28 | INV | 210 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 96184 | -1 | 96183 | 96183 | 100% | 0 | 0 | 0 | 12504 | 0 | 12504 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Supertek International | Individual | ASP | IND | FOA | 28 | INV | 211 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 83202 | 0 | 83202 | 83202 | 100% | 0 | 0 | 0 | 10816 | 0 | 10816 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Standard Electric Appliances | Individual | ASP | IND | FOA | 28 | INV | 212 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 78136 | 0 | 78136 | 78136 | 100% | 0 | 0 | 0 | 10158 | 0 | 10158 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC at Vimsons Aerosol by substituting with HAPs | Individual | ASP | IND | ARS | 28 | INV | 213 | A | O | I | CTC/CFC | 18 | 18 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-03-01 | 2002-11-01 | 66500 | -18505 | 47995 | 47995 | 100% | 0 | 0 | 0 | 8645 | -2406 | 6239 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at O.K. Industries | Individual | ASP | IND | FOA | 28 | INV | 214 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 66227 | -2012 | 64215 | 64215 | 100% | 0 | 0 | 0 | 8610 | -262 | 8348 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Primrose Multiplast P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 215 | A | O | D | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 117105 | -1131 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15224 | -147 | 15077 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Zenith Fire Services, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 216 | A | O | I | Halon | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 53280 | -3309 | 49971 | 49971 | 100% | 0 | 0 | 0 | 6926 | -430 | 6496 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to CFC-free technology in the manufacture of rigid polyurethane foam chemical systems at Shivathene Linopack | Individual | ASP | IND | FOA | 28 | INV | 218 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 209000 | -16227 | 192773 | 192773 | 100% | 0 | 0 | 0 | 27170 | -2110 | 25060 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Devisons P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 219 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 114940 | -5215 | 109725 | 109725 | 100% | 0 | 0 | 0 | 14942 | -678 | 14264 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Extinguisher production and elimination of its consumption of virgin halon-1301 at New Fire Engineers Pvt. Ltd. Mumbai | Individual | ASP | IND | HAL | 28 | INV | 220 | A | O | I | Halon | 120 | 120 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
COM | UNDP | Phaseout of CFC by substituting HAPs at Syncaps | Individual | ASP | IND | ARS | 28 | INV | 221 | A | O | I | CFC | 54 | 54 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2005-09-01 |  | 161518 | 0 | 161518 | 146248 | 90.55% | 15270 | 0 | 7635 | 20997 | 0 | 19011.9321 | 1985.0679 | 0 | Completed in 2005. Local works finally completed, crimper situation resolved, equipment now operating smoothly | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher to ABC powder and CO2 units together with the use of recycled halon-1301 in lieu of virgin product at Standard Castings Pvt. Ltd. New Delhi, under the name of Pyrosafety | Individual | ASP | IND | HAL | 28 | INV | 222 | A | O | I | Halon | 64 | 64 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-11-01 | 92000 | -23084 | 68916 | 68916 | 100% | 0 | 0 | 0 | 11960 | -3001 | 8959 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Nav Texfeb P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 224 | A | O | I | CFC | 32 | 32 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 163982 | -3561 | 160421 | 160421 | 100% | 0 | 0 | 0 | 21318 | -463 | 20855 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at N.D. Plastics | Individual | ASP | IND | FOA | 28 | INV | 226 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2001-12-01 | 101289 | -802 | 100487 | 100487 | 100% | 0 | 0 | 0 | 13168 | -104 | 13064 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC by substituting with HAPs at Ruby Aerosols | Individual | ASP | IND | ARS | 28 | INV | 227 | A | O | I | CTC/CFC | 22 | 22 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2002-01-01 | 2005-11-01 | 45800 | 0 | 45800 | 45784 | 99.97% | 16 | 0 | 0 | 5954 | 0 | 5951.92 | 2.08 | 0 | Completed in 2002. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ashoka Metals | Individual | ASP | IND | FOA | 28 | INV | 228 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2002-03-01 | 68066 | -1587 | 66479 | 66479 | 100% | 0 | 0 | 0 | 8849 | -206 | 8643 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 28 small and medium-sized enterprises | Individual | ASP | IND | FOA | 28 | INV | 229 | A | O | I | CFC | 106 | 106 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2002-12-01 | 2005-09-01 | 699139 | -39114 | 660025 | 660025 | 100% | 0 | 0 | 0 | 86905 | -4862 | 82043 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Tokyo Plast International, Ltd. | Individual | ASP | IND | FOA | 29 | INV | 231 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-06-01 | 2003-11-01 | 196394 | -37676 | 158718 | 158718 | 100% | 0 | 0 | 0 | 25531 | -4898 | 20633 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Santech Industries | Individual | ASP | IND | FOA | 29 | INV | 232 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 115101 | -9 | 115092 | 115092 | 100% | 0 | 0 | 0 | 14963 | -2 | 14961 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Saddle Poly Products P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 233 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 119087 | -44 | 119043 | 119043 | 100% | 0 | 0 | 0 | 15481 | -6 | 15475 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Coolwels Automobile Engineers | Individual | ASP | IND | FOA | 29 | INV | 234 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 133221 | -669 | 132552 | 132552 | 100% | 0 | 0 | 0 | 17319 | -87 | 17232 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Mayur Jugs P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 235 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 119412 | -16905 | 102507 | 102507 | 100% | 0 | 0 | 0 | 15524 | -2198 | 13326 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Premium Mouldings and Pressings P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 236 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 138432 | -87 | 138345 | 138345 | 100% | 0 | 0 | 0 | 17996 | -11 | 17985 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crystal Electronics and Plastics | Individual | ASP | IND | FOA | 29 | INV | 237 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 123343 | -20723 | 102620 | 102620 | 100% | 0 | 0 | 0 | 16035 | -2695 | 13340 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at National Plastics | Individual | ASP | IND | FOA | 29 | INV | 239 | A | O | I | CFC | 36 | 36 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 212481 | -39605 | 172876 | 172876 | 100% | 0 | 0 | 0 | 27623 | -5149 | 22474 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Reactive Polymers Ltd. | Individual | ASP | IND | FOA | 29 | INV | 240 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 354175 | -56621 | 297554 | 297554 | 100% | 0 | 0 | 0 | 46043 | -7361 | 38682 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Jaiswal Industries | Individual | ASP | IND | FOA | 29 | INV | 241 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 152070 | -14822 | 137248 | 137248 | 100% | 0 | 0 | 0 | 19769 | -1927 | 17842 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 24 SMEs | Individual | ASP | IND | FOA | 29 | INV | 242 | A | O | I | CFC | 98 | 98 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2003-04-01 |  | 886584 | -109386 | 777198 | 758919 | 97.65% | 18279 | 0 | 9139.5 | 107524 | -6489 | 98658.7474 | 2376.2526 | 0 | Completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | Individual | ASP | IND | HAL | 29 | TAS | 243 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2002-12-01 |  | 2005-12-01 |  | 88000 | 0 | 88000 | 80647 | 91.64% | 7353 | 0 | 3676.5 | 11440 | 0 | 10484.11 | 955.89 | 0 | Completed in 2005. Workshops held in Sept. 05. Standards approved and published | [10 empty] | 1999 | Non-Investment
COM | UNDP | Technical assistance for safety and technical programme to assist SME's manufacturing aerosol products (Phase I) | Individual | ASP | IND | ARS | 29 | TAS | 244 | A | O | I | CFC | 125 | 125 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2004-09-01 |  | 155000 | 0 | 155000 | 138463 | 89.33% | 16537 | 0 | 8268.5 | 20150 | 0 | 18000.19 | 2149.81 | 0 | Completed in 2004. | [10 empty] | 1999 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Delite Foam and Polymers | Individual | ASP | IND | FOA | 29 | INV | 245 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 188832 | -2784 | 186048 | 186048 | 100% | 0 | 0 | 0 | 24548 | -362 | 24186 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Harjas Plastic and Metal Components P. Ltd. | Individual | ASP | IND | FOA | 29 | INV | 246 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-05-01 | 2003-07-01 | 246386 | -30539 | 215847 | 215847 | 100% | 0 | 0 | 0 | 32030 | -3970 | 28060 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of 6 projects in the integral skin foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 250 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of an umbrella project in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 251 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 252 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
CLO | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 30 | PRP | 254 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at M/s Kooverji Devshi and Co. Pvt. Ltd., Mumbai | Individual | ASP | IND | HAL | 28 | INV | 256 | A | O | I | Halon | 26 | 26 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-05-01 | 2002-03-01 | 37740 | 0 | 37740 | 37740 | 100% | 0 | 0 | 0 | 4906 | 0 | 4906 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Fedders Lloyd Corporation Ltd. | Individual | ASP | IND | REF | 31 | INV | 257 | A | O | I | CFC | 21 | 21 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 257428 | -2616 | 254812 | 254812 | 100% | 0 | 0 | 0 | 33466 | -340 | 33126 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ramakrishna Moulders | Individual | ASP | IND | FOA | 31 | INV | 258 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-12-01 | 2003-04-01 | 78479 | -1311 | 77168 | 77168 | 100% | 0 | 0 | 0 | 10202 | -170 | 10032 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at M-Plast | Individual | ASP | IND | FOA | 31 | INV | 259 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 93279 | -451 | 92828 | 92828 | 100% | 0 | 0 | 0 | 12126 | -59 | 12067 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Naorang Plast | Individual | ASP | IND | FOA | 31 | INV | 260 | A | O | I | CFC | 14 | 14 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 53171 | -563 | 52608 | 52608 | 100% | 0 | 0 | 0 | 6912 | -73 | 6839 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Sanjay Industries | Individual | ASP | IND | FOA | 31 | INV | 261 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 99277 | -2381 | 96896 | 96896 | 100% | 0 | 0 | 0 | 12906 | -310 | 12596 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crown Industries | Individual | ASP | IND | FOA | 31 | INV | 263 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 113110 | -4382 | 108728 | 108728 | 100% | 0 | 0 | 0 | 14704 | -570 | 14134 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at sixteen enterprises | Individual | ASP | IND | FOA | 31 | INV | 267 | A | O | I | CFC | 211 | 211 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 1094567 | -75293 | 1019274 | 1019274 | 100% | 0 | 0 | 0 | 130402 | -8282 | 122120 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Enertech Engineering P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 268 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2004-01-01 | 123109 | -86 | 123023 | 123023 | 100% | 0 | 0 | 0 | 16004 | -11 | 15993 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Raipur Agencies | Individual | ASP | IND | FOA | 31 | INV | 269 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 144567 | -2814 | 141753 | 141753 | 100% | 0 | 0 | 0 | 18794 | -366 | 18428 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pyarelal Coir Products Ltd. | Individual | ASP | IND | FOA | 31 | INV | 270 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 167381 | -2886 | 164495 | 164495 | 100% | 0 | 0 | 0 | 21760 | -375 | 21385 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at R.H. Industries | Individual | ASP | IND | FOA | 31 | INV | 271 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 153895 | -2700 | 151195 | 151195 | 100% | 0 | 0 | 0 | 20006 | -351 | 19655 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pinnacle Industries Ltd. | Individual | ASP | IND | FOA | 31 | INV | 272 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 186392 | 0 | 186392 | 186392 | 100% | 0 | 0 | 0 | 24231 | 0 | 24231 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Nindra Foams | Individual | ASP | IND | FOA | 31 | INV | 273 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 148804 | -2244 | 146560 | 146560 | 100% | 0 | 0 | 0 | 19345 | -292 | 19053 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at SR Poly-steel P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 274 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 144299 | -1 | 144298 | 144298 | 100% | 0 | 0 | 0 | 18759 | 0 | 18759 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Enkay Foam P., Ltd. | Individual | ASP | IND | FOA | 31 | INV | 275 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 162339 | -4442 | 157897 | 157897 | 100% | 0 | 0 | 0 | 21104 | -577 | 20527 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Alka International Ltd. | Individual | ASP | IND | FOA | 31 | INV | 276 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 173155 | -6690 | 166465 | 166465 | 100% | 0 | 0 | 0 | 22510 | -870 | 21640 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Evershine Plastic Industry | Individual | ASP | IND | FOA | 31 | INV | 277 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 80060 | -2410 | 77650 | 77650 | 100% | 0 | 0 | 0 | 10408 | -313 | 10095 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Technical assistance to Ozone Cell, MOEF during the preparation of a refrigeration and air conditioning servicing sector strategy | RMP-Component | ASP | IND | REF | 32 | TAS | 279 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-07-01 | 2005-09-01 | 30000 | -3675 | 26325 | 26325 | 100% | 0 | 0 | 0 | 3900 | -478 | 3422 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Netplast Ltd. | Individual | ASP | IND | FOA | 32 | INV | 280 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-09-01 | 2005-09-01 | 177224 | 0 | 177224 | 175025 | 98.76% | 2199 | 0 | 0 | 23039 | 0 | 22753.1315 | 285.8685 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sandlas Air-Con Systems P. Ltd. | Individual | ASP | IND | REF | 32 | INV | 282 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 228517 | 0 | 228517 | 218990 | 95.83% | 9527 | 0 | 0 | 29707 | 0 | 28468.4988 | 1238.5012 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sun Steering Wheels, Ltd. | Individual | ASP | IND | FOA | 32 | INV | 285 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-02-01 | 2005-10-01 | 144379 | 0 | 144379 | 141382 | 97.92% | 2997 | 0 | 0 | 18769 | 0 | 18379.3956 | 389.6044 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 32 | INV | 286 | A | O | I | CFC | 54 | 54 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 789425 | 0 | 789425 | 768706 | 97.38% | 20719 | 0 | 0 | 96837 | 0 | 94295.4466 | 2541.5534 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sawhney Seating Systems | Individual | ASP | IND | FOA | 32 | INV | 289 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-07-01 | 2005-09-01 | 241619 | -3124 | 238495 | 238495 | 100% | 0 | 0 | 0 | 31410 | -406 | 31004 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IND | REF | 33 | PRP | 293 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the non-recycling halon sector | Individual | ASP | IND | HAL | 33 | PRP | 294 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2003-06-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 2001 | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | ASP | IND | FOA | 33 | PRP | 296 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | ASP | IND | FOA | 33 | PRP | 297 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | IND | ARS | 33 | PRP | 298 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IND | FOA | 33 | PRP | 299 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at UNC Plast Industries | Individual | ASP | IND | FOA | 34 | INV | 304 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 |  | 89607 | 0 | 89607 | 88464 | 98.72% | 1143 | 0 | 571.5 | 11649 | 0 | 11500.4088 | 148.5911 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Viking Engineers P. Ltd. | Individual | ASP | IND | FOA | 34 | INV | 305 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-10-01 | 144900 | 0 | 144900 | 142155 | 98.11% | 2745 | 0 | 0 | 18837 | 0 | 18480.15 | 356.85 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
COM | UNDP | Renewal of institutional strengthening project (phase IV) | Individual | ASP | IND | SEV | 34 | INS | 310 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-09-01 | 2003-08-01 |  | 2004-03-01 |  | 287100 | 0 | 287100 | 281489 | 98.05% | 5611 | 0 | 2805.5 | 37323 | 0 | 36593.57 | 729.43 | 0 | Completed in 2004. | [10 empty] | 2001 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Roome Plastics P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 312 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 100546 | 0 | 100546 | 98538 | 98% | 2008 | 0 | 0 | 13071 | 0 | 12809.9596 | 261.0404 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Essa Aircons Ltd. | Individual | ASP | IND | FOA | 34 | INV | 317 | A | O | I | CFC | 14 | 14 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 108837 | 0 | 108837 | 105841 | 97.25% | 2996 | 0 | 0 | 14149 | 0 | 13759.5148 | 389.4852 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCF-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at 14 enterprises | Individual | ASP | IND | FOA | 34 | INV | 321 | A | O | I | CFC | 178 | 178 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-09-01 | 2005-11-01 | 759165 | 0 | 759165 | 746599 | 98.34% | 12566 | 0 | 0 | 93508 | 0 | 91960.2185 | 1547.7815 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at 17 small and medium-sized enterprises | Individual | ASP | IND | FOA | 34 | INV | 322 | A | O | I | CFC | 56 | 56 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-03-01 | 2004-12-01 | 417740 | 0 | 417740 | 417740 | 100% | 0 | 0 | 0 | 54306 | 0 | 54306 | 0 | 0 | Completed in 2004. Financially completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of commercial refrigeration equipment at 5 enterprises (Ahmedabad Low Temp, Kalkura Cooling Machines, Mechelec Steel Products, Polfrost Aircon and Shri Ambica Engineering) | Individual | ASP | IND | REF | 34 | INV | 323 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-11-01 | 2005-11-01 | 323627 | 0 | 323627 | 316229 | 97.71% | 7398 | 0 | 0 | 42072 | 0 | 41110.2488 | 961.7512 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Apollo Steelcrafts | Individual | ASP | IND | FOA | 34 | INV | 324 | A | O | I | CFC | 14 | 14 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 76925 | 0 | 76925 | 73796 | 95.93% | 3129 | 0 | 0 | 10000 | 0 | 9593.2402 | 406.7598 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at SR Polymers and Printers | Individual | ASP | IND | FOA | 34 | INV | 325 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 95002 | 0 | 95002 | 92032 | 96.87% | 2970 | 0 | 0 | 12350 | 0 | 11963.9081 | 386.0919 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Caryaire Equipments India P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 326 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-07-01 | 2005-11-01 | 133509 | 0 | 133509 | 133509 | 100% | 0 | 0 | 0 | 17356 | 0 | 17356 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lear Insulation Engineering P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 328 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 82567 | 0 | 82567 | 80986 | 98.09% | 1581 | 0 | 0 | 10734 | 0 | 10528.4644 | 205.5356 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nandadeep Fibrotech P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 329 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 88526 | 0 | 88526 | 85248 | 96.3% | 3278 | 0 | 0 | 11508 | 0 | 11081.8741 | 426.1259 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Nu-Foam Rubber Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 330 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2003-02-01 | 2005-10-01 | 160150 | 0 | 160150 | 159035 | 99.3% | 1115 | 0 | 0 | 20820 | 0 | 20675.0465 | 144.9535 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Poly Glass Fibre Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 331 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-03-01 | 2005-10-01 | 134238 | 0 | 134238 | 131667 | 98.08% | 2571 | 0 | 0 | 17451 | 0 | 17116.7689 | 334.2311 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Polyrub Industries | Individual | ASP | IND | FOA | 34 | INV | 332 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 97953 | 0 | 97953 | 94809 | 96.79% | 3144 | 0 | 0 | 12734 | 0 | 12325.2765 | 408.7235 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Prince Plastoware Ltd. | Individual | ASP | IND | FOA | 34 | INV | 333 | A | O | I | CFC | 9 | 9 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2004-08-01 |  | 2002-06-01 | 2003-11-01 | 74010 | -3392 | 70618 | 70618 | 100% | 0 | 0 | 0 | 9621 | -441 | 9180 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Solvay Moulding P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 334 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-07-01 | 2005-09-01 | 196885 | -15868 | 181017 | 181017 | 100% | 0 | 0 | 0 | 25595 | -2063 | 23532 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bhatia Plastics | Individual | ASP | IND | FOA | 34 | INV | 335 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-03-01 | 2005-10-01 | 87070 | 0 | 87070 | 81672 | 93.8% | 5398 | 0 | 0 | 11319 | 0 | 10617.2662 | 701.7338 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at fourteen enterprises | Individual | ASP | IND | REF | 35 | INV | 339 | A | O | I | CFC | 68 | 68 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2003-11-01 | 2005-10-01 | 960097 | 0 | 960097 | 955073 | 99.48% | 5024 | 0 | 0 | 115611 | 0 | 115006.0302 | 604.9698 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ice-Make Refrigeration | Individual | ASP | IND | REF | 35 | INV | 340 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-12-01 | 157305 | 0 | 157305 | 156073 | 99.22% | 1232 | 0 | 0 | 20450 | 0 | 20289.8373 | 160.1627 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Konark Refrigeration Appliances P., Ltd. | Individual | ASP | IND | REF | 35 | INV | 341 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-09-01 | 182684 | -1327 | 181357 | 181357 | 100% | 0 | 0 | 0 | 23749 | -173 | 23576 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 35 | INV | 342 | A | O | I | CFC | 57 | 57 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 |  | 726448 | 0 | 726448 | 717362 | 98.75% | 9086 | 0 | 4543 | 89909 | 0 | 88784.4692 | 1124.5308 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | ASP | IND | REF | 36 | PRP | 344 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 20000 | 0 | 20000 | 17254 | 86.27% | 2746 | 0 | 0 | 2600 | 0 | 2243.02 | 356.98 | 0 | Completed in 2002. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the aerosol sector | Individual | ASP | IND | ARS | 36 | PRP | 345 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 25000 | 0 | 25000 | 21428 | 85.71% | 3572 | 0 | 0 | 3250 | 0 | 2785.64 | 464.36 | 0 | Completed in 2002. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | ASP | IND | FOA | 36 | PRP | 348 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 40000 | 0 | 40000 | 33950 | 84.88% | 6050 | 0 | 0 | 5200 | 0 | 4413.5 | 786.5 | 0 | Completed in 2002. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
ONG | UNDP | Country programme update | Individual | ASP | IND | SEV | 36 | CPG | 349 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-09-01 | 2003-10-01 | 2006-07-01 |  |  | 150000 | 0 | 150000 | 148653 | 99.1% | 1347 | 0 | 471.45 | 19500 | 0 | 19324.89 | 175.11 | 0 | Draft CP Update being finalized incorporating additional data. CP Update will be reviewed and discussed at a stakeholder workshop 1Q 2006 for submission to 49th ExCom after government endorsement | [8 empty] | 2004-12-01 |  | 2002 | Non-Investment
COM | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (first tranche) | Multi-Year | ASP | IND | FOA | 37 | INV | 353 | N | O | I | CFC | 162 | 162 | 0 | 0 | 2002-07-01 | 2003-11-01 | 2003-12-01 |  | 2004-12-01 |  | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Completed in 2004. | [10 empty] | 2002 | Investment | 639 | 639 |  |  | Yes | N/A | yes
ONG | UNDP | Plan for phase out of CFCs in the refrigeration manufacturing sector (first tranche) | Multi-Year | ASP | IND | REF | 38 | INV | 356 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2004-11-01 | 2006-07-01 |  |  | 2000000 | 0 | 2000000 | 1248662 | 62.43% | 751338 | 227080 | 262968.3 | 172971 | 0 | 107991.1574 | 64979.8426 | 19639.1273 | Project activities at 36 of the 38 first batch enterprises endorsed were completed and COC/HO finalized | [10 empty] | 2002 | Investment | 428 | 428 |  |  | Yes | N/A | yes
ONG | UNDP | Terminal umbrella project in the aerosol sector | Individual | ASP | IND | ARS | 38 | INV | 358 | A | O | I | CTC/CFC | 132 | 110 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-11-01 | 2007-02-01 |  |  | 583000 | 0 | 583000 | 452731 | 77.66% | 130269 | 0 | 26053.8 | 74130 | 0 | 57565.9503 | 16564.0497 | 0 | 8 out of 14 companies have successfully installed their equipment and completed all local works. Remaining companies' work is ongoing, expected to be completed by Dec.2006. | [10 empty] | 2002 | Investment
ONG | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 364 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 | 2006-12-01 |  |  | 476536 | 0 | 476536 | 0 | 0% | 476536 | 0 | 166787.6 | 43243 | 0 | 0 | 43243 | 0 | Equipment procurement completed for remaining 118 of 154 enterprises endorsed. Equipment delivered to 46 of the 118 remaining enterprises and installation commissioning in progress | [10 empty] | 2003 | Investment | 288 | 288 |  |  | Yes | N/A | yes
ONG | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (second tranche) | Multi-Year | ASP | IND | FOA | 41 | INV | 365 | N | O | I | CFC | 210 | 210 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 | 2006-07-01 |  |  | 1750000 | 0 | 1750000 | 1148685 | 65.64% | 601315 | 297685 | 210460.25 | 153500 | 0 | 100756.0843 | 52743.9157 | 26111.2271 | COC/HOP completed for the remaining 16 enterprise under 1st tranche. All activities completed and COC/HOP finalized for 42 additional enterprises | [10 empty] | 2003 | Investment | 429 | 429 |  |  | Yes | N/A | yes
ONG | UNDP | Extension of institutional strengthening project: phase 5 | Individual | ASP | IND | SEV | 41 | INS | 367 | N | T | I | No-ODP | 31 | 31 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 | 2006-07-01 |  |  | 373230 | 0 | 373230 | 229050 | 61.37% | 144180 | 3547 | 50463 | 27992 | 0 | 17178.5966 | 10813.4034 | 266.0226 | Phase close to completion, activities described in new phase | [10 empty] | 2003 | Non-Investment
ONG | UNDP | MDI Transitional Strategy | Individual | ASP | IND | ARS | 41 | TAS | 368 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 | 2006-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 10500 | 2250 | 0 | 0 | 2250 | 0 | Consultants continued to collect data and prepare strategy | [10 empty] | 2003 | Non-Investment
ONG | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 371 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-11-01 | 2005-04-01 | 2006-06-01 |  |  | 277200 | 0 | 277200 | 162381 | 58.58% | 114819 | 56040 | 40186.65 | 20790 | 0 | 12178.575 | 8611.425 | 4203 | R&R equipment for 143 Refrigeration Servicing Enterprises procured and delivered to 39. Equipment for 63 training institutes were procured and delivered. | [10 empty] | 2004 | Investment | 219 | 219 |  |  | Yes | N/A | yes
ONG | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 379 | N | O | I | CFC | 158 | 158 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-06-01 |  |  | 277050 | 0 | 277050 | 0 | 0% | 277050 | 0 | 96967.5 | 20779 | 0 | 0 | 20779 | 0 | Equipment for remaining 57 training institutes were procured and delivered. ITB for 513 Refrigeration Servicing Enterprises were conducted. Equipment to be ordered and delivered first half 2006 | [10 empty] | 2004 | Investment | 206.2 | 206.2 |  |  | Yes | Yes | yes
ONG | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (third tranche) | Multi-Year | ASP | IND | REF | 44 | INV | 383 | N | O | I | CFC | 141 | 141 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 0 | 87500 | 21621 | 0 | 0 | 21621 | 0 | Equipment procurement completed for 72 of the remaining 118 enterprises endorsed. Delivery and installation/commissioning expected to be completed in 2006 | [10 empty] | 2004 | Investment | 180 | 180 |  |  | Yes | Yes | yes
ONG | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (third tranche) | Multi-Year | ASP | IND | FOA | 44 | INV | 384 | N | O | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 1500000 | 0 | 1500000 | 0 | 0% | 1500000 | 0 | 525000 | 131000 | 0 | 0 | 131000 | 0 | Implemented at 4 more enterprises. Of the total 118 enterprises endorsed, cumulatively 74 subprojects completed. Activities initiated at 44 remaining enterprises of which 12 were completed by end 05 | [10 empty] | 2004 | Investment | 128 | 128 |  |  | Yes | Yes | yes
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IND | SEV | 45 | TAS | 391 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 183486 | 0 | 183486 | 0 | 0% | 183486 | 0 | 64220.1 | 16514 | 0 | 0 | 16514 | 0 | TORs for national and intl consultants defined for recruitment. Surveys and data collection to be initiated 1Q 2006 under supervision and guidance of national consultant | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IND | SEV | 47 | INS | 392 | N | T | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 373230 | 0 | 373230 | 0 | 0% | 373230 | 0 | 74646 | 27992 | 0 | 0 | 27992 | 0 | The Ozone Cell continued its effective supervision and management of the NPP, CFC and CTC production and CTC consumption phase-out plans, in close coordination with the IAs. It also continued playing its key role in policy, regulatory, enforcement and data reporting to ensure sustainable ODS phase-out. India continued to participate actively in Montreal protocol related meetings, including ExCom, UNEP Network Meeting, OEWP and MOP. Public awareness activities and stakeholder workshops were conducted to ensure effective and sustainable ODS phase out. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 395 | N | O | I | CFC | 414 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 1332377 | 0 | 1332377 | 0 | 0% | 1332377 | 0 | 466331.95 | 112417 | 0 | 0 | 112417 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment | 157 |  |  |  | Latest | Latest | Latest
FIN | UNDP | Study to determine production and consumption of ODS | Individual | ASP | IRA | SEV | 04 | TAS | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 30350 | 0 | 30350 | 30350 | 100% | 0 | 0 | 0 | 3946 | 0 | 3946 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1993-06-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IRA | SEV | 08 | INS | 05 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-12-01 | 2000-12-01 | 200200 | 0 | 200200 | 200200 | 100% | 0 | 0 | 0 | 26026 | 0 | 26026 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | IRA | SEV | 08 | PRP | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-11-01 | 1993-10-01 |  | 1995-03-01 | 1997-12-01 | 17935 | 0 | 17935 | 17935 | 100% | 0 | 0 | 0 | 2332 | 0 | 2332 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1992 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IRA | SEV | 23 | INS | 30 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-08-01 | 1999-12-01 |  | 2002-05-01 | 2003-11-01 | 133470 | 0 | 133470 | 133470 | 100% | 0 | 0 | 0 | 17351 | 0 | 17351 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Preparation of four projects in the integral skin foam subsector | Individual | ASP | IRA | FOA | 27 | PRP | 40 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of three projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 27 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Foroughmanesh Co. | Individual | ASP | IRA | REF | 28 | INV | 43 | A | O | I | CFC | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 399803 | -13456 | 386347 | 386347 | 100% | 0 | 0 | 0 | 51974 | -1749 | 50225 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Tahvieh Garm va Sard Co. | Individual | ASP | IRA | REF | 28 | INV | 44 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-02-01 | 278659 | -13367 | 265292 | 265292 | 100% | 0 | 0 | 0 | 36226 | -1738 | 34488 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Movaledsarma Co. (Zagross 1) | Individual | ASP | IRA | REF | 28 | INV | 46 | A | O | I | CFC | 78 | 78 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2004-01-01 | 816698 | -12094 | 804604 | 804604 | 100% | 0 | 0 | 0 | 99837 | -1331 | 98506 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 tgo HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Electro Shargh Mazandaran Co. | Individual | ASP | IRA | REF | 29 | INV | 55 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 301715 | -31900 | 269815 | 269815 | 100% | 0 | 0 | 0 | 39223 | -4147 | 35076 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardkaran Industrial Manufacturing Co. | Individual | ASP | IRA | REF | 29 | INV | 56 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2002-03-01 | 2003-11-01 | 155405 | -6082 | 149323 | 149323 | 100% | 0 | 0 | 0 | 20203 | -791 | 19412 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Khozestan Technique Co. | Individual | ASP | IRA | REF | 29 | INV | 58 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-04-01 | 132041 | -1 | 132040 | 132040 | 100% | 0 | 0 | 0 | 17165 | 0 | 17165 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Electro Sard Azna Co,. | Individual | ASP | IRA | REF | 29 | INV | 60 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 191061 | -33421 | 157640 | 157640 | 100% | 0 | 0 | 0 | 24838 | -4345 | 20493 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 62 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 |  | 30000 | -6577 | 23423 | 25598 | 109.3% | -2175 | 0 | 0 | 3900 | -855 | 3327.7509 | -282.7509 | 0 | Completed in 2000. Apparent overrun to be resolved in 2006. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 3 projects in the domestic refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 63 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Prepare 2 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 64 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HCFC-134a technology in the manufacture of commercial refrigeration equipment at Behsarma Co. | Individual | ASP | IRA | REF | 28 | INV | 65 | A | O | I | CFC | 34 | 34 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 455593 | -13588 | 442005 | 442005 | 100% | 0 | 0 | 0 | 59227 | -1766 | 57461 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fadak Refrigeration Industries | Individual | ASP | IRA | REF | 31 | INV | 66 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-11-01 | 2003-11-01 | 258937 | 0 | 258937 | 258937 | 100% | 0 | 0 | 0 | 33662 | 0 | 33662 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial and domestic refrigeration equipment at Jaleh & Segin Co. | Individual | ASP | IRA | REF | 31 | INV | 67 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 322309 | 0 | 322309 | 322309 | 100% | 0 | 0 | 0 | 41900 | 0 | 41900 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at MH Seyed Salaki Co. | Individual | ASP | IRA | REF | 31 | INV | 68 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 141590 | 0 | 141590 | 141590 | 100% | 0 | 0 | 0 | 18407 | 0 | 18407 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Baharanfarr Co. | Individual | ASP | IRA | REF | 31 | INV | 70 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-01-01 | 2003-08-01 |  |  | 2002-11-01 | 208070 | -207415 | 655 | 655 | 100% | 0 | 0 | 0 | 27049 | -26964 | 85 | 0 | 0 | Canceled in 2002. Financially completed in 2002. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fereidooni Refrigerant Industries | Individual | ASP | IRA | REF | 31 | INV | 71 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-11-01 | 157454 | 0 | 157454 | 157454 | 100% | 0 | 0 | 0 | 20469 | 0 | 20469 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | IRA | SEV | 32 | INS | 74 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-08-01 | 2004-01-01 | 133470 | -25 | 133445 | 133445 | 100% | 0 | 0 | 0 | 17351 | -3 | 17347.75 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2000 | Non-Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nobough Industrial Co. | Individual | ASP | IRA | FOA | 32 | INV | 75 | A | O | I | CFC | 32 | 21 | 0 | 0 | 2000-12-01 | 2002-01-01 | 2004-01-01 |  |  |  | 248736 | 0 | 248736 | 50655 | 20.36% | 198081 | 0 | 0 | 32336 | 0 | 6585.2152 | 25750.7848 | 0 | Canceled in 2003. Balance to be verified and returned in 2006. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to n-pentane technology in the manufacture of integral skin polyurethane foam products at Iran Polyurethane Manufacturing Co. | Individual | ASP | IRA | FOA | 32 | INV | 76 | A | O | I | CFC | 52 | 52 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-08-01 | 2003-11-01 | 796230 | 0 | 796230 | 796230 | 100% | 0 | 0 | 0 | 97585 | 0 | 97585 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 77 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 79 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 81 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Yakhchalsazi Yazd Co. | Individual | ASP | IRA | REF | 34 | INV | 82 | A | O | I | CFC | 30 | 30 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 248646 | -43159 | 205487 | 205487 | 100% | 0 | 0 | 0 | 32324 | -5611 | 26713 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the domestic refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Rezvan Co. | Individual | ASP | IRA | REF | 34 | INV | 84 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 182182 | -34099 | 148083 | 148083 | 100% | 0 | 0 | 0 | 23684 | -4433 | 19251.07 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Electro Ara Co. | Individual | ASP | IRA | REF | 34 | INV | 85 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-06-01 |  | 178784 | 0 | 178784 | 133475 | 74.66% | 45309 | 0 | 22654.5 | 23242 | 0 | 17351.8097 | 5890.1903 | 0 | Completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Boloorin Yazd Refrigerator Co. | Individual | ASP | IRA | REF | 34 | INV | 86 | A | O | I | CFC | 21 | 21 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2005-09-01 | 212320 | -37255 | 175065 | 175065 | 100% | 0 | 0 | 0 | 27602 | -4843 | 22759 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Sarmaye Sepahan Co. | Individual | ASP | IRA | REF | 34 | INV | 87 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 148525 | 0 | 148525 | 148525 | 100% | 0 | 0 | 0 | 19308 | 0 | 19308 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded and integral skin polyurethane foams at Abre Sanati Iran | Individual | ASP | IRA | FOA | 34 | INV | 88 | A | O | I | CFC | 48 | 48 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2005-11-01 | 344407 | 0 | 344407 | 336451 | 97.69% | 7956 | 0 | 0 | 44773 | 0 | 43738.7179 | 1034.2821 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Mersun Co. | Individual | ASP | IRA | REF | 34 | INV | 89 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 162891 | 0 | 162891 | 137697 | 84.53% | 25194 | 0 | 0 | 21176 | 0 | 17900.7537 | 3275.2463 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ideal Sardsir Co. | Individual | ASP | IRA | REF | 34 | INV | 90 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 187907 | -13311 | 174596 | 174596 | 100% | 0 | 0 | 0 | 24428 | -1730 | 22698 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parsa Sazan Co. | Individual | ASP | IRA | REF | 34 | INV | 91 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 212845 | 0 | 212845 | 152844 | 71.81% | 60001 | 0 | 0 | 27670 | 0 | 19869.8277 | 7800.1723 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Zenoz Sanaat Co. | Individual | ASP | IRA | REF | 34 | INV | 92 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2003-12-01 | 140036 | 0 | 140036 | 140036 | 100% | 0 | 0 | 0 | 18205 | 0 | 18205 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Part | Individual | ASP | IRA | REF | 34 | INV | 93 | A | O | I | CFC | 8 | 8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2005-10-01 | 114770 | 0 | 114770 | 114770 | 100% | 0 | 0 | 0 | 14920 | 0 | 14920 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sepand Afroz Co. | Individual | ASP | IRA | REF | 34 | INV | 94 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 172881 | 0 | 172881 | 159810 | 92.44% | 13071 | 0 | 0 | 22475 | 0 | 20775.7345 | 1699.2655 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Yakhchalsazi Anzabi Co. | Individual | ASP | IRA | REF | 34 | INV | 95 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 138935 | 0 | 138935 | 138918 | 99.99% | 17 | 0 | 0 | 18062 | 0 | 18059.7899 | 2.2101 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at General Industries | Individual | ASP | IRA | REF | 34 | INV | 96 | A | O | I | CFC | 31 | 31 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 428197 | 0 | 428197 | 428197 | 100% | 0 | 0 | 0 | 55666 | 0 | 55666 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ghaynar Khazar Co. | Individual | ASP | IRA | REF | 34 | INV | 97 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-11-01 | 2003-11-01 | 191092 | -30740 | 160352 | 160352 | 100% | 0 | 0 | 0 | 24842 | -3996 | 20846 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ojan Cooling Industries | Individual | ASP | IRA | REF | 34 | INV | 99 | A | O | I | CFC | 7 | 7 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2004-01-01 | 110863 | 0 | 110863 | 110863 | 100% | 0 | 0 | 0 | 14412 | 0 | 14412 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Hanzad Co. | Individual | ASP | IRA | REF | 34 | INV | 100 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 |  | 199627 | 0 | 199627 | 171203 | 85.76% | 28424 | 0 | 14212 | 25952 | 0 | 22256.8102 | 3695.1898 | 0 | Completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sana Commercial Co. | Individual | ASP | IRA | REF | 34 | INV | 109 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 156286 | 0 | 156286 | 155919 | 99.77% | 367 | 0 | 0 | 20317 | 0 | 20269.2904 | 47.7096 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Golsarma Co. | Individual | ASP | IRA | REF | 34 | INV | 110 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 230066 | -13115 | 216951 | 216951 | 100% | 0 | 0 | 0 | 29909 | -1705 | 28204 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Shagayegh Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 112 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 137985 | -514 | 137471 | 137471 | 100% | 0 | 0 | 0 | 17938 | -67 | 17871 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Investment
COM | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sandalisazi Esfanje Ghalebi Iran | Individual | ASP | IRA | FOA | 35 | INV | 117 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 |  | 188820 | 0 | 188820 | 181071 | 95.9% | 7749 | 0 | 3874.5 | 24547 | 0 | 23539.6136 | 1007.3864 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Alireza Abdolrezazadeh Co. | Individual | ASP | IRA | REF | 35 | INV | 131 | A | O | I | CFC | 8 | 8 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 116646 | 0 | 116646 | 116319 | 99.72% | 327 | 0 | 0 | 15164 | 0 | 15121.4899 | 42.5101 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Garm Iran Co. | Individual | ASP | IRA | REF | 35 | INV | 132 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 |  | 153447 | 0 | 153447 | 122941 | 80.12% | 30506 | 0 | 15253 | 19948 | 0 | 15982.2419 | 3965.7581 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
ONG | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Ghotb Jonoub Industrial Group | Individual | ASP | IRA | REF | 35 | INV | 133 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2001-12-01 | 2004-06-01 | 2004-07-01 | 2006-04-01 |  |  | 170125 | 0 | 170125 | 106025 | 62.32% | 64100 | 0 | 22435 | 22116 | 0 | 13783.0942 | 8332.9058 | 0 | Project activities completed. Intl consultant was not able to gain entry to Iran to undertake completion procedures. COC/HOP to be completed 1Q2006 | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Havasaz Manufacturing and Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 134 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 252294 | 0 | 252294 | 233273 | 92.46% | 19021 | 0 | 0 | 32798 | 0 | 30325.2866 | 2472.7134 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Mehran Sard, Co. | Individual | ASP | IRA | REF | 35 | INV | 135 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 144715 | 0 | 144715 | 143618 | 99.24% | 1097 | 0 | 0 | 18813 | 0 | 18670.3896 | 142.6104 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parto Shiva Sanaat | Individual | ASP | IRA | REF | 35 | INV | 136 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 |  | 283948 | 0 | 283948 | 247323 | 87.1% | 36625 | 0 | 18312.5 | 36913 | 0 | 32151.781 | 4761.219 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Sain Electric Co. | Individual | ASP | IRA | REF | 35 | INV | 137 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 152024 | 0 | 152024 | 119801 | 78.8% | 32223 | 0 | 0 | 19763 | 0 | 15574.0354 | 4188.9646 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Boroudati Maleki | Individual | ASP | IRA | REF | 35 | INV | 138 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 |  | 215052 | 0 | 215052 | 214874 | 99.92% | 178 | 0 | 89 | 27957 | 0 | 27933.8598 | 23.1402 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Fan, Co. | Individual | ASP | IRA | REF | 35 | INV | 139 | A | O | I | CFC | 21 | 21 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-10-01 | 267075 | 0 | 267075 | 240346 | 89.99% | 26729 | 0 | 0 | 34720 | 0 | 31245.205 | 3474.795 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Tehran Sardsazi Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 140 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 125244 | 0 | 125244 | 125244 | 100% | 0 | 0 | 0 | 16282 | 0 | 16282 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 141 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | 0 | 10000 | 9058 | 90.58% | 942 | 0 | 0 | 1300 | 0 | 1177.54 | 122.46 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 2 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 142 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | 0 | 10000 | 9058 | 90.58% | 942 | 0 | 0 | 1300 | 0 | 1177.54 | 122.46 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 4 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 143 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | 0 | 12500 | 0 | 0% | 12500 | 0 | 0 | 1625 | 0 | 0 | 1625 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 6 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 144 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | 0 | 12500 | 0 | 0% | 12500 | 0 | 0 | 1625 | 0 | 0 | 1625 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Project preparation in the manufacturing of refrigeration equipment sector (terminal phase-out) | Individual | ASP | IRA | REF | 36 | PRP | 147 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 35000 | 0 | 35000 | 29776 | 85.07% | 5224 | 0 | 0 | 4550 | 0 | 3870.88 | 679.12 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
COM | UNDP | Extension of institutional strengthening project | Individual | ASP | IRA | SEV | 38 | INS | 157 | N | T | I | CFC | 14 | 14 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2005-12-01 |  | 173511 | 0 | 173511 | 172092 | 99.18% | 1419 | 0 | 709.5 | 22556 | 0 | 22371.96 | 184.47 | 0 | Completed in 2005. Coordinated with IAs on implementation and completion of individual projects and NPP. Continued on data verification on CTC/TCA for change of baseline | [10 empty] | 2002 | Non-Investment
ONG | UNDP | National CFC phase-out plan: first tranche | Multi-Year | ASP | IRA | PHA | 42 | INV | 165 | N | O | I | CFC | 56 | 56 | 0 | 0 | 2004-04-01 | 2005-05-01 | 2007-04-01 | 2007-04-01 |  |  | 770000 | 0 | 770000 | 568664 | 73.85% | 201336 | 25774 | 40267.2 | 57750 | 0 | 42649.8 | 15100.2 | 1933.05 | Equipment procured and delivered to all 25 enterprises. Installation and commissioning initiated and will be completed by 1Q2006, phasing out 165.85 ODP tonnes | [10 empty] | 2004 | Investment | 56 | 56 |  |  | Yes | Yes | yes
ONG | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IRA | SEV | 44 | INS | 167 | N | T | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 | 2006-12-01 |  |  | 86755 | 0 | 86755 | 29651 | 34.18% | 57104 | 0 | 19986.4 | 6507 | 0 | 2223.9532 | 4283.0468 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IRA | SEV | 45 | TAS | 172 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 68807 | 0 | 68807 | 0 | 0% | 68807 | 0 | 24082.45 | 6193 | 0 | 0 | 6193 | 0 | TORs for national and intl consultants defined for recruitment. Surveys and data collection to be initiated 1Q 2006 under supervision and guidance of national consultant | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase V, year 2) | Individual | ASP | IRA | SEV | 47 | INS | 174 | N | T | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 86756 | 0 | 86756 | 0 | 0% | 86756 | 0 | 30364.6 | 6507 | 0 | 0 | 6507 | 0 | The Ozone Office continued the supervision and management of individual projects and the NPP, working in close coordination with all IAs. The Ozone Unit worked closely with UNDP to collect TCA/CTC data as supporting documents necessary to facilitate revision of database at the Implementation Committee. Strong support was also provided in policy formulation and enforcement. Public awareness activities and stakeholders’ workshop were conducted to promote and ensure sustainable ODS phase out. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | JAM | SEV | 14 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | JAM | REF | 18 | TAS | 03 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1997-05-01 | 2000-12-01 | 172465 | -13366 | 159099 | 159099 | 100% | 0 | 0 | 0 | 22420 | -1738 | 20682 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation in the aerosol, foam and refrigeration sectors | Individual | LAC | JAM | SEV | 21 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 30000 | -16175 | 13825 | 13825 | 100% | 0 | 0 | 0 | 3900 | -2103 | 1797 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at West Indies Synthetics Company, Ltd (Wisynco) | Individual | LAC | JAM | FOA | 22 | INV | 06 | A | O | I | CFC | 82 | 82 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 1998-12-01 | 2000-12-01 | 596000 | -3008 | 592992 | 592992 | 100% | 0 | 0 | 0 | 77480 | -391 | 77089 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | JAM | REF | 30 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2002-05-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Investment
ONG | UNDP | Terminal phase-out management plan for CFCs: retrofitting/replacement programme | Individual | LAC | JAM | PHA | 37 | TAS | 17 | N | O | I | CFC | 2 | 0 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2006-01-01 | 2006-12-01 |  |  | 140000 | 0 | 140000 | 70617 | 50.44% | 69383 | 0 | 24284.05 | 18200 | 0 | 9180.21 | 9019.79 | 0 | Project on track. Ntl project IA requested a no funds extension through end 2006. Extension sought to ensure that all end-users addressed. WP to project closure + budget for allocation of unspent balance (US $58,700) being elaborated in early 2006. | [10 empty] | 2002 | Non-Investment
COM | UNDP | Formulation of the solvent sectoral phase out plan | Individual | LAC | JAM | SOL | 39 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Project preparation completed. Project submitted to and approved at ExCom 42. Final budget revision pending. | [10 empty] | 2003 | Investment
ONG | UNDP | Technical assistance umbrella project to phase out ODS solvent use | Individual | LAC | JAM | SOL | 42 | TAS | 20 | N | O | I | TCA | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 | 2006-04-01 |  |  | 25000 | 0 | 25000 | 20881 | 83.52% | 4119 | 0 | 1441.65 | 2250 | 0 | 1879.29 | 370.71 | 0 | National training workshops held in February 05. Ongoing distance assistance provided to end-users directly throughout 2005 to ensure sustainability of phaseout. Project completion expected on time. Final budget revision to be prepared in 2006. | [10 empty] | 2004 | Non-Investment
FIN | UNDP | Technical assistance and pre-feasibility study in aerosol sector | Individual | ASP | JOR | ARS | 04 | TAS | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 | 0 | 3770 | 0 | 3770 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Feasibility study on deodorization of local gas as a CFC substitute in cosmetics | Individual | ASP | JOR | ARS | 06 | TAS | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Formulation of investment components of the RMP | Individual | ASP | KAM | REF | 36 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 15000 | 0 | 15000 | 13080 | 87.2% | 1920 | 0 | 0 | 1950 | 0 | 1700.4 | 249.6 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | KAM | REF | 39 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant and awareness and incentive programme for the MAC sub-sector | RMP-Update-Comp | ASP | KAM | REF | 41 | TAS | 05 | N | O | I | CFC | 20 | 2 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 | 2007-12-01 |  |  | 625000 | 0 | 625000 | 110414 | 17.67% | 514586 | 0 | 102917.2 | 46875 | 0 | 8281.05 | 38593.95 | 0 | Workshop conducted and R&R equipment distributed. MAC retrofit and incentive programme initiated. Phase-out strategy being reviewed due to price differential still not favourable enough | [10 empty] | 2003 | Investment
FIN | UNDP | Country programme preparation | Individual | AFR | KEN | SEV | 06 | CPG | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-07-01 |  | 1994-06-01 | 1997-12-01 | 25000 | -2270 | 22730 | 22730 | 100% | 0 | 0 | 0 | 3250 | -295 | 2955 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | KEN | SEV | 09 | INS | 03 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-06-01 | 2005-09-01 | 175000 | 0 | 175000 | 174966 | 99.98% | 34 | 0 | 0 | 22750 | 0 | 22745.58 | 4.42 | 0 | Completed in 1998. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1993 | Non-Investment
TRF | UNDP | Demonstration and training unit for maintenance and recharge of refrigeration and air conditioning equipment | RMP-Component | AFR | KEN | REF | 04 | TRA | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1993-06-01 |  |  | 1993-06-01 | 115100 | -105248 | 9852 | 9852 | 100% | 0 | 0 | 0 | 14963 | -13682 | 1281 | 0 | 0 | Transferred in 1993. Financially completed in 1993. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | KEN | SEV | 25 | INS | 18 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-12-01 | 2003-10-01 | 116667 | 0 | 116667 | 116667 | 100% | 0 | 0 | 0 | 15167 | 0 | 15167 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | AFR | KEN | SEV | 32 | INS | 25 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2005-09-01 | 116667 | 0 | 116667 | 116433 | 99.8% | 234 | 0 | 0 | 15167 | 0 | 15136.5794 | 30.4206 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation in the soil fumigant sector (cut flowers) | Individual | AFR | KEN | FUM | 36 | PRP | 28 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2002 | Investment
COM | UNDP | Extension of institutional strengthening project | Individual | AFR | KEN | SEV | 38 | INS | 30 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 |  | 151667 | 0 | 151667 | 151084 | 99.62% | 583 | 0 | 291.5 | 19717 | 0 | 19640.92 | 75.79 | 0 | Completed in 2004. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flower component (first tranche) | Multi-Year | AFR | KEN | FUM | 38 | INV | 31 | A | O | I | MeBr | 10 | 10 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 | 2006-12-01 |  |  | 510660 | 0 | 510660 | 166775 | 32.66% | 343885 | 0 | 120359.75 | 66173 | 0 | 21611.2523 | 44561.7478 | 0 | Impl. activities in place - training missions throughout 05, procurement, installation & adoption of alternatives. Negotiations to put in place contract for local procurement underway. Disbursements slow but WP in place and activities on track. | [9 empty] | 2005-07-01 | 2002 | Investment | 63 | 63 |  |  | Yes | N/A | yes
ONG | UNDP | Project preparation for the formulation of solvent sectoral phase-out plan | Individual | AFR | KEN | SOL | 42 | PRP | 34 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 8000 | 1500 | 0 | 1500 | 0 | 0 | Terms of Reference for National Expert prepared. Recruitment in 2006 to carry out survey. Project document expected to be submitted to 50th ExCom. | [10 empty] | 2004 | Investment
ONG | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation (second tranche) | Multi-Year | AFR | KEN | FUM | 44 | INV | 38 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 306396 | 0 | 306396 | 0 | 0% | 306396 | 0 | 107238.6 | 22980 | 0 | 0 | 22980 | 0 | Work Plan prepared but no disbursements yet as activities linked with 1st phase of project still ongoing. Implementation of Ph 2 activities projected for launch in early 2006. | [10 empty] | 2004 | Investment | 53 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Extension of institutional strengthening project (phase V) | Individual | AFR | KEN | SEV | 44 | INS | 39 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 151667 | 0 | 151667 | 45884 | 30.25% | 105783 | 0 | 37024.05 | 11375 | 0 | 3441.2924 | 7933.7076 | 0 | During the 2005 reporting period, the NOU continued to focus its efforts on various activities that would enable Kenya to meet its obligations under the Montreal Protocol, including supporting implementation of the MB investment projects. The NOU has also continued to assess Kenya’s needs for new projects and has participated in their development. In addition, awareness activities that contribute to better understanding of ODS and alternatives from the general public and various stakeholders were conducted. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Update-Comp | ASP | KYR | REF | 37 | TAS | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-08-01 | 2007-08-01 |  |  | 16500 | 0 | 16500 | 9970 | 60.42% | 6530 | 0 | 1306 | 2145 | 0 | 1296.1 | 848.9 | 0 | Two-year monitoring launched and underwent its first year. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Update-Comp | ASP | KYR | REF | 37 | TAS | 02 | A | O | I | CFC | 2 | 0 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-07-01 | 2007-07-01 |  |  | 187242 | 0 | 187242 | 95271 | 50.88% | 91971 | 0 | 18394.2 | 24341 | 0 | 12385.23 | 11956.23 | 0 | 3 additional applications for incentive received and processed, bringing the total to 9. More expected in 2006. Project on schedule. | [10 empty] | 2002 | Non-Investment
COM | UNDP | Implementation of the RMP: national programme for refrigerant recovery and recycling | RMP-Update-Comp | ASP | KYR | REF | 37 | TAS | 04 | A | O | I | CFC | 9 | 9 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2003-10-01 |  | 185175 | 0 | 185175 | 183647 | 99.17% | 1528 | 0 | 764 | 24073 | 0 | 23874.11 | 198.64 | 0 | Completed in 2003. | [10 empty] | 2002 | Investment
ONG | UNDP | Technical assistance project to install alternatives and phase-out methyl bromide | One-off-Phaseout | ASP | KYR | FUM | 41 | TAS | 08 | N | O | I | MeBr | 14 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2008-12-01 | 2008-12-01 |  |  | 300000 | 0 | 300000 | 48996 | 16.33% | 251004 | 0 | 50200.8 | 22500 | 0 | 3674.7 | 18825.3 | 0 | Ntl workshop held in 04-05, ntl expert trained in Russia and procurement process launched. Intl tech expert engaged and ntl TOT planned. Activities advancing slowly with expectation that adoption of alternatives will proceed in 06. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Project preparation of a terminal phase-out management plan | Individual | ASP | KYR | PHA | 47 | PRP | 11 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 10500 | 2250 | 0 | 0 | 2250 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in Latin America | Individual | LAC | LAC | FOA | 06 | TRA | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | 1312 | 53812 | 53812 | 100% | 0 | 0 | 0 | 6825 | 171 | 6996 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in Latin America | Individual | LAC | LAC | HAL | 06 | TRA | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1994-06-01 | 1997-12-01 | 60000 | -15158 | 44842 | 44842 | 100% | 0 | 0 | 0 | 7800 | -1971 | 5829 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Latin America | RMP-Component | LAC | LAC | REF | 06 | TRA | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1995-11-01 | 1994-02-01 |  | 1995-11-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Latin America | Individual | LAC | LAC | REF | 06 | TRA | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1992-09-01 | 1997-12-01 | 40000 | -16953 | 23047 | 23047 | 100% | 0 | 0 | 0 | 5200 | -2204 | 2996 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Methyl bromide data collection for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TAS | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 1998-12-01 | 57700 | 0 | 57700 | 57700 | 100% | 0 | 0 | 0 | 7501 | 0 | 7501 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Non-Investment
FIN | UNDP | Regional Latin America demonstration project in recovery of ODS in MACs: Phase I (Argentina, Colombia) | RMP-Component | LAC | LAC | REF | 18 | TAS | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1999-05-01 | 207000 | 0 | 207000 | 207000 | 100% | 0 | 0 | 0 | 26910 | 0 | 26910 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1995 | Non-Investment
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector in the Caribbean, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | LAC | REF | 47 | DEM | 36 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 0 | 200000 | 75000 | 0 | 0 | 75000 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | LAO | FOA | 36 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | 0 | 20000 | 17254 | 86.27% | 2746 | 0 | 0 | 2600 | 0 | 2243.02 | 356.98 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) in the manufacture of flexible polyurethane foam (box) at Prasert Foam Co., Ltd. | Individual | ASP | LAO | FOA | 38 | INV | 10 | A | O | I | CFC | 16 | 16 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-08-01 | 2005-11-01 | 139343 | 0 | 139343 | 139343 | 100% | 0 | 0 | 0 | 18115 | 0 | 18114.59 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2002 | Investment
FIN | UNDP | Formulation of a terminal phase out project in the foam sector | Individual | ASP | LAO | FOA | 39 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Conversion from CFC-11 in the manufacture of boxfoam (FPF) and insulated containers (RPF) in Prasert Sofa Shop Co., Ltd. | Individual | ASP | LAO | FOA | 44 | INV | 14 | N | O | I | CFC | 12 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 184660 | 0 | 184660 | 0 | 0% | 184660 | 0 | 64631 | 16619 | 0 | 0 | 16619 | 0 | Misunderstanding between Govt and ongoing enterprise arose, so that re-assessment of project was needed. Decision to be taken in 2Q06 as to whether implementation can start or if project to be canceled. | [10 empty] | 2004 | Investment
ONG | UNDP | Project preparation for foam multiple sub-sectors | Individual | ASP | LAO | FOA | 45 | PRP | 15 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 | 2006-04-01 |  |  | 22493 | 0 | 22493 | 17780 | 79.05% | 4713 | 0 | 4713 | 1687 | 0 | 1333.5198 | 353.4802 | 0 | Further to several missions, misunderstanding between Govt and new enterprise became apparent, so that re-assessment of need to prepare project was made. No project may be presented due to this. | [10 empty] | 2005 | Investment
FIN | UNDP | Creation of an Ozone Unit | Individual | ASP | LEB | SEV | 19 | INS | 08 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 2000-05-01 |  | 2000-12-01 | 2002-03-01 | 179000 | -63 | 178937 | 178937 | 100% | 0 | 0 | 0 | 23270 | -8 | 23262 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1996 | Non-Investment
FIN | UNDP | Project preparation for one methyl bromide alternative demonstration project | Individual | ASP | LEB | FUM | 25 | PRP | 23 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-08-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Demonstration project of alternative to methyl bromide for soil fumigation (greenhouse) | Individual | ASP | LEB | FUM | 26 | DEM | 24 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 328200 | -2958 | 325242 | 325242 | 100% | 0 | 0 | 0 | 42666 | -385 | 42281 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of project in the foam subsector | Individual | ASP | LEB | FOA | 27 | PRP | 27 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of four projects in the aerosol sector | Individual | ASP | LEB | ARS | 27 | PRP | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at International Cosmetic Manufacturing Co. (Incoma), SAL | Individual | ASP | LEB | ARS | 28 | INV | 30 | A | O | I | CFC | 54 | 54 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 158582 | 0 | 158582 | 153513 | 96.8% | 5069 | 0 | 0 | 20616 | 0 | 19957.0191 | 658.9809 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Group SME's project for the conversion to CFC-free technology in manufacturer of aerosol at Zahdreddine Trade and Manufacturing Sarl (ZTME), at Societe Nouvelle pour le Commerce et l'Industrie (SNCI) | Individual | ASP | LEB | ARS | 29 | INV | 32 | A | O | I | CFC | 51 | 51 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2004-09-01 | 2005-10-01 | 314092 | 0 | 314092 | 312545 | 99.51% | 1547 | 0 | 0 | 40832 | 0 | 40630.8898 | 201.1102 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Farjallah Co. | Individual | ASP | LEB | REF | 29 | INV | 34 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-07-01 | 200046 | 0 | 200046 | 200046 | 100% | 0 | 0 | 0 | 26006 | 0 | 26006 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosols at Societe Nougeaim PMOSAL | Individual | ASP | LEB | ARS | 28 | INV | 35 | A | O | I | CFC | 54 | 54 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 147333 | 0 | 147333 | 144690 | 98.21% | 2643 | 0 | 0 | 19153 | 0 | 18809.4152 | 343.5848 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Investment
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | ASP | LEB | SEV | 31 | INS | 37 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2003-07-01 | 2004-12-01 | 119300 | 0 | 119300 | 119300 | 100% | 0 | 0 | 0 | 15509 | 0 | 15509 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | LEB | FOA | 33 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 12000 | -1934 | 10066 | 10066 | 100% | 0 | 0 | 0 | 1560 | -251 | 1309 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | ASP | LEB | FUM | 33 | PRP | 42 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 2001 | Investment
COM | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 46 | N | O | I | MeBr | 26 | 26 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-12-01 |  | 2004-12-01 |  | 800000 | 0 | 800000 | 800000 | 100% | 0 | 0 | 0 | 98000 | 0 | 98000 | 0 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment | 186.1 | 186.1 |  |  | Yes | N/A | Yes
COM | UNDP | Preparation of a CFC terminal programme | Individual | ASP | LEB | PHA | 36 | PRP | 48 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-12-01 |  | 15000 | 0 | 15000 | 11399 | 75.99% | 3601 | 0 | 3601 | 1950 | 0 | 1481.87 | 468.13 | 0 | Completed in 2004. | [10 empty] | 2002 | Investment
FIN | UNDP | Country programme update | Individual | ASP | LEB | SEV | 36 | CPG | 49 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2003-12-01 | 2004-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 | 0 | 4875 | 0 | 4875 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2002 | Non-Investment
COM | UNDP | Renewal of institutional strengthening project (Phase 3) | Individual | ASP | LEB | SEV | 37 | INS | 50 | N | T | I | CFC | 13 | 13 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-12-01 |  | 155090 | 0 | 155090 | 154893 | 99.87% | 197 | 0 | 98.5 | 20162 | 0 | 20136.09 | 25.61 | 0 | Completed in 2004. | [10 empty] | 2002 | Non-Investment
COM | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (second tranche) | Multi-Year | ASP | LEB | FUM | 38 | INV | 51 | N | O | I | MeBr | 32 | 32 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2004-12-01 |  | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 76000 | 0 | 76000 | 0 | 0 | Completed in 2004. | [10 empty] | 2002 | Investment | 124.3 | 124.3 |  |  | Yes | N/A | Yes
ONG | UNDP | Sector phase-out of methyl bromide in vegetable, cut flower and tobacco production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 53 | N | O | I | MeBr | 54 | 54 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 | 2006-12-01 |  |  | 500000 | 0 | 500000 | 232457 | 46.49% | 267543 | 0 | 93640.05 | 37500 | 0 | 17434.275 | 20065.725 | 0 | Phase III ongoing. Refer to Yearly Progress Report for MY-Plan submitted to ExCom 44 for more detailed information and update on overall project implementation status. | [10 empty] | 2003 | Investment | 70.3 | 70.3 |  |  | Yes | N/A | Yes
FIN | UNDP | Project preparation for the formulation of a CFC phase-out plan | Individual | ASP | LEB | PHA | 42 | PRP | 55 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2004-12-01 | 2005-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 | 0 | 1200 | 0 | 1200 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2004 | Investment
ONG | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (first tranche) | Multi-Year | ASP | LEB | PHA | 44 | INV | 57 | N | O | I | CFC | 55 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 | 2006-07-01 |  |  | 1061420 | 0 | 1061420 | 15968 | 1.504% | 1045452 | 0 | 365908.2 | 79607 | 0 | 1197.6075 | 78409.3925 | 0 | Approved in Dec 2004. Procurement activities for manufacturing sector (Aerosol, Foam, Refrigeration) ongoing. Equipment delivery in 2006. | [10 empty] | 2004 | Investment | 417 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fourth tranche) | Multi-Year | ASP | LEB | FUM | 44 | INV | 58 | N | O | I | MeBr | 36 | 36 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 400000 | 0 | 400000 | 0 | 0% | 400000 | 0 | 140000 | 30000 | 0 | 0 | 30000 | 0 | Phase IV ongoing. Refer to Yearly Progress Report for MY-Plan submitted to ExCom 44 for more detailed information and update on overall project implementation status. | [10 empty] | 2004 | Investment | 34.3 | 34.3 |  |  | Yes | N/A | Yes
ONG | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | LEB | SEV | 44 | INS | 59 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 155090 | 0 | 155090 | 42164 | 27.19% | 112926 | 0 | 39524.1 | 11632 | 0 | 3162.368 | 8469.632 | 0 | During 2005, the Ozone Unit of Lebanon continued its monitoring, data collection, programme implementation and awareness activities. Some of the activities to be highlighted for 2005 include: overseeing the entry into force of the ODS licensing system; oversight management of the MB and NPMP projects; implementing various awareness activities; and, participating in regional/international meetings as Lebanon’s representatives. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | LEB | SEV | 45 | TAS | 60 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 45872 | 0 | 45872 | 0 | 0% | 45872 | 0 | 16055.2 | 4128 | 0 | 0 | 4128 | 0 | Approved in Apr 05. Activities initiated. Consultants identified. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 61 | N | O | I | MeBr | 34 | 11 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 210000 | 0 | 210000 | 0 | 0% | 210000 | 0 | 73500 | 15750 | 0 | 0 | 15750 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment | 0 |  |  |  | Latest | Latest | Latest
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | LES | REF | 21 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-06-01 | 2002-03-01 | 20000 | -2704 | 17296 | 17296 | 100% | 0 | 0 | 0 | 2600 | -352 | 2248 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | LES | REF | 22 | TAS | 04 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2000-12-01 | 56095 | 0 | 56095 | 56095 | 100% | 0 | 0 | 0 | 7292 | 0 | 7292 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Sebha Unit | Individual | AFR | LIB | FOA | 32 | INV | 05 | A | O | I | CFC | 26 | 19 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  |  |  | 128097 | 0 | 128097 | 92618 | 72.3% | 35479 | 0 | 0 | 16653 | 0 | 12040.622 | 4612.378 | 0 | Canceled in 2005. Missions took place in March and May. In the end project was canceled as company could not agree with ExCom milestone. | [10 empty] | 2000 | Investment
COM | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Garabouli Unit | Individual | AFR | LIB | FOA | 32 | INV | 06 | A | O | I | CFC | 40 | 40 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-12-01 |  | 109810 | 0 | 109810 | 38112 | 34.71% | 71698 | 0 | 35849 | 14275 | 0 | 4954.4559 | 9320.5441 | 0 | Completed in 2005. Missions took place in March and May. Equipment installed, trials completed and local works finalized. Project completed. | [10 empty] | 2000 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Electrical Household Appliance-Tajura by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | LIB | FOA | 32 | INV | 07 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2005-12-01 |  | 119802 | 0 | 119802 | 110956 | 92.62% | 8846 | 0 | 4423 | 15574 | 0 | 14424.0392 | 1149.9608 | 0 | Completed in 2005. Missions took place March and May. Equipment installed, trials completed and local works finalized. Project completed. | [10 empty] | 2000 | Investment
ONG | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Ben Ghazi Unit | Individual | AFR | LIB | FOA | 32 | INV | 08 | A | O | I | CFC | 31 | 22 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 | 2006-07-01 |  |  | 124860 | 0 | 124860 | 104749 | 83.89% | 20111 | 0 | 7038.85 | 16232 | 0 | 13617.5378 | 2614.4622 | 0 | Missions took place in March and May. Equipment ordered and installation to take place by October. Verification mission postponed to early 2006. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | LIB | FOA | 32 | PRP | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2000-12-01 | 2001-12-01 |  | 2001-03-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | LIB | FOA | 33 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | -1934 | 23066 | 23066 | 100% | 0 | 0 | 0 | 3250 | -251 | 2999 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Essadek | Individual | AFR | LIB | FOA | 34 | INV | 12 | A | O | I | CFC | 32 | 32 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 |  | 129109 | 0 | 129109 | 132593 | 102.7% | -3484 | 0 | 0 | 16784 | 0 | 17236.9154 | -452.9154 | 0 | Completed in 2005. Missions took place in March and May. Equipment installed, trials completed and local works finalized. Project completed. Apparent overrun to be resolved in 2006. | [10 empty] | 2001 | Investment
COM | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Hilal Africa | Individual | AFR | LIB | FOA | 34 | INV | 13 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 |  | 113727 | 0 | 113727 | 114602 | 100.8% | -875 | 0 | 0 | 14785 | 0 | 14898.7538 | -113.7538 | 0 | Completed in 2005. Missions took place in March and May. Equipment installed, trials completed and local works finalized. Project completed. Apparent overrun to be resolved in 2006. | [10 empty] | 2001 | Investment
COM | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate El Hani | Individual | AFR | LIB | FOA | 35 | INV | 14 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 |  | 112440 | 0 | 112440 | 111429 | 99.1% | 1011 | 0 | 505.5 | 14617 | 0 | 14485.5718 | 131.4282 | 0 | Completed in 2005. Missions took place in March and May. Supplier able to visit and resolve pending issued. Equipment commissioned, trials successful and local works finalized. Project completed. | [10 empty] | 2001 | Investment
ONG | UNDP | Phase out of CFC-11 by conversion to liquid carbon dioxide (LCD) in the manufacture of flexible polyurethane foam at El Houria Unit Plant | Individual | AFR | LIB | FOA | 35 | INV | 15 | A | O | I | CFC | 96 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 | 2006-12-01 |  |  | 520405 | 0 | 520405 | 453260 | 87.1% | 67145 | 0 | 23500.75 | 67245 | 0 | 58568.7468 | 8676.2532 | 0 | Missions took place in March and May. Company reorganization still ongoing. Very difficult to source a tank locally or regionally within budget. Beamech not able to offer any solutions. Project still on hold. New mission scheduled in 2006. | [10 empty] | 2001 | Investment
COM | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Ali Sannoga | Individual | AFR | LIB | FOA | 35 | INV | 16 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 |  | 125640 | 0 | 125640 | 125269 | 99.7% | 371 | 0 | 185.5 | 16333 | 0 | 16284.7706 | 48.2294 | 0 | Completed in 2005. Missions took place in March and May. Equipment installed, trials completed and local works finalized. Project completed. | [10 empty] | 2001 | Investment
COM | UNDP | Project preparation for 4 projects in the rigid foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 |  | 12500 | 0 | 12500 | 0 | 0% | 12500 | 0 | 12500 | 1625 | 0 | 0 | 1625 | 0 | Completed in 2002. | [10 empty] | 2002 | Investment
COM | UNDP | Project preparation for 6 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 |  | 12500 | 0 | 12500 | 0 | 0% | 12500 | 0 | 12500 | 1625 | 0 | 0 | 1625 | 0 | Completed in 2002. | [10 empty] | 2002 | Investment
COM | UNDP | Project preparation for 3 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-12-01 |  | 20000 | 0 | 20000 | 10854 | 54.27% | 9146 | 0 | 9146 | 2600 | 0 | 1411.02 | 1188.98 | 0 | Completed in 2003. | [10 empty] | 2002 | Investment
FIN | UNDP | Training in MAC sector | RMP-Component | ASP | MAL | REF | 04 | TRA | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-10-01 | 1993-12-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Institutional strengthening in relation to projects on reduction of ozone depleting substances | Individual | ASP | MAL | SEV | 09 | INS | 08 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-12-01 | 2003-04-01 | 322520 | -15703 | 306817 | 306817 | 100% | 0 | 0 | 0 | 41928 | -2041 | 39887 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam sheet at Jumaya Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 10 | INV | 11 | A | O | R | CFC | 150 | 150 | 0 | 0 | 1993-06-01 | 1993-12-01 | 1994-12-01 |  | 1993-12-01 | 1997-12-01 | 235811 | 62 | 235873 | 235873 | 100% | 0 | 0 | 0 | 30655 | 8 | 30663 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 10 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-12-01 |  | 1994-03-01 | 1997-12-01 | 50000 | 4438 | 54438 | 54438 | 100% | 0 | 0 | 0 | 6500 | 577 | 7077 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | National ODS conference | Individual | ASP | MAL | SEV | 10 | TRA | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-07-01 |  | 1993-07-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Key Asset Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 15 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-11-01 |  | 1995-02-01 | 1998-12-01 | 690000 | -15755 | 674245 | 674245 | 100% | 0 | 0 | 0 | 89700 | -2048 | 87652 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane insulation foam at Insafoam Insulation Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 16 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 310000 | -3393 | 306607 | 306607 | 100% | 0 | 0 | 0 | 40300 | -441 | 39859 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Island Resources Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 17 | A | O | I | TCA/CFC | 17 | 17 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-04-01 | 1998-12-01 | 230000 | -14204 | 215796 | 215796 | 100% | 0 | 0 | 0 | 29900 | -1846 | 28054 | 0 | 0 | Completed in 1994. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Conversion of metal cleaning processes from trichloroethane solvents to non-ODS organic solvents at Ngai Cheong Metal Industries | Individual | ASP | MAL | SOL | 11 | INV | 18 | A | O | I | TCA | 2 | 2 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-11-01 |  | 1995-04-01 | 1998-12-01 | 63480 | 0 | 63480 | 63480 | 100% | 0 | 0 | 0 | 8252 | 0 | 8252 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Main Plant | Individual | ASP | MAL | SOL | 11 | INV | 19 | A | O | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-10-01 |  | 1994-05-01 | 1998-12-01 | 113570 | -2661 | 110909 | 110909 | 100% | 0 | 0 | 0 | 14764 | -346 | 14418 | 0 | 0 | Completed in 1994. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Port Klang Plant | Individual | ASP | MAL | SOL | 11 | INV | 20 | A | O | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-10-01 |  | 1995-04-01 | 1998-12-01 | 173280 | 25992 | 199272 | 199272 | 100% | 0 | 0 | 0 | 22526 | 3379 | 25905 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polysterene and polyethylene foam sheet at Associated Air-Pack Industries, Sdb. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 21 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 234000 | 17126 | 251126 | 251126 | 100% | 0 | 0 | 0 | 30420 | 2226 | 32646 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of polyurethane insulated panel at Cycle World Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 22 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-03-01 |  | 1997-06-01 | 2000-12-01 | 353000 | -1 | 352999 | 352999 | 100% | 0 | 0 | 0 | 45890 | 0 | 45890 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-12 in the manufacture of EPS/EPE foam sheet at Pulai Lamipak Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 23 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1994-12-01 |  | 1996-08-01 | 2002-03-01 | 355000 | -17066 | 337934 | 337934 | 100% | 0 | 0 | 0 | 46150 | -2219 | 43931 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin, spoiler and moulded flexible foam at P.U. Tech Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 24 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 198000 | 0 | 198000 | 198000 | 100% | 0 | 0 | 0 | 25740 | 0 | 25740 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin polyurethane foam at P.U. Mate Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 25 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 113000 | -9294 | 103706 | 103706 | 100% | 0 | 0 | 0 | 14690 | -1208 | 13482 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam at Pexafoam Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 26 | A | O | I | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 2003-09-01 | 195000 | -5077 | 189923 | 189923 | 100% | 0 | 0 | 0 | 25350 | -660 | 24690 | 0 | 0 | Completed in 1995. Financially completed in 2003. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at N.L.Y. Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 27 | A | O | I | CFC | 55 | 55 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 130000 | -14651 | 115349 | 115349 | 100% | 0 | 0 | 0 | 16900 | -1905 | 14995 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the integral circuit lead frame cleaning processes at San Matech Sdn. Bhd. | Individual | ASP | MAL | SOL | 12 | INV | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-07-01 |  |  | 1995-07-01 | 141000 | -141000 | 0 | 0 |  | 0 | 0 | 0 | 18330 | -18330 | 0 | 0 | 0 | Canceled in 1995. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of home refrigerators at Sharp Roxy Appliance Corp. | Individual | ASP | MAL | REF | 12 | INV | 29 | A | O | D | CFC | 65 | 65 | 0 | 0 | 1994-03-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 962000 | -103353 | 858647 | 858647 | 100% | 0 | 0 | 0 | 125060 | -13436 | 111624 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Safety and technical programme to aid manufacturers of aerosol products | Individual | ASP | MAL | ARS | 12 | TAS | 30 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1996-03-01 |  | 1995-12-01 | 2001-12-01 | 145700 | -40377 | 105323 | 105323 | 100% | 0 | 0 | 0 | 18941 | -5249 | 13692 | 0 | 0 | Completed in 1995. Financially completed in 2001. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 12 | PRP | 31 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of flexible polyurethane foam (slabstock) at small scale producers | Individual | ASP | MAL | FOA | 12 | INV | 33 | A | O | I | CFC | 80 | 80 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-03-01 |  | 1998-08-01 | 2000-12-01 | 1045000 | -55552 | 989448 | 989448 | 100% | 0 | 0 | 0 | 135850 | -7222 | 128628 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of 111 TCA in the automobile bumper cleaning processes at Perusahaan Otomobil National Bhd. (Proton) | Individual | ASP | MAL | SOL | 12 | INV | 35 | A | O | I | TCA | 20 | 20 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1995-12-01 |  | 1995-04-01 | 1998-12-01 | 700439 | -59344 | 641095 | 641095 | 100% | 0 | 0 | 0 | 91057 | -7715 | 83342 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at United Refrigerator Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 37 | A | O | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-12-01 | 2003-07-01 | 351200 | -11852 | 339348 | 339348 | 100% | 0 | 0 | 0 | 45656 | -1541 | 44115 | 0 | 0 | Completed in 1997. Financially completed in 2003. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane foam panels for cold storage at Wong Brothers Electrical and Refrigeration Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 38 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1999-03-01 | 2001-12-01 | 299000 | -1 | 298999 | 298999 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-05-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Eversoft Foam Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 39 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1996-12-01 | 1998-12-01 | 185000 | -1 | 184999 | 184999 | 100% | 0 | 0 | 0 | 24050 | 0 | 24050 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Nian Aik Foam Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 40 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 245000 | -53100 | 191900 | 191900 | 100% | 0 | 0 | 0 | 31850 | -6903 | 24947 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid panels for commercial refrigerators at Pangkat Refrigeration Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 41 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 210000 | -6736 | 203264 | 203264 | 100% | 0 | 0 | 0 | 27300 | -876 | 26424 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of refrigeration products at Oyl Appliances | Individual | ASP | MAL | REF | 13 | INV | 42 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-12-01 |  | 1997-12-01 | 2002-03-01 | 625100 | -38549 | 586551 | 586551 | 100% | 0 | 0 | 0 | 81263 | -5011 | 76252 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of polyurethane foam for pipe insulation at Allied Foam Insulation | Individual | ASP | MAL | FOA | 13 | INV | 43 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 276000 | -2955 | 273045 | 273045 | 100% | 0 | 0 | 0 | 35880 | -384 | 35496 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at Phoenix Base Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 44 | A | O | I | CFC | 61 | 61 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-06-01 |  | 1995-02-01 | 1998-12-01 | 165000 | 12784 | 177784 | 177784 | 100% | 0 | 0 | 0 | 21450 | 1662 | 23112 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at Lian Pang Refrigerator and Electrical Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 45 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-07-01 |  | 1998-10-01 | 2003-09-01 | 201100 | -1 | 201099 | 201099 | 100% | 0 | 0 | 0 | 26143 | 0 | 26143 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam for use as imitation wood at Saferay (M) SDN BHD | Individual | ASP | MAL | FOA | 15 | INV | 46 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1997-06-01 | 1998-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of pipe insulation at Ricwil Sdn Bhd | Individual | ASP | MAL | FOA | 15 | INV | 47 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 118000 | -13464 | 104536 | 104536 | 100% | 0 | 0 | 0 | 15340 | -1750 | 13590 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of moulded and flexible PU foams at Dream Products Snd. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 48 | A | O | D | CFC | 15 | 15 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-11-01 |  | 1998-09-01 | 2000-07-01 | 66500 | -154 | 66346 | 66346 | 100% | 0 | 0 | 0 | 8645 | -20 | 8625 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels at Rigid Foam Industries, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 49 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1997-12-01 | 2000-07-01 | 335000 | -3198 | 331802 | 331802 | 100% | 0 | 0 | 0 | 43550 | -416 | 43134 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels and shipyard insulation works at Leading Refrigeration and Engineering, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 50 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 214000 | -13246 | 200754 | 200754 | 100% | 0 | 0 | 0 | 27820 | -1722 | 26098 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 15 | PRP | 52 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase out of the use of CFC in the manufacture of rigid PU panels at Shaga Cooling Technology | Individual | ASP | MAL | FOA | 15 | INV | 56 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1996-10-01 | 2000-12-01 | 190000 | -12498 | 177502 | 177502 | 100% | 0 | 0 | 0 | 24700 | -1625 | 23075 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to hydrocarbon technology in the manufacture of aerosol products at Maya Chemical Industries Sdn., Bhd. | Individual | ASP | MAL | ARS | 17 | INV | 60 | A | O | R | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 37808 | 0 | 37808 | 37808 | 100% | 0 | 0 | 0 | 4915 | 0 | 4915 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured PUF molded products at Urethane Technologies Sdn., Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 61 | A | O | D | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-07-01 |  | 1997-12-01 | 2000-12-01 | 199000 | -7010 | 191990 | 191990 | 100% | 0 | 0 | 0 | 25870 | -911 | 24959 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Alloychem Malaysia Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 64 | A | O | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2001-12-01 | 2003-11-01 | 99500 | -13228 | 86272 | 86272 | 100% | 0 | 0 | 0 | 12935 | -1720 | 11215 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Artwright Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 65 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2002-03-01 | 90320 | 0 | 90320 | 90320 | 100% | 0 | 0 | 0 | 11742 | 0 | 11742 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured/integral skin PUF molded at Muda Murni Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 66 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2000-12-01 | 236500 | -52362 | 184138 | 184138 | 100% | 0 | 0 | 0 | 30745 | -6807 | 23938 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of molded/integral skin PUF at Bristol Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 67 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-02-01 | 2000-07-01 | 123400 | -475 | 122925 | 122925 | 100% | 0 | 0 | 0 | 16042 | -61 | 15981 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Sze Chuan Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 68 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at TM Cooling Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 70 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam decorative products at Florafoam Marketing Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 71 | A | O | D | CFC | 23 | 23 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1997-06-01 | 2000-12-01 | 152000 | -1 | 151999 | 151999 | 100% | 0 | 0 | 0 | 19760 | 0 | 19760 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Converson of production of portable fire extinguishers at Eversafe | Individual | ASP | MAL | HAL | 18 | INV | 72 | A | O | D | Halon | 574 | 574 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 2002-03-01 | 179586 | -4214 | 175372 | 175372 | 100% | 0 | 0 | 0 | 23346 | -548 | 22798 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Umbrella project for elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration at 4 small enterprises: Lim Yew, Exquisite, FMC, Noblelane | Individual | ASP | MAL | REF | 18 | INV | 73 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2001-12-01 | 2003-04-01 | 680000 | -49438 | 630562 | 630562 | 100% | 0 | 0 | 0 | 88400 | -6427 | 81973 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1997-10-01 | [7 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Sanyo Industries (Malaysia) Berhad | Individual | ASP | MAL | REF | 18 | INV | 74 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 183260 | -1 | 183259 | 183259 | 100% | 0 | 0 | 0 | 23824 | 0 | 23824 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 18 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 18000 | -4 | 17996 | 17996 | 100% | 0 | 0 | 0 | 2340 | -1 | 2339 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
COM | UNDP | Umbrella project to phase out ODS at SMEs in the aerosol sector | Individual | ASP | MAL | ARS | 19 | INV | 85 | A | O | I | CFC | 250 | 250 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1998-04-01 |  | 2005-12-01 |  | 1486660 | 0 | 1486660 | 1321752 | 88.91% | 164908 | 0 | 82454 | 193266 | 0 | 171827.9378 | 21438.0622 | 0 | Completed in 2005. Safety audit workshop took place Dec. 2005. Final report due early 2006 |  |  |  | 1999-07-01 |  | 2001-12-01 |  |  |  |  | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology for the manufacture of flexible polyurethane foam at Nite Beauty Industries | Individual | ASP | MAL | FOA | 19 | INV | 88 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-06-01 | 1999-12-01 | 36875 | 0 | 36875 | 36875 | 100% | 0 | 0 | 0 | 4794 | 0 | 4794 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC -free technology for the manufacture of flexible polyurethane foam at Far East Foam Industries | Individual | ASP | MAL | FOA | 19 | INV | 89 | A | O | I | CFC | 41 | 41 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-09-01 | 2001-12-01 | 209000 | -2275 | 206725 | 206725 | 100% | 0 | 0 | 0 | 27170 | -296 | 26874 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 20 | INS | 91 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-10-01 |  | 1998-10-01 | 2003-04-01 | 215000 | -5523 | 209477 | 209477 | 100% | 0 | 0 | 0 | 27950 | -718 | 27232 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1996 | Non-Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | MAL | SEV | 21 | PRP | 93 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2004-12-01 | 100000 | -34365 | 65635 | 65635 | 100% | 0 | 0 | 0 | 13000 | -4467 | 8533 | 0 | 0 | Completed in 1998. Financially Completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Amstrad | Individual | ASP | MAL | FOA | 22 | INV | 94 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 108800 | -86 | 108714 | 108714 | 100% | 0 | 0 | 0 | 14144 | -11 | 14133 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-06-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Anchor Profit Sdn Bhd | Individual | ASP | MAL | FOA | 22 | INV | 95 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 | 0 | 17030 | 0 | 17030 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Rollbond | Individual | ASP | MAL | FOA | 22 | INV | 96 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 155500 | 0 | 155500 | 155500 | 100% | 0 | 0 | 0 | 20215 | 0 | 20215 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at RCA Group | Individual | ASP | MAL | FOA | 22 | INV | 98 | A | O | I | CFC | 42 | 42 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2000-12-01 | 284500 | -12922 | 271578 | 271578 | 100% | 0 | 0 | 0 | 36985 | -1680 | 35305 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CT Foam | Individual | ASP | MAL | FOA | 23 | INV | 99 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 236000 | 0 | 236000 | 236000 | 100% | 0 | 0 | 0 | 30680 | 0 | 30680 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufature of polyurethane foam at Kwang Tai Refrigeration | Individual | ASP | MAL | REF | 23 | INV | 103 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-04-01 | 316000 | -9988 | 306012 | 306012 | 100% | 0 | 0 | 0 | 41080 | -1298 | 39782 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free techology in the manufacture of polyurethane foam at Hi Tech Insulation | Individual | ASP | MAL | FOA | 23 | INV | 104 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2002-03-01 | 96815 | -3942 | 92873 | 92873 | 100% | 0 | 0 | 0 | 12586 | -512 | 12074 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Heng Huat Furniture | Individual | ASP | MAL | FOA | 23 | INV | 105 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 269500 | 0 | 269500 | 269500 | 100% | 0 | 0 | 0 | 35035 | 0 | 35035 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Frank Chee | Individual | ASP | MAL | FOA | 23 | INV | 106 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 174350 | 0 | 174350 | 174350 | 100% | 0 | 0 | 0 | 22666 | 0 | 22666 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at OAL Enterprise | Individual | ASP | MAL | FOA | 23 | INV | 107 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 58300 | -19611 | 38689 | 38689 | 100% | 0 | 0 | 0 | 7579 | -2549 | 5030 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 24 | PRP | 108 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project (timber) | Individual | ASP | MAL | FUM | 24 | PRP | 109 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-11-01 | 2004-12-01 | 30000 | -983 | 29017 | 29017 | 100% | 0 | 0 | 0 | 3900 | -128 | 3772 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of polyurethane foam at Tenaga | Individual | ASP | MAL | FOA | 25 | INV | 111 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 308800 | 0 | 308800 | 308800 | 100% | 0 | 0 | 0 | 40144 | 0 | 40144 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | MAL | SEV | 26 | INS | 114 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-05-01 | 215000 | -36884 | 178116 | 178116 | 100% | 0 | 0 | 0 | 27950 | -4795 | 23155 | 0 | 0 | Completed in 2000. Financially completed in 2005. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Minply | Individual | ASP | MAL | FOA | 26 | INV | 115 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 158050 | -3297 | 154753 | 154753 | 100% | 0 | 0 | 0 | 20547 | -429 | 20118 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Grorich | Individual | ASP | MAL | FOA | 26 | INV | 116 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 174150 | 0 | 174150 | 174150 | 100% | 0 | 0 | 0 | 22640 | 0 | 22640 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of two projects in commercial refrigeration subsector | Individual | ASP | MAL | REF | 27 | PRP | 117 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of three projects in rigid foam subsector | Individual | ASP | MAL | FOA | 27 | PRP | 119 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of cold room panels and insulation slabs by conversion to HCFC-141b at PKL Insulation | Individual | ASP | MAL | FOA | 28 | INV | 121 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-12-01 | 2003-07-01 | 57019 | -1434 | 55585 | 55585 | 100% | 0 | 0 | 0 | 7412 | -186 | 7226 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and blocks) at Polyedge Trading | Individual | ASP | MAL | FOA | 28 | INV | 122 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2002-02-01 |  | 2000-12-01 | 2001-12-01 | 80650 | 0 | 80650 | 80650 | 100% | 0 | 0 | 0 | 10485 | 0 | 10485 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1999 | Investment
FIN | UNDP | Retroactive project for phasing-out ODS consumption in the manufacture of cold room panels by conversion to HCFC-141b at FMCP Sdn. Bhd. | Individual | ASP | MAL | FOA | 28 | INV | 123 | A | O | R | CFC | 12 | 12 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-07-01 | 2001-12-01 | 45557 | 0 | 45557 | 45557 | 100% | 0 | 0 | 0 | 5922 | 0 | 5922 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 and R502 consumption at Thermo Cooling Engineering, Sdn. Bhd. | Individual | ASP | MAL | REF | 28 | INV | 126 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 46502 | -1900 | 44602 | 44602 | 100% | 0 | 0 | 0 | 6045 | -247 | 5798 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 and R-502 in the manufacture of commercial refrigerators by conversion HCFC-141b, HCFC-22 and HFC-404a at Gai Hin Refrigeration Sdn. Bhd. | Individual | ASP | MAL | REF | 29 | INV | 128 | A | O | I | CFC | 41 | 41 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 354147 | -16712 | 337435 | 337435 | 100% | 0 | 0 | 0 | 46039 | -2173 | 43866 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
ONG | UNDP | Alternatives to the use of methyl bromide on Malaysian timbers | Individual | ASP | MAL | FUM | 29 | DEM | 129 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 | 2006-07-01 |  |  | 230000 | 0 | 230000 | 197575 | 85.9% | 32425 | 0 | 11348.75 | 29900 | 0 | 25684.75 | 4215.25 | 0 | Dept.of Crop Protection training completed in 05. Analysis of results and final report expected in early 2006. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Masterfoam Products | Individual | ASP | MAL | FOA | 29 | INV | 130 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 208900 | 0 | 208900 | 208900 | 100% | 0 | 0 | 0 | 27157 | 0 | 27157 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible polyurethane foam at Kemas Mekar Sdn Bhd | Individual | ASP | MAL | FOA | 29 | INV | 131 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 385900 | -11270 | 374630 | 374630 | 100% | 0 | 0 | 0 | 50167 | -1465 | 48702 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 30 | PRP | 133 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -9678 | 20322 | 20322 | 100% | 0 | 0 | 0 | 3900 | -1258 | 2642 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | MAL | REF | 30 | PRP | 134 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 20000 | -4121 | 15879 | 15879 | 100% | 0 | 0 | 0 | 2600 | -537 | 2063 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam and to LCD technology in the manufacture of flexible molded foam at Sy Heng Huat | Individual | ASP | MAL | FOA | 31 | INV | 136 | A | O | I | CFC | 46 | 46 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-01-01 | 2003-11-01 | 272235 | 0 | 272235 | 272235 | 100% | 0 | 0 | 0 | 35391 | 0 | 35391 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to LCD and water-based technology in the manufacture of flexible molded foam at Unique Field | Individual | ASP | MAL | FOA | 31 | INV | 137 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 109990 | 0 | 109990 | 109990 | 100% | 0 | 0 | 0 | 14299 | 0 | 14299 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible molded foam at Pointray | Individual | ASP | MAL | FOA | 31 | INV | 138 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 130896 | -27 | 130869 | 130869 | 100% | 0 | 0 | 0 | 17016 | -4 | 17012 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at eleven small and sedium-sized enterprises | Individual | ASP | MAL | REF | 32 | INV | 140 | A | O | I | CFC | 65 | 65 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 960658 | 0 | 960658 | 930870 | 96.9% | 29788 | 0 | 0 | 115672 | 0 | 112085.2526 | 3586.7474 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at three enterprises (SKE Fookmei, Master Shanghai Turnparts and Maltar Industries) | Individual | ASP | MAL | REF | 32 | INV | 141 | A | O | I | CFC | 35 | 35 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-11-01 | 2005-09-01 | 505184 | 0 | 505184 | 492293 | 97.45% | 12891 | 0 | 0 | 65570 | 0 | 63896.8218 | 1673.1782 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
COM | UNDP | Extension of the institutional strengthening project (Phase IV) | Individual | ASP | MAL | SEV | 32 | INS | 142 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2005-03-01 |  | 215000 | 0 | 215000 | 175917 | 81.82% | 39083 | 362 | 19541.5 | 27950 | 0 | 22869.21 | 5080.79 | 47.06 | Completed in 2005. Enforcement visits to sites of completed project to ensure sustainability. Coordinated with IAs to monitor phase out activities. Undertook data reporting and public awareness activities | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation in the soil fumigant sector | Individual | ASP | MAL | FUM | 36 | PRP | 146 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-11-01 | 10000 | 0 | 10000 | 8906 | 89.06% | 1094 | 0 | 0 | 1300 | 0 | 1157.78 | 142.22 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
COM | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 38 | INS | 148 | N | T | I | CFC | 23 | 23 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 |  | 279500 | 0 | 279500 | 237318 | 84.91% | 42182 | 0 | 21091 | 36335 | 0 | 30851.34 | 5483.66 | 0 | Completed in 2005. Data collection, supervision and monitoring of NPP activities. Public awareness activities conducted to ensure sustainability | [10 empty] | 2002 | Non-Investment
COM | UNDP | Project preparation for the formulation of fumigant methyl bromide | Individual | ASP | MAL | FUM | 42 | PRP | 150 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-01-01 |  | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2005. Project approved at ExCom 43. Operationally complete. | [10 empty] | 2004 | Investment
ONG | UNDP | Technical assistance programme to install alternatives and phase-out all remaining non-QPS uses of methyl bromide | Individual | ASP | MAL | FUM | 43 | TAS | 151 | N | O | I | MeBr | 9 | 0 | 0 | 0 | 2004-07-01 |  | 2007-12-01 | 2007-12-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 40000 | 18000 | 0 | 0 | 18000 | 0 | ProDoc signed. Ntl training and adoption of alternatives underway.Project activities on track. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | MAL | SEV | 44 | INS | 153 | N | T | I | CFC | 23 | 11 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 279500 | 0 | 279500 | 0 | 0% | 279500 | 0 | 97825 | 20963 | 0 | 0 | 20963 | 0 | The Ozone Office continued its regular monitoring and supervision visits to enterprises with completed phase out activities to ensure sustainability of ODS phase out. It worked closely with IAs on effective projects and NPP implementation. Public awareness activities and stakeholders’ workshop were conducted to promote and ensure sustainability of ODS phase out. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | MAL | SEV | 45 | TAS | 155 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 91743 | 0 | 91743 | 0 | 0% | 91743 | 0 | 32110.05 | 8257 | 0 | 0 | 8257 | 0 | TORs for national and intl consultants defined for recruitment. Surveys and data collection to be initiated 1Q 2006 under supervision and guidance of national consultant | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Aerosol conversion at Compagnie Manufacturiere de Produits Cosmetiques Ltee. | Individual | AFR | MAR | ARS | 12 | INV | 03 | A | O | D | CFC | 25 | 25 | 0 | 0 | 1994-03-01 | 1996-06-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 62150 | 0 | 62150 | 62150 | 100% | 0 | 0 | 0 | 8080 | 0 | 8080 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Preparation of projects in the refrigeration and foam sectors | Individual | AFR | MAR | REF | 12 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Blyfridge Ltd. | Individual | AFR | MAR | REF | 15 | INV | 05 | A | O | I | CFC | 2 | 2 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 197208 | -20442 | 176766 | 176766 | 100% | 0 | 0 | 0 | 25637 | -2658 | 22979 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at A.H. Bahemia | Individual | AFR | MAR | REF | 15 | INV | 06 | A | O | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 213500 | -25495 | 188005 | 188005 | 100% | 0 | 0 | 0 | 27755 | -3314 | 24441 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
TRF | UNDP | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | RMP-Component | AFR | MAR | REF | 17 | TAS | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1996-07-01 |  |  | 1999-07-01 | 176350 | -162281 | 14069 | 14069 | 100% | 0 | 0 | 0 | 22926 | -21096 | 1830 | 0 | 0 | Transferred in 1999. Financially completed in 1999. |  |  |  | 1999-07-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | MAU | REF | 39 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Update-Comp | AFR | MAU | REF | 41 | TAS | 11 | N | O | I | CFC | 2 | 0 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 | 2007-12-01 |  |  | 100995 | 0 | 100995 | 32754 | 32.43% | 68241 | 0 | 13648.2 | 9090 | 0 | 2948.0059 | 6141.9941 | 0 | Projet document signed. Equipment in place. Tender process for the subcontract with R&R Centre selection ongoing. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: awareness and incentive programme for MAC, commercial and industrial end-users | RMP-Update-Comp | AFR | MAU | REF | 41 | TAS | 12 | N | O | I | CFC | 3 | 0 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 100000 | 0 | 100000 | 6873 | 6.873% | 93127 | 0 | 32594.45 | 9000 | 0 | 618.57 | 8381.43 | 0 | National consultant hired. During visit of Int.Cons. application form for incentives was discussed in detail. The project is waiting for the launch of awareness workshop to start the activities. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Update-Comp | ASP | MDV | REF | 38 | TAS | 05 | A | O | I | CFC | 4 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-05-01 | 2006-12-01 |  |  | 115000 | 0 | 115000 | 36644 | 31.86% | 78356 | 0 | 27424.6 | 14950 | 0 | 4763.72 | 10186.28 | 0 | Attempt at contracting NOU to carry out incentive programme stalled due to contractual conditions. Project on hold. | [10 empty] | 2002 | Non-Investment
FIN | UNDP | Preparation of terms of reference for investment projects identified in the country programme | Individual | LAC | MEX | SEV | 04 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1993-12-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 2277 | 52277 | 52277 | 100% | 0 | 0 | 0 | 6500 | 296 | 6796 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1991 | Investment
FIN | UNDP | Preparatory study on halons, inventory, and proposals for revisions of existing standards | Individual | LAC | MEX | HAL | 06 | TAS | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1994-04-01 |  | 1995-09-01 | 1998-12-01 | 25000 | 2223 | 27223 | 27223 | 100% | 0 | 0 | 0 | 3250 | 289 | 3539 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 11 | PRP | 22 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 14 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-12-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Ensambladora de Refrigeradores (Enresa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 30 | A | O | I | CFC | 47 | 47 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 867033 | -51481 | 815552 | 815552 | 100% | 0 | 0 | 0 | 112714 | -6693 | 106021 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Astral (Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 31 | A | O | I | CFC | 344 | 344 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 2439932 | -80899 | 2359033 | 2359033 | 100% | 0 | 0 | 0 | 317191 | -10517 | 306674 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at (Comasa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 32 | A | O | D | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-12-01 |  | 1995-11-01 | 1998-12-01 | 1188724 | -152860 | 1035864 | 1035864 | 100% | 0 | 0 | 0 | 154534 | -19872 | 134662 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
CLO | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at Fabricacion de Compresores S.A. (Facosa, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 33 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-06-01 |  |  | 1996-05-01 | 584000 | -581001 | 2999 | 2999 | 100% | 0 | 0 | 0 | 75920 | -75530 | 390 | 0 | 0 | Canceled in 1996. Financially completed in 1996. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Supermatic, S.A. (Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 34 | A | O | I | CFC | 366 | 366 | 0 | 0 | 1994-12-01 | 1996-03-01 | 1996-06-01 |  | 1997-04-01 | 2000-12-01 | 2017517 | -5120 | 2012397 | 2012397 | 100% | 0 | 0 | 0 | 262277 | -666 | 261611 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Estufas y Refrigeradores Nacionales S.A. (Erna, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 35 | A | O | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-09-01 | 2000-12-01 | 1038309 | -49630 | 988679 | 988679 | 100% | 0 | 0 | 0 | 134980 | -6452 | 128528 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of 1,1,1 TCA from the precision cleaning processes at Lucas Diesel | Individual | LAC | MEX | SOL | 15 | INV | 36 | A | O | D | TCA | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-06-01 |  | 1997-07-01 | 1999-12-01 | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 21840 | 0 | 21840 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-113 from the textile cleaning processes at Procesadora y Revitalizadora | Individual | LAC | MEX | SOL | 15 | INV | 37 | A | O | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-09-01 |  | 1996-08-01 | 2000-12-01 | 71337 | -1889 | 69448 | 69448 | 100% | 0 | 0 | 0 | 9274 | -246 | 9028 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 17 | PRP | 39 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1996-11-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Extension of institutional strengthening | Individual | LAC | MEX | SEV | 17 | INS | 40 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-12-01 |  | 1996-10-01 | 2003-11-01 | 47500 | 47500 | 95000 | 95000 | 100% | 0 | 0 | 0 | 6175 | 6175 | 12350 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [10 empty] | 1995 | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Paneles | Individual | LAC | MEX | FOA | 18 | INV | 41 | A | O | I | CFC | 81 | 81 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1997-08-01 | 2000-12-01 | 100000 | -5098 | 94902 | 94902 | 100% | 0 | 0 | 0 | 13000 | -663 | 12337 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels at Galvamet, S.A. de C.V. | Individual | LAC | MEX | FOA | 18 | INV | 42 | A | O | D | CFC | 89 | 89 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1996-04-01 | 1998-12-01 | 195500 | -6004 | 189496 | 189496 | 100% | 0 | 0 | 0 | 25415 | -781 | 24634 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Recovery of CFC-12 servicing of domestic refrigeration at Vitromatic Comercial y Servicios Integrados | RMP-Component | LAC | MEX | REF | 18 | TAS | 43 | N | O | I | CFC | 76 | 76 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1997-10-01 | 2002-12-01 | 352610 | -47579 | 305031 | 305031 | 100% | 0 | 0 | 0 | 45839 | -6185 | 39654 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 18 | PRP | 45 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels and doors at Multypanel | Individual | LAC | MEX | FOA | 19 | INV | 46 | A | O | I | CFC | 306 | 306 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-08-01 | 2001-12-01 | 428000 | -85789 | 342211 | 342211 | 100% | 0 | 0 | 0 | 55640 | -11153 | 44487 | 0 | 0 | Completed in 1997. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) - Group project (10 enterprises) | Individual | LAC | MEX | FOA | 19 | INV | 47 | A | O | I | CFC | 100 | 100 | 0 | 0 | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1998-11-01 | 2001-08-01 | 507500 | -43764 | 463736 | 463736 | 100% | 0 | 0 | 0 | 65975 | -5689 | 60286 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Carmovil | Individual | LAC | MEX | FOA | 20 | INV | 48 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 80500 | -1092 | 79408 | 79408 | 100% | 0 | 0 | 0 | 10465 | -142 | 10323 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Umbrella project for conversion to CFC-free technology in the manufacture of polyurethane shoe soles (seven enterprises) | Individual | LAC | MEX | FOA | 20 | INV | 49 | A | O | I | CFC | 95 | 95 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 2001-08-01 | 2003-04-01 | 1201590 | -3434 | 1198156 | 1198156 | 100% | 0 | 0 | 0 | 156207 | -446 | 155761 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1996 | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODSs under the Montreal Protocol | Individual | LAC | MEX | SEV | 20 | INS | 50 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-10-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1996 | Non-Investment
FIN | UNDP | Project preparation in the foam and solvent sectors | Individual | LAC | MEX | SEV | 21 | PRP | 52 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 52000 | -2539 | 49461 | 49461 | 100% | 0 | 0 | 0 | 6760 | -330 | 6430 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | LAC | MEX | SEV | 22 | PRP | 53 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Acsa | Individual | LAC | MEX | FOA | 22 | INV | 54 | A | O | I | CFC | 94 | 94 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 597000 | -1890 | 595110 | 595110 | 100% | 0 | 0 | 0 | 77610 | -245 | 77365 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Industrias Pol-Rym S.A. de C.V., (IPR) | Individual | LAC | MEX | FOA | 22 | INV | 55 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1998-11-01 |  | 1998-11-01 | 2001-12-01 | 421500 | -4909 | 416591 | 416591 | 100% | 0 | 0 | 0 | 54795 | -638 | 54157 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Tecnopolimeros | Individual | LAC | MEX | FOA | 22 | INV | 56 | A | O | I | CFC | 54 | 54 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2002-11-01 | 359000 | -1642 | 357358 | 357358 | 100% | 0 | 0 | 0 | 46670 | -213 | 46457 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-06-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Termopuertos | Individual | LAC | MEX | FOA | 22 | INV | 57 | A | O | D | CFC | 10 | 10 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-07-01 | 2000-12-01 | 78300 | -2557 | 75743 | 75743 | 100% | 0 | 0 | 0 | 10179 | -332 | 9847 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | MEX | SEV | 22 | TAS | 59 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1998-05-01 |  | 1998-05-01 | 2001-12-01 | 60000 | -1400 | 58600 | 58600 | 100% | 0 | 0 | 0 | 7800 | -182 | 7618 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Conversion to CFC-free technolog in the manufacture of rigid foam at Valsa Panel | Individual | LAC | MEX | FOA | 23 | INV | 66 | A | O | D | CFC | 24 | 24 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1998-07-01 | 2000-12-01 | 92000 | -312 | 91688 | 91688 | 100% | 0 | 0 | 0 | 11960 | -41 | 11919 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at group project Pumex | Individual | LAC | MEX | FOA | 23 | INV | 69 | A | O | I | CFC | 168 | 168 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 1133881 | -20532 | 1113349 | 1113349 | 100% | 0 | 0 | 0 | 147405 | -2669 | 144736 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin foam at Air Design | Individual | LAC | MEX | FOA | 23 | INV | 71 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 80500 | -1178 | 79322 | 79322 | 100% | 0 | 0 | 0 | 10465 | -153 | 10312 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid foam (spray) and integral skin foam at Con Espuma | Individual | LAC | MEX | FOA | 23 | INV | 72 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 96100 | -2230 | 93870 | 93870 | 100% | 0 | 0 | 0 | 12493 | -290 | 12203 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Group Project (Orca) | Individual | LAC | MEX | FOA | 23 | INV | 73 | A | O | I | CFC | 190 | 190 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-11-01 | 1471500 | -154071 | 1317429 | 1317429 | 100% | 0 | 0 | 0 | 191295 | -20029 | 171266 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for a halon sector phase out programme | Individual | LAC | MEX | HAL | 24 | PRP | 76 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-12-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 5 projects in the foam sector | Individual | LAC | MEX | FOA | 24 | PRP | 79 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 2 methyl bromide (flowers and crop storage) alternative demonstration projects | Individual | LAC | MEX | FUM | 24 | PRP | 80 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid foam for refrigeration systems at Refrigeración Rodríguez | Individual | LAC | MEX | FOA | 25 | INV | 82 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 132650 | -31006 | 101644 | 101644 | 100% | 0 | 0 | 0 | 17245 | -4031 | 13214 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Renewal of institutional strengthening project | Individual | LAC | MEX | SEV | 25 | INS | 83 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-07-01 |  | 2000-07-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Conversion to water-based technology in the manufacture of integral skin foam at Moldecor, S.A. de C.V. | Individual | LAC | MEX | FOA | 25 | INV | 84 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2000-04-01 | 2001-12-01 | 86500 | -845 | 85655 | 85655 | 100% | 0 | 0 | 0 | 11245 | -110 | 11135 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
ONG | UNDP | Alternatives to methyl bromide for structural fumigation in Mexico | Individual | LAC | MEX | FUM | 26 | DEM | 86 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 | 2006-07-01 |  |  | 498300 | 0 | 498300 | 330533 | 66.33% | 167767 | 0 | 58718.45 | 64779 | 0 | 42969.29 | 21809.71 | 0 | Strategy to organise final training sessions agreed to, including harmonisation with ongoing bilateral with Gov't of Cda. Final workshops delayed due to scheduling problems with experts. Completion projected for mid-2006. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Group Project Valcom (Uriel, Limas, Tecknipol, Anzaldua, and Negrete) | Individual | LAC | MEX | FOA | 26 | INV | 87 | A | O | I | CFC | 44 | 44 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-08-01 | 2002-11-01 | 314961 | -3630 | 311331 | 311331 | 100% | 0 | 0 | 0 | 40945 | -472 | 40473 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of three projects in the foam sector | Individual | LAC | MEX | FOA | 27 | PRP | 89 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-07-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | MEX | FOA | 30 | PRP | 94 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Foam phaseout sector strategy | Individual | LAC | MEX | FOA | 31 | TAS | 96 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-01-01 |  | 2001-12-01 | 2004-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 31 | INS | 97 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-08-01 | 2003-11-01 | 190000 | -45584 | 144416 | 144416 | 100% | 0 | 0 | 0 | 24700 | -5926 | 18774 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b or water-blown technology in rigid polyurethane foam (spray) and to water based formulations in integral skin foam at Comsisa | Individual | LAC | MEX | FOA | 31 | INV | 98 | A | O | I | CFC | 69 | 69 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2003-08-01 |  | 2003-10-01 | 2004-01-01 | 424050 | 0 | 424050 | 424050 | 100% | 0 | 0 | 0 | 55127 | 0 | 55127 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Project preparation in the recycling halon sector | Individual | LAC | MEX | HAL | 33 | PRP | 101 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Foam sector ODS phaseout plan (first trnache) | Individual | LAC | MEX | FOA | 35 | INV | 103 | N | O | I | CFC | 145 | 145 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2003-07-01 |  | 2004-11-01 |  | 833150 | 0 | 833150 | 833140 | 100% | 10 | 0 | 5 | 101647 | 0 | 101645.78 | 1.22 | 0 | Completed in 2004. | [10 empty] | 2000 | Investment
ONG | UNDP | National halon management and banking programme | Individual | LAC | MEX | HAL | 35 | TAS | 104 | A | O | I | Halon | 230 | 230 | 0 | 0 | 2001-12-01 | 2002-08-01 | 2005-01-01 | 2006-07-01 |  |  | 500000 | 0 | 500000 | 429782 | 85.96% | 70218 | 0 | 24576.3 | 65000 | 0 | 55871.66 | 9128.34 | 0 | While halon bank installed at CAISA, Govt indicated it wishes to use remaining balance for further awareness activities to assure sustainability. Outreach activities to take place in 2006. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the storage fumigant sector | Individual | LAC | MEX | FUM | 36 | PRP | 105 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2003. Financially closed in 2005. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of the country programme update | Individual | LAC | MEX | SEV | 38 | CPG | 111 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-10-01 | 48046 | 0 | 48046 | 30091 | 62.63% | 17955 | 0 | 0 | 6246 | 0 | 3911.83 | 2334.15 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Foam sector ODS phase-out plan (second tranche) | Individual | LAC | MEX | FOA | 42 | INV | 117 | N | O | D | CFC | 192 | 160 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 | 2006-12-01 |  |  | 1109120 | 0 | 1109120 | 828923 | 74.74% | 280197 | 0 | 98068.95 | 83184 | 0 | 62169.225 | 21014.775 | 0 | 7 workshops in order to inform enterprises about implementation procedures. Project uses reimbursement modality. 85 enterprises (of the 111 originally considered) found eligible and applications received started to be processed. | [10 empty] | 2004 | Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | MEX | SEV | 45 | TAS | 127 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 114679 | 0 | 114679 | 0 | 0% | 114679 | 0 | 40137.65 | 10321 | 0 | 0 | 10321 | 0 | Approved in Apr 05. Activities initiated and consultants identified. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 32 | TAS | 09 | A | O | I | CFC | 6 | 6 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-12-01 | 2004-01-01 | 102658 | -3518 | 99140.3 | 99140 | 100% | 0.3 | 0 | 0 | 13346 | -457 | 12888.761 | 0.039 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2000 | Investment
COM | UNDP | Implementation of the RMP: monitoring the activities in the refrigerant management plan | RMP-Component | AFR | MLI | REF | 32 | TAS | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2005-07-01 |  | 15455 | 0 | 15455 | 15413 | 99.73% | 42 | 0 | 21 | 2009 | 0 | 2003.5404 | 5.4596 | 0 | Completed in 2005. Final report received from National Consultant in July 2005. Government satisfied with report. | [10 empty] | 2000 | Non-Investment
ONG | UNDP | Implementation of the RMP update: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 45 | TAS | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 10000 | 4500 | 0 | 0 | 4500 | 0 | Int.Cons visited Mali in June but communication problems exist between NOU and CO and projects is starting up very slowly. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | MLW | REF | 17 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | MLW | SEV | 18 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 | 0 | 910 | 0 | 910 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MLW | REF | 19 | TAS | 05 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -311 | 106009 | 106009 | 100% | 0 | 0 | 0 | 13822 | -40 | 13782 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 21 | PRP | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 22 | PRP | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for a methyl bromide (tobacco) alternative demonstration project | Individual | AFR | MLW | FUM | 24 | PRP | 09 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-02-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Robry Ltd. | Individual | AFR | MLW | FOA | 26 | INV | 12 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 156500 | 0 | 156500 | 138952 | 88.79% | 17548 | 0 | 0 | 20345 | 0 | 18063.76 | 2281.24 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1998 | Investment
COM | UNDP | Phaseout of all non-essential and non-QPS methyl bromide (release of first tranche) | Multi-Year | AFR | MLW | FUM | 32 | DEM | 15 | N | O | I | MeBr | 19 | 19 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2001-12-01 |  | 2001-12-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2001. | [10 empty] | 2000 | Investment | 109.7 | 109.7 |  |  | Yes | N/A | Yes
COM | UNDP | Second payment under the national programme for the phaseout of all non-essential and non-quarantine and pre-shipment applications of methyl bromide | Multi-Year | AFR | MLW | FUM | 34 | INV | 16 | N | O | I | MeBr | 21 | 21 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2002-08-01 |  | 2004-12-01 |  | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment | 90 | 90 |  |  | Yes | N/A | Yes
COM | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (release of third tranche) | Multi-Year | AFR | MLW | FUM | 40 | INV | 18 | N | O | I | MeBr | 41 | 41 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 |  | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 56250 | 0 | 56250 | 0 | 0 | Completed in 2004. | [10 empty] | 2003 | Investment | 49.3 | 49.3 |  |  | Yes | N/A | Yes
ONG | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (fourth tranche) | Multi-Year | AFR | MLW | FUM | 43 | INV | 21 | N | O | I | MeBr | 30 | 30 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  |  | 849824 | 0 | 849824 | 643757 | 75.75% | 206067 | 0 | 72123.45 | 63737 | 0 | 48281.9265 | 15455.0735 | 0 | Further to MLFS evaluation conducted Dec 2004, exit strategy developed to ensure sustainability of phaseout. Project operationally complete with remaining $ being used for ongoing training. Consumption at zero. | [10 empty] | 2004 | Investment | 0
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | EUR | MOL | REF | 25 | TAS | 02 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2002-05-01 | 2002-11-01 | 254150 | -304 | 253846 | 253846 | 100% | 0 | 0 | 0 | 33040 | -40 | 33000 | 0 | 0 | Completed in 2002. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for the RMP proposal | RMP-Update-Comp | EUR | MOL | REF | 41 | PRP | 08 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: technical assistance programme | RMP-Component | EUR | MOL | REF | 44 | TAS | 12 | N | O | I | CFC | 7 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 173495 | 0 | 173495 | 52371 | 30.19% | 121124 | 0 | 42393.4 | 15615 | 0 | 4713.5258 | 10901.4742 | 0 | Workshops conducted & Nat.cons. provided services for End-User, MAC and for Tools&Equipm programs. Procurement of equipm carried out. Translation and distribution of materials & information disseminated at Exhibition “Food & Drinks 2005”. | [10 empty] | 2004 | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | MON | REF | 33 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant | RMP-Update-Comp | ASP | MON | REF | 35 | TAS | 06 | A | O | I | CFC | 6 | 6 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2005-11-01 | 108600 | 0 | 108600 | 108600 | 100% | 0 | 0 | 0 | 14118 | 0 | 14118 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of integral skin and cold cured molded PUF products at Maghreb Elastoplast | Individual | AFR | MOR | FOA | 20 | INV | 04 | A | O | D | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1997-09-01 | 2000-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MOR | FOA | 21 | PRP | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 80000 | -13195 | 66805 | 66805 | 100% | 0 | 0 | 0 | 10400 | -1715 | 8685 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richbond S.A. | Individual | AFR | MOR | FOA | 22 | INV | 08 | A | O | I | CFC | 150 | 150 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-06-01 |  |  | 2004-12-01 | 470625 | -40036 | 430589 | 430589 | 100% | 0 | 0 | 0 | 61181 | -5205 | 55976 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | AFR | MOR | SEV | 22 | PRP | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Dolidol | Individual | AFR | MOR | FOA | 22 | INV | 10 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 1999-06-01 |  |  | 2003-12-01 | 475822 | -61553 | 414269 | 414269 | 100% | 0 | 0 | 0 | 61857 | -8002 | 53855 | 0 | 0 | Canceled in 2001. Financially completed in 2003. | [10 empty] | 1997 | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Sodiflex and Tiznit Plastic S.A. | Individual | AFR | MOR | FOA | 23 | INV | 12 | A | O | I | CFC | 85 | 85 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2005-09-01 | 517300 | -5023 | 512277 | 512277 | 100% | 0 | 0 | 0 | 67249 | -653 | 66596.01 | 0 | 0 | Canceled in 2004. Financially completed in 2005. | [10 empty] | 1997 | Investment
CLO | UNDP | Phase out of CFC in the manufacture fo flexible foam (slabstock) at Salidor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 13 | A | O | I | CFC | 48 | 48 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richdor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 14 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 62300 | 0 | 62300 | 62300 | 100% | 0 | 0 | 0 | 8099 | 0 | 8099 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam at Panaf Isolation S.A. | Individual | AFR | MOR | FOA | 23 | INV | 15 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-09-01 | 2001-12-01 | 137000 | -3191 | 133809 | 133809 | 100% | 0 | 0 | 0 | 17810 | -415 | 17395 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Molen Industrie S.A. | Individual | AFR | MOR | FOA | 23 | INV | 16 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-12-01 | 1999-12-01 |  | 2002-06-01 | 2003-11-01 | 56070 | 0 | 56070 | 56070 | 100% | 0 | 0 | 0 | 7289 | 0 | 7289 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1997 | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Mousse d'Or S.A. | Individual | AFR | MOR | FOA | 23 | INV | 19 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 280350 | 0 | 280350 | 280350 | 100% | 0 | 0 | 0 | 36446 | 0 | 36446 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | AFR | MOR | FOA | 24 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1998 | Investment
CLO | UNDP | Conversion to LCD technology in the manufacture of flexible foam (slabstock) to replace CFC-11 at Bonbino Confort | Individual | AFR | MOR | FOA | 25 | INV | 22 | A | O | I | CFC | 90 | 90 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  |  | 2004-12-01 | 490200 | 0 | 490200 | 490200 | 100% | 0 | 0 | 0 | 63726 | 0 | 63726 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b/water technology in the manufacture of rigid polyurethane spray foam at Batcomar S.A. | Individual | AFR | MOR | FOA | 25 | INV | 23 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-07-01 | 2002-03-01 | 72000 | -10826 | 61174 | 61174 | 100% | 0 | 0 | 0 | 9360 | -1407 | 7953 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Interfer by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 43 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 78973 | 0 | 78973 | 78973 | 100% | 0 | 0 | 0 | 10266 | 0 | 10266 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Engequife by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 44 | A | O | I | CFC | 7 | 7 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 56391 | -146 | 56245 | 56245 | 100% | 0 | 0 | 0 | 7331 | -19 | 7312 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | MOZ | REF | 21 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -1643 | 18357 | 18357 | 100% | 0 | 0 | 0 | 2600 | -214 | 2386 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MOZ | REF | 22 | TAS | 06 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 115809 | -138 | 115671 | 115671 | 100% | 0 | 0 | 0 | 15055 | -18 | 15037 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
CLO | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (tobacco) | Individual | AFR | MOZ | FUM | 27 | PRP | 08 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 1999 | Investment
CLO | UNDP | Formulation of the investment components of theRMP | Individual | ASP | MYA | REF | 39 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  |  | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Canceled in 2004. While project prepared, it was given to UNIDO. | [10 empty] | 2003 | Investment
FIN | UNDP | Preparation of a refrigeration recovery and recycling project | Individual | ASP | NEP | REF | 27 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-07-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration subsector | Individual | ASP | NEP | REF | 27 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2001-12-01 | 20000 | -15000 | 5000 | 5000 | 100% | 0 | 0 | 0 | 2600 | -1950 | 650 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1999 | Investment
COM | UNDP | Implementation of the RMP: monitoring activities included in the RMP | RMP-Component | ASP | NEP | REF | 28 | TAS | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2005-01-01 | 2002-02-01 |  | 2005-12-01 |  | 8894 | 0 | 8894 | 3519 | 39.57% | 5375 | 0 | 2687.5 | 1156 | 0 | 457.383 | 698.617 | 0 | Completed in 2005. National consultants submitted final reports and government satisfied. Project completed. | [10 empty] | 1999 | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | ASP | NEP | REF | 28 | TAS | 08 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2003-10-01 | 2003-11-01 | 88577 | -1 | 88576 | 88576 | 100% | 0 | 0 | 0 | 11515 | 0 | 11515 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1999 | Investment
COM | UNDP | Project preparation for the refrigerant management plan update | Individual | ASP | NEP | REF | 43 | PRP | 12 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2005-07-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Activities completed, RMP-Update approved. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: recovery and recycling, retrofit and their monitoring | RMP-Component | ASP | NEP | REF | 44 | TAS | 16 | N | O | I | No_ODP | 11 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 57495 | 0 | 57495 | 0 | 0% | 57495 | 0 | 11499 | 5175 | 0 | 0 | 5175 | 0 | Project document submitted to Government for signature. Wf signature document. Activities to start in 2006. | [10 empty] | 2004 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | NER | REF | 21 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-03-01 | 2002-03-01 | 20000 | -3085 | 16915 | 16915 | 100% | 0 | 0 | 0 | 2600 | -401 | 2199 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | NER | REF | 27 | TAS | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 2002-01-01 | 2001-04-01 |  | 2004-12-01 | 2005-11-01 | 15455 | 0 | 15455 | 12150 | 78.62% | 3305 | 0 | 0 | 2009 | 0 | 1579.3821 | 429.6179 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1999 | Non-Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | NER | REF | 27 | TAS | 07 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2001-04-01 |  | 2003-08-01 | 2003-10-01 | 87603 | -8661 | 78942 | 78942 | 100% | 0 | 0 | 0 | 11388 | -1126 | 10262 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | NER | REF | 37 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-11-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2002 | Investment
COM | UNDP | Preparation of the RMP update proposal (investment component) | RMP-Update-Comp | LAC | NIC | REF | 41 | PRP | 10 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 14964 | 99.76% | 36 | 0 | 36 | 1125 | 0 | 1122.3 | 2.7 | 0 | Completed in 2005. Project prepared, submitted and approved at 45th Excom Meeting in April 2005. All payments done, awaiting final budget review and closure. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Project preparation for the formulation of transitional strategy for aerosol inhalant drug products | Individual | LAC | NIC | ARS | 42 | PRP | 11 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-07-01 | 2005-04-01 | 2006-07-01 |  |  | 30000 | 0 | 30000 | 3494 | 11.65% | 26506 | 0 | 26506 | 2250 | 0 | 262.05 | 1987.95 | 0 | Project prepared and ready for submission to the 47th Excom Meeting. Payments to consultants expected in 2006. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP update: incentive programme to promote good practices in refrigeration | RMP-Component | LAC | NIC | REF | 45 | TAS | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2008-04-01 | 2008-04-01 |  |  | 85000 | 0 | 85000 | 498 | 0.5859% | 84502 | 0 | 16900.4 | 7650 | 0 | 44.82 | 7605.18 | 0 | Approved in Apr 05. Project Document signed. UNDP as cooperating agency has provided assistance to NOU to start activities. Local consultant contracted. | [10 empty] | 2005 | Investment
FIN | UNDP | National seminar on industry and protection of the ozone layer | Individual | AFR | NIR | SEV | 04 | TRA | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-11-01 |  | 1992-12-01 | 1997-12-01 | 49650 | -23201 | 26449 | 26449 | 100% | 0 | 0 | 0 | 6455 | -3016 | 3439 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | NIR | SEV | 09 | INS | 06 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-01-01 | 1996-03-01 |  | 2001-01-01 | 2003-09-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1993 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | NIR | SEV | 17 | PRP | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Royal Foam Products | Individual | AFR | NIR | FOA | 20 | INV | 12 | A | O | D | CFC | 43 | 43 | 0 | 0 | 1996-10-01 | 1998-08-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 34000 | -600 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4420 | -78 | 4342 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Teju Industries Limited | Individual | AFR | NIR | FOA | 20 | INV | 13 | A | O | D | CFC | 47 | 47 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-10-01 | 2003-01-01 | 75000 | -6859 | 68141 | 68141 | 100% | 0 | 0 | 0 | 9750 | -892 | 8858 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam for thermoware in Eleganza Industries Ltd. at Ikeja, Lagos | Individual | AFR | NIR | FOA | 20 | INV | 14 | A | O | I | CFC | 48 | 48 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 314000 | -4065 | 309935 | 309935 | 100% | 0 | 0 | 0 | 40820 | -528 | 40292 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Sara Products Limited | Individual | AFR | NIR | FOA | 20 | INV | 15 | A | O | D | CFC | 28 | 28 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1999-07-01 | 2001-12-01 | 107000 | -2075 | 104925 | 104925 | 100% | 0 | 0 | 0 | 13910 | -270 | 13640 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | NIR | FOA | 21 | PRP | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Winco Foam Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 21 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 117200 | -321 | 116879 | 116879 | 100% | 0 | 0 | 0 | 15236 | -42 | 15194 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Bajabure Industrial Complex Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 22 | A | O | I | CFC | 32 | 32 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2002-11-01 | 135400 | -11117 | 124283 | 124283 | 100% | 0 | 0 | 0 | 17602 | -1445 | 16157 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Elico Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 23 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 133900 | -13658 | 120242 | 120242 | 100% | 0 | 0 | 0 | 17407 | -1776 | 15631 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Mouka Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 24 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2004-01-01 | 143600 | -3462 | 140138 | 140138 | 100% | 0 | 0 | 0 | 18668 | -450 | 18218 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1997 | Investment
COM | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Safa Foam Products (Nig) Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 25 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-12-01 |  | 2003-08-01 |  | 146400 | 0 | 146400 | 146400 | 100% | 0 | 0 | 0 | 19032 | 0 | 19032 | 0 | 0 | Completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manuyfacture of rigid PUF insulation products at Aluminium Manufacturing Company of Nigeria Plc (Alumaco) | Individual | AFR | NIR | FOA | 23 | INV | 26 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-12-01 |  | 2001-11-01 | 2002-11-01 | 38000 | -400 | 37600 | 37600 | 100% | 0 | 0 | 0 | 4940 | -52 | 4888 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for thermoware in 3 enterprises of the Eleganza Group (Eleganza Cooler and Household Industries Ltd., Eleganza Ceramics and Cooler Industries Ltd.) | Individual | AFR | NIR | FOA | 23 | INV | 27 | A | O | I | CFC | 74 | 74 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 568000 | -25762 | 542238 | 542238 | 100% | 0 | 0 | 0 | 73840 | -3349 | 70491 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Ugochukwu Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 28 | A | O | I | CFC | 119 | 119 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-07-01 | 2002-11-01 | 407600 | 0 | 407600 | 407600 | 100% | 0 | 0 | 0 | 52988 | 0 | 52988 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF spray insulation at Polyurethane Manufacturers Ltd. (Polyma) | Individual | AFR | NIR | FOA | 23 | INV | 29 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2004-01-01 | 80500 | -339 | 80161 | 80161 | 100% | 0 | 0 | 0 | 10465 | -44 | 10421 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Orbit Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 31 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-07-01 | 2003-11-01 | 135200 | -1 | 135199 | 135199 | 100% | 0 | 0 | 0 | 17576 | 0 | 17576 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Olufoam and Plastic Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 32 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1998-11-01 | 2001-10-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 84600 | 0 | 84600 | 84600 | 100% | 0 | 0 | 0 | 10998 | 0 | 10998 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [7 empty] | 2003-12-01 |  |  | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Okin Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 33 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-11-01 | 2002-11-01 | 133200 | 0 | 133200 | 133200 | 100% | 0 | 0 | 0 | 17316 | 0 | 17316 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Marta Industries (Nig.) Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 34 | A | O | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 130600 | -1299 | 129301 | 129301 | 100% | 0 | 0 | 0 | 16978 | -169 | 16809 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Confidence Products and Services Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 35 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 142300 | 0 | 142300 | 141090 | 99.15% | 1210 | 0 | 0 | 18499 | 0 | 18341.7 | 157.3 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Chemical and Wire Manufacturers Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 36 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-01-01 | 2003-11-01 | 164500 | 0 | 164500 | 164500 | 100% | 0 | 0 | 0 | 21385 | 0 | 21385 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [7 empty] | 2003-07-01 |  |  | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Bodefoam Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 37 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 136400 | 0 | 136400 | 136400 | 100% | 0 | 0 | 0 | 17732 | 0 | 17732 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Group Enterprises Nig. Ltd. (Polly Foam) | Individual | AFR | NIR | FOA | 26 | INV | 38 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 128900 | -2349 | 126551 | 126551 | 100% | 0 | 0 | 0 | 16757 | -305 | 16452 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pesaco Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 39 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1998-11-01 | 2000-08-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 126400 | 0 | 126400 | 126400 | 100% | 0 | 0 | 0 | 16432 | 0 | 16432 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation | Individual | AFR | NIR | FOA | 26 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Yinka-Oba Foam Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 42 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2003-08-01 | 2005-10-01 | 185300 | 0 | 185300 | 184671 | 99.66% | 629 | 0 | 0 | 24089 | 0 | 24007.23 | 81.77 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Universal Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 43 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-11-01 | 135300 | 0 | 135300 | 135300 | 100% | 0 | 0 | 0 | 17589 | 0 | 17589 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of three projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 45 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1999 | Investment
COM | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at United Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 46 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1999-07-01 | 2001-10-01 | 2002-02-01 |  | 2003-08-01 |  | 137310 | 0 | 137310 | 131212 | 95.56% | 6098 | 0 | 3049 | 17850 | 0 | 17057.2733 | 792.7267 | 0 | Completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Tinuola Bay Industries Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 47 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-09-01 | 2003-09-01 | 119410 | 0 | 119410 | 119410 | 100% | 0 | 0 | 0 | 15523 | 0 | 15523 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Diamond Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 49 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2001-11-01 | 2002-11-01 | 112150 | 0 | 112150 | 112150 | 100% | 0 | 0 | 0 | 14580 | 0 | 14580 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to liquid carbon dioxide blown technology in the manufacture of molded flexible polyurethane foam at Automotive Component Industries Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 50 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 204761 | 0 | 204761 | 204761 | 100% | 0 | 0 | 0 | 26619 | 0 | 26619 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Rubez (Nig.) Ltd. (Current Foam) | Individual | AFR | NIR | FOA | 29 | INV | 55 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2002-12-01 |  | 2003-08-01 | 2005-11-01 | 89803 | 0 | 89803 | 89738 | 99.93% | 65 | 0 | 0 | 11674 | 0 | 11665.5503 | 8.4497 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1999 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafco Industries Limited | Individual | AFR | NIR | FOA | 29 | INV | 56 | A | O | I | CFC | 34 | 34 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-12-01 |  | 58559 | 0 | 58559 | 58559 | 100% | 0 | 0 | 0 | 7613 | 0 | 7613 | 0 | 0 | Completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Vono Products PLC | Individual | AFR | NIR | FOA | 29 | INV | 57 | A | O | I | CFC | 56 | 56 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 173782 | 0 | 173782 | 173782 | 100% | 0 | 0 | 0 | 22592 | 0 | 22592 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride blown technology in the manufacture of flexible polyurethane foam at Betaday Industries Ltd. | Individual | AFR | NIR | FOA | 29 | INV | 58 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 104495 | -1 | 104494 | 104494 | 100% | 0 | 0 | 0 | 13584 | 0 | 13584 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to mehtylene chloride in the manufacture of flexible polyurethane foam at Vito Company (Nig.) Ltd., Victory Foam | Individual | AFR | NIR | FOA | 29 | INV | 59 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 133560 | -188 | 133372 | 133372 | 100% | 0 | 0 | 0 | 17363 | -25 | 17338 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of seven projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 60 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-04-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
COM | UNDP | Preparation of 8 projects in the general foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 63 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 |  | 30000 | 0 | 30000 | 52689 | 175.6% | -22689 | 0 | 0 | 3900 | 0 | 6849.57 | -2949.57 | 0 | Completed in 2000. Apparent overrun to be resolved in 2006. | [10 empty] | 2000 | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 64 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. | [10 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Sokoto Foam Factory (Nig.) Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 65 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-12-01 | 2005-09-01 | 141421 | -4328 | 137093 | 137093 | 100% | 0 | 0 | 0 | 18385 | -563 | 17822 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manfuacture of flexible slabstock foam by conversion to methylene chloride at Abeokuta Commercial and Industrial Co. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 66 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 118468 | -382 | 118086 | 118086 | 100% | 0 | 0 | 0 | 15401 | -50 | 15351 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Celplas Industries Limited | Individual | AFR | NIR | FOA | 31 | INV | 67 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-11-01 | 2002-12-01 | 215325 | 0 | 215325 | 215325 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Completed in 2002. Financially completed in 2002. | [10 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Climax Ind. Ltd. (Ely Foam) | Individual | AFR | NIR | FOA | 31 | INV | 68 | A | O | I | CFC | 30 | 30 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 173362 | -575 | 172787 | 172787 | 100% | 0 | 0 | 0 | 22537 | -75 | 22462 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Wappah Foam Limited | Individual | AFR | NIR | FOA | 31 | INV | 69 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 130081 | -4 | 130077 | 130077 | 100% | 0 | 0 | 0 | 16911 | -1 | 16910 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 2000 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafa Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 70 | A | O | I | CFC | 34 | 34 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-12-01 |  | 124667 | 0 | 124667 | 114786 | 92.07% | 9881 | 0 | 4940.5 | 16207 | 0 | 14922.447 | 1284.553 | 0 | Completed in 2002. | [10 empty] | 2000 | Investment
FIN | UNDP | Technical assistance to prepare a refrigeration management plan (RMP) | RMP-Component | AFR | NIR | REF | 32 | TAS | 72 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2003-01-01 |  | 2002-12-01 | 2003-11-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2000 | Non-Investment
CLO | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 78 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 79 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
CLO | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 81 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 82 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Atuchukwu Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 83 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 118488 | -1 | 118487 | 118487 | 100% | 0 | 0 | 0 | 15403 | 0 | 15403 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Apaco Foam and Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 84 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 147018 | 0 | 147018 | 147018 | 100% | 0 | 0 | 0 | 19112 | 0 | 19112 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Gasfa Industries Nig., Ltd. (Meka Foam) | Individual | AFR | NIR | FOA | 34 | INV | 85 | A | O | I | CFC | 40 | 40 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2003-08-01 | 2005-09-01 | 238843 | -9895 | 228948 | 228948 | 100% | 0 | 0 | 0 | 31050 | -1286 | 29764 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Adig Plastics Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 86 | A | O | I | CFC | 14 | 14 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-04-01 | 112050 | 0 | 112050 | 112050 | 100% | 0 | 0 | 0 | 14567 | 0 | 14567 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Phasing out CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Rima Foam Products Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 88 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 |  | 119036 | 0 | 119036 | 118453 | 99.51% | 583 | 0 | 291.5 | 15475 | 0 | 15399.2084 | 75.7916 | 0 | Completed in 2002. | [10 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Harmony Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 89 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2005-11-01 | 126531 | 0 | 126531 | 112963 | 89.28% | 13568 | 0 | 0 | 16449 | 0 | 14685.1632 | 1763.8368 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
CLO | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Global Plastic Industries, Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 91 | A | O | I | CFC | 5 | 5 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  |  | 2005-09-01 | 36801 | -3512 | 33289 | 33289 | 100% | 0 | 0 | 0 | 4784 | -457 | 4327 | 0 | 0 | Canceled in 2004. Financially completed in 2005. | [10 empty] | 2001 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bibafoam Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 92 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 |  | 114685 | 0 | 114685 | 114685 | 100% | 0 | 0 | 0 | 14909 | 0 | 14909 | 0 | 0 | Completed in 2002. | [10 empty] | 2001 | Investment
COM | UNDP | Renewal of institutional strengthening project (phase II) | Individual | AFR | NIR | SEV | 34 | INS | 93 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-08-01 |  | 200000 | 0 | 200000 | 198514 | 99.26% | 1486 | 0 | 743 | 26000 | 0 | 25806.82 | 193.18 | 0 | Completed in 2003. | [10 empty] | 2001 | Non-Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bamako Industrial, Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 94 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2005-11-01 | 114510 | 0 | 114510 | 111050 | 96.98% | 3460 | 0 | 0 | 14886 | 0 | 14436.2091 | 449.7909 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Agric Services (Nig.), Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 95 | A | O | I | CFC | 44 | 44 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-08-01 | 2005-10-01 | 239160 | 0 | 239160 | 238897 | 99.89% | 263 | 0 | 0 | 31091 | 0 | 31056.8098 | 34.1902 | 0 | Completed in 2003. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to methylene chloride (MC) technology in the manufacture of flexible polyurethane at ten box-foam enterprises in Lagos area | Individual | AFR | NIR | FOA | 35 | INV | 96 | A | O | I | CFC | 199 | 199 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 |  | 1062808 | 0 | 1062808 | 1062808 | 100% | 0 | 0 | 0 | 126909 | 0 | 126909 | 0 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | AFR | NIR | REF | 36 | PRP | 99 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-11-01 | 40000 | -1 | 39999 | 39999 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | AFR | NIR | FOA | 36 | PRP | 100 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Country programme update | Individual | AFR | NIR | SEV | 36 | CPG | 102 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-10-01 | 2006-07-01 |  |  | 241493 | 0 | 241493 | 188058 | 77.87% | 53435 | 0 | 18702.25 | 31394 | 0 | 24447.54 | 6946.55 | 0 | Country surveys completed. Document being written up. Some payments will be required to be made in 2006. Project to be completed in 2006 | [10 empty] | 2002 | Non-Investment
ONG | UNDP | National CFC phase-out plan: foam sector and refrigeration servicing sector (first tranche) | Multi-Year | AFR | NIR | PHA | 38 | INV | 106 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 | 2006-12-01 |  |  | 5013929 | 0 | 5013929 | 2202104 | 43.92% | 2811825 | 1673604 | 984138.75 | 449318 | 0 | 197339.2453 | 251978.7547 | 149978.2709 | Prodoc signed , Regional & Natl Coordinators recruited. Foam expert developed 3 industry sub-projects. Procurement initiated. Meetings at Customs and at National Board of Technical Education. Procurement action initiated on R&R equipment. | [9 empty] | 2005-12-01 | 2002 | Investment | 2388.8 | 2388.8 |  |  | Yes | N/A | Yes
ONG | UNDP | Extension of institutional strengthening project | Individual | AFR | NIR | SEV | 40 | INS | 107 | N | T | I | CFC | 22 | 22 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2005-07-01 | 2006-04-01 |  |  | 260000 | 0 | 260000 | 253208 | 97.39% | 6792 | 0 | 2377.2 | 19500 | 0 | 18990.6 | 509.4 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2003 | Non-Investment
ONG | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | NIR | PHA | 41 | INV | 108 | N | O | I | CFC | 830 | 830 | 0 | 0 | 2003-12-01 |  | 2004-12-01 | 2006-12-01 |  |  | 2976827 | 0 | 2976827 | 0 | 0% | 2976827 | 0 | 1041889.45 | 264834 | 0 | 0 | 264834 | 0 | Prodoc signed. Activities for foam equipment procurement started. R&R equipment procurement to start in 2006. | [10 empty] | 2003 | Investment | 1543.5 | 1543.5 |  |  | Yes | No | No
ONG | UNDP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | NIR | PHA | 44 | INV | 112 | N | O | I | CFC | 851 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2007-03-01 |  |  | 2077141 | 0 | 2077141 | 0 | 0% | 2077141 | 0 | 415428.2 | 183863 | 0 | 0 | 183863 | 0 | Approved in Dec 2004 pending funding disbursement after submission of verification report. Verification report to be submitted March 2006.. | [10 empty] | 2004 | Investment | 956.4 |  |  |  | Latest | No | No
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | PAK | SEV | 14 | INS | 05 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 2001-12-01 | 2003-05-01 | 259000 | -4042 | 254958 | 254958 | 100% | 0 | 0 | 0 | 33670 | -525 | 33145 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non-Investment
COM | UNDP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | PAK | SEV | 35 | INS | 44 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2004-01-01 |  | 2004-01-01 |  | 172666 | 0 | 172666 | 172491 | 99.9% | 175 | 0 | 87.5 | 22447 | 0 | 22424.2496 | 22.7504 | 0 | Completed in 2004. | [10 empty] | 2001 | Non-Investment
ONG | UNDP | Extension of institutional strengthening project: phase 3 | Individual | ASP | PAK | SEV | 41 | INS | 54 | N | T | I | No-ODP | 19 | 10 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 | 2006-07-01 |  |  | 224467 | 0 | 224467 | 82618 | 36.81% | 141849 | 1233 | 49647.15 | 16835 | 0 | 6196.3408 | 10638.6592 | 92.4749 | The Ozone Unit continued to coordinate on-going UNIDO and World Bank programmes in the country. Under the IS project extension approved in December 2004, the Ozone Office continued to focus efforts on policy, enforcement and awareness-raising activities. A full and detailed report of activities achieved during the present IS phase will be presented with the request for renewal of the project. | [10 empty] | 2003 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 11 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible and rigid polyurethane foam at Plastifoam, S.A., Profomsa, and Thermofoam, S.A. | Individual | LAC | PAN | FOA | 13 | INV | 05 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1999-08-01 | 2002-10-01 | 155000 | -13140 | 141860 | 141860 | 100% | 0 | 0 | 0 | 20150 | -1708 | 18442 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PAN | REF | 18 | TAS | 06 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-07-01 | 2003-11-01 | 172465 | -10608 | 161857 | 161857 | 100% | 0 | 0 | 0 | 22420 | -1379 | 21041 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 18 | PRP | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAN | FOA | 21 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2637 | 12363 | 12363 | 100% | 0 | 0 | 0 | 1950 | -343 | 1607 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
CLO | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at Productos Moldeados America S.R. Ltda. (Plasticos Modernos) | Individual | LAC | PAN | FOA | 22 | INV | 09 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2003-11-01 | 339296 | -213326 | 125970 | 125970 | 100% | 0 | 0 | 0 | 44108 | -27732 | 16376 | 0 | 0 | Canceled in 2003. Financially completed in 2003. | [10 empty] | 1997 | Investment
COM | UNDP | Project preparation for update of refrigerant management plan (investment components) | Individual | LAC | PAN | REF | 40 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Project submitted and approved at the 44th Excom Meeting. All payments done. | [10 empty] | 2003 | Investment
ONG | UNDP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | INV | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 250152 | 0 | 250152 | 0 | 0% | 250152 | 0 | 87553.2 | 18762 | 0 | 0 | 18762 | 0 | Project document signed. UNDP mission to establish workplan done. Local coordinator identified but not contracted yet. Disbursements will be reflected in 2006. Annual report and verification completed and submitted to Excom. | [10 empty] | 2004 | Investment | 168.4 | 168.4 |  |  | Yes | Yes | yes
ONG | UNDP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-Year | LAC | PAN | PHA | 47 | INV | 24 | N | O | I | CFC | 36 | 36 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 238000 | 0 | 238000 | 0 | 0% | 238000 | 0 | 83300 | 17850 | 0 | 0 | 17850 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment | 131.95 |  |  |  | Latest | Latest | Latest
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAR | FOA | 22 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of polyurethane foam at Superspuma Del Paraguay SAIC, Suenolar, La Asuncena, and Industrias Cel | Individual | LAC | PAR | FOA | 23 | INV | 04 | A | O | I | CFC | 56 | 56 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-10-01 | 405600 | -118208 | 287392 | 287392 | 100% | 0 | 0 | 0 | 52728 | -15367 | 37361 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | LAC | PAR | REF | 27 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-10-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recyling of CFC-12 refrigerant | RMP-Component | LAC | PAR | REF | 32 | TAS | 08 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2004-12-01 | 2005-11-01 | 285158 | 0 | 285158 | 276807 | 97.07% | 8351 | 0 | 0 | 37071 | 0 | 35985.3565 | 1085.6435 | 0 | Completed in 2004. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | PAR | REF | 33 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Terminal umbrella project to phase out CFC-11 and CFC-12 consumption in the manufacture of commercial refrigeration equipment by replacement with HCFC-141b and HFC-134a at 11 SMEs | Individual | LAC | PAR | REF | 34 | INV | 12 | A | O | I | CFC | 7 | 7 | 0 | 0 | 2001-07-01 | 2001-11-01 | 2005-02-01 |  | 2005-12-01 |  | 410379 | 0 | 410379 | 380617 | 92.75% | 29762 | 0 | 14881 | 53349 | 0 | 49479.9596 | 3869.0404 | 0 | Completed in 2005. New companies approved and equipment ordered, installed , test trials and local works completed. HOP issued Dec. 2005 | [10 empty] | 2001 | Investment
ONG | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | PAR | SOL | 45 | TAS | 14 | N | O | I | TCA/CTC | 2 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 10500 | 2700 | 0 | 0 | 2700 | 0 | Approved in Apr 05. Activities initiated. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | PAR | PHA | 47 | PRP | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2250 | 0 | 0 | 2250 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 13 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1996-07-01 |  | 1995-09-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Alfa S.A. | Individual | LAC | PER | REF | 15 | INV | 03 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-09-01 | 2000-12-01 | 252727 | -567 | 252160 | 252160 | 100% | 0 | 0 | 0 | 32855 | -74 | 32781 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-02-01 | [6 empty] | 1994 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Andina Industrial S.A. | Individual | LAC | PER | REF | 15 | INV | 04 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  |  | 2002-06-01 | 229816 | -75350 | 154466 | 154466 | 100% | 0 | 0 | 0 | 29876 | -9795 | 20081 | 0 | 0 | Canceled in 2000. Financially completed in 2002. |  |  | 1997-09-01 | [7 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coldex S.A. | Individual | LAC | PER | REF | 15 | INV | 05 | A | O | I | CFC | 67 | 67 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1998-01-01 | 2000-12-01 | 748966 | -102197 | 646769 | 646769 | 100% | 0 | 0 | 0 | 97366 | -13286 | 84080 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Lenche S.A. (Inlensa) | Individual | LAC | PER | REF | 15 | INV | 06 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 2002-09-01 | 2003-11-01 | 201443 | -29670 | 171773 | 171773 | 100% | 0 | 0 | 0 | 26188 | -3857 | 22331 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  | 1997-12-01 | [7 empty] | 1994 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Reunidas S.A. (Inresa) | Individual | LAC | PER | REF | 15 | INV | 07 | A | O | D | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1996-06-01 |  |  | 2003-01-01 | 267641 | -91077 | 176564 | 176564 | 100% | 0 | 0 | 0 | 34793 | -11840 | 22953 | 0 | 0 | Canceled in 1999. Financially completed in 2003. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrial Selva S.A. (Indusel) | Individual | LAC | PER | REF | 15 | INV | 08 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2002-03-01 | 412098 | -331 | 411767 | 411767 | 100% | 0 | 0 | 0 | 53573 | -43 | 53530 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the production of polystyrene foam at Productos Moldeados America SR, Ltd. (Promola) | Individual | LAC | PER | FOA | 17 | INV | 09 | A | O | D | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1998-11-01 | 1999-12-01 | 294960 | 0 | 294960 | 294960 | 100% | 0 | 0 | 0 | 38345 | 0 | 38345 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 18 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-03-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Master Service, S.A. | Individual | LAC | PER | REF | 19 | INV | 13 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-02-01 | 2002-04-01 | 140000 | -10839 | 129161 | 129161 | 100% | 0 | 0 | 0 | 18200 | -1409 | 16791 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest feezers at Compañia Peruana de Máquinas para Coser S.A. (Copemaco) | Individual | LAC | PER | REF | 19 | INV | 14 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 193834 | 0 | 193834 | 193834 | 100% | 0 | 0 | 0 | 25198 | 0 | 25198 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers and refrigerators at Formetal | Individual | LAC | PER | REF | 19 | INV | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  |  | 2001-12-01 | 118000 | -64335 | 53665 | 53665 | 100% | 0 | 0 | 0 | 15340 | -8364 | 6976 | 0 | 0 | Canceled in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Col-Frio S.A. | Individual | LAC | PER | REF | 19 | INV | 16 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 175000 | -468 | 174532 | 174532 | 100% | 0 | 0 | 0 | 22750 | -61 | 22689 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PER | REF | 19 | TAS | 17 | A | O | I | CFC | 29 | 29 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 2001-12-01 | 2003-04-01 | 342695 | -53108 | 289587 | 289587 | 100% | 0 | 0 | 0 | 44550 | -6904 | 37646 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | LAC | PER | FUM | 24 | PRP | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2000-06-01 | 2002-12-01 | 25000 | -863 | 24137 | 24137 | 100% | 0 | 0 | 0 | 3250 | -112 | 3138 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of a project in general foam subsector | Individual | LAC | PER | FOA | 27 | PRP | 24 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [10 empty] | 1999 | Investment
COM | UNDP | Phase-out of methyl bromide in soil fumigation | One-off-Phaseout | LAC | PER | FUM | 31 | INV | 28 | N | O | I | MeBr | 4 | 4 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2004-12-01 |  | 209770 | 0 | 209770 | 209770 | 100% | 0 | 0 | 0 | 27270 | 0 | 27270 | 0 | 0 | Completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | PER | FOA | 33 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
ONG | UNDP | Foam sector ODS phaseout plan (covering 5 enterprises: Molflex; Zetaflex; EMSA; Metusa; Polishoes) | Individual | LAC | PER | FOA | 35 | INV | 30 | A | O | I | CFC | 34 | 195 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2005-01-01 | 2006-07-01 |  |  | 325277 | 0 | 325277 | 301916 | 92.82% | 23361 | 0 | 8176.35 | 42286 | 0 | 39249.0707 | 3036.9293 | 0 | Technical assistance component partially completed during 2005. Workshops held, advisory activities undertaken, compliance verification ongoing. Final activities to take place mid 2006. | [10 empty] | 2001 | Investment
COM | UNDP | Formulation of the investment components of the RMP | Individual | LAC | PER | REF | 39 | PRP | 33 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Project submitted and approved at the 43rd Excom Meeting. All payments done. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP update: technical assistance for the refrigeration sector | RMP-Component | LAC | PER | REF | 43 | TAS | 37 | N | O | I | CFC | 17 | 0 | 0 | 0 | 2004-07-01 |  | 2007-12-01 | 2007-12-01 |  |  | 123000 | 0 | 123000 | 0 | 0% | 123000 | 0 | 24600 | 11070 | 0 | 0 | 11070 | 0 | Slow start. Project Document took a long time to be signed and local consultant took a long time to be recruited. UNDP as cooperating agency has assisted NOU to expedite processes. | [10 empty] | 2004 | Investment
FIN | UNDP | Training programme in the refrigeration sector | RMP-Component | ASP | PHI | REF | 04 | TRA | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-04-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 64000 | -1707 | 62293 | 62293 | 100% | 0 | 0 | 0 | 8320 | -222 | 8098 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | PHI | SEV | 08 | CPG | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 39820 | 39820 | 79640 | 79640 | 100% | 0 | 0 | 0 | 5177 | 5177 | 10354 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 11 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-07-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Survey of ODS usage, data base generation and technical assistance for ODS phase-out for small-scale enterprises | Individual | ASP | PHI | SEV | 11 | TAS | 22 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1996-09-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Elimination of CFC-use at small manufacturers of flexible foam | Individual | ASP | PHI | FOA | 12 | INV | 26 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1999-12-01 | 2003-04-01 | 745000 | -262154 | 482846 | 482846 | 100% | 0 | 0 | 0 | 96850 | -34080 | 62770 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the residual use of CFC in the manufacture of extruded polystyrene foam sheet in 3 companies: Concept Packaging Co., Amtes Co., and Q.C. Styropackaging Co. | Individual | ASP | PHI | FOA | 12 | INV | 27 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-12-01 | 1995-03-01 |  | 1997-12-01 | 1999-05-01 | 505000 | -230578 | 274422 | 274422 | 100% | 0 | 0 | 0 | 65650 | -29975 | 35675 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Nikkon Industrial Corporation | Individual | ASP | PHI | FOA | 12 | INV | 28 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-09-01 | 1998-12-01 | 315000 | -46523 | 268477 | 268477 | 100% | 0 | 0 | 0 | 40950 | -6048 | 34902 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible polyurethane foam at Foamcraft Incorporated | Individual | ASP | PHI | FOA | 13 | INV | 31 | A | O | I | CFC | 90 | 90 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1998-05-01 | 2001-12-01 | 185000 | -19094 | 165906 | 165906 | 100% | 0 | 0 | 0 | 24050 | -2482 | 21568 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of polyurethane insulated building elements at Metal Forming Co. | Individual | ASP | PHI | FOA | 13 | INV | 32 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 305000 | -16698 | 288302 | 288302 | 100% | 0 | 0 | 0 | 39650 | -2171 | 37479 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of commercial refrigerators and ice boxes at Unimagna Philippines, Inc. | Individual | ASP | PHI | REF | 13 | INV | 33 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 1015700 | -54324 | 961376 | 961376 | 100% | 0 | 0 | 0 | 132041 | -7062 | 124979 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the residual use of CFC in the manufacture of extruded polystyrene foam sheet at Styrotech Co. | Individual | ASP | PHI | FOA | 13 | INV | 34 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 60000 | -2297 | 57703 | 57703 | 100% | 0 | 0 | 0 | 7800 | -299 | 7501 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 15 | PRP | 35 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1994-12-01 | 1995-12-01 |  | 1996-03-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of flexible polyurethane (slabstock) at Mandaue Foam Industries Inc. | Individual | ASP | PHI | FOA | 17 | INV | 37 | A | O | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-12-01 |  | 1997-06-01 | 2000-07-01 | 217000 | -9332 | 207668 | 207668 | 100% | 0 | 0 | 0 | 28210 | -1213 | 26997 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Umbrella project for the conversion of production of portable halon fire extinguishers of members companies of Fire Protectors Federation Inc. | Individual | ASP | PHI | HAL | 18 | INV | 38 | N | O | I | Halon | 77 | 77 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 2000-09-01 | 2003-04-01 | 114108 | -8935 | 105173 | 105173 | 100% | 0 | 0 | 0 | 14834 | -1161 | 13673 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-06-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Matsushita Electric Philippines Corporation (Mepco) | Individual | ASP | PHI | REF | 18 | INV | 39 | A | O | R | CFC | 47 | 47 | 0 | 0 | 1995-11-01 | 1996-06-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 112244 | -4513 | 107731 | 107731 | 100% | 0 | 0 | 0 | 14592 | -587 | 14005 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 18 | PRP | 42 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Phaseout of the use of CFCs in the manufacture of PU foam for insulation and structural purposes at Himalaya Mfg. Corp. | Individual | ASP | PHI | FOA | 19 | INV | 43 | A | O | D | CFC | 17 | 17 | 0 | 0 | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 101000 | -4879 | 96121 | 96121 | 100% | 0 | 0 | 0 | 13130 | -634 | 12496 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Umbrella project for conversion from CFC-11 foam blowing agent into HCFC-141b, and CFC-12 and R-502 refrigerants into HFC-134a and HFC-404a at Gomeco, Chee Puck and Well Built | Individual | ASP | PHI | REF | 19 | INV | 44 | N | O | I | CFC | 28 | 28 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1998-04-01 |  | 2000-09-01 | 2003-04-01 | 156475 | -38769 | 117706 | 117706 | 100% | 0 | 0 | 0 | 20342 | -5040 | 15302 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-06-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Elimination of the use of CFC-113, 1,1,1 trichloroethane (TCA), CFC-11 and CFC-12 at multiple corporations that manufacture special formulations for various industrial markets | Individual | ASP | PHI | SOL | 19 | INV | 46 | N | O | I | TCA/CFC | 54 | 54 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1998-06-01 | 2003-09-01 | 642800 | -181667 | 461133 | 461133 | 100% | 0 | 0 | 0 | 83564 | -23617 | 59947 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | PHI | REF | 21 | PRP | 47 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 2000-12-01 | 35000 | -4264 | 30736 | 30736 | 100% | 0 | 0 | 0 | 4550 | -554 | 3996 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at PU Rigid Insulation Contractor | Individual | ASP | PHI | FOA | 22 | INV | 48 | N | O | I | CFC | 24 | 24 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1999-06-01 |  | 1999-12-01 | 2003-11-01 | 189290 | -14221 | 175069 | 175069 | 100% | 0 | 0 | 0 | 24608 | -1849 | 22759 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at MBA Urethane Products Contractor | Individual | ASP | PHI | FOA | 22 | INV | 50 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 1999-12-01 | 2003-08-01 | 113574 | -22017 | 91557 | 91557 | 100% | 0 | 0 | 0 | 14765 | -2862 | 11903 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Soutech | Individual | ASP | PHI | FOA | 23 | INV | 51 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 1999-12-01 | 2003-04-01 | 326750 | -1799 | 324951 | 324951 | 100% | 0 | 0 | 0 | 42478 | -234 | 42244 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Umbrella project: Conversion to CFC-free technology in small CFC consuming enterprises using CFC in the manufacture of rigid polyurethane foam (Ashlar Industrial Corporation, Alen International, Zegal | Individual | ASP | PHI | FOA | 23 | INV | 52 | N | O | I | CFC | 5 | 5 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 39930 | -13985 | 25945 | 25945 | 100% | 0 | 0 | 0 | 5191 | -1818 | 3373 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation to prepare the second and final phase for phaseout of ODS by solvent blenders | Individual | ASP | PHI | SOL | 24 | PRP | 54 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 | 1999-11-01 | 25000 | -22120 | 2880 | 2880 | 100% | 0 | 0 | 0 | 3250 | -2876 | 374 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | ASP | PHI | FUM | 25 | PRP | 55 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 1999-08-01 |  | 2000-12-01 | 2004-12-01 | 30000 | -358 | 29642 | 29642 | 100% | 0 | 0 | 0 | 3900 | -47 | 3853 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFC-113, l,l,l trichloroethane and CFC-12 at multiple corporations that manufacture special formulations for industrial markets (Ariad Industrial Co., Cloisonne, Redisol, Rodler) | Individual | ASP | PHI | SOL | 25 | INV | 56 | A | O | I | TCA/CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2003-04-01 | 334600 | -93314 | 241286 | 241286 | 100% | 0 | 0 | 0 | 43498 | -12131 | 31367 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Demonstration, training and policy development on alternatives to methyl bromide for banana soil fumigation | Individual | ASP | PHI | FUM | 26 | DEM | 57 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-07-01 | 2003-07-01 | 231000 | -214534 | 16466 | 16466 | 100% | 0 | 0 | 0 | 30030 | -27889 | 2141 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | ASP | PHI | FOA | 30 | PRP | 60 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 15000 | -3091 | 11909 | 11909 | 100% | 0 | 0 | 0 | 1950 | -401 | 1549 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of PUF foam at RGC Foam Group (Polyfoam/Uratex) | Individual | ASP | PHI | FOA | 18 | INV | 62 | A | O | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1997-05-01 |  | 1997-06-01 | 2000-07-01 | 650000 | -3624 | 646376 | 646376 | 100% | 0 | 0 | 0 | 84500 | -471 | 84029 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture or rigid polyurethane foam (sprayfoam) at Prescon Construction and Development | Individual | ASP | PHI | FOA | 31 | INV | 64 | N | O | I | CFC | 32 | 32 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-10-01 |  | 2002-09-01 | 2005-04-01 | 187926 | -25246 | 162680 | 162680 | 100% | 0 | 0 | 0 | 24430 | -3282 | 21148 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Project preparation assistance in recovery and recycling of refrigerant, foam and halon sectors | Individual | AFR | PRC | SEV | 18 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | PRC | REF | 20 | TAS | 04 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1996-10-01 | 1998-10-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 201200 | -13880 | 187320 | 187320 | 100% | 0 | 0 | 0 | 26156 | -1804 | 24352 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | AFR | PRC | REF | 34 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-09-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 2001 | Investment
ONG | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Update-Comp | AFR | PRC | REF | 41 | TAS | 11 | N | O | I | CFC | 3 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2007-12-01 |  |  | 118078 | 0 | 118078 | 0 | 0% | 118078 | 11058 | 23615.6 | 10627 | 0 | 0 | 10627 | 995.2181 | Equipment ordered but shipment delayed. Workshop therefore to take place in first half of 2006. | [10 empty] | 2003 | Investment
FIN | UNDP | Formulation of a refrigerant management plan | Individual | AFR | RWA | REF | 36 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2002 | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | RWA | REF | 39 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: refrigeration manufacturing and centralized recovery and recycling of refrigerants | RMP-Update-Comp | AFR | RWA | REF | 41 | TAS | 08 | N | O | I | CFC | 3 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 118758 | 0 | 118758 | 175 | 0.1474% | 118583 | 35861 | 41504.05 | 10688 | 0 | 15.7497 | 10672.2503 | 3227.4236 | After long wait, UNDP CO understood legislation was past, and thus placed PO for equipm in Nov 05. All stopped now, since we learned that legislation not yet past. Once resolved, subcontract with R&R center and recruitment Nat.Cons. will take place. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector, and recovery and recycling project | RMP-Update-Comp | AFR | SIL | REF | 41 | TAS | 05 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 92400 | 0 | 92400 | 23277 | 25.19% | 69123 | 0 | 24193.05 | 8316 | 0 | 2094.93 | 6221.07 | 0 | Prodoc signed. Mission was undertaken to initiate. Now awaiting legislation. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Update-Comp | AFR | SIL | REF | 41 | TAS | 06 | N | O | I | CFC | 2 | 0 | 0 | 0 | 2003-12-01 |  | 2008-12-01 | 2008-12-01 |  |  | 107350 | 0 | 107350 | 0 | 0% | 107350 | 0 | 21470 | 9662 | 0 | 0 | 9662 | 0 | Prodoc signed. Mission was undertaken to initiate. Now awaiting legislation. | [10 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: MAC recovery/recycling of CFC-12 | RMP-Update-Comp | AFR | SIL | REF | 41 | TAS | 07 | N | O | I | CFC | 12 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 61858 | 0 | 61858 | 0 | 0% | 61858 | 0 | 21650.3 | 5567 | 0 | 0 | 5567 | 0 | Prodoc signed. Mission was undertaken to initiate. Now awaiting legislation. | [10 empty] | 2003 | Investment
ONG | UNDP | Project preparation for a halon sectoral phase-out plan | Individual | AFR | SIL | HAL | 45 | PRP | 10 | N | O | I | HAL | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 | 2007-12-01 |  |  | 16870 | 0 | 16870 | 4000 | 23.71% | 12870 | 0 | 12870 | 1265 | 0 | 299.9407 | 965.0593 | 0 | Approved in Apr 05. National Consultant recruited for survey. Project document to be submitted in 2006. | [10 empty] | 2005 | Investment
FIN | UNDP | Formulation of refrigerant management plan | Individual | AFR | SOM | REF | 36 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2005-11-01 | 2005-12-01 | 15000 | 0 | 15000 | 341 | 2.273% | 14659 | 0 | 0 | 1950 | 0 | 44.33 | 1905.67 | 0 | Completed in 2005. Financially completed in 2005. Funds to be returned in 06. When country's security situation improves, PRP funds may be requested at that time. | [10 empty] | 2002 | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | SRL | SEV | 06 | CPG | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-09-01 |  | 1994-03-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | SRL | SEV | 12 | INS | 02 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1997-03-01 |  | 1997-10-01 | 2003-09-01 | 154680 | 0 | 154680 | 154680 | 100% | 0 | 0 | 0 | 20108 | 0 | 20108 | 0 | 0 | Completed in 1997. Financially completed in 2003. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | SRL | SEV | 14 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-06-01 |  | 1996-06-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Associated Electrical Corporation (AEC) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 04 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1998-08-01 | 2000-12-01 | 250114 | -912 | 249202 | 249202 | 100% | 0 | 0 | 0 | 32515 | -119 | 32396 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Glacio Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 05 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 239500 | -26843 | 212657 | 212657 | 100% | 0 | 0 | 0 | 31135 | -3490 | 27645 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-08-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Regnis (Lanka) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 06 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 284324 | -18407 | 265917 | 265917 | 100% | 0 | 0 | 0 | 36962 | -2393 | 34569 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at International Cosmetic Ltd. (ICL) | Individual | ASP | SRL | ARS | 18 | INV | 07 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1995-11-01 | 1997-04-01 | 1996-11-01 |  | 2001-08-01 | 2003-11-01 | 38968 | -5599 | 33369 | 33369 | 100% | 0 | 0 | 0 | 5066 | -728 | 4338 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-08-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | ASP | SRL | REF | 20 | TAS | 08 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1999-12-01 | 2001-12-01 | 352400 | -1472 | 350928 | 350928 | 100% | 0 | 0 | 0 | 45812 | -191 | 45621 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | SRL | SEV | 23 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-11-01 | 1999-12-01 |  | 1999-12-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [10 empty] | 1997 | Non-Investment
FIN | UNDP | Project preparation for one project in the solvent sector | Individual | ASP | SRL | SOL | 24 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation assistance for the methyl bromide sector | Individual | ASP | SRL | FUM | 25 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-06-01 | 2004-12-01 | 25000 | -1090 | 23910 | 23910 | 100% | 0 | 0 | 0 | 3250 | -142 | 3108 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [10 empty] | 1998 | Investment
ONG | UNDP | Alternatives to methyl bromide for eradication of tea nematodes in Sri Lanka | Individual | ASP | SRL | FUM | 27 | DEM | 13 | A | O | I | MeBr | 4 | 2 | 0 | 0 | 1999-03-01 | 2000-07-01 | 2001-04-01 | 2006-12-01 |  |  | 310200 | 0 | 310200 | 207756 | 66.97% | 102444 | 0 | 35855.4 | 40326 | 0 | 27008.28 | 13317.72 | 0 | Technical mission in 05 to address problems in field adoption of alternatives. Solutions and exit strategy proposed. Being discussed. Final activities, including production of training materials and final report slated for 2006. Completion expected 06. | [10 empty] | 1999 | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase III) | Individual | ASP | SRL | SEV | 29 | INS | 14 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2002-02-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 1999 | Non-Investment
ONG | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration | RMP-Component | ASP | SRL | REF | 32 | TAS | 15 | N | O | I | CFC | 5 | 0 | 0 | 0 | 2000-12-01 | 2002-04-01 | 2006-01-01 | 2006-12-01 |  |  | 250000 | 0 | 250000 | 31381 | 12.55% | 218619 | 0 | 76516.65 | 32500 | 0 | 4079.53 | 28420.47 | 0 | Initiation of incentive scheme had difficulty to get started. NOU mentioned rules to obtain incentives too strict, so they were revised. One incentive paid so far. Project expected to pick up pace in 2006. | [10 empty] | 2000 | Non-Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities included in the RMP | RMP-Component | ASP | SRL | REF | 32 | TAS | 18 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 | 2006-12-01 |  |  | 15455 | 0 | 15455 | 4302 | 27.84% | 11153 | 0 | 3903.55 | 2009 | 0 | 559.2182 | 1449.7818 | 0 | Project runs in conjunction with SRL/REF/32/TAS/15. Nat. cons. recruited. | [10 empty] | 2000 | Non-Investment
FIN | UNDP | Preparation of a terminal programme in the fumigant sector | Individual | ASP | SRL | FUM | 36 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2002-11-01 | 2005-11-01 | 25000 | 0 | 25000 | 21422 | 85.69% | 3578 | 0 | 0 | 3250 | 0 | 2784.86 | 465.14 | 0 | Completed in 2002. Financially completed in 2005. Funds returned at 48th ExCom. | [10 empty] | 2002 | Investment
COM | UNDP | Renewal of institutional strengthening project (Phase 4) | Individual | ASP | SRL | SEV | 37 | INS | 20 | N | T | I | CFC | 11 | 11 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-08-01 |  | 134056 | 0 | 134056 | 130754 | 97.54% | 3302 | 0 | 1651 | 17427 | 0 | 16998.02 | 429.26 | 0 | Completed in 2004. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Methyl bromide phase-out for all remaining uses excluding QPS applications | One-off-Phaseout | ASP | SRL | FUM | 38 | TAS | 21 | N | O | I | MeBr | 3 | 1 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-11-01 | 2006-12-01 |  |  | 130000 | 0 | 130000 | 122787 | 94.45% | 7213 | 0 | 2524.55 | 16900 | 0 | 15962.31 | 937.69 | 0 | Tech mission in 05 to address problems in demo tea project also provided advice to TAS project. Adoption of alternatives ongoing. Production of training materials and final report slated for 2006. Completion expected 06 after slight delay. | [9 empty] | 2005-11-01 | 2002 | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | SRL | SEV | 43 | INS | 22 | N | T | I | CFC | 11 | 5 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 | 2006-07-01 |  |  | 134056 | 0 | 134056 | 66747 | 49.79% | 67309 | 0 | 23558.15 | 10054 | 0 | 5005.9254 | 5048.0746 | 0 | During the 2005 reporting period, the Sri Lanka NOU continued management of ongoing ODS phase out activities. This included provision of support to implementation of the NCAP, data collection and reporting activities, implementation of MB projects and involvement in the launch of the HCFC survey. Additionally, a number of awareness activities raising activities were launched. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SRL | SEV | 45 | TAS | 30 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 36697 | 0 | 36697 | 0 | 0% | 36697 | 0 | 12843.95 | 3303 | 0 | 0 | 3303 | 0 | Approved in Apr 05. Activities initiated. Consultants identified. | [10 empty] | 2005 | Non-Investment
COM | UNDP | Formulation of the investment components of the RMP | Individual | AFR | STP | REF | 39 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-06-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Final payments done. | [10 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | STP | REF | 44 | TAS | 10 | N | O | I | No_ODP | 3 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 0 | 38500 | 9900 | 0 | 0 | 9900 | 0 | Approved in Dec 2004. Awaiting legislation and signing of prodoc. | [10 empty] | 2004 | Investment
ONG | UNDP | Terminal phase out management plan for CFCs (first phase) | Multi-Year | LAC | STV | PHA | 47 | INV | 11 | N | O | I | CFC | 1 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 101000 | 0 | 101000 | 0 | 0% | 101000 | 0 | 35350 | 9090 | 0 | 0 | 9090 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment | 2.1 |  |  |  | Latest | Latest | Latest
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | SUR | REF | 36 | PRP | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially closed in 2005. | [10 empty] | 2002 | Investment
COM | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | LAC | SUR | REF | 42 | PRP | 07 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 |  | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2005. Project preparation completed. Project submitted to and approved at ExCom 44. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the MAC and refrigeration service sectors | RMP-Component | LAC | SUR | REF | 44 | TAS | 09 | N | O | I | No_ODP | 16 | 0 | 0 | 0 | 2004-12-01 |  | 2007-06-01 | 2007-06-01 |  |  | 300430 | 0 | 300430 | 0 | 0% | 300430 | 0 | 60086 | 22532 | 0 | 0 | 22532 | 0 | Extraordinary delay to sign Project Document. Expected to be signed Q1 06. NOO has been on leave during part of 05. UNDP has assisted with preparation of execution of the project. | [10 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities within the RMP | RMP-Component | LAC | SUR | REF | 44 | TAS | 10 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2007-06-01 | 2007-06-01 |  |  | 25750 | 0 | 25750 | 0 | 0% | 25750 | 0 | 5150 | 2318 | 0 | 0 | 2318 | 0 | Extraordinary delay to sign Project Document. Expected to be signed Q1 06. NOO has been on leave during part of 05. UNDP has assisted with preparation of execution of the project. | [10 empty] | 2004 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ammar Industrial Establishment | Individual | ASP | SYR | REF | 26 | INV | 33 | A | O | I | CFC | 56 | 56 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 331080 | -222 | 330858 | 330858 | 100% | 0 | 0 | 0 | 43040 | -29 | 43011 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of domestic and commercial refrigeration equipment and foam sandwich panels at Ahmad Al-Hafez Al-Waha Refrigerator Co. | Individual | ASP | SYR | REF | 26 | INV | 38 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 330486 | 0 | 330486 | 330486 | 100% | 0 | 0 | 0 | 42963 | 0 | 42963 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1998 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at El-Effendi Refrigerator Plant | Individual | ASP | SYR | REF | 26 | INV | 39 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 |  | 182802 | 0 | 182802 | 157752 | 86.3% | 25050 | 0 | 12525 | 23764 | 0 | 20507.5356 | 3256.4644 | 0 | Completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1999 | Investment
CLO | UNDP | Preparation of one project in the flexible foam subsector | Individual | ASP | SYR | FOA | 27 | PRP | 42 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2004-01-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2001. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of three projects in the domestic refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 43 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Ihsan Co. | Individual | ASP | SYR | REF | 28 | INV | 46 | A | O | I | CFC | 38 | 38 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-01-01 | 2003-05-01 | 497250 | -16958 | 480292 | 480292 | 100% | 0 | 0 | 0 | 64643 | -2205 | 62438 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigerarion equipment at seven enterprises | Individual | ASP | SYR | REF | 29 | INV | 52 | A | O | I | CFC | 52 | 52 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2003-08-01 | 2005-09-01 | 743419 | -20056 | 723363 | 723363 | 100% | 0 | 0 | 0 | 91776 | -2206 | 89569.93 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 30 | PRP | 58 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Al-Wattar Home Appliances Co. | Individual | ASP | SYR | REF | 31 | INV | 64 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-05-01 | 2004-01-01 | 235860 | 0 | 235860 | 235860 | 100% | 0 | 0 | 0 | 30662 | 0 | 30662 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Assalam Refrigerator Co. | Individual | ASP | SYR | REF | 31 | INV | 65 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 144309 | 0 | 144309 | 144309 | 100% | 0 | 0 | 0 | 18760 | 0 | 18760 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alfa Refrigerators Co. | Individual | ASP | SYR | REF | 31 | INV | 66 | A | O | I | CFC | 8 | 8 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-08-01 |  | 114461 | 0 | 114461 | 112260 | 98.08% | 2201 | 0 | 1100.5 | 14880 | 0 | 14593.8687 | 286.1313 | 0 | Completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Dolphin Refrigerators | Individual | ASP | SYR | REF | 31 | INV | 67 | A | O | I | CFC | 8 | 8 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 113045 | 0 | 113045 | 113045 | 100% | 0 | 0 | 0 | 14696 | 0 | 14696 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Raed Refrigeration | Individual | ASP | SYR | REF | 32 | INV | 69 | A | O | I | CFC | 14 | 14 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-09-01 | 2005-11-01 | 211800 | 0 | 211800 | 211800 | 100% | 0 | 0 | 0 | 27534 | 0 | 27534 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2000 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Refrigeration House Co. | Individual | ASP | SYR | REF | 34 | INV | 79 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2001-07-01 | 2002-11-01 | 2004-08-01 |  | 2003-09-01 |  | 253653 | 0 | 253653 | 253653 | 100% | 0 | 0 | 0 | 32975 | 0 | 32975 | 0 | 0 | Completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Saad Refrigeration | Individual | ASP | SYR | REF | 35 | INV | 81 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2001-12-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 |  | 166323 | 0 | 166323 | 157497 | 94.69% | 8826 | 0 | 4413 | 21622 | 0 | 20474.6195 | 1147.3805 | 0 | Completed in 2004. | [10 empty] | 2001 | Investment
COM | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | SYR | REF | 36 | PRP | 84 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-09-01 |  | 20000 | 0 | 20000 | 13135 | 65.67% | 6865 | 0 | 6865 | 2600 | 0 | 1707.55 | 892.45 | 0 | Completed in 2002. | [10 empty] | 2002 | Investment
ONG | UNDP | Sector phase out plan for CFCs in the refrigeration manufacturing sector (except domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 86 | A | O | I | CFC | 246 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-12-01 | 2006-12-01 |  |  | 1665188 | 0 | 1665188 | 1062079 | 63.78% | 603109 | 0 | 211088.15 | 191422 | 0 | 122091.4914 | 69330.5086 | 0 | All Purchase Orders issued towards end-2004 and equipment deliveries / installation / commissioning took place throughout 2005 at 36 enterprises. Mission scheduled for April 06 to determine further actions and follow-ups. | [10 empty] | 2002 | Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SYR | SEV | 45 | TAS | 90 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 45872 | 0 | 45872 | 0 | 0% | 45872 | 0 | 16055.2 | 4128 | 0 | 0 | 4128 | 0 | Approved in Apr 05. Activities initiated. Consultants identified. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Training of Government technical staff | Individual | ASP | THA | SEV | 04 | TRA | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 50000 | 3785 | 53785 | 53785 | 100% | 0 | 0 | 0 | 6500 | 492 | 6992 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection Unit | Individual | ASP | THA | SEV | 09 | INS | 09 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-12-01 | 1996-03-01 |  | 2002-01-01 | 2003-05-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  | 1997-12-01 | [7 empty] | 1993 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 10 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-06-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
CLO | UNDP | Elimination of CFC-114 in the manufacture of extruded polystyrene foam sheet and profiles at Thermaflex Insulation Asia Co. Ltd. | Individual | ASP | THA | FOA | 11 | INV | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-07-01 |  |  | 2001-07-01 | 220000 | -220000 | 0 | 0 |  | 0 | 0 | 0 | 28600 | -28600 | 0 | 0 | 0 | Canceled in 1995. | [10 empty] | 1993 | Investment
FIN | UNDP | Elimination of the use of CFC-12 and CFC-114 in the manufacture of extruded low density polyethylene foam sheet at Mic-Cell Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 27 | A | O | I | CFC | 44 | 44 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-11-01 | 2001-12-01 | 339500 | -1726 | 337774 | 337774 | 100% | 0 | 0 | 0 | 44135 | -225 | 43910 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of laminated rigid polyurethane foam insulation panels at Modular Compound Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 29 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1996-12-01 | 2000-12-01 | 508000 | -3349 | 504651 | 504651 | 100% | 0 | 0 | 0 | 66040 | -435 | 65605 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at 2 companies (Tahi Poly Seal Material Industries Co. Ltd, and Food Box Co. Ltd.): Phase I | Individual | ASP | THA | FOA | 12 | INV | 30 | A | O | R | CFC | 100 | 100 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1995-03-01 |  | 1995-02-01 | 2000-12-01 | 455000 | -2639 | 452361 | 452361 | 100% | 0 | 0 | 0 | 59150 | -343 | 58807 | 0 | 0 | Completed in 1995. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of laminated rigid polyurethane foam for insulation panels at Henger Panel | Individual | ASP | THA | FOA | 12 | INV | 31 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-06-01 | 2000-12-01 | 257500 | -509 | 256991 | 256991 | 100% | 0 | 0 | 0 | 33475 | -66 | 33409 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination in the use of CFC in the manufacture of commercial refrigerators at Sanden Refrigerator Co. Ltd. | Individual | ASP | THA | REF | 13 | INV | 33 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1998-06-01 | 1999-12-01 | 533800 | 0 | 533800 | 533800 | 100% | 0 | 0 | 0 | 69394 | 0 | 69394 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible polyurethane foam at Lucky Group | Individual | ASP | THA | FOA | 13 | INV | 35 | A | O | I | CFC | 187 | 187 | 0 | 0 | 1994-07-01 | 1997-12-01 | 1995-07-01 |  | 1999-11-01 | 2003-07-01 | 605000 | -1836 | 603164 | 603164 | 100% | 0 | 0 | 0 | 78650 | -239 | 78411 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-06-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at Ponsri | Individual | ASP | THA | FOA | 13 | INV | 36 | A | O | I | CFC | 125 | 125 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1995-07-01 |  | 1996-06-01 | 2002-03-01 | 340000 | -6035 | 333965 | 333965 | 100% | 0 | 0 | 0 | 44200 | -784 | 43416 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1994 | Investment
FIN | UNDP | Safety and technical assistance programme to manufacturers of aerosol products | Individual | ASP | THA | ARS | 15 | TAS | 38 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1998-08-01 | 2002-03-01 | 127000 | -20 | 126980 | 126980 | 100% | 0 | 0 | 0 | 16510 | -3 | 16507 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance in foam, halon and aerosol sectors | Individual | ASP | THA | SEV | 15 | PRP | 39 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF cold cured mouldings, integral skin mouldings and rigid PUF articles at Thai Union PU Co. Ltd. | Individual | ASP | THA | FOA | 15 | INV | 41 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1996-12-01 | 2000-12-01 | 525000 | -72931 | 452069 | 452069 | 100% | 0 | 0 | 0 | 68250 | -9481 | 58769 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF slabstock and cold cured mouldings st Somboon Paisarn 85 Company Ltd. | Individual | ASP | THA | FOA | 15 | INV | 42 | A | O | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-11-01 |  | 1998-11-01 | 2000-12-01 | 225000 | -5000 | 220000 | 220000 | 100% | 0 | 0 | 0 | 29250 | -650 | 28600 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of flexible PUF slabstock at Karn Yang Yeen Yong Industry Ltd. | Individual | ASP | THA | FOA | 15 | INV | 44 | A | O | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-11-01 |  | 1999-04-01 | 2000-12-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 | 0 | 22100 | 0 | 22100 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-06-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Packserv Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 45 | A | O | D | CFC | 155 | 155 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 474705 | -1221 | 473484 | 473484 | 100% | 0 | 0 | 0 | 61712 | -159 | 61553 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Sanit & Sons Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 46 | A | O | I | CFC | 194 | 194 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 2000-04-01 | 2002-03-01 | 582100 | 0 | 582100 | 582100 | 100% | 0 | 0 | 0 | 75673 | 0 | 75673 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-09-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUF foam for thermoware at Krieng Thavorn Containers Co. Ltd. | Individual | ASP | THA | FOA | 18 | INV | 47 | A | O | I | CFC | 65 | 65 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 430000 | -32154 | 397846 | 397846 | 100% | 0 | 0 | 0 | 55900 | -4180 | 51720 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 18 | PRP | 49 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 2002-05-01 | 3000 | 0 | 3000 | 3000 | 100% | 0 | 0 | 0 | 390 | 0 | 390 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [10 empty] | 1995 | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUR foam for thermoware at Raengwa Standard Industry Co. Ltd. | Individual | ASP | THA | FOA | 19 | INV | 51 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-01-01 | 2000-12-01 | 181500 | -796 | 180704 | 180704 | 100% | 0 | 0 | 0 | 23595 | -103 | 23492 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Dacron Trade Co. | Individual | ASP | THA | FOA | 20 | INV | 55 | A | O | I | CFC | 48 | 48 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-11-01 | 2001-12-01 | 277800 | -19551 | 258249 | 258249 | 100% | 0 | 0 | 0 | 36114 | -2541 | 33573 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siam Matee | Individual | ASP | THA | FOA | 20 | INV | 56 | A | O | I | CFC | 34 | 34 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1998-09-01 |  | 1998-09-01 | 2001-12-01 | 198000 | -13801 | 184199 | 184199 | 100% | 0 | 0 | 0 | 25740 | -1794 | 23946 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | THA | SEV | 21 | PRP | 59 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2001-12-01 | 100000 | -40377 | 59623 | 59623 | 100% | 0 | 0 | 0 | 13000 | -5249 | 7751 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid and integral skin polyurethane foam at Bangkok Foam Group | Individual | ASP | THA | FOA | 22 | INV | 63 | A | O | I | CFC | 91 | 91 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2001-12-01 | 480500 | 0 | 480500 | 480500 | 100% | 0 | 0 | 0 | 62465 | 0 | 62465 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Asia Container | Individual | ASP | THA | FOA | 22 | INV | 64 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1999-11-01 | 2000-12-01 | 199000 | 0 | 199000 | 199000 | 100% | 0 | 0 | 0 | 25870 | 0 | 25870 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siriphan | Individual | ASP | THA | FOA | 22 | INV | 66 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-09-01 | 2001-12-01 | 215000 | -5001 | 209999 | 209999 | 100% | 0 | 0 | 0 | 27950 | -650 | 27300 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Ocean Plastics | Individual | ASP | THA | FOA | 22 | INV | 67 | A | O | I | CFC | 82 | 82 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 287000 | -16390 | 270610 | 270610 | 100% | 0 | 0 | 0 | 37310 | -2131 | 35179 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam at Chareon Porn | Individual | ASP | THA | FOA | 23 | INV | 68 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | -29 | 93471 | 93471 | 100% | 0 | 0 | 0 | 12155 | -4 | 12151 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam (boxfoam) at Thai International | Individual | ASP | THA | FOA | 23 | INV | 69 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | 0 | 93500 | 93500 | 100% | 0 | 0 | 0 | 12155 | 0 | 12155 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Novochem | Individual | ASP | THA | FOA | 23 | INV | 70 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2002-08-01 | 2004-01-01 | 196600 | 0 | 196600 | 196600 | 100% | 0 | 0 | 0 | 25558 | 0 | 25558 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane boxfoam at Nun Charoen | Individual | ASP | THA | FOA | 23 | INV | 71 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 | 0 | 13650 | 0 | 13650 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Century Plastics | Individual | ASP | THA | FOA | 23 | INV | 75 | A | O | D | CFC | 7 | 7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2001-12-01 | 56750 | -2560 | 54190 | 54190 | 100% | 0 | 0 | 0 | 7378 | -333 | 7045 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | P-Tech Manuchem Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 83 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2001-12-01 | 115830 | -8432 | 107398 | 107398 | 100% | 0 | 0 | 0 | 15058 | -1096 | 13962 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | J.M.T. Laboratories Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 84 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2003-11-01 | 127920 | -5082 | 122838 | 122838 | 100% | 0 | 0 | 0 | 16630 | -661 | 15969 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 3 projects in the foam sector | Individual | ASP | THA | FOA | 24 | PRP | 87 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 4 projects in the aerosol sector | Individual | ASP | THA | ARS | 24 | PRP | 89 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to LCD technology (flexible) and water based technology (integral skin) in the manufacture of polyurethane foam at Duriflex | Individual | ASP | THA | FOA | 25 | INV | 90 | A | O | I | TCA/CFC | 21 | 21 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2001-12-01 | 278800 | -285 | 278515 | 278515 | 100% | 0 | 0 | 0 | 36244 | -37 | 36207 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion to low index/additive technology and methylene chloride in the manufacture of flexible polyurethane boxfoam at City Foam Co., Ltd. | Individual | ASP | THA | FOA | 25 | INV | 91 | A | O | I | CFC | 42 | 42 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2000-12-01 | 156100 | 0 | 156100 | 156100 | 100% | 0 | 0 | 0 | 20293 | 0 | 20293 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1998 | Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol | Individual | ASP | THA | SEV | 25 | INS | 93 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-07-01 | 2000-07-01 |  | 2003-04-01 | 2003-05-01 | 266667 | -225128 | 41539 | 41539 | 100% | 0 | 0 | 0 | 34667 | -29267 | 5400 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Standard Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 94 | A | O | I | CFC | 41 | 41 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 138380 | -5000 | 133380 | 133380 | 100% | 0 | 0 | 0 | 17989 | -650 | 17339 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Mary Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 96 | A | O | I | CFC | 40 | 40 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 136400 | -4295 | 132105 | 132105 | 100% | 0 | 0 | 0 | 17732 | -558 | 17174 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam at J.S. Industry Co. Ltd. | Individual | ASP | THA | FOA | 26 | INV | 98 | A | O | I | CFC | 93 | 93 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 418800 | -15974 | 402826 | 402826 | 100% | 0 | 0 | 0 | 54444 | -2077 | 52367 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Urethane | Individual | ASP | THA | FOA | 26 | INV | 99 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2001-12-01 | 2004-01-01 | 98645 | 0 | 98645 | 98645 | 100% | 0 | 0 | 0 | 12824 | 0 | 12824 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Suwan Polymer L.P. | Individual | ASP | THA | FOA | 26 | INV | 100 | A | O | I | CFC | 58 | 58 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 298370 | -1026 | 297344 | 297344 | 100% | 0 | 0 | 0 | 38788 | -133 | 38655 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Sahakij Comos L.P. | Individual | ASP | THA | FOA | 26 | INV | 101 | A | O | I | CFC | 49 | 49 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 255850 | -11488 | 244362 | 244362 | 100% | 0 | 0 | 0 | 33261 | -1493 | 31768 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at P. Chongcharoen | Individual | ASP | THA | FOA | 26 | INV | 102 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 130500 | -256 | 130244 | 130244 | 100% | 0 | 0 | 0 | 16965 | -33 | 16932 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lohr Trade and Consulting PTS Ltd. | Individual | ASP | THA | FOA | 26 | INV | 103 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 93210 | -137 | 93073 | 93073 | 100% | 0 | 0 | 0 | 12117 | -18 | 12099 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam (flexible molded, integral skin) at World Plaster/Europlan Furniture Co. | Individual | ASP | THA | FOA | 26 | INV | 105 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 135800 | -5000 | 130800 | 130800 | 100% | 0 | 0 | 0 | 17654 | -650 | 17004 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ohm Intertrade L.P. | Individual | ASP | THA | FOA | 26 | INV | 106 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2002-03-01 | 146350 | -6393 | 139957 | 139957 | 100% | 0 | 0 | 0 | 19026 | -831 | 18195 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of six projects in general foam subsector | Individual | ASP | THA | FOA | 27 | PRP | 114 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Thai Steel Door L.P. | Individual | ASP | THA | FOA | 28 | INV | 117 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to low index additive (LIA) technology in the manufacture of flexible polyurethane foam at P.T. Foam Chiengmai L.P. | Individual | ASP | THA | FOA | 28 | INV | 118 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79120 | 0 | 79120 | 79120 | 100% | 0 | 0 | 0 | 10286 | 0 | 10286 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at S.K. Container Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 119 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to LIA (flexible), to water-based technology (flexible molded, structural and integral skin) and HCFC-141b technology (rigid) at Great Foam Products, Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 122 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 231843 | -23 | 231820 | 231820 | 100% | 0 | 0 | 0 | 30140 | -3 | 30137 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.S. Plastic Container L.P. | Individual | ASP | THA | FOA | 29 | INV | 123 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 75951 | 0 | 75951 | 75951 | 100% | 0 | 0 | 0 | 9874 | 0 | 9874 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [10 empty] | 1999 | Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | TOG | REF | 36 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [10 empty] | 2002 | Investment
ONG | UNDP | Implementation of the RMP: monitoring of the activities included in the RMP | RMP-Update-Comp | AFR | TOG | REF | 38 | TAS | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 | 2006-12-01 |  |  | 15000 | 0 | 15000 | 5819 | 38.79% | 9181 | 0 | 3213.35 | 1950 | 0 | 756.47 | 1193.53 | 0 | National consultant hired and monitoring ongoing. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration sector | RMP-Update-Comp | AFR | TOG | REF | 38 | TAS | 06 | A | O | I | CFC | 5 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2006-11-01 | 2006-11-01 |  |  | 110000 | 0 | 110000 | 16937 | 15.4% | 93063 | 0 | 32572.05 | 14300 | 0 | 2201.81 | 12098.19 | 0 | Mission planned in early 2006 to start identifying beneficiaries for incentive payments. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Implementation of the RMP: recovery and recycling of refrigerants | RMP-Update-Comp | AFR | TOG | REF | 38 | TAS | 07 | A | O | I | CFC | 8 | 4 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 | 2006-07-01 |  |  | 150000 | 0 | 150000 | 116750 | 77.83% | 33250 | 0 | 11637.5 | 19500 | 0 | 15177.5 | 4322.5 | 0 | While most equipm works well, the Government advised that some problems were experienced with the recovery bags and pumps and new items were ordered. Recovery still ongoing. | [10 empty] | 2002 | Investment
FIN | UNDP | Training of Government technical staff and preliminary work on country programme | Individual | LAC | TRI | SEV | 04 | TRA | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1995-07-01 | 1997-12-01 | 53800 | 102 | 53902 | 53902 | 100% | 0 | 0 | 0 | 6994 | 13 | 7007 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | TRI | SEV | 06 | CPG | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1995-07-01 | 1997-12-01 | 25000 | 1200 | 26200 | 26200 | 100% | 0 | 0 | 0 | 3250 | 156 | 3406 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | TRI | SEV | 20 | INS | 04 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 2000-12-01 | 2003-06-01 | 66000 | -5223 | 60777 | 60777 | 100% | 0 | 0 | 0 | 8580 | -679 | 7901 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Non-Investment
FIN | UNDP | Project preparation in the aerosol, refrigeration and solvent sectors | Individual | LAC | TRI | SEV | 21 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 40000 | -4596 | 35404 | 35404 | 100% | 0 | 0 | 0 | 5200 | -597 | 4603 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1997 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | TRI | REF | 23 | TAS | 09 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-11-01 | 1998-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 213990 | -12116 | 201874 | 201874 | 100% | 0 | 0 | 0 | 27819 | -1575 | 26244 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 1 project in the aerosol sector | Individual | LAC | TRI | ARS | 24 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1998 | Investment
COM | UNDP | Project to phaseout use of CFCs in aerosol filling at Hand Arnold Industries Limited (HAIL) | Individual | LAC | TRI | ARS | 25 | INV | 12 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2004-12-01 |  | 119570 | 0 | 119570 | 120964 | 101.2% | -1394 | 0 | 0 | 15544 | 0 | 15725.2188 | -181.2188 | 0 | Completed in 2004. Apparent overrun to be resolved in 2006. | [10 empty] | 1998 | Investment
COM | UNDP | Renewal of institutional strengthening (Phase II) | Individual | LAC | TRI | SEV | 32 | INS | 13 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 |  | 44000 | 0 | 44000 | 40347 | 91.7% | 3653 | 0 | 1826.5 | 5720 | 0 | 5245.11 | 474.89 | 0 | Completed in 2003. | [10 empty] | 2000 | Non-Investment
COM | UNDP | Project preparation for the RMP update | Individual | LAC | TRI | REF | 38 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2002-12-01 | 2003-12-01 |  | 2003-07-01 |  | 13500 | 0 | 13500 | 9595 | 71.07% | 3905 | 0 | 3905 | 1755 | 0 | 1247.35 | 507.65 | 0 | Completed in 2003. | [10 empty] | 2002 | Investment
ONG | UNDP | Extension of institutional strengthening project (phase 3) | Individual | LAC | TRI | SEV | 38 | INS | 15 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 | 2006-07-01 |  |  | 57200 | 0 | 57200 | 38503 | 67.31% | 18697 | 0 | 6543.95 | 7436 | 0 | 5005.39 | 2430.61 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | LAC | TRI | PHA | 40 | INV | 16 | N | O | I | CFC | 43 | 43 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2006-03-01 | 2006-07-01 |  |  | 220000 | 0 | 220000 | 33756 | 15.34% | 186244 | 0 | 65185.4 | 16500 | 0 | 2531.7 | 13968.3 | 0 | Project activities on track. Training of tech in MAC and refrigeration sector. Procurement and receipt of R&R equipment. Commercial Retrofit commenced in 2005. | [10 empty] | 2003 | Investment | 77 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Extension of institutional strengthening project (phase IV) | Individual | LAC | TRI | SEV | 44 | INS | 18 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 21000 | 4500 | 0 | 0 | 4500 | 0 | Trinidad and Tobago is in compliance with its obligations under the Montreal Protocol. During 2005, the NOU focused efforts on the implementation of the TPMP and the accelerated phase out of CFCs, in order to make sure that total phase out will be achieved by the end of 2007. Equipment procurement was completed in 2005. The NOU actively organized and participated in awareness raising activities (general public, technicians in MAC, etc.). A well functioning licensing system is in place and the ODS quotas for both 2006 and 2007 have been allocated to the importers. NOU has assisted with the training of technicians in MAC, as well as the customs training. | [10 empty] | 2004 | Non-Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | UGA | REF | 17 | PRP | 03 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | UGA | SEV | 18 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | UGA | REF | 19 | TAS | 05 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 56000 | -17 | 55983 | 55983 | 100% | 0 | 0 | 0 | 7280 | -2 | 7278 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | URT | SEV | 17 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1998-12-01 | 1999-12-01 | 47000 | 0 | 47000 | 47000 | 100% | 0 | 0 | 0 | 6110 | 0 | 6110 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1995 | Investment
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | URT | REF | 22 | TAS | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2001-12-01 | 161554 | -153795 | 7759 | 7759 | 100% | 0 | 0 | 0 | 21002 | -19993 | 1009 | 0 | 0 | Canceled in 2000. Financially completed in 2001. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation to formulate one flexible foam sector project | Individual | AFR | URT | FOA | 24 | PRP | 09 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [10 empty] | 1998 | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at H.K. Foam Ltd. | Individual | AFR | URT | FOA | 26 | INV | 10 | A | O | I | CFC | 2 | 2 | 0 | 0 | 1998-11-01 | 2003-01-01 | 2000-12-01 |  |  | 2003-11-01 | 113700 | -105743 | 7957 | 7957 | 100% | 0 | 0 | 0 | 14781 | -13747 | 1034 | 0 | 0 | Canceled in 2003. Financially completed in 2003. | [10 empty] | 1998 | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pan Africa Enterprises Ltd. | Individual | AFR | URT | FOA | 26 | INV | 11 | A | O | I | CFC | 35 | 0 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  |  | 2004-03-01 | 213800 | 0 | 213800 | 213800 | 100% | 0 | 0 | 0 | 27794 | 0 | 27794 | 0 | 0 | Canceled in 2002. Financially completed in 2004. | [10 empty] | 1998 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Plyfoam Limited | Individual | AFR | URT | FOA | 31 | INV | 13 | A | O | I | CFC | 40 | 40 | 0 | 0 | 2000-07-01 | 2002-07-01 | 2003-08-01 |  | 2004-12-01 |  | 175134 | 0 | 175134 | 175134 | 100% | 0 | 0 | 0 | 22767 | 0 | 22767 | 0 | 0 | Completed in 2004. | [10 empty] | 2000 | Investment
FIN | UNDP | Consultant mission to assess technical assistance requirement | Individual | LAC | URU | SEV | 04 | TAS | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-10-01 |  | 1992-12-01 | 1997-12-01 | 13050 | 992 | 14042 | 14042 | 100% | 0 | 0 | 0 | 1697 | 129 | 1826 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | URU | SEV | 08 | CPG | 02 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 23894 | 1550 | 25444 | 25444 | 100% | 0 | 0 | 0 | 3106 | 202 | 3308 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [10 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | URU | SEV | 10 | INS | 03 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 173800 | 29000 | 202800 | 202800 | 100% | 0 | 0 | 0 | 22594 | 3770 | 26364 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Conservation and demonstration programme for domestic and commercial refrigeration and installation of recovery and recycling equipment | RMP-Component | LAC | URU | REF | 12 | TAS | 04 | N | O | I | CFC | 22 | 22 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1996-03-01 |  | 1996-12-01 | 2004-01-01 | 175000 | -96 | 174904 | 174904 | 100% | 0 | 0 | 0 | 22750 | -12 | 22738 | 0 | 0 | Completed in 1996. Financially completed in 2004. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at 7 plants (Aislaciones de Uruguay, Metalizadora Uruguaya, Thermopur, Kubal SA, Kalisay SA, J.C. Scarone, Eraton SA) | Individual | LAC | URU | FOA | 13 | INV | 06 | N | O | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-12-01 | 1999-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 | 0 | 86450 | 0 | 86450 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | URU | SEV | 13 | PRP | 08 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1995-01-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at 5 plants (Sudamtex del Uruguay, S.A., Ronit Ltd., Maxi, Divino S.A., Poliflex, Ltd.) | Individual | LAC | URU | FOA | 13 | INV | 09 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 2001-12-01 | 2003-08-01 | 200000 | -5109 | 194891 | 194891 | 100% | 0 | 0 | 0 | 26000 | -664 | 25336 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-06-01 | [6 empty] | 1994 | Investment
FIN | UNDP | Total aerosol sector phaseout project (technical assistance) | Individual | LAC | URU | ARS | 18 | TAS | 16 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1999-12-01 | 2001-12-01 | 54000 | -1 | 53999 | 53999 | 100% | 0 | 0 | 0 | 7020 | 0 | 7020 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [6 empty] | 1995 | Non-Investment
FIN | UNDP | Conversion of production of halon-1211 fire extinguishers at Tornay and Mori | Individual | LAC | URU | HAL | 18 | INV | 17 | N | O | I | Halon | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-05-01 |  | 1997-09-01 | 1999-12-01 | 38150 | 0 | 38150 | 38150 | 100% | 0 | 0 | 0 | 4960 | 0 | 4960 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Transfer of technology and conversion of production of halon-1211 fire extinguishers at Izeta López Fire Company | Individual | LAC | URU | HAL | 18 | INV | 18 | N | O | I | Halon | 3 | 3 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-02-01 |  | 1996-12-01 | 1999-12-01 | 24225 | 0 | 24225 | 24225 | 100% | 0 | 0 | 0 | 3149 | 0 | 3149 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1995 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 20 | INS | 22 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-10-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 116000 | 0 | 116000 | 116000 | 100% | 0 | 0 | 0 | 15080 | 0 | 15080 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1996 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 25 | INS | 27 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-07-01 | 2003-12-01 | 116000 | -19 | 115981 | 115981 | 100% | 0 | 0 | 0 | 15080 | -3 | 15077 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1998 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | URU | SEV | 31 | INS | 35 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-07-01 | 2004-04-01 | 116000 | -196 | 115804 | 115804 | 100% | 0 | 0 | 0 | 15080 | -25 | 15055 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2000 | Non-Investment
ONG | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Update-Comp | LAC | URU | REF | 34 | TAS | 37 | N | O | I | CFC | 6 | 2 | 0 | 0 | 2001-07-01 | 2003-01-01 | 2007-08-01 | 2007-08-01 |  |  | 154934 | 0 | 154934 | 5592 | 3.609% | 149342 | 0 | 29868.4 | 20141 | 0 | 726.9448 | 19414.0552 | 0 | Out of the 17 companies that presented proposals for conversion the six ones with most relevant consumption were selected. Incentives were calculated according to project document. Companies signing agreements to receive incentive. Conversions started. | [10 empty] | 2001 | Investment
FIN | UNDP | Development of an MDI transition strategy | Individual | LAC | URU | ARS | 36 | TAS | 38 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-12-01 | 2004-04-01 | 30000 | -2577 | 27423 | 27423 | 100% | 0 | 0 | 0 | 3900 | -335 | 3565 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Renewal of institutional strengthening project (Phase 5) | Individual | LAC | URU | SEV | 37 | INS | 39 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 | 2006-01-01 |  |  | 150800 | 0 | 150800 | 141005 | 93.5% | 9795 | 0 | 3428.25 | 19604 | 0 | 18330.65 | 1273.35 | 0 | Phase close to completion, activities described in new phase | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Transition strategy for the phase-out of CFCs use in MDIs | Individual | LAC | URU | ARS | 38 | TAS | 40 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2005-01-01 | 2009-12-01 | 2009-12-01 |  |  | 70000 | 0 | 70000 | 24787 | 35.41% | 45213 | 0 | 9042.6 | 9100 | 0 | 3222.31 | 5877.69 | 0 | Measures to import and sell MDI in Uruguay being determined with authorities; some of the importer labs working on transition plans. 4 additional workshops to health professionals were done in several regions of the country. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | URU | SEV | 43 | INS | 41 | N | T | I | CFC | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 | 2006-07-01 |  |  | 150800 | 0 | 150800 | 16904 | 11.21% | 133896 | 0 | 46863.6 | 11310 | 0 | 1267.8 | 10042.2 | 0 | During 2005, the NOU of Uruguay successfully continued its activities of oversight of project implementation, and monitoring of national compliance with the Montreal Protocol through data collection and monitoring of consumption. The NOU continued the implementation of ongoing activities including the MDI investment project, the MDI transition strategy and the RMP update where end users were selected, conversion proposals prepared and agreements with the beneficiaries established. The NOU also started the implementation of a small project approved to assess the consumption of ODS used as solvents and provide technical assistance to the users on the phase out. The Decree stipulating the license system for production, import and export of ODS was agreed with stakeholders and is ready for application. The regulation related to the seal Ozono Amigo was amended to include MBR; during the year 2 producers free of MB received the seal. Awareness activities continued to be implemented, some of them were the distribution of publications to education institutions, and the presentation of an awareness video produced under the IS project in several events and its distribution to schools. The NOU has also continued actively participating in the regional network meetings by sharing their experience and practice and benefiting from that of the others. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | URU | ARS | 43 | INV | 42 | N | O | I | CFC | 10 | 0 | 0 | 0 | 2004-07-01 |  | 2007-07-01 | 2007-07-01 |  |  | 427023 | 0 | 427023 | 0 | 0% | 427023 | 0 | 85404.6 | 32027 | 0 | 0 | 32027 | 0 | International expert to help with formulations selected. Development of formulations starting. Equipment purchase process started. | [10 empty] | 2004 | Investment
ONG | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | URU | SOL | 45 | TAS | 43 | N | O | I | TCA/CTC | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 5102 | 17.01% | 24898 | 0 | 8714.3 | 2700 | 0 | 459.18 | 2240.82 | 0 | Approved in Apr 05. Activities initiated. | [10 empty] | 2005 | Non-Investment
ONG | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | URU | PHA | 47 | PRP | 44 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2250 | 0 | 0 | 2250 | 0 | Newly approved in Nov 2005. | [10 empty] | 2005 | Investment
FIN | UNDP | Technical assistance and training of servicing technicians in the refrigeration sector | RMP-Component | LAC | VEN | REF | 04 | TRA | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 30000 | -10980 | 19020 | 19020 | 100% | 0 | 0 | 0 | 3900 | -1427 | 2473 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [10 empty] | 1991 | Non-Investment
FIN | UNDP | Workshops for the recycling and banking of halons | Individual | LAC | VEN | HAL | 09 | TAS | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26800 | -3700 | 23100 | 23100 | 100% | 0 | 0 | 0 | 3484 | -481 | 3003 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Institutional strengthening of FONDOIN | Individual | LAC | VEN | SEV | 09 | INS | 13 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1995-12-01 | 1998-12-01 | 329192 | 0 | 329192 | 329192 | 100% | 0 | 0 | 0 | 42795 | 0 | 42795 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Workshops for identification of projects in the refrigeration and air conditioning sector | Individual | LAC | VEN | REF | 09 | PRP | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-12-01 | 1997-12-01 | 19800 | 0 | 19800 | 19800 | 100% | 0 | 0 | 0 | 2574 | 0 | 2574 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Investment
FIN | UNDP | Workshops on conversion and installation of new central air conditioning systems using non-ODS | RMP-Component | LAC | VEN | REF | 09 | TAS | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26200 | -13000 | 13200 | 13200 | 100% | 0 | 0 | 0 | 3406 | -1690 | 1716 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in domestic refrigeration | RMP-Component | LAC | VEN | REF | 09 | TAS | 17 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1994-03-01 |  | 1996-12-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1993 | Investment
FIN | UNDP | Finalization of the country programme | Individual | LAC | VEN | SEV | 11 | CPG | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1993 | Non-Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in MAC | RMP-Component | LAC | VEN | REF | 12 | DEM | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1997-12-01 | 13400 | 0 | 13400 | 13400 | 100% | 0 | 0 | 0 | 1742 | 0 | 1742 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Non-Investment
FIN | UNDP | Preparatory assistance for the domestic and commercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 15 | PRP | 31 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 40000 | 5445 | 45445 | 45445 | 100% | 0 | 0 | 0 | 5200 | 708 | 5908 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [10 empty] | 1994 | Investment
FIN | UNDP | Pilot project for recovery and recycling of CFC-12 in MAC (Phase II) | RMP-Component | LAC | VEN | REF | 15 | TAS | 32 | A | O | I | CFC | 75 | 16 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 1996-12-01 | 2000-12-01 | 220000 | -13204 | 206796 | 206796 | 100% | 0 | 0 | 0 | 28600 | -1717 | 26883 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [10 empty] | 1994 | Investment
FIN | UNDP | Preparatory assistance for the domestic and comercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 17 | PRP | 37 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-06-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Pinova, S.A. | Individual | LAC | VEN | REF | 17 | INV | 38 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1995-07-01 | 1996-07-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 517500 | -149132 | 368368 | 368368 | 100% | 0 | 0 | 0 | 67275 | -19387 | 47888 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Conversion of CFC-12 to compressor production facilities at Vecomesa, S.A. to manufacture HFC-134a compressors | Individual | LAC | VEN | REF | 17 | INV | 39 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1999-12-01 | 2000-12-01 | 362000 | -193742 | 168258 | 168258 | 100% | 0 | 0 | 0 | 47060 | -25186 | 21874 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-07-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Industrias Nutal, C.A. | Individual | LAC | VEN | REF | 17 | INV | 40 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1997-01-01 |  | 2001-12-01 | 2002-03-01 | 123623 | 0 | 123623 | 123623 | 100% | 0 | 0 | 0 | 16071 | 0 | 16071 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  |  | 1997-12-01 |  | 2000-12-01 | [5 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Grupo Frigilux, C.A. | Individual | LAC | VEN | REF | 18 | INV | 42 | A | O | I | CFC | 46 | 46 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1997-05-01 |  | 1999-12-01 | 2000-12-01 | 953000 | -371693 | 581307 | 581307 | 100% | 0 | 0 | 0 | 123890 | -48320 | 75570 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-09-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coresmalt Valencia, C.A. | Individual | LAC | VEN | REF | 18 | INV | 43 | A | O | I | CFC | 66 | 66 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2000-09-01 | 2002-03-01 | 685330 | -6585 | 678745 | 678745 | 100% | 0 | 0 | 0 | 89093 | -856 | 88237 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  | 1997-12-01 | [7 empty] | 1995 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Manufacturera de Aparatos Domésticos, S.A. (Madosa) | Individual | LAC | VEN | REF | 18 | INV | 44 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1997-05-01 |  |  | 2001-12-01 | 230274 | -51266 | 179008 | 179008 | 100% | 0 | 0 | 0 | 29936 | -6665 | 23271 | 0 | 0 | Canceled in 1999. Financially completed in 2001. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | VEN | SEV | 18 | PRP | 45 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of refrigerated display cases and bottle coolers at Neve Industrial, C.A. | Individual | LAC | VEN | REF | 19 | INV | 46 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2002-03-01 | 112100 | -3498 | 108602 | 108602 | 100% | 0 | 0 | 0 | 14573 | -455 | 14118 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-07-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Tecnocongeladores Venezolanos (Tecoven), C.A. | Individual | LAC | VEN | REF | 19 | INV | 48 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 190000 | -2599 | 187401 | 187401 | 100% | 0 | 0 | 0 | 24700 | -338 | 24362 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [6 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Hielomatic, C.A. | Individual | LAC | VEN | REF | 19 | INV | 49 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 2000-07-01 | 2001-12-01 | 162375 | -379 | 161996 | 161996 | 100% | 0 | 0 | 0 | 21109 | -49 | 21060 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  | 1998-04-01 | [7 empty] | 1996 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 20 | INS | 50 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [10 empty] | 1996 | Non-Investment
FIN | UNDP | Project preparation in commercial refrigeration recovery and recycling and in the production sector | Individual | LAC | VEN | SEV | 21 | PRP | 52 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-12-01 | 2000-12-01 | 155000 | -120000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 20150 | -15600 | 4550 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-07-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Implementation of a recovery and reclamation of refrigerants | RMP-Component | LAC | VEN | REF | 22 | TAS | 58 | A | O | I | CFC | 172 | 172 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 2003-12-01 | 2003-12-01 | 931622 | -61553 | 870069 | 870069 | 100% | 0 | 0 | 0 | 121111 | -8002 | 113109 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  |  |  | 1999-06-01 | [6 empty] | 1997 | Investment
FIN | UNDP | Institutional strengthening of FONDOIN (renewal) | Individual | LAC | VEN | SEV | 17 | INS | 60 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 54900 | 54900 | 109800 | 109800 | 100% | 0 | 0 | 0 | 7137 | 7137 | 14274 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [10 empty] | 1995 | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 25 | INS | 65 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-07-01 | 2001-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Non-Investment
CLO | UNDP | Preparation of one project in refrigeration MAC and compressors subsector | Individual | LAC | VEN | REF | 27 | PRP | 69 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1999. | [10 empty] | 1999 | Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | VEN | SEV | 31 | INS | 87 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-12-01 | 2004-02-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2002. Financially completed in 2004. Issues resolved in 2005. | [10 empty] | 2000 | Non-Investment
COM | UNDP | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | VEN | SEV | 37 | INS | 95 | N | T | I | CFC | 24 | 24 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 |  | 285480 | 0 | 285480 | 284499 | 99.66% | 981 | 0 | 490.5 | 37112 | 0 | 36984.87 | 127.53 | 0 | Completed in 2004. | [10 empty] | 2002 | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | VEN | SEV | 43 | INS | 99 | N | T | I | CFC | 24 | 12 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 | 2006-07-01 |  |  | 285480 | 0 | 285480 | 146677 | 51.38% | 138803 | 0 | 48581.05 | 21411 | 0 | 11000.775 | 10410.225 | 0 | During 2005 the NOU of Venezuela continued successfully implementing the ODS phase out activities, improving the ODS related legislation and monitoring national compliance with the Montreal Protocol through data collection and monitoring of consumption. The NOU worked in the implementation of the National Phase Out Plan, completing activities such as the delivery of equipment to the training centers, initiation of training courses in 14 training centers and establishment of centers for supply, regeneration and reuse of CFC. The NOU has continued supporting implementation of activities related to the production closure plan. Regular awareness activities were also implemented such as the celebration of the ozone day, the presentation of the good practices video to the media. The NOU of Venezuela also organized the Main Meeting of Latin American Ozone Officers and a regional workshop on illegal trade. | [10 empty] | 2004 | Non-Investment
ONG | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | VEN | SEV | 45 | TAS | 102 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 45872 | 0 | 45872 | 0 | 0% | 45872 | 0 | 16055.2 | 4128 | 0 | 0 | 4128 | 0 | Approved in Apr 05. Activities initiated. | [10 empty] | 2005 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | VIE | SEV | 12 | PRP | 01 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Saigon Cosmetics Company | Individual | ASP | VIE | ARS | 17 | INV | 07 | A | O | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 1998-08-01 | 2000-12-01 | 238430 | -2439 | 235991 | 235991 | 100% | 0 | 0 | 0 | 30996 | -317 | 30679 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [10 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at Daso Company Ltd. | Individual | ASP | VIE | ARS | 18 | INV | 10 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1999-12-01 | 2001-08-01 | 110340 | -320 | 110020 | 110020 | 100% | 0 | 0 | 0 | 14344 | -41 | 14303 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-06-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Cosmetics Producing and Trading Company (CP & T) | Individual | ASP | VIE | ARS | 18 | INV | 11 | A | O | I | CFC | 85 | 85 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 2002-05-01 | 2003-11-01 | 285120 | -2641 | 282479 | 282479 | 100% | 0 | 0 | 0 | 37066 | -343 | 36723 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  |  | 1999-09-01 | [6 empty] | 1995 | Investment
FIN | UNDP | Demonstration project in CFC recycling and emissions reduction in the commercial refrigeration sector | RMP-Component | ASP | VIE | REF | 20 | DEM | 13 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1998-09-01 |  | 2002-12-01 | 2004-09-01 | 168216 | -10238 | 157978 | 157978 | 100% | 0 | 0 | 0 | 21868 | -1331 | 20537 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  |  | 2000-07-01 | [6 empty] | 1996 | Non-Investment
CLO | UNDP | Project preparation in the domestic refrigeration sub-sector | Individual | ASP | VIE | REF | 22 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-12-01 |  |  | 1998-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 | 0 | 3250 | -3250 | 0 | 0 | 0 | Canceled in 1998. | [10 empty] | 1997 | Investment
FIN | UNDP | Project preparation for one project in the aerosol sector | Individual | ASP | VIE | ARS | 24 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [10 empty] | 1998 | Investment
FIN | UNDP | Preparation of two projects in general foam subsector | Individual | ASP | VIE | FOA | 27 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 21815 | 145.4% | -6815 | 0 | 0 | 1950 | 0 | 2835.95 | -885.95 | 0 | Completed in 2000. Financially completed in 2001. Apparent overrun to be resolved in 2006. | [10 empty] | 1999 | Investment
FIN | UNDP | Preparation of a project in the foam general sector | Individual | ASP | VIE | FOA | 30 | PRP | 24 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -625 | 19375 | 19375 | 100% | 0 | 0 | 0 | 2600 | -81 | 2519 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of a project in the aerosol sector | Individual | ASP | VIE | ARS | 30 | PRP | 25 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 10000 | -2192 | 7808 | 7808 | 100% | 0 | 0 | 0 | 1300 | -285 | 1015 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of a project in the refrigeration recycling subsector | Individual | ASP | VIE | REF | 30 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 5000 | -1096 | 3904 | 3904 | 100% | 0 | 0 | 0 | 650 | -142 | 508 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 2000 | Investment
COM | UNDP | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | Individual | ASP | VIE | ARS | 31 | INV | 28 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2003-08-01 |  | 2005-06-01 |  | 49720 | 0 | 49720 | 48085 | 96.71% | 1635 | 0 | 817.5 | 6464 | 0 | 6251.4368 | 212.5632 | 0 | Completed in 2005. Supplier completed installation. Trial successful and local works finalized. Project completion verified during visit in March. | [10 empty] | 2000 | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | VIE | REF | 33 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | VIE | ARS | 33 | PRP | 31 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | ASP | VIE | FOA | 33 | PRP | 32 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
COM | UNDP | Implementation of the RMP: MAC recovery and recycling of CFC-12 refrigerant | RMP-Update-Comp | ASP | VIE | REF | 34 | TAS | 35 | A | O | I | CFC | 6 | 6 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-08-01 |  | 50500 | 0 | 50500 | 50500 | 100% | 0 | 0 | 0 | 6565 | 0 | 6565 | 0 | 0 | Completed in 2003. | [10 empty] | 2001 | Non-Investment
COM | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Update-Comp | ASP | VIE | REF | 34 | TAS | 38 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-12-01 |  | 21600 | 0 | 21600 | 21358 | 98.88% | 242 | 0 | 121 | 2808 | 0 | 2776.54 | 31.46 | 0 | Completed in 2004. | [10 empty] | 2001 | Non-Investment
COM | UNDP | Implementation of the RMP: Programme for recovery and recycling of CFC-12 refrigerant | RMP-Update-Comp | ASP | VIE | REF | 35 | TAS | 39 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 |  | 290413 | 0 | 290413 | 267212 | 92.01% | 23201 | 0 | 11600.5 | 37754 | 0 | 34737.8452 | 3016.1548 | 0 | Completed in 2004. | [10 empty] | 2001 | Non-Investment
COM | UNDP | Terminal umbrella project for the aerosol sector to phase-out ODS consumption in the manufacture of aerosols and perfumes by conversion to hydrocarbon propellant (Dong A and Thorakao Cosmetics Ltd.) | Individual | ASP | VIE | ARS | 37 | INV | 40 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-04-01 |  | 2005-06-01 |  | 125400 | 0 | 125400 | 123809 | 98.73% | 1591 | 0 | 795.5 | 16302 | 0 | 16095.17 | 206.83 | 0 | Completed in 2005. Installations at both companies completed. Trials successful and local works finalized. Project completion verified during visit in March. | [10 empty] | 2002 | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | YEM | REF | 33 | PRP | 06 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2003-07-01 | 15000 | -1934 | 13066 | 13066 | 100% | 0 | 0 | 0 | 1950 | -251 | 1699 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [10 empty] | 2001 | Investment
ONG | UNDP | Implementation of the RMP: national recovery and recycling programme for refrigerants in the commercial and MAC sectors | RMP-Update-Comp | ASP | YEM | REF | 37 | TAS | 15 | A | O | I | CFC | 220 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 | 2007-08-01 |  |  | 1472730 | 0 | 1472730 | 1170320 | 79.47% | 302410 | 0 | 60482 | 172000 | 0 | 136681.8026 | 35318.4974 | 0 | First contract finally agreed to with Government for first phase. Once first phase over (1Q 06), second phase to commence. | [10 empty] | 2002 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 17 | PRP | 04 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-03-01 |  | 1996-06-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 18 | PRP | 05 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [10 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | ZAM | REF | 19 | TAS | 06 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -240 | 106080 | 106080 | 100% | 0 | 0 | 0 | 13822 | -31 | 13791 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | AFR | ZIM | FUM | 24 | PRP | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [10 empty] | 1998 | Investment
FIN | UNDP | Alternatives to the use of methyl bromide on stacked bags of maize under gas proof PVC sheets and plastic cocoons (storage) | Individual | AFR | ZIM | FUM | 27 | DEM | 17 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 2000-12-01 | 2003-04-01 | 212850 | -10142 | 202708 | 202708 | 100% | 0 | 0 | 0 | 27671 | -1319 | 26352 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [10 empty] | 1999 | Investment
FIN | UNDP | Project preparation in the fumigation storage sector | Individual | AFR | ZIM | FUM | 33 | PRP | 23 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [10 empty] | 2001 | Investment
ONG | UNDP | Project preparation for the re-formulation of solvent technical assistance | Individual | AFR | ZIM | SOL | 42 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 | 2006-12-01 |  |  | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 8000 | 1800 | 0 | 1800 | 0 | 0 | Terms of Reference for National Expert prepared. Recruitment in 2006. Project document expected to be submitted to 50th ExCom. | [10 empty] | 2004 | Investment
CLO | UNDP | Project preparation for a fumigant (methyl bromide) project | Individual | AFR | ZIM | FUM | 45 | PRP | 31 | N | O | I | MeBr | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 0 | 1500 | 0 | 0 | 1500 | 0 | UNIDO prepared a large project in the soil sector in 05 (approved ExCom 47). UNDP offered post-harvest work to UNIDO so harmonized strategic ntl phaseout could be implemented. UNDP ExCom 35 ProDoc submitted to UNIDO. Funds returned at 48th ExCom. | [10 empty] | 2005 | Investment
COM | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | AFG | SEV | 43 | INS | 01 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2005-07-01 |  | 40000 | 0 | 40000 | 21287 | 53.22% | 18713 |  | 18713 | 0 | 0 | 0 | 0 |  | Project completed in July 2005. Capacity Building workshops conducted for the members of the Steering Committee from different ministries and departments in March 2005. UNEP/GTZ joint mission in March 2005 to build awareness & capacity of national stakeholders on Montreal Protocol issues. As part of expedited assistance approach for new Parties, one day workshop for Refrigerant Technicians in Kabul was conducted wherein more than 30 technicians attended the workshop. For awareness programme: Flyers for Refrigerant Air Condition technicians were printed and distributed in more than 8 provinces in the country. NOU delivered presentations to the provincial directors of the National Environmental Protection Agency on the Ozone layer Science and its mechanism of depletions. | [10 empty] | 2004 | Non Investment
COM | UNEP | Preparation of the country programme/RMP project | Individual | ASP | AFG | SEV | 43 | CPG | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-03-01 |  | 2005-10-01 |  | 60000 | 0 | 60000 | 37050.74 | 61.75% | 22949.26 | 8000 | 22949.26 | 7800 | 0 | 4816.5962 | 2983.4038 | 1040 | Project completed in October 2005. Afghanistan CP/RMP was adopted/approved by the Government of Afghanistan and it was submitted to 47th ExCom. NPP was approved in the 47th ExCom in November 2005. | [10 empty] | 2004 | Non Investment
COM | UNEP | Start up of institutional strengthening project | Individual | ASP | AFG | SEV | 46 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-12-01 |  | 2005-10-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in October 2005. For awareness programme: International Ozone Day Celebration was held in Kabul with the involvement of different ministerial, international organizations participation on 15th December 2005 at the International Press centre, Ministry of Information, Culture and Tourism. MOU was signed between the Government of Afghanistan and UNEP as per agreement on this IS Phase I project. Initial payment was obligated in September 2005. o Printing materials developed in consultation with NEPA for the celebration of International Ozone Day on 16th September. Posters, Brochures, file folders, Printed Pens, Notebooks and Green Flags were printed in big numbers and distributed in universities, schools, and different ministries. OzzyOzone Video was dubbed in two national languages, the Pashto and Dari language and was broadcasted by two television networks, for three consecutive days on the eve of Ozone day celebrations. NOU delivered two presentations on the Ozone layer depletion and its threat to human life on earth and role of journalism in protecting the environment to the workshop participants “Journalism and Environment". Train the Trainers workshop was conducted for Custom officers on controlling the imports of Ozone Depleting substance in Kabul wherein more than 40 officers attended the workshop. Experts from NACEN India, RILO, UNEP, and Pakistan Customs also attended and delivered presentations. The national stakeholders like Customs Department, Chamber of Commerce, Ministry of Finance, and Ministry of Commerce attended the workshop. National Ozone Unit successfully got approval for Banning the imports of ODS based equipments. Presidential decree was issued from President Office banning the imports of ODS based equipments. The Draft ODS regulations are in final stages to come under operation. The NPP was prepared and submitted to the 47th ExCom meeting in November 2005. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Establishment of national ozone unit for implementing the phase-out of ODS (institutional strengthening) | Individual | ASP | AFG | SEV | 47 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | Project newly approved in the 47th ExCom meeting in November 2005. The budget and workplan was agreed with country and initial disbursement was released. NPP approved & implementation initiated. | [10 empty] | 2005 | Non Investment
ONG | UNEP | National phase-out plan (1st tranche) | Multi-year | ASP | AFG | PHA | 47 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 305000 | 0 | 305000 | 15 | 0.004918% | 304985 | 0 | 304985 | 39650 | 0 | 1.95 | 39648.05 | 0 | This project was approved in the 47th ExCom meeting in November 2005. Draft MOU prepared to obligate fund to the country. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Regional workshop for Africa | Individual | AFR | AFR | SEV | 06 | TRA | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1992-12-01 | 1993-12-01 | 210000 | 0 | 210000 | 210000 | 100% | 0 |  |  | 27300 | 0 | 27300 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Regional training course on refrigeration for Africa | Individual | AFR | AFR | REF | 06 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  | 1992-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 10 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1995-07-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 |  |  | 5642 | 0 | 5642 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 10 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-09-01 | 1994-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 |  |  | 5642 | 0 | 5642 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Follow-up on prior regional workshop and training activities | Individual | AFR | AFR | SEV | 12 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-06-01 | 1999-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Support to regional network for ODS officers in Africa (1994) | Individual | AFR | AFR | SEV | 12 | TAS | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-26 | 1995-03-01 |  | 1996-03-01 | 2000-03-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 |  |  | 23400 | 0 | 23400 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for English-speaking African countries | Individual | AFR | AFR | FUM | 16 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1995-09-01 | 1999-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for English-speaking Africa | Individual | AFR | AFR | SEV | 19 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 |  |  | 11050 | 0 | 11050 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | African Network (1996) | Individual | AFR | AFR | SEV | 19 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299400 | 0 | 299400 | 299400 | 100% | 0 |  |  | 38922 | 0 | 38922 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Regional survey and workshop on methyl bromide for French-speaking African countries | Individual | AFR | AFR | FUM | 21 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1998-04-01 | 1999-03-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 |  |  | 35750 | 0 | 35750 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | African Region Network (1997) | Individual | AFR | AFR | SEV | 21 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 411000 | -33344 | 377656 | 377656 | 100% | 0 |  |  | 53430 | -4334.72 | 49095.28 | 0 |  | Project financially completed. | $33344 plus $4335 PSC returned ExCom 30 | [9 empty] | 1993 | Non Investment
FIN | UNEP | Support to regional network for ODS officers in Africa (1995) | Individual | AFR | AFR | SEV | 16 | TAS | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-01-01 | 232200 | 0 | 232200 | 232200 | 100% | 0 |  |  | 30186 | 0 | 30186 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | African regional networks for French-speaking and English-speaking countries (1998) | Individual | AFR | AFR | SEV | 23 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-01-01 |  | 1998-12-01 | 2000-03-01 | 431000 | -21369 | 409631 | 409631 | 100% | 0 |  |  | 56030 | -2777.97 | 53252.03 | 0 |  | Project financially completed. | $21369 plus $2778 PSC returned ExCom 30 | [9 empty] | 1993 | Non Investment
FIN | UNEP | Africa Region Network (French-speaking and English-speaking) | Individual | AFR | AFR | SEV | 26 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 431000 | -14398 | 416602 | 416602 | 100% | 0 |  |  | 56030 | -1871.74 | 54158.26 | 0 |  | Project financially completed. | $14398 plus $1872 PSC returned ExCom 37 | [9 empty] | 1998 | Non Investment
COM | UNEP | Regional training of trainer courses for extension workers | Individual | AFR | AFR | FUM | 27 | TRA | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 |  | 80000 | -10681 | 69319 | 67462 | 97.32% | 1857 | 0 | 1857 | 10400 | -1389 | 8769.6026 | 241.3974 | 0 | Project completed. | $10681 plus $1389 PSC returned ExCom 46 | [9 empty] | 1999 | Non Investment
FIN | UNEP | Regional training workshops on policy development | Individual | AFR | AFR | FUM | 27 | TRA | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2000-03-01 |  | 1999-12-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  |  | 16900 | 0 | 16900 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | African regional network (French-and English-speaking countries) (2000) | Individual | AFR | AFR | SEV | 29 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-01-01 | 452550 | -30000 | 422550 | 422296 | 99.94% | 254 |  | 0 | 58831.5 | -3900 | 54898.48 | 33.02 |  | Project financially completed. | $30000 plus $3900 PSC returned ExCom46 | [9 empty] | 1999 | Non Investment
FIN | UNEP | African regional network (French-speaking, English-speaking) (2001) | Individual | AFR | AFR | SEV | 32 | TAS | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 464000 | -36863 | 427137 | 427137 | 100% | 0 |  |  | 60320 | -4792.19 | 55527.81 | 0 |  | Project financially completed. | $36863 plus 4792 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
COM | UNEP | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | Individual | AFR | AFR | SEV | 32 | TAS | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-06-01 |  | 2004-11-04 |  | 151500 | 0 | 151500 | 129414.9 | 85.42% | 22085.1 | 9136.96 | 22085.1 | 19695 | 0 | 16823.937 | 2871.063 | 739.44 | Project completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | AFR | AFR | FUM | 34 | TRA | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-08-01 | 2002-07-01 |  | 2004-03-01 |  | 80000 | 0 | 80000 | 48128.42 | 60.16% | 31871.58 | 27262.23 | 31871.58 | 10400 | 0 | 6256.6946 | 4143.3054 | 3544 | Project completed. | [7 empty] | 2003-09-01 |  |  | 2001 | Non Investment
ONG | UNEP | Sub-regional project on harmonisation of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in English-speaking Africa | Individual | AFR | AFR | SEV | 45 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 |  |  | 140000 | 0 | 140000 | 0 | 0% | 140000 | 0 | 140000 | 18200 | 0 | 0 | 18200 | 1948.05 | Consultations with ECOWAS, COMESA Secretariats made and MOUs drfated. COMESA signed MOU and implementation of activities commenced. Extensive consultations with ozone officers to finalise implementation modalities conducted during network meetings. Consultations with SACU Secretariat on going. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | EUR | ALB | SEV | 30 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-06-01 | 2005-12-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 |  | 0 | 7800 | -3770 | 4030 | 0 |  | Project completed. | $29000 plus 3770 PSC returned ExCom 46 | [5 empty] | 2002-09-01 |  |  |  | 2000 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | ALB | SEV | 35 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  |  | 5460 | 0 | 5460 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Establishment of the Ozone Unit (second year) | Individual | EUR | ALB | SEV | 38 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2003-12-01 |  | 2005-07-01 |  | 54600 | 0 | 54600 | 52898 | 96.88% | 1702 |  | 1702 | 0 | 0 | 0 | 0 |  | Project completed in July 2005. Actitivies under this Phase have been completed in July 2005. Albania is in compliance. Renewal request was approved at July ExCom meeting. NOU is operational. Training activities are ongoing: refrigeration training Phase 2 and Customs training Phase 2. NOU worked on ODS legislation and MP Amendments during 2005. NOU visited Croatia to learn from Croatia's experience in organisation of Refrigeration training activities, as well as in setting up ODS legislation. | [10 empty] | 2002 | Non Investment
COM | UNEP | National ODS phase-out plan: training of customs officers in monitoring of ODS | Individual | EUR | ALB | PHA | 39 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2005-08-01 |  | 35700 | 0 | 35700 | 35422.11 | 99.22% | 277.89 | 278 | 277.89 | 4641 | 0 | 4604.8743 | 36.1257 | 36 | Project completed in August 2005. Phase II was conducted from April-May 2005 in 5 different Customs Regions in Albania with a total of 70 customs officers and key stakeholders from national agencies taking part. A follow up report was submitted by the NOU Officer in June 2005. Release of final payment to Albania was authorized by UNON in August 2005. The first draft of the PCR is currently being prepared by the NOU. | [10 empty] | 2003 | Non Investment
ONG | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | Individual | EUR | ALB | PHA | 39 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 | 2006-07-01 |  |  | 82425 | 0 | 82425 | 29018.06 | 35.21% | 53406.94 | 53407 | 53406.94 | 10715.25 | 0 | 3772.3478 | 6942.9022 | 6943 | Eight "training of technicians" were carried out in various parts of the country and over 150 technicians trained. A training manual/handbook on Good Practices in Refrigeration was compiled and published locally in the Albanian language. This training publication was used as a resource material in the training. | [9 empty] | 2005-07-01 | 2003 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase I, year 3) | Individual | EUR | ALB | SEV | 46 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 |  | 2007-07-01 | 2007-07-01 |  |  | 54600 | 0 | 54600 | 0 | 0% | 54600 | 54600 | 54600 | 0 | 0 | 0 | 0 | 0 | NOU continued training workshops in Refrigeration and Customs. A training centre was set up in Tirana for delivery of training workshops. NOU is coordinating also the R&R activities (UNIDO). | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ALG | SEV | 09 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1993-06-01 |  | 1993-11-01 | 1994-12-01 | 15000 | 3000 | 18000 | 18000 | 100% | 0 |  |  | 1950 | 390 | 2340 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Institutional support for ODS phase-out | Individual | AFR | ALG | SEV | 11 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-01-01 | 1996-11-01 |  | 1999-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 |  |  | 38610 | 0 | 38610 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1993 | Non Investment
FIN | UNEP | Renewal of institutional strengthening - Phase II | Individual | AFR | ALG | SEV | 27 | INS | 32 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2003-06-01 | 90010 | 0 | 90010 | 90010 | 100% | 0 |  |  | 11701.3 | 0 | 11701.3 | 0 |  | Project financially completed. | [5 empty] | 2002-06-01 |  |  |  |  | 1999 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | AFR | ALG | SEV | 37 | INS | 54 | N | T | I | CFC | 21.2 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 | 2006-07-01 |  |  | 257000 | 0 | 257000 | 239302 | 93.11% | 17698 |  | 17698 | 0 | 0 | 0 | 0 |  | Implementation of IS activities was successfully done in 2005 in Algeria. There was a new ODS Officer appointed but the rest of the NOU team remaining the same the change did not hamper the activities. The use of the IS funds were rephased to sustain the NOU up-to June 2006. During the past year the NOU successfully coordinated the successfully implemention of phase-out activites under the RMP and other investment projects with UNIDO as IA. The NOU produced awreness material part of which were distributed to other ODS officer during the 2005 french-speaking Africa network meeting. | [10 empty] | 2002 | Non Investment
TRF | UNEP | Preparation of country programme | Individual | AFR | ANG | SEV | 32 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2002-04-01 |  |  | 2001-12-01 | 60000 | -60000 | 0 | 0 | 0% | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 |  | Project transferred | $60000 plus $7800 returned ExCom 34 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | ANT | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1998-09-01 | 1999-06-01 | 30000 | -969 | 29031 | 29031 | 100% | 0 |  |  | 3900 | -125.97 | 3774.03 | 0 |  | Project financially completed. | $969 plus $126 PSC returned ExCom 30 | [9 empty] | 1991 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | ANT | REF | 21 | PRP | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1998-09-01 | 1999-04-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 |  |  | 3900 | -650 | 3250 | 0 |  | Project financially completed. | $5000 plus $650 PSC returned ExCom 30 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | ANT | SEV | 26 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-09-01 | 2001-12-01 |  | 2002-12-01 | 2004-10-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 |  |  | 4680 | 0 | 4680 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
COM | UNEP | Renewal of institutional strengthening project | Individual | LAC | ANT | SEV | 38 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-06-01 |  | 31200 | 0 | 31200 | 14163 | 45.39% | 17037 |  | 17037 | 0 | 0 | 0 | 0 |  | Project completed in June 2005. All reports received and approved by UNON. Funds are sufficiently exhausted to allow for establishment of MOU under the IS renewal at the 44th Ex. Com. Data reporting to both the MLF and OS completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | ANT | SEV | 44 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Explanation on the new UNEP modality for ISP implementation and MOU type were provided by CAP team. MOU signed in July 2005. | [10 empty] | 2004 | Non Investment
FIN | UNEP | National train the trainer programme on good practices in refrigeration | Individual | LAC | ARG | REF | 21 | TRA | 51 | A | O | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 1999-12-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 |  |  | 27950 | 0 | 27950 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
ONG | UNEP | Policy assistance for the design and implementation of an ODS import/export licensing system for Argentina | Individual | LAC | ARG | SEV | 30 | TAS | 104 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-11-01 | 2006-09-01 |  |  | 90000 | 0 | 90000 | 89999.66 | 100% | 0.34 | 0 | 0.34 | 11700 | 0 | 11699.9558 | 0 | 0 | Amended MOU still under country review as of Feb-05. MLFS asked for clarification about new MOU in Mar-05. MOU cleared in May-05 and sigend by country in June-05. | [6 empty] | 2002-12-01 | 2003-10-01 |  |  | 2000 | Non Investment
ONG | UNEP | Training of customs officers | Individual | LAC | ARG | REF | 32 | TRA | 114 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-02-02 | 2006-06-01 |  |  | 175000 | 0 | 175000 | 121398.16 | 69.37% | 53601.84 | 53407.72 | 53601.84 | 22750 | 0 | 15781.7608 | 6968.2392 | 6943.0036 | Phase II work plan finalized in Feb-05. From Mar-05 to Dec-05 more than 200 customs officers and 39 officers from other institutions (including NGOs) were trained. Last workshop in Buenos Aires couldn't take place in Dec-05 due to internal restructuring of the Customs Administration. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Training programme for the refrigeration servicing sector (Phase III) | Individual | LAC | ARG | REF | 32 | TRA | 115 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2003-12-01 | 2006-12-01 |  |  | 300000 | 0 | 300000 | 204000 | 68% | 96000 | 28666 | 96000 | 39000 | 0 | 26520 | 12480 | 6240 | Training completed. Certification programme and complementary training activities to be implemented during first half of 2006 | [10 empty] | 2000 | Non Investment
FIN | UNEP | Regional workshop for Asia and the Pacific | Individual | ASP | ASP | SEV | 04 | TRA | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-11-01 |  | 1991-11-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 |  |  | 31980 | 0 | 31980 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
FIN | UNEP | Refrigeration training workshop for Asia and the Pacific | Individual | ASP | ASP | REF | 09 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-04-01 |  | 1994-04-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  |  | 11700 | 0 | 11700 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 10 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-02-01 | 1999-04-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 |  |  | 5642 | 0 | 5642 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 10 | TRA | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-09-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 |  |  | 5642 | 0 | 5642 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Workshop for small and medium size enterprises on management of ODS phase-out | Individual | ASP | ASP | SEV | 12 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-21 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Regional workshop on aerosol conversion for the SEAP region | Individual | ASP | ASP | ARS | 16 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1995-06-01 |  | 1995-05-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 15600 | 0 | 15600 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | ODS officers network for Asia and the Pacific (1995) | Individual | ASP | ASP | SEV | 16 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-20 | 1996-03-01 |  | 1996-03-01 | 2000-03-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 |  |  | 8060 | 0 | 8060 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-23 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 82500 | 0 | 82500 | 82500 | 100% | 0 |  |  | 10725 | 0 | 10725 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for West Asia | Individual | ASP | ASP | SEV | 19 | TRA | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 1999-03-01 | 80000 | -19056 | 60944 | 60944 | 100% | 0 |  |  | 10400 | -2477.28 | 7922.72 | 0 |  | Project financially completed. | $19056 plus $2477 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Networking and Training (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | West Asian Network (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-12-01 | 169200 | -24323 | 144877 | 144877 | 100% | 0 |  |  | 21996 | -3161.99 | 18834.01 | 0 |  | Project financially completed. | $24323 plus $3162 PSC returned ExCom 30 | [9 empty] | 1998 | Non Investment
FIN | UNEP | West Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 |  |  | 14300 | 0 | 14300 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | South Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 199000 | -109950 | 89050 | 89050 | 100% | 0 |  |  | 25870 | -14293.5 | 11576.5 | 0 |  | Project financially completed. | $109,950 plus 14294 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Asia Regional Networks for SEAP and East Asia (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 209000 | -48604 | 160396 | 160396 | 100% | 0 |  |  | 27170 | -6318.52 | 20851.48 | 0 |  | Project financially completed. | $48604 plus $6319 PSC returned ExCom 30 | [9 empty] | 1995 | Non Investment
FIN | UNEP | West Asian regional network 1998 | Individual | ASP | ASP | SEV | 23 | TAS | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  |  | 14950 | 0 | 14950 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Asia Regional Networks (South-East and Pacific and South Asia) | Individual | ASP | ASP | SEV | 26 | TAS | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 |  |  | 27170 | 0 | 27170 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | West Asian Region Network | Individual | ASP | ASP | SEV | 26 | TAS | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  |  | 14950 | 0 | 14950 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Asia and the Pacific Regional networks (South East Asia and Pacific and South Asia) (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 219450 | -18941 | 200509 | 200509 | 100% | 0 |  | 0 | 28528.5 | -2462.33 | 26066.17 | 0 |  | Project financially completed. | $18941 plus $2462 PSC returned ExCom 46 | [9 empty] | 1999 | Non Investment
FIN | UNEP | West Asian region network (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2005-12-01 | 120750 | -15000 | 105750 | 105750 | 100% | 0 |  | 0 | 15697.5 | -1950 | 13747.5 | 0 |  | Project financially completed. | $15000 plus $1950 PSC returned ExCom 46 | [9 empty] | 1999 | Non Investment
FIN | UNEP | West Asia military ODS workshop (to be held in conjunction with a global military environmental conference) | Individual | ASP | ASP | SEV | 30 | TRA | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-05-01 | 2003-06-01 | 150000 | -15122 | 134878 | 134878 | 100% | 0 |  |  | 19500 | -1965.86 | 17534.14 | 0 |  | Project financially completed. | $15122 plus $1966 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
COM | UNEP | Workshop for halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen | Individual | ASP | ASP | HAL | 30 | TRA | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2002-10-01 | 2001-10-01 |  | 2004-12-01 |  | 50000 | 0 | 50000 | 47639.67 | 95.28% | 2360.33 | 0 | 2360.33 | 6500 | 0 | 6193.1571 | 306.8429 | 0 | Project completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | West Asian regional network (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 124000 | -15001 | 108999 | 108999 | 100% | 0 |  |  | 16120 | -1950.13 | 14169.87 | 0 |  | Project financially completed. | $15001 plus $1950 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | ASP | ASP | FUM | 34 | TRA | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2002-06-01 |  | 2003-12-01 | 2005-12-01 | 80000 | -13239 | 66761 | 66760.95 | 100% | 0.05 | 0 | 0 | 10400 | -1721.07 | 8678.9235 | 0.0065 | 0 | Project financially completed. | $13239 plus $1721 returned ExCom 46 | [9 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the PIC Strategy: Three thematic meetings on issues related to the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-11-01 | 2005-04-01 | 2006-12-01 |  |  | 50000 | 0 | 50000 | 36552 | 73.1% | 13448 | 0 | 13448 | 6500 | 0 | 4751.76 | 1748.24 |  | The third thematic meeting was originally planned for August 2005. It is now being postponed to 2006 due to delay by countries not being able to establish their ODS regulations. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the PIC Strategy: Technical assistance for other countries not included in the strategy | Individual | ASP | ASP | REF | 36 | TAS | 45 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 | 2006-12-01 |  |  | 50000 | 0 | 50000 | 42316 | 84.63% | 7684 | 0 | 7684 | 6500 | 0 | 5501.08 | 998.92 |  | All eligible countries in the Pacific region are now Parties to the Montreal Protocol. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the PIC Strategy: Policy assistance and guidance to countries for development of regulations | Individual | ASP | ASP | REF | 36 | TAS | 46 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 | 2006-12-01 |  |  | 90000 | 0 | 90000 | 36666 | 40.74% | 53334 | 0 | 53334 | 11700 | 0 | 4766.58 | 6933.42 |  | Marshall Islands is the first PIC to establish ODS regulation. Tonga, Palau probably would establish their regulations within 2005. | [8 empty] | 2005-12-01 |  | 2002 | Non Investment
ONG | UNEP | Implementation of the PIC Strategy: Technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 47 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2005-12-01 | 2006-12-01 |  |  | 120000 | 0 | 120000 | 69231 | 57.69% | 50769 | 0 | 50769 | 15600 | 0 | 9000.03 | 6599.97 |  | Only 1 out of 8 customs training workshops was carried out due to delay in establishing the ODS regulations. APO at SPREP left in October 2005 and the replacement options are either contracting her as consultant (SPREP preferred option) or seek new APO. | [10 empty] | 2002 | Non Investment
FIN | UNEP | South East Asia and the Pacific and South Asia regional networks (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 48 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2002-06-01 | 2003-06-01 | 225000 | -20468 | 204532 | 204532 | 100% | 0 |  |  | 29250 | -2660.84 | 26589.16 | 0 |  | Project financially completed. | $20468 plus $2661 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 44 | TAS | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 |  | A Regional Consultant and one Assistant Programme Officer were contracted by SPREP to provide the service and monitor the implementation. They have maintained regular contacts with the countries to follow up issues including:Operation of the National Compliance Centre o Organization of technicians training workshops; Data reporting to the Ozone Secretariat and Fund Secretariat; Establishment of ODS regulations and licensing system. SPREP however has not submited any expenditure report to date. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | BAH | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-06-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | ASP | BAH | SEV | 20 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. |  |  | 2000-03-01 | [7 empty] | 1996 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | ASP | BAH | REF | 26 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-05-01 | 1999-12-01 |  | 2001-12-02 | 2001-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  |  | 5850 | 0 | 5850 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | ASP | BAH | REF | 26 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-02 |  | 2001-12-01 | 2003-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. |  |  |  |  | 2001-05-01 | [5 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | BAH | SEV | 31 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 |  |  | 5720 | 0 | 5720 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 3 | Individual | ASP | BAH | SEV | 41 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-12-01 |  | 2005-12-01 |  | 57200 | 0 | 57200 | 30803 | 53.85% | 26397 |  | 26397 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. Bahrain submitted the required reports to UNON in order to complete Phase 3 and accordingly they received the final payment in June 2005. They submitted their A7 reports to the OS as of 2004, along with their progress report to the MFS as of 2004. The ODS officer of Bahrain participated in all meetings & workshops organized by CAP, and with the cooperation of CAP he has also maintained good contact with IAs (UNIDO & UNDP), for preparation of approved projects - mainly CTC/TCA and RMPU (currently they are working on upgrading it to TPMP). | - Operation of the National Compliance Centre | [9 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | BAH | SEV | 47 | INS | 15 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | BAR | SEV | 09 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-12-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | BAR | SEV | 15 | INS | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1997-12-01 |  | 1998-12-01 | 1999-10-01 | 136000 | -1050 | 134950 | 134950 | 100% | 0 |  |  | 17680 | -136.5 | 17543.5 | 0 |  | Project financially completed. | $1050 plus $137 PSC returned ExCom 30 | [9 empty] | 1992 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BAR | SEV | 26 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2005-12-01 | 2005-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  | 0 | 11700 | 0 | 11700 | 0 |  | Project completed and financially completed in December 2005. Slow rate of disbursements due to non-submission of reports by country. UNEP Letter dated September 2005 sent to Minister requesting her intervention for the progress of this project. In 2004/2005 the staff of the NOO was stabilized with the appointment of an NOO assistant, supported through the IS funds. Finally, all outstanding IS reports submitted and accepted by UNON in Dec 2005. Country has sent ODS data reporting to both Secretariats. | o Data reporting to the Ozone Secretariat and Fund Secretariat | [9 empty] | 1998 | Non Investment
FIN | UNEP | Development of RMP | RMP | LAC | BAR | REF | 30 | PRP | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-05-01 | 2005-07-01 | 30000 | -17982 | 12018 | 12018 | 100% | 0 | 0 | 0 | 3900 | -2337.66 | 1562.34 | 0 |  | Project financially completed. | $17982 plus $2338 returned ExCom 46 | [9 empty] | 2000 | Non Investment
ONG | UNEP | Extension of Institutional strengthening project (phase III) | Individual | LAC | BAR | SEV | 42 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-05 | 2008-03-05 |  |  | 58500 | 0 | 58500 | 9381 | 16.04% | 49119 |  | 49119 | 0 | 0 | 0 | 0 |  | First cash advance requested in Dec 2005 because there was remaining funds of phase II. | o Establishment of ODS regulations and licensing system | [9 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: import-export licensing system and establishment of refrigeration and air-conditioning association | Individual | LAC | BAR | REF | 43 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-03-01 | 2006-12-01 | 2006-12-01 |  |  | 78000 | 0 | 78000 | 47000.25 | 60.26% | 30999.75 | 30003 | 30999.75 | 10140 | 0 | 6110.0325 | 4029.9675 | 3900 | Signed MOUs first week in March 2005. First payment made in March 2005. Launch of the RMP was done to stakeholders, March 2005. Launch of the Refrigeration Association done March 2005. National Association registered, Articles of Association completed and registered, August of 2005. Local Consultation recruited for the preparation of the ODS Licensing System. Policy workshop for the establishment of the ODS legislative process completed in March 2006. Legislation is planned for completion in June 2006 with customs training planned for July 2006. | o Organization of technicians training workshops | [9 empty] | 2004 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase III, year 2) | Individual | LAC | BAR | SEV | 46 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 |  | 2007-07-01 | 2007-07-01 |  |  | 58500 | 0 | 58500 | 0 | 0% | 58500 | 0 | 58500 | 0 | 0 | 0 | 0 | 0 | Budget and work plan submitted. Draft MOU submitted to Party for review and comments. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | AFR | BDI | SEV | 23 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-05-01 |  | 1998-09-01 | 1999-03-01 | 40000 | -10000 | 30000 | 30000 | 100% | 0 |  |  | 5200 | -1300 | 3900 | 0 |  | Project financially completed. | $10000 plus $1300 PSC returned ExCom 30 | [9 empty] | 1995 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training for customs officers | Individual | AFR | BDI | REF | 26 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training technicians in good management practices | Individual | AFR | BDI | REF | 26 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Establishment of an Ozone Unit | Individual | AFR | BDI | SEV | 26 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-11 | 2001-12-01 |  | 2002-07-01 | 2003-07-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | AFR | BDI | SEV | 37 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-12-04 | 2005-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 | 2006-07-01 |  |  | 30000 | 0 | 30000 | 15015 | 50.05% | 14985 | 14985 | 14985 | 3900 | 0 | 1951.95 | 1948.05 | 1948.05 | Burundi has finalised the phase I training programme since April 2005.Phase 2 started in June 2005 | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-06-01 | 2006-07-01 |  |  | 22500 | 0 | 22500 | 10000 | 44.44% | 12500 | 12500 | 12500 | 2925 | 0 | 1300 | 1625 | 1625 | Phase II training programme stared in january 2005 and finalised in April 2005 | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BDI | SEV | 44 | INS | 18 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | The NOU coordinated implementation and completion of activities under RMP update (customs traing and training of additional refrigeration technicians.). NOU organised awareness activities through the local media and organized conference accross the country including celebration of the Ozone Day. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | BEN | SEV | 13 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-04 | 1995-10-01 |  | 1995-10-01 | 1995-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 |  |  | 4550 | 0 | 4550 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | BEN | SEV | 18 | INS | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | BEN | REF | 27 | PRP | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2000-12-01 | 2001-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | BEN | SEV | 28 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-09-01 | 2001-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 |  |  | 4333.29 | 0 | 4333.29 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | BEN | SEV | 33 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-04 | 33333 | 0 | 33333 | 33333 | 100% | 0 |  |  | 4333.29 | 0 | 4333.29 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project | Individual | AFR | BEN | SEV | 40 | INS | 14 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 | 2006-07-01 |  |  | 43333 | 0 | 43333 | 32484 | 74.96% | 10849 |  | 10849 | 0 | 0 | 0 | 0 |  | After the illness and retirment of ODS officer in december 2004 activities of the NOU were slow. Under the direct coordination of the Director of Environment the government was able de coordinate the implemntation of some RMP activities including completing the training of customs officers and undertaking the training of environmental Inspectors (all 24 inspetors trained plus officers from other government departments). The NOU was reactivated towards the end of 2005. The IS project was to be completed in July 2005 but extended for one additional year. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Refrigerant management plan: Training prgramme for customs officers | Individual | ASP | BGD | REF | 29 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2001-12-01 |  | 2004-07-01 | 2004-07-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 | 0 | 0 | 2925 | 0 | 2925 | 0 | 0 | Project financially completed. | [10 empty] | 1999 | Non Investment
COM | UNEP | Refrigerant management plan: Training of trainers in good refrigerant management practices and implementation of a national technicians training programme | Individual | ASP | BGD | REF | 29 | TRA | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-03-01 | 2001-12-01 |  | 2004-12-04 |  | 88000 | 0 | 88000 | 54856 | 62.34% | 33144 | 32197 | 33144 | 11440 | 0 | 7131.28 | 4308.72 | 4186 | Project financially completed in September 2005. | [10 empty] | 1999 | Non Investment
ONG | UNEP | National ODS phase-out plan: training and certification programme for refrigeration service technicians, including development of a code of good practices (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2007-12-01 |  |  | 39500 | 0 | 39500 | 0 | 0% | 39500 | 0 | 39500 | 5135 | 0 | 0 | 5135 |  | CAP went for a mission in July 2005 with UNDP to push the country for the signature of the Project Document. Regional Director sent a letter to the Secretary in October 2005 for the same purpose apart from regular follow up with the country. | [9 empty] | 2007-12-01 | 2004 | Non Investment
ONG | UNEP | National ODS phase-out plan: training programme for custom officers (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 | 2006-12-01 |  |  | 21000 | 0 | 21000 | 11986 | 57.08% | 9014 | 0 | 9014 | 2730 | 0 | 1558.18 | 1171.82 |  | Identifiers and refrigeration equipment delivered to Bangladesh in March 2005 July 05: UNEP-UNDP Joint mission to Bangladesh - workplan for implementation agreed. Oct05: Regional Director sent a letter to the Secretary for signature of PD apart from regular follow up with the country. Nov05: Discussion with Ozone Officer on hiring national consultants – TOR and selection criteria | [10 empty] | 2004 | Non Investment
ONG | UNEP | National ODS phase-out plan: public awareness and information dissemination to main stakeholders (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 |  | CAP went for a mission in July 2005 with UNDP to push the country for the signature of the Project Document. Regional Director sent a letter to the Secretary in October 2005 for the same purpose apart from regular follow up with the country. | [9 empty] | 2007-12-01 | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | BHA | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
COM | UNEP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | BHA | SEV | 19 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-03-01 |  | 50000 | 0 | 50000 | 42502 | 85% | 7498 | 0 | 7498 | 6500 | 0 | 5525.26 | 974.74 |  | Project completed. | [10 empty] | 1996 | Non Investment
COM | UNEP | Implementation of the refrigerant management plan: Training in monitoring and controlling of ODSs | Individual | LAC | BHA | REF | 23 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-08-01 | 1998-02-04 |  | 2005-09-01 |  | 26500 | 0 | 26500 | 14000 | 52.83% | 12500 |  | 8333 | 3445 | 0 | 1820 | 1625 |  | Project completed in September 2005. Completion of the Custom training using the five days mixed approach. Expenditure reports received and final payments were processed and made by UNEP/PARIS in March 2006. Workshop report posted on the UNEP OzonAction webpage. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training the trainers of technicians in the refrigeration sector | Individual | LAC | BHA | REF | 23 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-05-01 | 2003-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Preparation of a terminal phaseout plan | RMP | LAC | BHA | SEV | 27 | PRP | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-12-01 | 2002-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 2 (one year) | Individual | LAC | BHA | SEV | 39 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2004-04-01 | 2006-07-01 |  |  | 21666 | 0 | 21666 | 0 | 0% | 21666 |  | 21666 | 0 | 0 | 0 | 0 |  | IS reports dated back to 2002 to the period December 2005 were received. Slow rate of disbursements due to non-reporting by the NOO. Letter form the office of UNEP/ROLAC Regional Director on the status of IS progress and the need for the intervention to progress in this project was sent to the Minister with responsibility for the Montreal Protocol in September 2005. As a result, country decided that ISP would be integrated to BEST, Government Unity in charge of TPMP. In spite of difficulties, country has sent ODS data, reporting to both Secretariats. ODS license system is approved and in force. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase II ) | Individual | LAC | BHA | SEV | 42 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2007-06-01 |  |  | 21667 | 0 | 21667 |  | 0% | 21667 |  | 21667 | 0 | 0 | 0 | 0 |  | First cash advance was not released yet because there were remaining funds from budget approved at the 39 ExCom meeting. | [10 empty] | 2004 | Non Investment
COM | UNEP | Preparation of country programme/RMP project | Individual | ASP | BHU | SEV | 43 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2006-07-01 |  | 2005-07-01 |  | 45000 | 0 | 45000 | 45000.48 | 100% | -0.48 | 0 | -0.48 | 5850 | 0 | 5850.0624 | 0 | 0 | Project completed in July 2005. The draft was finalized and sumbitted in Feb to the 45th Excom meeting for consideration. | [10 empty] | 2004 | Non Investment
COM | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | BHU | SEV | 43 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-07-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed in July 2005. Ozone Office set-up and work on ODS licensing system completed. Four customs officers were trained in India in February 2005. Bhutan participated in the dealers’ meeting in Guwahati on 20 March 2005 and was briefed on the awareness activities currently being undertaken through the India servicing sector project. RMP implementation workplan was discussed with the country and UNDP in April 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: train the trainer programme for customs and enforcement officers | Individual | ASP | BHU | REF | 45 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2006-04-01 | 2006-04-01 |  |  | 25000 | 0 | 25000 | 24892.74 | 99.57% | 107.26 | 0 | 107.26 | 3250 | 0 | 3236.0562 | 13.9438 | 0 | August 05: ODS regulations published. 2-3 November 05: National Train-the-trainer Customs workshop organised - 25 customs officers including HQ in Thimpu and Regional Customs Offices were trained November 05: 0,5 day training of 6 customs officers on practical use of ODS identifiers November 05: 3 ODS identifiers arrived in Thimpu | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | BHU | REF | 45 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-10-01 | 2006-06-01 |  |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Training programme- Phase I on RMP for refrigeration technicians was conducted in 14-17 November 2005. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Institutional strengthening project (phase I) | Individual | ASP | BHU | SEV | 46 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2008-07-01 | 2007-07-01 |  |  | 90000 | 0 | 90000 | 76838 | 85.38% | 13162 | 0 | 13162 | 0 | 0 | 0 | 0 | 0 | The MOU was signed between the Government of Bhutan and UNEP; the initial payment was obligated in November 2005. 3 Identifiers were delivered and subsequently had a practical exercise for customs officers in November 2005. Regional Green Customs Workshop was held in Bhutan in October 2005. Train the trainer workshops both for Refrigeration technicians and customs officers were conducted in November 2005. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | BKF | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-11-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 |  |  | 3900 | 390 | 4290 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Establishment of the Ozone Board | Individual | AFR | BKF | SEV | 11 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-12-01 | 1996-11-01 |  | 1997-06-01 | 1996-02-01 | 83500 | 0 | 83500 | 83500 | 100% | 0 |  |  | 10855 | 0 | 10855 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Training for refrigeration repair technicians | Individual | AFR | BKF | REF | 11 | TRA | 03 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1996-11-01 |  | 1996-11-01 | 1999-04-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 |  |  | 5395 | 0 | 5395 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs training) | Individual | AFR | BKF | SEV | 11 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-10-01 | 1994-12-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 |  |  | 1885 | 0 | 1885 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening renewal (Phase II) | Individual | AFR | BKF | SEV | 22 | INS | 06 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 1999-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 |  |  | 7241 | 0 | 7241 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | BKF | REF | 24 | PRP | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening - Phase III | Individual | AFR | BKF | SEV | 27 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-07-01 | 2001-12-12 | 55700 | 0 | 55700 | 55700 | 100% | 0 |  |  | 7241 | 0 | 7241 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase IV) | Individual | AFR | BKF | SEV | 33 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-01-03 | 2003-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 |  |  | 7241 | 0 | 7241 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (phase 5) | Individual | AFR | BKF | SEV | 38 | INS | 15 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-04 | 2004-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | BKF | SEV | 44 | INS | 17 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 72410 | 0 | 72410 | 58110 | 80.25% | 14300 | 14300 | 14300 | 0 | 0 | 0 | 0 | 0 | Second payment done in August 05 .The NOO coordinnated awareness activities and the preparation of the report on RMP activities which lead to the submission of the preparation of TPMP in December 2005. TPMP implemetation MoU with the country signed. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Project preparation request for TPMP | Individual | AFR | BKF | PHA | 47 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 2600 | 0 | 0 | 2600 | 1948.05 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Completion of country programme preparation | Individual | LAC | BOL | SEV | 16 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1995-10-01 | 1999-01-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Establishment of the Ozono Governmental Commission (COGO) | Individual | LAC | BOL | SEV | 18 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 1999-12-01 | 91000 | 0 | 91000 | 91000 | 100% | 0 |  |  | 11830 | 0 | 11830 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | BOL | REF | 24 | PRP | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 2001-01-01 | 1999-02-01 |  | 2001-12-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BOL | SEV | 26 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-03 | 60670 | 0 | 60670 | 60670 | 100% | 0 |  |  | 7887.1 | 0 | 7887.1 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | BOL | SEV | 34 | INS | 14 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 |  |  | 7887.1 | 0 | 7887.1 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project | Individual | LAC | BOL | SEV | 40 | INS | 24 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-08-01 | 2005-07-01 | 2006-12-01 |  |  | 100000 | 0 | 100000 | 87380 | 87.38% | 12620 |  | 12620 | 0 | 0 | 0 | 0 |  | Audit Report made minor suggestions in order to improve administrative controls and fund management procedures to be put in place. Two cash advances corresponding to ISP (IV) sent to the country during the 2005 year. Data collection, analysis and reporting to both Secretaries accomplished by NOU. ODS Licensing and imports quota systems in force, both in permanent evaluation to improve its implementation. NOU is in charge of the coordination of each project approved by MFS. NOO attended ODS Officers Network Meetings. Main achievements of public awareness activities are: educational videos distribution through the Education Ministry, awareness Spots produced and broadcasted for a whole month in 4 national TV channels; and production of an educational handbook to teach the future teachers on how to protect the ozone layer. ISP renewal submitted and approved at 47 ExCom Meeting. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | BOL | SEV | 47 | INS | 26 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 78867 | 0 | 78867 | 0 | 0% | 78867 | 0 | 78867 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | BOT | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1994-07-01 |  | 1994-06-01 | 1994-12-01 | 30000 | 10000 | 40000 | 40000 | 100% | 0 |  |  | 3900 | 1300 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Institutional strengthening (establishment of the Ozone Office) | Individual | AFR | BOT | SEV | 13 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1997-07-01 |  | 2003-12-01 | 2003-12-01 | 90200 | 0 | 90200 | 90200 | 100% | 0 |  |  | 11726 | 0 | 11726 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | BOT | SEV | 41 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 78173 | 0 | 78173 | 0 | 0% | 78173 |  | 78173 | 0 | 0 | 0 | 0 |  | NOU organised Customs officers and refrigeration technicians trainings. Country produced awareness materials (posters,calenders, pamphlets) and distributed to business community and schools. NOU celebrated ozone day. NOU conducted awareness workshop on MBr for farmers. Country reported ODS data consumption in time | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | BRU | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-09-25 | 1996-03-01 |  | 1998-09-01 | 1999-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
COM | UNEP | Creation of a Brunei Ozone Office | Individual | ASP | BRU | SEV | 26 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-11 | 2001-12-01 |  | 2004-07-04 |  | 80000 | 0 | 80000 | 72206 | 90.26% | 7794 | 0 | 7794 | 10400 | 0 | 9386.78 | 1013.22 |  | Project completed. | [10 empty] | 1998 | Non Investment
COM | UNEP | Development of RMP | RMP | ASP | BRU | REF | 30 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-11-04 |  | 30000 | 0 | 30000 | 14500 | 48.33% | 15500 | 0 | 15500 | 3900 | 0 | 1885 | 2015 |  | Project completed | [10 empty] | 2000 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | BRU | SEV | 43 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-07-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 |  | 70000 | 0 | 0 | 0 | 0 |  | Draft MOU sent to NOU for review in 2005. Repeated follow up by CAP but no progress on the signing of MOU due to turnover by Government officers in charge of ozone activities. Letter from Regional Director sent to the Government for speeding up the project. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and national technicians training | Individual | ASP | BRU | REF | 44 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2007-05-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 6500 | 0 | 0 | 6500 | 0 | Follow up with the country was made during the two network meetings in 2005 and regular contact. However, the country could not decide who should contract to deliver the training. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | BRU | REF | 44 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 | 2006-12-01 |  |  | 34000 | 0 | 34000 | 10810 | 31.79% | 23190 | 0 | 23190 | 4420 | 0 | 1405.3 | 3014.7 | 0 | Feb 05: Draft MOU sent to Brunei for signature. Dec 05: 12 Refrigerant Identifiers were delivered to the country. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring of the activities included in the RMP | Individual | ASP | BRU | REF | 44 | TAS | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 22000 | 0 | 22000 | 9 | 0.04091% | 21991 | 0 | 21991 | 2860 | 0 | 1.17 | 2858.83 | 0 | Draft MOU sent to NOU for review 17 Feb 05. Repeated follow up by CAP but no progress on the signing of MOU due to turnover by Government. Letter from Regional Director sent to the Government for speeding up the project. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | BZE | SEV | 24 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-02-01 |  | 1999-11-01 | 2000-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 |  |  | 6760 | 0 | 6760 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Creation of the national ozone unit | Individual | LAC | BZE | SEV | 29 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2003-01-01 | 2004-10-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 |  |  | 11505 | 0 | 11505 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
ONG | UNEP | Extension of institutional strengthening project | Individual | LAC | BZE | SEV | 40 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 | 2006-05-01 |  |  | 76700 | 0 | 76700 | 54169 | 70.62% | 22531 | 0 | 22531 | 0 | 0 | 0 | 0 |  | Disbursements released regularly, last cash advance corresponding to ISP (II) sent to the country in September 2005. NOU very active at international level, attended the Green Customs Initiative and ODS Officers Network Meetings. Data collection, analysis and reporting to the various Montreal Protocol agencies and Secretaries accomplished on time by NOU. ODS license system working properly, approximately 6.806 ODP tons of the 12.2 tons allowable for 2005 were imported. The ISP (III) was approved by 46 ExCom and the RMP update by 44 ExCom. RMPU launched in June 2005. Public awareness activities covered different sectors like children, mass media, and decision makers. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | BZE | REF | 41 | PRP | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-04 | 2005-06-01 | 15000 | 0 | 15000 | 13750 | 91.67% | 1250 | 0 | 0 | 1950 | 0 | 1787.5 | 162.5 | 0 | Project financially completed. | USD 1,250 returned to ExCom 49 | [9 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: certification and licensing of refrigeration technicians | Individual | LAC | BZE | REF | 44 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 | 2007-12-01 |  |  | 33682 | 0 | 33682 | 11310 | 33.58% | 22372 | 22372 | 22372 | 4378.6602 | 0 | 1470.3001 | 2908.3601 | 2908 | MOU signed and first disbursement released. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: prevention of illegal trade of CFCs | Individual | LAC | BZE | REF | 44 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 | 2007-12-01 |  |  | 22611 | 0 | 22611 | 7590 | 33.57% | 15021 | 15021 | 15021 | 2939.4299 | 0 | 986.7 | 1952.73 | 1952.73 | MOU signed and first disbursement released. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | BZE | REF | 44 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 | 2007-12-01 |  |  | 27140 | 0 | 27140 | 4600 | 16.95% | 22540 | 9104 | 22540 | 3528.2 | 0 | 598 | 2930.2 | 1184 | MOU signed and first disbursement released. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase III) | Individual | LAC | BZE | SEV | 46 | INS | 15 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 |  | 2007-07-01 | 2007-07-01 |  |  | 76700 | 0 | 76700 | 0 | 0% | 76700 | 0 | 76700 | 0 | 0 | 0 | 0 | 0 | Project approved in July 2005. Explanation on the new UNEP modality for ISP implementation and MOU type were provided by CAP team. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CAF | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-17 | 1995-06-01 |  | 1995-10-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of the National Technical Ozone Group (Ozone Unit) | Individual | AFR | CAF | SEV | 18 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 2000-06-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 |  |  | 5928 | 0 | 5928 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | CAF | SEV | 26 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2004-10-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 |  |  | 3952 | 0 | 3952 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | CAF | REF | 27 | PRP | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2001-05-01 | 2002-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
ONG | UNEP | Extension of institutional strengthening project | Individual | AFR | CAF | SEV | 38 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 | 2006-12-01 |  |  | 39520 | 0 | 39520 | 16680 | 42.21% | 22840 |  | 22840 | 0 | 0 | 0 | 0 |  | NOU CAR coodinated implentation of RMP training actvities with France before the programme was transferred during the 1st quarter 2005 to Ministry of Environment and a new ODS officer was appointed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CAF | SEV | 45 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | Completion of previous phase was delayed due to changes in NOU leading to delay in start of current phase. No disbursement done in 2005 for this phase. | [10 empty] | 2005 | Non Investment
COM | UNEP | Formulation of national phase out strategy | Individual | AFR | CBI | SEV | 35 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2003-08-01 |  | 2004-12-04 |  | 40000 | 0 | 40000 | 35017.22 | 87.54% | 4982.78 | 4372.78 | 4982.78 | 5200 | 0 | 4552.2386 | 647.7614 | 568.4614 | Project completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Establishment of the Ozone Unit | Individual | AFR | CBI | SEV | 36 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 | 2006-12-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 15000 | 15000 | 0 | 0 | 0 | 0 |  | First payment done in June 05. NOO coordinated some awareness activities and the approbation of the legislation. The legislation is validated by stakeholders in November 2005 and recommanded to the cabinet for approval | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | CBI | REF | 44 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 11669.55 | 29.17% | 28330.45 | 27032.45 | 28330.45 | 5200 | 0 | 1517.0415 | 3682.9585 | 1948.05 | First payment for the organisation the phase I has been done in June 05. Equipment ordered in May 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | CBI | REF | 44 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 | 2007-12-01 |  |  | 20000 | 0 | 20000 | 11670 | 58.35% | 8330 | 8230 | 8330 | 2600 | 0 | 1517.1 | 1082.9 | 1069.9 | First payment has been done in June 2005 and monitoring activities are pending on the approbation of the legislation. Regular technical assistance from UNEP is given to the country . | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CBI | REF | 44 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 | 2007-12-01 |  |  | 40000 | 0 | 40000 | 11669.53 | 29.17% | 28330.47 | 27812.47 | 28330.47 | 5200 | 0 | 1517.0389 | 3682.9611 | 1948.05 | First payment done in May 2005 and equipment for the training programme ordered in May 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | CBI | SEV | 44 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | First payment done in June 05. NOO coordinated some awareness activities and the approbation of the legislation. The legislation is validated by stakeholders in November 2005 and recommanded to the cabinet for approval | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CHD | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-05-02 | 1996-03-01 |  | 1998-05-01 | 1999-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
COM | UNEP | Establishment of a National Ozone Unit | Individual | AFR | CHD | SEV | 25 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-22 | 2001-07-01 |  | 2004-12-01 |  | 60000 | 0 | 60000 | 57104 | 95.17% | 2896 | 0 | 0 | 7800 | 0 | 7423.52 | 376.48 | [12 empty] | 1998 | Non Investment
FIN | UNEP | Refrigerant management plan: Training the trainers of refrigeration technicians in good service practices | Individual | AFR | CHD | REF | 29 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-04 |  | 2002-08-01 | 2003-11-01 | 80125 | 0 | 80125 | 80125 | 100% | 0 |  |  | 10416.25 | 0 | 10416.25 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Training programme for customs officers | Individual | AFR | CHD | REF | 29 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-04 |  | 2002-08-01 | 2003-11-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [5 empty] | 2002-10-02 |  |  |  |  | 1999 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | CHD | SEV | 44 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 24015 | 40.02% | 35985 | 35985 | 35985 | 0 | 0 | 0 | 0 | 0 | The NOU has been coordinating with UNDP for the implementation of activities under the RMP update. NOU organised awareness activities including broadcasting of Ozzy ozone Video on National TV and during conferences in schools. The NOU Chad has been facilitating enforcement of ODS regulations in cooperation with customs departpement. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | CHI | FUM | 30 | TAS | 141 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -8217 | 16783 | 16783 | 100% | 0 |  |  | 3250 | -1068.21 | 2181.79 | 0 |  | Project financially completed. | $8217 plus $1068 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: enabling a control and regulatory network | Individual | LAC | CHI | REF | 35 | TAS | 146 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2002-09-01 | 2006-12-01 |  |  | 111400 | 0 | 111400 | 30938.42 | 27.77% | 80461.58 | 80461.72 | 80461.58 | 14482 | 0 | 4021.9946 | 10460.0054 | 10460 | Legislation is still on Parliament as of Dec-05. MOU amended and pending signature. Training activites expected to start during first quarter of 2006. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: end-users and public awareness programme | Individual | LAC | CHI | REF | 35 | TAS | 148 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 | 2006-12-01 |  |  | 172000 | 0 | 172000 | 1993.54 | 1.159% | 170006.46 | 167946 | 170006.46 | 22360 | 0 | 259.1602 | 22100.8398 | 14952.08 | New MOU was required. Draft MOU with country in discussion as of July-05, They disagreed on UNCITRAL clause as well as with 'terrorism' clause. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring, evaluation and reporting of the activities in the RMP | Individual | LAC | CHI | REF | 35 | TAS | 149 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 | 2006-12-01 |  |  | 52000 | 0 | 52000 | 30000 | 57.69% | 22000 | 22000 | 22000 | 6760 | 0 | 3900 | 2860 | 2860 | SSA completed in Mar-05. New SSA will be prepared when there's some progress in other components. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | CKI | REF | 44 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 14000 | 0 | 14000 | 0 | 0% | 14000 | 0 | 14000 | 1820 | 0 | 0 | 1820 |  | Training programme schedules were finalized and planned to conduct in first quarter of 2006. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | CKI | SEV | 44 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-06-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 |  | National Compliance Centre was established in October 2005 under National Environment Service. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | CKI | REF | 44 | TAS | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 8000 | 0 | 8000 | 0 | 0% | 8000 | 0 | 8000 | 1040 | 0 | 0 | 1040 |  | Preliminary works was done in establishing licensing system and the Government hopes to begin National Consultation in early 2006 and to establish the regulations by July 2006. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CMR | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-06-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 |  |  | 3900 | 390 | 4290 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs officers) | Individual | AFR | CMR | SEV | 10 | TRA | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-08-01 | 1994-12-01 | 20200 | 0 | 20200 | 20200 | 100% | 0 |  |  | 2626 | 0 | 2626 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Establishment of the National Ozone Monitoring Commission | Individual | AFR | CMR | SEV | 11 | INS | 03 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-10-01 | 1996-11-01 |  | 1997-10-01 | 1997-06-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 |  |  | 20930 | 0 | 20930 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening renewal (Phase II) | Individual | AFR | CMR | SEV | 22 | INS | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-12-01 | 2000-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 |  |  | 13910 | 0 | 13910 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | AFR | CMR | SEV | 28 | INS | 14 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 |  |  | 13910 | 0 | 13910 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | CMR | FUM | 34 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-07-01 |  | 2003-07-01 | 2004-07-01 | 25000 | -10136 | 14864 | 14864 | 100% | 0 |  |  | 3250 | -1317.68 | 1932.32 | 0 |  | Project financially completed. | $10136 plus $1318 PSC returned ExCom 44 | [9 empty] | 2001 | Non Investment
COM | UNEP | Policy and technical assistance | Individual | AFR | CMR | SEV | 37 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-07-04 |  | 10000 | 0 | 10000 | 8006 | 80.06% | 1994 | 613 | 1994 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | CMR | SEV | 41 | INS | 19 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2004-12-04 | 2005-12-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2003 | Non Investment
COM | UNEP | Extension of institutional strengthening project (second year of phase IV) | Individual | AFR | CMR | SEV | 44 | INS | 22 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2005-12-01 |  | 69766 | 0 | 69766 | 28008.61 | 40.15% | 41757.39 | 41757.39 | 41757.39 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2005. Project was approved for an additional one year following cameroon return to compliance. The NOU was in position to coordinate implementation of RMP activities with UNIDO as IA. NOU also coordinated implementation of halon banking project (GTZ) and MB phase out strategy (UNDP). NOU has been assisting CEMAC secretariat in preparations for enforcement of harmonized regulation. The NOU was involved in organising a regional workshop in 2005 on enforcement of MEAs in Africa region where MP was presented as success story. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase V | Individual | AFR | CMR | SEV | 47 | INS | 23 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 139532 | 0 | 139532 | 0 | 0% | 139532 | 0 | 139532 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | COI | SEV | 19 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1997-11-01 | 1999-01-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 |  |  | 4290 | 0 | 4290 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Establishment of the National Ozone Unit | Individual | AFR | COI | SEV | 23 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 2000-12-01 |  | 2001-03-01 | 2001-12-12 | 27800 | 0 | 27800 | 27800 | 100% | 0 |  |  | 3614 | 0 | 3614 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | COI | REF | 27 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2000-04-01 |  | 2001-09-01 | 2001-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | COI | SEV | 32 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 18533 | 0 | 18533 | 18533 | 100% | 0 |  |  | 2409.29 | 0 | 2409.29 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring of RMP implementation and its impact in the service and end-users sectors | Individual | AFR | COI | REF | 35 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2005-04-01 | 2005-12-01 | 2006-07-01 |  |  | 18000 | 0 | 18000 | 16000 | 88.89% | 2000 | 0 | 2000 | 2340 | 0 | 2080 | 260 |  | First payment done in April 2005. Second payment done in October 2005 after report on RMP activities | [10 empty] | 2001 | Non Investment
COM | UNEP | Implementation of the RMP: assessment of the end-users subsector | Individual | AFR | COI | REF | 35 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-06-01 |  | 30000 | 0 | 30000 | 28023.64 | 93.41% | 1976.36 | 0.39 | 1976 | 3900 | 0 | 3643.0732 | 256.9268 | 0 | Project completed in June 2005. Project financially completed in October 2005 | [10 empty] | 2001 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer and training of refrigeration service technicians | Individual | AFR | COI | REF | 35 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2002-07-01 |  | 2003-12-01 | 2005-12-01 | 51000 | -7093 | 43907 | 43907 | 100% | 0 | 0 | 0 | 6630 | -922.09 | 5707.91 | 0 |  | Project financially completed. | $7093 plus $922 returned ExCom 46 | [9 empty] | 2001 | Non Investment
COM | UNEP | Implementation of the RMP: training of customs officers in identification and control of ODS imports | Individual | AFR | COI | REF | 35 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-07-01 |  | 2003-12-01 |  | 39000 | 0 | 39000 | 25614.37 | 65.68% | 13385.63 | 921.63 | 13385.63 | 5070 | 0 | 3329.8681 | 1740.1319 | 119.86 | Project financially completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | COI | SEV | 39 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 |  | 24093 | 0 | 24093 | 23068 | 95.75% | 1025 |  | 1025 | 0 | 0 | 0 | 0 |  | Project completed in April 2005. During 1st quarter 2005 NOU coordinated data collection for reporting purposes and held meeting with stakeholder to identify needs for activities to achieve final phase-out. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | COI | SEV | 45 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | NOU coordinated preparation of reports and assessment of outputs of RMP projects. NOU organised awareness activities including dissemination of information materal across the country ilands icluding copies of Ozzy ozone vidoe in schools. As a refrigeration expert, the ODS offcier of Comoros was involved in South-south assistance programme organised by CAP team and participated in training activities in other countries. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Project preparation for a TPMP | Individual | AFR | COI | PHA | 47 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 1948.05 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Training programme in good practices in refrigeration | Individual | LAC | COL | REF | 17 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 2003-12-01 | 2005-02-01 | 149100 | -42081.59 | 107018.41 | 107018 | 100% | 0.41 | 0 | 0 | 19383 | -5470.6067 | 13912.34 | 0.0533 |  | Project financially completed. | $42082 plus $5471 returned ExCom 46 |  |  | 1999-12-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 100% | 0 |  |  | 3250 | -1253.07 | 1996.93 | 0 |  | Project financially completed. | $9639 plus $1253 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Training workshop on safety aspects of CFC substitutes | Individual | ASP | CPR | SEV | 18 | TRA | 155 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1996-05-01 |  | 1996-05-01 | 1999-04-01 | 82400 | 0 | 82400 | 82400 | 100% | 0 |  |  | 10712 | 0 | 10712 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Sectoral policy plan for methyl bromide phaseout in China | Individual | ASP | CPR | FUM | 24 | TAS | 238 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-01-01 |  | 1999-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 |  |  | 19500 | 0 | 19500 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Development of policy training strategy and plan for local authorities | Individual | ASP | CPR | SEV | 27 | TAS | 268 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2000-04-01 |  | 2000-10-01 | 2001-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
TRF | UNEP | Evaluation and risk analysis of Montreal Protocol Implementation in China | Individual | ASP | CPR | SEV | 30 | TAS | 346 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project transferred | [11 empty] | Non Investment
FIN | UNEP | Policy training for local authorities (first tranche for 2001) | Individual | ASP | CPR | SEV | 34 | TRA | 377 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-12-01 | 2003-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Awareness raising workshop to support ratification of the Copenhagen Amendment | Individual | ASP | CPR | FUM | 35 | TAS | 381 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-04 |  | 100000 | 0 | 100000 | 46181.5 | 46.18% | 53818.5 | 0 | 53818.5 | 13000 | 0 | 6003.595 | 6996.405 | 0 | Project financially completed in December 2005 | [8 empty] | 2004-06-01 |  | 2001 | Non Investment
COM | UNEP | Techno-economic evaluation of methyl bromide alternatives | Individual | ASP | CPR | FUM | 35 | TAS | 382 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-04 |  | 80000 | 0 | 80000 | 41089 | 51.36% | 38911 | 30722 | 38911 | 10400 | 0 | 5341.57 | 5058.43 | 3994 | Project financially completed in December 2005 | [8 empty] | 2004-06-01 |  | 2001 | Non Investment
FIN | UNEP | Policy training for local authorities (second tranche) | Individual | ASP | CPR | SEV | 37 | TRA | 392 | A | O | I | CFC | 16.5 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-09-01 | 2005-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 |  | Project completed (Second Tranche) in September 2005 and financially completed in July 2005. 19-20/06/05 Training for Environment Supervision Bureau (ESB) system - Skeleton persons working in local ESB more than two years - Xingcheng - 150 participants. September 2005: Launch of on-line training system | [10 empty] | 2002 | Non Investment
ONG | UNEP | Policy training for local authorities (third tranche) | Individual | ASP | CPR | SEV | 43 | TRA | 413 | A | O | I | CFC | 27.7 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2007-12-01 | 2007-12-01 |  |  | 335000 | 0 | 335000 | 257439 | 76.85% | 77561 | 0 | 77561 | 43550 | 0 | 33467.07 | 10082.93 |  | Visit to SEPA to discuss implementation of 3rd tranche of the project in April 2005. Train-the-trainer Customs Workshop 20-22 Sept 2005, Li Jiang, China. 18-20 June 06 Planning meeting with SEPA - fianalisation work programme 2006. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Refrigeration servicing sector CFC phase-out plan (revised 2005 annual implementation programme) | Multi-year | ASP | CPR | REF | 45 | TAS | 426 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-12-01 | 2006-06-01 |  |  | 450000 | 0 | 450000 | 145538 | 32.34% | 304462 |  | 304462 | 58500 | 0 | 18919.94 | 39580.06 |  | March 2005: SEPA organized a study tour to Netherlands, Germany and Sweden for international review of vehicle disposal sector. China collected technical and policy information on the disposal, recycling and management of retired vehicles on CFC recovery. April 2005: 45th ExCom meeting approved the amendment of the agreement reflecting the request of the Government of China to include UNEP as co-operating implementing agency to undertake training and awareness activities. April 2005: SEPA with UNEP assistance conducted a desk study of the vehicle disposal sector by questionnaire. April 2005: Technical assistance expert workshop was held with UNEP assistance to design the training manual and code of good practices. October –December 2005: For Awareness generation, SEPA visited local enterprises and distributed booklets “Love Blue sky, Protect Ozone Layer”. This awareness programme reached out to 20 enterprises in nine provinces & municipalities of China. December 2005: Expert’s meeting was held for the preparation of the training of trainer’s workshop. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | EUR | CRO | SEV | 16 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | EUR | CRO | SEV | 20 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 101200 | 0 | 101200 | 101200 | 100% | 0 |  |  | 13156 | 0 | 13156 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | CRO | SEV | 29 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2001-12-01 |  | 2002-03-01 | 2003-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 |  |  | 8710 | 0 | 8710 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
COM | UNEP | Renewal of institutional strengthening projects (Phase III) | Individual | EUR | CRO | SEV | 36 | INS | 17 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-06-01 | 2004-04-01 |  | 2004-12-04 |  | 87900 | 0 | 87900 | 87900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project | Individual | EUR | CRO | SEV | 41 | INS | 21 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 | 2006-12-01 |  |  | 87707 | 0 | 87707 | 8652 | 9.865% | 79055 |  | 79055 | 0 | 0 | 0 | 0 |  | Although all activities under this phase completed as planned there are pending paymens related to previous commitments. The project will be turned COM after the settlement of the outstanding payments or the estabishment of the relevant obligations. Terminal report and action plan for Phase V submitted to MFS through UNEP. Renewal request was approved at November 2005 ExCom meeting. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | EUR | CRO | SEV | 47 | INS | 28 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-04-01 | 2008-04-01 |  |  | 87707 | 0 | 87707 | 0 | 0% | 87707 | 0 | 87707 | 0 | 0 | 0 | 0 | 0 | MOU has been drafted and being currently cleared by Croatia. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme | Individual | EUR | CYP | SEV | 22 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-05-01 |  | 1997-05-01 | 1997-05-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [11 empty] | Non Investment
COM | UNEP | Preparation of country programme | Individual | AFR | DJI | SEV | 30 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-07-01 |  | 60000 | -34200 | 25800 | 25800 | 100% | 0 |  | 0 | 7800 | -4446 | 3354 | 0 |  | Project completed. | $9000 plus $1170 returned ExCom 37 $25200 plus $3276 returned ExCom 46 | [5 empty] | 2002-07-01 |  |  |  | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training | Individual | AFR | DJI | REF | 37 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 | 2006-12-01 |  |  | 33100 | 0 | 33100 | 21125.64 | 63.82% | 11974.36 | 0 | 11974.36 | 4303 | 0 | 2746.3332 | 1556.6668 | 0 | Phase 1 held on 11-13 October 2004, 20 Customs Officers trained . Second payment for the organization of phase 2 done in January 2005. Phase 2 still ongoing. Slow progress made by the country in the implementation of the RMP despite regular calls and email ftom UNEP | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training in good practices of refrigeration | Individual | AFR | DJI | REF | 37 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-08-01 | 2003-08-01 | 2006-12-01 |  |  | 74200 | 0 | 74200 | 26984 | 36.37% | 47216 | 47216 | 47216 | 9646 | 0 | 3507.92 | 6138.08 | 6138 | Phase I set for July 23-27. 25 technicians have been trained. Second payment for Phase 2 done in August 2005. Report on the second phase pending | [10 empty] | 2002 | Non Investment
ONG | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | DJI | SEV | 37 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-08-01 | 2006-03-01 |  |  | 90000 | 0 | 90000 | 70010 | 77.79% | 19990 |  | 19990 | 0 | 0 | 0 | 0 |  | NOU coordinated implementation of RMP actvities with UNEP and UNDP. Training of customs officers was completed and training of refrigeration technicians underway. NOU also organised distribution of R&R equipment provided by UNDP. NOU is facilitating enforcement of ODS regulations in coperation with customs department. | [10 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: assistance to establish legislation | Individual | AFR | DJI | REF | 37 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2003-08-01 |  | 2004-04-04 |  | 9000 | 0 | 9000 | 0 | 0% | 9000 | 9000 | 9000 | 1170 | 0 | 0 | 1170 | 1170 | Project completed. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | DMI | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-08-01 |  | 1998-09-01 | 1999-07-01 | 40000 | -16000 | 24000 | 24000 | 100% | 0 |  |  | 5200 | -2080 | 3120 | 0 |  | Project financially completed. | $16000 plus $2080 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
ONG | UNEP | Implementation of the refrigerant management plan: Custom training | Individual | LAC | DMI | REF | 26 | TRA | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2003-06-01 | 2000-11-02 | 2006-04-01 |  |  | 15000 | 0 | 15000 | 8000 | 53.33% | 7000 |  | 7000 | 1950 | 0 | 1040 | 910 |  | Draft Legislation completed and submitted for approval. UNEP/ROLAC will proceed with Customs training activities. Five days mixed approach will be adopted in January 2006 to complete activities by first quarter 2006. | [10 empty] | 1998 | Non Investment
ONG | UNEP | Implementation of the refrigerant management plan: Training of trainers in good refrigerant management practices | Individual | LAC | DMI | REF | 26 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-11-02 | 2006-04-05 |  |  | 20000 | 0 | 20000 | 17000 | 85% | 3000 |  | 3000 | 2600 | 0 | 2210 | 390 |  | Training activites completed in August of 2005. Additional 30 technicians trained as of Jan 2006. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | DMI | SEV | 26 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-07-01 | 2001-12-01 |  | 2004-02-01 | 2005-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | Project completed. | [10 empty] | 1998 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | DMI | SEV | 42 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-12-01 |  | 13000 | 0 | 13000 | 5619 | 43.22% | 7381 | 0 | 7381 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. ISP submitted for renewal and approved at the 45th ExCom. Incomplete IS reports submitted in Jan 2005 by NOU. All outstanding IS reports submitted and accepted by UNON in December 2005, resulting in CASH release. Country has sent ODS data reporting to both Secretariats. ODS license system advanced draft is completed and awaiting approval of the Attorney General. NOU assisted in the TPMP preparation. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Preparation of refrigerant management plan | RMP | LAC | DMI | REF | 44 | PRP | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2005-12-01 | 2006-04-05 |  |  | 20000 | 0 | 20000 | 7131 | 35.66% | 12869 | 2000 | 12869 | 2600 | 0 | 927.03 | 1672.97 | 260 | Budget completed MOU submitted to Party for final comments before signing. International and national consultants recruited. Draft project report completed | [10 empty] | 2004 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | LAC | DMI | SEV | 45 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 13000 | 0 | 13000 | 0 | 0% | 13000 | 0 | 13000 | 0 | 0 | 0 | 0 | 0 | Budget and work plan completed. MOU established with country. First disbursement is pending on the exhaustion of funds under the budget approved at 42 ExCom. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | DOM | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1996-03-01 |  | 1995-07-01 | 1995-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of the National Commission for the Ozone (Cogo) | Individual | LAC | DOM | SEV | 17 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1998-10-01 |  | 2000-02-01 | 2001-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 |  |  | 20150 | 0 | 20150 | 0 |  | Project financially completed. |  |  | 1998-10-01 | [7 empty] | 1995 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | LAC | DOM | REF | 25 | TRA | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-03 |  | 2003-06-01 | 2005-01-01 | 38000 | -10000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 4940 | -1300 | 3640 | 0 | 0 | Project financially completed. | $25000 plus $3250 PSC returned ExCom 46 | [9 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | LAC | DOM | REF | 25 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-02-02 |  | 2001-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  |  | 5850 | 0 | 5850 | 0 |  | Project financially completed. |  |  |  |  | 2000-12-01 | [5 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | DOM | SEV | 29 | INS | 23 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 103000 | 0 | 103000 | 103000 | 100% | 0 |  |  | 13390 | 0 | 13390 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | DOM | FUM | 30 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -9183 | 15817 | 15817 | 100% | 0 |  |  | 3250 | -1194 | 2056 | 0 |  | Project financially completed. | $9183 plus $1194 PSC returned ExCom 43 | [9 empty] | 2000 | Non Investment
ONG | UNEP | Policy and technical assistance | Individual | LAC | DOM | SEV | 37 | TAS | 31 | A | O | I | CFC | 0.8 | 0 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 | 2006-06-01 |  |  | 10000 | 0 | 10000 | 7500 | 75% | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 |  | Activities completed. Awaiting financial and progress reports from country to allow for closure. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | DOM | SEV | 39 | INS | 34 | N | T | I | CFC | 17.1 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 | 2006-05-01 |  |  | 134333 | 0 | 134333 | 100600 | 74.89% | 33733 |  | 33733 | 0 | 0 | 0 | 0 |  | Disbursements released regularly, last cash advance corresponding to the ISP (III) received in December 2005. NOU very active at international level attended the Green Customs Initiative and ODS Officers Network Meetings. ODS Data reporting was submitted to Ozone Secretariat and MFS. Important decrease on the country imports of ozone depleting substance has taken place, thanks to the links created among NOU, Customs Directorate and Association of refrigeration technicians. The NOU priorities have been training of technicians on refrigeration providing certifications, a national campaign recommending the employment of certified technicians on good practices of refrigeration and promoting alternative ODS was carried out. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | DRC | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  |  | 5590 | 0 | 5590 | 0 |  | Project financially completed. |  |  |  | 1999-03-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Creation of an Ozone Office | Individual | AFR | DRC | SEV | 27 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2003-06-01 | 2000-04-01 |  | 2000-12-01 | 2004-04-01 | 32270 | 0 | 32270 | 32270 | 100% | 0 |  | 0 | 4195.1 | 0 | 4195.1 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
COM | UNEP | Assistance in developing the RMP project proposal | Individual | AFR | DRC | REF | 32 | TAS | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2002-01-01 |  | 2003-12-01 |  | 60000 | 0 | 60000 | 35195 | 58.66% | 24805 | 0 | 24805 | 7800 | 0 | 4575.35 | 3224.65 | 1666.6 | Project completed. | [7 empty] | 2003-12-01 |  |  | 2000 | Non Investment
FIN | UNEP | Institutional strengthening project | Individual | AFR | DRC | SEV | 32 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-09-01 | 2005-12-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 |  | 0 | 8390.2 | 0 | 8390.2 | 0 |  | Project completed in September 2005. NOU is coordinating the implementation of RMP activities with UNEP and UNDP. Additional training of customs officers was organised as well as phase one training for efrigeration technicians. Awareness activities including celebration of Ozone Day and awareness campains across the country. More Lectures were held for students in campuses and articles were published in local media. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for technicians in the refrigeration sector | Individual | AFR | DRC | REF | 41 | TRA | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-10-01 | 2006-03-01 |  |  | 115000 | 0 | 115000 | 39077 | 33.98% | 75923 | 75000 | 75923 | 14950 | 0 | 5080.01 | 9869.99 | 1948.05 | Phase I for the training of trainers done in september 2005 and 25 participants had been trained as trainers. Phase 2 started in November 2005 and still ongoing, so far 25 others technicians have been trained by trainers.Others training are scheduled upcountry. The country is progressing well | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | DRC | REF | 41 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 20045 | 50.11% | 19955 | 19955 | 19955 | 5200 | 0 | 2605.85 | 2594.15 | 1948.05 | Second payment done in November after report on RMP activities. The NOO coordinated the organisation of the phases 1 training of technicians and customs officers. He facilitated the organisation of the second phases and provided a report on the implementation of the RMP implementation . the preparation of DRC TPMP has been submitted. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | DRC | REF | 41 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 | 2006-11-01 |  |  | 109000 | 0 | 109000 | 33594 | 30.82% | 75406 | 75000 | 75406 | 14170 | 0 | 4367.22 | 9802.78 | 1948.05 | Phase 1 done in 12-14 April 2005 and 45 trainers had been trained as trainers. Second phase training started in November 2005 and so far 62 customs officers have been trained. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | DRC | SEV | 46 | INS | 22 | N | T | I | CFC | 5.2 | 0 | 0 | 0 | 2005-07-01 |  | 2007-07-01 | 2007-07-01 |  |  | 64540 | 0 | 64540 | 0 | 0% | 64540 | 56698 | 64540 | 0 | 0 | 0 | 0 | 0 | NOU is coordinating the implementation of RMP activities with UNEP and UNDP. Additional training of customs officers was organised as well as phase one training for efrigeration technicians. Awareness activities including celebration of Ozone Day and awareness campains across the country. More Lectures were held for students in campuses and articles were published in local media. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programe preparation | Individual | ASP | DRK | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 1996-10-01 | 1997-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Establishment of a National Ozone Cell | Individual | ASP | DRK | SEV | 21 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 2000-02-01 |  | 2000-12-01 | 2003-06-01 | 142560 | 0 | 142560 | 142560 | 100% | 0 |  |  | 18532.8 | 0 | 18532.8 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | ASP | DRK | SEV | 32 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-08-01 | 2003-01-01 |  | 2003-10-01 | 2003-12-01 | 95040 | 0 | 95040 | 95040 | 100% | 0 |  |  | 12355.2 | 0 | 12355.2 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Development of a refrigerant management plan | RMP | ASP | DRK | REF | 35 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2002-08-01 |  | 2003-06-01 | 2005-05-01 | 60000 | -17650 | 42350 | 42349.84 | 100% | 0.16 | 0 | 0 | 7800 | -2294.5 | 5505.4792 | 0.0208 |  | Project financially completed in May 2005 | $17650 plus $2295 PSC returned ExCom 46 | [9 empty] | 2001 | Non Investment
FIN | UNEP | Preparation of country programme update | Individual | ASP | DRK | SEV | 36 | CPG | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2003-04-01 |  | 2003-10-01 | 2005-05-01 | 30000 | -684 | 29316 | 29315.61 | 100% | 0.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed in May 2005 | $684 returned ExCom 46 | [9 empty] | 2002 | Non Investment
COM | UNEP | Monitoring the activities in the refrigeration servicing subsector | Individual | ASP | DRK | REF | 40 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 |  | 10000 | 0 | 10000 | 5000 | 50% | 5000 | 0 | 5000 | 1300 | 0 | 650 | 650 | 0 | Project financially completed in November 2005 | [10 empty] | 2003 | Non Investment
COM | UNEP | Training of refrigeration service technicians in good servicing practices | Individual | ASP | DRK | REF | 40 | TRA | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 |  | 70000 | 0 | 70000 | 64762.03 | 92.52% | 5237.97 | 0 | 5237.97 | 9100 | 0 | 8419.0639 | 680.9361 | 0 | Project financially completed in november 2005 | [10 empty] | 2003 | Non Investment
COM | UNEP | Assistance for the development of a licensing system and training of customs officers | Individual | ASP | DRK | REF | 40 | TRA | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-06-01 | 2006-07-01 |  | 2005-08-01 |  | 50000 | 0 | 50000 | 44514.16 | 89.03% | 5485.84 | 0 | 5485.84 | 6500 | 0 | 5786.8408 | 713.1592 | 0 | Project completed in August 2005. Project financially completed in November 2005. Mar 05: Evaluation report of RMP activities was submitted. | [10 empty] | 2003 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 2 | Individual | ASP | DRK | SEV | 41 | INS | 31 | N | T | I | CFC | 10.2 | 10.2 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 |  | 123552 | 0 | 123552 | 94105 | 76.17% | 29447 |  | 29447 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. NOU provided public information for ozone related scientific research results from the foreign countries and typical pictures of adverse impacts of ozone layer depletion and these materials were used in TV products for ozone public awareness in June and September 2005. Training programme of customs officers was completed in August 2005. The NPP was submitted and approved in the 47th ExCom meeting in November 2005. | [10 empty] | 2003 | Non Investment
COM | UNEP | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2005-11-01 |  | 25000 | 0 | 25000 | 21895.61 | 87.58% | 3104.39 | 0 | 3104.39 | 3250 | 0 | 2846.4293 | 403.5707 | 0 | Project completed in November 2005. The MOU was signed as per agreement with the Government of DPR Korea and funds were obligated. NPP was submitted for consideration to 47th ExCom. 47th ExCom meeting approved the NPP. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the NPP: regulations, training programme and monitoring (first tranche) | Multi-year | ASP | DRK | PHA | 47 | TAS | 39 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 234600 | 0 | 234600 | 0 | 0% | 234600 | 0 | 234600 | 30498 | 0 | 0 | 30498 | 0 | This project was approved in the 47th ExCom meeting in November 2005.signed MOUs received by the countries | [10 empty] | 2005 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | DRK | SEV | 47 | INS | 41 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 123552 | 0 | 123552 | 0 | 0% | 123552 | 0 | 123552 | 0 | 0 | 0 | 0 | 0 | Project newly approved in the 47th ExCom meeting in November 2005. The budget and workplan was agreed with country and initial disbursement was released. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | ELS | SEV | 16 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-06-01 |  | 1997-03-01 | 1999-01-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 |  |  | 5200 | -650 | 4550 | 0 |  | Project financially completed. | $5000 plus $650 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Area of Policies for the Protection of the Ozone Layer (institutional strengthening) | Individual | LAC | ELS | SEV | 22 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 2000-05-01 |  | 2001-06-01 | 2001-12-01 | 66900 | 0 | 66900 | 66900 | 100% | 0 |  |  | 8697 | 0 | 8697 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | LAC | ELS | REF | 25 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 2000-02-02 |  | 2001-12-01 | 2003-07-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 |  |  | 5070 | 0 | 5070 | 0 |  | Project financially completed. |  |  |  |  | 2000-12-01 | [5 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | LAC | ELS | REF | 25 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-03 |  | 2004-03-01 | 2005-02-01 | 38000 | -14300 | 23700 | 23700 | 100% | 0 |  | 0 | 4940 | -1859 | 3081 | 0 |  | Project financially completed. | $14300 plus 1859 returned ExCom 46 | [9 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | ELS | SEV | 32 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-03-01 | 2004-05-01 | 44600 | 0 | 44600 | 44600 | 100% | 0 |  |  | 5798 | 0 | 5798 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Renewal of institutional strengthening project | Individual | LAC | ELS | SEV | 38 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 |  | 57980 | 0 | 57980 | 49586 | 85.52% | 8394 |  | 8394 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. Disbursements were stopped until audit report was received. AR indicated that control problems or improper fund management were not detected. Last cash advance corresponding to ISP (III) sent to the country in October 2005. NOU attended ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. ODS license system working properly. Public awareness activities focused to school children. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | ELS | SEV | 44 | INS | 17 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 | 2007-07-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | Explanation on the new UNEP modality for ISP implementation and MOU type were provided by CAP team. Signature of MOU and first disbursement done in December 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | ERI | SEV | 47 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
ONG | UNEP | Country programme/RMP project preparation | RMP | AFR | ERI | SEV | 47 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | Project newly approved initial planning started | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ETH | SEV | 16 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-09-25 | 1996-06-01 |  | 1996-12-01 | 1996-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Establishment of national ozone cell for the implementation of Montreal Protocol in Ethiopia | Individual | AFR | ETH | SEV | 20 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-01-01 | 1999-11-01 | 60500 | 0 | 60500 | 60500 | 100% | 0 |  |  | 7865 | 0 | 7865 | 0 |  | Project financially completed. |  |  | 2000-03-01 | [7 empty] | 1996 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | ETH | SEV | 29 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 40300 | 0 | 40300 | 40300 | 100% | 0 |  |  | 5239 | 0 | 5239 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | ETH | FUM | 30 | TAS | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -7326 | 17674 | 17674 | 100% | 0 |  |  | 3250 | -952.38 | 2297.62 | 0 |  | Project financially completed. | $7326 plus $952 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
COM | UNEP | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 30 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-11-01 | 2003-06-01 |  | 2003-06-01 |  | 82735 | -24380 | 58355 | 58355 | 100% | 0 | 0 | 0 | 10755 | -3169.2379 | 7585.7621 | 0 |  | Project financially completed. | $24380 plus $3169 PSC returned ExCom 46 | [9 empty] | 2000 | Non Investment
ONG | UNEP | Extension of institutional strengthening project for a one year period (phase 3) | Individual | AFR | ETH | SEV | 39 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2004-04-01 | 2006-12-05 |  |  | 26216 | 0 | 26216 | 18246 | 69.6% | 7970 |  | 7970 | 0 | 0 | 0 | 0 |  | Implementation of Action Plan commenced | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | ETH | SEV | 41 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 26216 | 0 | 26216 | 0 | 0% | 26216 |  | 26216 | 0 | 0 | 0 | 0 |  | Turnover of NOU necessitates training and enhanced guidance of new NOU | [10 empty] | 2003 | Non Investment
COM | UNEP | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and the Slovak Republic) | Individual | EUR | EUR | SEV | 39 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 |  | 53666 | 0 | 53666 | 53666 | 100% | 0 | 0 | 0 | 6976.58 | 0 | 6976.58 | 0 | 0 | Project completed in February 2005. The Sub-Regional Workshop on RMP Implementation in the Balkans was held from 8 to 10 February 2005 in Ohrid, FYR Macedonia. The objective of the Workshop was therefore to facilitate transfer of knowledge and experience in RMP to Albania, Bosnia and Herzegovina and Serbia and Montenegro from other countries of the region in more advanced stages of RMP implementation. Implementation of the recommendations of the workshop is underway | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | FIJ | SEV | 04 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -2165 | 22835 | 22835 | 100% | 0 |  |  | 3250 | -281.45 | 2968.55 | 0 |  | Project financially completed. | $2165 plus $281 PSC returned ExCom 41 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | FIJ | SEV | 12 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1997-03-01 |  | 2000-07-01 | 2001-12-01 | 65890 | 0 | 65890 | 65890 | 100% | 0 |  |  | 8565.7 | 0 | 8565.7 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | FIJ | REF | 21 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1999-11-01 | 2002-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. |  |  |  | 1999-05-01 | [6 empty] | 1997 | Non Investment
COM | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | FIJ | SEV | 29 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2001-12-01 |  | 2002-05-01 |  | 43930 | 0 | 43930 | 36087 | 82.15% | 7843 | 7843 | 7843 | 5711 | 0 | 4691.3921 | 1019.6079 |  | Project completed. Financial completion can be considered only after all funds that were provided as cash advances be reported by the country as expenditures. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Train the trainer programme for refrigeration service technicians | Individual | ASP | FIJ | REF | 29 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-02 |  | 2003-01-01 | 2004-10-01 | 70500 | -24500 | 46000 | 46000 | 100% | 0 |  | 0 | 9165 | -3185 | 5980 | 0 |  | Project financially completed. | $24500 plus $3185 returned to ExCom 46 |  |  |  |  | 2002-12-02 |  |  |  |  | 1999 | Non Investment
COM | UNEP | Refrigerant management plan: Training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | FIJ | REF | 29 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-02 |  | 2004-07-01 |  | 42500 | 0 | 42500 | 24500 | 57.65% | 18000 | 18000 | 18000 | 5525 | 0 | 3185 | 2340 |  | Project financially completed. | [5 empty] | 2002-12-02 |  |  |  |  | 1999 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | ASP | FIJ | SEV | 37 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2004-08-01 |  | 2004-08-01 |  | 57000 | 0 | 57000 | 0 | 0% | 57000 | 0 | 57000 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | FIJ | SEV | 44 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2005. Regional Network Coordinator had a mission in June 2005 for discussion with relevant stakeholders in preparing the TPMP proposal. The TPMP was submitted and approved in the 47th ExCom meeting in November 2005. Methyl Bromide phase-out was submitted and approved in the 47th ExCom meeting in November 2005. | [10 empty] | 2004 | Non Investment
COM | UNEP | Development of a total ODS phase out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-11-01 |  | 15000 | 0 | 15000 | 14917 | 99.45% | 83 | 0 | 0 | 1950 | 0 | 1939.21 | 10.79 | 0 | Project completed in November 2005. MOU was signed as agreement with the Government of Fiji for the Terminal Phase out Plan. Funds was obligated to the countries. TPMP was submitted to 47th ExCom. TPMP was approved in the 47th ExCom meeting in November 2005. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-03-01 |  |  | 65000 | 0 | 65000 | 0 | 0% | 65000 | 0 | 65000 | 8450 | 0 | 0 | 8450 | 0 | This project was approved in the 47th ExCom meeting in November 2005. Initial planning of activities was discussed in Decemeber 2005. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV- year 2) | Individual | ASP | FIJ | SEV | 47 | INS | 14 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Project newly approved in the 47th ExCom meeting in November 2005. MOU prepared to obligate the funds to the country. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the TPMP (non-investment component) | Individual | ASP | FIJ | PHA | 47 | TAS | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 10400 | 0 | 0 | 10400 | 0 | TPMP in Fiji was approved in the 47th ExCom meeting. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | FSM | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 | 2006-06-01 |  |  | 34000 | 0 | 34000 | 20400 | 60% | 13600 | 0 | 13600 | 0 | 0 | 0 | 0 |  | National Compliance Centre was established under Department of Economic Affairs. Draft regulations prepared and being reviewed by the Attorney General’s office. The Government aims to complete the regulations in March 2006. A total of 24 Refrigeration technicians were trained in the country. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GAB | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-29 | 1995-12-01 |  | 1997-05-01 | 1997-06-01 | 10000 | 33000 | 43000 | 43000 | 100% | 0 |  |  | 1300 | 4290 | 5590 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Creation of a National Ozone Technical Group | Individual | AFR | GAB | SEV | 22 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2001-12-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 |  |  | 5928 | 0 | 5928 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | AFR | GAB | REF | 26 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-09-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  |  | 5850 | 0 | 5850 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | AFR | GAB | REF | 26 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2003-12-01 | 2005-01-01 | 31000 | -10000 | 21000 | 21000 | 100% | 0 |  | 0 | 4030 | -1300 | 2730 | 0 |  | Project financially completed. | $10,000 plus $1300 returned ExCom 46 | [9 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | GAB | SEV | 32 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-03 | 30400 | 0 | 30400 | 30400 | 100% | 0 |  |  | 3952 | 0 | 3952 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | AFR | GAB | SEV | 37 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2005-02-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme ( phase II) | Individual | AFR | GAB | REF | 41 | TRA | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2004-12-01 | 2006-12-01 |  |  | 50000 | 0 | 50000 | 48014.53 | 96.03% | 1985.47 | 1985.47 | 1985.47 | 6500 | 0 | 6241.8889 | 258.1111 | 258.1111 | Phase 1 held in May 05 and 20 Customs officers had been trained. Second payment done in May 05.Report on the Phase 2 still pending . Slow progress in the phase 2 implementation despite several recall from UNEP. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | GAB | REF | 41 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-07-01 | 2006-12-01 |  |  | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Phase 1 held in May 2005 and 25 technicians trained. Second payment done in May 05, Report on the Phase 2 still pending .low progress in the phase 2 implementation despite several recall from UNEP. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | GAB | SEV | 44 | INS | 16 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 48016 | 80.03% | 11984 | 11984 | 11984 | 0 | 0 | 0 | 0 | 0 | The NOU coodinated the implementation of activities under RMP update. MOU was signed for training of Customs officers and refrigeration technicians. Additional equipments(identifiers) acquired for customs officers. NOU was involved in preparation of CEMAC ministerial meeting for harmonisation of ODS regulation. Awareness actvities were done throughout the year (mostly on the ocasion of world envirnment day and ozone day) targeting the public through the media and decison makers through presentations for parlementarians. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GAM | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-06-01 |  | 1995-10-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | GAM | SEV | 19 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-09-01 | 2000-09-01 | 42200 | 0 | 42200 | 42200 | 100% | 0 |  |  | 5486 | 0 | 5486 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Training of customs officers | Individual | AFR | GAM | SEV | 19 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  | 2002-10-01 | 2003-10-01 | 9500 | 0 | 9500 | 9500 | 100% | 0 |  |  | 1235 | 0 | 1235 | 0 |  | Project financially completed. |  |  | 1997-12-01 | [7 empty] | 1996 | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | AFR | GAM | REF | 23 | PRP | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Refrigerant management plan: Policy development and related information dissemination | Individual | AFR | GAM | REF | 29 | TAS | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2000-12-02 |  | 2002-10-01 | 2003-10-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 |  |  | 2860 | 0 | 2860 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Training programme for technicians in good refrigeration practices | Individual | AFR | GAM | REF | 29 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-06-02 |  | 2002-10-01 | 2003-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | GAM | SEV | 30 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  |  | 3640 | 0 | 3640 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | GAM | SEV | 41 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 | 2006-12-01 |  |  | 36573 | 0 | 36573 | 13735 | 37.56% | 22838 |  | 22838 | 0 | 0 | 0 | 0 |  | A new Ozone Officer and an assistant were appointed and trained. NOU conducted training of refrigeration technicians and successfully trained fifty Custom Officers on ODS regulation, the Licensing system and use of identifiers. NOU submitted all progress and expenditure reports. The country celebrated National Ozone Day with series of events. The NOU conducted awareness programmes which included the printing of posters, brochures and T-shirts, TV and Radio Programmes, and essay and poster competitions for school children. | [10 empty] | 2003 | Non Investment
COM | UNEP | Establishment of ozone unit | Individual | AFR | GBS | SEV | 39 | INS | 01 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2004-04-01 |  | 2004-07-01 |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2003 | Non Investment
COM | UNEP | Formulation of the country programme/RMP | RMP | AFR | GBS | SEV | 39 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-07-01 |  | 60000 | 0 | 60000 | 27173.49 | 45.29% | 32826.51 | 0 | 32826.51 | 7800 | 0 | 3532.5537 | 4267.4463 | 0 | Project completed. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Establishment of the Ozone Unit (institutional strengthening project) | Individual | AFR | GBS | SEV | 43 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-07-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 |  | Despite political tension in the country, NOU facilitated implementation of CP/RMP activities mainly training of Customs officers and preparation of national training manuel for refrigeration technicians. NOU also carried on awareness raising workshops for journalist and conferences in secondary schools. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring of the activities in the RMP | Individual | AFR | GBS | REF | 43 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2007-07-01 | 2006-10-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 20000 | 2600 | 0 | 0 | 2600 | 1948.05 | The MoU with the country signed in July 2005. First payment done in July 05. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training for customs officials, police, coast guards, border guards and commercial inspectors | Individual | AFR | GBS | REF | 43 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2006-07-01 | 2006-12-01 |  |  | 70000 | 0 | 70000 | 54023.61 | 77.18% | 15976.39 | 14982.39 | 15976.39 | 9100 | 0 | 7023.0693 | 2076.9307 | 1948.05 | Second payment for phase 2 done in January 05 and activities will start with a refresher training set in January 2006. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training for refrigeration technicians | Individual | AFR | GBS | REF | 43 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 69360 | 70000 | 9100 | 0 | 0 | 9100 | 1948.05 | Equipment sent to the country in July 2005 and Phase 1 training held on 23-27 January 2006. 27 technicians trained as trainers. All the conditions are met for a quick coompletion of that programme. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | EUR | GEO | SEV | 23 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1997-11-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [11 empty] | Non Investment
COM | UNEP | Implementation of the refrigerant management plan: Training in monitoring and controlling of ODS | Individual | EUR | GEO | REF | 23 | TRA | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-01-01 | 1998-02-01 |  | 2005-06-01 |  | 35000 | 0 | 35000 | 35000 | 100% | 0 |  | 0 | 4550 | 0 | 4550 | 0 |  | Project completed in June 2002. Last training workshops have been delivered during 2005. Final payment under this component was done on 17 Nov 2005. In total, 155 officers have been trained in addition to 30 officers trained under Phase 1. 7 workshops have been delivered under this project. 10 ODS identifiers have been procured and distributed to Customs posts. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | GEO | SEV | 23 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 2000-12-01 |  | 2001-05-01 | 2001-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
COM | UNEP | Implementation of the refrigerant management plan: Training of trainers in the refrigeration servicing sector | Individual | EUR | GEO | REF | 23 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-11-01 | 1998-11-02 |  | 2001-11-01 |  | 50000 | -9800 | 40200 | 40200 | 100% | 0 |  | 0 | 6500 | -1274 | 5226 | 0 |  | Project completed | $9800 plus $1274 PSC returned to ExCom 46 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | GEO | SEV | 32 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-08-01 | 2003-01-01 |  | 2003-02-01 | 2003-12-01 | 46700 | 0 | 46700 | 46700 | 100% | 0 |  |  | 6071 | 0 | 6071 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Implementation of the RMP: training programme in the refrigeration sector (phase III) | Individual | EUR | GEO | REF | 35 | TRA | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2003-01-01 |  | 2005-11-01 |  | 20000 | 0 | 20000 | 17587.94 | 87.94% | 2412.06 | 2412 | 2412.06 | 2600 | 0 | 2286.4322 | 313.5678 | 313.56 | Completed in November 2005. First training under this Phase 3 took place in Tbilisi on 11-13 April 2005. 14 trainers participated in the workshop. Subsequently 10 workshops were delivered in 4 main cities of Georgia. In total 188 technicians have been trained. Remaining training activities under this Phase 3 have been delivered in full following the implementation schedule set by the NOU. Final report (PCR) is being prepared. | [10 empty] | 2001 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | GEO | SEV | 39 | INS | 14 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2004-12-01 |  | 60667 | 0 | 60667 | 55143 | 90.89% | 5524 |  | 5524 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project: phase IV | Individual | EUR | GEO | SEV | 45 | INS | 18 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 | 2007-04-01 |  |  | 60667 | 0 | 60667 | 24267 | 40% | 36400 | 36400 | 36400 | 0 | 0 | 0 | 0 | 0 | Two payments done under this phase. NOU has completed 2 training projects during 2005 (Refrigeration and Customs training). NOU is active within the Europe/central Asia network providing support to Armenia in organisation of Refrigeration training delivery. Currently NOU initiated formulation activities for their TPMPO (UNDP/Sweden). | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GHA | SEV | 04 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
FIN | UNEP | Implementation of train the trainer programme and national demonstration programme | Individual | AFR | GHA | REF | 10 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 1995-12-01 | 1999-04-01 | 99000 | 0 | 99000 | 99000 | 100% | 0 |  |  | 12870 | 0 | 12870 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
COM | UNEP | Implementation of the RMP: Customs training programme | Individual | AFR | GHA | REF | 32 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2003-01-01 |  | 81000 | -18194 | 62806 | 62806.45 | 100% | -0.45 | 0 | -0.45 | 10530 | -2365.22 | 8164.8385 | 0 |  | Project completed. | $18194 plus $2365 returned ExCom 46 |  |  |  |  | 2003-06-03 |  |  |  |  | 2000 | Non Investment
FIN | UNEP | Regional workshop for Arabic speaking countries | Individual | GLO | GLO | SEV | 04 | TRA | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-12-01 |  | 1991-12-01 | 1992-12-01 | 246000 | -104000 | 142000 | 142000 | 100% | 0 |  |  | 31980 | -13520 | 18460 | 0 |  | Project financially completed. | $104000 plus $13520 PSC returned ExCom 41 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Information exchange and technology transfer (1991-1992) | Individual | GLO | GLO | SEV | 04 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-12-01 |  | 1993-06-01 | 1993-12-01 | 526000 | 0 | 526000 | 526000 | 100% | 0 |  |  | 68380 | 0 | 68380 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
FIN | UNEP | Advisory group meeting (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-03-01 | 1992-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
FIN | UNEP | OzonAction Information Clearing-house (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 430000 | 0 | 430000 | 430000 | 100% | 0 |  |  | 55900 | 0 | 55900 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Preparation of technical documents and newsletter | Individual | GLO | GLO | SEV | 06 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 320000 | 0 | 320000 | 320000 | 100% | 0 |  |  | 41600 | 0 | 41600 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Support to training activities by UNEP | Individual | GLO | GLO | SEV | 06 | TRA | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1994-03-01 | 1994-12-01 | 365000 | 0 | 365000 | 365000 | 100% | 0 |  |  | 47450 | 0 | 47450 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Advisory group meeting (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-02-01 |  | 1993-03-01 | 1993-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 |  |  | 4550 | 0 | 4550 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Travel (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Preparation of training material for aerosol sector | Individual | GLO | GLO | ARS | 09 | TAS | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Support to networking activities | Individual | GLO | GLO | SEV | 09 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1993-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Aerosol training workshop | Individual | GLO | GLO | ARS | 09 | TRA | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  |  | 11700 | 0 | 11700 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Support to other national training activities | Individual | GLO | GLO | SEV | 09 | TRA | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Development of a training strategy | Individual | GLO | GLO | SEV | 09 | TRA | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | International halon bank clearing-house function | Individual | GLO | GLO | HAL | 09 | TAS | 37 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-05-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Travel (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 39 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Advisory group meeting (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 |  |  | 14300 | 0 | 14300 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Preparation of training material for refrigeration sector | Individual | GLO | GLO | REF | 09 | TAS | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 |  |  | 20800 | 0 | 20800 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Information Exchange Clearing-house System (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-06-01 | 1996-07-01 | 705000 | 0 | 705000 | 705000 | 100% | 0 |  |  | 91650 | 0 | 91650 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 10 | TRA | 45 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 |  |  | 5642 | 0 | 5642 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Updating OAIC diskette and on-line system (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 47 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-21 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Outreach at conferences and workshops (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 48 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-16 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Information dissemination (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 49 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-20 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 380000 | 0 | 380000 | 380000 | 100% | 0 |  |  | 49400 | 0 | 49400 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Sectoral data collection (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 50 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1997-03-01 | 1999-02-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 |  |  | 27950 | 0 | 27950 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Quality review technology catalogs | Individual | GLO | GLO | SEV | 12 | TAS | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-04-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Information papers and fact sheets for evaluation of technical options to replace ODS | Individual | GLO | GLO | SEV | 12 | TAS | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1999-12-01 | 2000-01-01 | 60000 | -3500 | 56500 | 56500 | 100% | 0 |  |  | 7800 | -455 | 7345 | 0 |  | Project financially completed. | $3500 plus $455 PSC returned ExCom 33 |  |  | 1998-12-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Translation of the "Protecting the Ozone Layer" sectoral technical brochures | Individual | GLO | GLO | SEV | 12 | TAS | 54 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-09-01 | 1999-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Halon bank management information collection and dissemination (1994) | Individual | GLO | GLO | HAL | 12 | TAS | 55 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Halon bank management case study logbook | Individual | GLO | GLO | HAL | 12 | TAS | 56 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1998-07-01 | 1995-03-01 |  | 2001-10-01 | 2001-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. |  |  |  | 1999-03-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Translate the halon management: banking for the future information kit | Individual | GLO | GLO | HAL | 12 | TAS | 57 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1996-03-01 | 1999-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Informal Advisory Group meeting (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 58 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-20 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Ad hoc Group meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 59 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Meeting of the consultants (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-04 | 1995-03-01 |  | 1995-07-01 | 1995-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Travel (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Query-response service (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 67 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | OzonAction newsletter and special supplements (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 68 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 |  |  | 19500 | 0 | 19500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Support to national training activities (1994) | Individual | GLO | GLO | SEV | 13 | TRA | 70 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1996-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Update the OAIC diskette version (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 72 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Translation of "Training Manual on Good Practices in Refrigeration" and "Training Manual on Chillers and Refrigerant Management" into Chinese, French and Spanish | Individual | GLO | GLO | REF | 16 | TRA | 73 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-25 | 1995-09-01 |  | 1997-12-01 | 1999-04-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 |  |  | 34320 | 0 | 34320 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Information papers and fact sheets to assist evaluation of technical options to replace ODS (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 74 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Develop sector specific videos | Individual | GLO | GLO | SEV | 16 | TAS | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-05-31 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  |  | 11700 | 0 | 11700 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Update Technology Sourcebooks and quality review updated material | Individual | GLO | GLO | SEV | 16 | TAS | 76 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 |  |  | 11700 | 0 | 11700 | 0 |  | Project financially completed. |  |  |  | 1999-07-01 |  |  | 2002-04-01 |  |  |  | 1995 | Non Investment
FIN | UNEP | Disseminate information (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 |  |  | 26000 | 0 | 26000 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 78 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 |  |  | 31850 | 0 | 31850 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Provide direct query-response service (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 79 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-20 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 |  |  | 4550 | 0 | 4550 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 80 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-12 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Halon bank management query response, information collection and dissemination (1995) | Individual | GLO | GLO | HAL | 16 | TAS | 81 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-20 | 1995-07-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 |  |  | 4550 | 0 | 4550 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Collect sectoral data from worldwide sources (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 82 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-08-28 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 |  |  | 23400 | 0 | 23400 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Informal advisory group meeting (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 83 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Meeting of halon bank managers | Individual | GLO | GLO | HAL | 16 | TAS | 84 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-21 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Development of a "self-help" guide for small halon-consuming countries | Individual | GLO | GLO | HAL | 16 | TAS | 85 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-08-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. |  |  |  | 1999-03-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Dissemination of the existing halon banking awareness flyer | Individual | GLO | GLO | HAL | 16 | TAS | 86 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-09-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Completion of "Recommendations for a Code of Good Practice in Refrigeration" for Article 5 countries | Individual | GLO | GLO | REF | 16 | TAS | 87 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1995-09-01 |  | 1998-07-01 | 1999-04-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 |  |  | 4940 | 0 | 4940 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Ad hoc group meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 88 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-03 | 1996-03-01 |  | 1997-06-01 | 1999-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Travel (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 89 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-09-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Produce sector-specific video for aerosol sector | Individual | GLO | GLO | ARS | 19 | TAS | 91 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1996-12-01 |  | 1999-12-01 | 2000-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. |  |  |  | 1999-03-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Produce a video on methyl bromide alternatives | Individual | GLO | GLO | FUM | 19 | TAS | 93 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-03-01 | 2000-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. |  |  |  | 1999-03-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Develop technical brochure on methyl bromide | Individual | GLO | GLO | FUM | 19 | TRA | 94 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Provide halon bank management query response, information collection and dissemination | Individual | GLO | GLO | HAL | 19 | TAS | 95 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 |  |  | 3770 | 0 | 3770 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Guidelines for the establishment of recovery and recycling systems and related legislation for low volume ODS consuming countries | Individual | GLO | GLO | REF | 19 | TAS | 96 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2000-06-01 | 2000-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 7150 | 0 | 7150 | 0 |  | Project financially completed. |  |  |  | 1999-07-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Training modules for national training courses on good practices in refrigeration | Individual | GLO | GLO | REF | 19 | TRA | 97 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. |  |  |  | 1999-07-01 |  |  | 2002-06-01 |  |  |  | 1996 | Non Investment
FIN | UNEP | Prepare guidance to assist hotel industry in LVCs to avoid, replace, or eliminate ODS | Individual | GLO | GLO | REF | 19 | TRA | 98 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1996-12-01 |  | 1998-04-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 19 | TAS | 99 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-04-01 | 1999-01-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  |  | 3640 | 0 | 3640 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Collect sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 19 | TAS | 100 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-12-01 | 1999-01-01 | 104500 | 0 | 104500 | 104500 | 100% | 0 |  |  | 13585 | 0 | 13585 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Provide direct query-response service (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 101 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 |  |  | 6240 | 0 | 6240 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Support to national activities | Individual | GLO | GLO | SEV | 19 | TAS | 102 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-05-01 | 1999-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Ad hoc Group meetings | Individual | GLO | GLO | SEV | 19 | TAS | 103 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Deliver OAIC-DV and other OzonAction Programme information through World Wide Web home page site on a one year trial basis | Individual | GLO | GLO | SEV | 19 | TAS | 104 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 |  |  | 1885 | 0 | 1885 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Continue to maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 19 | TAS | 105 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Prepare an inventory and assessment of environmentally sound and economically viable technologies and know-how conducive to phase out of ODS | Individual | GLO | GLO | SEV | 19 | TAS | 106 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 2000-12-01 | 1996-08-01 |  | 2004-04-01 | 2005-12-01 | 50000 | -27500 | 22500 | 22500 | 100% | 0 |  | 0 | 6500 | -3575 | 2925 | 0 |  | Project completed | $27500 plus $3575 returned ExCom 46 |  |  | 2000-03-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Travel (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special suplements | Individual | GLO | GLO | SEV | 19 | TAS | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 |  |  | 31850 | 0 | 31850 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Prepare information papers and case studies | Individual | GLO | GLO | SEV | 19 | TRA | 109 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 2001-09-01 | 2001-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 |  |  | 5980 | 0 | 5980 | 0 |  | Project financially completed. |  |  |  | 1999-03-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 110 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 |  |  | 3120 | 0 | 3120 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Produce handbook on technology options especially for SMEs | Individual | GLO | GLO | SEV | 19 | TRA | 111 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-11-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. |  |  |  | 1999-07-01 | [6 empty] | 1996 | Non Investment
CLO | UNEP | Training modules on management of ODS phase-out in SMEs | Individual | GLO | GLO | SEV | 19 | TAS | 112 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 20000 | 50% | 20000 | 20000 | 20000 | 5200 | 0 | 2600 | 2600 | 2600 | Document 'Training Resource Kit: Preparing Small Businesses for the Transition Away from CFCs in Refrigeration and Air Conditioning / A support guide for National Ozone Units (NOUs) and their Local Partners in Developing Countries', translated, printed and disseminated electronically via web site (http://www.unep.fr/ozonaction/library/mmc/lib_detail.asp?r=4363) in September 2005. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Disseminate information | Individual | GLO | GLO | SEV | 19 | TRA | 113 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-05-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 |  |  | 35100 | 0 | 35100 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Training modules on policy design and setting up of legislation | Individual | GLO | GLO | SEV | 19 | TRA | 114 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Provide International Halon Bank Management International Clearinghouse services | Individual | GLO | GLO | HAL | 21 | TAS | 115 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 |  |  | 11050 | 0 | 11050 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Study on drop-in substitutes for domestic refrigeration | Individual | GLO | GLO | REF | 21 | TAS | 116 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1999-08-01 | 2000-06-01 | 80000 | -21000 | 59000 | 59000 | 100% | 0 |  |  | 10400 | -2730 | 7670 | 0 |  | Project financially completed. | $21000 plus $2730 PSC returned ExCom 32 |  |  | 1999-05-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 21 | TAS | 118 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 |  |  | 44200 | 0 | 44200 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Provide direct query-response service (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 119 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 21 | TAS | 120 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-02-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 |  |  | 13910 | 0 | 13910 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 21 | TAS | 121 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-01-01 |  | 1997-12-01 | 1999-01-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 |  |  | 43550 | 0 | 43550 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Advisory and expert group meetings | Individual | GLO | GLO | SEV | 21 | TAS | 122 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 123 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Travel (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 124 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Update the OAIC diskette version including "Simple Search" versions of prioritized OzonAction publications | Individual | GLO | GLO | SEV | 21 | TAS | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-10-01 | 2000-06-01 | 63000 | -15400 | 47600 | 47600 | 100% | 0 |  |  | 8190 | -2002 | 6188 | 0 |  | Project financially completed. | $15400 plus $2002 PSC returned ExCom 32 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Deliver OzonAction newsletter and other information through the World Wide Web home page | Individual | GLO | GLO | SEV | 21 | TAS | 126 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Update existing technical brochure series to include 1994/95 TOC data | Individual | GLO | GLO | SEV | 21 | TAS | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 2001-01-01 | 2002-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
FIN | UNEP | Develop awareness materials for 1999 freeze to support national initiatives on awareness raising | Individual | GLO | GLO | SEV | 21 | TAS | 128 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Translate prioritized OzonAction Programme documents into French and Spanish | Individual | GLO | GLO | SEV | 21 | TAS | 129 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1997-12-01 |  | 1998-12-01 | 1999-08-01 | 40000 | -1191 | 38809 | 38809 | 100% | 0 |  |  | 5200 | -154.83 | 5045.17 | 0 |  | Project financially completed. | $1191 plus $155 PSC returned ExCom 30 | [9 empty] | 1998 | Non Investment
FIN | UNEP | Develop a handbook on the practical use of policy instruments | Individual | GLO | GLO | SEV | 21 | TAS | 130 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-11-01 | 1997-12-01 |  | 2003-06-01 | 2005-12-01 | 50000 | -10000 | 40000 | 40000 | 100% | 0 |  | 0 | 6500 | -1300 | 5200 | 0 |  | Project financially completed. | $50000 plus $6500 returned ExCom 46 |  |  | 1999-07-01 | [6 empty] | 1997 | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 21 | TAS | 131 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
COM | UNEP | Preparation of refrigerant management plans/country programmes for VLVC/LVC | Individual | GLO | GLO | SEV | 22 | CPG | 132 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1997-12-01 |  | 2002-03-01 |  | 200000 | -73040 | 126960 | 126960 | 100% | 0 |  | 0 | 26000 | -9495.2 | 16504.8 | 0 | 0 | Project completed | $73040 plus $9495 returned ExCom 46 |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 23 | TAS | 136 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-08-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  |  | 5460 | 0 | 5460 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 23 | TAS | 139 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 |  |  | 14560 | 0 | 14560 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Update the OAIC diskette version (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 140 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 23 | TAS | 141 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 |  |  | 44200 | 0 | 44200 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Provide direct query-response service (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 142 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through World Wide Web home page site | Individual | GLO | GLO | SEV | 23 | TAS | 143 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Advisory and expert group meetings (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 144 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -10000 | 65000 | 65000 | 100% | 0 |  |  | 9750 | -1300 | 8450 | 0 |  | Project financially completed. | $10000 plus $1300 PSC returned ExCom 32 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (1998) | Individual | GLO | GLO | HAL | 23 | TAS | 145 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 |  |  | 11570 | 0 | 11570 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Travel (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 146 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -2950 | 72050 | 72050 | 100% | 0 |  |  | 9750 | -383 | 9367 | 0 |  | Project financially completed. | $2950 plus $383 PSC returned ExCom 33 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 23 | TAS | 147 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-07-01 | 347000 | -1750 | 345250 | 345250 | 100% | 0 |  |  | 45110 | -227.5 | 44882.5 | 0 |  | Project financially completed. | $1750 plus $228 PSC returned ExCom 30 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Support to national activities (1998) | Individual | GLO | GLO | SEV | 23 | TRA | 148 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-10-01 |  | 1998-10-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Technical sourcebook of methyl bromide alternatives | Individual | GLO | GLO | FUM | 23 | TAS | 150 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-12-01 | 2002-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Handbook for NOUs reducing reliance on methyl bromide | Individual | GLO | GLO | FUM | 23 | TAS | 151 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1998-11-01 |  | 1999-02-01 | 1999-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 152 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Translate and print three guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 23 | TAS | 153 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 2002-12-01 | 2003-08-01 | 360000 | 0 | 360000 | 360000 | 100% | 0 |  |  | 46800 | 0 | 46800 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Compilation of legislations for regulatory authorities from Article 5 countries that discourage methyl bromide use and promote alternatives | Individual | GLO | GLO | FUM | 24 | TAS | 155 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Technical and institutional resources for methyl bromide alternatives projects | Individual | GLO | GLO | FUM | 24 | TAS | 156 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-10-01 |  | 1999-09-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Methyl bromide information kit | Individual | GLO | GLO | FUM | 24 | TAS | 157 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 1998-12-01 | 1999-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Data reporting handbook to provide information to Article 5 countries and assist them with their data reporting | Individual | GLO | GLO | SEV | 24 | TAS | 158 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-01-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 |  |  | 14300 | 0 | 14300 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Compilation of case studies on commercial, low-impact methyl bromide alternatives successfully implemented | Individual | GLO | GLO | FUM | 24 | TAS | 160 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through world wide web home page site (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 162 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 163 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 |  |  | 14560 | 0 | 14560 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 164 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 |  |  | 11570 | 0 | 11570 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 165 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 |  |  | 44200 | 0 | 44200 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 26 | TAS | 166 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  |  | 5460 | 0 | 5460 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 26 | TAS | 167 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Provide direct query-response service (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 168 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Advisory and expert group meetings (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 169 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 75000 | -3500 | 71500 | 71500 | 100% | 0 |  |  | 9750 | -455 | 9295 | 0 |  | Project financially completed. | $3500 plus $455 PSC returned ExCom 33 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 170 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 55000 | -6300 | 48700 | 48700 | 100% | 0 |  |  | 7150 | -819 | 6331 | 0 |  | Project financially completed. | $6300 plus $819 PSC returned ExCom 31 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Travel (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 171 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Support to national activities for 1999 | Individual | GLO | GLO | SEV | 26 | TAS | 173 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 26 | TAS | 174 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 347000 | 0 | 347000 | 347000 | 100% | 0 |  |  | 45110 | 0 | 45110 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Development of training manuals for extension workers | Individual | GLO | GLO | FUM | 27 | TRA | 178 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-02-01 | 50000 | -4000 | 46000 | 46000 | 100% | 0 |  |  | 6500 | -520 | 5980 | 0 |  | Project financially completed. | $4000 plus $520 PSC returned ExCom 43 | [9 empty] | 1999 | Non Investment
FIN | UNEP | National farmer's training and establishment of Farmer's Field School (FFS) | Individual | GLO | GLO | FUM | 27 | TRA | 179 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-04-01 |  | 2001-12-01 | 2003-12-03 | 60000 | -4000 | 56000 | 56000 | 100% | 0 |  |  | 7800 | -520 | 7280 | 0 |  | Project financially completed. | $4000 plus $520 PSC returned ExCom 43 | [9 empty] | 1999 | Non Investment
FIN | UNEP | Development of a handbook on standards and codes of good practice for halon sector | Individual | GLO | GLO | HAL | 27 | TAS | 181 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-09-01 | 2002-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Develop fact sheet describing win-win technology options relative to Kyoto and Montreal Protocols | Individual | GLO | GLO | SEV | 27 | TAS | 182 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2000-04-01 |  | 2002-12-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Update regulations to control ozone depleting substances | Individual | GLO | GLO | SEV | 27 | TAS | 183 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2001-09-01 | 2001-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Update the OAIC CD-Rom | Individual | GLO | GLO | SEV | 29 | TAS | 186 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-01-01 | 2002-01-01 | 69300 | 0 | 69300 | 69300 | 100% | 0 |  |  | 9009 | 0 | 9009 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Preparation of how-to crop manual on adopting methyl bromide alternatives for cut flowers | Individual | GLO | GLO | FUM | 29 | TAS | 187 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2000-11-01 |  | 2001-12-01 | 2002-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 2600 | 0 | 2600 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Support to national activities (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 188 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 192 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 7150 | 0 | 7150 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 29 | TAS | 193 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 117600 | 0 | 117600 | 117600 | 100% | 0 |  |  | 15288 | 0 | 15288 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Travel (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 194 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Diseminate awareness materials, technical and policy information (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 195 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 357000 | 0 | 357000 | 357000 | 100% | 0 |  |  | 46410 | 0 | 46410 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 196 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 93450 | 0 | 93450 | 93450 | 100% | 0 |  |  | 12148.5 | 0 | 12148.5 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Provide direct query-response service (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 197 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 84000 | 0 | 84000 | 84000 | 100% | 0 |  |  | 10920 | 0 | 10920 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
COM | UNEP | Complement for translation and printing of four guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 29 | TAS | 198 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2005-04-01 |  | 120000 | 0 | 120000 | 98000 | 81.67% | 22000 |  | 22000 | 15600 | 0 | 12740 | 2860 |  | Project completed in April 2005. 200 copies of the french version were printed and disseminated. | [5 empty] | 2002-12-02 |  |  |  |  | 1999 | Non Investment
FIN | UNEP | Advisory and expert group meetings (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 199 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  |  | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 200 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2002-03-01 | 364000 | 0 | 364000 | 364000 | 100% | 0 |  |  | 47320 | 0 | 47320 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 201 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 |  |  | 5720 | 0 | 5720 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through worldwide web home page site (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 202 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 26250 | 0 | 26250 | 26250 | 100% | 0 |  |  | 3412.5 | 0 | 3412.5 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
COM | UNEP | Organizing a global video competition on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 206 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2000-09-01 |  | 2002-11-01 |  | 60000 | -26684 | 33316 | 1315 | 3.947% | 32001 | 0 | 32001 | 7800 | -3468.92 | 170.95 | 4160.13 | 0 | Project financially completed. | $26684 plus $3469 PSC returned ExCom 44 |  |  |  |  | 2001-10-01 |  |  |  |  | 2000 | Non Investment
FIN | UNEP | Translation and printing of OzonAction documents into French, Spanish and Arabic | Individual | GLO | GLO | SEV | 30 | TAS | 207 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-05-01 | 2001-03-01 |  | 2001-12-01 | 2002-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Adapting existing audiovisual materials to promote control of illegal trade in ODS | Individual | GLO | GLO | SEV | 30 | TAS | 208 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2003-06-01 | 2003-10-01 | 50000 | -2353 | 47647 | 47647 | 100% | 0 |  |  | 6500 | -306 | 6194 | 0 |  | Project financially completed. | $2353 plus $306 PSC returned ExCom 43 | [9 empty] | 2000 | Non Investment
FIN | UNEP | New awareness raising activities and materials for dissemination to the general public | Individual | GLO | GLO | SEV | 30 | TAS | 209 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-02-01 |  | 2001-12-01 | 2002-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Develop materials to educate children on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 210 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2004-07-01 |  | 100000 | 0 | 100000 | 89552.46 | 89.55% | 10447.54 | 0 | 10447.54 | 13000 | 0 | 11641.8198 | 1358.1802 | 0 | Project financially completed in July 2005. | [7 empty] | 2003-07-01 |  |  | 2000 | Non Investment
FIN | UNEP | Policy development assistance to prevent future methyl bromide growth in low methyl bromide-consuming countries | Individual | GLO | GLO | FUM | 30 | TAS | 211 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2001-05-31 | 2002-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 |  |  | 26000 | 0 | 26000 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 214 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 |  |  | 9880 | 0 | 9880 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Travel for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 215 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-12-02 | 75000 | 0 | 75000 | 75000 | 100% | 0 |  | 0 | 9750 | 0 | 9750 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Provide direct query-response service in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 217 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 |  |  | 11180 | 0 | 11180 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Global enabling activity for customs training | Individual | GLO | GLO | SEV | 32 | TRA | 218 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2002-03-01 | 2003-06-01 | 165400 | -13971 | 151429 | 151429 | 100% | 0 | 0 |  | 21502 | -1816.23 | 19685.77 | 0 |  | Project financially completed. | $13971 plus $1816 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Disseminate awareness material, technical, and policy information in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 219 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 346000 | -13916 | 332084 | 332084 | 100% | 0 |  |  | 44980 | -1809.08 | 43170.92 | 0 |  | Project financially completed. | $13916 plus $1809 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Deliver OzonAction Newsletter and other information through world wide web home page site in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 220 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 221 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 280000 | -5051 | 274949 | 274949 | 100% | 0 |  |  | 36400 | -656.63 | 35743.37 | 0 |  | Project financially completed. | $5051 plus $657 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Support to national activities for 2001 | Individual | GLO | GLO | SEV | 32 | TRA | 222 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Advisory and expert group meetings for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 223 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 75000 | -7392 | 67608 | 67608 | 100% | 0 |  |  | 9750 | -960.96 | 8789.04 | 0 |  | Project financially completed. | $7392 plus $961 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
COM | UNEP | Regional awareness raising and South-South assistance | Individual | GLO | GLO | SEV | 32 | TAS | 224 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2001-12-01 |  | 2004-12-01 |  | 191000 | 0 | 191000 | 164787.96 | 86.28% | 26212.04 | 18000 | 26212.04 | 24830 | 0 | 21422.4348 | 3407.5652 | 2340 | Project completed. | [7 empty] | 2003-07-01 |  |  | 2000 | Non Investment
FIN | UNEP | Maintain contact database of experts and mailing list for OzonAction programme publications in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 225 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  |  | 5850 | 0 | 5850 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 226 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 55000 | -5 | 54995 | 54995 | 100% | 0 |  |  | 7150 | -1 | 7149 | 0 |  | Project financially completed. | $5 plus $1 PSC returned ExCom 43 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Prioritized sectoral data from worldwide sources in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 228 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 121000 | 0 | 121000 | 121000 | 100% | 0 |  |  | 15730 | 0 | 15730 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Preparation of a booklet on data reporting for methyl bromide | Individual | GLO | GLO | SEV | 33 | TAS | 229 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2001-12-01 |  | 2001-11-01 | 2003-06-01 | 42500 | -2002 | 40498 | 40498 | 100% | 0 |  |  | 5525 | -260.26 | 5264.74 | 0 |  | Project financially completed. | $2002 plus $260 PSC returned ExCom 41 | [9 empty] | 2001 | Non Investment
COM | UNEP | Study on development of ODS phase-out strategy for SMEs | Individual | GLO | GLO | SEV | 34 | TAS | 230 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-09-01 | 2002-12-01 |  | 2005-12-01 |  | 100000 | 0 | 100000 | 10000 | 10% | 90000 | 0 | 90000 | 13000 | 0 | 1300 | 11700 | 0 | Project completed in December 2005. Document "Implementing the Montreal Protocol in Small Businesses: Chemical Management Under a Multilateral Environmental Agreement" printed and disseminated electronically via web site (http://www.unep.fr/ozonaction/library/mmc/lib_detail.asp?r=4364) in September 2005.. | [10 empty] | 2001 | Non Investment
FIN | UNEP | Global public awareness and education campaign to sustain the phase out (first tranche) | Individual | GLO | GLO | SEV | 34 | TAS | 231 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-01-01 | 2003-01-01 | 60000 | -11755 | 48245 | 48245.26 | 100% | -0.26 | 0 | 0 | 7800 | -1528.15 | 6271.8838 | 0 | 0 | Project financially completed. | $5810 plus $755 PSC returned ExCom 44 $5945 plus $773 PSC returned ExCom 46 | [9 empty] | 2001 | Non Investment
CLO | UNEP | Development of tracking system for ODS and ODS-based equipment | Individual | GLO | GLO | SEV | 34 | TAS | 232 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2002-12-01 |  |  | 2005-03-01 | 40000 | -40000 | 0 | 0 | 0% | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 |  | This project was cancelled by ExCom 44 | $40000 plus $5200 PSC returned ExCom 45 | [9 empty] | 2001 | Non Investment
FIN | UNEP | Compliance Assistance Programme: 2002 work programme: | Individual | GLO | GLO | SEV | 35 | TAS | 237 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2002-12-01 |  | 2002-12-01 | 2005-01-01 | 5351450 | -1492528 | 3858922 | 3850859 | 99.79% | 8063 | 0 | 0 | 428116 | -119401.88 | 308069.0792 | 645.0408 |  | Project financially completed. | $ 50,000 transferred for 5 policy projects ExCom 37 / $1,265,686.30 plus $ 105,254.90 PSC returned Excom 41 / $176,842 plus $14,147 PSC returned Excom 44 | [9 empty] | 1991 | Non Investment
ONG | UNEP | Translation of OzonAction Publications into other UN languages | Individual | GLO | GLO | SEV | 36 | TAS | 238 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2002-11-01 | 2006-07-01 |  |  | 93000 | 0 | 93000 | 58933.25 | 63.37% | 34066.75 | 9144.75 | 34066.75 | 12090 | 0 | 7661.3225 | 4428.6775 | 1189 | Two Spanish translations were completed by ROLAC | [7 empty] | 2004-07-01 |  |  | 2002 | Non Investment
COM | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 37 | TAS | 241 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2005-12-01 |  | 200000 | 0 | 200000 | 166888.74 | 83.44% | 33111.26 | 19274 | 33111.26 | 26000 | 0 | 21695.5362 | 4304.4638 | 2506 | Project completed in December 2005. The funding was apportioned to each Region and the Network members as a group decided how to use the funds, with guidance provided by UNEP. As such, there are multiple sub-components to this project, most of which (but not all) are completed. | [8 empty] | 2004-12-01 |  | 2002 | Non Investment
FIN | UNEP | Compliance assistance programme: 2003 work programme | Individual | GLO | GLO | SEV | 38 | TAS | 242 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-07-01 | 5830885 | -466383 | 5364502 | 5364502 | 100% | 0 | 0 | 0 | 466471 | -37310.6646 | 429160.3354 | 0 |  | Project financially completed | $173035 plus $13,843 PSC returned ExCom 43 $293348 plus $23468 PSC returned ExCom 46 | [9 empty] | 2002 | Non Investment
ONG | UNEP | Development of guidelines to promote safety an aerosol conversions | Individual | GLO | GLO | ARS | 39 | TAS | 246 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2003-12-01 | 2006-06-01 |  |  | 52000 | 0 | 52000 | 31988.85 | 61.52% | 20011.15 | 6092.31 | 20011.15 | 6760 | 0 | 4158.5505 | 2601.4495 | 792 | English version printed and disseminated (see http://www.unep.fr/ozonaction/library/mmc/lib_detail.asp?r=4375). UNEP has issued a request for bids for Spanish, Arabic and Chinese at the end of 2005 and received quotations. However, for the Arabic and Chinese translations, all quotations exceeded the budget available under this project for translation and we have been forced to re-issue the request for bids in order to meet the budget. It should be noted that this project has a very modest overall budget and the translation of technical information related to safety is quite complex and is costly. The health and safety implications resulting from a poor quality translation are of concern. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 39 | TAS | 247 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-02-01 | 2004-04-01 | 2006-04-01 |  |  | 200000 | 0 | 200000 | 122044.32 | 61.02% | 77955.68 | 1093.7 | 77955.68 | 26000 | 0 | 15865.7616 | 10134.2384 | 142 | Project completed in April 2005. The funding was apportioned to each Region and the Network members as a group decided how to use the funds, with guidance provided by UNEP. As such, there are multiple sub-components to this project, most of which (but not all) are completed. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Production of OzonAction Newsletter in Russian, translation of 4 refrigeration/customs training modules into Russian, and reprinting and updating existing publications | Individual | GLO | GLO | SEV | 39 | TAS | 248 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-03-01 | 2006-11-01 |  |  | 75000 | 0 | 75000 | 5000 | 6.667% | 70000 | 70000 | 70000 | 9750 | 0 | 650 | 9100 | 9100 | "Training Manual for Custom offices: Saving the Ozone Layer – Phasing out Ozone Depleting Substances in Developing Countries" was printed in Russian by the NOU of Georgia and distributed in all Russian speaking countries (12 countries). He manual was also sent to the participants of the Green Customs Workshop for Central Asia. Layout of the Russian version of "Planning, Designing and Implementing Policies to Control Ozone depleting Substances under the Montreal Protocol: A Handbook of Policy setting at the National Level" is being prepared by NOU of Georgia. The manual is planned for printing and distribution in April-May 2006. "Green Customs Manual" was translated in Russian and distributed to participants of the Green Customs Workshop for Central Asia electronically. | [9 empty] | 2005-09-01 | 2003 | Non Investment
COM | UNEP | Compliance assistance programme: 2004 budget | Individual | GLO | GLO | SEV | 41 | TAS | 252 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2004-12-01 |  | 2004-12-04 |  | 6757900 |  | 6757900 | 6567683 | 97.19% | 190217 | 190217 | 190217 | 540632 | 0 | 525414.64 | 15217.36 | 15217 | Project completed | [10 empty] | 2003 | Non Investment
ONG | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 42 | TAS | 255 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 | 2006-04-01 |  |  | 200000 | 0 | 200000 | 99509 | 49.75% | 100491 | 27533 | 100491 | 26000 | 0 | 12936.17 | 13063.83 | 3579 | Funding was apportioned to each Region and the Network members as a group decided how to use the funds, with guidance provided by UNEP. As such, there are multiple sub-components to this project, most of which (but not all) are completed. | [10 empty] | 2004 | Non Investment
COM | UNEP | Compliance assistance programme: 2005 budget | Individual | GLO | GLO | SEV | 44 | TAS | 260 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 |  | 7157544 | 0 | 7157544 | 6311283 | 88.18% | 846261 | 734336 | 846261 | 572604 | 0 | 504903.0632 | 67700.9368 | 58747 | Project completed o, December 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Assistance for regional awareness raising (2005) | Individual | GLO | GLO | SEV | 45 | TAS | 262 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2006-04-01 |  |  | 200000 | 0 | 200000 | 27302 | 13.65% | 172698 | 42268 | 172698 | 26000 | 0 | 3549.26 | 22450.74 | 5495 | Project newly approved | [10 empty] | 2005 | Non Investment
ONG | UNEP | Development of effective awareness materials | Individual | GLO | GLO | SEV | 45 | TAS | 263 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 | 2006-04-01 |  |  | 120000 | 0 | 120000 | 105063 | 87.55% | 14937 | 14937 | 14937 | 15600 | 0 | 13658.19 | 1941.81 | 1941.81 | Three public service announcements and two radio spots were developed. Cartoon book "Ozzy Ozone - Defender" of Our Planet was created. UNEP launched a new children's website | [10 empty] | 2005 | Non Investment
ONG | UNEP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 264 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 |  | 2005-11-01 | 2006-04-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | Consultations were carried out with all relevant stakeholders including the IAs, MFS, industry, and a project proposal prepared for submission to the ExCom at its 47th Meeting. Due to funding constraints, UNEP was requested to prepare a revised proposal with a maximum budget of $200,000 for submission to the 48th Meeting of the ExCom. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Compliance Assistance Programme: 2006 budget | Individual | GLO | GLO | SEV | 47 | TAS | 270 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 7770000 | 0 | 7770000 | 0 | 0% | 7770000 | 0 | 7770000 | 621600 | 0 | 0 | 621600 |  | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GRN | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-08-01 |  | 1999-10-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
ONG | UNEP | Creation of a National Ozone Unit | Individual | LAC | GRN | SEV | 30 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2003-04-01 | 2006-12-05 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 |  | No disbursements due to non-submission of reports by country. UNEP letter dated September 2005 sent to the Minister of the Environment requesting her intervention. Discussions held on rationalization of the NOU from the Ministry of Energy to the Ministry of Environment. The Minister has agreed that the NOU which is presently under another Ministry need reviewing and rationalization. Awaiting for final answer from the country and for expenditure report of last disbursement. On the other hand, NOU has prepared and submitted ODS data report to both Secretariats and ODS license system advanced draft is completed and awaiting final approval from the Attorney General Office. NOO attended regional network meetings. NOU assisted in the TPMP preparation. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: Train the trainer programme for refrigeration service technicians | Individual | LAC | GRN | REF | 30 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2000-10-01 | 2006-06-01 |  |  | 52000 | 0 | 52000 | 29000 | 55.77% | 23000 |  | 23000 | 6760 | 0 | 3770 | 2990 |  | NOO submitted report on the status of the Training of Technicians- as part of the RMP project preparation. Financial expenditures were not provided to allow for last payment processing. Both the Train the trainer and training of remaining technicians are completed. Awaiting financial reports to allow for project closure. | [5 empty] | 2002-06-02 |  |  |  |  | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: Training of custom officers, ODS inspectorate and Ozone Unit staff | Individual | LAC | GRN | REF | 30 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 | 2006-06-01 |  |  | 36700 | 0 | 36700 | 19721 | 53.74% | 16979 | 2438 | 16979 | 4771 | 0 | 2563.73 | 2207.27 |  | Activities completed in June 2005. Awaiting financial reports from country to allow for closure. | [5 empty] | 2002-12-02 |  |  |  |  | 2000 | Non Investment
ONG | UNEP | Institutional strengthening project | Individual | LAC | GRN | SEV | 44 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-05-05 |  |  | 18000 | 0 | 18000 | 0 | 0% | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | Agreement reached with NOO on the budget lines to allow for the rebuilding of the NOO. Budget and work plan agreed by party. MOU submitted for signing. UNEP/ROLAC is pursuing South/south cooperation to assist this party in project implementation and reporting. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | GRN | REF | 46 | PRP | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2006-07-01 | 2006-07-01 |  |  | 15000 | 0 | 15000 | 5000 | 33.33% | 10000 | 5000 | 10000 | 1950 | 0 | 650 | 1300 | 650 | Budget and work plan completed. International and national Consultants Contracted. Draft TPMP completed and being prepard for submission to the 49th Ex. Com. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GUA | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-23 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 |  |  | 3900 | 390 | 4290 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Institutional strengthening: Establishment of COGO | Individual | LAC | GUA | SEV | 10 | INS | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-12-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 |  |  | 22360 | 0 | 22360 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | GUA | REF | 21 | TRA | 13 | A | O | I | CFC | 68.3 | 68.3 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2001-12-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | GUA | SEV | 22 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2000-05-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 |  |  | 12480 | 0 | 12480 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the RMP: Custom officers training programme | Individual | LAC | GUA | REF | 27 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2000-10-02 |  | 2002-11-01 | 2003-11-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  |  | 4420 | 0 | 4420 | 0 |  | Project financially completed. | [5 empty] | 2001-12-01 |  |  |  |  | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Code of good practices in refrigeration | Individual | LAC | GUA | REF | 27 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-02 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [5 empty] | 2001-12-01 |  |  |  |  | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Licensing system | Individual | LAC | GUA | REF | 27 | TAS | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-02 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | LAC | GUA | SEV | 28 | INS | 22 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-12-01 | 2003-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 |  |  | 12480 | 0 | 12480 | 0 |  | Project financially completed. |  |  |  |  | 2002-06-01 | [5 empty] | 1999 | Non Investment
ONG | UNEP | Implementation of the RMP: establishment of licensing system | Individual | LAC | GUA | REF | 35 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 | 2007-12-01 |  |  | 23200 | 0 | 23200 | 14100 | 60.78% | 9100 | 0 | 9100 | 3016 | 0 | 1833 | 1183 |  | It was decided that an SSA will be prepared to implement this component. Ministry won't be able to open a special account. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: alternatives to the use of CFC-12 in the refrigeration sector | Individual | LAC | GUA | REF | 35 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 | 2007-03-01 |  |  | 58000 | 0 | 58000 | 1518.57 | 2.618% | 56481.43 | 16868 | 56481.43 | 7540 | 0 | 197.4141 | 7342.5859 | 9.1 | An MOU with technical instittution (INTECAP) will be negotiated to implement this component | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | GUA | REF | 35 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 31800 | 0 | 31800 | 0 | 0% | 31800 | 0 | 31800 | 4134 | 0 | 0 | 4134 |  | Minister's communication advising UNEP that he will be the focal point for all Montreal Protocol activities delivered in Mar-2005. MOUs resent directly to Minister for his consideration. Mission in Sep-05 to address no response and to speed up signature of proposed MOUs. As of Dec-05 there is no response from the governement despite efforts made at a higher level. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: establishment and enforcement of legislation | Individual | LAC | GUA | REF | 35 | TAS | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 | 2007-12-01 |  |  | 62000 | 0 | 62000 | 14775.44 | 23.83% | 47224.56 | 9102.56 | 47224.56 | 8060 | 0 | 1920.8072 | 6139.1928 | 1183.39 | Minister's communication advising UNEP that he will be the focal point for all Montreal Protocol activities delivered in Mar-2005. MOUs resent directly to Minister for his consideration. Mission in Sep-05 to address no response and to speed up signature of proposed MOUs. As of Dec-05 there is no response from the governement despite efforts made at a higher level. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme | Individual | LAC | GUA | REF | 35 | TRA | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2007-12-01 | 2007-12-01 |  |  | 56000 | 0 | 56000 | 11600 | 20.71% | 44400 | 1000 | 44400 | 7280 | 0 | 1508 | 5772 | 130 | Several campaigns to increase public awareness took place. | [10 empty] | 2001 | Non Investment
COM | UNEP | Renewal of the institutional strengthening project | Individual | LAC | GUA | SEV | 35 | INS | 28 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-09-01 | 2004-01-01 |  | 2004-03-01 |  | 96000 | 0 | 96000 | 85092 | 88.64% | 10908 |  | 10908 | 12480 | 0 | 11061.96 | 1418.04 |  | Project completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | LAC | GUA | SEV | 43 | INS | 30 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2005-07-01 | 2007-01-01 |  |  | 62400 | 0 | 62400 | 0 | 0% | 62400 |  | 62400 | 0 | 0 | 0 | 0 |  | Disbursements stopped until audit report be prepared by Gov. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. 2004 ODS consumption according to the Action Plan approved by MOP. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GUI | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-10-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  |  | 5590 | 0 | 5590 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | GUI | SEV | 18 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | GUI | REF | 21 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 2000-01-01 | 2001-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 2600 | 0 | 2600 | 0 |  | Project financially completed. |  |  |  | 1999-05-01 | [6 empty] | 1997 | Non Investment
COM | UNEP | Implementation of the RMP: Training for customs officers | Individual | AFR | GUI | REF | 30 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-03-01 | 2001-04-01 |  | 2003-03-01 |  | 42500 | -23512 | 18988 | 18988 | 100% | 0 |  | 0 | 5525 | -3056.56 | 2468.44 | 0 |  | Project completed. | $23512 plus $3057 PSC returned ExCom 46 |  |  |  |  | 2003-03-03 |  |  |  |  | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Train the trainer programme in the refrigeration servicing sector | Individual | AFR | GUI | REF | 30 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2002-09-01 | 2003-09-01 | 66500 | 0 | 66500 | 66500 | 100% | 0 |  |  | 8645 | 0 | 8645 | 0 |  | Project financially completed. | [5 empty] | 2002-12-02 |  |  |  |  | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | GUI | SEV | 28 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-11-01 | 2001-12-12 | 33333 | 0 | 33333 | 33333 | 100% | 0 |  |  | 4333.29 | 0 | 4333.29 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | GUI | SEV | 34 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 |  |  | 4333.29 | 0 | 4333.29 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
FIN | UNEP | Preparation of a country programme/RMP | RMP | AFR | GUI | REF | 39 | PRP | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2004-11-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | GUI | SEV | 41 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 | 2006-12-01 |  |  | 43333 | 0 | 43333 | 32363 | 74.68% | 10970 |  | 10970 | 0 | 0 | 0 | 0 |  | The NOO coordinated the organisation of the Customs Officers training in November 2005 and the one of technicians in refrigeration in October 2005. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: customs officers training in monitoring and control of ODS (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 25000 | 25000 | 3250 | 0 | 0 | 3250 | 1948.05 | MoU with the country signed in July 2005. Phase 1 training held on 9-11 November 2005 | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for refrigeration technicians (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-10-01 | 2006-10-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 25000 | 25000 | 3250 | 0 | 0 | 3250 | 1948.05 | MoU with the country signed in July 2005. phase 1 training held on 26-29 October 2005 | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities of the RMP | Individual | AFR | GUI | REF | 45 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 20000 | 2600 | 0 | 0 | 2600 | 1948.05 | MoU with the country signed in July 2005. First payment done in August 2005. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GUY | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-02-26 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 |  |  | 5200 | -650 | 4550 | 0 |  | Project financially completed. | $5000 plus $650 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | GUY | REF | 21 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-12-01 | 30000 | -4000 | 26000 | 26000 | 100% | 0 |  |  | 3900 | -520 | 3380 | 0 |  | Project financially completed. | $4000 plus $520 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
COM | UNEP | Creation of the National Ozone Action Unit | Individual | LAC | GUY | SEV | 23 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 2000-11-01 |  | 2001-08-01 |  | 65000 | 0 | 65000 | 63421 | 97.57% | 1579 |  | 0 | 8450 | 0 | 8244.73 | 205.27 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training of trainers for good refrigeration servicing practices | Individual | LAC | GUY | REF | 23 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 2001-04-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training on monitoring and control of ODS and ODS using equipment | Individual | LAC | GUY | REF | 23 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-06-01 |  | 2003-08-01 | 2003-09-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 |  |  | 2080 | 0 | 2080 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project | Individual | LAC | GUY | SEV | 34 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2005-02-01 | 2003-08-01 | 2006-05-01 |  |  | 43400 | 0 | 43400 | 22565 | 51.99% | 20835 |  | 20835 | 5642 | 0 | 2933.45 | 2708.55 |  | IS reports and request for CASH advance made and submitted to UNON for processing. UNON acknowledge receipt of submission. One disbursement of US$25,000.00 was completed in February 2005 and received by party in December 2005. IS reports and CASH advance request submitted to UNON for processing. UNON satisfied with all submissions. CASH advance will be processed in January 2006. NOO attended regional network meetings. ODS data repors sent to MLF and OS. IS renewal will be submitted in 48th Ex.Com. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: assistance for implementation of additional activities in the RMP | Individual | LAC | GUY | REF | 35 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 | 2007-01-01 |  |  | 65500 | 0 | 65500 | 16000 | 24.43% | 49500 | 13500 | 49500 | 8515 | 0 | 2080 | 6435 | 1755 | Equipment purchased by UNEP/ROLAC. Delivered in February 2005. Customs Training ongoing. Refresher course in May 2005 with the establishment of ODS Import/Export License System. Reports received on Training of Technicians and Customs Officers. Draft report received on the phase 1. | [10 empty] | 2001 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | LAC | HAI | SEV | 32 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-04-01 |  | 2003-07-01 | 2005-06-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 | 0 | 7800 | -3770 | 4030 | 0 |  | Project financially completed. | $9000 plus $1170 PSC returned ExCom 44 $20000 plus $ 2600 PSC retuned ExCom 46 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | HAI | SEV | 38 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-07-01 | 2003-12-01 |  | 2004-08-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the refrigerant management plan: train the technicians on good practices in refrigeration | Individual | LAC | HAI | REF | 39 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 | 2007-12-01 |  |  | 74200 | 0 | 74200 | 38200 | 51.48% | 36000 | 36000 | 36000 | 9646 | 0 | 4966 | 4680 | 4680 | Political instability during first half of 2005 has prevented any action in Haiti | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the refrigerant management plan: training for customs officers | Individual | LAC | HAI | REF | 39 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-04-01 | 2007-03-01 |  |  | 33100 | 0 | 33100 | 12729 | 38.46% | 20371 | 18000 | 20371 | 4303 | 0 | 1654.77 | 2648.23 | 2340 | Political instability during first half of 2005. Slow progress in legislation | [10 empty] | 2003 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase I, years 2 and 3) | Individual | LAC | HAI | SEV | 43 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 | 2006-07-01 |  |  | 100000 | 0 | 100000 | 38952 | 38.95% | 61048 |  | 61048 | 0 | 0 | 0 | 0 |  | Audit Report indicated that control problems or improper fund management were not detected. Two cash advances sent to the country during the 2005 year. NOU attended ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. ODS license system did not approve due to political instability during first half of 2005. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | HON | SEV | 13 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-28 | 1995-10-01 |  | 1996-06-01 | 1999-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit Cell for the institutional strengthening programme | Individual | LAC | HON | SEV | 20 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1999-10-01 |  | 2001-06-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. |  |  | 2000-03-01 | [7 empty] | 1996 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | HON | SEV | 32 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-05-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 |  |  | 5720 | 0 | 5720 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Extension of institutional strengthening project | Individual | LAC | HON | SEV | 40 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-07-01 | 2005-07-01 |  | 2005-07-01 |  | 57200 | 0 | 57200 | 55426 | 96.9% | 1774 |  | 1774 | 0 | 0 | 0 | 0 |  | Project completed in July 2005. Disbursements released regularly, last cash advance corresponding to ISP (III) sent to the country in March 2005. NOU attended the ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. Revision of the MB Plan of Action was prepared by NOU and approved by 17 MOP. | [10 empty] | 2003 | Non Investment
COM | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | HON | REF | 41 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 |  | 15000 | 0 | 15000 | 3750 | 25% | 11250 | 0 | 11250 | 1950 | 0 | 487.5 | 1462.5 | 0 | Project financially completed. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: programme for certification and licensing of refrigeration technicians | Individual | LAC | HON | REF | 44 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 94000 | 0 | 94000 | 0 | 0% | 94000 | 0 | 94000 | 12220 | 0 | 0 | 12220 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: programme for prevention of illegal ODS trade | Individual | LAC | HON | REF | 44 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 23000 | 0 | 23000 | 0 | 0% | 23000 | 0 | 23000 | 2990 | 0 | 0 | 2990 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: programme for permanent monitoring of the RMP | Individual | LAC | HON | REF | 44 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 38000 | 0 | 38000 | 0 | 0% | 38000 | 0 | 38000 | 4940 | 0 | 0 | 4940 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | HON | SEV | 45 | INS | 19 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 | 2007-04-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | On July 8th 2005, the MOU was signed by the Minister of the Environment of Honduras and UNEP. First disbursement received by country in July 2005. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Develop policy and customs training strategies | Individual | ASP | IND | SEV | 30 | TAS | 253 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2003-04-01 | 2005-12-01 | 50000 | -22000 | 28000 | 28000 | 100% | 0 |  | 0 | 6500 | -2860 | 3640 | 0 |  | Project financially completed. | $22000 plus $2860 PSC returned ExCom 46 | [9 empty] | 2000 | Non Investment
COM | UNEP | Overall strategy for the solvent sector to support the phaseout of ODS in SMEs | Individual | ASP | IND | SOL | 35 | TAS | 343 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2003-12-01 |  | 2005-06-01 |  | 169000 | 0 | 169000 | 116419.3 | 68.89% | 52580.7 | 10000 | 52580.7 | 21970 | 0 | 15134.509 | 6835.491 |  | Project completed in June 2005 | [10 empty] | 2001 | Non Investment
COM | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-year | ASP | IND | REF | 42 | TAS | 377 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 |  | 256300 | 0 | 256300 | 236379.16 | 92.23% | 19920.84 | 0 | 19920.84 | 33319 | 0 | 30729.2908 | 2589.7092 | 0 | Project completed in April 2005. Total of 145 Officers trained on Monitoring and Control of Ozone Depleting Substances. The workshops conducted by NACENwere as follows. Two workshop conducted on 17-18 February 2005 wherein 18 officers get trained. Two workshop conducted on 19-20 April 2005 wherein 10 officers get trained. Two workshop conducted on 2-3 June 2005 wherein 6 officers get trained. Two workshop conducted on 14-15 July 2005 wherein 20 officers get trained. Two workshop conducted on 11-12 August 2005 wherein 23 officers get trained. Two workshop conducted on 15-16 September 2005 wherein 33 officers get trained. Two workshop conducted on 22-23 September wherein 35 officers got trained. Two workshops conducted on 19-20 April 2005 wherein 10 officers got trained. 39 equipments were distributed to NACEN/MoEF in March 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-year | ASP | IND | REF | 44 | TAS | 382 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 | 2006-03-01 |  |  | 256300 | 0 | 256300 | 14205.06 | 5.542% | 242094.94 | 0 | 242094.94 | 33319 | 0 | 1846.6578 | 31472.3422 | 0 | A. For awareness programme implementation: - Nine workshops was held for outreach/awareness workshops for RSEs on the deal offered under the equipment support scheme in 3-4 states. - Two issues was circulated on newletter publication in July and November. - Four Dealer network workshops conducted to support technician training. B. For the Training programme implementation: - Training programme for 2004-2005 was completed wherein the initial planned of 9 workshops were conducted and a total of 145 identified target officers were trained by NACEN on Monitoring and Control of Ozone Depleting Substances from February to December 2005. These workshops were conducted in: - NACEN Headquarters, on 17- 18 February 2005, 19-20 February 2005 and 2-3 June 2005 with 34 officers get trained - Kolkata, on 14-15 July 2005 with 20 officers get trained - Kanpur, on 11-12 August 2005 with 23 officers get trained - Mumbai, on 15-16 September 2005 with 33 officers get trained - Bangalore, on 22-23 August 2005 with 35 officers get trained - Chennai, on 17-18 November 2005 and 37 officers were trained - Hazaribagh, on 5-6 December 2005 and 26 officers were trained - Additional 2 workshops conducted in: Shimla, on 17-18 November 2005 and a total of 25 officers get trained. Hyderabad, on 8-9 December 2005 and 29 officers were trained Training modules were developed by MoEF which is being used in the training programme. -39 equipments were distributed to NACEN/MoEF in March 2005 | [10 empty] | 2004 | Non Investment
ONG | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-year | ASP | IND | REF | 47 | TAS | 396 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2007-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | The third tranche of the India NCCoPP which includes this omponent was approved only at the 47th ExCom Meeting. A workplan for 2006 has been finalised with the National Partner, and work for 2006 will draw upon results from 2005 activities. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Preparation of country programme update | Individual | ASP | IRA | SEV | 36 | CPG | 145 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 26250 | -3250 | 23000 | 23000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed in May 2005 | $3250 returned ExCom 46 | [9 empty] | 2002 | Non Investment
ONG | UNEP | National CFC phase-out plan: first tranche | Multi-year | ASP | IRA | PHA | 41 | TAS | 161 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 | 2006-12-01 |  |  | 140253 | 0 | 140253 | 105317.51 | 75.09% | 34935.49 | 0 | 34935.49 | 18232.89 | 0 | 13691.2763 | 4541.6137 | 0 | Implementation workplan for the year 2005 to 2006 was submitted to UNEP on how to manage the Enforcement Centre along with the comprehensive draft ODS regulation and licensing system for import/export of ODS. Policy and Enforcement Centre is being set-up in Ministry of Environment. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | IVC | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-03-01 | 1994-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  |  | 1690 | 0 | 1690 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening (establishment of the Ozone Secretariat) | Individual | AFR | IVC | SEV | 13 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-01-01 | 1997-07-01 |  | 1998-10-01 | 1999-07-01 | 122810 | -300 | 122510 | 122510 | 100% | 0 |  |  | 15965.3 | -39 | 15926.3 | 0 |  | Project financially completed. | $300 plus $39 PSC returned ExCom 31 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Training for refrigeration and air conditioning technicians | Individual | AFR | IVC | REF | 13 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-04 | 1995-07-01 |  | 1997-03-01 | 1999-04-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 |  |  | 9880 | 0 | 9880 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | IVC | SEV | 26 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-08-10 | 2000-12-01 |  | 2004-04-01 | 2004-12-01 | 81800 | 0 | 81800 | 81800 | 100% | 0 |  |  | 10634 | 0 | 10634 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
COM | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | IVC | SEV | 43 | INS | 20 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-09-01 | 2005-07-01 |  | 2005-11-01 |  | 53170 | 0 | 53170 | 40463 | 76.1% | 12707 |  | 12707 | 0 | 0 | 0 | 0 |  | Project completed in November 2005. IS renewal will be submitted at the next ExCom | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | JAM | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-06-26 | 1995-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Institutional strengthening through creation of a National Ozone Unit | Individual | LAC | JAM | SEV | 20 | INS | 04 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-05-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. |  |  | 2000-03-01 | [7 empty] | 1996 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | JAM | REF | 24 | PRP | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-02-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | JAM | SEV | 29 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-01-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 |  |  | 5720 | 0 | 5720 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | JAM | SEV | 35 | INS | 15 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-08-01 | 2004-10-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 |  |  | 5720 | 0 | 5720 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Extension of institutional strengthening project | Individual | LAC | JAM | SEV | 40 | INS | 19 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 | 2006-04-01 |  |  | 57200 | 0 | 57200 | 39265 | 68.65% | 17935 |  | 17935 | 0 | 0 | 0 | 0 |  | Disbursements released regularly, last cash advance corresponding to ISP (IV) sent to the country in November 2005. NOU attended the ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished by NOU. ODS license system working properly. NOU is also leading TPMP, solvents and MB phase out projects. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | JAM | SEV | 47 | INS | 23 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-02-01 | 2008-02-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Formulation of national phase out strategy | Individual | ASP | KAM | SEV | 35 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2005-01-01 | 60000 | 0 | 60000 | 59566.82 | 99.28% | 433 | 0 | 0 | 7800 | 0 | 7743.6866 | 56.3134 |  | Project financially completed in January 2005 | [10 empty] | 2001 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | KAM | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: refrigeration and air-conditioning technicians training programme | Individual | ASP | KAM | REF | 41 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 | 2006-12-01 |  |  | 130000 | 0 | 130000 | 127338.9 | 97.95% | 2661.1 | 0 | 2661.1 | 16900 | 0 | 16554.057 | 345.943 | 0 | As of September 2005, 238 technicians were trained under the implementaton of phase II with a total of 7 courses. The impact of training and awareness program in Cambodia results to dramtically reduced in ODS consumption. As of December 2005, 391 technicians were trained as per submitted progress report on December 2005 | [10 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | KAM | REF | 41 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 |  | 85000 | 0 | 85000 | 84801.25 | 99.77% | 198.75 | 0 | 198.75 | 11050 | 0 | 11024.1625 | 25.8375 | 0 | Project completed in December 2005. Feb 05: Country Handbook prepared. March 2005: Subdecree ODS Management, signed. May 2005: Phase I Customs Training. 30 Officers trained (27 customs officers and 7 officers from Camcontrol Dpt. Dec05: Phase II training programme was completed. A total of 344 trained Customs and Camcontrol Officers on ODS related issues including tracking of illegal imports of ODS (under Phase I, 30 selected officers with 23 Customs Officers and 7 Camcontrol Officers; and under Phase II, 314 trained officers with 238 Customs Officers and 76 Camcontrol Officers) | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: implementation support and monitoring | Individual | ASP | KAM | REF | 41 | TAS | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2006-12-01 | 2006-12-01 |  |  | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | As of September 2005, 238 technicians have been trained and after conducting training they found that approximately 40-50% of the ODS consumption have been reduced. Plan to phase out CFCs: 2006 (28.27), 2007 (14.13), 2008 (4.71), 2009 (.9), 2010 (0). As of December 2005, there were 391 technicians trained from this training programme. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 2 | Individual | ASP | KAM | SEV | 41 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 | 2006-12-01 |  |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. NOU submitted progress and expenditure reports. ODS Sub-Decree is expected to be adopted. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | KAM | SEV | 47 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 112667 | 0 | 112667 | 0 | 0% | 112667 | 0 | 112667 | 0 | 0 | 0 | 0 | 0 | Project newly approved in the 47th ExCom meeting in November 2005. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Support to a national workshop on refrigeration | Individual | AFR | KEN | REF | 10 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 2001-07-01 | 2001-07-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  |  | 14950 | 0 | 14950 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1993 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | KEN | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9392 | 15608 | 15608 | 100% | 0 |  |  | 3250 | -1221 | 2029 | 0 |  | Project financially completed. | $9392 plus $1221 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
ONG | UNEP | Policy and technical assistance | Individual | AFR | KEN | SEV | 37 | TAS | 29 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 | 2006-06-01 |  |  | 10000 | 0 | 10000 | 8000 | 80% | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 |  | Activities under the project are completed, the ODS regulations were developed and the final copy of the regulations was sent to the Attorney General's Office for gazettement. The CAP team facilitated communication between NOU, the Permanent Secretary for Environment and the Attorney General. The Kenya authorities assured that the ODS regulations will be gazzetted by July 2006 at the latest. The implementation and enforcement will start immediately after gazettement. The NOU is preparing an expenditure report that will submitted to UNEP by the end of May 2006. The final disbursement of funds under the project will be processed upon the receipt of the expenditure report and the project will be completed in June 2006. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | KIR | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 |  |  | 2600 | -910 | 1690 | 0 |  | Project financially completed. | $7000 plus $910 PSC returned ExCom 41 |  |  | 1999-10-01 | [6 empty] | 1995 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | KIR | SEV | 36 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 | 2006-06-01 |  |  | 23000 | 0 | 23000 | 13800 | 60% | 9200 | 0 | 9200 | 0 | 0 | 0 | 0 |  | Draft regulations prepared and reviewed in National Consultation Workshop which was conducted in May 2005. Currently plan to ban imports of CFCs under the “prohibited goods” of the Customs Act. However, the rest of the ODS regulations will await the approval of the Environment Bill by end of 2006. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | ASP | KUW | SEV | 30 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-06-01 |  | 2002-07-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Institutional strengthening and capacity building | Individual | ASP | KUW | SEV | 37 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-03-01 | 2005-08-01 | 2006-12-01 |  |  | 121520 | 0 | 121520 | 88131 | 72.52% | 33389 | 8000 | 33389 | 0 | 0 | 0 | 0 |  | Kuwait submitted their terminal report and requested for ISP renewal in September 2005, which was approved by ExCom in its 47th meeting. During 2005, Kuwait has taken significant steps to enforce its Licensing System and Quota System, and has tried to stop attempts of illegal trades. In response to Decision IV/7 Paragraph 7, Kuwait reported to the Ozone Secretariat about their seizer of eight attempts of illegal trades in ODS for the period 2004-2005. Kuwait organized in cooperation with CAP, training sessions for customs officers and refrigerant technicians. Overall, their national awareness of ODS was enhanced and information of new technologies and alternatives was disseminated. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers in monitoring of ODS | Individual | ASP | KUW | REF | 37 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2004-01-01 |  | 2004-12-01 |  | 53445 | 0 | 53445 | 53445 | 100% | 0 | 0 | 0 | 6947.85 | 0 | 6947.85 | 0 | 0 | Project completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme on good refrigerant management practices and hydrocarbon (HC) refrigerants safe handling | Individual | ASP | KUW | REF | 37 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-09-01 | 2004-08-01 | 2006-12-01 |  |  | 95325 | 0 | 95325 | 28218.99 | 29.6% | 67106.01 | 55701 | 67106.01 | 12392.25 | 0 | 3668.4687 | 8723.7813 | 7241 | Train the Trainers WS conducted in March 2005 for 30 Master Trainers, Phase II started immediately and 5 additional WS were organized during 2005 for around 125 technicians. Remaining WSs will be completed by end of 2006 with a possibility to shift the last two WSs till 1st Qrt. of 2007 to accommodate the academic calendar of the Training Institute. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | KUW | REF | 37 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2005-12-01 | 2005-08-01 | 2007-06-01 |  |  | 27000 | 0 | 27000 | 0 | 0% | 27000 | 0 | 0 | 3510 | 0 | 0 | 3510 | 0 | The project will start by the second half of 2006, there was difficulty in agreeing on the independent monitoring national group that will take the responsibility of monitoring and evaluating the RMP. The final short list includes Kuwait University, Society of Engineers and Kuwait ASHRAE Chapter. Kuwait NOU will take the final decision and inform UNEP to contract the selected entity by mid 2006 at latest. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | KUW | SEV | 47 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 105320 | 0 | 105320 | 0 | 0% | 105320 | 6859 | 105320 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
COM | UNEP | Implementation of the RMP: training for customs excise and personnel involved in the monitoring of ODS/equipment | Individual | EUR | KYR | REF | 37 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2005-06-01 |  | 74910 | 0 | 74910 | 66243.55 | 88.43% | 8666.45 | 8666 | 8666.45 | 9738.3 | 0 | 8611.6615 | 1126.6385 | 1126.58 | Phase 2 seminars continued as per workplan set up for 2005 and completed in July 2005. In total 114 persons have been trained in addition to 30 persons trained under Phase 1. 11 workshops have been delivered under this project. Some updates to the legislation were introduced - namely ban on export/import of ODS containing products. | [10 empty] | 2002 | Non Investment
COM | UNEP | Establishment of the Ozone Unit | Individual | EUR | KYR | SEV | 37 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-10-01 | 2005-08-01 |  | 2004-12-01 |  | 133650 | 0 | 133650 | 129002 | 96.52% | 4648 |  | 4648 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | EUR | KYR | REF | 37 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2003-08-01 |  | 2005-08-01 |  | 97900 | 0 | 97900 | 24008 | 24.52% | 73892 | 73892 | 73892 | 12727 | 0 | 3121.04 | 9605.96 | 9606 | Project completed in August 2005. Project activities completed as planned. Project completion report is drafted. To be submitted early 2006. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme | Individual | EUR | KYR | SEV | 37 | CPG | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2002-07-01 |  | 2002-07-01 | 2002-07-01 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | EUR | KYR | SEV | 44 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 | 2006-12-01 |  |  | 115830 | 0 | 115830 | 46000 | 39.71% | 69830 | 69830 | 69830 | 0 | 0 | 0 | 0 | 0 | MOU was signed. Two payments under MOU have been paid to NOU. Training activities are being completed. Preparatory work for development of TPMP is ongoing (UNEP/UNDP). | [10 empty] | 2004 | Non Investment
FIN | UNEP | Regional workshop for Latin America and the Caribbean | Individual | LAC | LAC | SEV | 04 | TRA | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-05-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 |  |  | 31980 | 0 | 31980 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
FIN | UNEP | Support to regional network for OzonAction/ODS focal points | Individual | LAC | LAC | SEV | 09 | TAS | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-03-01 | 2000-12-01 | 130000 | -9000 | 121000 | 121000 | 100% | 0 |  |  | 16900 | -1170 | 15730 | 0 |  | Project financially completed. | $9000 plus $1170 PSC returned ExCom 31 | [9 empty] | 1999 | Non Investment
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1994) | Individual | LAC | LAC | SEV | 12 | TAS | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-26 | 1995-03-01 |  | 1995-03-01 | 2000-12-01 | 224000 | -14500 | 209500 | 209500 | 100% | 0 |  |  | 29120 | -1885 | 27235 | 0 |  | Project financially completed. | $14500 plus $1885 PSC returned ExCom 31 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Regional workshop on non-CFC technologies for domestic refrigerator manufacturing industries | Individual | LAC | LAC | REF | 15 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-05-01 |  | 1995-05-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  |  | 13000 | 0 | 13000 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1995) | Individual | LAC | LAC | SEV | 16 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-05-01 | 1996-03-01 |  | 1995-08-01 | 2000-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 |  |  | 38870 | 0 | 38870 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on technology assessment in refrigeration | Individual | LAC | LAC | REF | 16 | TAS | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-01-01 | 1996-03-01 |  | 1999-05-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. |  |  |  | 1999-05-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-24 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 15600 | 0 | 15600 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for Latin America and Caribbean | Individual | LAC | LAC | SEV | 19 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-04-01 | 1999-04-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 |  |  | 13650 | 0 | 13650 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Networking and Training in Latin American Region Network (including English-speaking Caribbean) | Individual | LAC | LAC | SEV | 19 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299000 | -57167 | 241833 | 241833 | 100% | 0 |  |  | 38870 | -7431.71 | 31438.29 | 0 |  | Project financially completed. | $57167 plus $7432 PSC returned ExCom 30 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Latin American Region Network (1997) | Individual | LAC | LAC | SEV | 21 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 380000 | -38093 | 341907 | 341907 | 100% | 0 |  |  | 49400 | -4952.09 | 44447.91 | 0 |  | Project financially completed. | $38093 plus $4952 PSC returned ExCom 30 | [9 empty] | 1998 | Non Investment
FIN | UNEP | Latin America Region Networks for LAC South, LAC Central, and Caribbean (1998) | Individual | LAC | LAC | SEV | 23 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 399000 | -53324 | 345676 | 345676 | 100% | 0 |  |  | 51870 | -6932.12 | 44937.88 | 0 |  | Project financially completed. | $53,324 plus $6932 PSC returned ExCom 30 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for the Caribbean region | Individual | LAC | LAC | SEV | 23 | TRA | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-11-01 |  | 1998-06-01 | 1999-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 |  |  | 11050 | 0 | 11050 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Latin America Region Network (South America, Central America and the Caribbean) | Individual | LAC | LAC | SEV | 26 | TAS | 29 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-12-01 | 2000-12-01 | 399000 | -55099 | 343901 | 343901 | 100% | 0 |  |  | 51870 | -7162.87 | 44707.13 | 0 |  | Project financially completed. | $55099 plus $7163 PSC returned ExCom 37 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Regional training workshop on policy development | Individual | LAC | LAC | FUM | 27 | TRA | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-03-01 |  | 2000-04-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  |  | 16900 | 0 | 16900 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | LAC | LAC | FUM | 27 | TRA | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-12-03 | 80000 | -4000 | 76000 | 76000 | 100% | 0 |  | 0 | 10400 | -520 | 9880 | 0 |  | Project financially completed. | $4000 plus $520 PSC returned ExCom 43 | [9 empty] | 1999 | Non Investment
FIN | UNEP | Latin America and the Caribbean regional networks (South America, Central America, Caribbean) (2000) | Individual | LAC | LAC | SEV | 29 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 418950 | -30000 | 388950 | 388950 | 100% | 0 |  | 0 | 54463.5 | -3900 | 50563.5 | 0 |  | Project completed | $30000 plus 3900 returned ExCom 46 | [9 empty] | 1999 | Non Investment
CLO | UNEP | Development of regional halon banking management plan for the Latin American region (Dominican Republic, El Salvador, Chile, Colombia and Peru) | Individual | LAC | LAC | HAL | 29 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2001-06-01 |  |  | 2002-07-01 | 174000 | -174000 | 0 | 0 | 0% | 0 |  |  | 22620 | -22620 | 0 | 0 |  | Project was cancelled by 37th ExCom. | $174,000 plus $22620 PSC returned ExCom 38 | [9 empty] | 1997 | Non Investment
FIN | UNEP | South American, Central American and the Caribbean regional networks (2001) | Individual | LAC | LAC | SEV | 32 | TAS | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 429000 | -17257 | 411743 | 411743 | 100% | 0 |  |  | 55770 | -2243.41 | 53526.59 | 0 |  | Project financially completed. | $17257 plus $2243 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | LAO | SEV | 27 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-07-01 |  | 2001-07-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
COM | UNEP | Establishment of the Ozone Unit for implementing the phase-out of ODS under the Montreal Protocol | Individual | ASP | LAO | SEV | 34 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-08-01 |  | 66000 | 0 | 66000 | 57145 | 86.58% | 8855 | 0 | 8855 | 8580 | 0 | 7428.85 | 1151.15 |  | Project completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: Monitoring the activities contained in the RMP | Individual | ASP | LAO | REF | 34 | TAS | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-06-01 | 2003-08-01 | 2006-06-01 |  |  | 17500 | 0 | 17500 | 5000 | 28.57% | 12500 | 0 | 12500 | 2275 | 0 | 650 | 1625 |  | First Monitoring report was received on 31 September 2005. Mr. Liko Solangkan was hired as part time national consultant to continue the monitoring activities together with the NOU. The technicans training was started and the customs training is expected to start in early 2006. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | LAO | SEV | 43 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-07-01 |  |  | 57200 | 0 | 57200 | 0 | 0% | 57200 |  | 57200 | 0 | 0 | 0 | 0 |  | First progress report was received in September 2005; NOU of STEA together with the Asia Consultant Co Ltd inputs developed and produced the training materials in Lao Language, including refrigeration and MAC matters. 21 Lao relevant officials were trained under Phase I of the training programme. Procurement of 8 units of refrigeration equipment. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | LEB | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-28 | 1995-07-01 |  | 1996-05-01 | 1995-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | LES | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-05-25 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | LES | SEV | 20 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1999-10-01 |  | 1999-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. |  |  | 2000-03-01 | [7 empty] | 1996 | Non Investment
COM | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | LES | SEV | 29 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-12-01 |  | 2005-04-01 |  | 20000 | 0 | 20000 | 8343 | 41.72% | 11657 |  | 0 | 2600 | 0 | 1084.59 | 1515.41 |  | Project completed in April 2005. NOU conducted training of refrigeration technician and customs officers. The Country submitted ODS data in good time. NOU serviced a Joint Committee which is overseing implementation of TPMP. | [10 empty] | 1999 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LES | SEV | 45 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 26000 | 0 | 26000 | 0 | 0% | 26000 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | NOU conducted training of refrigeration technician and customs officers. Tne country celebrated national ozone day and submitted ODS data in good time. NOU serviced a Joint Committee which is overseing implementation of TPMP. The country implemented retrofit and drop-in programme for major cold rooms and chillers. | [10 empty] | 2005 | Non Investment
COM | UNEP | Country programme preparation | Individual | AFR | LIR | SEV | 27 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2000-07-01 |  | 2003-09-01 |  | 50000 | 0 | 50000 | 33000 | 66% | 17000 | 17000 | 17000 | 6500 | 0 | 4290 | 2210 |  | Project completed. | [7 empty] | 2003-12-01 |  |  | 1999 | Non Investment
ONG | UNEP | Establishment of the ozone unit | Individual | AFR | LIR | SEV | 41 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 | 2006-12-01 |  |  | 127820 | 0 | 127820 | 85790 | 67.12% | 42030 | 0 | 42030 | 0 | 0 | 0 | 0 |  | Implementation of IS activities were successfully done in 2005 in Liberia. The NOU established and commissioned for use a National Refrigeration Demonstration Center. Organized and implemented TOT workshop and several trainings for refrigeration and air-conditioning technicians. Conducted training of Custom Officers, printed and distributed the Liberia Customs Handbook to all Customs Officers trained. The country celebrated the International Ozone Day which was characterized by series of events including the Ozone day drama; launched and posted on UNEP website, 2006 calendar depicting activities of 2005 Ozone Day Celebration. NOU conducted awareness programmes which included the printing of posters, brochures and T-shirts, TV and Radio Programmes. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | LIR | REF | 41 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 | 2006-06-05 |  |  | 40040 | 0 | 40040 | 30015 | 74.96% | 10025 | 9389 | 10025 | 5205 | 0 | 3901.8001 | 1303.1999 | 1220.5231 | Country conducted phase two training of customs officer from 26 -28 June 2005 and 32 customs officers were trained. Country is implementing ODS regulations | [10 empty] | 2003 | Non Investment
COM | UNEP | Creation of a Ozone Unit | Individual | AFR | MAG | SEV | 29 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2004-07-01 |  | 70000 | 0 | 70000 | 70000 | 100% | 0 |  | 0 | 9100 | 0 | 9100 | 0 |  | Project completed. | [10 empty] | 1999 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MAG | SEV | 43 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2006-07-01 | 2006-07-01 |  |  | 60700 | 0 | 60700 | 47250 | 77.84% | 13450 |  | 13450 | 0 | 0 | 0 | 0 |  | NOU completed 1st phase RMP with France and coordinated the preparation of a RMP update with UNEP and France. Awareness activities included broadcast of information material in local languague on national TV and radio and celebration of Ozone Day. | [10 empty] | 2004 | Non Investment
COM | UNEP | Preparation of refrigerant management plan update | RMP update | AFR | MAG | REF | 44 | PRP | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2005-12-01 |  | 2005-06-01 |  | 20000 | 0 | 20000 | 20000.48 | 100% | -0.48 | 0 | -0.48 | 2600 | 0 | 2600.0624 | 0 | 0 | Project completed in June 2005. RMPU planned to be submitted at Excon47 | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training of customs officers and other officers to control and follow-up of ODS and its containers | Individual | AFR | MAG | REF | 47 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 22000 | 0 | 22000 | 0 | 0% | 22000 | 0 | 22000 | 2860 | 0 | 0 | 2860 | 1948.05 | MoU with the country established in December 2005. Request for First done in December 2005 and a survey on the distribution of customs officers and controllers in Madagascar done in October 2005. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP: training of maintenance technicians including small craftsmen of informal sector | Individual | AFR | MAG | REF | 47 | TRA | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 3250 | 0 | 0 | 3250 | 1948.05 | MoU with the country established in December 2005. Request for First done in December 2005 and training of trainers set for March 2006. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Support to a sub-regional workshop on halon and halon bank management | Individual | ASP | MAL | HAL | 09 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-01-01 | 1994-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Complement for country programme preparation | Individual | AFR | MAR | SEV | 09 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-06-01 |  | 1993-06-01 | 1993-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
COM | UNEP | Institutional strengthening for the phase-out of ozone depleting substances | Individual | AFR | MAR | SEV | 10 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-08-01 | 1996-06-01 |  | 2004-12-01 |  | 50000 | 0 | 50000 | 26535 | 53.07% | 23465 |  | 23465 | 6500 | 0 | 3449.55 | 3050.45 |  | Project completed |  |  |  | 1999-12-01 | [6 empty] | 1993 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | MAR | SEV | 45 | INS | 17 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | NOU produced several awareness materials including calenders, posters, caps, key holders, pens, T-shirts and distributed some during network meeting. Conducted awareness programmes on TV, radio stations, newspapers and visisted schools. Country implementing quota and licensing system effectively. Conducted customs officers trainings in enforcemnet of ODS regulations and refrigerations technicians in good refrigeration technicians.Country celebrated international ozone day | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MAS | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 |  | 0 | 5200 | -3250 | 1950 | 0 |  | Project completed | $25000 plus $3250 PSC returned ExCom 46 |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | MAS | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 | 2006-06-01 |  |  | 34000 | 0 | 34000 | 20400 | 60% | 13600 | 0 | 13600 | 0 | 0 | 0 | 0 |  | Training programme for Refrigeration technicians was conducted wherein a total of 20 technicians were trained. Training Programme for Customs Officers was conducted in April 2005 wherein 12 officers were trained. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme preparation | Individual | EUR | MAT | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-06-01 |  | 1995-07-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
COM | UNEP | Development of an RMP | Individual | AFR | MAU | REF | 33 | PRP | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2003-12-01 |  | 2003-12-01 |  | 60000 | 0 | 60000 | 21905.23 | 36.51% | 38094.77 | 5000 | 38094.77 | 7800 | 0 | 2847.6799 | 4952.3201 | 2742.35 | Project completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | MAU | SEV | 33 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2004-01-01 | 2003-04-01 |  | 2004-01-01 |  | 25900 | 0 | 25900 | 25849 | 99.8% | 51 |  | 0 | 3367 | 0 | 3360.37 | 6.63 |  | Project completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for customs excise | Individual | AFR | MAU | REF | 41 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 | 2006-12-01 |  |  | 39800 | 0 | 39800 | 38731.32 | 97.31% | 1068.68 | 906.68 | 1068.68 | 5174 | 0 | 5035.0716 | 138.9284 | 117.8684 | Equipment for the organization of phase 2 sent to the country in June 2005. A one day refresher training had been done in November 2006. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians | Individual | AFR | MAU | REF | 41 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2005-07-01 | 2006-12-01 |  |  | 65000 | 0 | 65000 | 23648.91 | 36.38% | 41351.09 | 39906.09 | 41351.09 | 8450 | 0 | 3074.3583 | 5375.6417 | 1948.05 | Equipment for the organization of phase 1 sent to the country in June 2005. Phase 1 set on 29 November 2005. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | MAU | REF | 41 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 29166.36 | 97.22% | 833.64 | 833.64 | 833.64 | 3900 | 0 | 3791.6268 | 108.3732 | 108.3732 | A survey has been done in November 2005 for data collection and the organization of the phase 2 trainings.He coordinated the organisation of the refrigeration training hed in Nouakchott in November 2005. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MAU | SEV | 43 | INS | 14 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 33670 | 0 | 33670 | 0 | 0% | 33670 |  | 33670 | 0 | 0 | 0 | 0 |  | Payment done in January 05 after activities report . The NOO coordinnated the organisation of the Refrigeration training held in November 2005 and did a planning for the training phase 2. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MDV | SEV | 04 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -5500 | 19500 | 19500 | 100% | 0 |  |  | 3250 | -715 | 2535 | 0 |  | Project financially completed. | $5500 plus $715 PSC returned ExCom 41 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | MDV | SEV | 12 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1997-03-01 |  | 2002-05-01 | 2005-12-01 | 41250 | 0 | 41250 | 41250 | 100% | 0 | 0 | 0 | 5362.5 | 0 | 5362.5 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Development of RMP | RMP | ASP | MDV | REF | 30 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-04-01 |  | 2002-09-01 | 2003-09-01 | 30000 | -1849 | 28151 | 28151 | 100% | 0 |  |  | 3900 | -240.37 | 3659.63 | 0 |  | Project financially completed. | $1849 plus $240 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | MDV | SEV | 37 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2004-08-01 |  | 2004-10-01 | 2005-12-01 | 35753 | 0 | 35753 | 35753 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project financially completed | [10 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: monitoring and review | Individual | ASP | MDV | REF | 38 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-08-01 |  | 15000 | 0 | 15000 | 1036 | 6.907% | 13964 | 0 | 13964 | 1950 | 0 | 134.68 | 1815.32 | 0 | Project completed in August 2005 and financially completed in November 2005. | [10 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MDV | REF | 38 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-07-01 |  | 35000 | 0 | 35000 | 33000 | 94.29% | 2000 | 0 | 2000 | 4550 | 0 | 4290 | 260 | 0 | Project completed in July 2005. Project financially completed in November 2005 | [10 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: training of customs officials and the Ozone Unit staff | Individual | ASP | MDV | REF | 38 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2005-05-01 |  | 2005-11-01 |  | 35000 | 0 | 35000 | 27972.84 | 79.92% | 7027.16 | 0 | 7027.16 | 4550 | 0 | 3636.4692 | 913.5308 | 0 | Project completed in November 2005. Project financially completed in November 05. May 2005: Final Phase II of the training programme was conducted. A total of 105 Customs Officers were trained under the Training programme for Customs Officers. Maldives Handbook on national regulations and Import Licensing System for the Phase out of Ozone Depleting Substances was prepared by the Environment Research Centre (ERC) was distributed to the participants during the final workshop. Sustainability: A Montreal Protocol related training module will be included in the ongoing training programme of the customs department for new customs officers. It will also be integrated in the refresher courses for experienced officers. Thus the sustainability of the training programme will be ensured. | [10 empty] | 2002 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | MDV | SEV | 44 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2005-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RMP Training programme completed for both Refrigeration technician in August 2005 and Customs Officers in November 2005. The LOA between Maldives and Sri Lanka has been signed on south-south cooperation issues and specifically on supply of CFCs to Maldives in 2006. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MLI | SEV | 19 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-05-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  |  | 5590 | 0 | 5590 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | MLI | REF | 24 | PRP | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Institutional strengthening project for Mali | Individual | AFR | MLI | SEV | 24 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Refrigerant management plan: Assistance in drafting ODS-related legislation | Individual | AFR | MLI | REF | 29 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-02 |  | 2002-07-01 | 2003-08-01 | 10980 | 0 | 10980 | 10980 | 100% | 0 |  |  | 1427.4 | 0 | 1427.4 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Training programme for customs officers | Individual | AFR | MLI | REF | 29 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-02 |  | 2003-12-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [5 empty] | 2003-03-03 |  |  |  |  | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Train the trainers programme in the refrigeration servicing sector | Individual | AFR | MLI | REF | 29 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-02 |  | 2002-05-01 | 2005-01-01 | 60000 | -18414 | 41586 | 41586 | 100% | 0 |  | 0 | 7800 | -2393.82 | 5406.18 | 0 |  | Project financially completed. | $18414 plus $2394 PSC returned ExCom 46 |  |  |  |  | 2002-12-02 |  |  |  |  | 1999 | Non Investment
COM | UNEP | Renewal of the institutional strengthening project | Individual | AFR | MLI | SEV | 35 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-03-01 |  | 46667 | 0 | 46667 | 34182 | 73.25% | 12485 |  | 12485 | 6066.71 | 0 | 4443.66 | 1623.05 |  | Project completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Preparation of the refrigerant management plan update | RMP update | AFR | MLI | REF | 43 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2005-07-01 |  | 2005-11-01 |  | 10000 | 0 | 10000 | 0 | 0% | 10000 | 10000 | 10000 | 1300 | 0 | 0 | 1300 | 1300 | Project completed in November 2005 | [10 empty] | 2004 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | MLI | SEV | 44 | INS | 15 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2004-04-04 | 2006-12-01 | 2006-12-01 |  |  | 60677 | 0 | 60677 | 24000 | 39.55% | 36677 | 36667 | 36677 | 0 | 0 | 0 | 0 | 0 | The NOO coordinated the organisation of the Refrigeration training in december 2005. During the year 2005, the NOO organised several meeting with the medias and some schools. He recenced the customs officer and technicians who are not yet trained in October 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP update: training programme for customs officers (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-10-01 | 2006-10-01 |  |  | 29546 | 0 | 29546 | 0 | 0% | 29546 | 29546 | 29546 | 3841 | 0 | 0 | 3841 | 1948.05 | First payment sent to the country in August 2005 for the organization of phase 1 training. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP update: training programme for refrigeration service technicians (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-10-01 | 2006-10-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 25000 | 25000 | 3250 | 0 | 0 | 3250 | 1948.05 | Contract country establised in July 2005. First payment done in August 2005. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | AFR | MLI | REF | 45 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 20000 | 2600 | 0 | 0 | 2600 | 1948.05 | MoU with the country signed in July 2005. First payment done in August 2005. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MLW | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-05-01 | 1993-05-01 |  | 1994-03-01 | 1994-12-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 |  |  | 3900 | -650 | 3250 | 0 |  | Project financially completed. | $5000 plus $650 PSC returned ExCom 41 | [9 empty] | 1991 | Non Investment
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | MLW | SEV | 12 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1997-03-01 |  | 1998-10-01 | 1999-10-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 |  |  | 10010 | 0 | 10010 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Request for renewal of institutional strengthening | Individual | AFR | MLW | SEV | 25 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-06-01 |  | 2000-12-01 | 2003-12-01 | 51350 | 0 | 51350 | 51350 | 100% | 0 |  |  | 6675.5 | 0 | 6675.5 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | MLW | FUM | 30 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9242 | 15758 | 15758 | 100% | 0 |  |  | 3250 | -1201.46 | 2048.54 | 0 |  | Project financially completed. | $9242 plus $1201 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | MLW | SEV | 31 | INS | 14 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-01-01 | 2005-12-01 | 51300 | 0 | 51300 | 51300 | 100% | 0 | 0 | 0 | 6669 | 0 | 6669 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | MLW | SEV | 41 | INS | 19 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2005-12-01 |  | 66733 | 0 | 66733 | 34894 | 52.29% | 31839 |  | 31839 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. NOU trained 102 customs officers on enforcing ODS regulations and confiscations and seisures of ODS and ODS based equipment taking place, About 40 regrigeration technicians were trained. NOU conducted awareness programmes including TV programmes, radio programmes, sms ODS messages on cellphones, press releases, stamping of letters with ODS messages, electying of billboards, calenders, posters, conference bags, caps, T-shirts and celebration of ozone day. NOU submited ODS data in time. Country completely phased out methyl bromide. Country organised a Joint UNEP, South Africa and Malawi mission to investigate on illegal importation of second hand fridges to Malawi | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | MLW | SEV | 47 | INS | 22 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 66733 | 0 | 66733 | 0 | 0% | 66733 | 0 | 66733 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | MOL | SEV | 25 | INS | 01 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2002-07-01 | 2004-05-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  |  | 10400 | 0 | 10400 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme for good practices in the refrigeration sector | Individual | EUR | MOL | REF | 25 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-09-01 | 1999-08-01 |  | 2003-12-01 | 2005-12-01 | 66000 | -11000 | 55000 | 55000 | 100% | 0 |  | 0 | 8580 | -1430 | 7150 | 0 |  | Project completed | $11000 plus $1430 PSC returned ExCom 46 |  |  |  | 2001-06-01 | [5 empty] | 1998 | Non Investment
COM | UNEP | Implementation of the refrigerant management plan: Training on monitoring and control of CFC and CFC using equipment | Individual | EUR | MOL | REF | 25 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2001-06-01 | 1999-08-01 |  | 2004-12-01 |  | 66550 | 0 | 66550 | 38000 | 57.1% | 28550 |  | 28550 | 8651.5 | 0 | 4940 | 3711.5 |  | Project completed |  |  |  |  | 2002-01-01 | [5 empty] | 1998 | Non Investment
FIN | UNEP | Country programme | Individual | EUR | MOL | SEV | 25 | CPG | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 1998-07-01 |  | 1998-07-01 | 1998-07-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [11 empty] | Non Investment
COM | UNEP | Renewal of institutional strengthening projects (Phase II) | Individual | EUR | MOL | SEV | 36 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2004-04-01 |  | 2004-07-01 |  | 69334 | 0 | 69334 | 64330 | 92.78% | 5004 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MOL | SEV | 43 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-03-01 |  |  | 69334 | 0 | 69334 | 30725 | 44.31% | 38609 |  | 38609 | 0 | 0 | 0 | 0 |  | NOU submitted their Progress Report for 2005. RMP Update have been officially launched on 23 May 2005, a book on UV radiation in Romanian was produced in April 2005, 2000 copies were distributed around Moldova. Flyers on ODS/non-ODS refrigerants, servicing equipment was printed and distributed to refrigeration technicians. Several articles in newspapers were published in national and local newspapers. Together with youth magazine Noi a competition was organized. It included questions on Ozone. A radio broadcast on Ozone was delivered in January and April 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | EUR | MOL | REF | 44 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 19885 | 0 | 19885 | 0 | 0% | 19885 | 19885 | 19885 | 2585 | 0 | 0 | 2585 | 2585 | MOU has been signed on 21 April 2005. The following activities have been monitored under this component during 2005: End-user project, MAC and R&R programme. CFC consumption and progress reports on individual components have been submitted to UNEP. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme formulation | Individual | ASP | MON | SEV | 20 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. |  |  |  | 1999-05-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | ASP | MON | SEV | 28 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-08-01 |  | 2002-08-01 | 2003-09-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Train the trainer programme for refrigeration service technicians | Individual | ASP | MON | REF | 32 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-03 |  | 2003-10-01 | 2005-01-01 | 65970 | -15415 | 50555 | 50546.91 | 99.98% | 8 | 1.1653e-12 | 0 | 8576.1 | -2003.95 | 6571.0983 | 1.0517 |  | Project financially completed in January 2005 | $1886 plus $245 PSC returned ExCom 44 $13529 plus $1759 PSC retuned ExCom 46 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | MON | REF | 32 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-03 |  | 2003-06-01 | 2003-06-01 | 77200 | -15003 | 62197 | 62197.12 | 100% | -0.12 | 0 | 0 | 10036 | -1950.39 | 8085.6256 | 0 |  | Project financially completed. | $5003 plus $650 PSC returned ExCom 44 $10000 plus $1300 returned ExCom 46 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | ASP | MON | SEV | 36 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | MON | SEV | 43 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 | 2006-07-01 |  |  | 57200 | 0 | 57200 | 24435 | 42.72% | 32765 | 0 | 32765 | 0 | 0 | 0 | 0 |  | Meeting of the Mongolia dialogue (Mongolia and China) was held in Bangkok in September 2005. National Stakeholders Consultation meeting for the Preparation of Terminal phase out Management Plan on Ozone Depleting Substances was conducted in 28 November 2005. The TPMP was prepared as a Japan Bilateral and approved in the 47th ExCom meeting in November 2005. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MOR | SEV | 19 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-05-01 |  | 1996-05-01 | 1996-05-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [11 empty] | Non Investment
COM | UNEP | Creation of Ozone Unit | Individual | AFR | MOR | SEV | 19 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1999-05-01 |  | 2004-07-01 |  | 179000 | 0 | 179000 | 174305 | 97.38% | 4695 |  | 4695 | 23270 | 0 | 22659.65 | 610.35 |  | Project completed |  |  | 1999-12-01 | [7 empty] | 1996 | Non Investment
ONG | UNEP | Preparation of a refrigerant management plan | RMP | AFR | MOR | REF | 27 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-04-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 21016 | 70.05% | 8984 | 8984 | 8984 | 3900 | 0 | 2732.08 | 1167.92 |  | Preparation of RMP could not be completed as CP update covers all counry requirements. Consultations are now underway for preparation of non-investment activities under a TPMP. | [10 empty] | 1999 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MOR | SEV | 43 | INS | 49 | N | T | I | CFC | 12.8 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2006-07-01 |  |  | 155000 | 0 | 155000 | 0 | 0% | 155000 |  | 155000 | 0 | 0 | 0 | 0 |  | NOU coordinating implementation of investment activities under CP update with UNIDO. NOU continued awarenss thruough dissemission of activities in schools. Enforcement of ODS regulation is done en cooperation with customs and trade departments through a well organised licensing system that allows tracking of authorisations for imports. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MOZ | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [11 empty] | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | MOZ | SEV | 15 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1997-12-01 |  | 2003-12-01 | 2005-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 |  | 0 | 12012 | 0 | 12012 | 0 |  | Project completed | [10 empty] | 1994 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | MOZ | SEV | 41 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-03-01 | 2005-12-01 | 2006-12-01 |  |  | 80080 | 0 | 80080 | 9061 | 11.31% | 71019 |  | 71019 | 0 | 0 | 0 | 0 |  | Country conducted a national survey on methyl bromide uses to establish sources for increased 2002 consumption. NOU produced awareness materials including posters, calenders, pamphlets, booklets and T-shirts. Country celebrated international ozone day. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MYA | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-09 | 1995-06-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. |  |  |  | 1999-05-01 | [6 empty] | 1994 | Non Investment
ONG | UNEP | Establishment of the national Ozone Cell for implementing the phase out of ODSs under the Montreal Protocol | Individual | ASP | MYA | SEV | 29 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 | 2006-12-01 |  |  | 76000 | 0 | 76000 | 0 | 0% | 76000 |  | 76000 | 9880 | 0 | 0 | 9880 |  | Due to restructuring, NCEA moved from Ministry of Foreign Affairs to Ministry of Forestry. Regional Director had a mission in May 2005 and met the Minister of Forestry for discussion of the projects to be implemented by UNEP. UNEP had a discussion of UNIDO after their mission in the country in September 2005. | [10 empty] | 1999 | Non Investment
COM | UNEP | Preparation of a refrigerant management plan | RMP | ASP | MYA | REF | 29 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2000-12-01 |  | 2005-04-01 |  | 30000 | 0 | 30000 | 5134.31 | 17.11% | 24865.69 | 0 | 24865.69 | 3900 | 0 | 667.4603 | 3232.5397 |  | Project completed in April 2005. Project financially completed | [10 empty] | 1999 | Non Investment
ONG | UNEP | Implementation of the RMP: preparation of ozone regulations for control of ODSs | Individual | ASP | MYA | REF | 45 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-11-01 | 2006-12-01 |  |  | 13000 | 0 | 13000 | 0 | 0% | 13000 | 0 | 13000 | 1690 | 0 | 0 | 1690 | 0 | MOU was prepared and sent to country for agreement on November 2005. Official letter was sent on November 2005 to the country signed by Regional Director for the same purpose of MOU signature. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring implementation of the RMP | Individual | ASP | MYA | REF | 45 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2008-04-01 | 2008-04-01 |  |  | 22000 | 0 | 22000 | 0 | 0% | 22000 | 0 | 22000 | 2860 | 0 | 0 | 2860 | 0 | RMP Implementation was approved in the 45th ExCom meeting in April 2005, 3 components were approved such as: 1) Preparation of ozone regulations for control of ODS; 2) Monitoring of RMP implementation; 3) Establishing conversion of practice of domestic refrigerators. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | NAM | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-04-01 | 1996-03-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | AFR | NAM | SEV | 18 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 2000-02-01 | 2001-12-12 | 61765 | 0 | 61765 | 61765 | 100% | 0 |  |  | 8029.45 | 0 | 8029.45 | 0 |  | Project financially completed. |  |  | 1998-11-01 | [7 empty] | 1995 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | NAM | SEV | 31 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 41177 | 0 | 41177 | 41177 | 100% | 0 |  |  | 5353.01 | 0 | 5353.01 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | NAM | SEV | 41 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-12-01 |  | 2005-12-01 |  | 53530 | 0 | 53530 | 52199 | 97.51% | 1331 | 1 | 1331 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. NOU implementing ODS regulations which became effective on 1st January, 2005. 2005. Trained 10 Customs Officers,.Produced awareness materials including posters, bookltes, calenders, newsletters and distributed to schools, and general public. Conducted awareness programmes on the radio, TV and during trade fair. Serviced the National Ozone Committee meetings and the NOU celebrated international ozone day. Country submitted ODS consumption data in time | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | NAM | SEV | 47 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NAU | REF | 44 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 8000 | 0 | 8000 | 0 | 0% | 8000 | 0 | 8000 | 1040 | 0 | 0 | 1040 |  | Model ODS regulations provided to the country. Main work to start in 2006. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NAU | SEV | 44 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 |  | National Compliance Centre discussed and finalized. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NAU | REF | 44 | TAS | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 14000 | 0 | 14000 | 0 | 0% | 14000 | 0 | 14000 | 1820 | 0 | 0 | 1820 |  | Training programme schedules were finalized and planned to conduct in May 2006. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | NEP | SEV | 19 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | ASP | NEP | REF | 24 | PRP | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-06-01 | 2000-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Establishment of an Ozone Unit | Individual | ASP | NEP | SEV | 26 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-10 | 2001-12-01 |  | 2002-05-01 | 2003-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 |  |  | 8060 | 0 | 8060 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Refrigerant management plan: policy development and related information dissemination | Individual | ASP | NEP | REF | 28 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-08-03 |  | 2001-12-01 | 2002-10-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 |  |  | 780 | 0 | 780 | 0 |  | Project financially completed. | [5 empty] | 2001-12-01 |  |  |  |  | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: training of trainers in refrigeration | Individual | ASP | NEP | REF | 28 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-02-03 |  | 2004-03-01 | 2004-10-01 | 70000 | -29000 | 41000 | 41000 | 100% | 0 |  | 0 | 9100 | -3770 | 5330 | 0 |  | Project financially completed. | $29000 plus $3770 PSC returned Excom 46 | [9 empty] | 1999 | Non Investment
COM | UNEP | Refrigerant management plan: training in monitoring and control of CFC and establishment of import/export licensing system | Individual | ASP | NEP | REF | 28 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2001-08-02 |  | 2004-07-01 |  | 44400 | 0 | 44400 | 25000 | 56.31% | 19400 |  | 19400 | 5772 | 0 | 3250 | 2522 |  | Project completed in February 2005 | [5 empty] | 2002-12-02 |  |  |  |  | 1999 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | NEP | SEV | 37 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-08-01 |  | 53733 | 0 | 53733 | 49458 | 92.04% | 4275 |  | 4275 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | NEP | SEV | 44 | INS | 14 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The action plan for compliance was prepared and reviewed during the first Informal Advisory Group meeting on compliance in Beijing in April 2005. It was approved in 16th MOP and the country was declared in compliance. Network Meeting for South Asia was hosted by Government of Nepal in October 2005. Training materials for Customs officers was published in Nepali local language. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: assistance to remain in compliance with the Montreal Protocol | Individual | ASP | NEP | REF | 44 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2007-12-01 | 2007-12-01 |  |  | 51440 | 0 | 51440 | 51331 | 99.79% | 109 | 0 | 109 | 6687.2002 | 0 | 6673.0302 | 14.17 | 0 | MOU was signed on April 2005 The first disbursement was transferred on May 2005 CAP went for a mission in June 2005 for further discussion on this project implementation with the NOU, trainers for Refrigeration technicians, meeting with the Secretary of Environment was held to introduce the project. Nov05-10 identifiers delivered to the country. Training materials for the training programme were published in Nepali in training more customs officers and other border security personnel. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Technical assistance in CTC management | Individual | ASP | NEP | SOL | 47 | TAS | 17 | A | O | I | CTC | 0.9 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | Project newly approved in the 47th ExCom meeting in November 2005. The budget and workplan was agreed with country and initial disbursement was released. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | NER | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1994-12-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  |  | 5590 | 0 | 5590 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Creation of an Ozone Secretariat | Individual | AFR | NER | SEV | 15 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1997-12-01 |  | 1999-05-01 | 1999-10-01 | 74800 | 0 | 74800 | 74800 | 100% | 0 |  |  | 9724 | 0 | 9724 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | NER | SEV | 26 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-28 | 2000-12-01 |  | 2001-06-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the RMP: Customs officers training programme | Individual | AFR | NER | REF | 27 | TAS | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-08-01 | 2000-10-02 |  | 2003-12-01 | 2005-02-01 | 63000 | -24000 | 39000 | 39000 | 100% | 0 |  | 0 | 8190 | -3120 | 5070 | 0 |  | Project financially completed. | $24000 plus $3120 PSC returned Excom 46 | [9 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Train the trainers programme in the refrigeration sector | Individual | AFR | NER | REF | 27 | TAS | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-10-02 |  | 2002-05-01 | 2003-05-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 |  |  | 5395 | 0 | 5395 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | NER | SEV | 33 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Policy and technical assistance | Individual | AFR | NER | SEV | 37 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2003-08-01 |  | 2004-01-01 |  | 10000 | 0 | 10000 | 8005 | 80.05% | 1995 | 1995 | 1995 | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | NER | SEV | 41 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 |  | 64827 | 0 | 64827 | 49396 | 76.2% | 15431 |  | 15431 | 0 | 0 | 0 | 0 |  | Last payments incurred in 2005 to be reported. Completed 2005 activities, report on IS and RMPU . | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP update: training for customs technicians | Individual | AFR | NER | REF | 42 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 25000 | 25000 | 3250 | 0 | 0 | 3250 | 1948.05 | Equipment sent to the country in May 2005 and phase 2 training started in June 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP update: train the trainer programme for refrigeration service technicians | Individual | AFR | NER | REF | 42 | TRA | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-10-01 | 2006-12-01 |  |  | 55747 | 0 | 55747 | 11221.23 | 20.13% | 44525.77 | 43000 | 44525.77 | 7247 | 0 | 1458.7378 | 5788.2622 | 1948.05 | Equipment sent to the country in May 2005 and phase 2 training stared in June 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP update: monitoring of the activities | Individual | AFR | NER | REF | 42 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 23000 | 0 | 23000 | 0 | 0% | 23000 | 23000 | 23000 | 2990 | 0 | 0 | 2990 | 1948.05 | Data collection done in October 2005 and regular visits to Recovery & Recycling done between March to June 2005 .The NOO coordinated the implementation of the RMPU and provided report on the refrigeration training and Customs training held in January, May and June 2005 | [10 empty] | 2004 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NER | SEV | 47 | INS | 16 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 64827 | 0 | 64827 | 0 | 0% | 64827 | 0 | 64827 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | NIC | SEV | 13 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-22 | 1995-10-01 |  | 1996-11-01 | 1999-03-01 | 40000 | -3825 | 36175 | 36175 | 100% | 0 |  |  | 5200 | -497.25 | 4702.75 | 0 |  | Project financially completed. | $3825 plus $497 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | NIC | SEV | 22 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2002-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 |  |  | 8580 | 0 | 8580 | 0 |  | Project financially completed. |  |  |  | 2000-05-01 | [6 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | NIC | SEV | 31 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2002-08-01 |  | 2003-09-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 |  |  | 5720 | 0 | 5720 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | NIC | SEV | 39 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-10-01 | 2005-04-01 | 2006-04-01 |  |  | 57200 | 0 | 57200 | 44007 | 76.94% | 13193 |  | 13193 | 0 | 0 | 0 | 0 |  | Audit Report indicated that control problems or improper fund management were not detected. Two cash advances corresponding to ISP (III) sent to the country during the2005 year. NOO attended ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. ODS license system working properly. Public awareness activities focused to school children. | [10 empty] | 2003 | Non Investment
COM | UNEP | Preparation of the RMP update proposal | RMP update | LAC | NIC | REF | 41 | PRP | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2004-12-01 |  | 2005-02-01 |  | 15000 | 0 | 15000 | 14100 | 94% | 900 | 900 | 900 | 1950 | 0 | 1833 | 117 | 117 | Project completed in February 2005. RMPU approved. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP update: licensing and certification system for refrigeration technicians | Individual | LAC | NIC | REF | 45 | TRA | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2008-04-01 | 2008-04-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP update: programme for prevention of illegal CFC trade | Individual | LAC | NIC | REF | 45 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2008-04-01 | 2008-04-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 1950 | 0 | 0 | 1950 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP update: monitoring the activities of the RMP | Individual | LAC | NIC | REF | 45 | TAS | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2008-04-01 | 2008-04-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | NIR | FUM | 34 | TAS | 90 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -16990 | 8010 | 8010 | 100% | 0 |  |  | 3250 | -2208.7 | 1041.3 | 0 |  | Project financially completed. | $16990 plus $2209 PSC returned ExCom 44 | [9 empty] | 2001 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NIU | SEV | 44 | INS | 01 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-06-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 |  | Established National Compliance Centre in September 2005 under Department of Environment. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NIU | REF | 44 | TAS | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 14000 | 0 | 14000 | 0 | 0% | 14000 | 0 | 14000 | 1820 | 0 | 0 | 1820 |  | Training programme schedules were finalized | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NIU | REF | 44 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 8000 | 0 | 8000 | 0 | 0% | 8000 | 0 | 8000 | 1040 | 0 | 0 | 1040 |  | Model ODS regulations provided to the country. Now in process of drafting regulation and licensing system. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Policy and technical assistance | Individual | ASP | OMA | SEV | 37 | TAS | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 | 2006-03-01 |  |  | 10000 | 0 | 10000 | 5000 | 50% | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 |  | Project completed in March 2006. Country enacted their ODS legislation under Ministerial Decision 243/2005 in October 2005. NOU in cooperation with CAP organized a one-day meeting for main stakeholders on 7/2/2006 in Muscat to introduce the new legislation and discussed means of its enforcement to secure commitment from them for implementation of the same. Accordingly UNEP transferred the final payment ($5000.00) on 01/03/2006 and received confirmation from the bank that the amount was transferred on 06 March 2006. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | PAK | SEV | 09 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1996-06-01 | 1996-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  |  | 7800 | 0 | 7800 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PAN | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | -3000 | 27000 | 27000 | 100% | 0 |  |  | 3900 | -390 | 3510 | 0 |  | Project financially completed. | $6000 plus $780 PSC returned ExCom 41 ($3000 plus $390 PSC added ExCom 11) | [9 empty] | 1992 | Non Investment
FIN | UNEP | Institutional strengthening: Establishment of COGO | Individual | LAC | PAN | SEV | 10 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-04-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  |  | 22425 | 0 | 22425 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1993 | Non Investment
FIN | UNEP | Development of refrigerant management plans | RMP | LAC | PAN | REF | 24 | PRP | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
ONG | UNEP | Refrigerant management plan: Training and certification programme in refrigeration | Individual | LAC | PAN | REF | 29 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 | 2006-12-01 |  |  | 126200 | 0 | 126200 | 50000 | 39.62% | 76200 |  | 76200 | 16406 | 0 | 6500 | 9906 |  | Equipment purchased in May-05. Plan of Action submitted in Dec-05 by monitoring consultant for project completion in 2006 | [10 empty] | 1999 | Non Investment
ONG | UNEP | Refrigerant management plan: Monitoring on assistance to develop legislation | Individual | LAC | PAN | REF | 29 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2002-12-01 | 2006-12-01 |  |  | 10000 | 0 | 10000 | 6000 | 60% | 4000 |  | 4000 | 1300 | 0 | 780 | 520 |  | SSA prepared with local consultant. Two progress reports with action plans for completion of RMP have been submitted as of Dec-05. Last dibursement to be processed upon completion of RMP in 2006. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PAN | SEV | 31 | INS | 15 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2002-08-01 |  | 2002-12-01 | 2004-10-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  |  | 14950 | 0 | 14950 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Renewal of institutional strengthening (phase 3) | Individual | LAC | PAN | SEV | 38 | INS | 17 | N | T | I | CFC | 12.35 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 | 2006-12-01 |  |  | 149500 | 0 | 149500 | 36396 | 24.35% | 113104 |  | 113104 | 0 | 0 | 0 | 0 |  | Last cash advance released in July 2005. Disbursements were stopped until audit report be sent by Gov. NOU attended ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. ODS license system working properly and inspections conducted at ODS importers and suppliers' store and distribution sites. Launching of the TPMP jointly organized by NOU, UNDP and UNEP. Additional public awareness activities were focused on the effects of ozone depletion on human health and UV-B radiation. This included mass media, TV, brochure and public education campaigns. | [10 empty] | 2002 | Non Investment
COM | UNEP | Project preparation for refrigerant management plan update | RMP update | LAC | PAN | REF | 40 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-03-01 | 2004-07-01 |  | 2004-10-01 |  | 15000 | 0 | 15000 | 13375 | 89.17% | 1625 | 0 | 1625 | 1950 | 0 | 1738.75 | 211.25 | 0 | Project completed. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAN | SEV | 44 | INS | 21 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 |  |  | 149500 | 0 | 149500 | 0 | 0% | 149500 | 0 | 149500 | 0 | 0 | 0 | 0 | 0 | Project has not started due to the existence of funds remaining from Phase III. | [10 empty] | 2004 | Non Investment
ONG | UNEP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2007-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 900 | 25000 | 3250 | 0 | 0 | 3250 | 117 | Customs officers and focal points have been changed three times during 2005, last one being in Nov-05. MOU resent in Dec-05 for the consideration of new focal point within the Customs Autority. | [10 empty] | 2004 | Non Investment
ONG | UNEP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-year | LAC | PAN | PHA | 47 | TRA | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 1950 | 0 | 0 | 1950 |  | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PAR | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-10-01 |  | 1996-10-01 | 1999-05-01 | 43000 | -4000 | 39000 | 39000 | 100% | 0 |  |  | 5590 | -520 | 5070 | 0 |  | Project financially completed. | $4000 plus $520 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | LAC | PAR | SEV | 21 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 2000-02-01 |  | 2001-07-01 | 2001-12-01 | 66300 | 0 | 66300 | 66300 | 100% | 0 |  |  | 8619 | 0 | 8619 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
ONG | UNEP | Implementation of the RMP: Monitoring and control of ODS and ODS based equipment, and training of customs officers and other inspection officers | Individual | LAC | PAR | REF | 32 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2001-12-03 | 2006-12-01 |  |  | 44920 | 0 | 44920 | 20804.86 | 46.32% | 24115.14 | 3984 | 24115.14 | 5839.6 | 0 | 2704.6318 | 3134.9682 |  | Disbursement modalities for all projects in Paraguay have been agreed with local UNDP and Ministry, following audit recommendations. Internal restructuring for implementation of MP activities are taking place as of Dec-05 | [5 empty] | 2003-06-03 |  |  |  |  | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: Train of trainers and training of refrigeration service technicians | Individual | LAC | PAR | REF | 32 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-12-03 | 2006-12-01 |  |  | 168020 | 0 | 168020 | 48340.31 | 28.77% | 119679.69 | 80094.69 | 119679.69 | 21842.6 | 0 | 6284.2403 | 15558.3597 | 10525.84 | Disbursement modalities for all projects in Paraguay have been agreed with local UNDP and Ministry, following audit recommendations. Internal restructuring for implementation of MP activities are taking place as of Dec-05 | [10 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | PAR | SEV | 32 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-01-01 | 2004-09-01 | 44200 | 0 | 44200 | 44200 | 100% | 0 |  |  | 5746 | 0 | 5746 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Implementation of the RMP: Policy dialogue programme on complementary policy and enforcement | Individual | LAC | PAR | REF | 32 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2001-09-02 | 2006-12-01 |  |  | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Disbursement modalities for all projects in Paraguay have been agreed with local UNDP and Ministry, following audit recommendations. Internal restructuring for implementation of MP activities are taking place as of Dec-06 | [10 empty] | 2000 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | PAR | SEV | 39 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2005-04-01 | 2007-03-01 |  |  | 57460 | 0 | 57460 | 601 | 1.046% | 56859 |  | 56859 | 0 | 0 | 0 | 0 |  | Disbursements resumed due to Progress and Financial Reports were received and administrative measures were installed. 2005 Audit Report was required. NOU attended ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PER | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1995-07-01 | 1995-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 |  |  | 6890 | 0 | 6890 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | PER | SEV | 17 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1998-10-01 |  | 2000-08-01 | 2001-08-01 | 154000 | 0 | 154000 | 154000 | 100% | 0 |  |  | 20020 | 0 | 20020 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | PER | REF | 21 | TRA | 21 | A | O | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2002-12-01 | 2003-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the RMP: Custom officers training programme | Individual | LAC | PER | REF | 27 | TRA | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2004-05-04 | 2005-12-01 | 34000 | -13000 | 21000 | 21000 | 100% | 0 |  | 0 | 4420 | -1690 | 2730 | 0 |  | Project completed. | $13000 plus $1690 PSC returned Excom 46 |  |  |  | 2001-12-01 | [5 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Support for a licensing system | Individual | LAC | PER | REF | 27 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-02 |  | 2002-02-01 | 2003-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Code of good practices in refrigeration | Individual | LAC | PER | REF | 27 | TAS | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2002-02-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
COM | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PER | SEV | 29 | INS | 27 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2002-06-01 |  | 102700 | 0 | 102700 | 57990 | 56.47% | 44710 |  | 44710 | 13351 | 0 | 7538.7 | 5812.3 |  | Project completed. | [10 empty] | 1999 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | PER | SEV | 37 | INS | 31 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2004-08-01 | 2007-01-01 |  |  | 133510 | 0 | 133510 | 0 | 0% | 133510 | 0 | 133510 | 0 | 0 | 0 | 0 | 0 | Disbursements resumed due to Progress and Financial Reports were received. Audit Report is still pending. NOU attended ODS Officers Network Meetings. Data collection, analysis and reporting to both Secretaries accomplished on time by NOU. ODS license system working properly | [10 empty] | 2002 | Non Investment
COM | UNEP | Preparation of the refrigerant management plan update proposal | RMP Update | LAC | PER | REF | 37 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-02-01 | 2003-08-01 |  | 2004-07-01 |  | 15000 | 0 | 15000 | 7000 | 46.67% | 8000 | 6625 | 6625 | 0 | 0 | 0 | 0 | 0 | Project completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | LAC | PER | REF | 43 | TAS | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2007-12-01 | 2007-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 5200 | 0 | 0 | 5200 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP update: refrigeration technicians certification and licensing system | Individual | LAC | PER | REF | 43 | TAS | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2007-12-01 | 2007-12-01 |  |  | 86000 | 0 | 86000 | 0 | 0% | 86000 | 0 | 86000 | 11180 | 0 | 0 | 11180 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP update: technical assistance for prevention of illegal CFC trade | Individual | LAC | PER | REF | 43 | TAS | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2007-12-01 | 2007-12-01 |  |  | 26000 | 0 | 26000 | 0 | 0% | 26000 | 0 | 26000 | 3380 | 0 | 0 | 3380 | 0 | Work plan and preparatory arrangements for involved stakeholder project implementation were agreed with NOO. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Information exchange programme | Individual | ASP | PHI | SEV | 11 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1995-12-01 |  | 2000-12-01 | 2003-07-01 | 200000 | -1488 | 198512 | 198512 | 100% | 0 |  |  | 26000 | -193.44 | 25806.56 | 0 |  | Project financially completed. | $1488 plus $193 PSC returned ExCom 41 | [9 empty] | 1993 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | ASP | PHI | FUM | 30 | TAS | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -8880 | 16120 | 16120 | 100% | 0 |  |  | 3250 | -1154 | 2096 | 0 |  | Project financially completed. | $8880 plus $1154 PSC returned ExCom 43 | [9 empty] | 2000 | Non Investment
COM | UNEP | Training programme for customs officials and other key stakeholders | Individual | ASP | PHI | REF | 35 | TRA | 66 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2005-12-01 |  | 170250 | 0 | 170250 | 166149.72 | 97.59% | 4100.28 | 512.24 | 4100.28 | 22132.5 | 0 | 21599.4636 | 533.0364 |  | Project completed in December 2005 | [10 empty] | 2001 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | PNG | SEV | 13 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-02-14 | 1995-10-01 |  | 1996-05-01 | 1999-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
COM | UNEP | Creation of an Ozone Unit | Individual | ASP | PNG | SEV | 19 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1999-05-01 |  | 2003-12-01 |  | 45800 | 0 | 45800 | 21085 | 46.04% | 24715 |  | 24715 | 5954 | 0 | 2741.05 | 3212.95 |  | Project completed |  |  |  | 1999-05-01 | [6 empty] | 1996 | Non Investment
TRF | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | PNG | REF | 21 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 |  | 1997-09-01 |  |  | 1998-07-01 | 30000 | -30000 | 0 | 0 | 0% | 0 |  |  | 3900 | -3900 | 0 | 0 |  | Project transferred | $30000 plus $3900 PSC returned ExCom 25 |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | PRC | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  | 1995-07-01 | 1996-07-01 | 0 | 0 | 0 | 0 | 0% | 0 |  |  | 0 | 0 |  | 0 |  | Project financially completed. | [11 empty] | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | PRC | SEV | 17 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 2000-12-01 | 2001-12-12 | 62920 | 0 | 62920 | 62920 | 100% | 0 |  |  | 8179.6 | 0 | 8179.6 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | PRC | REF | 27 | PRP | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-12 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | PRC | SEV | 32 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 41950 | 0 | 41950 | 41950 | 100% | 0 |  |  | 5453.5 | 0 | 5453.5 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Assistance for information-sharing | Individual | AFR | PRC | REF | 32 | TAS | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-01-02 |  | 2003-12-01 | 2005-02-01 | 16000 | -2967 | 13033 | 13032.55 | 100% | 0.45 | 0 | 0 | 2080 | -385.71 | 1694.2315 | 0.0585 |  | Project financially completed. | $2967 plus 386 returned ExCom 46 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Customs training programme | Individual | AFR | PRC | REF | 32 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-12-01 |  | 2003-12-01 | 2005-01-01 | 69400 | -25378 | 44022 | 44021.75 | 100% | 0.25 | 0 | 0 | 9022 | -3299.14 | 5722.8275 | 0.0325 |  | Project financially completed. | $25378 plus $3299 returned ExCom 46 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | PRC | SEV | 39 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2005-12-01 | 54531 | 0 | 54531 | 54531 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed in April 2005. The NOU coordinated implementation of activities under RMP update and regional MeBr project with UNDP. NOU also organised awareness activities through the local media and organized conferences the university and in secondary schools. Kits for good practices were distributed to refrigeration technicians. As an expert in atmospheric science, the ODS Officer of Congo has been providing usefull information on the ozone Layer to fellllow officers in the region. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extensionl of the institutional strengthening project (phase IV) | Individual | AFR | PRC | SEV | 45 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
COM | UNEP | Formulation of national phase out strategy | Individual | AFR | RWA | SEV | 35 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 |  | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 6500 | -4550 | 1950 | 0 |  | Project completed. | $35000 plus $4550 returned ExCom 46 | [9 empty] | 2001 | Non Investment
COM | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2003-04-01 |  | 2005-01-01 |  | 22000 | 0 | 22000 | 7982 | 36.28% | 14018 | 0 | 14018 | 0 | 0 | 0 | 0 |  | Project completed in January 2005 | [10 empty] | 2002 | Non Investment
ONG | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 41 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 64600 | 0 | 64600 | 0 | 0% | 64600 | 0 | 64600 | 0 | 0 | 0 | 0 |  | The NOU coordinated implementation of CP/RMP activities with UNEP and UNDP. Equipment were purchased and planning done for start of training programme. ODS regulation were adopted and arrangement are made to raise awareness of stakeholders on the said regulations. Celebrations were done for the international Ozone Day. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | AFR | RWA | REF | 41 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 | 2006-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 49461 | 50000 | 6500 | 0 | 0 | 6500 | 1948.05 | Request of payment for the organisation of Phase 1 done in November 2005 , phase 1 held in February 06-09 ,2006. 27 technicians were trained and report provided by the NOO on the training programme. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | RWA | REF | 41 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 | 2006-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 49482 | 50000 | 6500 | 0 | 0 | 6500 | 1948.05 | Phase 1 done in November 2005 and second payment for the organization of phase 2 done in December 2005. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | RWA | REF | 41 | TAS | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 20000 | 2600 | 0 | 0 | 2600 | 1948.05 | Data collection has been done in October 2005 and awareness activities throught the media are ongoing. After phases 1 training, the NOO assessed the need of training for Customs officers and technicians in refrigeration and scheduled the phases 2 trainings. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | SAM | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-18 | 1995-06-01 |  | 1997-05-01 | 1999-02-01 | 35000 | -4850 | 30150 | 30150 | 100% | 0 |  |  | 4550 | -630.5 | 3919.5 | 0 |  | Project financially completed. | $4850 plus $631 PSC returned ExCom 30 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Establishment of the National Ozone Committee | Individual | ASP | SAM | SEV | 22 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-04-01 | 2000-06-01 |  | 2003-04-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the RMP: Training of customs officials and NOU staff | Individual | ASP | SAM | REF | 32 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-06-03 |  | 2003-09-01 | 2003-12-01 | 53500 | -9474 | 44026 | 44026 | 100% | 0 | 0 |  | 6955 | -1232 | 5723 | 0 |  | Project financially completed. | $9474 plus $1232 PSC returned ExCom 43 |  |  |  |  | 2003-06-03 |  |  |  |  | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Training of refrigeration service technicians | Individual | ASP | SAM | REF | 32 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-02-02 |  | 2002-10-01 | 2003-10-01 | 48800 | -5864 | 42936 | 42936 | 100% | 0 | 0 |  | 6344 | -762.32 | 5581.68 | 0 |  | Project financially completed. | $5864 plus $762 PSC returned ExCom 41 |  |  |  |  | 2002-12-02 |  |  |  |  | 2000 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | SAM | SEV | 25 | PRP | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1997-05-01 | 2000-12-01 |  | 2000-12-01 | 2002-06-01 | 0 | 30000 | 30000 | 30000 | 100% | 0 |  |  | 0 | 3900 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase 2) | Individual | ASP | SAM | SEV | 39 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2005-04-01 | 2006-12-01 |  |  | 26000 | 0 | 26000 | 17971 | 69.12% | 8029 |  | 8029 | 0 | 0 | 0 | 0 |  | The IS renewal was deferred twice due to delay in establishing the ODS regulation. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | SAM | SEV | 47 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved in the 47th ExCom meeting in November 2005. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SEN | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1993-11-01 | 1993-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  |  | 1690 | 0 | 1690 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Ozone Focal Point | Individual | AFR | SEN | SEV | 11 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1996-11-01 |  | 1997-12-01 | 1999-09-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 |  |  | 22750 | 0 | 22750 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Expansion and upgrading of statistics networks for customs | Individual | AFR | SEN | SEV | 11 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1994-10-01 | 1994-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 |  |  | 3380 | 0 | 3380 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Training and upgrading for repair technicians | Individual | AFR | SEN | REF | 11 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-11-01 |  | 1994-12-01 | 1995-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 |  |  | 7540 | 0 | 7540 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEN | SEV | 23 | INS | 09 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-02-01 | 2000-02-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 |  |  | 15210 | 0 | 15210 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | SEN | REF | 24 | PRP | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 2000-12-01 | 2001-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEN | SEV | 29 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-12-01 |  | 2001-12-01 | 2003-12-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 |  |  | 15210 | 0 | 15210 | 0 |  | Project financially completed. | [10 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Activities for supporting and monitoring the RMP | Individual | AFR | SEN | REF | 33 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-07-01 | 2003-12-01 |  | 2002-05-01 | 2003-06-01 | 44500 | -37 | 44463 | 44463 | 100% | 0 | 0 |  | 5785 | -4.81 | 5780.19 | 0 |  | Project financially completed. | $37 plus $5 PSC returned ExCom 41 | [9 empty] | 2001 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | SEN | FUM | 34 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -9000 | 16000 | 16000 | 100% | 0 |  |  | 3250 | -1170 | 2080 | 0 |  | Project financially completed. | $9000 plus $1170 PSC returned ExCom 44 | [9 empty] | 2001 | Non Investment
FIN | UNEP | Renewal of institutional strengthening projects (Phase IV) | Individual | AFR | SEN | SEV | 36 | INS | 18 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 5 | Individual | AFR | SEN | SEV | 41 | INS | 19 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 |  | 152100 | 0 | 152100 | 127976 | 84.14% | 24124 |  | 24124 | 0 | 0 | 0 | 0 |  | Project completed in Decemer 2005. The NOO provided activities report in November 2005. He coordinated data collection in October 2005.The NOO was involved in the organisation of the Exom 47 and meeting of Parties organised in Dakar | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | SEN | SEV | 47 | INS | 20 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 152100 | 0 | 152100 | 0 | 0% | 152100 | 0 | 152100 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SEY | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1994-07-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | SEY | SEV | 13 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-03-01 | 1997-07-01 |  | 2000-07-01 | 2000-07-01 | 31900 | 0 | 31900 | 31900 | 100% | 0 |  |  | 4147 | 0 | 4147 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEY | SEV | 31 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2002-08-01 |  | 2004-12-01 | 2005-12-01 | 21267 | 0 | 21267 | 21267 | 100% | 0 |  | 0 | 2764.71 | 0 | 2764.71 | 0 |  | Project financially complleted. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SEY | SEV | 44 | INS | 10 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | NOU conducted training of refrigeration technicians including new recruits in good refrigeration practices and all trained technicians issued with certificate for them to practicer. Country is implementing quota and licensing system successfully. NOU disseminated awareness information through national radio, television, newspapers and organised school talks. NOU conducted trainings for customs officers including new recruits. Country submitted ODS data in time. | [10 empty] | 2004 | Non Investment
COM | UNEP | Formulation of national phase out strategy | Individual | AFR | SIL | SEV | 35 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-08-01 |  | 2003-12-01 |  | 40000 | 0 | 40000 | 15000 | 37.5% | 25000 | 0 | 25000 | 5200 | 0 | 1950 | 3250 | 3250 | Project completed. | [10 empty] | 2001 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SIL | SEV | 36 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2003-12-03 | 2004-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project financially completed. | [10 empty] | 2002 | Non Investment
COM | UNEP | Establishment of the Ozone Unit | Individual | AFR | SIL | SEV | 41 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-02-01 | 2005-12-01 |  | 2005-12-01 |  | 85800 | 0 | 85800 | 60385 | 70.38% | 25415 |  | 25415 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. Implementation of IS activities were successfully done in 2005 in Sierra Leone. NOU conducted national workshops for policy makers and Parliamentarians to sensitize them on the need to implement the phase out plan and ratify the ODS regulation. Both the Cabinet and Parliament have approved the ODS regulation which is currently undergoing final drafting by the Law Officer's Department of the Ministry of Justice. NOU conducted training of refrigeration technicians and custom officers. NOU submitted ODS data in good time and conducted awareness programmes which included Radio and TV talk-shows and disseminated information materials. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: training of trainers in code of good refrigeration practices/establishment of national refrigeration demonstration centre | Individual | AFR | SIL | REF | 41 | TRA | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 119460 | 0 | 119460 | 0 | 0% | 119460 | 119460 | 119460 | 15530 | 0 | 0 | 15530 | 1948.05 | Equipment sent to the country in July 2005. Phase 1 training set on 7 november 2005. Second payment done and phase 2 training ongoing | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | SIL | REF | 41 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 41840 | 0 | 41840 | 0 | 0% | 41840 | 41757 | 41840 | 5439 | 0 | 0 | 5439 | 1948.05 | Phase one train the trainer workshop for customs officers conducted from 20-21 May, 2005. About 30 customs officers were trained on the enforcement of ODS regualtions, identification of ODS and ODS-based equipment and tricks of illegal ODS trade. Phase two trainings expected to be completed by June, 2006 | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | SIL | REF | 41 | TAS | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 15455 | 0 | 15455 | 0 | 0% | 15455 | 15455 | 15455 | 2009 | 0 | 0 | 2009 | 1948.05 | MOU was signed and first disbursement done in June, 2005. Monitoring of activities under the RMP is on going. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | SIL | SEV | 47 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 48445 | 0 | 48445 | 0 | 0% | 48445 | 0 | 48445 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
ONG | UNEP | Methyl bromide communication programme | Individual | AFR | SIL | FUM | 47 | TAS | 12 | A | O | I | MB | 0.4 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 6500 | 0 | 0 | 6500 | 1948.05 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | SOI | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 |  |  | 2600 | -910 | 1690 | 0 |  | Project financially completed. | $7000 plus $910 PSC returned ExCom 41 |  |  | 1999-12-01 | [6 empty] | 1995 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | SOI | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 | 2006-06-01 |  |  | 20250 | 0 | 20250 | 12150 | 60% | 8100 | 0 | 8100 | 0 | 0 | 0 | 0 |  | Draft regulations prepared and currently working on the Attorney General’s office for recommendation to place regulations under “prohibited goods” of Customs and Excise Act. Training programme for Refrigeration technicians was conducted and a total of 23 technicians were trained. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Formulation of national phase out strategy | Individual | AFR | SOM | SEV | 35 | TAS | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2002-08-01 | 2006-09-05 |  |  | 60000 | 0 | 60000 | 35098 | 58.5% | 24902 | 0 | 24902 | 7800 | 0 | 4562.74 | 3237.26 |  | Project document is to be revised and to be re-submitted to 49th Excom | [7 empty] | 2003-12-01 |  |  | 2001 | Non Investment
ONG | UNEP | Establishment of the Ozone Unit | Individual | AFR | SOM | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 | 2006-09-05 |  |  | 26000 | 0 | 26000 | 0 | 0% | 26000 |  | 26000 | 0 | 0 | 0 | 0 |  | Political and institutional uncertainities hinder any progress | [10 empty] | 2002 | Non Investment
ONG | UNEP | Establishment of the National Ozone Committee (institutional strengthening) | Individual | AFR | SOM | SEV | 44 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 26000 | 0 | 26000 | 0 | 0% | 26000 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | One year project approved for Somalia in view of the current political situation | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: Customs training programme | Individual | ASP | SRL | REF | 32 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-02 | 2003-01-03 | 2006-12-01 |  |  | 87000 | 0 | 87000 | 45367.38 | 52.15% | 41632.62 | 1095.43 | 41632.62 | 11310 | 0 | 5897.7594 | 5412.2406 | [12 empty] | 2000 | Non Investment
COM | UNEP | Implementation of the RMP: Train the trainers and training of refrigeration service technicians including | Individual | ASP | SRL | REF | 32 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-02 | 2003-12-02 |  | 2004-09-01 |  | 219000 | 0 | 219000 | 140997.35 | 64.38% | 78002.65 | 56000 | 78002.65 | 28470 | 0 | 18329.6555 | 10140.3445 |  | Project completed | [10 empty] | 2000 | Non Investment
ONG | UNEP | National compliance action plan: enhancement of national capacity to monitor trade and prevent illegal trade of ODS | Individual | ASP | SRL | PHA | 43 | TRA | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2009-12-01 | 2009-12-01 |  |  | 135000 | 0 | 135000 | 107327.44 | 79.5% | 27672.56 | 0 | 27672.56 | 17550 | 0 | 13952.5672 | 3597.4328 | 0 | Organisation of Customs training workshops: Under the Train-the-Trainers programme which was held in 2001, 21 Nos. of trainers were trained. Resource persons were selected from these trainers for the above workshops. In 2005, a total of 175 customs officers have been trained and 5 workshops were organised. The trainings were held in: 28 Feb, 41 officers were trained; 7 Apr, 31 officers were trained; 24 Jun, 36 officers were trained; 18 Aug, 36 officers were trained 20 Dec, 31 officers were trained. Establishment of the Information Centre: The Laboratory of Sri Lanka Customs has been selected as the location. TOR for the Information / enforcement Centre has been finalised. Two ODS task Force meetings were conducted in January and May 2005. The country introduced several regulations to control import of ODS and ODS equipment. A database that contains information on illegal ODS trade was developed which is expected to improve more to facilitate the implementation of ODS regulations and exchange of information on illegal trade ODS trade activities. | [10 empty] | 2004 | Non Investment
ONG | UNEP | National compliance action plan: halon bank management | Individual | ASP | SRL | PHA | 43 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2009-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 25000 | 40000 | 5200 | 0 | 0 | 5200 |  | Sri Lanka has received the first payment and has appointed a national expert to convene a complete survey on sectors that use halons, as well as halons that are imported in the country (to cover the country's needs on a yearly bases), alongwith the nature of needs, to phase out halon in the country according to their commitment toward MP. However no expenditures were reported | [10 empty] | 2004 | Non Investment
ONG | UNEP | National compliance action plan: extension training of the established refrigeration technicians | Individual | ASP | SRL | PHA | 43 | TRA | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2007-12-01 | 2007-12-01 |  |  | 174600 | 0 | 174600 | 126817.93 | 72.63% | 47782.07 | 0 | 47782.07 | 22698 | 0 | 16486.3309 | 6211.6691 | 0 | Draft on development of codes of good practice was made. Refrigeration Association has been formed in November, 2004. The name of the Association is Environment Friendly Refrigeration Association of Sri Lanka (EFRASL). One 3-day Train the Trainers Workshop on Good Practices in Refrigeration was conducted for Tamil speaking Trainers. 17 Trainers were trained. Ten 3-day Training Workshops on Good Practices in Refrigeration were conducted in many parts of the country. A total of 465 Technicians and Technical Personnel engaged in the refrigeration & Air Conditioning industry were trained. A Technical Committee (TC) was appointed in August 2005 by the Coordinating Committee to Implement the Montreal Protocol to formulate and develop Codes on Good Practice in refrigeration adapting international Codes to national standards. The TC formulated a draft and submitted to the Sri Lanka Standards Institute (SLSI) in December 2005 to follow the relevant SLSI procedures in order to make it a national document. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | STK | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-12-01 | 1999-12-01 | 35000 | -12500 | 22500 | 22500 | 100% | 0 |  |  | 4550 | -1625 | 2925 | 0 |  | Project financially completed. | $12500 plus $1625 returned ExCom 30 | [9 empty] | 2001 | Non Investment
ONG | UNEP | Institutional strengthening | Individual | LAC | STK | SEV | 21 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 2000-02-01 | 2006-12-05 |  |  | 30000 | 0 | 30000 | 3982 | 13.27% | 26018 |  | 26018 | 3900 | 0 | 517.66 | 3382.34 |  | IS reports for Period ending September 2005 received and reviewed and re-submitted to NOO for further information required as the information submitted was inadequate of onward submission to UNON. ODS data reporting sent to both the OS and MLF. ODS license system in force. New Assistant NOO recruited. NOO attended regional network meetings. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | STK | REF | 21 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-09-01 | 1998-03-01 |  | 1998-03-01 | 1999-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STK | SEV | 42 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2007-12-05 |  |  | 13000 | 0 | 13000 | 0 | 0% | 13000 |  | 13000 | 0 | 0 | 0 | 0 |  | First disbursement is pending on the exhaustion of funds under the old IS. Progress reports received. UNEP/ROLAC is assisting country through South/south cooperation for the completion of the required reports. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Preparation of a refrigerant management plan | RMP | LAC | STK | REF | 44 | PRP | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 | 2006-03-01 |  |  | 15000 | 0 | 15000 | 7178 | 47.85% | 7822 | 1500 | 7822 | 1950 | 0 | 933.14 | 1016.86 | 195 | National and international consultant recruited. First draft submitted for review. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | STK | SEV | 47 | INS | 08 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | STL | SEV | 13 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-10-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Development of a refrigeration management plan | RMP | LAC | STL | REF | 21 | PRP | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-03-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 |  |  | 1950 | -130 | 1820 | 0 |  | Project financially completed. | $1000 plus $130 PSC returned ExCom 30 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of an Ozone Cell | Individual | LAC | STL | SEV | 21 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 2000-02-01 |  | 2000-08-01 | 2001-08-01 | 36580 | 0 | 36580 | 36580 | 100% | 0 | 0 |  | 4755.4 | 0 | 4755.4 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | STL | SEV | 30 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2002-04-01 |  | 2002-06-01 | 2003-07-01 | 24400 | 0 | 24400 | 24400 | 100% | 0 | 0 |  | 3172 | 0 | 3172 | 0 |  | Project financially completed. | [10 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | STL | SEV | 37 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-06-01 | 2005-12-01 | 31200 | 0 | 31200 | 31200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project completed | [10 empty] | 2002 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | LAC | STL | SEV | 43 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-10-01 | 2006-07-01 | 2006-07-01 |  |  | 31200 | 0 | 31200 | 4048 | 12.97% | 27152 | 0 | 27152 | 0 | 0 | 0 | 0 |  | Disbursements released regularly, last cash advance corresponding to the ISP (IV) sent to country in November 2005. NOU very active at international level, attended the Green Customs Initiative and ODS Officers Network Meetings. ODS Data reporting was submitted to Ozone Secretariat and MFS. NOU is developing meetings with Customs Department to evaluate implementation of the ODS licensing system. Training of Customs Officers in the Monitoring and Control of ODS Trade was resumed, as well as Training in Good Refrigerant Practices and R&R under the RMP update. NOU supported and organized the celebration of Ozone Day and Ozone depleting issues, incorporated them in the Agenda of Celebration for the World Environment Day. Furthermore, awareness activities to encourage CFC recovery and recycling in the refrigeration and air conditioning sector were carried out. | [10 empty] | 2004 | Non Investment
COM | UNEP | Preparation of country programme and refrigerant management plan | Individual | AFR | STP | SEV | 36 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 |  | 30000 | 0 | 30000 | 26461.69 | 88.21% | 3538.31 | 3364.18 | 3364 | 0 | 0 | 0 | 0 | 0 | Project completed. | [10 empty] | 2002 | Non Investment
COM | UNEP | Establishment of the Ozone Unit | Individual | AFR | STP | SEV | 38 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 |  | 30000 | 0 | 30000 | 23105 | 77.02% | 6895 |  | 6895 | 0 | 0 | 0 | 0 |  | Project completed in December 2005 | [10 empty] | 2002 | Non Investment
ONG | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | STP | SEV | 44 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | NOU held consultations with main stakeholders in the country in preparation of ODS regulations. NOU also carried out awareness raising activities targeting student and lecturer and published awarenss materail in local media. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: assistance for development of a licensing system | Individual | AFR | STP | REF | 44 | TAS | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-06-01 | 2006-06-01 |  |  | 20000 | 0 | 20000 | 15000 | 75% | 5000 | 5000 | 5000 | 2600 | 0 | 1950 | 650 | 650 | Draft ODS Regulations prepared awaiting enactment. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for custom officers | Individual | AFR | STP | REF | 44 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 45000 | 45000 | 5850 | 0 | 0 | 5850 | 1948.05 | ODS legislation not yet in place. Contract country established in July 2005 and first payment done in August 2005 | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | STP | REF | 44 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 55000 | 55000 | 7150 | 0 | 0 | 7150 | 1948.05 | Contract country established in July 2005 and first payment done in August 2005. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | STP | REF | 44 | TAS | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 20000 | 2600 | 0 | 0 | 2600 | 1948.05 | Contact with the country established in July 2005. First payment done in August 2005 and activities pending on the approval of the legislation. The country is informing UNEP in a regular basis on the evolution of the issue. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | LAC | STV | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-08-01 |  | 1998-05-01 | 1999-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training of trainers for good practices in refrigeration | Individual | LAC | STV | REF | 25 | TRA | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
COM | UNEP | Implementation of the refrigerant management plan: Monitoring and control of ODS and ODS based equipment | Individual | LAC | STV | REF | 25 | TRA | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2004-03-01 | 2000-02-01 |  | 2005-02-01 |  | 25000 | 0 | 25000 | 13000 | 52% | 12000 |  | 12000 | 3250 | 0 | 1690 | 1560 |  | Project completed in February 2005 | [10 empty] | 1998 | Non Investment
FIN | UNEP | Creation of the National Ozone Unit | Individual | LAC | STV | SEV | 25 | INS | 04 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-04-22 | 2001-06-01 |  | 2004-03-01 | 2005-12-01 | 30300 | 0 | 30300 | 30300 | 100% | 0 |  | 0 | 3939 | 0 | 3939 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 42 | INS | 06 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-03-01 | 2005-04-01 |  | 2005-03-01 | 2005-12-01 | 13130 | 0 | 13130 | 13130 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Financially Completed. Project completed in March 2005. ISP report submitted to UNON for processing and disbursements. Disbursement of USD $13,130.00 executed, representing total sum available to UNON for this phase. ISP renewal submitted and approved at the 45 Ex. Com. | [10 empty] | 2004 | Non Investment
COM | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | STV | REF | 44 | PRP | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2005-12-01 |  | 2005-11-01 |  | 20000 | 0 | 20000 | 10414.05 | 52.07% | 9585.95 | 0 | 9586 | 2600 | 0 | 1353.8265 | 1246.1735 | 0 | Project completed in November 2005. TPMP project document was submitted and approved at the 47th Ex. Com. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 45 | INS | 09 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 | 2006-04-01 |  |  | 30000 | 0 | 30000 | 13500 | 45% | 16500 | 16500 | 16500 | 0 | 0 | 0 | 0 | 0 | Budget and work plan completed. Draft MOU sent to country for review and signing. Country advised that disbursement of this phase cannot commence until funds allocated under the old ISP are exhausted. NOO attended regional network meetings. ODS data reporting sent to both Secretariats. ODS license system in force. NOU assisted in the TPMP preparation. | [10 empty] | 2005 | Non Investment
ONG | UNEP | Terminal phase out management plan for CFCs (first tranche) | Individual | LAC | STV | PHA | 47 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 67000 | 0 | 67000 | 0 | 0% | 67000 | 1500 | 67000 | 8710 | 0 | 0 | 8710 |  | National Stakeholder meeting, Briefing to the NOO on implementation process | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SUD | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1994-03-01 | 1994-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | SUD | SEV | 12 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1997-03-01 |  | 1999-07-01 | 1999-12-01 | 168300 | 0 | 168300 | 168300 | 100% | 0 |  |  | 21879 | 0 | 21879 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | SUD | SEV | 28 | INS | 12 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-12-01 | 2001-12-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 |  |  | 14586 | 0 | 14586 | 0 |  | Project financially completed. |  |  |  |  | 2001-06-01 | [5 empty] | 1999 | Non Investment
COM | UNEP | Renewal of institutional strengthening project | Individual | AFR | SUD | SEV | 34 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-12-01 |  | 112200 | 0 | 112200 | 43696 | 38.94% | 68504 |  | 68504 | 14586 | 0 | 5680.48 | 8905.52 |  | Project completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Extension of institutional strengthening: phase IV | Individual | AFR | SUD | SEV | 42 | INS | 16 | N | T | I | CFC | 12.1 | 0 | 0 | 0 | 2004-04-01 |  | 2006-04-01 | 2006-04-01 |  |  | 145860 | 0 | 145860 | 0 | 0% | 145860 |  | 145860 | 0 | 0 | 0 | 0 |  | Communication with NOU still remains complicated. Non-attendance of network meetings by NOU made consultations and guidance difficult. | [10 empty] | 2004 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | LAC | SUR | SEV | 30 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-06-01 |  | 2003-08-01 | 2005-05-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 6500 | -4550 | 1950 | 0 |  | Project financially completed. | $25000 plus $3250 PSC returned ExCom 44 $10000 plus $1300 PSC returned ExCom 46 | [6 empty] | 2003-07-01 |  |  | 2000 | Non Investment
ONG | UNEP | Institutional strengthening and capacity building: establishment of the Ozone Unit | Individual | LAC | SUR | SEV | 41 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 | 2006-12-01 |  |  | 110000 | 0 | 110000 | 69800 | 63.45% | 40200 | 0 | 40200 | 0 | 0 | 0 | 0 |  | IS progress reports submitted to UNEP/ROLAC and UNON. Project is proceeding satisfactorily. ODS Legislation completed. Ratification process of amendments has been completed at national parliamentary level and country is in the process of submitting same to the UN New York Office. Data submission to both the OS and MLF were completed. NOO attended ODS Network Meetings. NOU leads the RMP implementation at country level. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: development and strengthening of policy and regulatory framework for acceleration of compliance with the Montreal Protocol | Individual | LAC | SUR | REF | 41 | TAS | 04 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 | 2006-12-06 |  |  | 20000 | 0 | 20000 | 10000 | 50% | 10000 | 10000 | 10000 | 2600 | 0 | 1300 | 1300 | 1300 | National Stakeholder committee organized. ODS Legislation Completed. Country is using the Trade Ordinance Act, adjusted to include ODS and ODS containing technologies. Equipment for Customs Training Delivered in June of 2005. Customs Training Planned for March 2006. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: training of customs officers and other relevant stakeholders in monitoring of ODS | Individual | LAC | SUR | REF | 41 | TRA | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 | 2006-12-01 |  |  | 42000 | 0 | 42000 | 23000 | 54.76% | 19000 | 13000 | 19000 | 5460 | 0 | 2990 | 2470 | 1690 | First stakeholder meeting held in January 2005. Ratification of all amendments to the Protocol approved by Parliament. Advance ODS legislation completed in May 2005. Equipment received in June 2005. Training using Five days mixed approach to be done in February 2006. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Implementation of the RMP: training of trainers in good practices of refrigeration | Individual | LAC | SUR | REF | 41 | TRA | 06 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-07-01 | 2006-12-01 |  |  | 70000 | 0 | 70000 | 35000 | 50% | 35000 | 35000 | 35000 | 9100 | 0 | 4550 | 4550 | 4550 | First stakeholder meeting held. National Training institute selected for both the Train the Trainer Workshop and contination of furhter training. ROLAC purchased training equipment. Equipment Received June 2005 . Train the Trainer completed in August of 2005. | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SWA | SEV | 12 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-09 | 1995-06-01 |  | 1994-12-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
COM | UNEP | Institutional strengthening | Individual | AFR | SWA | SEV | 15 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1998-12-01 |  | 2003-12-01 |  | 67320 | 0 | 67320 | 67320 | 100% | 0 |  | 0 | 8751.6 | 0 | 8751.6 | 0 |  | Project completed. |  |  | 1998-03-01 | [7 empty] | 1994 | Non Investment
ONG | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | SWA | SEV | 41 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 | 2006-10-01 |  |  | 58344 | 0 | 58344 | 15752 | 27% | 42592 |  | 42592 | 0 | 0 | 0 | 0 |  | NOU produced awareness materials including calenders, pamphlets, posters, stickers and distributed during the international ozone day and conducted activities including radio programme, side events during International Trade Fair. NOU conducted customs officer and refrigeration technician training in preparation for enfrocement of ODS regulations.NOU conducted a study on methyl bromide uses and corresponding amounts. NOU reported ODS consumption data in time | [10 empty] | 2003 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | SYR | SEV | 04 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-11-01 | 1993-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | SYR | REF | 23 | PRP | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
ONG | UNEP | Refrigerant management plan: Training programme for custom officials | Individual | ASP | SYR | REF | 29 | TRA | 47 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-03 | 2006-12-01 |  |  | 72600 | 0 | 72600 | 10000 | 13.77% | 62600 |  | 62600 | 9438 | 0 | 1300 | 8138 |  | Project was reactivated during the second half of 2005, agreements made between NOU and Customs authority to conduct the training workshops of phase II in sites. Project planned for completion by the end of 2006 | [5 empty] | 2002-12-02 |  |  |  |  | 1999 | Non Investment
ONG | UNEP | Refrigerant management plan: Training for trainers and refrigeration technician on good service practices | Individual | ASP | SYR | REF | 29 | TRA | 49 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2002-12-01 | 2006-12-01 |  |  | 201300 | 0 | 201300 | 129664 | 64.41% | 71636 |  | 71636 | 26169 | 0 | 16856.32 | 9312.68 |  | 575 technicians were trained in 25 workshops in 5 major cities since the beginning of the project till now, about half of them were trained during 2005 after reactivating the project in 2004. Country submitted detailed financial and progress reports during 2005 and payment were disbursed accordingly. Project to be completed by the end of 2006 | [10 empty] | 1999 | Non Investment
COM | UNEP | Refrigerant management plan: Assistance for the establishment of regulations and legislation | Individual | ASP | SYR | REF | 29 | TAS | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-03 |  | 2002-06-01 |  | 25500 | -10000 | 15500 | 15500 | 100% | 0 |  | 0 | 3315 | -1300 | 2015 | 0 |  | Project completed. | $10000 plus $1300 PSC returned ExCom 46 | [9 empty] | 1999 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | ASP | THA | FUM | 30 | TAS | 126 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -9096 | 15904 | 15904 | 100% | 0 |  |  | 3250 | -1182.48 | 2067.52 | 0 |  | Project financially completed. | $9096 plus $1182 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
ONG | UNEP | Institutional strengthening project (phase I) | Individual | EUR | TKM | SEV | 46 | INS | 01 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 |  | 2008-07-01 | 2008-07-01 |  |  | 115693 | 0 | 115693 | 0 | 0% | 115693 | 115693 | 115693 | 0 | 0 | 0 | 0 | 0 | NOU was established under the ODS phase-out programme funded by GEF. Currently the NOU is complete and fully operational. MOU between UNEP and the NOU has been signed in August 2005. First tranche has been paid in Oct 2005. The remaining training activities under GEF funding are ongoing and planned for completion during 2006. NOU has been advised by CAP on reporting requirements and procedures under Article 5. NOU is now officially participating in the ECA Network meetings and other activities under the Network. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | TOG | SEV | 06 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-02-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1992 | Non Investment
FIN | UNEP | Establishment of the National Ozone Office | Individual | AFR | TOG | SEV | 23 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-07-01 | 2004-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 |  |  | 9100 | 0 | 9100 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
COM | UNEP | Development of a refrigerant management plan | RMP | AFR | TOG | REF | 35 | PRP | 03 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-08-01 |  | 2002-10-01 |  | 60000 | -20927 | 39073 | 39072.79 | 100% | 0 | 0 | 0 | 7800 | -2720.51 | 5079.4627 | 0.0273 |  | Project completed. | $20927 plus $2721 PSC returned ExCom 46 | [9 empty] | 2001 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | AFR | TOG | SEV | 37 | INS | 05 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-08-01 |  | 60667 | 0 | 60667 | 60667 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | AFR | TOG | REF | 38 | TRA | 08 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-03-01 | 2004-05-01 | 2006-07-01 |  |  | 64000 | 0 | 64000 | 64000 | 100% | 0 | 0 | 0 | 8320 | 0 | 8320 | 0 | 0 | The Customs phase 2 was completed in April 2006. UNEP waiting for the country to send the follow up and expenditure reports to close the project. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training of customs officers | Individual | AFR | TOG | REF | 38 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-05-01 | 2006-12-01 |  |  | 43500 | 0 | 43500 | 20501 | 47.13% | 22999 | 16985 | 22999 | 5655 | 0 | 2665.13 | 2989.87 | 2208 | Phase 2 started in August 2005 and so far 50 customs officers and controllers have been trained. The training programme was stopped because of the war in Togo. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | TOG | SEV | 44 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 60667 | 0 | 60667 | 0 | 0% | 60667 | 36400 | 60667 | 0 | 0 | 0 | 0 | 0 | First payment done in may 2005. The NOO coordinated the training of trainer of technicians in refrigeration which took place in August 2005 .Second payment pending on the activities report. | [10 empty] | 2004 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TON | SEV | 36 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 | 2006-06-01 |  |  | 19700 | 0 | 19700 | 11820 | 60% | 7880 | 0 | 7880 | 0 | 0 | 0 | 0 |  | Draft ODS Bill is being reviewed by law sub-committee of the Crown Law and the Bill is now ready to be submitted to the Law Committee for another round of review. Tonga’s ODS Bill is one of four legislation to be approved and it’s 4th in line. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training the trainers of technicians in the refrigeration sector | Individual | LAC | TRI | REF | 23 | TRA | 07 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-02 |  | 2002-09-01 | 2003-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  |  | 6500 | 0 | 6500 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training in monitoring and controlling of ODSs | Individual | LAC | TRI | REF | 23 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-02-01 |  | 2002-04-01 | 2003-05-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 |  |  | 3445 | 0 | 3445 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TTR | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 | 2006-06-01 |  |  | 34000 | 0 | 34000 | 20400 | 60% | 13600 | 0 | 13600 | 0 | 0 | 0 | 0 |  | National Compliance Centre was established under Environmental Quality Protection Board. Palau became the second country to establish regulations entitled “Ozone Layer Protection Regulations 2005” under the Republic of Palau Environmental Quality Protection Act. Training programme for Refrigeration technicians was conducted and a total of 23 technicians were trained. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | TUV | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 |  | 0 | 5200 | -3250 | 1950 | 0 |  | Project completed | $25000 plus 3250 returned ExCom 46 |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TUV | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 | 2006-06-01 |  |  | 17500 | 0 | 17500 | 10500 | 60% | 7000 | 0 | 7000 | 0 | 0 | 0 | 0 |  | National Compliance Centre was established under Department of Environment, Office of the Prime Minister. Training programme was conducted wherein a total of 17 technicians were trained. Draft regulations prepared and currently being reviewed by the Attorney General’s office. The Government plan to conduct the National Consultation with SPREP in first half of 2006. | [10 empty] | 2002 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | UGA | SEV | 04 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1994-06-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
ONG | UNEP | Institutional strengthening (establishment of the ODS unit) | Individual | AFR | UGA | SEV | 13 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1997-07-01 | 2006-12-06 |  |  | 64515 | 0 | 64515 | 15687 | 24.32% | 48828 |  | 48828 | 8386.95 | 0 | 2039.31 | 6347.64 |  | Implementation of the licensing system commenced in January 2006. Utilisation of IS funds is still low. |  |  |  | 1999-12-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | URT | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1996-07-01 | 1999-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  |  | 1300 | 0 | 1300 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
COM | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | URT | SEV | 20 | INS | 07 | N | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1999-10-01 |  | 2004-12-01 |  | 66000 | 0 | 66000 | 66000 | 100% | 0 |  | 0 | 8580 | 0 | 8580 | 0 |  | Project completed | [10 empty] | 1996 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | URT | SEV | 44 | INS | 17 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 | 2006-12-01 |  |  | 57200 | 0 | 57200 | 23000 | 40.21% | 34200 | 34200 | 34200 | 0 | 0 | 0 | 0 | 0 | Implementation of IS Phase II has improved with re-location of the NOU | [10 empty] | 2004 | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | LAC | URU | REF | 23 | PRP | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1998-11-01 |  | 1999-01-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1997 | Non Investment
ONG | UNEP | Implementation of the RMP: Demonstration and training project for the use of hydrocarbons as refrigerants | Individual | LAC | URU | REF | 34 | TAS | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 | 2006-06-01 |  |  | 65000 | 0 | 65000 | 62168.93 | 95.64% | 2831.07 | 2831 | 2831.07 | 8450 | 0 | 8081.9609 | 368.0391 | 368.03 | It was agreed on Dec-05 that complementary training and awareness raising activities will be implemented with the balance that resulted from cost savings due to in-kind contributions of participating institutions. | [10 empty] | 2001 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VAN | SEV | 17 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-06-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 |  |  | 2600 | -910 | 1690 | 0 |  | Project financially completed. | $7000 plus $910 PSC returned ExCom 41 |  |  | 1999-12-01 | [6 empty] | 1995 | Non Investment
ONG | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | VAN | SEV | 36 | INS | 03 | N | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 | 2006-06-01 |  |  | 20250 | 0 | 20250 | 12150 | 60% | 8100 | 0 | 8100 | 0 | 0 | 0 | 0 |  | National Compliance Centre was established under Environment Unit. Training programme was conducted wherein a total of 9 technicians were trained. | [10 empty] | 2002 | Non Investment
COM | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | Individual | LAC | VEN | SEV | 34 | TAS | 90 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2002-12-01 |  | 2005-12-01 |  | 80000 | 0 | 80000 | 35500 | 44.38% | 44500 | 0 | 44500 | 10400 | 0 | 4615 | 5785 |  | Project completed in December 2005. Last disbursement processed in Dec-05 upon submission of corresponding reports by country. Project completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Training of customs officers | Individual | LAC | VEN | REF | 34 | TRA | 92 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-12-01 |  | 2005-12-01 |  | 120000 | 0 | 120000 | 83200.14 | 69.33% | 36799.86 | 24635.66 | 36799.86 | 15600 | 0 | 10816.0182 | 4783.9818 | 3224 | Project completed in December 2005. Refreshing workshop by Argentinian consultant took place on June-05. Last set of identifiers with country as of June-05 | [10 empty] | 2001 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VIE | SEV | 13 | CPG | 02 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-11-17 | 1995-10-01 |  | 1996-05-01 | 1996-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [10 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of the ozone unit (institutional strengthening) | Individual | ASP | VIE | SEV | 17 | INS | 08 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 1999-04-01 | 1999-11-01 | 137280 | 0 | 137280 | 137280 | 100% | 0 |  |  | 17846.4 | 0 | 17846.4 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Technology cooperation workshop for ODS elimination | Individual | ASP | VIE | SEV | 17 | TRA | 09 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1995-12-01 |  | 1996-06-01 | 1999-04-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 |  |  | 3510 | 0 | 3510 | 0 |  | Project financially completed. | [10 empty] | 1995 | Non Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | VIE | REF | 23 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-07-01 | 2002-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | ASP | VIE | SEV | 28 | INS | 27 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-06-01 | 2001-12-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 |  |  | 11897.6 | 0 | 11897.6 | 0 |  | Project financially completed. |  |  |  |  | 2001-06-01 | [5 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | ASP | VIE | SEV | 33 | INS | 30 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-08-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 |  |  | 11897.6 | 0 | 11897.6 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
FIN | UNEP | Implementation of the RMP: Workshop for finalisation of regulations | Individual | ASP | VIE | REF | 34 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2001-10-01 |  | 2002-01-01 | 2003-06-01 | 4350 | 0 | 4350 | 4350 | 100% | 0 | 0 |  | 565.5 | 0 | 565.5 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
COM | UNEP | Implementation of the RMP: Train the trainer programme in the refrigeration servicing sector | Individual | ASP | VIE | REF | 34 | TRA | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 |  | 200000 | -40959 | 159041 | 159041.12 | 100% | -0.12 | 0 | -0.12 | 26000 | -5324.67 | 20675.3456 | 0 |  | Project completed | $40959 plus $ 5325 returned ExCom 46 | [9 empty] | 2001 | Non Investment
COM | UNEP | Extension of institutional strengthening project | Individual | ASP | VIE | SEV | 40 | INS | 42 | N | T | I | CFC | 9.8 | 9.8 | 0 | 0 | 2003-07-01 | 2004-01-04 | 2005-07-01 |  | 2005-07-01 |  | 118976 | 0 | 118976 | 91799 | 77.16% | 27177 | 0 | 27177 | 0 | 0 | 0 | 0 |  | Project completed in July 2005. The NOU is working with the Ministry of Trade to set up the quota system to control the import of CFCs to be within the limit of the Montreal Protocol. As requested by Vietnam NOU, UNEP will be supporting Thailand ODS Specialist to assist Vietnam to develop the quota system in March 2005 under its south-south cooperation. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase V) | Individual | ASP | VIE | SEV | 46 | INS | 46 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2007-07-01 | 2007-07-01 |  |  | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Regional Network Coordinator had a mission in March 2005 along with Thailand expert to assist the country to develop the import quota system as part of the south-south cooperation. Licensing and quota system established in July2005. | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | YEM | SEV | 19 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  |  | 5590 | 0 | 5590 | 0 |  | Project financially completed. | [10 empty] | 1996 | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | ASP | YEM | SEV | 25 | INS | 02 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-02-22 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 15600 | 0 | 15600 | 0 |  | Project financially completed. | [10 empty] | 1998 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | YEM | REF | 27 | PRP | 05 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-12-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 3900 | 0 | 3900 | 0 |  | Project financially completed. | [5 empty] | 2001-09-01 |  |  |  |  | 1999 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | ASP | YEM | SEV | 35 | INS | 13 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2003-12-01 | 2004-12-01 | 118000 | 0 | 118000 | 118000 | 100% | 0 |  |  | 15340 | 0 | 15340 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: establishment of regulations and legislation | Individual | ASP | YEM | REF | 37 | TAS | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2004-01-01 | 2006-06-01 |  |  | 25000 | 0 | 25000 | 20000 | 80% | 5000 | 5000 | 5000 | 3250 | 0 | 2600 | 650 | 650 | Final ODS Legislation is in place, the legislation is a comprehensive package includes licensing, quota, ban on import of ODS equipment and other needed regulatory measures for phase out ODS in the industry and service sectors. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme on good practices in refrigeration | Individual | ASP | YEM | REF | 37 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2005-08-01 | 2007-12-01 |  |  | 189500 | 0 | 189500 | 0 | 0% | 189500 | 120000 | 189500 | 24635 | 0 | 0 | 24635 | 15600 | MOU with the country signed along with a detailed implementation plan, Global equipment bid was raised and phase I is planned to be completed 2nd half of 2006 while phase II will start by end of 2006 | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | YEM | REF | 37 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2004-08-01 | 2007-12-01 |  |  | 91825 | 0 | 91825 | 0 | 0% | 91825 | 0 | 91825 | 11937.25 | 0 | 0 | 11937.25 | 0 | Implementation will start in 2006 since ODS legislation just enacted late 2005, MOU and implementation plan are ready for signature. | [10 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | YEM | REF | 37 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2005-08-01 | 2007-12-01 |  |  | 57750 | 0 | 57750 | 0 | 0% | 57750 | 0 | 57750 | 7507.5 | 0 | 0 | 7507.5 | 0 | The monitoring project will start in 2006 because customs training, refrigeration training and R&R projects just started to be ready for starting implementation by end of 2005 | [10 empty] | 2002 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 3 | Individual | ASP | YEM | SEV | 41 | INS | 20 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 |  | 104000 | 0 | 104000 | 92135 | 88.59% | 11865 |  | 11865 | 0 | 0 | 0 | 0 |  | Project completed in December 2005. Yemen received the final payment in September 2005. They submitted their terminal report and requested renewal in September 2005, which was approved by ExCom in its 47th meeting. They submitted their A7 reports to the OS as of 2004, along with their progress report to the MFS as of 2004.Yemen enacted its legislation for control of import/export of ODS after had been discussed by various stakeholders in the five main governorates. Yemen appears to have made significant progress in its ODS phase out. According to 2004 data reporting, Yemen succeeded to phase out nearly 70% of its CFC consumption, surpassing the 50% reduction required in 2005. | [10 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | YEM | SEV | 47 | INS | 24 | N | T | I | CFC | 8.6 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 104000 | 0 | 104000 | 0 | 0% | 104000 | 0 | 104000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [10 empty] | 2005 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ZAM | SEV | 04 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  |  | 3250 | 0 | 3250 | 0 |  | Project financially completed. | [10 empty] | 1991 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | ZAM | SEV | 09 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1999-12-01 | 2004-05-01 | 75600 | 0 | 75600 | 75600 | 100% | 0 |  |  | 9828 | 0 | 9828 | 0 |  | Project financially completed. |  |  |  | 1999-12-01 | [6 empty] | 1993 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | ZAM | FUM | 30 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9259 | 15741 | 15741 | 100% | 0 |  |  | 3250 | -1203.67 | 2046.33 | 0 |  | Project financially completed. | $9259 plus $1204 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
COM | UNEP | Renewal of institutional strengthening | Individual | AFR | ZAM | SEV | 30 | INS | 11 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2004-08-01 | 2002-07-01 |  | 2004-12-01 |  | 50400 | 0 | 50400 | 7777 | 15.43% | 42623 |  | 42623 | 6552 | 0 | 1011.01 | 5540.99 |  | Project completed. | [10 empty] | 2000 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | ZAM | SEV | 44 | INS | 15 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2006-12-01 | 2006-12-01 |  |  | 65520 | 0 | 65520 | 26208 | 40% | 39312 | 39312 | 39312 | 0 | 0 | 0 | 0 | 0 | Country effectively implementing and enforcing ODS licensing and quota system successfully. NOU conducted trainings for customs officers and refrigeration technicians. Country celebrated ozone day. NOU produced and distributed awareness materials including calenders, pamphlets, posters, T-shirts, caps. Country reported ODS consumption data in time | [10 empty] | 2004 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ZIM | SEV | 09 | CPG | 01 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 5200 | 0 | 5200 | 0 |  | Project financially completed. | [10 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of an Ozone Office | Individual | AFR | ZIM | SEV | 13 | INS | 02 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1997-07-01 |  | 1999-10-01 | 2000-12-01 | 171050 | 0 | 171050 | 171050 | 100% | 0 |  |  | 22236.5 | 0 | 22236.5 | 0 |  | Project financially completed. |  |  |  | 1999-05-01 | [6 empty] | 1994 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | ZIM | FUM | 30 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -2765 | 22235 | 22235 | 100% | 0 |  |  | 3250 | -359 | 2891 | 0 |  | Project financially completed. | $2765 plus $359 PSC returned ExCom 41 | [9 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | ZIM | SEV | 28 | INS | 20 | N | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-12-01 | 2003-06-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 |  |  | 14824.29 | 0 | 14824.29 | 0 |  | Project financially completed. |  |  |  |  | 2001-06-01 | [5 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | ZIM | SEV | 34 | INS | 24 | N | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2003-08-01 |  | 2004-07-01 | 2004-12-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 |  |  | 14824.29 | 0 | 14824.29 | 0 |  | Project financially completed. | [10 empty] | 2001 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | ZIM | SEV | 43 | INS | 27 | N | T | I | CFC | 12.2 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 | 2006-07-01 |  |  | 148242 | 0 | 148242 | 49463 | 33.37% | 98779 |  | 98779 | 0 | 0 | 0 | 0 |  | NOU continued servicing National Ozone Committe and sub-committees. NOU started implementing ODS licensing and quota system, celebrated international ozone day and distributed awareness materials including posters, phamplets, T-shirts, pens, calenders. The country reported data in good time | [10 empty] | 2004 | Non Investment
FIN | UNIDO | Preparation of a recovery and recycling projects in Benin, Botswana, Burkina Faso, Gambia, Guinea, Namibia and Senegal | Individual | AFR | AFR | REF | 17 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1997-09-01 | 1999-08-01 | 45000 | -1189 | 43811 | 43811 | 100% | 0 | 0 |  | 5850 | -154.57 | 5695.43 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | ALB | PHA | 36 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-07-01 |  | 2003-12-01 | 2004-12-01 | 40000 | -521 | 39479 | 39479 | 100% | 0 | 0 |  | 5200 | -67.73 | 5132.27 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
ONG | UNIDO | National ozone depleting substances phase-out plan: refrigerant recovery and recycling network | Multi-Year | EUR | ALB | PHA | 39 | TAS | 05 | A | O | I | CFC | 6.8 | 6.8 |  |  | 2003-04-01 | 2004-12-01 | 2006-04-01 | 2006-12-01 |  |  | 100000 | 0 | 100000 | 11935 | 11.94% | 88065 | 12150 | 30000 | 7500 | 0 | 895.125 | 6604.875 | 911.25 | Since the legislation was approved in 2005, implementation of the refrigerant recovery and recycling network component could not start earlier. A joint UNIDO/UNEP mission was undertaken and an international consultant was recruited to accelerate the pace of project implementation. Resurvey of service market was completed. Eligible enterprises will be selected by NOU. As a first step, the 10-20 biggest CFC consumers will be selected for assistance and potential enterprises will be identified by NOU for establishment of a recovery and recycling centre. In addition, refrigeration demonstration unit for training of service technicians was procured which is being shipped to Albania. | [9 empty] | 2005-06-01 | 2002 |  | 61.2 | 36.57 |  |  | Yes | Yes | Yes
FIN | UNIDO | National ozone depleting substances phase-out plan: awareness workshop to prevent the introduction of methyl bromide | Multi-Year | EUR | ALB | PHA | 39 | TAS | 08 | A | O | I | MBR | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2005-09-01 | 20000 | -350 | 19650 | 19650 | 100% | 0 | 0 |  | 1500 | -26.25 | 1473.75 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2003
ONG | UNIDO | National ozone depleting substances phase-out plan: programme management and auditing | Multi-Year | EUR | ALB | PHA | 39 | TAS | 09 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2005-04-01 | 2009-12-01 | 2009-12-01 |  |  | 16068 | 0 | 16068 | 8339 | 51.9% | 7729 | 5400 | 7000 | 1205.1 | 0 | 625.425 | 579.675 | 405 | Audit to verify 2003/2004 consumption took place. Remaining funds will be used for management and monitoring activities. | [10 empty] | 2003
COM | UNIDO | National ozone depleting substances phase-out plan: conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Energy Combinat Ltd., Elbasan | Multi-Year | EUR | ALB | PHA | 39 | INV | 10 | A | O | I | CTC | 2.3 | 2.3 |  |  | 2003-04-01 | 2005-09-01 | 2005-04-01 |  | 2005-12-01 |  | 45000 | 0 | 45000 | 27045 | 60.1% | 17955 | 4026 | 17955 | 3375 | 0 | 2028.375 | 1346.625 | 301.95 | Project completed in Dec 2005. | [10 empty] | 2002
ONG | UNIDO | National ODS phase out plan (2nd tranche) | Multi-Year | EUR | ALB | PHA | 46 | INV | 11 | A | O | I | CFC | 25 | 25 |  |  | 2005-07-01 |  | 2006-07-01 | 2007-05-01 |  |  | 172322 | 0 | 172322 | 0 | 0% | 172322 | 0 | 30000 | 12924.15 | 0 | 0 | 12924.15 | 0 | Second tranche was released by 46th ExCom in July 2005. Revised terms of reference for management and monitoring component were submitted to NOU for review and approval. A phase-out of 25 ODP tonnes was achieved. In Apr 2006, terms of reference for the development and establishment of a Code of Practice and the establishment of an infrastructure to re-use ODS in Albania were approved by NOU. Terms of reference for provision of services related to the improvement of vocational schools are being finalized. | [10 empty] | 2005 | INV | 36.2 | 14.4 |  |  | Yes | No | No
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production at ENIEM | Individual | AFR | ALG | SEV | 12 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-08-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -714 | 24286 | 24286 | 100% | 0 | 0 |  | 3250 | -92.82 | 3157.18 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the aerosol production and solvent conversion at ENAD | Individual | AFR | ALG | SEV | 12 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -5081 | 19919 | 19919 | 100% | 0 | 0 |  | 3250 | -660.53 | 2589.47 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for the phase-out of CFC-11 in the manufacture of sandwich panels at Prosider (Annaba-Algeria) | Individual | AFR | ALG | FOA | 15 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -1621 | 23379 | 23379 | 100% | 0 | 0 |  | 3250 | -210.73 | 3039.27 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for establishment of a National Centre for recovery and recycling CFC-11, CFC-12 and CFC-502 | Individual | AFR | ALG | REF | 15 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1998-11-01 | 1995-06-01 |  | 1999-12-01 | 2001-11-01 | 25000 | -8281 | 16719 | 16719 | 100% | 0 | 0 |  | 3250 | -1076.53 | 2173.47 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of an investment project for CFC phase-out in the production of rigid foam at Batimetal | Individual | AFR | ALG | FOA | 15 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -4278 | 20722 | 20722 | 100% | 0 | 0 |  | 3250 | -556.14 | 2693.86 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise Nationale des Industries de l'Electromenager, ENIEM | Individual | AFR | ALG | REF | 15 | INV | 09 | A | O | I | CFC | 425 | 425 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2002-09-01 | 6589550 | -93233 | 6496317 | 6496317 | 100% | 0 | 0 |  | 856641.5 | -12120.29 | 844521.21 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise nationale des Detergents (ENAD-Lames) | Individual | AFR | ALG | SOL | 17 | INV | 10 | A | O | I | CFC | 5.6 | 5.6 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-06-01 | 2001-03-01 | 109900 | -779 | 109121 | 109121 | 100% | 0 | 0 |  | 14287 | -101.27 | 14185.73 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phasing out ODS in small- and medium-scale industries | Individual | AFR | ALG | SEV | 17 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1996-01-01 |  | 1999-12-01 | 2001-03-01 | 50000 | -1486 | 48514 | 48514 | 100% | 0 | 0 |  | 6500 | -193.18 | 6306.82 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNIDO | Phasing out of CFCs at Entreprise Nationale des Detergents (ENAD) | Individual | AFR | ALG | ARS | 18 | INV | 12 | A | O | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 2002-05-01 | 614850 | -351 | 614499 | 614499 | 100% | 0 | 0 |  | 79930.5 | -45.63 | 79884.87 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels by discontinuous method at Prosider Berrahal | Individual | AFR | ALG | FOA | 19 | INV | 13 | A | O | I | CFC | 82 | 82 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  |  | 2003-03-01 | 434500 | -1252 | 433248 | 433248 | 100% | 0 | 0 |  | 56485 | -162.76 | 56322.24 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels at Batimetal Beni Mansour | Individual | AFR | ALG | FOA | 19 | INV | 14 | A | O | I | CFC | 110 | 110 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 1998-12-01 | 2003-03-01 | 496650 | -598 | 496052 | 496052 | 100% | 0 | 0 |  | 64564.5 | -77.74 | 64486.76 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Etablissement Has Mohamed | Individual | AFR | ALG | ARS | 20 | INV | 15 | A | O | I | CFC | 22.5 | 22.5 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 82018 | -18 | 82000 | 82000 | 100% | 0 | 0 |  | 10662.34 | -2.34 | 10660 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Vague de Fraicheur | Individual | AFR | ALG | ARS | 20 | INV | 16 | A | O | I | CFC | 51.4 | 51.4 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2001-12-01 | 164623 | -101 | 164522 | 164522 | 100% | 0 | 0 |  | 21400.99 | -13.13 | 21387.86 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ets. Wouroud | Individual | AFR | ALG | ARS | 20 | INV | 17 | A | O | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 187772 | -717 | 187055 | 187055 | 100% | 0 | 0 |  | 24410.36 | -93.21 | 24317.15 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Laboratoire Bendi | Individual | AFR | ALG | ARS | 20 | INV | 18 | A | O | I | CFC | 19.2 | 19.2 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  |  | 2002-05-01 | 56790 | -3090 | 53700 | 53700 | 100% | 0 | 0 |  | 7382.7 | -401.7 | 6981 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFCs at Ets. COPHYD | Individual | AFR | ALG | ARS | 20 | INV | 19 | A | O | I | CFC | 15 | 15 |  |  | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1997-07-01 | 1999-08-01 | 53024 | -1373 | 51651 | 51651 | 100% | 0 | 0 |  | 6893.12 | -178.49 | 6714.63 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the aerosol, foam and refrigeration sectors | Individual | AFR | ALG | SEV | 21 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-05-01 | 1997-08-01 |  | 1998-02-01 | 2002-09-01 | 50000 | -2765 | 47235 | 47235 | 100% | 0 | 0 |  | 6500 | -359.45 | 6140.55 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Ets Leulmi Essaid flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 21 | A | O | I | CFC | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1998-06-01 |  |  | 2002-09-01 | 61880 | -55382 | 6498 | 6498 | 100% | 0 | 0 |  | 8044.4 | -7199.66 | 844.74 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 at Snam flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 22 | A | O | I | CFC | 32 | 32 |  |  | 1997-05-01 | 1997-11-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 88360 | -547 | 87813 | 87813 | 100% | 0 | 0 |  | 11486.8 | -71.11 | 11415.69 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sammo flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 23 | A | O | I | CFC | 24 | 24 |  |  | 1997-05-01 | 1997-10-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 98770 | -1565 | 97205 | 97205 | 100% | 0 | 0 |  | 12840.1 | -203.45 | 12636.65 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ALG | FUM | 22 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1998-06-01 |  | 2000-01-01 | 2000-07-01 | 8000 | -3800 | 4200 | 4200 | 100% | 0 | 0 |  | 1040 | -494 | 546 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at La Mousse du Sud flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 23 | INV | 25 | A | O | I | CFC | 95 | 95 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-10-01 | 2003-07-01 | 553480 | -2305 | 551175 | 551175 | 100% | 0 | 0 |  | 71952.4 | -299.65 | 71652.75 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC 134a for commercial refrigeration at Enapat | Individual | AFR | ALG | REF | 25 | INV | 26 | A | O | I | CFC | 9.2 | 9.2 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 1998-12-01 | 2000-12-01 | 139932 | -17132 | 122800 | 122800 | 100% | 0 | 0 |  | 18191.16 | -2227.16 | 15964 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Matelas Djurdjura | Individual | AFR | ALG | FOA | 25 | INV | 27 | A | O | I | CFC | 28 | 28 |  |  | 1998-07-01 | 1998-12-01 | 1999-08-01 |  | 2001-07-01 | 2002-09-01 | 82608 | -883 | 81725 | 81725 | 100% | 0 | 0 |  | 10739.04 | -114.79 | 10624.25 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with hydrocarbons in the aerosol sector at Ets Djadir | Individual | AFR | ALG | ARS | 25 | INV | 28 | A | O | I | CFC | 38.4 | 38.4 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2000-12-01 | 2002-08-01 | 147807 | -550 | 147257 | 147257 | 100% | 0 | 0 |  | 19214.91 | -71.5 | 19143.41 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Maghreb Mousse | Individual | AFR | ALG | FOA | 26 | INV | 29 | A | O | I | CFC | 24 | 24 |  |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 2001-07-01 | 2002-09-01 | 96492 | -652 | 95840 | 95840 | 100% | 0 | 0 |  | 12543.96 | -84.76 | 12459.2 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for domestic refrigeration at Enapem | Individual | AFR | ALG | REF | 26 | INV | 30 | A | O | I | CFC | 12.8 | 12.8 |  |  | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 167332 | -3151 | 164181 | 164181 | 100% | 0 | 0 |  | 21753.16 | -409.63 | 21343.53 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the foam sector (flexible) | Individual | AFR | ALG | FOA | 27 | PRP | 31 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 18000 | -48 | 17952 | 17952 | 100% | 0 | 0 |  | 2340 | -6.24 | 2333.76 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Matelas Atlas (Sam Atlas) | Individual | AFR | ALG | FOA | 27 | INV | 33 | A | O | I | CFC | 22 | 22 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2004-03-01 | 120060 | 0 | 120060 | 120060 | 100% | 0 | 0 |  | 15607.8 | 0 | 15607.8 | 0 | 0 | FIN |  |  |  |  | 2001-07-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at King's Matelas | Individual | AFR | ALG | FOA | 27 | INV | 34 | A | O | I | CFC | 20 | 20 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2003-07-01 | 110179 | -213 | 109966 | 109966 | 100% | 0 | 0 |  | 14323.27 | -27.69 | 14295.58 | 0 | 0 | FIN |  |  |  |  | 2001-07-01
FIN | UNIDO | Project preparation in the commercial refrigeration sector (commercial) | Individual | AFR | ALG | REF | 27 | PRP | 35 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-10-01 | 1999-12-01 |  | 2000-11-01 | 2001-07-01 | 15000 | -11985 | 3015 | 3015 | 100% | 0 | 0 |  | 1950 | -1558.05 | 391.95 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | AFR | ALG | ARS | 27 | PRP | 36 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-11-01 | 2001-09-01 | 15000 | -621 | 14379 | 14379 | 100% | 0 | 0 |  | 1950 | -80.73 | 1869.27 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Matelas Mondial | Individual | AFR | ALG | FOA | 28 | INV | 37 | A | O | I | CFC | 20 | 20 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 97986 | -221 | 97765 | 97765 | 100% | 0 | 0 |  | 12738.18 | -28.73 | 12709.45 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC11/CFC12 by conversion to hydrocarbons technology in the manufacture of aerosols at Floreal | Individual | AFR | ALG | ARS | 28 | INV | 38 | A | O | I | CFC | 18.1 | 18.1 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-07-01 | 2002-09-01 | 77145 | -200 | 76945 | 76945 | 100% | 0 | 0 |  | 10028.85 | -26 | 10002.85 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Orania Mousse Ameublement (OMA) | Individual | AFR | ALG | FOA | 28 | INV | 39 | A | O | I | CFC | 18 | 18 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 99477 | -262 | 99215 | 99215 | 100% | 0 | 0 |  | 12932.01 | -34.06 | 12897.95 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | AFR | ALG | FOA | 30 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -33 | 19967 | 19967 | 100% | 0 | 0 |  | 2600 | -4.29 | 2595.71 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11/CFC-12 by conversion to hydrocarbon technology in the manufacture of aerosols at company Saco | Individual | AFR | ALG | ARS | 28 | INV | 41 | A | O | I | CFC | 19 | 19 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2002-02-01 | 2003-05-01 | 73691 | -191 | 73500 | 73500 | 100% | 0 | 0 |  | 9579.83 | -24.83 | 9555 | 0 | 0 | FIN | [6 empty] | 2002-03-01
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | AFR | ALG | REF | 31 | PRP | 43 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-06-01 | 2002-01-01 |  | 2003-01-01 | 2003-06-01 | 60000 | -1106 | 58894 | 58894 | 100% | 0 | 0 |  | 7800 | -143.78 | 7656.22 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the RCA (Société de Réfrigeration et de Conditionnement de l'air) | Individual | AFR | ALG | REF | 32 | INV | 47 | A | O | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-07-01 | 2003-05-01 |  | 2003-12-01 | 2004-12-01 | 351768 | -6411 | 345357 | 345357 | 100% | 0 | 0 |  | 45729.84 | -833.43 | 44896.41 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN.
ONG | UNIDO | Project preparation to replace methyl bromide in fumigation of dates in ten units | Individual | AFR | ALG | FUM | 34 | PRP | 50 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 12300 | 49.2% | 12700 | 0 | 1 | 3250 | 0 | 1599 | 1651 | 0 | Alternative has not yet been identified. PRP is kept until suitable alternative is found. | [10 empty] | 2001 | INV
CLO | UNIDO | Preparation of 8 investment projects in the aerosol sector | Individual | AFR | ALG | ARS | 36 | PRP | 52 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of a refrigeration sectoral phase-out plan | Individual | AFR | ALG | REF | 36 | PRP | 53 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-07-01 |  | 2004-12-01 | 2005-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Financial completion in Nov 2005. | [10 empty] | 2002 | INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector (includes: training in good refrigerant management practices, training of customs officers, and national recovery and recycling) | RMP | AFR | ALG | REF | 37 | TAS | 55 | A | O | I | CFC | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2003-12-01 |  | 2004-06-01 | 2004-07-01 | 200000 | -46 | 199954 | 199954 | 100% | 0 | 0 |  | 26000 | -5.98 | 25994.02 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the first group of commercial refrigerator manufacturers | Individual | AFR | ALG | REF | 37 | INV | 56 | A | O | I | CFC | 18.6 | 18.6 |  |  | 2002-07-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 |  | 224320 | 0 | 224320 | 154442 | 68.85% | 69878 | 62662 | 62662 | 29161.6 | 0 | 20077.46 | 9084.14 | 8146.06 | [11 empty] | 2002 | INV
COM | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector (including training in good refrigerant management practices, training of customs officers, and national recovery and recycling): Second tranche | RMP Update | AFR | ALG | REF | 39 | TAS | 58 | A | O | I | CFC | 45 | 110 |  |  | 2003-04-01 | 2004-03-01 | 2004-04-01 |  | 2005-06-01 |  | 700000 | 0 | 700000 | 677062 | 96.72% | 22938 | 22797 | 22797 | 52500 | 0 | 50779.65 | 1720.35 | 1709.775 | Project completed in Jun 2005. | [10 empty] | 2003
ONG | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector: 2004 programme | RMP Update | AFR | ALG | REF | 42 | TAS | 59 | A | O | I | CFC | 200 | 90 |  |  | 2004-04-01 | 2004-12-01 | 2005-04-01 | 2006-11-01 |  |  | 524647 | 0 | 524647 | 304537 | 58.05% | 220110 | 137035 | 177035 | 39348.525 | 0 | 22840.275 | 16508.25 | 10277.625 | Recovery and recycling equipment was delivered and distributed. A partial phase-out of 90 ODP tonnes was achieved. Training on delivered equipment will take place last week of Feb 2006. Terms of reference for monitoring component are being prepared. Project is expected to be completed by Nov 2006. | [10 empty] | 2004 | INV
ONG | UNIDO | Conversion of CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the last group of commercial refrigerator manufactures ( refrigeration sector terminal project) | Individual | AFR | ALG | REF | 44 | INV | 62 | A | O | I | CFC | 72.8 | 0 |  |  | 2004-12-01 |  | 2007-04-01 | 2007-04-01 |  |  | 589000 | 0 | 589000 | 258 | 0.0438% | 588742 | 112310 | 250000 | 44175 | 0 | 19.35 | 44155.65 | 8423.25 | Refrigeration equipment was ordered. Foaming equipment will be reallocated to the two companies from a completed project where the company went bankrupt (ALG/REF/32/INV/47). Installation of foaming and refrigeration equipment is expected by third quarter of 2006. | [10 empty] | 2004 | INV
ONG | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | ALG | PHA | 46 | PRP | 63 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 |  | 2006-03-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 1875 | 0 | 0 | 1875 | 0 | PRP project was approved by 46th ExCom in July 2005. Detailed background information has been collected. Project is under preparation. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the foam production at BANDEX, CELPACK & PRENSIPLANT | Individual | LAC | ARG | FOA | 11 | PRP | 05 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-12-01 | 1998-08-01 | 35000 | 8990 | 43990 | 43990 | 100% | 0 | 0 |  | 4550 | 1168.7 | 5718.7 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of ODS at Bandex S.A. | Individual | LAC | ARG | FOA | 13 | INV | 09 | A | O | I | CFC | 214 | 214 |  |  | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1995-11-01 | 1998-08-01 | 517630 | -1375 | 516255 | 516255 | 100% | 0 | 0 |  | 67291.9 | -178.75 | 67113.15 | 0 | 0 | FIN
FIN | UNIDO | Phase out of ODS at CELPACK S.A. | Individual | LAC | ARG | FOA | 13 | INV | 10 | A | O | I | CFC | 135 | 135 |  |  | 1994-07-01 | 1994-12-01 | 1995-07-01 |  | 1995-12-01 | 1998-08-01 | 503094 | 377 | 503471 | 503471 | 100% | 0 | 0 |  | 65402.22 | 49.01 | 65451.23 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | LAC | ARG | FOA | 18 | PRP | 32 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -523 | 19477 | 19477 | 100% | 0 | 0 |  | 2600 | -67.99 | 2532.01 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 at Mallol Saic | Individual | LAC | ARG | FOA | 20 | INV | 47 | A | O | I | CFC | 36.5 | 36.5 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2003-12-01 | 2004-03-01 | 299344 | -402 | 298942 | 298942 | 100% | 0 | 0 |  | 38914.72 | -52.26 | 38862.46 | 0 | 0 | FIN |  |  | 1998-04-01 | 2000-06-01
FIN | UNIDO | Phasing out of CFC-12 at Multiespuma Saic | Individual | LAC | ARG | FOA | 20 | INV | 49 | A | O | I | CFC | 60 | 60 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2000-12-01 | 2001-11-01 | 282438 | -12410 | 270028 | 270028 | 100% | 0 | 0 |  | 36716.94 | -1613.3 | 35103.64 | 0 | 0 | FIN |  |  | 1998-04-01 | 2000-06-01
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | ARG | SEV | 21 | PRP | 52 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 2000-06-02 | 2002-05-01 | 32140 | -1 | 32139 | 32139 | 100% | 0 | 0 |  | 4178.2 | -0.13 | 4178.07 | 0 | 0 | FIN |  |  |  | 1999-06-01
CLO | UNIDO | Phasing out of CFCs in the manufacturing plant of domestic refrigerators of Radio Victoria Catamarca, S.A. | Individual | LAC | ARG | REF | 22 | INV | 58 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  |  | 2001-07-01 | 599896 | -454544 | 145352 | 145352 | 100% | 0 | 0 |  | 77986.48 | -59090.72 | 18895.76 | 0 | 0 | CLO
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Frare S.A., Buenos Aires | Individual | LAC | ARG | REF | 23 | INV | 64 | A | O | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-05-01 | 2002-09-01 | 514384 | -3112 | 511272 | 511272 | 100% | 0 | 0 |  | 66869.92 | -404.56 | 66465.36 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Bambi S.A., Santa Fe | Individual | LAC | ARG | REF | 23 | INV | 67 | A | O | I | CFC | 30.6 | 30.6 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 515258 | -182 | 515076 | 515076 | 100% | 0 | 0 |  | 66983.54 | -23.66 | 66959.88 | 0 | 0 | FIN
FIN | UNIDO | Demonstration Project: Open and closed circuit non-soil cultivation as main alternatives to the use of methyl bromide in tomato, cut flowers and strawberry production | Individual | LAC | ARG | FUM | 23 | DEM | 71 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-06-01 | 2002-09-01 | 481800 | -19845 | 461955 | 461955 | 100% | 0 | 0 |  | 62634 | -2579.85 | 60054.15 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | ARG | FOA | 27 | PRP | 84 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 40000 | -2 | 39998 | 39998 | 100% | 0 | 0 |  | 5200 | -0.26 | 5199.74 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (flowers) | Individual | LAC | ARG | FUM | 27 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 40000 | -5676 | 34324 | 34324 | 100% | 0 | 0 |  | 5200 | -737.88 | 4462.12 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (strawberries, tomatoes) | Individual | LAC | ARG | FUM | 27 | PRP | 89 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-14 | 2000-11-09 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid P.U. foams: umbrella project (Tarco, Mondino, Schaum, Fadep, Occhipinti and Friolatina) | Individual | LAC | ARG | FOA | 29 | INV | 97 | A | O | I | CFC | 30.4 | 30.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2001-06-01 | 2002-09-01 | 227048 | -56 | 226992 | 226992 | 100% | 0 | 0 |  | 29516.24 | -7.28 | 29508.96 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of methyl bromide in strawberry, protected vegetables and cut flower production | Individual | LAC | ARG | FUM | 30 | INV | 105 | A | O | I | MBR | 331 | 224.4 |  |  | 2000-03-01 | 2000-07-01 | 2015-01-01 | 2015-01-01 |  |  | 3183390 | 0 | 3183390 | 2957023 | 92.89% | 226367 | 186300 | 50000 | 360172.9 | 0 | 335272.53 | 24900.37 | 20493 | According to the revised agreement approved by 45th ExCom in Apr 2005, the project will be mainly implemented until 2010 leaving a small consumption till 2015. Subcontractor (INTA) continued to provide training and assistance to farmers. Equipment will be transferred to the Farmers Association in 2006.
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141B as a blowing agent in the manufacture of P.U. blocks and tank spraying at Polwer S.R.L. | Individual | LAC | ARG | FOA | 28 | INV | 110 | A | O | I | CFC | 26.8 | 26.8 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2001-06-01 | 2002-11-01 | 111641 | -246 | 111395 | 111395 | 100% | 0 | 0 |  | 14513.33 | -31.98 | 14481.35 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams at 7 companies (Aislaciones y Servicios Maximo; Baduco D and D; Bolatti; Hi-Tec Poliuretano Alberto; Najera Jose; Stefanelli Vincer, SRL) | Individual | LAC | ARG | FOA | 32 | INV | 117 | A | O | I | CFC | 46.1 | 46.1 |  |  | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-06-01 | 2004-09-01 | 329495 | -283 | 329212 | 329212 | 100% | 0 | 0 |  | 42834.35 | -36.79 | 42797.56 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 118 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2003-10-01 | 2003-12-01 | 35000 | -954 | 34046 | 34046 | 100% | 0 | 0 |  | 4550 | -124.02 | 4425.98 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of umbrella project in the commercial refrigeration sector | Individual | LAC | ARG | REF | 36 | PRP | 124 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-05-01 | 2003-05-01 | 25000 | -30 | 24970 | 24970 | 100% | 0 | 0 |  | 3250 | -3.9 | 3246.1 | 0 | 0 | FIN | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of an investment project in the solvents sector (CFC-113 and TCA) | Individual | LAC | ARG | SOL | 36 | PRP | 125 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 40000 | -1188 | 38812 | 38812 | 100% | 0 | 0 |  | 5200 | -154.44 | 5045.56 | 0 | 0 | FIN | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | ARG | REF | 36 | PRP | 127 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2004-08-01 |  | 2004-08-01 | 2004-08-01 | 100000 | -83 | 99917 | 99917 | 100% | 0 | 0 |  | 13000 | -10.79 | 12989.21 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
CLO | UNIDO | Preparation of country programme update | Individual | LAC | ARG | SEV | 39 | CPG | 134 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 |  | 2004-10-01 |  |  | 2005-08-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Financial completion in Aug 2005. Refund was reported to 47th ExCom, Nov 2005. CLO. | [10 empty] | 2003
ONG | UNIDO | Plan for phase-out of ODS in the solvent sector | Individual | LAC | ARG | SOL | 41 | INV | 137 | A | O | I | CFC CTC TCA | 42 | 34.4 |  |  | 2003-12-01 | 2004-04-01 | 2009-12-01 | 2009-12-01 |  |  | 635986 | 0 | 635986 | 157417 | 24.75% | 478569 | 29498 | 35000 | 47698.95 | 0 | 11806.275 | 35892.675 | 2212.35 | A new survey of small-scale industries using ODS solvents started in Sep 2005. A partial phase-out of 14.4 ODP tonnes was achieved in 2005 through the phase-out of CTC from cleaning operations and TCA from formulation of cleaning degreasers. Contracts will be awarded to local companies to conduct tests with new solvents. Further search for local companies consuming ozone-depleting solvents. | [10 empty] | 2003 | INV
ONG | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | ARG | PHA | 42 | INV | 138 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 | 2006-12-01 |  |  | 2740000 | 0 | 2740000 | 735553 | 26.85% | 2004447 | 264648 | 1 | 205500 | 0 | 55166.475 | 150333.525 | 19848.6 | Office staff of the Government were trained. In 2006, additional technicians training was carried out. First batch of equipment for technicians was supplied and is being distributed. All equipment for manufacturing sector was delivered. Implementation will continue according to the approved implementation programme. | [10 empty] | 2003 | INV | 3220 | 2212 |  |  | Yes | Yes | Yes
ONG | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | ARG | PHA | 47 | INV | 147 | A | O | I | CFC | 100 | 100 |  |  | 2005-11-01 |  | 2006-12-01 | 2007-10-01 |  |  | 1850000 | 0 | 1850000 | 0 | 0% | 1850000 | 0 | 300000 | 138750 | 0 | 0 | 138750 | 0 | 2006 work programme was approved by 47th ExCom in Nov 2005. A total phase-out of 100 ODP tonnes was achieved. In 2006, additional technicians training was carried out. First batch of equipment for technicians was supplied and is being distributed. All equipment for manufacturing sector was delivered. Implementation will continue according to the approved implementation programme. | [10 empty] | 2005 | INV | 2047 | 1675.6 |  |  | Yes | No | No
ONG | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | ASP | BAH | SOL | 45 | TAS | 14 | A | O | I | CTC TCA | 1.7 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 15000 | 5400 | 0 | 0 | 5400 | 0 | Project was approved by 45th ExCom in Apr 2005. National expert was identified by the National Ozone Unit to undertake the survey of CTC/TCA users. Training is planned during the first half of 2006. | [10 empty] | 2005 | INV
FIN | UNIDO | Preparation of project for retrofitting in all ice-making systems, icebin compressor systems, blast freezers, cold storage and chiller rooms | Individual | LAC | BAR | REF | 15 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | CFC-recovery, recycling and training in refrigeration | RMP | LAC | BAR | REF | 18 | TAS | 04 | A | O | I | CFC | 14 | 14 |  |  | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 1997-06-01 | 2000-07-01 | 165170 | -483 | 164687 | 164687 | 100% | 0 | 0 |  | 21472.1 | -62.79 | 21409.31 | 0 | 0 | FIN
ONG | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | AFR | BDI | SOL | 45 | TAS | 19 | A | O | I | TCA | 0.1 | 0 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 | 2006-09-01 |  |  | 35000 | 0 | 35000 | 2013 | 5.751% | 32987 | 9 | 15000 | 3150 | 0 | 181.17 | 2968.83 | 0.81 | Project was approved by 45th ExCom in Apr 2005. National expert has been identified by the National Ozone Unit to undertake the survey of TCA users. Potential subcontractors are to be determined. Training is planned for the second quarter of 2006. | [10 empty] | 2005 | INV
CLO | UNIDO | Preparation of investment project for ODS phase-out in a foam producing plant (SIBAO) | Individual | AFR | BEN | FOA | 17 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 |  | 1995-09-01 |  |  | 1998-08-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BEN | REF | 22 | TAS | 04 | A | O | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 114000 | -97 | 113903 | 113903 | 100% | 0 | 0 |  | 14820 | -12.61 | 14807.39 | 0 | 0 | FIN
FIN | UNIDO | Country Programme Preparation | Individual | EUR | BHE | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 80000 | -19 | 79981 | 79981 | 100% | 0 | 0 |  | 10400 | -2.47 | 10397.53 | 0 | 0 | FIN
COM | UNIDO | Establishment of an Ozone Unit | Individual | EUR | BHE | SEV | 27 | INS | 02 | N | T | I |  | 0 | 0 |  |  | 1999-03-01 | 2001-05-01 | 2002-04-01 |  | 2004-12-01 | 2005-12-01 | 110000 | 0 | 110000 | 104543 | 95.04% | 5457 | 0 | 1 | 14300 | 0 | 13590.59 | 709.41 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [5 empty] | 2003-12-01
CLO | UNIDO | Project preparation in the aerosol sector | Individual | EUR | BHE | ARS | 30 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-04-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | EUR | BHE | FOA | 30 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-08-01 | 2001-04-01 |  | 2002-10-01 | 2003-06-01 | 15000 | -261 | 14739 | 14739 | 100% | 0 | 0 |  | 1950 | -33.93 | 1916.07 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial/ domestic refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 05 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -8036 | 6964 | 6964 | 100% | 0 | 0 |  | 1950 | -1044.68 | 905.32 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-04-01 | 15000 | -1634 | 13366 | 13366 | 100% | 0 | 0 |  | 1950 | -212.42 | 1737.58 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of two investment projects in the flexible foam sector | Individual | EUR | BHE | FOA | 34 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-08-01 | 2002-08-01 |  | 2004-01-01 | 2004-04-01 | 15000 | -761 | 14239 | 14239 | 100% | 0 | 0 |  | 1950 | -98.93 | 1851.07 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Inga Co. | Individual | EUR | BHE | FOA | 35 | INV | 08 | A | O | I | CFC | 21 | 21 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2005-12-01 |  | 101950 | 0 | 101950 | 96571 | 94.72% | 5379 | 1816 | 1816 | 13253.5 | 0 | 12554.23 | 699.27 | 236.08 | Project completed in Dec 2005. | [10 empty] | 2001 | INV
COM | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with cyclopentane in the manufacture of commercial refrigeration equipment at Bira, Bihac | Individual | EUR | BHE | REF | 35 | INV | 09 | A | O | I | CFC | 29 | 29 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2005-12-01 |  | 536956 | 0 | 536956 | 453161 | 84.39% | 83795 | 83000 | 83000 | 69065.16 | 0 | 58910.93 | 10154.23 | 10066.78 | Project completed in Dec 2005. | [10 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerants CFC-12 and R-502 with HFC-134a and R-404A, and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment and cold refrigeration chambers at Soko | Individual | EUR | BHE | REF | 35 | INV | 10 | A | O | I | CFC | 17.4 | 17.4 |  |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-05-01 | 159707 | -1070 | 158637 | 158637 | 100% | 0 | 0 |  | 20761.91 | -139.1 | 20622.81 | 0 | 0 | Financial completion in May 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of two investment projects in the commercial refrigeration sector | Individual | EUR | BHE | REF | 36 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -3482 | 11518 | 11518 | 100% | 0 | 0 |  | 1950 | -452.66 | 1497.34 | 0 | 0 | FIN | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of an investment project in the rigid foam sector | Individual | EUR | BHE | FOA | 36 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-09-01 | 2003-04-01 |  | 2004-01-01 | 2004-12-01 | 15000 | -440 | 14560 | 14560 | 100% | 0 | 0 |  | 1950 | -57.2 | 1892.8 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | BHE | PHA | 36 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2003-12-01 | 2005-05-01 | 80000 | -2046 | 77954 | 77954 | 100% | 0 | 0 |  | 10400 | -265.98 | 10134.02 | 0 | 0 | Financial completion in May 2005. | [10 empty] | 2002 | INV
COM | UNIDO | Replacement of CFC-12 with HFC-134a, CFC-11 with HCFC-141b, and TCA with non-cleaning process in the manufacture of commercial refrigeration equipment, panels, and heat exchangers at three enterprises (Soko Paneli, Soko IPV and Kuca Leda) | Individual | EUR | BHE | REF | 39 | INV | 14 | A | O | I | CFC TCA | 13.7 | 13.7 |  |  | 2003-04-01 | 2003-11-01 | 2004-07-01 |  | 2005-12-01 |  | 175283 | 0 | 175283 | 138508 | 79.02% | 36775 | 4380 | 4380 | 15775.47 | 0 | 12465.72 | 3309.75 | 394.2 | Project completed in Dec 2005. | [10 empty] | 2002
ONG | UNIDO | Phase-out of CFC-11 by conversion to n-pentane in the manufacture of rigid foam products for insulating purposes at Stirokart Co. | Individual | EUR | BHE | FOA | 39 | INV | 15 | A | O | I | CFC | 33 | 0 |  |  | 2003-04-01 | 2004-04-01 | 2004-07-01 | 2006-11-01 |  |  | 364650 | 0 | 364650 | 305246 | 83.71% | 59404 | 54448 | 54400 | 27348.75 | 0 | 22893.45 | 4455.3 | 4083.6 | Project is monitored under project implementation delays as reported to the 48th ExCom in Apr 2006. Missing press was delivered. However, preparatory works at project site have not been finalized as planned. Final equipment installations are envisaged in June 2006. Project is planned to be completed by Nov 2006 after issuance of safety certification. | [10 empty] | 2002
ONG | UNIDO | National ODS phase-out plan (first trance) | Multi-Year | EUR | BHE | PHA | 41 | INV | 16 | A | O | I | CFC TCA | 0 | 27.3 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 | 2006-07-01 |  |  | 265300 | 0 | 265300 | 209275 | 78.88% | 56025 | 51768 | 55000 | 19897.5 | 0 | 15695.625 | 4201.875 | 3882.6 | Technical specification for purchase of equipment for seven commercial refrigeration companies was prepared. Procurement was finalized and foaming equipment was delivered. Refrigeration part of equipment was delivered in Mar 2006. Terms of reference for ODS consumption verification audit were prepared and submitted to NOU for competitive bidding. Draft audit report which was submitted by contractor in 2006, is being discussed with NOU. A phase-out of 27.3 ODP tonnes was achieved in 2005 by implementing the foam and production refrigeration component of the programme. Non-compliance in the solvent sector will be solved through phase-out of TCA at the only ODS consuming company. | [10 empty] | 2003 | INV | 168.7 | 190.3 |  |  | No | No | No
ONG | UNIDO | Phase-out of methyl bromide in tobacco seedling vegetables and flower production sector | Individual | EUR | BHE | FUM | 41 | INV | 17 | A | O | I | MBR | 11.8 | 6.2 |  |  | 2003-12-01 | 2004-08-01 | 2006-12-01 | 2006-09-01 |  |  | 229000 | 0 | 229000 | 205427 | 89.71% | 23573 | 5469 | 15000 | 20610 | 0 | 18488.43 | 2121.57 | 492.21 | Farmers of tobacco, vegetables and flowers were trained. Walk-in tunnels were delivered and installed. The 2005 phase-out reduction of 6.2 ODP tonnes was achieved. Project is planned to be completed by Sep 2006 after local purchase of micro-tunnels. | [10 empty] | 2003 | INV
ONG | UNIDO | Phase-out of halon consumption | Individual | EUR | BHE | HAL | 42 | TAS | 18 | A | O | I | HAL | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2006-04-01 | 2006-12-01 |  |  | 64600 | 0 | 64600 | 3406 | 5.272% | 61194 | 21 | 45000 | 5814 | 0 | 306.54 | 5507.46 | 1.89 | Report on survey of the halon sector was prepared by national consultant. Awareness workshop on halon management is planned for May 2006. After the workshop, beneficiary for halon recycling equipment will be identified. | [10 empty] | 2003 | INV
ONG | UNIDO | Extension of institutional strengthening: phase II | Individual | EUR | BHE | SEV | 43 | INS | 19 | N | T | I |  | 0 | 0 |  |  | 2004-07-01 |  | 2006-07-01 | 2007-12-01 |  |  | 95333 | 0 | 95333 | 0 | 0% | 95333 | 0 | 20000 | 7149.975 | 0 | 0 | 7149.975 | 0 | Following the designation of a new Ozone Officer (OO), practical training was provided/arranged by UNEP to enable her to understand MP requirements and tasks of an OO. In a meeting between OO, UNEP and UNIDO, IS support was discussed, including non-compliance of the country with regard to licensing system. Upon request, additional detailed information was provided by UNIDO in writing on the achievements of Phase I and on the nature of IS support granted by the Multilateral Fund in general. ODS licensing system was drafted in 2005 with the assistance of the Ozone Secretariat and UNIDO. A joint letter to the three Ministries of State and Entity level was prepared to facilitate adoption of the ODS lycensing system, which could however not be sent as the relevant coordinates have not been communicated by the OO to UNEP. A joint high-level mission by UNIDO and UNEP was offered to clarify to the relevant ministries the important tasks of an Ozone Unit to achieve the country's commitments towards the MP, but no reaction/official request has been received so far from the Ozone Unit. The project document is to date unsigned. | [10 empty] | 2004 | NON-INV
ONG | UNIDO | National ODS Phase-out Plan: second tranche | Multi-Year | EUR | BHE | PHA | 44 | INV | 21 | A | O | I | CFC TCA | 0 | 0 |  |  | 2004-12-01 | 2005-12-01 | 2005-12-01 | 2006-10-01 |  |  | 295860 | 0 | 295860 | 993 | 0.3356% | 294867 | 0 | 150000 | 22189.5 | 0 | 74.475 | 22115.025 | 0 | Non-compliance in the solvent sector will be solved through phase-out of TCA at the only ODS consuming company. | [10 empty] | 2004 | INV | 103.2 | not available |  |  | not available | No | No
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BKF | REF | 22 | TAS | 05 | A | O | I | CFC | 15.48 | 15.48 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | FIN
FIN | UNIDO | Workshop to raise awareness on use of methyl bromide in tobacco cultivation | Individual | AFR | BKF | FUM | 34 | TRA | 14 | A | O | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-01-01 | 2002-08-01 |  | 2002-12-01 | 2003-06-01 | 30000 | -7533 | 22467 | 22467 | 100% | 0 | 0 |  | 3900 | -979.29 | 2920.71 | 0 | 0 | FIN | [10 empty] | 2001 | NON-INV
FIN | UNIDO | Preparation of a demonstration project (grain fumigation) | Individual | AFR | BOT | FUM | 24 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1987 | 23013 | 23013 | 100% | 0 | 0 |  | 3250 | -258.31 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: non-soil cultivation techniques, bio-fumigation with solarization, and application of various mixtures of other chemicals in low doses in tomatoes and curcubits | Individual | AFR | BOT | FUM | 25 | DEM | 05 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-11-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 146300 | 0 | 146300 | 146300 | 100% | 0 | 0 | 0 | 19019 | 0 | 19019 | 0 | 0 | Financial completion in Dec 2005.
FIN | UNIDO | Preparation of investment projects for elimination of CFCs in the polymer foams manufacturing | Individual | LAC | BRA | FOA | 09 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-09-01 |  | 1996-08-01 | 1999-08-01 | 150000 | -5374 | 144626 | 144626 | 100% | 0 | 0 |  | 19500 | -698.62 | 18801.38 | 0 | 0 | FIN
FIN | UNIDO | Conversion of the assembly of refrigeration compressors to phase out CFC-12 and CFC/HCFC-502 by using HFC-134a and R-404a at Elgin Maquinas SA | Individual | LAC | BRA | REF | 17 | INV | 20 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-10-01 | 1999-07-01 |  | 1998-12-01 | 2001-07-01 | 460339 | 0 | 460339 | 460339 | 100% | 0 | 0 |  | 59844.07 | 0 | 59844.07 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in a plant (Elgin) consuming 60 metric tons of TCA used as a degreasing agent in the production of compressors | Individual | LAC | BRA | SEV | 17 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-05-01 | 1995-09-01 |  | 1997-10-01 | 1998-08-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of ODS at Frisokar Equipamentos Plasticos Ltd. | Individual | LAC | BRA | FOA | 17 | INV | 26 | A | O | I | CFC | 42 | 42 |  |  | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1997-10-01 | 2000-07-01 | 267948 | -13924 | 254024 | 254024 | 100% | 0 | 0 |  | 34833.24 | -1810.12 | 33023.12 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from 1,1,1 TCA to aqueous cleaning and using trichlorethane at Elgin Maquinas SA | Individual | LAC | BRA | SOL | 18 | INV | 39 | A | O | I | TCA | 6 | 6 |  |  | 1995-11-01 | 1996-12-01 | 1997-02-01 |  | 1997-11-01 | 1999-08-01 | 156567 | -6288 | 150279 | 150279 | 100% | 0 | 0 |  | 20353.71 | -817.44 | 19536.27 | 0 | 0 | FIN
FIN | UNIDO | Formulation of two investment projects in the commercial and domestic refrigerator sector | Individual | LAC | BRA | REF | 18 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-02-01 |  | 1997-12-01 | 1998-08-01 | 50000 | 87 | 50087 | 50087 | 100% | 0 | 0 |  | 6500 | 11.31 | 6511.31 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-12 by HFC-134a as refrigerant and CFC-11 by cyclopentane as foam blowing agent in commercial refrigeration equipment for supermarkets at Eletrofrio S/A | Individual | LAC | BRA | REF | 20 | INV | 54 | A | O | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-07-01 | 1998-10-01 |  | 1999-12-01 | 2001-12-01 | 610650 | -481 | 610169 | 610169 | 100% | 0 | 0 |  | 79384.5 | -62.53 | 79321.97 | 0 | 0 | FIN
CLO | UNIDO | Phase out of 1,1,1 TCA at Teperman | Individual | LAC | BRA | SOL | 20 | INV | 58 | A | O | R |  | 0 | 0 |  |  | 1996-10-01 |  | 1998-10-01 |  |  | 2000-06-01 | 152176 | -152176 | 0 | 0 |  | 0 | 0 |  | 19782.88 | -19782.88 | 0 | 0 | 0 | CLO
CLO | UNIDO | Elimination of 1,1,1 TCA used for autoparts cleaning at Brosol | Individual | LAC | BRA | SOL | 20 | INV | 59 | A | O | I |  | 0 | 0 |  |  | 1996-10-01 |  | 1997-10-01 |  |  | 1999-03-01 | 178361 | -178361 | 0 | 0 |  | 0 | 0 |  | 23186.93 | -23186.93 | 0 | 0 | 0 | CLO
FIN | UNIDO | Elimination of 1,1,1 TCA used as solvent at Rodabras | Individual | LAC | BRA | SOL | 20 | INV | 60 | A | O | I | TCA | 4.2 | 4.2 |  |  | 1996-10-01 | 1998-09-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 151577 | -315 | 151262 | 151262 | 100% | 0 | 0 |  | 19705.01 | -40.95 | 19664.06 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 TCA used for the formulation of tapping fluids at Tapmatic | Individual | LAC | BRA | SOL | 20 | INV | 61 | A | O | I | TCA | 9.9 | 9.9 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1997-12-01 | 2001-12-01 | 194500 | -27647 | 166853 | 166853 | 100% | 0 | 0 |  | 25285 | -3594.11 | 21690.89 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | BRA | SEV | 21 | PRP | 63 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-06-01 | 2000-12-01 | 57140 | -807 | 56333 | 56333 | 100% | 0 | 0 |  | 7428.2 | -104.91 | 7323.29 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNIDO | Demonstration project: three alternatives to the use of methyl bromide: non-soil cultivation, solarization and low-dose chemicals | Individual | LAC | BRA | FUM | 22 | DEM | 73 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2000-05-01 | 2002-09-01 | 393800 | -28691 | 365109 | 365109 | 100% | 0 | 0 |  | 51194 | -3729.83 | 47464.17 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFC-12 by HFC-134a and CFC-11 by cyclopentane in the production of commercial refrigeration equipment at Refrigeracao Rubra | Individual | LAC | BRA | REF | 23 | INV | 83 | A | O | I | CFC | 21.8 | 0 |  |  | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-10-01 | 320540 | -199971 | 120569 | 120569 | 100% | 0 | 0 |  | 41670.2 | -25996.23 | 15673.97 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the commercial refrigeration sector (Tecpur, Crios, Panamante and others) | Individual | LAC | BRA | REF | 24 | PRP | 97 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 2000-07-01 | 2001-07-01 | 50000 | -2586 | 47414 | 47414 | 100% | 0 | 0 |  | 6500 | -336.18 | 6163.82 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with cyclopentane at Crios Industrial Ltd. (suppliers of Eletrofrio Company) | Individual | LAC | BRA | FOA | 25 | INV | 103 | A | O | I | CFC | 46 | 46 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 357270 | -383 | 356887 | 356887 | 100% | 0 | 0 |  | 46445.1 | -49.79 | 46395.31 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with cyclopentane in the production of commercial refrigeration equipment at Panamante Refrigeracao | Individual | LAC | BRA | REF | 25 | INV | 106 | A | O | I | CFC | 34.3 | 0 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  |  | 2002-09-01 | 377202 | -140624 | 236578 | 236578 | 100% | 0 | 0 |  | 49036.26 | -18281.12 | 30755.14 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the commercial refrigeration sector for four companies | Individual | LAC | BRA | REF | 27 | PRP | 119 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2001-03-01 | 2002-09-01 | 40000 | -8581 | 31419 | 31419 | 100% | 0 | 0 |  | 5200 | -1115.53 | 4084.47 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | BRA | FOA | 27 | PRP | 126 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 50000 | -9155 | 40845 | 40845 | 100% | 0 | 0 |  | 6500 | -1190.15 | 5309.85 | 0 | 0 | FIN
CLO | UNIDO | Project preparation in the aerosol sector | Individual | LAC | BRA | ARS | 27 | PRP | 127 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 1999-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-12 with HFC-134A and CFC-11 with HFC-141b at five commercial refrigeration companies (Arparna, Begel, Belliere, Genaredx and Katz Refrigeracao) (umbrella project) | Individual | LAC | BRA | REF | 28 | INV | 139 | A | O | I | CFC | 26 | 26 |  |  | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 485916 | -116063 | 369853 | 369853 | 100% | 0 | 0 |  | 63169.08 | -15088.19 | 48080.89 | 0 | 0 | FIN
CLO | UNIDO | Phase-out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polyethylene foams for thermal insulation and food packaging purposes at Epex Co. | Individual | LAC | BRA | FOA | 28 | INV | 141 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 |  | 2001-08-01 |  |  | 2001-07-01 | 632391 | -632391 | 0 | 0 |  | 0 | 0 |  | 79563.01 | -79563.01 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out methyl bromide in the entire Tobacco Sector | Individual | LAC | BRA | FUM | 28 | INV | 142 | A | O | I | MBR | 84.4 | 84.4 |  |  | 1999-07-01 | 2000-06-01 | 2002-08-01 |  | 2001-12-01 | 2002-10-01 | 2344440 | -23656 | 2320784 | 2320784 | 100% | 0 | 0 |  | 267888.4 | -2602.16 | 265286.24 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 30 | PRP | 159 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 25000 | -448 | 24552 | 24552 | 100% | 0 | 0 |  | 3250 | -58.24 | 3191.76 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigant/ methyl bromide sector (tobacco) | Individual | LAC | BRA | FUM | 27 | PRP | 165 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-04-01 | 2001-07-01 | 50000 | -3928 | 46072 | 46072 | 100% | 0 | 0 |  | 6500 | -510.64 | 5989.36 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Ingecold Ltda. | Individual | LAC | BRA | REF | 31 | INV | 170 | A | O | I | CFC | 1.7 | 1.7 |  |  | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 25320 | -60 | 25260 | 25260 | 100% | 0 | 0 |  | 3291.6 | -7.8 | 3283.8 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Klima Ltda. | Individual | LAC | BRA | REF | 31 | INV | 171 | A | O | I | CFC | 5.7 | 5.7 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 86464 | -13625 | 72839 | 72839 | 100% | 0 | 0 |  | 11240.32 | -1771.25 | 9469.07 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Tecnigel Ltda | Individual | LAC | BRA | REF | 31 | INV | 172 | A | O | I | CFC | 2.5 | 2.5 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 34000 | -693 | 33307 | 33307 | 100% | 0 | 0 |  | 4420 | -90.09 | 4329.91 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 and R-502 with HFC-134a and HFC-404A as well as of CFC-11 with HCFC-141 at Kalten Ltd. | Individual | LAC | BRA | REF | 31 | INV | 174 | A | O | I | CFC | 8.1 | 8.1 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2004-04-01 | 2004-09-01 | 122151 | -6342 | 115809 | 115809 | 100% | 0 | 0 |  | 15879.63 | -824.46 | 15055.17 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Metalplan Ltda. | Individual | LAC | BRA | REF | 31 | INV | 176 | A | O | I | CFC | 1.9 | 1.9 |  |  | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 28885 | -25 | 28860 | 28860 | 100% | 0 | 0 |  | 3755.05 | -3.25 | 3751.8 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Domnick Hunter Ltda. | Individual | LAC | BRA | REF | 31 | INV | 177 | A | O | I | CFC | 1.2 | 1.2 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 17971 | 0 | 17971 | 17971 | 100% | 0 | 0 |  | 2336.23 | 0 | 2336.23 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown and HCFC-141b technology at Sector Co. in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | LAC | BRA | FOA | 31 | INV | 186 | A | O | I | CFC | 17.7 | 17.7 |  |  | 2000-07-01 | 2001-11-01 | 2003-01-01 |  | 2002-12-01 | 2003-02-01 | 130490 | -51 | 130439 | 130439 | 100% | 0 | 0 |  | 16963.7 | -6.63 | 16957.07 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for six projects in the commercial/domestic refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 203 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -1700 | 23300 | 23300 | 100% | 0 | 0 |  | 3250 | -221 | 3029 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Project preparation for two projects in the integral skin sector | Individual | LAC | BRA | FOA | 33 | PRP | 204 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-06-01 | 2003-03-01 | 20000 | -646 | 19354 | 19354 | 100% | 0 | 0 |  | 2600 | -83.98 | 2516.02 | 0 | 0 | FIN | [10 empty] | 2001 | INV
CLO | UNIDO | Project preparation for four projects in the solvents (CTC) sector | Individual | LAC | BRA | SOL | 33 | PRP | 205 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  |  | 2003-05-01 | 30000 | -26817 | 3183 | 3183 | 100% | 0 | 0 |  | 3900 | -3486.21 | 413.79 | 0 | 0 | CLO | [10 empty] | 2001 | INV
FIN | UNIDO | Project preparation for two projects in the rigid foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 206 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-06-01 | 2003-06-01 | 20000 | -161 | 19839 | 19839 | 100% | 0 | 0 |  | 2600 | -20.93 | 2579.07 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Umbrella project for four enterprises converting from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a at EZ Industria, Menoncin, Unifrio and from CFC-12 to HFC-134a at Croydon | Individual | LAC | BRA | REF | 34 | INV | 219 | A | O | I | CFC | 30.18 | 30.18 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-04-01 | 2004-12-01 | 469452 | -95482 | 373970 | 373970 | 100% | 0 | 0 |  | 61028.76 | -12412.66 | 48616.1 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Danica Co. | Individual | LAC | BRA | FOA | 34 | INV | 222 | A | O | I | CFC | 146.6 | 146.6 |  |  | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2004-02-01 | 2004-06-01 | 616625 | -759 | 615866 | 615866 | 100% | 0 | 0 |  | 77828.75 | -83.49 | 77745.26 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the commercial refrigeration sector | Individual | LAC | BRA | REF | 34 | PRP | 223 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-06-01 | 2002-08-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -4093 | 20907 | 20907 | 100% | 0 | 0 |  | 3250 | -532.09 | 2717.91 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Umbrella project for two enterprises converting from CFC-11 and HCFC-141b and from CFC-12 to HFC-134a at Argi and Hornburg | Individual | LAC | BRA | REF | 35 | INV | 241 | A | O | I | CFC | 11.2 | 11.2 |  |  | 2001-12-01 | 2002-11-01 | 2004-05-01 |  | 2004-10-01 | 2005-05-01 | 108050 | -12593 | 95457 | 95457 | 100% | 0 | 0 |  | 14046.5 | -1637.09 | 12409.41 | 0 | 0 | Financial completion in May 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
COM | UNIDO | Assistance for the preparation of a survey on the consumption of methyl bromide | Individual | LAC | BRA | FUM | 38 | TAS | 263 | A | O | I | MBR | 0 | 0 |  |  | 2002-11-01 | 2004-04-01 | 2003-12-01 |  | 2005-09-01 |  | 40000 | 0 | 40000 | 37938 | 94.84% | 2062 | 1779 | 1779 | 5200 | 0 | 4931.94 | 268.06 | 231.27 | Project completed in Sep 2005. | [10 empty] | 2002 | NON-INV
COM | UNIDO | Project preparation in methyl bromide (tobacco, flowers, horticulture) | Individual | LAC | BRA | FUM | 44 | PRP | 269 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2005-12-01 |  | 40000 | 0 | 40000 | 38878 | 97.19% | 1122 | 1100 | 1100 | 3000 | 0 | 2915.85 | 84.15 | 82.5 | Project completed in Dec 2005. | [10 empty] | 2004
ONG | UNIDO | Total phase-out of MB used in tobacco, flowers, ornamentals, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 273 | A | O | I | MBR | 153.2 | 0 |  |  | 2005-07-01 | 2005-10-01 | 2007-07-01 | 2007-07-01 |  |  | 1450251 | 0 | 1450251 | 21732 | 1.498% | 1428519 | 285 | 400000 | 108768.825 | 0 | 1629.9 | 107138.925 | 21.375 | Project was approved by 46th ExCom in July 2005. Implementation agreement will be signed by the Brazilian authorities in Apr 2006. Subsequently, major part of the equipment will be purchased and farmers will be trained. | [10 empty] | 2005 | INV
FIN | UNIDO | Preparation of an investment project proposal for phase out of CFCs at FAEM, Cameroun | Individual | AFR | CMR | REF | 11 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-04-01 | 1994-11-01 |  | 1995-02-01 | 1998-08-01 | 20000 | -2074 | 17926 | 17926 | 100% | 0 | 0 |  | 2600 | -269.62 | 2330.38 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC at FAEM.SA | Individual | AFR | CMR | REF | 13 | INV | 05 | A | O | I | CFC | 62 | 62 |  |  | 1994-07-01 | 1995-11-01 | 1996-01-01 |  | 1996-06-01 | 2000-04-01 | 1935860 | -45792 | 1890068 | 1890068 | 100% | 0 | 0 |  | 251661.8 | -5952.96 | 245708.84 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project for phasing out CFC-11 in the manufacture of domestic refrigerators, freezers and air-conditioners at Union Camerounaise | Individual | AFR | CMR | REF | 15 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Union Camerounaise d'Entreprise | Individual | AFR | CMR | REF | 18 | INV | 07 | A | O | I | CFC | 115.1 | 115.1 |  |  | 1995-11-01 | 1996-12-01 | 1997-03-01 |  | 2001-12-01 | 2002-12-01 | 1321400 | -22939 | 1298461 | 1298461 | 100% | 0 | 0 |  | 171782 | -2982.07 | 168799.93 | 0 | 0 | FIN
CLO | UNIDO | Project formulation of investment projects in the foam and refrigeration sectors | Individual | AFR | CMR | SEV | 21 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  |  | 2001-07-01 | 50000 | -23686 | 26314 | 26314 | 100% | 0 | 0 |  | 6500 | -3079.18 | 3420.82 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 at Scimpos | Individual | AFR | CMR | FOA | 23 | INV | 10 | A | O | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-06-01 | 541350 | -1348 | 540002 | 540002 | 100% | 0 | 0 |  | 70375.5 | -175.24 | 70200.26 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sonopol | Individual | AFR | CMR | FOA | 23 | INV | 11 | A | O | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-02-01 | 506310 | -235 | 506075 | 506075 | 100% | 0 | 0 |  | 65820.3 | -30.55 | 65789.75 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | AFR | CMR | REF | 24 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1999-02-01 | 1999-04-01 |  | 2001-04-01 | 2001-11-01 | 30000 | -112 | 29888 | 29888 | 100% | 0 | 0 |  | 3900 | -14.56 | 3885.44 | 0 | 0 | FIN |  |  |  | 1999-05-01
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | AFR | CMR | FUM | 24 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1987 | 23013 | 23013 | 100% | 0 | 0 |  | 3250 | -258.31 | 2991.69 | 0 | 0 | FIN
COM | UNIDO | Two alternatives to the use of methyl bromide: non-soil cultivation techniques and application of various mixtures of other chemicals in low doses in tobacco | Individual | AFR | CMR | FUM | 25 | DEM | 16 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 160600 | 0 | 160600 | 159314 | 99.2% | 1286 | 0 | 1 | 20878 | 0 | 20710.82 | 167.18 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom.
ONG | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration servicing sector (includes: training in good refrigerant management practices, training of customs officers, and recovery and recycling programme) | Individual | AFR | CMR | REF | 38 | TAS | 18 | A | O | I | CFC | 112.6 | 82 |  |  | 2002-11-01 | 2003-03-01 | 2007-12-01 | 2007-12-01 |  |  | 522982 | 0 | 522982 | 406833 | 77.79% | 116149 | 36302 | 1 | 67528.02 | 0 | 52888.29 | 14639.73 | 4719.26 | Workshop on the use of recovery and recycling equipment took place in 4th quarter of 2005. Additional customs officers were trained and a partial phase-out of 36 ODP tonnes was achieved. Training of technicians will be completed in 2006. | [10 empty] | 2002 | NON-INV
ONG | UNIDO | Project preparation in the refrigeration sector | Individual | AFR | CMR | REF | 43 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2004-07-01 | 2005-03-01 | 2005-07-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 17110 | 68.44% | 7890 | 3200 | 7800 | 1875 | 0 | 1283.25 | 591.75 | 240 | National Phase-out Plan is under preparation for submission to 50th ExCom. Project is expected to be completed by Dec 2006. | [10 empty] | 2004 | NON-INV
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | LAC | COL | FUM | 21 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-08-01 |  | 1998-01-01 | 2001-07-01 | 7140 | -568 | 6572 | 6572 | 100% | 0 | 0 |  | 928.2 | -73.84 | 854.36 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in banana growing at Cenibanano | Individual | LAC | COL | FUM | 26 | DEM | 32 | A | O | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2002-12-01 | 2003-06-01 | 123200 | -572 | 122628 | 122628 | 100% | 0 | 0 |  | 16016 | -74.36 | 15941.64 | 0 | 0 | FIN
FIN | UNIDO | Elimination of ODS used in the production of compressors for household refrigerators at Jiaxipera Compressor Co. Ltd. | Individual | ASP | CPR | REF | 09 | PRP | 28 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-06-01 | 1996-03-01 |  | 1994-12-01 | 1998-08-01 | 36000 | 4294 | 40294 | 40294 | 100% | 0 | 0 |  | 4680 | 558.22 | 5238.22 | 0 | 0 | FIN
FIN | UNIDO | Conversion from halon 1211 to ABC dry powder and foam water spray at Nanjing Fire Fighting Equipment Factory | Individual | ASP | CPR | HAL | 15 | INV | 104 | A | O | I | HAL | 1110 | 1480 |  |  | 1994-12-01 | 1995-10-01 | 1996-12-01 |  | 1996-12-01 | 2000-12-01 | 496000 | -408 | 495592 | 495592 | 100% | 0 | 0 |  | 64480 | -53.04 | 64426.96 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 15 | PRP | 105 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-04-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 25000 | -9013 | 15987 | 15987 | 100% | 0 | 0 |  | 3250 | -1171.69 | 2078.31 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 by hydrocarbon isobutane and cyclopentane at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 17 | INV | 119 | A | O | I | CFC | 360 | 360 |  |  | 1995-07-01 | 1996-03-01 | 1997-07-01 |  | 2003-12-01 | 2004-12-01 | 2790320 | -1 | 2790319 | 2790319 | 100% | 0 | 0 |  | 362741.6 | -0.13 | 362741.47 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. |  |  | 1998-06-01 | 1999-12-01
FIN | UNIDO | Project formulation of investment projects in the halon sector in the 3 fire equipment factories (Xiangshan, Xiangshan No. 1 and Dalian Jinzhou) and in domestic refrigeration sectors and solvents | Individual | ASP | CPR | SEV | 17 | PRP | 132 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 1998-12-01 | 2000-07-01 | 100000 | -351 | 99649 | 99649 | 100% | 0 | 0 |  | 13000 | -45.63 | 12954.37 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Workshop on domestic and commercial refrigerator compressor conversion | Individual | ASP | CPR | REF | 17 | TRA | 133 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1998-08-01 | 40000 | 237 | 40237 | 40237 | 100% | 0 | 0 |  | 5200 | 30.81 | 5230.81 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment projects in the tobacco sector | Individual | ASP | CPR | OTH | 18 | PRP | 144 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1996-11-01 |  | 1999-12-01 | 2002-06-01 | 50000 | -1310 | 48690 | 48690 | 100% | 0 | 0 |  | 6500 | -170.3 | 6329.7 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Conversion of compressor production for domestic refrigerators from CFC-12 to hydrocarbon refrigerant at Jiaxipera compressor factory | Individual | ASP | CPR | REF | 18 | INV | 145 | A | O | I | CFC | 96 | 96 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 1490000 | -1 | 1489999 | 1489999 | 100% | 0 | 0 |  | 193700 | -0.13 | 193699.87 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at Hangzhou Huari Refrigerator Co. | Individual | ASP | CPR | REF | 18 | INV | 147 | A | O | I | CFC | 338 | 338 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 2827911 | -18345 | 2809566 | 2809566 | 100% | 0 | 0 |  | 367628.43 | -2384.85 | 365243.58 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Formulation of investment projects in the refrigeration sector with particular attention to domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 18 | PRP | 151 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-10-01 | 2000-07-01 | 55000 | -1 | 54999 | 54999 | 100% | 0 | 0 |  | 7150 | -0.13 | 7149.87 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Phasing out ODS at the X'ian Yuan Dong Compressor Co., Xi'an | Individual | ASP | CPR | REF | 19 | INV | 164 | A | O | I |  | 0 | 0 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1999-06-01 | 2000-12-01 | 1599000 | -8385 | 1590615 | 1590615 | 100% | 0 | 0 |  | 207870 | -1090.05 | 206779.95 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNIDO | Phasing out ODS at the compressor factory of the Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | REF | 19 | INV | 165 | A | O | I | CFC | 60 | 60 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1998-12-01 | 2002-05-01 | 899030 | -254 | 898776 | 898776 | 100% | 0 | 0 |  | 116873.9 | -33.02 | 116840.88 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Aucma Electric Appliances Group Co. | Individual | ASP | CPR | REF | 20 | INV | 173 | A | O | I | CFC | 708 | 708 |  |  | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 1998-12-01 | 2002-07-01 | 2914904 | -1477 | 2913427 | 2913427 | 100% | 0 | 0 |  | 378937.52 | -192.01 | 378745.51 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Household Refrigerator Compressor Factory of the Guangzhou Wanbao Compressor Group | Individual | ASP | CPR | REF | 20 | INV | 185 | A | O | I | CFC | 3 | 3 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 1999-10-01 | 2002-09-01 | 2250000 | -266 | 2249734 | 2249734 | 100% | 0 | 0 |  | 292500 | -34.58 | 292465.42 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the refrigeration (including compressors), solvents and methyl bromide sectors | Individual | ASP | CPR | SEV | 21 | PRP | 190 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1999-12-01 | 2002-09-01 | 182140 | -863 | 181277 | 181277 | 100% | 0 | 0 |  | 23678.2 | -112.19 | 23566.01 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in tobacco expansion in China | Individual | ASP | CPR | OTH | 09 | TAS | 193 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-05-01 | 1998-08-01 | 72000 | 4499 | 76499 | 76499 | 100% | 0 | 0 |  | 9360 | 584.87 | 9944.87 | 0 | 0 | FIN
FIN | UNIDO | Substituting halon in fire fighting equipment at Nanjing | Individual | ASP | CPR | HAL | 09 | PRP | 194 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-04-01 | 1996-03-01 |  | 1995-03-01 | 1998-08-01 | 36000 | -6972 | 29028 | 29028 | 100% | 0 | 0 |  | 4680 | -906.36 | 3773.64 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigeration plant of Hefei Meiling | Individual | ASP | CPR | REF | 22 | INV | 196 | A | O | I | CFC | 849 | 849 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1998-12-01 | 2002-09-01 | 3247877 | -49672 | 3198205 | 3198205 | 100% | 0 | 0 |  | 422224.01 | -6457.36 | 415766.65 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project on alternatives to the use of methyl bromide in soil fumigation | Individual | ASP | CPR | FUM | 22 | DEM | 201 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-08-01 | 443300 | -14623 | 428677 | 428677 | 100% | 0 | 0 |  | 57629 | -1900.99 | 55728.01 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Jiaxipera compressor factory | Individual | ASP | CPR | SOL | 22 | INV | 203 | A | O | I | CFC | 76 | 76 |  |  | 1997-05-01 | 1998-10-01 | 1998-12-01 |  | 1999-05-01 | 2000-04-14 | 308604 | 0 | 308604 | 308604 | 100% | 0 | 0 |  | 40118.52 | 0 | 40118.52 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Hualing refrigerator plant | Individual | ASP | CPR | REF | 22 | INV | 204 | A | O | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-04-01 | 879788 | -208532 | 671256 | 671256 | 100% | 0 | 0 |  | 114372.44 | -27109.16 | 87263.28 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zerowatt Electric Appliances Group | Individual | ASP | CPR | REF | 22 | INV | 207 | A | O | I | CFC | 423 | 423 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 2394178 | -14466 | 2379712 | 2379712 | 100% | 0 | 0 |  | 311243.14 | -1880.58 | 309362.56 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Zel Tianjin Compressor Co., Ltd. | Individual | ASP | CPR | REF | 22 | INV | 211 | A | O | I | CFC | 30 | 30 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 1999-07-01 | 962175 | 0 | 962175 | 962175 | 100% | 0 | 0 |  | 125082.75 | 0 | 125082.75 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from CFC-113 to trichloroethylene at Hangli Refrigeration Ltd. | Individual | ASP | CPR | SOL | 22 | INV | 212 | A | O | I | CFC | 28.8 | 28.8 |  |  | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1999-12-01 | 2001-03-01 | 217762 | -62 | 217700 | 217700 | 100% | 0 | 0 |  | 28309.06 | -8.06 | 28301 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | SOL | 22 | INV | 213 | A | O | I | CFC | 37.6 | 37.6 |  |  | 1997-05-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 1999-07-01 | 236242 | 0 | 236242 | 236242 | 100% | 0 | 0 |  | 30711.46 | 0 | 30711.46 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Yuhuan Compressor Factory in Kanmen Town in Yuhuan County, South East China | Individual | ASP | CPR | REF | 23 | INV | 219 | A | O | I | CFC | 116 | 116 |  |  | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1465155 | -11494 | 1453661 | 1453661 | 100% | 0 | 0 |  | 190470.15 | -1494.22 | 188975.93 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zhejiang Rongsheng Electric Co. Ltd., Zhejiang, Deqing Country | Individual | ASP | CPR | REF | 23 | INV | 220 | A | O | I | CFC | 177.8 | 177.8 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1053910 | -69372 | 984538 | 984538 | 100% | 0 | 0 |  | 137008.3 | -9018.36 | 127989.94 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Changshu Refrigerating Equipment Works (Baixue), Changsu | Individual | ASP | CPR | REF | 23 | INV | 221 | A | O | I | CFC | 425.7 | 425.7 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 3548775 | -526754 | 3022021 | 3022021 | 100% | 0 | 0 |  | 461340.75 | -68478.02 | 392862.73 | 0 | 0 | FIN
ONG | UNIDO | Phasing out ODS at the refrigerator plant of Bole Electric Appliances Group | Individual | ASP | CPR | REF | 23 | INV | 222 | A | O | I | CFC | 132 | 132 |  |  | 1997-11-01 | 1998-09-01 | 2007-04-01 | 2006-12-01 |  |  | 1469029 | -11 | 1469018 | 1355768 | 92.29% | 113250 | 0 | 50000 | 190973.77 | -4531.43 | 176249.84 | 10192.5 | 0 | Project was reinstated at the 45th ExCom in Apr 2005 with a duration of 24 months. Building on the new site was completed. Installation of equipment is in progress. Start-up of CFC-free production is expected by Dec 2006.
FIN | UNIDO | Phasing out ODS at the freezer plant of Xing Xing Electric Appliances Industrial Co. | Individual | ASP | CPR | REF | 23 | INV | 223 | A | O | I | CFC | 348 | 348 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2002-04-01 | 3346941 | -339213 | 3007728 | 3007728 | 100% | 0 | 0 |  | 435102.33 | -44097.69 | 391004.64 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a sectoral strategy in the tobacco sector | Individual | ASP | CPR | OTH | 24 | PRP | 237 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-11-01 | 2001-07-01 | 200000 | -8324 | 191676 | 191676 | 100% | 0 | 0 |  | 26000 | -1082.12 | 24917.88 | 0 | 0 | FIN |  |  |  | 1999-10-01
FIN | UNIDO | Preparation of investment projects (50 companies) in the foam sector (polysterene/polyethylene) | Individual | ASP | CPR | FOA | 24 | PRP | 240 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 100000 | -2466 | 97534 | 97534 | 100% | 0 | 0 |  | 13000 | -320.58 | 12679.42 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 25 enterprises (umbrella project) | Individual | ASP | CPR | FOA | 25 | INV | 248 | A | O | I | CFC | 1146 | 1146 |  |  | 1998-07-01 | 1998-12-01 | 2000-01-01 |  | 2000-12-01 | 2002-09-01 | 4488516 | -2624 | 4485892 | 4485892 | 100% | 0 | 0 |  | 583507.08 | -341.12 | 583165.96 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Hefei Hualing Electronic Co., Ltd. | Individual | ASP | CPR | REF | 25 | INV | 253 | A | O | I | CFC | 82.8 | 82.8 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 785984 | -9497 | 776487 | 776487 | 100% | 0 | 0 |  | 102177.92 | -1234.61 | 100943.31 | 0 | 0 | FIN
CLO | UNIDO | Conversion from CFC-12 to isobutane technologies and products at the compressor factory of the Hangli Refrigeration Ltd., in Hangzhou, China | Individual | ASP | CPR | REF | 26 | INV | 256 | A | O | I | CFC | 0 | 0 |  |  | 1998-11-01 | 1999-11-01 | 2001-12-01 |  |  | 2003-12-01 | 861000 | -181871 | 679129 | 679129 | 100% | 0 | 0 |  | 104710 | -20005.81 | 84704.19 | 0 | 0 | CLO
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b foam blowing agent and CFC-12 with HFC-134a in the manufacture of domestic refrigerators/ freezers at the Beijing Freezing Equipment Factory. | Individual | ASP | CPR | REF | 26 | INV | 259 | A | O | I | CFC | 35.3 | 35.3 |  |  | 1998-11-01 | 1999-09-01 | 2000-12-01 |  | 2000-12-01 | 2002-09-01 | 280901 | -8686 | 272215 | 272215 | 100% | 0 | 0 |  | 36517.13 | -1129.18 | 35387.95 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | ASP | CPR | FOA | 27 | PRP | 283 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2001-05-01 | 2002-09-01 | 50000 | -693 | 49307 | 49307 | 100% | 0 | 0 |  | 6500 | -90.09 | 6409.91 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 27 enterprises (Umbrella Project) | Individual | ASP | CPR | FOA | 28 | INV | 301 | A | O | I | CFC | 825.7 | 825.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 5289441 | -1696 | 5287745 | 5287745 | 100% | 0 | 0 |  | 591838.51 | -186.56 | 591651.95 | 0 | 0 | FIN | [5 empty] | 2002-12-01
FIN | UNIDO | Elimination of CFC-11 in manufacturing of PU rigid foam for insulation at 31 enterprises | Individual | ASP | CPR | FOA | 29 | INV | 306 | A | O | I | CFC | 707.3 | 707.3 |  |  | 1999-11-01 | 2000-04-01 | 2002-06-01 |  | 2003-01-01 | 2004-04-01 | 5516900 | -3912 | 5512988 | 5512988 | 100% | 0 | 0 |  | 616859 | -430.32 | 616428.68 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Moganshan Electric Appliances Co. | Individual | ASP | CPR | REF | 29 | INV | 308 | A | O | I | CFC | 667.6 | 667.6 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 2769118 | -757584 | 2011534 | 2011534 | 100% | 0 | 0 |  | 314602.98 | -83334.24 | 231268.74 | 0 | 0 | FIN
COM | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Zhejian Electrical Equipment Co. | Individual | ASP | CPR | REF | 29 | INV | 336 | A | O | I | CFC | 199 | 199 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 |  | 2189782 | 0 | 2189782 | 2126268 | 97.1% | 63514 | 25898 | 25898 | 250876.02 | 0 | 243889.48 | 6986.54 | 2848.78
FIN | UNIDO | Preparation of investment project in the polystyrene/ polyethylene foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 337 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2915 | 47085 | 47085 | 100% | 0 | 0 |  | 6500 | -378.95 | 6121.05 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 338 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2702 | 47298 | 47298 | 100% | 0 | 0 |  | 6500 | -351.26 | 6148.74 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the domestic refrigeration (hydrocarbons) sector | Individual | ASP | CPR | REF | 30 | PRP | 339 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration compressor subsector | Individual | ASP | CPR | REF | 30 | PRP | 340 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 50000 | -864 | 49136 | 49136 | 100% | 0 | 0 |  | 6500 | -112.32 | 6387.68 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the transportation refrigeration sector (foam component) | Individual | ASP | CPR | REF | 30 | PRP | 341 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 40000 | -10 | 39990 | 39990 | 100% | 0 | 0 |  | 5200 | -1.3 | 5198.7 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and HFC-134a in the production of refrigerators at Banshen Electric Appliances Co. | Individual | ASP | CPR | REF | 31 | INV | 357 | A | O | I | CFC | 563 | 563 |  |  | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-06-01 | 2005-04-01 | 2988840 | -200851 | 2787989 | 2787989 | 100% | 0 | 0 |  | 338772.4 | -22093.61 | 316678.79 | 0 | 0 | Financial completion in April 2005 Refund was reported to 45th ExCom, Apr 2005. FIN.
FIN | UNIDO | Preparation of 2 investment projects in the domestic (hydrocarbons) refrigeration sub-sector | Individual | ASP | CPR | REF | 31 | PRP | 360 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-08-01 | 2002-11-01 | 40000 | -18000 | 22000 | 22000 | 100% | 0 | 0 |  | 5200 | -2340 | 2860 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Little Swan Electric (Jingzhou) Co. Ltd. | Individual | ASP | CPR | REF | 32 | INV | 365 | A | O | I | CFC | 211.9 | 211.9 |  |  | 2000-12-01 | 2001-06-01 | 2003-12-01 |  | 2004-05-01 | 2005-09-01 | 2392316 | -2294 | 2390022 | 2390022 | 100% | 0 | 0 |  | 273154.76 | -252.34 | 272902.42 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN.
FIN | UNIDO | 2001 Annual work programme of the tobacco sector plan | Multi-Year | ASP | CPR | OTH | 32 | INV | 366 | A | O | I | CFC | 90 | 90 |  |  | 2000-12-01 | 2001-06-01 | 2001-12-01 |  | 2001-12-01 | 2004-02-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN | [10 empty] | 2000 |  | 1000 | 1000 |  |  | Yes | Yes | Yes
COM | UNIDO | Replacement of CFC-11 with HCFC-141b in manufacturing of PU rigid spray foam for insulation at 26 enterprises | Individual | ASP | CPR | FOA | 32 | INV | 369 | A | O | I | CFC | 891.4 | 891.4 |  |  | 2000-12-01 | 2001-07-01 | 2003-07-01 |  | 2004-12-01 |  | 3295600 | 2042859 | 5338459 | 5074796 | 95.06% | 263663 | 191434 | 191434 | 372516 | 234714.49 | 577239.7732 | 29990.7168 | 21774.9282 | [11 empty] | 2000 | INV
FIN | UNIDO | Project preparation for two umbrella projects in the polystyrene/polyethylene foam sector | Individual | ASP | CPR | FOA | 33 | PRP | 371 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-10-01 |  | 2002-12-01 | 2003-12-01 | 100000 | -2840 | 97160 | 97160 | 100% | 0 | 0 |  | 13000 | -369.2 | 12630.8 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Phasing out CFC-11 with HCFC-141b at six companies Hongyu, Longan, Songliao, Tianyun, Xinyang and Yizheng) and phasing out CFC-11 by conversion to water blown technology at one company (Yinxian) | Individual | ASP | CPR | FOA | 34 | INV | 375 | A | O | I | CFC | 191.6 | 191.6 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-07-01 | 2005-12-01 | 1087764 | 0 | 1087764 | 1005714 | 92.46% | 82050 | 0 | 1 | 129654.04 | 0 | 120628.54 | 9025.5 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2001 | INV
COM | UNIDO | Phase out of CFC-12 in the manufacture of extruded polystyrene foams to butane at 9 enterprises (umbrella) | Individual | ASP | CPR | FOA | 34 | INV | 376 | A | O | I | CFC | 750 | 750 |  |  | 2001-07-01 | 2002-02-01 | 2003-08-01 |  | 2004-12-01 |  | 2808338 | 0 | 2808338 | 2435708 | 86.73% | 372630 | 356292 | 356292 | 318917.18 | 0 | 277927.88 | 40989.3 | 39192.12 | [11 empty] | 2001 | INV
ONG | UNIDO | Phase out of CFC-12 in the manufacturing of extruded polystyrene foams through the use of butane as a blowing agent at 7 enterprises (terminal umbrella project) | One-off Phase Out | ASP | CPR | FOA | 35 | INV | 379 | A | O | I | CFC | 359 | 300 |  |  | 2001-12-01 | 2002-12-01 | 2004-01-01 | 2007-03-01 |  |  | 2450123 | 0 | 2450123 | 1675587 | 68.39% | 774536 | 690000 | 200000 | 279513.53 | 0 | 194314.57 | 85198.96 | 75900 | Project is monitored under project implementation delays as reported to the 48th ExCom in Apr 2006. The contract for provision of equipment for the 7th enterprise was awarded in May 2005. Equipment supply was, however, delayed due to lengthy negotiations of terms of payment with the contractor. Contract for delivery of equipment to be finalized Apr/May 2006. Internal procedures of SEPA were accelerated. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of a sectoral phase-out plan in domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 36 | PRP | 385 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-07-01 |  | 2003-07-01 | 2004-04-01 | 70000 | -95 | 69905 | 69905 | 100% | 0 | 0 |  | 9100 | -12.35 | 9087.65 | 0 | 0 | FIN | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of a sectoral strategy in the methyl bromide sector | Individual | ASP | CPR | FUM | 36 | PRP | 386 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-05-01 |  | 2003-12-01 | 2004-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
COM | UNIDO | Terminal umbrella project for the elimination of CFC-12 in manufacturing of EPE foam packaging nets at 30 enterprises | One-off Phase Out | ASP | CPR | FOA | 36 | INV | 387 | A | O | I | CFC | 849.3 | 849.3 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-12-01 |  | 1525648 | 2800061 | 4325709 | 3451687 | 79.79% | 874022 | 840036 | 840036 | 171352 | 314476 | 389685.57 | 96142.43 | 92403.96 | [11 empty] | 2001 2002 | INV
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2002 workplan | Multi-Year | ASP | CPR | OTH | 36 | INV | 388 | A | O | I | CFC | 120 | 200 |  |  | 2002-03-01 | 2002-08-01 | 2003-03-01 |  | 2002-12-01 | 2003-07-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN | [10 empty] | 2001 | INV | 880 | 800 |  |  | Yes | Yes | Yes
ONG | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors | Multi-Year | ASP | CPR | REF | 38 | INV | 394 | A | O | I | CFC | 600 | 236.25 |  |  | 2002-11-01 | 2003-09-01 | 2007-05-01 | 2007-05-01 |  |  | 3400000 | 0 | 3400000 | 2661009 | 78.26% | 738991 | 738991 | 250000 | 299200 | 0 | 229490.81 | 69709.19 | 66509.19 | The Guizhou Haier project (Italian contribution) and the Mudanjiang Kangjia project were completed. Equipment for Beijing Hisense is under commissioning. Contracts for equipment supply were signed for Jinzhou Wanyin and Liuzhou Hongpu companies. A partial phase-out of 169 ODP tonnes was achieved. In 2006, phase-out agreements with almost all remaining enterprises were finalized. Agreement for only one company is still outstanding. Govt. will finalize its negotiation soon. Compressor factories will be provided with technical assistance for their conversion and an awareness campaign will be made. | [10 empty] | 2002 | INV | 918 | 918 |  |  | Yes | Yes | n.a.
FIN | UNIDO | Tobacco sector plan: 2003 annual work programme | Multi-Year | ASP | CPR | OTH | 39 | INV | 400 | A | O | I | CFC | 180 | 180 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2003-12-01 | 2005-09-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | Financial completion in Sep 2005. | [10 empty] | 2002 |  | 700 | 620 |  |  | Yes | Yes | Yes
ONG | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (second tranche) | Multi-Year | ASP | CPR | REF | 41 | INV | 406 | A | O | I | CFC | 318 | 0 |  |  | 2003-12-01 |  | 2007-12-01 | 2007-12-01 |  |  | 2171539 | -15000 | 2156539 | 0 | 0% | 2156539 | 639999 | 300000 | 192239 | -1350 | 0 | 190889 | 57599.91 | The Guizhou Haier project (Italian contribution) and the Mudanjiang Kangjia project were completed. Equipment for Beijing Hisense is under commissioning. Contracts for equipment supply were signed for Jinzhou Wanyin and Liuzhou Hongpu companies. A partial phase-out of 169 ODP tonnes was achieved. In 2006, phase-out agreements with almost all remaining enterprises were finalized. Agreement for only one company is still outstanding. Govt. will finalize its negotiation soon. Compressor factories will be provided with technical assistance for their conversion and an awareness campaign will be made. | [10 empty] | 2003 | INV | 609 | 609 |  |  | Yes | n.a. | n.a.
ONG | UNIDO | National phase-out of methyl bromide (first tranche) | Multi-Year | ASP | CPR | FUM | 41 | INV | 407 | A | O | I | MBR | 364 | 207.8 |  |  | 2003-12-01 | 2004-04-01 | 2007-03-01 | 2006-12-01 |  |  | 4086600 | 0 | 4086600 | 2861897 | 70.03% | 1224703 | 816468 | 1 | 306495 | 0 | 214642.275 | 91852.725 | 61235.1 | Annual implementation plan was submitted and approved. Training programme and procurement of equipment are ongoing. A partial phase-out of 207.8 ODP tonnes was achieved. In 2006, first set of equipment for tobacco seedling and commodity fumigation sectors was delivered and will be installed. | [10 empty] | 2003 | INV | 880 | 688.84 |  |  | Yes | n.a. | n.a.
COM | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2004 workplan | Multi-Year | ASP | CPR | OTH | 42 | INV | 409 | A | O | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-04-01 |  | 1800000 | 0 | 1800000 | 1710000 | 95% | 90000 | 90000 | 90000 | 135000 | 0 | 128250 | 6750 | 6750 | Project completed in Apr 2005. | [10 empty] | 2003 | INV | 500 | 420 |  |  | Yes | Yes | Yes
COM | UNIDO | Preparation of a methyl bromide consumption phase-out plan | Individual | ASP | CPR | FUM | 43 | PRP | 412 | A | O | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2004-12-01 | 2005-05-01 | 20000 | 0 | 20000 | 19924 | 99.62% | 76 | 0 | 1 | 1500 | 0 | 1494.3 | 5.7 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2004 | NON-INV
ONG | UNIDO | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 419 | A | O | I | CFC | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2006-12-01 | 2006-12-01 |  |  | 1000000 | -450000 | 550000 | 14320 | 2.604% | 535680 | 371655 | 420000 | 75000 | -33750 | 1074 | 40176 | 27874.125 | Revised annual implementation plan was approved by 45th ExCom in Apr 2005. Contract was signed for support services and purchase of recovery and recycling equipment for disposal centre. Equipment was delivered. 511 ODP tonnes were phased out in 2005 as a result of UNIDO's and Japan's activities. However, phase-out will be reflected under Japanese component to follow inventory. The second tranche (Japanese contribution) was approved by 47th ExCom in Nov 2005. Institution and trainers were selected for training of trainers workshops. In 2006, training of trainers and technicians training programme was continued. In Apr 2006, study tour to equipment suppliers was undertaken to finalize equipment specifications for servicing workshops and automobile disposal stations. Awareness campaign will be made and service R&R equipment will be purchased (under Japanese component). | [10 empty] | 2004 | INV | 4572 | 4572 |  |  | Yes | No | n.a.
ONG | UNIDO | Preparation of a MDI sector plan | Individual | ASP | CPR | ARS | 44 | PRP | 422 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2005-12-01 | 2007-07-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 69000 | 60000 | 6750 | 0 | 0 | 6750 | 5175 | MDI sector plan will be ready mid-2007 for submission to ExCom. | [10 empty] | 2004
ONG | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2005 | Multi-Year | ASP | CPR | OTH | 45 | INV | 427 | A | O | I | CFC | 200 | 200 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 | 2006-04-01 |  |  | 1700000 | 0 | 1700000 | 340000 | 20% | 1360000 | 1360000 | 1360000 | 127500 | 0 | 25500 | 102000 | 102000 | Annual programme for 2005 was approved by 45th ExCom in Apr 2005. Subcontract was prepared and signed. A total phase-out of 200 ODP tonnes was achieved. Last tranche was submitted and approved by 48th ExCom in Apr 2006. | [10 empty] | 2005 | INV | 300 | 220 |  |  | Yes | Yes | Yes
COM | UNIDO | Preparation of a production phase-out plan in the fumigants sector (methyl bromide) | Individual | ASP | CPR | FUM | 45 | PRP | 430 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-12-01 |  | 40000 | 0 | 40000 | 39906 | 99.77% | 94 | 52 | 50 | 3000 | 0 | 2992.95 | 7.05 | 3.9 | Project completed in Dec 2005. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Sector plan for methyl bromide production sector (first tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 436 | A | O | I | MBR | 0 | 0 | 231 |  | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 3000000 | 0 | 3000000 | 0 | 0% | 3000000 | 0 | 2000000 | 225000 | 0 | 0 | 225000 | 0 | First tranche was released by 47th ExCom in Nov 2005. Subcontract was issued to SEPA in Mar 2006. Training plan will be implemented and working arrangement contract will be signed with counterpart companies. | [10 empty] | 2005 | INV |  |  | 621 | not available | Yes | No | No
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | EUR | CRO | FOA | 21 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -732 | 29268 | 29268 | 100% | 0 | 0 |  | 3900 | -95.16 | 3804.84 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Oriolik Co. flexible polyurethane foam plant | Individual | EUR | CRO | FOA | 22 | INV | 04 | A | O | I | CFC | 25 | 25 |  |  | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-11-01 | 2000-07-01 | 110780 | -200 | 110580 | 110580 | 100% | 0 | 0 |  | 14401.4 | -26 | 14375.4 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Pliva D.D. | Individual | EUR | CRO | ARS | 22 | INV | 05 | A | O | I | CFC | 10.6 | 10.6 |  |  | 1997-05-01 | 1997-10-01 | 1998-08-01 |  | 2000-10-01 | 2001-12-01 | 89779 | -2483 | 87296 | 87296 | 100% | 0 | 0 |  | 11671.27 | -322.79 | 11348.48 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | CRO | REF | 24 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-02-01 | 1999-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (tobacco, tomatoes) | Individual | EUR | CRO | FUM | 24 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1590 | 18410 | 18410 | 100% | 0 | 0 |  | 2600 | -206.7 | 2393.3 | 0 | 0 | FIN
FIN | UNIDO | Two alternatives to the use of methyl bromide in tobacco production; namely: solarization plus bio-fumigation, the use of low-dose chemicals, and non-soil cultivation, in combination with an integrated pest management programme | Individual | EUR | CRO | FUM | 25 | DEM | 08 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-09-01 | 2000-08-01 |  | 2001-05-01 | 2003-03-01 | 288200 | -28577 | 259623 | 259623 | 100% | 0 | 0 |  | 37466 | -3715.01 | 33750.99 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | EUR | CRO | REF | 28 | TRA | 09 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2003-02-01 | 2003-07-01 | 70000 | -1592 | 68408 | 68408 | 100% | 0 | 0 |  | 9100 | -206.96 | 8893.04 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | EUR | CRO | REF | 28 | TAS | 10 | A | O | I | CFC | 15 | 15 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2003-10-01 | 289910 | -4193 | 285717 | 285717 | 100% | 0 | 0 |  | 37688.3 | -545.09 | 37143.21 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | EUR | CRO | REF | 28 | TRA | 12 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 2001-04-01 | 2001-08-01 |  | 2002-06-01 | 2003-07-01 | 38250 | -2284 | 35966 | 35966 | 100% | 0 | 0 |  | 4972.5 | -296.92 | 4675.58 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the tobacco fumigation sector | Individual | EUR | CRO | FUM | 33 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -16363 | 13637 | 13637 | 100% | 0 | 0 |  | 3900 | -2127.19 | 1772.81 | 0 | 0 | FIN | [10 empty] | 2001 | INV
ONG | UNIDO | Phase out of methyl bromide in tobacco seedlings | Individual | EUR | CRO | FUM | 35 | INV | 14 | A | O | I | MBR | 16.2 | 15.8 |  |  | 2001-12-01 | 2002-07-01 | 2007-01-01 | 2006-12-01 |  |  | 476833 | 0 | 476833 | 346103 | 72.58% | 130730 | 16075 | 60000 | 61988.29 | 0 | 44993.39 | 16994.9 | 2089.75 | The project is implemented as planned. Seminars and workshops were held with technicians and engineers. Trays were purchased and distributed. Study tour to Spain was undertaken. The country has already reported zero consumption in the last two years. Due to some small users of methyl bromide who are spread all over the country, the remaining 0.4 ODP tonne is expected to be phased out by Dec 2006. | [10 empty] | 2001 | INV
COM | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | INV | 20 | A | O | I | CFC | 0 | 33 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2005-04-01 |  | 184000 | 0 | 184000 | 141343 | 76.82% | 42657 | 42208 | 42657 | 13800 | 0 | 10600.725 | 3199.275 | 3165.6 | Project completed in Apr 2005. | [10 empty] | 2003 |  | 98 | 88.7 |  |  | Yes | Yes | Yes
COM | UNIDO | Terminal phase-out management plan: 2004 annual implementation programme | Multi-Year | EUR | CRO | PHA | 42 | TAS | 22 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 |  | 48300 | 0 | 48300 | 6458 | 13.37% | 41842 | 40500 | 41842 | 3622.5 | 0 | 484.35 | 3138.15 | 3037.5 | Project completed in Dec 2005. | [10 empty] | 2004 | INV | 98 | 78.2 |  |  | Yes | Yes | Yes
ONG | UNIDO | Training and awareness workshop in the solvents (CTC) sector | Individual | EUR | CRO | SOL | 45 | TAS | 25 | A | O | I | CTC | 2.3 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 | 2006-08-01 |  |  | 40000 | 0 | 40000 | 1101 | 2.752% | 38899 | 1015 | 10000 | 3600 | 0 | 99.09 | 3500.91 | 91.35 | Project was approved by 45th ExCom in Apr 2005. National expert was recruited and a survey on the consumption of CTC was initiated. Preparation of workshop is in progress. Training is planned to be conducted in May 2006. | [10 empty] | 2005 | INV
ONG | UNIDO | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 26 | A | O | I | CFC | 20 | 0 |  |  | 2005-07-01 | 2005-12-01 | 2006-07-01 | 2006-07-01 |  |  | 35000 | 0 | 35000 | 6000 | 17.14% | 29000 | 24000 | 25000 | 2625 | 0 | 450 | 2175 | 1800 | Third tranche was released by 46th ExCom in July 2005. Contract was awarded for follow-up training of national technicians in good refrigerant management practices. In addition, University of Zagreb was subcontracted to assist the Govt. in establishing a reuse scheme. Three reclamation centres have been selected and it seems that all centres are in agreement with the Ministry of Environment to operate as reclamation centres. Furthermore, since the by-law has been updated, the Code of Practice will be updated accordingly. The next tranche will be submitted to the 49th ExCom in July 2006. | [10 empty] | 2005 | INV | 65 | 45 |  |  | Yes | No | No
FIN | UNIDO | Preparation of an investment project (hospitals) in the commercial refrigeration sector | Individual | LAC | CUB | REF | 24 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-02-14 | 2001-07-01 | 50000 | -1950 | 48050 | 48050 | 100% | 0 | 0 |  | 6500 | -253.5 | 6246.5 | 0 | 0 | FIN |  |  |  | 1999-04-01
FIN | UNIDO | Preparation of a phase out project (tobacco) | Individual | LAC | CUB | FUM | 24 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-01-01 | 2001-07-01 | 20000 | -1590 | 18410 | 18410 | 100% | 0 | 0 |  | 2600 | -206.7 | 2393.3 | 0 | 0 | FIN
FIN | UNIDO | Phasing out methyl bromide in the tobacco sector | Individual | LAC | CUB | FUM | 26 | INV | 11 | A | O | I | MBR | 48 | 48 |  |  | 1998-11-01 | 1999-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-12-01 | 1673324 | -2946 | 1670378 | 1670378 | 100% | 0 | 0 |  | 194065.64 | -324.06 | 193741.58 | 0 | 0 | FIN
COM | UNIDO | Project preparation to eliminate methyl bromide consumption (horticulture) | Individual | LAC | CUB | FUM | 43 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 |  | 30000 | 0 | 30000 | 28932 | 96.44% | 1068 | 1026 | 1000 | 2250 | 0 | 2169.9 | 80.1 | 76.95 | Project completed in Jul 2005. | [11 empty] | NON-INV
ONG | UNIDO | Total phase-out of methyl bromide in soil, substrate, storage and structure fumigation | Individual | LAC | CUB | FUM | 44 | INV | 29 | A | O | I | MBR | 24.1 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2008-12-01 | 2008-12-01 |  |  | 537763 | 0 | 537763 | 28825 | 5.36% | 508938 | 12736 | 100000 | 40332.225 | 0 | 2161.875 | 38170.35 | 955.2 | Office equipment was purchased for logistic purposes. First workshop took place in June 2005 and nine additional workshops are planned for the coming years. Procurement of two greenhouses is in progress. Three small centres for the production of grafted plants in the horticulture sector are planned to be established in 2006. | [10 empty] | 2004 | INV
FIN | UNIDO | Preparation of a demonstration project (tobacco, curcubits, flowers, tomatoes) | Individual | LAC | DOM | FUM | 25 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 30000 | -2385 | 27615 | 27615 | 100% | 0 | 0 |  | 3900 | -310.05 | 3589.95 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: alternatives to the use of methyl bromide: soil pasteurization (steam), non soil cultivation, solarization with biofumigation and low dose chemicals all in combination with IPM system | Individual | LAC | DOM | FUM | 26 | DEM | 19 | A | O | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2002-03-01 | 2003-05-01 | 324500 | -1212 | 323288 | 323288 | 100% | 0 | 0 |  | 42185 | -157.56 | 42027.44 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the fumigants (methyl bromide) sector for TPO-soil fumigation | Individual | LAC | DOM | FUM | 36 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2004-03-01 | 30000 | -2765 | 27235 | 27235 | 100% | 0 | 0 |  | 3900 | -359.45 | 3540.55 | 0 | 0 | FIN | [10 empty] | 2002 | INV
ONG | UNIDO | Phase-out of methyl bromide in melon, flowers and tobacco | Individual | LAC | DOM | FUM | 38 | INV | 33 | A | O | I | MBR | 141 | 100 |  |  | 2002-11-01 | 2003-01-01 | 2006-12-01 | 2006-12-01 |  |  | 922900 | 0 | 922900 | 272797 | 29.56% | 650103 | 246101 | 150000 | 111519 | 0 | 35463.61 | 76055.39 | 31615.17 | The project is being implemented as planned. Agreements have been reached with most of the consumer farmers for reduction of methyl bromide. Contract fumigation agreement was received from FLORDON and FLOWERS del JUNAR. Second progress report was received from FUNDO DESA. Boilers for steam pasteurization were purchased. Metam sodium for soil fumigation and tractors for its application are being purchased. A partial phase-out of 60 ODP tonnes was achieved. A detailed progress report was submitted and approved by 48th ExCom in Apr 2006. | [10 empty] | 2002 | INV
ONG | UNIDO | Preparation of a phase-out plan in the solvents (CTC) sector | Individual | AFR | DRC | SOL | 45 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 155 | 0.5167% | 29845 | 0 | 25000 | 2250 | 0 | 11.625 | 2238.375 | 0 | PRP project was approved by 45th ExCom in Apr 2005. First contacts with National Ozone Unit were established. Relevant survey on consumption of CTC was initiated. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Project formulation of investment projects in all sectors | Individual | ASP | DRK | SEV | 21 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 2000-10-01 | 2001-07-01 | 70000 | -1828 | 68172 | 68172 | 100% | 0 | 0 |  | 9100 | -237.64 | 8862.36 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | DRK | FUM | 23 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-01-01 | 2001-07-01 | 15000 | 8013 | 23013 | 23013 | 100% | 0 | 0 |  | 1950 | 1041.69 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 23 | INV | 05 | A | O | I | CTC | 110 | 110 |  |  | 1997-11-01 | 1999-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-07-01 | 311922 | 0 | 311922 | 311922 | 100% | 0 | 0 |  | 40549.86 | 0 | 40549.86 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Hamhung Foam Factory, Hamgyong South Province | Individual | ASP | DRK | FOA | 23 | INV | 06 | A | O | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 102680 | -2304 | 100376 | 100376 | 100% | 0 | 0 |  | 13348.4 | -299.52 | 13048.88 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Pyongyang Foam Plant | Individual | ASP | DRK | FOA | 23 | INV | 07 | A | O | I | CFC | 83 | 83 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 103570 | -2145 | 101425 | 101425 | 100% | 0 | 0 |  | 13464.1 | -278.85 | 13185.25 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Chongjin Foam Factory, Hamgyong North Province | Individual | ASP | DRK | FOA | 23 | INV | 08 | A | O | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 103670 | -236 | 103434 | 103434 | 100% | 0 | 0 |  | 13477.1 | -30.68 | 13446.42 | 0 | 0 | FIN
FIN | UNIDO | Non-investment project: promotion and information transfer of alternatives to the use of methyl bromide in the preparation of seedbeds for the cultivation of rice and maize | Individual | ASP | DRK | FUM | 25 | TAS | 09 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 1999-07-01 |  | 1999-11-01 | 2001-03-01 | 27500 | -196 | 27304 | 27304 | 100% | 0 | 0 |  | 3575 | -25.48 | 3549.52 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvent to vapour at Pyongyang September 18 Bearings Factory | Individual | ASP | DRK | SOL | 26 | INV | 10 | A | O | I | CTC | 121 | 121 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 1081024 | -4135 | 1076889 | 1076889 | 100% | 0 | 0 |  | 128912.64 | -454.85 | 128457.79 | 0 | 0 | FIN
FIN | UNIDO | Conversion of remaining metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 26 | INV | 11 | A | O | I | CTC | 168 | 168 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2001-12-01 | 2002-12-01 | 490157 | -2971 | 487186 | 487186 | 100% | 0 | 0 |  | 63720.41 | -386.23 | 63334.18 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from CTC solvent to TCE vapour degreasing at Ceramic Tools Factory (CTF) | Individual | ASP | DRK | SOL | 28 | INV | 12 | A | O | I | CTC | 19.8 | 19.8 |  |  | 1999-07-01 | 2000-08-01 | 2000-08-01 |  | 2001-12-01 | 2002-12-01 | 206657 | 0 | 206657 | 206657 | 100% | 0 | 0 |  | 26865.41 | 0 | 26865.41 | 0 | 0 | FIN
FIN | UNIDO | Preparation for four projects in the solvent (CTC) sector | Individual | ASP | DRK | SOL | 33 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-10-01 |  | 2002-12-01 | 2003-05-01 | 70000 | -128 | 69872 | 69872 | 100% | 0 | 0 |  | 9100 | -16.64 | 9083.36 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Closure of ODS production plant | Multi-Year | ASP | DRK | PRO | 36 | INV | 17 | A | O | R | CFC | 0 | 0 | 500 | 500 | 2002-03-01 | 2002-10-01 | 2003-03-01 |  | 2002-10-01 | 2003-05-01 | 1344350 | 0 | 1344350 | 1344350 | 100% | 0 | 0 |  | 67217 | 0 | 67217.5 | -0.5 | 0 | FIN | [10 empty] | 2002 | INV |  |  |  |  | n.a. | Yes | Yes
COM | UNIDO | Conversion of cleaning installations from carbon tetrachloride to aqueous cleaning techniques at the Gumsong Tractor Factory (GST) | Individual | ASP | DRK | SOL | 36 | INV | 18 | A | O | I | CTC | 198 | 198 |  |  | 2002-03-01 | 2002-06-01 | 2004-09-01 |  | 2004-12-01 |  | 1932207 | 0 | 1932207 | 1877597 | 97.17% | 54610 | 54600 | 54600 | 222542.77 | 0 | 216535.67 | 6007.1 | 6006 | [11 empty] | 2001 | INV
COM | UNIDO | Conversion of cleaning processes from CTC to aqueous and solvent cleaning techniques at Huichon February 26 Factory (HUI) | Individual | ASP | DRK | SOL | 37 | INV | 19 | A | O | I | CTC | 209 | 209 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-12-01 |  | 1945477 | 0 | 1945477 | 1936445 | 99.54% | 9032 | 7080 | 7080 | 224002.47 | 0 | 223008.95 | 993.52 | 778.8 | [11 empty] | 2002 | INV
COM | UNIDO | Conversion of methyl chloroform and CTC to non-ODS solvent cleaning in the plating workshop of the Taedong-gang Television Factory (PTV), Taedong-gang District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 20 | A | O | I | CTC | 59.8 | 59.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-06-01 |  | 597886 | 0 | 597886 | 568426 | 95.07% | 29460 | 27893 | 27893 | 75767.46 | 0 | 72526.86 | 3240.6 | 3068.23 | Project completed in Jun 2005. | [10 empty] | 2002 | INV
COM | UNIDO | Conversion of Cleaning Processes from CTC to perchloroethylene cleaning at the galvanising workshop of the Pyongyang Illuminating Fixtures Factory (PIF) | Individual | ASP | DRK | SOL | 38 | INV | 21 | A | O | I | CTC | 29.7 | 29.7 |  |  | 2002-11-01 | 2004-06-01 | 2004-06-01 |  | 2004-12-01 |  | 230172 | 0 | 230172 | 226304 | 98.32% | 3868 | 3868 | 3868 | 29922.36 | 0 | 29419.52 | 502.84 | 502.84 | [11 empty] | 2002 | INV
COM | UNIDO | Conversion of cleaning processes from CTC (formerly methyl chloroform) to perchloroethylene cleaning at the Plating Workshop (PLT) of the refrigeration factory of the 5 October Automation Complex, Pyongchon District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 22 | A | O | I | CTC | 69.3 | 69.3 |  |  | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 |  | 508068 | 0 | 508068 | 435218 | 85.66% | 72850 | 72850 | 72850 | 65887.48 | 0 | 56578.34 | 9309.14 | 9309.14 | [11 empty] | 2002 | INV
FIN | UNIDO | Preparation of investment projects in the solvents, process agents and fumigants sector (CTC) | Individual | ASP | DRK | MUS | 39 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 40000 | -85 | 39915 | 39915 | 100% | 0 | 0 |  | 3000 | -6.375 | 2993.625 | 0 | 0 | FIN | [10 empty] | 2003
FIN | UNIDO | Preparation of investment projects in the refrigeration sector (CFC) | Individual | ASP | DRK | REF | 39 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 20000 | -298 | 19702 | 19702 | 100% | 0 | 0 |  | 1500 | -22.35 | 1477.65 | 0 | 0 | FIN | [10 empty] | 2003
COM | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (first tranche) | Multi-Year | ASP | DRK | REF | 40 | INV | 26 | A | O | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-10-01 | 2004-07-01 |  | 2004-12-01 |  | 384000 | 0 | 384000 | 289090 | 75.28% | 94910 | 93384 | 94905 | 28800 | 0 | 21681.75 | 7118.25 | 7003.8 | [11 empty] | 2003 |  | 56 | 56 |  |  | n.a. | n.a. | n.a.
COM | UNIDO | Provision of basic tools for the registered service workshops | RMP Update | ASP | DRK | REF | 40 | TAS | 29 | A | O | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-09-01 |  | 100000 | 0 | 100000 | 89520 | 89.52% | 10480 | 5514 | 5514 | 9000 | 0 | 8056.8 | 943.2 | 496.26 | Project completed in Sep 2005. | [10 empty] | 2003
ONG | UNIDO | Plan for terminal phase-out of CTC (first tranche) | Multi-Year | ASP | DRK | PHA | 41 | INV | 30 | A | O | I | CTC | 0 | 613.8 |  |  | 2003-12-01 | 2004-02-01 | 2004-12-01 | 2006-12-01 |  |  | 3500000 | 0 | 3500000 | 1653626 | 47.25% | 1846374 | 1668480 | 800000 | 262500 | 0 | 124021.95 | 138478.05 | 125136 | Terms of reference were prepared for procurement of additional equipment in the process agent part of the project. International bidding started. Equipment is being manufactured and will be delivered and installed at the companies by July 2006. | [10 empty] | 2003 | INV | 2200 | 2198.9 |  |  | Yes | Yes | Yes
ONG | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (second tranche) | Multi-Year | ASP | DRK | REF | 42 | INV | 32 | A | O | I | CFC | 56 | 56 |  |  | 2004-04-01 | 2004-08-01 | 2005-12-01 | 2006-10-01 |  |  | 981011 | 0 | 981011 | 629674 | 64.19% | 351337 | 7289 | 200000 | 73575.825 | 0 | 47225.55 | 26350.275 | 546.675 | Foaming equipment was installed and commissioned. Trial CFC-free production started. Conversion of refrigeration manufacture was completed, thus a total phase-out of 56 ODP tonnes was achieved. Prototype for the compressor was manufactured. Equipment for the conversion of the compressor factory is being purchased. | [10 empty] | 2004 | INV | 56 | 0 |  |  | n.a. | n.a. | n.a.
FIN | UNIDO | Closure of ODS production plant: verification of complete closure of all CFC-11 and CFC-12 production facilities (second tranche) | Multi-Year | ASP | DRK | PRO | 42 | INV | 33 | A | O | I | CFC | 0 | 0 | 1250 | 1250 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2004-06-01 | 2004-12-01 | 733700 | 0 | 733700 | 733700 | 100% | 0 | 0 |  | 36685 | 0 | 36685 | 0 | 0 | FIN | [10 empty] | 2003 | INV |  |  |  |  | n.a. | Yes | Yes
ONG | UNIDO | Plan for terminal phase-out of CTC (third tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 35 | A | O | I | CTC | 1441.4 | 597.7 |  |  | 2005-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 300000 | 0 | 300000 | 0 | 0% | 300000 | 97764 | 50000 | 22500 | 0 | 0 | 22500 | 7332.3 | Third tranche was released by 46th ExCom in July 2005. A partial phase-out of 613.8 ODP tonnes has already been achieved in 2004 under the first tranche. In 2005, additional 597.7 ODP tonnes of CTC were phased out in the fumigation sector. Terms of reference were prepared for procurement of additional equipment in the process agent part of the project. International bidding started. Equipment is being manufactured and will be delivered and installed at the companies by July 2006. | [10 empty] | 2005 | INV
ONG | UNIDO | Plan for terminal phase-out of CTC (second tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 36 | A | O | I | CTC | 0 | 0 |  |  | 2005-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 884800 | 400000 | 75000 | 0 | 0 | 75000 | 66360 | Second tranche was released by 46th ExCom in July 2005. Terms of reference were prepared for procurement of additional equipment in the process agent part of the project. International bidding started. Equipment is being manufactured and will be delivered and installed at the companies by July 2006. | [10 empty] | 2005 | INV | 192.8 | 191.4 |  |  | Yes | Yes | Yes
ONG | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 38 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-09-01 | 2006-07-01 | 2006-07-01 |  |  | 15000 | 0 | 15000 | 3804 | 25.36% | 11196 | 0 | 1 | 1125 | 0 | 285.3 | 839.7 | 0 | PRP project was approved by 46th ExCom in July 2005. National phase-out plan was prepared, submitted and approved by 47th ExCom. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Implementation of the NPP: recovery and recycling (first tranche) | Multi-Year | ASP | DRK | PHA | 47 | TAS | 40 | A | O | I | CFC | 192.7 | 0 |  |  | 2005-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 536000 | 0 | 536000 | 0 | 0% | 536000 | 0 | 300000 | 40200 | 0 | 0 | 40200 | 0 | First tranche was released by 47th ExCom in Nov 2005. Coordination meeting with UNEP and National Ozone Unit was held in March 2006 to agree on work plan. Recovery and recycling equipment has been identified and will be ordered. Phase-out will occur in 2006 as per agreement. | [10 empty] | 2005 | INV | 177 | 177 |  |  | not available | No | No
CLO | UNIDO | Preparation of an investment project in a plant (Elasta) for the production of polyurethane flexible foam for automotive industry | Individual | LAC | ECU | SEV | 17 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1995-09-01 |  |  | 1999-12-01 | 15000 | -9252 | 5748 | 5748 | 100% | 0 | 0 |  | 1950 | -1202.76 | 747.24 | 0 | 0 | CLO
FIN | UNIDO | Preparatory assistance for elimination of CFCs in manufacturing foams at Advechems and El Fateh | Individual | AFR | EGY | REF | 09 | TAS | 11 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-08-01 | 1998-08-01 | 50000 | -9354 | 40646 | 40646 | 100% | 0 | 0 |  | 6500 | -1216.02 | 5283.98 | 0 | 0 | FIN
FIN | UNIDO | Institutional strengthening unit for the Montreal Protocol related activities | Individual | AFR | EGY | SEV | 10 | INS | 14 | N | T | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1996-05-01 |  | 1996-12-01 | 2000-07-01 | 263450 | 0 | 263450 | 263450 | 100% | 0 | 0 |  | 34248.5 | 0 | 34248.5 | 0 | 0 | FIN
FIN | UNIDO | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at (ADVECHEMS) | Individual | AFR | EGY | FOA | 10 | INV | 16 | A | O | I | CFC | 196 | 183.3 |  |  | 1993-06-01 | 1994-03-01 | 1994-06-01 |  | 1994-12-01 | 2000-12-01 | 904000 | -339 | 903661 | 903661 | 100% | 0 | 0 |  | 117520 | -44.07 | 117475.93 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plants of Delta Industrial Co. | Individual | AFR | EGY | REF | 13 | INV | 32 | A | O | I | CFC | 97 | 117 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1997-05-01 | 2000-07-01 | 2611986 | -137018 | 2474968 | 2474968 | 100% | 0 | 0 |  | 339558.18 | -17812.34 | 321745.84 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Electrostar for Refrigeration Co. | Individual | AFR | EGY | REF | 13 | INV | 33 | A | O | I | CFC | 46 | 51 |  |  | 1994-07-01 | 1995-02-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1450585 | -16273 | 1434312 | 1434312 | 100% | 0 | 0 |  | 188576.05 | -2115.49 | 186460.56 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in production of household refrigeration at additional four companies | Individual | AFR | EGY | REF | 13 | PRP | 34 | A | O | I |  | 0 | 0 |  |  | 1994-07-01 | 1994-10-01 | 1994-10-01 |  | 1995-08-01 | 1998-08-01 | 15000 | 3364 | 18364 | 18364 | 100% | 0 | 0 |  | 1950 | 437.32 | 2387.32 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Kiriazi Refrigerators Manufacturing Co. | Individual | AFR | EGY | REF | 13 | INV | 35 | A | O | I | CFC | 137 | 137 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1643040 | -55455 | 1587585 | 1587585 | 100% | 0 | 0 |  | 213595.2 | -7209.15 | 206386.05 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Helwan Company for Metallic Appliances domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 38 | A | O | I | CFC | 7.5 | 7.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 644239 | -30394 | 613845 | 613845 | 100% | 0 | 0 |  | 83751.07 | -3951.22 | 79799.85 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Super Bosh Factory domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 39 | A | O | I | CFC | 13 | 13 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 760066 | -35859 | 724207 | 724207 | 100% | 0 | 0 |  | 98808.58 | -4661.67 | 94146.91 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Islamic Company for Industrialization (Siltal) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 40 | A | O | I | CFC | 26 | 26 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 866633 | -40887 | 825746 | 825746 | 100% | 0 | 0 |  | 112662.29 | -5315.31 | 107346.98 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Société Mondiale pour Refroidissement (Alaska) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 41 | A | O | I | CFC | 55 | 55 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 1518606 | -71646 | 1446960 | 1446960 | 100% | 0 | 0 |  | 197418.78 | -9313.98 | 188104.8 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at International Co. for Refrigeration and Appliances (Iberna) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 42 | A | O | I | CFC | 19 | 19 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 852738 | -40231 | 812507 | 812507 | 100% | 0 | 0 |  | 110855.94 | -5230.03 | 105625.91 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at El Nasr Company for Electric and Electronic Apparatus (Philips) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 43 | A | O | I | CFC | 22.5 | 22.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 854690 | -40323 | 814367 | 814367 | 100% | 0 | 0 |  | 111109.7 | -5241.99 | 105867.71 | 0 | 0 | FIN
CLO | UNIDO | Conversion of cleaning processes from CFC-113 to Aqueous Cleaning at Optica | Individual | AFR | EGY | SOL | 18 | INV | 51 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-06-01 |  |  | 1996-06-01 | 12043 | -12043 | 0 | 0 |  | 0 | 0 |  | 1565.59 | -1565.59 | 0 | 0 | 0 | CLO
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to non-ODS cleaning at 3 electronic companies | Individual | AFR | EGY | SOL | 18 | INV | 52 | A | O | I | CFC TCA | 13.7 | 13.7 |  |  | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-10-01 | 1998-11-01 | 227203 | 0 | 227203 | 227203 | 100% | 0 | 0 |  | 29536.39 | 0 | 29536.39 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from CFC-113 and 1,1,1 TCA to semi-aqueous cleaning at Arab International Optronics | Individual | AFR | EGY | SOL | 18 | INV | 53 | A | O | I | CFC TCA | 2.1 | 2.1 |  |  | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1999-12-01 | 2000-03-01 | 48533 | 0 | 48533 | 48533 | 100% | 0 | 0 |  | 6309.29 | 0 | 6309.29 | 0 | 0 | FIN |  |  |  | 1999-07-01
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Siltal | Individual | AFR | EGY | SOL | 18 | INV | 54 | A | O | I | TCA | 2 | 2 |  |  | 1995-11-01 | 1997-11-01 | 1996-06-01 |  | 1998-10-01 | 2000-07-01 | 48784 | -496 | 48288 | 48288 | 100% | 0 | 0 |  | 6341.92 | -64.48 | 6277.44 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Technopol | Individual | AFR | EGY | SOL | 19 | INV | 56 | A | O | I | TCA | 6 | 6 |  |  | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2000-05-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282.37 | 0 | 16282.37 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to cleaning in perchloroethylene at Abbasol | Individual | AFR | EGY | SOL | 19 | INV | 57 | A | O | I | TCA | 8 | 8 |  |  | 1996-05-01 | 1998-10-01 | 1997-05-01 |  | 1998-12-01 | 1999-07-01 | 154544 | 0 | 154544 | 154544 | 100% | 0 | 0 |  | 20090.72 | 0 | 20090.72 | 0 | 0 | FIN
FIN | UNIDO | Institutional strengthening project for the Montreal Protocol related activities (Phase II) | Individual | AFR | EGY | SEV | 21 | INS | 61 | N | T | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1999-02-01 |  | 1998-12-01 | 1999-09-01 | 43900 | 131730 | 175630 | 175630 | 100% | 0 | 0 |  | 5707 | 17124.9 | 22831.9 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector | Individual | AFR | EGY | SOL | 21 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-07-01 | 1997-06-01 |  | 2000-07-01 | 2000-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNIDO | Preparatory assistance for phase out of ODS in the production of household refrigerators at Electrostar & Kiriazi | Individual | AFR | EGY | REF | 09 | TAS | 63 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-03-01 | 1998-08-01 | 50000 | 6602 | 56602 | 56602 | 100% | 0 | 0 |  | 6500 | 858.26 | 7358.26 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 27 | PRP | 72 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2001-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Phase III: Institutional Strengthening Project for the Montreal Protocol Related Activities | Individual | AFR | EGY | SEV | 27 | INS | 73 | N | T | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 2001-04-01 |  | 2001-11-01 | 2002-05-01 | 175000 | -9 | 174991 | 174991 | 100% | 0 | 0 |  | 22750 | -1.17 | 22748.83 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | EGY | FUM | 30 | PRP | 77 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-12-01 | 2003-05-01 | 25000 | -896 | 24104 | 24104 | 100% | 0 | 0 |  | 3250 | -116.48 | 3133.52 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 30 | PRP | 78 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-12-01 | 2001-04-01 |  | 2004-11-01 | 2004-12-01 | 15000 | -8 | 14992 | 14992 | 100% | 0 | 0 |  | 1950 | -1.04 | 1948.96 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN.
FIN | UNIDO | Conversion of TCA used for the formulation of degreasing and contact cleaners and crack detectors to new formulations with special hydrocarbons and heavy chlorinated ester at Sien | Individual | AFR | EGY | SOL | 28 | INV | 79 | A | O | I | TCA | 9 | 9 |  |  | 1999-07-01 | 2000-11-01 | 2000-08-01 |  | 2002-06-01 | 2003-10-01 | 231435 | -258 | 231177 | 231177 | 100% | 0 | 0 |  | 30086.55 | -33.54 | 30053.01 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at Maasara Co. for engineering industries | Individual | AFR | EGY | SOL | 31 | INV | 80 | A | O | I | TCA | 10.7 | 10.7 |  |  | 2000-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-12-01 | 2004-03-01 | 294950 | -25 | 294925 | 294925 | 100% | 0 | 0 |  | 38343.5 | -3.25 | 38340.25 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | AFR | EGY | FUM | 33 | PRP | 82 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-12-01 | 2003-05-01 | 30000 | -575 | 29425 | 29425 | 100% | 0 | 0 |  | 3900 | -74.75 | 3825.25 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Renewal of institutional strengthening project (phase IV) | Individual | AFR | EGY | SEV | 34 | INS | 83 | N | T | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-12-01 | 175000 | -8934 | 166066 | 166066 | 100% | 0 | 0 |  | 22750 | -1161.42 | 21588.58 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | NON-INV
COM | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | EGY | PHA | 36 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-04-01 | 2003-09-01 |  | 2005-12-01 |  | 75000 | 0 | 75000 | 65044 | 86.73% | 9956 | 4554 | 4554 | 9750 | 0 | 8455.72 | 1294.28 | 592.02 | Project document was prepared, submitted and approved by 46th ExCom in July 2005. Project completed in Dec 2005. Remaining funds will be returned upon financial completion of the project. | [10 empty] | 2002 | INV
ONG | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation | Individual | AFR | EGY | FUM | 38 | INV | 86 | A | O | I | MBR | 185.6 | 185.6 |  |  | 2002-11-01 | 2003-09-01 | 2009-11-01 | 2007-12-01 |  |  | 2750592 | 0 | 2750592 | 65701 | 2.389% | 2684891 | 408371 | 714284 | 312565.12 | 0 | 8541.13 | 304023.99 | 53088.23 | Project document and terms of reference for subcontract were cleared by Ministry of Agriculture. Subcontract with Agriculture Research Centre was signed. National Project Coordinator was recruited and project staff were agreed upon. The 20% reduction target was achieved in 2005. Progress report was submitted and approved by 48th ExCom in Apr 2006. The work programme for 2006 and 2007 is focused to keep the achieved reduction permanent and sustainable. | [10 empty] | 2002 | INV
ONG | UNIDO | Extension of institutional strengthening project | Individual | AFR | EGY | SEV | 40 | INS | 87 | N | T | I |  | 18.9 | 0 |  |  | 2003-07-01 | 2004-08-01 | 2005-07-01 | 2007-03-01 |  |  | 228323 | 0 | 228323 | 117182 | 51.32% | 111141 | 13080 | 87205 | 17125 | 0 | 8789.0478 | 8335.9522 | 981.0444 | In line with the requirements of IS projects, the Ozone Unit conducted awareness campaigns especially directed to decision makers, customs officials, investors and the public at large, including celebration of the International Ozone Day; the information system to track imports and consumption was updated and an import/export licensing system was established in collaboration with customs, including application of a quota system for CFC and methyl bromide imports; established a strategic executive plan for methyl bromide in the agricultural sector and in cooperation with the Ministry of Agriculture, carried out a workshop on illegal trade of ODSs and a workshop on safe use of hydrocarbons in the manufacture of foam. | [10 empty] | 2003
ONG | UNIDO | Terminal solvent sector umbrella project | Individual | AFR | EGY | SOL | 44 | INV | 89 | A | O | I | CFC CTC TCA | 41 | 0 |  |  | 2004-12-01 | 2005-02-01 | 2006-06-01 | 2006-12-01 |  |  | 778464 | 0 | 778464 | 118282 | 15.19% | 660182 | 574666 | 400000 | 58384.8 | 0 | 8871.15 | 49513.65 | 43099.95 | Bidding was initiated and one cleaning machine was procured. A survey will be conducted in Apr 2006 to identify small users of ozone-depleting solvents. After conduction of two training workshops in Nov 2006, full phase-out of ozone-depleting solvents in small-scale industries is expected to be achieved by Dec 2006. | [10 empty] | 2004 | INV
ONG | UNIDO | Preparation of a MDI phase-out plan (CFC) | Individual | AFR | EGY | ARS | 45 | PRP | 90 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2007-07-01 |  |  | 50000 | 0 | 50000 | 6893 | 13.79% | 43107 | 5571 | 30000 | 3750 | 0 | 516.975 | 3233.025 | 417.825 | PRP project was approved by 45th ExCom in Apr 2005. MDI sector plan will be ready mid-2007 for submission to ExCom. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | AFR | EGY | PHA | 46 | INV | 91 | A | O | I | CFC | 190 | 0 |  |  | 2005-07-01 | 2005-08-01 | 2006-07-01 | 2006-12-01 |  |  | 1000000 | 0 | 1000000 | 13834 | 1.383% | 986166 | 8670 | 500000 | 75000 | 0 | 1037.55 | 73962.45 | 650.25 | First tranche was released by 46th ExCom in July 2005. Implementation modalities were agreed upon. The National Ozone Unit was strengthened to execute the project. Refrigeration and air-conditioning services sectors will be provided with training and necessary equipment which is under procurement. | [10 empty] | 2005 | INV | 822 | 822 |  |  | not available | No | No
ONG | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | ELS | FUM | 45 | TAS | 18 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 3600 | 0 | 0 | 3600 | 0 | Project was approved by 45th ExCom in Apr 2005. More detailed background information was collected through the counterpart for the organization of the workshop. A work programme was drafted. The workshop will take place in May 2006. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | AFR | ETH | SOL | 45 | TAS | 15 | A | O | I | CTC TCA | 8.4 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 7528 | 18.82% | 32472 | 4808 | 1 | 3600 | 0 | 677.52 | 2922.48 | 432.72 | Project was approved by 45th ExCom in Apr 2005. National expert was recruited to collect information from main users of CTC/TCA. Survey report was used for international expert and logistic support to organize the training course. However, the training and awareness workshop was cancelled upon request from the Government of Ethiopia. | [10 empty] | 2005 | INV
ONG | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers (Croatia, Macedonia, Romania, and Serbia and Montenegro) | Individual | EUR | EUR | REF | 47 | DEM | 06 | A | O | I |  | 0 | 0 |  |  | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 1069074 | 0 | 1069074 | 0 | 0% | 1069074 | 0 | 300000 | 80180.55 | 0 | 0 | 80180.55 | 0 | Project was approved by 47th ExCom in Nov 2005. Working arrangement will be finalized and agreed upon with National Ozone Unit and counterparts in 2006. Offers for supply of new chillers will be obtained and contracts will be awarded after having ensured availability of external resources. | [10 empty] | 2005 | INV
FIN | UNIDO | Refrigeration recovery and recycling scheme | RMP | AFR | GAM | REF | 22 | TAS | 05 | A | O | I | CFC | 7.7 | 7.7 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 68000 | -350 | 67650 | 67650 | 100% | 0 | 0 |  | 8840 | -45.5 | 8794.5 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | EUR | GEO | FUM | 33 | PRP | 09 | A | O | I | MBR | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-05-01 | 2003-05-01 | 30000 | -1047 | 28953 | 28953 | 100% | 0 | 0 |  | 3900 | -136.11 | 3763.89 | 0 | 0 | FIN | [10 empty] | 2001 | INV
ONG | UNIDO | Technical assistance for the phase-out of methyl bromide for soil fumigation | Individual | EUR | GEO | FUM | 37 | TAS | 13 | A | O | I | MBR | 6 | 0 |  |  | 2002-07-01 | 2003-02-01 | 2006-08-01 | 2006-12-01 |  |  | 220000 | 0 | 220000 | 118714 | 53.96% | 101286 | 31081 | 50000 | 28600 | 0 | 15432.82 | 13167.18 | 4040.53 | Second phase of the project started. Farmers were provided with direct assistance in the adoption of alternatives. Project is expected to be completed by Dec 2006. | [10 empty] | 2002 | NON-INV
ONG | UNIDO | Preparation of a national halon bank | Individual | EUR | GEO | HAL | 44 | PRP | 16 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 | 2006-02-01 |  |  | 15000 | 0 | 15000 | 3240 | 21.6% | 11760 | 3234 | 3200 | 1125 | 0 | 243 | 882 | 242.55 | Project document was prepared, submitted and approved by 47th ExCom. | [10 empty] | 2004
COM | UNIDO | Preparation of structure in fumigation of commodities in mill factories and grain storage | Individual | EUR | GEO | FUM | 44 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 |  | 30000 | 0 | 30000 | 25929 | 86.43% | 4071 | 4034 | 4000 | 2250 | 0 | 1944.675 | 305.325 | 302.55 | Project completed in Dec 2005. | [10 empty] | 2004
ONG | UNIDO | Technical assistance for the elimination of methyl bromide in grain and storage facilities | Individual | EUR | GEO | FUM | 47 | INV | 20 | A | O | I | MBR | 7.2 | 0 |  |  | 2005-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 225500 | 0 | 225500 | 0 | 0% | 225500 | 0 | 30000 | 20295 | 0 | 0 | 20295 | 0 | Project was approved by 47th ExCom in Nov 2005. Terms of reference for equipment and training are under preparation. | [10 empty] | 2005 | INV
ONG | UNIDO | Halon banking management programme | Individual | EUR | GEO | HAL | 47 | TAS | 21 | A | O | I | HAL | 37.4 | 0 |  |  | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 64930 | 0 | 64930 | 0 | 0% | 64930 | 0 | 30000 | 5843.7 | 0 | 0 | 5843.7 | 0 | Project was approved by 47th ExCom in Nov 2005. Project site will be selected for establishment of halon recovery and recycling centre and equipment specification will be prepared. | [10 empty] | 2005 | INV
FIN | UNIDO | Strategy for phasing out of ODS in low ODS-consuming countries | Individual | GLO | GLO | REF | 11 | TAS | 46 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-09-01 | 1994-11-01 |  | 1996-06-01 | 1998-08-01 | 100000 | -317 | 99683 | 99683 | 100% | 0 | 0 |  | 13000 | -41.21 | 12958.79 | 0 | 0 | FIN
FIN | UNIDO | Joint UNIDO/UNEP preparation of country programmes | Individual | GLO | GLO | SEV | 12 | TAS | 62 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1996-06-01 | 1998-08-01 | 75000 | -3269 | 71731 | 71731 | 100% | 0 | 0 |  | 9750 | -424.97 | 9325.03 | 0 | 0 | FIN
FIN | UNIDO | Development of Refrigeration Management Plans | Individual | GLO | GLO | REF | 22 | PRP | 134 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1997-12-01 |  | 2001-04-01 | 2001-09-01 | 60000 | -23797 | 36203 | 36203 | 100% | 0 | 0 |  | 7800 | -3093.61 | 4706.39 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 175 | A | O | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  | 1999-12-01 | 2001-02-01 | 169000 | -169000 | 0 | 0 |  | 0 | 0 |  | 21970 | -21970 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance for 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 189 | A | O | I |  | 0 | 0 |  |  | 1999-11-01 |  | 2000-04-01 |  | 2000-12-01 | 2003-05-01 | 170000 | -170000 | 0 | 0 |  | 0 | 0 |  | 22100 | -22100 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 216 | A | O | I |  | 0 | 0 |  |  | 2000-12-01 |  | 2001-12-01 |  | 2001-03-01 | 2001-03-01 | 139500 | -139500 | 0 | 0 |  | 0 | 0 |  | 18135 | -18135 | 0 | 0 | 0 | FIN
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 35 | PRP | 234 | A | O | I |  | 0 | 0 |  |  | 2001-12-01 |  | 2002-03-01 |  | 2002-03-01 | 2002-03-01 | 176250 | -176250 | 0 | 0 |  | 0 | 0 |  | 22912.5 | -22912.5 | 0 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Core unit (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 244 | A | O | I |  | 0 | 0 |  |  | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNIDO | Core unit (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 250 | A | O | I |  | 0 | 0 |  |  | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN | [10 empty] | 2003
FIN | UNIDO | Core unit budget for 2005 | Individual | GLO | GLO | SEV | 44 | TAS | 258 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN | [10 empty] | 2004
ONG | UNIDO | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 265 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-08-01 | 2005-11-01 | 2006-06-01 |  |  | 119000 | 0 | 119000 | 72944 | 61.3% | 46056 | 24972 | 46000 | 8925 | 0 | 5470.8 | 3454.2 | 1872.9 | PRP project was approved by 46th ExCom in July 2005. Project concept was developed. Demonstration projects were approved by 47th ExCom in Nov 2005 for Europe (Croatia, Macedonia, Romania, Serbia and Montenegro) and Syria. Project preparation in the Africa region was initiated. Strategic demonstration project in 5 African countries was approved by 48th ExCom in Apr 2006. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 272 | A | O | I |  | 0 | 0 |  |  | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1700000 | 0 | 0 | 1700000 | 0 | - | [10 empty] | 2005
FIN | UNIDO | Project formulation of demonstraton project in the methyl bromide sector | Individual | LAC | GUA | FUM | 21 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-03-01 | 1997-08-01 |  | 1999-01-01 | 2001-07-01 | 7140 | -568 | 6572 | 6572 | 100% | 0 | 0 |  | 928.2 | -73.84 | 854.36 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Demonstration project: four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization, and low-dose chemicals in combination with an IPM system | Individual | LAC | GUA | FUM | 22 | DEM | 15 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-07-01 | 440000 | -58383 | 381617 | 381617 | 100% | 0 | 0 |  | 57200 | -7589.79 | 49610.21 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the phase out of 800 tonnes in the methyl bromide sector (melon) | Individual | LAC | GUA | FUM | 29 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 1999-11-01 | 2002-04-01 | 2000-12-01 |  | 2002-12-01 | 2003-12-01 | 45000 | -1233 | 43767 | 43767 | 100% | 0 | 0 |  | 5850 | -160.29 | 5689.71 | 0 | 0 | FIN
ONG | UNIDO | National phase out of methyl bromide | Individual | LAC | GUA | FUM | 38 | INV | 29 | A | O | I | MBR | 502.6 | 376.2 |  |  | 2002-11-01 | 2003-03-01 | 2008-11-01 | 2008-12-01 |  |  | 3257377 | 0 | 3257377 | 2335538 | 71.7% | 921839 | 54061 | 151991 | 368311.47 | 0 | 266909.18 | 101402.29 | 5946.71 | Melon sector: All equipment was delivered and installed. The implementation plan related to crop season 2004/2005 was executed as planned. Final report is available. Despite the availability of a number of proved effective methyl bromide alternatives, the Melon Producer Association and methyl bromide dealers got import licences approved by Ministry of Environment for 980 ODS tonnes in 2005 compared to a consumption of 806.7 ODS tonnes in 2004. Project expenditures were, therefore, frozen from 1 May 2005 until there was a decision by the 47th ExCom. Project monitoring, however, continued thanks to the ongoing contract with national consultants/field expert. Tomato sector: Project implementation was completed. Tomato producers do not use methyl bromide any longer. Flower sector: One steam boiler was delivered. We have an agreement with other two flower producers for the provision of similar equipment. A partial phase-out of 79.6 ODP tonnes was achieved. Progress report was submitted and approved by 48th ExCom in Apr 2006. | [10 empty] | 2002 | INV
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | AFR | GUI | FOA | 21 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -9000 | 11000 | 11000 | 100% | 0 | 0 |  | 2600 | -1170 | 1430 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | GUI | REF | 22 | TAS | 05 | A | O | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-01 | 80780 | 0 | 80780 | 80780 | 100% | 0 | 0 |  | 10501.4 | 0 | 10501.4 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at a domestic refrigeration plant (Guyana Refrigeration Ltd.) | Individual | LAC | GUY | REF | 17 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1995-09-01 |  | 1998-01-01 | 1999-08-01 | 15000 | -682 | 14318 | 14318 | 100% | 0 | 0 |  | 1950 | -88.66 | 1861.34 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Guyana Refrigerator Ltd., Guyana (GRL) | Individual | LAC | GUY | REF | 23 | INV | 05 | A | O | I | CFC | 7.2 | 7.2 |  |  | 1997-11-01 | 1998-08-01 | 1999-06-01 |  | 2001-04-01 | 2002-09-01 | 461000 | -49 | 460951 | 460951 | 100% | 0 | 0 |  | 59930 | -6.37 | 59923.63 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | HON | FOA | 21 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1998-04-01 | 1997-05-01 |  | 2000-12-01 | 2001-09-01 | 30000 | -11432 | 18568 | 18568 | 100% | 0 | 0 |  | 3900 | -1486.16 | 2413.84 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | HON | REF | 24 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-11-01 | 2000-07-01 | 30000 | -7287 | 22713 | 22713 | 100% | 0 | 0 |  | 3900 | -947.31 | 2952.69 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | LAC | HON | REF | 28 | TRA | 05 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2002-04-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 38250 | 0 | 38250 | 38250 | 100% | 0 | 0 |  | 4972.5 | 0 | 4972.5 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | LAC | HON | REF | 28 | TRA | 06 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | LAC | HON | REF | 28 | TAS | 07 | A | O | I | CFC | 14.2 | 14.2 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 245900 | -1339 | 244561 | 244561 | 100% | 0 | 0 |  | 31967 | -174.07 | 31792.93 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [5 empty] | 2003-06-01
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | LAC | HON | FUM | 33 | PRP | 09 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-03-01 | 2002-04-01 |  | 2002-11-01 | 2003-05-01 | 30000 | -529 | 29471 | 29471 | 100% | 0 | 0 |  | 3900 | -68.77 | 3831.23 | 0 | 0 | FIN | [10 empty] | 2001 | INV
ONG | UNIDO | Phase-out of methyl bromide in melon and banana production sector and tobacco seedling | Individual | LAC | HON | FUM | 37 | INV | 10 | A | O | I | MBR | 213 | 213 |  |  | 2002-07-01 | 2002-11-01 | 2008-12-01 | 2008-12-01 |  |  | 1977454 | 0 | 1977454 | 1969111 | 99.58% | 8343 | 5913 | 5913 | 227519 | 0 | 226602.21 | 916.79 | 650.43 | All equipment was delivered and installed. Implementation plan related to crop season 2004/2005 was executed as planned. Final report is available. A total phase-out of 213 ODP tonnes was achieved. The area treated with methyl bromide alternatives has grown considerably compared to the previous crop season and it is likely to grow more during the crop season 2005/2006. A new phase-out schedule was approved by 47th ExCom in Nov 2005 in order to reach the 20% reduction target by 2008, giving time to further develop and softly apply the new technology. Progress report was submitted and approved by 48th ExCom in Apr 2006. | [10 empty] | 2002 | INV
FIN | UNIDO | Project formulation for phasing out ODS in small and medium scale industries | Individual | ASP | IDS | SEV | 15 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-01-01 | 2002-05-01 | 80000 | -2925 | 77075 | 77075 | 100% | 0 | 0 |  | 10400 | -380.25 | 10019.75 | 0 | 0 | FIN |  |  | 1997-12-01 | 1999-02-01
FIN | UNIDO | Phasing out of ODS at P.T. Air Tech. Co. Ltd. | Individual | ASP | IDS | REF | 18 | INV | 35 | A | O | I | CFC | 30.1 | 30.1 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-05-01 | 409850 | 0 | 409850 | 409850 | 100% | 0 | 0 |  | 53280.5 | 0 | 53280.5 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out ODS at PT Naviri Kencana Perdana | Individual | ASP | IDS | FOA | 19 | INV | 43 | A | O | I | CFC | 47.8 | 47.8 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 377382 | -1000 | 376382 | 376382 | 100% | 0 | 0 |  | 49059.66 | -130 | 48929.66 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the aerosol and foam sectors | Individual | ASP | IDS | SEV | 21 | PRP | 54 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 2000-10-01 | 2001-07-01 | 20000 | -4503 | 15497 | 15497 | 100% | 0 | 0 |  | 2600 | -585.39 | 2014.61 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Phasing out CFC-11 at PT Winnerfoam Abadi | Individual | ASP | IDS | FOA | 22 | INV | 56 | A | O | I | CFC | 40 | 40 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 79472 | -1411 | 78061 | 78061 | 100% | 0 | 0 |  | 10331.36 | -183.43 | 10147.93 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Panca Duta foam industry | Individual | ASP | IDS | FOA | 22 | INV | 57 | A | O | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2001-12-01 | 86955 | -758 | 86197 | 86197 | 100% | 0 | 0 |  | 11304.15 | -98.54 | 11205.61 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at PT Elastino Satyajaya flexible polyurethane foam plant | Individual | ASP | IDS | FOA | 22 | INV | 58 | A | O | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 75943 | -35 | 75908 | 75908 | 100% | 0 | 0 |  | 9872.59 | -4.55 | 9868.04 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at P.T. Jalur Sejuk | Individual | ASP | IDS | REF | 22 | INV | 59 | A | O | I | CFC | 30.85 | 30.85 |  |  | 1997-05-01 | 1997-09-01 | 1998-11-01 |  | 1999-06-01 | 2001-07-01 | 171470 | -129 | 171341 | 171341 | 100% | 0 | 0 |  | 22291.1 | -16.77 | 22274.33 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of an investment project for phasing out ODS at three enterprises including the companies Nirwana and P.T. Success | Individual | ASP | IDS | SEV | 23 | PRP | 64 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-10-01 | 2001-07-01 | 10000 | 8995 | 18995 | 18995 | 100% | 0 | 0 |  | 1300 | 1169.35 | 2469.35 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector (tobacco, tomatoes, pepper) | Individual | ASP | IDS | FUM | 23 | PRP | 69 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 1998-09-01 | 2001-07-01 | 10000 | 17615 | 27615 | 27615 | 100% | 0 | 0 |  | 1300 | 2289.95 | 3589.95 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in store products (rice, coffee and corn) | Individual | ASP | IDS | FUM | 26 | DEM | 94 | A | O | I |  | 0 | 0 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-12-01 | 2003-10-01 | 332200 | -6502 | 325698 | 325698 | 100% | 0 | 0 |  | 43186 | -845.26 | 42340.74 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IDS | FOA | 27 | PRP | 109 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2002-01-01 | 2003-05-01 | 50000 | -256 | 49744 | 49744 | 100% | 0 | 0 |  | 6500 | -33.28 | 6466.72 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Nirwana in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 110 | A | O | I | CFC | 32.6 | 32.6 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 206911 | -208 | 206703 | 206703 | 100% | 0 | 0 |  | 26898.43 | -27.04 | 26871.39 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Meta Presindo Utama in the manufacture of polyurethane integral skin and moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 113 | A | O | I | CFC | 21.8 | 21.8 |  |  | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 213603 | -118 | 213485 | 213485 | 100% | 0 | 0 |  | 27768.39 | -15.34 | 27753.05 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown technology in the manufacturing of polyurethane integral skin shoe soles at P.T. Trias Rantai Mas | Individual | ASP | IDS | FOA | 31 | INV | 119 | A | O | I | CFC | 18.4 | 18.4 |  |  | 2000-07-01 | 2000-11-01 | 2003-01-01 |  | 2003-01-01 | 2003-12-01 | 141319 | -2 | 141317 | 141317 | 100% | 0 | 0 |  | 18371.47 | -0.26 | 18371.21 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 122 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -2240 | 22760 | 22760 | 100% | 0 | 0 |  | 3250 | -291.2 | 2958.8 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of a phase-out project in the fumigant (methyl bromide) sector in TPO-grain fumigation | Individual | ASP | IDS | FUM | 36 | PRP | 139 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Financial completion in May 2005. | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of a sector phase-out plan in process agents sector | Individual | ASP | IDS | PAG | 36 | PRP | 140 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-12-01 | 2004-12-01 | 60000 | -1982 | 58018 | 58018 | 100% | 0 | 0 |  | 7800 | -257.66 | 7542.34 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of integral skin automotive parts at PT Wulansari Raharja | Individual | ASP | IDS | FOA | 36 | INV | 141 | A | O | I | CFC | 10.8 | 10.8 |  |  | 2002-03-01 | 2004-02-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 101301 | -792 | 100509 | 100509 | 100% | 0 | 0 |  | 13169.13 | -102.96 | 13066.17 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
COM | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid insulation foam parts at two companies: PT Morodadi Prima and PT Tentrem Industri Karosseri | Individual | ASP | IDS | FOA | 36 | INV | 143 | A | O | I | CFC | 25.5 | 25.5 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-11-01 |  | 164947 | 0 | 164947 | 126281 | 76.56% | 38666 | 38056 | 38056 | 21443.11 | 0 | 16416.53 | 5026.58 | 4947.28 | [11 empty] | 2001 | INV
COM | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT Solindah Kita | Individual | ASP | IDS | FOA | 36 | INV | 144 | A | O | I | CFC | 48 | 48 |  |  | 2002-03-01 | 2002-08-01 | 2004-09-01 |  | 2005-12-01 |  | 390760 | 0 | 390760 | 142897 | 36.57% | 247863 | 190569 | 190569 | 50798.8 | 0 | 18576.61 | 32222.19 | 24773.97 | Project completed in Dec 2005. | [10 empty] | 2001 | INV
COM | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT. Accurai | Individual | ASP | IDS | FOA | 37 | INV | 147 | A | O | I | CFC | 50 | 50 |  |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2005-06-01 |  | 523943 | 0 | 523943 | 522477 | 99.72% | 1466 | 79 | 79 | 67633.73 | 0 | 67472.47 | 161.26 | 8.69 | Project completed in Jun 2005. | [10 empty] | 2002 | INV
COM | UNIDO | Project to phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Ganesha Rattesko and Sindari Nusatama | Individual | ASP | IDS | FOA | 38 | INV | 150 | A | O | I | CFC | 52 | 52 |  |  | 2002-11-01 | 2003-12-01 | 2005-06-01 |  | 2005-12-01 |  | 283490 | 0 | 283490 | 205841 | 72.61% | 77649 | 77599 | 77000 | 36853.7 | 0 | 26759.33 | 10094.37 | 10087.87 | Project completed in Dec 2005. | [10 empty] | 2002 | INV
COM | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Delta Atlantik and Samudra Plastics | Individual | ASP | IDS | FOA | 38 | INV | 152 | A | O | I | CFC | 18.8 | 18.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2004-11-01 |  | 146388 | 0 | 146388 | 140387 | 95.9% | 6001 | 5921 | 5921 | 19030.44 | 0 | 18250.31 | 780.13 | 769.73 | [11 empty] | 2002 | INV
ONG | UNIDO | Plan for terminal phase-out of ODS in the solvent sector | Individual | ASP | IDS | SOL | 44 | INV | 162 | A | O | I | CFC CTC TCA | 100.5 | 76.5 |  |  | 2004-12-01 | 2005-02-01 | 2006-12-01 | 2007-10-01 |  |  | 1464733 | 0 | 1464733 | 5683 | 0.388% | 1459050 | 607003 | 500000 | 108974 | 0 | 422.8069 | 108551.1931 | 45160.1383 | Degreasing equipment was procured for three major shoe sole producing companies. Mission was undertaken beginning of 2006 to agree upon the overall concept of project implementation and particular modalities for other solvent-related sub-sectors with the Government due to the reorganization at the Ministry of Environment in Indonesia. A partial phase-out of 76.5 ODP tonnes was achieved. | [10 empty] | 2004 | INV
ONG | UNIDO | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 44 | INV | 168 | A | O | I | MBR | 37.8 | 5 |  |  | 2004-12-01 | 2005-04-01 | 2007-12-01 | 2007-12-01 |  |  | 350000 | 0 | 350000 | 8395 | 2.399% | 341605 | 157001 | 216121 | 26250 | 0 | 629.625 | 25620.375 | 11775.075 | Implementation started only in Nov 2005 since approval of the project document by Govt. of Indonesia took from Jan to Oct 2005. Since Nov 2005, National Project Coordinator was recruited and subcontract was signed with KLH/Biotrop for provision of logistic support and technical assistance. A partial phase-out of 5 ODP tonnes was achieved. In April 2006, a mission will be undertaken to finalize technical specifications for procurement of equipment which is planned to be delivered in second half of 2006. | [10 empty] | 2004 | INV
FIN | UNIDO | Feasibility study for recovery/recycling of CFC refrigerants | RMP | ASP | IND | REF | 10 | TAS | 05 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-02-01 | 1993-10-01 |  | 1998-06-01 | 1999-08-01 | 55000 | -42939 | 12061 | 12061 | 100% | 0 | 0 |  | 7150 | -5582.07 | 1567.93 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phasing out ODS in the unorganized sector | Individual | ASP | IND | SEV | 10 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-05-01 | 1993-10-01 |  | 1999-12-01 | 2000-09-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Project formulation for the conversion of electronic cleaning processes from CFC-113/alcohol blended and 1,1,1 trichlorethane to non-CFC cleaning | Individual | ASP | IND | SOL | 10 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-10-01 | 1993-10-01 |  | 1998-12-01 | 2000-07-01 | 74000 | -449 | 73551 | 73551 | 100% | 0 | 0 |  | 9620 | -58.37 | 9561.63 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents aqueous cleaning at ITI Mankapur | Individual | ASP | IND | SOL | 13 | INV | 25 | A | O | I | CFC | 34 | 48.8 |  |  | 1994-07-01 | 1996-06-01 | 1996-01-01 |  | 1996-10-01 | 2000-12-01 | 610160 | -13 | 610147 | 610147 | 100% | 0 | 0 |  | 79320.8 | -1.69 | 79319.11 | 0 | 0 | FIN
CLO | UNIDO | Preparation of umbrella project for ODS phase out in the Aerosol sector (small-scale industries) | Individual | ASP | IND | ARS | 18 | PRP | 53 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-05-01 |  |  | 1997-06-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Conversion of electronic cleaning processes for ODS solvents to non-clean and hydrocarbon cleaning technologies at ERL-Bangalore | Individual | ASP | IND | SOL | 18 | INV | 65 | A | O | I | CFC TCA | 16.4 | 16.4 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2000-12-01 | 192421 | -2201 | 190220 | 190220 | 100% | 0 | 0 |  | 25014.73 | -286.13 | 24728.6 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to no-clean and aqueous photo resist developing and stripping technologies at ITI Palakkad | Individual | ASP | IND | SOL | 18 | INV | 66 | A | O | I | CFC TCA | 15 | 15 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1998-08-01 | 235744 | 5652 | 241396 | 241396 | 100% | 0 | 0 |  | 30646.72 | 734.76 | 31381.48 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to semi-aqueous cleaning and no-clean soldering technologies at ITI, Bangalore | Individual | ASP | IND | SOL | 19 | INV | 95 | A | O | I | CFC TCA | 7 | 7 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1996-12-01 | 1999-08-01 | 107954 | -978 | 106976 | 106976 | 100% | 0 | 0 |  | 14034.02 | -127.14 | 13906.88 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for phasing out ODS in the refrigeration sector (project under identification | Individual | ASP | IND | REF | 23 | PRP | 159 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2002-05-01 | 25000 | 24291 | 49291 | 49291 | 100% | 0 | 0 |  | 3250 | 3157.83 | 6407.83 | 0 | 0 | FIN
FIN | UNIDO | Preparation investment projects in the solvent (CFC 113) sector at Harbans Lal Mahotra & Sons Ltd. Calcutta | Individual | ASP | IND | SOL | 24 | PRP | 162 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 25000 | -216 | 24784 | 24784 | 100% | 0 | 0 |  | 3250 | -28.08 | 3221.92 | 0 | 0 | FIN
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS solvents to heat cleaning technologies and ODS free solvent coating at Malhotra Shaving Products Ltd. | Individual | ASP | IND | SOL | 25 | INV | 181 | A | O | I | CFC | 13.6 | 13.6 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-01-01 | 255112 | 0 | 255112 | 255112 | 100% | 0 | 0 |  | 33164.56 | 0 | 33164.56 | 0 | 0 | FIN
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS to heat cleaning technologies and ODS free solvent coating at Lal Malhotra & Sons Ltd. | Individual | ASP | IND | SOL | 26 | INV | 191 | A | O | I | CFC | 16 | 16 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 308899 | -58 | 308841 | 308841 | 100% | 0 | 0 |  | 40156.87 | -7.54 | 40149.33 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the solvent sector | Individual | ASP | IND | SOL | 27 | PRP | 195 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-07-20 | 2000-11-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 and CTC to processes based on IPA at Vidyut Metallics Ltd. (VML) | Individual | ASP | IND | SOL | 28 | INV | 223 | A | O | I | CFC CTC | 19.7 | 19.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2003-09-01 | 2004-06-01 | 225452 | -744 | 224708 | 224708 | 100% | 0 | 0 |  | 29308.76 | -96.72 | 29212.04 | 0 | 0 | FIN | [6 empty] | 2002-03-01
FIN | UNIDO | Conversion of cleaning processes from TCA and CTC to non-ODS solvent cleaning technologies (trichloroethylene and alkozypropanol) at Videocon Group (VDC) | Individual | ASP | IND | SOL | 28 | INV | 225 | A | O | I | CTC TCA | 7.2 | 7.2 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2002-01-01 | 2003-03-01 | 234978 | -376 | 234602 | 234602 | 100% | 0 | 0 |  | 30547.14 | -48.88 | 30498.26 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 to IPA and xylene at Microraj Electronics PVT Ltd. & RCC (Sales) PVT ltd., Hyderabad (MRJ) | Individual | ASP | IND | SOL | 28 | INV | 230 | A | O | I | CFC | 4.3 | 4.3 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2001-11-01 | 2002-12-01 | 85431 | -566 | 84865 | 84865 | 100% | 0 | 0 |  | 11106.03 | -73.58 | 11032.45 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 30 | PRP | 248 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 20000 | -734 | 19266 | 19266 | 100% | 0 | 0 |  | 2600 | -95.42 | 2504.58 | 0 | 0 | FIN
FIN | UNIDO | Formulation of CTC process cleaning agent project in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 264 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2002-03-01 | 2003-05-01 | 20000 | -292 | 19708 | 19708 | 100% | 0 | 0 |  | 2600 | -37.96 | 2562.04 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for SMEs in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 265 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2002-04-01 |  | 2003-06-01 | 2003-06-01 | 30000 | -76 | 29924 | 29924 | 100% | 0 | 0 |  | 3900 | -9.88 | 3890.12 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Blue Star Ltd., Thane | Individual | ASP | IND | SOL | 31 | INV | 266 | A | O | I | CTC | 6.6 | 6.6 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-12-01 | 2003-10-01 | 76027 | 0 | 76027 | 76027 | 100% | 0 | 0 |  | 9883.51 | 0 | 9883.51 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to trichloromethane at M/S Alpha Drugs India Ltd., Patiala | Individual | ASP | IND | PAG | 32 | INV | 283 | A | O | I | CTC | 69.7 | 69.7 |  |  | 2000-12-01 | 2001-11-01 | 2002-06-01 |  | 2003-03-01 | 2004-04-01 | 145866 | -361 | 145505 | 145505 | 100% | 0 | 0 |  | 15453 | -38.2442 | 15414.7558 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Svis Labs Ltd., Ranipet | Individual | ASP | IND | PAG | 32 | INV | 284 | A | O | R | CTC | 54.2 | 54.2 |  |  | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 249547 | -84 | 249463 | 249463 | 100% | 0 | 0 |  | 25352 | -8.5337 | 25343.4663 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Satya Deeptha Pharmaceuticals Ltd., Humnabad | Individual | ASP | IND | PAG | 32 | INV | 287 | A | O | I | CTC | 27.9 | 27.9 |  |  | 2000-12-01 | 2001-11-01 | 2002-07-01 |  | 2002-12-01 | 2004-12-01 | 260133 | -1070 | 259063 | 259063 | 100% | 0 | 0 |  | 33817.29 | -139.1 | 33678.19 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN.
FIN | UNIDO | Umbrella project for the conversion of three commercial refrigeration enterprises in New Delhi (Gaurav Controls, Thermoking and Western Engineering) | Individual | ASP | IND | REF | 32 | INV | 290 | A | O | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-01-01 | 2003-02-01 |  | 2004-08-01 | 2005-09-01 | 328894 | -49727 | 279167 | 279167 | 100% | 0 | 0 |  | 42756.22 | -6464.51 | 36291.71 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN.
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Doctors Organic Chemicals Ltd., Tanuku | Individual | ASP | IND | PAG | 32 | INV | 291 | A | O | I | CTC | 94.6 | 94.6 |  |  | 2000-12-01 | 2002-01-01 | 2002-06-01 |  | 2002-12-01 | 2003-12-01 | 288809 | -629 | 288180 | 288180 | 100% | 0 | 0 |  | 37545.17 | -81.77 | 37463.4 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the process agent (pharmaceutical) sector | Individual | ASP | IND | PAG | 33 | PRP | 302 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-10-01 |  | 2003-10-01 | 2004-09-01 | 70000 | -5915 | 64085 | 64085 | 100% | 0 | 0 |  | 9100 | -768.95 | 8331.05 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at M/S Benzo Chemical Industries, Tarapore | Individual | ASP | IND | PAG | 34 | INV | 303 | A | O | I | CTC | 23 | 23 |  |  | 2001-07-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 |  | 136786 | 0 | 136786 | 118502 | 86.63% | 18284 | 11269 | 11269 | 17782.18 | 0 | 15405.26 | 2376.92 | 1464.97 | [8 empty] | 2004-12-01 |  |  | 2001 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Engineering, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 306 | A | O | I | CTC | 14.5 | 14.5 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 240435 | -143 | 240292 | 240292 | 100% | 0 | 0 |  | 31256.55 | -18.59 | 31237.96 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Engineer Industries, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 308 | A | O | I | CTC | 20.2 | 20.2 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 238776 | -67 | 238709 | 238709 | 100% | 0 | 0 |  | 31040.88 | -8.71 | 31032.17 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at Praddep Shetye Ltd., Alibagh | Individual | ASP | IND | PAG | 34 | INV | 311 | A | O | I | CTC | 133.9 | 133.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 |  | 279001 | 0 | 279001 | 231266 | 82.89% | 47735 | 47645 | 47645 | 36270.13 | 0 | 30064.58 | 6205.55 | 6193.85 | [8 empty] | 2004-12-01 |  |  | 2001 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to ethylene dichloride at Chiplun Fine Chemicals Ltd., Ratnagiri | Individual | ASP | IND | PAG | 34 | INV | 313 | A | O | I | CTC | 16.7 | 16.7 |  |  | 2001-07-01 | 2002-02-01 | 2003-02-01 |  | 2003-07-01 | 2004-09-01 | 155830 | -15 | 155815 | 155815 | 100% | 0 | 0 |  | 20257.9 | -1.95 | 20255.95 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at FDC Limited, Roha | Individual | ASP | IND | PAG | 34 | INV | 314 | A | O | I | CTC | 34.1 | 34.1 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 |  | 238371 | 0 | 238371 | 215206 | 90.28% | 23165 | 22974 | 22974 | 30988.23 | 0 | 27976.78 | 3011.45 | 2986.62 | [11 empty] | 2001 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at GRD Chemicals Ltd., Indore, M.P. | Individual | ASP | IND | PAG | 34 | INV | 316 | A | O | I | CTC | 17.9 | 17.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-04-01 | 127667 | -70 | 127597 | 127597 | 100% | 0 | 0 |  | 16596.71 | -9.1 | 16587.61 | 0 | 0 | Financial completion in Apr 2005. | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Coils Ltd., Palghar | Individual | ASP | IND | SOL | 34 | INV | 327 | A | O | I | CTC | 22.8 | 22.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 245024 | -145 | 244879 | 244879 | 100% | 0 | 0 |  | 31853.12 | -18.85 | 31834.27 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion of carbon tetrachloride as process agent to cyclohexane at Amoli Organics Ltd., Mumbai | Individual | ASP | IND | PAG | 35 | INV | 338 | A | O | I | CTC | 38.5 | 38.5 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-08-01 |  | 385367 | 0 | 385367 | 312982 | 81.22% | 72385 | 72341 | 72000 | 50097.71 | 0 | 40687.66 | 9410.05 | 9404.33 | [11 empty] | 2001 | INV
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 36 | PRP | 346 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-04-01 |  | 2003-09-01 | 2004-09-01 | 30000 | -4929 | 25071 | 25071 | 100% | 0 | 0 |  | 3900 | -640.77 | 3259.23 | 0 | 0 | FIN | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of an investment project in the solvent (CFC-113) sector | Individual | ASP | IND | SOL | 36 | PRP | 347 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-04-01 | 2004-04-01 | 30000 | -526 | 29474 | 29474 | 100% | 0 | 0 |  | 3900 | -68.38 | 3831.62 | 0 | 0 | FIN | [10 empty] | 2002 | INV
COM | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Navdeep Engineering, Palghar | Individual | ASP | IND | SOL | 38 | INV | 354 | A | O | I | CTC | 53.9 | 53.9 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-12-01 |  | 661842 | 0 | 661842 | 634442 | 95.86% | 27400 | 15815 | 15815 | 82802.62 | 0 | 79788.62 | 3014 | 1739.65 | Project completed in Dec 2005. | [10 empty] | 2002 | INV
ONG | UNIDO | Plan for phase-out of CFCs in the refrigeration (manufacturing) sector | Multi-Year | ASP | IND | REF | 38 | INV | 359 | A | O | I | CFC | 40 | 0 |  |  | 2002-11-01 | 2003-02-01 | 2004-12-01 | 2006-07-01 |  |  | 500000 | 0 | 500000 | 90367 | 18.07% | 409633 | 409633 | 409633 | 65000 | 0 | 11747.71 | 53252.29 | 53252.29 | Major delay due to time-consuming identification of all companies of transport refrigeration sub-sector eligible for assistance under the project. Government verified eligibility of enterprises and endorsed final list of 34 eligible companies on 27 Oct 2005. Sub-agreements with companies were signed. Bidding for supply of equipment and services started. Refrigeration equipment was delivered in Mar 2006, foaming equipment in Apr 2006. Installation and commissioning of equipment as well as training are expected during second quarter of 2006. In addition to the above 34 companies, Ozone Cell has identified another 5 companies of this sub-sector. Bidding for new equipment will start upon endorsement of 5 companies. Expected date of completion: July 2006. | [10 empty] | 2002 | INV | n.a. | n.a. |  |  | n.a. | n.a. | n.a.
ONG | UNIDO | Preparation of an investment project in the fumigant sector | Individual | ASP | IND | FUM | 39 | PRP | 360 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2004-07-01 | 2004-04-01 |  |  | 2005-12-01 | 35000 | 0 | 35000 | 960 | 2.743% | 34040 | 0 | 1 | 2625 | 0 | 72 | 2553 | 0 | There was a general agreement between the National Ozone Unit and UNIDO to cancel the project since there was no methyl bromide consumption. Financial completion in Dec 2005. | [10 empty] | 2003
COM | UNIDO | Conversion of CFC-113 as cleaning solvent to TCE at Bharat Electronics Limited (BEL), Bangalore | Individual | ASP | IND | SOL | 40 | INV | 362 | A | O | I | CFC | 16 | 16 |  |  | 2003-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-12-01 |  | 151291 | 0 | 151291 | 99641 | 65.86% | 51650 | 48325 | 48325 | 13616.19 | 0 | 8967.69 | 4648.5 | 4349.25 | Project completed in Dec 2005. | [10 empty] | 2003
ONG | UNIDO | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 366 | A | O | I | CFC | 67 | 0 |  |  | 2003-12-01 |  | 2005-12-01 | 2006-07-01 |  |  | 173200 | 0 | 173200 | 0 | 0% | 173200 | 0 | 60000 | 19052 | 0 | 0 | 19052 | 0 | Major delay due to time-consuming identification of all companies of transport refrigeration sub-sector eligible for assistance under the project. Government verified eligibility of enterprises and endorsed final list of 34 eligible companies on 27 Oct 2005. Sub-agreements with companies were signed. Bidding for supply of equipment and services started. Refrigeration equipment was delivered in Mar 2006, foaming equipment in Apr 2006. Installation and commissioning of equipment as well as training are expected during second quarter of 2006. In addition to the above 34 companies, Ozone Cell has identified another 5 companies of this sub-sector. Bidding for new equipment will start upon endorsement of 5 companies. Expected date of completion: July 2006. | [10 empty] | 2003 | INV | n.a. | n.a. |  |  | n.a. | n.a. | n.a.
ONG | UNIDO | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 385 | A | O | I | CTC | 733 | 0 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 | 2006-12-01 |  |  | 3500000 | 0 | 3500000 | 47476 | 1.356% | 3452524 | 18055 | 1200000 | 262500 | 0 | 3560.7 | 258939.3 | 1354.125 | 2005 annual programme was approved by 45th ExCom in Apr 2005. Eleven sub-projects were identified, prepared and approved. Procurement of equipment started in Nov 2005. The close investigation verified that the 2005 usage had been dramatically reduced. Programme for the eleven enterprises will be completed in 2006. Decision will be taken on activities for additional two enterprises. | [10 empty] | 2005 | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in domestic refrigeration industry | Individual | ASP | IRA | REF | 09 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-06-01 |  | 1996-05-01 | 1998-08-01 | 50000 | 13632 | 63632 | 63632 | 100% | 0 | 0 |  | 6500 | 1772.16 | 8272.16 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase-out CFC-11 and CFC-12 | Individual | ASP | IRA | REF | 11 | INV | 08 | A | O | I | CFC | 757 | 757 |  |  | 1993-11-01 | 1994-12-01 | 1995-11-01 |  | 1997-12-01 | 2002-09-01 | 3228395 | 5660850 | 8889245 | 8889245 | 100% | 0 | 0 |  | 419691.35 | 735910.5 | 1155601.85 | 0 | 0 | Status as at end March 2006 (in case of questions by the MFS at a later point): prodoc signed and Ozone Officer (Mr. Spasojevic) re-designated.
FIN | UNIDO | Preparation of investment project for phase-out of CFC-11 and CFC-12 in the commercial and small domestic refrigeration industry | Individual | ASP | IRA | REF | 15 | PRP | 09 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 50000 | -1 | 49999 | 49999 | 100% | 0 | 0 |  | 6500 | -0.13 | 6499.87 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector | Individual | ASP | IRA | SEV | 17 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-08-01 | 32065 | 698 | 32763 | 32763 | 100% | 0 | 0 |  | 4168.45 | 90.74 | 4259.19 | 0 | 0 | FIN
FIN | UNIDO | DBL project Iran. Phasing out CFC-11 through conversion of rigid PU-foam manufactured with the technique of continuous lamination at Fabis, Iran Steel, Mammoth Tehran, F.M., and Urethane Systems | Individual | ASP | IRA | FOA | 17 | INV | 11 | A | O | I | CFC | 1200 | 1200 |  |  | 1995-07-01 | 1995-12-01 | 1997-07-01 |  | 1998-12-01 | 2003-05-01 | 2571250 | -2772 | 2568478 | 2568478 | 100% | 0 | 0 |  | 334262.5 | -360.36 | 333902.14 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Movalled Home Appliances Co. | Individual | ASP | IRA | REF | 18 | INV | 12 | A | O | I | CFC | 70 | 70 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 607732 | -2461 | 605271 | 605270.7394 | 100% | 0.2606 | 0 |  | 79005.16 | -319.93 | 78685.1961 | 0.033878 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Machine Manufacturing Co. | Individual | ASP | IRA | REF | 18 | INV | 13 | A | O | I | CFC | 62 | 62 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 608605 | -2699 | 605906 | 605905.5278 | 100% | 0.4722 | 0 |  | 79118.65 | -350.87 | 78767.7186 | 0.061386 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Lorestan Refrigerator Manufacturing Industries | Individual | ASP | IRA | REF | 18 | INV | 14 | A | O | I | CFC | 94 | 94 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 615018 | -2765 | 612253 | 612253.4118 | 100% | -0.4118 | 0 |  | 79952.34 | -359.45 | 79592.9435 | -0.053534 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Gadook Industries, Co. | Individual | ASP | IRA | REF | 18 | INV | 15 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 373838 | -1535 | 372303 | 372303.3966 | 100% | -0.3966 | 0 |  | 48598.94 | -199.55 | 48399.4416 | -0.051558 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Faritz, Iran | Individual | ASP | IRA | REF | 18 | INV | 16 | A | O | I | CFC | 109 | 109 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 612504 | -2790 | 609714 | 609714.2582 | 100% | -0.2582 | 0 |  | 79625.52 | -362.7 | 79262.8536 | -0.033566 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Monark Co. | Individual | ASP | IRA | REF | 18 | INV | 17 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 369939 | -1444 | 368495 | 368494.6662 | 100% | 0.3338 | 0 |  | 48092.07 | -187.72 | 47904.3066 | 0.043394 | 0 | FIN
FIN | UNIDO | Project formulation in the commercial refrigeration sector (remaining enterprises), compressors and the foam sector | Individual | ASP | IRA | SEV | 21 | PRP | 19 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-03-01 | 50000 | -59 | 49941 | 49941 | 100% | 0 | 0 |  | 6500 | -7.67 | 6492.33 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Safoam Co. | Individual | ASP | IRA | FOA | 22 | INV | 20 | A | O | I | CFC | 120 | 120 |  |  | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 2002-12-01 | 2003-12-01 | 487125 | -659 | 486466 | 486466 | 100% | 0 | 0 |  | 63326.25 | -85.67 | 63240.58 | 0 | 0 | FIN |  |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Urethane Systems Company (USC) | Individual | ASP | IRA | FOA | 22 | INV | 21 | A | O | I | CFC | 110 | 110 |  |  | 1997-05-01 | 2001-09-01 | 1998-06-01 |  | 2003-03-01 | 2004-02-01 | 487125 | -5455 | 481670 | 481670 | 100% | 0 | 0 |  | 63326.25 | -709.15 | 62617.1 | 0 | 0 | FIN |  |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 from flexible slabstock foam manufacturing at Shizar Co. | Individual | ASP | IRA | FOA | 22 | INV | 22 | A | O | I | CFC | 120 | 120 |  |  | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2003-12-01 | 2004-12-01 | 487125 | 0 | 487125 | 487125 | 100% | 0 | 0 |  | 63326.25 | 0 | 63326.25 | 0 | 0 | FIN |  |  |  | 2000-11-01
FIN | UNIDO | Phasing out ODS at Electro Steel Co. | Individual | ASP | IRA | REF | 23 | INV | 24 | A | O | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 898159 | -22145 | 876014 | 876014 | 100% | 0 | 0 |  | 116760.67 | -2878.85 | 113881.82 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Chavan Manufacturing Company | Individual | ASP | IRA | REF | 23 | INV | 25 | A | O | I | CFC | 41.8 | 41.8 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-03-01 | 527802 | 0 | 527802 | 527802 | 100% | 0 | 0 |  | 68614.26 | 0 | 68614.26 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Saran Co. | Individual | ASP | IRA | REF | 23 | INV | 26 | A | O | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 2002-06-01 | 2003-10-01 | 458663 | -3698 | 454965 | 454965 | 100% | 0 | 0 |  | 59626.19 | -480.74 | 59145.45 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector for phasing out ODS at three enterprises including Bahaman Plastic | Individual | ASP | IRA | FOA | 23 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-06-01 |  | 2000-09-01 | 2001-07-01 | 10000 | -2573 | 7427 | 7427 | 100% | 0 | 0 |  | 1300 | -334.49 | 965.51 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Zagross II Co. | Individual | ASP | IRA | REF | 23 | INV | 28 | A | O | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 444858 | -4433 | 440425 | 440425 | 100% | 0 | 0 |  | 57831.54 | -576.29 | 57255.25 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Mashhad Foam | Individual | ASP | IRA | FOA | 23 | INV | 29 | A | O | I | CFC | 90 | 90 |  |  | 1997-11-01 | 1999-01-01 | 1998-12-01 |  | 2003-12-01 | 2004-12-01 | 503330 | -2651 | 500679 | 500679 | 100% | 0 | 0 |  | 65432.9 | -344.63 | 65088.27 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. |  |  |  | 2000-11-01
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | IRA | FUM | 23 | PRP | 33 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13013 | 23013 | 23013 | 100% | 0 | 0 |  | 1300 | 1691.69 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at Sobouhi Refrigeration | Individual | ASP | IRA | REF | 26 | INV | 35 | A | O | I | CFC | 30.4 | 30.4 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 237847 | -24107 | 213740 | 213740 | 100% | 0 | 0 |  | 30920.11 | -3133.91 | 27786.2 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b in manufacture of commercial refrigeration equipment at Yazd Arg Metal, Yazd Sardin and Shervin Electric | Individual | ASP | IRA | REF | 26 | INV | 37 | A | O | I | CFC | 62.2 | 62.2 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2003-02-01 | 743990 | -96393 | 647597 | 647597 | 100% | 0 | 0 |  | 91838.9 | -10603.23 | 81235.67 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 27 | PRP | 38 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -1836 | 18164 | 18164 | 100% | 0 | 0 |  | 2600 | -238.68 | 2361.32 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IRA | FOA | 27 | PRP | 39 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 18000 | -1187 | 16813 | 16813 | 100% | 0 | 0 |  | 2340 | -154.31 | 2185.69 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and domestic refrigeration at the Sherkate Sanayee Emerson (Emerson Co). | Individual | ASP | IRA | REF | 28 | INV | 42 | A | O | I | CFC | 45.8 | 45.8 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-05-01 | 343873 | -10568 | 333305 | 333305 | 100% | 0 | 0 |  | 44703.49 | -1373.84 | 43329.65 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b AND cfc-12 TO hfc-134A in commercial refrigeration at the second group of Iranian Commercial Refrigeration Manufacturers | Individual | ASP | IRA | REF | 28 | INV | 45 | A | O | I | CFC | 42.5 | 42.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-09-01 | 309966 | -2110 | 307856 | 307856 | 100% | 0 | 0 |  | 40295.58 | -274.3 | 40021.28 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Broudati Ghandil Iran (Ghandil Co.) | Individual | ASP | IRA | REF | 28 | INV | 47 | A | O | I | CFC | 27.5 | 27.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 335423 | -4448 | 330975 | 330975 | 100% | 0 | 0 |  | 43604.99 | -578.24 | 43026.75 | 0 | 0 | FIN
ONG | UNIDO | Phasing out ODS in manufacturing of flexible PU slabstock foam through the use of liquid CO2 blowing technology at Bahman Plastic Co. | Individual | ASP | IRA | FOA | 28 | INV | 50 | A | O | I | CFC | 83 | 0 |  |  | 1999-07-01 | 2000-11-01 | 2001-02-01 | 2006-12-01 |  |  | 485929 | 0 | 485929 | 435445 | 89.61% | 50484 | 45000 | 50000 | 63170.77 | 0 | 56607.85 | 6562.92 | 5850 | Project is monitored under project implementation delays as reported to the 48th ExCom in Apr 2006. According to the NOU of Iran, the company's management has resolved the labour relation issues and soon will be moving the equipment to the new site which is under preparation. Project is planned to be completed by Dec 2006 after installation and commissioning of equipment. | [5 empty] | 2002-06-01
ONG | UNIDO | Replacement of CFC-12 refrigerant by HFC-134a at Iran Compressor Manufacturing Company (ICMC) | Individual | ASP | IRA | REF | 28 | INV | 51 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 | 2006-12-01 |  |  | 1076148 | 84000 | 1160148 | 1098472 | 94.68% | 61676 | 38397 | 45000 | 128376.28 | 9240 | 130831.92 | 6784.36 | 4223.67 | Project is monitored under project implementation delays as reported to the 48th ExCom in Apr 2006. Arrangement was made for repair of the damaged equipment at the UK. Upon its arrival, repair will take around 3 months. Project is expected to be completed by Dec 2006 after installation and commissioning of equipment.
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Saiwan Sannat Co. | Individual | ASP | IRA | REF | 29 | INV | 52 | A | O | I | CFC | 14.9 | 14.9 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-03-01 | 200709 | 0 | 200709 | 200709 | 100% | 0 | 0 |  | 26092.17 | 0 | 26092.17 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Sanaayee Toulidy Bard Co. | Individual | ASP | IRA | REF | 29 | INV | 53 | A | O | I | CFC | 16.4 | 16.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 205529 | -2 | 205527 | 205527 | 100% | 0 | 0 |  | 26718.77 | -0.26 | 26718.51 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Minavand Refrigeration Company | Individual | ASP | IRA | REF | 29 | INV | 54 | A | O | I | CFC | 13.4 | 13.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 176777 | -3583 | 173194 | 173194 | 100% | 0 | 0 |  | 22981.01 | -465.79 | 22515.22 | 0 | 0 | FIN
ONG | UNIDO | Phasing out of the important non critical, non-essential use of methyl bromide for post-harvest treatment | Individual | ASP | IRA | FUM | 29 | INV | 57 | A | O | I | MBR | 12.4 | 10 |  |  | 1999-11-01 | 2000-04-01 | 2001-12-01 | 2006-12-01 |  |  | 260698 | 0 | 260698 | 172843 | 66.3% | 87855 | 55365 | 50000 | 33890.74 | 0 | 22469.59 | 11421.15 | 7197.45 | Project is monitored under project implementation delays as reported to the 48th ExCom in Apr 2006. Project is delayed since none of the proposals received for modification of the chambers were technically acceptable. National expert has been recruited to re-assess the items to be modified in the selected chambers. After completion of this assessment, proposals will be requested from companies. Project is planned to be completed by Dec 2006.
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Forouzan Yakhchal Company (Forouzan Ref. Co.) | Individual | ASP | IRA | REF | 29 | INV | 59 | A | O | I | CFC | 16.7 | 16.7 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 192704 | -5655 | 187049 | 187049 | 100% | 0 | 0 |  | 25051.52 | -735.15 | 24316.37 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 30 | PRP | 61 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-05-01 | 2003-02-01 | 30000 | -155 | 29845 | 29845 | 100% | 0 | 0 |  | 3900 | -20.15 | 3879.85 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at Sanayee Broudati Partou Sard Tawan (Barez-Himalia) and Sanayee Broudati Himalia (Himalia) | Individual | ASP | IRA | REF | 31 | INV | 69 | A | O | I | CFC | 36.09 | 36.09 |  |  | 2000-07-01 | 2000-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-06-01 | 377544 | -4346 | 373198 | 373198 | 100% | 0 | 0 |  | 49080.72 | -564.98 | 48515.74 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | ASP | IRA | REF | 31 | PRP | 72 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-04-01 | 2002-01-01 |  | 2002-08-01 | 2003-02-01 | 70000 | -1540 | 68460 | 68460 | 100% | 0 | 0 |  | 9100 | -200.2 | 8899.8 | 0 | 0 | FIN
COM | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Rashestan Co. | Individual | ASP | IRA | FOA | 31 | INV | 73 | A | O | I | CFC | 70 | 70 |  |  | 2000-07-01 | 2001-04-01 | 2003-01-01 |  | 2005-07-01 | 2005-12-01 | 539882 | 0 | 539882 | 539160 | 99.87% | 722 | 0 | 1 | 69387.02 | 0 | 69307.6 | 79.42 | 0 | Project completed in Jul 2005. The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom.
CLO | UNIDO | Project preparation in soil fumigation | Individual | ASP | IRA | FUM | 33 | PRP | 78 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  |  | 2003-05-01 | 25000 | -19853 | 5147 | 5147 | 100% | 0 | 0 |  | 3250 | -2580.89 | 669.11 | 0 | 0 | CLO | [10 empty] | 2001 | INV
COM | UNIDO | Project preparation in the solvent (CTC) sector | Individual | ASP | IRA | SOL | 33 | PRP | 80 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2005-12-01 |  | 20000 | 0 | 20000 | 19982 | 99.91% | 18 | 0 | 1 | 2600 | 0 | 2597.66 | 2.34 | 0 | Project completed in Dec 2005. | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the Takran Mobbarad Co. | Individual | ASP | IRA | REF | 34 | INV | 98 | A | O | I | CFC | 9.6 | 9.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 119864 | -3100 | 116764 | 116764 | 100% | 0 | 0 |  | 15582.32 | -403 | 15179.32 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Tehran Shirak | Individual | ASP | IRA | REF | 34 | INV | 101 | A | O | I | CFC | 20.5 | 20.5 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2005-09-01 | 202836 | -1968 | 200868 | 200868 | 100% | 0 | 0 |  | 26368.68 | -255.84 | 26112.84 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2000 | INV
FIN | UNIDO | Preparation of 12 investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 102 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 15000 | -426 | 14574 | 14574 | 100% | 0 | 0 |  | 1950 | -55.38 | 1894.62 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Donyaye Mojdeh | Individual | ASP | IRA | REF | 34 | INV | 103 | A | O | I | CFC | 15.4 | 15.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2004-09-01 | 191020 | -2524 | 188496 | 188496 | 100% | 0 | 0 |  | 24832.6 | -328.12 | 24504.48 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Zarifan Mashad | Individual | ASP | IRA | REF | 34 | INV | 104 | A | O | I | CFC | 22 | 22 |  |  | 2001-07-01 | 2002-03-01 | 2003-12-01 |  | 2004-06-01 | 2005-12-01 | 200550 | 0 | 200550 | 199051 | 99.25% | 1499 | 0 | 1 | 26071.5 | 0 | 25876.63 | 194.87 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Novin Enjemad | Individual | ASP | IRA | REF | 34 | INV | 105 | A | O | I | CFC | 10.1 | 10.1 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 138702 | -1882 | 136820 | 136820 | 100% | 0 | 0 |  | 18031.26 | -244.66 | 17786.6 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | ASP | IRA | FOA | 34 | PRP | 106 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-03-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 20000 | -870 | 19130 | 19130 | 100% | 0 | 0 |  | 2600 | -113.1 | 2486.9 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Roshan Ind. Group | Individual | ASP | IRA | REF | 34 | INV | 107 | A | O | I | CFC | 18.6 | 18.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 |  | 203960 | 0 | 203960 | 198444 | 97.3% | 5516 | 4423 | 4423 | 26514.8 | 0 | 25797.72 | 717.08 | 574.99 | [11 empty] | 2000 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Avaj Sarma Co. | Individual | ASP | IRA | REF | 34 | INV | 108 | A | O | I | CFC | 15.2 | 15.2 |  |  | 2001-07-01 | 2001-11-01 | 2004-08-01 |  | 2004-06-01 | 2005-08-01 | 176477 | -813 | 175664 | 175664 | 100% | 0 | 0 |  | 22942.01 | -105.69 | 22836.32 | 0 | 0 | Financial closure in Aug 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Arjah Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 111 | A | O | I | CFC | 27.4 | 27.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2005-06-01 |  | 209425 | 0 | 209425 | 192121 | 91.74% | 17304 | 17000 | 17000 | 27225.25 | 0 | 24975.73 | 2249.52 | 2210 | Project completed in Jun 2005. | [10 empty] | 2000 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Gasso Co. | Individual | ASP | IRA | REF | 34 | INV | 113 | A | O | I | CFC | 11.7 | 11.7 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 |  | 158232 | 0 | 158232 | 153178 | 96.81% | 5054 | 4717 | 4717 | 20570.16 | 0 | 19913.14 | 657.02 | 613.21 | [11 empty] | 2001 | INV
FIN | UNIDO | Phasing out ODS in the manufacture of flexible slab stock foam through the use of LCD blowing technology at Abre Shomal Co. | Individual | ASP | IRA | FOA | 35 | INV | 115 | A | O | I | CFC | 90.4 | 90.4 |  |  | 2001-12-01 | 2002-06-01 | 2003-07-01 |  | 2004-03-01 | 2005-08-01 | 552148 | -51404 | 500744 | 500744 | 100% | 0 | 0 |  | 70736.28 | -5654.44 | 65081.84 | 0 | 0 | Financial completion in Aug 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Abbaspour Co. | Individual | ASP | IRA | REF | 35 | INV | 119 | A | O | I | CFC | 9.7 | 9.7 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 144206 | -968 | 143238 | 143238 | 100% | 0 | 0 |  | 18746.78 | -125.84 | 18620.94 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Moradi Company | Individual | ASP | IRA | REF | 35 | INV | 120 | A | O | I | CFC | 6.4 | 6.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 |  | 82400 | 0 | 82400 | 74242 | 90.1% | 8158 | 6250 | 6250 | 10712 | 0 | 9651.46 | 1060.54 | 812.5 | [11 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Bouran Saz Karaj (Kohsar Co.) | Individual | ASP | IRA | REF | 35 | INV | 121 | A | O | I | CFC | 9.6 | 9.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 120526 | -2212 | 118314 | 118314 | 100% | 0 | 0 |  | 15668.38 | -287.56 | 15380.82 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Sherkate Taavoni 435 (Khorsandi Co.) | Individual | ASP | IRA | REF | 35 | INV | 122 | A | O | I | CFC | 5.4 | 5.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 82107 | -1998 | 80109 | 80109 | 100% | 0 | 0 |  | 10673.91 | -259.74 | 10414.17 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alborz Neishabour | Individual | ASP | IRA | REF | 35 | INV | 123 | A | O | I | CFC | 16 | 16 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2005-08-01 | 189669 | -4860 | 184809 | 184809 | 100% | 0 | 0 |  | 24656.97 | -631.8 | 24025.17 | 0 | 0 | Aug 2005: Financial completion in Aug 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at the Ariz Pooyaye Sanat (Ariz Co.) | Individual | ASP | IRA | REF | 35 | INV | 124 | A | O | I | CFC | 7.6 | 7.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 |  | 86365 | 0 | 86365 | 76482 | 88.56% | 9883 | 6000 | 6000 | 11227.45 | 0 | 9942.66 | 1284.79 | 780 | [11 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Yaghoubali Bazdid Vahdat (Isun Co.) | Individual | ASP | IRA | REF | 35 | INV | 125 | A | O | I | CFC | 10.5 | 10.5 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 131605 | -3104 | 128501 | 128501 | 100% | 0 | 0 |  | 17108.65 | -403.52 | 16705.13 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Darvish Mohamad Nazari Company (Jahan Nama) | Individual | ASP | IRA | REF | 35 | INV | 126 | A | O | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 |  | 139970 | 0 | 139970 | 122259 | 87.35% | 17711 | 16953 | 17000 | 18196.1 | 0 | 15893.67 | 2302.43 | 2203.89 | [11 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Borna Sanat Arak | Individual | ASP | IRA | REF | 35 | INV | 127 | A | O | I | CFC | 8 | 8 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 |  | 108238 | 0 | 108238 | 90936 | 84.01% | 17302 | 16500 | 16500 | 14070.94 | 0 | 11821.68 | 2249.26 | 2145 | [11 empty] | 2001 | INV
COM | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sard Va Garm | Individual | ASP | IRA | REF | 35 | INV | 128 | A | O | I | CFC | 8.4 | 8.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 |  | 125350 | 0 | 125350 | 104089 | 83.04% | 21261 | 16500 | 16500 | 16295.5 | 0 | 13531.57 | 2763.93 | 2145 | [11 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardintous Co. | Individual | ASP | IRA | REF | 35 | INV | 129 | A | O | I | CFC | 10.3 | 10.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 145879 | -512 | 145367 | 145367 | 100% | 0 | 0 |  | 18964.27 | -66.56 | 18897.71 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Gostar Co. | Individual | ASP | IRA | REF | 35 | INV | 130 | A | O | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 100384 | -3956 | 96428 | 96428 | 100% | 0 | 0 |  | 13049.92 | -514.28 | 12535.64 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of 3 umbrella investment projects in the commercial and domestic refrigeration sector | Individual | ASP | IRA | REF | 36 | PRP | 146 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 30000 | -2153 | 27847 | 27847 | 100% | 0 | 0 |  | 3900 | -279.89 | 3620.11 | 0 | 0 | FIN | [10 empty] | 2002 | INV
FIN | UNIDO | Formulation of two umbrella investment projects in the rigid and flexible foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 148 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2003-10-01 | 2004-07-01 | 35000 | -612 | 34388 | 34388 | 100% | 0 | 0 |  | 4550 | -79.56 | 4470.44 | 0 | 0 | FIN | [10 empty] | 2002 | INV
ONG | UNIDO | Phasing out of ODS in the manufacture of flexible slabstock foam through the use of LCD blowing technology at Esfanj Shirvan Co. | Individual | ASP | IRA | FOA | 37 | INV | 149 | A | O | I | CFC | 91.1 | 91.1 |  |  | 2002-07-01 | 2002-11-01 | 2004-03-01 | 2006-11-01 |  |  | 373515 | 0 | 373515 | 299425 | 80.16% | 74090 | 74000 | 74000 | 48556.95 | 0 | 38925.25 | 9631.7 | 9620 | The company is not using CFCs (by making high-density foams). Awaiting manufacturing of CO2 tank and finalization of commissioning. | [8 empty] | 2005-06-01 |  | 2002 | INV
COM | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Yakhchavan Co. | Individual | ASP | IRA | FOA | 37 | INV | 155 | A | O | I | CFC | 73.6 | 73.6 |  |  | 2002-07-01 | 2002-11-01 | 2005-03-01 |  | 2005-12-01 |  | 531838 | 0 | 531838 | 509646 | 95.83% | 22192 | 17569 | 17569 | 68502.18 | 0 | 66061.06 | 2441.12 | 1932.59 | Project completed in Dec 2005. | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of investment projects in the solvent sector (CTC/TCA) | Individual | ASP | IRA | SOL | 39 | PRP | 158 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | -1 | 9999 | 9999 | 100% | 0 | 0 |  | 750 | -0.075 | 749.925 | 0 | 0 | FIN | [10 empty] | 2003
COM | UNIDO | National CFC phase-out plan (first tranche of implementation plan 2004) | Multi-Year | ASP | IRA | PHA | 41 | INV | 162 | A | O | I | CFC | 274.1 | 274.1 |  |  | 2003-12-01 | 2004-03-01 | 2005-04-01 |  | 2005-12-01 |  | 361840 | 2104066 | 2465906 | 1797029 | 72.88% | 668877 | 661648 | 668877 | 27138 | 157804.95 | 134777.175 | 50165.775 | 49623.6 | Project completed in Dec 2005. | [10 empty] | 20032004 | INV | n.a. | n.a. |  |  | n.a. | n.a. | n.a.
COM | UNIDO | Preparation of investment projects in the solvent sector CTC/TCA | Individual | ASP | IRA | SOL | 42 | PRP | 164 | A | O | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 7590 | 50.6% | 7410 | 7309 | 7309 | 1125 | 0 | 569.25 | 555.75 | 548.175 | Project completed in Dec 2005. | [10 empty] | 2004 | NON-INV
COM | UNIDO | Preparatory assistance in methyl bromide (soil fumigation in olive tree nurseries) | Individual | ASP | IRA | FUM | 44 | PRP | 168 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 |  | 9830 | 0 | 9830 | 6846 | 69.64% | 2984 | 1861 | 1861 | 737.25 | 0 | 513.45 | 223.8 | 139.575 | Project completed in Dec 2005. Remaining funds will be returned upon financial completion of the project. | [10 empty] | 2004
ONG | UNIDO | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 170 | A | O | I | CFC | 115.5 | 115.5 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  |  | 742449 | 0 | 742449 | 66921 | 9.014% | 675528 | 224078 | 400000 | 55683.675 | 0 | 5019.075 | 50664.6 | 16805.85 | 2005 annual implementation programme was approved by 45th ExCom in Apr 2005. Training of trainers and customs training were completed. Equipment was procured and delivered. A total phase-out of 115.5 ODP tonnes was achieved. In 2006, 75 sets of recovery and recycling equipment were distributed, installed and commissioned. Remaining recovery and recycling equipment is being purchased. The next tranche was submitted and approved by 48th ExCom in Apr 2006. | [10 empty] | 2005 | INV | n.a. | n.a. |  |  | n.a. | n.a. | n.a.
ONG | UNIDO | Preparation of an MDI project | Individual | ASP | IRA | ARS | 47 | PRP | 173 | A | O | I |  |  | 0 |  |  | 2005-11-01 |  | 2006-12-01 | 2007-08-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 35000 | 5250 | 0 | 0 | 5250 | 0 | PRP project was approved by 47th ExCom in Nov 2005. MDI sector plan will be ready mid-2007 for submission to ExCom. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Total phase-out of methyl bromide in soil fumigation in olive seedings, fruit trees, nurseries and others | Individual | ASP | IRA | FUM | 47 | INV | 175 | A | O | I | MBR | 14.4 | 0 |  |  | 2005-11-01 |  | 2010-12-01 | 2010-12-01 |  |  | 227950 | 0 | 227950 | 0 | 0% | 227950 | 0 | 50000 | 20515.5 | 0 | 0 | 20515.5 | 0 | Project was approved by 47th ExCom in Nov 2005. Terms of reference for the purchase of boilers are under preparation. | [10 empty] | 2005 | INV
CLO | UNIDO | Project formulation for the ODS phase-out in the refrigeration sector | Individual | AFR | IVC | REF | 16 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  |  | 1999-11-01 | 15000 | -108 | 14892 | 14892 | 100% | 0 | 0 |  | 1950 | -14.04 | 1935.96 | 0 | 0 | CLO
FIN | UNIDO | ODS phase-out of a foam producing plant (Fabrique Ivoirienne de mousse et amemblement) and 2 aerosol fillers (Sicobel and Gandoor) | Individual | AFR | IVC | SEV | 17 | PRP | 05 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-02-01 | 1995-09-01 |  | 1996-10-01 | 1998-08-01 | 10000 | -403 | 9597 | 9597 | 100% | 0 | 0 |  | 1300 | -52.39 | 1247.61 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at F.I.M.A. flexible polyurethane foam plant | Individual | AFR | IVC | FOA | 19 | INV | 06 | A | O | I | CFC | 53.1 | 53.1 |  |  | 1996-05-01 | 1997-09-01 | 1997-07-01 |  | 1997-12-01 | 2001-03-01 | 85087 | -380 | 84707 | 84707 | 100% | 0 | 0 |  | 11061.31 | -49.4 | 11011.91 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Parfumerie Gandour D.A.F. | Individual | AFR | IVC | ARS | 20 | INV | 07 | A | O | I | CFC | 66 | 66 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-10-01 | 106061 | 0 | 106061 | 106061 | 100% | 0 | 0 |  | 13787.93 | 0 | 13787.93 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Sicobel | Individual | AFR | IVC | ARS | 20 | INV | 08 | A | O | I | CFC | 20.8 | 20.8 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-09-01 | 59171 | -546 | 58625 | 58625 | 100% | 0 | 0 |  | 7692.23 | -70.98 | 7621.25 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of an investment project in the domestic refrigeration (hydrocarbon) sector for Serti | Individual | AFR | IVC | REF | 24 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-10-01 | 2000-12-01 | 20000 | -10932 | 9068 | 9068 | 100% | 0 | 0 |  | 2600 | -1421.16 | 1178.84 | 0 | 0 | FIN |  |  |  | 1999-06-01
CLO | UNIDO | Preparation of a project for stored commodities (cocoa beans) | Individual | AFR | IVC | FUM | 27 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector | Individual | AFR | IVC | FUM | 39 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-11-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | -214 | 9786 | 9786 | 100% | 0 | 0 |  | 750 | -16.05 | 733.95 | 0 | 0 | FIN | [10 empty] | 2003
ONG | UNIDO | Phase-out the use of methyl bromide commodities and storage fumigation | Individual | AFR | IVC | FUM | 42 | INV | 19 | A | O | I | MBR | 8.5 | 4.7 |  |  | 2004-04-01 | 2004-04-01 | 2006-10-01 | 2006-12-01 |  |  | 222210 | 0 | 222210 | 143405 | 64.54% | 78805 | 20944 | 60944 | 19998.9 | 0 | 12906.45 | 7092.45 | 1884.96 | All equipment was delivered. First and second sections of training were executed in May and Oct 2005. Due to the very tense political situation, further training has been frozen. A partial phase-out of 2.5 ODP tonnes was achieved. Progress report was submitted and approved by 48th ExCom in Apr 2006. Project is planned to be completed by Dec 2006 after procurement and delivery of last set of equipment. | [10 empty] | 2004 | INV
COM | UNIDO | Preparation of an investment project in the aerosol sector | Individual | AFR | IVC | ARS | 44 | PRP | 22 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 13168 | 87.79% | 1832 | 1423 | 1400 | 1125 | 0 | 987.6 | 137.4 | 106.725 | Project completed in Dec 2005. | [10 empty] | 2004
ONG | UNIDO | Phase-out of CFC-12 in the manufacture of cosmetics aerosols (deodorants) by conversion to hydrocarbon aerosol propellant (HAP) at COPACI, Abidjan (terminal aerosol sector project) | Individual | AFR | IVC | ARS | 46 | INV | 23 | A | O | I | CFC | 43.4 | 0 |  |  | 2005-07-01 | 2005-10-01 | 2007-09-01 | 2007-09-01 |  |  | 110428 | 0 | 110428 | 908 | 0.8223% | 109520 | 25 | 60000 | 9938.52 | 0 | 81.72 | 9856.8 | 2.25 | Project was approved by 46th ExCom in July 2005. Mission was undertaken to verify status and scope of equipment to be redeployed from Alkaloid, Macedonia, to COPACI, Abidjan. Feasibility of equipment redeployment is being discussed with subcontractor. | [10 empty] | 2005 | INV
FIN | UNIDO | Preparation of a phase out project (tobacco fumigation) | Individual | LAC | JAM | FUM | 24 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-09-01 | 2001-07-01 | 25000 | -1987 | 23013 | 23013 | 100% | 0 | 0 |  | 3250 | -258.31 | 2991.69 | 0 | 0 | FIN
CLO | UNIDO | Demonstration project - alternatives to the use of methyl bromide in structural and commodity fumigation | Individual | LAC | JAM | FUM | 26 | DEM | 10 | A | O | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  |  | 2001-07-01 | 102850 | -102850 | 0 | 0 |  | 0 | 0 |  | 13370.5 | -13370.5 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of investment project for phase out of ODS in selected industries in the refrigeration and air-conditioning sector | Individual | ASP | JOR | REF | 10 | PRP | 16 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1993-10-01 |  | 1994-12-01 | 1998-08-01 | 90000 | -15049 | 74951 | 74951 | 100% | 0 | 0 |  | 11700 | -1956.37 | 9743.63 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at National Refrigeration Co. (NRC) | Individual | ASP | JOR | REF | 13 | INV | 18 | A | O | I | CFC | 14.3 | 19.3 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-07-01 | 813887 | -1319 | 812568 | 812568 | 100% | 0 | 0 |  | 105805.31 | -171.47 | 105633.84 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Household Appliance Manufacturing Co. (HAMCO) | Individual | ASP | JOR | REF | 13 | INV | 19 | A | O | I | CFC | 21.2 | 21.2 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 775602 | -145 | 775457 | 775457 | 100% | 0 | 0 |  | 100828.26 | -18.85 | 100809.41 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Middle East Electrical Industries Co. Ltd. | Individual | ASP | JOR | REF | 13 | INV | 20 | A | O | I | CFC | 16.6 | 23 |  |  | 1994-07-01 | 1994-12-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 883153 | -1451 | 881702 | 881702 | 100% | 0 | 0 |  | 114809.89 | -188.63 | 114621.26 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for investment projects in commercial refrigeration, air-conditioning, foam and halon sectors | Individual | ASP | JOR | SEV | 15 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 50000 | -905 | 49095 | 49095 | 100% | 0 | 0 |  | 6500 | -117.65 | 6382.35 | 0 | 0 | FIN |  |  | 1997-07-01 | 1999-02-01
FIN | UNIDO | Phasing out CFC at Abdin Industrial Est.Co. | Individual | ASP | JOR | REF | 20 | INV | 29 | A | O | I | CFC | 10.4 | 21.5 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1997-12-01 | 2000-07-01 | 116928 | -820 | 116108 | 116108 | 100% | 0 | 0 |  | 15200.64 | -106.6 | 15094.04 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at the Ihsan & Tahseen Baalbaki Co. | Individual | ASP | JOR | REF | 23 | INV | 35 | A | O | I | CFC | 66.5 | 66.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-06-01 | 2001-12-01 | 545103 | -6183 | 538920 | 538920 | 100% | 0 | 0 |  | 70863.39 | -803.79 | 70059.6 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | JOR | FUM | 23 | PRP | 36 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-03-01 | 2001-07-01 | 10000 | 13013 | 23013 | 23013 | 100% | 0 | 0 |  | 1300 | 1691.69 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | JOR | REF | 24 | PRP | 39 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-05-01 | 2000-12-01 | 30000 | -3452 | 26548 | 26548 | 100% | 0 | 0 |  | 3900 | -448.76 | 3451.24 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation and optimal use of soil fumigants in combination with an integrated pest management | Individual | ASP | JOR | FUM | 25 | DEM | 40 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-10-01 | 2000-08-01 |  | 2001-12-01 | 2003-08-01 | 385000 | -64725 | 320275 | 320275 | 100% | 0 | 0 |  | 50050 | -8414.25 | 41635.75 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at six Jordanian companies | Individual | ASP | JOR | REF | 26 | INV | 42 | A | O | I | CFC | 25.1 | 25.1 |  |  | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 1999-12-01 | 2002-09-01 | 305764 | -5299 | 300465 | 300465 | 100% | 0 | 0 |  | 39749.32 | -688.87 | 39060.45 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in manufacture of commercial refrigeration equipment at Maurice al-Deek Co. | Individual | ASP | JOR | REF | 26 | INV | 43 | A | O | I | CFC | 25.7 | 25.7 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 336233 | -7564 | 328669 | 328669 | 100% | 0 | 0 |  | 43710.29 | -983.32 | 42726.97 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 27 | PRP | 45 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 1999-12-01 | 2001-03-01 | 5000 | -700 | 4300 | 4300 | 100% | 0 | 0 |  | 650 | -91 | 559 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | ASP | JOR | REF | 28 | TRA | 47 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2001-08-01 |  | 2002-10-01 | 2004-03-01 | 70000 | -764 | 69236 | 69236 | 100% | 0 | 0 |  | 9100 | -99.32 | 9000.68 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | ASP | JOR | REF | 28 | TRA | 48 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-07-01 | 2003-06-01 | 38250 | -247 | 38003 | 38003 | 100% | 0 | 0 |  | 4972.5 | -32.11 | 4940.39 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: technical assistance and support to develop regulations for ODS to implement the Environment law of 1999 | RMP | ASP | JOR | REF | 28 | TAS | 49 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-03-01 | 2002-07-01 | 20000 | -3006 | 16994 | 16994 | 100% | 0 | 0 |  | 2600 | -390.78 | 2209.22 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | ASP | JOR | REF | 28 | TAS | 50 | A | O | I | CFC | 19.1 | 19.1 |  |  | 1999-07-01 | 2001-09-01 | 2001-08-01 |  | 2004-06-01 | 2005-09-01 | 311950 | -3140 | 308810 | 308810 | 100% | 0 | 0 |  | 40553.5 | -408.2 | 40145.3 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [5 empty] | 2002-12-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Third Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 52 | A | O | I | CFC | 16.8 | 17.74 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 243764 | -79924 | 163840 | 163840 | 100% | 0 | 0 |  | 31689.32 | -10390.12 | 21299.2 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigertion equipment at Al-Arghawin & Marka commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 29 | INV | 55 | A | O | I | CFC | 27.4 | 27.4 |  |  | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 255203 | -9460 | 245743 | 245743 | 100% | 0 | 0 |  | 33176.39 | -1229.8 | 31946.59 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | ASP | JOR | ARS | 30 | PRP | 56 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-08-01 | 2001-04-01 |  | 2001-01-01 | 2002-05-01 | 20000 | -7433 | 12567 | 12567 | 100% | 0 | 0 |  | 2600 | -966.29 | 1633.71 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 30 | PRP | 57 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-04-01 | 2001-04-01 |  | 2002-12-01 | 2003-08-01 | 20000 | -1788 | 18212 | 18212 | 100% | 0 | 0 |  | 2600 | -232.44 | 2367.56 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (CFC-113) sector | Individual | ASP | JOR | SOL | 30 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2002-12-01 | 2003-06-01 | 25000 | -2491 | 22509 | 22509 | 100% | 0 | 0 |  | 3250 | -323.83 | 2926.17 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Second Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 62 | A | O | I | CFC | 25.8 | 25.8 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2000-08-01 | 2002-09-01 | 278950 | -2862 | 276088 | 276088 | 100% | 0 | 0 |  | 36263.5 | -372.06 | 35891.44 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in production commercial refrigeration equipment at the medium size commercial refrigerator manufacturers (Jordan Catering Supplies, El-Shami, and Nedal Raja Al-Dwaik companies) in Jordan | Individual | ASP | JOR | REF | 31 | INV | 65 | A | O | I | CFC | 34.72 | 34.72 |  |  | 2000-07-01 | 2000-10-01 | 2003-08-01 |  | 2002-12-01 | 2004-09-01 | 469525 | -33950 | 435575 | 435575 | 100% | 0 | 0 |  | 61038.25 | -4413.5 | 56624.75 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at Fourth Group of small size Jordanian Commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 31 | INV | 66 | A | O | I | CFC | 23.1 | 23.07 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 270034 | -19229 | 250805 | 250805 | 100% | 0 | 0 |  | 35104.42 | -2499.77 | 32604.65 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Jordan Tunisian Chemical Company | Individual | ASP | JOR | ARS | 32 | INV | 68 | A | O | I | CFC | 12 | 12 |  |  | 2000-12-01 | 2001-10-01 | 2003-03-01 |  | 2002-12-01 | 2003-10-01 | 52800 | -107 | 52693 | 52693 | 100% | 0 | 0 |  | 6864 | -13.91 | 6850.09 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration (umbrella project) sector | Individual | ASP | JOR | REF | 33 | PRP | 70 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-04-01 |  | 2002-07-01 | 2003-09-01 | 20000 | -508 | 19492 | 19492 | 100% | 0 | 0 |  | 2600 | -66.04 | 2533.96 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in the production of commercial refrigeration equipment at the second medium-size commercial refrigerator manufacturers group (Abu Azmi, Hasouni Refrigeration and Majdi) | Individual | ASP | JOR | REF | 34 | INV | 71 | A | O | I | CFC | 26.4 | 26.4 |  |  | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-07-01 | 2005-09-01 | 342652 | -5964 | 336688 | 336688 | 100% | 0 | 0 |  | 44544.76 | -775.32 | 43769.44 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at 6th group of SMEs (Abu-Khalaf, Al-Taghwa, Farough Refrigeration, Dawudiah Workshop, Makka Refrigeration and Teck-Tack workshop) | Individual | ASP | JOR | REF | 34 | INV | 72 | A | O | I | CFC | 24.4 | 24.4 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 286523 | -6112 | 280411 | 280411 | 100% | 0 | 0 |  | 37247.99 | -794.56 | 36453.43 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacturing commercial refrigeration equipment at 5th group of SMEs (Abdoulah Factory, Emad Addin Al- Sareegy, Ma-nna, Al-Mansour, Al-Ostath, Raed) | Individual | ASP | JOR | REF | 34 | INV | 74 | A | O | I | CFC | 26 | 26 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 244954 | -6160 | 238794 | 238794 | 100% | 0 | 0 |  | 31844.02 | -800.8 | 31043.22 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the King Hussein Workshop, Zarqa | Individual | ASP | JOR | SOL | 34 | INV | 75 | A | O | I | TCA | 6.4 | 6.4 |  |  | 2001-07-01 | 2002-12-01 | 2003-02-01 |  | 2003-12-01 | 2004-10-01 | 191316 | 0 | 191316 | 191316 | 100% | 0 | 0 |  | 24871.08 | 0 | 24871.08 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the Royal Jordanian Air Force | Individual | ASP | JOR | SOL | 37 | INV | 76 | A | O | I | TCA | 45 | 45 |  |  | 2002-07-01 | 2003-11-01 | 2004-08-01 |  | 2005-12-01 |  | 342757 | 0 | 342757 | 300419 | 87.65% | 42338 | 42210 | 42210 | 44558.41 | 0 | 39054.47 | 5503.94 | 5487.3 | Project completed in Dec 2005. | [10 empty] | 2002 | INV
ONG | UNIDO | National ODS phase out plan: commercial manufacturing and servicing and transport refrigeration | One-off Phase Out | ASP | JOR | PHA | 38 | INV | 78 | A | O | I | CFC | 41 | 0 |  |  | 2002-11-01 | 2003-06-01 | 2009-12-01 | 2006-12-01 |  |  | 410000 | 0 | 410000 | 384823 | 93.86% | 25177 | 9984 | 25000 | 53300 | 0 | 50026.99 | 3273.01 | 1297.92 | All activities have been completed. Implementation of monitoring component continues. Project is expected to be completed by Dec 2006. | [10 empty] | 2002 | INV
ONG | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | KAM | FUM | 46 | TAS | 10 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 |  | 2006-07-01 | 2006-07-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 1 | 2700 | 0 | 0 | 2700 | 0 | Project was approved by 46th ExCom in July 2005. More detailed background information was collected through the counterpart for a series of workshops which are being organized in 2006. Project is expected to be completed by July 2006. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | CFC-phase out project at Kenya Cold Storages Ltd. and subsidiary companies: Hall Equatorial, Premier Refrigeration and Engineering, Refrigeration Services | Individual | AFR | KEN | REF | 11 | INV | 06 | A | O | I | CFC | 40.8 | 40.8 |  |  | 1993-11-01 | 1996-12-01 | 1997-03-01 |  | 1998-12-01 | 2001-07-01 | 380875 | 122341 | 503216 | 503216 | 100% | 0 | 0 |  | 49513.75 | 15904.33 | 65418.08 | 0 | 0 | FIN
FIN | UNIDO | Identification and preparation of projects in the solvents and aerosols sectors | Individual | AFR | KEN | SEV | 17 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1995-11-01 |  | 1998-03-02 | 1999-08-01 | 15000 | -960 | 14040 | 14040 | 100% | 0 | 0 |  | 1950 | -124.8 | 1825.2 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFCs at Aesthetics Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 10 | A | O | I | CFC | 107 | 107 |  |  | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 55000 | -8 | 54992 | 54992 | 100% | 0 | 0 |  | 7150 | -1.04 | 7148.96 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mirage Industries Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 11 | A | O | I | CFC | 51 | 51 |  |  | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 47250 | -445 | 46805 | 46805 | 100% | 0 | 0 |  | 6142.5 | -57.85 | 6084.65 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from TCA to aqueous cleaning and cleaning in TCE at Kenyan Railways Central Workshop | Individual | AFR | KEN | SOL | 23 | INV | 14 | A | O | I | TCA | 6 | 6 |  |  | 1997-11-01 | 1998-08-01 | 1998-12-01 |  | 1999-12-01 | 2002-09-01 | 205524 | -1 | 205523 | 205523 | 100% | 0 | 0 |  | 26718.12 | -0.13 | 26717.99 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | AFR | KEN | FUM | 23 | PRP | 15 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13013 | 23013 | 23013 | 100% | 0 | 0 |  | 1300 | 1691.69 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in cut-flowers at Kenya Agricultural Research Institute - KARI | Individual | AFR | KEN | FUM | 24 | DEM | 17 | A | O | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-10-01 | 2000-04-01 |  | 2003-03-01 | 2004-03-01 | 328900 | -3475 | 325425 | 325425 | 100% | 0 | 0 |  | 42757 | -451.75 | 42305.25 | 0 | 0 | FIN
CLO | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | AFR | KEN | FUM | 30 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
ONG | UNIDO | Implementation of the RMP: national recovery and recycling | RMP Update | ASP | KUW | REF | 37 | TAS | 05 | A | O | I | CFC | 64 | 0 |  |  | 2002-07-01 | 2003-07-01 | 2005-08-01 | 2006-12-01 |  |  | 448816 | 0 | 448816 | 273826 | 61.01% | 174990 | 4286 | 174990 | 22441 | 35905 | 35597.38 | 22748.62 | 557.18 | Equipment for the second phase was procured. Project is planned to be completed by Dec 2006 after delivery, installation and commissioning of equipment and purchase of remaining equipment based on required needs and budget availability. | [10 empty] | 2002 | INV
ONG | UNIDO | Preparation of a halon phase-out plan | Individual | ASP | KUW | HAL | 45 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-07-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 1875 | 0 | 0 | 1875 | 0 | PRP project was approved by 45th ExCom in Apr 2005. Survey of halon sector is underway. Upon completion of the survey, National Ozone Unit will provide its results and respective recommendations to UNIDO for preparation of the halon phase-out plan. | [10 empty] | 2005 | NON-INV
CLO | UNIDO | Preparation of a demonstration project for broccoli, cucurbits, tobacco, seed beds, grain fumigation in El Salvador, Honduras and Nicaragua | Individual | LAC | LAC | FUM | 27 | PRP | 31 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  |  | 2001-12-01 | 40000 | -29203 | 10797 | 10797 | 100% | 0 | 0 |  | 5200 | -3796.39 | 1403.61 | 0 | 0 | CLO
FIN | UNIDO | Project formulation for phase out of ODS in aerosol sector (Cosmaline Industries S.A.) | Individual | ASP | LEB | ARS | 16 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -8794 | 6206 | 6206 | 100% | 0 | 0 |  | 1950 | -1143.22 | 806.78 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phase out of ODS in the refrigeration sector (Weather-mate and OPACO Ltd.) | Individual | ASP | LEB | REF | 16 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1997-08-01 | 1995-07-01 |  | 1997-12-01 | 2000-12-01 | 15000 | -1518 | 13482 | 13482 | 100% | 0 | 0 |  | 1950 | -197.34 | 1752.66 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for the phase out of ODS in the foam sector in 2 plants (Ets. Henri Abdallah and Nasri Karam) | Individual | ASP | LEB | FOA | 16 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-07-01 |  | 1997-03-01 | 1998-08-01 | 20000 | -7378 | 12622 | 12622 | 100% | 0 | 0 |  | 2600 | -959.14 | 1640.86 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of CFCs at Cosmaline Industries s.a.al. | Individual | ASP | LEB | ARS | 19 | INV | 05 | A | O | I | CFC | 87.7 | 87.7 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-07-01 | 212500 | 0 | 212500 | 212500 | 100% | 0 | 0 |  | 27625 | 0 | 27625 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Zeeni's Trading Agency | Individual | ASP | LEB | ARS | 19 | INV | 06 | A | O | I | CFC | 212 | 212 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 361900 | -10026 | 351874 | 351874 | 100% | 0 | 0 |  | 47047 | -1303.38 | 45743.62 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Nasri Karam and Sons | Individual | ASP | LEB | FOA | 20 | INV | 09 | A | O | I | CFC | 22 | 22 |  |  | 1996-10-01 | 1997-07-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 100109 | -265 | 99844 | 99844 | 100% | 0 | 0 |  | 13014.17 | -34.45 | 12979.72 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Ets. Henri Abdallah P.F.M. | Individual | ASP | LEB | FOA | 21 | INV | 18 | A | O | I | CFC | 16.6 | 16.6 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 81291 | -711 | 80580 | 80580 | 100% | 0 | 0 |  | 10567.83 | -92.43 | 10475.4 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Lebanese Modern Industrial and Trading Co. | Individual | ASP | LEB | REF | 22 | INV | 19 | A | O | I | CFC | 135 | 135 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1999-12-01 | 2002-10-01 | 1313121 | -67505 | 1245616 | 1245616 | 100% | 0 | 0 |  | 170705.73 | -8775.65 | 161930.08 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141B and CFC-12 to HFC-134a in the manufacture of commercial refrigeration at the first group of Lebanese Commercial Refrigerator Manufacturers | Individual | ASP | LEB | REF | 29 | INV | 33 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2000-07-01 | 2002-09-01 | 258006 | -9168 | 248838 | 248838 | 100% | 0 | 0 |  | 33540.78 | -1191.84 | 32348.94 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the second group of Lebanese commercial refrigeration manufacturers | Individual | ASP | LEB | REF | 31 | INV | 36 | A | O | I | CFC | 15.66 | 15.66 |  |  | 2000-07-01 | 2000-09-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 203191 | -1363 | 201828 | 201828 | 100% | 0 | 0 |  | 26414.83 | -177.19 | 26237.64 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of two umbrella investment projects in the commercial refrigeration sector, covering six SME factories each | Individual | ASP | LEB | REF | 31 | PRP | 38 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1106 | 18894 | 18894 | 100% | 0 | 0 |  | 2600 | -143.78 | 2456.22 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the third group of Lebanese commercial refrigerator manufacturers | Individual | ASP | LEB | REF | 31 | INV | 39 | A | O | I | CFC | 15.8 | 15.8 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 208498 | -8451 | 200047 | 200047 | 100% | 0 | 0 |  | 27104.74 | -1098.63 | 26006.11 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two umbrella projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 33 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-01-01 | 2002-04-01 |  | 2002-07-01 | 2003-06-01 | 15000 | -252 | 14748 | 14748 | 100% | 0 | 0 |  | 1950 | -32.76 | 1917.24 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Project preparation in the fumigants (strawberries) sector | Individual | ASP | LEB | FUM | 33 | PRP | 43 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -950 | 29050 | 29050 | 100% | 0 | 0 |  | 3900 | -123.5 | 3776.5 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 44 | A | O | I | MBR | 6 | 6 |  |  | 2001-07-01 | 2002-04-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | FIN | [10 empty] | 2001 | INV | 44.4 | 44.4 |  |  | Yes | n.a. | n.a.
COM | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 4th group of enterprises | Individual | ASP | LEB | REF | 34 | INV | 45 | A | O | I | CFC | 18.8 | 18.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2004-06-01 | 2005-12-01 | 279672 | 0 | 279672 | 269734 | 96.45% | 9938 | 0 | 1 | 36357.36 | 0 | 35065.42 | 1291.94 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2001 | INV
CLO | UNIDO | Preparation of 2 umbrella investment projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 36 | PRP | 47 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO | [10 empty] | 2002 | INV
COM | UNIDO | Phase-out of methyl bromide (strawberries): release of second tranche | Multi-Year | ASP | LEB | FUM | 38 | INV | 52 | A | O | I | MBR | 10.1 | 10.1 |  |  | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 |  | 421946 | 0 | 421946 | 407299 | 96.53% | 14647 | 14188 | 14000 | 54852.98 | 0 | 52948.87 | 1904.11 | 1844.44 | [11 empty] | 2002 | INV | 34.3 | 34.3 |  |  | Yes | n.a. | n.a.
ONG | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 54 | A | O | I | MBR | 14.2 | 25.3 |  |  | 2003-12-01 | 2005-07-01 | 2004-12-01 | 2007-07-01 |  |  | 450000 | 0 | 450000 | 29459 | 6.546% | 420541 | 24636 | 266618 | 33750 | 0 | 2209.425 | 31540.575 | 1847.7 | All equipment and goods foreseen for 2005 were delivered. Soil treatment plan was executed as planned. Through the assistance of national experts, the project team developed a protocol for application of methyl bromide alternatives for the crop season 2005/2006. An additional phase-out of 15.3 ODP tonnes was achieved. In 2006, the ongoing crop season 2005/2006 will be monitored. Equipment and goods will be procured for the crop season 2006/2007. Technical assistance programme addressed to strawberry producers will be implemented. | [10 empty] | 2003 | INV | 20.1 | 24.3 |  |  | No | n.a. | n.a.
ONG | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 62 | A | O | I | MBR | 9 | 0 |  |  | 2005-11-01 |  | 2006-12-01 | 2007-12-01 |  |  | 42504 | 0 | 42504 | 0 | 0% | 42504 | 0 | 1 | 3187.8 | 0 | 0 | 3187.8 | 0 | Fifth tranche was released by 47th ExCom in Nov 2005. In 2006, the ongoing crop season 2005/2006 will be monitored. Equipment and goods will be procured for the crop season 2006/2007. Technical assistance programme addressed to strawberry producers will be implemented. | [10 empty] | 2005 | INV | 9 | 9 |  |  | Yes | n.a. | n.a.
FIN | UNIDO | Preparation of country programme | Individual | AFR | LIB | SEV | 27 | CPG | 01 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 80000 | -3561 | 76439 | 76439 | 100% | 0 | 0 |  | 10400 | -462.93 | 9937.07 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the Refrigeration sector | Individual | AFR | LIB | REF | 30 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2003-07-01 | 2004-04-01 | 20000 | -581 | 19419 | 19419 | 100% | 0 | 0 |  | 2600 | -75.53 | 2524.47 | 0 | 0 | FIN
COM | UNIDO | Phasing out ODS in the production of refrigerators and freezers at Electrical Household Appliance Manufacturing | Individual | AFR | LIB | REF | 32 | INV | 03 | A | O | I | CFC | 53.4 | 53.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-06-01 |  | 2004-03-01 |  | 558113 | 0 | 558113 | 364970 | 65.39% | 193143 | 192656 | 192656 | 71392.43 | 0 | 47446.1 | 23946.33 | 23892.76
ONG | UNIDO | Creation of the National Ozone Unit | Individual | AFR | LIB | SEV | 32 | INS | 04 | N | T | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-12-01 | 2004-01-01 | 2007-12-01 |  |  | 157000 | 0 | 157000 | 55205 | 35.16% | 101795 | 70150 | 5000 | 20410 | 0 | 7176.65 | 13233.35 | 9119.5 | There was no movement in 2005 since the Ozone Officer does not react to UNIDO's requests for reports (financial and activity reports) under the subcontract and activity reports of Ozone Unit staff having held national expert contracts. A mission was undertaken to Libya in Dec 2005, however with partial success only relating to staff reports.
CLO | UNIDO | Project preparation in the commercial refrigeration sector | Individual | AFR | LIB | REF | 33 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 |  | 2002-04-01 |  |  | 2003-06-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | AFR | LIB | REF | 36 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-06-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 20000 | -753 | 19247 | 19247 | 100% | 0 | 0 |  | 2600 | -97.89 | 2502.11 | 0 | 0 | FIN | [10 empty] | 2002 | INV
COM | UNIDO | National phase-out plan | Individual | AFR | LIB | SEV | 38 | PRP | 21 | A | O | I | CFC | 0 | 0 |  |  | 2002-11-01 | 2003-09-01 | 2003-12-01 |  | 2005-06-01 |  | 40000 | 0 | 40000 | 39532 | 98.83% | 468 | 178 | 170 | 5200 | 0 | 5139.16 | 60.84 | 23.14 | Project completed in Jun 2005. | [10 empty] | 2002 | INV
COM | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | LIB | PHA | 41 | INV | 22 | A | O | I | CFC | 150 | 150.4 |  |  | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-08-01 |  | 1500000 | 0 | 1500000 | 1261337 | 84.09% | 238663 | 238663 | 238663 | 112500 | 0 | 94600.275 | 17899.725 | 17899.725 | Project completed in Aug 2005. | [10 empty] | 2003 | INV | 461 | 459 |  |  | Yes | Yes | Yes
ONG | UNIDO | Preparation of a halon phase-out plan | Individual | AFR | LIB | HAL | 45 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 | 2006-07-01 |  |  | 25000 | 0 | 25000 | 6464 | 25.86% | 18536 | 5656 | 10000 | 1875 | 0 | 484.8 | 1390.2 | 424.2 | Project document was prepared, submitted and approved by 47th ExCom. As per decision of the ExCom, remaining funds will be used for preparation of a plan to ensure sustainability of the project. | [10 empty] | 2005 | NON-INV
COM | UNIDO | Preparation of a phase-out plan in the fumigants sector (methyl bromide) | Individual | AFR | LIB | FUM | 45 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 |  | 15000 | 0 | 15000 | 9654 | 64.36% | 5346 | 4209 | 4209 | 1125 | 0 | 724.05 | 400.95 | 315.675 | Project completed in Dec 2005. Remaining funds will be returned upon financial completion of the project. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | AFR | LIB | PHA | 45 | INV | 25 | A | O | I | CFC | 124 | 124 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  |  | 720000 | 0 | 720000 | 7906 | 1.098% | 712094 | 459937 | 500000 | 54000 | 0 | 592.95 | 53407.05 | 34495.275 | Second tranche was released by 45th ExCom in Apr 2005. As required by 45th ExCom, Libya reported its outstanding 2004 Article 7 data to the Ozone Secretariat. In addition, Government indicated that the legislation would be in place by end 2005. UNIDO, therefore, proceeded with the project as per the annual implementation plan. A total phase-out of 124 ODP tonnes was achieved. In 2006, main foam equipment was installed and commissioned. Delivered recovery and recycling equipment will be installed and commissioned. Remaining recovery and recycling equipment will be ordered based on budget availability. | [10 empty] | 2005 | INV | 300 | 300 |  |  | not available | No | No
ONG | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | AFR | LIB | HAL | 47 | TAS | 26 | A | O | I | HAL | 653.9 | 0 |  |  | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 343500 | 0 | 343500 | 0 | 0% | 343500 | 0 | 80000 | 25762.5 | 0 | 0 | 25762.5 | 0 | Project was approved by 47th ExCom in Nov 2005. In 2006, a business model will be elaborated for a self-sustainable operation of the halon-banking centre. | [10 empty] | 2005 | INV
ONG | UNIDO | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others | Individual | AFR | LIB | FUM | 47 | INV | 27 | A | O | I | MBR | 56 | 0 |  |  | 2005-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 743000 | 0 | 743000 | 0 | 0% | 743000 | 0 | 250000 | 55725 | 0 | 0 | 55725 | 0 | Project was approved by 47th ExCom in Nov 2005. A work plan will be prepared and terms of reference for procurement of equipment will be agreed upon. Subcontract for provision of technical assistance and logistic services will be signed. | [10 empty] | 2005 | INV
ONG | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | AFR | MAG | FUM | 45 | TAS | 09 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 46 | 0.115% | 39954 | 2005 | 39954 | 3600 | 0 | 4.14 | 3595.86 | 180.45 | Project was approved by 45th ExCom in Apr 2005. More detailed background information was collected through the counterpart for the organization of the workshop. A work programme was drafted. The workshop is planned to take place during 3rd quarter of 2006. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | ASP | MAL | FOA | 18 | PRP | 69 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-02-01 |  | 1999-02-01 | 2000-07-01 | 40000 | -98 | 39902 | 39902 | 100% | 0 | 0 |  | 5200 | -12.74 | 5187.26 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Phasing out ODS at Summer Technologies Sdn. Bhd. | Individual | ASP | MAL | FOA | 23 | INV | 100 | A | O | I | CFC | 12.1 | 12.1 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 89407 | 0 | 89407 | 89407 | 100% | 0 | 0 |  | 11622.91 | 0 | 11622.91 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Kean Chong Industries Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 101 | A | O | I | CFC | 16.3 | 16.3 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-11-23 | 107819 | 0 | 107819 | 107819 | 100% | 0 | 0 |  | 14016.47 | 0 | 14016.47 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Visdamax Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 102 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 139959 | 0 | 139959 | 139959 | 100% | 0 | 0 |  | 18194.67 | 0 | 18194.67 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector (rigid polyurethane) for Chon Son, Ngui Soon, Ming Soon, Yon Tuck | Individual | ASP | MAL | FOA | 24 | PRP | 110 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 20000 | -236 | 19764 | 19764 | 100% | 0 | 0 |  | 2600 | -30.68 | 2569.32 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the insulation of GRP fish boxes and flotation buoys at C.C. Chong Co. | Individual | ASP | MAL | FOA | 26 | INV | 112 | A | O | I | CFC | 4.5 | 4.5 |  |  | 1998-11-01 | 1999-03-01 | 2000-06-01 |  | 2000-05-01 | 2001-09-01 | 34583 | -6 | 34577 | 34577 | 100% | 0 | 0 |  | 4495.79 | -0.78 | 4495.01 | 0 | 0 | FIN
FIN | UNIDO | The replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Ming Soon Enterprise Sdn. Bhd. | Individual | ASP | MAL | FOA | 26 | INV | 113 | A | O | I | CFC | 6.2 | 6.23 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-02-01 | 2002-09-01 | 48799 | -64 | 48735 | 48735 | 100% | 0 | 0 |  | 6343.87 | -8.32 | 6335.55 | 0 | 0 | FIN
FIN | UNIDO | Preparation of three investment projects in the foam sector (rigid polyrethane) | Individual | ASP | MAL | FOA | 27 | PRP | 118 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 25000 | -87 | 24913 | 24913 | 100% | 0 | 0 |  | 3250 | -11.31 | 3238.69 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Yong Tuck Refrigerators Trading Co. | Individual | ASP | MAL | FOA | 27 | INV | 120 | A | O | I | CFC | 8 | 8 |  |  | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2000-06-01 | 2001-09-01 | 61735 | -740 | 60995 | 60995 | 100% | 0 | 0 |  | 8025.55 | -96.2 | 7929.35 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFC-11 consumption by conversion to HCFC-141b AT Perniagaan Hower in the manufacture of sandwich panels | Individual | ASP | MAL | FOA | 28 | INV | 124 | A | O | I | CFC | 5.3 | 5.3 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 41499 | -153 | 41346 | 41346 | 100% | 0 | 0 |  | 5394.87 | -19.89 | 5374.98 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology at Automated Plastic System Sdn. Bhd. in the manufacture of insulated fishing boxes | Individual | ASP | MAL | FOA | 28 | INV | 125 | A | O | I | CFC | 5.2 | 5.2 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-01-01 | 2001-12-01 | 40716 | -1 | 40715 | 40715 | 100% | 0 | 0 |  | 5293.08 | -0.13 | 5292.95 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFC-11 consumption at Chong Brother Group of Companies | Individual | ASP | MAL | FOA | 28 | INV | 127 | A | O | I | CFC | 27.6 | 27.6 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 216108 | -160 | 215948 | 215948 | 100% | 0 | 0 |  | 28094.04 | -20.8 | 28073.24 | 0 | 0 | FIN
FIN | UNIDO | Preparation of three investment projects in the rigid foam sector | Individual | ASP | MAL | FOA | 31 | PRP | 139 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2001-07-01 |  | 2002-01-01 | 2003-05-01 | 20000 | -771 | 19229 | 19229 | 100% | 0 | 0 |  | 2600 | -100.23 | 2499.77 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigerating equipment at Tung Kiong Factories Sdn. Bhd. | Individual | ASP | MAL | REF | 32 | INV | 143 | A | O | I | CFC | 18.9 | 18.9 |  |  | 2000-12-01 | 2001-10-01 | 2003-07-01 |  | 2003-03-01 | 2004-05-01 | 202075 | -823 | 201252 | 201252 | 100% | 0 | 0 |  | 26269.75 | -106.99 | 26162.76 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Composites Truck Body Sdn., Bhd. | Individual | ASP | MAL | FOA | 34 | INV | 143 | A | O | I | CFC | 8.1 | 8.1 |  |  | 2001-07-01 | 2002-12-01 | 2004-02-01 |  | 2003-12-01 | 2003-12-01 | 63280 | -229 | 63051 | 63051 | 100% | 0 | 0 |  | 8226.4 | -29.77 | 8196.63 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of a Country Programme | Individual | EUR | MDN | SEV | 15 | CPG | 01 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-08-01 | 1995-12-01 |  | 1996-12-01 | 1998-08-01 | 80000 | -7894 | 72106 | 72106 | 100% | 0 | 0 |  | 10400 | -1026.22 | 9373.78 | 0 | 0 | FIN
FIN | UNIDO | Preparation of projects in the refrigeration, aerosol and foam sector | Individual | EUR | MDN | SEV | 18 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-01-01 | 1996-03-01 |  | 2000-12-01 | 2002-05-01 | 30000 | -3717 | 26283 | 26283 | 100% | 0 | 0 |  | 3900 | -483.21 | 3416.79 | 0 | 0 | FIN |  |  | 1997-07-01 | 1999-02-01
FIN | UNIDO | Phasing out of CFCs at the refrigerator plant of Frinko | Individual | EUR | MDN | REF | 20 | INV | 03 | A | O | I | CFC | 104 | 104 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1998-12-01 | 2001-12-01 | 1081724 | -2270 | 1079454 | 1079454 | 100% | 0 | 0 |  | 140624.12 | -295.1 | 140329.02 | 0 | 0 | FIN
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | MDN | SEV | 20 | INS | 04 | N | T | I |  | 0 | 0 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-08-01 | 2001-07-01 | 152900 | -192 | 152708 | 152708 | 100% | 0 | 0 |  | 19877 | -24.96 | 19852.04 | 0 | 0 | FIN |  |  | 1999-10-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 05 | A | O | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2002-09-01 | 520125 | -5712 | 514413 | 514413 | 100% | 0 | 0 |  | 67616.25 | -742.56 | 66873.69 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from manufacturing of rigid PU sandwich panels at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 06 | A | O | I | CFC | 67.6 | 67.6 |  |  | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1997-12-01 | 2002-05-01 | 284236 | -7101 | 277135 | 277135 | 100% | 0 | 0 |  | 36950.68 | -923.13 | 36027.55 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | EUR | MDN | REF | 24 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 30000 | -4502 | 25498 | 25498 | 100% | 0 | 0 |  | 3900 | -585.26 | 3314.74 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in methyl bromide (tobacco, pepper, tomatoes) | Individual | EUR | MDN | FUM | 25 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 20000 | -1590 | 18410 | 18410 | 100% | 0 | 0 |  | 2600 | -206.7 | 2393.3 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - three alternatives to the use of methyl bromide: non-soil cultivation, biofumigation and low dose chemicals in tobacco and horticultural production | Individual | EUR | MDN | FUM | 26 | DEM | 09 | A | O | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-04-01 | 2003-05-01 | 259600 | -969 | 258631 | 258631 | 100% | 0 | 0 |  | 33748 | -125.97 | 33622.03 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | MDN | REF | 28 | TAS | 10 | A | O | I | CFC | 13.5 | 13.5 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2002-02-01 | 2003-12-01 | 220044 | -43941 | 176103 | 176103 | 100% | 0 | 0 |  | 28605.72 | -5712.33 | 22893.39 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | MDN | REF | 28 | TRA | 11 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-06-01 |  | 2002-03-01 | 2003-05-01 | 70000 | -6247 | 63753 | 63753 | 100% | 0 | 0 |  | 9100 | -812.11 | 8287.89 | 0 | 0 | FIN
FIN | UNIDO | Institutional strengthening for Montreal Protocol related activities, Phase II | Individual | EUR | MDN | SEV | 30 | INS | 12 | N | T | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 101950 | -1 | 101949 | 101949 | 100% | 0 | 0 |  | 13253.5 | -0.13 | 13253.37 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | EUR | MDN | ARS | 30 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2001-07-01 | 15000 | -2445 | 12555 | 12555 | 100% | 0 | 0 |  | 1950 | -317.85 | 1632.15 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | MDN | FUM | 30 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -530 | 19470 | 19470 | 100% | 0 | 0 |  | 2600 | -68.9 | 2531.1 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers | RMP | EUR | MDN | REF | 28 | TRA | 15 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-03-01 |  | 2002-03-01 | 2003-05-01 | 37180 | -7021 | 30159 | 30159 | 100% | 0 | 0 |  | 4833.4 | -912.73 | 3920.67 | 0 | 0 | FIN
COM | UNIDO | Phase-out of methyl bromide in tobacco seedling and horticulture production sector | Individual | EUR | MDN | FUM | 32 | INV | 16 | A | O | I | MBR | 27.2 | 27.2 |  |  | 2000-12-01 | 2001-10-01 | 2006-01-01 |  | 2004-12-01 |  | 1075207 | 0 | 1075207 | 1059179 | 98.51% | 16028 | 15854 | 15854 | 128272.77 | 0 | 126509.69 | 1763.08 | 1743.94
ONG | UNIDO | Phase-out of CFC 11/12 in the manufacture of aerosols by conversion to HFC and hydrocarbon propellants at Alkaloid A.D. | Individual | EUR | MDN | ARS | 32 | INV | 17 | A | O | I | CFC | 25 | 0 |  |  | 2000-12-01 | 2001-12-01 | 2003-03-01 |  |  |  | 110000 | 0 | 110000 | 99424 | 90.39% | 10576 | 0 | 8000 | 14300 | 0 | 12925.12 | 1374.88 | 0 | Project was cancelled by mutual agreement at 45th ExCom in Apr 2005.
FIN | UNIDO | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MDN | SEV | 35 | INS | 18 | N | T | I |  | 0 | 0 |  |  | 2001-12-01 | 2002-08-01 | 2004-01-01 |  | 2004-07-01 | 2005-09-01 | 101950 | -2 | 101948 | 101948 | 100% | 0 | 0 |  | 13253.5 | -0.26 | 13253.24 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | NON-INV
FIN | UNIDO | Technical assistance in preparation of the national halon management plan | Individual | EUR | MDN | HAL | 37 | TAS | 19 | A | O | I | HAL | 0 | 0 |  |  | 2002-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-05-01 | 2004-02-01 | 25000 | -48 | 24952 | 24952 | 100% | 0 | 0 |  | 3250 | -6.24 | 3243.76 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project: phase IV | Individual | EUR | MDN | SEV | 42 | INS | 20 | N | T | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2006-04-01 | 2006-12-01 |  |  | 132347 | 0 | 132347 | 80917 | 61.14% | 51430 | 51 | 50511 | 9926.025 | 0 | 6068.775 | 3857.25 | 3.825 | The Ozone Unit carried out a number of specific workshops in the MAC and refrigeration sector, phase-out of CFCs in household refrigerators for service technicians and organized a sub-regional Balkan Workshop on Implementation of RMP (in cooperation with UNEP OzonAction Programme). In the framework of country-to-country assistance, Ozone Unit provided training to the new Ozone Officer for BIH. On the occasion of the International Ozone Day, a Parliamentarian Club event was organized and a new brochure "Global Protection of the Earth" was introduced. A thematic lesson was organized in a secondary high school in Skopje on the subject. Further public awareness activities took place through newspapers, TV and radio. The national experts assist the Ozone Unit Manager in technical aspects of the MP programme and related projects as well as in the preparation of an extensive public awareness programme. Phase V was approved by 48th ExCom in Apr 2006. | [10 empty] | 2004 | NON-INV
ONG | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | MDN | PHA | 45 | INV | 21 | A | O | I | CFC | 10 | 0 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 | 2006-06-01 |  |  | 154210 | 0 | 154210 | 6500 | 4.215% | 147710 | 129765 | 129000 | 11565.75 | 0 | 487.5 | 11078.25 | 9732.375 | First tranche was released by 45th ExCom in Apr 2005. Terms of reference for training courses in refrigerant management and other related services were prepared and competitive bidding was initiated. Training courses are being organized by contractor. Technical specification for refrigerant management and recovery and recycling equipment was prepared, equipment was procured and delivered in 2006. In addition, terms of reference for ODS consumption verification audit have been submitted to NOU for competitive bidding. Second funding tranche is due for submission to 49th ExCom in July 2006. | [10 empty] | 2005 | INV | 25 | 11.83 |  |  | Yes | No | No
FIN | UNIDO | Preparation of investment projects | Individual | LAC | MEX | SEV | 18 | PRP | 44 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-08-01 |  | 1997-09-01 | 2000-07-01 | 50000 | -555 | 49445 | 49445 | 100% | 0 | 0 |  | 6500 | -72.15 | 6427.85 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | LAC | MEX | FUM | 22 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-07-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1590 | 18410 | 18410 | 100% | 0 | 0 |  | 2600 | -206.7 | 2393.3 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Criotec S.A. | Individual | LAC | MEX | REF | 23 | INV | 67 | A | O | R | CFC | 16 | 16 |  |  | 1997-11-01 | 1998-09-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 240794 | 0 | 240794 | 240794 | 100% | 0 | 0 |  | 31303.22 | 0 | 31303.22 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Torrey S.A. | Individual | LAC | MEX | REF | 23 | INV | 68 | A | O | I | CFC | 15.1 | 15.1 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 228165 | -4785 | 223380 | 223380 | 100% | 0 | 0 |  | 29661.45 | -622.05 | 29039.4 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Nieto S.A. | Individual | LAC | MEX | REF | 23 | INV | 70 | A | O | R | CFC | 24.6 | 24.6 |  |  | 1997-11-01 | 1998-06-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 353976 | 0 | 353976 | 353976 | 100% | 0 | 0 |  | 46016.88 | 0 | 46016.88 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Vendo S.A. | Individual | LAC | MEX | REF | 23 | INV | 74 | A | O | R | CFC | 16.5 | 16.5 |  |  | 1997-11-01 | 1999-03-01 | 1998-10-01 |  | 1998-12-01 | 1999-07-01 | 248524 | 0 | 248524 | 248524 | 100% | 0 | 0 |  | 32308.12 | 0 | 32308.12 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for phasing out ODS at several small enterprises in the commercial refrigeration | Individual | LAC | MEX | REF | 23 | PRP | 75 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-06-01 |  | 1999-11-01 | 2001-03-01 | 20000 | -81 | 19919 | 19919 | 100% | 0 | 0 |  | 2600 | -10.53 | 2589.47 | 0 | 0 | FIN
COM | UNIDO | Demonstration project - Alternatives to the use of methyl bromide in the cultivation of tomatoes, strawberries, tobacco, melons and cut flowers | Individual | LAC | MEX | FUM | 25 | DEM | 81 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-08-01 |  | 2004-12-01 |  | 790350 | 0 | 790350 | 773648 | 97.89% | 16702 | 2815 | 2815 | 102745.5 | 0 | 100574.24 | 2171.26 | 365.95
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Plasticos Tecnicos Mexicanos (PTM) in the manufacture of commercial refrigeration equipment | Individual | LAC | MEX | REF | 25 | INV | 85 | A | O | I | CFC | 50.6 | 50.6 |  |  | 1998-07-01 | 1998-11-01 | 2000-01-01 |  | 1999-12-01 | 2002-09-01 | 398439 | -7 | 398432 | 398432 | 100% | 0 | 0 |  | 51797.07 | -0.91 | 51796.16 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | MEX | REF | 27 | PRP | 88 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 15000 | -2179 | 12821 | 12821 | 100% | 0 | 0 |  | 1950 | -283.27 | 1666.73 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with cyclopentane and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators of Metaplus S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 90 | A | O | I | CFC | 20.1 | 20.1 |  |  | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-12-01 | 2004-04-01 | 303094 | -1883 | 301211 | 301211 | 100% | 0 | 0 |  | 39402.22 | -244.79 | 39157.43 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators at Refrigeracion Duran S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 91 | A | O | I | CFC | 15.1 | 15.1 |  |  | 2000-03-01 | 2000-09-01 | 2001-10-01 |  | 2002-07-01 | 2003-10-01 | 112985 | -21 | 112964 | 112964 | 100% | 0 | 0 |  | 14688.05 | -2.73 | 14685.32 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the rigid foam sector | Individual | LAC | MEX | FOA | 30 | PRP | 92 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-04-01 |  | 2001-10-01 | 2003-03-01 | 30000 | -884 | 29116 | 29116 | 100% | 0 | 0 |  | 3900 | -114.92 | 3785.08 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | MEX | REF | 31 | TAS | 99 | A | O | I | CFC | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2002-05-01 |  | 2004-06-01 | 2004-12-01 | 100000 | -452 | 99548 | 99548 | 100% | 0 | 0 |  | 13000 | -58.76 | 12941.24 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [7 empty] | 2003-12-01
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | LAC | MEX | REF | 33 | PRP | 100 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2004-04-01 | 2004-12-01 | 50000 | -20 | 49980 | 49980 | 100% | 0 | 0 |  | 6500 | -2.6 | 6497.4 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of a sectoral phase-out plan in refrigeration | Individual | LAC | MEX | REF | 36 | PRP | 107 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-04-01 | 2005-05-01 | 30000 | -9 | 29991 | 29991 | 100% | 0 | 0 |  | 3900 | -1.17 | 3898.83 | 0 | 0 | Financial completion in May 2005. | [10 empty] | 2002 | INV
CLO | UNIDO | Preparation of a sectoral phase-out plan in the solvents sector | Individual | LAC | MEX | SOL | 36 | PRP | 108 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-07-01 |  |  | 2003-05-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | CLO | [10 empty] | 2002 | INV
FIN | UNIDO | Renewal of the institutional strengthening project for the phase out of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 37 | INS | 109 | N | T | I |  | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2002-08-01 |  | 2003-12-01 | 2005-03-01 | 0 | 49961 | 49961 | 49961 | 100% | 0 | 0 |  | 0 | 6494.93 | 6494.93 | 0 | 0 | Financial completion in March 2005 Refund was reported to 45th ExCom, Apr 2005. FIN. | [11 empty] | NON-INV
COM | UNIDO | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | MEX | SEV | 37 | INS | 110 | N | T | I | CFC | 20.4 | 20.4 |  |  | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2005-03-01 |  | 247000 | 0 | 247000 | 238556 | 96.58% | 8444 | 7904 | 7904 | 32110 | 0 | 31012.28 | 1097.72 | 1027.52 | Project completed in Mar 2005. | [10 empty] | 2002 | NON-INV
FIN | UNIDO | Closure of CFC production facilities of the company Quimobasicos | Individual | LAC | MEX | PRO | 38 | PRP | 112 | A | O | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-06-01 | 2004-04-01 | 38000 | -346 | 37654 | 37654 | 100% | 0 | 0 |  | 4940 | -44.98 | 4895.02 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector (methyl bromide) | Individual | LAC | MEX | FUM | 39 | PRP | 113 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-01-01 | 2005-05-01 | 50000 | -41 | 49959 | 49959 | 100% | 0 | 0 |  | 3750 | -3.075 | 3746.925 | 0 | 0 | Project completed in Jan 2005. Financial completion in May 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2003
CLO | UNIDO | Preparation of investment projects in the solvent sector (TCA) | Individual | LAC | MEX | SOL | 39 | PRP | 114 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  |  | 2004-06-01 | 30000 | -18982 | 11018 | 11018 | 100% | 0 | 0 |  | 2250 | -1423.65 | 826.35 | 0 | 0 | CLO | [10 empty] | 2003
COM | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (first tranche) | Multi-Year | LAC | MEX | PRO | 40 | INV | 115 | A | O | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-11-01 | 2004-03-01 |  | 2005-06-01 |  | 5300000 | 0 | 5300000 | 5283260 | 99.68% | 16740 | 16732 | 16740 | 397500 | 0 | 396244.5 | 1255.5 | 1254.9 | Project completed in Jun 2005. | [10 empty] | 2003 |  |  |  | 12355 | 8694 | Yes | Yes | Yes
COM | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (second tranche) | Multi-Year | LAC | MEX | PRO | 42 | INV | 119 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-05-01 | 2005-04-01 |  | 2005-06-01 |  | 10700000 | 0 | 10700000 | 10675213 | 99.77% | 24787 | 21722 | 24787 | 802500 | 0 | 800640.975 | 1859.025 | 1629.15 | Project completed in Jun 2005. | [10 empty] | 2004 | INV |  |  | 12355 | 8044 | Yes | Yes | Yes
ONG | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | MEX | PHA | 42 | INV | 120 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 | 2006-12-01 |  |  | 3517000 | 0 | 3517000 | 825640 | 23.48% | 2691360 | 383562 | 800000 | 263775 | 0 | 61923 | 201852 | 28767.15 | Article 7 consumption target was met and audited in Sep 2005. Equipment for customs training was purchased. Manuals were completed in Sep 2005. Customs training and first training of technicians took place in Sep/Oct 2005. Large-scale training of technicians is under preparation and will be partially completed in 2006. During the first quarter of 2006, recovery and recycling equipment was purchased and delivered for technicians training. In addition, equipment for technicians was purchased and will be delivered in three tranches during 2006/2007. | [10 empty] | 2003 | INV | 4403 | 3208.44 |  |  | Yes | Yes | Yes
ONG | UNIDO | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 121 | A | O | I | MBR | 36.9 | 106 |  |  | 2004-04-01 | 2004-11-01 | 2006-10-01 | 2006-12-01 |  |  | 207035 | 0 | 207035 | 68266 | 32.97% | 138769 | 29955 | 50000 | 18633.15 | 0 | 6143.94 | 12489.21 | 2695.95 | The University of Chapingo is the national institution assisting UNIDO and the Govt. of Mexico in the provision of direct assistance to farmers on alternatives to the use of methyl bromide. Two workshops on flowers and tomatos were organized. The 2005 consumption of methyl bromide was 891 ODP tonnes. | [10 empty] | 2003 | INV
ONG | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | MEX | PHA | 45 | INV | 123 | A | O | I | CFC | 100 | 100 |  |  | 2005-04-01 |  | 2007-04-01 | 2007-12-01 |  |  | 4478000 | 0 | 4478000 | 0 | 0% | 4478000 | 0 | 500000 | 335850 | 0 | 0 | 335850 | 0 | Second tranche was released by 45th ExCom in Apr 2005. As required by 45th ExCom, revised work programme and audit report were submitted to the Secretariat in Sep 2005 for its consideration. Additional information was requested which was provided beginning of Nov 2005. Funds were released by the Secretariat beginning of 2006. A total phase-out of 100 ODP tonnes was achieved. | [10 empty] | 2005 | INV | 2205 | 2005.78 |  |  | Yes | No | No
ONG | UNIDO | Extension of institutional strengthening project: phase VII | Individual | LAC | MEX | SEV | 45 | INS | 125 | N | T | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2007-04-01 | 2007-04-01 |  |  | 247000 | 0 | 247000 | 65732 | 26.61% | 181268 | 37853 | 90000 | 18525 | 0 | 4929.9 | 13595.1 | 2838.975 | Project extension was approved by 45th ExCom in Apr 2005. The project operates under MOD modality and national expert contracts. The Ozone Unit in its day-to-day work put particular focus on two sectors, i.e. methyl bromide and halons (National Halon Bank). In the framework of a public awareness programme, the Ozone Unit produced 3 documentary videos on national and international experience in the use of methyl bromide alternatives. Economic measures were discussed with a view to reduce consumption of ODSs. In this connection, it was proposed to introduce an environmental tax for the consumption of methyl bromide and other ODSs. Steps were taken to advance the ratification of the Montreal Amendment (expected in Apr 2006) and the Beijing Amendment (planned for Sep 2006). | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: third tranche | Multi-Year | LAC | MEX | PRO | 45 | INV | 126 | A | O | I | CFC | 0 | 0 | 5616 | 5616 | 2005-04-01 | 2005-06-01 | 2006-12-01 | 2006-12-01 |  |  | 4000000 | 0 | 4000000 | 3865293 | 96.63% | 134707 | 24322 | 20000 | 300000 | 0 | 289896.975 | 10103.025 | 1824.15 | Third tranche was released by 45th ExCom in Apr 2005. CFC production was closed on 25 Aug 2005 and closure was subsequently audited. Full phase-out took place. CFC consumption monitoring system is ready and operational. In 2006, closure of CFC production will be continuously monitored (annually). | [10 empty] | 2005 | INV |  |  | 6739 | 5201 | Yes | Yes | Yes
ONG | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: fourth tranche | Multi-Year | LAC | MEX | PRO | 47 | INV | 128 | A | O | I | CFC | 0 | 0 | 6739 | 6739 | 2005-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 11850000 | 0 | 11850000 | 0 | 0% | 11850000 | 4000000 | 10000000 | 888750 | 0 | 0 | 888750 | 300000 | Fourth tranche was released by 47th ExCom in Nov 2005. Payment of compensation was made to Cydsa in 2006 and closure of CFC production will be continuously monitored (annually). | [10 empty] | 2005 | INV
FIN | UNIDO | Preparation of an awareness workshop in the methyl bromide sector | Individual | AFR | MLI | FUM | 36 | TRA | 12 | A | O | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-03 |  | 2003-07-01 | 2004-04-01 | 30000 | -643 | 29357 | 29357 | 100% | 0 | 0 |  | 3900 | -83.59 | 3816.41 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
ONG | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | EUR | MOL | FUM | 45 | TAS | 13 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 20000 | 2700 | 0 | 0 | 2700 | 0 | Project was approved by 45th ExCom in Apr 2005. Activity to organize awareness campaign will start in 2006. A workshop is planned to take place in June 2006. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Project formulation of investment projects in domestic refrigeration and methyl bromide sectors | Individual | AFR | MOR | SEV | 21 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-06-01 |  | 1999-09-01 | 2000-12-01 | 22150 | -1535 | 20615 | 20615 | 100% | 0 | 0 |  | 2879.5 | -199.55 | 2679.95 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Demonstration project - four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization and low-dose chemicals in combination with an integrated pesticide management system | Individual | AFR | MOR | FUM | 22 | DEM | 11 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 2000-12-01 | 2002-08-01 | 487300 | -7999 | 479301 | 479301 | 100% | 0 | 0 |  | 63349 | -1039.87 | 62309.13 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector for Allom du Nord and others | Individual | AFR | MOR | REF | 24 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-09-01 | 2001-03-01 | 15000 | -4107 | 10893 | 10893 | 100% | 0 | 0 |  | 1950 | -533.91 | 1416.09 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Alom du Nord | Individual | AFR | MOR | REF | 25 | INV | 24 | A | O | I | CFC | 7.7 | 7.7 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-04-01 | 2002-09-01 | 99402 | -12925 | 86477 | 86477 | 100% | 0 | 0 |  | 12922.26 | -1680.25 | 11242.01 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Batinox | Individual | AFR | MOR | REF | 25 | INV | 25 | A | O | I | CFC | 4.5 | 4.5 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-05-01 | 2002-09-01 | 32920 | -393 | 32527 | 32527 | 100% | 0 | 0 |  | 4279.6 | -51.09 | 4228.51 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Smifam | Individual | AFR | MOR | REF | 26 | INV | 27 | A | O | I | CFC | 4.9 | 4.9 |  |  | 1998-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-04-01 | 2002-09-01 | 62447 | -2362 | 60085 | 60085 | 100% | 0 | 0 |  | 8118.11 | -307.06 | 7811.05 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (bananas) | Individual | AFR | MOR | FUM | 27 | PRP | 28 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -505 | 14495 | 14495 | 100% | 0 | 0 |  | 1950 | -65.65 | 1884.35 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (flowers) | Individual | AFR | MOR | FUM | 27 | PRP | 29 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -172 | 14828 | 14828 | 100% | 0 | 0 |  | 1950 | -22.36 | 1927.64 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | MOR | REF | 27 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-09-01 | 1999-12-01 |  | 2001-04-01 | 2001-10-01 | 7000 | -1526 | 5474 | 5474 | 100% | 0 | 0 |  | 910 | -198.38 | 711.62 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | MOR | ARS | 27 | PRP | 31 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -7958 | 12042 | 12042 | 100% | 0 | 0 |  | 2600 | -1034.54 | 1565.46 | 0 | 0 | FIN
FIN | UNIDO | Conversion of HCFC-141b technology (rigid foam) and HFC-134a (refrigeration) in the manufacture of domestic refrigerators and freezers at Manar | Individual | AFR | MOR | REF | 29 | INV | 33 | A | O | R | CFC | 38.6 | 38.6 |  |  | 1999-11-01 | 2000-04-01 | 2000-07-01 |  | 1999-12-01 | 2000-11-01 | 434183 | 0 | 434183 | 434183 | 100% | 0 | 0 |  | 26050.98 | 0 | 26050.98 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Siafmo | Individual | AFR | MOR | REF | 29 | INV | 34 | A | O | I | CFC | 8.7 | 8.7 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 126240 | -3445 | 122795 | 122795 | 100% | 0 | 0 |  | 16411.2 | -447.85 | 15963.35 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Mafidec | Individual | AFR | MOR | REF | 29 | INV | 35 | A | O | I | CFC | 5.6 | 5.6 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 117360 | -8053 | 109307 | 109307 | 100% | 0 | 0 |  | 15256.8 | -1046.89 | 14209.91 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Sonyafroid | Individual | AFR | MOR | REF | 29 | INV | 36 | A | O | I | CFC | 13.1 | 13.1 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 275895 | -3000 | 272895 | 272895 | 100% | 0 | 0 |  | 35866.35 | -390 | 35476.35 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic commercial refrigeration equiment at Comafro | Individual | AFR | MOR | REF | 29 | INV | 38 | A | O | I | CFC | 6.5 | 6.5 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 134750 | -1354 | 133396 | 133396 | 100% | 0 | 0 |  | 17517.5 | -176.02 | 17341.48 | 0 | 0 | FIN
FIN | UNIDO | Preparation of phase-out project in the methyl bromide sector | Individual | AFR | MOR | FUM | 30 | PRP | 39 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -307 | 29693 | 29693 | 100% | 0 | 0 |  | 3900 | -39.91 | 3860.09 | 0 | 0 | FIN
ONG | UNIDO | Phase out of methyl bromide for soil fumigation in strawberry production | Individual | AFR | MOR | FUM | 32 | INV | 41 | A | O | I | MBR | 155 | 122.3 |  |  | 2000-12-01 | 2001-01-01 | 2006-01-01 | 2007-06-01 |  |  | 2189729 | 0 | 2189729 | 1198427 | 54.73% | 991302 | 66650 | 150000 | 250870.19 | 0 | 141826.97 | 109043.22 | 7331.5 | Application of alternative chemicals and direct assistance and training to farmers continued. Project is expected to be completed by Jun 2007.
COM | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (first tranche) | Multi-Year | AFR | MOR | FUM | 34 | INV | 44 | A | O | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-10-01 | 2002-12-01 |  | 2005-09-01 |  | 400000 | 0 | 400000 | 121451 | 30.36% | 278549 | 248985 | 278549 | 52000 | 0 | 15788.63 | 36211.37 | 32368.05 | Project completed in Sep 2005. | [10 empty] | 2001 | INV | 355.8 | 355.8 |  |  | Yes | n.a. | n.a.
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Climatisation et Froid Loudaya (CFL) | Individual | AFR | MOR | REF | 35 | INV | 45 | A | O | I | CFC | 15 | 15 |  |  | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 177312 | -1127 | 176185 | 176185 | 100% | 0 | 0 |  | 23050.56 | -146.51 | 22904.05 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at First Clim Co. | Individual | AFR | MOR | REF | 35 | INV | 46 | A | O | I | CFC | 9 | 9 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 135258 | -1193 | 134065 | 134065 | 100% | 0 | 0 |  | 17583.54 | -155.09 | 17428.45 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Etablissement Lahdar | Individual | AFR | MOR | REF | 35 | INV | 47 | A | O | I | CFC | 7.4 | 7.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 101451 | -1522 | 99929 | 99929 | 100% | 0 | 0 |  | 13188.63 | -197.86 | 12990.77 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Country programme update | Individual | AFR | MOR | SEV | 38 | CPG | 48 | A | O | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-12-01 | 2005-05-01 | 40000 | -1808 | 38192 | 38192 | 100% | 0 | 0 |  | 5200 | -235.04 | 4964.96 | 0 | 0 | May 2005: Financial completion in May 2005. | [10 empty] | 2002 | NON-INV
ONG | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the terminal umbrella group of commercial refrigeration manufactures. | Individual | AFR | MOR | REF | 43 | INV | 50 | A | O | I | CFC | 18.4 | 15 |  |  | 2004-07-01 | 2004-11-01 | 2006-07-01 | 2006-07-01 |  |  | 359864 | 0 | 359864 | 318921 | 88.62% | 40943 | 8910 | 40000 | 26989.8 | 0 | 23919.075 | 3070.725 | 668.25 | Equipment was delivered and installed. Technicians were trained and prototypes were designed. A partial phase-out of 15 ODP tonnes was achieved. Trial productions of remaining companies will start in 2006. Project is planned to be completed by July 2006. | [10 empty] | 2004 | INV
ONG | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (balance of the first tranche) | Multi-Year | AFR | MOR | FUM | 44 | INV | 52 | A | O | I | MBR | 34.1 | 34.1 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 | 2006-10-01 |  |  | 607513 | 0 | 607513 | 238130 | 39.2% | 369383 | 368121 | 1 | 45563.475 | 0 | 17859.75 | 27703.725 | 27609.075 | Project national staff were recruited. Contract with Farmers' Association was finalized. First seminar on alternatives to methyl bromide was organized. Due to the complexity of equipment to be provided (greenhouses and nursery equipment), purchase order was placed only in Sep 2005. In 2006, first set of equipment for grafted seedling production was delivered. Equipment installation is expected to be completed by Aug 2006. Terms of reference for procurement of second set of equipment are under preparation. | [10 empty] | 2004 | INV | 355.8 | 355.8 |  |  | Yes | n.a. | n.a.
ONG | UNIDO | Training and awareness workshop in the solvent and process agents (CTC & TCA ) sectors | Individual | AFR | MOR | SOL | 45 | TAS | 53 | A | O | I | CTC | 0.1 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 | 2006-08-01 |  |  | 40000 | 0 | 40000 | 6173 | 15.43% | 33827 | 3015 | 28000 | 3600 | 0 | 555.57 | 3044.43 | 271.35 | Project was approved by 45th ExCom in Apr 2005. National expert was recruited to collect information from main users of CTC/TCA which will be used to tailor a training course. Training will take place during second quarter of 2006. | [10 empty] | 2005 | INV
ONG | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (third tranche) | Multi-Year | AFR | MOR | FUM | 47 | INV | 54 | A | O | I | MBR | 39 | 39 |  |  | 2005-11-01 |  | 2006-12-01 | 2007-07-01 |  |  | 1670995 | 0 | 1670995 | 0 | 0% | 1670995 | 0 | 1218087 | 125324.625 | 0 | 0 | 125324.625 | 0 | Work plan for 2005 was approved and a total phase-out of 39 ODP tonnes was achieved. In 2006, first set of equipment for grafted seedling production was delivered. Equipment installation is expected to be completed by Aug 2006. Terms of reference for procurement of second set of equipment are under preparation. Training for grafted seedling production will be implemented and production will start. Chemical alternatives will be applied for the crop season 2006/2007. | [10 empty] | 2005 | INV | 316.8 | 316.8 |  |  | Yes | n.a. | n.a.
FIN | UNIDO | Preparation of projects in commercial refrigeration | Individual | AFR | MOZ | REF | 15 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-08-01 | 1998-08-01 | 15000 | -1718 | 13282 | 13282 | 100% | 0 | 0 |  | 1950 | -223.34 | 1726.66 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFCs at INDATEC/Industria de aplicacoes technico-domesticas Ltd. | Individual | AFR | MOZ | REF | 18 | INV | 04 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1997-03-01 |  |  | 2002-04-01 | 581515 | -247401 | 334114 | 334114 | 100% | 0 | 0 |  | 75596.95 | -32162.13 | 43434.82 | 0 | 0 | CLO |  |  | 1997-12-01 | 1999-11-01
ONG | UNIDO | Implementation of the RMP: establishing conversion practice of domestic refrigerators | Individual | ASP | MYA | REF | 45 | TAS | 07 | A | O | I | CFC | 2.1 | 0 |  |  | 2005-04-01 | 2005-10-01 | 2006-10-01 | 2007-07-01 |  |  | 80000 | 0 | 80000 | 4094 | 5.117% | 75906 | 0 | 1 | 7200 | 0 | 368.46 | 6831.54 | 0 | Project was approved by 45th ExCom in Apr 2005. Mission to Myanmar was undertaken in Sep 2005 to start up project implementation. Implementation modalities were agreed upon and a detailed technical proposal has already been submitted to National Ozone Unit. Purchase of recovery and recycling equipment is planned for 2006. | [10 empty] | 2005 | INV
FIN | UNIDO | Project formulation of investment projects in the refrigeration sector | Individual | LAC | NIC | REF | 21 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-08-01 |  | 1998-05-01 | 2001-12-01 | 50000 | -8415 | 41585 | 41585 | 100% | 0 | 0 |  | 6500 | -1093.95 | 5406.05 | 0 | 0 | FIN
CLO | UNIDO | Preparation of refrigerant management plan | Individual | LAC | NIC | REF | 24 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 |  | 1999-04-01 |  |  | 2001-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Fogel S.A. in the manufacture of commercial refrigeration equipment | Individual | LAC | NIC | REF | 25 | INV | 05 | A | O | R | CFC | 9.6 | 9.6 |  |  | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 1999-12-01 | 2001-03-01 | 130027 | -168 | 129859 | 129859 | 100% | 0 | 0 |  | 16903.51 | -21.84 | 16881.67 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a project for the phase-out of methyl bromide soil fumigation | Individual | LAC | NIC | FUM | 34 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-05-01 | 2003-12-01 | 30000 | -27246 | 2754 | 2754 | 100% | 0 | 0 |  | 3900 | -3541.98 | 358.02 | 0 | 0 | FIN | [10 empty] | 2001 | INV
ONG | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | NIC | FUM | 45 | TAS | 12 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2700 | 0 | 0 | 2700 | 0 | Project was approved by 45th ExCom in Apr 2005. More detailed background information was collected through the counterpart for the organization of the workshop. A work programme was drafted. The workshop will take place in May 2006. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Preparation of CFC phase out strategy for refrigeration and A/C industries and services | Individual | AFR | NIR | REF | 11 | TAS | 07 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1999-12-01 | 2000-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Phasing out of CFCs at Debo Industries Ltd. Nigeria | Individual | AFR | NIR | REF | 18 | INV | 10 | A | O | I | CFC | 52 | 52 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1048053 | -340 | 1047713 | 1047713 | 100% | 0 | 0 |  | 136246.89 | -44.2 | 136202.69 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Thermocool Eng. Co. Ltd. | Individual | AFR | NIR | REF | 18 | INV | 11 | A | O | I | CFC | 82 | 82 |  |  | 1995-11-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1465750 | -71 | 1465679 | 1465679 | 100% | 0 | 0 |  | 190547.5 | -9.23 | 190538.27 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at A.G. Leventis | Individual | AFR | NIR | REF | 26 | INV | 30 | A | O | I | CFC | 19.1 | 19.1 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2003-03-01 | 2004-04-01 | 190420 | 0 | 190420 | 190420 | 100% | 0 | 0 |  | 24754.6 | 0 | 24754.6 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at New Ltd. | Individual | AFR | NIR | REF | 26 | INV | 40 | A | O | I | CFC | 20.9 | 20.9 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2003-05-01 | 361770 | -2 | 361768 | 361768 | 100% | 0 | 0 |  | 47030.1 | -0.26 | 47029.84 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at Kolinton Technical Industries | Individual | AFR | NIR | REF | 26 | INV | 44 | A | O | I | CFC | 39.5 | 39.5 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2003-12-01 | 2004-06-01 | 674348 | -1970 | 672378 | 672378 | 100% | 0 | 0 |  | 84178.28 | -216.7 | 83961.58 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Soesons Ltd. | Individual | AFR | NIR | REF | 28 | INV | 48 | A | O | I | CFC | 16.1 | 16.1 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-08-01 | 221353 | 0 | 221353 | 221353 | 100% | 0 | 0 |  | 28775.89 | 0 | 28775.89 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Onward Electrical Industry Ltd. | Individual | AFR | NIR | REF | 28 | INV | 51 | A | O | I | CFC | 10.7 | 10.7 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2003-12-01 | 2004-04-01 | 146927 | 0 | 146927 | 146927 | 100% | 0 | 0 |  | 19100.51 | 0 | 19100.51 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at United Technologies Ltd. | Individual | AFR | NIR | REF | 28 | INV | 52 | A | O | I | CFC | 9.6 | 9.6 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-12-01 | 130579 | -50 | 130529 | 130529 | 100% | 0 | 0 |  | 16975.27 | -6.5 | 16968.77 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration equipment at De Johnson Ltd. | Individual | AFR | NIR | REF | 29 | INV | 53 | A | O | I | CFC | 9 | 9 |  |  | 1999-11-01 | 2000-09-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 123816 | 0 | 123816 | 123816 | 100% | 0 | 0 |  | 16096.08 | 0 | 16096.08 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration at Austin-Laz & Co. Ltd | Individual | AFR | NIR | REF | 29 | INV | 54 | A | O | I | CFC | 11.6 | 11.6 |  |  | 1999-11-01 | 2000-10-01 | 2001-06-01 |  | 2002-08-01 | 2003-07-01 | 147181 | 0 | 147181 | 147181 | 100% | 0 | 0 |  | 19133.53 | 0 | 19133.53 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosols sector | Individual | AFR | NIR | ARS | 30 | PRP | 61 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2000-10-01 | 2001-09-01 | 25000 | -9291 | 15709 | 15709 | 100% | 0 | 0 |  | 3250 | -1207.83 | 2042.17 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | NIR | REF | 30 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-02-01 | 2002-09-01 | 25000 | -2248 | 22752 | 22752 | 100% | 0 | 0 |  | 3250 | -292.24 | 2957.76 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC=12 withHFC-134a, and foam flowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration equipment at Bosmak Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 71 | A | O | I | CFC | 10.8 | 10.8 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2003-10-01 | 2004-06-01 | 154245 | -664 | 153581 | 153581 | 100% | 0 | 0 |  | 20051.85 | -86.32 | 19965.53 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Coldcare Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 76 | A | O | I | CFC | 11.4 | 11.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-12-01 | 2003-12-01 | 173200 | 0 | 173200 | 173200 | 100% | 0 | 0 |  | 22516 | 0 | 22516 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Akocen Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 77 | A | O | I | CFC | 12.1 | 12.1 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2003-10-01 | 157894 | 0 | 157894 | 157894 | 100% | 0 | 0 |  | 20526.22 | 0 | 20526.22 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for three projects in the commercial refrigeration sector | Individual | AFR | NIR | REF | 33 | PRP | 80 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1747 | 18253 | 18253 | 100% | 0 | 0 |  | 2600 | -227.11 | 2372.89 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Polade | Individual | AFR | NIR | REF | 35 | INV | 97 | A | O | I | CFC | 8.3 | 8.3 |  |  | 2001-12-01 | 2002-03-01 | 2004-05-01 |  | 2004-06-01 | 2005-03-01 | 70382 | -30 | 70352 | 70352 | 100% | 0 | 0 |  | 9149.66 | -3.9 | 9145.76 | 0 | 0 | Financial completion in March 2005 Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
COM | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Ristian | Individual | AFR | NIR | REF | 35 | INV | 98 | A | O | I | CFC | 11 | 11 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2004-06-01 | 2006-03-01 | 143729 | 0 | 143729 | 142811 | 99.36% | 918 | 0 | 1 | 18684.77 | 0 | 18565.4 | 119.3 | 0 | Financial completion in Mar 2006. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of a sectoral phase-out plan in solvents | Individual | AFR | NIR | SOL | 36 | PRP | 101 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-06-01 | 2004-11-01 | 70000 | -64 | 69936 | 69936 | 100% | 0 | 0 |  | 9100 | -8.32 | 9091.68 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
ONG | UNIDO | National CFC phase-out plan: refrigeration manufacturing | Multi-Year | AFR | NIR | PHA | 38 | INV | 105 | A | O | I | CFC | 42.9 | 34.65 |  |  | 2002-11-01 | 2003-03-01 | 2005-06-01 | 2006-03-01 |  |  | 682386 | 0 | 682386 | 613667 | 89.93% | 68719 | 65068 | 50000 | 82521 | 0 | 74210.8052 | 8310.1948 | 7868.6791 | Injection and spray foaming machines as well as refrigerating equipment were installed. In Dec 2005, foaming equipment was commissioned at all recipients after chemicals availability. Project will be completed in Mar 2006. | [7 empty] | 2005-06-01 |  |  | 2002 | INV | n.a. | n.a. |  |  | n.a. | n.a. | n.a.
ONG | UNIDO | National CFC phase-out plan (aerosol sector) | Multi-Year | AFR | NIR | PHA | 41 | INV | 109 | A | O | I | CFC | 57.9 | 0 |  |  | 2003-12-01 | 2004-07-01 | 2005-12-01 | 2006-06-01 |  |  | 255000 | 0 | 255000 | 87835 | 34.45% | 167165 | 154065 | 150000 | 33150 | 0 | 11418.55 | 21731.45 | 20028.45 | Project has experienced long delay. Due to limited space available for LPG storage installation and recommended safety distances from LPG tank to aerosol plant and factory fence, instead of the initially agreed one underground LPG storage tank, subcontractor suggested to install two smaller on the ground tanks requesting the counterpart to pay for cost difference. In following negotiations with subcontractor, UNIDO insisted on supply of the initially envisaged single LPG bulk storage tank to be put on the concrete cradle and covered with sand. Time-consuming approval of new layout by local fire authorities caused additional delay. During first quarter of 2006, all equipment was manufactured and shipped to the project site. Equipment installation was carried out in Apr 2006. | [10 empty] | 2003 | INV | n.a. | n.a. |  |  | n.a. | n.a. | n.a.
COM | UNIDO | Terminal ODS phase out umbrella project in the solvent sector (first tranche) | Multi-Year | AFR | NIR | SOL | 43 | INV | 110 | A | O | I | CTC | 152.1 | 152.1 |  |  | 2004-07-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 |  | 530000 | 0 | 530000 | 512516 | 96.7% | 17484 | 12781 | 17484 | 39750 | 0 | 38438.7 | 1311.3 | 958.575 | Project completed in Dec 2005. | [10 empty] | 2004 | INV | 198 | 197.85 |  |  | Yes | Yes | Yes
ONG | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (2nd tranche) | Multi-Year | AFR | NIR | SOL | 46 | INV | 113 | A | O | I | CTC TCA | 0 | 0 |  |  | 2005-07-01 | 2005-11-01 | 2006-07-01 | 2006-12-01 |  |  | 317000 | 0 | 317000 | 21097 | 6.655% | 295903 | 0 | 295903 | 23775 | 0 | 1582.275 | 22192.725 | 0 | Second tranche was released by 46th ExCom in July 2005. As required by 46th ExCom, UNIDO submitted a verification report of specified 2004 consumption limits to the Secretariat. The Secretariat reviewed the report and agreed in 2006 on the disbursement of funds. The 2005 consumption is well below the new limit and all activities have been progressed. | [10 empty] | 2005 | INV | 45.9 | 0 |  |  | Yes | Yes | No
FIN | UNIDO | Country programme preparation | Individual | ASP | OMA | SEV | 29 | CPG | 01 | A | O | I |  | 0 | 0 |  |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-12-01 | 2002-05-01 | 80000 | -1579 | 78421 | 78421 | 100% | 0 | 0 |  | 10400 | -205.27 | 10194.73 | 0 | 0 | FIN
COM | UNIDO | Institutional Strengthening/Support to the National Ozone Unit in Oman | Individual | ASP | OMA | SEV | 32 | INS | 02 | N | T | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2005-12-01 |  | 79000 | 0 | 79000 | 73290 | 92.77% | 5710 | 5700 | 5700 | 10270 | 0 | 9527.7 | 742.3 | 741 | Project completed in Dec 2005.
COM | UNIDO | Implementation of the RMP: Training of trainers in good refrigerant management practices | RMP Update | ASP | OMA | REF | 34 | TRA | 02 | A | O | I | CFC | 0 | 0 |  |  | 2001-07-01 | 2002-06-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 178000 | 0 | 178000 | 176361 | 99.08% | 1639 | 0 | 1 | 23140 | 0 | 22926.93 | 213.07 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2001 | NON-INV
FIN | UNIDO | Implementation of the RMP: Customs training programme | RMP Update | ASP | OMA | REF | 34 | TRA | 04 | A | O | I | CFC | 0 | 0 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-09-01 | 42000 | -4528 | 37472 | 37472 | 100% | 0 | 0 |  | 5460 | -588.64 | 4871.36 | 0 | 0 | FIN | [10 empty] | 2001 | NON-INV
ONG | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | OMA | REF | 34 | TAS | 05 | A | O | I | CFC | 0 | 0 |  |  | 2001-07-01 |  | 2004-08-01 | 2006-11-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 5000 | 2600 | 0 | 0 | 2600 | 0 | Final clearance on terms of reference for monitoring contract was given by Government in Dec 2005. Contract for monitoring implementation of all three components of RMP will be awarded in May 2006. Project is expected to be completed by Nov 2006. | [10 empty] | 2001 | NON-INV
COM | UNIDO | Implementation of the RMP: Recovery and recycling project | RMP Update | ASP | OMA | REF | 34 | TAS | 06 | A | O | I | CFC | 13 | 13 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2005-12-01 |  | 230000 | 0 | 230000 | 137451 | 59.76% | 92549 | 80566 | 80566 | 29900 | 0 | 17868.63 | 12031.37 | 10473.58 | Project completed in Dec 2005. | [10 empty] | 2001 | INV
ONG | UNIDO | Awareness workshop and training on methyl bromide alternatives | Individual | ASP | OMA | FUM | 44 | TRA | 10 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2005-12-01 | 2006-09-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 35000 | 3150 | 0 | 0 | 3150 | 0 | Ministry of Agriculture and Environment provided the requested information to set training course. Some alternative options were put forward for execution of the programmed training which will take place in May 2006. | [10 empty] | 2004 | NON-INV
ONG | UNIDO | Training and awareness workshop in the solvent sector (CTC) | Individual | ASP | OMA | SOL | 45 | TAS | 11 | A | O | I | CTC | 0.1 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  |  | 35000 | 0 | 35000 | 82 | 0.2343% | 34918 | 0 | 20000 | 3150 | 0 | 7.38 | 3142.62 | 0 | Project was approved by 45th ExCom in Apr 2005. National expert was recruited to collect information from main users of CTC which will be used to tailor a training course. Survey will be ready in Mar 2006. Training will take place during second quarter of 2006. | [10 empty] | 2005 | INV
ONG | UNIDO | Halon consumption phase-out through a technical assistance programme and a halon recycling | Individual | ASP | OMA | HAL | 46 | TAS | 12 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 |  | 2006-12-01 | 2006-12-01 |  |  | 64600 | 0 | 64600 | 0 | 0% | 64600 | 0 | 35000 | 5814 | 0 | 0 | 5814 | 0 | Project was transferred from World Bank to UNIDO at 46th ExCom in July 2005. Project document was received, implementation activities are coordinated with the National Ozone Unit. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | OMA | PHA | 46 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 25000 | 2250 | 0 | 0 | 2250 | 0 | PRP project was approved by 46th ExCom in July 2005. TPMP is expected to be submitted to 50th ExCom. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Renewal of institutional strengthening support (phase II) | Individual | ASP | OMA | SEV | 46 | INS | 14 | N | T | I |  | 0 | 0 |  |  | 2005-07-01 |  | 2007-07-01 | 2007-12-01 |  |  | 68467 | 0 | 68467 | 0 | 0% | 68467 | 0 | 30000 | 5135.025 | 0 | 0 | 5135.025 | 0 | Phase II was approved by 46th ExCom in July 2005. Project document which was made available to the Ministry of Regional Municipalities, Environment and Water Resources/Ozone Unit, was signed in Feb 2006. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Strategy for ODS phase out in refrigeration industry | Individual | ASP | PAK | REF | 12 | TAS | 03 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1995-08-01 | 1994-06-01 |  | 1998-03-01 | 2000-07-01 | 50000 | -311 | 49689 | 49689 | 100% | 0 | 0 |  | 6500 | -40.43 | 6459.57 | 0 | 0 | FIN |  |  |  | 1999-02-01
COM | UNIDO | Phasing out ODS at the Chest Freezer Factory of Riaz Electric Co. Ltd. | Individual | ASP | PAK | REF | 19 | INV | 09 | A | O | I | CFC | 48.2 | 48.2 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-12-01 | 2005-12-01 | 822987 | 0 | 822987 | 817606 | 99.35% | 5381 | 0 | 1 | 106988.31 | 0 | 106288.78 | 699.53 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. |  |  | 1997-10-01 | 1999-12-01
COM | UNIDO | Phasing out ODS at the refrigerator and chest freezer plants of Pak Elektron Ltd. (PEL) | Individual | ASP | PAK | REF | 19 | INV | 10 | A | O | I | CFC | 68 | 68 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-10-01 |  | 1210295 | 0 | 1210295 | 1091218 | 90.16% | 119077 | 101755 | 101755 | 157338.35 | 0 | 141858.34 | 15480.01 | 13228.15 |  |  |  | 1997-10-01 | 1999-12-01
FIN | UNIDO | Conversion of ODS coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Hyderabad | Individual | ASP | PAK | SOL | 22 | INV | 13 | A | O | I | CFC | 18.9 | 18.9 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 1999-12-01 | 2002-09-01 | 321172 | -3705 | 317467 | 317467 | 100% | 0 | 0 |  | 41752.36 | -481.65 | 41270.71 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning and coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Lahore | Individual | ASP | PAK | SOL | 22 | INV | 14 | A | O | I | CFC | 40.7 | 40.7 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2002-06-01 | 2003-06-01 | 510162 | -283 | 509879 | 509879 | 100% | 0 | 0 |  | 66321.06 | -36.79 | 66284.27 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the freezer factory of Hirra Farooq's (Pvt) Ltd. | Individual | ASP | PAK | REF | 23 | INV | 17 | A | O | I | CFC | 31.2 | 31.2 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 2003-08-01 | 2003-12-01 | 521580 | -3932 | 517648 | 517648 | 100% | 0 | 0 |  | 67805.4 | -511.16 | 67294.24 | 0 | 0 | FIN
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | ASP | PAK | FUM | 24 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-12-01 | 1999-04-01 |  | 2000-01-01 | 2000-07-01 | 30000 | -21132 | 8868 | 8868 | 100% | 0 | 0 |  | 3900 | -2747.16 | 1152.84 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | PAK | REF | 27 | PRP | 32 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-03-01 | 1999-12-01 |  | 2003-07-01 | 2003-10-01 | 30000 | -2250 | 27750 | 27750 | 100% | 0 | 0 |  | 3900 | -292.5 | 3607.5 | 0 | 0 | FIN | [5 empty] | 2001-12-01
FIN | UNIDO | Project preparation for four projects in the solvent (CTC) sector | Individual | ASP | PAK | SOL | 33 | PRP | 41 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | -7058 | 22942 | 22942 | 100% | 0 | 0 |  | 3900 | -917.54 | 2982.46 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
ONG | UNIDO | Conversion of carbon tetrachloride as process solvent to 1,2-dichloroethane at Himont Chemicals Ltd. | Individual | ASP | PAK | PAG | 35 | INV | 42 | A | O | I | CTC | 80 | 0 |  |  | 2001-12-01 | 2002-04-01 | 2004-01-01 | 2006-07-01 |  |  | 485701 | 0 | 485701 | 173287 | 35.68% | 312414 | 187098 | 187000 | 63141.13 | 0 | 22527.31 | 40613.82 | 24322.74 | Project is monitored under project implementation delays as reported to the 48th ExCom in Apr 2006. Procurement of some more technological components was initiated to complete installation. Project is experiencing some delay since offers received were technically not acceptable. Further plans of project implementation will be discussed with National Ozone Unit and new owner of the company. Project is expected to be completed by July 2006. | [10 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the production of domestic refrigeration equipment at Ideal Appliances, Ltd. | Individual | ASP | PAK | REF | 35 | INV | 43 | A | O | I | CFC | 12.9 | 12.9 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2004-07-01 | 2005-09-01 | 173101 | -1614 | 171487 | 171487 | 100% | 0 | 0 |  | 22503.13 | -209.82 | 22293.31 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of two projects in the solvents sector | Individual | ASP | PAK | SOL | 36 | PRP | 45 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 20000 | -670 | 19330 | 19330 | 100% | 0 | 0 |  | 2600 | -87.1 | 2512.9 | 0 | 0 | FIN | [10 empty] | 2002 | INV
COM | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Riaz Electric Ltd., Lahore | Individual | ASP | PAK | SOL | 37 | INV | 47 | A | O | I | CTC | 10 | 10 |  |  | 2002-07-01 | 2004-10-01 | 2004-08-01 |  | 2005-12-01 |  | 122078 | 0 | 122078 | 105993 | 86.82% | 16085 | 15430 | 15430 | 15870.14 | 0 | 13779.09 | 2091.05 | 2005.9 | Project completed in Dec 2005. | [10 empty] | 2002 | INV
FIN | UNIDO | Preparation of investment projects in the solvents sector (CTC/TCA) | Individual | ASP | PAK | SOL | 39 | PRP | 48 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 25000 | -845 | 24155 | 24155 | 100% | 0 | 0 |  | 1875 | -63.375 | 1811.625 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2003
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector | Individual | ASP | PAK | FUM | 39 | PRP | 49 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2004-04-01 | 2004-06-01 | 30000 | -9356 | 20644 | 20644 | 100% | 0 | 0 |  | 2250 | -701.7 | 1548.3 | 0 | 0 | FIN | [10 empty] | 2003
FIN | UNIDO | Preparation of a phase-out plan in the refrigeration sector (CFC manufacturing) | Individual | ASP | PAK | REF | 39 | PRP | 50 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 | 2005-05-01 | 20000 | -199 | 19801 | 19801 | 100% | 0 | 0 |  | 1500 | -14.925 | 1485.075 | 0 | 0 | Financial completion in May 2005. | [10 empty] | 2003
COM | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) and methyl chloroform (MCF) to tetrachloroethylene (PER) and water in combination with partial process modification at Hirra Farooq Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 51 | A | O | I | CTC MCF | 37.5 | 37.5 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 |  | 246493 | 0 | 246493 | 239467 | 97.15% | 7026 | 6464 | 6464 | 22184.37 | 0 | 21552.03 | 632.34 | 581.76 | Project completed in Dec 2005. | [10 empty] | 2003
COM | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC), methyl chloroform (MCF) and CFC-113 to tetrachloroethylene (PER) and water in combination with process modification at Breeze Frost Industries Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 52 | A | O | I | CTC MCF CFC | 33.2 | 33.2 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 |  | 282056 | 0 | 282056 | 271822 | 96.37% | 10234 | 10014 | 10000 | 21254 | 0 | 20482.8289 | 771.1711 | 754.5933 | Project completed in Dec 2005. | [10 empty] | 2003
FIN | UNIDO | Project preparation for a halon sector phase-out plan | Individual | ASP | PAK | HAL | 40 | PRP | 53 | A | O | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2003-12-01 | 2004-12-01 | 22000 | -814 | 21186 | 21186 | 100% | 0 | 0 |  | 1650 | -61.05 | 1588.95 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2003
ONG | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | ASP | PAK | HAL | 41 | TAS | 55 | A | O | I | HAL | 24.2 | 0 |  |  | 2003-12-01 | 2004-02-01 | 2006-12-01 | 2006-12-01 |  |  | 209400 | 0 | 209400 | 171585 | 81.94% | 37815 | 37526 | 37526 | 18846 | 0 | 15442.65 | 3403.35 | 3377.34 | Some delay occurred due to bankruptcy of subcontractor. New subcontractor was selected. Halon recovery and recycling centre was established and put into operation. Equipment was manufactured and delivered to project site. Government requested to introduce full ban on halon import by 30 June 2006. | [10 empty] | 2003 | INV
COM | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (first tranche) | Multi-Year | ASP | PAK | REF | 41 | TAS | 56 | A | O | I | CFC | 36 | 36 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2004-12-01 |  | 191000 | 0 | 191000 | 146123 | 76.5% | 44877 | 44671 | 44877 | 14325 | 0 | 10959.225 | 3365.775 | 3350.325 | [11 empty] | 2003 | INV | 614 | 578 |  |  | Yes | n.a. | n.a.
ONG | UNIDO | Sector phase-out plan of CTC | Multi-Year | ASP | PAK | PHA | 41 | INV | 57 | A | O | I | CTC | 100 | 109.7 |  |  | 2003-12-01 | 2004-03-01 | 2004-12-01 | 2006-07-01 |  |  | 1200000 | 0 | 1200000 | 460389 | 38.37% | 739611 | 695602 | 500000 | 90000 | 0 | 34529.175 | 55470.825 | 52170.15 | Public awareness workshop was held in Oct 2005. Cleaning equipment for 14 enterprises in metal cleaning and textile sectors was purchased and delivered in three shipments. The equipment is expected to be installed by June 2006. | [10 empty] | 2002 2003 | INV | 61.9 | not available |  |  | not available | No | No
ONG | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (second tranche) | Multi-Year | ASP | PAK | REF | 44 | TAS | 61 | A | O | I | CFC | 80 | 0 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 | 2006-03-01 |  |  | 534200 | 0 | 534200 | 136261 | 25.51% | 397939 | 33704 | 200000 | 40065 | 0 | 10219.575 | 29845.425 | 2527.8 | New PMU structure was formed in the country. Training of technicians in Punjab was started by the Training, Education and Vocational Authority of the Punjab Government. Training of technicians in other provinces was discussed with National Training Bureau. Second tranche will be completed in Mar 2006. | [10 empty] | 2004 | INV | 614 | 373.6 |  |  | Yes | n.a. | n.a.
ONG | UNIDO | Sector phase-out plan of CTC (second tranche) | Multi-Year | ASP | PAK | PHA | 44 | INV | 62 | A | O | I | CTC | 326.5 | 92 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 | 2006-10-01 |  |  | 1300000 | 0 | 1300000 | 7219 | 0.5553% | 1292781 | 9398 | 13000 | 97500 | 0 | 541.425 | 96958.575 | 704.85 | Project implementation team was re-established through recruitment of new national experts. Local engineering and consultancy company was recruited to carry out further verification of CTC end-users eligible to receive equipment and to assist with other project implementation activities, including organization of workshops, public awareness campaigns, assistance in installation and commissioning of equipment. Auditing company was selected and audit to verify 2004 CTC consumption is in progress. 2005 annual implementation plan performance report will be submitted after receipt of audit report and after reduction of CTC consumption to limits stipulated in the agreement. A partial phase-out of 92 ODP tonnes was achieved. | [10 empty] | 2004 | INV | 61.9 | not available |  |  | not available | No | No
ONG | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | PAK | FUM | 45 | TAS | 63 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 20000 | 2700 | 0 | 0 | 2700 | 0 | Project was approved by 45th ExCom in Apr 2005. Activity to organize awareness campaign will start in 2006. A workshop is planned to take place in June 2006. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (third tranche) | Multi-Year | ASP | PAK | REF | 47 | INV | 64 | A | O | I | CFC | 80 | 0 |  |  | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 414300 | 0 | 414300 | 0 | 0% | 414300 | 0 | 100000 | 31072.5 | 0 | 0 | 31072.5 | 0 | Third tranche was released by 47th ExCom in Nov 2005. Contract with the Sindh Directorate is being arranged to start training in Sindh. Bidding for training in Balotictan, NWFP, has started. Training of technicians in Punjab, Sindh and other provinces is planned to be partly completed in 2006. Certified technicians will be provided with equipment for good practice and recovery operation. The 2005 consumption is well below the target in the service sector. | [10 empty] | 2005 | INV | 534 | 350 |  |  | Yes | n.a. | n.a.
FIN | UNIDO | Preparation of an awareness workshop on methyl bromide | Individual | LAC | PAN | FUM | 36 | TRA | 16 | A | O | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-10-01 | 2003-12-01 | 30000 | -5383 | 24617 | 24617 | 100% | 0 | 0 |  | 3900 | -699.79 | 3200.21 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
FIN | UNIDO | Project preparation assistance in solvent sector | Individual | LAC | PER | SOL | 17 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -8132 | 21868 | 21868 | 100% | 0 | 0 |  | 3900 | -1057.16 | 2842.84 | 0 | 0 | FIN |  |  |  | 1999-01-01
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Faber Castell | Individual | LAC | PER | SOL | 20 | INV | 18 | A | O | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-11-01 | 1997-10-01 |  | 1998-09-01 | 2000-12-01 | 16409 | -4845 | 11564 | 11564 | 100% | 0 | 0 |  | 2133.17 | -629.85 | 1503.32 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Carbolan | Individual | LAC | PER | SOL | 20 | INV | 19 | A | O | I | TCA | 0.4 | 0.4 |  |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 31457 | -7345 | 24112 | 24112 | 100% | 0 | 0 |  | 4089.41 | -954.85 | 3134.56 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Papeles Industriales | Individual | LAC | PER | SOL | 20 | INV | 20 | A | O | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-12-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 47953 | -1031 | 46922 | 46922 | 100% | 0 | 0 |  | 6233.89 | -134.03 | 6099.86 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a recovery and recycling project in the refrigeration sector | Individual | ASP | PHI | REF | 18 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-01-01 |  | 1997-11-01 | 1998-08-01 | 15000 | 543 | 15543 | 15543 | 100% | 0 | 0 |  | 1950 | 70.59 | 2020.59 | 0 | 0 | FIN
FIN | UNIDO | National CFC recovery and recycling scheme | RMP | ASP | PHI | REF | 22 | TAS | 49 | A | O | I | CFC | 60 | 60 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2002-05-01 | 557500 | -933 | 556567 | 556567 | 100% | 0 | 0 |  | 72475 | -121.29 | 72353.71 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment project in the aerosol sector | Individual | ASP | PHI | ARS | 27 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of the Country Programme | Individual | ASP | QAT | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 1999-09-01 | 80000 | -1 | 79999 | 79999 | 100% | 0 | 0 |  | 10400 | -0.13 | 10399.87 | 0 | 0 | FIN
COM | UNIDO | Institutional Strengthening Project: Creation of the National Ozone Unit | Individual | ASP | QAT | SEV | 27 | INS | 02 | N | T | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-11-01 | 2002-04-01 |  | 2004-10-01 | 2005-12-01 | 68450 | 0 | 68450 | 64069 | 93.6% | 4381 | 0 | 1 | 8898.5 | 0 | 8328.97 | 569.53 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [5 empty] | 2002-04-01
ONG | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | QAT | REF | 34 | TAS | 02 | A | O | I | CFC | 0 | 0 |  |  | 2001-07-01 |  | 2004-08-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 10000 | 2600 | 0 | 0 | 2600 | 0 | Implementation of the monitoring component started and will be continued in 2006. Project is expected to be completed by Dec 2006. | [10 empty] | 2001 | NON-INV
ONG | UNIDO | Implementation of RMP: National recovery and recycling project | RMP Update | ASP | QAT | REF | 34 | TAS | 03 | A | O | I | CFC | 13 | 0 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 | 2006-12-01 |  |  | 295000 | 0 | 295000 | 177771 | 60.26% | 117229 | 972 | 117229 | 38350 | 0 | 23110.23 | 15239.77 | 126.36 | Equipment for second phase was procured and will be delivered, installed and commissioned in 2006. Training of technicians and distribution of equipment to workshops will follow. Project is expected to be completed by Dec 2006. | [10 empty] | 2001 | INV
FIN | UNIDO | Implementation of the RMP: Training of customs and Ozone Unit in monitoring and control of ODS | RMP Update | ASP | QAT | REF | 34 | TRA | 04 | A | O | I | CFC | 0 | 0 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 50000 | -2576 | 47424 | 47424 | 100% | 0 | 0 |  | 6500 | -334.88 | 6165.12 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | NON-INV
COM | UNIDO | Implementation of RMP: Training of trainers and technicians training in good refrigerant management practices | RMP Update | ASP | QAT | REF | 34 | TRA | 05 | A | O | I | CFC | 0 | 0 |  |  | 2001-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-12-01 |  | 105000 | 0 | 105000 | 98865 | 94.16% | 6135 | 4500 | 4500 | 13650 | 0 | 12852.45 | 797.55 | 585 | [11 empty] | 2001 | NON-INV
ONG | UNIDO | Extension of institutional strengthening project: phase 2 | Individual | ASP | QAT | SEV | 41 | INS | 06 | N | T | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-11-01 | 2004-12-01 | 2006-09-01 |  |  | 44500 | 0 | 44500 | 33085 | 74.35% | 11415 | 7671 | 11415 | 3337.5 | 0 | 2481.375 | 856.125 | 575.325 | Subcontract was signed by Supreme Council for Environment and Natural Reserves on 9 Jan 2005. Implementation of subcontract by the Ozone Unit is slow and reporting unsatisfactory and protracted (half-yearly progress report was submitted to UNIDO in draft in Nov 2005, but due to missing items relating to financial reports and clarifications as to the contents of the activity report, clearance action is still pending despite repeated reminders. The Ozone Unit reported public awareness activities through radio, TV and printed media as well as lectures at schools and inclusion of environmental issues in education materials. It seems that the Law for Protection of the Ozone Layer, containing 16 articles, was finalized. The major articles concern 1. control of substances and equipment using ODS, 2. setting up an Ozone Protection Committee consisting of different Ministries, 3. introduction of a quota system and 4. economic measures through penalties. | [10 empty] | 2003 | NON-INV
ONG | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | QAT | PHA | 46 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 |  | 2006-07-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 20000 | 2250 | 0 | 0 | 2250 | 0 | PRP project was approved by 46th ExCom in July 2005. TPMP is expected to be submitted to 50th ExCom. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Preparation of Country Programme | Individual | EUR | ROM | SEV | 11 | CPG | 01 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1995-07-01 | 1998-08-01 | 80000 | -23547 | 56453 | 56453 | 100% | 0 | 0 |  | 10400 | -3061.11 | 7338.89 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 at refrigerator plant at mechanical enterprises SADU and ARCTIC | Individual | EUR | ROM | REF | 15 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-04-01 | 1995-06-01 |  | 1996-07-01 | 1998-08-01 | 50000 | -4978 | 45022 | 45022 | 100% | 0 | 0 |  | 6500 | -647.14 | 5852.86 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS at Spumotim flexible foam plant | Individual | EUR | ROM | FOA | 16 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1996-05-01 | 15000 | 132 | 15132 | 15132 | 100% | 0 | 0 |  | 1950 | 17.16 | 1967.16 | 0 | 0 | FIN
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | ROM | SEV | 17 | INS | 04 | N | T | I |  | 0 | 0 |  |  | 1995-07-01 | 1997-12-01 | 1998-07-01 |  | 2003-12-01 | 2005-01-01 | 168443 | -80490 | 87953 | 87953 | 100% | 0 | 0 |  | 21897.59 | -10463.7 | 11433.89 | 0 | 0 | Financial completion in January 2005 Refund was reported to 45th ExCom, Apr 2005. FIN. |  |  | 1999-03-01 | 2000-01-01
FIN | UNIDO | Phasing out of CFCs at FARMEC SA | Individual | EUR | ROM | ARS | 18 | INV | 05 | A | O | I | CFC | 730 | 730 |  |  | 1995-11-01 | 1996-09-01 | 1997-11-01 |  | 1998-12-01 | 2001-07-01 | 895880 | -30773 | 865107 | 865107 | 100% | 0 | 0 |  | 116464.4 | -4000.49 | 112463.91 | 0 | 0 | FIN
FIN | UNIDO | Phase out ODS at the domestic refrigeration factory Arctic S.A. | Individual | EUR | ROM | REF | 18 | INV | 06 | A | O | R | CFC | 206 | 206.7 |  |  | 1995-11-01 | 1996-10-01 | 1997-05-01 |  | 1997-05-01 | 2000-07-01 | 1095300 | -49669 | 1045631 | 1045631 | 100% | 0 | 0 |  | 142389 | -6456.97 | 135932.03 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the domestic and commercial refrigeration sector | Individual | EUR | ROM | REF | 18 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-05-01 |  | 1999-03-01 | 2000-07-01 | 20000 | -838 | 19162 | 19162 | 100% | 0 | 0 |  | 2600 | -108.94 | 2491.06 | 0 | 0 | FIN |  |  |  | 1999-03-01
CLO | UNIDO | Conversion of commercial refrigeration equipment to phase out CFC-12, HCFC-502 and CFC-11 at Technofrig S.A. | Individual | EUR | ROM | REF | 19 | INV | 08 | A | O | I | CFC | 6.92 | 6.92 |  |  | 1996-05-01 | 1997-03-01 | 1999-06-01 |  |  | 2000-07-01 | 297768 | -255744 | 42024 | 42024 | 100% | 0 | 0 |  | 38709.84 | -33246.72 | 5463.12 | 0 | 0 | CLO |  |  | 1999-07-01
FIN | UNIDO | Phasing out of CFC-11 at S.C. Spumotim S.A. | Individual | EUR | ROM | FOA | 20 | INV | 09 | A | O | I | CFC | 30 | 30 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1997-12-01 | 2000-07-01 | 142293 | -308 | 141985 | 141985 | 100% | 0 | 0 |  | 18498.09 | -40.04 | 18458.05 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 and CFC-12 in the production of domestic refrigerators and replacing them by cyclopentane and HFC-134a at Ratmil, Uzine Mecanica Sadu | Individual | EUR | ROM | REF | 20 | INV | 10 | A | O | I | CFC | 73.3 | 73.3 |  |  | 1996-10-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2002-05-01 | 937859 | 0 | 937859 | 937859 | 100% | 0 | 0 |  | 121921.67 | 0 | 121921.67 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | EUR | ROM | FUM | 23 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-03-01 | 2001-07-01 | 10000 | -795 | 9205 | 9205 | 100% | 0 | 0 |  | 1300 | -103.35 | 1196.65 | 0 | 0 | FIN |  |  |  | 1999-09-01
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | EUR | ROM | FOA | 23 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-05-01 | 2001-07-01 | 10000 | 1649 | 11649 | 11649 | 100% | 0 | 0 |  | 1300 | 214.37 | 1514.37 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | ROM | REF | 24 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 30000 | -1089 | 28911 | 28911 | 100% | 0 | 0 |  | 3900 | -141.57 | 3758.43 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC 11 and CFC-12 in the manufacture of extruded polyethylene and polystyrene foams through the use of butane as a blowing agent at Romcarbon, S.A. | Individual | EUR | ROM | FOA | 27 | INV | 15 | A | O | I | CFC | 132.4 | 132.4 |  |  | 1999-03-01 | 2000-04-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 516512 | -106 | 516406 | 516406 | 100% | 0 | 0 |  | 66816.32 | -11.66 | 66804.66 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | ROM | REF | 28 | TAS | 16 | A | O | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 373840 | -531 | 373309 | 373309 | 100% | 0 | 0 |  | 48599.2 | -69.03 | 48530.17 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | EUR | ROM | REF | 28 | TRA | 17 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-10-01 |  | 2002-08-01 | 2003-10-01 | 23100 | -1383 | 21717 | 21717 | 100% | 0 | 0 |  | 3003 | -179.79 | 2823.21 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | ROM | FUM | 30 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 10000 | -337 | 9663 | 9663 | 100% | 0 | 0 |  | 1300 | -43.81 | 1256.19 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | ROM | REF | 28 | TRA | 19 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2001-01-01 | 2001-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Country programme update | Individual | EUR | ROM | SEV | 36 | CPG | 20 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-01-01 | 2004-04-01 | 60000 | -451 | 59549 | 59549 | 100% | 0 | 0 |  | 7800 | -58.63 | 7741.37 | 0 | 0 | FIN | [10 empty] | 2002 | NON-INV
COM | UNIDO | Preparation of investment projects in the solvent sector | Individual | EUR | ROM | SOL | 39 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-10-01 | 2005-05-01 | 15000 | 0 | 15000 | 14192 | 94.61% | 808 | 0 | 1 | 1125 | 0 | 1064.4 | 60.6 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2003
COM | UNIDO | Terminal umbrella project for the phase-out of ODS solvents | Individual | EUR | ROM | SOL | 41 | INV | 22 | A | O | I | CTC | 11.1 | 11.1 |  |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-12-01 |  | 220615 | 0 | 220615 | 197294 | 89.43% | 23321 | 15515 | 15515 | 19855.35 | 0 | 17756.46 | 2098.89 | 1396.35 | Project completed in Dec 2005. | [10 empty] | 2003 | INV
FIN | UNIDO | Project preparation: CFC phase-out plan (aerosol and refrigeration) | Individual | EUR | ROM | PHA | 42 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2006-10-01 |  | 2005-08-01 | 2005-08-01 | 10000 | -1026 | 8974 | 8974 | 100% | 0 | 0 |  | 750 | -76.95 | 673.05 | 0 | 0 | Project completed and financial closure in Aug 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2004 | NON-INV
ONG | UNIDO | Phase-out of CFC-12 in the manufacture of pharmaceutical aerosols by conversion to HFC-134a propellant at MEBRA, Brasov (terminal aerosol sector project) | Individual | EUR | ROM | ARS | 44 | INV | 26 | A | O | I | CFC | 46.5 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2007-02-01 | 2006-06-01 |  |  | 204776 | 0 | 204776 | 41641 | 20.33% | 163135 | 16359 | 140000 | 18429.84 | 0 | 3747.69 | 14682.15 | 1472.31 | Subcontractor for supply of equipment and services was selected. Equipment was delivered. Installation and commissioning of equipment will be done during first quarter of 2006. | [10 empty] | 2004 | INV
ONG | UNIDO | Preparation of a terminal umbrella project to phase out CTC | Individual | EUR | ROM | SOL | 44 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 | 2006-12-01 |  |  | 20000 | 0 | 20000 | 3738 | 18.69% | 16262 | 3 | 1 | 1500 | 0 | 280.35 | 1219.65 | 0.225 | CTC applications were approved. Two project documents will be formulated for submission to 50th ExCom. | [10 empty] | 2004
COM | UNIDO | Preparation of a closure project in the production of CFC/CTC/MBR |  | EUR | ROM | PRO | 45 | PRP | 28 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 |  | 25000 | 0 | 25000 | 10823 | 43.29% | 14177 | 10658 | 10658 | 1875 | 0 | 811.725 | 1063.275 | 799.35 | Project completed in Dec 2005. Remaining funds will be returned upon financial completion of the project. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Extension of institutional strengthening project: phase II | Individual | EUR | ROM | SEV | 45 | INS | 29 | N | T | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2007-04-01 | 2007-12-01 |  |  | 145984 | 0 | 145984 | 19396 | 13.29% | 126588 | 6669 | 45000 | 10948.8 | 0 | 1454.7 | 9494.1 | 500.175 | Project extension was approved by 45th ExCom in Apr 2005. The project operates under subcontract and national expert arrangements which were made following signature of project document in Sep 2005. Romania celebrated the International Ozone Day in Sep 2005 and organized a workshop on the status of phase-out with participants from ministries, industry and representatives from the EU Commission. Legislative measures were initiated with regard to elaboration of consumption quota allocation (official publication of the Ministerial Order during Mar 2006. Collection of data and updating of the inventory of halon and halon-containing equipment were initiated for the halon management plan. Ratification procedure for the Beijing Amendment was followed up. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | INV | 30 | A | O | I | CFC | 14.6 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-09-01 |  |  | 159050 | 0 | 159050 | 5 | 0.003144% | 159045 | 2000 | 100000 | 11928.75 | 0 | 0.375 | 11928.375 | 150 | First tranche was released by 45th ExCom in Apr 2005. After a preliminary communication between NOU, Sweden and UNIDO, kick-off meetings took place in 2005. Contract for the PMU establishment and monitoring is being finalized with the National Ozone Unit. Code of practice will be investigated and training will be conducted. The next tranche was submitted and approved by 48th ExCom in Apr 2006. | [10 empty] | 2005 | INV | 220 | 185 |  |  | Yes | No | No
ONG | UNIDO | Sector plan for production sector | Multi-Year | EUR | ROM | PRO | 47 | INV | 32 | A | O | I | MBR | 0 | 0 | 5 |  | 2005-11-01 |  | 2006-07-01 | 2006-07-01 |  |  | 3200000 | 0 | 3200000 | 0 | 0% | 3200000 | 0 | 1500000 | 240000 | 0 | 0 | 240000 | 0 | Project was approved by 47th ExCom in Nov 2005. CFC production plant was dismantled. Four ODS plants will be provided with first installment of funding. National Ozone Unit to start monitoring activity. Audit will be organized by UNIDO. | [10 empty] | 2005 | INV |  |  | 175 | not available | not available | No | No
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | AFR | SEN | FOA | 18 | PRP | 05 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 10000 | -559 | 9441 | 9441 | 100% | 0 | 0 |  | 1300 | -72.67 | 1227.33 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | SEN | REF | 22 | TAS | 08 | A | O | I | CFC | 36.12 | 36.12 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-03-01 | 136250 | 0 | 136250 | 136250 | 100% | 0 | 0 |  | 17712.5 | 0 | 17712.5 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (tobacco, peanuts) | Individual | AFR | SEN | FUM | 25 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-01-01 | 2001-07-01 | 30000 | -2385 | 27615 | 27615 | 100% | 0 | 0 |  | 3900 | -310.05 | 3589.95 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide used in peanut seed fumigation in Novasen Ltd. | Individual | AFR | SEN | FUM | 26 | INV | 12 | A | O | I | MBR | 0.7 | 0.7 |  |  | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-02-01 | 62945 | -3321 | 59624 | 59624 | 100% | 0 | 0 |  | 8182.85 | -431.73 | 7751.12 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the RMP: Refrigerant recovery and recycling scheme | RMP Update | AFR | SEN | REF | 33 | TAS | 16 | A | O | I | CFC | 5 | 5 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2003-03-01 | 2004-04-01 | 85000 | -2102 | 82898 | 82898 | 100% | 0 | 0 |  | 11050 | -273.26 | 10776.74 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of a project proposal for setting up a national refrigerant recovery and recycling centre, National Halon Bank | Individual | AFR | SEY | REF | 15 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1998-01-01 | 2000-07-01 | 15000 | -10853 | 4147 | 4147 | 100% | 0 | 0 |  | 1950 | -1410.89 | 539.11 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Preparation of investment projects in the refrigeration, aerosol and foam sectors | Individual | AFR | SUD | SEV | 14 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-03-01 | 1995-01-01 |  | 1998-04-01 | 1999-08-01 | 50000 | -5513 | 44487 | 44487 | 100% | 0 | 0 |  | 6500 | -716.69 | 5783.31 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Sudanese Cosmetics and Household Products | Individual | AFR | SUD | ARS | 18 | INV | 04 | A | O | I | CFC | 281.5 | 281.5 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 497613 | -1085 | 496528 | 496528 | 100% | 0 | 0 |  | 64689.69 | -141.05 | 64548.64 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Patra Foam Co. flexible polyurethane foam plant | Individual | AFR | SUD | FOA | 19 | INV | 05 | A | O | I | CFC | 16 | 16 |  |  | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1997-12-01 | 2000-04-01 | 72227 | -1 | 72226 | 72226 | 100% | 0 | 0 |  | 9389.51 | -0.13 | 9389.38 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of ODS at three small domestic refrigerator factories in Sudan (Coldair Refrigerator Factory, Modern Refrigerator + Metal furniture Co., Sheet Metal Industries Co. Refrigerator Factory) | Individual | AFR | SUD | REF | 19 | INV | 06 | A | O | I | CFC | 7.28 | 7.3 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 2002-03-01 | 2003-05-01 | 100000 | -13774 | 86226 | 86226 | 100% | 0 | 0 |  | 13000 | -1790.62 | 11209.38 | 0 | 0 | FIN |  |  | 1997-08-01
FIN | UNIDO | Preparation of Refrigerant Management Plan | Individual | AFR | SUD | REF | 23 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 1998-12-01 | 2000-04-01 | 10000 | 16132 | 26132 | 26132 | 100% | 0 | 0 |  | 1300 | 2097.16 | 3397.16 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | SUD | ARS | 27 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 25000 | -7421 | 17579 | 17579 | 100% | 0 | 0 |  | 3250 | -964.73 | 2285.27 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | AFR | SUD | REF | 28 | TRA | 09 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2002-06-01 |  | 2003-12-01 | 2003-12-01 | 70000 | -620 | 69380 | 69380 | 100% | 0 | 0 |  | 9100 | -80.6 | 9019.4 | 0 | 0 | FIN
COM | UNIDO | Refrigerant management plan: recovery and recycling | RMP | AFR | SUD | REF | 28 | TAS | 10 | A | O | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2004-08-01 |  | 350000 | 0 | 350000 | 342919 | 97.98% | 7081 | 5000 | 5000 | 45500 | 0 | 44579.47 | 920.53 | 650
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | AFR | SUD | REF | 28 | TRA | 11 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2001-08-01 | 2001-02-01 |  | 2002-10-01 | 2004-09-01 | 38250 | -1974 | 36276 | 36276 | 100% | 0 | 0 |  | 4972.5 | -256.62 | 4715.88 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Tag Cosmetics Ltd. | Individual | AFR | SUD | ARS | 28 | INV | 13 | A | O | I | CFC | 45.1 | 45.1 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2002-07-01 | 2002-12-01 | 131718 | -68 | 131650 | 131650 | 100% | 0 | 0 |  | 17123.34 | -8.84 | 17114.5 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the domestic/commercial refrigeration sector | Individual | AFR | SUD | REF | 39 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-09-01 | 2004-04-01 |  | 2005-04-01 | 2005-08-01 | 20000 | -376 | 19624 | 19624 | 100% | 0 | 0 |  | 1500 | -28.2 | 1471.8 | 0 | 0 | Project completed in Apr 2005. Financial completion in Aug 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2003
COM | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | SUD | PHA | 41 | PRP | 15 | A | O | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 70000 | 0 | 70000 | 69596 | 99.42% | 404 | 0 | 1 | 5250 | 0 | 5219.7 | 30.3 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2003 | INV
ONG | UNIDO | National CFC/CTC phase-out plan (first tranche) | Multi-Year | AFR | SUD | PHA | 44 | INV | 18 | A | O | I | CFC CTC | 16.77 | 16.77 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 | 2006-12-01 |  |  | 499480 | 0 | 499480 | 30135 | 6.033% | 469345 | 55067 | 150000 | 37461 | 0 | 2260.125 | 35200.875 | 4130.025 | During UNIDO's mission in Mar 2005, project implementation modalities were comprehensively discussed with National Ozone Unit and related Ministers. A contract with NOU was prepared to coordinate training of technicians and project monitoring. In addition, project management structure was re-established; awareness programme is continued; two courses for trainers' training were executed to certify 18 national trainers in Nov 2005; five new training centres were selected; specification of necessary equipment was determined; supplementary service equipment and parts of equipment provided under the RMP have already been delivered; purchase order for first batch of recovery equipment is being arranged by UNIDO after completion of international competitive bidding; plan of technicians training and plan for upgrading recovery scheme were prepared; preliminary work for code of practice was initiated. A study tour was undertaken by ten selected national experts to the IKK 2005 exhibition. A total phase-out of 16.77 ODP tonnes was achieved. During first quarter of 2006, NOU provided interim report on project monitoring which was submitted to the Secretariat. The 2005 consumption is below the new target. In addition, technicians training will start and equipment will be arranged in 2006. | [10 empty] | 2004 | INV | 200.3 | 198 |  |  | Yes | No | No
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration production at FridgeMaster | Individual | AFR | SWA | REF | 15 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 25000 | -13327 | 11673 | 11673 | 100% | 0 | 0 |  | 3250 | -1732.51 | 1517.49 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration industry | Individual | ASP | SYR | SEV | 09 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-11-01 | 1993-09-01 |  | 1994-12-01 | 1996-05-01 | 35000 | -60 | 34940 | 34940 | 100% | 0 | 0 |  | 4550 | -7.8 | 4542.2 | 0 | 0 | FIN
FIN | UNIDO | Support to strengthening the General Commission for Environmental Affairs to implement Montreal Protocol related activities | Individual | ASP | SYR | SEV | 10 | INS | 03 | N | T | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 2002-11-01 | 2003-06-01 | 235180 | -15622 | 219558 | 219558 | 100% | 0 | 0 |  | 30573.4 | -2030.86 | 28542.54 | 0 | 0 | FIN |  |  | 1997-07-01 | 1999-10-01
FIN | UNIDO | Phasing out of CFCs at Al Hafez Refrigeration Co. | Individual | ASP | SYR | REF | 13 | INV | 04 | A | O | I | CFC | 106.7 | 100.7 |  |  | 1994-07-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 2001-05-01 | 2883277 | 0 | 2883277 | 2883277 | 100% | 0 | 0 |  | 374826.01 | 0 | 374826.01 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFC at Penguin (Syrian Batric Co.) | Individual | ASP | SYR | REF | 15 | INV | 05 | A | O | I | CFC | 82.3 | 77.3 |  |  | 1994-12-01 | 1996-01-01 | 1996-06-01 |  | 1996-12-01 | 2000-12-01 | 1719900 | -3965 | 1715935 | 1715935 | 100% | 0 | 0 |  | 223587 | -515.45 | 223071.55 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC in manufacturing of refrigerators at Krayem Int. Co. | Individual | ASP | SYR | REF | 15 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -734 | 14266 | 14266 | 100% | 0 | 0 |  | 1950 | -95.42 | 1854.58 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 from the manufacturing of pre-fabricated sandwich panels at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 15 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -1426 | 13574 | 13574 | 100% | 0 | 0 |  | 1950 | -185.38 | 1764.62 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for phasing out of CFC-11 from the sub sector of flexible foams manufacturing | Individual | ASP | SYR | FOA | 15 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Phasing out CFC at Barada General Co. for Metallic Industry | Individual | ASP | SYR | REF | 15 | INV | 09 | A | O | I | CFC | 109 | 97 |  |  | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-12-01 | 2001-07-01 | 989650 | -97010 | 892640 | 892640 | 100% | 0 | 0 |  | 128654.5 | -12611.3 | 116043.2 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | ASP | SYR | ARS | 18 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-05-01 |  | 1998-05-01 | 1999-08-01 | 25000 | -784 | 24216 | 24216 | 100% | 0 | 0 |  | 3250 | -101.92 | 3148.08 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs from Manufacturing of domestic and commercial refrigerators at Krayem Brothers Co. | Individual | ASP | SYR | REF | 18 | INV | 11 | A | O | I | CFC | 89 | 89 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1998-12-01 | 2002-09-01 | 1071575 | -15235 | 1056340 | 1056340 | 100% | 0 | 0 |  | 139304.75 | -1980.55 | 137324.2 | 0 | 0 | FIN
CLO | UNIDO | Preparation of an investment project in recovery and recycling sector | Individual | ASP | SYR | REF | 18 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-01-01 |  |  | 2001-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  | 1998-12-01 | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Gaston Banna & Sons Co. | Individual | ASP | SYR | ARS | 19 | INV | 13 | A | O | I | CFC | 104 | 104 |  |  | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 1998-12-01 | 2000-04-01 | 299500 | 0 | 299500 | 299500 | 100% | 0 | 0 |  | 38935 | 0 | 38935 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Dakkak Co. flexible polyurethane foam plant | Individual | ASP | SYR | FOA | 19 | INV | 14 | A | O | I | CFC | 17 | 17 |  |  | 1996-05-01 | 1996-10-01 | 1997-05-01 |  | 1998-12-01 | 2001-11-01 | 96553 | -131 | 96422 | 96422 | 100% | 0 | 0 |  | 12551.89 | -17.03 | 12534.86 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 19 | INV | 15 | A | O | I | CFC | 65 | 65 |  |  | 1996-05-01 | 1996-11-01 | 1997-09-01 |  | 1998-12-01 | 2001-07-01 | 644600 | -10235 | 634365 | 634365 | 100% | 0 | 0 |  | 83798 | -1330.55 | 82467.45 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Careesse Cosmetics | Individual | ASP | SYR | ARS | 21 | INV | 16 | A | O | I | CFC | 185 | 185 |  |  | 1997-02-01 | 1997-06-01 | 1998-04-01 |  | 1998-12-01 | 2000-12-01 | 272621 | -1638 | 270983 | 270983 | 100% | 0 | 0 |  | 35440.73 | -212.94 | 35227.79 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Abdul Karim Sbei | Individual | ASP | SYR | FOA | 21 | INV | 17 | A | O | I | CFC | 61.7 | 61.7 |  |  | 1997-02-01 | 1997-06-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 92256 | -2127 | 90129 | 90129 | 100% | 0 | 0 |  | 11993.28 | -276.51 | 11716.77 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Walid and Nabil Rankousi Ltd. | Individual | ASP | SYR | FOA | 21 | INV | 18 | A | O | I | CFC | 38.7 | 38.7 |  |  | 1997-02-01 | 1998-11-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 86782 | -2309 | 84473 | 84473 | 100% | 0 | 0 |  | 11281.66 | -300.17 | 10981.49 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | ASP | SYR | FOA | 21 | PRP | 19 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-06-01 |  | 2000-12-01 | 2002-09-01 | 10000 | -377 | 9623 | 9623 | 100% | 0 | 0 |  | 1300 | -49.01 | 1250.99 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al Yaman | Individual | ASP | SYR | ARS | 22 | INV | 20 | A | O | I | CFC | 95 | 95 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2002-08-01 | 216128 | -3075 | 213053 | 213053 | 100% | 0 | 0 |  | 28096.64 | -399.75 | 27696.89 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ahmed Ali Harsho Sons Co. | Individual | ASP | SYR | ARS | 22 | INV | 21 | A | O | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-12-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 175328 | -4068 | 171260 | 171260 | 100% | 0 | 0 |  | 22792.64 | -528.84 | 22263.8 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Taki Eddin & Co. | Individual | ASP | SYR | ARS | 22 | INV | 22 | A | O | I | CFC | 118.8 | 118.8 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 244203 | -341 | 243862 | 243862 | 100% | 0 | 0 |  | 31746.39 | -44.33 | 31702.06 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Laboratories Kosmeto | Individual | ASP | SYR | ARS | 23 | INV | 23 | A | O | I | CFC | 59.9 | 59.9 |  |  | 1997-11-01 | 1998-10-01 | 1999-02-01 |  | 1999-10-01 | 2001-11-01 | 175062 | -2047 | 173015 | 173015 | 100% | 0 | 0 |  | 22758.06 | -266.11 | 22491.95 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Dina Cosmetics | Individual | ASP | SYR | ARS | 23 | INV | 24 | A | O | I | CFC | 70 | 70 |  |  | 1997-11-01 | 1998-10-01 | 1999-08-01 |  | 2000-07-01 | 2001-12-01 | 228477 | -817 | 227660 | 227660 | 100% | 0 | 0 |  | 29702.01 | -106.21 | 29595.8 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Akal Factory | Individual | ASP | SYR | FOA | 23 | INV | 25 | A | O | I | CFC | 101 | 101 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 2002-10-01 | 2004-04-01 | 510130 | -200 | 509930 | 509930 | 100% | 0 | 0 |  | 66316.9 | -26 | 66290.9 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of at least three investment projects in the aerosol sector for phasing out ODS at three enterprises including Nweylati | Individual | ASP | SYR | ARS | 23 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2001-05-01 | 10000 | 4457 | 14457 | 14457 | 100% | 0 | 0 |  | 1300 | 579.41 | 1879.41 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | SYR | FUM | 23 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13013 | 23013 | 23013 | 100% | 0 | 0 |  | 1300 | 1691.69 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for NPD in Damascus and others in rigid foam sector | Individual | ASP | SYR | FOA | 24 | PRP | 29 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-04-01 | 2002-09-01 | 15000 | -261 | 14739 | 14739 | 100% | 0 | 0 |  | 1950 | -33.93 | 1916.07 | 0 | 0 | FIN |  |  |  | 1999-09-01
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in horticulture and commodities fumigation | Individual | ASP | SYR | FUM | 24 | DEM | 30 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 2001-05-01 | 2003-05-01 | 509850 | -34038 | 475812 | 475812 | 100% | 0 | 0 |  | 66280.5 | -4424.94 | 61855.56 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mariza Co. | Individual | ASP | SYR | ARS | 25 | INV | 31 | A | O | I | CFC | 90 | 90 |  |  | 1998-07-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 207652 | -3534 | 204118 | 204118 | 100% | 0 | 0 |  | 26994.76 | -459.42 | 26535.34 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU slabstock foam through the use of CO2 blowing technology at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 26 | INV | 32 | A | O | I | CFC | 96 | 96 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2001-12-01 | 2003-12-01 | 543918 | -27 | 543891 | 543891 | 100% | 0 | 0 |  | 69830.98 | -2.97 | 69828.01 | 0 | 0 | FIN | [5 empty] | 2001-12-01
FIN | UNIDO | Phasing out CFC-11 in the manufacture of flexible PU slabstock foam through the use of methylene chloride as blowing agent at Chaar Bros Co. | Individual | ASP | SYR | FOA | 26 | INV | 34 | A | O | I | CFC | 50 | 50 |  |  | 1998-11-01 | 1999-02-01 | 2000-04-01 |  | 2000-05-01 | 2001-07-01 | 98248 | -235 | 98013 | 98013 | 100% | 0 | 0 |  | 12772.24 | -30.55 | 12741.69 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al-Fajer Co. | Individual | ASP | SYR | ARS | 26 | INV | 36 | A | O | I | CFC | 44 | 44 |  |  | 1998-11-01 | 1999-10-01 | 2000-04-01 |  | 2000-06-01 | 2001-07-01 | 169985 | -1327 | 168658 | 168658 | 100% | 0 | 0 |  | 22098.05 | -172.51 | 21925.54 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of investment projects in the domestic refrigeration sector | Individual | ASP | SYR | REF | 27 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2002-09-01 | 20000 | -2883 | 17117 | 17117 | 100% | 0 | 0 |  | 2600 | -374.79 | 2225.21 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 27 | PRP | 44 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-07-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 8000 | -1370 | 6630 | 6630 | 100% | 0 | 0 |  | 1040 | -178.1 | 861.9 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Golden Penguin Co. | Individual | ASP | SYR | REF | 28 | INV | 45 | A | O | I | CFC | 18.4 | 18.4 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 247481 | -52569 | 194912 | 194912 | 100% | 0 | 0 |  | 32172.53 | -6833.97 | 25338.56 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 30 | PRP | 57 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Alaman Co. | Individual | ASP | SYR | REF | 28 | INV | 60 | A | O | I | CFC | 15.9 | 15.9 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 215910 | -37168 | 178742 | 178742 | 100% | 0 | 0 |  | 28068.3 | -4831.84 | 23236.46 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to cyclopenthane in the production of rigid foam panels at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 31 | INV | 61 | A | O | I | CFC | 61.1 | 61.1 |  |  | 2000-07-01 | 2001-04-01 | 2002-08-01 |  | 2004-10-01 | 2005-04-01 | 426104 | -348 | 425756 | 425756 | 100% | 0 | 0 |  | 55393.52 | -45.24 | 55348.28 | 0 | 0 | Financial completion in Apr 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [7 empty] | 2003-11-01
FIN | UNIDO | Preparation of a project in the flexible foam sector | Individual | ASP | SYR | FOA | 31 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-12-01 | 2003-05-01 | 20000 | -59 | 19941 | 19941 | 100% | 0 | 0 |  | 2600 | -7.67 | 2592.33 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a project in the fumigant (methyl bromide) sector for grain fumigation | Individual | ASP | SYR | FUM | 31 | PRP | 63 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2001-07-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -5380 | 14620 | 14620 | 100% | 0 | 0 |  | 2600 | -699.4 | 1900.6 | 0 | 0 | FIN
COM | UNIDO | Conversion from CFC-11 to HCFC-141b in the production of rigid foam panels at Bassam Baghdan | Individual | ASP | SYR | FOA | 32 | INV | 68 | A | O | I | CFC | 16.4 | 16.4 |  |  | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2005-12-01 |  | 126862 | 0 | 126862 | 110511 | 87.11% | 16351 | 1200 | 14062 | 16492.06 | 0 | 14366.43 | 2125.63 | 156 | Project completed in Dec 2005. IOC of US$ 12,862 will be disbursed in 2006.
FIN | UNIDO | Phase-out o fCFC-11 and 12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Badran and Co. | Individual | ASP | SYR | ARS | 32 | INV | 71 | A | O | I | CFC | 15.6 | 15.6 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 68640 | -25 | 68615 | 68615 | 100% | 0 | 0 |  | 8923.2 | -3.25 | 8919.95 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Mahmoud Hamida | Individual | ASP | SYR | ARS | 32 | INV | 72 | A | O | I | CFC | 10.5 | 10.5 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 46200 | -21 | 46179 | 46179 | 100% | 0 | 0 |  | 6006 | -2.73 | 6003.27 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 and 12 in the manufacture of hair sprays by conversion to hydrocarbon propellant at Khadji and Zahka | Individual | ASP | SYR | ARS | 32 | INV | 73 | A | O | I | CFC | 11 | 11 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 48400 | -108 | 48292 | 48292 | 100% | 0 | 0 |  | 6292 | -14.04 | 6277.96 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of insecticides by conversion to hydrocarbon propellant at Cheikh Ghazal Insecticide Plant | Individual | ASP | SYR | ARS | 32 | INV | 74 | A | O | I | CFC | 36 | 36 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 87298 | -907 | 86391 | 86391 | 100% | 0 | 0 |  | 11348.74 | -117.91 | 11230.83 | 0 | 0 | FIN
ONG | UNIDO | Renewal of institutional strengthening (Phase II) | Individual | ASP | SYR | SEV | 33 | INS | 75 | N | T | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-12-01 | 2003-04-01 | 2006-06-01 |  |  | 195000 | 0 | 195000 | 172732 | 88.58% | 22268 | 22174 | 10000 | 25350 | 0 | 22455.16 | 2894.84 | 2882.62 | Contracts of Ozone Unit staff were extended. | [10 empty] | 2001 | NON-INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al-Muzayek | Individual | ASP | SYR | FOA | 34 | INV | 76 | A | O | I | CFC | 33.7 | 33.7 |  |  | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-12-01 | 2004-12-01 | 106789 | -66 | 106723 | 106723 | 100% | 0 | 0 |  | 13882.57 | -8.58 | 13873.99 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
ONG | UNIDO | Phase-out of the use of methyl bromide in grain storage (first tranche) | Multi-Year | ASP | SYR | FUM | 34 | INV | 80 | A | O | I | MBR | 5 | 5 |  |  | 2001-07-01 | 2002-08-01 | 2002-12-01 | 2006-07-01 |  |  | 300000 | 0 | 300000 | 190588 | 63.53% | 109412 | 60534 | 109412 | 39000 | 0 | 24776.44 | 14223.56 | 7869.42 | Equipment and goods were delivered and installed at project sites. First and second sections of training were completed in July and Nov 2005. In 2006, last set of equipment was procured. | [7 empty] | 2005-12-01 |  |  | 2001 | INV | 99 | 99 |  |  | Yes | n.a. | n.a.
FIN | UNIDO | Preparation of an investment project in the extruded polystyrene foam sector | Individual | ASP | SYR | FOA | 36 | PRP | 82 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 15000 | -104 | 14896 | 14896 | 100% | 0 | 0 |  | 1950 | -13.52 | 1936.48 | 0 | 0 | FIN | [10 empty] | 2002 | INV
CLO | UNIDO | Preparation of an investment project in the domestic refrigeration sector | Individual | ASP | SYR | REF | 36 | PRP | 83 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO | [10 empty] | 2002 | INV
CLO | UNIDO | Preparation of a national ODS phase-out plan | Individual | ASP | SYR | PHA | 36 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-10-01 |  |  | 2003-05-01 | 60000 | -56850 | 3150 | 3150 | 100% | 0 | 0 |  | 7800 | -7390.5 | 409.5 | 0 | 0 | CLO | [10 empty] | 2002 | INV
ONG | UNIDO | Plan for elimination of CFCs in the refrigeration manufacturing sector (domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 87 | A | O | I | CFC | 51 | 0 |  |  | 2002-11-01 | 2003-06-01 | 2004-11-01 | 2006-06-01 |  |  | 353100 | 0 | 353100 | 296565 | 83.99% | 56535 | 40382 | 1 | 40590 | 0 | 34091.1168 | 6498.8832 | 4642.043 | Suppliers have not yet made commissioning of equipment. Project is expected to be completed by June 2006. | [10 empty] | 2002 | INV
FIN | UNIDO | Phasing out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polystyrene (EPS) foam for packing purposes at Shanko and Partners Co. | Individual | ASP | SYR | FOA | 38 | INV | 88 | A | O | I | CFC | 16 | 16 |  |  | 2002-11-01 | 2003-11-01 | 2005-06-01 |  | 2004-08-01 | 2004-12-01 | 132200 | -177 | 132023 | 132023 | 100% | 0 | 0 |  | 17186 | -23.01 | 17162.99 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
ONG | UNIDO | Phase-out of methyl bromide in grain storage (second tranche) | Multi-Year | ASP | SYR | FUM | 41 | INV | 89 | A | O | I | MBR | 29.8 | 29.8 |  |  | 2003-12-01 | 2005-02-01 | 2004-12-01 | 2006-12-01 |  |  | 351725 | 0 | 351725 | 227355 | 64.64% | 124370 | 0 | 124370 | 26379.375 | 0 | 17051.625 | 9327.75 | 0 | Equipment and goods were delivered and installed at project sites. First and second sections of training were completed in July and Nov 2005. Phase-out target was achieved. In 2006, last set of equipment was procured which will be delivered by Aug 2006. Third training section will take place shortly after. | [9 empty] | 2006-12-01 | 2003 | INV | 65.7 | 65.7 |  |  | Yes | n.a. | n.a.
ONG | UNIDO | Extension of institutional strengthening: phase III | Individual | ASP | SYR | SEV | 45 | INS | 91 | N | T | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2007-04-01 | 2007-06-01 |  |  | 203823 | 0 | 203823 | 13639 | 6.692% | 190184 | 3481 | 45000 | 15286.725 | 0 | 1022.925 | 14263.8 | 261.075 | Project extension was approved by 45th ExCom in Apr 2005. The project is implemented on basis of MODs for operational costs and incentive payments through national expert contracts directly with UNIDO. In the framework of the RMP, the Ozone Unit organized a number of training workshops for technicians and customs officers. In the framework of the IS project, workshops were organized on import, export and control of ODSs, on compliance with and enforcement of M.E.A. and Green Customs, as well as general public awareness events on the ozone layer and its protection. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Preparation of CFC-phase-out plan including methyl bromide | Individual | ASP | SYR | PHA | 45 | PRP | 92 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 | 2006-07-01 |  |  | 70000 | 0 | 70000 | 20609 | 29.44% | 49391 | 2353 | 49000 | 5250 | 0 | 1545.675 | 3704.325 | 176.475 | PRP project was approved by 45th ExCom in Apr 2005. Project will be submitted to 49th ExCom. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers | Individual | ASP | SYR | REF | 47 | DEM | 93 | A | O | I |  | 0 | 0 |  |  | 2005-11-01 |  | 2008-12-01 | 2008-12-01 |  |  | 585961 | 0 | 585961 | 0 | 0% | 585961 | 0 | 200000 | 43947.075 | 0 | 0 | 43947.075 | 0 | Project was approved by 47th ExCom in Nov 2006. Working arrangement will be finalized and agreed upon with National Ozone Unit and counterparts in 2006. Offers for supply of new chillers will be obtained and contracts will be awarded after having ensured availability of external resources. | [10 empty] | 2005 | INV
ONG | UNIDO | Phase-out methyl bromide in grain fumigation (third tranche) | Multi-Year | ASP | SYR | FUM | 47 | INV | 94 | A | O | I | MBR | 70.2 | 0 |  |  | 2005-11-01 |  | 2006-12-01 | 2007-10-01 |  |  | 432414 | 0 | 432414 | 0 | 0% | 432414 | 0 | 30000 | 32431.05 | 0 | 0 | 32431.05 | 0 | Third tranche was approved by 47th ExCom in Nov 2005. Project activities and PH3 fumigation are monitored in the country. In 2006, subcontract was extended for provision of technical assistance and logistic services. Work plan was prepared and last set of equipment was procured which will be delivered by Aug 2006. Third training section will take place shortly after. | [10 empty] | 2005 | INV | 43.4 | not available |  |  | not available | n.a. | n.a.
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | THA | FUM | 22 | PRP | 65 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-12-01 |  | 1998-05-01 | 2001-07-01 | 8000 | -636 | 7364 | 7364 | 100% | 0 | 0 |  | 1040 | -82.68 | 957.32 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide ingrain storage (rice, maize, tapioca, feed grains and pulses) | Individual | ASP | THA | FUM | 25 | DEM | 97 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-04-01 | 2000-08-01 |  | 2003-07-01 | 2004-12-01 | 280500 | -22097 | 258403 | 258403 | 100% | 0 | 0 |  | 36465 | -2872.61 | 33592.39 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. |  |  |  |  | 2001-12-01
FIN | UNIDO | Preparation of investment projects in the aerosol, foam, domestic refrigeration and solvent sectors | Individual | AFR | TUN | SEV | 17 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1998-03-01 | 1999-08-01 | 30000 | -1742 | 28258 | 28258 | 100% | 0 | 0 |  | 3900 | -226.46 | 3673.54 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Jasminal Laboratories | Individual | AFR | TUN | ARS | 19 | INV | 14 | A | O | I | CFC | 86 | 86 |  |  | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1998-12-01 | 2001-03-01 | 210000 | -410 | 209590 | 209590 | 100% | 0 | 0 |  | 27300 | -53.3 | 27246.7 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Satem Parfums et Produits Cosmetiques | Individual | AFR | TUN | ARS | 19 | INV | 15 | A | O | I | CFC | 29 | 29 |  |  | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 119500 | 0 | 119500 | 119500 | 100% | 0 | 0 |  | 15535 | 0 | 15535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Meublatex | Individual | AFR | TUN | FOA | 19 | INV | 16 | A | O | I | CFC | 28 | 28 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-10-01 | 2000-07-01 | 105000 | -846 | 104154 | 104154 | 100% | 0 | 0 |  | 13650 | -109.98 | 13540.02 | 0 | 0 | FIN
FIN | UNIDO | Umbrella project to phase out ODS at the six small refrigerator manufacturers | Individual | AFR | TUN | REF | 19 | INV | 17 | A | O | I | CFC | 78.5 | 78.5 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 1997-05-01 | 2001-10-01 | 764557 | -125209 | 639348 | 639348 | 100% | 0 | 0 |  | 99392.41 | -16277.17 | 83115.24 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the aerosol, foam, solvents and methyl bromide sectors | Individual | AFR | TUN | SEV | 21 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 1999-05-01 | 2000-12-01 | 27150 | -1061 | 26089 | 26089 | 100% | 0 | 0 |  | 3529.5 | -137.93 | 3391.57 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at CODIFA | Individual | AFR | TUN | ARS | 22 | INV | 19 | A | O | I | CFC | 60.25 | 60.25 |  |  | 1997-05-01 | 1997-09-01 | 1998-09-01 |  | 1999-12-01 | 2000-11-01 | 179986 | 0 | 179986 | 179986 | 100% | 0 | 0 |  | 23398.18 | 0 | 23398.18 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Alki S.A. | Individual | AFR | TUN | ARS | 22 | INV | 20 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 |  | 1998-09-01 |  |  | 1999-12-01 | 74565 | -74565 | 0 | 0 |  | 0 | 0 |  | 9693.45 | -9693.45 | 0 | 0 | 0 | CLO |  |  |  | 1999-03-01
FIN | UNIDO | Phasing out CFCs at Sogepar | Individual | AFR | TUN | ARS | 22 | INV | 21 | A | O | I | CFC | 18.15 | 18.15 |  |  | 1997-05-01 | 1998-11-01 | 1998-09-01 |  | 2000-01-01 | 2001-07-01 | 68833 | -31 | 68802 | 68802 | 100% | 0 | 0 |  | 8948.29 | -4.03 | 8944.26 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sud Inter Mousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 23 | A | O | I | CFC | 102 | 102 |  |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 2001-12-01 | 2003-08-01 | 546920 | -1138 | 545782 | 545782 | 100% | 0 | 0 |  | 71099.6 | -147.94 | 70951.66 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sotrapoc flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 24 | A | O | I | CFC | 20 | 20 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 90037 | -1844 | 88193 | 88193 | 100% | 0 | 0 |  | 11704.81 | -239.72 | 11465.09 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Parhycos, Sfax, Tunisia | Individual | AFR | TUN | ARS | 23 | INV | 25 | A | O | I | CFC | 10 | 10 |  |  | 1997-11-01 | 1999-04-01 | 1999-02-01 |  | 1999-12-01 | 2001-03-01 | 41195 | -20 | 41175 | 41175 | 100% | 0 | 0 |  | 5355.35 | -2.6 | 5352.75 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Polymousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 26 | A | O | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 104343 | -253 | 104090 | 104090 | 100% | 0 | 0 |  | 13564.59 | -32.89 | 13531.7 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project to phase out ODS at 7 manufacturers of commercial and domestic refrigerators (Chahed Refrigeration, Sogima, Sotiem, Rei, Frigo BAF, Societe Moderne Refrigeration, Frigo Technique) | Individual | AFR | TUN | REF | 23 | INV | 27 | A | O | I | CFC | 29 | 29 |  |  | 1997-11-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2001-03-01 | 374111 | -1625 | 372486 | 372486 | 100% | 0 | 0 |  | 48634.43 | -211.25 | 48423.18 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide in horticulture at Société Méditeranéene Fruitière | Individual | AFR | TUN | FUM | 24 | DEM | 29 | A | O | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 2001-02-01 | 2003-05-01 | 301730 | -11912 | 289818 | 289818 | 100% | 0 | 0 |  | 39224.9 | -1548.56 | 37676.34 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | AFR | TUN | REF | 24 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 1998-12-01 | 2000-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Laboratoires Parcos | Individual | AFR | TUN | ARS | 28 | INV | 35 | A | O | I | CFC | 29.8 | 29.8 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2004-03-01 | 2004-09-01 | 76127 | -589 | 75538 | 75538 | 100% | 0 | 0 |  | 9896.51 | -76.57 | 9819.94 | 0 | 0 | FIN
ONG | UNIDO | Project preparation in the fumigants (dates) sector | Individual | AFR | TUN | FUM | 33 | PRP | 41 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 | 2006-12-01 |  |  | 25000 | 0 | 25000 | 9894 | 39.58% | 15106 | 0 | 1 | 3250 | 0 | 1286.22 | 1963.78 | 0 | Alternative has not yet been identified. PRP is kept until suitable alternative is found. | [10 empty] | 2001 | INV
ONG | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | TUN | SOL | 45 | TAS | 45 | A | O | I | CTC | 0.9 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 20000 | 4500 | 0 | 0 | 4500 | 0 | Project was approved by 45th ExCom in Apr 2005. National expert is being identified by National Ozone Unit to make survey of CTC/TCA users. Training is planned during second half of 2006. | [10 empty] | 2005 | INV
FIN | UNIDO | Preparation of investment projects in ODS phase out in the foam sector | Individual | EUR | TUR | FOA | 15 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-04-01 | 2001-07-01 | 50000 | -45 | 49955 | 49955 | 100% | 0 | 0 |  | 6500 | -5.85 | 6494.15 | 0 | 0 | FIN |  |  | 1997-12-01 | 1999-02-01
CLO | UNIDO | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Barlan Metal | Individual | EUR | TUR | FOA | 18 | INV | 18 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  |  | 1997-09-01 | 804050 | -802118 | 1932 | 1932 | 100% | 0 | 0 |  | 104526.5 | -104275.34 | 251.16 | 3.4959e-12 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 at Urosan Kimiya Sanayii A.S. | Individual | EUR | TUR | FOA | 20 | INV | 22 | A | O | I | CFC | 135 | 135 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1999-12-01 | 2002-04-01 | 643500 | -11958 | 631542 | 631542 | 100% | 0 | 0 |  | 83655 | -1554.54 | 82100.46 | 0 | 0 | FIN |  |  |  | 1999-04-01
FIN | UNIDO | Phasing out CFC-11 at Isbir Termoset Plastic San. A.S., Ankara, Turkey | Individual | EUR | TUR | FOA | 23 | INV | 30 | A | O | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1999-03-01 | 1998-12-01 |  | 2001-04-01 | 2002-09-01 | 501350 | -339 | 501011 | 501011 | 100% | 0 | 0 |  | 65175.5 | -44.07 | 65131.43 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Go-Ya Sungar Ltd. Sti. | Individual | EUR | TUR | FOA | 23 | INV | 31 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-11-01 | 1998-12-01 |  |  | 2002-04-01 | 533400 | -313629 | 219771 | 219771 | 100% | 0 | 0 |  | 69342 | -40771.77 | 28570.23 | 0 | 0 | CLO
FIN | UNIDO | Preparation of investment project in the rigid foam sub sector | Individual | EUR | TUR | FOA | 24 | PRP | 35 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-11-01 | 2001-05-01 | 15000 | -9592 | 5408 | 5408 | 100% | 0 | 0 |  | 1950 | -1246.96 | 703.04 | 0 | 0 | FIN |  |  |  | 1999-09-01
FIN | UNIDO | Preparation of a demonstration project (flowers, tobacco) | Individual | EUR | TUR | FUM | 24 | PRP | 36 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1987 | 23013 | 23013 | 100% | 0 | 0 |  | 3250 | -258.31 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector (polyurethane) at Sungersan AS and Serra Sunger | Individual | EUR | TUR | FOA | 24 | PRP | 37 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1999-12-01 | 2000-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticulture (tomatoes and cucumbers) and ornamental (carnations) crops | Individual | EUR | TUR | FUM | 25 | DEM | 46 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-02-01 | 2000-08-01 |  | 2001-05-01 | 2002-12-01 | 314600 | -9808 | 304792 | 304792 | 100% | 0 | 0 |  | 40898 | -1275.04 | 39622.96 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of CO2 blowing technology at Serra Sunger | Individual | EUR | TUR | FOA | 25 | INV | 47 | A | O | I | CFC | 86 | 86 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-08-01 | 454358 | -122 | 454236 | 454236 | 100% | 0 | 0 |  | 59066.54 | -15.86 | 59050.68 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in the manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Sungersan | Individual | EUR | TUR | FOA | 27 | INV | 52 | A | O | I | CFC | 78 | 78 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 467397 | 0 | 467397 | 467397 | 100% | 0 | 0 |  | 60761.61 | 0 | 60761.61 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU molded foam through the use of CO2 blosing technology at Sungersan, Bursa | Individual | EUR | TUR | FOA | 27 | INV | 53 | A | O | I | CFC | 30 | 30 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2002-05-01 | 327374 | -70 | 327304 | 327304 | 100% | 0 | 0 |  | 42558.62 | -9.1 | 42549.52 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the flexible foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 57 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 15000 | -10132 | 4868 | 4868 | 100% | 0 | 0 |  | 1950 | -1317.16 | 632.84 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-09-01 | 2001-04-01 |  | 2002-03-01 | 2002-05-01 | 15000 | -963 | 14037 | 14037 | 100% | 0 | 0 |  | 1950 | -125.19 | 1824.81 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector (horticulture) | Individual | EUR | TUR | FUM | 30 | PRP | 59 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -833 | 29167 | 29167 | 100% | 0 | 0 |  | 3900 | -108.29 | 3791.71 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane panels for thermal insulation for cold rooms and cold storages at Izotek | Individual | EUR | TUR | FOA | 28 | INV | 65 | A | O | I | CFC | 74.8 | 74.8 |  |  | 1999-07-01 | 2000-08-01 | 2001-08-01 |  | 2001-08-01 | 2002-09-01 | 430721 | -5482 | 425239 | 425239 | 100% | 0 | 0 |  | 55993.73 | -712.66 | 55281.07 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 31 | PRP | 67 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 |  | 2001-07-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Espol Sunger Company | Individual | EUR | TUR | FOA | 31 | INV | 68 | A | O | I | CFC | 95 | 95 |  |  | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2004-02-01 | 2004-12-01 | 552297 | -278 | 552019 | 552019 | 100% | 0 | 0 |  | 70752.67 | -30.58 | 70722.09 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN.
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology at Purtiz Co. in the manufacture of rigid polyurethane foam for insulating purposes | Individual | EUR | TUR | FOA | 32 | INV | 72 | A | O | I | CFC | 52.8 | 52.8 |  |  | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-07-01 | 2004-09-01 | 301094 | -616 | 300478 | 300478 | 100% | 0 | 0 |  | 39142.22 | -80.08 | 39062.14 | 0 | 0 | FIN
COM | UNIDO | Phase out of methyl bromide in protected tomato, cucumber and carnation crops (first tranche) | Multi-Year | EUR | TUR | FUM | 35 | INV | 74 | A | O | I | MBR | 29.2 | 29.2 |  |  | 2001-12-01 | 2002-08-01 | 2002-12-01 |  | 2003-12-01 |  | 1000000 | 0 | 1000000 | 974796 | 97.48% | 25204 | 25204 | 25204 | 120000 | 0 | 117227.56 | 2772.44 | 2772.44 | [11 empty] | 2001 | INV | 263 | 263 |  |  | Yes | n.a. | n.a.
FIN | UNIDO | Preparation of a sectoral phase-out project in the solvents sector | Individual | EUR | TUR | SOL | 36 | PRP | 78 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-07-01 |  | 2004-09-01 | 2004-12-01 | 50000 | -16 | 49984 | 49984 | 100% | 0 | 0 |  | 6500 | -2.08 | 6497.92 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
ONG | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (second tranche) | Multi-Year | EUR | TUR | FUM | 41 | INV | 82 | A | O | I | MBR | 58 | 58 |  |  | 2003-12-01 | 2005-04-01 | 2005-12-01 | 2006-10-01 |  |  | 1000000 | 0 | 1000000 | 226861 | 22.69% | 773139 | 236230 | 500000 | 75000 | 0 | 17014.575 | 57985.425 | 17717.25 | All equipment and goods were delivered to project sites as planned. A workshop on soil fumigation technology was held in June 2005. Soil treatment started in July 2005. Second section of training on soil-less culture was held in Sep 2005. Project staff took part in study tour to Spain (soil fumigation and biosolarization) and to Italy (soil-less culture). Study tours in Colombia were completed in Sep 2005 (flowers and substrates) and in Israel in Dec 2005 (methyl bromide alternatives workshop). Phase-out target was achieved. In 2006, two additional training sections took place. Alternatives applied in the course of 2005/2006 are being evaluated. | [10 empty] | 2003 | INV | 147 | 223 |  |  | Yes | n.a. | n.a.
COM | UNIDO | Terminal umbrella project for phase-out of remaining ozone depleting solvents | Individual | EUR | TUR | SOL | 41 | INV | 83 | A | O | I | CTC | 24 | 24 |  |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2005-12-01 |  | 531644 | 0 | 531644 | 94530 | 17.78% | 437114 | 380107 | 380107 | 39873.3 | 0 | 7089.75 | 32783.55 | 28508.025 | Project completed in Dec 2005. | [10 empty] | 2003 | INV
ONG | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (third and fourth tranches) | Multi-Year | EUR | TUR | FUM | 47 | INV | 88 | A | O | I | MBR | 147 | 127 |  |  | 2005-11-01 |  | 2006-12-01 | 2007-10-01 |  |  | 1408844 | 0 | 1408844 | 0 | 0% | 1408844 | 0 | 200000 | 105663.3 | 0 | 0 | 105663.3 | 0 | Third and fourth tranches were released by 47th ExCom in Nov 2005. Work plan for 2006 was agreed upon, first set of equipment will be delivered by July 2006. Various equipment and goods will be procured for the application of methyl bromide alternative for the crop season 2006/2007, including specific equipment for the improvement of IPM programme through biological antagonist and for the production of local substrate for soil-less cultivation. A national workshop will be implemented. Study tours will be undertaken to improve specific competencies on IPM and disease identification and monitoring. A partial phase-out of 127 ODP tonnes was achieved. | [10 empty] | 2005 | INV | 78.4 | 78 |  |  | Yes | n.a. | n.a.
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | UGA | FUM | 30 | PRP | 08 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -607 | 29393 | 29393 | 100% | 0 | 0 |  | 3900 | -78.91 | 3821.09 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | UGA | FUM | 34 | INV | 08 | A | O | I | MBR | 30 | 24 |  |  | 2001-07-01 | 2002-10-01 | 2006-12-01 | 2006-12-01 |  |  | 228800 | 0 | 228800 | 194371 | 84.95% | 34429 | 22367 | 10000 | 29744 | 0 | 25268.23 | 4475.77 | 2907.71 | Activities continued as planned and in accordance with Dec. 41/78 (c). The metam sodium machine is working well. Training on identification and use of substrates is well advanced. As per the revised phase-out schedule of Uganda which was approved by MOP, the total impact of the project is 30 ODP tonnes, out of which 24 ODP tonnes were phased out in 2005. Project is expected to be completed by Dec 2006. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production | Individual | AFR | URT | REF | 15 | PRP | 02 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-05-01 | 1996-05-01 | 10000 | -67 | 9933 | 9933 | 100% | 0 | 0 |  | 1300 | -8.71 | 1291.29 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in aerosol sector at Mansoor Daya | Individual | AFR | URT | ARS | 15 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 10000 | -1470 | 8530 | 8530 | 100% | 0 | 0 |  | 1300 | -191.1 | 1108.9 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Mansoor Daya Chemicals Ltd. | Individual | AFR | URT | ARS | 18 | INV | 05 | A | O | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1997-12-01 | 1999-08-01 | 417163 | -2796 | 414367 | 414367 | 100% | 0 | 0 |  | 54231.19 | -363.48 | 53867.71 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFCs at Tanzania Domestic Appliance Manufacturers Ltd. | Individual | AFR | URT | REF | 18 | INV | 06 | A | O | I | CFC | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1997-03-01 |  |  | 2002-12-01 | 592790 | -101782 | 491008 | 491008 | 100% | 0 | 0 |  | 77062.7 | -13231.66 | 63831.04 | 0 | 0 | CLO |  |  | 1997-12-01 | 1999-12-01
FIN | UNIDO | Preparation of a demonstration project (tomatoes, cucumber, strawberries, flowers) | Individual | LAC | URU | FUM | 24 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1987 | 23013 | 23013 | 100% | 0 | 0 |  | 3250 | -258.31 | 2991.69 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticultural crops (cucumbers and peppers), seedbeds and nurseries (vegetables, tobacco and forestry) | Individual | LAC | URU | FUM | 25 | DEM | 28 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-06-01 | 299200 | -1853 | 297347 | 297347 | 100% | 0 | 0 |  | 38896 | -240.89 | 38655.11 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the fumigants (methyl bromide) sector | Individual | LAC | URU | FUM | 30 | PRP | 33 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 25000 | -973 | 24027 | 24027 | 100% | 0 | 0 |  | 3250 | -126.49 | 3123.51 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of methyl bromide in horticulture (tomatoes and cut flowers) | Individual | LAC | URU | FUM | 34 | INV | 35 | A | O | I | MBR | 24 | 15.4 |  |  | 2001-07-01 | 2002-02-01 | 2012-12-01 | 2012-12-01 |  |  | 469370 | 0 | 469370 | 392485 | 83.62% | 76885 | 26693 | 20000 | 61018.1 | 0 | 51023.05 | 9995.05 | 3470.09 | An extension of the phase-out agreement was approved by 46th ExCom in July 2005. According to this agreement, total phase-out will be achieved by Jan 2013. Remaining funds under this project should be used in accordance with this schedule. New plan of action was approved by the Parties and the project will be implemented accordingly. Subcontractor (INIA) will continue training and assistance to farmers. A partial phase-out of 2.4 ODP tonnes was achieved in 2005. | [10 empty] | 2001 | INV
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | VEN | FOA | 21 | PRP | 51 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 1998-12-01 | 2000-07-01 | 30000 | -973 | 29027 | 29027 | 100% | 0 | 0 |  | 3900 | -126.49 | 3773.51 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Decocar | Individual | LAC | VEN | FOA | 22 | INV | 54 | A | O | I | CFC | 16.2 | 16.2 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2001-12-01 | 126614 | -21 | 126593 | 126593 | 100% | 0 | 0 |  | 16459.82 | -2.73 | 16457.09 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Veniber C.A. | Individual | LAC | VEN | FOA | 22 | INV | 56 | A | O | I | CFC | 21.6 | 21.6 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1998-12-01 | 2001-09-01 | 164592 | -323 | 164269 | 164269 | 100% | 0 | 0 |  | 21396.96 | -41.99 | 21354.97 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Daniven C.A. | Individual | LAC | VEN | FOA | 22 | INV | 57 | A | O | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2000-04-01 | 104030 | -125 | 103905 | 103905 | 100% | 0 | 0 |  | 13523.9 | -16.25 | 13507.65 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Industrias Todos C.A., Caracas | Individual | LAC | VEN | FOA | 23 | INV | 61 | A | O | I | CFC | 17.8 | 17.8 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-19 | 137520 | 0 | 137520 | 137520 | 100% | 0 | 0 |  | 17877.6 | 0 | 17877.6 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane for Fanesi Barquisimeto | Individual | LAC | VEN | FOA | 24 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 10000 | -72 | 9928 | 9928 | 100% | 0 | 0 |  | 1300 | -9.36 | 1290.64 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 and CFC-12 withHCFC-141b and HFC-134a at INVITREL in the manufacture of commercial refrigeration equipment | Individual | LAC | VEN | REF | 25 | INV | 63 | A | O | I | CFC | 46.4 | 46.4 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2002-09-01 | 419094 | -2376 | 416718 | 416718 | 100% | 0 | 0 |  | 54482.22 | -308.88 | 54173.34 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC -11 with HCFC-141b at TECNOFRIGO in the production of rigid PU panels | Individual | LAC | VEN | FOA | 25 | INV | 64 | A | O | I | CFC | 9 | 9 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2001-01-01 | 2002-09-01 | 71946 | -103 | 71843 | 71843 | 100% | 0 | 0 |  | 9352.98 | -13.39 | 9339.59 | 0 | 0 | FIN |  |  |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Liderfrio in the production of rigid PU panels | Individual | LAC | VEN | FOA | 26 | INV | 66 | A | O | I | CFC | 13.9 | 13.9 |  |  | 1998-11-01 | 1999-12-01 | 2000-04-01 |  | 2000-12-01 | 2002-09-01 | 107850 | -47 | 107803 | 107803 | 100% | 0 | 0 |  | 14020.5 | -6.11 | 14014.39 | 0 | 0 | FIN
FIN | UNIDO | Workshop on alternatives to methyl bromide in tobacco cultivation | Individual | LAC | VEN | FUM | 27 | TRA | 67 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 1999-11-01 | 2001-03-01 | 40000 | -17 | 39983 | 39983 | 100% | 0 | 0 |  | 5200 | -2.21 | 5197.79 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | LAC | VEN | FOA | 27 | PRP | 68 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-06-01 | 2001-07-01 | 10000 | -16 | 9984 | 9984 | 100% | 0 | 0 |  | 1300 | -2.08 | 1297.92 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (integral skin) | Individual | LAC | VEN | FOA | 27 | PRP | 70 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2002-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | LAC | VEN | REF | 27 | PRP | 71 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2000-10-01 | 2001-10-01 | 25000 | -364 | 24636 | 24636 | 100% | 0 | 0 |  | 3250 | -47.32 | 3202.68 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (polystyrene/ polyethylene) | Individual | LAC | VEN | FOA | 27 | PRP | 72 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -69 | 19931 | 19931 | 100% | 0 | 0 |  | 2600 | -8.97 | 2591.03 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Fricava C.A. | Individual | LAC | VEN | FOA | 27 | INV | 73 | A | O | I | CFC | 15.3 | 15.3 |  |  | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 115382 | -77 | 115305 | 115305 | 100% | 0 | 0 |  | 14999.66 | -10.01 | 14989.65 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by 100% water blown system in the production of moulded integral skin flexible PU foam at Fanesi | Individual | LAC | VEN | FOA | 27 | INV | 74 | A | O | I | CFC | 11.4 | 11.4 |  |  | 1999-03-01 | 1999-06-01 | 2000-08-01 |  | 2001-06-01 | 2002-12-01 | 157882 | 0 | 157882 | 157882 | 100% | 0 | 0 |  | 20524.66 | 0 | 20524.66 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the refrigeration/MACS and compressor sector | Individual | LAC | VEN | REF | 27 | PRP | 75 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2000-09-01 | 2002-09-01 | 20000 | -145 | 19855 | 19855 | 100% | 0 | 0 |  | 2600 | -18.85 | 2581.15 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at five commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 76 | A | O | I | CFC | 30.9 | 30.9 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 469140 | -64650 | 404490 | 404490 | 100% | 0 | 0 |  | 60988.2 | -8404.5 | 52583.7 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Novemeca in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 77 | A | O | I | CFC | 16.2 | 16.2 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2000-11-01 | 2002-09-01 | 69886 | -742 | 69144 | 69144 | 100% | 0 | 0 |  | 9085.18 | -96.46 | 8988.72 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Amerio Industrial S.A. in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 78 | A | O | I | CFC | 11.8 | 11.8 |  |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2001-07-01 | 2002-09-01 | 88039 | -312 | 87727 | 87727 | 100% | 0 | 0 |  | 11445.07 | -40.56 | 11404.51 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at three domestic refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 79 | A | O | I | CFC | 27 | 27 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 371705 | -76434 | 295271 | 295271 | 100% | 0 | 0 |  | 48321.65 | -9936.42 | 38385.23 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | LAC | VEN | FOA | 30 | PRP | 80 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-04-01 | 2002-05-01 | 25000 | -2 | 24998 | 24998 | 100% | 0 | 0 |  | 3250 | -0.26 | 3249.74 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | VEN | REF | 30 | PRP | 81 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-06-01 | 2003-10-01 | 20000 | -155 | 19845 | 19845 | 100% | 0 | 0 |  | 2600 | -20.15 | 2579.85 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 at Fandec C.A. (EPSR Foam) | Individual | LAC | VEN | FOA | 28 | INV | 82 | A | O | I | CFC | 45 | 45 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2003-12-01 | 2004-07-01 | 290481 | -109 | 290372 | 290372 | 100% | 0 | 0 |  | 37762.53 | -14.17 | 37748.36 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 with HCFC-141b at Friobox in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 83 | A | O | I | CFC | 16.5 | 1.1 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  |  | 2003-05-01 | 128387 | -119572 | 8815 | 8815 | 100% | 0 | 0 |  | 16690.31 | -15544.36 | 1145.95 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Nevecor in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 84 | A | O | I | CFC | 36.4 | 36.4 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-11-01 | 2003-12-01 | 198374 | -100 | 198274 | 198274 | 100% | 0 | 0 |  | 25788.62 | -13 | 25775.62 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration sector (domestic/commercial) | Individual | LAC | VEN | REF | 31 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2002-05-01 |  | 2002-06-01 | 2003-05-01 | 30000 | -285 | 29715 | 29715 | 100% | 0 | 0 |  | 3900 | -37.05 | 3862.95 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | VEN | REF | 31 | TAS | 86 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2002-12-01 | 2003-10-01 | 70000 | -3018 | 66982 | 66982 | 100% | 0 | 0 |  | 9100 | -392.34 | 8707.66 | 0 | 0 | FIN
COM | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at seven commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 32 | INV | 88 | A | O | I | CFC | 32.3 | 32.3 |  |  | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2005-05-01 | 2005-12-01 | 403590 | 0 | 403590 | 318406 | 78.89% | 85184 | 0 | 1 | 52466.7 | 0 | 41392.78 | 11073.92 | 0 | Project completed in May 2005. The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom.
FIN | UNIDO | Project preparation for two umbrella projects in the rigid foam sector | Individual | LAC | VEN | FOA | 33 | PRP | 89 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-12-01 | 20000 | -258 | 19742 | 19742 | 100% | 0 | 0 |  | 2600 | -33.54 | 2566.46 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams (Umbrella No. 1: Frimac, Frizer, El Control, Incumaca, Frive, Lunger, Profibra, Recovenca, Refriven, Requiven, Tefiven and Vanger) | Individual | LAC | VEN | FOA | 34 | INV | 91 | A | O | I | CFC | 62.8 | 53.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2003-12-01 | 2005-02-01 | 438017 | -71904 | 366113 | 366113 | 100% | 0 | 0 |  | 56942.21 | -9347.52 | 47594.69 | 0 | 0 | Financial completion in February 2005 Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | LAC | VEN | PHA | 36 | PRP | 93 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-03-01 | 2003-07-01 |  | 2004-04-01 | 2004-12-01 | 95000 | -90 | 94910 | 94910 | 100% | 0 | 0 |  | 12350 | -11.7 | 12338.3 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to water system as a blowing agent in the manufacture of flexible polyurethane foams at Manufacturas Enveta, C.A. Cumana | Individual | LAC | VEN | FOA | 36 | INV | 94 | A | O | I | CFC | 32 | 32 |  |  | 2002-03-01 | 2003-12-01 | 2004-03-01 |  | 2004-06-01 | 2004-12-01 | 198882 | -114 | 198768 | 198768 | 100% | 0 | 0 |  | 25854.66 | -14.82 | 25839.84 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
COM | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid p.u. foams: Umbrella No. 2 project. | Individual | LAC | VEN | FOA | 38 | INV | 96 | A | O | I | CFC | 135.5 | 135.5 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-03-01 |  | 851432 | 0 | 851432 | 763441 | 89.67% | 87991 | 1686 | 1 | 103657.52 | 0 | 93978.51 | 9679.01 | 185.46 | Project completed in Mar 2005. | [10 empty] | 2002 | INV
ONG | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | VEN | PHA | 42 | INV | 98 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-07-01 | 2005-04-01 | 2006-12-01 |  |  | 1895062 | 0 | 1895062 | 791195 | 41.75% | 1103867 | 867593 | 1 | 142129.65 | 0 | 59339.625 | 82790.025 | 65069.475 | Part of recovery and recycling equipment was purchased. Equipment is expected to be delivered, installed and commissioned during the first half of 2006. FONDOIN provided a report on all the achievements till the first quarter of 2006. | [10 empty] | 2003 | INV | 3262 | 2944.64 |  |  | Yes | Yes | Yes
ONG | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | LAC | VEN | SOL | 45 | TAS | 103 | A | O | I | TCA | 1.9 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-07-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 10000 | 3600 | 0 | 0 | 3600 | 0 | Project was approved by 45th ExCom in Apr 2005. National expert was recruited to collect information from main users of TCA which will be used to tailor a training course. Training workshop will be conducted during first half of 2006. | [10 empty] | 2005 | INV
ONG | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | VEN | FUM | 45 | TAS | 104 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2006-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 3600 | 0 | 0 | 3600 | 0 | Project was approved by 45th ExCom in Apr 2005. More detailed background information was collected through the counterpart for the organization of the workshop. A work programme was drafted. The workshop is planned to take place during 4th quarter of 2006. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | VEN | PHA | 45 | INV | 105 | A | O | I | CFC | 50.2 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2007-12-01 |  |  | 1631831 | 0 | 1631831 | 0 | 0% | 1631831 | 0 | 1 | 122387.325 | 0 | 0 | 122387.325 | 0 | Second tranche was approved by 45th ExCom in Apr 2005. As required by 45th ExCom, audit report was submitted to the Secretariat for consideration by 47th ExCom in Nov 2005. Audit report is still under review. | [10 empty] | 2005 | INV | 1661 | 1658.63 |  |  | Yes | No | No
FIN | UNIDO | Phasing out ODS at the Searefico and Searee industrial refrigeration plants of Seaprodex Co. | Individual | ASP | VIE | REF | 15 | INV | 04 | A | O | I | CFC | 40 | 40 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2000-07-01 | 497070 | -3474 | 493596 | 493596 | 100% | 0 | 0 |  | 64619.1 | -451.62 | 64167.48 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project proposals for the reduction of refrigerant emission and establishment of collection and reclaiming network in domestic refrigeration sector | Individual | ASP | VIE | REF | 15 | PRP | 05 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-09-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 15000 | -14776 | 224 | 224 | 100% | 0 | 0 |  | 1950 | -1920.88 | 29.12 | -1.1013e-13 | 0 | FIN
FIN | UNIDO | Preparation of investment project for reduction of refrigerant emissions and conversion of food processing and other industrial refrigeration and A/C equipment to suitable alternatives | Individual | ASP | VIE | REF | 15 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -11182 | 8818 | 8818 | 100% | 0 | 0 |  | 2600 | -1453.66 | 1146.34 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | VIE | FUM | 22 | PRP | 16 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -636 | 7364 | 7364 | 100% | 0 | 0 |  | 1040 | -82.68 | 957.32 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Alternatives to the use of methyl bromide on stacked bags of rice, grain in silos and timber on a warehouse under tarps at Vietnam Fumigation Company | Individual | ASP | VIE | FUM | 24 | DEM | 20 | A | O | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2003-12-01 | 2004-12-01 | 411180 | -10380 | 400800 | 400800 | 100% | 0 | 0 |  | 53453.4 | -1349.4 | 52104 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN.
FIN | UNIDO | Technical assistance in preparation of the national halon bank management programme | Individual | ASP | VIE | HAL | 29 | TAS | 23 | A | O | I | HAL | 0 | 0 |  |  | 1999-11-01 | 2000-09-01 | 2000-12-01 |  | 2003-01-01 | 2003-12-01 | 25000 | -7176 | 17824 | 17824 | 100% | 0 | 0 |  | 3250 | -932.88 | 2317.12 | 0 | 0 | FIN
CLO | UNIDO | Preparation of project in the foam sector | Individual | ASP | YEM | FOA | 27 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of project in the aerosol sector | Individual | ASP | YEM | ARS | 27 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2001-10-01 | 20000 | -2912 | 17088 | 17088 | 100% | 0 | 0 |  | 2600 | -378.56 | 2221.44 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | ASP | YEM | REF | 33 | PRP | 07 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-07-01 | 2003-10-01 | 20000 | -3295 | 16705 | 16705 | 100% | 0 | 0 |  | 2600 | -428.35 | 2171.65 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Phase out of CFC-11, CFC-12 and CFC-114 in the manufacture of aerosols by conversion to hydrocarbon propellant at Arabia Felix Industries Ltd. | Individual | ASP | YEM | ARS | 34 | INV | 08 | A | O | R | CFC | 96.6 | 96.6 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-05-01 | 2005-12-01 | 366804 | 0 | 366804 | 360322 | 98.23% | 6482 | 0 | 1 | 34676 | 0 | 34063.2209 | 612.7791 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2001 | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacture of aerosols by conversion to hydrocarbon propellant at Al-Thowra Industrial Complex | Individual | ASP | YEM | ARS | 34 | INV | 10 | A | O | I | CFC | 82.7 | 82.7 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-04-01 | 2004-09-01 | 179508 | -251 | 179257 | 179257 | 100% | 0 | 0 |  | 23336.04 | -32.63 | 23303.41 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Nagman Co. | Individual | ASP | YEM | REF | 35 | INV | 11 | A | O | I | CFC | 7.3 | 7.3 |  |  | 2001-12-01 | 2002-04-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 105641 | -1493 | 104148 | 104148 | 100% | 0 | 0 |  | 13733.33 | -194.09 | 13539.24 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Styrco | Individual | ASP | YEM | REF | 35 | INV | 12 | A | O | I | CFC | 6.1 | 6.1 |  |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 90231 | -1597 | 88634 | 88634 | 100% | 0 | 0 |  | 11730.03 | -207.61 | 11522.42 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
CLO | UNIDO | Preparation of a terminal investment project in commercial refrigeration sector | Individual | ASP | YEM | REF | 36 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-04-01 |  |  | 2003-05-01 | 10000 | -2361 | 7639 | 7639 | 100% | 0 | 0 |  | 1300 | -306.93 | 993.07 | 0 | 0 | CLO | [10 empty] | 2002 | INV
ONG | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | ASP | YEM | SOL | 45 | TAS | 22 | A | O | I | TCA | 0.2 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 | 2006-07-01 |  |  | 35000 | 0 | 35000 | 228 | 0.6514% | 34772 | 10034 | 25000 | 3150 | 0 | 20.52 | 3129.48 | 903.06 | Project was approved by 45th ExCom in Apr 2005. National expert was recruited to collect information from main users of TCA which will be used to tailor a training course. Training will take place in second quarter of 2006. | [10 empty] | 2005 | INV
ONG | UNIDO | Preparation of a terminal umbrella project in refrigeration (CFC) | Individual | ASP | YEM | REF | 45 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 | 2006-12-01 |  |  | 30000 | 0 | 30000 | 5443 | 18.14% | 24557 | 4521 | 24500 | 2250 | 0 | 408.225 | 1841.775 | 339.075 | PRP project was approved by 45th ExCom in Apr 2005. Project document is under preparation. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Country Programme preparation | Individual | EUR | YUG | SEV | 21 | CPG | 01 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-08-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the refrigeration sector for phasing out ODS at Obod | Individual | EUR | YUG | REF | 23 | PRP | 04 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-07-01 | 1998-03-01 |  | 1999-12-01 | 2000-07-01 | 10000 | -8 | 9992 | 9992 | 100% | 0 | 0 |  | 1300 | -1.04 | 1298.96 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the solvent sector for phasing out ODS at Hemofarm | Individual | EUR | YUG | SOL | 23 | PRP | 05 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-02-01 | 2001-07-01 | 10000 | -2599 | 7401 | 7401 | 100% | 0 | 0 |  | 1300 | -337.87 | 962.13 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | YUG | REF | 24 | PRP | 06 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-06-01 | 2000-03-31 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Creation of Ozone Secretariat | Individual | EUR | YUG | SEV | 25 | INS | 07 | N | T | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2004-10-01 | 2005-09-01 | 151500 | -35 | 151465 | 151465 | 100% | 0 | 0 |  | 19695 | -4.55 | 19690.45 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN.
FIN | UNIDO | Replacement of CFC-113 as solvent for dyaliser cleaning by water and steam at Hemomed Ltd. | Individual | EUR | YUG | SOL | 26 | INV | 08 | A | O | R | CFC | 54.6 | 54.6 |  |  | 1998-11-01 | 1999-02-01 | 1999-06-01 |  | 1998-12-01 | 1999-09-01 | 608729 | 0 | 608729 | 608729 | 100% | 0 | 0 |  | 76960.19 | 0 | 76960.19 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | YUG | HAL | 33 | PRP | 09 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-04-01 | 2003-05-01 | 20000 | -114 | 19886 | 19886 | 100% | 0 | 0 |  | 2600 | -14.82 | 2585.18 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | EUR | YUG | REF | 33 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 10000 | -2337 | 7663 | 7663 | 100% | 0 | 0 |  | 1300 | -303.81 | 996.19 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the flexible foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-04-01 | 15000 | -39 | 14961 | 14961 | 100% | 0 | 0 |  | 1950 | -5.07 | 1944.93 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-09-01 | 15000 | -224 | 14776 | 14776 | 100% | 0 | 0 |  | 1950 | -29.12 | 1920.88 | 0 | 0 | FIN | [10 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at seven enterprises (Jugostroj, Frigozika, Prva Petoletka, EIAD, BS Inzenjering, Soko and Alfa Klima) | Individual | EUR | YUG | REF | 34 | INV | 12 | A | O | I | CFC | 59.6 | 59.6 |  |  | 2001-07-01 | 2001-11-01 | 2004-02-01 |  | 2003-12-01 | 2005-09-01 | 755162 | -20317 | 734845 | 734845 | 100% | 0 | 0 |  | 93067.82 | -2234.87 | 90832.95 | 0 | 0 | Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2001 | INV
ONG | UNIDO | Phase out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim Co. | Individual | EUR | YUG | FOA | 35 | INV | 14 | A | O | I | CFC | 75 | 0 |  |  | 2001-12-01 | 2003-08-01 | 2004-07-01 | 2006-07-01 |  |  | 475728 | 0 | 475728 | 374615 | 78.75% | 101113 | 95220 | 95000 | 61844.64 | 0 | 48699.95 | 13144.69 | 12378.6 | Project is monitored under project implementation delays as reported to the 48th ExCom in Apr 2006. Contract was concluded for preparatory works at project site including some safety related local works. Works are in progress. Equipment installation has not yet been carried out. Project is experiencing some delay since counterpart did not succeed to obtain permissions according to local regulations. In addition, counterpart is in privatization process. | [10 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Prva Iskra-Poliuretani | Individual | EUR | YUG | FOA | 35 | INV | 15 | A | O | I | CFC | 34.4 | 34.4 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-02-01 | 2004-12-01 | 100240 | -328 | 99912 | 99912 | 100% | 0 | 0 |  | 13031.2 | -42.64 | 12988.56 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2001 | INV
COM | UNIDO | Halon bank management programme | Individual | EUR | YUG | HAL | 35 | TAS | 16 | A | O | I | HAL | 370 | 370 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-12-01 | 2005-12-01 | 249700 | 0 | 249700 | 245095 | 98.16% | 4605 | 0 | 1 | 32461 | 0 | 31862.35 | 598.65 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2001 | INV
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | EUR | YUG | REF | 36 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-07-01 | 2004-12-01 | 20000 | -150 | 19850 | 19850 | 100% | 0 | 0 |  | 2600 | -19.5 | 2580.5 | 0 | 0 | Refund was reported to 45th ExCom, Apr 2005. FIN. | [10 empty] | 2002 | INV
COM | UNIDO | Umbrella refrigeration project 2, replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at three enterprises | Individual | EUR | YUG | REF | 37 | INV | 18 | A | O | I | CFC | 10.9 | 10.9 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-10-01 | 2005-12-01 | 150109 | 0 | 150109 | 148005 | 98.6% | 2104 | 0 | 1 | 19514.17 | 0 | 19240.65 | 273.52 | 0 | The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2002 | INV
ONG | UNIDO | Conversion of CFC-12 to HFC-134a in the manufacture of open compressors at Prva Petoletka - Kocna Tehnika Co. | Individual | EUR | YUG | REF | 38 | INV | 19 | A | O | I | CFC | 2 | 0 |  |  | 2002-11-01 | 2003-06-01 | 2005-06-01 | 2006-06-01 |  |  | 223412 | 0 | 223412 | 154480 | 69.15% | 68932 | 46565 | 50000 | 29043.56 | 0 | 20082.4 | 8961.16 | 6053.45 | All tools and moulds for newly designed compressors were delivered to the factory. The project which is delayed by several months due to delayed prototype production, is expected to be completed by June 2006 after having tested the new compressors. | [10 empty] | 2002 | INV
FIN | UNIDO | Assistance to prepare a national CFC phase-out plan (manufacturing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2005-04-01 | 2005-09-01 | 40000 | -7533 | 32467 | 32467 | 100% | 0 | 0 |  | 3000 | -564.975 | 2435.025 | 0 | 0 | Project completed in Apr 2005. Financial completion in Sep 2005. Refund was reported to 47th ExCom, Nov 2005. FIN. | [10 empty] | 2003
ONG | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 23 | A | O | I | CFC | 2 | 0 |  |  | 2004-07-01 | 2004-08-01 | 2005-03-01 | 2006-07-01 |  |  | 474700 | 0 | 474700 | 151158 | 31.84% | 323542 | 15690 | 200000 | 35602.5 | 0 | 11336.85 | 24265.65 | 1176.75 | Research and development on new formulation of medical aerosols with HAP were completed. Certification of new formulation was expected in Nov 2005. Confirmation is still awaited. Technical offer on modernization of existing automatic aerosol line which was submitted to local fire authorities, was not approved in 2006. In addition, UNIDO was informed on 28 Mar 2006 that the company's ownership had been changed and that the new management is considering either to redeploy equipment to another company's entity or to change the replacement technology from HAP to HFC-134a. UNIDO is negotiating these options. Equipment for refrigeration manufacturing sector was delivered to recipient enterprises. Equipment was installed and commissioned during first quarter of 2006. Project Management Unit is being established. Project implementation in foam sector is planned for second quarter of 2006. | [10 empty] | 2004 | INV | 410 | 282.82 |  |  | Yes | Yes | Yes
ONG | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | YUG | SEV | 44 | INS | 25 | N | T | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2006-12-01 | 2007-12-01 |  |  | 131300 | 0 | 131300 | 0 | 0% | 131300 | 0 | 30000 | 9847.5 | 0 | 0 | 9847.5 | 0 | Due to a number of government restructurings, the project document remained unsigned and the institutional setting of the Ozone Unit was not decided/reconfirmed in 2005. However, at the same time, assistance to UNIDO and its individual projects continued through the Ozone Unit. During first quarter of 2006, project document was signed and Ozone Officer was re-designated. | [10 empty] | 2004 | NON-INV
ONG | UNIDO | Project preparation in the fumigants sector (methyl bromide) | Individual | EUR | YUG | FUM | 45 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2007-04-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 15000 | 1875 | 0 | 0 | 1875 | 0 | PRP project was approved by 45th ExCom in Apr 2005. A national consultant is being identified to collect information on the consumption level of methyl bromide in Serbia and Montenegro. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Project preparation for the terminal phase-out in the solvent sector (CTC) | Individual | EUR | YUG | SOL | 45 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 |  | 2006-04-01 | 2007-01-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 10000 | 1125 | 0 | 0 | 1125 | 0 | PRP project was approved by 45th ExCom in Apr 2005. UNIDO, through the National Ozone Unit, has contacted several potential CTC consumers, including the Ministry of Defense. National consultant is being recruited to undertake a detailed survey. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | INV | 28 | A | O | I | cFC | 18 | 0 |  |  | 2005-11-01 |  | 2006-12-01 | 2006-12-01 |  |  | 759000 | 0 | 759000 | 0 | 0% | 759000 | 0 | 300000 | 56925 | 0 | 0 | 56925 | 0 | Second tranche was released by 47th ExCom in Nov 2005. Trainers at vocational schools will be trained and vocational schools will be strengthened. Process to establish Code of Practice for service technicians will be initiated. | [10 empty] | 2005 | INV | 392 | not available |  |  | not available | No | No
FIN | UNIDO | Preparation of training and certification programmes for refrigeration technicians and preparation of investment projects for the refrigeration sector | Individual | AFR | ZAM | REF | 15 | TAS | 03 | A | O | I |  | 0 | 17.7 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-12-01 | 1999-08-01 | 82100 | -5746 | 76354 | 76354 | 100% | 0 | 0 |  | 10673 | -746.98 | 9926.02 | 0 | 0 | FIN
CLO | UNIDO | Preparation of a demonstration project (tobacco, flowers) | Individual | AFR | ZAM | FUM | 27 | PRP | 09 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
ONG | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | ZAM | SOL | 45 | TAS | 16 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 | 2006-06-01 |  |  | 40000 | 0 | 40000 | 1808 | 4.52% | 38192 | 1759 | 15000 | 3600 | 0 | 162.72 | 3437.28 | 158.31 | Project was approved by 45th ExCom in Apr 2005. National expert was recruited to collect information from main users of CTC/TCA which will be used to tailor a training course. Training and awareness workshop is expected to take place in second quarter of 2006. | [10 empty] | 2005 | NON-INV
FIN | UNIDO | Preparation of investment projects in the refrigeration, air conditioning and recovery/recycling | Individual | AFR | ZIM | SEV | 14 | PRP | 03 | A | O | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-02-01 | 1995-03-01 |  | 1997-11-01 | 1999-08-01 | 40000 | -526 | 39474 | 39474 | 100% | 0 | 0 |  | 5200 | -68.38 | 5131.62 | 0 | 0 | FIN
FIN | UNIDO | CFC refrigerant recovery and reclaim project | RMP | AFR | ZIM | REF | 17 | TAS | 04 | A | O | I | CFC | 47 | 47 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-08-01 | 312300 | -638 | 311662 | 311662 | 100% | 0 | 0 |  | 40599 | -82.94 | 40516.06 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ZIM | FUM | 22 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -636 | 7364 | 7364 | 100% | 0 | 0 |  | 1040 | -82.68 | 957.32 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Demonstration project - Two alternatives to the use of methyl bromide in the production of tobacco drought-resistant seedlings: non-soil cultivation and low-dose chemicals | Individual | AFR | ZIM | FUM | 23 | DEM | 13 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-11-01 |  | 2000-12-01 | 2002-09-01 | 370700 | -17962 | 352738 | 352738 | 100% | 0 | 0 |  | 48191 | -2335.06 | 45855.94 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector (cut flowers) | Individual | AFR | ZIM | FUM | 30 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -617 | 29383 | 29383 | 100% | 0 | 0 |  | 3900 | -80.21 | 3819.79 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | ZIM | FUM | 31 | INV | 21 | A | O | I | MBR | 132 | 132 |  |  | 2000-07-01 | 2001-03-01 | 2004-08-01 | 2006-06-01 |  |  | 904200 | 0 | 904200 | 854432 | 94.5% | 49768 | 24000 | 20000 | 109462 | 0 | 103987.52 | 5474.48 | 2640 | Continuous assistance was provided to flower growers and the remaining 21.4 ODP tonnes were phased out. Project is expected to be completed by June 2006.
FIN | UNIDO | Project preparation in the fumigants (tobacco) sector | Individual | AFR | ZIM | FUM | 33 | PRP | 22 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2002-12-01 | 2004-03-01 | 30000 | -647 | 29353 | 29353 | 100% | 0 | 0 |  | 3900 | -84.11 | 3815.89 | 0 | 0 | FIN | [10 empty] | 2001 | INV
COM | UNIDO | Project preparation in the fumigants (methyl bromide) sector (phase out in tobacco seedling) | Individual | AFR | ZIM | FUM | 45 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2005-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 14378 | 95.85% | 622 | 0 | 1 | 1125 | 0 | 1078.35 | 46.65 | 0 | Project completed in Dec 2005. The project was financially completed internally at UNIDO. Funds have been returned to the 48th ExCom. | [10 empty] | 2005 | NON-INV
ONG | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (first tranche) | Multi-Year | AFR | ZIM | FUM | 47 | INV | 32 | A | O | I | MBR | 50 | 0 |  |  | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 1862486 | 0 | 1862486 | 0 | 0% | 1862486 | 0 | 500000 | 139686.45 | 0 | 0 | 139686.45 | 0 | First tranche was released by 47th ExCom in Nov 2005. A plan of action was prepared in 2006 based on which most of the equipment will be purchased and training to farmers will be carried out. Bidding of equipment started. Sub-contract for training to farmers is being requested. | [10 empty] | 2005 | INV | 184.2 | 184.2 |  |  | not available | n.a. | n.a.
FIN | USA | Project preparation/technical assistance |  | LAC | ARG | SEV | 13 | PRP | 08 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | MAC servicing demonstration |  | LAC | ARG | REF | 16 | DEM | 22 | A | O | I |  |  | 20 |  |  | 1995-03-01 | 1995-09-01 | 1995-12-01 |  | 1997-06-01 | 1998-06-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1995 | 1997-06-01
FIN | USA | Southeast Asia halon 1211 training workshop in Japan |  | ASP | ASP | HAL | 08 | TRA | 07 | A | O | I | [5 empty] | 1992-10-01 |  | 1992-10-01 |  | 1992-10-01 | 1992-10-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Demonstration MAC and refrigerated transport |  | LAC | CHI | REF | 19 | DEM | 15 | A | O | I |  | 10 | 10 |  |  | 1996-05-01 | 1996-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-10-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1995 | 1997-12-01
FIN | USA | MAC emissions reduction demonstration program |  | LAC | COL | REF | 15 | DEM | 13 | A | O | I |  |  | 12 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1999-06-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report will be submitted in May 2000. Project will be classified as financially complete at that time. |  | 1994
FIN | USA | MAC and refrigerated transport demonstration project |  | LAC | COS | REF | 19 | DEM | 09 | A | O | I |  | 10 |  |  |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 2000-05-01 | 2000-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | [5 empty] | Training workshop and equipment delivery are planned for May 2000. |  | 1995 | 1997-12-01
FIN | USA | Support for the FESCAST international conference |  | ASP | CPR | SEV | 08 | TRA | 25 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1994-04-01 | 87000 | 96000 | 183000 | 183000 | 100% | 0 |  | 0 | [5 empty] | Completed. Adjustment of US $96,000 credited against 1993 contributions (11th Meeting). |  | 1992/1993
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1a: model prototype development and testing) |  | ASP | CPR | REF | 10 | TAS | 33 | A | O | I | [5 empty] | 1993-06-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 396110 | 0 | 396110 | 396110 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1993
FIN | USA | Halon management resource manual |  | ASP | CPR | HAL | 11 | TAS | 53 | A | O | I | [5 empty] | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1993
FIN | USA | Halon 1211 recovery/recharge training workshops |  | ASP | CPR | HAL | 11 | TRA | 57 | A | O | I | [5 empty] | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 271000 | 0 | 271000 | 271000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1993
FIN | USA | Deployment of halon 1211 recovery/recharge machines |  | ASP | CPR | HAL | 12 | INV | 59 | A | O | I |  | 200 | 231 |  |  | 1994-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1996-06-01 | 735000 | 72000 | 807000 | 807000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Project Preparation |  | ASP | CPR | HAL | 13 | PRP | 80 | A | O | I | [5 empty] | 1994-07-01 |  | 1996-01-01 |  | 1997-12-01 | 1998-04-01 | 200000 | -68517 | 131483 | 131483 | 100% | 0 |  | 0 | [5 empty] | Completed. No further activities foreseen on this project with the approval of China's Halon Sector Strategy (23rd meeting). |  | 1994 | 1997-12-01
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) |  | ASP | CPR | REF | 16 | INV | 116 | N | O | I |  | 29 |  |  |  | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 2000-05-01 | 2000-05-01 | 1643865 | 0 | 1643865 | 1643865 | 100% | 0 |  | 0 | [5 empty] | Conversion of line to produce cyclopentane-152a/22 refrigerators completed, certified Aug96; CFCs eliminated. Final funding to follow verification of old equipment destruction, review of receipts, final safety certification, and initial production. |  | 1995 | 1997-07-01 |  | 1999-12-01
FIN | USA | MAC servicing demonstration |  | ASP | CPR | REF | 16 | DEM | 117 | A | O | I |  | 5-10 | 11.4 |  |  | 1995-03-01 | 1995-04-01 | 1995-03-01 |  | 1996-03-01 | 1996-03-01 | 172500 | -6667 | 165833 | 165833 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report submitted October 1999. |  | 1995
FIN | USA | Refrigeration management demonstration project preparation |  | ASP | CPR | REF | 16 | PRP | 118 | A | O | I | [5 empty] | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1995
FIN | USA | Halon leak reduction demonstration |  | ASP | CPR | HAL | 16 | DEM | 121 | A | O | I |  |  | 74 |  |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-12-01 | 1998-06-01 | 90437 | 0 | 90437 | 90437 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1995
FIN | USA | Demonstration project (refrigeration in large food stores) |  | ASP | CPR | REF | 17 | DEM | 135 | A | O | I | [5 empty] | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1998-01-01 | 1998-12-01 | 132000 | 26400 | 158400 | 158400 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report submitted October 1999. |  | 1995 | 1997-06-01
FIN | USA | Refrigeration MAC servicing |  | ASP | CPR | REF | 19 | DEM | 163 | A | O | I | [5 empty] | 1996-05-01 | 1996-07-01 | 1999-05-01 |  | 1998-11-01 | 1998-12-01 | 385000 | 77600 | 462600 | 462600 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report will be submitted May 2000. |  | 1995 | 1997-12-01
ONG | USA | CFCs, CTC and halon accelerated phase-out plan | Multi-Year | ASP | CPR | PRO | 44 | INV | 425 | A | O | I |  | 0 |  | 0 |  | 2004-12-01 |  | 2005-12-01 |  |  |  | 5000000 | 0 | 5000000 |  | 0% | 5000000 |  |  | 375000 | 0 |  | 375000
ONG | USA | CFCs, CTC and halon accelerated phase-out-plan | Multi-Year | ASP | CPR | PRO | 47 | INV | 439 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 | 2007-12-01 |  |  | 5000000 | 0 | 5000000 |  | 0% | 5000000 |  |  | 375000 | 0 |  | 375000
FIN | USA | Project preparation in commercial refrigeration |  | LAC | DOM | REF | 17 | PRP | 02 | A | O | I | [5 empty] | 1995-07-01 |  | 1996-01-01 |  | 1995-09-01 | 1995-09-01 | 19000 | 0 | 19000 | 19000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1995
FIN | USA | Demonstration project in MACs |  | LAC | DOM | REF | 17 | DEM | 03 | A | O | I |  |  | 10 |  |  | 1995-07-01 | 1995-09-01 | 1996-12-01 |  | 1997-12-01 | 1999-10-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | USA | Demonstration project in commercial refrigeration (food storage, distribution and retailing) |  | LAC | DOM | REF | 18 | DEM | 05 | A | O | I |  |  | 7 |  |  | 1995-11-01 | 1995-11-01 | 1996-12-01 |  | 1998-02-01 | 1999-10-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | USA | Technical assistance in aerosol project preparation |  | LAC | ECU | ARS | 08 | PRP | 07 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-04-01 |  | 1993-04-01 | 1993-04-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Feasibility study for reduction of CFC-11 in rigid polyurethane foam insulation for refrigerators using water/CO2 formulation |  | LAC | ECU | FOA | 08 | PRP | 08 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 41000 | 50000 | 91000 | 91000 | 100% | 0 |  | 0 | [5 empty] | Completed. Adjustment of US $50,000 credited against 1993 contributions (11th Meeting). |  | 1992/1993
FIN | USA | Support for country program preparation |  | LAC | ECU | SEV | 07 | CPG | 09 | A | O | I | [5 empty] | 1992-06-01 |  | 1993-09-01 |  | 1993-09-01 | 1993-09-01 | 50000 | 6000 | 56000 | 56000 | 100% | 0 |  | 0 | [5 empty] | Completed. Adjustment of US $6,000 credited against 1993 contributions (11th Meeting). |  | 1991/1992
FIN | USA | Assistance in implementation of country program |  | LAC | ECU | SEV | 11 | CPG | 14 | A | O | I | [5 empty] | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1993
FIN | USA | Halon 1211 management |  | LAC | ECU | HAL | 13 | TAS | 16 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Regional workshops in halon 1211 training |  | GLO | GLO | HAL | 08 | TRA | 30 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 429000 | 0 | 429000 | 429000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Refrigeration: MAC and refrigerated transport |  | LAC | GUA | REF | 19 | DEM | 10 | A | O | I |  | 10 |  |  |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 1998-08-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report will be submitted in May 2000. |  | 1995 | 1997-12-01
FIN | USA | Demonstration project in MAC |  | LAC | JAM | REF | 23 | DEM | 07 | A | O | I |  | 9.6 |  |  |  | 1997-11-01 | 1998-02-01 | 1998-12-01 |  | 1999-06-01 | 2000-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | [5 empty] | Equipment delivered and training conducted in March 99, with follow-up mission in June 1999. Final report will be submitted June 2000. |  | 1997
FIN | USA | Followup to regional halon 1211 workshop |  | LAC | LAC | HAL | 08 | TRA | 06 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Project preparation for low-consuming countries |  | LAC | LAC | REF | 13 | PRP | 09 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Project preparation: Central America/Caribbean |  | LAC | LAC | REF | 19 | PRP | 16 | A | O | I | [5 empty] | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1998-02-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | [5 empty] | Final report submitted in June 1998. |  | 1995 | 1997-05-01
FIN | USA | Regional Central America MAC servicing demonstration project |  | LAC | LAC | REF | 24 | DEM | 27 | A | O | I | [5 empty] | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-06-01 | 2000-07-01 | 569000 |  | 569000 | 569000 | 100% | 0 |  | 0 | [5 empty] | Training and equipment were provided in El Salvador, Honduras, Nicaragua and Panama in April - May 1999. Final report will be submitted in June 2000.
FIN | USA | Conference on the elimination of ozone-depleting solvents |  | ASP | MAL | SOL | 11 | TRA | 14 | A | O | I | [5 empty] | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1993
FIN | USA | Project preparation in the halon sector |  | ASP | MAL | HAL | 15 | PRP | 54 | A | O | I | [5 empty] | 1994-12-01 |  | 1995-06-01 |  | 1995-06-01 | 1996-06-01 | 45000 | -28116 | 16884 | 16884 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Institutional Strengthening |  | LAC | MEX | SEV | 07 | INS | 16 | A | T | I | [5 empty] | 1992-06-01 |  | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 285000 | 65000 | 350000 | 350000 | 100% | 0 |  | 0 | [5 empty] | Completed. US $65,000 against 1994 contributions (15th meeting) |  | 1991/1994
FIN | USA | Support for country program preparation and development of project proposals |  | LAC | MEX | SEV | 07 | PRP | 17 | A | O | I | [5 empty] | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-06-01 | 145000 | 136000 | 281000 | 281000 | 100% | 0 |  | 0 | [5 empty] | Completed. Adjustment of US $136,000 credited against 1993 contributions (11th Meeting). |  | 1991/1993
FIN | USA | Assistance to country program and investment projects preparation |  | LAC | MEX | SEV | 08 | CPG | 18 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Chiller hands-on training |  | LAC | MEX | REF | 08 | TRA | 19 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 81000 | 259000 | 340000 | 340000 | 100% | 0 |  | 0 | [5 empty] | Completed. Adjustment of US $259,000 credited against 1993 contributions (11th Meeting). |  | 1992/1993
FIN | USA | Mexican solvents program to reduce CFC-113 and methyl chloroform |  | LAC | MEX | SOL | 08 | TRA | 20 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 360000 | 138000 | 498000 | 498000 | 100% | 0 |  | 0 | [5 empty] | Completed. Adjustment of US $138,000 credited against 1993 contributions (11th Meeting). |  | 1992/1993
FIN | USA | Cancun chiller workshop |  | LAC | MEX | REF | 13 | TRA | 25 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Pilot sectoral study and action plan in commercial refrigeration |  | LAC | MEX | REF | 13 | TAS | 26 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 410000 | -139742 | 270258 | 270258 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Demonstration project in MAC |  | LAC | MEX | REF | 13 | DEM | 27 | A | O | I |  | 25 |  |  |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Project preparation: solvents |  | LAC | MEX | SOL | 13 | PRP | 28 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 450000 | -119143 | 330857 | 330857 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Technical assistance in halon 1211 management |  | LAC | PAN | HAL | 13 | TAS | 04 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 120000 | -42445 | 77555 | 77555 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | MACs servicing demonstration project |  | ASP | PHI | REF | 18 | DEM | 41 | A | O | I |  | 11 |  |  |  | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1999-09-01 | 1999-09-01 | 285500 | 0 | 285500 | 285500 | 100% | 0 |  | 0 | [5 empty] | UNDP is working with the Government of the Philippines to complete the project. |  | 1995 | 1997-05-01
FIN | USA | Followup activities of the USA/Thailand/Japan conference on solvent conservation, containment and alternatives |  | ASP | THA | SOL | 08 | TAS | 08 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 203000 | -67000 | 136000 | 136000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Demonstration project in MAC |  | LAC | TRI | REF | 23 | DEM | 08 | A | O | I |  | 10 |  |  |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1999-05-01 | 2000-05-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 |  | 0 | [5 empty] | Completed. Final report will be submitted May 2000. |  | 1997
FIN | USA | Demonstration project in MAC |  | EUR | TUR | REF | 23 | DEM | 32 | A | O | I |  | 12 |  |  |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 2000-07-01 | 205000 | 0 | 205000 | 205000 | 100% | 0 |  | 0 | [5 empty] | Training workshop and equipment delivery planned for May 99. |  | 1997
FIN | USA | Technical assistance in halon 1211 management |  | LAC | URU | HAL | 13 | TAS | 07 | A | O | I | [5 empty] | 1994-07-01 |  | 1994-09-01 |  | 1994-09-01 | 1994-09-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Training in the halon sector |  | LAC | URU | HAL | 15 | TRA | 13 | A | O | I | [5 empty] | 1994-12-01 | 1994-12-01 | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Technical assistance and demonstration project in CFC recycling in MAC |  | LAC | VEN | REF | 08 | DEM | 06 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-10-01 |  | 1995-07-01 | 1998-09-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Assistance in country program preparation |  | LAC | VEN | SEV | 08 | CPG | 07 | A | O | I | [5 empty] | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1992
FIN | USA | Technical assistance in halon 1211 management |  | LAC | VEN | HAL | 13 | DEM | 27 | A | O | I |  | 2 |  |  |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 31000 | 3000 | 34000 | 34000 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Demonstration project in MAC |  | LAC | VEN | REF | 13 | DEM | 28 | A | O | I | [5 empty] | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1998-09-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 |  | 0 | [5 empty] | Project completed. |  | 1994
FIN | USA | Training in all ODS sectors in Venezuelan military |  | LAC | VEN | SEV | 15 | TRA | 29 | A | O | I | [5 empty] | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 3500 | 43500 | 43500 | 100% | 0 |  | 0 | [5 empty] | Completed. |  | 1994
FIN | USA | Demonstration project in the refrigeration sector: MAC |  | LAC | VEN | REF | 15 | DEM | 30 | A | O | I | [5 empty] | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1998-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 |  | 0 | [5 empty] | Project completed. |  | 1994
FIN | USA | MACs servicing demonstration project |  | ASP | VIE | REF | 20 | DEM | 15 | A | O | I | [5 empty] | 1996-10-01 | 1997-03-01 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 300000 | -159091 | 140909 | 140909 | 100% | 0 |  | 0 | [5 empty] | Terminated. |  | 1996 | 1998-12-01
Note on A3803: Modified from ONG according to remarks
Note on A3821: Modified from ONG according to remarks
Note on A3920: Modified from COM according to remark "project completed in 2006"
Note on V3920: Moved from date completed since the project was completed in 2006
Note on X1351: Still being confirmed with the cooperating agency.
Note on X1352: Still being confirmed with the cooperating agency.
Note on AL1365: Still being confirmed with the cooperating agency.
Note on AL1370: Still being confirmed with the cooperating agency.
Note on AL1371: Still being confirmed with the cooperating agency.
Note on AL1372: Still being confirmed with the cooperating agency.
Note on AL1373: Still being confirmed with the cooperating agency.
Note on AY1362: Still being confirmed with the cooperating agency.
Note on AY1365: Still being confirmed with the cooperating agency.
Note on AZ1362: Still being confirmed with the cooperating agency.
Note on AZ1365: Still being confirmed with the cooperating agency.
Note on BA1362: Still being confirmed with the cooperating agency.
Note on BA1365: Still being confirmed with the cooperating agency.
Note on BB1362: Still being confirmed with the cooperating agency.
Note on BB1365: Still being confirmed with the cooperating agency.
Note on BC1362: Still being confirmed with the cooperating agency.
Note on BC1365: Still being confirmed with the cooperating agency.
Note on BD1362: Still being confirmed with the cooperating agency.
Note on BD1365: Still being confirmed with the cooperating agency.
Note on BE1362: Still being confirmed with the cooperating agency.
Note on BE1365: Still being confirmed with the cooperating agency.