## Investment
Code | Agency | Type | Sector | Project Title | Lessons Learnt | Lessons Learnt (Continued) | Lessons Learnt (Continued) | Lessons Learnt (Continued) | Lessons Learnt (Continued) | Lessons Learnt (Continued)
ARG/FOA/32/INV/113 | UNDP | INV | FOA | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constructora Vimac; Gaspar Adragna; Placido Sandova... | Complex group projects should reflect a longer timeframe than individual projects due to the logistics of completing all actions at all enterprises included in the project. Most actions at most companies may be completed in a timely manner, but delays at one enterprise can affect the timeliness of the entire project.
ARG/FOA/34/INV/122 | UNDP | INV | FOA | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 4 foam manufacturers (Artestamp, Pasissan, Forever, Termica) | Complex group projects should reflect a longer timeframe than individual projects due to the logistics of completing all actions at all enterprises included in the project. Most actions at most companies may be completed in a timely manner, but delays at one enterprise can affect the timeliness of the entire project.
ARG/REF/15/INV/19 | IBRD | INV | REF | Helametal S.A. & Helemetal Catamarca. Conversion of a domestic refrigeration plant. replacement of CFC-11 used as blowing agent with cyclopentane and CFC-12 used as refrigerant with HFC-134a | The company is currently producing refrigeration units without CFC and the quality of its products has improved. Nonetheless, due to economic and political conditions in the country, the company has posted lower production figures than originally expected.
BAH/REF/29/INV/09 | UNDP | INV | REF | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | The costs for trials and site preparation need to be realistically estimated and the eligible part funded accordingly.
BAH/REF/29/INV/10 | UNDP | INV | REF | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | The scheduling of project activities needs full involvement of the beneficiary enterprise in order to prevent delays.
BHE/FOA/39/INV/15 | UNIDO | INV | FOA | Phase-out of CFC-11 by conversion to n-pentane in the manufacture of rigid foam products for insulating purposes at Stirokart Co. | Good cooperation between counterpart, supplier and implementing agency was basic for the success implementation of the project.
BHE/FUM/41/INV/17 | UNIDO | INV | FUM | Phase-out of methyl bromide in tobacco seedling, vegetables and flower production sector | Good cooperation between enterprises, growers, National Ozone Unit of BiH and implementing agency was basic for the success implementation of the project. Involvement of scientific institutions as a Faculty of Agriculture in Sarajevo and Tobacco Institute from Zagreb was essential for successful training, which were underway to transfer the new technologies to growers, cooperatives and local enterprises, and also for the implementation of the project without delays.
BRA/FOA/36/INV/244 | UNDP | INV | FOA | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Decorfrio | During the project planning and implementation stage, it is vital to understand any company plans that may impact project implementation. Any such plans must be taken into consideration and planned for in the implementation plans. In this case, a move to a new facility introduced major delays in project implementation.
CHI/STE/35/INV/151 | UNDP | INV | STE | Terminal conversion of ethylene oxide/CFC-12 mixtures to alternative non-ozone depleting technologies in 26 hospitals | (1) The confirmation of a technical committee was a key cornerstone, since it allowed all interested parties to agree on a common technical solution for the whole sector. This participatory approach developed a strong commitment and ownership of all participants, and this was critical for the success of the project. (2) The project also helped in the development of a market that was very static for a long time and could refresh this sector with new technologies and procedures that improved the quality of the services brought to community.
COL/FOA/29/INV/39 | IBRD | INV | FOA | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises. | There were valuable experiences learnt, all related with the implementation of a conversion project and all its life cycle. It is very important to follow up very closely to all the beneficiary companies, especially the small ones, to avoid delays in overall project implementation. Gathering information from so many beneficiary companies (i.e. consumption figures, costs, dates, etc) is complex. It is in the interest of project implementation to develop simplified templates for data collection and to start the data gathering process as early as possible.
COL/REF/38/INV/57 | IBRD | INV | REF | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 Colombian enterprises | (1) It is very important to follow up very closely all the beneficiary companies, especially the small ones. The smaller the company, the greater the follow up and assistance required. Gathering information from multiple beneficiary companies (i.e. consumption figures, costs, dates, etc) is complex. It is in the interest of project implementation to develop simplified templates for data collection and to start the data gathering process as early as possible. (2) Given that the cost of equipment provided under this project was relatively low, smaller companies were more interested in receiving IOC than ICC.
CPR/FOA/24/INV/245 | UNDP | INV | FOA | Jixi City Thermal Power Company - Conversion to Cyclopentane in Manufacture of Heating Pipes | Enterprise must have a pool of technicians to understand and communicate effectively during implementation. It is critical to the success of the project.
CPR/FOA/25/INV/247 | UNDP | INV | FOA | Conversion to LCD technology in the manufacture of flexible (slabstock) polyurethane foam at Jinling Petrochemical Plastic Factory | Adequate technical exchange required among parties to identify and resolve problems
CPR/FOA/26/INV/264 | UNDP | INV | FOA | Conversion of Refrigeration Manufacture in Zhenjiang Radio Factory from CFC-11 to N-pentane Foam Blowing Agent in the Production of PU Insulation Panels | Timely confirmation and availability of equipment supplier and enterprise personnel to undertake early agreement for timely installation and resolution of issues will improve project implementation.
CPR/FOA/28/INV/294 | IBRD | INV | FOA | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiangsu Taizhou Commercial Machinery General Factory | Ownership reform takes a long time, not only at Taizhou but also at other enterprises. Implementation of such projects requires better planning.
CPR/FOA/29/INV/328 | UNDP | INV | FOA | Phaseout of CFC-11 by conversion to Water Blown Technology in the Manufacture of Integral Skin Foam at Guangzhou Haohua Automobile Carpet Plant | The lessons learned for future action is as follows: (1) Getting supervision and technical assistance in time is very important for successful project implementation. (2) Coordination and management from the government and DIA is very necessary for project implementation. (3) The situation that DIA and the procurement agent is the same organization is good for project implementation. (d) Technical strength, operation and management scale and active cooperation and understanding of the beneficiary enterprise is the foundation for successful implementation of the project.
CPR/FOA/29/INV/333 | UNDP | INV | FOA | Phaseout of CFC-11 by conversion to Water Blown Technology in the Manufacture of Flexible Foam at Jizhou Beinei Automobile Cushion Plant | The lessons learned for future action is as follows: (1) Getting supervision and technical assistance in time is very important for effective project implementation. (2) Coordination and management from the government and DIA is very necessary for project implementation. (3) The situation that DIA and the procurement agent is the same organization is good for project implementation. (4) Technical strength, operation and management scale and active cooperation and understanding of the beneficiary enterprise are the foundation for successful implementation of the project.
CPR/REF/23/INV/222 | UNIDO | INV | REF | Phasing out ODS at the refrigerator plant of Bole Electric Appliances Group | (1) The initial success of the project was the result of the good cooperation between the Counterpart, SEPA and UNIDO. The Counterpart closely cooperated with UNIDO during the project formulation phase. The selection of alternative chemicals and technologies, suppliers and each equipment item was carried out with full involvement and in agreement of the Counterpart. This ensured proper sense of ownership on the part of Bole. UNIDO experts regularly visited the project site to provide technical advice, monitor the progress, resolve disputes between the suppliers and the Counterpart, and inspect the quality of installation and safety. SEPA on behalf of the Government was involved at all critical stages. | (2) Nevertheless, there were some gaps in the information flow between the parties, especially regarding the financial situation of the Plant and later on the relocation of the main plant. Proper and continuous information flow should be maintained, however the sudden financial collapse was not foreseen and could not have been prevented. (3) It was important that the enterprise and the local authorities did not give up in time of difficulties. They tried their best to find additional funds and new cooperation partner to finalize the project and also create a promising future for the enterprise.
CPR/REF/28/INV/298 | IBRD | INV | REF | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | (1) Enterprise’s management support of the implementation are crucial to smooth implementation. (2) Enterprise’s counterpart funding should be solid and on time. (3) The imported compressor introduced from HKT is relatively outdated and not much welcome in Chinese market. The enterprise had to renovate the imported technology based on its experience and market demand. (4) The operators of those imported equipment received good training during the implementation, they became popular in the local labor market. How to retain these trained operators for a long time in the beneficiary enterprise is a new challenge for WCMF. WCMF is now planning to train more operators of machining centers in coming years.
CRO/FUM/35/INV/14 | UNIDO | INV | FUM | Phase-out of methyl bromide in tobacco seedlings | Good cooperation between enterprises, growers, National Ozone Unit of Croatia and implementing agency was basic for the success implementation of the project. Involvement of scientific institutions as a Faculty of Agriculture and Forestry of Republic Croatia (Institut for Plant Protection) and Tobacco Institute from Zagreb was essential for successful training, which were underway to transfer the new technologies to growers, cooperatives and local enterprises, and also for the implementation of the project without delays.
CUB/ARS/34/INV/18 | UNDP | INV | ARS | Phase-out of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | N/A
DRC/FOA/35/INV/06 | UNDP | INV | FOA | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Complast SPRL | Improved coordination with Customs is required to assure timely clearing of internationally procured equipment.
DRC/FOA/35/INV/07 | UNDP | INV | FOA | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at M.K. SPRL | Improved coordination with Customs is required to assure timely clearing of internationally procured equipment.
DRC/FOA/37/INV/10 | UNDP | INV | FOA | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Bek SPRL by conversion to methylene chloride | By planning in advance for the application of the eligible funds toward a larger-scale conversion project (replacement of boxfoam production by continuous production equipment), the project was able to be implemented and completed basically within the allotted project timeframe. This was a major improvement over other such projects where the technology upgrade was not planned or considered prior to project approval.
DRC/FOA/37/INV/11 | UNDP | INV | FOA | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Ekanawe SPRL by conversion to methylene chloride | It is helpful to review the enterprise’s operations completely to determine whether operational safety can be enhanced within the eligible project budget. In this case, the enterprise was able to install a semi-automatic boxfoam unit within the budget allotted for retrofit of the manual unit, which contributes to improved overall employee safety.
DRC/FOA/37/INV/12 | UNDP | INV | FOA | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Sokamo SPRL by conversion to methylene chloride | By properly planning ahead for the replacement of the baseline boxfoam unit by a semi-automatic unit, implementation delays were avoided and the project was completed within budget and on-time. Such advance planning is essential for successful project completion when the project scope exceeds the eligible funded activities.
EGY/FOA/22/INV/64 | UNDP | INV | FOA | Phase-out of the remaining ODS consumption in the foam sector (11 enterprises) | (1) This was one of the earliest projects approved that covered a sector-wide phaseout in a country. As such, it served as a test case for the funding flexibility clause, and the logistics of making changes to the participant list during implementation. There was some confusion as to whether substituted enterprises had to get MLF ExCom approval before being included in the project. Through discussions and negotiation, the process was developed whereby substitution of cancelled enterprises was possible by qualified enterprises, with these decisions at the government level. The experiences of this project helped to pave the way for future sector phaseout plans, which were largely implemented during the period of country-driven projects, rather than agency-driven projects. This project helped to demonstrate how these types of plans can and should work, with the country taking ownership of the process and being allowed greater flexibility in disbursement of the funding. | By allowing the country this control, it enhanced the involvement and understanding of the government in the entire process. (2) This substitution process created additional challenges in the timeliness of project completion however, as it was unclear how much funding would remain available for coverage of later-applying participants. In this case, approval of the final two participants was delayed until financial completion f the other projects, resulting in significant delays in completion of the overall project. These activities point out the need for a targeted and aggressive awareness campaign early in the implementation stage of a sector phaseout plan, with an established mechanism for approval and management of later-identified participant enterprises.
IDS/ARS/22/INV/61 | IBRD | INV | ARS | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | Under-funding projects leads to delays. Regional financial conditions can result in delays, and affect the implementation timetable. Implementing agency paperwork - in this case contractual arrangements between WB and GOI - can result in delays.
IDS/ARS/44/INV/167 | UNDP | INV | ARS | National strategy for phasing out the use of CFC in the aerosol: conversion from CFC to hydrocarbon aerosol propellants at P.T Yulia | Training on safety issues to enterprise is important factor in the implementation of the project.
IDS/FOA/35/INV/129 | IBRD | INV | FOA | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | NA
IDS/FOA/35/INV/130 | IBRD | INV | FOA | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (house ware products) at PT Maspion Plastic and Metal Industry | The project and its implementation confirmed the approach and the use of experienced local consultant.
IND/ARS/28/INV/221 | UNDP | INV | ARS | Phase-out of CFC by substituting HAPs at Syncaps | (1) Doing projects with basically insolvent companies will lead to long delays. (2) Because of safety factors, aerosol projects were not subject to a "one size fits all" or "cookie cutter" solutions. Despite spending much more time preparing projects than in other sectors, mistakes were possible. In the case of Syncaps, the owner was an excellent expositor, and convinced the consultants that the company had adequate financial capabilities and technical personnel. The reality is that the enterprise was almost insolvent, and had no technical personnel at all.
IND/REF/22/INV/124 | IBRD | INV | REF | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | Don’t delay, ask for a checklist & complete the action.
IND/REF/22/INV/126 | IBRD | INV | REF | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HFC-134a refrigerant at Voltas Ltd. | (1) The enterprise reported that for successful implementation of the project, a high degree of coordination among the equipment suppliers, their manufacturers, and their commissioning personnel, was required from timely inspection of the manufacturing of new equipment, transportation, availability of technicians for equipment installation and commissioning and until the operations of new equipment and new processes were stabilized. (2) The Warora unit indicated that there were some problems with the new software and chemical processes during the initial start-up. Some time was lost in fully stabilizing the process. | (3) The Hyderabad unit reported that it faced difficulty in stabilizing the operations using cyclopentane technology and therefore, there was a delay in decommissioning its existing CFC foaming lines. Technical experts had to revisit the plant for rectification of the foaming equipment and stabilization of the operations. The enterprises reported that to survive in a competitive market like one in India it is essential that these types of problems are minimized.
IRA/FOA/34/INV/114 | Germany | INV | FOA | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Iranogharb | The use of the LCD technology for the production of mattresses and furniture using high pressure dispensing equipment is a perfectly viable proposition. However, the technology requires a change of habits and methods from the personnel during the production process. Some personnel had a low level of education and therefore needed extra training.
IRA/FOA/35/INV/116 | Germany | INV | FOA | FILLIN "project_title"Conversion of the use of CFC to LCD in the manufacture of flexible foam at Esfanj Jajerood foam company | The use of the LCD technology for the production of mattresses and furniture with flexible PUF molding, using high pressure dispensing equipment, was a perfectly viable proposition in this company.
IRA/FOA/37/INV/150 | Germany | INV | FOA | Conversion from CFC-11 to pentane technology in the manufacture of integral skin PU foam at Jahad Tahghihat Group | The use of the PB technology for the production of components for the automobile sector using high pressure dispensing equipment is perfectly viable. This is especially true in case of Jahad Tahghighat where the production is destined for international car manufacturers which require a higher product quality.
IRA/FOA/37/INV/151 | Germany | INV | FOA | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Abre Baspar foam company | The use of the LCD technology for the production of mattresses and furniture using high pressure dispensing equipment is a perfectly viable proposition. However, it requires a change of habits and methods in the production. The educational level of personnel is low and therefore, any change needs more training than is eligible under the fund.
IRA/FOA/37/INV/153 | Germany | INV | FOA | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Nikou Esfandj | The use of the WB technology for the production of flexible moulded foam using high pressure dispensing equipment is a perfectly viable proposition.
IRA/FOA/37/INV/156 | Germany | INV | FOA | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Phira Khodro | Phira Khodro is one of the few projects with very good communication between the owner and the implementing agency
IRA/FUM/29/INV/57 | UNIDO | INV | FUM | Phasing out of the important non critical, non essential use of methyl bromide for post-harvest treatment | No information available.
IRA/REF/35/INV/133 | UNDP | INV | REF | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Ghotb Jonoub Industrial Group | In cases where the beneficiary enterprise manufactures a range of end-product models with different properties and applications, extensive trials are needed to establish performance of equipment for each formulation separately, therefore leading to higher costs of trials. Also, there are costs incurred for preparing the site, such as utility connections, air dryers, etc. The funding of trial and site preparation costs should take these elements into consideration adequately.
JOR/ARS/20/INV/26 | IBRD | INV | ARS | Jordan Industrial Petrochemical | The issue of savings in the aerosol sector should be re-evaluated.
LIB/FOA/32/INV/06 | UNDP | INV | FOA | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Garabouli Unit | It is essential to thoroughly discuss all technology options with an enterprise prior to project approval. It must be made clear that changes in technology during project implementation are not to be taken lightly, and must have sound reasoning for the change. Contemplation of technology changes can lead to implementation delays; therefore, thorough discussion of technology options should be ensured during project development.
LIB/FOA/32/INV/07 | UNDP | INV | FOA | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Electrical Household Appliance-Tajura by conversion to a combination of water and HCFC-141b based systems | Implementation was smooth and uneventful and as such there were no particular "lessons learned".
LIB/FOA/34/INV/12 | UNDP | INV | FOA | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Essadek | It is sometimes necessary to adjust implementation modalities to adjust for changing economic situations present at an enterprise. As long as the project objectives of ODP phase-out are met using appropriate technology and the project timeline is not negatively impacted, it is prudent to be responsive to such requests for adjustment in order to complete the project and achieve the ODS reduction objectives.
LIB/FOA/34/INV/13 | UNDP | INV | FOA | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Hilal Africa
LIB/FOA/35/INV/14 | UNDP | INV | FOA | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate El Hani | If an enterprise wishes to enlarge the project scope by capitalizing on the eligible funding to upgrade to continuous rather than discontinuous foam production, the intent should be revealed during project planning, and the appropriate implementation schedule should be developed to reflect the actual work to be done. Certain preparation work may be required by the enterprise in order to approve such projects, and such projects should be clearly planned from the beginning.
LIB/FOA/35/INV/16 | UNDP | INV | FOA | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Ali Sannoga
MOR/REF/43/INV/50 | UNIDO | INV | REF | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment | (1) Counterpart’s dedication is fundamental for successful execution of the project. (2) Clear technical concept and straightforward strategy for the implementation of the project, as well as the teamwork spirit created by the implementing agency made the implementation process moving smoothly and steadily. The actual fund approved was not according to the original Project Document. Therefore counterparts provided required additional equipment for smooth conversion of plants.
NIR/FOA/35/INV/96 | UNDP | INV | FOA | Conversion from CFC-11 to methylene chloride (MC) technology in the manufacture of flexible polyurethane at ten box-foam enterprises in Lagos area | Based on previous flexible slabstock foam projects in Nigeria, advance planning with the enterprises assured that the project was implemented as planned for in the project document. As a result, this complex project covering 10 enterprises was able to be completed ahead of schedule and within budget.
PAK/FOA/17/INV/06 | IBRD | INV | FOA | Pakistan: 4 plants: Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Indusries Ltd., Procon: Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group | (1) Equipment destruction should be implemented right after replacement and phase-in of the new technology in order to avoid problems with witnessing / documenting equipment destruction. In the Master case, the disposal certification was delayed for when all plants were completed with conversions which led to some difficulties in the Procon plant which had a fire that destroyed the baseline equipment. This prevented easy verification that the baseline was destroyed. (Baseline equipment disposal was not an ExCom requirement until two years after this project was approved.) | (2) Implementation in dynamic companies as Master Enterprises is a challenge as continuous changes (not associated to CFC phaseout) are implemented and the project needs to be adjusted to those changes. Flexibility from both parties is required. (This is related to the company’s relocation of plant and equipment from one place to another.) (3) Before implementation of MLF projects, all necessary documentation, procedures and guidelines should have been in place. NDFC/NBP passed through a learning curve to understand all the procedures at the start of the MLF projects.
PAK/FOA/23/INV/22 | IBRD | INV | FOA | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible molded, rigid foam) at Diamond Group Industries | Two different LCs were opened for one machine of the value of funding provided by the WB and the counterpart, having two shipments .This created hurdles during clearance due to mismatch of the relevant documents. Therefore, there should be only one LC even if the machine is jointly procured by the WB and the enterprise. In future, LC would be opened for full amount, and the counterpart funding would be deposited in NBP prior to the opening of LC.
PAK/REF/32/INV/39 | IBRD | INV | REF | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | (1) In the rare event that there are some omissions during project preparation due to unforeseen circumstances, there should be some flexibility to make adjustments to the project in order to ensure no CFC consumption remains after conversion – if there is solid proof that omissions were made. One of the main reasons for delay in implementation was that it took time to make changes to the baseline information due to the discovery of the mobile dispensers. | (2) PAECO made a mistake in dismantling the machinery prior to the installation of the new machine in anticipation that the new machine would arrive within two to three months. However, it ended up taking more than a year to order and deliver the equipment. It is therefore suggested that the enterprise not make major changes in the plant until it is certain about the shipment and installation dates.
ROM/ARS/44/INV/26 | UNIDO | INV | ARS | Phase-out of CFC-12 in the manufacture of pharmaceutical aerosols by conversion to HFC-134a propellant at MEBRA, Brasov (terminal aerosol sector project) | 1) Resolute promotion of eco-efficient cleaning technologies is crucial to attract the attention of the counterpart. Counterpart’s dedication to the whole process of project implementation is vital. 2) Not only environmental but also technological and techno economical benefits should be promoted prior to the project implementation to attract counterpart’s commitment to implement the project. Counterpart’s dedication is fundamental for successful execution of the project. 3) Clear technical concept and straightforward strategy for the implementation of the project, as well as the teamwork spirit created by the implementing agency made the implementation process moving smoothly and steadily.
ROM/FUM/34/INV/19 | Italy | INV | FUM | Phase out of methyl bromide in horticulture | Convincing the companies (farms) to co-finance the pilot greenhouse for grafting technology, improved the implementation process making it sustainable.
SYR/REF/35/INV/81 | UNDP | INV | REF | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Saad Refrigeration | The costs for trials and site preparation need to be realistically estimated and the eligible part funded accordingly.
SYR/REF/38/INV/87 | UNIDO | INV | REF | Plan for elimination of CFCs in the refrigeration manufacturing sector (domestic refrigeration). | Not only environmental but also technological and techno economical benefits should be promoted prior to the project implementation to attract counterpart’s commitment to implement the project. Good communication between UNIDO, NOU and Counterparts is also fundamental for thesucess of the project. Counterpart’s dedication is fundamental for successful execution of the project.
THA/FOA/31/INV/131 | IBRD | INV | FOA | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | N/A
THA/REF/26/INV/104 | IBRD | INV | REF | Program to reduce the usage of CFC-11 and CFC-12 in chiller servicing by replacing CFC-based chillers with HFC-134a and HCFC-123 chillers at Electricity Generating Authority of Thailand(EGAT) | (A) Project Design Period: (1) No budget for maintaining S/A and auditing available: The budget should have been provided at Baht 300,000 per year. (2) No technical assistance budget provided (PPC+PMC = 5 M Baht) : WB did not provide budget for technical assistance because at the first stage, this project was designed for EGAT, which had its own engineering expert. When WB passed on this project to TMB(IFCT), which did not have its own technical team, TMB had to acquire new budget for this item. (3) No spread fee available: WB firstly assigned EGAT to develop this project without fee because EGAT did not have to take any financial risks and instead asked its customers to provide bank guarantees. When WB transferred this project to TMB for further development, TMB had to take increased responsibilities such as identifying customers, making F/S study, submitting progress reports, taking risks of possible losses, etc. Therefore, TMB had to charge the management fee from customers in order to cover some administrative costs and risks. | (4) SDR currency: At the first stage, the source of fund (GEF) would support grant in term of SDR currency which caused problems since it was difficult to identify the exact amount of loan. However this problem was solved by fixing the exchange rate at SDR1 = USD1.27645. (5) Delay in negotiating on clause of default : There were some unacceptable clauses for TMB in loan agreement such as the WB could default the loan scheme at any time, therefore TMB spent more time to negotiate this issue. (6) Individual Loan Scheme was new to WB : WB guidelines and regulations are suitable for national or large projects. But this program had to deal with many individual enterprises and some guidelines were not applicable. TMB had to spend more time to settle the suitable guideline. (7) Limited timeframe : WB designed this project with limited timeframe for each task such as giving only 2 months for TMB to identify customers, 10 months for equipment installing and commissioning, and return all amount of loan to WB at the end of the 5th year. | This timeframe was rather rigid and made it difficult for TMB to seek additional potential customers to join the program. (B) Implementation Period: (1) Limited target group due to: (a) Low operation hours: Some potential enterprises such as hotels, department stores, had occasionally low operation hours and sometimes decided to switch the chiller equipment other types of suitable refrigeration equipment. Therefore their energy saving costs were less than the projected designed. (b) No confidence on chiller technologies: Some enterprises had no confidence on chiller technology. This problem was later on solved by performance guarantee. (c) Limited target sectors : TMB (IFCT at that time) could support only customers in industrial sectors, therefore other potential customers, such as service and trading sectors could not join this program. (d) Power consumption criteria for existing and new chillers: Criteria were originally designed such that the performance of old chillers should be more than 0.8 kW/ton while that of new chillers would not to exceed 0.63 kW/ton. | This criteria was not flexible for many enterprises that would like to join this program. However, this problem has been solved by setting the new criteria that the new chiller must have better performance than the old one, not less than 0.27 kW/ton. (e) Power consumption measurement constraint : There was constraint in the measurement of energy consumption of the old chiller. (i) Financial limit: Following initial measures of energy consumption of approximately 40 chillers, it was originally estimated that roughly 24 units would join this program. But in fact, there were only 17 of chillers joining in this program. Therefore, the budget for measuring energy consumption was not sufficient. (ii) Technical limit: Some enterprises had made preventive maintenance on their chillers just before the measurement of energy consumption; therefore the performance of their old chillers was better than that of most chillers that had not undergone maintenance. | (f) Unclear definition of capacity expansion : There were misinterpretations of the definition of capacity expansion of an enterprise, as related to chillers. In some instances, according to the enterprises, an expansion on chiller size did not mean increase in the enterprise’s capacity. This issue took more time to clarify with WB and enterprise. (g) Unclear definition on how to scrap and/or dismantle existing chiller : Some enterprises withdrew from this project because of initial lack of clarity of the issue of equipment disposal. Enterprises did not initially understand whether that they were required to scrap their old chillers. Sometimes they would have liked to keep some parts to use as spare parts. (h) Higher investment cost for participating : When joining the project, the cost of investment was higher than the normal replacement of chiller equipment as there would be cost of approximately US$15,000 for installing data logger and scrapping the compressor. | It was the regulation that all participants had to pay for those costs because the project needed to monitor the performance and energy saving of the new chiller. This requirement was the reason why some enterprises decided not to participate in the program and instead changed the chillers by themselves. (i) Participant uncertainty due to failure of similar program : Some enterprises were involved in a similar program implemented by EGAT did not have confidence in this project because EGAT’s project was never developed. When TMB took care of this project, some enterprises were still reluctant to participate. (j) Suppliers not giving full support : Some suppliers did not give full support to the program because the complex requirement of the program such as performance guarantee, proposal submission and bank guarantee. These activities were beyond the scope of normal work, therefore some suppliers suggested the enterprises change chillers directly with them, without additional requirements. (k) Unlike grant program, loan scheme needs more flexibility:
THA/REF/26/INV/104 (Continued) |  |  |  |  | WB procedures require that grant projects have strict rules and conditions. This program involved a large number of individual enterprises. These strict regulations should have been made more flexible to better accommodate the condition of the project and the enterprises. (l) No previous investment demand in chiller : This project was a pilot, with no previous investment demand in chiller products before. Formerly, chillers were replaced only when their lifetime had expired. It was difficult to persuade enterprises to join in this project. This problem was solved by demonstrating to them the benefits of the return on investment, payback period and by providing performance guarantees. (m) Energy efficiency will also depend on appropriate size of chiller : Energy saving is also depending on the suitable size of chiller and load. TMB found that some enterprise had chillers that were over or under adequate load design. When the old chiller was replaced with the new one at the same size, the energy consumption was still high. | The technician team must evaluate the proper size of chiller for each customer. (n) Chiller Replacement is considered as second priority : Some enterprises such as hotel, consider that the first priority of their investment is convenient facilities, room decoration and renovation. It is difficult to persuade enterprises in this type of sectors to join this program. (o) Building Owner to invest in absorption chillers : Enterprises that have waste heat will tend to invest in absorption chillers instead of electrical chillers because they have lower energy consumption than electrical chiller. (p) Cost of FI is very high : Operation cost of TMB (Financial Intermediary) is high because TMB had to take on many responsibilities, starting from developing the project, designing the process, identifying the customers , preparing progress reports, collecting loan and taking its own risk, etc., while the loan amount for each chiller is small and the fee earning from each chiller is too low. | (q) Many Building Owners cancelled because of complicated condition : This program requires performance guarantee which involves both suppliers and the fund managed by TMB. This caused complexity in preparing and revising subloan agreements between TMB and the enterprises, and some contracts between the suppliers and the enterprises. Therefore it took time for TMB to deal and negotiate with the enterprises as well as the suppliers. (r) One contract for one chiller : Due to WB regulation that one contract will be made for one chiller , enterprises that needed to change multiple chillers did not like this rule. At the same time, TMB had to spend more time to prepare and adjust the contracts as well as to clarify details with the enterprises. (s) Balance of two loan support : It was difficult to balance the disbursement of the two loans (MLF and GEF), because differences in amounts and costs of projects for each participant. (C) Commissioning Operation and Maintenance period: | (1) Dismantling or scrapping of old chillers : According to the project guidelines, each enterprise had to scrap the old chiller after finishing the installment and commissioning of the new chiller. Some enterprises requested to keep the old chiller as a spare one until they were assured that the new chiller could run smoothly. This request was not possible to satisfy, and this caused the withdrawal of some of the enterprises that were originally interested in participating in the project. (2) Inadequate load to commissioning : some enterprises had low cooling load (less than 90%), therefore the team could not commission this chiller. This reason caused project delays because TMB had to wait until the load was 90% in order to commission. Otherwise, the performance guarantee point would have not been known. (3) Less operating hours of chiller : Operating hours of chillers were less than originally designed, because enterprises switched to run other chillers instead. This caused the energy saving of new chiller less than designed. | (4) Problem on Refrigerant: (a) No agent to take care of the refrigerant that was recovered from the old chiller. (b) No agent to clean up and check the quality of recovered refrigerant, therefore there is no confidence to reuse these recovered refrigerant. (5) After sale services : Supplier had low performance in after sale service, because of the lack of coordination between service team and selling team. Supplier took long time to support the customer. (6) Data collection : Data from data locker is in text file that is difficult to manipulate in order to calculate the performance of chiller. Sometimes data cannot be recorded because the enterprise would turn off the data logger, therefore the actual performance of chillers was difficult to calculate. Suppliers should install data loggers that can calculate performance data automatically.
TRI/ARS/25/INV/12 | UNDP | INV | ARS | Project to phase-out use of CFCs in aerosol filling at Hand Arnold Industries Limited (HAIL) | Proper planning during the project development stage helps to ensure that a project will be able to be implemented as planned for. In this case, it became apparent during project planning that it would be necessary to move the operations to an open, industrial area. The enterprise was able to secure a facility and begin required governmental approvals of the facility so that implementation could proceed once project approval was granted.
TUR/FOA/32/INV/71 | IBRD | INV | FOA | Conversion from CFC-11 into all-water technology for flexible molded and HCFC-141b for integral skin foams at 11 enterprises (Erdogan, Rurmenier, KarakayaCelik, Una Polyurtan, Iksan Ltd., Ak-kom, Karsan, Goldsit, Buoflex, Gervener, Yaris Karbin, Hisari. | Enterprises have used the new and cleaner technology and seen that it is more suitable for the company. Also, they have achieved good product quality.
TUR/FUM/29/INV/56 | IBRD | INV | FUM | Introduction of alternatives to methyl bromide in protected strawberry, pepper and eggplant in East Mediterranean region and in strawberry in Aydm province of Turkey | (1) Working closely with farmers and extension specialists is a must for adoption of the innovations. (2) Costs have to be taken into consideration in recommending a new practice. (3) Knowledge and experience sharing with international community is needed to achieve results in a shorter period of time.
TUR/SOL/35/INV/76 | IBRD | INV | SOL | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | The alternative cleaning system has been accepted by the beneficiary companies.
UGA/FUM/34/INV/08 | UNIDO | INV | FUM | Phase-out of methyl bromide in cut flowers | N/A
URU/FOA/31/INV34 | IBRD | INV | FOA | Terminal program for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | (1) In spite of the small project budget, the conversion was a success due to the efficient use of the available resources and the effort made by the enterprises. The project made possible the 100 % CFC phase-out of eligible firms’ consumption in the foam manufacturing sector. (2) Although national legislation and the market economy are not matters that could or should be solved by the Multilateral Fund, we wish to point out that these problems affect the decision making process, and it may delay the start up of alternative technologies of a higher operational cost than those required on the use of CFCs. | (3) As a support to the enterprises for all these efforts, the right to the use of the Ozone Friendly Seal was issued, within the framework of the institutional strengthening project. This implies an endorsement that aims at improving the management image in the public opinion and at the same time establishes a monitoring mechanism of the finalized project by the Laboratorio Tecnológico del Uruguay (LATU), which is the institution that gives the Seal together with the National Ozone Unit.
VIE/ARS/31/INV/28 | UNDP | INV | ARS | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | N/A
VIE/ARS/37/INV/40 | UNDP | INV | ARS | Terminal umbrella project for the aerosol sector to phase-out ODS consumption in the manufacture of aerosols and perfumes by conversion to hydrocarbon propellant (Dong A and Thorakao Cosmetics Ltd.) - VIE/02/G61 | N/A
YUG/REF/38/INV/19 | UNIDO | INV | REF | Conversion of CFC-12 to HFC-134a in the manufacture of open compressors at Prva Petoletka - Kocna Tehnika Co. | Involvement of the National Ozone Unit (NOU) for local coordination facilitated smooth implementation of the project. Particularly, communication between Implementing Agency (IA) and Beneficiary Company was improved with this arrangement.
ZIM/FUM/31/INV/21 | UNIDO | INV | FUM | Phase-out of methyl bromide in cut flowers | Before the begining of project activities it is necessary to take into consideration recent political stability and economic changes in the country in order to prevent problems in project implementation.

## Non-Investment
Code | Agency | Type | Sector | Project Title | Lessons Learnt | Lessons Learnt (Continued) | Lessons Learnt (Continued) | Lessons Learnt (Continued)
BHU/REF/45/TRA/04 | UNEP | TRA | REF | Implementation of RMP: Train-The-Trainer for Customs and Enforcement Officers | At the end of the training workshops the participating customs officers were asked to provide comments and recommendations on how to implement and enforce ODS import/export control and import licensing system. Several useful suggestions were made by the participants. These are; 1) The customs officers of Bhutan should be well exposed to licensing and control of ODS in Bhutan and India. | 2) More case studies on illegal trade in ODS maybe provided to the customs officers for detecting similar cases in their jurisdiction. 3) Provide more information to the customs officers about smuggling of ODS in other countries through video tapes and CDs. Such suggestions could be studied so that they could be implemented wherever similar situation exists.
BHU/REF/45/TRA/05 | UNEP | TRA | REF | Implementation of the RMP: Train the Trainer Programme for refrigeration service technicians | 1) Collaboration with Royal Bhutan Institute of Technology need to be established to integrate the Good Practices into the on going refrigeration curriculum; 2) More awareness programmes on ODS should be implemented to the public and other line-ministries through TV, newspaper and radio.
BKF/REF/32/TAS/11 | UNDP | TAS | REF | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector
BKF/REF/34/TAS/13 | UNDP | TAS | REF | Implementation of the RMP: monitoring the activities included in the RMP | NA
BRA/REF/34/TRA/228 | Germany | TRA | REF | Pilot project: training programme for the refrigeration maintenance sector | The training of 200 technicians (in refrigeration practices) and contracting several vocational training centers (VTC) in different regions in the country, resulted in a good operating network between NOU, companies and the VTCs for the implementation phase.
COI/REF/35/TAS/06 | UNEP | TAS | REF | Implementation of the RMP: assessment of the end-users subsector | The Union des Cores is composed of three differents islands and each island wanted to organize its own workshop. To face that problem we got some participants of the two others islands to travel to the main island which is the capital city of Union des Comores. There is need to monitor the two cold rooms retrofitted and the local expertise in retrofitting cold room
COL/REF/32/TAS/46 | UNDP | TAS | REF | Technical assistance for RMP survey and preparation | (1) During the Preparation of the National Phase Out Plan of Colombia the National Ozone Unit had a central role coordinating the work at the local level and interacting with the companies involved and relevant stakeholders in order to obtain feedback from the sectors and from the institutions on the needs and best possible ways to achieve the phase out CFCs. The participation of local stakeholders in the formulation of technical assistance activities was very important to achieve a realistic proposal that can be implemented and receives the support of the different groups involved. | (2) The permanent exchange of ideas between the National Ozone Unit and the International Consultants produced as a result a document that reflects the national needs and includes a strategy tailored for the particular case of Colombia. This strategy is currently in implementation with no changes from the original plan.
COL/REF/35/TRA/52 | Canada | TRA | REF | TRAINING PROGRAMME FOR CUSTOMS OFFICERS | 1) NOU was concerned with the cost involved in organizing regional workshops. At the beginning the main idea was to follow a centralized vision, having all workshops delivered at main capital city of Bogotá. However, a greater local content was the primary concern, since every customs office face a somewhat different situation. For instance, inner customs offices have different operations than those from the borders or located at sea ports. Hence, a decentralized approach addressed these needs in a more efficient manner, since bringing local experts was radically less expensive than taking them to Bogotá. | 2) As a consequence, this regional approach was a better way to tap into local-customs-office needs. Evidence of this is clearly observed in some workshops which were attended by Venezuelan customs officers as well, creating a greater synergy effect. 3) Attendance of an Environment Canada enforcement expert at Phase I training was a useful in-kind contribution.
COS/REF/32/TAS/23 | UNDP | TAS | REF | Technical assistance for RMP survey and preparation | The enactment of environmental laws and regulations in developing countries is traditionally a very lengthy process and, what seemed a very good idea at first (passing all necessary regulations in only one all-encompassing decree, or "Super Decree", turned out to become a stumbling block that paralyzed Montreal Protocol related activities for quite some time. The main reason was that the decree contained measures related to the use of methyl bromide, which affected a very critical economic sector, the melon-growing sector, which in turn reacted very strongly to the decree.
CRO/SOL/45/TAS/25 | UNIDO | TAS | SOL | Training and awareness workshop in the solvents (CTC) sector | Cooperation of all parties and sharing expertise strengthens the results of the training.
DOM/REF/25/TAS/13 | UNDP | TAS | REF | Implementation of the RMP: implementation of a national programme for recovery and recycling of refrigerants | We encountered some obstacles when it came down to the use of the Recovery and Recycling Centers; and believe these can be of help for future projects: (1) The Centers were placed too far away from the technicians. (2) More technical assistance and follow-up could have improved the efficiency of the centers. (3) The machines were considered expensive for the affordable reach of midlevel technicians; we need to create strategies so that the prices of the machines become low enough for midlevel technicians.
DOM/REF/25/TAS/15 | UNDP | TAS | REF | Implementation of the RMP: monitoring of the activities included in the RMP | (1) The monitoring required is a time consuming task that requires a person to establish contact with the beneficiaries of the project. Beneficiaries do not by themselves turn in the data that is needed for the Ozone Unit to efficiently monitor the use of the equipment. Proactivity and persistence is needed. (2) More technical assistance and follow-up to the beneficiary workshops would probably have increased the efficiency of the equipments, as well as the documentation of the results. It is expected that much more R12 was recovered and recycled than the offical data shows. (3) It is difficult for the Ozone Unit to assume the monitoring by themselves given the daily tasks in the NOU. Additional people needs to be hired.
FIJ/REF/29/TAS/04 | UNDP | TAS | REF | Implementation of the RMP: national programme for recovery and recycling of refrigerants | (1) Documentation of the CFC recovered and recycled was initially a weak point in the monitoring system. While a standardized record-keeping and documentation system was put in place by the Government in 2005 (see comment under section 3.6 above), it would be helpful to develop a standardized data collection method and reporting format earlier on and include it during the initial training sessions in order to facilitate proper reporting and ensure that accurate records were kept to during the monitoring period. (2) In this project, a good program was put in place with criteria for possession of the equipment, so that during the monitoring period, equipment reallocation was possible from those companies not meeting the agreement.
GEO/FUM/37/TAS/13 | UNIDO | TAS | FUM | Technical assistance for the phase-out of methyl bromide for soil fumigation | Regional cooperation and sharing expertise strengthens the results of the training.
GEO/REF/35/TAS/10 | UNDP | TAS | REF | Implementation of the RMP: incentive programme for the end-users in the commercial/industrial refrigeration and refrigerated transport sub-sectors | If technical assistance and incentive funding is made available, end-users are encouraged and willing to undertake conversion or permanent retrofit of their installations even though CFC refrigerant is still available.
GHA/REF/32/TAS/12 | UNDP | TAS | REF | Implementation of the RMP: mobile air conditioning recovery and recycling of CFC-12 | (1) Several issues were identified related to service items for the R&R equipment that should be budgeted for in project proposals. Consumables such as filters and vacuum pump oil should be included in the project budgets. (2) Due to the popularity of the program, additional enterprises were contacting EPA to inquire about purchasing R&R units themselves. It may be helpful to set up a collaborative purchasing program for other interested enterprises who may not be benefiting directly from the project, but express interest in completing the same activities. | (3) Local service arrangements are essential to assure the success of the program. These arrangements should be anticipated and established as quickly as possible in order to assure the program can be implemented without delays for equipment servicing issues. This will also help to assure the long-term sustainability of the program.
GHA/REF/32/TAS/14 | UNDP | TAS | REF | Implementation of the RMP: incentive programme for the commercial/industrial refrigeration end-user sector | If technical assistance and incentive funding is made available, end-users are encouraged and willing to undertake conversion or permanent retrofit of their installations even though CFC refrigerant is still available
GHA/SOL/44/TAS/22 | UNDP | TAS | SOL | Technical assistance for the CTC sector | A detailed survey was useful in obtaining the confidence that there indeed was no use of CTC and MCF in commercial/industrial applications.
IND/HAL/29/TAS/243 | UNDP | TAS | HAL | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | (1) This particular project was developed out of the Indian Halon Phaseout Strategy document submitted and approved by the MLF ExCom and was aimed to be the benchmark against which all other Article 5(1) Countries would be able to follow and implement once completed. The project was one of significant technical complexity due to the much larger than expected tasks facing the personnel involved in its implementation. Primarily, it involved the development of new standards incorporating non ODP technologies to replace all other existing halon based. In addition, all other existing local fire codes etc that contained reference to the approved use of halon based chemicals needed to be completely revised to take account of the proposed change to non ODP chemicals. The ultimate goal of the project once completed was to remove the ability of ALL stakeholders to be able to legally design and / or install ANY new halon based products in future in accordance with various local rules and regulations throughout India. | (2) However, as this project was breaking new ground in terms of its concept under MLF guidelines, it was always going to be difficult to judge the amount of time necessary to be allocated in order to meet the original objectives. Whilst some of the earlier project milestones were achieved in accordance with the initial timetable, the pure complexity of developing both the 13 new standards and amending over 150 existing codes by going through each one word for word proved to be far more time consuming than first thought. Also, the dissemination of the finished products by way of workshops and conferences across as much of India as possible, again took far longer than anticipated. Irrespective, the risk of compromising the outcome of the whole project by simply compressing the overall timetable just to meet original estimates, was certainly not an option and would have also proved to be a waste of MLF funds not to mention the confusion locally in India of having a mixture of half finished regulations. | Adopting this approach would have caused continuation of halon use rather than its gradual elimination. (3) Although accepting that the project ran over by approximately 30 months from the original approved timetable, it became well known by most, if not all stakeholders during the project implementation stage as to the proposed project objectives. Consequently, it was observed even in the very early stages that installation of new halon based systems and products reduced dramatically as owners / users / manufacturers realised the changes were imminent and commenced embracing the various non halon technologies well before legal requirements to do otherwise.
JAM/SOL/42/TAS/20 | UNDP | TAS | SOL | Technical assistance umbrella project to phase out ODS solvent use | (1) Removal of technical test support costs, incentive payments, and all funding associated with testing of alternatives by the University from the project (2/3 of the project cost), left the project fully dependent on the enterprises to fund and run their own tests. This did not lend itself to timely phase-out activities since the enterprises normally have much more immediate priorities, associated with their ability to function effectively in a competitive marketplace. Leaving some funds available would have provided the enterprises with some incentive to produce more timely results. | (2) The fact that the companies undertook to seek solutions using their own funds – but on their own timetable – is a tribute to their commitment to the environment and to their responsible attitude regarding the treaty and the ozone layer.
KAM/FUM/46/TAS/10 | UNIDO | TAS | FUM | Training and awareness workshop in the fumigants sector (methyl bromide) | Regional cooperation with UNEP RRCAP and sharing expertise strengthens the results of the training.
KAM/REF/41/TAS/08 | UNEP | TAS | REF | Implementation of the RMP:Implementation Support and Monitoring | (1) Continuing awareness campaign for vehicle owners about harmfulness of CFC-12 and retrofitting incentive is a very effective methods of encouraging customers to have their vehicle retrofitted. (2) Awareness campaign including production of TV ads and other other media advertisements and publishing are very effective awareness raising strategy. (3) The training equipment including MAC were well arranged before the course started, which made the practical session successful. (4) Splitting the training session into theory and a practice was a good way to achieve the objectives of the workshop. | (5) Additional refrigeration identifiers are very important to all customs checkpoints along the border in Cambodia to ensure that they are properly equipped for monitoring and controlling of ODS. (6) More Khmer versions of ODS documents made available for public distribution. (7) Close coordination with relevant Ministries for monitoring activities are effective strategy for the timely submission of data and reports.
KAM/REF/41/TRA/06 | UNEP | TRA | REF | Implementation of the RMP: Refrigeration and Air Conditioning Technicians Training Programme | (1) The training equipment including MAC were well arranged before the course started, which made the practical session successful. (2) Splitting the training session into theory and a practice was a good way to achieve the objectives of the workshop. (3) The NOU established a training team with a trainers from the train-the trainer workshops, local consultant and NOU staff. The training team also prepared a detail training plan in consultation with the local workshops. This approach is very effective as part of the preparation in conduct of trainings. (4) The local consultant under UNDP’s project under the RMP had activitely participated in the technicans training programme as one of the resource persons.
KUW/REF/37/TAS/05 | UNIDO | TAS | REF | Implementation of the RMP: national recovery and recycling | Regional cooperation and sharing expertise strengthens the results of the training. Limitations due to institutional structure of the local executing agency should be taken care of during the project preparation.
KYR/REF/37/TAS/01 | UNDP | TAS | REF | Implementation of the RMP: monitoring the activities in the RMP | The close collaboration of the National consultant with the NOU was vital to the success of this project.
KYR/REF/37/TAS/04 | UNDP | TAS | REF | Implementation of the RMP: national programme for refrigerant recovery and recycling | (1) As in some other R&R projects, it was very beneficial to have the monitoring consultant selected and on-board to participate in the training workshops. This allowed for a segment of the workshop to be devoted to training in what data is to be collected and how, as well as to introduce the monitoring consultant to the participating enterprises. This also allowed prompt initiation of the monitoring program and reinforcement of the usage of the recovery and recycling equipment. This allowed for the participant agreements to include provisions about the reporting requirements, and in the training, the reporting obligations could be stressed, allowing better data collection and reporting through the monitoring program. (2) Regular reporting and contact between the UNDP international expert and the national consultant resulted in a rapid transfer of information and increased and more efficient productivity from the participants.
LAC/HAL/26/TAS/28 | Canada | TAS | HAL | Development of a regional halon bank management plan for the English-speaking Caribbean (Bahamas, Barbados, Grenda, Guyana, Jamaica, and Trinidad and Tobago) | 1) Initial project objectives evolved over the implementation of the project. While originally it was believed that a regional HBMP should only be developed and implemented once each country finalized a national HBMP, a number of factors suggested that a different approach was required to implement the project. In this regard, and due to approaching compliance targets, (2002 freeze, and 50% reduction target) those countries that were ready to implement at the national level to ensure compliance could not wait for other countries who were not ready to implement, thus postponing any regional initiative. At the Regional Workshop in Guyana in 2002, countries discussed concerns about what was working or not working in their respective countries and what they needed particular assistance with. Countries were able to agree on a basic approach to move forward despite the fact that countries were all varying levels of progress with implementation. | This approached allowed for a flexible solution to a problem which ultimately caused significant delay. Proceeding with the plan and moving forward on specific activities at the regional and national levels simultaneously, offered the advantage that countries learned from the implementation of activities that have taken place and thus be able to design a more informed and realistic regional plan. 2) As this was the first project of its kind to receive funding under the Multilateral Fund, it is not surprising that the initial design of the project changed to suit the realistic needs of the countries as new and relevant information emerged over time. In this respect, the regional workshops and network meetings provided a much needed forum for all stakeholders to discuss meaningful ways forward to a number of problems countries were facing. This ultimately led to the successful completion of the project, including countries being able to meet their compliance targets for halon under the Montreal Protocol. | 3) It should be noted that, while technically, the completion of the project was very much delayed, Canada and UNEP made a conscious decision to keep the project open as long as it was felt that there was still a need to provide guidance and assistance to the countries involved. It was found more useful for the countries concerned to maintain the project open over a long period of time, even though this involved additional overhead costs for Canada and UNEP, as the need for technical assistance and information proved to be an ongoing one, rather than one that could be met within a specific time-frame, particularly in light of the fact that most NOU officers changed over time. 4) Establshing a sub/regional halon banking facility with the objectives originally planned under this project involves the following considerations: | a) the uniformity of the participating countries in the areas of national and sub/regional capacities; b) legisltative mechanism to support change in ownership of the halon inventories from provate sector to public sector; c) that each participatication country has ratified and established regional and international agreements to allow for the shipment of halon; d) the physical location of the "Halon Bank" and the rights of property of the inventories contained in the Halon Bank; e) verifiaction of quality of halons and suitable for sale/transfer; f) disposal of untransferable and or unsaleable inventories as may be generated in the "Halon Bank"; g) hand-over processes and ownership of ngoing operating cost, and fund mechanisms for the management of the national and sub/regional banks.
LAO/REF/34/TAS/07 | UNEP | TAS | REF | Implementation of the RMP: Monitoring the activities contained in the RMP | Due to the unexpected long-duration of the RMP implementation, the budget for the monitoring project has been exhausted.
MAG/FUM/45/TAS/09 | UNIDO | TAS | FUM | Training and awareness workshop in the fumigants sector (methyl bromide) | Non
MLI/REF/32/TAS/09 | UNDP | TAS | REF | Implementation of the RMP: national programme for recovery and recycling of refrigerants | (1) Lessons learned from this project are the same as contained in decision 41/100 further to the overall evaluation that was undertaken on RMPs. (2) In addition, it was found that distribution of recovery units and bags throughout too many parts of the country, results in a lack of "critical mass" needed to make the project work.
MOL/FUM/45/TAS/13 | UNIDO | TAS | FUM | Training and awareness workshop in the fumigants sector (methyl bromide) | A deep analysis of the sectors susceptible of using methyl bromide should be made in order to allow us to better identify the target groups, the main problems and realistic solutions.
MON/REF/35/TAS/06 | UNDP | TAS | REF | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant | It was very beneficial to have the monitoring consultant selected and on-board to participate in the training workshops. This allowed for a segment of the workshop to be devoted to training in what data is to be collected and how, as well as to introduce the monitoring consultant to the participating enterprises. This also allowed prompt initiation of the monitoring program and reinforcement of the usage of the recovery and recycling equipment. Regular reporting and contact between the UNDP international expert and the national consultant resulted in a rapid transfer of information and increased and more efficient productivity from the participants.
MOR/SOL/45/TAS/53 | UNIDO | TAS | SOL | Training and awareness workshop in the solvent and process agents (CTC and TCA) sectors | Additional attention should be paid to military sector (Air Force, etc.)
NIC/FUM/45/TAS/12 | UNIDO | TAS | FUM | Training and awareness workshop in the fumigants sector (methyl bromide) | No information available
OMA/FUM/44/TRA/10 | UNIDO | TAS | FUM | Awareness workshop and training on methyl bromide alternatives | No information available
OMA/SEV/37/TAS/07 | UNEP | TAS | SEV | Policy and technical assistance | Although the involvement of relevant sectors and stakeholders in formulating the legislation is seen as key to be comprehensive and enforceable; this is not an easy task and needs lots of time and effort as was the case in this Oman legislation.
OMA/SOL/45/TAS/11 | UNIDO | TAS | SOL | Training and awareness workshop in the solvent sector (CTC) | Cooperation of all parties and sharing expertise strengthens the results of the training.
PAK/FUM/45/TAS/63 | UNIDO | TAS | FUM | Training and awareness workshop in the fumigants sector (methyl bromide) | No information available
PAK/HAL/41/TAS/55 | UNIDO | TAS | HAL | Plan for the phase-out of import and net consumption of halons in the fire fighting sector in Pakistan (MP/PAK/03/101) | Regional cooperation and sharing expertise strengthens the results of the training.
PAR/REF/32/TAS/08 | UNDP | TAS | REF | Implementation of the RMP: national programme for recovery and recycling of CFC-12 refrigerant | (1) As in other countries, the low prices and total availability of CFC 12 had not created yet the market conditions to apply a recovery and recycling system in an effective way. Despite of that, the project allowed creating the infrastructure for recovery and recycling that can be used when the conditions make it interesting for the workshops and technicians. During the preparation of the TPMP of Paraguay a new collection of information on the assisted workshops was undertaken in order to asses the condition of the equipment and the level of recovery today. | (2) At the time the project did not consider several types of equipment based on the size and infrastructure of the workshops. Today there are several lines of equipment that can be provided to small scale workshops or individual technicians. All this is being taken into account in the recently designed activities for the servicing sector.
QAT/REF/34/TAS/03 | UNIDO | TAS | REF | Implementation of the RMP: national recovery and recycling project | Regional cooperation and sharing expertise strengthens the results of the training. The difficulties due to language understanding should be taken care of during the project preparation.
SEY/REF/40/TAS/08 | Germany | TAS | REF | Refrigerant Management Plan
SYR/HAL/34/TAS/77 | Germany | TAS | HAL | Establishing a halon bank and umbrella project for 63 manufacturers
SYR/HAL/34/TAS/78 | France | TAS | HAL | Establishing a halon bank and umbrella project for 63 manufacturers
VEN/SOL/45/TAS/103 | UNIDO | TAS | SOL | Training and awareness workshop in the process agents (TCA) sector | Cooperation of all parties and sharing expertise strengthens the results of the training.
VIE/REF/34/TAS/35 | UNDP | TAS | REF | Implementation of the RMP: MAC recovery and recycling of CFC-12 refrigerant | (1) Local suppliers for spare parts and consumables should be investigated for R&R projects. Often, many of these parts can be sourced locally at lower prices, and void the issues of customs clearance and duties. (2) Special attention should be paid to varying conditions in different parts of a country when determining the optimal distribution of R&R equipment. The distribution should be implemented in a manner that maximizes the effectiveness of the program, and not necessarily according to an equal distribution of equipment throughout the country.
VIE/REF/34/TAS/38 | UNDP | TAS | REF | Implementation of the RMP: monitoring the activities in the RMP | In this case, hiring two consultants to work together on the monitoring project was a cost-effective and workable solution. The monitoring duties were split between the consultants by location, which allowed the most efficient use of resources. If this approach is sued, it is imperative that the consultants have a good working relationship with each other in order to provide consistent and timely monitoring reports.
VIE/REF/35/TAS/39 | UNDP | TAS | REF | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | (1) Local suppliers for spare parts and consumables should be investigated for R&R projects. Often, many of these parts can be sourced locally at lower prices, and void the issues of customs clearance and duties. (2) Hand pumps were found to be very useful and convenient for the participants who work in the field. They are convenient and easy to move from place-to-place.
YEM/SOL/45/TAS/22 | UNIDO | TAS | SOL | Training and awareness workshop in the process agents (TCA) sector | Close cooperation and sharing expertise strengthens the results of the training.
ZAM/SOL/45/TAS/16 | UNIDO | TAS | SOL | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | See attached Report prepared by National Expert.