## DataBase
Status | Agency | Project Title | Multi-Year/Multi-Year Partial Phase-out/One-off Phase-Out/Individual/RMP/RMP Update/RMP for Non-LVC/Halon Banking | Region | Country | Sector | Mtg | Type | Num | A/N | O/T | IRD | Chemical | Consumption ODP to be Phased Out per Proposal | Consumption ODP Phased Out | Production ODP to be Phased Out per Proposal | Production ODP Phased Out | Date Approved | First Disbursment Date | Date of Compl per Proposal | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Funds Disbursed (US$) | Per Cent of Funds Disbursed | Balance (US$) | Funds Obligated (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Cost Disbursed (US$) | Support Cost Balance (US$) | Support Cost Obligated (US$) | Remarks (Specify milestone achieved, remedial actions, and issue | Remarks (continued) (for Multi-Year, One-off address provisions | Year of Contribution | 22nd Mtg Planned Date of Completion | 28th Mtg Planned Date of Completion | 31st Mtg Planned Date of Completion | 34th Mtg Planned Date of Completion | 37th Mtg Planned Date of Completion | 40th Mtg Planned Date of Completion | 43rd Mtg Planned Date of Completion | 46th Mtg Planned Date of Completion | 49th Mtg Planned Date of Completion | 52nd Mtg Planned Date of Completion | 55th Mtg Planned Date of Completion | Year of Business Plan | Business Plan Allocation (Investment/Non-Investment) | Multi-Year Current Tranche - Consumption Performance Target (ODP Tonnes) | Multi-Year Current Tranche - Actual Consumption (ODP Tonnes) | Multi-Year Current Tranche - Production Performance Target (Odp Tonnes) | Multi-Year Current Tranche - Actual Production (ODP Tonnes) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Annual Target Met as Reported by Country (Yes/No) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Verification Completed (Yes/No) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Verification Report to ExCom (Yes/No)
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | AFG | SEV | 43 | INS | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2005-07-01 | 2007-04-01 | 40000 | -13 | 39987 | 39987 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Preparation of the country programme/RMP project | Individual | ASP | AFG | SEV | 43 | CPG | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-03-01 |  | 2005-10-01 |  | 60000 | -11923 | 48077 | 40077 | 83.36% | 8000 | 0 | 8000 | 7800 | -1550 | 5210.01 | 1039.99 | 0 | Project completed. | $ 55 plus $ 7 returned to ExCom 51. $11,868 plus $1,543 PSC returned at ExCom 52 | [12 empty] | 2004 | Non Investment
FIN | UNEP | Start up of institutional strengthening project | Individual | ASP | AFG | SEV | 46 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-12-01 |  | 2005-10-01 | 2006-10-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 13 reinstated at ExCom 54 | [12 empty] | 2005 | Non Investment
FIN | UNEP | Establishment of national ozone unit for implementing the phase-out of ODS (institutional strengthening) | Individual | ASP | AFG | SEV | 47 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
ONG | UNEP | National phase-out plan (1st tranche) | Multi-year | ASP | AFG | PHA | 47 | TAS | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2009-12-01 | 2009-12-01 |  |  | 305000 | 0 | 305000 | 305000.05 | 100% | -0.05 | 0 | -0.05 | 39650 | 0 | 39650.0065 | -0.0065 | 0 | The NOU allocated annual import /consumption quota for ODS imports of 40 ODP Tons (Based on NPP import limit for the year 2008) for the year 2008 in accordance with the National Phase Out Plan and ODS regulations of Afghanistan. This quota was awarded to only one importer. NOU organized the Custom Training and regional cooperation workshop to control Illegal Trade in ODS 29-31st March 2008 with 35 participants. The remaining eleven ODS identifiers were distributed among the custom department located in different provinces / locations on the occasion of the Customs Training Program on 29-31 March, 2008. Umbrella Foam Project, the GTZ organized a training course at the Karamadan Company in Tehran Iran from 22-30 April 2008. In the year 2008, another training centre (third centre) was established at Heart. Fourth training centre for training the workshop technicians was established at Jalalabad (not listed under the MOU) in Nangrahar province on 24th August 2008. These training centres have been equipped with essential equipment required for providing training to refrigeration technicians and also include one Recovery and recycling machine at each centre. A total of 127 technicians have been trained in Good practices in refrigeration and recovery and recycling techniques under the project till the end of year 2008. Ozone Day was celebrated on 16th September 2008 at the Speen Ghar Hotel in Jallalabad Nangrahar Province. The function was widely attended by the Government officials, University Teachers, school children and general public. Speeches on the importance of the depletion of the Ozone layer were made and awareness literature was distributed. The National Ozone Unit distributed awareness material such as school bags, Pens, Notebooks, stickers and brochures to concerned stakeholders through out the year. | [13 empty] | 2005 | Non Investment
COM | Germany | National phase-out plan (1st tranche) | Multi-Year | ASP | AFG | PHA | 47 | INV | 6 | A | O | I | CFC | 28 | 28 | 0 |  | 2005-11-01 | 2006-05-07 | 2007-12-01 |  | 2008-08-01 |  | 118438 | 0 | 118438 | 118438 | 100% | 0 | 0 | 0 | 15397 | 0 | 15397 | 0 | 0 | The foam sector was evaluated. A strategy was worked out based on the training of technicians for one foam company. A training was conducted for Afghan technicians in Tehran, Iran in April 2008. In addition, an inspection was carried out to the foam company in Afghanistan, Kabul in 2008. | [15 empty] | 57
ONG | Germany | National phase-out plan (2nd tranche) | Multi-Year | ASP | AFG | PHA | 48 | INV | 7 | A | O | I | CFC | 151.8 | 151.8 | 0 |  | 2006-04-01 | 2006-05-06 | 2009-12-01 | 2009-12-09 |  |  | 642368 | 0 | 642368 | 642368 | 100% | 0 | 0 | 0 | 83508 | 0 | 83508 | 0 | 0 | R&R equipment was delivered in Apr-2007, training and commissioning was accomplished in May 2007, 83 R&R units have been distributed until 12-2008, furhter 63 will be distributed in 2009. In addition, two train the trainer workshops were organized in 2007 and 2008. | [15 empty] | 57
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | AFG | SEV | 53 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-30 | 2009-11-30 |  |  | 150000 | 0 | 150000 | 149999.69 | 100% | 0.31 | 0 | 0.31 | 0 | 0 | 0 | 0 | 0 | The new officer travelled to Bangkok to receive induction training from the UNEP regional office. A 3-day Customs Training and Regional Cooperation Workshop to combat illegal trade in ODS in South Asia was held from 29-31 March 2008. The participants of the workshop included representatives from NEPA; UNEP ROAP CAP, UNEP Kabul Office, GTZ – Proklima and Pakistan Customs Department, along with national and provincial level participation on behalf of Government of Afghanistan. From 6-8 July the National Ozone Unit in cooperation with UNEP and the GTZ organized a further training workshop in Good Practices in Refrigeration and the Use of Recovery and Recycling Units for 23 technicians in Kabul. The National Ozone Unit organized this years’ celebration of the International Day for the Preservation of the Ozone Layer in the provinces of Nangarhar and Herat. Awareness raising events including public presentations and screening of the Ozzy Ozone video were organized. Ozone Day was celebrated on 16th September 2008 at the Speen Ghar Hotel in Jallalabad Nangrahar Province. The function was widely attended by the Government officials, University Teachers, school children and general public. Speeches on the importance of the depletion of the Ozone layer were made and awareness literature was distributed. The National Ozone Unit distributed awareness material such as school bags, Pens, Notebooks, stickers and brochures to concerned stakeholders through out the year. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | AFG | PHA | 55 | PRP | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 84332 | 99.21% | 668 | 0 | 668 | 11050 | 0 | 10963.16 | 86.84 | 0 | National consultant finalisation is underway - prepatory work undertaken by NOU. Kick off mission planned in May 2009. | [13 empty] | 2008
FIN | UNEP | Regional workshop for Africa | Individual | AFR | AFR | SEV | 6 | TRA | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1992-12-01 | 1993-12-01 | 210000 | 0 | 210000 | 210000 | 100% | 0 | 0 | 0 | 27300 | 0 | 27300 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 06 | TRA | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [13 empty] | 1992 | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 06 | TRA | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [13 empty] | 1992 | Non-Investment
FIN | UNEP | Regional training course on refrigeration for Africa | Individual | AFR | AFR | REF | 6 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 0 | 1992-12-01 |  | 1992-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 10 | TRA | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1995-07-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 10 | TRA | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-09-01 | 1994-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | South Africa | Industry workshop on the practical implementation of the Protocol for English-speaking countries |  | AFR | AFR | SEV | 11 | TRA | 7 | A | O | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 | 1994-09-01 | 1994-09-01 | 1994-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | UNEP | Follow-up on prior regional workshop and training activities | Individual | AFR | AFR | SEV | 12 | TRA | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-06-01 | 1999-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Support to regional network for ODS officers in Africa (1994) | Individual | AFR | AFR | SEV | 12 | TAS | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-26 | 1995-03-01 |  | 1996-03-01 | 2000-03-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 | 0 | 23400 | 0 | 23400 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for English-speaking African countries | Individual | AFR | AFR | FUM | 16 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1995-09-01 | 1999-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | France | Technology transfer workshop for African countries on practical implementation of the Montreal Protocol |  | AFR | AFR | SEV | 17 | TRA | 11 | A | O | D |  | 0 |  | 0 |  | 1995-07-01 | 1995-12-01 | 1996-01-01 |  | 1996-02-01 | 1996-02-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Exécuté en février 1996 en coopération ave le PNUE. Project completed.
FIN | UNIDO | Preparation of a recovery and recycling projects in Benin, Botswana, Burkina Faso, Gambia, Guinea, Namibia and Senegal | Individual | AFR | AFR | REF | 17 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1997-09-01 | 1999-08-01 | 45000 | -1119 | 43881 | 43881 | 100% | 0 | 0 |  | 5850 | -155 | 5695 | 0 | 0 | FIN
FIN | Australia | Replacement of methyl bromide with non-ozone depleting alternative in grain storage | Individual | AFR | AFR | FUM | 17 | TAS | 14 | A | O | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-10-01 | 1995-11-01 | 38896 | 0 | 38896 | 38896 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | UNDP | Methyl bromide data collection for Africa | Individual | AFR | AFR | FUM | 17 | TAS | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-01-01 |  | 1998-04-01 | 2000-12-01 | 179850 | 0 | 179850 | 179850 | 100% | 0 | 0 | 0 | 23381 | 0 | 23381 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Non-Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for English-speaking Africa | Individual | AFR | AFR | SEV | 19 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | African Network (1996) | Individual | AFR | AFR | SEV | 19 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299400 | 0 | 299400 | 299400 | 100% | 0 | 0 | 0 | 38922 | 0 | 38922 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Regional survey and workshop on methyl bromide for French-speaking African countries | Individual | AFR | AFR | FUM | 21 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1998-04-01 | 1999-03-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | African Region Network (1997) | Individual | AFR | AFR | SEV | 21 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 411000 | -33344 | 377656 | 377656 | 100% | 0 | 0 | 0 | 53430 | -4334.72 | 49095.28 | 0 | 0 | Project financially completed. | $33,344 plus $4,335 PSC returned ExCom 30 | [12 empty] | 1993 | Non Investment
FIN | UNEP | Support to regional network for ODS officers in Africa (1995) | Individual | AFR | AFR | SEV | 16 | TAS | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-01-01 | 232200 | 0 | 232200 | 232200 | 100% | 0 | 0 | 0 | 30186 | 0 | 30186 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | African regional networks for French-speaking and English-speaking countries (1998) | Individual | AFR | AFR | SEV | 23 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-01-01 |  | 1998-12-01 | 2000-03-01 | 431000 | -21369 | 409631 | 409631 | 100% | 0 | 0 | 0 | 56030 | -2777.97 | 53252.03 | 0 | 0 | Project financially completed. | $21,369 plus $2,778 PSC returned ExCom 30 | [12 empty] | 1993 | Non Investment
FIN | UNEP | Africa Region Network (French-speaking and English-speaking) | Individual | AFR | AFR | SEV | 26 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 431000 | -14398 | 416602 | 416602 | 100% | 0 | 0 | 0 | 56030 | -1871.74 | 54158.26 | 0 | 0 | Project financially completed. | $14,398 plus $1,872 PSC returned ExCom 37 | [12 empty] | 1998 | Non Investment
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | AFR | AFR | FUM | 27 | TRA | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2006-02-01 | 80000 | -16044 | 63956 | 63956 | 100% | 0 | 0 | 0 | 10400 | -2086 | 8314.28 | -0.28 | 0 | Project financially completed. | $10,681 plus $1,389 PSC returned ExCom 46; $ -3,506 plus $ -456 returned from ExCom 48 $ 1,857 plus $ 241 returned to ExCom 50 $ 7,012 plus $ 912 returned at ExCom 52 | [12 empty] | 1999 | Non Investment
FIN | UNEP | Regional training workshops on policy development | Individual | AFR | AFR | FUM | 27 | TRA | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2000-03-01 |  | 1999-12-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | African regional network (French-and English-speaking countries) (2000) | Individual | AFR | AFR | SEV | 29 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-01-01 | 452550 | -30254 | 422296 | 422296 | 100% | 0 | 0 | 0 | 58831.5 | -3933 | 54898.48 | 0.02 | 0 | Project financially completed. | $30,000 plus $3900 PSC returned ExCom46; $ 254 plus $ 33 returned from ExCom 49 | [12 empty] | 1999 | Non Investment
FIN | France | Refrigeration and global environment evaluation of equipment modernization study |  | AFR | AFR | REF | 32 | TAS | 26 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-07-23 | 2002-07-01 |  | 2002-12-01 | 2002-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. Final report sent to the Secretariat in Mai 2003.
FIN | UNEP | African regional network (French-speaking, English-speaking) (2001) | Individual | AFR | AFR | SEV | 32 | TAS | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 464000 | -36863 | 427137 | 427137 | 100% | 0 | 0 | 0 | 60320 | -4792.19 | 55527.81 | 0 | 0 | Project financially completed. | $36,863 plus 4,792 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
COM | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | AFR | AFR | FUM | 34 | TRA | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-08-01 | 2002-07-01 |  | 2004-03-01 |  | 80000 | -4610 | 75390 | 55823 | 74.05% | 19567 | 0 | 19567 | 10400 | -599 | 7256.99 | 2544.01 | 0 | Project completed | $ 4,610 plus $ 599 returned to ExCom 50 | [6 empty] | 2003-09-01 | [5 empty] | 2001 | Non Investment
FIN | UNEP | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | Individual | AFR | AFR | SEV | 32 | TAS | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-06-01 |  | 2004-11-04 | 2007-12-01 | 151500 | -22085 | 129415 | 129415 | 100% | 0 | 0 | 0 | 19695 | -2871 | 16823.95 | 0.05 | 0 | Project financially completed. | $15,675 plus $ 2038 PSC returned to ExCom 50 $6,410 plus $833 returned to ExCom 54 | [12 empty] | 2000 | Non Investment
ONG | Germany | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | Halon banking | AFR | AFR | HAL | 35 | TAS | 29 | A | O | I | HAL | 27 |  | 0 |  | 2001-12-01 | 2002-08-01 | 2005-01-01 | 2009-12-01 |  |  | 350000 | 0 | 350000 | 260200 | 74.34% | 89800 | 0 | 89800 | 45500 | 0 | 33826 | 11674 | 0 | The recycling centre in SA is functioning. Stored halons at the SA halon bank is being recycled. Additionally Zimbabwe Power company did undertake a tender process but no local company qualified and now the tender info has been passed on to Namibian companies. it is hoped in the first half of 2009, Zimbabwe would decomission all halons. Botswana too is tendering for their halon conversion. Lesotho is decomissioning the last remaining Halons through the incentive scheme. Namibia has already decomissioned halons in store which will be transported to SA. Other countries namely Kenya, Ethiopia, Tanzania have not responded to repeated requests so it is assumed that there are no halons remaining. | [13 empty] | 2001
FIN | UNDP | Regional surveys in halon and methyl bromide sector | Individual | AFR | AFR | SEV | 36 | TAS | 30 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-11-01 | 2005-10-01 | 30000 | -146 | 29854 | 29854 | 100% | 0 | 0 | 0 | 3900 | -19 | 3881 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Non-Investment
ONG | UNDP | Sectoral phase out programme: establishing a regional halon bank for West and Central Africa (Benin, Burkina Faso, Cameroon, Congo, Congo DR, and Guinea) | Individual | AFR | AFR | HAL | 37 | TAS | 31 | A | O | I | Halon | 61 | 44.2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 | 2009-12-01 |  |  | 300000 | 0 | 300000 | 217492 | 72.5% | 82508 | 0 | 0 | 39000 | 0 | 28273.96 | 10726.04 | 0 | Canceled in 2008. At first, all participating countries were re-contacted. Benin and Burkina Faso have very small quantities of excess halons and did not import halons since 1996 and 1997. Cameroon is still importing halons but the country already exported halons 1211 to the US. Guinea wanted to centralise the excess halons in one place. Decommissioning of halons systems was ongoing in Congo. Meanwhile, we contacted RemTec – USA and looked for other Cies for halon treatment in Nigeria and in South Africa. After discussing the possibilities with the countries concerned in a regional network meeting held in Aug 08 in Cotonou, it was concluded that the original plans would not work out with the limited funds availble. Instead, a proposal was made to use remaining funds through subcontract arrangements, which the countries accepted. However UNDP was informed that this solution - while OK in other sectors - is inleigible for the halons sector which does not have such flexibility. As such, project was Canceled at 56th ExCom meeting and funds will be returned to Excom in 2009. | [13 empty] | 2002 | Non-Investment
ONG | UNDP | Technical assistance for methyl bromide reductions and formulation of regional phase-out strategies for low-volume consuming countries | Individual | AFR | AFR | FUM | 38 | TAS | 32 | A | O | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-02-01 | 2010-01-01 |  |  | 550000 | 0 | 550000 | 402443 | 73.17% | 147557 | 0 | 29511.4 | 70500 | 0 | 51585.8755 | 18914.1245 | 0 | Djibouti, Central African Republic and Congo have finalized the activities and have received payments. Democratic Republic of Congo and Swaziland accepted to participate in the project as non-consuming countries and agreed on a milestone date (March 2009 and June 2009 for DRC). Contracts have been requested and prepared by UNOPS for both countries. Swaziland prepared a work plan and first payment has already been received. DRC requested a new contract (to reflect a change on the name of the contractor) and sent it back (Jan. 2009). Activities are still ongoing in Benin (the NOU finally approved the contact extension). Sudan needs a new technical expert to finalize the activities. 3 candidates have been identified and the selection process may be finalized in February 2009. It will be followed by procurement and installation of purchased equipment. The national expert has been contacted and he's preparing a report to facilitate the transition with the new expert. | [13 empty] | 2002 | Non-Investment
ONG | UNEP | Sub-regional project on harmonisation of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in English-speaking Africa | Individual | AFR | AFR | SEV | 45 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-12-01 | 2009-12-01 |  |  | 140000 | 0 | 140000 | 70000.19 | 50% | 69999.81 | 10000 | 69999.81 | 18200 | 0 | 9100.0247 | 9099.9753 | 1300 | COMESA approved Regional ODS Regulations, MOU was agreed with ECOWAS and identification of expert was done to draft the ECOWAS ODS Regulations | [13 empty] | 2005 | Non Investment
ONG | Germany | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 34 | A | O | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2006-09-06 | 2009-09-01 | 2010-08-01 |  |  | 192500 | 0 | 192500 | 115915.75 | 60.22% | 76584.25 | 0 | 10000 | 25025 | 0 | 15069.0475 | 9955.9525 | 0 | During 2008, UNIDO finalized the surveys and established work plan for each country. GTZ assisted UNIDO on these activities and followed up with project partners.
ONG | Japan | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 35 | A | O | I | CFC | 0 |  | 0 |  | 2006-04-01 |  | 2009-09-01 | 2009-09-01 |  |  | 700000 | 0 | 700000 |  | 0% | 700000 |  |  | 91000 | 0 |  | 91000 |  | The German Government committed external resources to enable organize a regional workshop. The Strategic Workshop on Energy Efficient Replacements of CFC Chillers in Africa took place in Cairo during the period 19—21 September 2006 with the participation
ONG | France | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 36 | A | O | I | CFC | 0 |  | 0 |  | 2006-04-01 |  | 2009-09-01 | 2010-03-01 |  |  | 360000 | 0 | 360000 | 0 | 0% | 360000 |  | 50000 | 46800 | 0 | 0 | 46800 |  | The French contribution is implemented by UNIDO. The financial agreement in between UNIDO and AFD was signed and funds transferred. Each country prepared a strategy for dealing with the chiller sector. The national steering committees in Egypt was established and is working on the overall procedures for the project implementation while other countries are working on establishing the steering committee. Activities for replacing the chillers will start in March 2009.
ONG | UNIDO | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 37 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2009-09-01 | 2010-03-01 |  |  | 747500 | 0 | 747500 | 194064 | 25.96% | 553436 | 38146 | 150000 | 56063 | 0 | 14555 | 41508 | 2861 | Each country prepared a strategy for dealing with the chiller sector. The national steering committees in Egypt was established and is working on the overall procedures for the project implementation, while other countries are working on establishing the steering committee. Activities for replacing the chillers will start in March 2009. | [13 empty] | 2006 | INV
ONG | UNEP | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-30 | 2009-11-30 |  |  | 160000 | 0 | 160000 | 143010.96 | 89.38% | 16989.04 | 11359.52 | 16989.04 | 20800 | 0 | 18591.4248 | 2208.5752 | 1476.7376 | Customs Enforcement Networks were established and are operational in COMESA, CEMAC and UEMOA | [13 empty] | 2007 | Non Investment
ONG | France | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 39 | A | O | I | CFC | 0 |  | 0 |  | 2007-11-01 |  | 2009-11-01 | 2010-03-01 |  |  | 75000 | 0 | 75000 |  | 0% | 75000 |  | 60000 | 9750 | 0 |  | 9750 |  | This project is implemented in cooperation with UNEP. The French contribution not being foreseen for travel expenses, the identification of the right beneficiairy took longer than foreseen. However, a cross boarder training institution has now been identified.
ONG | UNIDO | Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia) | Individual | AFR | AFR | FUM | 54 | DEM | 40 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-06-01 | 2010-03-31 | 2010-03-01 |  |  | 306812 | 0 | 306812 | 35803 | 11.67% | 271009 | 23668 | 100000 | 23011 | 0 | 2685 | 20326 | 1775 | During 2008 subcontract was made with the local dates producer and laboratory in Algeria to undertake treatment and tests of dates. Due to difficulties in supplying the chemicals to the country the first laboratory tests were undertaken in France. The tests showed positive results. The detailed analysis is under preparation. During 2009 large-scale test are planned for both countries. | [13 empty] | 2008 | INV
FIN | UNEP | Preparation of country programme | Individual | EUR | ALB | SEV | 30 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-06-01 | 2005-12-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 | 0 | 7800 | -3770 | 4030 | 0 | 0 | Project financially completed. | $29,000 plus 3,770 PSC returned ExCom 46 | [5 empty] | 2002-09-01 | [6 empty] | 2000 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | ALB | SEV | 35 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | ALB | PHA | 36 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-07-01 |  | 2003-12-01 | 2004-12-01 | 40000 | -458 | 39542 | 39542 | 100% | 0 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNEP | Establishment of the Ozone Unit (second year) | Individual | EUR | ALB | SEV | 38 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2003-12-01 |  | 2005-07-01 | 2007-06-01 | 54600 | 0 | 54600 | 54600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNIDO | National ozone depleting substances phase-out plan: refrigerant recovery and recycling network | Multi-Year | EUR | ALB | PHA | 39 | TAS | 5 | A | O | I | CFC | 6.8 | 6.8 |  |  | 2003-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-12-01 | 2008-09-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Financial completion in Sep 2008. FIN: Total disbursement = Total approval. | [9 empty] | 2005-06-01 | 2006-12-01 |  |  | 2002 |  | 61.2 | 36.57 |  |  | Yes | Yes | Yes
FIN | UNEP | National ODS phase-out plan: training of customs officers in monitoring of ODS | Multi-year | EUR | ALB | PHA | 39 | TRA | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2005-08-01 | 2007-04-01 | 35700 | -278 | 35422 | 35422 | 100% | 0 | 0 | 0 | 4641 | -36 | 4604.86 | 0.14 | 0 | Project financially completed. | $ 278 plus $ 36 PSC returned at ExCom 52 | [12 empty] | 2003 | Non Investment
COM | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | Multi-year | EUR | ALB | PHA | 39 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2006-07-01 |  | 82425 | -6805 | 75620 | 50022.95 | 66.15% | 25597.05 | 0 | 25597.05 | 10715.25 | -885 | 6502.9835 | 3327.2665 | 0 | Project completed | $6,805 plus $885 PSC returned at ExCom 53 | [8 empty] | 2005-07-01 |  |  |  | 2003 | Non Investment
FIN | UNIDO | National ozone depleting substances phase-out plan: awareness workshop to prevent the introduction of methyl bromide | Multi-Year | EUR | ALB | PHA | 39 | TAS | 8 | A | O | I | MBR | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2005-09-01 | 20000 | -319 | 19681 | 19681 | 100% | 0 | 0 |  | 1500 | -26 | 1474 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | National ozone depleting substances phase-out plan: programme management and auditing | Multi-Year | EUR | ALB | PHA | 39 | TAS | 9 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2005-04-01 | 2009-12-01 |  | 2007-12-01 | 2008-07-01 | 16068 | 0 | 16068 | 16068 | 100% | 0 | 0 |  | 1205 | 0 | 1205 | 0 | 0 | Financial completion in Jul 2008. FIN: Total disbursement = Total approval. | [10 empty] | 2009-12-01 |  |  | 2003
FIN | UNIDO | National ozone depleting substances phase-out plan: conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Energy Combinat Ltd., Elbasan | Multi-Year | EUR | ALB | PHA | 39 | INV | 10 | A | O | I | CTC | 2.3 | 2.3 |  |  | 2003-04-01 | 2005-09-01 | 2005-04-01 |  | 2005-12-01 | 2007-09-01 | 45000 | -192 | 44808 | 44808 | 100% | 0 | 0 |  | 3375 | -14 | 3361 | 0 | 0 | FIN | [13 empty] | 2002 |  | 15.2 | 15.19 |  |  | Yes | Yes | Yes
COM | UNIDO | National ODS phase out plan (2nd tranche) | Multi-Year | EUR | ALB | PHA | 46 | INV | 11 | A | O | I | CFC | 25 | 25 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-04-01 |  | 172322 | 0 | 172322 | 171305 | 99.41% | 1017 | 1017 | 1000 | 12924 | 0 | 12848 | 76 | 76 | Project completed in Apr 2008. | [13 empty] | 2005 | INV | 36.2 | 14.4 |  |  | Yes | Yes | Yes
FIN | UNEP | Renewal of institutional strengthening project (phase I, year 3) | Individual | EUR | ALB | SEV | 46 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2007-07-01 |  | 2006-07-01 | 2008-03-01 | 54600 | 0 | 54600 | 54599.86 | 100% | 0.14 | 0 | 0.14 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase II) | Individual | EUR | ALB | SEV | 49 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-08-01 | 2008-06-30 |  | 2008-06-30 |  | 109200 | 0 | 109200 | 72906.97 | 66.76% | 36293.03 | 0 | 36293.03 | 0 | 0 | 0 | 0 | 0 | Project completed in June 2008 | [13 empty] | 2006 | Non Investment
ONG | UNIDO | National ODS phase out plan (3rd tranche) | Multi-Year | EUR | ALB | PHA | 50 | INV | 14 | A | O | I | CFC | 21 | 21 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 | 2009-12-01 |  |  | 72322 | 0 | 72322 | 45409 | 62.79% | 26913 | 3350 | 3000 | 5424 | 0 | 3406 | 2018 | 251 | Procurement of tools and equipment for service workshop was done in 2008 and under the third tranche R&R equipment was ordered and delivered. | [13 empty] | 2006 | INV | 6.2 | 6.2 |  |  | Yes | No | No
ONG | UNIDO | National ODS phase out plan (fourth and fifth tranches) | Multi-Year | EUR | ALB | PHA | 54 | INV | 15 | A | O | I | CFC | 13 | 10.8 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2009-12-01 |  |  | 64644 | 0 | 64644 | 123 | 0.1903% | 64521 | 0 | 10000 | 4848 | 0 | 9 | 4839 | 0 | The fourth and fifth tranches were approved at 54th ExCom Meeting. Translation of manuals and training works are planned in 2009. Management and monitoring programme are ongoing. R+R equipment delivered. Translation of manuals and training works planed for 1st quarter 2009. | [13 empty] | 2008 | INV
ONG | UNEP | Renewal of institutional strengthening project (phase III) | Individual | EUR | ALB | SEV | 54 | INS | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2010-06-30 | 2010-06-30 |  |  | 109200 | 0 | 109200 | 0 | 0% | 109200 | 88775 | 109200 | 0 | 0 | 0 | 0 | 0 | SSFA signed by both parties. NOU is implementing investment components of NPP (with UNIDO). NOU actively participating in the ECA network activities. NOU hosted ECA annual network meeting in March 2008 | [13 empty] | 2008
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | ALB | PHA | 55 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 1648 | 5.493% | 28352 | 0 | 10000 | 2250 | 0 | 124 | 2126 | 0 | National consultants were recruited to conduct HCFC survey and to update the existing legislation. | Two national consultants hired, visits to 20 companies undertaken and presently report is under preparation by them. Consultants working on legislation for importing and consumption of HCFC. Initial workshop will be organized upon completion of the survey. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | AFR | ALG | SEV | 9 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1993-06-01 |  | 1993-11-01 | 1994-12-01 | 15000 | 3000 | 18000 | 18000 | 100% | 0 | 0 | 0 | 1950 | 390 | 2340 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Institutional support for ODS phase-out | Individual | AFR | ALG | SEV | 11 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-01-01 | 1996-11-01 |  | 1999-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 | 0 | 38610 | 0 | 38610 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1993 | Non Investment
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production at ENIEM | Individual | AFR | ALG | SEV | 12 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-08-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -675 | 24325 | 24325 | 100% | 0 | 0 |  | 3250 | -93 | 3157 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the aerosol production and solvent conversion at ENAD | Individual | AFR | ALG | SEV | 12 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -5049 | 19951 | 19951 | 100% | 0 | 0 |  | 3250 | -661 | 2589 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects |  | AFR | ALG | SEV | 12 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -93039 | 6961 | 6961 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of an investment project for the phase-out of CFC-11 in the manufacture of sandwich panels at Prosider (Annaba-Algeria) | Individual | AFR | ALG | FOA | 15 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -1584 | 23416 | 23416 | 100% | 0 | 0 |  | 3250 | -211 | 3039 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for establishment of a National Centre for recovery and recycling CFC-11, CFC-12 and CFC-502 | Individual | AFR | ALG | REF | 15 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1998-11-01 | 1995-06-01 |  | 1999-12-01 | 2001-11-01 | 25000 | -8254 | 16746 | 16746 | 100% | 0 | 0 |  | 3250 | -1077 | 2173 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of an investment project for CFC phase-out in the production of rigid foam at Batimetal | Individual | AFR | ALG | FOA | 15 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -4245 | 20755 | 20755 | 100% | 0 | 0 |  | 3250 | -556 | 2694 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise Nationale des Industries de l'Electromenager, ENIEM | Individual | AFR | ALG | REF | 15 | INV | 9 | A | O | I | CFC | 425 | 425 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2002-09-01 | 6589550 | -82919 | 6506631 | 6506631 | 100% | 0 | 0 |  | 856642 | -12121 | 844521 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise nationale des Detergents (ENAD-Lames) | Individual | AFR | ALG | SOL | 17 | INV | 10 | A | O | I | CFC | 5.6 | 5.6 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-06-01 | 2001-03-01 | 109900 | -606 | 109294 | 109294 | 100% | 0 | 0 |  | 14287 | -101 | 14186 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phasing out ODS in small- and medium-scale industries | Individual | AFR | ALG | SEV | 17 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1996-01-01 |  | 1999-12-01 | 2001-03-01 | 50000 | -1409 | 48591 | 48591 | 100% | 0 | 0 |  | 6500 | -193 | 6307 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNIDO | Phasing out of CFCs at Entreprise Nationale des Detergents (ENAD) | Individual | AFR | ALG | ARS | 18 | INV | 12 | A | O | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 2002-05-01 | 614850 | 0 | 614850 | 614850 | 100% | 0 | 0 |  | 79931 | -46 | 79885 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels by discontinuous method at Prosider Berrahal | Individual | AFR | ALG | FOA | 19 | INV | 13 | A | O | I | CFC | 82 | 82 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  |  | 2003-03-01 | 434500 | -564 | 433936 | 433936 | 100% | 0 | 0 |  | 56485 | -163 | 56322 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels at Batimetal Beni Mansour | Individual | AFR | ALG | FOA | 19 | INV | 14 | A | O | I | CFC | 110 | 110 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 1998-12-01 | 2003-03-01 | 496650 | 0 | 496650 | 496650 | 100% | 0 | 0 |  | 64565 | -78 | 64487 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Etablissement Has Mohamed | Individual | AFR | ALG | ARS | 20 | INV | 15 | A | O | I | CFC | 22.5 | 22.5 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 82018 | 0 | 82018 | 82018 | 100% | 0 | 0 |  | 10662 | -2 | 10660 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Vague de Fraicheur | Individual | AFR | ALG | ARS | 20 | INV | 16 | A | O | I | CFC | 51.4 | 51.4 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2001-12-01 | 164623 | 0 | 164623 | 164623 | 100% | 0 | 0 |  | 21401 | -13 | 21388 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ets. Wouroud | Individual | AFR | ALG | ARS | 20 | INV | 17 | A | O | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 187772 | -420 | 187352 | 187352 | 100% | 0 | 0 |  | 24410 | -93 | 24317 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Laboratoire Bendi | Individual | AFR | ALG | ARS | 20 | INV | 18 | A | O | I | CFC | 19.2 | 19.2 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  |  | 2002-05-01 | 56790 | -3005 | 53785 | 53785 | 100% | 0 | 0 |  | 7383 | -402 | 6981 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFCs at Ets. COPHYD | Individual | AFR | ALG | ARS | 20 | INV | 19 | A | O | I | CFC | 15 | 15 |  |  | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1997-07-01 | 1999-08-01 | 53024 | -1291 | 51733 | 51733 | 100% | 0 | 0 |  | 6893 | -178 | 6715 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of investment projects in the aerosol, foam and refrigeration sectors | Individual | AFR | ALG | SEV | 21 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-05-01 | 1997-08-01 |  | 1998-02-01 | 2002-09-01 | 50000 | -2690 | 47310 | 47310 | 100% | 0 | 0 |  | 6500 | -359 | 6141 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Ets Leulmi Essaid flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 21 | A | O | I | CFC | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1998-06-01 |  |  | 2002-09-01 | 61880 | -55372 | 6508 | 6508 | 100% | 0 | 0 |  | 8044 | -7199 | 845 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 at Snam flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 22 | A | O | I | CFC | 32 | 32 |  |  | 1997-05-01 | 1997-11-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 88360 | -408 | 87952 | 87952 | 100% | 0 | 0 |  | 11487 | -71 | 11416 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sammo flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 23 | A | O | I | CFC | 24 | 24 |  |  | 1997-05-01 | 1997-10-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 98770 | -1411 | 97359 | 97359 | 100% | 0 | 0 |  | 12840 | -203 | 12637 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ALG | FUM | 22 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1998-06-01 |  | 2000-01-01 | 2000-07-01 | 8000 | -3793 | 4207 | 4207 | 100% | 0 | 0 |  | 1040 | -494 | 546 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at La Mousse du Sud flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 23 | INV | 25 | A | O | I | CFC | 95 | 95 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-10-01 | 2003-07-01 | 553480 | -1430 | 552050 | 552050 | 100% | 0 | 0 |  | 71952 | -299 | 71653 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC 134a for commercial refrigeration at Enapat | Individual | AFR | ALG | REF | 25 | INV | 26 | A | O | I | CFC | 9.2 | 9.2 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 1998-12-01 | 2000-12-01 | 139932 | -16937 | 122995 | 122995 | 100% | 0 | 0 |  | 18191 | -2227 | 15964 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Matelas Djurdjura | Individual | AFR | ALG | FOA | 25 | INV | 27 | A | O | I | CFC | 28 | 28 |  |  | 1998-07-01 | 1998-12-01 | 1999-08-01 |  | 2001-07-01 | 2002-09-01 | 82608 | -753 | 81855 | 81855 | 100% | 0 | 0 |  | 10739 | -115 | 10624 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with hydrocarbons in the aerosol sector at Ets Djadir | Individual | AFR | ALG | ARS | 25 | INV | 28 | A | O | I | CFC | 38.4 | 38.4 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2000-12-01 | 2002-08-01 | 147807 | -316 | 147491 | 147491 | 100% | 0 | 0 |  | 19215 | -72 | 19143 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Maghreb Mousse | Individual | AFR | ALG | FOA | 26 | INV | 29 | A | O | I | CFC | 24 | 24 |  |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 2001-07-01 | 2002-09-01 | 96492 | -500 | 95992 | 95992 | 100% | 0 | 0 |  | 12544 | -85 | 12459 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for domestic refrigeration at Enapem | Individual | AFR | ALG | REF | 26 | INV | 30 | A | O | I | CFC | 12.8 | 12.8 |  |  | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 167332 | -2890 | 164442 | 164442 | 100% | 0 | 0 |  | 21753 | -409 | 21344 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the foam sector (flexible) | Individual | AFR | ALG | FOA | 27 | PRP | 31 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 18000 | -20 | 17980 | 17980 | 100% | 0 | 0 |  | 2340 | -6 | 2334 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening - Phase II | Individual | AFR | ALG | SEV | 27 | INS | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2003-06-01 | 90010 | 0 | 90010 | 90010 | 100% | 0 | 0 | 0 | 11701.3 | 0 | 11701.3 | 0 | 0 | Project financially completed. | [5 empty] | 2002-06-01 | [7 empty] | 1999 | Non Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Matelas Atlas (Sam Atlas) | Individual | AFR | ALG | FOA | 27 | INV | 33 | A | O | I | CFC | 22 | 22 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2004-03-01 | 120060 | 0 | 120060 | 120060 | 100% | 0 | 0 |  | 15608 | 0 | 15608 | 0 | 0 | FIN |  |  |  |  | 2001-07-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at King's Matelas | Individual | AFR | ALG | FOA | 27 | INV | 34 | A | O | I | CFC | 20 | 20 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2003-07-01 | 110179 | -38 | 110141 | 110141 | 100% | 0 | 0 |  | 14323 | -27 | 14296 | 0 | 0 | FIN |  |  |  |  | 2001-07-01
FIN | UNIDO | Project preparation in the commercial refrigeration sector (commercial) | Individual | AFR | ALG | REF | 27 | PRP | 35 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-10-01 | 1999-12-01 |  | 2000-11-01 | 2001-07-01 | 15000 | -11980 | 3020 | 3020 | 100% | 0 | 0 |  | 1950 | -1558 | 392 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | AFR | ALG | ARS | 27 | PRP | 36 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-11-01 | 2001-09-01 | 15000 | -598 | 14402 | 14402 | 100% | 0 | 0 |  | 1950 | -81 | 1869 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Matelas Mondial | Individual | AFR | ALG | FOA | 28 | INV | 37 | A | O | I | CFC | 20 | 20 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 97986 | -66 | 97920 | 97920 | 100% | 0 | 0 |  | 12738 | -29 | 12709 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC11/CFC12 by conversion to hydrocarbons technology in the manufacture of aerosols at Floreal | Individual | AFR | ALG | ARS | 28 | INV | 38 | A | O | I | CFC | 18.1 | 18.1 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-07-01 | 2002-09-01 | 77145 | -78 | 77067 | 77067 | 100% | 0 | 0 |  | 10029 | -26 | 10003 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Orania Mousse Ameublement (OMA) | Individual | AFR | ALG | FOA | 28 | INV | 39 | A | O | I | CFC | 18 | 18 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 99477 | -104 | 99373 | 99373 | 100% | 0 | 0 |  | 12932 | -34 | 12898 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | AFR | ALG | FOA | 30 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1 | 19999 | 19999 | 100% | 0 | 0 |  | 2600 | -4 | 2596 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11/CFC-12 by conversion to hydrocarbon technology in the manufacture of aerosols at company Saco | Individual | AFR | ALG | ARS | 28 | INV | 41 | A | O | I | CFC | 19 | 19 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2002-02-01 | 2003-05-01 | 73691 | -74 | 73617 | 73617 | 100% | 0 | 0 |  | 9580 | -25 | 9555 | 0 | 0 | FIN | [6 empty] | 2002-03-01
FIN | Germany | Project preparation, technical assistance in the halon sector | Individual | AFR | ALG | HAL | 31 | PRP | 42 | A | O | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-01-01 | 2002-01-01 |  | 2001-06-01 | 2002-03-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project document submitted and approved. | [13 empty] | 1999
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | AFR | ALG | REF | 31 | PRP | 43 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-06-01 | 2002-01-01 |  | 2003-01-01 | 2003-06-01 | 60000 | -1013 | 58987 | 58987 | 100% | 0 | 0 |  | 7800 | -144 | 7656 | 0 | 0 | FIN
FIN | Germany | Conversion of Algeria Mousse Polyurethane (AMP) | Individual | AFR | ALG | FOA | 31 | INV | 44 | A | O | I | CFC | 152 | 152 | 0 |  | 2000-07-01 | 2000-08-01 | 2003-08-01 |  | 2004-12-01 | 2007-12-01 | 565728 | 0 | 565728 | 565728 | 100% | 0 | 0 | 0 | 73545 | 0 | 73545 | 0 | 0 | Project completed. PCR has been submitted to the country | [13 empty] | 2002
FIN | Germany | Conversion of SOFTPM, Choupot Oran, to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 45 | A | O | I | CFC | 80 | 80 | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 | 0 | 64792 | 0 | 64792 | 0 | 0 | Project completed. PCR has been submitted to the country | [13 empty] | 2002
FIN | Germany | Conversion of Matelas Souf to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 46 | A | O | I | CFC | 95 | 95 | 0 |  | 2000-12-01 | 2001-01-11 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 561379 | 0 | 561379 | 561379 | 100% | 0 | 0 | 0 | 72979 | 0 | 72979 | 0 | 0 | Project completed. PCR has been submitted to the country | [13 empty] | 2002
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the RCA (Société de Réfrigeration et de Conditionnement de l'air) | Individual | AFR | ALG | REF | 32 | INV | 47 | A | O | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-07-01 | 2003-05-01 |  | 2003-12-01 | 2004-12-01 | 351768 | -5863 | 345905 | 345905 | 100% | 0 | 0 |  | 45730 | -834 | 44896 | 0 | 0 | FIN
FIN | Germany | Project preparation in the solvent sector | Individual | AFR | ALG | SOL | 33 | PRP | 48 | A | O | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed. Strategy will be included in NPP. | [13 empty] | 2002
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector | Individual | AFR | ALG | FOA | 33 | PRP | 49 | A | O | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30900 | 0 | 30900 | 30900 | 100% | 0 | 0 | 0 | 4017 | 0 | 4017 | 0 | 0 | Project completed. A report has been prepared and will be used in preparation of the terminal phase out plan. | [13 empty] | 2002
ONG | UNIDO | Project preparation to replace methyl bromide in fumigation of dates in ten units | Individual | AFR | ALG | FUM | 34 | PRP | 50 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 | 2010-12-01 |  |  | 25000 | 0 | 25000 | 12720 | 50.88% | 12280 | 611 | 600 | 3250 | 0 | 1654 | 1596 | 79 | The MBTOC has not yet identified any alternatives applicable for the fumigation of palm dates. DEMO project is ongoing to identify potential alternatives. The project preparation will stem from the result of that project (results expected in 2010). | [13 empty] | 2001 | INV
COM | Germany | Sectoral phase out programme: establishment of a halon bank | Individual | AFR | ALG | HAL | 35 | TAS | 51 | A | O | I | HAL | 392.3 | 392.3 | 0 |  | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2007-12-01 |  | 259500 | 0 | 259500 | 259500 | 100% | 0 | 0 | 0 | 33735 | 0 | 33735 | 0 | 0 | Project is completed, PCR in preparation. The contract with Gaz Industriel was finished.
CLO | UNIDO | Preparation of 8 investment projects in the aerosol sector | Individual | AFR | ALG | ARS | 36 | PRP | 52 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of a refrigeration sectoral phase-out plan | Individual | AFR | ALG | REF | 36 | PRP | 53 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-07-01 |  | 2004-12-01 | 2005-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | AFR | ALG | SEV | 37 | INS | 54 | A | T | I | CFC | 21.2 | 21.2 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2006-07-01 | 2007-07-01 | 257000 | -1 | 256999 | 256999 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | US$ 1 returned to ExCom 55 | [12 empty] | 2002 | Non Investment
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector (includes: training in good refrigerant management practices, training of customs officers, and national recovery and recycling) | Multi-Year | AFR | ALG | REF | 37 | TAS | 55 | A | O | I | CFC | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2003-12-01 |  | 2004-06-01 | 2004-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | -6 | 25994 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV | 0 | 0 |  |  | Yes | Yes | Yes
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the first group of commercial refrigerator manufacturers | Individual | AFR | ALG | REF | 37 | INV | 56 | A | O | I | CFC | 18.6 | 18.6 |  |  | 2002-07-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2006-12-01 | 224320 | -22701 | 201619 | 201619 | 100% | 0 | 0 |  | 29162 | -2952 | 26210 | 0 | 0 | FIN | [13 empty] | 2002 | INV
CLO | Germany | Project preparation for terminal ODS phase out management plan, excluding the refrigeration sector | Individual | AFR | ALG | PHA | 37 | PRP | 57 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  |  | 2007-09-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | The TPMP preparation was cancelled by the Government of Algeria long after the work was completely prepared. The results will be used by UNIDO.
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector (including training in good refrigerant management practices, training of customs officers, and national recovery and recycling): Second tranche | Multi-Year | AFR | ALG | REF | 39 | TAS | 58 | A | O | I | CFC | 45 | 110 |  |  | 2003-04-01 | 2004-03-01 | 2004-04-01 |  | 2005-06-01 | 2007-05-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | FIN | [13 empty] | 2003 |  | 0 | 0 |  |  | Yes | Yes | Yes
COM | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector: 2004 programme | Multi-Year | AFR | ALG | REF | 42 | TAS | 59 | A | O | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2007-11-01 |  | 524647 | 0 | 524647 | 512104 | 97.61% | 12543 | 0 | 1 | 39349 | 0 | 38408 | 941 | 0 | Financial completion in Dec 2008. | [13 empty] | 2004 | INV | 0 | 0 |  |  | N/A | N/A | N/A
CLO | Germany | Development of a country programme update | Individual | AFR | ALG | SEV | 43 | CPG | 60 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-09-01 | 2005-07-01 |  |  | 2007-09-01 | 13500 | 0 | 13500 | 13500 | 100% | 0 | 0 | 0 | 1215 | 0 | 1215 | 0 | 0 | The CPU update was cancelled by the Government of Algeria. The results have been used by UNIDO for the National Phase Out Plan.
ONG | UNIDO | Conversion of CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the last group of commercial refrigerator manufactures ( refrigeration sector terminal project) | Individual | AFR | ALG | REF | 44 | INV | 62 | A | O | I | CFC | 72.8 | 72.8 |  |  | 2004-12-01 | 2006-03-01 | 2007-04-01 | 2009-04-01 |  |  | 589000 | 0 | 589000 | 169977 | 28.86% | 419023 | 159030 | 150000 | 44175 | 0 | 12748 | 31427 | 11927 | The two foaming machines were purchased following a process of intenational competitive bidding. The machines should be delivered in April 2009. The request for proposal to supply services related for the training on the development of prototypes has to be reannounced since none of the French Institutes identified was interested in bidding for the project. The ozone office agreed to re-intiate the bid accepting that the training will be conducted in English with the assistance of a translator. | [13 empty] | 2004 | INV
COM | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | ALG | PHA | 46 | PRP | 63 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-04-01 | 2006-03-01 |  | 2008-04-01 |  | 25000 | 0 | 25000 | 23404 | 93.62% | 1596 | 0 | 1 | 1875 | 0 | 1755 | 120 | 0 | Project completed in Apr 2008. Financial completion in Dec 2008. | [13 empty] | 2005 | NON-INV
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ALG | SEV | 48 | INS | 64 | A | T | I | CFC | 21.3 | 21.3 | 0 | 0 | 2006-04-01 | 0 | 2008-04-01 |  | 2008-12-01 |  | 257400 | 0 | 257400 | 181035.14 | 70.33% | 76364.86 | 76350 | 76364.86 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. Renewal request submitted to 57 ExCom meeting. NOU is is charge of implementation of NPP, as well as IS activities (public awareness, data reporting, etc.) | [13 empty] | 2006 | Non Investment
COM | UNIDO | Technical assistance to phase out methyl bromide in pulses disinfestations | Individual | AFR | ALG | FUM | 50 | TAS | 65 | A | O | I | MBR | 1.6 | 1.6 |  |  | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2008-12-01 |  | 51000 | 0 | 51000 | 34543 | 67.73% | 16457 | 16412 | 15500 | 4590 | 0 | 3109 | 1481 | 1477 | Training and the last set of equipment was procured. Project completed in Dec 2008. | [13 empty] | 2006 | INV
FIN | UNIDO | Project preparation for an ODS phase-out management plan | Individual | AFR | ALG | PHA | 51 | PRP | 66 | A | O | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2007-11-01 | 2007-12-01 | 15000 | -882 | 14118 | 14118 | 100% | 0 | 0 |  | 1125 | -66 | 1059 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2007 | NON-INV
ONG | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | ALG | PHA | 53 | INV | 67 | A | O | I | CFC TCA | 50.5 | 0 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 | 2009-12-01 |  |  | 723500 | 0 | 723500 | 34684 | 4.794% | 688816 | 1679 | 50000 | 54263 | 0 | 2601 | 51662 | 126 | Survey of the refrigeration service sector and foam sector was completed by the NOU. Equipment for the service wroskhops are under procurement. Investment activities are under preparation for the phase-out CFCs in the foam sector. A national expert for the review and update of ODS legislation has completed his assignment. Contract for the update of the refrigeration curricula and the preparation of the Code of Practice was awarded and is under preparation. Training of customs master trainers is planned for May 2009. | [13 empty] | 2007 | INV | 225.6 | 221.7 |  |  | Yes | Yes | Yes
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | ALG | PHA | 55 | PRP | 68 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 7148 | 8.409% | 77852 | 0 | 50000 | 6375 | 0 | 536 | 5839 | 0 | Recruitment of national experts for the data collection as well as the preparation of the kick-off meeting has started and are ongoing. | Subcontract for the preparation of the HPMP is ongoing. It includes: • Assistance for policy and legislation; • Survey of HCFCs use and analysis of data collectes; • Consultation with national stackeholders in the data collection and analysis. Regarding the policy aspect, the subcantroc is requested to assess and analyze the institutional framework, legislation, licensing and quota system regulating consumption of ozone depleting substances in Algeria with particular focus on HCFCs. The contractor is also requested to assess the current national policies on climate change, chemical management and energy policies, as well as the CFCs phase out activities and lessons learned from previous ODS phase-out activities. Expected outputs: assessment of the current status of legislation and recommendations on necessary institutional and regulatory improvements to facilitate a smooth compliance with the HCFCs phase out obligations. | [12 empty] | 2008 | NON-INV
TRF | UNEP | Preparation of country programme | Individual | AFR | ANG | SEV | 32 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2002-04-01 |  |  | 2001-12-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Project transferred | $60,000 plus $7800 returned ExCom 34 | [12 empty] | 2000 | Non Investment
FIN | Germany | Country programme preparation | Individual | AFR | ANG | SEV | 34 | CPG | 2 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | National consultants contracted, survey on ODS consump finalized, Country Programme prepared and submitted together with prop. for I.S. Angola. Aproved at 38th ExCom. (1st instalment of 1st tranche of IS funding of 81000) Request for 2nd instalment of IS | [13 empty] | 1998
FIN | Germany | Establishment of the Ozone Unit | Individual | AFR | ANG | SEV | 38 | INS | 3 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-06-01 | 71682 | 141618 | 213300 | 213300 | 100% | 0 | 0 | 0 | 9319 | 18411 | 27730 | 0 | 0 | 1st phase of Institutional Strengthening project is completed. - the infrastructure of the NOU-office in Luanda has been completed, with internet and telepone / fax connection. - Regional support groups have been created in serveral of Angolas provinces in order to assist NOU in data collection, public awareness activities, etc.- ODS data up to reporting year 2006 have been submitted to both Ozone Secretariat and Multilateral Fund Secretariat. - Angola is in compliance with phase-out schedule and data reporting obligations. | [13 empty] | 1998
ONG | Germany | Implementation of the RMP: enforcement of regulations, training of customs officers, training of refrigeration service technicians, recovery and recycling, incentive programme for end-users, and public awareness | RMP Update | AFR | ANG | REF | 39 | TAS | 4 | A | O | I | CFC | 97.6 | 97.8 | 0 | 0 | 2003-04-01 | 2003-11-01 | 2008-04-01 | 2009-06-30 |  |  | 700000 | 0 | 700000 | 671200 | 95.89% | 28800 | 0 | 28800 | 87000 | 0 | 83420.5714 | 3579.4286 | 0 | Additional Training courses in Refrigeration Sector were conducted in Huige and Huambo Provices.- A public awareness campaign has been launched in the provinces of Huila, Moxico, Huambo, Bie and Malange, with the additional aim of formation of interministerial support groups.- Working group of legal experts has been created in order to finalize and submit draft on ODS related legislation and regulations. - Survey has been undertaken in provinces and Luanda in order to identify ODS consuming companies which may qualify for Incentive programme. - R&R centre has been established in Huambo (Central Angola). 1st Customs Training was done in Luanda during January 08, 2nd & 03rd Customs Training in the towns of Namibe and Benguela respectively are planned for January 2009. Together with National Customs office for identification of CFCs is going to be established at border with Namibia during May 2009. Establishment for another identification office in Luanda is planned for May 2009 with CFC identifyers already supplied throug gtz-Proklima. - According to Angolan NOU enforcement of ODS related legislation can be expected for May/June 2009. Remaining funds will then be spent, completion of RMP is expected for June 2009. | [13 empty] | 1998
ONG | Germany | Extension of the institutional strengthening project (phase II) | Individual | AFR | ANG | SEV | 50 | INS | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 | 2009-04-01 |  |  | 134400 | 0 | 134400 | 134400 | 100% | 0 | 0 | 0 | 17472 | 0 | 17472 | 0 | 0 | NOU moved into the building of the Ministry (Urbanism & Environment). NOU collected and reported data for 2006, preparations for reporting of ODS data for 2007 has started. - After General elections in Angola restructuring of Government took place. Angolan NOU is now part of newly created Ministry of Environment. According to NOU ODS data for 2007 have been reported to Ozone Secretariat and MFsecretariat. - Funds approved for ISP-II have been spent, and accordingly programme is concluded during December 2008. Financial completion is expected for May/June 2009. | [13 empty] | 1998
ONG | UNEP | Project preparation for a terminal phase-out management plan | Individual | AFR | ANG | PHA | 51 | PRP | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  |  | 18000 | 0 | 18000 | 13000 | 72.22% | 5000 | 5000 | 5000 | 2340 | 0 | 1690 | 650 | 650 | TPMP was prepared and finalised. Submission for approval awaiting country to approval ODS Regulations and ratify Montreal Protocol Ammendments | [13 empty] | 2007 | Non Investment
ONG | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ANG | PHA | 51 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-04-01 | 2008-03-01 | 2010-01-01 |  |  | 12000 | 0 | 12000 | 380 | 3.167% | 11620 | 0 | 11620 | 900 | 0 | 28.5 | 871.5 | 0 | TPMP withdrawn from submission at 57th ExCom by lead UNEP because ExCom precondition that country needs to ratify London Amendment was not fulfilled. | [13 empty] | 2007 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | ANG | PHA | 55 | PRP | 8 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Prodoc is expected to be signed in Q1-2009. activities to be launched in Q2-2009. However ratification of various MP amendments may be an issue before HPMP can be submitted. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | ANT | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1998-09-01 | 1999-06-01 | 30000 | -969 | 29031 | 29031 | 100% | 0 | 0 | 0 | 3900 | -125.97 | 3774.03 | 0 | 0 | Project financially completed. | $969 plus $126 PSC returned ExCom 30 | [12 empty] | 1991 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | ANT | REF | 21 | PRP | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1998-09-01 | 1999-04-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3900 | -650 | 3250 | 0 | 0 | Project financially completed. | $5,000 plus $650 PSC returned ExCom 30 | [12 empty] | 1996 | Non Investment
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | ANT | SEV | 26 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-09-01 | 2001-12-01 |  | 2002-12-01 | 2004-10-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 | 0 | 0 | 4680 | 0 | 4680 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | Canada | Implementation of the RMP: training of customs | RMP | LAC | ANT | REF | 26 | TRA | 4 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2002-10-01 | 2002-12-01 | 42940 | 0 | 42940 | 42940 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Complete. PCR submitted. |  | 1998 | [11 empty] | 1998 | Non-Inv.
FIN | Canada | Implementation of the RMP: training the trainers in good refrigerant management practices | RMP | LAC | ANT | REF | 26 | TRA | 5 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 47460 | 0 | 47460 | 47460 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed PCR submitted. |  | 1998 | [11 empty] | 1998 | Non-Inv.
FIN | Canada | Implementation of the RMP: national recovery and recycling | RMP | LAC | ANT | REF | 26 | TAS | 6 | A | O | I | CFC | 1 |  | 0 |  | 1998-11-01 | 2000-06-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. PCR submitted. |  | 1998 | [11 empty] | 1998 | Non-Inv.
COM | UNEP | Renewal of institutional strengthening project | Individual | LAC | ANT | SEV | 38 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-06-01 |  | 31200 | -13 | 31187 | 26663 | 85.49% | 4524 | 0 | 4524 | 0 | 0 | 0 | 0 | 0 | Project completed. | $ 13 returned to ExCom 51 | [12 empty] | 2002 | Non Investment
FIN | IBRD | Preparation of a national CFC phase-out plan |  | LAC | ANT | PHA | 39 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-09-01 | 2004-09-01 |  | 2004-09-01 | 2004-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | Project prepared, submitted and then approved at the 44th ExCom. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | CFC phase-out management plan | Multiyear | LAC | ANT | PHA | 44 | INV | 10 | N | O | I | CFC | 2 | 3 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2012-01-01 |  |  | 69400 | 0 | 69400 | 0 | 0% | 69400 | 69400 | 30000 | 6246 | 0 | 0 | 6246 | 6246 | Grant agreement will be signed and will become effective in Feb 09. Launch workshop for representatives from relevant government agencies and industry to be held in Feb 09. 2009 action plan will be adopted and implementation is expected to start thereafter. | [13 empty] | 2004 | INV | 1.4 | 0.5 | 0 | 0 |  | No | No
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | ANT | SEV | 44 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 | 2010-03-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | Progress report for 2008 sent and received. The National Ozone Unit continued to monitor all imports of ods refrigerants and systems by ensuring proper application of the Licensing Regime in collaboration with the customs department. Public education and awareness remained on-going, including school visits/lectures. Ensured that designated importers stayed within their quota limit. Held Meeting with the Local Refrigeration Association to discuss the accelerated phase out of HCFCs and the use/availability of alternatives. Only Financial report for 2007 and 2008 is pending in order to make second disbursment. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | ANT | PHA | 55 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions for project implementation and further arrangements are being set. | [13 empty] | 2008
FIN | UNDP | Tecnical assistance for country programme preparation | Individual | LAC | ARG | SEV | 04 | CPG | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-07-01 | 1993-02-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 06 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 149337 | -59619 | 89718 | 89718 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ARG | SEV | 09 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 63000 | -29084 | 33916 | 33916 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector project identification and preparation (1993) |  | LAC | ARG | SEV | 10 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 100000 | 65560 | 165560 | 165560 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparatory assistance for phase out of ODS in the foam production at BANDEX, CELPACK & PRENSIPLANT | Individual | LAC | ARG | FOA | 11 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-12-01 | 1998-08-01 | 35000 | 8990 | 43990 | 43990 | 100% | 0 | 0 |  | 4550 | 1169 | 5719 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects in the refrigeration and foam sectors (1994) |  | LAC | ARG | SEV | 12 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 192929 | 4741 | 197670 | 197670 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Technical assistance to prepare a national halon programme | Individual | LAC | ARG | HAL | 13 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-01-01 |  | 1996-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1994 | Non-Investment
FIN | USA | Project preparation/technical assistance |  | LAC | ARG | SEV | 13 | PRP | 8 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNIDO | Investment project for phasing out of ODS at Bandex S.A. | Individual | LAC | ARG | FOA | 13 | INV | 9 | A | O | I | CFC | 214 | 214 |  |  | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1995-11-01 | 1998-08-01 | 517630 | -555 | 517075 | 517075 | 100% | 0 | 0 |  | 67292 | -179 | 67113 | 0 | 0 | FIN
FIN | UNIDO | Phase out of ODS at CELPACK S.A. | Individual | LAC | ARG | FOA | 13 | INV | 10 | A | O | I | CFC | 135 | 135 |  |  | 1994-07-01 | 1994-12-01 | 1995-07-01 |  | 1995-12-01 | 1998-08-01 | 503094 | 377 | 503471 | 503471 | 100% | 0 | 0 |  | 65402 | 49 | 65451 | 0 | 0 | FIN
TRF | IBRD | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | O | D |  | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1997-07-01 |  |  | 1994-07-01 | 359500 | -359500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transfered to UNDP | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1997-07-01 |  | 1999-12-01 | 2000-12-01 | 359500 | 0 | 359500 | 359500 | 100% | 0 | 0 | 0 | 46735 | 0 | 46735 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance (1994) | Individual | LAC | ARG | SEV | 14 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-09-01 | 1995-09-01 |  | 1995-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Prensiplast | Individual | LAC | ARG | FOA | 14 | INV | 13 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-09-01 | 1995-12-01 | 1995-09-01 |  | 1999-11-01 | 2001-12-01 | 345000 | -5021 | 339979 | 339979 | 100% | 0 | 0 | 0 | 44850 | -653 | 44197 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of sandwich polyurethane panels at Cinter, S.R.L. | Individual | LAC | ARG | FOA | 15 | INV | 14 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 2001-12-01 | 2003-09-01 | 725000 | -32679 | 692321 | 692321 | 100% | 0 | 0 | 0 | 94250 | -4248 | 90002 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1997-12-01 | [10 empty] | 1994 | Investment
FIN | IBRD | Conversion to non-CFC technology in the production of heat exchangers for mobile air conditioning at Interclima, S.A. | Individual | LAC | ARG | REF | 15 | INV | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-07-01 | 1995-12-01 |  | 1999-06-01 | 1999-11-01 | 1983430 | -314039 | 1669391 | 1669391 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. PCR was sent to ExCom. |  |  | 1997-07-01 | 1999-08-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of condensers for mobile air conditioning at Simon Cachan, S.A. | Individual | LAC | ARG | REF | 15 | INV | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-12-01 |  | 2001-01-01 | 2002-03-01 | 2738217 | -459396 | 2278821 | 2278821 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  | 1997-07-01 | 1999-11-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of complete mobile air conditioning systems at Mirgor, S.A. | Individual | LAC | ARG | REF | 15 | INV | 17 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-06-01 | 1995-12-01 |  | 1999-06-01 | 1999-06-01 | 35632 | -4082 | 31550 | 31550 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-07-01 | 1999-08-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of ODP in the production of household refrigerators at the Fribe La Rioja Plant | Individual | LAC | ARG | REF | 15 | INV | 18 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1488127 | -1444783 | 43344 | 43344 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned at 27th meeting. |  |  | 1999-03-01 | 1997-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in two manufacturing plants of domestic refrigerators at Helametal S.A., and Helametal Catamarca S.A. | Individual | LAC | ARG | REF | 15 | INV | 19 | N | O | I | CFC | 62 | 62 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1996-12-01 |  | 2003-10-01 | 2004-07-01 | 2959085 | -59591.29 | 2899493.71 | 2899493.71 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-03-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of ODS in the production of domestic refrigerators in the Fribe, S.A. plant | Individual | LAC | ARG | REF | 15 | INV | 20 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1822750 | -1769660 | 53090 | 53090 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned to 27th meeting. |  |  | 1999-03-01 | 1997-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in the domestic refrigerator manufacturing plant of McLean | Individual | LAC | ARG | REF | 15 | INV | 21 | N | O | I | CFC | 74 | 74 | 0 | 0 | 1994-12-01 | 1998-02-01 | 1996-12-01 |  | 2001-01-01 | 2001-05-01 | 2440570 | -1567990 | 872580 | 872580 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | All pending payments were effected by May 2001. The project is complete and the PCR has been submitted to EXCOM. |  |  | 1999-03-01 | 2000-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | MAC servicing demonstration |  | LAC | ARG | REF | 16 | DEM | 22 | A | O | I | CFC | 20.4 | 20 | 0 |  | 1995-03-01 | 1995-09-01 | 1995-12-01 |  | 1997-06-01 | 1998-06-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-06-01
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ARG | SEV | 16 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 185000 | -4503 | 180497 | 180497 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | Australia | Provision of training in leak reduction, emission control and recycling and management of non-CFC refrigerants in domestic and commercial refrigeration and air conditioning | Individual | LAC | ARG | REF | 17 | TAS | 24 | A | O | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1996-02-01 | 1996-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 17 | PRP | 25 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-03-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Belmo Buenos Aires and Belmo San Luis | Individual | LAC | ARG | FOA | 18 | INV | 26 | A | O | I | CFC | 145 | 145 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2001-08-01 | 715000 | -10 | 714990 | 714990 | 100% | 0 | 0 | 0 | 92950 | -1 | 92949 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Nuvel Corp. S.A. | Individual | LAC | ARG | FOA | 18 | INV | 27 | A | O | I | CFC | 53 | 53 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 313500 | 0 | 313500 | 313500 | 100% | 0 | 0 | 0 | 40755 | 0 | 40755 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  |  | 1999-06-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Mentvil S.A. | Individual | LAC | ARG | FOA | 18 | INV | 28 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1997-04-01 | 2001-12-01 | 115000 | -12796 | 102204 | 102204 | 100% | 0 | 0 | 0 | 14950 | -1663 | 13287 | 0 | 0 | Completed in 1997. Financially completed in 2001. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Limansky | Individual | LAC | ARG | FOA | 18 | INV | 29 | A | O | I | CFC | 95 | 95 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 473000 | -364 | 472636 | 472636 | 100% | 0 | 0 | 0 | 61490 | -47 | 61443 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Piero SAIC | Individual | LAC | ARG | FOA | 18 | INV | 30 | A | O | I | CFC | 64 | 64 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 341000 | -1708 | 339292 | 339292 | 100% | 0 | 0 | 0 | 44330 | -222 | 44108 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  |  | 1999-06-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstock) at Sueño Estelar S.A. and Estelar San Luis S.A. | Individual | LAC | ARG | FOA | 18 | INV | 31 | A | O | I | CFC | 128.6 | 128.6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 690000 | -2837 | 687163 | 687163 | 100% | 0 | 0 | 0 | 89700 | -369 | 89331 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | LAC | ARG | FOA | 18 | PRP | 32 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -492 | 19508 | 19508 | 100% | 0 | 0 |  | 2600 | -68 | 2532 | 0 | 0 | FIN
FIN | UNDP | Elimination of the use of CFC's in the manufacture of sandwich panels and spray foams at Montisol Argentina S.A. and Art Nouveau Puntana, S.A. | Individual | LAC | ARG | FOA | 18 | INV | 33 | A | O | I | CFC | 36.5 | 36.5 | 0 | 0 | 1995-11-01 | 1997-07-01 | 1996-11-01 |  | 2001-12-01 | 2003-04-01 | 285000 | -631 | 284369 | 284369 | 100% | 0 | 0 | 0 | 37050 | -82 | 36968 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-01-01 | [10 empty] | 1995 | Investment
CLO | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores at Market Costan S.A. | Individual | LAC | ARG | REF | 18 | INV | 34 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1997-05-01 |  |  | 1998-07-01 | 423000 | -421642 | 1358 | 1358 | 100% | 0 | 0 | 0 | 54990 | -54813 | 177 | 0 | 0 | Canceled in 1998. Financially completed in 1998. | [13 empty] | 1995 | Investment
CLO | IBRD | Elimination of CFCs in domestic refrigerator production plants in Aurora S.A. | Individual | LAC | ARG | REF | 18 | INV | 35 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 567590 | -567590 | 0 | 0 |  | 0 | 0 |  | 73786.7 | -73786.7 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in 2 domestic refrigerator manufacturing plants at Piragua S.A., and Piragua San Luis | Individual | LAC | ARG | REF | 18 | INV | 36 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 1040264 | -1040264 | 0 | 0 |  | 0 | 0 |  | 135234.32 | -135234.32 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in domestic refrigerator production plant in Autosal, S.A. | Individual | LAC | ARG | REF | 18 | INV | 37 | N | O | I | CFC | 22 | 22 | 0 | 0 | 1995-11-01 | 1998-11-01 | 1997-11-01 |  | 2003-06-01 | 2004-03-01 | 797390 | 0 | 797390 | 797390 | 100% | 0 | 0 |  | 103660.7 | 0 | 103660.7 | 0 | 0 | Project completed. |  |  | 1998-05-01 | 1999-11-01 |  | 2001-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Briket, S.A. | Individual | LAC | ARG | REF | 18 | INV | 38 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1998-02-01 | 1997-11-01 |  | 2001-10-01 | 2001-11-08 | 726400 | 0 | 726400 | 726400 | 100% | 0 | 0 |  | 94432 | 0 | 94432 | 0 | 0 | The company has been producing without CFCs since Aug. 2001. Destruction of old equipment was completed Oct. 2001. |  |  | 1998-05-01 | 1999-10-01 | [10 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba, S.A. | Individual | LAC | ARG | REF | 18 | INV | 39 | N | O | I | CFC | 29 | 5 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1997-11-01 | 2010-06-01 |  |  | 686370 | 0 | 686370 | 628760.4 | 91.61% | 57609.6 | 57609.6 | 57609.6 | 89228.1 | 0 | 81738.85 | 7489.25 | 7489.25 | Impianti has delivered all the equipment. The components of the second and last shipment are still in port due to the complex economic situation that has seriously affected the sector's activity. Company has incorporated the change in the refrigeration system and has stopped using CFC-12. It is able to continue assembly at the foaming facility and is substituting the use of CFC-11 with C5. |  |  | 1998-05-01 | 1999-10-01 |  | 2001-09-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of mobile air conditioning systems at Sistemaire, S.A. | Individual | LAC | ARG | REF | 18 | INV | 40 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-11-01 |  | 2000-09-01 | 2000-12-01 | 2370550 | -1400728 | 969822 | 969822 | 100% | 0 | 0 |  | 308171.5 | -182094.64 | 126076.5 | 0.36 | 0.36 | Completed. PCR submitted to ExCom. Savings returned to 34th ExCom. |  |  | 1998-05-01 | 1999-08-01 | 2000-11-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 18 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 18 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators at Adzen S.A. C.I.F. | Individual | LAC | ARG | REF | 19 | INV | 43 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 2003-12-01 | 356970 | -356970 | 0 | 0 |  | 0 | 0 |  | 46406 | -41051.45 | 5354.55 | 0 | 0 | Project cancelled at the 40th ExCom. |  |  | 1997-11-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators of Frimetal, Rosario | Individual | LAC | ARG | REF | 19 | INV | 44 | N | O | I | CFC | 89.7 | 89.7 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1998-05-01 |  | 2004-09-01 | 2004-10-01 | 1855000 | 0 | 1855000 | 1855000 | 100% | 0 | 0 |  | 241150 | 0 | 241150 | 0 | 0 | Project financially and physically completed. |  |  | 1998-11-01 | 2000-01-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFC's in the manufacture of display cabinet and walk-in freezers at Disthel | Individual | LAC | ARG | REF | 19 | INV | 45 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 196000 | -5726 | 190274 | 190274 | 100% | 0 | 0 | 0 | 25480 | -744 | 24736 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | Switzerland | Technical assistance and training on safe designs of hydrocarbon based domestic and commercial refrigeration appliances | Individual | LAC | ARG | REF | 19 | TRA | 46 | A | O | D |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-08-01 | 1997-10-01 |  | 1997-08-01 | 1997-10-01 | 242600 | 0 | 242600 | 242600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Balance has been compensated with separate Swiss funding |  | 1996
FIN | UNIDO | Phasing out CFC-12 at Mallol Saic | Individual | LAC | ARG | FOA | 20 | INV | 47 | A | O | I | CFC | 36.5 | 36.5 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2003-12-01 | 2004-03-01 | 299344 | 0 | 299344 | 299344 | 100% | 0 | 0 |  | 38915 | -53 | 38862 | 0 | 0 | FIN |  |  | 1998-04-01 | 2000-06-01
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstocks) at Suavestar S.A. | Individual | LAC | ARG | FOA | 20 | INV | 48 | A | O | I | CFC | 92.5 | 92.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2002-11-01 | 2004-01-01 | 561000 | 0 | 561000 | 561000 | 100% | 0 | 0 | 0 | 72930 | 0 | 72930 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  | 1998-01-01 | [10 empty] | 1996 | Investment
FIN | UNIDO | Phasing out of CFC-12 at Multiespuma Saic | Individual | LAC | ARG | FOA | 20 | INV | 49 | A | O | I | CFC | 60 | 60 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2000-12-01 | 2001-11-01 | 282438 | -11981 | 270457 | 270457 | 100% | 0 | 0 |  | 36717 | -1613 | 35104 | 0 | 0 | FIN |  |  | 1998-04-01 | 2000-06-01
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 21 | PRP | 50 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNEP | National train the trainer programme on good practices in refrigeration | Individual | LAC | ARG | REF | 21 | TRA | 51 | A | O | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 1999-12-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 | 0 | 27950 | 0 | 27950 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | ARG | SEV | 21 | PRP | 52 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 2000-06-02 | 2002-05-01 | 32140 | 0 | 32140 | 32140 | 100% | 0 | 0 |  | 4178 | 0 | 4178 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 21 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation | Individual | LAC | ARG | SEV | 22 | PRP | 54 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Eliminations of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Rheem S.A. | Individual | LAC | ARG | FOA | 22 | INV | 55 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-12-01 | 2001-12-01 | 76650 | 0 | 76650 | 76650 | 100% | 0 | 0 | 0 | 9965 | 0 | 9965 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstocks) at FPV S.A. | Individual | LAC | ARG | FOA | 22 | INV | 56 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-05-01 | 2004-01-01 | 118000 | -34528 | 83472 | 83472 | 100% | 0 | 0 | 0 | 15340 | -4489 | 10851 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Calofrig Asilaciones Jacobi S.A.I.C. | Individual | LAC | ARG | FOA | 22 | INV | 57 | A | O | I | CFC | 72 | 72 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1999-06-01 |  | 2001-12-01 | 2003-04-01 | 563750 | 0 | 563750 | 563750 | 100% | 0 | 0 | 0 | 73288 | 0 | 73288 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
CLO | UNIDO | Phasing out of CFCs in the manufacturing plant of domestic refrigerators of Radio Victoria Catamarca, S.A. | Individual | LAC | ARG | REF | 22 | INV | 58 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  |  | 2001-07-01 | 599896 | -454313 | 145583 | 145583 | 100% | 0 | 0 |  | 77986 | -59090 | 18896 | 0 | 0 | CLO
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 12 | CPG | 59 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program was completed and presented at the 13th E.C. meeting. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFCs in the manufacture of commercial refrigerators and display cabinets at Trevi | Individual | LAC | ARG | REF | 23 | INV | 60 | A | O | I | CFC | 3.5 | 3.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-11-01 | 2001-08-01 | 53850 | -4409 | 49441 | 49441 | 100% | 0 | 0 | 0 | 7001 | -573 | 6428 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Bonano | Individual | LAC | ARG | FOA | 23 | INV | 61 | A | O | I | CFC | 72 | 72 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 456500 | 0 | 456500 | 456500 | 100% | 0 | 0 | 0 | 59345 | 0 | 59345 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
CLO | UNDP | Conversion to non CFC technology in the manufacture of integral skin and flexible moulded foam at Strapur | Individual | LAC | ARG | FOA | 23 | INV | 62 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2001-08-01 | 212500 | -162380 | 50120 | 50120 | 100% | 0 | 0 | 0 | 27625 | -21109 | 6516 | 0 | 0 | Canceled in 2001. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of moulded foam at Cifor S.A. | Individual | LAC | ARG | FOA | 23 | INV | 63 | A | O | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-03-01 | 2001-12-01 | 132000 | -9838 | 122162 | 122162 | 100% | 0 | 0 | 0 | 17160 | -1279 | 15881 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Frare S.A., Buenos Aires | Individual | LAC | ARG | REF | 23 | INV | 64 | A | O | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-05-01 | 2002-09-01 | 514384 | -2300 | 512084 | 512084 | 100% | 0 | 0 |  | 66870 | -405 | 66465 | 0 | 0 | FIN
CLO | UNDP | Elimination of the use of CFCs in the manufacture of rigid foam blocks for insulated trailers at Fruehauf | Individual | LAC | ARG | FOA | 23 | INV | 65 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2003-11-01 | 175000 | -40597 | 134403 | 134403 | 100% | 0 | 0 | 0 | 22750 | -5278 | 17472 | 0 | 0 | Canceled in 2002. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores and walk-in coolers at Eurofrio | Individual | LAC | ARG | REF | 23 | INV | 66 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2002-11-01 | 2004-01-01 | 377350 | 0 | 377350 | 377350 | 100% | 0 | 0 | 0 | 49056 | 0 | 49056 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [5 empty] | 2001-05-01 | [7 empty] | 1997 | Investment
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Bambi S.A., Santa Fe | Individual | LAC | ARG | REF | 23 | INV | 67 | A | O | I | CFC | 30.6 | 30.6 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 515258 | 0 | 515258 | 515258 | 100% | 0 | 0 |  | 66984 | -24 | 66960 | 0 | 0 | FIN
FIN | IBRD | Elimination of CFCs in 1 manufacturing plant of domestic refrigerators of enterprise Whirlpool Argentina S.A. | Individual | LAC | ARG | REF | 23 | INV | 68 | N | O | I | CFC | 90.55 | 90.55 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-04-26 | 863879 | -99292 | 764587 | 764587 | 100% | 0 | 0 |  | 112304 | -12907.69 | 99396.31 | 0 | 0 | Project completed and funding disbursed. PCR submitted Dec. 01. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators at Lobato San Luis S.A. | Individual | LAC | ARG | REF | 23 | INV | 69 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 2002-11-01 | 410683 | -410683 | 0 | 0 |  | 0 | 0 |  | 53389 | -47229 | 6160 | 0 | 0 | Cancelled - 37th ExCom | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators at Gepasa S.A. and Gesal S.R.L. | Individual | LAC | ARG | REF | 23 | INV | 70 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2000-12-01 | 550400 | -550400 | 0 | 0 |  | 0 | 0 |  | 71552 | -71552 | 0 | 0 | 0 | Project cancelled at 31st ExCom. Funds returnd at 32nd ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Demonstration Project: Open and closed circuit non-soil cultivation as main alternatives to the use of methyl bromide in tomato, cut flowers and strawberry production | Individual | LAC | ARG | FUM | 23 | DEM | 71 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-06-01 | 2002-09-01 | 481800 | -19112 | 462688 | 462688 | 100% | 0 | 0 |  | 62634 | -2580 | 60054 | 0 | 0 | FIN
FIN | IBRD | Project preparation in the refrigeration, halon and MAC sectors |  | LAC | ARG | SEV | 24 | PRP | 72 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation for methyl bromide (tobacco) demonstration project | Individual | LAC | ARG | FUM | 24 | PRP | 73 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 24 | PRP | 74 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation for methyl bromide (citrus and cotton) demonstration project |  | LAC | ARG | FUM | 25 | PRP | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-30 | 1999-08-01 |  | 1999-06-30 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to low index additive technology in the manufacture of flexible boxfoam at Rozen S.R.L. | Individual | LAC | ARG | FOA | 25 | INV | 76 | A | O | I | CFC | 19.6 | 19.6 | 0 | 0 | 1998-07-01 | 2000-08-01 | 2000-08-01 |  | 2002-11-01 | 2004-01-01 | 122100 | 0 | 122100 | 122100 | 100% | 0 | 0 | 0 | 15873 | 0 | 15873 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | IBRD | Substituting CFCs by HCFC-141b and HFC-134a in manufacturing of domestic and commercial refrigerators at El Dorado, S.A. | Individual | LAC | ARG | REF | 25 | INV | 77 | N | O | I | CFC | 12.8 | 12.8 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-09-01 | 2000-06-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 22880 | 0 | 22880 | 0 | 0 | Completed. PCR has been sent | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Comenco | Individual | LAC | ARG | FOA | 26 | INV | 78 | A | O | I | CFC | 31.2 | 31.2 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-08-01 | 2001-12-01 | 210150 | -3022 | 207128 | 207128 | 100% | 0 | 0 | 0 | 27320 | -393 | 26927 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Demonstration and training in viable alternatives, information dissemination and development of a national plan for phasing out methyl bromide in the tobacco sector | Individual | LAC | ARG | FUM | 26 | DEM | 79 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-04-01 | 2003-11-01 | 273350 | -1493 | 271857 | 271857 | 100% | 0 | 0 | 0 | 35536 | -194 | 35342 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
ONG | IBRD | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Individual | LAC | ARG | HAL | 26 | TAS | 80 | N | O | I | HAL | 200 | 0 | 0 | 0 | 1998-11-01 | 2002-02-01 | 2000-12-01 | 2010-12-01 |  |  | 290620 | 0 | 290620 | 186116.54 | 64.04% | 104503.46 | 104503.46 | 60000 | 37780.6 | 0 | 24195.15 | 13585.45 | 13585.45 | Construction of storage facility for containers of products to be analyzed is finished and is in operation. INTI continues monitoring evolution of the halon market. UEPRO will carry out inspection of finished work in 2009. Remaining work will be on dissemination activities regarding recuperation of existing halons in essential or critical facilities. Work program, which will include proposed activities to be conducted in cooperation with the operator, as well as the disbursement schedule for the second half of 2009 will be submitted before Jun 09. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam in panels for thermal insulation at Arneg Raffo | Individual | LAC | ARG | FOA | 27 | INV | 81 | N | O | I | CFC | 67 | 67 | 0 | 0 | 1999-03-01 | 2001-02-20 | 2001-04-01 |  | 2002-07-01 | 2004-03-01 | 177960 | 0 | 177960 | 177960 | 100% | 0 | 0 |  | 23134.8 | 0 | 23134.8 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in sterilization via ETO at Asisthos SRL | Individual | LAC | ARG | STE | 27 | INV | 82 | N | O | I | CFC | 20.69 | 20.69 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2001-04-01 |  | 2000-09-01 | 2001-03-01 | 395095 | 0 | 395095 | 395095 | 100% | 0 | 0 |  | 51362.35 | 0 | 51362.35 | 0 | 0 | Completed. PCR submitted Feb. 01. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of two projects in the integral skin foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | ARG | FOA | 27 | PRP | 84 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (flowers) | Individual | LAC | ARG | FUM | 27 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 40000 | -5622 | 34378 | 34378 | 100% | 0 | 0 |  | 5200 | -738 | 4462 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects in the refrigeration and solvent cleaning sectors |  | LAC | ARG | SEV | 27 | PRP | 86 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-30 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of an umbrella project and three other projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 87 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 27 | PRP | 88 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (strawberries, tomatoes) | Individual | LAC | ARG | FUM | 27 | PRP | 89 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-14 | 2000-11-09 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
CLO | IBRD | Replacement of 1,1,1-trichloethane sheet steel cleaning system on the steel sheet-cutting table with an aqueous-mechanical system in the steel enterprise Siderar, SAIC | Individual | LAC | ARG | SOL | 28 | INV | 90 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2001-08-01 |  |  | 2003-04-01 | 105147 | -105147 | 0 | 0 |  | 0 | 0 |  | 13669.11 | -11566 | 2103 | 0.11 | 0.11 | Cancelled - 38th ExCom | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. | Individual | LAC | ARG | SOL | 28 | INV | 91 | N | O | I | TCA | 7.1 | 2.3 | 0 | 0 | 1999-07-01 | 2001-02-20 | 2000-08-01 |  | 2004-03-01 | 2004-03-01 | 272157 | -183607 | 88550 | 88550 | 100% | 0 | 0 |  | 35380.41 | -23868.91 | 11511.5 | 0 | 0 | Orbis and Buffalo have completed conversion. Argelite, Unisol and Cincam cancelled at the 39th ExCom. Grimoldi, Integral Metalurgica, Heliodino and Trosh were cancelled at the 44th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and of CFC-12 by conversion to HFC-134a in the manufacture of commercial refrigeration display cabinets and polyurethane panels for cold stores AT Perito Moreno Ref. | Individual | LAC | ARG | REF | 28 | INV | 92 | A | O | I | CFC | 31.1 | 31.1 | 0 | 0 | 1999-07-01 | 1999-09-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 379605 | 0 | 379605 | 379605 | 100% | 0 | 0 | 0 | 49349 | 0 | 49349 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Individual | LAC | ARG | FUM | 29 | DEM | 93 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-08-01 | 2001-12-01 | 2009-12-01 |  |  | 375000 | 0 | 375000 | 192328 | 51.29% | 182672 | 182672 | 90000 | 48750 | 0 | 25002.64 | 23747.36 | 23747.36 | Validation tests and lab work have suffered delays due to the dengue epidemic that affected the zone of insect capture. As a result no disbursement could take place in 2008. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at OSIR (Organización de Servicios Integrales Rosario) | Individual | LAC | ARG | FOA | 29 | INV | 94 | A | O | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 127392 | 0 | 127392 | 127392 | 100% | 0 | 0 | 0 | 16561 | 0 | 16561 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Obras de Ingenieria | Individual | LAC | ARG | FOA | 29 | INV | 95 | A | O | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2000-12-01 | 2003-04-01 | 124025 | -221 | 123804 | 123804 | 100% | 0 | 0 | 0 | 16123 | -29 | 16094 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and boxfoam) at Mendoza de Poliuretanos | Individual | LAC | ARG | FOA | 29 | INV | 96 | A | O | I | CFC | 43.9 | 43.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-11-01 | 2004-01-01 | 234409 | 0 | 234409 | 234409 | 100% | 0 | 0 | 0 | 30473 | 0 | 30473 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid P.U. foams: umbrella project (Tarco, Mondino, Schaum, Fadep, Occhipinti and Friolatina) | Individual | LAC | ARG | FOA | 29 | INV | 97 | A | O | I | CFC | 30.4 | 30.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2001-06-01 | 2002-09-01 | 227048 | 0 | 227048 | 227048 | 100% | 0 | 0 |  | 29516 | -7 | 29509 | 0 | 0 | FIN
COM | UNDP | Renewal of the institutional strengthening under the Montreal Protocol (Phase II) | Individual | LAC | ARG | SEV | 29 | INS | 98 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2003-05-01 |  | 239700 | 0 | 239700 | 239700 | 100% | 0 | 0 | 0 | 31161 | 0 | 31161 | 0 | 0 | Completed in 2003. | [13 empty] | 1999 | Non-Investment
FIN | IBRD | Preparation of an investment project in methyl bromide sector |  | LAC | ARG | FUM | 30 | PRP | 100 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 101 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 102 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of one project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 30 | PRP | 103 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNEP | Policy assistance for the design and implementation of an ODS import/export licensing system for Argentina | Individual | LAC | ARG | SEV | 30 | TAS | 104 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-11-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | [6 empty] | 2002-12-01 | 2003-10-01 | [5 empty] | 2000 | Non Investment
ONG | UNIDO | Phase-out of methyl bromide in strawberry, protected vegetables and cut flower production | Individual | LAC | ARG | FUM | 30 | INV | 105 | A | O | I | MBR | 331 | 224.4 |  |  | 2000-03-01 | 2000-07-01 | 2015-01-01 | 2015-01-01 |  |  | 3183390 | 0 | 3183390 | 3069611 | 96.43% | 113779 | 93365 | 20000 | 360173 | 0 | 347657 | 12516 | 10270 | As explained at the last meeting, the ExCom at its 45th Meeting approved a revised phase-out schedule for Argentina. As per Decision 45/13, before the end of 2010, UNIDO and Argentina has to submit a full report on the implementation of the phase-out plan, together with a status report on the alternatives to methyl bromide in the strawberry sector available in Argentina. In addition, at that time, Argentina would consider the possibility of completing the phase-out of methyl bromide earlier than 2015. The ban of import will be put in place once the total phase out is accomplished.
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Fasax | Individual | LAC | ARG | FOA | 30 | INV | 106 | A | O | I | CFC | 50 | 50 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2003-04-01 |  | 2002-11-01 | 2004-01-01 | 252000 | 0 | 252000 | 252000 | 100% | 0 | 0 | 0 | 32760 | 0 | 32760 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | ARG | REF | 30 | PRP | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | LAC | ARG | FOA | 30 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2000-12-01 | 2000-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the solvent (TCA) sub-sector |  | LAC | ARG | SOL | 30 | PRP | 109 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-03-01 |  | 2001-12-01 | 2001-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141B as a blowing agent in the manufacture of P.U. blocks and tank spraying at Polwer S.R.L. | Individual | LAC | ARG | FOA | 28 | INV | 110 | A | O | I | CFC | 26.8 | 26.8 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2001-06-01 | 2002-11-01 | 111641 | -69 | 111572 | 111572 | 100% | 0 | 0 |  | 14513 | -32 | 14481 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam at four enterprises: Cosmos; La Cardeuse; Jovis; and Micropore | Individual | LAC | ARG | FOA | 31 | INV | 111 | A | O | I | CFC | 48.7 | 48.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2003-12-01 | 2005-09-01 | 295300 | -97042 | 198258 | 198258 | 100% | 0 | 0 | 0 | 38389 | -12615 | 25774 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | IBRD | Project preparation for the CFC production sector |  | LAC | ARG | PRO | 31 | PRP | 112 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constuctora Vimac; Gaspar Adragna; Placido Sandoval) | Individual | LAC | ARG | FOA | 32 | INV | 113 | A | O | I | CFC | 49.6 | 49.6 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 320332 | -90 | 320242 | 320242 | 100% | 0 | 0 | 0 | 41643 | -12 | 41631 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2000 | Investment
FIN | UNEP | Training of customs officers | Individual | LAC | ARG | REF | 32 | TRA | 114 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-02-02 |  | 2007-11-01 | 2008-12-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22750 | 0 | 22750 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
ONG | UNEP | Training programme for the refrigeration servicing sector (Phase III) | Individual | LAC | ARG | REF | 32 | TRA | 115 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2003-12-01 | 2009-06-01 |  |  | 300000 | 0 | 300000 | 286666 | 95.56% | 13334 | 0 | 13334 | 39000 | 0 | 37266.58 | 1733.42 | 0 | Agreements with certification institutions have been signed among INTI (National Technology Certification Insitutte) and local centers. Certification evaluation forms have been designed and approved. Examinations planned to start in October throughout the country. 500 technicians will be certified by December 2008 when project will be completed. | [13 empty] | 2000 | Non Investment
FIN | IBRD | Replacement of CFC-11 by HCFC-141b in the manufacture of rigid polyurethane foam for domestic refrigerators and sandwich panels at MTH S.R.L. | Individual | LAC | ARG | REF | 32 | INV | 116 | N | O | I | CFC | 8 | 8 | 0 | 0 | 2000-12-01 | 2001-05-30 | 2002-12-01 |  | 2002-10-01 | 2004-03-01 | 82695 | 0 | 82695 | 82695 | 100% | 0 | 0 |  | 10750.35 | 0 | 10750.35 | 0 | 0 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams at 7 companies (Aislaciones y Servicios Maximo; Baduco D and D; Bolatti; Hi-Tec Poliuretano Alberto; Najera Jose; Stefanelli Vincer, SRL) | Individual | LAC | ARG | FOA | 32 | INV | 117 | A | O | I | CFC | 46.1 | 46.1 |  |  | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-06-01 | 2004-09-01 | 329495 | 0 | 329495 | 329495 | 100% | 0 | 0 |  | 42834 | -36 | 42798 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 118 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2003-10-01 | 2003-12-01 | 35000 | -900 | 34100 | 34100 | 100% | 0 | 0 |  | 4550 | -124 | 4426 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | ARG | REF | 33 | PRP | 119 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in soil fumigation (tobacco) | Individual | LAC | ARG | FUM | 33 | PRP | 120 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 121 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 4 foam manufacturers (Artestamp, Paissan, Forever, Termica) | Individual | LAC | ARG | FOA | 34 | INV | 122 | A | O | I | CFC | 54.9 | 54.9 | 0 | 0 | 2001-07-01 | 2002-09-01 | 2004-08-01 |  | 2005-01-01 | 2007-01-01 | 352896 | -12969 | 339927 | 339927 | 100% | 0 | 0 | 0 | 45876 | -1686 | 44190 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam insulation panels at Frio Star | Individual | LAC | ARG | FOA | 34 | INV | 123 | A | O | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-12-01 | 2005-09-01 | 147987 | -53810 | 94177 | 94177 | 100% | 0 | 0 | 0 | 19238 | -6995 | 12243 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNIDO | Preparation of umbrella project in the commercial refrigeration sector | Individual | LAC | ARG | REF | 36 | PRP | 124 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-05-01 | 2003-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | -4 | 3246 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of an investment project in the solvents sector (CFC-113 and TCA) | Individual | LAC | ARG | SOL | 36 | PRP | 125 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 40000 | -1126 | 38874 | 38874 | 100% | 0 | 0 |  | 5200 | -154 | 5046 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | ARG | FOA | 36 | PRP | 126 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | ARG | REF | 36 | PRP | 127 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2004-08-01 |  | 2004-08-01 | 2004-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | -11 | 12989 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Electroquimica Delta | Individual | LAC | ARG | ARS | 36 | INV | 128 | N | O | I | CFC | 60 | 60 | 0 | 0 | 2002-03-01 | 2004-08-01 | 2005-04-01 |  | 2004-12-01 | 2006-07-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 34320 | 0 | 34320 | 0 | 0 | Project physically and financially completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (2001 and 2002 tranches) | Multi-Year | LAC | ARG | FUM | 36 | INV | 129 | N | O | I | MeBr | 29 | 29 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2002-12-01 |  | 2004-12-01 |  | 1720000 | 0 | 1720000 | 1720000 | 100% | 0 | 0 | 0 | 199200 | 0 | 199200 | 0 | 0 | Completed in 2004. | [8 empty] | 2004-03-01 |  |  |  |  | 2001 | Investment | 156 | 156 |  |  | Yes | Yes | yes
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | ARG | SEV | 38 | INS | 130 | N | T | I | No_ODP | 25.7 | 25.7 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 | 2008-10-01 | 311610 | -197 | 311413 | 311413 | 100% | 0 | 0 | 0 | 40509 | -26 | 40483.69 | -0.69 | 0 | Completed in 2005. Financially completed in 2008. | [13 empty] | 2002 | Non-Investment
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | Individual | LAC | ARG | ARS | 38 | INV | 131 | N | O | I | CFC | 36.4 | 36.4 | 0 | 0 | 2002-11-01 | 2004-08-01 | 2005-11-01 |  | 2005-02-01 | 2006-07-01 | 160160 | 0 | 160160 | 160160 | 100% | 0 | 0 |  | 20820.8 | 0 | 20820.8 | 0 | 0 | Project physically and financially completed. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | ARG | FOA | 38 | INV | 132 | A | O | I | CFC | 192.3 | 192.3 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2007-12-01 |  | 1324843 | 0 | 1324843 | 1307107 | 98.66% | 17736 | 0 | 14188.8 | 155733 | 0 | 153647.8679 | 2085.1321 | 0 | Completed in 2007. | [13 empty] | 2002 | Investment
COM | IBRD | CFC production closure plan (first tranche) | Multiyear | LAC | ARG | PRO | 38 | INV | 133 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-12-01 | 2003-12-01 |  | 2003-12-01 |  | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 20000 | 0 | 20000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. | [13 empty] | 2002 | INV | 0 | 0 | 3020 | 3018 | Yes | Yes | Yes
CLO | UNIDO | Preparation of country programme update | Individual | LAC | ARG | SEV | 39 | CPG | 134 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 |  | 2004-10-01 |  |  | 2005-08-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | CLO | [13 empty] | 2003
CLO | IBRD | Preparation of one investment project in the aerosol filling industry |  | LAC | ARG | ARS | 39 | PRP | 135 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2003-12-01 |  |  | 2005-11-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 750 | -750 | 0 | 0 | 0 | Funds returned to the 47th ExCom. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (third tranche) | Multi-Year | LAC | ARG | FUM | 40 | INV | 136 | N | O | I | MeBr | 21 | 21 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-03-01 |  | 2005-12-01 |  | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Completed in 2005. | [9 empty] | 2005-07-01 |  |  |  | 2003 | Investment | 106 | 106 |  |  | Yes | Yes | yes
ONG | UNIDO | Plan for phase-out of ODS in the solvent sector | Individual | LAC | ARG | SOL | 41 | INV | 137 | A | O | I | CFC CTC TCA | 42 | 48 |  |  | 2003-12-01 | 2004-04-01 | 2009-12-01 | 2010-12-01 |  |  | 635986 | 0 | 635986 | 393127 | 61.81% | 242859 | 18281 | 50000 | 47699 | 0 | 29485 | 18214 | 1371 | Identification of the new ODS consuming companies has been made in 2008 and sub-projects have been prepared for their TCA phase -out. In 2009 lab uses will be addressed. The project is expected to be completed in Dec 2010. The project deals with TCA phase out in SSIs. Therefore, one additional year for project implementation will be needed. | [13 empty] | 2003 | INV
COM | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | ARG | PHA | 42 | INV | 138 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2008-12-01 |  | 2740000 | 0 | 2740000 | 2558568 | 93.38% | 181432 | 177664 | 181000 | 205500 | 0 | 191893 | 13607 | 13325 | Project completed in Dec 2008. | [10 empty] | 2006-12-01 |  |  | 2003 | INV | 3220 | 2212 |  |  | Yes | Yes | Yes
COM | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fourth tranche) | Multi-Year | LAC | ARG | FUM | 43 | INV | 139 | N | O | I | MeBr | 16 | 16 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-07-01 |  | 2006-12-01 |  | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment | 90 | 90 |  |  | Yes | Yes | yes
COM | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2004 annual programme | Multiyear | LAC | ARG | PRO | 44 | INV | 141 | N | O | I | CFC | 0 | 0 | 1373 | 1373 | 2004-12-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 |  | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 | 0 | 200000 | 0 | 200000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. | [13 empty] | 2003 | INV | 0 | 0 | 3020 | 3016 | Yes | Yes | Yes
FIN | IBRD | Preparation of MDI phase-out plan |  | LAC | ARG | ARS | 45 | PRP | 142 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2008-12-01 | 2005-12-01 |  | 2008-12-01 | 2008-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | With World Bank assistance an Argentinian Strategy for MDIs was prepared, presented to and approved at the 56th ExCom. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2005 annual programme | Multiyear | LAC | ARG | PRO | 45 | INV | 143 | N | O | I | CFC | 0 | 0 | 1373 | 1373 | 2005-04-01 | 2007-09-01 | 2006-04-01 |  | 2006-04-01 |  | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. | [13 empty] | 2005 | INV | 0 | 0 | 1647 | 1645 | Yes | Yes | Yes
COM | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | ARG | SEV | 45 | TAS | 144 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 |  | 68807 | 0 | 68807 | 58536 | 85.07% | 10271 | 0 | 8216.8 | 6193 | 0 | 5268.5548 | 924.4452 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Extension for institutional strengthening project (phase IV) | Individual | LAC | ARG | SEV | 46 | INS | 145 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2008-05-01 |  | 311567 | 0 | 311567 | 311046 | 99.83% | 521 | 0 | 416.8 | 23368 | 0 | 23328.9242 | 39.0758 | 0 | Completed in 2008. The NOU coordinated ODS phase out projects in multiple sectors. In foams, the phase out project was technically completed, and verification visits were conducted to the enterprises in order to sign the SOC document and to destroy the previous existing machines. Within the National CFC phase-out plan, the sub-project activities for the first medium and small sized enterprises in the manufacturing refrigeration sector took place. In the project for Training Technicians in the Refrigeration Servicing Sector, A total of 93 new courses were held in 34 cities in the country, were 2272 new technicians were certified in the use of good practices in the repairing and servicing of refrigeration equipment and recovery and recycling of refrigerants. Also during this time 1739 technicians received the corresponding equipment in 42 events held in 31 locations throughout the country. Implementation will continue in 2008. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fifth tranche) | Multi-Year | LAC | ARG | FUM | 46 | INV | 146 | N | O | I | MeBr | 33.3 | 33.3 | 0 | 0 | 2005-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 |  | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment | 56.5 | 56.5 |  |  | Yes | Yes | yes
ONG | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | ARG | PHA | 47 | INV | 147 | A | O | I | CFC | 100 | 100 |  |  | 2005-11-01 | 2006-04-01 | 2006-12-01 | 2009-12-01 |  |  | 1850000 | 0 | 1850000 | 585515 | 31.65% | 1264485 | 109556 | 300000 | 138750 | 0 | 43914 | 94836 | 8217 | End user sector survey continued. Detailed report was submitted to 53rd ExCom Meeting based on which the 4th tranche was released. The R&R and refrigeration centers started their operation in 2008. The end user sector activities were continued. Further training and equipment for technicians were provided. Training of customs officers was carried out. The above-mentioned activities will be continued in 2009 with an increased focus on the end-users sector and ODS destruction as well as monitoring of project performance. | [13 empty] | 2005 | INV | 2047 | 1675.5 |  |  | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2006 work programme | Multiyear | LAC | ARG | PHA | 47 | INV | 148 | N | O | I | CFC | 1.5 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2009-12-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 | 500000 | 500000 | 37500 | 0 | 0 | 37500 | 37500 | The World Bank approved the country's TOR to hire a consultant to analyze the market and possible mechanisms to optimize the use of available funds. | [13 empty] | 2005 | INV | 1.5 | 1.5 | 0 | 0
ONG | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (sixth tranche) | Multi-Year | LAC | ARG | FUM | 48 | INV | 149 | N | O | I | MeBr | 56.5 | 56.5 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 | 2010-01-01 |  |  | 467000 | 0 | 467000 | 307841 | 65.92% | 159159 | 0 | 31831.8 | 35025 | 0 | 23088.075 | 11936.925 | 0 | Project had by the end of 2007 achieved almost 100 % of the promised MB reductions in the sector. The residual uses are looked at case by case .Awareness-raising continued: local outreach events & production of training materials for growers & extensionists. Training of MB growers, technicians and workers continued. Permanent meetings with stakeholders were held in all provinces. Activities are now focused on maintaining the zero (or very low) consumption of MB in this sector. | [13 empty] | 2006 | Investment | 0 |  |  |  | Latest | Latest | Latest
ONG | UNIDO | National CFC phase-out plan: 2007 work programme | Multi-Year | LAC | ARG | PHA | 50 | INV | 150 | A | O | I | CFC | 200 | 0 |  |  | 2006-11-01 | 2007-09-01 | 2007-11-01 | 2009-12-01 |  |  | 1103500 | 0 | 1103500 | 5549 | 0.5029% | 1097951 | 0 | 60000 | 82763 | 0 | 416 | 82347 | 0 | End user sector survey continued. Detailed report was submitted to 53rd ExCom Meeting based on which the 4th tranche was released. The R&R and refrigeration centers started their operation in 2008. The end user sector activities were continued. Further training and equipment for technicians were provided. Training of customs officers was carried out. The above-mentioned activities will be continued in 2009 with an increased focus on the end-users sector and ODS destruction as well as monitoring of project performance. | [13 empty] | 2006 | INV | 1997 | 1654.29 |  |  | Yes | Yes | Yes
COM | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2006 annual programme | Multiyear | LAC | ARG | PRO | 50 | INV | 151 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-10-01 |  | 2007-10-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. | [13 empty] | 2006 | INV | 0 | 0 | 1647 | 1645 | Yes | Yes | Yes
ONG | UNIDO | National CFC phase-out plan: 2008 work programme | Multi-Year | LAC | ARG | PHA | 53 | INV | 152 | A | O | I | CFC | 400 | 0 |  |  | 2007-11-01 | 2008-12-01 | 2009-12-31 | 2009-12-01 |  |  | 1167350 | 0 | 1167350 | 60 | 0.00514% | 1167290 | 0 | 20000 | 87551 | 0 | 5 | 87546 | 0 | End user sector survey continued. Detailed report was submitted to 53rd ExCom Meeting based on which the 4th tranche was released. The R&R and refrigeration centers started their operation in 2008. The end user sector activities were continued. Further training and equipment for technicians were provided. Training of customs officers was carried out. The above-mentioned activities will be continued in 2009 with an increased focus on the end-users sector and ODS destruction as well as monitoring of project performance. | [13 empty] | 2007 | INV | 686 | 529.1 |  |  | Yes | Yes | No
ONG | UNDP | Extension for institutional strengthening project (phase V) | Individual | LAC | ARG | SEV | 53 | INS | 153 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 | 2010-05-01 |  |  | 311567 | 0 | 311567 | 59388 | 19.06% | 252179 | 0 | 50435.8 | 23368 | 0 | 4454.1905 | 18913.8095 | 0 | Two-year extension of ARG-145 (see above). Ongoing. | [13 empty] | 2007 | Non-Investment
COM | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2007 annual programme | Multiyear | LAC | ARG | PRO | 53 | INV | 154 | N | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-30 |  | 2008-03-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. | [13 empty] | 2007 | INV | 0 | 0 | 686 | 442.9 | Yes | Yes | Yes
COM | IBRD | Accelerated phase-out plan for CFC production | Multiyear | LAC | ARG | PRO | 53 | INV | 155 | N | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2008-03-01 |  | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 | 0 | 172500 | 0 | 172500 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 | n/a | n/a | n/a
ONG | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2008 annual programme | Multiyear | LAC | ARG | PRO | 54 | INV | 156 | N | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2009-03-31 |  |  | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 | Yes | Yes | Yes
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 157 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-01 | 2010-04-01 |  |  | 95750 | 0 | 95750 | 4602 | 4.806% | 91148 | 0 | 91148 | 7181 | 0 | 345.15 | 6835.85 | 0 | The launch of the HPMP took place in December. National and international consultants have been hired, and process to develop / update de HCFC survey is on-going. | [13 empty] | 2008 | Investment
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 158 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 78000 | 0 | 78000 | 5071 | 6.501% | 72929 | 0 | 30000 | 5850 | 0 | 380 | 5470 | 0 | National consultants were recruited for the preparation of survey in refrigeration sector. | Initial workshop was held in December 2008. Consultant hired. The survey is being prepared. Lead Agency is UNDP and is responsible for the legislation component, however it is to be noted that the country has an efficient ODS licensing system and is tightly monitoring the HCFC consumption. The legislation for the a/c sector will be formulated as part of the investment project. First investment project is being formulated to phase out HCFC-22 in 10 a/c companies practically (the entire sector), consuming around 1400 tonnes of HCFC-22. Please reclassify the project: initial workshop was held, consultants hired for sectors, survey and investment project preparation are underway. | [12 empty] | 2008 | NON-INV
ONG | IBRD | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | ARG | ARS | 56 | INV | 159 | N | O | I | CFC | 118.4 | 0 | 0 | 0 | 2008-11-01 |  | 2012-01-31 | 2012-01-31 |  |  | 2806874 | 0 | 2806874 | 0 | 0% | 2806874 | 2806874 | 1000000 | 210516 | 0 | 0 | 210516 | 210516 | Newly approved. The 6 subgrant agreements to be signed with each of the medicine labs committed to carry out the reconversion are being prepared. | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0
CLO | UNEP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  |  | 2008-11-30 | 18000 | -18000 | 0 | 0 |  | 0 | 0 | 0 | 2340 | -2340 | 0 | 0 | 0 | $ 18,000 plus $ 2,340 returned to ExCom 54 | $ 18,000 plus $ 2,340 returned to ExCom 54 | [12 empty] | 2007 | Non Investment
ONG | UNDP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 2 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 |  |  | 12000 | 0 | 12000 | 0 | 0% | 12000 | 0 | 0 | 900 | 0 | 0 | 900 | 0 | Canceled in 2008. PRP was approved in Nov 07 but to be returned at 54th ExCom (GEF country). Funds will be returned in 2009. | [13 empty] | 2007 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | ARM | PHA | 55 | PRP | 3 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Prepared prodoc & TORs and held discussions on them. Prodoc is expected to be signed in Q1-2009. activities to be launched in Q2-2009. | [13 empty] | 2008 | Investment
FIN | UNEP | Regional workshop for Asia and the Pacific | Individual | ASP | ASP | SEV | 4 | TRA | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-11-01 |  | 1991-11-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 06 | TRA | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Asia | RMP-Component | ASP | ASP | REF | 06 | TRA | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1994-07-01 |  | 1996-08-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 06 | TRA | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in Asia | Individual | ASP | ASP | FOA | 06 | TRA | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -15672 | 36828 | 36828 | 100% | 0 | 0 | 0 | 6825 | -2037 | 4788 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | Australia | Support for delegates from six Asian countries to participate in regional workshop on alternatives to CFC | Individual | ASP | ASP | SEV | 07 | TRA | 6 | A | O | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-07-01 | 39394 | -4420 | 34974 | 34974 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1992
FIN | USA | South-east Asia halon-1211 training workshop in Japan |  | ASP | ASP | HAL | 08 | TRA | 7 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1992-10-01 |  | 1992-10-01 | 1992-10-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | Australia | Support to ASEAN regional conference on CFC and halons | Individual | ASP | ASP | SEV | 08 | TRA | 8 | A | O | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 4420 | -103 | 4317 | 4317 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1993
FIN | UNEP | Refrigeration training workshop for Asia and the Pacific | Individual | ASP | ASP | REF | 9 | TRA | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-04-01 |  | 1994-04-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 10 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-02-01 | 1999-04-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 10 | TRA | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-09-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | Singapore | Regional methyl chloroform elimination programme for ASEAN countries |  | ASP | ASP | SOL | 11 | TAS | 12 | A | O | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 |  | 1995-03-01 |  | 31976 | 0 | 31976 | 31976 | 100% | 0 | [5 empty] | 0 |  |  |  | 93
FIN | UNEP | Workshop for small and medium size enterprises on management of ODS phase-out | Individual | ASP | ASP | SEV | 12 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-21 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | Australia | Support to participants to the regional workshop on refrigeration and air conditioning training programme | Individual | ASP | ASP | REF | 12 | TRA | 14 | A | O | D |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-04-01 | 1994-05-01 | 66800 | 0 | 66800 | 66800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1994
FIN | Singapore | Training workshop on CFC-113 and methyl chloroform substitutes and alternative technologies in ASEAN countries |  | ASP | ASP | REF | 13 | TRA | 15 | A | O | D |  | 0 |  |  |  | 1994-07-01 |  | 1995-07-01 |  | 1995-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | UNEP | Regional workshop on aerosol conversion for the SEAP region | Individual | ASP | ASP | ARS | 16 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1995-06-01 |  | 1995-05-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | ODS officers network for Asia and the Pacific (1995) | Individual | ASP | ASP | SEV | 16 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-20 | 1996-03-01 |  | 1996-03-01 | 2000-03-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 | 0 | 8060 | 0 | 8060 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-23 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 82500 | 0 | 82500 | 82500 | 100% | 0 | 0 | 0 | 10725 | 0 | 10725 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNDP | Methyl bromide data collection for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TAS | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 2000-12-01 | 102000 | -64974 | 37026 | 37026 | 100% | 0 | 0 | 0 | 13260 | -8447 | 4813 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1995 | Non-Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for West Asia | Individual | ASP | ASP | SEV | 19 | TRA | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 1999-03-01 | 80000 | -19056 | 60944 | 60944 | 100% | 0 | 0 | 0 | 10400 | -2477.28 | 7922.72 | 0 | 0 | Project financially completed. | $19,056 plus $2,477 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Networking and Training (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | West Asian Network (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-12-01 | 169200 | -24323 | 144877 | 144877 | 100% | 0 | 0 | 0 | 21996 | -3161.99 | 18834.01 | 0 | 0 | Project financially completed. | $24,323 plus $3,162 PSC returned ExCom 30 | [12 empty] | 1998 | Non Investment
FIN | UNEP | West Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | South Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 199000 | -109950 | 89050 | 89050 | 100% | 0 | 0 | 0 | 25870 | -14293.5 | 11576.5 | 0 | 0 | Project financially completed. | $109,950 plus 14294 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Asia Regional Networks for SEAP and East Asia (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 209000 | -48604 | 160396 | 160396 | 100% | 0 | 0 | 0 | 27170 | -6318.52 | 20851.48 | 0 | 0 | Project financially completed. | $48,604 plus $6,319 PSC returned ExCom 30 | [12 empty] | 1995 | Non Investment
FIN | UNEP | West Asian regional network 1998 | Individual | ASP | ASP | SEV | 23 | TAS | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Asia Regional Networks (South-East and Pacific and South Asia) | Individual | ASP | ASP | SEV | 26 | TAS | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 | 0 | 27170 | 0 | 27170 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | West Asian Region Network | Individual | ASP | ASP | SEV | 26 | TAS | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | France | Survey for halon banking management plan in West Asia (Bahrain, Lebanon, Qatar and Yemen) |  | ASP | ASP | HAL | 28 | TAS | 29 | N | O | D |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2000-02-01 |  | 2000-02-01 | 2002-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed.
FIN | UNEP | Asia and the Pacific Regional networks (South East Asia and Pacific and South Asia) (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 219450 | -18941 | 200509 | 200509 | 100% | 0 | 0 | 0 | 28528.5 | -2462.33 | 26066.17 | 0 | 0 | Project financially completed. | $18,941 plus $2,462 PSC returned ExCom 46 | [12 empty] | 1999 | Non Investment
FIN | Sweden | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 31 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2001-02-01 | 2002-05-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | Regional Workshop on Control and Monitoring of ODS Consumption for the Southeast Asia/Pacific Region (funded with equal bilateral contributions from Sweden and Japan and implemented through UNEP) was held 22-27 May 2000 and was attended by ozone and customs officers from ten countries in the region. The participating countries developed a joint set of declarations and drafted national action plans for further work in their respective country. The report from the workshop was prepared by Sweden in February 2001. The project completion report prepared in coordination with UNEP was submitted 1 May 2002. The project was financially completed 27 May 2002. |  | 1999 | [11 empty] | 1999
FIN | UNEP | West Asian region network (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2005-12-01 | 120750 | -15000 | 105750 | 105750 | 100% | 0 | 0 | 0 | 15697.5 | -1950 | 13747.5 | 0 | 0 | Project financially completed. | $15,000 plus $1,950 PSC returned ExCom 46 | [12 empty] | 1999 | Non Investment
FIN | Japan | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 33 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-02-01 | 2002-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Regional workshop on monitoring and control of ODS consumption for the South Asia region | Individual | ASP | ASP | SEV | 29 | TRA | 34 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-07-01 | 2001-06-01 |  | 2001-08-01 | 2002-06-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | UNEP | West Asia military ODS workshop (to be held in conjunction with a global military environmental conference) | Individual | ASP | ASP | SEV | 30 | TRA | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-05-01 | 2003-06-01 | 150000 | -15122 | 134878 | 134878 | 100% | 0 | 0 | 0 | 19500 | -1965.86 | 17534.14 | 0 | 0 | Project financially completed. | $15,122 plus $1,966 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | Germany | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) | Halon banking | ASP | ASP | HAL | 30 | TAS | 36 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-02-01 | 2001-10-01 |  | 2005-04-01 | 2007-12-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 | 0 | 0 | 15275 | 0 | 15275 | 0 | 0 | Evaluation meeting Beirut 31.5.-4.6.2004; Comment on Terms, Comment on evaluation report; Calculation of operational costs of halon R&R equipment; contact addresses and quotations received for storage cylinders; discussion of alternative strategies. Proje | [13 empty] | 1997
FIN | France | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with Germany) |  | ASP | ASP | HAL | 30 | TAS | 37 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2004-04-21 | 2001-10-01 |  | 2004-12-07 | 2005-01-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 |  | 0 | 5875 | 0 | 5875 | 0 |  | Project completed. Final payment to GTZ in 2004.
FIN | UNEP | Workshop for halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen | Individual | ASP | ASP | HAL | 30 | TRA | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2002-10-01 | 2001-10-01 |  | 2004-12-01 | 2006-12-01 | 50000 | -2360 | 47640 | 47640 | 100% | 0 | 0 | 0 | 6500 | -307 | 6193.2 | -0.2 | 0 | Project financially completed. | $2,360 plus $ 307 returned at ExCom 52 | [12 empty] | 2000 | Non Investment
FIN | Germany | Survey for halon banking management plan in West Asia: Bahrain, Lebanon, Qatar and Yemen | Halon banking | ASP | ASP | HAL | 28 | TAS | 39 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-02-01 |  | 2000-03-01 | 2000-09-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project approved at 30th ExCom. | [13 empty] | 2001
FIN | UNEP | West Asian regional network (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 124000 | -15001 | 108999 | 108999 | 100% | 0 | 0 | 0 | 16120 | -1950.13 | 14169.87 | 0 | 0 | Project financially completed. | $15,001 plus $1,950 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region | Individual | ASP | ASP | SEV | 34 | TAS | 41 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 148500 | 0 | 148500 | 148500 | 100% | 0 | 0 | 0 | 19305 | 0 | 19305 | 0 | 0 | Project completed in May 2003. Balance of 25,000 USD transferred to Phase II for partly covering activities in Mongolia |  | 2001 | [12 empty] | Non-Investment
FIN | Sweden | Regional cooperation for monitoring and control of ODS consumption | Individual | ASP | ASP | SEV | 34 | TAS | 42 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-03-01 | 2005-04-01 |  | 2006-12-31 | 2008-05-30 | 250000 | 155818 | 405818 | 405818 | 110.9% | 0 | 0 | 0 | 0 | 20256 | 20256 | 0 | 0 | The final financial report was received from UNEP in May 2008. The final report reported a balance of USD 49,926. In July 2008 the MLF confirmed the return of the same amount as part of the Swedish contribution to the MLF. |  | 2002 | [11 empty] | 2001
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | ASP | ASP | FUM | 34 | TRA | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2002-06-01 |  | 2003-12-01 | 2005-12-01 | 80000 | -13239 | 66761 | 66760.95 | 100% | 0.05 | 0 | 0.05 | 10400 | -1721.07 | 8678.9235 | 0.0065 | 0 | Project financially completed. | $13,239 plus $1,721 returned ExCom 46 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: Three thematic meetings on issues related to the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-11-01 | 2005-04-01 |  | 2006-01-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: Technical assistance for other countries not included in the strategy | Individual | ASP | ASP | REF | 36 | TAS | 45 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-01-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: Policy assistance and guidance to countries for development of regulations | Individual | ASP | ASP | REF | 36 | TAS | 46 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | [8 empty] | 2005-12-01 |  |  |  |  | 2002 | Non Investment
FIN | UNEP | Implementation of the PIC Strategy: Technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 47 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2005-12-01 |  | 2007-12-01 | 2007-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | South East Asia and the Pacific and South Asia regional networks (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 48 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2002-06-01 | 2003-06-01 | 225000 | -20468 | 204532 | 204532 | 100% | 0 | 0 | 0 | 29250 | -2660.84 | 26589.16 | 0 | 0 | Project financially completed. | $20,468 plus $2,661 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region (phase 2) | Individual | ASP | ASP | SEV | 38 | TAS | 49 | A | O | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-06-01 | 2003-11-01 |  | 2004-03-01 | 2005-11-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 | 0 | 16250 | 0 | 16250 | 0 | 0 | Mongolia: Public awareness and IEC activities; Task Force Meeting China/Mongolia August 2003 / Iran: 15-02-04 National Consultation Meeting. Some funds were also used for building urgent capacity in the two new Parties Afghanistan and Bhutan as part of UN |  | 2002 | [12 empty] | Non-Investment
FIN | UNEP | Implementation of the PIC strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 44 | TAS | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | 0 | 30000 | 29527 | 98.42% | 473 | 0 | 0 | 3900 | 0 | 3838.51 | 61.49 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 2004 | Non Investment
ONG | Australia | Additional support for the regional strategy for 11 Article 5 countries in the Pacific (PIC strategy) | Individual | ASP | ASP | SEV | 50 | TAS | 52 | A | O | I |  | 0 |  | 0 |  | 2006-11-01 |  | 2007-11-01 | 2009-06-01 |  |  | 115000 | 0 | 115000 |  | 0% | 115000 |  | 115000 | 14950 | 0 |  | 14950 |  | Project will be completed in 2009. Only two countries do not have import/export controls and 4 countries will have customs training in mid 2009, organised by SPREP.
ONG | Japan | Project preparation for a demonstration project on ODS disposal | Individual | ASP | ASP | DES | 54 | PRP | 53 | A | O | I | [5 empty] | 2008-04-01 |  | 2009-03-01 |  |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 0 | 3900 | 0 | 0 | 3900 | 0 | Not provided. | [14 empty] | Non-Investment
FIN | UNEP | Country programme preparation | Individual | ASP | BAH | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-06-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | ASP | BAH | SEV | 20 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | [10 empty] | 1996 | Non Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BAH | REF | 21 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | ASP | BAH | REF | 22 | TAS | 4 | A | O | I | CFC | 20.5 | 20.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 242000 | -2849 | 239151 | 239151 | 100% | 0 | 0 | 0 | 31460 | -370 | 31090 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | ASP | BAH | REF | 26 | TRA | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-05-01 | 1999-12-01 |  | 2001-12-02 | 2001-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | ASP | BAH | REF | 26 | TRA | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-02 |  | 2001-12-01 | 2003-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  |  | 2001-05-01 | [8 empty] | 1998 | Non Investment
FIN | UNDP | Preparation of two project proposals in the commercial refrigeration subsector | Individual | ASP | BAH | REF | 27 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | Individual | ASP | BAH | REF | 29 | INV | 9 | A | O | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 |  | 173835 | 0 | 173835 | 157227 | 90.45% | 16608 | 0 | 13286.4 | 22599 | 0 | 20439.917 | 2159.083 | 0 | Completed in 2004. Disbursements do not yet reflect final figure and a correction will be made in 2009. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | Individual | ASP | BAH | REF | 29 | INV | 10 | A | O | I | CFC | 6.3 | 6.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-06-01 | 224478 | -51106 | 173372 | 173372 | 100% | 0 | 0 | 0 | 29182 | -6644 | 22538 | 0 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 1999 | Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | BAH | SEV | 31 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | ASP | BAH | SEV | 41 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNDP | Project preparation for a refrigerant management plan update | Individual | ASP | BAH | REF | 43 | PRP | 13 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-03-01 |  | 2006-12-01 |  | 24000 | 0 | 24000 | 22537 | 93.9% | 1463 | 0 | 1463 | 1800 | 0 | 1690.275 | 109.725 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment
COM | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | ASP | BAH | SOL | 45 | TAS | 14 | A | O | I | CTC TCA | 1.7 | 1.7 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 |  | 60000 | 0 | 60000 | 44132 | 73.55% | 15868 | 0 | 15000 | 5400 | 0 | 3972 | 1428 | 0 | The project is expected to be financially completed in 2009. | [11 empty] | 2007-07-01 |  | 2005 | INV
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | BAH | SEV | 47 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | BAH | PHA | 50 | INV | 16 | N | O | I | CFC | 38.4 | 38.4 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-12-01 |  | 2008-12-01 |  | 272500 | 0 | 272500 | 13537 | 4.968% | 258963 | 229432 | 207170.4 | 20437 | 0 | 1015.2502 | 19421.7498 | 17206.979 | Completed in 2009. During 2008, the international consultant was recruited and completed specifications of equipment for the R&R and MAC servicing components; suggested names and contacts for reliable suppliers for both components; prepared bidding document; Evaluated technical offers including recommended supplier(s); worked closely with the Project's Committee (UNDP/UNEP/ the NOU) during the preparation of the equipment specs and the final bid evaluation in discussing and clearing relevant pending issues, and; prepared a plan for the component of technical support to large-end users sector as per consultation with related stakeholders and end-users. Final accounts due in 2009. | [13 empty] | 2006 | Investment | 58.7 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | BAH | PHA | 50 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2008-07-01 | 2009-07-01 |  |  | 210000 | 0 | 210000 | 0 | 0% | 210000 | 110000 | 210000 | 27300 | 0 | 0 | 27300 | 14300 | Country contract signature delay due to change of national training institute. (phase I of project completed by March 09) | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | BAH | SEV | 53 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | Current ongoing ISP Phase with Bahrain. Based on SSFA, first payment was disbursed and second payment is expected to be disbursed soon, following submission of required reports of previous ISP Phase IV. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BAH | PHA | 55 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-03-01 |  |  | 105000 | 0 | 105000 | 0 | 0% | 105000 | 0 | 105000 | 13650 | 0 | 0 | 13650 | 0 | work plan agreed with country and UNIDO | [13 empty] | 2008
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | BAH | PHA | 55 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 0 | 10000 | 3375 | 0 | 0 | 3375 | 0 | UNEP is in the process of recruiting national experts to collect the required data. The first stakeholder workshop will take place in March 2009. | Recruitment of the national experts will be concluded this month. Legislation related matters are part of the responsibility of UNEP. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | LAC | BAR | SEV | 9 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-12-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNIDO | Preparation of project for retrofitting in all ice-making systems, icebin compressor systems, blast freezers, cold storage and chiller rooms | Individual | LAC | BAR | REF | 15 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | BAR | SEV | 15 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1997-12-01 |  | 1998-12-01 | 1999-10-01 | 136000 | -1050 | 134950 | 134950 | 100% | 0 | 0 | 0 | 17680 | -136.5 | 17543.5 | 0 | 0 | Project financially completed. | $1,050 plus $137 PSC returned ExCom 30 | [12 empty] | 1992 | Non Investment
FIN | UNIDO | CFC-recovery, recycling and training in refrigeration | RMP | LAC | BAR | REF | 18 | TAS | 4 | A | O | I | CFC | 14 | 14 |  |  | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 1997-06-01 | 2000-07-01 | 165170 | -222 | 164948 | 164948 | 100% | 0 | 0 |  | 21472 | -63 | 21409 | 0 | 0 | FIN
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BAR | SEV | 26 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2005-12-01 | 2005-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Development of RMP | RMP | LAC | BAR | REF | 30 | PRP | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-05-01 | 2005-07-01 | 30000 | -7982 | 22018 | 22018 | 100% | 0 | 0 | 0 | 3900 | -1038 | 2862.34 | -0.34 | 0 | Project financially completed. | $17,982 plus $2,338 returned ExCom 46; $ -10,000 plus $ -1,300 PSC returned from ExCom 48 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Formulation of investment components of the RMP | Individual | LAC | BAR | REF | 39 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2003 | Investment
COM | UNEP | Extension of Institutional strengthening project (phase III) | Individual | LAC | BAR | SEV | 42 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-05 |  | 2007-11-01 |  | 58500 | 0 | 58500 | 57939.73 | 99.04% | 560.27 | 0 | 560.27 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan for end-users | Individual | LAC | BAR | REF | 42 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
ONG | UNEP | Implementation of the RMP: import-export licensing system and establishment of refrigeration and air-conditioning association | Individual | LAC | BAR | REF | 43 | TAS | 10 | A | O | I | CFC | 5.2 | 0 | 0 | 0 | 2004-07-01 | 2005-03-01 | 2006-12-01 | 2009-12-01 |  |  | 78000 | 0 | 78000 | 78000.3 | 100% | -0.3 | 0 | -0.3 | 10140 | 0 | 10140.039 | -0.039 | 0 | Final terminal and financial reports from old IS phases are pending and required for processing next payment. | [13 empty] | 2004 | Non Investment
ONG | UNDP | Implementation of the RMP: technical assistance project to the MAC and end-users sectors | RMP-Component | LAC | BAR | REF | 43 | TAS | 11 | N | O | I | CFC | 11.4 | 0 | 0 | 0 | 2004-07-01 |  | 2006-12-01 | 2010-02-01 |  |  | 172611 | 0 | 172611 | 0 | 0% | 172611 | 0 | 34522.2 | 15535 | 0 | 0 | 15535 | 0 | Implementing Agencies had been informed by Government of Barbados about approval of ODS licensing system in late 2007. This was not correct given that it has not yet been gazetted. Local and International consultants have been identified for project implementation, and the procurement process will initiate as soon as the ODS legislation has been gazetted. This is expected to happen in early 2009. | [13 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | LAC | BAR | REF | 43 | TAS | 12 | N | O | I | CFC | 1.7 | 0 | 0 | 0 | 2004-07-01 |  | 2006-12-01 | 2010-02-01 |  |  | 26150 | 0 | 26150 | 0 | 0% | 26150 | 0 | 5230 | 2354 | 0 | 0 | 2354 | 0 | See BAR-11. TORs developed for local and international consultants. Hiring process will begin in early 2009. | [13 empty] | 2004 | Non-Investment
ONG | UNEP | Renewal of institutional strengthening project (phase III, year 2) | Individual | LAC | BAR | SEV | 46 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2008-01-08 | 2007-07-01 | 2010-03-01 |  |  | 58500 | 0 | 58500 | 3700 | 6.325% | 54800 | 0 | 54800 | 0 | 0 | 0 | 0 | 0 | Funding agreement (SSFA) still not signed. Consequently, no disbursement has been paid. UNEP continues to encourage country to sign the document, including submission of letters to corresponding ministry, high level country missions and bilateral meetings through network activity. | [13 empty] | 2005 | Non Investment
ONG | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | BAR | PHA | 54 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-01 | 2010-01-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 1125 | 0 | 0 | 1125 | 0 | No activities in 2008 due to reasons explained below in BAR-11. | [13 empty] | 2008 | Investment
ONG | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | BAR | PHA | 54 | PRP | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-31 | 2010-03-31 |  |  | 15000 | 0 | 15000 | 2699 | 17.99% | 12301 | 10000 | 12301 | 1950 | 0 | 350.87 | 1599.13 | 1300 | No agreement for project implementation has been reached with the country so far. A mission to the country will take place in March 2009 to encourage that project preparation begins. | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BAR | PHA | 55 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 10000 | 85000 | 11050 | 0 | 0 | 11050 | 1300 | Preliminary discussions for project implementation and further arrangements are being set. First regional planning meeting will take place in March 2009. UNEP is also working in the Caribbean energy efficiency project, which will require the preparation of the national HCFC inventory in the hotel sector. | [13 empty] | 2008
FIN | UNEP | Preparation of country programme | Individual | AFR | BDI | SEV | 23 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-05-01 |  | 1998-09-01 | 1999-03-01 | 40000 | -10000 | 30000 | 30000 | 100% | 0 | 0 | 0 | 5200 | -1300 | 3900 | 0 | 0 | Project financially completed. | $10,000 plus $1,300 PSC returned ExCom 30 | [12 empty] | 1995 | Non Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities included in the RMP | RMP-Component | AFR | BDI | REF | 26 | TAS | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2001-07-01 | 2000-12-01 |  | 2003-11-01 | 2003-11-01 | 10450 | -415 | 10035 | 10035 | 100% | 0 | 0 | 0 | 1359 | -54 | 1305 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training for customs officers | Individual | AFR | BDI | REF | 26 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training technicians in good management practices | Individual | AFR | BDI | REF | 26 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 26 | TAS | 5 | A | O | I | CFC | 5.4 | 5.4 | 0 | 0 | 1998-11-01 | 2001-05-01 | 2000-12-01 |  | 2003-11-01 | 2004-01-01 | 119577 | -3603 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15545 | -468 | 15077 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNEP | Establishment of an Ozone Unit | Individual | AFR | BDI | SEV | 26 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-11 | 2001-12-01 |  | 2002-07-01 | 2003-07-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | AFR | BDI | ARS | 33 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | BDI | FOA | 33 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
COM | UNDP | Phase-out of CFC-11 and CFC-12 mixture in the manufacture of insecticides by conversion to hydrocarbon propellant at Fadi, S.A. (Fabrication d'insecticide et de product chimique) | Individual | AFR | BDI | ARS | 35 | INV | 9 | A | O | I | CFC | 8.8 | 8.8 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2004-12-01 |  | 2003-12-01 |  | 128900 | 0 | 128900 | 128720 | 99.86% | 180 | 0 | 144 | 16757 | 0 | 16733.6 | 23.4 | 0 | Completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Exim, S.A. | Individual | AFR | BDI | FOA | 35 | INV | 10 | A | O | I | CFC | 26.3 | 26.3 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2005-01-01 |  | 2003-12-01 | 2006-06-01 | 78262 | -8335 | 69927 | 69927 | 100% | 0 | 0 | 0 | 10174 | -1084 | 9090 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | AFR | BDI | SEV | 37 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-12-04 | 2005-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Project preparation for update of refrigerant management plan | Individual | AFR | BDI | REF | 40 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2004-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially Completed in 2005. | [13 empty] | 2003 | Investment
FIN | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 41 | TAS | 13 | N | O | I | CFC | 4.7 | 4.7 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 32500 | -153 | 32347 | 32347 | 100% | 0 | 0 | 0 | 2925 | -14 | 2911.23 | -0.23 | 0 | Completed in 2006. Financially Completed in 2008. | [13 empty] | 2003 | Investment
COM | UNEP | Implementation of the RMP: customs training programme (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 14 | A | O | I | CFC | 4.3 | 4.3 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2006-07-01 |  | 30000 | 0 | 30000 | 15015 | 50.05% | 14985 | 14985 | 14985 | 3900 | 0 | 1951.95 | 1948.05 | 1948.05 | Project completed | [13 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 15 | A | O | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-06-01 |  | 2006-07-01 |  | 22500 | 0 | 22500 | 10000 | 44.44% | 12500 | 12500 | 12500 | 2925 | 0 | 1300 | 1625 | 1625 | Project completed | [13 empty] | 2003 | Non Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | BDI | REF | 41 | TAS | 16 | N | O | I | CFC | 2.9 | 2.9 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 20000 | -464 | 19536 | 19536 | 100% | 0 | 0 | 0 | 1800 | -42 | 1758.24 | -0.24 | 0 | Completed in 2006. Financially Completed in 2008. | [13 empty] | 2003 | Non-Investment
COM | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BDI | SEV | 44 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 |  | 60000 | 0 | 60000 | 48008.55 | 80.01% | 11991.45 | 11991.39 | 11991.45 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | AFR | BDI | SOL | 45 | TAS | 19 | A | O | I | TCA | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2007-12-01 |  | 35000 | 0 | 35000 | 32871 | 93.92% | 2129 | 2025 | 2000 | 3150 | 0 | 2958 | 192 | 182 | The project will be financially completed upon disbursement of unliquidated obligations. | [11 empty] | 2007-07-01 |  | 2005 | INV
COM | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | BDI | PHA | 47 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-12-01 |  | 30000 | 0 | 30000 | 26037 | 86.79% | 3963 | 0 | 3963 | 2250 | 0 | 1952.775 | 297.225 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | BDI | SEV | 50 | INS | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2008-11-01 | 2009-06-01 |  |  | 60000 | 0 | 60000 | 43037.73 | 71.73% | 16962.27 | 13500 | 16962.27 | 0 | 0 | 0 | 0 | 0 | Implementation of IS project ongoing successfully. The NOU organised consultative meetings with various stakeholders (refrigeration technicians, customs officers and parlementatrian to discuss steps for enfocement of ODS regulations and also identify acti | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2009-07-01 |  |  | 74000 | 0 | 74000 | 0 | 0% | 74000 | 69000 | 74000 | 9620 | 0 | 0 | 9620 | 8970 | MoU for the implementation of the TPMP signed. No progress recorded so far as NOU is undergoing some changes. | $22,000 plus $2,860 PSC returned ExCom 46 | [12 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BDI | PHA | 55 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MoU for organization of HCFC survey sent to the country in Dec 2008 | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | INV | 24 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-12-31 | 2009-12-01 |  |  | 76000 | 0 | 76000 | 0 | 0% | 76000 | 0 | 20000 | 6840 | 0 | 0 | 6840 | 0 | UNIDO has been continuously following up with UNEP on the implementation of the project, however, to date no activities have started by the lead agency. Equipment will be purchased once UNIDO receives guidance from the lead agency. | [13 empty] | 2008 | INV | 3.1 | 3.1 |  |  | Not yet confirmed | N/A | N/A
FIN | UNEP | Country programme preparation | Individual | AFR | BEN | SEV | 13 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-04 | 1995-10-01 |  | 1995-10-01 | 1995-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
CLO | UNIDO | Preparation of investment project for ODS phase-out in a foam producing plant (SIBAO) | Individual | AFR | BEN | FOA | 17 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 |  | 1995-09-01 |  |  | 1998-08-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | BEN | SEV | 18 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BEN | REF | 22 | TAS | 4 | A | O | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 114000 | 0 | 114000 | 114000 | 100% | 0 | 0 |  | 14820 | -13 | 14807 | 0 | 0 | FIN
FIN | UNDP | Preparation of two projects in the general foam subsector | Individual | AFR | BEN | FOA | 27 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | BEN | REF | 27 | PRP | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2000-12-01 | 2001-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | BEN | SEV | 28 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-09-01 | 2001-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333.29 | 0 | 4333.29 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | Canada | Implementation of the RMP: training of custom officials | RMP Update | AFR | BEN | REF | 32 | TRA | 8 | A | O | I |  | 5.2 | 5.2 | 0 |  | 2000-12-01 | 2003-01-01 | 2003-06-01 |  | 2006-08-08 | 2006-08-08 | 59900 | 0 | 59900 | 59900 | 100% | 0 |  | 0 | 7787 | 0 | 7787 | 0 |  | Project delayed until ODS import/export legislation was passed in April 2002. Train-the-Trainer Worshop held August 2003 and second phase followed in 2004. Canada asked that more customs officers be trained, as results are lower than under other comparabl |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practices | RMP Update | AFR | BEN | REF | 32 | TRA | 9 | A | O | I |  | 12.6 | 12.6 | 0 |  | 2000-12-01 | 2001-10-01 | 2002-12-01 |  | 2003-12-01 | 2004-12-01 | 144000 | 0 | 144000 | 144000 | 100% | 0 |  | 0 | 18720 | 0 | 18720 | 0 |  | Train-the-Trainer workshop held in Jan. 2002. Phase II training and monitoring completed in 2003. |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | Canada | Implementation of the RMP: development of code of good practice for technicians | RMP Update | AFR | BEN | REF | 32 | TAS | 10 | A | O | I |  | 0.9 | 0.9 | 0 |  | 2000-12-01 | 2003-01-01 | 2002-12-01 |  | 2004-06-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 1300 | 0 | 1300 | 0 |  | Final copies of Code of Good Practice received by Canada. |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | Canada | Implementation of the RMP: training of environmental inspectors and investigators | RMP Update | AFR | BEN | REF | 32 | TRA | 11 | A | O | I |  | 5 | 5 | 0 |  | 2000-12-01 | 2005-01-01 | 2003-12-01 |  | 2007-02-07 | 2007-02-07 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Train-the-Trainer workshop for 25 environmental inspectors completed in March 2005 and second and final workshop held in June 2006. Small remaining balance was left and Canada agreed that it be used for an ODS survey. Benin submitted survey and final expenditure report. PCR was submitted Dec. 2007. |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Plastique Elastomeres du Benin (P.E.B.) | Individual | AFR | BEN | FOA | 32 | INV | 12 | A | O | I | CFC | 27.3 | 27.3 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2003-07-01 |  | 2003-08-01 | 2005-09-01 | 143027 | -6481 | 136546 | 136546 | 100% | 0 | 0 | 0 | 18594 | -843 | 17751 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | BEN | SEV | 33 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-04 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333.29 | 0 | 4333.29 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | BEN | SEV | 40 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
ONG | Canada | Project preparation for a terminal phase-out management plan |  | AFR | BEN | PHA | 49 | PRP | 15 | A | O | I |  | 0 |  | 0 |  | 2006-07-01 |  | 2007-07-01 | 2009-07-09 |  |  | 12000 | 0 | 12000 | 0 | 0% | 12000 |  | 0 | 1560 | 0 | 0 | 1560 |  | TPMP has been prepared by UNEP and approved at 55th meeting, without the need for the funds approved for Canada. Therefore, Canada will ask for cancellation of this project at the 58th meeting and return related funds. |  | 2006 | [11 empty] | 2006 | Non-Inv.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | BEN | PHA | 49 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2007-07-31 |  | 2007-10-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase V) | Individual | AFR | BEN | SEV | 49 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-06-01 | 2008-06-30 |  | 2008-12-01 |  | 60000 | 0 | 60000 | 32501 | 54.17% | 27499 | 0 | 27499 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008 Subsequent phase approved at the 56 ExCom | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 | 2009-07-01 |  |  | 85000 | 0 | 85000 | 12500 | 14.71% | 72500 | 12500 | 72500 | 11050 | 0 | 1625 | 9425 | 1625 | No activities in 2008 | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | INV | 19 | A | O | I | CFC | 3.9 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-12-31 | 2009-12-01 |  |  | 106000 | 0 | 106000 | 1880 | 1.774% | 104120 | 0 | 50000 | 9540 | 0 | 169 | 9371 | 0 | Joint UNEP-UNIDO mission was organized to Benin in October 2008, where the implementation modalities have been agreed upon. Bidding for the procurement of equipment for the training centres and service workshops was completed, delivery of equipment is expected in June 2009. | [13 empty] | 2008 | INV | 7.9 | 7.9 |  |  | Not yet confirmed | N/A | N/A
ONG | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | AFR | BEN | SEV | 56 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-31 | 2010-12-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNDP | Reconnaissance survey and training | Individual | ASP | BGD | SEV | 04 | TAS | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1993-06-01 | 1997-12-01 | 55000 | -1150 | 53850 | 53850 | 100% | 0 | 0 | 0 | 7150 | -150 | 7000 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | BGD | SEV | 06 | CPG | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-06-01 |  | 1994-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | BGD | SEV | 14 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | BGD | SEV | 14 | INS | 4 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-09-01 | 1997-09-01 |  | 1999-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at Advanced Chemical Industries Ltd. (ACI) | Individual | ASP | BGD | ARS | 17 | INV | 5 | N | O | I | CFC | 123.6 | 123.6 | 0 | 0 | 1995-07-01 | 1998-12-01 | 1996-07-01 |  | 2002-08-01 | 2003-10-01 | 322920 | -343 | 322577 | 322577 | 100% | 0 | 0 | 0 | 41980 | -45 | 41935 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  |  | 1999-12-01 |  | 2001-05-01 | [7 empty] | 1995 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BGD | REF | 21 | PRP | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-01-01 |  | 1999-09-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Investment
CLO | IBRD | Country programme preparation |  | ASP | BGD | SEV | 04 | PRP | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 25564 | -25564 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Refrigerant management plan: Training prgramme for customs officers | Individual | ASP | BGD | REF | 29 | TRA | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2001-12-01 |  | 2004-07-01 | 2004-07-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 | 0 | 0 | 2925 | 0 | 2925 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase II) | Individual | ASP | BGD | SEV | 29 | INS | 9 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2001-12-01 | 2008-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2001. Financially completed in 2008. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national recovery and recycling project | RMP-Component | ASP | BGD | REF | 29 | TAS | 10 | A | O | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2005-07-01 | 2007-03-01 | 298270 | 0 | 298270 | 298270 | 100% | 0 | 0 | 0 | 38775 | 0 | 38775 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 1999 | Investment
COM | UNEP | Refrigerant management plan: Training of trainers in good refrigerant management practices and implementation of a national technicians training programme | Individual | ASP | BGD | REF | 29 | TRA | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-03-01 | 2001-12-01 |  | 2004-12-04 |  | 88000 | -947 | 87053 | 63299 | 72.71% | 23754 | 0 | 23754 | 11440 | -123 | 8228.87 | 3088.13 | 0 | Project completed | $ 947 plus $ 123 PSC returned to ExCom 50 | [12 empty] | 1999 | Non Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | ASP | BGD | REF | 29 | TAS | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2005-12-01 | 2007-01-01 | 15455 | -69 | 15386 | 15386 | 100% | 0 | 0 | 0 | 2009 | -9 | 2000 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | BGD | SEV | 35 | INS | 13 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-01-01 |  | 2004-12-01 | 2008-08-01 | 100000 | 0 | 100000 | 97901 | 97.9% | 2099 | 0 | 0 | 13000 | 0 | 12727.13 | 272.87 | 0 | Completed in 2004. Financially completed in 2008. | [13 empty] | 2001 | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | BGD | SEV | 36 | CPG | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-10-01 |  | 2006-12-01 | 2007-03-01 | 18750 | -202 | 18548 | 18548 | 100% | 0 | 0 | 0 | 2438 | -26 | 2411.24 | 0.76 | 0 | Completed in 2006. Financially completed in 2007. | [13 empty] | 2002 | Non-Investment
FIN | UNDP | Formulation of a national phase out plan | Individual | ASP | BGD | PHA | 39 | PRP | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
COM | UNEP | National ODS phase-out plan: training and certification programme for refrigeration service technicians, including development of a code of good practices (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 |  | 2008-04-01 |  | 39500 | 0 | 39500 | 0 | 0% | 39500 | 0 | 39500 | 5135 | 0 | 0 | 5135 | 0 | Project completed in April 2008 | [9 empty] | 2007-12-01 |  |  |  | 2004 | Non Investment
COM | UNEP | National ODS phase-out plan: training programme for custom officers (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2008-12-01 |  | 21000 | 0 | 21000 | 11986 | 57.08% | 9014 | 0 | 9014 | 2730 | 0 | 1558.18 | 1171.82 | 0 | Project completed in December 2008. The Customs training manual is being translated into Bangla and has already been included into the curriculum of the Training of Customs Officers. | [13 empty] | 2004 | Non Investment
COM | UNEP | National ODS phase-out plan: public awareness and information dissemination to main stakeholders (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 |  | 2008-12-01 |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Project completed in December 2008 | [9 empty] | 2007-12-01 |  |  |  | 2004 | Non Investment
ONG | UNDP | National ODS phase-out plan: technical assistance programme for the refrigeration servicing sub-sector (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 19 | N | O | I | CFC | 36 | 22 | 0 | 0 | 2004-04-01 | 2008-02-01 | 2005-04-01 | 2010-01-01 |  |  | 96000 | 0 | 96000 | 21870 | 22.78% | 74130 | 162 | 14826 | 7200 | 0 | 1640.25 | 5559.75 | 12.15 | Recruitment of project staff was completed, although there was some difficulty in identifying suitably qualified candidates for some of the positions in the PMU which resulted in a lengthy recruitment process. Due to the difficulty in attracting bids for the procurement of Retrofit Kits to conduct training workshop, project activities were delayed. Finally, a manufacturer of equipment was selected. An estimated list of tools & equipment and tentative training schedule for imparting training on retrofitting of domestic refrigerators with hydrocarbon refrigerants were prepared. ToR for the training was also revised. It is expected that retrofit training program will be completed in 2009. | [13 empty] | 2004 | Investment | 267.6 |  |  |  | Yes | No | No
ONG | UNDP | National ODS phase-out plan: technical assistance for the phase-out of ODS solvents (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 20 | N | O | I | CTC | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2009-01-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 10000 | 1875 | 0 | 0 | 1875 | 0 | See BGD-19. | [13 empty] | 2004 | Investment |  |  |  |  | Yes | No | No
ONG | UNDP | National ODS phase-out plan: monitoring and management unit (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 21 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2009-01-01 |  |  | 34000 | 0 | 34000 | 0 | 0% | 34000 | 0 | 13600 | 2550 | 0 | 0 | 2550 | 0 | See BGD-19. | [13 empty] | 2004 | Non-Investment |  |  |  |  | Yes | No | No
COM | UNDP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | BGD | SEV | 44 | INS | 23 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2007-12-01 |  | 130000 | 0 | 130000 | 128412 | 98.78% | 1588 | 0 | 1270.4 | 9750 | 0 | 9630.9 | 119.1 | 0 | Completed in 2007. | [13 empty] | 2004 | Non-Investment
COM | UNDP | Formulation of a phase-out project in the MDI sector | Individual | ASP | BGD | ARS | 50 | PRP | 24 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-04-01 |  | 30000 | 0 | 30000 | 22950 | 76.5% | 7050 | 0 | 7050 | 2250 | 0 | 1721.25 | 528.75 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
FIN | UNEP | Formulation of a transitional strategy for MDI | Individual | ASP | BGD | ARS | 50 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
ONG | UNDP | Phase-out of CFC consumption in the manufacture of aerosol MDIs (Beximco, Square Pharmaceutical and Acme Pharmaceutical) | Individual | ASP | BGD | ARS | 52 | INV | 26 | N | O | I | CFC | 76.3 | 0 | 0 | 0 | 2007-07-01 |  | 2011-07-01 | 2011-07-01 |  |  | 2776778 | 0 | 2776778 | 0 | 0% | 2776778 | 0 | 555355.6 | 208258 | 0 | 0 | 208258 | 0 | The project document was signed by the Government in October 2008 and project activities have commenced in 2008 including recruiting the international technical expert. | [13 empty] | 2007 | Investment
ONG | UNEP | Transition strategy for phasing out use of CFCs in the manufacturing of MDIs | Individual | ASP | BGD | ARS | 52 | TAS | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2011-07-31 | 2011-07-31 |  |  | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | MOU has been signed in October 2008. In the mean time, workshops on awareness have been implemented since April 2008 by Bangladesh Lung Foundation in cooperation with industry. Consultations were also undertaken on regulations implementation with the NOU during missions in the year 2008. Assistance was provided to the country to address the challenging compliance situation relating to CFC MDI phaseout by expeditious project implementation, expeditious implementation of national regulations etc. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | BGD | SEV | 53 | INS | 28 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 | 2010-01-01 |  |  | 130000 | 0 | 130000 | 17765 | 13.67% | 112235 | 0 | 22447 | 9750 | 0 | 1332.375 | 8417.625 | 0 | Project Document has been signed in 2008 and activities, including extension of the project staff has been completed | [13 empty] | 2007 | Non-Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | BGD | PHA | 56 | PRP | 29 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 125000 | 0 | 125000 | 0 | 0% | 125000 | 0 | 125000 | 9375 | 0 | 0 | 9375 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BGD | PHA | 56 | PRP | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 3250 | 0 | 0 | 3250 | 0 | Newly approved project. Discussions underway to kick-off HPMP preparation | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | BHA | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | BHA | SEV | 19 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-03-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | BHA | REF | 21 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2543 | 12457 | 12457 | 100% | 0 | 0 | 0 | 1950 | -331 | 1619 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training in monitoring and controlling of ODSs | Individual | LAC | BHA | REF | 23 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-08-01 | 1998-02-04 |  | 2005-09-01 | 2008-12-01 | 26500 | -4167 | 22333 | 18166 | 81.34% | 4167 | 0 | 0 | 3445 | -542 | 2361.58 | 541.42 | 0 | Project financially completed balance to be returned to ExCom 57 | $ 4,167 plus 542 PSC returned to ExCom 50 | [12 empty] | 1997 | Non Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BHA | REF | 23 | TAS | 5 | A | O | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-05-01 | 151400 | -12625 | 138775 | 138775 | 100% | 0 | 0 | 0 | 19682 | -1641 | 18041 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training the trainers of technicians in the refrigeration sector | Individual | LAC | BHA | REF | 23 | TRA | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-05-01 | 2003-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Preparation of a terminal phaseout plan | RMP | LAC | BHA | SEV | 27 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-12-01 | 2002-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
COM | IBRD | Terminal phaseout management plan | Multiyear | LAC | BHA | PHA | 35 | INV | 8 | N | O | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2004-11-01 | 2003-12-01 |  | 2003-12-01 |  | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 | 0 | 31200 | 0 | 31200 | 0 | 0 | Verification reports of CFC consumption in the Bahamas in 2004 and 2005 was 21.318 and 13 ODP MT, respectively. Phaseout in both years was ahead of agreed schedule. The import/export control system has already been established and made operational in 2006. Regulations to ban imports of CFC equipment and CFCs have already been promulgated. | [13 empty] | 2001 | INV | 48 | 48 | 0 | 0 | Yes | Yes | Yes
FIN | UNEP | Extension of institutional strengthening project: phase 2 (one year) | Individual | LAC | BHA | SEV | 39 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-04-01 |  | 2006-07-01 | 2007-07-01 | 21666 | 0 | 21666 | 21666 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase II ) | Individual | LAC | BHA | SEV | 42 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2006-07-01 |  | 21667 | 0 | 21667 | 16968 | 78.31% | 4699 | 0 | 4699 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | IBRD | Terminal phase-out management plan: 2004-2005 biennial programme | Multiyear | LAC | BHA | PHA | 44 | INV | 12 | N | O | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2005-12-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Complete phaseout was achieved in 2008. A review was made at the end of 2008 to determine whether any additional efforts were required to ensure sustainable phaseout. | [13 empty] | 2003 | INV | 25 | 13 | 0 | 0 | Yes | Yes | Yes
ONG | UNEP | Extension of the institutional strengthening project (phase III ) | Individual | LAC | BHA | SEV | 50 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-06-01 | 2008-07-01 | 2009-07-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | SSFA completed and sent to country for signing. First payment made. | [13 empty] | 2006 | Non Investment
ONG | IBRD | Terminal phase-out management plan: 2006-2007 biennial programme | Multiyear | LAC | BHA | PHA | 51 | INV | 14 | N | O | I | CFC | 25 | 25 | 0 | 0 | 2007-03-01 |  | 2009-03-01 | 2009-03-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 120000 | 120000 | 15600 | 0 | 0 | 15600 | 15600 | Complete phaseout was achieved in 2008. A review was made at the end of 2008 to determine whether any additional efforts were required to ensure sustainable phaseout. | [13 empty] | 2005 | INV | 14 | 4 | 0 | 0 | Yes | No | No
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BHA | PHA | 55 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions for project implementation and further arrangements are being set. First regional planning meeting will take place in March 2009. | [13 empty] | 2008
FIN | UNIDO | Country Programme Preparation | Individual | EUR | BHE | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | -2 | 10398 | 0 | 0 | FIN
FIN | UNIDO | Establishment of an Ozone Unit | Individual | EUR | BHE | SEV | 27 | INS | 2 | N | T | I |  | 0 | 0 |  |  | 1999-03-01 | 2001-05-01 | 2002-04-01 |  | 2004-12-01 | 2005-12-01 | 110000 | -5291 | 104709 | 104709 | 100% | 0 | 0 |  | 14300 | -709 | 13591 | 0 | 0 | FIN | [5 empty] | 2003-12-01
CLO | UNIDO | Project preparation in the aerosol sector | Individual | EUR | BHE | ARS | 30 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-04-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | EUR | BHE | FOA | 30 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-08-01 | 2001-04-01 |  | 2002-10-01 | 2003-06-01 | 15000 | -238 | 14762 | 14762 | 100% | 0 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial/ domestic refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -8025 | 6975 | 6975 | 100% | 0 | 0 |  | 1950 | -1045 | 905 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-04-01 | 15000 | -1613 | 13387 | 13387 | 100% | 0 | 0 |  | 1950 | -212 | 1738 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of two investment projects in the flexible foam sector | Individual | EUR | BHE | FOA | 34 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-08-01 | 2002-08-01 |  | 2004-01-01 | 2004-04-01 | 15000 | -738 | 14262 | 14262 | 100% | 0 | 0 |  | 1950 | -99 | 1851 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Inga Co. | Individual | EUR | BHE | FOA | 35 | INV | 8 | A | O | I | CFC | 21 | 21 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 101950 | -1506 | 100444 | 100444 | 100% | 0 | 0 |  | 13254 | -196 | 13058 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with cyclopentane in the manufacture of commercial refrigeration equipment at Bira, Bihac | Individual | EUR | BHE | REF | 35 | INV | 9 | A | O | I | CFC | 29 | 29 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2005-12-01 | 2006-12-01 | 536956 | -795 | 536161 | 536161 | 100% | 0 | 0 |  | 69065 | -87 | 68978 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerants CFC-12 and R-502 with HFC-134a and R-404A, and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment and cold refrigeration chambers at Soko | Individual | EUR | BHE | REF | 35 | INV | 10 | A | O | I | CFC | 17.4 | 17.4 |  |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-05-01 | 159707 | -818 | 158889 | 158889 | 100% | 0 | 0 |  | 20762 | -139 | 20623 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of two investment projects in the commercial refrigeration sector | Individual | EUR | BHE | REF | 36 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -3464 | 11536 | 11536 | 100% | 0 | 0 |  | 1950 | -453 | 1497 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of an investment project in the rigid foam sector | Individual | EUR | BHE | FOA | 36 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-09-01 | 2003-04-01 |  | 2004-01-01 | 2004-12-01 | 15000 | -417 | 14583 | 14583 | 100% | 0 | 0 |  | 1950 | -57 | 1893 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | BHE | PHA | 36 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2003-12-01 | 2005-05-01 | 80000 | -1922 | 78078 | 78078 | 100% | 0 | 0 |  | 10400 | -266 | 10134 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a, CFC-11 with HCFC-141b, and TCA with non-cleaning process in the manufacture of commercial refrigeration equipment, panels, and heat exchangers at three enterprises (Soko Paneli, Soko IPV and Kuca Leda) | Individual | EUR | BHE | REF | 39 | INV | 14 | A | O | I | CFC TCA | 13.7 | 13.7 |  |  | 2003-04-01 | 2003-11-01 | 2004-07-01 |  | 2005-12-01 | 2007-09-01 | 175283 | -5869 | 169414 | 169414 | 100% | 0 | 0 |  | 15775 | -528 | 15247 | 0 | 0 | FIN | [13 empty] | 2002
COM | UNIDO | Phase-out of CFC-11 by conversion to n-pentane in the manufacture of rigid foam products for insulating purposes at Stirokart Co. | Individual | EUR | BHE | FOA | 39 | INV | 15 | A | O | I | CFC | 33 | 33 |  |  | 2003-04-01 | 2004-04-01 | 2004-07-01 |  | 2006-12-01 |  | 364650 | 0 | 364650 | 350677 | 96.17% | 13973 | 13957 | 13000 | 27349 | 0 | 26301 | 1048 | 1047 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2002
COM | UNIDO | National ODS phase-out plan (first trance) | Multi-Year | EUR | BHE | PHA | 41 | INV | 16 | A | O | I | CFC TCA | 0 | 27.3 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2006-12-01 |  | 265300 | 0 | 265300 | 263301 | 99.25% | 1999 | 747 | 1000 | 19898 | 0 | 19748 | 150 | 56 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2003 | INV | 168.7 | 190.3 |  |  | No | N/A | N/A
COM | UNIDO | Phase-out of methyl bromide in tobacco seedling vegetables and flower production sector | Individual | EUR | BHE | FUM | 41 | INV | 17 | A | O | I | MBR | 11.8 | 11.8 |  |  | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2006-12-01 |  | 229000 | 0 | 229000 | 225663 | 98.54% | 3337 | 0 | 1 | 20610 | 0 | 20310 | 300 | 0 | Financial completion in Dec 2008. | [13 empty] | 2003 | INV
ONG | UNIDO | Phase-out of halon consumption | Individual | EUR | BHE | HAL | 42 | TAS | 18 | A | O | I | HAL | 4.1 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2006-04-01 | 2009-06-01 |  |  | 64600 | 0 | 64600 | 14181 | 21.95% | 50419 | 0 | 25000 | 5814 | 0 | 1276 | 4538 | 0 | The scope of international and local equipment procurement finalized. Bidding will be started upon settlement of the issue with the customs clearance and VAT exemption. | [13 empty] | 2003 | INV
ONG | UNIDO | Extension of institutional strengthening: phase II | Individual | EUR | BHE | SEV | 43 | INS | 19 | N | T | I |  | 0 | 0 |  |  | 2004-07-01 | 2008-12-01 | 2006-07-01 | 2010-12-01 |  |  | 95333 | 0 | 95333 | 60 | 0.06294% | 95273 | 0 | 40000 | 7150 | 0 | 5 | 7145 | 0 | Despite UNIDO's efforts, signature of the official documents has not yet been achieved. Mission will take place in March 2009 to revive the project implementation. | [13 empty] | 2004 | NON-INV
ONG | UNIDO | National ODS Phase-out Plan: second tranche | Multi-Year | EUR | BHE | PHA | 44 | INV | 21 | A | O | I | CFC TCA | 0 | 31.1 |  |  | 2004-12-01 | 2005-12-01 | 2005-12-01 | 2009-05-01 |  |  | 295860 | 0 | 295860 | 188887 | 63.84% | 106973 | 22072 | 30000 | 22190 | 0 | 14167 | 8023 | 1655 | The training the trainers programme for refrigeration service technicians is in progress. Selection of training centers has been completed. The scope of training equipments has been coordinated with NOU. Contract on the arrangment of training the trainers workshop has been arranged. The NOU has advised that from 1st January 2009 no more CFC import licenses will be issued. | [13 empty] | 2004 | INV | 103.2 | 50.8 |  |  | No | N/A | N/A
ONG | UNIDO | National ODS phase-out plan (third tranche) | Multi-Year | EUR | BHE | PHA | 52 | INV | 22 | A | O | I | CFC | 121.1 | 0 |  |  | 2007-07-01 | 2008-12-01 | 2008-07-31 | 2009-12-01 |  |  | 303000 | 0 | 303000 | 41 | 0.01353% | 302959 | 16435 | 25000 | 22725 | 0 | 3 | 22722 | 1233 | The training the trainers programme for refrigeration service technicians is in progress. Selection of training centers has been completed. The scope of training equipments has been coordinated with NOU. Contract on the arrangment of training the trainers workshop has been arranged. The NOU has advised that from 1st January 2009 no more CFC import licenses will be issued. | [13 empty] | 2007 | INV | 3 | 3 |  |  | Not yet confirmed | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | BHE | PHA | 55 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 40000 | 11250 | 0 | 0 | 11250 | 0 | TOR on HPMP preparation developed and submitted to NOU for identification of potential local contractors. | Bidding for all components of the HPMP preparation will be organized in due course. Initial workshop will be held upon award of contract. Work on legislation will be part of the sub-contract. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Preparation of country programme/RMP project | Individual | ASP | BHU | SEV | 43 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2006-07-01 |  | 2005-07-01 | 2006-08-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNDP | Preparation of investment component of the refrigerant management plan | Individual | ASP | BHU | REF | 43 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | BHU | SEV | 43 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-07-01 | 2006-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for customs and enforcement officers | Individual | ASP | BHU | REF | 45 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2006-04-01 |  | 2006-09-01 | 2007-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | BHU | REF | 45 | TRA | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-10-01 |  | 2006-09-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNDP | Implementation of the RMP: technical assistance in the refrigeration servicing sector | RMP-Component | ASP | BHU | REF | 45 | TAS | 6 | N | O | I | CFC | 0.1 | 0.1 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2006-12-01 |  | 45000 | 0 | 45000 | 44959 | 99.91% | 41 | 0 | 32.8 | 4050 | 0 | 4046.31 | 3.69 | 0 | Completed in 2006. | [13 empty] | 2005 | Non-Investment
FIN | UNEP | Institutional strengthening project (phase I) | Individual | ASP | BHU | SEV | 46 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2008-07-01 |  | 2007-07-01 | 2008-06-01 | 90000 | 0 | 90000 | 90000.42 | 100% | -0.42 | 0 | -0.42 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | BHU | PHA | 50 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 15000 | 0 | 15000 | 14999.73 | 100% | 0.27 | 0 | 0.27 | 1950 | 0 | 1949.9649 | 0.0351 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | BHU | PHA | 50 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-12-01 |  | 2007-03-01 |  | 15000 | 0 | 15000 | 4735 | 31.57% | 10265 | 0 | 10265 | 1125 | 0 | 355.125 | 769.875 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Terminal phase-out management plan | Individual | ASP | BHU | PHA | 52 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-05-01 | 2010-07-31 | 2010-07-31 |  |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | The Regulation on control of ODS in Bhutan has been updated after numerous consultation with the different Ministries and stakeholders and was approved for immediate implementation by the Government at the 26th Commission meeting on the 21 August 2008. The main revision in the regulation consists of the following: Update to reflect the recent Adjustment to the Montreal Protocol on HCFCs phase-out scheme. This will enable the licensing system for HCFC to be functional. Strengthening of penalties: For illegal activities concerning ODS and ODS based equipment, the penalties enforced can be as per the National Environment Protection Act, 2007 as well as the Customs Act. The previous regulation had penalty clauses only as per the Customs Act. The whole regulation is now linked to the National Environment Protection Act 2007. The earlier regulation did not address production based on the fact that there is no production in the country. This revised version now prohibits production of any type of ODS in the country, so that there will be no future complications. Equipment support (2 units of vacuum pump and evacuation unit) was provided by NOU, India, to NOU Bhutan under south-south cooperation with coordination from UNEP regional CAP team, Bangkok in June 2008. Assistance was provided for training the new National Ozone Officer in January 2008 at the NOU in New Delhi (three days) and at the UN Regional CAP Office in Bangkok (two days) in November 2007. A Training of Trainers programme on MAC and good refrigeration practices was organized in Thimphu during 9-12 June 2008 with technical assistance from UNEP, with 23 participants from different sectors such as education, the armed forces, private service technicians and other stakeholders. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan | One-off-Phaseout | ASP | BHU | PHA | 52 | INV | 11 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2010-07-01 | 2010-07-01 |  |  | 35000 | 0 | 35000 | 15005 | 42.87% | 19995 | 0 | 3999 | 3150 | 0 | 1350.45 | 1799.55 | 0 | Procurement of servicing equipment and tools were finalized and the procurement is in progress. The programme for USD 20 incentive payment for 250 domestic/commercial refrigeration/air conditioning equipment was initiated. However, the number of domestic refrigerators and commercial refrigerators volunteered for the retrofitting incentive was unsatisfactory. In spite of the incentive, the proponent found it more cost effective to buy new appliances. MAC retrofitting incentive programme has not been carried out due to lack of technical capacity. The activity will start after capacity of the Vocational Training Institute at Samthang is developed. End user conversion by retrofitting CFC based equipment in industrial refrigeration was completed. | [13 empty] | 2007 | Investment
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | BHU | SEV | 53 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project newly approved in the 53rd ExCom. The agreement between UNEP and Bhutan was signed in December 2008. But even with the delay of signing, the activities were continually implemented. Regulation on Control of Ozone Depleting Substances, 2008 (a revised regulation) has been developed, approved and enforced. ODS identifier supplied by UNEP given to the border customs; Meeting with custom officers in July 2008 on implementation of the ODS regulation. May 2008 – July 2008: Bilateral Meetings with relevant stakeholders such as department of trade, department of Industries, Dept. of Customs, Bhutan Food and Agriculture Regulatory Authority, Drug Regulatory Authority of Bhutan Awareness Programme: World Ozone Day celebrated on Sept. 16, 2008; Over 100 youths were sensitized on Ozone issue during the Environment Advocacy week in Jan 2008; Interschool quiz competition on 15 Sept. 2008; Interschool poster competition on 10 Sept. 2008; Ozone Advocacy program for the general public at the Centenary Ground from 19 Dec until 23 Dec. 2008; Initiation of ozone issues in the school in environment curriculum (pilot phase for 5 private schools in Thimphu); Development of posters for schools; Development of ozone advocacy car stickers for Bhutan Meetings Conducted with industry, stakeholders, Ministries and government agencies: 10th June 2008 for training of trainers of technicians in MAC; 19 Dec 2008 meeting with Hotel Association of Bhutan and other stakeholders for the phase out of CFC and introduction of the HCFC time-line (22 participants)· 21 August 2008: High level NEC Commission meeting during which progress, activities and ozone issues were presented to the members. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BHU | PHA | 55 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Country has been given inputs for National survey | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | ASP | BHU | PHA | 56 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 55000 | 7150 | 0 | 0 | 7150 | 0 | Newly approved project. Country has been given inputs for National survey | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | BKF | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-11-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 3900 | 390 | 4290 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Establishment of the Ozone Board | Individual | AFR | BKF | SEV | 11 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-12-01 | 1996-11-01 |  | 1997-06-01 | 1996-02-01 | 83500 | 0 | 83500 | 83500 | 100% | 0 | 0 | 0 | 10855 | 0 | 10855 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Training for refrigeration repair technicians | Individual | AFR | BKF | REF | 11 | TRA | 3 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1996-11-01 |  | 1996-11-01 | 1999-04-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 | 0 | 5395 | 0 | 5395 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs training) | Individual | AFR | BKF | SEV | 11 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-10-01 | 1994-12-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 | 0 | 1885 | 0 | 1885 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BKF | REF | 22 | TAS | 5 | A | O | I | CFC | 15.48 | 15.48 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | FIN
FIN | UNEP | Institutional strengthening renewal (Phase II) | Individual | AFR | BKF | SEV | 22 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 1999-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 | 0 | 7241 | 0 | 7241 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | BKF | REF | 24 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of institutional strengthening - Phase III | Individual | AFR | BKF | SEV | 27 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-07-01 | 2001-12-12 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 | 0 | 7241 | 0 | 7241 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | Canada | Implementation of the RMP: training of customs officers programme | RMP | AFR | BKF | REF | 29 | TRA | 9 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2002-08-01 | 2003-01-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 |  | 0 | 5525 | 0 | 5525 | 0 |  | Project Complete. PCR submitted. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers and technicians in good refrigeration management practices | RMP | AFR | BKF | REF | 29 | TRA | 10 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-03-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 5200 | 0 | 5200 | 0 |  | Training of technicians is completed as of March 2002. PCR submitted. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | BKF | REF | 32 | TAS | 11 | N | O | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2006-01-01 |  | 2006-12-01 | 2008-09-01 | 132250 | 0 | 132250 | 124841 | 94.4% | 7409 | 0 | 0 | 17193 | 0 | 16229.802 | 963.198 | 0 | Completed in 2006. Financially completed in 2008. | [13 empty] | 2000 | Non-Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase IV) | Individual | AFR | BKF | SEV | 33 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-01-03 | 2003-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 | 0 | 7241 | 0 | 7241 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | AFR | BKF | REF | 34 | TAS | 13 | N | O | I | CFC | 3.4 | 3.4 | 0 | 0 | 2001-07-01 |  | 2007-08-01 |  | 2006-12-01 | 2008-09-01 | 16350 | 0 | 16350 | 0 | 0% | 16350 | 0 | 0 | 2126 | 0 | 0 | 2126 | 0 | Completed in 2006. Financially completed in 2008. | [13 empty] | 2001 | Non-Investment
FIN | UNIDO | Workshop to raise awareness on use of methyl bromide in tobacco cultivation | Individual | AFR | BKF | FUM | 34 | TRA | 14 | A | O | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-01-01 | 2002-08-01 |  | 2002-12-01 | 2003-06-01 | 30000 | -7497 | 22503 | 22503 | 100% | 0 | 0 |  | 3900 | -979 | 2921 | 0 | 0 | FIN | [13 empty] | 2001 | NON-INV
FIN | UNEP | Renewal of institutional strengthening project (phase 5) | Individual | AFR | BKF | SEV | 38 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-04 | 2004-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | BKF | SEV | 44 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Project preparation request for TPMP | Individual | AFR | BKF | PHA | 47 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | Canada | Project preparation for the terminal phase-out management plan |  | AFR | BKF | PHA | 47 | PRP | 19 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-06 | 2006-12-01 |  | 2006-10-01 | 2006-10-01 | 10000 | -650 | 9350 | 9350 | 100% | 0 |  | 0 | 1300 | -100 | 1200 | 0 |  | TPMP prepared and submitted with UNEP at ExCom 50. Project completed. Remaining balance of $650 and associated support costs ($100) were returned to Fund. |  | 2005 | [11 empty] | 2005 | Non-Inv.
COM | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | BKF | SEV | 50 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2008-11-01 |  | 2008-12-01 |  | 72410 | 0 | 72410 | 71110 | 98.2% | 1300 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | Project Completed in December 2008 | [13 empty] | 2006 | Non Investment
COM | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | BKF | PHA | 50 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-03-01 |  | 2008-03-01 |  | 100900 | 0 | 100900 | 95082.95 | 94.23% | 5817.05 | 5186.05 | 5817.05 | 13117 | 0 | 12360.7835 | 756.2165 | 674.1865 | Project completed in March 2008. Second tranche approved in March 2008 | [13 empty] | 2006 | Non Investment
FIN | Canada | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | BKF | PHA | 50 | INV | 22 | A | O | I | CFC | 2 |  | 0 |  | 2006-11-01 | 2007-01-01 | 2008-03-01 |  | 2008-09-08 | 2008-10-08 | 98500 | 0 | 98500 | 98500 | 100% | 0 |  | 0 | 12805 | 0 | 12805 | 0 |  |  |  | 2006 | [11 empty] | 2006 | Investment | 5.44 | 4.2 |  |  | Yes
ONG | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2009-03-31 | 2009-03-31 |  |  | 102100 | 0 | 102100 | 72000 | 70.52% | 30100 | 30100 | 30100 | 13273 | 0 | 9360 | 3913 | 3913 | MOU signed and 1st disbursement done in August 2008 | [13 empty] | 2008
ONG | Canada | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | INV | 24 | A | O | I | CFC | 5.4 |  | 0 |  | 2008-04-01 | 2008-10-08 | 2009-03-01 | 2009-12-09 |  |  | 86500 | 0 | 86500 | 13000 | 15.03% | 73500 |  | 73500 | 11245 | 0 | 1000 | 10245 |  | Process for last phase of equipment procurement initiated in Sept. 2008; contract signed in January 2009 obligating $57,480. $13,000 provided to Burkina Faso for awareness-raising and local purchase of tools. Country has not yet confirmed 2008 consumption. |  | 2008 | [11 empty] | 2008 | Investment | 5.44 | n/a |  |  | No
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BKF | PHA | 55 | PRP | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | MOU sent to Country for Signing | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | BKF | SEV | 56 | INS | 26 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-31 | 2010-12-31 |  |  | 72410 | 0 | 72410 | 0 | 0% | 72410 | 0 | 72410 | 0 | 0 | 0 | 0 | 0 | MOU for implementation sent to the country in Dec 2008 | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | AFR | BKF | PHA | 56 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 55000 | 7150 | 0 | 0 | 7150 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Completion of country programme preparation | Individual | LAC | BOL | SEV | 16 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1995-10-01 | 1999-01-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Establishment of the Ozono Governmental Commission (COGO) | Individual | LAC | BOL | SEV | 18 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 1999-12-01 | 91000 | 0 | 91000 | 91000 | 100% | 0 | 0 | 0 | 11830 | 0 | 11830 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BOL | SEV | 18 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-05-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BOL | REF | 20 | TAS | 4 | A | O | I | CFC | 13.8 | 13.8 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 146000 | -691 | 145309 | 145309 | 100% | 0 | 0 | 0 | 18980 | -90 | 18890 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BOL | FOA | 21 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | -2187 | 22813 | 22813 | 100% | 0 | 0 | 0 | 3250 | -284 | 2966 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration and one in domestic refrigeration sub-sectors | Individual | LAC | BOL | REF | 24 | PRP | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | BOL | REF | 24 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 2001-01-01 | 1999-02-01 |  | 2001-12-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BOL | SEV | 26 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-03 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 | 0 | 7887.1 | 0 | 7887.1 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (cotton and soy) | Individual | LAC | BOL | FUM | 27 | PRP | 9 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
CLO | Belgium | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Quimica Andina |  | LAC | BOL | FOA | 28 | INV | 10 | A | O | I |  | 5 | 0 |  |  | 1999-07-01 | 0 | 2002-02-01 |  |  |  | 108480 | -108480 | 0 | 0 | 0% | 0 |  | 0 | 0 |  |  | 0 |  | Agreement between UNDP and the Belgian Government finally signed in September 2000. However, funds not yet received as of 31 December 2000. Info as of 31 May 2001: funds received in Feb. 2001. Project document not yet signed by Bolivian Govt. However, invitations to bid were sent out and bid analysi was done. However, we had to re-bid because offers did not meet specs for one machine. New bid analysis on-going. Info as of 31 December 2001: New ministry was undergoing some verification of the enterprises which were being considered for MLF funding since according to some new regulations, in order for Quimica Andina to qualify it needed to be one of the higher national consumers of CFC-11. Only if this was the case would the project be approved and the PRODOC signed. |  | 36923
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | BOL | FUM | 33 | PRP | 11 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BOL | REF | 33 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BOL | FOA | 33 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | BOL | SEV | 34 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 | 0 | 7887.1 | 0 | 7887.1 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNDP | Foam sector ODS phaseout (two enterprises: Isolcruz and Teplo) | Individual | LAC | BOL | FOA | 35 | INV | 15 | A | O | I | CFC | 4.9 | 4.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-05-01 | 2007-01-01 | 161211 | -5875 | 155336 | 155336 | 100% | 0 | 0 | 0 | 20957 | -764 | 20193 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Investment
COM | UNDP | Terminal methyl bromide phase-out, excluding QPS applications | One-off-Phaseout | LAC | BOL | FUM | 35 | INV | 16 | N | O | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-12-01 |  | 2007-12-01 |  | 221032 | 0 | 221032 | 221031 | 100% | 1 | 0 | 0.8 | 28734 | 0 | 28733.87 | 0.13 | 0 | Completed in 2007. | [13 empty] | 2001 | Investment
FIN | Canada | Implementation of the RMP: assistance in preparation of regulations and technical norms | RMP | LAC | BOL | REF | 36 | TAS | 17 | A | O | I |  | 1.3 | 1.3 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2003-11-01 | 2003-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  | 0 | 1690 | 0 | 1690 | 0 |  | Funds disbursed for legal consultant and workshops to develop legislation. Legislation approved in March 2004. Project completed. PCR submitted. |  | 2002 | [11 empty] | 2002 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration (terminal phase-out) sector | Individual | LAC | BOL | REF | 36 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-09-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | Canada | Implementation of the RMP: training programme for customs officers and technical staff in municipalities | RMP | LAC | BOL | REF | 36 | TRA | 19 | A | O | I |  | 5 | 5 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2005-04-01 | 2005-04-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 |  | 0 | 6240 | 0 | 6240 | 0 |  | Train-the-trainers workshop completed in 2004. Phase II customs officers training completed in March 2005 with 83 officers trained. A total of $13,972 remained in funding after project completion and were used on other RMP components (principally the moni |  | 2002 | [11 empty] | 2002 | Investment
FIN | Canada | Implementation of the RMP: public awareness programme on issues related to the ozone layer | RMP | LAC | BOL | REF | 36 | TAS | 20 | A | O | I |  | 5.4 | 5.4 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2008-03-08 | 2008-03-08 | 52000 | 0 | 52000 | 52000 | 100% | 0 |  | 0 | 6760 | 0 | 6760 | 0 |  | Last remaining activity, production of school texts on ozone depletion, was delayed due to administration difficulties - now completed. Final report was received in early 2008. |  | 2002 | [11 empty] | 2002 | Investment
FIN | Canada | Implementation of the RMP: training programme for refrigeration technicians | RMP | LAC | BOL | REF | 36 | TRA | 21 | A | O | I |  | 5.7 | 5.7 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2005-06-01 | 2005-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | Train-the Trainers workshop held in Sept. 2004. Training equipment purchased and distributed. Phase II training completed in May 2005 with 265 technicians trained. Remaining funds from 2005 were used in 2006 on other RMP components (mainly the monitoring) |  | 2002 | [11 empty] | 2002 | Investment
FIN | Canada | Implementation of the RMP: monitoring the activities in the RMP project | RMP | LAC | BOL | REF | 36 | TAS | 22 | A | O | I |  | 5.9 | 5.9 | 0 |  | 2002-03-01 | 2002-09-01 | 2005-12-01 |  | 2008-03-08 | 2008-03-08 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Monitoring database and information system installed and working, as well as ODS monitoring and reporting activities. Funds used principally for local project consultant to implement, monitor and report on project activities. All activities have been completed and final report received in early 2008. |  | 2002 | [11 empty] | 2002 | Investment
FIN | Canada | Implementation of the RMP: recovery and recycling | RMP | LAC | BOL | REF | 39 | TAS | 23 | A | O | I | CFC | 30.3 | 30.3 | 0 |  | 2003-04-01 | 2005-01-01 | 2005-12-01 |  | 2008-03-08 | 2008-03-08 | 292000 | 0 | 292000 | 292000 | 100% | 0 |  | 0 | 37960 | 0 | 37960 | 0 |  | 1st Phase of R&R equipment was shipped to Bolivia in April 2005 and 2nd Phase in Dec. 2005. The majority of the equipment has been distributed to technicians and training has been completed. A few batches of R&R machines have not been distributed due to administrative problems, but Bolivia expects to distribute them prior to end of April 2009. |  | 2003 | [11 empty] | 2002 | Investment
FIN | UNEP | Extension of the institutional strengthening project | Individual | LAC | BOL | SEV | 40 | INS | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNDP | Terminal umbrella project for the commercial refrigeration manufacturing sector | Individual | LAC | BOL | REF | 42 | INV | 25 | N | O | I | CFC | 5.8 | 5.8 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2007-04-01 |  | 2007-12-01 |  | 88840 | 0 | 88840 | 88710 | 99.85% | 130 | 0 | 104 | 7995 | 0 | 7983.3009 | 11.6991 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment
COM | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | BOL | SEV | 47 | INS | 26 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2008-12-01 |  | 78867 | 0 | 78867 | 78866.76 | 100% | 0.24 | 0 | 0.24 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. Country has complied with reporting requirements. ISP (phase VI) started | [13 empty] | 2005 | Non Investment
FIN | Canada | Project preparation for the terminal phase-out management plan |  | LAC | BOL | PHA | 47 | PRP | 27 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-06 | 2006-12-01 |  | 2007-02-07 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | TPMP prepared, submitted to ExCom 51 and approved. Project and last payment completed in February 2007. |  | 2005 | [11 empty] | 2005 | Non-Inv.
ONG | Canada | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | TAS | 28 | A | O | I | CFC,CTC | 0 |  | 0 |  | 2007-03-01 | 2007-06-01 | 2009-12-01 | 2009-03-01 |  |  | 79000 | 0 | 79000 | 67000 | 84.81% | 12000 |  | 12000 | 10270 | 0 | 5000 | 5270 |  |  |  | 2007 | [11 empty] | 2007 | Investment | 11.4 | 2.96 |  |  | Yes
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | INV | 29 | N | O | I | CFC | 0.1 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-03-01 | 2010-03-01 |  |  | 151000 | 0 | 151000 | 40245 | 26.65% | 110755 | 0 | 22151 | 11325 | 0 | 3018.375 | 8306.625 | 0 | During 2008 three workshops were developed with the refrigeration technicians in Cochabamba, La Paz and Santa Cruz, to evaluate strengths, opportunities, weaknesses and risks with regards to the incentives component of the TPMP. Also during 2008, the development and review of the draft "Bolivian Law for the protection of the ozone layer" took place, as well as the development of training courses to begin the application of the NOU WEB site to provide a place for the periodic reporting of ODS consumption by the refrigeration technicians, so as to facilitate the exchange of information and promote consultations within the sector. Second tranche expected to be approved at 57th ExCom. | [13 empty] | 2007 | Investment | 26.7 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | BOL | SEV | 53 | INS | 30 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 | 2009-11-01 |  |  | 78867 | 0 | 78867 | 63094 | 80% | 15773 | 15773 | 15773 | 0 | 0 | 0 | 0 | 0 | During 2008 the IS project in Bolivia has assisted in areas such as: 1) ODS control and monitoring system, having 13 companies authorized to import refrigerants, 3 training centres for the refrigerant sector, 300 technicians trained, from which 90 are already certified, 2) Further implementation of the country's TPMP, bringing support to the preparation of the national strategy for incentives to eliminate CFC consumption, purchase of storage cilinders and refrigerant ID devices, as well as inspections in duty free zones, and further revisions to the national ODS regulatory framework. In addition, 159 customs officers from 13 regional customs bureaus received training. 3) Public awareness: 10 conferences to general public performed, distribution of ozone materials (posters, brochures, etc.) in all the 9 provinces of the country and advertising campaign during the carnaval. | [13 empty] | 2007 | Non Investment
ONG | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BOL | PHA | 55 | PRP | 31 | A | O | I | HCFC | 0 |  | 0 |  | 2008-07-01 |  | 2009-07-01 | 2009-12-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 19500 | 0 | 0 | 19500 | 0 | Project agreement has been signed between GTZ and Ministry. Consultants were selected and terms of references were agreed on. The survey will start during May/June 09, together with legislation and regulation preparation which will be reviewed during coming months.
FIN | UNEP | Country programme preparation | Individual | AFR | BOT | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1994-07-01 |  | 1994-06-01 | 1994-12-01 | 30000 | 10000 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3900 | 1300 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Institutional strengthening (establishment of the Ozone Office) | Individual | AFR | BOT | SEV | 13 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1997-07-01 |  | 2003-12-01 | 2003-12-01 | 90200 | 0 | 90200 | 90200 | 100% | 0 | 0 | 0 | 11726 | 0 | 11726 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | BOT | REF | 21 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -8880 | 11120 | 11120 | 100% | 0 | 0 | 0 | 2600 | -1154 | 1446 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of a demonstration project (grain fumigation) | Individual | AFR | BOT | FUM | 24 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: non-soil cultivation techniques, bio-fumigation with solarization, and application of various mixtures of other chemicals in low doses in tomatoes and curcubits | Individual | AFR | BOT | FUM | 25 | DEM | 5 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-11-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 146300 | 0 | 146300 | 146300 | 100% | 0 | 0 |  | 19019 | 0 | 19019 | 0 | 0 | FIN
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | BOT | REF | 26 | TAS | 6 | A | O | I | CFC | 1.5 | 1.66 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2005-06-05 | 2006-06-01 | 70375 | 0 | 70375 | 70375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted in 2006 | [13 empty] | 2000
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | BOT | REF | 39 | PRP | 7 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-12-01 | 2005-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project preparation completetd. RMP update to be submitted for approval at 45th Excom | [13 empty] | 2002
COM | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | BOT | SEV | 41 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-06-01 | 2005-12-01 |  | 2008-02-01 |  | 78173 | 0 | 78173 | 44980 | 57.54% | 33193 | 0 | 33193 | 0 | 0 | 0 | 0 | 0 | Project completed in February 2008. | [13 empty] | 2003 | Non Investment
ONG | Germany | Implementation of the RMP update | RMP Update | AFR | BOT | REF | 45 | TAS | 9 | A | O | I | CFC | 5.8 | 5.8 | 0 |  | 2005-04-01 | 2005-11-01 | 2008-04-01 | 2009-06-01 |  |  | 64295 | 0 | 64295 | 52000 | 80.88% | 12295 | 0 | 12295 | 8358 | 0 | 6759.7169 | 1598.2831 | 0 | Botswana government worked very hard to get its regulations approved in 2009 which allowed for the conducting of customs officers trainings which awaited the approval of the regulations.
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BOT | SEV | 53 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 78173 | 0 | 78173 | 0 | 0% | 78173 | 0 | 78173 | 0 | 0 | 0 | 0 | 0 | MOU for implementation agreed with the country. First payment under process | [13 empty] | 2007 | Non Investment
ONG | Germany | Project preparation for a terminal phase-out management plan | Individual | AFR | BOT | PHA | 55 | PRP | 11 | A | O | I |  | 0 |  | 0 |  | 2008-07-01 | 2008-10-01 | 2009-01-01 | 2009-03-01 |  |  | 30000 | 0 | 30000 | 15000 | 50% | 15000 | 0 | 15000 | 3900 | 0 | 1950 | 1950 | 0 | TPMP project was submitted for apprval at the 57th Excom.
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | BRA | SEV | 04 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 114583 | -73761 | 40822 | 40822 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 06 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 123788 | -122316 | 1472 | 1472 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | BRA | SEV | 06 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -89419 | 102459 | 102459 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Demonstration programme to improve domestic refrigerator servicing and CFC recycling in service shops | Individual | LAC | BRA | REF | 06 | DEM | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-02-01 | 1993-12-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Project preparation on converting CFC-11 central air conditioning units with HCFC-123 or HFC-134a |  | LAC | BRA | REF | 07 | PRP | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-12-01 | 1993-06-01 |  | 1995-12-01 | 1995-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Assembly line refitting for HFC-134a refrigerator compressor, commercial production | Individual | LAC | BRA | REF | 07 | INV | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 530000 | -530000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1995-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC-12 collection, recycling and conservation programme for household refrigerator maintenance and repair shops | Individual | LAC | BRA | REF | 07 | TAS | 7 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1999-06-01 | 1995-06-01 |  |  | 2001-07-01 | 2000000 | -1980000 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1995-06-01 | 1999-12-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment projects for elimination of CFCs in the polymer foams manufacturing | Individual | LAC | BRA | FOA | 09 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-09-01 |  | 1996-08-01 | 1999-08-01 | 150000 | -5144 | 144856 | 144856 | 100% | 0 | 0 |  | 19500 | -699 | 18801 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | BRA | SEV | 09 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112000 | -20388 | 91612 | 91612 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening support for the implementation of the Montreal Protocol | Individual | LAC | BRA | SEV | 10 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-03-01 | 1999-12-01 | 403100 | 0 | 403100 | 403100 | 100% | 0 | 0 | 0 | 52403 | 0 | 52403 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1993 | Non-Investment
FIN | Canada | Refrigeration training workshop in the state of Sao Paulo | Individual | LAC | BRA | REF | 11 | TRA | 11 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-09-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1993 and approved in retroactive funding in November 1993. |  | 1993 | 2000-01-01 | [10 empty] | 1993 | Non-Inv.
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 11 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1994-11-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Therm-Jet (Belo Horizonte), Zenimont and Lavale (Sao Paulo) | Individual | LAC | BRA | FOA | 12 | INV | 13 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1994-03-01 | 1996-02-01 | 1995-03-01 |  | 1997-07-01 | 2000-12-01 | 370000 | -15282 | 354718 | 354718 | 100% | 0 | 0 | 0 | 48100 | -1987 | 46113 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation of investment projects in the refrigeration sector (1994) |  | LAC | BRA | REF | 12 | PRP | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 164380 | -53297 | 111083 | 111083 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | System for storage and charging of ester oils used in the manufacture of HFC-134a compressors at Embraco | Individual | LAC | BRA | REF | 13 | INV | 15 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1994-09-01 |  | 1994-07-01 | 1995-07-01 | 221200 | 0 | 221200 | 221200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully implemented resulting in savings of 270 tons per year ODP. Project completed. |  |  | 1994-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to reduced CFC technology in the manufacture of Refrigerators at Refrigeracao Parana S.A., Unidade Sao Carlos | Individual | LAC | BRA | FOA | 15 | INV | 16 | N | O | I | CFC | 96 | 96 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-12-01 |  | 1999-06-01 | 1999-05-01 | 162603 | -12710 | 149893 | 149893 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | Canada | Montreal Protocol Technology Transfer Workshop on ODS (Phase II) | Individual | LAC | BRA | SEV | 15 | TRA | 17 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1994-09-01 | 1995-12-01 | 58390 | 0 | 58390 | 58390 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1994 and approved in retroactive funding in December 1994 |  | 1994 | 2000-01-01 | [10 empty] | 1994 | Non-Inv.
FIN | IBRD | Replacement of CFC-11/12 to cyclopentane/HFC-134a foaming agent/refrigerant factory conversion at Metalfrio S.A. | Individual | LAC | BRA | REF | 15 | INV | 18 | N | O | I |  | 205.5 | 205.5 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1998-07-01 | 1999-05-01 | 2360360 | -776471 | 1583889 | 1583889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Foaming process began operation in July 98 and refrigeration process in June 98. Final disbursement to Metalfrio was made on May 99. |  |  | 1997-12-01 | 1999-05-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | BRA | SEV | 16 | PRP | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 235906 | 0 | 235906 | 235906 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of the assembly of refrigeration compressors to phase out CFC-12 and CFC/HCFC-502 by using HFC-134a and R-404a at Elgin Maquinas SA | Individual | LAC | BRA | REF | 17 | INV | 20 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-10-01 | 1999-07-01 |  | 1998-12-01 | 2001-07-01 | 460339 | 0 | 460339 | 460339 | 100% | 0 | 0 |  | 59844 | 0 | 59844 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam for steering wheels at Plascar | Individual | LAC | BRA | FOA | 17 | INV | 21 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-12-01 |  | 1997-10-01 | 2000-07-01 | 119400 | -25268 | 94132 | 94132 | 100% | 0 | 0 | 0 | 15522 | -3285 | 12237 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 17 | PRP | 22 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-07-01 |  | 1996-01-01 | 1997-12-01 | 75000 | -2 | 74998 | 74998 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1995 | Investment
FIN | UNIDO | Preparation of investment project in a plant (Elgin) consuming 60 metric tons of TCA used as a degreasing agent in the production of compressors | Individual | LAC | BRA | SEV | 17 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-05-01 | 1995-09-01 |  | 1997-10-01 | 1998-08-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFCs in the manufacture of domestic chest freezers at Multibras, S.A. Electrodomésticos | Individual | LAC | BRA | REF | 17 | INV | 24 | N | O | I | CFC | 165.9 | 165.9 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-12-01 |  | 1997-12-01 | 1999-12-01 | 598499 | 0 | 598499 | 598499 | 100% | 0 | 0 | 0 | 77805 | 0 | 77805 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | Canada | Ozone depleting solvents workshop in Brazil | Individual | LAC | BRA | SOL | 17 | TRA | 25 | A | O | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1994-05-01 | 1996-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in May 1994 and approved by retroactive funding in August 1995 |  | 1995 | 2000-01-01 | [10 empty] | 1995 | Non-Inv.
FIN | UNIDO | Investment project for phasing out of ODS at Frisokar Equipamentos Plasticos Ltd. | Individual | LAC | BRA | FOA | 17 | INV | 26 | A | O | I | CFC | 42 | 42 |  |  | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1997-10-01 | 2000-07-01 | 267948 | -13521 | 254427 | 254427 | 100% | 0 | 0 |  | 34833 | -1810 | 33023 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Macform | Individual | LAC | BRA | FOA | 18 | INV | 27 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 243500 | -8086 | 235414 | 235414 | 100% | 0 | 0 | 0 | 31655 | -1051 | 30604 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Nacra | Individual | LAC | BRA | FOA | 18 | INV | 28 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 254500 | -47523 | 206977 | 206977 | 100% | 0 | 0 | 0 | 33085 | -6178 | 26907 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at MBR | Individual | LAC | BRA | FOA | 18 | INV | 29 | A | O | I | CFC | 40 | 40 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 338500 | -44421 | 294079 | 294079 | 100% | 0 | 0 | 0 | 44005 | -5775 | 38230 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Sao Rafael Ind. Com. | Individual | LAC | BRA | FOA | 18 | INV | 30 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-10-01 |  | 1999-09-01 | 1998-02-01 | 82676 | -2016 | 80660 | 80660 | 100% | 0 | 0 |  | 10748 | -262.08 | 10485.8 | 0.12 | 0.12 | Complete. |  |  | 1998-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Randon Implementos S.A. | Individual | LAC | BRA | FOA | 18 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-09-01 |  |  | 1999-07-01 | 92180 | -92180 | 0 | 0 |  | 0 | 0 |  | 11983 | -11983 | 0 | 0 | 0 | Cancelled. |  |  | 1998-06-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Recrusul SEA | Individual | LAC | BRA | FOA | 18 | INV | 32 | N | O | I | CFC | 201 | 201 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1999-06-01 | 1999-08-01 | 1075650 | -121339 | 954311 | 954311 | 100% | 0 | 0 |  | 139835 | -15774.5 | 124060.5 | 0 | 0 | Complete. |  |  | 1997-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at M. Agostini, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 33 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1996-08-01 |  | 1999-09-01 | 1999-02-01 | 85217 | -2078 | 83139 | 83139 | 100% | 0 | 0 |  | 11078 | -269.93 | 10808.07 | 0 | 0 | All three foaming machines now installed and in routine operation. |  |  | 1998-06-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Termolar, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 34 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-08-01 |  |  | 1996-09-01 | 61716 | -61716 | 0 | 0 |  | 0 | 0 |  | 8023 | -8023 | 0 | 0 | 0 | Cancelled. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the manufacture of commercial chest freezers at Refrigeracao Parana S.A. Curitiba | Individual | LAC | BRA | REF | 18 | INV | 35 | N | O | I | CFC | 363 | 363 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1998-11-01 | 1999-08-01 | 1557613 | -210305.8 | 1347307.2 | 1347307 | 100% | 0.2 | 0.2 |  | 202490 | -27340.31 | 175149.69 | 0 | 0 | The firm went ahead with its own funds and completed one line (vertical freezers) in July 97; and the other line (horizontal freezers) in Nov. 98. FINEP reimbursed the firm retroactively for capital and operating costs. Final reimbursement made on August 2, 1999. |  |  | 1997-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase out of CFC-113 at DMG used in medical equipment parts cleaning | Individual | LAC | BRA | SOL | 18 | INV | 36 | N | O | I | CFC | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1997-11-01 | 2000-12-01 | 38000 | -6 | 37994 | 37994 | 100% | 0 | 0 | 0 | 4940 | -1 | 4939 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-113 from the precision cleaning and drying process at Brasimet | Individual | LAC | BRA | SOL | 18 | INV | 37 | N | O | I | CFC | 1.6 | 1.6 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1996-11-01 |  | 1999-12-01 | 2000-09-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-07-01 | [9 empty] | 1995 | Investment
CLO | IBRD | Phase out of CFC-113 and of MCF used in vapor degreasers to clean aircraft parts at Embraer | Individual | LAC | BRA | SOL | 18 | INV | 38 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1998-07-01 | 308215 | -308215 | 0 | 0 |  | 0 | 0 |  | 40068 | -40068 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1998-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of ODS cleaning processes from 1,1,1 TCA to aqueous cleaning and using trichlorethane at Elgin Maquinas SA | Individual | LAC | BRA | SOL | 18 | INV | 39 | A | O | I | TCA | 6 | 6 |  |  | 1995-11-01 | 1996-12-01 | 1997-02-01 |  | 1997-11-01 | 1999-08-01 | 156567 | -6049 | 150518 | 150518 | 100% | 0 | 0 |  | 20354 | -818 | 19536 | 0 | 0 | FIN
FIN | UNIDO | Formulation of two investment projects in the commercial and domestic refrigerator sector | Individual | LAC | BRA | REF | 18 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-02-01 |  | 1997-12-01 | 1998-08-01 | 50000 | 87 | 50087 | 50087 | 100% | 0 | 0 |  | 6500 | 11 | 6511 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 18 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-08-01 | 1997-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | LAC | BRA | SEV | 18 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Madef/Isoltec | Individual | LAC | BRA | FOA | 19 | INV | 43 | A | O | I | CFC | 65.3 | 65.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-12-01 | 2001-12-01 | 346000 | -64202 | 281798 | 281798 | 100% | 0 | 0 | 0 | 44980 | -8346 | 36634 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at three enterprises: Brafer, Invicta and Therm-Jet | Individual | LAC | BRA | FOA | 19 | INV | 44 | A | O | I | CFC | 38 | 38 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-07-01 | 1999-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1996 | Investment
FIN | UNDP | Umbrella project covering 6 companies for the conversion to CFC-free technology in the manufacture of integral rigid skin and flexible molded polyurethane foam (Rorispuma, Indek, Flexfom, Walrod, Rigi | Individual | LAC | BRA | FOA | 19 | INV | 45 | A | O | I | CFC | 51.8 | 51.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-11-01 | 2000-07-01 | 746000 | 2 | 746002 | 746002 | 100% | 0 | 0 | 0 | 96980 | 0 | 96980 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free techcnology in the manufacture of polyurethane foam at Blitz Ind. Com. de Plasticos | Individual | LAC | BRA | FOA | 19 | INV | 46 | A | O | I | TCA/CFC | 9.8 | 9.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-07-01 | 2000-07-01 | 120000 | -36822 | 83178 | 83178 | 100% | 0 | 0 | 0 | 15600 | -4787 | 10813 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | Canada | Halon recycling and bank management | Halon Banking | LAC | BRA | HAL | 19 | TAS | 47 | A | O | I |  | 21.3 | 21.3 | 0 |  | 1996-05-01 | 1996-10-01 | 1998-05-01 |  | 1999-05-01 | 1999-05-01 | 499360 | -20031 | 479329 | 479329 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented although one year later than planned. Adjustment results of exchange rate fluctuations |  | 1996 | 1998-09-01 | [10 empty] | 1996 | Non-Inv.
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Reubli, S.A. | Individual | LAC | BRA | REF | 19 | INV | 48 | N | O | I | CFC | 89.9 | 89.9 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 1999-06-01 | 901270 | -200188 | 701082 | 701082 | 100% | 0 | 0 |  | 117165 | -26024.34 | 91140.66 | 0 | 0 | Complete. |  |  | 1997-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Geltec Comercio e Industria S.A. | Individual | LAC | BRA | REF | 19 | INV | 49 | N | O | I | CFC | 18.3 | 18.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-02-01 | 1998-02-01 | 228250 | -93750 | 134500 | 134500 | 100% | 0 | 0 |  | 29673 | -12188 | 17485 | 0 | 0 | Refrigeration equipment installed and operating. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-11 to cyclopentane foam blowing agent and CFC-12 to HFC-134a refrigerant at Tecnomecanica Esmaltec Ltda. | Individual | LAC | BRA | REF | 19 | INV | 50 | N | O | I | CFC | 68.7 | 68.7 | 0 | 0 | 1996-05-01 | 1998-08-01 | 1997-11-01 |  | 2000-03-01 | 1999-06-01 | 924040 | 0 | 924040 | 924040 | 100% | 0 | 0 |  | 120125 | 0 | 120125 | 0 | 0 |  |  |  | 1998-06-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Everest Refrigeracao Ind. e Comercio Ltda. | Individual | LAC | BRA | REF | 19 | INV | 51 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 149050 | -149050 | 0 | 0 |  | 0 | 0 |  | 19377 | -19377 | 0 | 0 | 0 | Cancelled. |  |  | 1998-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-113 in medical parts cleaning and silicone deposition, and CFC-12 used in sterilization at Tecnobio | Individual | LAC | BRA | SOL | 19 | INV | 52 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 1997-11-01 | 317492 | -317492 | 0 | 0 |  | 0 | 0 |  | 41274 | -41274 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Panisol, S.A. (Paineis Isolantes) | Individual | LAC | BRA | FOA | 20 | INV | 53 | A | O | I | CFC | 54.4 | 54.4 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 1999-12-01 | 2003-11-01 | 315958 | -41 | 315917 | 315917 | 100% | 0 | 0 | 0 | 41075 | -5 | 41070 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [9 empty] | 1996 | Investment
FIN | UNIDO | Phasing out of CFC-12 by HFC-134a as refrigerant and CFC-11 by cyclopentane as foam blowing agent in commercial refrigeration equipment for supermarkets at Eletrofrio S/A | Individual | LAC | BRA | REF | 20 | INV | 54 | A | O | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-07-01 | 1998-10-01 |  | 1999-12-01 | 2001-12-01 | 610650 | 0 | 610650 | 610650 | 100% | 0 | 0 |  | 79385 | -63 | 79322 | 0 | 0 | FIN
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Gelopar | Individual | LAC | BRA | REF | 20 | INV | 55 | N | O | I | CFC | 13.14 | 13.14 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-05-01 | 1998-05-01 | 200200 | -145442 | 54758 | 54758 | 100% | 0 | 0 |  | 26026 | -18907.46 | 7118.54 | 0 | 0 | Refrigeration equipment acquired and installed. 134a production began May 98. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the production of refrigeration equipment (drinking water fountains and coolers) at Industria Brasileira de Bebedouros Ltda. (IBBL) | Individual | LAC | BRA | REF | 20 | INV | 56 | N | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-07-01 | 1998-05-01 | 82500 | -23113 | 59387 | 59387 | 100% | 0 | 0 |  | 10725 | -3004.69 | 7720.31 | 0 | 0 |  |  |  |  | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
COM | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Multibras, S.A. | Individual | LAC | BRA | REF | 20 | INV | 57 | N | O | I | CFC | 1068.8 | 1068.8 | 0 | 0 | 1996-10-01 | 1997-07-01 | 1999-09-01 |  | 2001-12-01 |  | 4899790 | 0 | 4899790 | 4899790 | 100% | 0 | 0 | 0 | 636973 | 0 | 636973 | 0 | 0 | Completed in 2001. |  |  | 1999-12-01 | [10 empty] | 1996 | Investment
CLO | UNIDO | Phase out of 1,1,1 TCA at Teperman | Individual | LAC | BRA | SOL | 20 | INV | 58 | A | O | R |  | 0 | 0 |  |  | 1996-10-01 |  | 1998-10-01 |  |  | 2000-06-01 | 152176 | -152176 | 0 | 0 |  | 0 | 0 |  | 19783 | -19783 | 0 | 0 | 0 | CLO
CLO | UNIDO | Elimination of 1,1,1 TCA used for autoparts cleaning at Brosol | Individual | LAC | BRA | SOL | 20 | INV | 59 | A | O | I |  | 0 | 0 |  |  | 1996-10-01 |  | 1997-10-01 |  |  | 1999-03-01 | 178361 | -178361 | 0 | 0 |  | 0 | 0 |  | 23187 | -23187 | 0 | 0 | 0 | CLO
FIN | UNIDO | Elimination of 1,1,1 TCA used as solvent at Rodabras | Individual | LAC | BRA | SOL | 20 | INV | 60 | A | O | I | TCA | 4.2 | 4.2 |  |  | 1996-10-01 | 1998-09-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 151577 | -75 | 151502 | 151502 | 100% | 0 | 0 |  | 19705 | -41 | 19664 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 TCA used for the formulation of tapping fluids at Tapmatic | Individual | LAC | BRA | SOL | 20 | INV | 61 | A | O | I | TCA | 9.9 | 9.9 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1997-12-01 | 2001-12-01 | 194500 | -27382 | 167118 | 167118 | 100% | 0 | 0 |  | 25285 | -3594 | 21691 | 0 | 0 | FIN
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 21 | PRP | 62 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | BRA | SEV | 21 | PRP | 63 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-06-01 | 2000-12-01 | 57140 | -718 | 56422 | 56422 | 100% | 0 | 0 |  | 7428 | -105 | 7323 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Giroflex | Individual | LAC | BRA | FOA | 22 | INV | 64 | A | O | I | CFC | 23.4 | 23.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-08-01 | 2002-11-01 | 177500 | 0 | 177500 | 177500 | 100% | 0 | 0 | 0 | 23075 | 0 | 23075 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyethylene foam tubing at Polipex | Individual | LAC | BRA | FOA | 22 | INV | 65 | A | O | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2002-01-01 | 2002-12-01 | 191000 | 0 | 191000 | 191000 | 100% | 0 | 0 | 0 | 24830 | 0 | 24830 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Trambusti Naue | Individual | LAC | BRA | FOA | 22 | INV | 66 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2000-11-01 | 2001-11-01 | 763600 | -2355 | 761245 | 761245 | 100% | 0 | 0 | 0 | 99268 | -306 | 98962 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Industrias Facchini, Ldta. | Individual | LAC | BRA | FOA | 22 | INV | 67 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-03-01 | 2001-11-01 | 258000 | -85574 | 172426 | 172426 | 100% | 0 | 0 | 0 | 33540 | -11125 | 22415 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Dalla Rosa E Cia | Individual | LAC | BRA | FOA | 22 | INV | 68 | A | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-05-01 |  | 1999-12-01 | 2001-12-01 | 71600 | 0 | 71600 | 71600 | 100% | 0 | 0 | 0 | 9308 | 0 | 9308 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Aquedores Cumulus S.A. | Individual | LAC | BRA | FOA | 22 | INV | 69 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 86000 | -49 | 85951 | 85951 | 100% | 0 | 0 | 0 | 11180 | -6 | 11174 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Tekcor Utilidades Domesticas Ltd. | Individual | LAC | BRA | FOA | 22 | INV | 70 | A | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1998-07-01 | 2003-05-01 | 71600 | -2957 | 68643 | 68643 | 100% | 0 | 0 | 0 | 9308 | -384 | 8924 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Metallurgica Barra | Individual | LAC | BRA | FOA | 22 | INV | 71 | A | O | I | CFC | 36.3 | 36.3 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1997-07-01 | 2000-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Isolenge | Individual | LAC | BRA | FOA | 22 | INV | 72 | A | O | I | CFC | 66 | 66 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-04-01 | 2000-12-01 | 516000 | -84186 | 431814 | 431814 | 100% | 0 | 0 | 0 | 67080 | -10944 | 56136 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNIDO | Demonstration project: three alternatives to the use of methyl bromide: non-soil cultivation, solarization and low-dose chemicals | Individual | LAC | BRA | FUM | 22 | DEM | 73 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2000-05-01 | 2002-09-01 | 393800 | -28111 | 365689 | 365689 | 100% | 0 | 0 |  | 51194 | -3730 | 47464 | 0 | 0 | FIN
FIN | UNDP | Project preparation | Individual | LAC | BRA | SEV | 22 | PRP | 74 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | IBRD | Project preparation in the foam sector |  | LAC | BRA | FOA | 22 | PRP | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1999-03-31 | 1997-12-01 |  | 1999-12-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 |  |  |  |  | 1999-12-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 12 | CPG | 76 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 49000 | -45000 | 4000 | 4000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brazil Country Program was completed, presented and approved at the 13th Meeting of the Executive Committee. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technlogy in the manufacture of polyurethane foam at Plasmold | Individual | LAC | BRA | FOA | 23 | INV | 77 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 161500 | -737 | 160763 | 160763 | 100% | 0 | 0 | 0 | 20995 | -96 | 20899 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bulltrade | Individual | LAC | BRA | FOA | 23 | INV | 78 | A | O | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 223000 | -358 | 222642 | 222642 | 100% | 0 | 0 | 0 | 28990 | -47 | 28943 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CMZ Poliuretanos | Individual | LAC | BRA | FOA | 23 | INV | 79 | A | O | I | CFC | 5.5 | 5.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 92750 | -305 | 92445 | 92445 | 100% | 0 | 0 | 0 | 12058 | -40 | 12018 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bruzze | Individual | LAC | BRA | FOA | 23 | INV | 80 | A | O | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-11-01 |  | 2000-11-01 | 2002-03-01 | 278190 | -456 | 277734 | 277734 | 100% | 0 | 0 | 0 | 36165 | -59 | 36106 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Artico | Individual | LAC | BRA | REF | 23 | INV | 81 | A | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 225100 | -927 | 224173 | 224173 | 100% | 0 | 0 | 0 | 29263 | -120 | 29143 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Bernini | Individual | LAC | BRA | FOA | 23 | INV | 82 | A | O | I | CFC | 22.9 | 22.9 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-11-01 | 135150 | 0 | 135150 | 135150 | 100% | 0 | 0 | 0 | 17570 | 0 | 17570 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1997 | Investment
CLO | UNIDO | Phasing out of CFC-12 by HFC-134a and CFC-11 by cyclopentane in the production of commercial refrigeration equipment at Refrigeracao Rubra | Individual | LAC | BRA | REF | 23 | INV | 83 | A | O | I | CFC | 21.8 | 0 |  |  | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-10-01 | 320540 | -199780 | 120760 | 120760 | 100% | 0 | 0 |  | 41670 | -25996 | 15674 | 0 | 0 | CLO
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Polistecom | Individual | LAC | BRA | FOA | 23 | INV | 84 | A | O | I | CFC | 42.6 | 42.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 303000 | 0 | 303000 | 303000 | 100% | 0 | 0 | 0 | 39390 | 0 | 39390 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
COM | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | BRA | SEV | 23 | TAS | 85 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1999-05-01 |  | 2000-07-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2000. | [13 empty] | 1997 | Non-Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Niju Ind. Com Implem Rodov Ltda. | Individual | LAC | BRA | REF | 23 | INV | 86 | A | O | I | CFC | 8.4 | 8.4 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 111600 | 0 | 111600 | 111600 | 100% | 0 | 0 | 0 | 14508 | 0 | 14508 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mikawa & Cia | Individual | LAC | BRA | FOA | 23 | INV | 87 | A | O | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 80600 | 0 | 80600 | 80600 | 100% | 0 | 0 | 0 | 10478 | 0 | 10478 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mais Frio | Individual | LAC | BRA | REF | 23 | INV | 88 | A | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 154400 | -25 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20072 | -3 | 20069 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kalf Calcados | Individual | LAC | BRA | FOA | 23 | INV | 89 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-11-01 | 2003-11-01 | 101100 | 0 | 101100 | 101100 | 100% | 0 | 0 | 0 | 13143 | 0 | 13143 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Increal Ltda. | Individual | LAC | BRA | REF | 23 | INV | 90 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 418000 | -4 | 417996 | 417996 | 100% | 0 | 0 | 0 | 54340 | -1 | 54339 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Friar | Individual | LAC | BRA | REF | 23 | INV | 91 | A | O | I | CFC | 14.9 | 14.9 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2003-04-01 | 185726 | -1023 | 184703 | 184703 | 100% | 0 | 0 | 0 | 24144 | -133 | 24011 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Fast Frio | Individual | LAC | BRA | FOA | 23 | INV | 92 | A | O | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at FJ Polymers | Individual | LAC | BRA | FOA | 23 | INV | 93 | A | O | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 89500 | -992 | 88508 | 88508 | 100% | 0 | 0 | 0 | 11635 | -129 | 11506 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Espumatec | Individual | LAC | BRA | FOA | 23 | INV | 94 | A | O | I | CFC | 64.6 | 64.6 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-04-01 | 2003-04-01 | 372000 | -271 | 371729 | 371729 | 100% | 0 | 0 | 0 | 48360 | -35 | 48325 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Zenimont | Individual | LAC | BRA | FOA | 23 | INV | 95 | A | O | I | CFC | 38.1 | 38.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2001-04-01 | 2002-03-01 | 298300 | 0 | 298300 | 298300 | 100% | 0 | 0 | 0 | 38779 | 0 | 38779 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1997 | Investment
CLO | UNDP | Project preparation for two methyl bromide demonstration projects (soil fumigation for flowers, tomatoes, cucumbers and strawberries) | Individual | LAC | BRA | FUM | 24 | PRP | 96 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  |  | 2000-12-01 | 40000 | -31187 | 8813 | 8813 | 100% | 0 | 0 | 0 | 5200 | -4054 | 1146 | 0 | 0 | Canceled in 2000. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNIDO | Project preparation in the commercial refrigeration sector (Tecpur, Crios, Panamante and others) | Individual | LAC | BRA | REF | 24 | PRP | 97 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 2000-07-01 | 2001-07-01 | 50000 | -2511 | 47489 | 47489 | 100% | 0 | 0 |  | 6500 | -336 | 6164 | 0 | 0 | FIN
FIN | UNDP | Project preparation to prepare 16 projects in the foam sector | Individual | LAC | BRA | FOA | 24 | PRP | 98 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 70000 | -12756 | 57244 | 57244 | 100% | 0 | 0 | 0 | 9100 | -1658 | 7442 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 4 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 24 | PRP | 99 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-07-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1998 | Investment
COM | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | BRA | SEV | 24 | INS | 100 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 2000-04-01 |  | 2000-11-01 |  | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 2000. | [13 empty] | 1998 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Injebank | Individual | LAC | BRA | FOA | 25 | INV | 101 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-04-01 | 86300 | -10846 | 75454 | 75454 | 100% | 0 | 0 | 0 | 11219 | -1410 | 9809 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to hexane and LCD technology in the manufacture of polyurethane foam at Herval | Individual | LAC | BRA | FOA | 25 | INV | 102 | A | O | I | CFC | 64.5 | 64.5 | 0 | 0 | 1998-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 637335 | 0 | 637335 | 637335 | 100% | 0 | 0 | 0 | 82854 | 0 | 82854 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNIDO | Phasing out CFC-11 with cyclopentane at Crios Industrial Ltd. (suppliers of Eletrofrio Company) | Individual | LAC | BRA | FOA | 25 | INV | 103 | A | O | I | CFC | 46 | 46 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 357270 | 0 | 357270 | 357270 | 100% | 0 | 0 |  | 46445 | -50 | 46395 | 0 | 0 | FIN
FIN | UNDP | Conversion to water based technology in the manufacture of polyurethane foam at Refratarios Isolamentos e Pinturas (RIP) | Individual | LAC | BRA | FOA | 25 | INV | 104 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-07-01 | 2003-04-01 | 94000 | -945 | 93055 | 93055 | 100% | 0 | 0 | 0 | 12220 | -123 | 12097 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Panther | Individual | LAC | BRA | FOA | 25 | INV | 105 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2000-11-01 | 2003-05-01 | 275805 | 0 | 275805 | 275805 | 100% | 0 | 0 | 0 | 35855 | 0 | 35855 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Investment
CLO | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with cyclopentane in the production of commercial refrigeration equipment at Panamante Refrigeracao | Individual | LAC | BRA | REF | 25 | INV | 106 | A | O | I | CFC | 34.3 | 0 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  |  | 2002-09-01 | 377202 | -140248 | 236954 | 236954 | 100% | 0 | 0 |  | 49036 | -18281 | 30755 | 0 | 0 | CLO
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Gnatus | Individual | LAC | BRA | FOA | 25 | INV | 107 | A | O | I | CFC | 29.7 | 29.7 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-04-01 | 207225 | -488 | 206737 | 206737 | 100% | 0 | 0 | 0 | 26939 | -63 | 26876 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Cougar | Individual | LAC | BRA | FOA | 25 | INV | 108 | A | O | I | CFC | 18.2 | 18.2 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 154375 | 0 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20069 | 0 | 20069 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of polyurethane foam at SSM Tecnologia | Individual | LAC | BRA | FOA | 25 | INV | 109 | A | O | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2003-11-01 | 106500 | 0 | 106500 | 106500 | 100% | 0 | 0 | 0 | 13845 | 0 | 13845 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of polyurethane foam at Delta Pack | Individual | LAC | BRA | FOA | 25 | INV | 110 | A | O | I | CFC | 27.5 | 27.5 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 202500 | 0 | 202500 | 202500 | 100% | 0 | 0 | 0 | 26325 | 0 | 26325 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b (foam) and HFC-134a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at Termisa | Individual | LAC | BRA | REF | 25 | INV | 111 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2001-12-01 | 322205 | 0 | 322205 | 322205 | 100% | 0 | 0 | 0 | 41887 | 0 | 41887 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at Isoblock | Individual | LAC | BRA | FOA | 26 | INV | 112 | A | O | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-04-01 | 106500 | -132 | 106368 | 106368 | 100% | 0 | 0 | 0 | 13845 | -17 | 13828 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at C.A. Cunha | Individual | LAC | BRA | FOA | 26 | INV | 113 | A | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-11-01 | 70100 | 0 | 70100 | 70100 | 100% | 0 | 0 | 0 | 9113 | 0 | 9113 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at P.F.I. Ind. E Com. Refrigeracao Ltd. (P.F.I.) | Individual | LAC | BRA | FOA | 26 | INV | 114 | A | O | I | CFC | 8.2 | 8.2 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-11-01 | 64200 | 0 | 64200 | 64200 | 100% | 0 | 0 | 0 | 8346 | 0 | 8346 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and CFC-12 by conversion to HFC-134a in the manufacture of small commercial freezers and coolers at Bebber | Individual | LAC | BRA | REF | 26 | INV | 115 | A | O | I | CFC | 9.5 | 9.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2002-04-01 | 144500 | -3024 | 141476 | 141476 | 100% | 0 | 0 | 0 | 18785 | -393 | 18392 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by HCFC-141b in the manufacture of integral skin foam furniture and conversion from CFC-11 to methylene chloride in the manufacture of polyurethane boxfoam at Cantegril | Individual | LAC | BRA | FOA | 26 | INV | 116 | A | O | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-05-01 | 154740 | -4476 | 150264 | 150264 | 100% | 0 | 0 | 0 | 20116 | -582 | 19534 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams (microcellular) at Bicicletos Caloi, S.A. | Individual | LAC | BRA | FOA | 27 | INV | 117 | A | O | I | CFC | 41 | 41 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 227600 | -4765 | 222835 | 222835 | 100% | 0 | 0 | 0 | 29588 | -619 | 28969 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b technology (foam) and HFC-134a -134a technology (refrigerant) in the manufacture of refrigerated truck trailers at Artica | Individual | LAC | BRA | REF | 27 | INV | 118 | A | O | I | CFC | 22.3 | 22.3 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-11-01 | 2003-10-01 | 183623 | -7277 | 176346 | 176346 | 100% | 0 | 0 | 0 | 23871 | -946 | 22925 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Project preparation in the commercial refrigeration sector for four companies | Individual | LAC | BRA | REF | 27 | PRP | 119 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2001-03-01 | 2002-09-01 | 40000 | -8531 | 31469 | 31469 | 100% | 0 | 0 |  | 5200 | -1116 | 4084 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Conter Ind. e Isolantes Termocos, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 120 | A | O | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 85347 | 0 | 85347 | 85347 | 100% | 0 | 0 | 0 | 11095 | 0 | 11095 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of four projects in the foam sector | Individual | LAC | BRA | FOA | 27 | PRP | 121 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration sector | Individual | LAC | BRA | REF | 27 | PRP | 122 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of six projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 123 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of five projects in integral skin foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 124 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of integral skin foams at Spandy Peças em Poliuretano, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 125 | A | O | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 261400 | -4032 | 257368 | 257368 | 100% | 0 | 0 | 0 | 33982 | -524 | 33458 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | BRA | FOA | 27 | PRP | 126 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 50000 | -9090 | 40910 | 40910 | 100% | 0 | 0 |  | 6500 | -1190 | 5310 | 0 | 0 | FIN
CLO | UNIDO | Project preparation in the aerosol sector | Individual | LAC | BRA | ARS | 27 | PRP | 127 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 1999-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 27 | PRP | 128 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fabrica De Carrocerias Farage, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 129 | A | O | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 52770 | 0 | 52770 | 52770 | 100% | 0 | 0 | 0 | 6860 | 0 | 6860 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Posto de Molas Vivian, Ltda. (Posmovil) | Individual | LAC | BRA | FOA | 27 | INV | 130 | A | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 44700 | 0 | 44700 | 44700 | 100% | 0 | 0 | 0 | 5811 | 0 | 5811 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane sprayfoam at Isotherm Tratamento Thermo Acoustico Ltda. | Individual | LAC | BRA | FOA | 28 | INV | 131 | A | O | I | CFC | 26.3 | 26.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 116768 | 0 | 116768 | 116768 | 100% | 0 | 0 | 0 | 15180 | 0 | 15180 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
COM | UNDP | Phase-out of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers by conversion to cyclo-pentane and HCF-134a at Metalurgica Venan Ltda. | Individual | LAC | BRA | REF | 28 | INV | 132 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-02-01 |  | 2004-03-01 |  | 741800 | 0 | 741800 | 735007 | 99.08% | 6793 | 0 | 5434.4 | 91598 | 0 | 90759.1955 | 838.8045 | 0 | Completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11, CFC-12 and R-502 by conversion to HCFC-141b technology (foam) and HFC-134a and R-404a technology (refrigerant) in the manufacture of milk coolers and display cabinets at Incomar | Individual | LAC | BRA | REF | 28 | INV | 133 | A | O | I | CFC | 4.9 | 4.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 74529 | 0 | 74529 | 74529 | 100% | 0 | 0 | 0 | 9689 | 0 | 9689 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-402a in the manufacture of commercial refrigeration products at General Icy | Individual | LAC | BRA | REF | 28 | INV | 134 | A | O | I | CFC | 27.9 | 27.9 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 411139 | 0 | 411139 | 411139 | 100% | 0 | 0 | 0 | 53448 | 0 | 53448 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam at Polsul Group | Individual | LAC | BRA | FOA | 28 | INV | 135 | A | O | I | CFC | 55 | 55 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2002-11-01 | 2006-10-01 | 536892 | -24390 | 512502 | 512502 | 100% | 0 | 0 | 0 | 69058 | -2683 | 66375 | 0 | 0 | Completed in 2002. Financially completed in 2006. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible integral skin at Moldepol | Individual | LAC | BRA | FOA | 28 | INV | 136 | A | O | I | CFC | 34.8 | 34.8 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 421444 | -2 | 421442 | 421442 | 100% | 0 | 0 | 0 | 54788 | 0 | 54788 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ananda | Individual | LAC | BRA | FOA | 28 | INV | 137 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2002-04-01 | 37380 | -14147 | 23233 | 23233 | 100% | 0 | 0 | 0 | 4859 | -1839 | 3020 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in flexible molded foam, to water and methylene chloride technology in semi-rigid packaging foam, and to HCFC-141b in flexible integral skin foams at Espuma Oeste | Individual | LAC | BRA | FOA | 28 | INV | 138 | A | O | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 181616 | -5766 | 175850 | 175850 | 100% | 0 | 0 | 0 | 23610 | -750 | 22860 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phasing out CFC-12 with HFC-134A and CFC-11 with HFC-141b at five commercial refrigeration companies (Arparna, Begel, Belliere, Genaredx and Katz Refrigeracao) (umbrella project) | Individual | LAC | BRA | REF | 28 | INV | 139 | A | O | I | CFC | 26 | 26 |  |  | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 485916 | -115476 | 370440 | 370440 | 100% | 0 | 0 |  | 63169 | -15088 | 48081 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and integral skin foam at JNP Group | Individual | LAC | BRA | FOA | 28 | INV | 140 | A | O | I | CFC | 80.3 | 80.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2002-12-01 | 2006-10-01 | 823867 | -22056 | 801811 | 801811 | 100% | 0 | 0 | 0 | 100625 | -2426 | 98199 | 0 | 0 | Completed in 2002. Financially completed in 2006. | [13 empty] | 1999 | Investment
CLO | UNIDO | Phase-out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polyethylene foams for thermal insulation and food packaging purposes at Epex Co. | Individual | LAC | BRA | FOA | 28 | INV | 141 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 |  | 2001-08-01 |  |  | 2001-07-01 | 632391 | -632391 | 0 | 0 |  | 0 | 0 |  | 79563 | -79563 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out methyl bromide in the entire Tobacco Sector | Individual | LAC | BRA | FUM | 28 | INV | 142 | A | O | I | MBR | 84.4 | 84.4 |  |  | 1999-07-01 | 2000-06-01 | 2002-08-01 |  | 2001-12-01 | 2002-10-01 | 2344440 | -19971 | 2324469 | 2324469 | 100% | 0 | 0 |  | 267888 | -2602 | 265286 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in rigid polyurethane foam (spray and pour in place) at SIFC | Individual | LAC | BRA | FOA | 28 | INV | 143 | A | O | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2000-11-01 | 2003-05-01 | 74385 | 0 | 74385 | 74385 | 100% | 0 | 0 | 0 | 9670 | 0 | 9670 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibrart | Individual | LAC | BRA | FOA | 29 | INV | 144 | A | O | I | CFC | 29.9 | 29.9 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 111838 | 0 | 111838 | 111838 | 100% | 0 | 0 | 0 | 14539 | 0 | 14539 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Durothan | Individual | LAC | BRA | FOA | 29 | INV | 145 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 228625 | 0 | 228625 | 228625 | 100% | 0 | 0 | 0 | 29721 | 0 | 29721 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at ACS Fibra | Individual | LAC | BRA | FOA | 29 | INV | 146 | A | O | I | CFC | 17.4 | 17.4 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 119336 | -2316 | 117020 | 117020 | 100% | 0 | 0 | 0 | 15514 | -301 | 15213 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam for packaging and to HCFC-141b technology for insulation applications at World Pack da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 147 | A | O | I | CFC | 86.6 | 86.6 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-10-01 | 405610 | 0 | 405610 | 405610 | 100% | 0 | 0 | 0 | 52729 | 0 | 52729 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for display cabinets at Vacuum Systems | Individual | LAC | BRA | FOA | 29 | INV | 148 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2001-12-01 | 2003-09-01 | 117450 | -1 | 117449 | 117449 | 100% | 0 | 0 | 0 | 15269 | 0 | 15269 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Plastwork Embalagens da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 149 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 144855 | -1757 | 143098 | 143098 | 100% | 0 | 0 | 0 | 18831 | -228 | 18603 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Intertelhas | Individual | LAC | BRA | FOA | 29 | INV | 150 | A | O | I | CFC | 48.9 | 48.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2000-12-01 | 2002-11-01 | 170074 | -62845 | 107229 | 107229 | 100% | 0 | 0 | 0 | 22110 | -8170 | 13940 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of rigid integral skin foam at Spray | Individual | LAC | BRA | FOA | 29 | INV | 151 | A | O | I | CFC | 31.8 | 31.8 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 211080 | -4717 | 206363 | 206363 | 100% | 0 | 0 | 0 | 27440 | -613 | 26827 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams at Nicos do Brasil | Individual | LAC | BRA | FOA | 29 | INV | 152 | A | O | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Brasinj Ind. E Comm. | Individual | LAC | BRA | FOA | 29 | INV | 153 | A | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 71253 | 0 | 71253 | 71253 | 100% | 0 | 0 | 0 | 9263 | 0 | 9263 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam and sprayfoam at Calorisol | Individual | LAC | BRA | FOA | 29 | INV | 154 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 91477 | -33 | 91444 | 91444 | 100% | 0 | 0 | 0 | 11892 | -4 | 11888 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at ELV TEC Industria e Commercio Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 155 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 134265 | 0 | 134265 | 134265 | 100% | 0 | 0 | 0 | 17454 | 0 | 17454 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin and flexible molded foams at Purtec | Individual | LAC | BRA | FOA | 29 | INV | 156 | A | O | I | CFC | 18.9 | 18.9 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2005-10-01 | 140769 | -3174 | 137595 | 137595 | 100% | 0 | 0 | 0 | 18300 | -413 | 17887 | 0 | 0 | Completed in 2001. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isolamento Termico Brasfoam Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 157 | A | O | I | CFC | 61.6 | 61.6 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 110200 | -2358 | 107842 | 107842 | 100% | 0 | 0 | 0 | 14326 | -307 | 14019 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Fibrasil Ind. Commercio de Carroceria Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 158 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-05-01 | 2003-09-01 | 93425 | -32890 | 60535 | 60535 | 100% | 0 | 0 | 0 | 12145 | -4275 | 7870 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 30 | PRP | 159 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 25000 | -409 | 24591 | 24591 | 100% | 0 | 0 |  | 3250 | -58 | 3192 | 0 | 0 | FIN
FIN | UNDP | Preparation of 10 projects in the integral skin foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 160 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 161 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of 3 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 30 | PRP | 162 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector (SMEs) | Individual | LAC | BRA | FOA | 30 | PRP | 163 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
CLO | UNDP | Preparation of 5 projects in the foam sector | Individual | LAC | BRA | FOA | 30 | PRP | 164 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2004-02-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
FIN | UNIDO | Project preparation in the fumigant/ methyl bromide sector (tobacco) | Individual | LAC | BRA | FUM | 27 | PRP | 165 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-04-01 | 2001-07-01 | 50000 | -3855 | 46145 | 46145 | 100% | 0 | 0 |  | 6500 | -511 | 5989 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-404a in the manufacture of freezer rooms and panels, and rigid foam at Schmit | Individual | LAC | BRA | REF | 31 | INV | 166 | A | O | I | CFC | 43.3 | 43.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2002-10-01 | 2003-11-01 | 288764 | -29918 | 258846 | 258846 | 100% | 0 | 0 | 0 | 37539 | -3889 | 33650 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and flexible molded foam at Fabbrini | Individual | LAC | BRA | FOA | 31 | INV | 167 | A | O | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 124887 | -17316 | 107571 | 107571 | 100% | 0 | 0 | 0 | 16235 | -2251 | 13984 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Menaf | Individual | LAC | BRA | FOA | 31 | INV | 168 | A | O | I | CFC | 10.7 | 10.7 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 80994 | -11239 | 69755 | 69755 | 100% | 0 | 0 | 0 | 10529 | -1461 | 9068 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water-based technology in the manufacture of rigid polyurethane foam at Polyfoam | Individual | LAC | BRA | FOA | 31 | INV | 169 | A | O | I | CFC | 41.9 | 41.9 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2003-10-01 | 2005-09-01 | 178873 | -23652 | 155221 | 155221 | 100% | 0 | 0 | 0 | 23253 | -3075 | 20178 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Ingecold Ltda. | Individual | LAC | BRA | REF | 31 | INV | 170 | A | O | I | CFC | 1.7 | 1.7 |  |  | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 25320 | -20 | 25300 | 25300 | 100% | 0 | 0 |  | 3292 | -8 | 3284 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Klima Ltda. | Individual | LAC | BRA | REF | 31 | INV | 171 | A | O | I | CFC | 5.7 | 5.7 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 86464 | -13509 | 72955 | 72955 | 100% | 0 | 0 |  | 11240 | -1771 | 9469 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Tecnigel Ltda | Individual | LAC | BRA | REF | 31 | INV | 172 | A | O | I | CFC | 2.5 | 2.5 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 34000 | -640 | 33360 | 33360 | 100% | 0 | 0 |  | 4420 | -90 | 4330 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Massimo | Individual | LAC | BRA | FOA | 31 | INV | 173 | A | O | I | CFC | 8 | 8 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-09-01 | 2003-09-01 | 52279 | -5260 | 47019 | 47019 | 100% | 0 | 0 | 0 | 6796 | -684 | 6112 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Phasing out CFC-12 and R-502 with HFC-134a and HFC-404A as well as of CFC-11 with HCFC-141 at Kalten Ltd. | Individual | LAC | BRA | REF | 31 | INV | 174 | A | O | I | CFC | 8.1 | 8.1 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2004-04-01 | 2004-09-01 | 122151 | -6158 | 115993 | 115993 | 100% | 0 | 0 |  | 15880 | -825 | 15055 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and rigid foam at Injepol | Individual | LAC | BRA | FOA | 31 | INV | 175 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 107678 | -9727 | 97951 | 97951 | 100% | 0 | 0 | 0 | 13998 | -1265 | 12733 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Metalplan Ltda. | Individual | LAC | BRA | REF | 31 | INV | 176 | A | O | I | CFC | 1.9 | 1.9 |  |  | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 28885 | 0 | 28885 | 28885 | 100% | 0 | 0 |  | 3755 | -3 | 3752 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Domnick Hunter Ltda. | Individual | LAC | BRA | REF | 31 | INV | 177 | A | O | I | CFC | 1.2 | 1.2 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 17971 | 0 | 17971 | 17971 | 100% | 0 | 0 |  | 2336 | 0 | 2336 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin and flexible molded foam at PPU | Individual | LAC | BRA | FOA | 31 | INV | 178 | A | O | I | CFC | 9.4 | 9.4 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2003-09-01 | 64568 | -5159 | 59409 | 59409 | 100% | 0 | 0 | 0 | 8394 | -671 | 7723 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Packo Plurinox | Individual | LAC | BRA | FOA | 31 | INV | 179 | A | O | I | CFC | 13.4 | 13.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2000-12-01 | 2001-12-01 | 39750 | 0 | 39750 | 39750 | 100% | 0 | 0 | 0 | 5168 | 0 | 5168 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at Mach-Plast | Individual | LAC | BRA | FOA | 31 | INV | 180 | A | O | I | CFC | 29.5 | 29.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 188951 | -12871 | 176080 | 176080 | 100% | 0 | 0 | 0 | 24564 | -1673 | 22891 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin and rigid foam at Montreal | Individual | LAC | BRA | FOA | 31 | INV | 181 | A | O | I | CFC | 11.8 | 11.8 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2003-08-01 |  | 2002-08-01 | 2003-09-01 | 83117 | 0 | 83117 | 83117 | 100% | 0 | 0 | 0 | 10805 | 0 | 10805 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Politermo | Individual | LAC | BRA | FOA | 31 | INV | 182 | A | O | I | CFC | 50.2 | 50.2 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 219136 | -2808 | 216328 | 216328 | 100% | 0 | 0 | 0 | 28488 | -365 | 28123 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin foam, flexible molded foam and rigid foam at Jetpol | Individual | LAC | BRA | FOA | 31 | INV | 183 | A | O | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-12-01 | 2003-08-01 |  | 2002-05-01 | 2003-09-01 | 214600 | -9772 | 204828 | 204828 | 100% | 0 | 0 | 0 | 27898 | -1270 | 26628 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam and rigid foam at Trantor | Individual | LAC | BRA | FOA | 31 | INV | 184 | A | O | I | CFC | 19.6 | 19.6 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 102234 | -5218 | 97016 | 97016 | 100% | 0 | 0 | 0 | 13290 | -679 | 12611 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refripor | Individual | LAC | BRA | FOA | 31 | INV | 185 | A | O | I | CFC | 10.9 | 10.9 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2001-12-01 | 2004-01-01 | 85350 | -16916 | 68434 | 68434 | 100% | 0 | 0 | 0 | 11096 | -2199 | 8897 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown and HCFC-141b technology at Sector Co. in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | LAC | BRA | FOA | 31 | INV | 186 | A | O | I | CFC | 17.7 | 17.7 |  |  | 2000-07-01 | 2001-11-01 | 2003-01-01 |  | 2002-12-01 | 2003-02-01 | 130490 | 0 | 130490 | 130490 | 100% | 0 | 0 |  | 16964 | -7 | 16957 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam, from CFC-11 to water-blown foam in flexible molded foam, and from CFC-11 to HCFC-141b in flexible integral skin foam at Multispuma | Individual | LAC | BRA | FOA | 31 | INV | 187 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 123929 | 0 | 123929 | 123929 | 100% | 0 | 0 | 0 | 16111 | 0 | 16111 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin (shoesoles) at Prosola | Individual | LAC | BRA | FOA | 31 | INV | 188 | A | O | I | CFC | 18.1 | 18.1 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 214118 | -165 | 213953 | 213953 | 100% | 0 | 0 | 0 | 27835 | -21 | 27814 | 0 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and flexible molded/integral skin foam at 50 small enterprises centered around their systems house Plastquim | Individual | LAC | BRA | FOA | 31 | INV | 189 | A | O | I | CFC | 153.4 | 153.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-12-01 | 931599 | -41480 | 890119 | 890119 | 100% | 0 | 0 | 0 | 112476 | -4563 | 107913 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Rytpak | Individual | LAC | BRA | FOA | 32 | INV | 190 | A | O | I | CFC | 27 | 27 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-03-01 | 2003-04-01 | 211410 | -22300 | 189110 | 189110 | 100% | 0 | 0 | 0 | 27483 | -2899 | 24584 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams (shoesoles) at Megaflex | Individual | LAC | BRA | FOA | 32 | INV | 191 | A | O | I | CFC | 41.5 | 41.5 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-04-01 | 2003-05-01 | 205568 | -4726 | 200842 | 200842 | 100% | 0 | 0 | 0 | 26724 | -614 | 26110 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Plastiron | Individual | LAC | BRA | FOA | 32 | INV | 192 | A | O | I | CFC | 32.4 | 32.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 131768 | -5277 | 126491 | 126491 | 100% | 0 | 0 | 0 | 17130 | -686 | 16444 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refri-Leste | Individual | LAC | BRA | FOA | 32 | INV | 193 | A | O | I | CFC | 30 | 30 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-09-01 | 2003-04-01 | 136840 | -232 | 136608 | 136608 | 100% | 0 | 0 | 0 | 17789 | -30 | 17759 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam and to HCFC-141b for rigid polyurethane foam at Poliumetka | Individual | LAC | BRA | FOA | 32 | INV | 194 | A | O | I | CFC | 25.5 | 25.5 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-05-01 | 2003-09-01 | 136183 | -10263 | 125920 | 125920 | 100% | 0 | 0 | 0 | 17704 | -1334 | 16370 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Termobras | Individual | LAC | BRA | FOA | 32 | INV | 195 | A | O | I | CFC | 77 | 77 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2003-08-01 | 2005-09-01 | 294590 | -39496 | 255094 | 255094 | 100% | 0 | 0 | 0 | 38297 | -5135 | 33162 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-12 to isobutane technology in the manufacture of extruded polyethylene foam at Thermo-flex | Individual | LAC | BRA | FOA | 32 | INV | 196 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-10-01 | 123300 | 0 | 123300 | 123300 | 100% | 0 | 0 | 0 | 16029 | 0 | 16029 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water technology in the manufacture of rigid polyurethane foam at Ser Therm | Individual | LAC | BRA | FOA | 32 | INV | 197 | A | O | I | CFC | 72 | 72 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 359791 | -76117 | 283674 | 283674 | 100% | 0 | 0 | 0 | 46773 | -9895 | 36878 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manfuacture of rigid polyurethane foam at Jose Sola | Individual | LAC | BRA | FOA | 32 | INV | 198 | A | O | I | CFC | 38.7 | 38.7 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2002-11-01 | 2005-09-01 | 150369 | -24740 | 125629 | 125629 | 100% | 0 | 0 | 0 | 19548 | -3216 | 16332 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2000 | Investment
COM | UNDP | Renewal of institutional strengthening (Phase III) | Individual | LAC | BRA | SEV | 32 | INS | 199 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2006-07-01 |  | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 2006. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | BRA | REF | 32 | TAS | 200 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2003-07-01 | 100000 | -1 | 99999 | 99999 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Frigs | Individual | LAC | BRA | FOA | 32 | INV | 201 | A | O | I | CFC | 90 | 90 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 311056 | -73855 | 237201 | 237201 | 100% | 0 | 0 | 0 | 40437 | -9601 | 30836 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 202 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNIDO | Project preparation for six projects in the commercial/domestic refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 203 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -1663 | 23337 | 23337 | 100% | 0 | 0 |  | 3250 | -221 | 3029 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Project preparation for two projects in the integral skin sector | Individual | LAC | BRA | FOA | 33 | PRP | 204 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-06-01 | 2003-03-01 | 20000 | -615 | 19385 | 19385 | 100% | 0 | 0 |  | 2600 | -84 | 2516 | 0 | 0 | FIN | [13 empty] | 2001 | INV
CLO | UNIDO | Project preparation for four projects in the solvents (CTC) sector | Individual | LAC | BRA | SOL | 33 | PRP | 205 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  |  | 2003-05-01 | 30000 | -26812 | 3188 | 3188 | 100% | 0 | 0 |  | 3900 | -3486 | 414 | 0 | 0 | CLO | [13 empty] | 2001 | INV
FIN | UNIDO | Project preparation for two projects in the rigid foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 206 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-06-01 | 2003-06-01 | 20000 | -130 | 19870 | 19870 | 100% | 0 | 0 |  | 2600 | -21 | 2579 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 207 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 208 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 209 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-12-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 210 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Juntafacil | Individual | LAC | BRA | FOA | 34 | INV | 211 | A | O | I | CFC | 12.2 | 12.2 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2004-01-01 | 55204 | -3500 | 51704 | 51704 | 100% | 0 | 0 | 0 | 7177 | -455 | 6722 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Ornati-Luce | Individual | LAC | BRA | FOA | 34 | INV | 212 | A | O | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2003-11-01 | 46292 | -1550 | 44742 | 44742 | 100% | 0 | 0 | 0 | 6018 | -202 | 5816 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam at Paranoa | Individual | LAC | BRA | FOA | 34 | INV | 213 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-05-01 | 2004-01-01 | 84660 | -1 | 84659 | 84659 | 100% | 0 | 0 | 0 | 11006 | 0 | 11006 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam and rigid integral skin foam at Piatex | Individual | LAC | BRA | FOA | 34 | INV | 214 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-11-01 | 83075 | 0 | 83075 | 83075 | 100% | 0 | 0 | 0 | 10800 | 0 | 10800 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of flexible molded foam and to HCFC-141b for flexible integral skin foam at Rosil | Individual | LAC | BRA | FOA | 34 | INV | 215 | A | O | I | CFC | 5.2 | 5.2 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 87672 | -2545 | 85127 | 85127 | 100% | 0 | 0 | 0 | 11397 | -331 | 11066 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible integral skin and flexible molded foams at Royal Rubber | Individual | LAC | BRA | FOA | 34 | INV | 216 | A | O | I | CFC | 15.3 | 15.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 120795 | -3396 | 117399 | 117399 | 100% | 0 | 0 | 0 | 15703 | -442 | 15261 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for electrical resistance floats at Taurus | Individual | LAC | BRA | FOA | 34 | INV | 217 | A | O | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 88075 | 0 | 88075 | 88075 | 100% | 0 | 0 | 0 | 11450 | 0 | 11450 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Thermoblock | Individual | LAC | BRA | FOA | 34 | INV | 218 | A | O | I | CFC | 41.1 | 41.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 260592 | -36386 | 224206 | 224206 | 100% | 0 | 0 | 0 | 33877 | -4730 | 29147 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNIDO | Umbrella project for four enterprises converting from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a at EZ Industria, Menoncin, Unifrio and from CFC-12 to HFC-134a at Croydon | Individual | LAC | BRA | REF | 34 | INV | 219 | A | O | I | CFC | 30.18 | 30.18 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-04-01 | 2004-12-01 | 469452 | -94888 | 374564 | 374564 | 100% | 0 | 0 |  | 61029 | -12413 | 48616 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based and HCFC-141b technology in the manufacture of rigid and flexible integral skin foam at VM | Individual | LAC | BRA | FOA | 34 | INV | 220 | A | O | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-11-01 | 83902 | 0 | 83902 | 83902 | 100% | 0 | 0 | 0 | 10907 | 0 | 10907 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for surfboards at Jedda | Individual | LAC | BRA | FOA | 34 | INV | 221 | A | O | I | CFC | 54 | 54 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 148272 | -32257 | 116015 | 116015 | 100% | 0 | 0 | 0 | 19275 | -4193 | 15082 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Danica Co. | Individual | LAC | BRA | FOA | 34 | INV | 222 | A | O | I | CFC | 146.6 | 146.6 |  |  | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2004-02-01 | 2004-06-01 | 616625 | 0 | 616625 | 616625 | 100% | 0 | 0 |  | 77829 | -84 | 77745 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the commercial refrigeration sector | Individual | LAC | BRA | REF | 34 | PRP | 223 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-06-01 | 2002-08-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -4060 | 20940 | 20940 | 100% | 0 | 0 |  | 3250 | -532 | 2718 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Transen | Individual | LAC | BRA | FOA | 34 | INV | 224 | A | O | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 61940 | -1800 | 60140 | 60140 | 100% | 0 | 0 | 0 | 8052 | -234 | 7818 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam for cold room panels, freezers and coolers at Central Equipment | Individual | LAC | BRA | FOA | 34 | INV | 225 | A | O | I | CFC | 15.1 | 15.1 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 118233 | -8399 | 109834 | 109834 | 100% | 0 | 0 | 0 | 15370 | -1092 | 14278 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isar | Individual | LAC | BRA | FOA | 34 | INV | 226 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 174320 | -12870 | 161450 | 161450 | 100% | 0 | 0 | 0 | 22662 | -1673 | 20989 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoeste | Individual | LAC | BRA | FOA | 34 | INV | 227 | A | O | I | CFC | 64.9 | 64.9 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2006-06-01 | 237296 | -33228 | 204068 | 204068 | 100% | 0 | 0 | 0 | 30848 | -4320 | 26528 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 2001 | Investment
FIN | Germany | Pilot project: training programme for the refrigeration maintenance sector | Individual | LAC | BRA | REF | 34 | TRA | 228 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2004-08-01 | 2007-12-01 | 247400 | 0 | 247400 | 247400 | 100% | 0 | 0 | 0 | 32162 | 0 | 32162 | 0 | 0 | Project completed. Strategy derived from the demonstration project has been subvmitted with the National Phase Out Plan or Brazil | [13 empty] | 2002
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid and flexible integral skin foams at Air Micro | Individual | LAC | BRA | FOA | 34 | INV | 229 | A | O | I | CFC | 17.3 | 17.3 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2004-01-01 | 56490 | -2984 | 53506 | 53506 | 100% | 0 | 0 | 0 | 7344 | -388 | 6956 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Beneplast | Individual | LAC | BRA | FOA | 34 | INV | 230 | A | O | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 135176 | -12534 | 122642 | 122642 | 100% | 0 | 0 | 0 | 17573 | -1629 | 15944 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Korta Calhas | Individual | LAC | BRA | FOA | 34 | INV | 231 | A | O | I | CFC | 75.7 | 75.7 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 151812 | 0 | 151812 | 151812 | 100% | 0 | 0 | 0 | 19736 | 0 | 19736 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam, rigid foam and flexible molded foam at Carolinas | Individual | LAC | BRA | FOA | 34 | INV | 232 | A | O | I | CFC | 49.7 | 49.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 237597 | -80 | 237517 | 237517 | 100% | 0 | 0 | 0 | 30888 | -10 | 30878 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam and rigid integral skin foam, and to HCFC-141b for rigid, flexible integral skin and phenolic foams at J. Dal Ponte | Individual | LAC | BRA | FOA | 34 | INV | 233 | A | O | I | CFC | 97.6 | 97.6 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 384134 | 0 | 384134 | 384134 | 100% | 0 | 0 | 0 | 49937 | 0 | 49937 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HFC-141b in the manufacture of rigid polyurethane foam at Danko | Individual | LAC | BRA | FOA | 34 | INV | 234 | A | O | I | CFC | 41.4 | 41.4 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 199684 | -3329 | 196355 | 196355 | 100% | 0 | 0 | 0 | 25959 | -433 | 25526 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for truck bodies and panels at 9 enterprises (ABC Furgoes, Fricam Refri, Junges, Rafaeli, Refri Santos, Rondofrio, Tresmaiense, Trevosul Refrig, Verde Lago Furgoes) | Individual | LAC | BRA | FOA | 34 | INV | 235 | A | O | I | CFC | 65.3 | 65.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-12-01 | 450479 | -69602 | 380877 | 380877 | 100% | 0 | 0 | 0 | 58562 | -9048 | 49514 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Grupo ACO | Individual | LAC | BRA | FOA | 34 | INV | 236 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2004-08-01 |  |  | 2002-07-01 | 174139 | -174139 | 0 | 0 |  | 0 | 0 | 0 | 22638 | -22638 | 0 | 0 | 0 | Canceled in 2002. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoprice | Individual | LAC | BRA | FOA | 34 | INV | 237 | A | O | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-12-01 | 2006-10-01 | 126846 | -9673 | 117173 | 117173 | 100% | 0 | 0 | 0 | 16490 | -1257 | 15233 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible microcellular foams at Hidroplas | Individual | LAC | BRA | FOA | 34 | INV | 238 | A | O | I | CFC | 33 | 33 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2002-11-01 | 2004-01-01 | 166211 | -5537 | 160674 | 160674 | 100% | 0 | 0 | 0 | 21607 | -720 | 20887 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam for ice cream makers and coolers at three enterprises (A.V. Bertollo, Citrocar, Systherm) | Individual | LAC | BRA | FOA | 34 | INV | 239 | A | O | I | CFC | 25.5 | 25.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-10-01 | 2005-12-01 | 135345 | -2457 | 132888 | 132888 | 100% | 0 | 0 | 0 | 17595 | -319 | 17276 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Injetec | Individual | LAC | BRA | FOA | 34 | INV | 240 | A | O | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 43334 | -2371 | 40963 | 40963 | 100% | 0 | 0 | 0 | 5633 | -308 | 5325 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNIDO | Umbrella project for two enterprises converting from CFC-11 and HCFC-141b and from CFC-12 to HFC-134a at Argi and Hornburg | Individual | LAC | BRA | REF | 35 | INV | 241 | A | O | I | CFC | 11.2 | 11.2 |  |  | 2001-12-01 | 2002-11-01 | 2004-05-01 |  | 2004-10-01 | 2005-05-01 | 108050 | -12441 | 95609 | 95609 | 100% | 0 | 0 |  | 14047 | -1638 | 12409 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | IBRD | Project preparation in the process agent sub-sector |  | LAC | BRA | PAG | 36 | PRP | 242 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-12-01 | 50000 | -14819 | 35181 | 35181 | 100% | 0 | 0 |  | 6500 | -1926 | 4573.53 | 0.47 | 0.47 | Upon confirmation of very low national CTC consumption, arrangements with Ministry of Environment are being made to transfer project to UNDP. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Pretty Glass | Individual | LAC | BRA | FOA | 36 | INV | 243 | A | O | I | CFC | 17.2 | 17.2 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 91508 | -6465 | 85043 | 85043 | 100% | 0 | 0 | 0 | 11896 | -840 | 11056.04 | -0.04 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Decorfrio | Individual | LAC | BRA | FOA | 36 | INV | 244 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2005-12-01 | 2007-03-01 | 98416 | -3 | 98413 | 98413 | 100% | 0 | 0 | 0 | 12794 | 0 | 12794.08 | -0.08 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Simonaggio | Individual | LAC | BRA | FOA | 36 | INV | 245 | A | O | I | CFC | 15.8 | 15.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-09-01 | 120383 | -10640 | 109743 | 109743 | 100% | 0 | 0 | 0 | 15650 | -1383 | 14266.79 | 0.21 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Heliotek | Individual | LAC | BRA | FOA | 36 | INV | 246 | A | O | I | CFC | 27.4 | 27.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 127133 | -12221 | 114912 | 114912 | 100% | 0 | 0 | 0 | 16527 | -1588 | 14939.29 | -0.29 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isojet | Individual | LAC | BRA | FOA | 36 | INV | 247 | A | O | I | CFC | 47.4 | 47.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 130427 | 0 | 130427 | 130427 | 100% | 0 | 0 | 0 | 16956 | 0 | 16955.51 | 0.49 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Tecnosono | Individual | LAC | BRA | FOA | 36 | INV | 248 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2003-07-01 | 2004-01-01 | 134718 | -4512 | 130206 | 130206 | 100% | 0 | 0 | 0 | 17513 | -587 | 16926.34 | -0.34 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Tolling Quimica | Individual | LAC | BRA | FOA | 36 | INV | 249 | A | O | I | CFC | 21.9 | 21.9 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-08-01 | 2005-10-01 | 159662 | -1356 | 158306 | 158306 | 100% | 0 | 0 | 0 | 20756 | -176 | 20580.06 | -0.06 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibral | Individual | LAC | BRA | FOA | 36 | INV | 250 | A | O | I | CFC | 47.5 | 47.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-03-01 | 197613 | -1856 | 195757 | 195757 | 100% | 0 | 0 | 0 | 25690 | -241 | 25448.69 | 0.31 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Preparation of a CFC terminal phase-out programme | Individual | LAC | BRA | PHA | 36 | PRP | 251 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam, and water-blown technology for flexible moulded foam at Arquespuma | Individual | LAC | BRA | FOA | 36 | INV | 252 | A | O | I | CFC | 55.8 | 55.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-01-01 | 207741 | 0 | 207741 | 207741 | 100% | 0 | 0 | 0 | 27006 | 0 | 27006.33 | -0.33 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isosister | Individual | LAC | BRA | FOA | 36 | INV | 254 | A | O | I | CFC | 82.5 | 82.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2007-03-01 | 277668 | -6748 | 270920 | 270920 | 100% | 0 | 0 | 0 | 36097 | -877 | 35219.84 | 0.16 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water/methylene chloride/hydrocarbon-blown technology in the manufacture of rigid and flexible foam at Toro | Individual | LAC | BRA | FOA | 36 | INV | 255 | A | O | I | CFC | 22.4 | 22.4 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2004-12-01 | 2005-10-01 | 279477 | 0 | 279477 | 279477 | 100% | 0 | 0 | 0 | 36332 | 0 | 36332.01 | -0.01 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Repor | Individual | LAC | BRA | FOA | 36 | INV | 256 | A | O | I | CFC | 50.8 | 50.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2008-04-01 | 323201 | -35934 | 287267 | 287267 | 100% | 0 | 0 | 0 | 42016 | -4671 | 37345.13 | -0.13 | 0 | Completed in 2004. Financially completed in 2008. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid foam and flexible integral skin foam and water-blown technology for flexible moulded foam and rigid integral skin foam at Ariston Polimeros | Individual | LAC | BRA | FOA | 36 | INV | 257 | A | O | I | CFC | 75.1 | 75.1 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-08-01 | 2005-09-01 | 369242 | -12749 | 356493 | 356493 | 100% | 0 | 0 | 0 | 48001 | -1657 | 46344.46 | -0.46 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Indaru | Individual | LAC | BRA | FOA | 36 | INV | 258 | A | O | I | CFC | 93.8 | 93.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2004-06-01 | 2007-03-01 | 423121 | 0 | 423121 | 423121 | 100% | 0 | 0 | 0 | 55006 | 0 | 55005.73 | 0.27 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam, elastomers and integral skin foam for automotive applications and to HCFC-141b for furniture integral skin foam applications at Steel Plastik | Individual | LAC | BRA | FOA | 36 | INV | 259 | A | O | I | CFC | 46.7 | 46.7 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-12-01 | 2005-11-01 | 247882 | 0 | 247882 | 247882 | 100% | 0 | 0 | 0 | 32225 | 0 | 32224.66 | 0.34 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | Germany | National CFC phase out plan: training of customs officers | Multi-Year | LAC | BRA | PHA | 37 | TRA | 260 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2007-12-01 | 2008-12-01 | 141200 | 0 | 141200 | 141200 | 100% | 0 | 0 | 0 | 18356 | 0 | 18356 | 0 | 0 | Training activities for 55 customs officers/instructors as well 9 staff members from the national environmental protection agency are completed. Refrigerant identifiers were purchased in 2007 and distributed to Customs officers. The project is completed. | [15 empty] | 1000
FIN | Germany | National CFC phase-out plan: training of refrigeration mechanics in domestic and commercial refrigeration service sub-sectors (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | TRA | 261 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2006-12-01 | 2007-12-01 | 435937 | 1062863 | 1498800 | 1498800 | 100% | 0 | 0 | 0 | 56672 | 95658 | 152330 | 0 | 0 | By end of 2006 7000 technicians had been trained under this tranche. A total of 27 mobile training units have been built and are used in the field. Production of 8,000 free books with photo-training on good practices for mechanics in the commercial and do | [15 empty] | 1000
COM | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | INV | 262 | N | O | I | CFC | 1251 | 1251 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2003-12-01 |  | 2005-12-01 |  | 7860000 | 0 | 7860000 | 7860000 | 100% | 0 | 0 | 0 | 687700 | 0 | 687700 | 0 | 0 | Completed in 2005. | [13 empty] | 2002 | Investment | 5801 | 5801 |  |  | Yes | Yes | yes
FIN | UNIDO | Assistance for the preparation of a survey on the consumption of methyl bromide | Individual | LAC | BRA | FUM | 38 | TAS | 263 | A | O | I | MBR | 0 | 0 |  |  | 2002-11-01 | 2004-04-01 | 2003-12-01 |  | 2005-09-01 | 2006-09-01 | 40000 | -862 | 39138 | 39138 | 100% | 0 | 0 |  | 5200 | -112 | 5088 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
COM | UNDP | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 264 | N | O | I | CFC | 737 | 737 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2008-12-01 |  | 5720000 | 0 | 5720000 | 5720000 | 100% | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 0 | Completed in 2008. National CFC Phase-out Plan . See 2008 progress in BRA/PHA/53/INV/280. 3rd Tranche, for 2003/4 Action Plan. | [13 empty] | 2003 | Investment | 4550 | 4550 |  |  | Yes | Yes | Yes
COM | Germany | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 265 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 |  | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 63000 | 0 | 63000 | 0 | 0 | By end of 2008, more than 300 technicians had been trained under this tranche. One train the trainer course with 35 participants was conducted. A total of 12 mobile training units have been built and are used in the field. Continue to further distribute educational materials and public relation materials and to monitor and to follow up the success of training activities of technicians. | [15 empty] | 1000
FIN | UNDP | Project preparation for the formulation of CTC as a process agent | Individual | LAC | BRA | SOL | 42 | PRP | 266 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
COM | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BRA | SEV | 43 | INS | 267 | N | T | I | No_ODP | 29 | 29 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 |  | 351000 | 0 | 351000 | 274518 | 78.21% | 76482 | 0 | 61185.6 | 26325 | 0 | 20588.85 | 5736.15 | 0 | Completed in 2007. | [13 empty] | 2004 | Non-Investment
FIN | UNIDO | Project preparation in methyl bromide (tobacco, flowers, horticulture) | Individual | LAC | BRA | FUM | 44 | PRP | 269 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-11-01 | 40000 | -1133 | 38867 | 38867 | 100% | 0 | 0 |  | 3000 | -85 | 2915 | 0 | 0 | FIN | [13 empty] | 2004
ONG | UNDP | National CFC phase-out plan: third tranche | Multi-Year | LAC | BRA | PHA | 45 | INV | 270 | N | O | I | CFC | 743 | 743 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2006-04-01 | 2010-01-01 |  |  | 3970000 | 0 | 3970000 | 628872 | 15.84% | 3341128 | 23200 | 668225.6 | 342500 | 0 | 54254.0705 | 288245.9295 | 2001.5113 | National CFC Phase-out Plan. See 2008 progress in BRA/PHA/53/INV/280. 4th Tranche, for 2005/6 Action Plan | [13 empty] | 2005 | Investment | 3813 | 3813 |  |  | Yes | Yes | Yes
COM | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | BRA | SEV | 45 | TAS | 271 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 |  | 183486 | 0 | 183486 | 166627 | 90.81% | 16859 | 0 | 13487.2 | 16514 | 0 | 14996.6661 | 1517.3339 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
ONG | Spain | Total phase-out of MB used in tobacco, flowers, ornamental plants, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 272 | A | O | I | MBR | 65.4 | 0 | 0 |  | 2005-07-01 | 2006-10-01 | 2007-07-01 | 2009-06-01 |  |  | 580390 | 0 | 580390 | 46348 | 7.986% | 534042 | 76510 | 280000 | 75451 | 0 | 6025.24 | 69425.76 | 9946.3 | This project is about to be completed. Completion date is expected to be june 2009. They are finalising the preparation of some brochures and publications with the results of the project. | [13 empty] | 2005 | Investment
COM | UNIDO | Total phase-out of MB used in tobacco, flowers, ornamentals, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 273 | A | O | I | MBR | 153.2 | 153.2 |  |  | 2005-07-01 | 2005-10-01 | 2007-07-01 |  | 2008-12-01 |  | 1450251 | 0 | 1450251 | 1361658 | 93.89% | 88593 | 70426 | 70000 | 108769 | 0 | 102124 | 6645 | 5282 | Some delays in the procurement process of the solar collectors caused delay in the project. However, the procurement was finally done. The last equipment items and training in the use of such devices were carried out. Project completed in Dec 2008. | [12 empty] | 2008-12-01 | 2005 | INV
ONG | UNDP | National CFC phase-out plan: fourth tranche | Multi-Year | LAC | BRA | PHA | 47 | INV | 274 | N | O | I | CFC | 1020 | 1020 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2010-01-01 |  |  | 2856400 | 0 | 2856400 | 0 | 0% | 2856400 | 0 | 571280 | 242276 | 0 | 0 | 242276 | 0 | National CFC Phase-out Plan. See 2008 progress in BRA/PHA/53/INV/280. 5th Tranche, for 2007 Action Plan. | [13 empty] | 2005 | Investment | 3070 | 3070 |  |  | Yes | Yes | Yes
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | BRA | REF | 47 | DEM | 275 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2010-01-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 0 | 200000 | 75000 | 0 | 0 | 75000 | 0 | Project had IADB portion of financial mechanisms revised after due diligence process. Submission for CEO endorsement expected before May 09. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Project preparation for solvent and process agent sectors | Individual | LAC | BRA | SOL | 48 | PRP | 276 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 |  | 50000 | 0 | 50000 | 37074 | 74.15% | 12926 | 0 | 12926 | 3750 | 0 | 2780.55 | 969.45 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | Germany | National CFC phase-out plan: third and fourth tranches | Multi-Year | LAC | BRA | PHA | 48 | INV | 277 | A | O | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-12-06 | 2007-04-01 | 2010-04-10 |  |  | 1543600 | 0 | 1543600 | 1143600 | 74.09% | 400000 | 0 | 400000 | 138924 | 0 | 102924 | 36000 | 0 | A new training agreement for 5000 technicians was concluded in 2008 to continue training for the period 2008/09. | [15 empty] | 1000
ONG | UNDP | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | BRA | PHA | 50 | INV | 278 | N | O | I | CFC | 1050 | 1050 | 0 | 0 | 2006-11-01 |  | 2009-12-01 | 2010-01-01 |  |  | 1190000 | 0 | 1190000 | 0 | 0% | 1190000 | 0 | 238000 | 92300 | 0 | 0 | 92300 | 0 | National CFC Phase-out Plan. See 2008 progress in BRA/PHA/53/INV/280. 6th Tranche, for 2008 Action Plan. | [13 empty] | 2006 | Investment | 2050 | 2050 |  |  | Yes | Yes | Yes
ONG | UNDP | Extension of institutional strengthening project (phase V) | Individual | LAC | BRA | SEV | 52 | INS | 279 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-06-01 | 2010-01-01 |  |  | 351000 | 0 | 351000 | 46568 | 13.27% | 304432 | 0 | 60886.4 | 26325 | 0 | 3492.6 | 22832.4 | 0 | During 2008 the Institutional Strengthening Project, Phase-V, provided to Brazil support on the implementation of ozone layer protection policies, timely reporting of ODS consumption to the Montreal Protocol bodies, technical support on ozone issues, creation and printing of public awareness material on subjects related to the ozone layer problematic and protection, and missions for public awareness and capacity building in the different regions of the country. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | National CFC phase-out plan (sixth tranche) | Multi-Year | LAC | BRA | PHA | 53 | INV | 280 | N | O | I | CFC | 576 | 576 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 |  |  | 870000 | 0 | 870000 | 0 | 0% | 870000 | 0 | 174000 | 63500 | 0 | 0 | 63500 | 0 | 2008 achievements include: procurement of 10 units of R&R equipments to services in Chillers with CFC-11 and CFC-12; distribution of last 800 units of CFC-12 recovery machines; import, installation and commissioning of 3 remaining Reclaim Center equipments, distribution of the last 25 units of CFC-12 for MAC services; completion of Recovery Bags tests and procurement of 3.000 Kits with tools and bags; beginning of procurement of 120 units of small Recycle Centers; completion of 2 national workshops (i) on Domestic Refrigerators de-manufacturing, (ii) on service in commercial refrigeration. 7th tranche approved at 56th ExCom. | [13 empty] | 2007 | Investment | 1000 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Phase-out of CTC as process agent in two applications at Braskem | Individual | LAC | BRA | PAG | 54 | INV | 281 | N | O | I | CTC | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 1178554 | 0 | 1178554 | 0 | 0% | 1178554 | 0 | 235710.8 | 88392 | 0 | 0 | 88392 | 0 | International expert and local expert for verification recruited, mission planned for end of April 2009. | [13 empty] | 2008 | Investment
ONG | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BRA | PHA | 55 | PRP | 282 | A | O | I | HCFC | 0 |  | 0 |  | 2008-07-01 |  | 2009-07-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | The first Interagency meeting was organized in Mar-2009. In 2008 only some research activities on subsector background were done. Consultants will be hired during May/June 09 to start with surveys and review of legislation, regulation during next months.
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | BRA | PHA | 55 | PRP | 283 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 143750 | 0 | 143750 | 0 | 0% | 143750 | 0 | 143750 | 10781 | 0 | 0 | 10781 | 0 | Meetings with involved sectors and National Ozone Unit held in order to start HPMP preparation. | [13 empty] | 2008 | Investment
ONG | UNDP | National CFC phase-out plan (seventh tranche) | Multi-Year | LAC | BRA | PHA | 56 | INV | 284 | N | O | I | CFC | 350 | 50 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 0 | 100000 | 12500 | 0 | 0 | 12500 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNDP | Pilot project for validation of methyl formate as a blowing agent in the manufacture of polyurethane foam (phase I) | Individual | LAC | BRA | FOA | 56 | TAS | 285 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-06-01 | 2009-12-01 |  |  | 401500 | 0 | 401500 | 0 | 0% | 401500 | 0 | 160600 | 30113 | 0 | 0 | 30113 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
FIN | UNEP | Country programme preparation | Individual | ASP | BRU | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-09-25 | 1996-03-01 |  | 1998-09-01 | 1999-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
COM | UNEP | Creation of a Brunei Ozone Office | Individual | ASP | BRU | SEV | 26 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-11 | 2001-12-01 |  | 2004-07-04 |  | 80000 | 0 | 80000 | 71136.98 | 88.92% | 8863.02 | 0 | 8863.02 | 10400 | 0 | 9247.8074 | 1152.1926 | 0 | Project completed | [13 empty] | 1998 | Non Investment
COM | UNEP | Development of RMP | RMP | ASP | BRU | REF | 30 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-11-01 |  | 30000 | -5000 | 25000 | 14500 | 58% | 10500 | 0 | 10500 | 3900 | -650 | 1885 | 1365 | 0 | Project completed | $ 5,000 plus $ 650 returned to ExCom 50 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | BRU | REF | 39 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | BRU | SEV | 43 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2009-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 70000 | 0 | 0 | 0 | 0 | 0 | No progress, the agreement is not yet signed. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and national technicians training | Individual | ASP | BRU | REF | 44 | TRA | 7 | A | O | I | CFC | 6.7 | 0 | 0 | 0 | 2004-12-01 | 2008-06-01 | 2006-12-01 | 2009-04-01 |  |  | 50000 | 0 | 50000 | 44111.95 | 88.22% | 5888.05 | 0 | 5888.05 | 6500 | 0 | 5734.5535 | 765.4465 | 0 | 25-29Feb08: National Train-the-Trainer's Workshop On Good Practices in the Refrigeration Sector | [13 empty] | 2004 | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | BRU | REF | 44 | TRA | 8 | A | O | I | CFC | 4.6 | 4.6 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 34000 | 0 | 34000 | 33999.66 | 100% | 0.34 | 0 | 0.34 | 4420 | 0 | 4419.9558 | 0.0442 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring of the activities included in the RMP | Individual | ASP | BRU | REF | 44 | TAS | 9 | A | O | I | CFC | 2.9 | 0 | 0 | 0 | 2004-12-01 | 2008-05-01 | 2007-12-01 | 2009-12-01 |  |  | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | Train-the-trainer workshop for refrigeration technicians was conducted in February 2008. Brunei Darussalam has been meeting the obligations under the Montreal Protocol since becoming a Party in 1993.The reported 2007 CFC consumption met the 85% reduction target under the Montreal Protocol. | [13 empty] | 2004 | Non Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration service and MAC sectors | RMP-Component | ASP | BRU | REF | 44 | TAS | 10 | N | O | I | CFC | 52.3 | 0 | 0 | 0 | 2004-12-01 |  | 2007-05-01 | 2010-12-01 |  |  | 390000 | 0 | 390000 | 0 | 0% | 390000 | 0 | 78000 | 29250 | 0 | 0 | 29250 | 0 | The Project document in 2008 was not signed as at 31st December. We expect that in 2009 the project will be signed and the activities will be accelerated for Brunei to meet the 2010 phase out schedule. | [13 empty] | 2004 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BRU | PHA | 55 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Newly approved project. The agreement was in the stage of processing. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | BZE | SEV | 24 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-02-01 |  | 1999-11-01 | 2000-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 | 0 | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | Canada | Implementation of the RMP: training of trainers and refrigeration technicians in good servicing practices | RMP | LAC | BZE | REF | 29 | TRA | 2 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Train the trainers workshop held in April 2001. Subsequent training took place in 2002 and finalized in 2003. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: monitoring and control of ODS and ODS based equipment and training programme for customs and other inspection officers | RMP | LAC | BZE | REF | 29 | TAS | 3 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 3640 | 0 | 3640 | 0 |  | Train-the-trainer customs workshop held in March 2002. Phase II training completed in 2003. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: policy dialogue programme and regulatory framework for phasing out ODSs | RMP | LAC | BZE | REF | 29 | TAS | 4 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2000-09-01 |  | 2001-11-01 | 2002-12-01 | 15500 | 0 | 15500 | 15500 | 100% | 0 |  | 0 | 2015 | 0 | 2015 | 0 |  | Planning and Policy Dialogue component completed Nov. 2001. Regulatory framework developed and adopted by Government. PCR submitted |  | 1999 |  |  |  | 2001-12-01 | [7 empty] | 1999 | Non-Inv.
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | BZE | REF | 29 | TAS | 5 | A | O | I | CFC | 1.7 | 1.7 | 0 | 0 | 1999-11-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2003-09-01 | 61125 | 0 | 61125 | 61125 | 100% | 0 | 0 | 0 | 7946 | 0 | 7946 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNEP | Creation of the national ozone unit | Individual | LAC | BZE | SEV | 29 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2003-01-01 | 2004-10-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 | 0 | 11505 | 0 | 11505 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | BZE | SEV | 40 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-07-01 | 2007-07-01 | 76700 | 0 | 76700 | 76700.21 | 100% | -0.21 | 0 | -0.21 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | BZE | REF | 41 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-04 | 2005-06-01 | 15000 | -1250 | 13750 | 13750 | 100% | 0 | 0 | 0 | 1950 | -163 | 1787.5 | -0.5 | 0 | Project financially completed. | $ 1,250 plus $ 163 returned to ExCom 49 | [12 empty] | 2003 | Non Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment component) | Individual | LAC | BZE | REF | 42 | PRP | 9 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 | 2007-06-01 | 20000 | -1164 | 18836 | 18836 | 100% | 0 | 0 | 0 | 1500 | -87 | 1412.7 | 0.3 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2004 | Investment
ONG | UNEP | Implementation of the RMP: certification and licensing of refrigeration technicians | Individual | LAC | BZE | REF | 44 | TAS | 11 | A | O | I | CFC | 5 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 | 2009-06-01 |  |  | 33682 | 0 | 33682 | 33682 | 100% | 0 | 0 | 0 | 4378.6602 | 0 | 4378.66 | 0.00015625 | 0 | A total of six (6) training workshops for technicians were conducted under the Certification and Licensing Programme for technicians of the RMP. All six training sessions were on “Good Practices in Refrigeration”. Most of the participants had a strong background in refrigeration practices. Technicians worked in different field including domestic, commercials and industrial refrigeration and air conditioning, including mobile air conditioning (MAC). Under the RMP implementation, approximately 150 technicians were trained and certified in Good Practices in Refrigeration. They came from private sector companies and recognized service workshops, all comprising of the formal refrigeration sector of Belize. The RMP focused more in training technicians in the formal sector, thus training approximately 85% of technicians in the formal sector. The current TPMP is focusing in the training the remainder of technicians of the formal sector and is making great efforts in training technicians of the informal sector. | [13 empty] | 2004 | Non Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | LAC | BZE | REF | 44 | TAS | 12 | N | O | I | CFC | 6.7 | 6.7 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2007-12-01 |  | 2006-12-01 | 2007-06-01 | 44879 | -211 | 44668 | 44668 | 100% | 0 | 0 | 0 | 4039 | -19 | 4020 | 0 | 0 | Completed in 2006. Financially completed in 2007. | [13 empty] | 2004 | Investment
ONG | UNEP | Implementation of the RMP: prevention of illegal trade of CFCs | Individual | LAC | BZE | REF | 44 | TAS | 13 | A | O | I | CFC | 3.4 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 | 2009-06-01 |  |  | 22611 | 0 | 22611 | 22611 | 100% | 0 | 0 | 0 | 2939.4299 | 0 | 2939.43 | -6.8359e-05 | 0 | UNEP continues to encourage project implementation and assists country by providing information through its networks and e-fora focused on illegal trade prevention. NOU continues to assist customs in monitoring illegal ports of entries in the country where illegal CFC imports can be introduced. In addition, the NOU handed-over refrigerant identifiers to the Customs Department which were distributed to all ports of entry. Under the CFC illegal trade prevention component of the RMP, the NOU established a good working relationship with the Customs Department, thus training 40 Customs Officers in the prevention of illegal ODS trade and ODS import/exporting licensing system. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | BZE | REF | 44 | TAS | 14 | A | O | I | CFC | 4 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 | 2009-06-01 |  |  | 27140 | 0 | 27140 | 27140.16 | 100% | -0.16 | 0 | -0.16 | 3528.2 | 0 | 3528.2208 | -0.020849 | 0 | With regards to monitoring and follow up of the network of recycling and recovery (R&R), NOU visited the 80% of technicians and workshops belonging to such Network. Interim progress and financial reports for each of the RMP components were prepared. Under the monitoring programme of the RMP, the NOU with the assistance of technicians that are active within the Ozone Programme, visited and contacted the servicing workshops in order to verify working modalities, tools used, tool lacked quantity and type of refrigerants used, etc., both for the workshop and the certified technicians. he NOU visited to the servicing workshops that have been granted Equipment and tools (UNDP component of RMP), to verify if they are complying with the terms and conditions of the Memorandum of Understanding (MOU) that were signed between the NOU and the technicians. | [13 empty] | 2004 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase III) | Individual | LAC | BZE | SEV | 46 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-07-01 | 2007-07-01 |  | 2008-09-01 |  | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in September 2008. Terminal progress and financial reports were sent accordingly, as well as reports to OS and MFS. The Belizean Ozone Unit continues leading successfully the implementation of further activities through projects from the Multilateral Fund and public awareness campaign at national level. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | BZE | PHA | 50 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2007-09-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | BZE | PHA | 50 | PRP | 17 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2008-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2006 | Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | BZE | SEV | 53 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 | 2010-07-01 |  |  | 76700 | 0 | 76700 | 30400 | 39.63% | 46300 | 46300 | 46300 | 0 | 0 | 0 | 0 | 0 | IS project in Belize has assisted in strengthening cooperation links between the NOU and the Customs Department, particularly through the operation of the ODS license system, whereby reduction in the consumption of CFC has been successfully achieved. In the case of the refrigeration sector, the new Association of Refrigeration and Air Conditioning Technicians (ARACT) was established and oficially registered in December 2008. A full plan of certification and public awareness is already being considered as part of their activities with NOU supervision. NOU carried out various outreach activities, being the most relevant the broadcasting of the Ozzy Ozone TV spot for the whole month of September as well as the distribution of Ozzy Ozone materials in schools and agricultural fairs and tradeshows. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | BZE | PHA | 53 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  |  | 53000 | 0 | 53000 | 31073.34 | 58.63% | 21926.66 | 21926.68 | 21926.66 | 6890 | 0 | 4039.5342 | 2850.4658 | 2850.4684 | Main achievement is the creation of the Association of Refrigeration and Air Conditioning Technicians of Belize, which has been officially registered in December 2008. When the Refrigeration Technicians (Licensing ) Bill is enacted, it will become a legal requirement for all technicians handling refrigerants to be licensed. Currently 5 levels of certification are being considered, covering the domestic, commercial, MAC and industrial sectors. The TPMP is focusing in training of technicians in the informal refrigeration and air conditioning sector, since approximately 85% of technicians in the formal sector were trained and certified under the RMP. Under TPMP, 20 technicians, all from the informal sector were trained in August 2008. With regards to Training of Customs and Enforcement Officers, the initial action plan comprised two phases, phase I being the train-the customs-trainers and phase II being the training of the remaining Customs Officers. Phase I was successful achieved in October 2008, with 16 officers being trained. However, due to the time of the year and high season for the Belize Customs Department, Phase II is going to be implemented in 2009. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | BZE | PHA | 53 | INV | 20 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-09-01 | 2009-11-01 | 2010-01-01 |  |  | 122000 | 0 | 122000 | 59071 | 48.42% | 62929 | 0 | 12585.8 | 10980 | 0 | 5316.39 | 5663.61 | 0 | In September a training workshop for 19 technicians in the informal sector was conducted. 10 technicians from the informal sector is in the process of receiving a 1 year technical training at the training institute in Belize. Needs assessment carried out and procurement of equipment in process. The equipment is expected to be deliver in early 2009. | [13 empty] | 2007 | Investment | 3.7 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BZE | PHA | 55 | PRP | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2010-07-31 |  |  | 85000 | 0 | 85000 | 10575 | 12.44% | 74425 | 0 | 74425 | 11050 | 0 | 1374.75 | 9675.25 | 0 | Preliminary discussions for HCFC survey, identification of country needs and further arrangements are being set. Funding agreement (SSAF) currently being negotiated with the country. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | CAF | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-17 | 1995-06-01 |  | 1995-10-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of the National Technical Ozone Group (Ozone Unit) | Individual | AFR | CAF | SEV | 18 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 2000-06-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 | 0 | 5928 | 0 | 5928 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | CAF | SEV | 18 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
CLO | UNDP | Continuation of conversion to CFC-free technology in manufacturing of flexible polyurethane foam at Vita-Centrafrique | Individual | AFR | CAF | FOA | 19 | INV | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1997-05-01 |  |  | 2001-12-01 | 62000 | -30537 | 31463 | 31463 | 100% | 0 | 0 | 0 | 8060 | -3970 | 4090 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  |  | 1998-04-01 | [10 empty] | 1996 | Investment
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | CAF | REF | 20 | TAS | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-09-01 |  |  | 2001-12-01 | 66441 | -923 | 65518 | 65518 | 100% | 0 | 0 | 0 | 8637 | -120 | 8517 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  |  |  | 1999-06-01 | [9 empty] | 1996 | Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | CAF | SEV | 26 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2004-10-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | CAF | REF | 27 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2001-05-01 | 2002-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
CLO | France | Implementation of the RMP: training programme for customs officers |  | AFR | CAF | REF | 34 | TRA | 8 | N | O | I |  | 4.4 | 2.86 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  | 2008-07-14 | 2009-04-01 | 77440 | 0 | 77440 | 50500 | 65.21% | 26940 |  | 0 | 10067 | 0 | 6564.8696 | 3502.1304 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
CLO | France | Implementation of the RMP: train the trainers programme for refrigeration technicians in good management practices and a training programme to address technicians in the informal sector |  | AFR | CAF | REF | 34 | TRA | 9 | A | O | I |  | 3.4 | 2.408 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  | 2008-07-14 | 2009-04-01 | 60900 | 0 | 60900 | 43141.4894 | 70.84% | 17758.5106 |  | 0 | 7917 | 0 | 5608.3936 | 2308.6064 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
CLO | France | Implementation of the RMP: development and implementation of a tax/incentive programme |  | AFR | CAF | REF | 34 | TAS | 10 | N | O | I |  | 0.3 | 0.09 | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  | 2008-07-14 | 2009-04-01 | 5500 | 0 | 5500 | 1595.7447 | 29.01% | 3904.2553 |  | 0 | 715 | 0 | 207 | 508 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom)
CLO | France | Implementation of the RMP: monitoring the activities of the RMP project, including registration of refrigeration service technicians, distributors and importers of CFCs |  | AFR | CAF | REF | 34 | TAS | 11 | N | O | I |  | 1.5 | 0.98 | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  | 2008-07-14 | 2009-04-01 | 26250 | 0 | 26250 | 17263.8298 | 65.77% | 8986.1702 |  | 0 | 3413 | 0 | 2245 | 1168 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
FIN | UNEP | Extension of institutional strengthening project | Individual | AFR | CAF | SEV | 38 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2006-01-01 | 2007-04-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CAF | SEV | 45 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-06-01 | 2007-04-01 | 2009-04-01 |  |  | 60000 | 0 | 60000 | 24395.17 | 40.66% | 35604.83 | 35604.57 | 35604.83 | 0 | 0 | 0 | 0 | 0 | NOU organise consultation with various stakeholder for preparation of TPMP and implementation of remaining RMP activities. NOU collected data and report to the OS the MFS and prepared various reports for Implementing Agencies (UNEP & France). | [13 empty] | 2005 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CAF | PHA | 49 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-07-31 |  | 2008-07-01 |  | 30000 | 0 | 30000 | 8000.22 | 26.67% | 21999.78 | 22000.08 | 21999.78 | 3900 | 0 | 1040.0286 | 2859.9714 | 2860.0104 | Project completed in July 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 | 2009-12-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 7800 | 0 | 0 | 7800 | 0 | MoU for the implementation of the TPMP sent to the country in Nov 2008 | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CAF | PHA | 55 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for Signing | [13 empty] | 2008
ONG | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | INV | 17 | A | O | I | CFC | 0.7 |  | 0 |  | 2008-07-01 |  | 2009-12-01 | 2009-12-01 |  |  | 55000 | 0 | 55000 |  | 0% | 55000 |  | 45000 | 7150 | 0 | 0 | 7150 |  | Coordination meeting took place with NOU and UNEP. Financial agreement between AFD and CAF should be signed soon.
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | CBI | SEV | 35 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2003-08-01 |  | 2004-12-04 | 2008-12-01 | 40000 | -4983 | 35017 | 35017 | 100% | 0 | 0 | 0 | 5200 | -648 | 4552.21 | -0.21 | 0 | Project financially completed. | $ 1,983 plus $ 258 returned to ExCom 50 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | CBI | SEV | 36 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2005-06-01 | 2003-04-01 |  | 2007-11-01 | 2008-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | AFR | CBI | REF | 42 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
COM | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | CBI | REF | 44 | TRA | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 |  | 40000 | 0 | 40000 | 22577.93 | 56.44% | 17422.07 | 16138.52 | 17422.07 | 5200 | 0 | 2935.1309 | 2264.8691 | 2098.0076 | Project completed in December 2008 | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | CBI | REF | 44 | TAS | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2008-12-01 |  | 20000 | 0 | 20000 | 12360.47 | 61.8% | 7639.53 | 7640 | 7639.53 | 2600 | 0 | 1606.8611 | 993.1389 | 993.2 | Project completed in December 2008 | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CBI | REF | 44 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 |  | 40000 | 0 | 40000 | 33358.47 | 83.4% | 6641.53 | 6498.35 | 6641.53 | 5200 | 0 | 4336.6011 | 863.3989 | 844.7855 | Project completed in December 2008 | [13 empty] | 2004 | Non Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | CBI | REF | 44 | TAS | 8 | N | O | I | CFC | 1.3 | 1 | 0 | 0 | 2004-12-01 | 2008-12-01 | 2007-06-01 | 2010-01-01 |  |  | 75400 | 0 | 75400 | 9340 | 12.39% | 66060 | 0 | 13212 | 6786 | 0 | 840.6 | 5945.4 | 0 | After extended delays to pass legislation, Govt informed in Feb 08 that legislation has been approved by the Council of Ministers. As such, UNDP prodoc was signed and implementation commenced. Selection of international consultant resulted in delays, but mission finally took place in Dec 2008. Needs in equipment were re-assessed (in view of long time elapsed since project approval) and list of equipment was established. Launching of bids to take place 1Q 2009. | [13 empty] | 2004 | Investment
COM | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | CBI | SEV | 44 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-09-01 |  | 60000 | 0 | 60000 | 45000.41 | 75% | 14999.59 | 15000 | 14999.59 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | CBI | SEV | 50 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 |  | 2008-11-01 |  | 60000 | 0 | 60000 | 11520 | 19.2% | 48480 | 0 | 48480 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008 | [13 empty] | 2006 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CBI | PHA | 50 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 0 | 2007-11-01 |  | 2008-12-01 |  | 30000 | 0 | 30000 | 22000.4 | 73.33% | 7999.6 | 8000 | 7999.6 | 3900 | 0 | 2860.052 | 1039.948 | 1040 | Project completed in December 2008. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | CBI | PHA | 54 | TAS | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-08 | 2010-03-31 | 2010-03-31 |  |  | 70000 | 0 | 70000 | 50162.69 | 71.66% | 19837.31 | 15000 | 19837.31 | 9100 | 0 | 6521.1497 | 2578.8503 | 1950 | MOU signed with Country 1st payment made in August 2008 | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CBI | PHA | 56 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | CHD | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-05-02 | 1996-03-01 |  | 1998-05-01 | 1999-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | AFR | CHD | SEV | 25 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-22 | 2001-07-01 |  | 2004-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | -376 | 7800 | -376 | 0 | Project financially completed. | $ 0 plus $ 376 PSC returned to ExCom 49 | [12 empty] | 1998 | Non Investment
FIN | UNDP | Preparation of a project in refrigerant recovery/recycling and RMP preparation | Individual | AFR | CHD | REF | 27 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | CHD | REF | 29 | TAS | 4 | A | O | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 198252 | -36260 | 161992 | 161992 | 100% | 0 | 0 | 0 | 25773 | -4714 | 21059 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNEP | Refrigerant management plan: Training the trainers of refrigeration technicians in good service practices | Individual | AFR | CHD | REF | 29 | TRA | 5 | A | O | I | CFC | 5.1 | 5.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-04 |  | 2002-08-01 | 2003-11-01 | 80125 | 0 | 80125 | 80125 | 100% | 0 | 0 | 0 | 10416.25 | 0 | 10416.25 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Training programme for customs officers | Individual | AFR | CHD | REF | 29 | TRA | 6 | A | O | I | CFC | 4.8 | 4.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-04 |  | 2002-08-01 | 2003-11-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [5 empty] | 2002-10-02 | [7 empty] | 1999 | Non Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | CHD | REF | 29 | TAS | 7 | A | O | I | No_ODP | 1 | 1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-07-01 | 2005-10-01 | 15455 | -4669 | 10786 | 10786 | 100% | 0 | 0 | 0 | 2009 | -607 | 1402 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | CHD | REF | 37 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-07-01 |  | 2002-12-01 | 2005-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
ONG | UNDP | Incentive programme for commercial/industrial end-user sector | RMP-Component | AFR | CHD | REF | 38 | TAS | 9 | N | O | I | CFC | 6 | 4 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 | 2009-12-01 |  |  | 184416 | 0 | 184416 | 148318 | 80.43% | 36098 | 0 | 14439.2 | 23974 | 0 | 19281.34 | 4692.66 | 0 | Although for political reasons activities have been disrupted, final payments to 6 end users were authorized in Dec 08. One of the initial recipients (Palais du 15) has apparently suffered heavy war damages and at this stage it is not sure if this application will proceed. 2 new applications were received and evaluated late 2008 and a series of final applications is expected early 2009, mainly from users in the regions. | [13 empty] | 2002 | Non-Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | CHD | SEV | 44 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000.16 | 100% | -0.16 | 0 | -0.16 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CHD | PHA | 48 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-01-01 |  | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project completed in January 2008 | [13 empty] | 2006 | Non Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | CHD | PHA | 48 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2006 | Investment
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | CHD | SEV | 50 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-07 | 2008-11-01 |  | 2008-12-01 |  | 60000 | 0 | 60000 | 59999.65 | 100% | 0.35 | 0 | 0.35 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | CHD | PHA | 53 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 | 2009-03-01 |  |  | 94000 | 0 | 94000 | 91024.55 | 96.83% | 2975.45 | 1000 | 2975.45 | 12220 | 0 | 11833.1915 | 386.8085 | 130 | Training of 30 technicians trainers organized in August 2008 | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CHD | PHA | 53 | INV | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-01-01 |  |  | 92000 | 0 | 92000 | 0 | 0% | 92000 | 0 | 18400 | 8280 | 0 | 0 | 8280 | 0 | Consultant mission carried out end 2008 to agree on best way forward. Given situation in country (both political and as result of move of the local UNDP offices) bidding process to purchase equipment, tools and refrigerant internationally was initiated by MPU NY. Contracts relative to strengthening of training centers have been prepared and are ready for implementation once equipment arrives in country (Est. 1st quarter 2009). Second tranche expected at 57th ExCom. | [13 empty] | 2007 | Investment | 5.2 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CHD | PHA | 55 | PRP | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for Signature | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CHD | SEV | 56 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-31 | 2010-12-31 |  |  | 60000 | 0 | 60000 | 12040 | 20.07% | 47960 | 35985 | 47960 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | IBRD | Country programme preparation | Individual | LAC | CHI | SEV | 04 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 121166 | -115333 | 5833 | 5833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Demonstration programme for service centre technicians on CFC-11 venting and leakage from refrigerators during operation and servicing | Individual | LAC | CHI | REF | 06 | DEM | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | CHI | SEV | 06 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -134385 | 57493 | 57493 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of the Technology Conversion Financing Programme (Tecfin) | Individual | LAC | CHI | MUS | 07 | INV | 4 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  | 1998-07-01 | 2000-03-01 | 69548 | -69548 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Part of $1,206,000 line-of-grant project. Funding returnd at the 30th ExCom. |  |  | 1997-04-30 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (approved at the 7th ExCom meeting) |  | LAC | CHI | SEV | 12 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30208 | 2849 | 33057 | 33057 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | Canada | Bromosorb technology in commodity fumigation | Individual | LAC | CHI | FUM | 15 | DEM | 6 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1997-04-01 | 1997-04-01 | 300000 | 17000 | 317000 | 317000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 1996-12-01 | [10 empty] | 1994 | Non-Inv.
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | CHI | SEV | 09 | PRP | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 82890 | -10881 | 72009 | 72009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Establishment of the Ozone Team | Individual | LAC | CHI | SEV | 07 | INS | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-10-01 | 1996-11-01 | 213000.03 | -2093 | 210907.03 | 210906.86 | 100% | 0.17 | 0.17 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-31 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Ozone seal programme | Individual | LAC | CHI | SEV | 07 | TAS | 9 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1993-06-01 |  | 1996-06-01 | 1996-06-01 | 8000 | -600 | 7400 | 7400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-06-30 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Public awareness programme | Individual | LAC | CHI | SEV | 07 | TAS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-06-01 | 1996-07-01 | 378000 | -5932 | 372068 | 372067.8 | 100% | 0.2 | 0.2 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-07-31 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of a sector specific training programme | Individual | LAC | CHI | SEV | 07 | TRA | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1996-01-01 | 1996-06-01 |  | 1997-10-01 | 1998-12-01 | 111000 | -14033 | 96967 | 96967 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-06-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | CHI | SEV | 16 | PRP | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-12-01 |  | 1995-12-31 | 1995-12-31 | 130312 | 0 | 130312 | 130312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | CHI | SEV | 18 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-03-01 | 1997-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Funds committed in CY96 were disbursed in CY97. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Montreal Protocol implementation programme - phase II | Individual | LAC | CHI | MUS | 19 | INV | 14 | N | O | I | CFC | 400 | 216 | 0 | 0 | 1996-05-01 | 1998-12-01 | 2000-05-01 |  | 2004-12-01 | 2007-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 130000 | 0 | 130000 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. |  |  | 1997-12-31 | 2000-05-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | Demonstration mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | CHI | REF | 19 | DEM | 15 | A | O | I | CFC | 10 | 10 | 0 |  | 1996-05-01 | 1996-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-10-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-12-01
FIN | IBRD | Institutional strengthening II | Individual | LAC | CHI | SEV | 20 | INS | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-10-01 |  | 1998-10-01 | 1998-10-01 | 113500 | 0 | 113500 | 113500 | 100% | 0 | 0 |  | 14755 | 0 | 14755 | 0 | 0 | Completed |  |  | 1998-10-31 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | CHI | SEV | 04 | PRP | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 162736 | -134936 | 27800 | 27800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Retrofit of freezing chambers at Frigorent Frigorifico Sociedad Limitada | Individual | LAC | CHI | REF | 07 | INV | 18 | N | O | I | CFC | 0.03 | 0.03 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-09-01 |  | 1996-10-01 | 1996-10-01 | 20166.36 | 0 | 20166.36 | 20166.36 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-31 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Frigocar | Individual | LAC | CHI | FOA | 07 | INV | 19 | N | O | I | CFC | 0.6 | 0.6 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-10-01 |  | 1996-10-01 | 1996-10-01 | 15784 | 0 | 15784 | 15784 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Foam project |  |  | 1996-10-31 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Kifafi | Individual | LAC | CHI | FOA | 07 | INV | 20 | N | O | I | CFC | 0.9 | 0.8 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFCs at Mimet | Individual | LAC | CHI | REF | 07 | INV | 21 | N | O | I | CFC | 47.8 | 47.8 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1996-12-01 |  | 1996-12-01 | 1997-01-01 | 93671.85 | 0 | 93671.85 | 93671.85 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-23 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and recycling programme at Central De Servicios Tecnicos (CST) | Individual | LAC | CHI | REF | 07 | TAS | 22 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1997-03-01 |  | 1996-11-01 | 1997-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Polimin | Individual | LAC | CHI | FOA | 07 | INV | 23 | N | O | I | CFC | 0.3 | 0.28 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 9120 | 0 | 9120 | 9120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-28 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of ODS at Supermercado Gran Avenida | Individual | LAC | CHI | REF | 07 | INV | 24 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Vicuna McKenna | Individual | LAC | CHI | REF | 07 | INV | 25 | N | O | I | CFC | 0.64 | 0.05 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 5558 | 0 | 5558 | 5558 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Macul | Individual | LAC | CHI | REF | 07 | INV | 26 | N | O | I | CFC | 0.4 | 0.08 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 2505 | 0 | 2505 | 2505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Plaza Egana | Individual | LAC | CHI | REF | 07 | INV | 27 | N | O | I | CFC | 0.32 | 0.03 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 3300 | 0 | 3300 | 3300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC phase out at Himmer & Himmer | Individual | LAC | CHI | FOA | 07 | INV | 28 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC phase out at SAAM, S.A. | Individual | LAC | CHI | FOA | 07 | INV | 29 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from Inventory |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Instapanel (IPAC) | Individual | LAC | CHI | FOA | 07 | INV | 30 | N | O | I | CFC | 64.2 | 64.2 | 0 | 0 | 1992-06-01 | 1997-02-01 | 1997-03-01 |  | 1996-12-01 | 1997-02-01 | 131606.92 | 0 | 131606.92 | 131606.92 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-16 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Inversiones Overjuna (Metalcargo) | Individual | LAC | CHI | FOA | 07 | INV | 31 | N | O | I | CFC | 0.2 | 0.2 | 0 | 0 | 1992-06-01 | 1996-12-01 | 1997-03-01 |  | 1996-12-01 | 1996-12-01 | 4740 | 0 | 4740 | 4740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-01-31 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project for soil fumigation in nurseries and seed beds for apples and kiwis | Individual | LAC | CHI | FUM | 24 | PRP | 32 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 2000-07-01 | 2003-12-01 | 25000 | -11504 | 13496 | 13496 | 100% | 0 | 0 | 0 | 3250 | -1496 | 1754 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation in the methyl bromide sector for tomatoes |  | LAC | CHI | FUM | 24 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the Phase II auction scheme |  | LAC | CHI | SEV | 25 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-30 | 1999-08-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Newly approved. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment applications for tomatoes and peppers | Individual | LAC | CHI | FUM | 25 | DEM | 35 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2006-12-01 | 2007-06-01 | 348130 | -73.55 | 348056.45 | 348056.45 | 100% | 0 | 0 |  | 45256.9 | -9.57 | 45247.33 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of the whole umbrella project in Jun 07. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Ozone protection and institutional strengthening project (renewal) | Individual | LAC | CHI | SEV | 25 | INS | 36 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-12-01 | 2000-12-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Montreal Protocol implementation programme (Phase II, second tranche) | Individual | LAC | CHI | MUS | 26 | INV | 37 | N | O | I | CFC | 270 | 202.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2004-12-01 | 2007-06-01 | 2800000 | -1512624 | 1287376 | 1287376 | 100% | 0 | 0 |  | 318000 | -166389 | 151611 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Extension of institutional strengthening project |  | LAC | CHI | SEV | 38 | INS | 52 | N | T | I | CFC | 15.42 | 15.42 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 | 186550 | 0 | 186550 | 186550 | 100% | 0 | 0 |  | 46800 | 0 | 46800 | 0 | 0 | Phase V of the IS project completed. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | Canada | Refrigerant management plan formulation project | Individual | LAC | CHI | REF | 27 | TAS | 138 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-10-01 | 2001-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. RMP was submitted to the 35th EXCOM and has been approved. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | IBRD | Preparation of investment project in the methyl bromide sector |  | LAC | CHI | FUM | 30 | PRP | 139 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of a project in the aerosol (sterilants) subsector | Individual | LAC | CHI | ARS | 30 | PRP | 140 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | CHI | FUM | 30 | TAS | 141 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -8217 | 16783 | 16783 | 100% | 0 | 0 | 0 | 3250 | -1068.21 | 2181.79 | 0 | 0 | Project financially completed. | $8,217 plus $1,068 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | IBRD | Renewal of institutional strengthening |  | LAC | CHI | SEV | 32 | INS | 142 | N | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2003-01-01 | 2003-01-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | NOU completed the IS tranche with work on several activities: the RMP, methyl bromide demo. project, sterilization project, and methyl bromide phase out in the tree sub-sector. New IS approved at the 38th ExCom. | [13 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | UNDP | Demonstration and phase-out project for methyl bromide soil fumigation for fruit tree production and replant | One-off-Phaseout | LAC | CHI | FUM | 32 | INV | 143 | N | O | I | MeBr | 76.2 | 76.2 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2006-06-01 |  | 2007-12-01 |  | 805000 | 0 | 805000 | 804709 | 99.96% | 291 | 0 | 232.8 | 98550 | 0 | 98514.3751 | 35.6249 | 0 | Completed in 2007. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the sterilants sector | Individual | LAC | CHI | STE | 33 | PRP | 144 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | IBRD | Project preparation for 2 projects in the methyl bromide sector |  | LAC | CHI | FUM | 33 | PRP | 145 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2002-09-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | The proposal is being prepare by the Bank and the INIA | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
ONG | UNEP | Implementation of the RMP: enabling a control and regulatory network | Individual | LAC | CHI | REF | 35 | TAS | 146 | A | O | I |  | 18.4 | 0 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2002-09-01 | 2009-06-01 |  |  | 111400 | 0 | 111400 | 111049.45 | 99.69% | 350.55 | 0 | 350.55 | 14482 | 0 | 14436.4285 | 45.5715 | 0 | A workshop on prevention of ODS illegal traffic has been jointly formulated between CONAMA and the National Customs Service, the entity responsible for the ODS quota and control systems. It is expected that the workshop will be held in July 2009 and will complete the first set of training courses to customs officers, providing them with tools to develop a risk assessment approach to prevent ODS illegal trade. | [13 empty] | 2001 | Non Investment
ONG | Canada | Implementation of the RMP: recovery and recycling programme | RMP | LAC | CHI | REF | 35 | TAS | 147 | A | O | I | CFC | 88 |  | 0 |  | 2001-12-01 | 2006-08-06 | 2005-04-01 | 2009-02-01 |  |  | 531620 | 0 | 531620 | 526620 | 99.06% | 5000 |  | 5000 | 53162 | 0 | 52057 | 1105 |  | 1st set of R&R equipment was delivered to Chile in April 2007. 2nd set of equipment delivered in May 2008. All equipment has been distributed, is in use and training has been completed. Monitoring of use of equipment was completed in early 2009. Project completed in Feb. 2009 and last payment to Chile was made in April 2009. |  | 2001 | [11 empty] | 2001 | Non-Inv.
ONG | UNEP | Implementation of the RMP: end-users and public awareness programme | Individual | LAC | CHI | REF | 35 | TAS | 148 | A | O | I |  | 28.5 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 | 2009-06-01 |  |  | 172000 | 0 | 172000 | 108750.66 | 63.23% | 63249.34 | 59253.5 | 63249.34 | 22360 | 0 | 14137.5858 | 8222.4142 | 7702.955 | A new agreement was signed to conclude outreach activities, this time by creating an interactive exhibition on ODS, the effects over the ozone layer and the effects of high radiation levels over human beings and the environment. The exhibit officially opened on October 15th. First disbursement will be issued in order to pay a maintenance service for three years, which is the life expectancy of the exhibit. Promoting materials are currently being designed and will be distributed amongst school teachers and students. Under a second agreement signed between amongst UNEP, CONAMA and UNDP, further outreach activities will be carried out, including the creation of signs and flyers about UV radiation and human protection measures, which will be distributed and set in the beaches along the center and north part of the country. In addition, an awareness campaign on Metered Dose Inhalers (MDIs) is also considered. Through this activity, the general public will be advised on the alternatives for almost all CFC-MDIs preventing further funding for a special strategy to eliminate CFC-based MDIs. | [13 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring, evaluation and reporting of the activities in the RMP | Individual | LAC | CHI | REF | 35 | TAS | 149 | A | O | I |  | 8.6 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 | 2009-06-01 |  |  | 52000 | 0 | 52000 | 29999.9 | 57.69% | 22000.1 | 20798.5 | 22000.1 | 6760 | 0 | 3899.987 | 2860.013 | 2703.805 | A new agreement was signed between UNEP, CONAMA and UNDP, which includes several activities on RMP monitoring and compliance, such as a social assessment of the RMP stakeholders (customs officers, importers, technicans and students, amongst others). It is expected that the activity will be completed by June 2009. | [13 empty] | 2001 | Non Investment
FIN | Canada | Implementation of the RMP: training programme for technicians and establishment of refrigeration standards | RMP | LAC | CHI | REF | 35 | TRA | 150 | A | O | I |  | 43 | 43 | 0 |  | 2001-12-01 | 2002-09-01 | 2004-12-01 |  | 2006-12-06 | 2007-05-01 | 260000 | 0 | 260000 | 260000 | 100% | 0 |  | 0 | 33800 | 0 | 33800 | 0 |  | Refrigeration equipment purchased and distributed to training centres. 1650 technicians trained. Code/standard of good practices completed in July 2005. Retrofit demonstration strategy developed and demonstrations completed in 2006. |  | 2001 | [11 empty] | 2001 | Non-Inv.
FIN | UNDP | Terminal conversion of ethylene oxide/CFC-12 mixtures to alternative non-ozone depleting technologies in 26 hospitals | Individual | LAC | CHI | STE | 35 | INV | 151 | A | O | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2005-12-01 | 2007-03-01 | 412741 | -113 | 412628 | 412628 | 100% | 0 | 0 | 0 | 53656 | -15 | 53641 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | IBRD | Preparation of a national halon bank |  | LAC | CHI | HAL | 39 | PRP | 152 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Proposal will be submitted to the 42nd ExCom Meeting. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Formulation of solvent sectoral phase-out plan | Individual | LAC | CHI | SOL | 39 | PRP | 153 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
ONG | UNDP | Technical assistance to phase-out ozone depleting solvents | Individual | LAC | CHI | SOL | 41 | TAS | 154 | N | O | I | CFC/TCA/CTC | 17.1 | 15 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2005-12-01 | 2009-10-01 |  |  | 245690 | 0 | 245690 | 172912 | 70.38% | 72778 | 4114 | 29111.2 | 22112 | 0 | 15562.0096 | 6549.9904 | 370.2583 | During 2008, the conversion of the production processes of 7 enterprises which used TCA and CFC-113 was finalized. Due to the need for testing new formulations within the specific applications of their clients, companies requested 2 samples of alternate solvents. Regarding chemical and analytical laboratories, 10 received technical assistance to eliminate the use of CBT. Of these, 5 have completed conversion of their analytical techniques to non- ODS alternatives, 2 eliminated the analytical techniques with ODS and 3 are testing alternative solvents, with samples provided through the project. | [13 empty] | 2003 | Non-Investment
COM | UNDP | Project preparation for the formulation of commercial refrigeration project | Individual | LAC | CHI | REF | 42 | PRP | 155 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2005-04-01 |  | 2006-12-01 |  | 32000 | 0 | 32000 | 31671 | 98.97% | 329 | 0 | 329 | 2400 | 0 | 2375.325 | 24.675 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment
TRF | IBRD | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Halon Banking | LAC | CHI | HAL | 42 | TAS | 156 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2006-10-01 |  |  | 2007-03-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Project transferred to UNDP in 2007 at the 51st ExCom. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Extension of the institutional strengthening project (phase VI, second year) | Individual | LAC | CHI | SEV | 45 | INS | 157 | N | T | I | CFC | 7.7 | 7.7 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase-out of all the remaining uses of methyl bromide in soil application pest control (first tranche) | Multiyear | LAC | CHI | FUM | 45 | INV | 158 | N | O | I | MBR | 1.3 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-07-01 | 691703 | -691703 | 0 | 0 |  | 0 | 0 |  | 51878 | -51878 | 0 | 0 | 0 | Project cancelled. | [13 empty] | 2005 | INV | 170 | 168.2 | 0 | 0 | Yes | No | No
FIN | IBRD | Extension of institutional strengthening (phase VI, year 2) | Individual | LAC | CHI | SEV | 47 | INS | 159 | N | T | D | CFC | 7.7 | 7.7 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2006-12-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | UNDP | Terminal umbrella project for phase-out of the use of CFC-11, CFC-12 and R-502 (CFC-115) in the manufacture of refrigeration equipment | Individual | LAC | CHI | REF | 48 | INV | 160 | N | O | I | CFC | 21.7 | 11 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2009-04-01 | 2010-03-01 |  |  | 282025 | 0 | 282025 | 142912 | 50.67% | 139113 | 0 | 27822.6 | 21152 | 0 | 10718.4633 | 10433.5367 | 0 | During 2008 the final verification and payment to the first company (Sinedelen) was completed. With regards to the group of small companies, the project beneficiaries were identified through a visit by the international expert and collection of updated information and follow up visits by the local consultant. They are still in the process of sending CONAMA a formal record of their economic activities for review. | [13 empty] | 2006 | Investment
ONG | UNDP | Terminal umbrella project for phase-out of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | CHI | FOA | 48 | INV | 161 | N | O | I | CFC | 51.4 | 16 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-09-01 | 2010-03-01 |  |  | 429962 | 0 | 429962 | 125755 | 29.25% | 304207 | 6250 | 60841.4 | 32247 | 0 | 9431.5811 | 22815.4189 | 468.7478 | During 2008 the Refricentro project was completed and the equipment needs for the second group of project beneficiaries were determined through one mission by the international expert and several meetings and follow up visits done by the local consultant. CONAMA also ran a background check on the economic activities of the beneficiaries in order to elaborate the necessary documents required for commitment. | [12 empty] | 2009-09-01 | 2006 | Investment
FIN | Canada | Project preparation for a national phase-out plan |  | LAC | CHI | PHA | 50 | PRP | 162 | A | O | I |  | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2008-04-08 | 2008-04-08 | 30000 | 0 | 30000 | 29998.64 | 100% | 1.36 |  | 0 | 3900 | 0 | 3900 | 0 |  | Chile servicing sector terminal phase-out plan preparation began in Oct 2007. Final proposal was completed by April 2008 and TPMP approved in July 2008. |  | 2006 | [11 empty] | 2006 | Non-Inv.
ONG | UNDP | Extension of institutional strengthening (phase VII) | Individual | LAC | CHI | SEV | 51 | INS | 163 | N | T | I | No_ODP | 15.4 | 13 | 0 | 0 | 2007-03-01 | 2007-04-01 | 2009-03-01 | 2009-06-01 |  |  | 186550 | 0 | 186550 | 139475 | 74.77% | 47075 | 0 | 18830 | 13991 | 0 | 10460.4381 | 3530.5619 | 0 | The System of "Maximum Import Volumes" and the "Registry of Importers and Exporters of ODS" is fully operational and under the responsibility of the National Customs Office. During 2008 the NOU also worked actively in the implementation of activities in the solvents (including laboratory uses), foams, methyl bromide and refrigeration sector, as well as in the data collection and reporting and public awareness. Phase 8 to be submitted at 57th ExCom meeting. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Individual | LAC | CHI | HAL | 51 | TAS | 164 | N | O | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 |  | 2009-09-01 | 2010-09-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 12000 | 4500 | 0 | 0 | 4500 | 0 | The project is still in early stages of implementation. Project document signed by CONAMA and sent to UNDP-Chile. The project is expected to speed up implementation in 2009. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CHI | PHA | 55 | PRP | 165 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-09-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | Approved at 55th ExCom. Maintained initial discussions with NOU on the activities to be included in the preparation of the HPMP. Project document sent to the country for signatures and launching event programmed for first half 2009. | [13 empty] | 2008 | Investment
ONG | Canada | Servicing sector terminal CFC phase-out plan (first tranche) | Multi-Year | LAC | CHI | PHA | 55 | INV | 166 | A | O | I | CFC | 0 |  | 0 |  | 2008-07-01 |  | 2011-07-01 | 2010-03-01 |  |  | 176000 | 0 | 176000 | 0 | 0% | 176000 |  | 120000 | 22880 | 0 | 0 | 22880 |  | Project activities initiated in February 2009. |  | 2008 | [11 empty] | 2008 | Investment | 124.3 | 47.9 |  |  | Yes
COM | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | CKI | REF | 44 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-07 |  | 14000 | 0 | 14000 | 10723 | 76.59% | 3277 | 0 | 3277 | 1820 | 0 | 1393.99 | 426.01 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | CKI | SEV | 44 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-10-01 | 2005-12-01 |  | 2007-01-01 |  | 15000 | 0 | 15000 | 9000 | 60% | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | CKI | REF | 44 | TAS | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2009-12-01 |  |  | 8000 | 0 | 8000 | 0 | 0% | 8000 | 0 | 8000 | 1040 | 0 | 0 | 1040 | 0 | UNEP is planning to organise the customs training workshop on April 2009 as per the established ODS regulation. The Environment Act (Ozone Layer Protection) Regulations 2008 was established under Section 70 of the Environment Act 2004. Cook Islands requires permit for import of HCFCs and methyl bromide (for QPS use) while prohibiting import of other ODS. Cook islands prohibits export of any ODS | [13 empty] | 2004 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase I) | Individual | ASP | CKI | SEV | 50 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-12-01 |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. UNEP is discussing the closure of the Regional Strategy and has requested SPREP to disburse all remaining IS funding to the country. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | CKI | SEV | 53 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008. First disbursement will start after country receive final payment of previous IS phase from SPREP. | [13 empty] | 2007 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CMR | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-06-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 3900 | 390 | 4290 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs officers) | Individual | AFR | CMR | SEV | 10 | TRA | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-08-01 | 1994-12-01 | 20200 | 0 | 20200 | 20200 | 100% | 0 | 0 | 0 | 2626 | 0 | 2626 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Establishment of the National Ozone Monitoring Commission | Individual | AFR | CMR | SEV | 11 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-10-01 | 1996-11-01 |  | 1997-10-01 | 1997-06-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 | 0 | 20930 | 0 | 20930 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNIDO | Preparation of an investment project proposal for phase out of CFCs at FAEM, Cameroun | Individual | AFR | CMR | REF | 11 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-04-01 | 1994-11-01 |  | 1995-02-01 | 1998-08-01 | 20000 | -2046 | 17954 | 17954 | 100% | 0 | 0 |  | 2600 | -270 | 2330 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC at FAEM.SA | Individual | AFR | CMR | REF | 13 | INV | 5 | A | O | I | CFC | 62 | 62 |  |  | 1994-07-01 | 1995-11-01 | 1996-01-01 |  | 1996-06-01 | 2000-04-01 | 1935860 | -42791 | 1893069 | 1893069 | 100% | 0 | 0 |  | 251662 | -5953 | 245709 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project for phasing out CFC-11 in the manufacture of domestic refrigerators, freezers and air-conditioners at Union Camerounaise | Individual | AFR | CMR | REF | 15 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Union Camerounaise d'Entreprise | Individual | AFR | CMR | REF | 18 | INV | 7 | A | O | I | CFC | 115.1 | 115.1 |  |  | 1995-11-01 | 1996-12-01 | 1997-03-01 |  | 2001-12-01 | 2002-12-01 | 1321400 | -20877 | 1300523 | 1300523 | 100% | 0 | 0 |  | 171782 | -2982 | 168800 | 0 | 0 | FIN
CLO | UNIDO | Project formulation of investment projects in the foam and refrigeration sectors | Individual | AFR | CMR | SEV | 21 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  |  | 2001-07-01 | 50000 | -23644 | 26356 | 26356 | 100% | 0 | 0 |  | 6500 | -3079 | 3421 | 0 | 0 | CLO
FIN | UNEP | Institutional strengthening renewal (Phase II) | Individual | AFR | CMR | SEV | 22 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-12-01 | 2000-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNIDO | Phasing out CFC-11 at Scimpos | Individual | AFR | CMR | FOA | 23 | INV | 10 | A | O | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-06-01 | 541350 | -491 | 540859 | 540859 | 100% | 0 | 0 |  | 70376 | -176 | 70200 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sonopol | Individual | AFR | CMR | FOA | 23 | INV | 11 | A | O | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-02-01 | 506310 | 0 | 506310 | 506310 | 100% | 0 | 0 |  | 65820 | -30 | 65790 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | AFR | CMR | REF | 24 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1999-02-01 | 1999-04-01 |  | 2001-04-01 | 2001-11-01 | 30000 | -65 | 29935 | 29935 | 100% | 0 | 0 |  | 3900 | -15 | 3885 | 0 | 0 | FIN |  |  |  | 1999-05-01
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | AFR | CMR | FUM | 24 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | AFR | CMR | SEV | 28 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | CMR | FUM | 34 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-07-01 |  | 2003-07-01 | 2004-07-01 | 25000 | -10136 | 14864 | 14864 | 100% | 0 | 0 | 0 | 3250 | -1317.68 | 1932.32 | 0 | 0 | Project financially completed. | $10,136 plus $1,318 PSC returned ExCom 44 | [12 empty] | 2001 | Non Investment
FIN | UNIDO | Two alternatives to the use of methyl bromide: non-soil cultivation techniques and application of various mixtures of other chemicals in low doses in tobacco | Individual | AFR | CMR | FUM | 25 | DEM | 16 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 160600 | -1033 | 159567 | 159567 | 100% | 0 | 0 |  | 20878 | -167 | 20711 | 0 | 0 | FIN
FIN | UNEP | Policy and technical assistance | Individual | AFR | CMR | SEV | 37 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-07-04 | 2007-07-01 | 10000 | -1994 | 8006 | 8006 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 1,994 returned to ExCom 50 | [12 empty] | 2002 | Non Investment
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration servicing sector (includes: training in good refrigerant management practices, training of customs officers, and recovery and recycling programme) | Individual | AFR | CMR | REF | 38 | TAS | 18 | A | O | I | CFC | 218.4 | 218.4 |  |  | 2002-11-01 | 2003-03-01 | 2007-12-01 |  | 2007-06-01 | 2008-05-01 | 522982 | 0 | 522982 | 522982 | 100% | 0 | 0 |  | 67528 | 0 | 67528 | 0 | 0 | Financial completion in May 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2002 | NON-INV
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | CMR | SEV | 41 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2004-12-04 | 2005-12-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNIDO | Project preparation in the refrigeration sector | Individual | AFR | CMR | REF | 43 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2004-07-01 | 2005-03-01 | 2005-07-01 |  | 2006-06-01 | 2006-12-01 | 25000 | -174 | 24826 | 24826 | 100% | 0 | 0 |  | 1875 | -13 | 1862 | 0 | 0 | FIN | [13 empty] | 2004 | NON-INV
FIN | UNEP | Extension of institutional strengthening project (second year of phase IV) | Individual | AFR | CMR | SEV | 44 | INS | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase V | Individual | AFR | CMR | SEV | 47 | INS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 139532 | 0 | 139532 | 139531.79 | 100% | 0.21 | 0 | 0.21 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | CMR | PHA | 49 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-08-01 | 2007-07-01 |  | 2006-11-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN | [13 empty] | 2006 | NON-INV
FIN | UNIDO | Project preparation for the total phase-out of methyl bromide in all remaining uses | Individual | AFR | CMR | FUM | 50 | PRP | 25 | A | O | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -60 | 29940 | 29940 | 100% | 0 | 0 |  | 2250 | -4 | 2246 | 0 | 0 | Financial completion in Jun 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2006 | NON-INV
COM | UNIDO | Terminal CFC/TCA phase-out management plan (first tranche) | Multi-Year | AFR | CMR | PHA | 50 | INV | 26 | A | O | I | CFC TCA | 12.7 | 12.7 |  |  | 2006-11-01 | 2007-01-01 | 2008-07-01 |  | 2008-12-01 |  | 600000 | 0 | 600000 | 538138 | 89.69% | 61862 | 61147 | 50000 | 45000 | 0 | 40360 | 4640 | 4586 | Project completed in Dec 2008. | [13 empty] | 2006 | INV | 125.7 | 125.7 |  |  | Yes | Yes | Yes
ONG | Italy | Total phase-out of methyl bromide used in stored commodities fumigation | Individual | AFR | CMR | FUM | 52 | INV | 27 | A | O | I | MBR | 14.5 |  | 0 |  | 2007-07-01 | 2008-04-01 | 2010-12-01 | 2010-12-01 |  |  | 259713 | 0 | 259713 | 63194 | 24.33% | 196519 |  | 40000 | 33763 | 0 | 8215.22 | 25547.78 | 0 | In 2008 the project implementation plan was agreed between UNIDO and the Government of Cameroon. Training activity has been organized for local companies and plant protection inspectors with main focus on the use of Phosphine and the application of the Integrated Pest Management. National consultant has been recruited to update the list of equipment to be purchased and distributed to the local companies. 2009 activities include purchasing the needed equipment; training activities addressed to local companies and local inspectors in order to complete the training needs; publication of awareness material to support and ensure the sustainability of the MB phase-out. |  | 2007 | [11 empty] | 2007 | Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | CMR | SEV | 53 | INS | 28 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 | 2009-11-01 |  |  | 139532 | 0 | 139532 | 30508.91 | 21.87% | 109023.09 | 109023.39 | 109023.09 | 0 | 0 | 0 | 0 | 0 | The NOU organised awareness raising activities including dissemination of awareness matierial and celebration of the Ozone day 2008. The NOU continued the monitoring of ODS phase through followup of completed projects . NOU organised survey to assiss the | [13 empty] | 2007 | Non Investment
ONG | UNIDO | Terminal CFC/TCA phase-out management plan (second tranche) | Multi-Year | AFR | CMR | PHA | 54 | INV | 29 | A | O | I | CFC CTC | 13.9 | 13.9 |  |  | 2008-04-01 |  | 2009-03-31 | 2009-12-01 |  |  | 105000 | 0 | 105000 | 0 | 0% | 105000 | 25516 | 25000 | 7875 | 0 | 0 | 7875 | 1914 | The solvent component phasing out TCA has been successfully completed during 2008. In addition training of technicians and custom officers as well as a supplementary R&R programme was implemented. For 2009 additional training of technicians focusing on drop-in technologies and alternatives, extension of customs training, enforcement of legislation and public awareness activities. | [13 empty] | 2008 | INV | 25.7 | 25.7 |  |  | Yes | N/A | N/A
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | CMR | PHA | 55 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 81 | 0.09529% | 84919 | 0 | 20000 | 6375 | 0 | 6 | 6369 | 0 | National consultant contracted, detailed national survey of HCFCs is on-going. NOU requested mission in Vienna at UNIDO HQ first semester of 2009, to agree the working plan HPMP development. Investigation to identify investment activities is carried out on foam industry. | The job description of the consultant addresses survey of the existing legislation and needed measures to extend its provisions on HCFCs. Intitial workshop is planned to take place end of June 2009, as the results of the survey will be subject of debates in identifying the country priorities | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | AFR | COI | SEV | 19 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1997-11-01 | 1999-01-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 | 0 | 4290 | 0 | 4290 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Establishment of the National Ozone Unit | Individual | AFR | COI | SEV | 23 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 2000-12-01 |  | 2001-03-01 | 2001-12-12 | 27800 | 0 | 27800 | 27800 | 100% | 0 | 0 | 0 | 3614 | 0 | 3614 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | COI | REF | 27 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2000-04-01 |  | 2001-09-01 | 2001-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | COI | SEV | 32 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 18533 | 0 | 18533 | 18533 | 100% | 0 | 0 | 0 | 2409.29 | 0 | 2409.29 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: monitoring of RMP implementation and its impact in the service and end-users sectors | Individual | AFR | COI | REF | 35 | TAS | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-07-01 | 2008-09-01 | 18000 | 0 | 18000 | 16000 | 88.89% | 2000 | 0 | 0 | 2340 | 0 | 2080 | 260 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 2001 | Non Investment
FIN | UNEP | Implementation of the RMP: assessment of the end-users subsector | Individual | AFR | COI | REF | 35 | TAS | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-06-01 | 2006-06-01 | 30000 | -2218 | 27782 | 27782 | 100% | 0 | 0 | 0 | 3900 | -289 | 3611.66 | -0.66 | 0 | Project financially completed. | $ 1,028 plus $ 134 PSC returned to ExCom 50. $ 1,190 plus $ 155 PSC returned to ExCom 52 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer and training of refrigeration service technicians | Individual | AFR | COI | REF | 35 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2002-07-01 |  | 2003-12-01 | 2005-12-01 | 51000 | -7093 | 43907 | 43907 | 100% | 0 | 0 | 0 | 6630 | -922.09 | 5707.91 | 0 | 0 | Project financially completed. | $7,093 plus $922 returned ExCom 46 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers in identification and control of ODS imports | Individual | AFR | COI | REF | 35 | TRA | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-07-01 |  | 2003-12-01 | 2006-06-01 | 39000 | -13386 | 25614 | 25614 | 100% | 0 | 0 | 0 | 5070 | -1740 | 3329.82 | 0.18 | 0 | Project financially completed. | $10,406 plus $ 1,353 PSC returned to ExCom 50. $ 2,980 plus $ 387 returned to ExCom 53 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | COI | SEV | 39 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24093 | 0 | 24093 | 24093 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | COI | SEV | 45 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2008-04-01 |  | 60000 | 0 | 60000 | 12000 | 20% | 48000 | 48000 | 48000 | 0 | 0 | 0 | 0 | 0 | Project completed in April 2008. NOU Congo organised training sessions and awareness raising campaigns in Brazzaville and Pointe Noire. The NOU Congo also collected data for reporting and coordinated preparation of TPMP with UNEP and UNIDO. | [13 empty] | 2005 | Non Investment
COM | UNEP | Project preparation for a TPMP | Individual | AFR | COI | PHA | 47 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2006-12-01 |  | 2008-12-01 |  | 30000 | 0 | 30000 | 29999.97 | 100% | 0.03 | 0 | 0.03 | 3900 | 0 | 3899.9961 | 0.0039 | 0 | Project completed in December 2008 | [13 empty] | 2005 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | COI | SEV | 51 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-05-07 | 2009-03-01 | 2009-04-01 |  |  | 60000 | 0 | 60000 | 59698.15 | 99.5% | 301.85 | 0 | 301.85 | 0 | 0 | 0 | 0 | 0 | NOU coordinated implementation of TPMP with UNEP and UNDP(approved in July 2007 | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | COI | PHA | 52 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-31 | 2009-07-31 |  |  | 77000 | 0 | 77000 | 70021.97 | 90.94% | 6978.03 | 1000 | 6978.03 | 10010 | 0 | 9102.8561 | 907.1439 | 130 | In April – May 2008, 30 Refrigerant practitioners have been trained and certified. 30 toolkits and 30 vacuum pumps have been purchased.In May 2008, 30 customs officers have been trained | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | COI | PHA | 52 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2009-07-01 | 2009-07-01 |  |  | 43000 | 0 | 43000 | 3893 | 9.053% | 39107 | 14652 | 15642.8 | 3870 | 0 | 350.37 | 3519.63 | 1318.68 | Consultant mission carried out end 2008. Bidding process for purchase of equipment has been completed and equipment, tools and refrigerant gas are expected to arrive in country 1st quarter 2009. Second tranche approved at 56th ExCom. | [13 empty] | 2007 | Investment | 0.4 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | COI | PHA | 55 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for Signature | [13 empty] | 2008
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | TAS | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 53000 | 0 | 53000 | 0 | 0% | 53000 | 0 | 53000 | 6890 | 0 | 0 | 6890 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | INV | 17 | N | O | I | CFC | 0.4 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 32000 | 0 | 32000 | 0 | 0% | 32000 | 0 | 12800 | 2880 | 0 | 0 | 2880 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COL | SEV | 12 | CPG | 1 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-03-01 |  | 1994-03-01 | 1994-03-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1994. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Institutional strengthening for implementation of the Montreal Protocol in Colombia | Individual | LAC | COL | SEV | 12 | INS | 2 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1997-03-01 |  | 1998-03-01 | 1999-12-01 | 317790 | 0 | 317790 | 317790 | 100% | 0 | 0 | 0 | 41313 | 0 | 41313 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 12 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Polarix Electrodomesticos, S.A. | Individual | LAC | COL | REF | 13 | INV | 4 | A | O | I | CFC | 63 | 63 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 844824 | -205206 | 639618 | 639618 | 100% | 0 | 0 | 0 | 109827 | -26677 | 83150 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Haceb, S.A. | Individual | LAC | COL | REF | 13 | INV | 5 | A | O | I | CFC | 69 | 69 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1386314 | -340578 | 1045736 | 1045736 | 100% | 0 | 0 | 0 | 180221 | -44275 | 135946 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Icasa, S.A. | Individual | LAC | COL | REF | 13 | INV | 6 | A | O | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1410680 | -358123 | 1052557 | 1052557 | 100% | 0 | 0 | 0 | 183388 | -46556 | 136832 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion of CFC-12 to HFC-134a compresors at Compresores Andinos, S.A. | Individual | LAC | COL | REF | 13 | INV | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 313650 | -23379 | 290271 | 290271 | 100% | 0 | 0 | 0 | 40774 | -3039 | 37735 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Corporacion de Electrodomesticos, S.A. (Corelsa) | Individual | LAC | COL | REF | 13 | INV | 8 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1999-07-01 | 2000-12-01 | 853432 | -166101 | 687331 | 687331 | 100% | 0 | 0 | 0 | 110946 | -21593 | 89353 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-02-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Manufacturas Ajover Ltda. | Individual | LAC | COL | FOA | 13 | INV | 9 | A | O | I | CFC | 190 | 190 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  | 1998-12-01 | 2001-12-01 | 691500 | -22425 | 669075 | 669075 | 100% | 0 | 0 | 0 | 89895 | -2915 | 86980 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1994 | Investment
CLO | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Industria Nacional de Desechables (Inaldes) | Individual | LAC | COL | FOA | 13 | INV | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  |  | 2001-12-01 | 380500 | -373255 | 7245 | 7245 | 100% | 0 | 0 | 0 | 49465 | -48523 | 942 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  |  |  | 2000-03-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industrias de Refrigeracion Comercial S.A. (Indufrial) | Individual | LAC | COL | REF | 15 | INV | 11 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-10-01 | 2000-12-01 | 442644 | -8866 | 433778 | 433778 | 100% | 0 | 0 | 0 | 57544 | -1153 | 56391 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Wonder S.A. | Individual | LAC | COL | REF | 15 | INV | 12 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-12-01 | 1999-12-01 | 251315 | 0 | 251315 | 251315 | 100% | 0 | 0 | 0 | 32671 | 0 | 32671 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1994 | Investment
FIN | USA | MAC emissions reduction demonstration programme |  | LAC | COL | REF | 15 | DEM | 13 | A | O | I | CFC | 11.5 | 12 | 0 |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1999-06-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. Project will be classified as financially complete at that time. |  | 1994
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrial Colombia S.A. (Inducol) | Individual | LAC | COL | REF | 15 | INV | 14 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2001-12-01 | 381548 | -36480 | 345068 | 345068 | 100% | 0 | 0 | 0 | 49601 | -4743 | 44858 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-02-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Friomix, S.A. | Individual | LAC | COL | REF | 17 | INV | 15 | A | O | D | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1999-01-01 | 1996-07-01 |  | 1999-02-01 | 2000-12-01 | 11146 | 0 | 11146 | 11146 | 100% | 0 | 0 | 0 | 1449 | 0 | 1449 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-02-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Westell Ltd. | Individual | LAC | COL | REF | 17 | INV | 16 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 227602 | -2 | 227600 | 227600 | 100% | 0 | 0 | 0 | 29588 | 0 | 29588 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 17 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-04-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1995 | Investment
FIN | UNEP | Training programme in good practices in refrigeration | Individual | LAC | COL | REF | 17 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 2003-12-01 | 2005-02-01 | 149100 | -42081.59 | 107018.41 | 107018 | 100% | 0.41 | 0 | 0.41 | 19383 | -5470.6067 | 13912.34 | 0.0533 | 0 | Project financially completed. | $42,082 plus $5471 returned ExCom 46 |  |  | 1999-12-01 | [9 empty] | 1995 | Non Investment
COM | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COL | REF | 17 | TAS | 19 | N | O | I | CFC | 111 | 111 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-07-01 |  | 1999-07-01 |  | 787030 | -5 | 787025 | 787025 | 100% | 0 | 0 | 0 | 102314 | -1 | 102313 | 0 | 0 | Completed in 1999. |  |  |  | 1999-06-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 18 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Unilemh Ltd. (Challenger) | Individual | LAC | COL | REF | 18 | INV | 21 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-07-01 | 155350 | -1561 | 153789 | 153789 | 100% | 0 | 0 | 0 | 20196 | -203 | 19993 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refrigeracion Supernordico Ltda. | Individual | LAC | COL | REF | 19 | INV | 22 | A | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2004-01-01 | 162500 | -1243 | 161257 | 161257 | 100% | 0 | 0 | 0 | 21125 | -162 | 20963 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1996 | Investment
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | LAC | COL | FUM | 21 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-08-01 |  | 1998-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN
FIN | IBRD | Project preparation identification |  | LAC | COL | SEV | 21 | PRP | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | COL | SEV | 24 | INS | 25 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 2000-03-01 |  | 2000-03-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2000. Financially completed in 2007. | [13 empty] | 1998 | Non-Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | COL | FOA | 24 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-07-01 | 1998-12-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | COL | REF | 24 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Daniel J. Fernandez and Cia. Ltd. | Individual | LAC | COL | FOA | 26 | INV | 28 | N | O | I | CFC | 22.2 | 22.2 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2002-02-01 | 2002-05-01 | 173822 | 0 | 173822 | 173822 | 100% | 0 | 0 |  | 22596.86 | 0 | 22596.86 | 0 | 0 | Project has been fully executed. PCR is being revised for submission. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Friotermica S.A. | Individual | LAC | COL | FOA | 26 | INV | 29 | N | O | I | CFC | 8.6 | 8.6 | 0 | 0 | 1998-11-01 | 2001-12-01 | 2000-12-01 |  | 2002-09-01 | 2002-12-01 | 67338 | 0 | 67338 | 67338 | 100% | 0 | 0 |  | 8753.94 | 0 | 8753.94 | 0 | 0 | Project fully completed during the last trimester of 2002. PCR is being prepared. | [5 empty] | 2002-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Indufrio | Individual | LAC | COL | FOA | 26 | INV | 30 | N | O | I | CFC | 9.65 | 9.65 | 0 | 0 | 1998-11-01 | 2002-12-01 | 2000-12-01 |  | 2003-10-01 | 2003-12-01 | 75548 | 0 | 75548 | 75548 | 100% | 0 | 0 |  | 9821.24 | 0 | 9821.24 | 0 | 0 | Project has been financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-22 technology at Master Cooler and Cia Ltd. | Individual | LAC | COL | FOA | 26 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70862 | -70862 | 0 | 0 |  | 0 | 0 |  | 9212.06 | -9212 | 0 | 0.06 | 0.06 | Project cancelled and funds returned at the 35th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in banana growing at Cenibanano | Individual | LAC | COL | FUM | 26 | DEM | 32 | A | O | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2002-12-01 | 2003-06-01 | 123200 | -377 | 122823 | 122823 | 100% | 0 | 0 |  | 16016 | -74 | 15942 | 0 | 0 | FIN
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and solvent sectors |  | LAC | COL | SEV | 27 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Polares Ltda. | Individual | LAC | COL | REF | 28 | INV | 34 | N | O | I | CFC | 4.64 | 4.64 | 0 | 0 | 1999-07-01 | 2001-09-11 | 2001-08-01 |  | 2002-03-01 | 2002-06-01 | 58109 | 0 | 58109 | 58109 | 100% | 0 | 0 |  | 7554.17 | 0 | 7554.17 | 0 | 0 | Project has been fully executed. PCR being prepared. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Rojas Hnos., Ltda. | Individual | LAC | COL | FOA | 28 | INV | 35 | N | O | R | CFC | 8.2 | 8.2 | 0 | 0 | 1999-07-01 | 2001-08-30 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 64206 | 0 | 64206 | 64206 | 100% | 0 | 0 |  | 8346.78 | 0 | 8346.78 | 0 | 0 | The project is completed, equipment destroyed and funding disbursed. PCR is expected May 2002. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Manilit, S.A. | Individual | LAC | COL | FOA | 29 | INV | 36 | A | O | I | CFC | 15.4 | 15.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2004-01-01 | 62230 | -679 | 61551 | 61551 | 100% | 0 | 0 | 0 | 8090 | -88 | 8002 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Industrias Refridcol, Ltda. | Individual | LAC | COL | FOA | 29 | INV | 37 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-09-01 | 117450 | 0 | 117450 | 117450 | 100% | 0 | 0 | 0 | 15268 | 0 | 15268 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Dinalsa | Individual | LAC | COL | FOA | 29 | INV | 38 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78625 | 0 | 78625 | 78625 | 100% | 0 | 0 | 0 | 10221 | 0 | 10221 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises | Individual | LAC | COL | FOA | 29 | INV | 39 | N | O | I | CFC | 56.6 | 37.6 | 0 | 0 | 1999-11-01 | 2002-09-01 | 2002-06-01 |  | 2005-01-01 | 2005-08-01 | 584727 | -170557 | 414170 | 414170 | 100% | 0 | 0 |  | 74319.97 | -21678.14 | 52641.83 | 0 | 0 | Project is physically and financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration subsector |  | LAC | COL | REF | 30 | PRP | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [14 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | COL | FOA | 30 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Renewal of institutional strengthening: Phase 3 | Individual | LAC | COL | SEV | 30 | INS | 42 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2002-04-01 |  | 2003-05-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2000 | Non-Investment
FIN | IBRD | Project preparation in MACs and compressors project category |  | LAC | COL | REF | 30 | PRP | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [14 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Industrias Supernórdico | Individual | LAC | COL | REF | 28 | INV | 44 | N | O | I | CFC | 9.6 | 9.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-02-01 | 2002-06-01 | 128381 | 0 | 128381 | 128381 | 100% | 0 | 0 |  | 16689.53 | 0 | 16689.53 | 0 | 0 | Project has been fully executed. PCR has been prepared and is being evaluated. Actual phaseout as reported in the PCR and confirmed with enterprise, country and revised proposal. | [5 empty] | 2002-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 100% | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | Project is physically and financially completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COL | REF | 32 | TAS | 46 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2003-12-01 | 2005-10-01 | 40000 | -2578 | 37422 | 37422 | 100% | 0 | 0 | 0 | 5200 | -335 | 4865 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [7 empty] | 2003-01-01 | [5 empty] | 2000 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at Olaflex with a technical assistance programme covering 10 small customers | Individual | LAC | COL | FOA | 32 | INV | 47 | A | O | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2001-12-01 | 2003-10-01 | 191833 | 0 | 191833 | 191833 | 100% | 0 | 0 | 0 | 24938 | 0 | 24938 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion rom CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at 25 small enterprises centered around their systems house Espumlatex | Individual | LAC | COL | FOA | 32 | INV | 48 | A | O | I | CFC | 38.4 | 38.4 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2004-12-01 | 2004-12-01 | 332768 | 0 | 332768 | 332768 | 100% | 0 | 0 | 0 | 43260 | 0 | 43260 | 0 | 0 | Completed in 2004. Financially completed in 2004. | [13 empty] | 2000 | Investment
COM | UNDP | Retroactive funding for the conversion from CFC-11 to water-based technology in the manufacture of flexible molded and integral skin foam at Espumlatex-Promicolda | Individual | LAC | COL | FOA | 32 | INV | 49 | N | O | R | CFC | 11.5 | 11.5 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2001-05-01 |  | 82020 | 0 | 82020 | 82020 | 100% | 0 | 0 | 0 | 4921 | 0 | 4921 | 0 | 0 | Completed in 2001. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | COL | FOA | 33 | PRP | 50 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Thermo-coil, Calaires, Auto Aires, and Servi Aires | Individual | LAC | COL | REF | 34 | INV | 51 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-11-01 | 2003-12-01 | 1358647 | -13905 | 1344742 | 1344742.18 | 100% | -0.18 | -0.18 |  | 159451.17 | -1632 | 157819.3 | -0.13 | -0.13 | Project physically and financially completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | Canada | Training programme for customs officers | Individual | LAC | COL | REF | 35 | TRA | 52 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2004-07-01 |  | 2006-08-06 | 2006-08-06 | 106150 | 0 | 106150 | 106150 | 100% | 0 |  | 0 | 13799 | 0 | 13799 | 0 |  | 300 customs officers trained and monitoring and evaluation completed by June 2005. However, one final activity, reproduction of training manual was completed only by August 2006. PCR submitted in 2006. |  | 2000 | [11 empty] | 2001 | Non-Inv.
FIN | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 100% | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | COL | REF | 36 | PRP | 54 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2004-06-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | COL | FOA | 36 | PRP | 55 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Country programme update | Individual | LAC | COL | SEV | 36 | CPG | 56 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-10-01 |  | 2004-06-01 | 2005-11-01 | 30000 | -415 | 29585 | 29585 | 100% | 0 | 0 | 0 | 3900 | -54 | 3846 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Non-Investment
FIN | IBRD | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 enterprises | Individual | LAC | COL | REF | 38 | INV | 57 | N | O | I | CFC | 25.8 | 7.85 | 0 | 0 | 2002-11-01 | 2005-12-01 | 2004-12-01 |  | 2005-10-01 | 2005-12-01 | 211636 | -130071 | 81565 | 81565 | 100% | 0 | 0 |  | 27512.68 | -16909.24 | 10603.44 | 0 | 0 | Project is physically and financially completed. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | COL | FOA | 38 | INV | 58 | A | O | I | CFC | 123.2 | 123.2 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-04-01 | 840170 | 0 | 840170 | 840170 | 100% | 0 | 0 | 0 | 102419 | 0 | 102418.7 | 0.3 | 0 | Completed in 2006. Financially completed in 2008. | [13 empty] | 2002 | Investment
COM | UNDP | Renewal of the institutional strengthening (phase 4) | Individual | LAC | COL | SEV | 38 | INS | 59 | N | T | I | No_ODP | 22.8 | 22.8 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 |  | 275600 | 0 | 275600 | 275596 | 100% | 4 | 0 | 3.2 | 35828 | 0 | 35827.48 | 0.52 | 0 | Completed in 2005. | [13 empty] | 2002 | Non-Investment
COM | UNDP | National phase-out plan for Annex A (Group I and II) substances: first implementation programme | Multi-Year | LAC | COL | PHA | 41 | INV | 60 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2008-12-01 |  | 2146820 | 0 | 2146820 | 2131371 | 99.28% | 15449 | 15449 | 12359.2 | 161011 | 0 | 159852.3286 | 1158.6714 | 1158.6714 | Completed in 2008. National CFC Phase-out Plan . See 2008 progress in COL/PHA/55/INV/69 | [13 empty] | 2003 | Investment | 805.9 | 805.9 |  |  | Yes | Yes | yes
COM | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | COL | SEV | 45 | INS | 61 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-12-01 |  | 275600 | 0 | 275600 | 275586 | 99.99% | 14 | 0 | 11.2 | 20670 | 0 | 20668.95 | 1.05 | 0 | Completed in 2007. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | COL | SEV | 45 | TAS | 62 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 |  | 68807 | 0 | 68807 | 58536 | 85.07% | 10271 | 0 | 8216.8 | 6193 | 0 | 5268.5548 | 924.4452 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
ONG | UNDP | National phase-out plan for Annex A (Group I and II) substances: second implementation programme | Multi-Year | LAC | COL | PHA | 47 | INV | 63 | N | O | I | CFC | 805.8 | 726 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2009-12-01 |  |  | 2353180 | 0 | 2353180 | 0 | 0% | 2353180 | 2955 | 941272 | 176488 | 0 | 0 | 176488 | 221.6244 | The program for eliminating the use of CFCs in the manufacturing sector of commercial refrigeration was completed with the participation of 16 companies. 1383 technicians were certified by the SENA in the Labor Competency Standards for the Environmental Management of Refrigerants and 85 beneficiaries have received R&R equipment. Progress was made in expanding work to 19 regional departments and regions, with the main purpose of implementing the NPP in the regions with the highest consumption of ODS. | [13 empty] | 2005 | Investment | 631.25 |  |  |  | Latest | Latest | Latest
TRF | IBRD | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 47 | INV | 64 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 |  |  | 2006-04-01 | 114480 | -114480 | 0 | 0 |  | 0 | 0 |  | 10303 | -10303 | 0 | 0 | 0 | All project funds and support costs were transferred to UNDP at 48th Meeting. | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | COL | REF | 47 | DEM | 65 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2010-12-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 0 | 200000 | 75000 | 0 | 0 | 75000 | 0 | Co-financing secured from GEF through a PIF. Associated MSP formulated but did not obtain approval in 2008, it is expected that it received GEF CEO approval in 2009. | [13 empty] | 2005 | Non-Investment
ONG | UNDP | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 48 | INV | 66 | N | O | I | CTC | 2 | 0 | 0 | 0 | 2006-04-01 |  | 2007-12-01 | 2010-03-01 |  |  | 114480 | 0 | 114480 | 0 | 0% | 114480 | 0 | 22896 | 10303 | 0 | 0 | 10303 | 0 | Verification of all existing lab uses completed and it was determined that all of them have ODS free alternatives and all these analytical uses can be replaced. Therefore a series of three workshops was prepared for Feb-09 to assist the users to replace their techniques . With regards to PRODESAL, the company was being merged to a Mexican company and all projects were put on hold. However the merge was suspended and the project was reactivated. PRODESAL prepared an updated timetable for the implementation of the proposed conversion to be completed by 2010, keeping in mind that total phase out must occur in 2009. Disbursements to be reflected in 2009. | [13 empty] | 2006 | Investment
ONG | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COL | SEV | 52 | INS | 67 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-10-01 | 2010-01-01 |  |  | 275600 | 0 | 275600 | 134403 | 48.77% | 141197 | 0 | 28239.4 | 20670 | 0 | 10080.225 | 10589.775 | 0 | Since the project began in the year 2006, country continues in compliance, reports have been prepared and sent timely, a total of 3500 technicians have been certified in the environmental management of refrigerants. Also during the year 2008 through a national consultancy, a guideline for the proper handling of hydrocarbons as a coolant as well as a training course was developed for SENA. A diffusion strategy was also initiated for the transition towards the use of CFC-free MDIs, and the approval of the project "Technical assistance to Colombia for the elimination of Methyl Bromide", amounting to $ 40,000, was obtained. | [13 empty] | 2007 | Non-Investment
COM | UNDP | Project preparation for a MDI investment project | Individual | LAC | COL | ARS | 54 | PRP | 68 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-12-01 |  | 30000 | 0 | 30000 | 1000 | 3.333% | 29000 | 19522 | 29000 | 2250 | 0 | 75 | 2175 | 1464.15 | Completed in 2008. International expert recruited. Mission to company completed, information collected and discussions on products to be replaced and production line needs completed. Project formulated, submitted and approved at the 56th Excom Meeting. Final payment to expert to be done in 2009. | [13 empty] | 2008 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COL | PHA | 55 | PRP | 69 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-12-01 |  |  | 173750 | 0 | 173750 | 0 | 0% | 173750 | 0 | 173750 | 13031 | 0 | 0 | 13031 | 0 | Approved at 55th ExCom. Maintained initial discussions with NOU on the activities to be included in the preparation of the HPMP. Launching event programmed for February 2009 | [13 empty] | 2008 | Investment
ONG | UNIDO | Technical assistance in the methyl bromide sector | Individual | LAC | COL | FUM | 55 | TAS | 70 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2010-07-01 | 2010-07-01 |  |  | 40000 | 0 | 40000 | 3985 | 9.963% | 36015 | 0 | 36000 | 3600 | 0 | 359 | 3241 | 0 | In December 2008, an international consultant was recruited to work on the alternatives in cooperation with a national agro institute. After completion of the national survey, awareness raising activities will be organized. | [13 empty] | 2008 | NON-INV
ONG | UNDP | Phase-out of CFC in the manufacturing of MDIs | Individual | LAC | COL | ARS | 56 | INV | 71 | N | O | I | CFC | 7.4 | 0 | 0 | 0 | 2008-11-01 |  | 2011-11-01 | 2011-11-01 |  |  | 409359 | 0 | 409359 | 0 | 0% | 409359 | 0 | 81871.8 | 30701 | 0 | 0 | 30701 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNDP | ODS reconnaissance study | Individual | LAC | COS | SEV | 04 | TAS | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 20000 | 3422 | 23422 | 23422 | 100% | 0 | 0 | 0 | 2600 | 445 | 3045 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COS | SEV | 06 | CPG | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1992-09-01 |  | 1992-09-01 | 1997-12-01 | 20000 | 2909 | 22909 | 22909 | 100% | 0 | 0 | 0 | 2600 | 378 | 2978 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | COS | SEV | 08 | INS | 3 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-08-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 213160 | 0 | 213160 | 213160 | 100% | 0 | 0 | 0 | 27711 | 0 | 27711 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COS | REF | 08 | TAS | 4 | A | O | I | CFC | 37.1 | 37.1 | 0 | 0 | 1992-10-01 | 1997-01-01 | 1998-09-01 |  | 2000-06-01 | 2004-03-01 | 88000 | 233693 | 321693 | 321693 | 100% | 0 | 0 | 0 | 11440 | 30380 | 41820 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  |  |  | 1999-08-01 | [9 empty] | 1992 | Investment
FIN | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 08 | TRA | 5 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 100% | 0 | 0 | 0 | 2746 | 0 | 2746 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Seminar/workshop in the solvent sector | Individual | LAC | COS | SOL | 08 | TRA | 6 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | -3219 | 17901 | 17901 | 100% | 0 | 0 | 0 | 2746 | -418 | 2328 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Assistance in project preparation | Individual | LAC | COS | SEV | 08 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-05-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [13 empty] | 1992 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Atlas Eléctrica S.A. | Individual | LAC | COS | REF | 18 | INV | 8 | A | O | D | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-04-01 |  | 1998-05-01 | 1999-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | COS | REF | 19 | DEM | 9 | A | O | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 2000-05-01 | 2000-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery are planned for May 2000. |  | 1995 | 1997-12-01
FIN | UNDP | Renewal of institutional strengthening project (Phase II) | Individual | LAC | COS | SEV | 21 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1999-02-01 |  | 1999-02-01 | 2000-12-01 | 108087 | 0 | 108087 | 108087 | 100% | 0 | 0 | 0 | 14051 | 0 | 14051 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Non-Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | LAC | COS | SEV | 21 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-04-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration subsector | Individual | LAC | COS | REF | 24 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 100% | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 100% | 0 | 0 | 0 | 25155 | -15 | 25140 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol (Phase III) | Individual | LAC | COS | SEV | 27 | INS | 16 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-04-01 |  | 2001-12-01 | 2005-11-01 | 108087 | -2519 | 105568 | 105568 | 100% | 0 | 0 | 0 | 14051 | -327 | 13724 | 0 | 0 | Completed in 2001. Financially completed in 2005. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Omega, S.A. | Individual | LAC | COS | REF | 27 | INV | 17 | A | O | I | CFC | 4.3 | 4.3 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 159883 | 0 | 159883 | 159883 | 100% | 0 | 0 | 0 | 20785 | 0 | 20785 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Wimmer Hnos., S.A. | Individual | LAC | COS | REF | 27 | INV | 18 | A | O | I | CFC | 4.6 | 4.6 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 186217 | 0 | 186217 | 186217 | 100% | 0 | 0 | 0 | 24208 | 0 | 24208 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Hermanos González, S.A. | Individual | LAC | COS | REF | 27 | INV | 19 | A | O | I | CFC | 4.4 | 4.4 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-04-01 | 185168 | 0 | 185168 | 185168 | 100% | 0 | 0 | 0 | 24072 | 0 | 24072 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
CLO | UNDP | Phaseout of CFC-11and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Quena S.A. | Individual | LAC | COS | REF | 27 | INV | 20 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  |  | 2002-11-01 | 219430 | -111322 | 108108 | 108108 | 100% | 0 | 0 | 0 | 28526 | -14472 | 14054 | 0 | 0 | Canceled in 2002. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-25 | 2000-12-01 |  | 2001-09-25 | 2001-09-01 | 30000 | -19257 | 10743 | 10743.0998 | 100% | -0.099788 |  | 0 | 1500 | -963 | 537.155 | -0.15499 |  | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 100% | 0 | 0 | 0 | 3250 | -1253.07 | 1996.93 | 0 | 0 | Project financially completed. | $9,639 plus $1,253 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
COM | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COS | REF | 32 | TAS | 23 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2005-12-01 |  | 40000 | 0 | 40000 | 25358 | 63.4% | 14642 | 0 | 11713.6 | 5200 | 0 | 3296.54 | 1903.46 | 0 | Completed in 2005. | [7 empty] | 2003-01-01 | [5 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | COS | FUM | 33 | PRP | 24 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
COM | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (first tranche) | Multi-Year | LAC | COS | FUM | 35 | INV | 25 | N | O | I | MeBr | 84.4 | 84.4 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2002-12-01 |  | 2005-07-01 |  | 1211321 | 0 | 1211321 | 1211321 | 100% | 0 | 0 | 0 | 143245 | 0 | 143245 | 0 | 0 | Completed in 2005. | [8 empty] | 2004-07-01 |  |  |  |  | 2001 | Investment | 426.9 | 426.9 |  |  | Yes | Yes | yes
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | COS | SEV | 35 | INS | 26 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2004-12-01 | 2007-06-01 | 108087 | -3863 | 104224 | 104224 | 100% | 0 | 0 | 0 | 14051 | -502 | 13548.8 | 0.2 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Non-Investment
COM | UNDP | Implementation of the RMP: incentive programme for the commercial, industrial, and fishing fleet refrigeration end-user sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 27 | N | O | I | CFC | 67.5 | 67.5 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 |  | 200000 | 0 | 200000 | 198988 | 99.49% | 1012 | 0 | 809.6 | 18000 | 0 | 17908.92 | 91.08 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
COM | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 28 | N | O | I | CFC | 60.8 | 60.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 |  | 180000 | 0 | 180000 | 179483 | 99.71% | 517 | 0 | 413.6 | 16200 | 0 | 16153.47 | 46.53 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
COM | UNDP | Implementation of the RMP: technical assistance for certification and licensing of refrigeration technicians | RMP-Component | LAC | COS | REF | 41 | TRA | 29 | N | O | I | CFC | 33.8 | 33.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 |  | 100000 | 0 | 100000 | 99203 | 99.2% | 797 | 0 | 637.6 | 9000 | 0 | 8928.27 | 71.73 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
COM | UNDP | Implementation of the RMP: technical assistance for training of customs officers | RMP-Component | LAC | COS | REF | 41 | TRA | 30 | N | O | I | CFC | 30.4 | 30.4 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 |  | 90000 | 0 | 90000 | 88996 | 98.88% | 1004 | 0 | 803.2 | 8100 | 0 | 8009.64 | 90.36 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
COM | UNDP | Implementation of the RMP: ensuring the effectiveness of all the project proposed with the RMP project | RMP-Component | LAC | COS | REF | 41 | TAS | 31 | N | O | I | CFC | 20.3 | 20.3 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 |  | 60000 | 0 | 60000 | 57314 | 95.52% | 2686 | 0 | 2148.8 | 5400 | 0 | 5158.26 | 241.74 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | COS | SEV | 41 | INS | 32 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 140513 | 0 | 140513 | 139737 | 99.45% | 776 | 0 | 0 | 10538 | 0 | 10479.8026 | 58.1974 | 0 | Completed in 2006. Financially Completed in 2008. | [13 empty] | 2003 | Non-Investment
COM | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranches II and III) | Multi-Year | LAC | COS | FUM | 43 | INV | 33 | N | O | I | MeBr | 130.8 | 130.8 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 |  | 1938114 | 0 | 1938114 | 1938114 | 100% | 0 | 0 | 0 | 145359 | 0 | 145359 | 0 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment | 358.5 | 358.5 |  |  | Yes | Yes | yes
COM | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COS | SEV | 47 | INS | 34 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2008-12-01 |  | 2008-02-01 |  | 140513 | 0 | 140513 | 138068 | 98.26% | 2445 | 0 | 1956 | 10538 | 0 | 10354.6333 | 183.3667 | 0 | Completed in 2008. IS activities for 2008 described under subsequent phase that started activities in early 2008. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | COS | PHA | 48 | PRP | 35 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-07-01 |  | 30000 | 0 | 30000 | 27621 | 92.07% | 2379 | 0 | 2379 | 2250 | 0 | 2071.575 | 178.425 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranche IV) | Multi-Year | LAC | COS | FUM | 49 | INV | 36 | N | O | I | MeBr | 63.6 | 0 | 0 | 0 | 2006-07-01 | 2008-01-01 | 2008-12-01 | 2010-02-01 |  |  | 969057 | 0 | 969057 | 429596 | 44.33% | 539461 | 0 | 107892.2 | 72679 | 0 | 32219.5781 | 40459.4219 | 0 | Training activities of Melon growers, technicians and workers continued in 2008. Investment activities continued to reduce the dependence of MB. Meteorological events in 2007 (end) and 2008 affected the effectiveness of some new alternatives, and the project is focusing on finding long term alternatives. | [13 empty] | 2006 | Investment | 338.1 |  |  |  | Latest | Latest | Latest
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | COS | PHA | 52 | INV | 37 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 |  | 2008-12-01 |  | 200000 | 0 | 200000 | 193245 | 96.62% | 6755 | 0 | 5404 | 15000 | 0 | 14493.375 | 506.625 | 0 | Completed in 2008. Project Document signed and Project Coordinator hired. Phase II of the reconversion programme in Fishery sector continued (including technical assistance and training for technicians). Several seminars for Customs officials took place, and no illegal imports detected. Formal training programme at technical institutions in place thanks to support from TPMP. | [13 empty] | 2007 | Investment | 37.5 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Extension of institutional strengthening project (phase VII) | Individual | LAC | COS | SEV | 53 | INS | 38 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 | 2009-11-01 |  |  | 140513 | 0 | 140513 | 60420 | 43% | 80093 | 0 | 32037.2 | 10538 | 0 | 4531.2958 | 6006.7042 | 0 | IS project is being implemented according to the plan. ODS Licensing system is operating well. Awareness raising and celebration of National Ozone Day in 2008 with high level participation. Continuous support to the implementation of TPMP and MB projects. The country is expected to achieve cero import of CFC by the end of 2009. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COS | PHA | 55 | PRP | 39 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | Local and international consultants have been identified. The inception workshop is expected to take place in early 2009. | [13 empty] | 2008 | Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-year | LAC | COS | PHA | 55 | INV | 40 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-07-01 | 2010-07-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 40000 | 15000 | 0 | 0 | 15000 | 0 | See activities described in COS 37. | [13 empty] | 2008 | Investment
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | CPR | SEV | 04 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 184000 | -167746 | 16254 | 16254 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Technical assistance for Guandong aerosols investment project and investigation of non-ODS filling technology and LPG purification | Individual | ASP | CPR | ARS | 06 | TAS | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1996-12-01 | 1998-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Feasibility study on the application of HFC-134a technology in MACs and CFC recycling | RMP-Component | ASP | CPR | REF | 06 | TAS | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-09-01 |  | 1993-12-01 | 1997-12-01 | 40000 | -15164 | 24836 | 24836 | 100% | 0 | 0 | 0 | 5200 | -1971 | 3229 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Establishment of a training programme for centrifugal chillers and domestic refrigeration service managers and technicians | RMP-Component | ASP | CPR | REF | 06 | TRA | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Establishment of a quality control testing plant for using CFC-12 substitute technology in refrigeration and rigid foams | Individual | ASP | CPR | REF | 06 | TAS | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-12-01 | 1993-12-01 |  | 1998-06-01 | 1998-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1998. Financially completed in 1998. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 06 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 100% | 0 | 0 | 0 | 8450 | -648 | 7802 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Pre-feasibility study to phase-out CFC-113 in electronic cleaning in four production lines | Individual | ASP | CPR | SOL | 06 | TAS | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-10-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 40000 | 1829 | 41829 | 41829 | 100% | 0 | 0 | 0 | 5200 | 238 | 5438 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical study on halons usage and applications of halons substitutes | Individual | ASP | CPR | HAL | 06 | TAS | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 40000 | 3345 | 43345 | 43345 | 100% | 0 | 0 | 0 | 5200 | 435 | 5635 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening, including establishment of the Information Clearing-house at NEPA | Individual | ASP | CPR | SEV | 06 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-04-01 | 1995-02-01 |  | 1996-12-01 | 1998-12-01 | 150000 | 299997 | 449997 | 449997 | 100% | 0 | 0 | 0 | 19500 | 39000 | 58500 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | CPR | SEV | 06 | CPG | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Country programme studies | Individual | ASP | CPR | SEV | 06 | CPG | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 180000 | -73841 | 106159 | 106159 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Technical assistance for CFC-11 substitute technology in rigid polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Shanghai CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 14 | N | O | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-09-01 | 1997-06-01 | 1900000 | 409000 | 2309000 | 2309000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhejiang foam plant conversion to butane | Individual | ASP | CPR | FOA | 07 | INV | 15 | N | O | I | CFC | 400 | 400 | 0 | 0 | 1992-06-01 | 1994-04-01 | 1994-06-01 |  | 1995-09-01 | 1996-09-01 | 1042000 | -49000 | 993000 | 993000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. ODP phaseout target reached. |  |  | 1995-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project I: 50% CFC foam | Individual | ASP | CPR | FOA | 07 | INV | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1994-06-01 |  | 1996-06-01 | 1996-06-01 | 645000 | 0 | 645000 | 645000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Fully disbursed and distributed to 50% foam projects that were approved a year after this approval. Disbursed amount appeared to exceed grant by $1000. Thru Dec. 37/14, the Bank was able to return the $1,000 to the MLF in the context of the reconciliation of the Accounts of the Fund at the 38th ExCom (Dec. 38/9). |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhejiang halon extinguisher conversion | Individual | ASP | CPR | HAL | 07 | INV | 17 | N | O | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1993-12-01 |  | 1996-11-01 | 1996-01-01 | 797000 | -67000 | 730000 | 730000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and ODP phaseout target reached. The project was commissioned in May 97. |  |  | 1996-11-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Beijing ABC powder production project | Individual | ASP | CPR | HAL | 07 | INV | 18 | N | O | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1996-04-01 | 1996-08-01 | 403000 | 527000 | 930000 | 930000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Dalian precision parts cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 19 | N | O | I | CFC | 69 | 69 | 0 | 0 | 1992-06-01 | 1996-04-01 | 1994-06-01 |  | 1996-09-01 | 1998-12-01 | 495000 | -34191 | 460809 | 460809 | 100% | 0 | 0 | 0 | 64350 | -4445 | 59905 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1992 | Investment
FIN | UNDP | Dandong electronic tuner aqueous cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 20 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1992-06-01 | 1995-07-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 495000 | -663 | 494337 | 494337 | 100% | 0 | 0 | 0 | 64350 | -86 | 64264 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1992 | Investment
FIN | IBRD | Project preparation advance for developing components of Project I (1992) |  | ASP | CPR | SEV | 07 | PRP | 21 | N | O | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PPA I is complete. These funds were used to support implementation of the China ODS Projects I and II. No money was allocated, however $600,000 from ODS II and $900,000 from ODS I was used. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Technical assistance for the Beijing Household Electric Appliances Research Institute (Bheari) | Individual | ASP | CPR | FOA | 09 | TAS | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-10-01 | 1995-06-01 |  | 1998-10-01 | 2003-07-01 | 0 | 444945 | 444945 | 444945 | 100% | 0 | 0 | 0 | 0 | 57843 | 57843 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1993 | Non-Investment
FIN | IBRD | Tianjin CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 23 | N | O | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-03-01 | 1997-06-01 | 2500000 | 270000 | 2770000 | 2770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Pre-investment activities for Nanjing compressor and four refrigeration projects |  | ASP | CPR | REF | 08 | PRP | 24 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. In addition, a sector-wide phaseout strategy for the commercial refrigeration and air-conditioning sector was prepared (12,500 tons of CFCs). | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Support for the FESCAST international conference |  | ASP | CPR | SEV | 08 | TRA | 25 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1994-04-01 | 87000 | 96000 | 183000 | 183000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $96,000 credited against 1993 contributions (11th Meeting).
FIN | UNDP | Survey and assessment of small CFC plant conversion possibilities | Individual | ASP | CPR | SEV | 09 | TAS | 26 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-05-01 | 1994-03-01 |  | 1998-10-01 | 2001-12-01 | 90000 | -701 | 89299 | 89299 | 100% | 0 | 0 | 0 | 11700 | -91 | 11609 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Import and promotion of applications for CFC substitute chemicals in the refrigeration sector in Southern China | RMP-Component | ASP | CPR | REF | 09 | TAS | 27 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1994-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1993 | Non-Investment
FIN | UNIDO | Elimination of ODS used in the production of compressors for household refrigerators at Jiaxipera Compressor Co. Ltd. | Individual | ASP | CPR | REF | 09 | PRP | 28 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-06-01 | 1996-03-01 |  | 1994-12-01 | 1998-08-01 | 36000 | 4294 | 40294 | 40294 | 100% | 0 | 0 |  | 4680 | 558 | 5238 | 0 | 0 | FIN
FIN | IBRD | Financial agent fee for the implementation of approved projects (two aerosols, two foams, two halons) | Individual | ASP | CPR | SEV | 09 | TAS | 29 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1996-12-01 | 1996-12-01 | 185000 | 0 | 185000 | 185000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The FA completed appraisal reports for all subprojects and all have been cleared by the Bank. PPA I has been fully disbursed. ODS II was disbursed, and its accounts closed in 1997. Project completion report for ODS I& II completed. |  |  | 1996-12-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of investment projects | Individual | ASP | CPR | SEV | 09 | PRP | 30 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | CPR | SEV | 09 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 326000 | -133667 | 192333 | 192333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Tianjin conversion to CFC-free technology in the manufacture of flexible polyurethane foam | Individual | ASP | CPR | FOA | 10 | INV | 32 | N | O | I | CFC | 180 | 180 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1994-09-01 |  | 1995-04-01 | 1998-12-01 | 1080000 | -41407 | 1038593 | 1038593 | 100% | 0 | 0 | 0 | 140400 | -5383 | 135017 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1a: model prototype development and testing) |  | ASP | CPR | REF | 10 | TAS | 33 | A | O | I |  | 0 |  | 0 |  | 1993-06-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 396110 | 0 | 396110 | 396110 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | IBRD | Production-sector pre-investment studies |  | ASP | CPR | PRO | 10 | PRP | 34 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-06-28 | 1994-06-01 |  | 1996-03-01 | 1996-03-01 | 240000 | 80000 | 320000 | 320000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete, including many proposals and six sector phaseout strategies. 26 foam projects, to be implemented by UNDP and the Bank, were prepared following first two workshops. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | CPR | SEV | 10 | PRP | 35 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 280000 | -131872 | 148128 | 148128 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC in cleaning operations at Nanjing Wire Works | Individual | ASP | CPR | SOL | 10 | INV | 36 | A | O | I | CFC | 8.8 | 8.8 | 0 | 0 | 1993-06-01 | 1996-08-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 409000 | -511 | 408489 | 408489 | 100% | 0 | 0 | 0 | 53170 | -66 | 53104 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at the Chengdu Qianfeng Radio Instrument Factory | Individual | ASP | CPR | SOL | 10 | INV | 37 | N | O | I | CFC | 7.2 | 7.2 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1995-12-01 |  | 1997-12-01 | 1999-12-01 | 394700 | -13224 | 381476 | 381476 | 100% | 0 | 0 | 0 | 51311 | -1719 | 49592 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1993 | Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | CPR | FOA | 10 | TAS | 38 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-05-01 | 1994-06-01 |  | 1997-07-01 | 2000-06-01 | 200000 | -574 | 199426 | 199426 | 100% | 0 | 0 | 0 | 26000 | -75 | 25925 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Revision of design standards for cold storage | RMP-Component | ASP | CPR | REF | 10 | TAS | 39 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-01-01 | 1994-09-01 |  | 1999-03-01 | 2000-12-01 | 200000 | -18764 | 181236 | 181236 | 100% | 0 | 0 | 0 | 26000 | -2439 | 23561 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-03-01 | [9 empty] | 1993 | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: current situation, revision of national codes, and education and training | Individual | ASP | CPR | HAL | 10 | TAS | 40 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1996-06-01 |  | 1998-09-01 | 2000-12-01 | 280000 | -24125 | 255875 | 255875 | 100% | 0 | 0 | 0 | 36400 | -3136 | 33264 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: transfer of technology on alternatives to halon fire protection systems | Individual | ASP | CPR | HAL | 10 | TAS | 41 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-11-01 | 1996-06-01 |  | 1999-06-01 | 2000-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-06-01 | [9 empty] | 1993 | Non-Investment
FIN | IBRD | Liming Research and development of polyol and blended polyol production techniques for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 42 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-01-01 | 1996-09-01 | 457000 | 0 | 457000 | 457000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1996-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Wuxi production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 43 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1995-06-01 |  | 1995-09-01 | 1997-05-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1995-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Chengde conversion to 50% reduced CFC foam in insulation panel and in-situ foaming formulations | Individual | ASP | CPR | FOA | 10 | INV | 44 | N | O | D | CFC | 32 | 50 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1997-06-01 |  | 1994-10-01 | 1996-09-01 | 163000 | 0 | 163000 | 163000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1995-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Dalian conversion to 50% CFC reduced foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 45 | N | O | D | CFC | 14 | 30 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1996-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Tianjin conversion to 50% reduced CFC foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 46 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 443000 | -443000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Transferred to UNDP. $443,000 credited to the MLF at 17th Meeting. |  |  | 1995-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Qindao Haier conversion to 50% reduced CFC foam in freezer cabinets | Individual | ASP | CPR | FOA | 10 | INV | 47 | N | O | D | CFC | 120 | 232 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1994-06-01 | 1997-06-01 | 476000 | 0 | 476000 | 476000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1994-08-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Henan Xinfei conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 48 | N | O | D | CFC | 103 | 250 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1994-10-01 | 1997-06-01 | 1042000 | 0 | 1042000 | 1042000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. Funding approved for final conversion to non-ODS. |  |  | 1996-11-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shangling conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 49 | N | O | I | CFC | 103 | 244.1 | 0 | 0 | 1993-06-01 | 1995-12-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 958000 | 0 | 958000 | 958000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1996-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shuangyan conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 50 | N | O | D | CFC | 28 | 63 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1993-06-01 | 1997-03-01 | 485000 | 0 | 485000 | 485000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1994-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shenyang production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 51 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-09-01 | 1997-06-01 |  | 1994-08-01 | 1996-12-01 | 165000 | 0 | 165000 | 165000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. By using the contingency fund, the factory went one step ahead to develop 100% CFC-free technology. |  |  | 1995-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | Canada | Activities in Sichuan Province | Individual | ASP | CPR | SEV | 11 | TRA | 52 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-10-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Workshop held in October 1993 and approved by retroactive funding in September 1994. |  | 1993 | 2000-01-01 | [10 empty] | 1993 | Non-Inv.
FIN | USA | Halon management resource manual |  | ASP | CPR | HAL | 11 | TAS | 53 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | UNDP | Conversion to CFC free technology in the manufacture of rigid PUF (spray) at Beijing Commercial Machinery Factory (BCMF) | Individual | ASP | CPR | FOA | 11 | INV | 54 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1998-12-01 | 2000-12-01 | 435000 | -91690 | 343310 | 343310 | 100% | 0 | 0 | 0 | 56550 | -11920 | 44630 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1993 | Investment
FIN | UNDP | Survey on policy and planning measures to promote recycling of CFC | RMP-Component | ASP | CPR | REF | 11 | TAS | 55 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-05-01 | 1994-11-01 |  | 1997-12-01 | 2000-12-01 | 100000 | -19358 | 80642 | 80642 | 100% | 0 | 0 | 0 | 13000 | -2517 | 10483 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1993 | Investment
FIN | UNDP | National product qualification and standards evaluation for non-ODS alternatives to CFC applications | Individual | ASP | CPR | SEV | 11 | TAS | 56 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-11-01 |  | 1998-03-01 | 2000-12-01 | 362500 | -29055 | 333445 | 333445 | 100% | 0 | 0 | 0 | 47125 | -3777 | 43348 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1993 | Non-Investment
FIN | USA | Halon-1211 recovery/recharge training workshops |  | ASP | CPR | HAL | 11 | TRA | 57 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 271000 | 0 | 271000 | 271000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 11 | PRP | 58 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | USA | Deployment of halon-1211 recovery/recharge machines |  | ASP | CPR | HAL | 12 | INV | 59 | A | O | I | HAL | 200 | 231 | 0 |  | 1994-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1996-06-01 | 735000 | 72000 | 807000 | 807000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Survey of production and consumption of methyl bromide in China | Individual | ASP | CPR | FUM | 12 | TAS | 60 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-03-01 |  | 1998-10-01 | 2001-12-01 | 87000 | -1791 | 85209 | 85209 | 100% | 0 | 0 | 0 | 11310 | -232 | 11078 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Cleaning applications deployment center for replication of ODS-free process across China | Individual | ASP | CPR | SOL | 12 | TAS | 61 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-03-01 | 1995-03-01 |  | 1998-05-01 | 2000-12-01 | 489400 | -66345 | 423055 | 423055 | 100% | 0 | 0 | 0 | 63622 | -8625 | 54997 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1994 | Non-Investment
FIN | IBRD | Preparation of projects ODS III (1994) |  | ASP | CPR | SEV | 12 | PRP | 62 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 660000 | -138768 | 521232 | 521232 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation of China ODS I (1994) |  | ASP | CPR | SEV | 12 | PRP | 63 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 79000 | -35235 | 43765 | 43765 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation of China ODS II (1994) |  | ASP | CPR | SEV | 12 | PRP | 64 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 110000 | 10949 | 120949 | 120949 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | ODS-free cleaning equipment manufacturing center for phasing out ODS consuming solvents across China | Individual | ASP | CPR | SOL | 12 | INV | 65 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1997-06-01 | 1996-03-01 |  | 1999-11-01 | 2002-07-01 | 524734 | -50707 | 474027 | 474027 | 100% | 0 | 0 | 0 | 68215 | -6592 | 61623 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Acquisition of local air compressors for halon recycling machines | Individual | ASP | CPR | HAL | 12 | INV | 66 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-12-01 | 1998-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
CLO | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Yanfeng | Individual | ASP | CPR | FOA | 13 | INV | 67 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1995-07-01 |  |  | 1995-07-01 | 670000 | -670000 | 0 | 0 |  | 0 | 0 | 0 | 87100 | -87100 | 0 | 0 | 0 | Canceled in 1995. | [13 empty] | 1994 | Investment
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-134a refrigerant with Tecumseh designed compressors at Hua Yi Electrical Appliances General Co. | Individual | ASP | CPR | REF | 13 | INV | 68 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-09-01 | 1368000 | 0 | 1368000 | 1368000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-152a refrigerant in conventional compressors at Wanbao Electrical Appliances Industrial Corporation | Individual | ASP | CPR | REF | 13 | INV | 69 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 1999-07-01 | 2002-09-01 | 1360000 | 0 | 1360000 | 1360000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1997-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Engineering assistance for conversion of refrigerator manufacture to a ternary blend refrigerant (MP-39) in conventional compressors at Shanghai Shuanglu Electrical Appliances Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 70 | N | O | I | CFC | 70 | 64.3 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1996-07-01 |  |  | 1998-09-01 | 1010000 | -82008 | 927992 | 927992 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to financial difficulties. Undisbursed balance of $82,007.65 has been returned to MLF at the 30th ExCom Meeting. Four charging machines are proposed to be transferred to the new Shanghai Shangling project. PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-152a/HCFC-22 blended refrigerant in conventional compressors at Chang Ling Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 71 | N | O | I | CFC | 70 | 70 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-09-01 | 1997-03-01 | 853000 | -10 | 852990 | 852990 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 26th ExCom. |  |  | 1997-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam at Shanghai No. 18 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 72 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-07-01 | 1996-09-01 | 1995-07-01 |  | 1998-09-01 | 1998-09-01 | 450000 | 0 | 450000 | 450000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 27th ExCom. |  |  | 1997-02-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-12 used in the manufacture of EPE foam sheet at Danshui Huaya Plastics Industries Co. Ltd. | Individual | ASP | CPR | FOA | 13 | INV | 73 | A | O | R | CFC | 160 | 160 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1995-04-01 | 1997-12-01 | 241000 | 0 | 241000 | 241000 | 100% | 0 | 0 | 0 | 31330 | 0 | 31330 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 used in the manufacture of rigid polyurethane foam at Tianjin Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 13 | INV | 74 | N | O | I | CFC | 130 | 130 | 0 | 0 | 1994-07-01 | 1998-11-01 | 1995-07-01 |  | 2001-08-01 | 2003-07-01 | 690000 | -431333 | 258667 | 258667 | 100% | 0 | 0 | 0 | 89700 | -56073 | 33627 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Shanghai No. 6 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 75 | N | O | I | CFC | 105 | 105 | 0 | 0 | 1994-07-01 | 1996-10-01 | 1995-07-01 |  | 1998-06-01 | 1998-12-01 | 687000 | -1292 | 685708 | 685708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 31th ExCom. |  |  | 1997-02-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Halon 1211 production closure at Tongxiang Chemical Fertilizer Factory | Individual | ASP | CPR | PRO | 13 | INV | 76 | N | O | I | HAL | 0 | 0 | 1200 | 1200 | 1994-07-01 | 1996-08-01 | 1995-01-01 |  | 1994-12-01 | 1996-08-01 | 838000 | -730880 | 107120 | 107120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom. |  |  | 1994-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for conversion of compressor manufacturing to HFC-134a rotary compressor designs at Shanghai Refrigerator Compressor Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 77 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-05-01 | 1997-06-01 | 1280000 | 0 | 1280000 | 1280000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCOM. |  |  | 1998-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-134a with rotary compressor at Shanghai Shangling General Refrigerator Factory | Individual | ASP | CPR | REF | 13 | INV | 78 | N | O | I | CFC | 108 | 108 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 2000-06-01 | 2002-09-01 | 1327000 | 0 | 1327000 | 1327000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998-01-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhongshan Fine Chemical Aerosol Filling Center CFC-12 substitution project | Individual | ASP | CPR | ARS | 13 | INV | 79 | N | O | I | CFC | 4067 | 4067 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-05-01 | 1998-10-01 | 1351360 | -319 | 1351041 | 1351041 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 29th ExCom. |  |  | 1998-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | Project preparation |  | ASP | CPR | HAL | 13 | PRP | 80 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1996-01-01 |  | 1997-12-01 | 1998-04-01 | 200000 | -68517 | 131483 | 131483 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. No further activities foreseen on this project with the approval of China's Halon Sector Strategy (23rd meeting). |  | 1994 | 1997-12-01
CLO | Canada | Feasibility study to establish a refrigerant conservation programme in Sichuan Province | Individual | ASP | CPR | REF | 14 | TAS | 81 | A | O | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  |  | 1997-06-01 | 58400 | -58400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | [10 empty] | 1994 | Non-Inv.
FIN | Canada | No-clean technology programme | Individual | ASP | CPR | SOL | 14 | TAS | 82 | A | O | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  | 1994-11-01 | 1995-09-01 | 51100 | 0 | 51100 | 51100 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | [10 empty] | 1994 | Non-Inv.
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Lanzhou Plastic Packing Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 83 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1997-08-01 | 1997-11-01 | 222100 | -37 | 222063 | 222063 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom in January 1999. |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Cangzhou No. 2 Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 84 | N | O | I | CFC | 140 | 140 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1998-11-01 | 1999-04-01 | 394000 | 0 | 394000 | 394000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the 30th ExCom. |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Beijing Foam Plastic General Factory | Individual | ASP | CPR | FOA | 15 | INV | 85 | N | O | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-11-01 | 1999-11-01 | 720000 | 0 | 720000 | 720000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted December 2000. |  |  | 1997-06-01 | 1999-05-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in manufacture of extruded polyethylene and polystyrene foam sheet at Zhengzhou Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 86 | N | O | I | CFC | 260 | 260 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 2003-04-01 | 2004-05-01 | 267100 | 0 | 267100 | 267100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 1997-03-01 | 1999-09-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shijiazhuang Plastic Cement General Factory | Individual | ASP | CPR | FOA | 15 | INV | 87 | A | O | I | CFC | 160 | 160 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 621000 | 0 | 621000 | 621000 | 100% | 0 | 0 | 0 | 80730 | 0 | 80730 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE foam tubing at Suzhou Plastic Works No. 7 | Individual | ASP | CPR | FOA | 15 | INV | 88 | A | O | I | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 358000 | -36690 | 321310 | 321310 | 100% | 0 | 0 | 0 | 46540 | -4770 | 41770 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Sino-Foreign Joint Stock Shenyang Shenrong Co. | Individual | ASP | CPR | FOA | 15 | INV | 89 | A | O | I | CFC | 48 | 48 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-05-01 | 2002-04-01 | 166700 | -1 | 166699 | 166699 | 100% | 0 | 0 | 0 | 21671 | 0 | 21671 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-06-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE foam sheet and netting at Feicheng Plastic Products Factory | Individual | ASP | CPR | FOA | 15 | INV | 90 | A | O | I | CFC | 150 | 150 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-04-01 | 2002-04-01 | 388000 | 0 | 388000 | 388000 | 100% | 0 | 0 | 0 | 50440 | 0 | 50440 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-04-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guangxing Plastics Products Co., Hubei | Individual | ASP | CPR | FOA | 15 | INV | 91 | A | O | I | CFC | 36 | 36 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shenzhen Shentie Plastics Tableware Products Company, Shenzhen | Individual | ASP | CPR | FOA | 15 | INV | 92 | A | O | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 345000 | 0 | 345000 | 345000 | 100% | 0 | 0 | 0 | 44850 | 0 | 44850 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE netting at Hebei Sixing Polypack Products Co. Ltd., Shijiazhuang | Individual | ASP | CPR | FOA | 15 | INV | 93 | A | O | I | CFC | 65 | 65 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 436000 | -183121 | 252879 | 252879 | 100% | 0 | 0 | 0 | 56680 | -23806 | 32874 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Beijing Yanxi | Individual | ASP | CPR | FOA | 15 | INV | 94 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 125000 | -31250 | 93750 | 93750 | 100% | 0 | 0 | 0 | 16250 | -4063 | 12187 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Faw-Trim | Individual | ASP | CPR | FOA | 15 | INV | 95 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of integral skin polyurethane foam at Hubei Auto Engineering | Individual | ASP | CPR | FOA | 15 | INV | 96 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Dalian No. 1 | Individual | ASP | CPR | FOA | 15 | INV | 97 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1998-12-01 |  |  | 2000-07-01 | 490000 | -457910 | 32090 | 32090 | 100% | 0 | 0 | 0 | 63700 | -59528 | 4172 | 0 | 0 | Canceled in 1999. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinfeng | Individual | ASP | CPR | FOA | 15 | INV | 98 | A | O | R | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 235340 | 0 | 235340 | 235340 | 100% | 0 | 0 | 0 | 30594 | 0 | 30594 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinan | Individual | ASP | CPR | FOA | 15 | INV | 99 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 337000 | 0 | 337000 | 337000 | 100% | 0 | 0 | 0 | 43810 | 0 | 43810 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guizhou Jinchang Plastics Products Co. Ltd. | Individual | ASP | CPR | FOA | 15 | INV | 100 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 390000 | -117155 | 272845 | 272845 | 100% | 0 | 0 | 0 | 50700 | -15230 | 35470 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Hailun Plastic Packaging Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 101 | A | O | I | CFC | 95 | 95 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 321000 | -2 | 320998 | 320998 | 100% | 0 | 0 | 0 | 41730 | 0 | 41730 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE/PS foam sheet at Shanghai Jianhua Electro-Mechanical and Mechanical Company | Individual | ASP | CPR | FOA | 15 | INV | 102 | A | O | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-11-01 | 2002-04-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-04-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Foshan No. 3 Plastic Factory | Individual | ASP | CPR | FOA | 15 | INV | 103 | A | O | I | CFC | 360 | 360 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 1065000 | -1 | 1064999 | 1064999 | 100% | 0 | 0 | 0 | 138450 | 0 | 138450 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNIDO | Conversion from halon 1211 to ABC dry powder and foam water spray at Nanjing Fire Fighting Equipment Factory | Individual | ASP | CPR | HAL | 15 | INV | 104 | A | O | I | HAL | 1110 | 1480 |  |  | 1994-12-01 | 1995-10-01 | 1996-12-01 |  | 1996-12-01 | 2000-12-01 | 496000 | 0 | 496000 | 496000 | 100% | 0 | 0 |  | 64480 | -53 | 64427 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 15 | PRP | 105 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-04-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 25000 | -8988 | 16012 | 16012 | 100% | 0 | 0 |  | 3250 | -1172 | 2078 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 15 | PRP | 106 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Conversion of medium sized semi-hermetic CFC-12 air conditioning compressor production to HCFC-22 at Beijing Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 15 | INV | 107 | N | O | I | CFC | 233 | 233 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1997-12-01 |  | 2000-08-01 | 2002-04-01 | 3098000 | -1000 | 3097000 | 3097000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-06-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) in Gaofeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 108 | N | O | I | CFC | 180 | 180 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-01-01 | 2002-09-01 | 458400 | 0 | 458400 | 458400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997-12-01 | 1999-05-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Hebei Dongfeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 109 | N | O | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  | 1999-05-01 | 1999-03-01 | 268600 | 0 | 268600 | 268600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to 30th ExCom. |  |  | 1997-12-01 | 1999-01-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium sized open-type CFC-12 refrigeration compressor production to HCFC-22 at Shanghai Refrigerating Machine Works (SRMW) | Individual | ASP | CPR | REF | 16 | INV | 110 | N | O | I | CFC | 162 | 162 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 1998-09-01 | 1999-09-01 | 2710000 | 0 | 2710000 | 2710000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the ExCom March 2000. |  |  | 1999-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small open-type CFC-12 refrigeration compressor production to HCFC-22 at Anhui Provincial Refrigerating Machinery Factory (APRMF) | Individual | ASP | CPR | REF | 16 | INV | 111 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 2002-07-01 | 2004-04-01 | 2224000 | 0 | 2224000 | 2224000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 1999-06-01 |  |  | 2001-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Jiangsu Taizhou Commercial Machinery Factory (JTCMF) | Individual | ASP | CPR | REF | 16 | INV | 112 | N | O | I | CFC | 285 | 285 | 0 | 0 | 1995-03-01 | 1996-10-01 | 1998-03-01 |  | 1999-12-01 | 2002-09-01 | 2797500 | 0 | 2797500 | 2797500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Nanjing Refrigerator General Works (NRGW) | Individual | ASP | CPR | REF | 16 | INV | 113 | N | O | I | CFC | 242 | 242 | 0 | 0 | 1995-03-01 | 1996-04-01 | 1998-03-01 |  | 1999-05-01 | 2002-04-01 | 2890000 | -27 | 2889973 | 2889973 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Production of small ammonia refrigerating compressor at Yantai Refrigerating Machinery Works (YRMW) | Individual | ASP | CPR | REF | 16 | INV | 114 | N | O | I | CFC | 240 | 240 | 0 | 0 | 1995-03-01 | 1996-12-01 | 1998-03-01 |  | 1999-05-01 | 2000-06-01 | 2874000 | 0 | 2874000 | 2874000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed.PCR and certificates were submitted to 30th ExCom Meeting. |  |  | 1999-06-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | Germany | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) | Individual | ASP | CPR | REF | 16 | INV | 115 | N | O | I | CFC | 174 | 174 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 1336918 | 0 | 1336918 | 1336918 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Oct 99 |  |  | 2000-01-01 | [10 empty] | 2002
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) |  | ASP | CPR | REF | 16 | INV | 116 | N | O | I | CFC | 29 |  | 0 |  | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 2000-05-01 | 2000-05-01 | 1643865 | 0 | 1643865 | 1643865 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Conversion of line to produce cyclopentane-152a/22 refrigerators completed, certified Aug96; CFCs eliminated. Final funding to follow verification of old equipment destruction, review of receipts, final safety certification, and initial production. |  | 1995 | 1997-07-01 |  | 1999-12-01
FIN | USA | MAC servicing demonstration |  | ASP | CPR | REF | 16 | DEM | 117 | A | O | I | CFC | 7 | 11.4 | 0 |  | 1995-03-01 | 1995-04-01 | 1995-03-01 |  | 1996-03-01 | 1996-03-01 | 172500 | -6667 | 165833 | 165833 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995
FIN | USA | Refrigeration management demonstration project preparation |  | ASP | CPR | REF | 16 | PRP | 118 | A | O | I |  | 0 |  | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 by hydrocarbon isobutane and cyclopentane at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 17 | INV | 119 | A | O | I | CFC | 360 | 360 |  |  | 1995-07-01 | 1996-03-01 | 1997-07-01 |  | 2003-12-01 | 2004-12-01 | 2790320 | 0 | 2790320 | 2790320 | 100% | 0 | 0 |  | 362742 | -1 | 362741 | 0 | 0 | FIN |  |  | 1998-06-01 | 1999-12-01
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | CPR | SEV | 16 | PRP | 120 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 103131 | 0 | 103131 | 103131 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Halon leak reduction demonstration |  | ASP | CPR | HAL | 16 | DEM | 121 | A | O | I | HAL | 221.7 | 74 | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-12-01 | 1998-06-01 | 90437 | 0 | 90437 | 90437 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Yifeng Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 17 | INV | 122 | N | O | I | CFC | 90 | 60 | 0 | 0 | 1995-07-01 | 1998-01-01 | 1997-01-01 |  | 1998-04-01 | 1998-08-01 | 214600 | 0 | 214600 | 214600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1998-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Guangdong Kelon Electrical Holding Company Ltd. | Individual | ASP | CPR | REF | 17 | INV | 123 | N | O | I | CFC | 767.2 | 767.2 | 0 | 0 | 1995-07-01 | 1997-04-01 | 1997-01-01 |  | 1999-06-01 | 2003-07-01 | 4483050 | -6913 | 4476137 | 4476137 | 100% | 0 | 0 | 0 | 582797 | -899 | 581898 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-06-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Changsha Zhongyi Group Corp. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 124 | A | O | I | CFC | 360.2 | 360.2 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 2000-09-01 | 2004-01-01 | 2961000 | -2311 | 2958689 | 2958689 | 100% | 0 | 0 | 0 | 384930 | -300 | 384630 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Cangzhou Foreign Trade Packaging Co. | Individual | ASP | CPR | FOA | 17 | INV | 125 | N | O | I | CFC | 75 | 75 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 450800 | -445 | 450355 | 450355 | 100% | 0 | 0 | 0 | 58604 | -58 | 58546 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Handan No. 7 | Individual | ASP | CPR | FOA | 17 | INV | 126 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 400950 | -446 | 400504 | 400504 | 100% | 0 | 0 | 0 | 52124 | -58 | 52066 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Joint Industrial Plastic Corporation, Buotou | Individual | ASP | CPR | FOA | 17 | INV | 127 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2001-05-01 | 604450 | -446 | 604004 | 604004 | 100% | 0 | 0 | 0 | 78579 | -58 | 78521 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 17 | PRP | 128 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-04-01 |  | 1996-03-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Shanghai Ek Chor General Machinery Co. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 129 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1996-01-01 | 1998-06-01 | 961000 | 0 | 961000 | 961000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1998-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | Denmark | Establishment of a CFC recycling centre at Zhejiang Donggyang Chemical Factory |  | ASP | CPR | REF | 17 | TAS | 130 | N | O | I |  | 20 |  |  |  | 1995-07-01 | 1996-10-01 | 1996-07-01 | 1998-12-01 | 1998-12-01 |  | 205000 | 0 | 205000 | 161053.25 | 78.56% | 43946.75 |  | 0 |  |  |  | 0 |  | Completed. Project Document signed in March 1996. Procurement comtract initialed in August 1996 but contract was not signed until 1997. Major delay caused by disagreement on contractual terms. Building modification work completed by enterprise in May 1998 and equipment delivered and installed in June 1998. A seminar for evaluation and dissemination of work experience was held 15-16 December 1998. All project activities were completed in December 1998. More than 50 tons of CFC has been recovered. A few tons of CFC had further been recycled at the reclaim station. |  |  | 1996-12-01
FIN | UNDP | Demonstration project (refrigeration - large food stores) | RMP-Component | ASP | CPR | REF | 17 | DEM | 131 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1997-06-01 | 2002-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1995 | Non-Investment
FIN | UNIDO | Project formulation of investment projects in the halon sector in the 3 fire equipment factories (Xiangshan, Xiangshan No. 1 and Dalian Jinzhou) and in domestic refrigeration sectors and solvents | Individual | ASP | CPR | SEV | 17 | PRP | 132 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 1998-12-01 | 2000-07-01 | 100000 | -193 | 99807 | 99807 | 100% | 0 | 0 |  | 13000 | -46 | 12954 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Workshop on domestic and commercial refrigerator compressor conversion | Individual | ASP | CPR | REF | 17 | TRA | 133 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1998-08-01 | 40000 | 237 | 40237 | 40237 | 100% | 0 | 0 |  | 5200 | 31 | 5231 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane products at Daimei | Individual | ASP | CPR | FOA | 17 | INV | 134 | N | O | I | CFC | 77 | 77 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-12-01 |  | 1998-12-01 | 2001-12-01 | 362600 | -43425 | 319175 | 319175 | 100% | 0 | 0 | 0 | 47138 | -5645 | 41493 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1995 | Investment
FIN | USA | Demonstration project (refrigeration - large food stores) |  | ASP | CPR | REF | 17 | DEM | 135 | A | O | I |  | 0 |  | 0 |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1998-01-01 | 1998-12-01 | 132000 | 26400 | 158400 | 158400 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-06-01
FIN | IBRD | Development of a cost effective sector based ODS phase out approach | Individual | ASP | CPR | SEV | 17 | TAS | 136 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-10-31 | 1996-12-01 |  | 1996-12-01 | 1996-12-01 | 350000 | -150000 | 200000 | 200000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | $100,000 transferred to PPA-V. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Liangzhu | Individual | ASP | CPR | FOA | 17 | INV | 137 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-08-01 | 2002-09-01 | 167800 | 0 | 167800 | 167800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted to ExCom. |  |  | 1997-12-01 | 1999-08-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zhenjiang No. 5 Plastic Factory | Individual | ASP | CPR | FOA | 17 | INV | 138 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  |  | 2001-03-01 | 276800 | -60003 | 216797 | 216797 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. Remaining amount of $60,000 has been returned to ExCom. |  |  | 1998-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS III (1995) |  | ASP | CPR | SEV | 16 | PRP | 139 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Processing of the third ODS Phaseout project for China has been completed. Grant agreement was signed in June 1995. $50,000 was transferred from PPA-IV (China) (CPR/SEV/16/PRP/217) to this project preparation (ODS III - China). Thus, $700,000 was disbursed under this activity. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Penglai Polyurethane Plastic Factory | Individual | ASP | CPR | FOA | 18 | INV | 140 | N | O | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-01-01 | 320583 | -83 | 320500 | 320500 | 100% | 0 | 0 |  | 41675.79 | -11 | 41665 | -0.21 | -0.21 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Tianjin Daqui Foam Plant | Individual | ASP | CPR | FOA | 18 | INV | 141 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 160000 | -60 | 159940 | 159940 | 100% | 0 | 0 | 0 | 20800 | -8 | 20792 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin and cold cured PUF moldings at Jiangxi Auto Engineering Plastic Plant | Individual | ASP | CPR | FOA | 18 | INV | 142 | N | O | I | CFC | 39 | 39 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 2001-03-01 | 2003-07-01 | 170000 | -6784 | 163216 | 163216 | 100% | 0 | 0 | 0 | 22100 | -882 | 21218 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Tianjin Gangda | Individual | ASP | CPR | FOA | 18 | INV | 143 | N | O | I | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1997-05-01 |  | 2000-10-01 | 2003-07-01 | 404250 | -1033 | 403217 | 403217 | 100% | 0 | 0 | 0 | 52553 | -134 | 52419 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNIDO | Formulation of investment projects in the tobacco sector | Individual | ASP | CPR | OTH | 18 | PRP | 144 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1996-11-01 |  | 1999-12-01 | 2002-06-01 | 50000 | -1233 | 48767 | 48767 | 100% | 0 | 0 |  | 6500 | -170 | 6330 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Conversion of compressor production for domestic refrigerators from CFC-12 to hydrocarbon refrigerant at Jiaxipera compressor factory | Individual | ASP | CPR | REF | 18 | INV | 145 | A | O | I | CFC | 96 | 96 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 1490000 | 0 | 1490000 | 1490000 | 100% | 0 | 0 |  | 193700 | 0 | 193700 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | IBRD | Conversion from CFC-11 foaming agent to cyclopentane at Chang Ling (Group) Co. Ltd. | Individual | ASP | CPR | FOA | 18 | INV | 146 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-12-01 | 1999-01-01 | 2062000 | 0 | 2062000 | 2062000 | 100% | 0 | 0 |  | 268060 | 0 | 268060 | 0 | 0 | Project completed; PCR submitted December 2000. |  |  | 1998-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at Hangzhou Huari Refrigerator Co. | Individual | ASP | CPR | REF | 18 | INV | 147 | A | O | I | CFC | 338 | 338 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 2827911 | -13884 | 2814027 | 2814027 | 100% | 0 | 0 |  | 367628 | -2384 | 365244 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Yueyang Hengli Air Conditioning Equipment Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 148 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 2000-02-01 | 1767961 | 0 | 1767961 | 1767961 | 100% | 0 | 0 |  | 229834.93 | 0 | 229834.93 | 0 | 0 | Project completed; PCR submitted to the 31th ExCom. |  |  | 1998-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Guangzhou Haohua Automobile Parts Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 149 | N | O | I |  | 0.65 | 0.65 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 2001-03-01 | 2001-07-08 | 2212039 | -202829 | 2009210 | 2009210.43 | 100% | -0.43 | -0.43 |  | 287565.07 | -25353.62 | 262211.45 | 0 | 0 | Project completed; Draft PCR is under review. |  |  | 1998-06-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Shanghai Automobile Air Conditioner Co. (SAAC) | Individual | ASP | CPR | REF | 18 | INV | 150 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1996-12-01 | 1997-03-01 | 1642330 | -30 | 1642300 | 1642300 | 100% | 0 | 0 |  | 213502.9 | -3.9 | 213499.15 | -0.15 | -0.15 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Formulation of investment projects in the refrigeration sector with particular attention to domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 18 | PRP | 151 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-10-01 | 2000-07-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Hunan Computer Factory | Individual | ASP | CPR | SOL | 18 | INV | 152 | A | O | R | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 1997-12-01 | 2000-12-01 | 104700 | -18343 | 86357 | 86357 | 100% | 0 | 0 | 0 | 13611 | -2385 | 11226 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 18 | PRP | 153 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 18 | PRP | 154 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Training workshop on safety aspects of CFC substitutes | Individual | ASP | CPR | SEV | 18 | TRA | 155 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1996-05-01 |  | 1996-05-01 | 1999-04-01 | 82400 | 0 | 82400 | 82400 | 100% | 0 | 0 | 0 | 10712 | 0 | 10712 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Hangzhou Plastic Foam Factory | Individual | ASP | CPR | FOA | 19 | INV | 156 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1997-11-01 |  | 1999-03-01 | 1999-08-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 41210 | 0 | 41210 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-06-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qingyang Chemical Corp. | Individual | ASP | CPR | FOA | 19 | INV | 157 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1996-05-01 | 1999-08-01 | 1997-11-01 |  | 2001-09-01 | 2002-10-01 | 362000 | 0 | 362000 | 362000 | 100% | 0 | 0 |  | 47060 | 0 | 47060 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-06-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Yinguang Chemical Group | Individual | ASP | CPR | FOA | 19 | INV | 158 | N | O | I | CFC | 85 | 85 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1999-05-01 | 2000-10-01 | 376000 | 0 | 376000 | 376000 | 100% | 0 | 0 |  | 48880 | 0 | 48880 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qinhuangdao No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 159 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-08-01 | 1998-10-01 | 370000 | 0 | 370000 | 370000 | 100% | 0 | 0 |  | 48100 | 0 | 48100 | 0 | 0 | Project completed. PCR will be submitted in January 2001. |  |  | 1999-06-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFCs in the manufacture of flexible slabstock PUF at Jinan Shiyan Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 160 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1996-05-01 | 1998-04-01 | 1997-05-01 |  | 1999-01-01 | 2001-11-23 | 209300 | 0 | 209300 | 209300.29 | 100% | -0.29 | -0.29 |  | 27209 | 0 | 27209.03 | -0.03 | -0.03 | Project completed; PCR submitted. |  |  | 1998-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Jiangsu Jintan Insulation Material Plant | Individual | ASP | CPR | FOA | 19 | INV | 161 | N | O | I | CFC | 12 | 12 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 66000 | -5638 | 60362 | 60362 | 100% | 0 | 0 | 0 | 8580 | -733 | 7847 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zibo No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 162 | N | O | I | CFC | 100 | 55 | 0 | 0 | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1999-01-01 | 2000-12-01 | 249000 | 0 | 249000 | 249000 | 100% | 0 | 0 |  | 32370 | 0 | 32370 | 0 | 0 | Project complete; PCR submitted to 29th ExCOM. |  |  | 1999-06-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | Refrigeration mobile air conditioning (MAC) servicing |  | ASP | CPR | REF | 19 | DEM | 163 | A | O | I | CFC | 11.4 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1999-05-01 |  | 1998-11-01 | 1998-12-01 | 385000 | 77600 | 462600 | 462600 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1995 | 1997-12-01
FIN | UNIDO | Phasing out ODS at the X'ian Yuan Dong Compressor Co., Xi'an | Individual | ASP | CPR | REF | 19 | INV | 164 | A | O | I |  | 0 | 0 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1999-06-01 | 2000-12-01 | 1599000 | -5860 | 1593140 | 1593140 | 100% | 0 | 0 |  | 207870 | -1090 | 206780 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNIDO | Phasing out ODS at the compressor factory of the Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | REF | 19 | INV | 165 | A | O | I | CFC | 60 | 60 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1998-12-01 | 2002-05-01 | 899030 | 0 | 899030 | 899030 | 100% | 0 | 0 |  | 116874 | -33 | 116841 | 0 | 0 | FIN
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Hua Yi Electrical Appliance General Company | Individual | ASP | CPR | FOA | 19 | INV | 166 | N | O | I | CFC | 170 | 170 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-02-01 |  | 1998-05-01 | 1998-09-01 | 972490 | 0 | 972490 | 972490 | 100% | 0 | 0 |  | 126423.7 | 0 | 126423.7 | 0 | 0 | Project completed; PCR submitted to 29th ExCOM. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Guingdao Haier General Freezer Company | Individual | ASP | CPR | REF | 19 | INV | 167 | N | O | I | CFC | 278.8 | 278.8 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2000-04-01 | 2003-07-01 | 2548280 | -22910 | 2525370 | 2525370 | 100% | 0 | 0 | 0 | 331276 | -2978 | 328298 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  | 1998-05-01 | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Henan Freezer Factory | Individual | ASP | CPR | REF | 19 | INV | 168 | N | O | I | CFC | 167.7 | 167.7 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2001-06-01 | 2003-09-01 | 2550605 | -54725 | 2495880 | 2495880 | 100% | 0 | 0 | 0 | 331579 | -7114 | 324465 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Sixth Radio Factory | Individual | ASP | CPR | SOL | 19 | INV | 169 | N | O | I | CFC | 4.5 | 4.5 | 0 | 0 | 1996-05-01 | 1999-09-01 | 1998-04-01 |  | 2001-08-01 | 2003-09-01 | 138400 | -14098 | 124302 | 124302 | 100% | 0 | 0 | 0 | 17992 | -1833 | 16159 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-05-01 | [10 empty] | 1996 | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the electron gun final cleaning processes at the Tianjin Picture Tube Factory | Individual | ASP | CPR | SOL | 19 | INV | 170 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1998-04-01 |  |  | 1999-03-01 | 132600 | -132600 | 0 | 0 |  | 0 | 0 | 0 | 17238 | -17238 | 0 | 0 | 0 | Canceled in 1999. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of the use of CFC-113 and methyl chloroform in the color picture tube cleaning processes at the Shanghai Novel CPT. Corp. Factory | Individual | ASP | CPR | SOL | 19 | INV | 171 | N | O | I | CFC | 75 | 75 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1998-04-01 |  | 2002-11-01 | 2008-10-01 | 849950 | -150442 | 699508 | 699508 | 100% | 0 | 0 | 0 | 110494 | -19558 | 90936 | 0 | 0 | Completed in 2002. Financially completed in 2008. |  |  | 1998-05-01 | [10 empty] | 1996 | Investment
FIN | UNDP | Elimination of the use of TCA in the Baoshi Electronics Corporation Shijazhuang Manufacturing Operations | Individual | ASP | CPR | SOL | 19 | INV | 172 | N | O | I | TCA | 7.4 | 7.4 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1998-04-01 |  | 2000-07-01 | 2003-03-01 | 284900 | -7138 | 277762 | 277762 | 100% | 0 | 0 | 0 | 37037 | -928 | 36109 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  | 1998-05-01 | [10 empty] | 1996 | Investment
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Aucma Electric Appliances Group Co. | Individual | ASP | CPR | REF | 20 | INV | 173 | A | O | I | CFC | 708 | 708 |  |  | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 1998-12-01 | 2002-07-01 | 2914904 | 0 | 2914904 | 2914904 | 100% | 0 | 0 |  | 378938 | -192 | 378746 | 0 | 0 | FIN
CLO | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Shanghai Shuanglu Electrical Appliance Co. Ltd. | Individual | ASP | CPR | FOA | 20 | INV | 174 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-07-01 |  |  | 1999-07-01 | 1899230 | -1899230 | 0 | 0 |  | 0 | 0 |  | 246899.9 | -246900 | 0 | -0.1 | -0.1 | Project cancelled. Company bankrupt. Funds returned at 27th meeting. |  |  | 1998-06-01 | 1998-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium-sized semi-hermetic CFC-12 refrigerating compressor production to HCFC-22 production at Tianjin Tian Shan Refrigeration Equipment Co. | Individual | ASP | CPR | REF | 20 | INV | 175 | N | O | I | CFC | 275.5 | 275.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2003-05-01 | 2004-09-01 | 2256000 | 0 | 2256000 | 2256000 | 100% | 0 | 0 |  | 293280 | 0 | 293280 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane and CFC-12 refrigerant to HFC-134a at Gansu Changfeng Baoan Industry Co. Ltd. | Individual | ASP | CPR | REF | 20 | INV | 176 | N | O | I | CFC | 65.2 | 65.2 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1998-10-01 |  | 2002-04-01 | 2004-07-01 | 634150 | 260000 | 894150 | 894150 | 100% | 0 | 0 |  | 82439.5 | 33800 | 116239.5 | 0 | 0 | Project financially completed. |  |  | 1999-06-01 |  | 2000-08-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of rigid PUF products at Handan Plastics No. 8 | Individual | ASP | CPR | FOA | 20 | INV | 177 | N | O | I | CFC | 101.64 | 101.64 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1997-10-01 |  | 1999-05-01 | 2002-07-01 | 265000 | 0 | 265000 | 265000 | 100% | 0 | 0 |  | 34450 | 0 | 34450 | 0 | 0 |  |  |  | 1997-12-01 | 1999-04-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai Automation Instrumentation Factory | Individual | ASP | CPR | SOL | 20 | INV | 178 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1996-10-01 | 1999-08-01 | 1998-09-01 |  | 2001-03-01 | 2003-03-01 | 325000 | -5336 | 319664 | 319664 | 100% | 0 | 0 | 0 | 42250 | -694 | 41556 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [10 empty] | 1996 | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexibe (slabstock) polyurethane foam at Chengdu Plastics No. 7 | Individual | ASP | CPR | FOA | 20 | INV | 179 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1996-10-01 | 2001-01-01 | 1998-04-01 |  | 2005-04-01 | 2005-01-01 | 301000 | 0 | 301000 | 301000 | 100% | 0 | 0 |  | 39130 | 0 | 39130 | 0 | 0 | Project completed. |  |  | 1998-04-01 | 2000-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigerating compressor production at Shanghai General Machinery (Group) Corp. (SGMC) | Individual | ASP | CPR | REF | 20 | INV | 180 | N | O | I | CFC | 209 | 209 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 2039800 | 0 | 2039800 | 2039800 | 100% | 0 | 0 |  | 265174 | 0 | 265174 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol - Phase II | Individual | ASP | CPR | SEV | 20 | INS | 181 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 300000 | -1 | 299999 | 299999 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1996 | Non-Investment
FIN | IBRD | Conversion of CFC-11 and CFC-12 centrifugal refrigerating compressor to HFC-134a centrifugal technology at Chongqing General Machinery Factory (CGMF) | Individual | ASP | CPR | REF | 20 | INV | 182 | N | O | I | CFC | 220 | 220 | 0 | 0 | 1996-10-01 | 1998-01-01 | 2000-04-01 |  | 2000-08-01 | 2002-03-01 | 2632000 | 0 | 2632000 | 2632000 | 100% | 0 | 0 |  | 342160 | 0 | 342160 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  | 2000-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 20 | INV | 183 | N | O | I | CFC | 108.5 | 108.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 1974000 | 0 | 1974000 | 1974000 | 100% | 0 | 0 |  | 256620 | 0 | 256620 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Additional preparation of halon sector approach |  | ASP | CPR | HAL | 20 | PRP | 184 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-31 | 1997-08-01 |  | 1997-09-30 | 1997-09-30 | 132500 | 0 | 132500 | 132500 | 100% | 0 | 0 |  | 17225 | 0 | 17225 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at the Household Refrigerator Compressor Factory of the Guangzhou Wanbao Compressor Group | Individual | ASP | CPR | REF | 20 | INV | 185 | A | O | I | CFC | 3 | 3 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 1999-10-01 | 2002-09-01 | 2250000 | 0 | 2250000 | 2250000 | 100% | 0 | 0 |  | 292500 | -35 | 292465 | 0 | 0 | FIN
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai No 8 Radio Factory | Individual | ASP | CPR | SOL | 20 | INV | 186 | N | O | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 2000-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-09-01 | 378000 | -81073 | 296927 | 296927 | 100% | 0 | 0 | 0 | 49140 | -10539 | 38601 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [10 empty] | 1996 | Investment
FIN | IBRD | Project preparation in the halon sector |  | ASP | CPR | HAL | 21 | PRP | 187 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 133000 | -500 | 132500 | 132500 | 100% | 0 | 0 |  | 17290 | -65 | 17225 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Update of the country programme and policy workshop | Individual | ASP | CPR | SEV | 21 | CPG | 188 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-03-01 |  | 1998-12-01 | 2002-06-01 | 225000 | -17054 | 207946 | 207946 | 100% | 0 | 0 | 0 | 29250 | -2217 | 27033 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Non-Investment
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 21 | PRP | 189 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 32500 | 0 | 32500 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Project preparation in the refrigeration (including compressors), solvents and methyl bromide sectors | Individual | ASP | CPR | SEV | 21 | PRP | 190 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1999-12-01 | 2002-09-01 | 182140 | -575 | 181565 | 181565 | 100% | 0 | 0 |  | 23678 | -112 | 23566 | 0 | 0 | FIN
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 21 | PRP | 191 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1997 | Investment
FIN | UNDP | Preparation of a sectoral financing plan for the solvents sector | Individual | ASP | CPR | SOL | 21 | TAS | 192 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2003-07-01 | 200000 | -19236 | 180764 | 180764 | 100% | 0 | 0 | 0 | 26000 | -2501 | 23499 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1997 | Non-Investment
FIN | UNIDO | Preparatory assistance for phase out of ODS in tobacco expansion in China | Individual | ASP | CPR | OTH | 09 | TAS | 193 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-05-01 | 1998-08-01 | 72000 | 4499 | 76499 | 76499 | 100% | 0 | 0 |  | 9360 | 585 | 9945 | 0 | 0 | FIN
FIN | UNIDO | Substituting halon in fire fighting equipment at Nanjing | Individual | ASP | CPR | HAL | 09 | PRP | 194 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-04-01 | 1996-03-01 |  | 1995-03-01 | 1998-08-01 | 36000 | -6926 | 29074 | 29074 | 100% | 0 | 0 |  | 4680 | -906 | 3774 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Railway Communication Equipment Factory | Individual | ASP | CPR | SOL | 22 | INV | 195 | N | O | I | CFC | 14.4 | 14.4 | 0 | 0 | 1997-05-01 | 1999-09-01 | 1999-06-01 |  | 2001-03-01 | 2003-03-01 | 276287 | -1 | 276286 | 276286 | 100% | 0 | 0 | 0 | 35917 | 0 | 35917 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNIDO | Phasing out ODS at the refrigeration plant of Hefei Meiling | Individual | ASP | CPR | REF | 22 | INV | 196 | A | O | I | CFC | 849 | 849 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1998-12-01 | 2002-09-01 | 3247877 | -44594 | 3203283 | 3203283 | 100% | 0 | 0 |  | 422224 | -6457 | 415767 | 0 | 0 | FIN
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 22 | PRP | 197 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion of CFC-12 medium open-type refrigerating compressor to HCFC-22 compressor at Guangzhou Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 198 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-04-01 | 2004-09-01 | 1904769 | 0 | 1904769 | 1904769 | 100% | 0 | 0 |  | 247619.97 | 0 | 247619.97 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 |  | 2002-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | ASP | CPR | FUM | 22 | DEM | 199 | A | O | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-06-01 | 1999-06-01 |  | 1998-10-01 | 1998-10-01 | 145000 | 0 | 145000 | 145000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed |  | 1997 | [11 empty] | 1997 | Non-Inv.
FIN | IBRD | Conversion of CFC-12 small open-type refrigerating compressor to HCFC-22 refrigerating compressor at Subei Refrigeration Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 200 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-01-01 | 2004-04-01 | 1806908 | 0 | 1806908 | 1806908 | 100% | 0 | 0 |  | 234898.04 | 0 | 234898.04 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Demonstration project on alternatives to the use of methyl bromide in soil fumigation | Individual | ASP | CPR | FUM | 22 | DEM | 201 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-08-01 | 443300 | -13942 | 429358 | 429358 | 100% | 0 | 0 |  | 57629 | -1901 | 55728 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhejiang Wanpeng Clique Co., Ltd. | Individual | ASP | CPR | FOA | 22 | INV | 202 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 412666 | -10472 | 402194 | 402194 | 100% | 0 | 0 | 0 | 53647 | -1362 | 52285 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Jiaxipera compressor factory | Individual | ASP | CPR | SOL | 22 | INV | 203 | A | O | I | CFC | 76 | 76 |  |  | 1997-05-01 | 1998-10-01 | 1998-12-01 |  | 1999-05-01 | 2000-04-14 | 308604 | 0 | 308604 | 308604 | 100% | 0 | 0 |  | 40119 | 0 | 40119 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Hualing refrigerator plant | Individual | ASP | CPR | REF | 22 | INV | 204 | A | O | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-04-01 | 879788 | -207466 | 672322 | 672322 | 100% | 0 | 0 |  | 114372 | -27109 | 87263 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects in the production sector for 1998 submission |  | ASP | CPR | PRO | 22 | PRP | 205 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhoushan Fuchuan Plastic Products Factory | Individual | ASP | CPR | FOA | 22 | INV | 206 | N | O | I | CFC | 61 | 61 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 403711 | -9045 | 394666 | 394666 | 100% | 0 | 0 | 0 | 52482 | -1175 | 51307 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Investment
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zerowatt Electric Appliances Group | Individual | ASP | CPR | REF | 22 | INV | 207 | A | O | I | CFC | 423 | 423 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 2394178 | -10688 | 2383490 | 2383490 | 100% | 0 | 0 |  | 311243 | -1880 | 309363 | 0 | 0 | FIN
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Wuhan New World Refrigeration Industrial Co. Ltd. | Individual | ASP | CPR | REF | 22 | INV | 208 | N | O | I | CFC | 209 | 209 | 0 | 0 | 1997-05-01 | 1999-09-01 | 2000-06-01 |  | 2003-08-01 | 2004-12-01 | 1459871 | 0 | 1459871 | 1459871 | 100% | 0 | 0 |  | 189783.23 | 0 | 189783.23 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 22 | INV | 209 | N | O | I | CFC | 186 | 186 | 0 | 0 | 1997-05-01 | 2001-12-31 | 2000-11-01 |  | 2002-12-01 | 2004-04-01 | 1048286 | 0 | 1048286 | 1048286 | 100% | 0 | 0 |  | 136277.18 | 0 | 136277.18 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small and medium open type refrigerating compressor production at Zhejiang Chunhui Company (Group) (ZCC) | Individual | ASP | CPR | REF | 22 | INV | 210 | N | O | I | CFC | 361 | 361 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-02-01 | 2004-05-01 | 3200394 | 0 | 3200394 | 3200394 | 100% | 0 | 0 |  | 416051.22 | 0 | 416051.22 | 0 | 0 | Project is financially completed. |  |  |  | 2000-06-01 |  | 2002-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at the Zel Tianjin Compressor Co., Ltd. | Individual | ASP | CPR | REF | 22 | INV | 211 | A | O | I | CFC | 30 | 30 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 1999-07-01 | 962175 | 0 | 962175 | 962175 | 100% | 0 | 0 |  | 125083 | 0 | 125083 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from CFC-113 to trichloroethylene at Hangli Refrigeration Ltd. | Individual | ASP | CPR | SOL | 22 | INV | 212 | A | O | I | CFC | 28.8 | 28.8 |  |  | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1999-12-01 | 2001-03-01 | 217762 | 0 | 217762 | 217762 | 100% | 0 | 0 |  | 28309 | -8 | 28301 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | SOL | 22 | INV | 213 | A | O | I | CFC | 37.6 | 37.6 |  |  | 1997-05-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 1999-07-01 | 236242 | 0 | 236242 | 236242 | 100% | 0 | 0 |  | 30711 | 0 | 30711 | 0 | 0 | FIN
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Chongqing Bingyang Refrigerating Machine Co. | Individual | ASP | CPR | REF | 22 | INV | 214 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-12-01 | 2004-05-01 | 1805370 | 0 | 1805370 | 1805370 | 100% | 0 | 0 |  | 234698.1 | 0 | 234698.1 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open type refrigerating compressor production at Ningbo Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 215 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2002-10-01 | 2004-04-01 | 1786949 | 0 | 1786949 | 1786949 | 100% | 0 | 0 |  | 232303.37 | 0 | 232303.37 | 0 | 0 | Project financially completed. |  |  |  | 2000-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Computer Factory | Individual | ASP | CPR | SOL | 22 | INV | 216 | N | O | I | CFC | 6.3 | 6.3 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-11-01 | 2003-08-01 | 116767 | -1 | 116766 | 116766 | 100% | 0 | 0 | 0 | 15180 | 0 | 15180 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | IBRD | Preparation/supervision of investment projects ODS IV (1995) |  | ASP | CPR | SEV | 16 | PRP | 217 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-12-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. Actual disbursement for PPA IV was $200,000. and the balance of $50,000 was utilized for project preparation under ODS III (CPR/SEV/16/PRP/139). | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Hefei General Machinery Research Institute (HGMRI): four technical assistance projects to support conversion of commercial refrigeration compressors | Individual | ASP | CPR | REF | 23 | INV | 218 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-06-01 | 2001-11-01 |  | 2002-11-01 | 2002-11-01 | 692400 | -39141 | 653259 | 653259 | 100% | 0 | 0 |  | 90012 | -4892.63 | 85119.37 | 0 | 0 | Project completed. Draft PCR underway. Savings to be returned to the MLF. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at the Yuhuan Compressor Factory in Kanmen Town in Yuhuan County, South East China | Individual | ASP | CPR | REF | 23 | INV | 219 | A | O | I | CFC | 116 | 116 |  |  | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1465155 | -9186 | 1455969 | 1455969 | 100% | 0 | 0 |  | 190470 | -1494 | 188976 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zhejiang Rongsheng Electric Co. Ltd., Zhejiang, Deqing Country | Individual | ASP | CPR | REF | 23 | INV | 220 | A | O | I | CFC | 177.8 | 177.8 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1053910 | -67809 | 986101 | 986101 | 100% | 0 | 0 |  | 137008 | -9018 | 127990 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Changshu Refrigerating Equipment Works (Baixue), Changsu | Individual | ASP | CPR | REF | 23 | INV | 221 | A | O | I | CFC | 425.7 | 425.7 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 3548775 | -521956 | 3026819 | 3026819 | 100% | 0 | 0 |  | 461341 | -68478 | 392863 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Bole Electric Appliances Group | Individual | ASP | CPR | REF | 23 | INV | 222 | A | O | I | CFC | 132 | 132 |  |  | 1997-11-01 | 1998-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 1469029 | -1564 | 1467465 | 1467465 | 100% | 0 | 0 |  | 190974 | -4672 | 186302 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN.
FIN | UNIDO | Phasing out ODS at the freezer plant of Xing Xing Electric Appliances Industrial Co. | Individual | ASP | CPR | REF | 23 | INV | 223 | A | O | I | CFC | 348 | 348 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2002-04-01 | 3346941 | -334438 | 3012503 | 3012503 | 100% | 0 | 0 |  | 435102 | -44097 | 391005 | 0 | 0 | FIN
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Fujian Putian Vikay Electronics Co. Ltd. | Individual | ASP | CPR | SOL | 23 | INV | 224 | N | O | I | CFC | 56 | 56 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2002-11-01 | 2008-10-01 | 619780 | 0 | 619780 | 617424 | 99.62% | 2356 | 0 | 0 | 80571 | 0 | 80264.7215 | 306.2785 | 0 | Completed in 2002. Financially completed in 2008. | [13 empty] | 1997 | Investment
CLO | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Jilin Jinouer Electric Appliances Group Co. | Individual | ASP | CPR | REF | 23 | INV | 225 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-12-01 |  |  | 2003-09-01 | 2548360 | -1223403 | 1324957 | 1324957 | 100% | 0 | 0 | 0 | 331287 | -159042 | 172245 | 0 | 0 | Canceled in 2002. Financially completed in 2003. |  |  |  |  | 2000-12-01 | [8 empty] | 1997 | Investment
COM | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Wanbao Electrical Appliance Industries Co. | Individual | ASP | CPR | REF | 23 | INV | 226 | N | O | I | CFC | 574.2 | 574.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2003-12-01 |  | 4566985 | 0 | 4566985 | 4566985 | 100% | 0 | 0 | 0 | 593708 | 0 | 593708 | 0 | 0 | Completed in 2003. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 227 | N | O | I | CFC | 462.6 | 462.6 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2001-12-01 | 2002-11-01 | 1132682 | -2956 | 1129726 | 1129726 | 100% | 0 | 0 |  | 147249 | -370 | 146879 | 0 | 0 | Project completed. PCR submitted to ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels, pipes and spray foams at Baoding Oil Depot & Storage Engineering Company | Individual | ASP | CPR | FOA | 23 | INV | 228 | N | O | I | CFC | 75.5 | 75.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-09-01 | 400960 | -34986 | 365974 | 365974 | 100% | 0 | 0 | 0 | 52125 | -4549 | 47576 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid and spray polyurethane foams at Xinjiang Tianye Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 229 | N | O | I | CFC | 92.3 | 92.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 2001-01-01 | 2004-01-01 | 300620 | -15937 | 284683 | 284683 | 100% | 0 | 0 | 0 | 39081 | -2072 | 37009 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Shanghai General Machinery Company (SGMC) | Individual | ASP | CPR | FOA | 23 | INV | 230 | N | O | I | CFC | 88.3 | 88.3 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2002-12-01 | 2004-09-01 | 380300 | -1711.2 | 378588.8 | 378588.8 | 100% | 0 | 0 |  | 49439 | -171.12 | 49267.88 | 0 | 0 | Financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 1998 Annual Programme | Multiyear | ASP | CPR | HAL | 23 | INV | 231 | N | O | I | HAL | 9939 | 9939 | 11739 | 11739 | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 |  | 12400000 | 0 | 12400000 | 12400000 | 100% | 0 | 0 | 0 | 1240000 | 0 | 1240000 | 0 | 0 | 1998 Annual Plan was successfully completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Honxiang Group, Laizhou Freezer Plant | Individual | ASP | CPR | REF | 23 | INV | 232 | N | O | I | CFC | 301.5 | 301.5 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2003-09-01 | 2005-03-01 | 1339203 | -6776 | 1332427 | 1332427 | 100% | 0 | 0 | 0 | 174096 | -881 | 173215 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1997 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic freezers at DeBao Refrigeration Equipment Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 233 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-06-01 | 1208176 | -683628 | 524548 | 524548 | 100% | 0 | 0 | 0 | 157063 | -88872 | 68191 | 0 | 0 | Canceled in 2002. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Henan Xinfei Electric Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 234 | N | O | I | CFC | 375 | 375 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-12-01 |  | 1998-12-01 | 2000-09-01 | 1556490 | 0 | 1556490 | 1556490 | 100% | 0 | 0 |  | 202344 | 0 | 202344 | 0 | 0 | Project was completed; PCR submitted to 30th ExCOM. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Shanghai Shangling Chang-An Refrigerator Co., Ltd (former Shanghai Yuandong Refrigerator Co. Ltd.) | Individual | ASP | CPR | REF | 23 | INV | 235 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 2000-11-01 |  |  | 2000-12-01 | 1237663 | -1237663 | 0 | 0 |  | 0 | 0 |  | 160896 | -158482.56 | 2413.44 | 0 | 0 | Project cancelled due to financial difficulties. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels at Luoyang Refrigeration Machinery Factory | Individual | ASP | CPR | FOA | 23 | INV | 236 | N | O | I | CFC | 117.8 | 117.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-01-01 | 2003-07-01 | 698595 | -41580 | 657015 | 657015 | 100% | 0 | 0 | 0 | 90817 | -5405 | 85412 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of a sectoral strategy in the tobacco sector | Individual | ASP | CPR | OTH | 24 | PRP | 237 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-11-01 | 2001-07-01 | 200000 | -8020 | 191980 | 191980 | 100% | 0 | 0 |  | 26000 | -1082 | 24918 | 0 | 0 | FIN |  |  |  | 1999-10-01
FIN | UNEP | Sectoral policy plan for methyl bromide phaseout in China | Individual | ASP | CPR | FUM | 24 | TAS | 238 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-01-01 |  | 1999-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNDP | Project preparation for 2 projects in the domestic refrigeration (hydrocarbon) subsector | Individual | ASP | CPR | REF | 24 | PRP | 239 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNIDO | Preparation of investment projects (50 companies) in the foam sector (polysterene/polyethylene) | Individual | ASP | CPR | FOA | 24 | PRP | 240 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 100000 | -2311 | 97689 | 97689 | 100% | 0 | 0 |  | 13000 | -321 | 12679 | 0 | 0 | FIN
FIN | UNDP | Project preparation for 10 projects in the rigid and integral skin foam sub-sectors | Individual | ASP | CPR | FOA | 24 | PRP | 241 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to cylopentane and R-134a in the manufacture of domestic freezers at Wanbao Freezer Industrial Corporation | Individual | ASP | CPR | REF | 24 | INV | 242 | N | O | I | CFC | 138.2 | 138.2 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-08-01 | 2004-06-01 | 1402370 | -52248 | 1350122 | 1350122 | 100% | 0 | 0 | 0 | 182308 | -6792 | 175516 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation in the aerosol, foam, MAC and commercial refrigeration sectors |  | ASP | CPR | SEV | 24 | PRP | 243 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 78000 | 0 | 78000 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project to complete CFC phaseout in general purpose aerosols at NCLI and Fujiang Light Industry Co. | Individual | ASP | CPR | ARS | 24 | INV | 244 | N | O | I | CFC | 1224 | 1224 | 0 | 0 | 1998-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-12-01 | 2004-05-01 | 547675 | 0 | 547675 | 547675 | 100% | 0 | 0 |  | 71197.75 | 0 | 71197.75 | 0 | 0 | Project financially completed. | [5 empty] | 2002-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to cyclopentane in the manufacture of heating pipes at Jixi City Thermal Power Company | Individual | ASP | CPR | FOA | 24 | INV | 245 | N | O | I | CFC | 86 | 86 | 0 | 0 | 1998-03-01 | 2000-12-01 | 2000-04-01 |  | 2003-12-01 | 2008-10-01 | 673380 | 0 | 673380 | 670247 | 99.53% | 3133 | 0 | 0 | 87539 | 0 | 87131.7119 | 407.2881 | 0 | Completed in 2003. Financially completed in 2008. | [13 empty] | 1998 | Investment
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | CPR | SEV | 16 | PRP | 246 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 68017 | 0 | 68017 | 68017 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to LCD technology int he manufacture of flexible (slabstock) polyurethane foam at Jinling Petrochemical Co. Plastics Factory | Individual | ASP | CPR | FOA | 25 | INV | 247 | N | O | I | CFC | 81 | 81 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2000-08-01 |  | 2003-05-01 | 2005-02-01 | 504630 | -4472 | 500158 | 500158 | 100% | 0 | 0 | 0 | 65602 | -581 | 65021 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1998 | Investment
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 25 enterprises (umbrella project) | Individual | ASP | CPR | FOA | 25 | INV | 248 | A | O | I | CFC | 1146 | 1146 |  |  | 1998-07-01 | 1998-12-01 | 2000-01-01 |  | 2000-12-01 | 2002-09-01 | 4488516 | 0 | 4488516 | 4488516 | 100% | 0 | 0 |  | 583507 | -341 | 583166 | 0 | 0 | FIN
FIN | UNDP | Conversion to cyclopentane and isobutane in the manufacture of domestic refrigerators at Hangzhou Household Electrical Appliance Industrial Corporation (HHEAIC) | Individual | ASP | CPR | REF | 25 | INV | 249 | N | O | I | CFC | 247.8 | 247.8 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2004-11-01 | 2008-10-01 | 2238580 | -1062 | 2237518 | 2237518 | 100% | 0 | 0 | 0 | 291015 | -138 | 290876.94 | 0.06 | 0 | Completed in 2004. Financially completed in 2008. | [5 empty] | 2001-12-01 | [7 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride and forced cooling system in the manufacture of flexible polyurethane foam (slabstock) at Cangzhou New-Type Foam Decoration Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 250 | N | O | I | CFC | 67 | 67 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2001-05-01 | 2003-09-01 | 417410 | -17009 | 400401 | 400401 | 100% | 0 | 0 | 0 | 54263 | -2211 | 52052 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
CLO | IBRD | Conversion of refrigerator manufacture in Changhe Group to HFC-134a as refrigerant and cyclopentane as foam blowing agent | Individual | ASP | CPR | REF | 25 | INV | 251 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2001-08-01 |  |  | 2001-12-31 | 1267638 | -1267638 | 0 | 0 |  | 0 | 0 |  | 164792.94 | -162321.05 | 2471.89 | 1.4097e-11 | 0 | Project has been cancelled. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture to forced cooling and methylene chloride at Wuxi New Type Raw Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 252 | N | O | I | CFC | 231 | 231 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-08-01 |  | 1999-10-01 | 2002-08-01 | 488150 | 0 | 488150 | 488150 | 100% | 0 | 0 |  | 63459.5 | 0 | 63459.5 | 0 | 0 | [15 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Hefei Hualing Electronic Co., Ltd. | Individual | ASP | CPR | REF | 25 | INV | 253 | A | O | I | CFC | 82.8 | 82.8 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 785984 | -8264 | 777720 | 777720 | 100% | 0 | 0 |  | 102178 | -1235 | 100943 | 0 | 0 | FIN
FIN | UNDP | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Victory Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 25 | INV | 254 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1998-07-01 | 2001-11-01 | 2000-08-01 |  | 2003-11-01 | 2008-10-01 | 563760 | 0 | 563760 | 563487 | 99.95% | 273 | 0 | 0 | 73289 | 0 | 73253.5099 | 35.4901 | 0 | Completed in 2003. Financially completed in 2008. | [13 empty] | 1998 | Investment
FIN | IBRD | MAC ODS phaseout sector plan | One off phaseout | ASP | CPR | REF | 26 | INV | 255 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-04-01 | 7700000 | 0 | 7700000 | 7700000 | 100% | 0 | 0 |  | 820000 | 0 | 820000 | 0 | 0 | Project completed. Completion report submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | UNIDO | Conversion from CFC-12 to isobutane technologies and products at the compressor factory of the Hangli Refrigeration Ltd., in Hangzhou, China | Individual | ASP | CPR | REF | 26 | INV | 256 | A | O | I | CFC | 0 | 0 |  |  | 1998-11-01 | 1999-11-01 | 2001-12-01 |  |  | 2003-12-01 | 861000 | -180793 | 680207 | 680207 | 100% | 0 | 0 |  | 104710 | -20006 | 84704 | 0 | 0 | CLO
FIN | UNDP | Conversion to cyclopentane in the manufacture of PU-insulated heating pipes at Tianjin Pipeline Engineering Group Co. Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 257 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-09-01 | 2005-03-01 | 626400 | -346 | 626054 | 626054 | 100% | 0 | 0 | 0 | 78904 | -44 | 78860 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Guangdong Commercial Refrigeration Equipment Co. (GCREC) | Individual | ASP | CPR | FOA | 26 | INV | 258 | N | O | I | CFC | 60.3 | 60.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-10-01 | 2003-07-01 | 472150 | -18041 | 454109 | 454109 | 100% | 0 | 0 | 0 | 61380 | -2345 | 59035 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b foam blowing agent and CFC-12 with HFC-134a in the manufacture of domestic refrigerators/ freezers at the Beijing Freezing Equipment Factory. | Individual | ASP | CPR | REF | 26 | INV | 259 | A | O | I | CFC | 35.3 | 35.3 |  |  | 1998-11-01 | 1999-09-01 | 2000-12-01 |  | 2000-12-01 | 2002-09-01 | 280901 | -8254 | 272647 | 272647 | 100% | 0 | 0 |  | 36517 | -1129 | 35388 | 0 | 0 | FIN
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Kaifeng Air Separation Group Ltd. (KFAS) | Individual | ASP | CPR | FOA | 26 | INV | 260 | N | O | I | CFC | 68.2 | 68.2 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-04-01 | 2001-11-01 | 534090 | -14357 | 519733 | 519733 | 100% | 0 | 0 | 0 | 68750 | -1579 | 67171 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [13 empty] | 1998 | Investment
COM | IBRD | Sector plan for halon phaseout in China, 1999 Annual Programme | Multiyear | ASP | CPR | HAL | 26 | INV | 261 | N | O | I | HAL | 5370 | 5370 | 5826 | 5826 | 1998-11-01 | 1999-03-31 | 1999-12-01 |  | 1999-12-01 |  | 9700000 | 0 | 9700000 | 9700000 | 100% | 0 | 0 | 0 | 970000 | 0 | 970000 | 0 | 0 | 1999 annual plan completed successfully. | [14 empty] | INV | 19110 | 18880 | 24090 | 22735 | Yes | Yes | Yes
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol (Phase III) | Individual | ASP | CPR | SEV | 26 | INS | 262 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Non-Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and pour-in-place polyurethane foams at Corrosionproof and Insulation Co., Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 263 | N | O | I | CFC | 99.1 | 99.1 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-04-01 | 2004-01-01 | 776110 | -13913 | 762197 | 762197 | 100% | 0 | 0 | 0 | 95372 | -1530 | 93842 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of refrigerator manufacture in Zhenjiang Radio Factory from CFC-11 to N-pentane foam blowing agent in the production of PU insulation panels | Individual | ASP | CPR | FOA | 26 | INV | 264 | N | O | I | CFC | 120.5 | 120.5 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-09-01 | 2005-02-01 | 617860 | -4968 | 612892 | 612892 | 100% | 0 | 0 | 0 | 77965 | -627 | 77338 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1998 | Investment
COM | UNDP | Conversion to HCFC-141b in the manufacture of rigid and spray polyurethane foams at Daqing Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 26 | INV | 265 | N | O | I | CFC | 167.8 | 167.8 | 0 | 0 | 1998-11-01 | 2001-11-01 | 2001-06-01 |  | 2003-11-01 |  | 1124560 | 0 | 1124560 | 1123942 | 99.95% | 618 | 0 | 494.4 | 133702 | 0 | 133628.5243 | 73.4757 | 0 | Completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of flexible slabstock polyurethane foam at Ningbo Yongling Rubber and Plastic Co. | Individual | ASP | CPR | FOA | 26 | INV | 266 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 448560 | -20224 | 428336 | 428336 | 100% | 0 | 0 | 0 | 58313 | -2629 | 55684 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | IBRD | Conversion of refrigerator manufacture from CFC-11 to pentane foam blowing agent in the production of PU insulation panels at Foshan Refrigeration Equipment General Factory | Individual | ASP | CPR | FOA | 26 | INV | 267 | N | O | I | CFC | 120.3 | 120.3 | 0 | 0 | 1998-11-01 | 2000-09-01 | 2001-12-01 |  | 2005-03-01 | 2005-08-01 | 743500 | 0 | 743500 | 743500 | 100% | 0 | 0 |  | 91785 | 0 | 91785 | 0 | 0 | Completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNEP | Development of policy training strategy and plan for local authorities | Individual | ASP | CPR | SEV | 27 | TAS | 268 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2000-04-01 |  | 2000-10-01 | 2001-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Handan Fuyang Chemical Corporation | Individual | ASP | CPR | FOA | 27 | INV | 269 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2002-10-01 |  |  | 2001-12-01 | 436100 | -436100 | 0 | 0 |  | 0 | 0 |  | 56693 | -55842.6 | 850.4 | 0 | 0 | Project cancelled at the 35th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Qingdao Changlong Commercial Machinery Co. Ltd. | Individual | ASP | CPR | FOA | 27 | INV | 270 | N | O | I | CFC | 57.7 | 57.7 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-02-01 | 2003-10-01 | 451791 | -3921.96 | 447869.04 | 447869.04 | 100% | 0 | 0 |  | 58732.83 | -490.25 | 58242.58 | 0 | 0 | Physically and financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Xiaoshan Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 27 | INV | 271 | N | O | I | CFC | 111 | 111 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 603058 | 0 | 603058 | 603058 | 100% | 0 | 0 |  | 76336.38 | 0 | 76336.38 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of 16 projects in general foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 272 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and CFC production sectors |  | ASP | CPR | SEV | 27 | PRP | 273 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-31 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shenyin Polyurethane Xinzhuang Plant | Individual | ASP | CPR | FOA | 27 | INV | 274 | N | O | I | CFC | 86.1 | 86.1 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-11-01 | 2005-04-01 | 536403 | 0 | 536403 | 536403 | 100% | 0 | 0 |  | 69004.33 | 0 | 69004.33 | 0 | 0 | Completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Henan Huojia Huashi Co. | Individual | ASP | CPR | FOA | 27 | INV | 275 | N | O | I | CFC | 109.5 | 109.5 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 583186 | 0 | 583186 | 583186 | 100% | 0 | 0 |  | 74150.46 | 0 | 74150.46 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Zhenjiang Commercial Refrigeration Equipment General Plant | Individual | ASP | CPR | FOA | 27 | INV | 276 | N | O | I | CFC | 30.81 | 30.81 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 145376 | -4908 | 140468 | 140468 | 100% | 0 | 0 |  | 18899 | -490.8 | 18408.2 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jiangsu Haimen Foam plant | Individual | ASP | CPR | FOA | 27 | INV | 277 | N | O | I | CFC | 73 | 73 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-08-01 | 2004-12-01 | 454790 | 0 | 454790 | 454790 | 100% | 0 | 0 |  | 59122.7 | 0 | 59122.7 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of ten projects in the integral skin foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 278 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2005-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 2000. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Nanjing Kanglian Industrial Corporation | Individual | ASP | CPR | FOA | 27 | INV | 279 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1999-03-01 | 2000-04-01 | 2001-10-01 |  | 2001-04-01 | 2002-06-01 | 234900 | -14525 | 220375 | 220375 | 100% | 0 | 0 | 0 | 30537 | -1888 | 28649 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Shanghai Haiou Electric Appliance General Factory | Individual | ASP | CPR | FOA | 27 | INV | 280 | N | O | I | CFC | 33.34 | 33.34 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-09-01 | 2004-04-01 | 261052 | 0 | 261052 | 261052 | 100% | 0 | 0 |  | 33936.76 | 0 | 33936.76 | 0 | 0 | Financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Putuo Zhujiajian Rubber and Plastic Plant | Individual | ASP | CPR | FOA | 27 | INV | 281 | N | O | I | CFC | 112 | 112 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-07-01 | 2005-03-01 | 525483 | 0 | 525483 | 525483 | 100% | 0 | 0 |  | 67803.13 | 0 | 67803.13 | 0 | 0 | Completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at China Aerospace Industry Corp. Kunming Refrigerator Factory | Individual | ASP | CPR | REF | 27 | INV | 282 | A | O | I | CFC | 95.5 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-04-01 |  | 2004-12-01 | 2006-10-01 | 1451137 | 0 | 1451137 | 1451137 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR has been submitted. | [13 empty] | 2002
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | ASP | CPR | FOA | 27 | PRP | 283 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2001-05-01 | 2002-09-01 | 50000 | -615 | 49385 | 49385 | 100% | 0 | 0 |  | 6500 | -90 | 6410 | 0 | 0 | FIN
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shanghai Shenyin Polyurethane Baoshan Plant | Individual | ASP | CPR | FOA | 27 | INV | 284 | N | O | I | CFC | 76 | 76 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-10-01 | 2005-04-01 | 473480 | 0 | 473480 | 473480 | 100% | 0 | 0 |  | 61552.4 | 0 | 61552.4 | 0 | 0 | Completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Chengdu Jinjiang Foam General Plant | Individual | ASP | CPR | FOA | 27 | INV | 285 | N | O | I | CFC | 89 | 89 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-08-01 | 2004-11-01 | 554470 | 0 | 554470 | 554470 | 100% | 0 | 0 |  | 70991.7 | 0 | 70991.7 | 0 | 0 | Financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Hengfeng Polyurethane Spray Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 286 | N | O | I | CFC | 154.1 | 154.1 | 0 | 0 | 1999-07-01 | 2001-06-01 | 2002-02-01 |  | 2003-09-01 | 2005-02-01 | 1206600 | -101036 | 1105564 | 1105564 | 100% | 0 | 0 | 0 | 142726 | -11114 | 131612 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNDP | Elimination of ODS used in the production lines at Irico (Caihong) Color Picture Tube Factory | Individual | ASP | CPR | SOL | 28 | INV | 287 | N | O | I | TCA/CFC | 202 | 202 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2003-08-01 |  | 2002-10-01 | 2004-06-01 | 2853200 | -38805 | 2814395 | 2814395 | 100% | 0 | 0 | 0 | 323852 | -4405 | 319447 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | FOA | 28 | INV | 288 | N | O | I | CFC | 29.3 | 29.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-11-01 | 2004-11-01 | 149195 | 0 | 149195 | 149195 | 100% | 0 | 0 |  | 19395.35 | 0 | 19395.35 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Jiangsu Chemical Research Institute | Individual | ASP | CPR | FOA | 28 | INV | 289 | N | O | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2001-12-01 | 2004-06-01 | 253690 | -9289 | 244401 | 244401 | 100% | 0 | 0 | 0 | 32980 | -1208 | 31772 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiaxing Anti-Corrosion Factory | Individual | ASP | CPR | FOA | 28 | INV | 290 | N | O | I | CFC | 19.4 | 19.4 | 0 | 0 | 1999-07-01 | 2000-10-01 | 2002-02-01 |  | 2002-05-01 | 2004-06-01 | 151590 | -6492 | 145098 | 145098 | 100% | 0 | 0 | 0 | 19707 | -844 | 18863 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
CLO | UNDP | Phase-out of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane insulation foam at Suzhou Purification Equipment Factory | Individual | ASP | CPR | FOA | 28 | INV | 291 | N | O | I | CFC | 66 | 66 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  |  | 2005-12-01 | 516780 | -259990 | 256790.16 | 256790 | 100% | 0.16 | 0 | 0 | 66846 | -33463 | 33382.9792 | 0.0208 | 0 | Canceled in 2004. | [13 empty] | 1999 | Investment
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Heilongjiang Commercial Installation Corporation | Individual | ASP | CPR | FOA | 28 | INV | 292 | N | O | I | CFC | 52.6 | 52.6 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2001-11-01 | 2003-02-01 | 411858 | 0 | 411858 | 411858 | 100% | 0 | 0 |  | 53541.54 | 0 | 53541.54 | 0 | 0 | Project physically and financially completed and PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Changzhou Huangfa Co. Ltd., Foam Plant | Individual | ASP | CPR | FOA | 28 | INV | 293 | N | O | I | CFC | 70.7 | 70.7 | 0 | 0 | 1999-07-01 | 2001-01-01 | 2002-08-01 |  | 2004-06-01 | 2005-04-01 | 440461 | 0 | 440461 | 440461 | 100% | 0 | 0 |  | 57259.93 | 0 | 57259.93 | 0 | 0 | Completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiangsu Taizhou Commercial Machiner General Factory | Individual | ASP | CPR | FOA | 28 | INV | 294 | N | O | I | CFC | 28.3 | 28.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 192890 | -106.2 | 192783.8 | 192783.8 | 100% | 0 | 0 |  | 25075.7 | -10.62 | 25065.08 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane foam sandwich panels at Chengde Commercial Machinery Group Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 295 | N | O | I | CFC | 106 | 106 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-07-01 | 829980 | 0 | 829980 | 829980 | 100% | 0 | 0 |  | 101297.8 | 0 | 101297.8 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Shandong Tianhua (Group) Plastic Plant | Individual | ASP | CPR | FOA | 28 | INV | 296 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2002-08-01 |  |  | 2001-12-01 | 534534 | -534534 | 0 | 0 |  | 0 | 0 |  | 68798.74 | -67766.76 | 1031.98 | 1.0459e-11 | 0 | Project cancelled at the 35 th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Penglai Polyurethane Industry Co. | Individual | ASP | CPR | FOA | 28 | INV | 297 | N | O | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2001-04-01 | 2003-07-01 | 497200 | -50527 | 446673 | 446673 | 100% | 0 | 0 | 0 | 64636 | -6569 | 58067 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 298 | N | O | I | CFC | 104.2 | 104.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1457583 | 0 | 1457583 | 1457583 | 100% | 0 | 0 |  | 170334.13 | 0 | 170334.13 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Guangdong Zhujiang Refrigeration and Air Conditioning Co. | Individual | ASP | CPR | FOA | 28 | INV | 299 | N | O | I | CFC | 87.7 | 87.7 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2002-02-01 | 2003-06-01 | 581230 | 0 | 581230 | 581230 | 100% | 0 | 0 |  | 73935.3 | 0 | 73935.3 | 0 | 0 | Project completed. PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium sized open type compressors at Zhejiang Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 300 | N | O | I | CFC | 251.7 | 251.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1710295 | 0 | 1710295 | 1710295 | 100% | 0 | 0 |  | 198132.45 | 0 | 198132.45 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 27 enterprises (Umbrella Project) | Individual | ASP | CPR | FOA | 28 | INV | 301 | A | O | I | CFC | 825.7 | 825.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 5289441 | 0 | 5289441 | 5289441 | 100% | 0 | 0 |  | 591839 | -187 | 591652 | 0 | 0 | FIN | [5 empty] | 2002-12-01
FIN | Japan | Phasing out ODS in the production of compressors at Changshu Refrigerating Equipment Works | Individual | ASP | CPR | REF | 28 | INV | 302 | A | O | I | CFC | 75 | 75 | 0 |  | 1999-07-01 | 2001-11-01 | 2002-12-01 |  | 2004-10-01 | 2005-12-01 | 2250000 | 0 | 2250000 | 2246858 | 99.86% | 3142 | 0 | 0 | 257500 | 0 | 248026 | 9474 | 9128 | The project was succesfully completed in October 2004. |  | 1999
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of semi-hermetic compressors at Yueyang Hengli Air-Cool Equipment Co. Ltd. | Individual | ASP | CPR | REF | 28 | INV | 303 | N | O | I | CFC | 220.2 | 220.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1951757 | -291.22 | 1951465.78 | 1951465.78 | 100% | 0 | 0 |  | 224693.27 | -33.53 | 224659.74 | 0 | 0 | Financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phaseout of CFC-11 by conversion to water blown and HCFC-141b in the manufacture of ISF at 4 SMEs (Ningbo Yongling Rubber & Plastic, Sichuan Mianyang Jinpan Automobile Parts, Zhenjiang Xingda Auto Par | Individual | ASP | CPR | FOA | 29 | INV | 304 | N | O | I | CFC | 17.6 | 17.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2008-10-01 | 245710 | -19126 | 226584 | 226584 | 100% | 0 | 0 | 0 | 31942 | -2486 | 29455.63 | 0.37 | 0 | Completed in 2003. Financially completed in 2008. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Hangzhou Fanlong Steering Wheel, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 305 | N | O | I | CFC | 10.5 | 10.5 | 0 | 0 | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 176520 | -4703 | 171817 | 171817 | 100% | 0 | 0 | 0 | 22948 | -612 | 22336 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNIDO | Elimination of CFC-11 in manufacturing of PU rigid foam for insulation at 31 enterprises | Individual | ASP | CPR | FOA | 29 | INV | 306 | A | O | I | CFC | 707.3 | 707.3 |  |  | 1999-11-01 | 2000-04-01 | 2002-06-01 |  | 2003-01-01 | 2004-04-01 | 5516900 | 0 | 5516900 | 5516900 | 100% | 0 | 0 |  | 616859 | -430 | 616429 | 0 | 0 | FIN
FIN | Japan | Project preparation assistance for enterprises in the city of Shenzhen for the elimination of CFC-113 and TCA in the production lines of LC display and TV picture tube | Individual | ASP | CPR | SOL | 29 | PRP | 307 | A | O | I | CFC-113andCTA | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2003-07-01 | 50000 | 0 | 50000 | 19084 | 38.17% | 30916 |  | 0 | 6500 | 0 | 2481 | 4019 | 0 | Completed. Project proposal prepared but activities incorporated into China Solvent Sector Plan |  | 1999
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Moganshan Electric Appliances Co. | Individual | ASP | CPR | REF | 29 | INV | 308 | A | O | I | CFC | 667.6 | 667.6 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 2769118 | -754390 | 2014728 | 2014728 | 100% | 0 | 0 |  | 314603 | -83334 | 231269 | 0 | 0 | FIN
COM | IBRD | Sector plan for halon phaseout in China, 2000 Annual Programme | Multiyear | ASP | CPR | HAL | 29 | INV | 309 | N | O | I | HAL | 3712 | 3712 | 5970 | 5970 | 1999-11-01 | 2000-08-01 | 2000-12-01 |  | 2000-12-01 |  | 10600000 | 0 | 10600000 | 10600000 | 100% | 0 | 0 | 0 | 1060000 | 0 | 1060000 | 0 | 0 | Annual Program fully completed and disbursed. | [14 empty] | INV | 13740 | 14720 | 18120 | 16214 | Yes | Yes | Yes
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Chengde Machinery Installation Co. Qinghuangdao Branch | Individual | ASP | CPR | FOA | 29 | INV | 310 | N | O | I | CFC | 19.99 | 19.99 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2004-04-01 | 156600 | -5284 | 151316 | 151316 | 100% | 0 | 0 |  | 20358 | -660.5 | 19697.5 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to methylene chloride and vertifoam from CFC-11 to liquid carbon dioxide technology at Shenzhou Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 311 | N | O | I | CFC | 134.9 | 134.9 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2005-05-01 | 2005-12-01 | 609616 | 0 | 609616 | 609616 | 100% | 0 | 0 |  | 77057.76 | 0 | 77057.76 | 0 | 0 | Completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hanfeng Polyurethane Company | Individual | ASP | CPR | FOA | 29 | INV | 312 | N | O | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 440830 | -9007 | 431823 | 431823 | 100% | 0 | 0 | 0 | 57308 | -1171 | 56137 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [6 empty] | 2002-12-01 | [6 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Henan Bingxiong Refrigeration Truck Plant | Individual | ASP | CPR | FOA | 29 | INV | 313 | N | O | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2004-06-01 | 440780 | -97144 | 343636 | 343636 | 100% | 0 | 0 | 0 | 57301 | -12629 | 44672 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [6 empty] | 2003-07-01 | [6 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Tianjin Relong Insulation Pipe Plant | Individual | ASP | CPR | FOA | 29 | INV | 314 | N | O | I | CFC | 11.9 | 11.9 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 93190 | -5957 | 87233 | 87233 | 100% | 0 | 0 | 0 | 12115 | -774 | 11341 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [6 empty] | 2002-12-01 | [6 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Zhenjiang Feichi Automobile Group, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 315 | N | O | I | CFC | 31.7 | 31.7 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 223900 | -11388 | 212512 | 212512 | 100% | 0 | 0 | 0 | 29107 | -1481 | 27626 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [6 empty] | 2002-12-01 | [6 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Taiyuan No. 2 Plastic Factory | Individual | ASP | CPR | FOA | 29 | INV | 316 | N | O | I | CFC | 16.3 | 16.3 | 0 | 0 | 1999-11-01 | 2002-10-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 127790 | -7057 | 120733 | 120733 | 100% | 0 | 0 | 0 | 16613 | -917 | 15696 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Qianjin Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 317 | N | O | I | CFC | 64.77 | 64.77 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-08-01 | 2003-11-01 | 507109 | -79316 | 427793 | 427793 | 100% | 0 | 0 |  | 65781.99 | -10169 | 55613 | -0.01 | -0.01 | Project physically and financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Harbin Dongguang Machinery Plant | Individual | ASP | CPR | FOA | 29 | INV | 318 | N | O | I | CFC | 57.1 | 57.1 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 447170 | -23616 | 423554 | 423554 | 100% | 0 | 0 | 0 | 58132 | -3070 | 55062 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [6 empty] | 2002-12-01 | [6 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Dongfeng Automobile Body Company | Individual | ASP | CPR | FOA | 29 | INV | 319 | N | O | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 111120 | -9255 | 101865 | 101865 | 100% | 0 | 0 | 0 | 14446 | -1203 | 13243 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hangxing Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 320 | N | O | I | CFC | 60.6 | 60.6 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-09-01 | 2004-09-01 | 471217 | -85471 | 385746 | 385746 | 100% | 0 | 0 |  | 61258.21 | -11111 | 50147.21 | 0 | 0 | Project financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Yangzhou Tongli Refrigeration Container Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 321 | N | O | I | CFC | 14.63 | 14.63 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-11-01 | 2003-06-01 | 114513 | 0 | 114513 | 114513 | 100% | 0 | 0 |  | 14886.69 | 0 | 14886.69 | 0 | 0 | Project physically and financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Fuxing Jiahe Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 322 | N | O | I | CFC | 136.67 | 136.67 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2005-03-01 | 2005-07-01 | 515970 | 0 | 515970 | 515970 | 100% | 0 | 0 |  | 66756.7 | 0 | 66756.7 | 0 | 0 | Completed. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Huisheng Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 323 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-12-01 | 522207 | -522207 | 0 | 0 |  | 0 | 0 |  | 67442.77 | -67443 | 0 | -0.23 | -0.23 | Project cancelled at the 40th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane vertifoam manufacture from CFC-11 to liquid carbon dioxide technology in Tonxiang Shule Plastic Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 324 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2001-12-01 | 498400 | -498400 | 0 | 0 |  | 0 | 0 |  | 64792 | -63820.12 | 971.88 | 0 | 0 | Project cancelled at the 35th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Zhifu Zhenxing Polyurethane Materials Plant | Individual | ASP | CPR | FOA | 29 | INV | 325 | N | O | I | CFC | 36.3 | 36.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 261480 | -24023 | 237457 | 237457 | 100% | 0 | 0 | 0 | 33992 | -3123 | 30869 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Hebei Tianye Automobile Group Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 326 | N | O | I | CFC | 19.7 | 19.7 | 0 | 0 | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 98800 | -21345 | 77455 | 77454 | 100% | 1 | 0 | 0 | 12844 | -2775 | 10068.87 | 0.13 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | France | Project preparation of phase out of use of ODS solvent in production of parts working in high voltage conditions |  | ASP | CPR | SOL | 29 | PRP | 327 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-07-26 | 2000-12-01 |  | 2002-09-01 | 2002-09-01 | 27500 | 0 | 27500 | 27500 | 100% | 0 |  | 0 | 1375 | 0 | 1375 | 0 |  | Project completed.
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of integral skin foam at Guangzhou Haohua Automobile Carpet Plant | Individual | ASP | CPR | FOA | 29 | INV | 328 | N | O | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-09-01 | 2004-06-01 | 119540 | -8640 | 110900 | 110900 | 100% | 0 | 0 | 0 | 15540 | -1123 | 14417 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Ningxian Oriental Auto Parts Plant | Individual | ASP | CPR | FOA | 29 | INV | 329 | N | O | I | CFC | 7.3 | 7.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 122235 | -6311 | 115924 | 115924 | 100% | 0 | 0 | 0 | 15891 | -821 | 15070 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [6 empty] | 2002-12-01 | [6 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Fushan Anti-Corrosion Insulation Engineering Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 330 | N | O | I | CFC | 54.4 | 54.4 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2002-08-01 | 2004-06-01 | 425950 | -15465 | 410485 | 410485 | 100% | 0 | 0 | 0 | 55374 | -2010 | 53364 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam and flexible molded foam at Zhongqi Jinan Auto Parts Factory | Individual | ASP | CPR | FOA | 29 | INV | 331 | N | O | I | CFC | 21.6 | 21.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 236130 | -8780 | 227350 | 227350 | 100% | 0 | 0 | 0 | 30697 | -1141 | 29556 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Anqiu Polyurethane Materials Factory | Individual | ASP | CPR | FOA | 29 | INV | 332 | N | O | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 497200 | -9710 | 487490 | 487490 | 100% | 0 | 0 | 0 | 64636 | -1262 | 63374 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Jizhou Beinei Automobile Cushion Plant | Individual | ASP | CPR | FOA | 29 | INV | 333 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-05-01 | 2005-03-01 | 484040 | -18030 | 466010 | 466010 | 100% | 0 | 0 | 0 | 62925 | -2344 | 60581 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [6 empty] | 2002-12-01 | [6 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Qingdao No. 10 Plastic Plant | Individual | ASP | CPR | FOA | 29 | INV | 334 | N | O | I | CFC | 38.1 | 38.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 298480 | -30327 | 268153 | 268153 | 100% | 0 | 0 | 0 | 38802 | -3943 | 34859 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shanghai Furong Food Machinery Factory | Individual | ASP | CPR | FOA | 29 | INV | 335 | N | O | I | CFC | 23.1 | 23.1 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2002-06-01 | 2003-09-01 | 139379 | 0 | 139379 | 139379 | 100% | 0 | 0 |  | 18119.27 | 0 | 18119.27 | 0 | 0 | Physically completed. Draft PCR under review. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Zhejian Electrical Equipment Co. | Individual | ASP | CPR | REF | 29 | INV | 336 | A | O | I | CFC | 199 | 199 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-09-01 | 2189782 | -42893 | 2146889 | 2146889 | 100% | 0 | 0 |  | 250876 | -4718 | 246158 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the polystyrene/ polyethylene foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 337 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2840 | 47160 | 47160 | 100% | 0 | 0 |  | 6500 | -379 | 6121 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 338 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2627 | 47373 | 47373 | 100% | 0 | 0 |  | 6500 | -351 | 6149 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the domestic refrigeration (hydrocarbons) sector | Individual | ASP | CPR | REF | 30 | PRP | 339 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration compressor subsector | Individual | ASP | CPR | REF | 30 | PRP | 340 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 50000 | -786 | 49214 | 49214 | 100% | 0 | 0 |  | 6500 | -112 | 6388 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the transportation refrigeration sector (foam component) | Individual | ASP | CPR | REF | 30 | PRP | 341 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | -1 | 5199 | 0 | 0 | FIN
FIN | IBRD | Project preparation in the flexible polyurethane foam subsector |  | ASP | CPR | FOA | 30 | PRP | 342 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
CLO | UNDP | Preparation of 7 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 343 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 35000 | -35000 | 0 | 0 |  | 0 | 0 | 0 | 4550 | -4550 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of a project in the domestic refrigeration subsector (hydrocarbons) | Individual | ASP | CPR | REF | 30 | PRP | 344 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 35000 | -7212 | 27788 | 27788 | 100% | 0 | 0 | 0 | 4550 | -938 | 3612 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
CLO | UNDP | Preparation of 4 projects in the foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 345 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
TRF | UNEP | Evaluation and risk analysis of Montreal Protocol Implementation in China | Individual | ASP | CPR | SEV | 30 | TAS | 346 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project transferred | [13 empty] | 2000 | Non Investment
COM | IBRD | Sector plan for CFC production phaseout: 2000 annual programme | Multiyear | ASP | CPR | PRO | 30 | INV | 347 | N | O | I | CFC | 0 | 0 | 4931 | 4931 | 2000-03-01 | 2000-08-07 | 2000-12-01 |  | 2000-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 1170000 | 0 | 1170000 | 0 | 0 | Annual Program fully completed and disbursed. | [13 empty] | 2000 | INV | 0 | 0 | 40000 | 39990.5 | Yes | Yes | Yes
CLO | UNDP | Preparation of 8 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 348 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 60000 | -60000 | 0 | 0 |  | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
FIN | IBRD | Project preparation in the foam flexible subsector |  | ASP | CPR | FOA | 30 | PRP | 349 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam (general) sector |  | ASP | CPR | FOA | 30 | PRP | 350 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration sub-sector |  | ASP | CPR | REF | 30 | PRP | 351 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the domestic refrigeration subsector |  | ASP | CPR | REF | 30 | PRP | 352 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | ASP | CPR | FOA | 30 | PRP | 353 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed | [13 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the solvent (process agent) sector |  | ASP | CPR | PAG | 30 | PRP | 354 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed | [13 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | UNDP | ODS phaseout in China solvent sector: 2000 annual programme | Multi-Year | ASP | CPR | SOL | 30 | INV | 355 | N | O | I | TCA/CTC/CFC | 382.8 | 382.8 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-03-01 |  | 2003-05-01 |  | 6750000 | 0 | 6750000 | 6750000 | 100% | 0 | 0 | 0 | 675000 | 0 | 675000 | 0 | 0 | Completed in 2003. | [13 empty] | 2000 | Investment | 4031 | 4031 |  |  | yes | yes | yes
COM | IBRD | Sector plan for CFC production phaseout: 1999 annual programme | Multiyear | ASP | CPR | PRO | 27 | INV | 356 | N | O | I | CFC | 0 | 0 | 5497.6 | 5497.6 | 1999-03-01 | 1999-09-30 | 1999-12-01 |  | 1999-12-01 |  | 10000000 | 10000000 | 20000000 | 20000000 | 100% | 0 | 0 | 0 | 900000 | 900000 | 1800000 | 0 | 0 | 1999 annual plan successfully completed. | [14 empty] | INV | 0 | 0 | 44931 | 44793 | Yes | Yes | Yes
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and HFC-134a in the production of refrigerators at Banshen Electric Appliances Co. | Individual | ASP | CPR | REF | 31 | INV | 357 | A | O | I | CFC | 563 | 563 |  |  | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-06-01 | 2005-04-01 | 2988840 | -196425 | 2792415 | 2792415 | 100% | 0 | 0 |  | 338772 | -22093 | 316679 | 0 | 0 | FIN
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Qujing Plastic No. 2 Plant | Individual | ASP | CPR | FOA | 31 | INV | 358 | N | O | I | CFC | 99 | 99 | 0 | 0 | 2000-07-01 | 2003-04-01 | 2003-08-01 |  | 2004-09-01 | 2005-12-01 | 600066 | 0 | 600066 | 600066 | 100% | 0 | 0 |  | 76007.26 | 0 | 76007.26 | 0 | 0 | Completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | Japan | Develop a strategy for the refrigeration servicing sector | Individual | ASP | CPR | REF | 31 | TAS | 359 | A | O | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-07-01 | 2001-12-01 |  | 2003-12-01 | 2005-06-01 | 350000 | -1376 | 348624 | 348624 | 100% | 0 | 0 | 0 | 45500 | -179 | 45500 | -179 | 0 | Completed the data survey for the four sub-sectors and developed the first draft strategy. The national workshop was organized in July 2002 to review the draft. The second draft is being prepared as per comments received from the workshop and other source |  | 2000
FIN | UNIDO | Preparation of 2 investment projects in the domestic (hydrocarbons) refrigeration sub-sector | Individual | ASP | CPR | REF | 31 | PRP | 360 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-08-01 | 2002-11-01 | 40000 | -17965 | 22035 | 22035 | 100% | 0 | 0 |  | 5200 | -2340 | 2860 | 0 | 0 | FIN
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Wuxian Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 361 | N | O | I | CFC | 80 | 80 | 0 | 0 | 2000-07-01 | 2003-12-01 | 2003-08-01 |  | 2004-10-01 | 2005-04-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 |  | 64792 | 0 | 64792 | 0 | 0 | Completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Nantong Xinyuan Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 362 | N | O | I | CFC | 82 | 82 | 0 | 0 | 2000-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 510860 | 0 | 510860 | 510860 | 100% | 0 | 0 |  | 66194.6 | 0 | 66194.6 | 0 | 0 | Financially completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jintan Tiaoxi Shuya Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 363 | N | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 420525 | -420525 | 0 | 0 |  | 0 | 0 |  | 54668.25 | -53848.23 | 820.02 | -3.1832e-12 | 0 | Project cancelled at the 35th ExCom. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 2001 Annual Programme | Multiyear | ASP | CPR | HAL | 32 | INV | 364 | N | O | I | HAL | 1389 | 1389 | 1980 | 1980 | 2000-12-01 | 2002-12-01 | 2001-12-01 |  | 2001-12-01 |  | 4500000 | 0 | 4500000 | 4500000 | 100% | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | Completed and fully disbursed. | [13 empty] | 2000 | INV | 12351 | 10296 | 16131 | 11484 | Yes | Yes | Yes
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Little Swan Electric (Jingzhou) Co. Ltd. | Individual | ASP | CPR | REF | 32 | INV | 365 | A | O | I | CFC | 211.9 | 211.9 |  |  | 2000-12-01 | 2001-06-01 | 2003-12-01 |  | 2004-05-01 | 2005-09-01 | 2392316 | 0 | 2392316 | 2392316 | 100% | 0 | 0 |  | 273155 | -253 | 272902 | 0 | 0 | FIN
FIN | UNIDO | 2001 Annual work programme of the tobacco sector plan | Multi-Year | ASP | CPR | OTH | 32 | INV | 366 | A | O | I | CFC | 90 | 90 |  |  | 2000-12-01 | 2001-06-01 | 2001-12-01 |  | 2001-12-01 | 2004-02-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN | [13 empty] | 2000 |  | 1000 | 1000 |  |  | Yes | Yes | Yes
COM | UNDP | Phaseout of CFC-11 by conversion to cyclopentane technology and CFC-12 by conversion to isobutane (600a) technology in the manufacture of domestic freezers at Qingdao Haier No. 2 Freezer Plant | Individual | ASP | CPR | REF | 32 | INV | 367 | N | O | I | CFC | 180.8 | 180.8 | 0 | 0 | 2000-12-01 | 2003-06-01 | 2004-01-01 |  | 2004-11-01 |  | 788359 | 0 | 788359 | 774399 | 98.23% | 13960 | 0 | 11168 | 96720 | 0 | 95007.3143 | 1712.6857 | 0 | Completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | ASP | CPR | SEV | 32 | INS | 368 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2003-01-01 |  | 2003-06-01 | 2008-10-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2003. Financially completed in 2008. | [13 empty] | 2000 | Non-Investment
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b in manufacturing of PU rigid spray foam for insulation at 26 enterprises | Individual | ASP | CPR | FOA | 32 | INV | 369 | A | O | I | CFC | 891.4 | 891.4 |  |  | 2000-12-01 | 2001-07-01 | 2003-07-01 |  | 2004-12-01 | 2006-09-01 | 3295600 | 2025174 | 5320774 | 5320774 | 100% | 0 | 0 |  | 372516 | 232769 | 605285 | 0 | 0 | FIN | [13 empty] | 2000 | INV
COM | IBRD | Sector plan for CFC production phaseout: 2001 annual programme | Multiyear | ASP | CPR | PRO | 33 | INV | 370 | N | O | I | CFC | 0 | 0 | 3800 | 3804 | 2001-03-01 | 2001-07-19 | 2001-12-01 |  | 2001-12-31 |  | 6500000 | 6500000 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 585000 | 585000 | 1170000 | 0 | 0 | Annual Program fully completed and disbursed. | [13 empty] | 2001 | INV | 0 | 0 | 36200 | 36196 | Yes | Yes | Yes
FIN | UNIDO | Project preparation for two umbrella projects in the polystyrene/polyethylene foam sector | Individual | ASP | CPR | FOA | 33 | PRP | 371 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-10-01 |  | 2002-12-01 | 2003-12-01 | 100000 | -2686 | 97314 | 97314 | 100% | 0 | 0 |  | 13000 | -369 | 12631 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Germany | Project preparation/technical assistance in the refrigeration sector (thermostat) | Individual | ASP | CPR | SEV | 33 | PRP | 372 | A | O | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2001-12-01 |  | 2002-01-02 | 2002-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed; no PCR due to project preparation only | [13 empty] | 2002
COM | UNDP | ODS phaseout in China solvent sector: 2000-2001 annual programme | Multi-Year | ASP | CPR | SOL | 33 | INV | 373 | N | O | I | TCA/CTC/CFC | 534 | 534 | 0 | 0 | 2001-03-01 | 2003-03-01 | 2002-03-01 |  | 2005-01-01 |  | 6955000 | 0 | 6955000 | 6955000 | 100% | 0 | 0 | 0 | 695500 | 0 | 695500 | 0 | 0 | Completed in 2005. | [7 empty] | 2003-09-01 | [5 empty] | 2001 | Investment | 4031 | 4031 |  |  | yes | yes | yes
FIN | IBRD | Project preparation for the process agent sector plan |  | ASP | CPR | PAG | 34 | PRP | 374 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-06-01 |  | 2001-12-01 | 2001-12-01 | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 |  | 15860 | 0 | 15860 | 0 | 0 | [14 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at six companies Hongyu, Longan, Songliao, Tianyun, Xinyang and Yizheng) and phasing out CFC-11 by conversion to water blown technology at one company (Yinxian) | Individual | ASP | CPR | FOA | 34 | INV | 375 | A | O | I | CFC | 191.6 | 191.6 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-07-01 | 2005-12-01 | 1087764 | -80453 | 1007311 | 1007311 | 100% | 0 | 0 |  | 129654 | -9025 | 120629 | 0 | 0 | FIN | [13 empty] | 2001 | INV
COM | UNIDO | Phase out of CFC-12 in the manufacture of extruded polystyrene foams to butane at 9 enterprises (umbrella) | Individual | ASP | CPR | FOA | 34 | INV | 376 | A | O | I | CFC | 750 | 750 |  |  | 2001-07-01 | 2002-02-01 | 2003-08-01 |  | 2004-12-01 |  | 2808338 | 0 | 2808338 | 2655750 | 94.57% | 152588 | 136270 | 136270 | 318917 | 1 | 302133 | 16785 | 14990 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2001 | INV
FIN | UNEP | Policy training for local authorities (first tranche for 2001) | Individual | ASP | CPR | SEV | 34 | TRA | 377 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-12-01 | 2003-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | Individual | ASP | CPR | REF | 34 | INV | 378 | N | O | I | CFC | 174.2 | 174.2 | 0 | 0 | 2001-07-01 | 2003-05-01 | 2004-08-01 |  | 2005-12-01 | 2006-11-01 | 1400000 | 0 | 1400000 | 1400000 | 100% | 0 | 0 |  | 164000 | 0 | 164000 | 0 | 0 | Project is completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | UNIDO | Phase out of CFC-12 in the manufacturing of extruded polystyrene foams through the use of butane as a blowing agent at 7 enterprises (terminal umbrella project) | One-off Phase Out | ASP | CPR | FOA | 35 | INV | 379 | A | O | I | CFC | 359 | 359 |  |  | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2007-12-01 |  | 2450123 | 0 | 2450123 | 2446383 | 99.85% | 3740 | 2000 | 2750 | 279514 | 0 | 279102 | 412 | 220 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2001 | INV
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2002 annual programme | Multiyear | ASP | CPR | FOA | 35 | INV | 380 | N | O | I | CFC | 2000 | 2000 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 9940000 | 0 | 9940000 | 9940000 | 100% | 0 | 0 | 0 | 886600 | 0 | 886600 | 0 | 0 | Annual program fully completed and disbursed. | [13 empty] | 2000 | INV | 14143 | 14143 | 0 | 0 | Yes | Yes | Yes
COM | UNEP | Awareness raising workshop to support ratification of the Copenhagen Amendment | Individual | ASP | CPR | FUM | 35 | TAS | 381 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-04 |  | 100000 | -29818 | 70182 | 46182 | 65.8% | 24000 | 0 | 24000 | 13000 | -3876 | 6003.66 | 3120.34 | 0 | Project completed. | $ 29,818 plus $ 3,876 PSC returned at ExCom 52 | [7 empty] | 2004-06-01 |  |  |  |  | 2001 | Non Investment
FIN | UNEP | Techno-economic evaluation of methyl bromide alternatives | Individual | ASP | CPR | FUM | 35 | TAS | 382 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-04 | 2008-12-01 | 80000 | -9093 | 70907 | 70907 | 100% | 0 | 0 | 0 | 10400 | -1182 | 9217.91 | 0.09 | 0 | Project financially completed. | $ 9,093 plus $ 1182 returned to ExCom 50 | [7 empty] | 2004-06-01 |  |  |  |  | 2001 | Non Investment
COM | IBRD | Sector plan for halon phaseout in China, 2002 Annual Programme | Multiyear | ASP | CPR | HAL | 35 | INV | 383 | N | O | I | HAL | 2889 | 2889 | 2160 | 2160 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 3700000 | 0 | 3700000 | 3700000 | 100% | 0 | 0 | 0 | 370000 | 0 | 370000 | 0 | 0 | Annual Program completed and final disbursement for the tranche made. | [13 empty] | 2001 | INV | 9462 | 6492 | 13962 | 7408 | Yes | Yes | Yes
FIN | Germany | Conversion of the use of CFC-12 to HC in the manufacture of thermostats at Foshan Tongbao Co., Ltd. | Individual | ASP | CPR | REF | 35 | INV | 384 | A | O | I | CFC | 11.5 |  | 0 |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 | 2006-10-01 | 213271 | 0 | 213271 | 213271 | 100% | 0 | 0 | 0 | 27725 | 0 | 27725 | 0 | 0 | Project completed. PCR has been submitted. | [13 empty] | 2002
FIN | UNIDO | Preparation of a sectoral phase-out plan in domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 36 | PRP | 385 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-07-01 |  | 2003-07-01 | 2004-04-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | -12 | 9088 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of a sectoral strategy in the methyl bromide sector | Individual | ASP | CPR | FUM | 36 | PRP | 386 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-05-01 |  | 2003-12-01 | 2004-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
COM | UNIDO | Terminal umbrella project for the elimination of CFC-12 in manufacturing of EPE foam packaging nets at 30 enterprises | One-off Phase Out | ASP | CPR | FOA | 36 | INV | 387 | A | O | I | CFC | 849.3 | 849.3 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-12-01 |  | 1525648 | 2800061 | 4325709 | 4104095 | 94.88% | 221614 | 213137 | 213137 | 171352 | 314476 | 461450 | 24378 | 23445 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 20012002 | INV
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2002 workplan | Multi-Year | ASP | CPR | OTH | 36 | INV | 388 | A | O | I | CFC | 120 | 200 |  |  | 2002-03-01 | 2002-08-01 | 2003-03-01 |  | 2002-12-01 | 2003-07-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN | [13 empty] | 2001 | INV | 880 | 800 |  |  | Yes | Yes | Yes
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium open compressors at 5 enterprises (Dalian No.2, Shanghai Minhang, Zhejiang Beifeng, Zhejiang Chunlian, Zhejiang Yuhuan) | One off phaseout | ASP | CPR | REF | 36 | INV | 389 | N | O | I | CFC | 764.9 | 764.9 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-03-01 |  | 2007-12-01 | 2008-05-01 | 5250852 | 0 | 5250852 | 5250852 | 100% | 0 | 0 | 0 | 587593.72 | 0 | 587593.72 | 0 | 0 | Project completed. PCR prepared. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | UNDP | ODS phase-out in China solvent sector: 2002 annual programme | Multi-Year | ASP | CPR | SOL | 36 | INV | 390 | N | O | I | TCA/CTC/CFC | 580 | 580 | 0 | 0 | 2002-03-01 | 2005-01-01 | 2003-03-01 |  | 2005-09-01 |  | 6330000 | 0 | 6330000 | 6330000 | 100% | 0 | 0 | 0 | 633000 | 0 | 633000 | 0 | 0 | Completed in 2005. | [8 empty] | 2004-06-01 |  |  |  |  | 2002 | Investment | 3423 | 3423 |  |  | yes | yes | yes
COM | IBRD | Sector plan for CFC production phase-out: 2002 annual programme | Multiyear | ASP | CPR | PRO | 36 | INV | 391 | N | O | I | CFC | 0 | 0 | 3298 | 3300 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 910000 | 0 | 910000 | 0 | 0 | Annual program completed. CFC production verified and confirmed to be within target. | [13 empty] | 2002 | INV | 0 | 0 | 32900 | 32896 | Yes | Yes | Yes
FIN | UNEP | Policy training for local authorities (second tranche) | Individual | ASP | CPR | SEV | 37 | TRA | 392 | A | O | I | CFC | 16.5 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-09-01 | 2005-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | Italy | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (first tranche) | Multi-year | ASP | CPR | REF | 38 | INV | 393 | A | O | I | CFC | 181 | 181 | 0 |  | 2002-11-01 | 2003-09-01 | 2005-11-01 |  | 2005-10-01 | 2005-12-01 | 1788991 | 0 | 1788991 | 1788991 | 100% | 0 | 0 |  | 161009 | 0 | 161009 | 0 |  | Project completed in Oct 2005. Financial completion internally in Dec 2005. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2003 | [11 empty] | 2002 | Investment | 0 | 0 | 0 | 0 | n.a.
FIN | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors | Multi-Year | ASP | CPR | REF | 38 | INV | 394 | A | O | I | CFC | 600 | 600 |  |  | 2002-11-01 | 2003-09-01 | 2007-05-01 |  | 2007-06-01 | 2007-12-01 | 3400000 | 0 | 3400000 | 3400000 | 100% | 0 | 0 |  | 299200 | 0 | 299200 | 0 | 0 | FIN | [13 empty] | 2002 | INV | 918 | 918 |  |  | Yes | Yes | N/A
COM | IBRD | Sector plan for halon phaseout in China: 2003 annual programme | Multiyear | ASP | CPR | HAL | 38 | INV | 395 | N | O | I | HAL | 2292 | 2292 | 1992 | 1992 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 5900000 | 0 | 5900000 | 5900000 | 100% | 0 | 0 | 0 | 442500 | 0 | 442500 | 0 | 0 | Annual Program completed and final disbursement for tranche made. | [13 empty] | 2002 | INV | 7170 | 4945 | 11970 | 5654 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2003 annual programme | Multiyear | ASP | CPR | FOA | 38 | INV | 396 | N | O | I | CFC | 2500 | 2721 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2003-12-01 |  | 2003-12-01 |  | 12570000 | 0 | 12570000 | 12570000 | 100% | 0 | 0 | 0 | 1115300 | 0 | 1115300 | 0 | 0 | Annual Program fully completed. Disbursement will be completed in 2007. | [13 empty] | 2002 | INV | 13830 | 13830 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): First tranche | Multiyear | ASP | CPR | PAG | 38 | INV | 397 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-10-01 | 2003-12-01 |  | 2003-12-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | First tranche completed. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Extension of institutional strengthening (phase 5) | Individual | ASP | CPR | SEV | 38 | INS | 398 | N | T | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2005-09-01 | 2008-10-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 50700 | 0 | 50700 | 0 | 0 | Completed in 2005. Financially completed in 2008. | [13 empty] | 2002 | Non-Investment
FIN | IBRD | Project preparation funds for CTC and TCA production closure plan |  | ASP | CPR | PRO | 38 | PRP | 399 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | TCA Sector Plan will be submitted to the 43rd ExCom. CTC sector plan will be submitted for information purpose to the 42nd ExCom. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Tobacco sector plan: 2003 annual work programme | Multi-Year | ASP | CPR | OTH | 39 | INV | 400 | A | O | I | CFC | 180 | 180 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2003-12-01 | 2005-09-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | FIN | [13 empty] | 2002 |  | 700 | 620 |  |  | Yes | Yes | Yes
COM | IBRD | CFC production sector: 2003 annual programme | Multiyear | ASP | CPR | PRO | 39 | INV | 401 | N | O | I | CFC | 0 | 0 | 2900 | 2900 | 2003-04-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | Annual Program completed and fully disbursed. | [13 empty] | 2003 | INV | 0 | 0 | 30000 | 29986 | Yes | Yes | Yes
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2003 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 39 | INV | 402 | N | O | I | CTC | 0 | 0 | 2638 | 2638 | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 |  | 20000000 | 0 | 20000000 | 20000000 | 100% | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Annual Program completed. | [13 empty] | 2003 | INV | 5066.2 | 5066.2 | 61514 | 61199 | Yes | Yes | Yes
COM | UNDP | ODS phase-out in China solvent sector: 2003 annual programme | Multi-Year | ASP | CPR | SOL | 40 | INV | 403 | N | O | I | CFC/TCA/CTC | 580 | 580 | 0 | 0 | 2003-07-01 | 2005-01-01 | 2004-03-01 |  | 2005-12-01 |  | 5755000 | 0 | 5755000 | 5755000 | 100% | 0 | 0 | 0 | 431625 | 0 | 431625 | 0 | 0 | Completed in 2005. | [9 empty] | 2005-06-01 |  |  |  | 2003 | Investment | 2915 | 2915 |  |  | yes | yes | yes
COM | IBRD | Sector plan for halon phase-out in China: 2004 annual programme | Multiyear | ASP | CPR | HAL | 41 | INV | 404 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2004-12-01 |  | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 | 0 | 90000 | 0 | 90000 | 0 | 0 | Annual Program successfully completed with full disbursement made. | [13 empty] | 2003 | INV | 7170 | 4433 | 11970 | 5053 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2004 annual programme | Multiyear | ASP | CPR | FOA | 41 | INV | 405 | N | O | I | CFC | 2500 | 2500 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 | 0 | 961270 | 0 | 961270 | 0 | 0 | No disbursement in 2006. The third tranche will be disbursed in early 2007. | [13 empty] | 2003 | INV | 11666 | 11666 | 0 | 0 | Yes | Yes | Yes
ONG | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (second tranche) | Multi-Year | ASP | CPR | REF | 41 | INV | 406 | A | O | I | CFC | 318 | 318 |  |  | 2003-12-01 | 2006-12-01 | 2007-12-01 | 2010-12-01 |  |  | 2171539 | -15000 | 2156539 | 1861323 | 86.31% | 295216 | 278688 | 150000 | 192239 | -1350 | 164758 | 26131 | 24668 | Technical assistance to compressor manufacturing enterprises was undertaken in 2008. Ban of the use of CFCs in the sector was issued. A TÜV workshop based on plant inspections was performed in 2009, instead of 2008, due to unavaliability of TUV staff. Technical assistance in safety and monitoring and verification of the project performance will continue until end 2010 to ensure sustainability of the project. | [13 empty] | 2003 | INV | 609 | 0 |  |  | Yes | N/A | N/A
FIN | UNIDO | National phase-out of methyl bromide (first tranche) | Multi-Year | ASP | CPR | FUM | 41 | INV | 407 | A | O | I | MBR | 364 | 364 |  |  | 2003-12-01 | 2004-04-01 | 2007-03-01 |  | 2007-12-01 | 2008-09-01 | 4086600 | -1 | 4086599 | 4086599 | 100% | 0 | 0 |  | 306495 | 0 | 306495 | 0 | 0 | Financial completion in Sep 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2003 | INV | 723.8 | 723.8 |  |  | Yes | N/A | N/A
FIN | IBRD | Project preparation for the second phase of process agents phase-out plan |  | ASP | CPR | PAG | 42 | PRP | 408 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2004-12-01 |  | 2006-04-01 | 2007-01-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 9375 | 0 | 9375 | 0 | 0 | Completed technically and financially. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2004 workplan | Multi-Year | ASP | CPR | OTH | 42 | INV | 409 | A | O | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | FIN | [13 empty] | 2003 | INV | 500 | 420 |  |  | Yes | Yes | Yes
COM | UNDP | ODS phase-out in China solvent sector: 2004 annual programme | Multi-Year | ASP | CPR | SOL | 42 | INV | 410 | N | O | I | CFC | 733 | 733 | 0 | 0 | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2006-12-01 |  | 5555000 | 0 | 5555000 | 5555000 | 100% | 0 | 0 | 0 | 416625 | 0 | 416625 | 0 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment | 2335 | 2335 |  |  | yes | yes | yes
COM | IBRD | Sector plan for CFC production phase-out: 2004 annual programme | Multiyear | ASP | CPR | PRO | 42 | INV | 411 | N | O | I | CFC | 0 | 0 | 4700 | 4700 | 2004-04-01 | 2005-11-01 | 2004-12-01 |  | 2005-04-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | Annual Program completed and fully disbursed. | [13 empty] | 2004 | INV | 0 | 0 | 25300 | 25285 | Yes | Yes | Yes
FIN | UNIDO | Preparation of a methyl bromide consumption phase-out plan | Individual | ASP | CPR | FUM | 43 | PRP | 412 | A | O | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2004-12-01 | 2005-05-01 | 20000 | -44 | 19956 | 19956 | 100% | 0 | 0 |  | 1500 | -6 | 1494 | 0 | 0 | FIN | [13 empty] | 2004 | NON-INV
ONG | UNEP | Policy training for local authorities (third tranche) | Individual | ASP | CPR | SEV | 43 | TRA | 413 | A | O | I | CFC | 27.7 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2007-12-01 | 2009-12-01 |  |  | 335000 | 0 | 335000 | 325764.19 | 97.24% | 9235.81 | 0 | 9235.81 | 43550 | 0 | 42349.3447 | 1200.6553 | 0 | Ongoing on-line training - Contract with consultants for evaluation on-line training signed, and evaluation ongoing | [13 empty] | 2004 | Non Investment
COM | Germany | Development of a suitable strategy for the long term management of HCFCs, in particular HCFC-22 | Individual | ASP | CPR | REF | 43 | TAS | 414 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-11-01 | 2005-12-01 |  | 2007-03-01 |  | 300300 | 0 | 300300 | 300297.2 | 100% | 2.8 | 0 | 0 | 39039 | 0 | 39038.636 | 0.364 | 0 | Project was completed and approved by the Chinese authorities. Project report was submitted to 51st ExCom. PCR was submitted in December 2008.
FIN | IBRD | Project preparation for pharmaceutical aerosol |  | ASP | CPR | ARS | 43 | PRP | 415 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2005-07-01 |  | 2007-03-01 | 2007-07-01 | 135500 | 0 | 135500 | 135500 | 100% | 0 | 0 |  | 10163 | 0 | 10163 | 0 | 0 | Completed technically and financially. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2004 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 43 | INV | 416 | N | O | I | CTC | 0 | 0 | 6657 | 6657 | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 |  | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 | 0 | 1200000 | 0 | 1200000 | 0 | 0 | Implemented as planned and fully disbursed. | [13 empty] | 2004 | INV | 5063 | 5063 | 54857 | 52353 | Yes | Yes | Yes
COM | IBRD | Strategy for gradual phase-out of 1,1,1-trichlorethane (TCA) production (first stage programme) | Multiyear | ASP | CPR | PRO | 43 | INV | 417 | N | O | I | TCA | 0 | 0 | 33.8 | 33.8 | 2004-07-01 | 2005-12-01 | 2008-07-01 |  | 2008-07-01 |  | 1400000 | 0 | 1400000 | 1140000 | 81.43% | 260000 | 260000 | 260000 | 105000 | 0 | 85500 | 19500 | 19500 | Activities under this tranche have been completed. The last tranche will be disbursed to China in early 2009. | [13 empty] | 2003 | INV | 0 | 0 | 113 | 78 | Yes | Yes | Yes
COM | UNIDO | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 419 | A | O | I | CFC | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 |  | 1000000 | -450000 | 550000 | 388557 | 70.65% | 161443 | 161400 | 100000 | 75000 | -33750 | 29142 | 12108 | 12105 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2004 | INV | 3790 | 3790 |  |  | Yes | Yes | Yes
COM | Japan | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 420 | A | O | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2005-12-01 |  | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 130000 | 0 | 130000 | 0 | 0 | A monitoring officer is stationed at the NOU on a regular basis to communicate with the ozone officer and different NOU officers in charge of individual project components, compiling the records of financial expenditure and implementation progress. On a monthly basis, the “project budget details” table and the “progress details” table, among other things, are updated. |  | 2004 | [12 empty] | investment | 5083 | 4868 | not applicable | not applicable | Yes
COM | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | CPR | SEV | 44 | INS | 421 | N | T | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 |  | 390000 | 0 | 390000 | 389871 | 99.97% | 129 | 0 | 103.2 | 29250 | 0 | 29240.325 | 9.675 | 0 | Completed in 2006. | [13 empty] | 2004 | Non-Investment
COM | UNIDO | Preparation of a MDI sector plan | Individual | ASP | CPR | ARS | 44 | PRP | 422 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-07-01 |  | 90000 | 0 | 90000 | 68923 | 76.58% | 21077 | 20700 | 20100 | 6750 | 0 | 5169 | 1581 | 1553 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2004
COM | IBRD | Sector plan for halon phase-out in China: 2005 annual programme | Multiyear | ASP | CPR | HAL | 44 | INV | 423 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2005-11-01 |  | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 | 0 | 135000 | 0 | 135000 | 0 | 0 | technically and financially completed. | [13 empty] | 2004 | INV | 7170 | 4502 | 7970 | 5478 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2005 annual programme | Multiyear | ASP | CPR | FOA | 44 | INV | 424 | N | O | I | CFC | 2500 | 2500 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2005-12-01 |  | 2005-12-01 |  | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 | 0 | 961270 | 0 | 961270 | 0 | 0 | The annual program has been completed except for one TA activity which is still ongoing. Disbursement have been completed. | [13 empty] | 2004 | INV | 9000 | 6085 | 0 | 0 | Yes | Yes | Yes
COM | USA | CFCs, CTC and halon accelerated phase-out plan (first tranche) | Multi-Year | ASP | CPR | PRO | 44 | INV | 425 | A | O | I |  | 0 |  | 0 |  | 2004-12-01 | 2006-10-01 | 2005-12-01 |  | 2006-10-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 | 0 | 375000 | 0 | 375000 | 0 | 0 | Completed. Funds disbursed in Oct. 2006. | [15 empty] | 7170 | 4448 | 26720 | 24198 | Yes
ONG | UNEP | Refrigeration servicing sector CFC phase-out plan (revised 2005 annual implementation programme) | Multi-year | ASP | CPR | REF | 45 | TAS | 426 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-12-01 | 2009-12-01 |  |  | 450000 | 0 | 450000 | 316345 | 70.3% | 133655 | 0 | 133655 | 58500 | 0 | 41124.85 | 17375.15 | 0 | MEP jointly with the Ministry of Transportation organized one workshop on CFC recovery and emission reduction in the MAC servicing sector during 27-28 November 2008. More than 100 participants from provincial transportation bureau attended the workshop to review the CFC recovery/recylcing programme and other policy issues at the national level. | [13 empty] | 2005 | Non Investment
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2005 | Multi-Year | ASP | CPR | OTH | 45 | INV | 427 | A | O | I | CFC | 200 | 200 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-03-01 | 1700000 | 0 | 1700000 | 1700000 | 100% | 0 | 0 |  | 127500 | 0 | 127500 | 0 | 0 | FIN | [13 empty] | 2005 | INV | 300 | 220 |  |  | Yes | Yes | Yes
COM | IBRD | Sector plan for CFC production phase-out: 2005 annual programme | Multiyear | ASP | CPR | PRO | 45 | INV | 428 | N | O | I | CFC | 0 | 0 | 6500 | 6500 | 2005-04-01 | 2005-12-01 | 2005-12-01 |  | 2006-04-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | Fully completed and disbursed. 2005 CFC production was verified and within the control target. | [13 empty] | 2005 | INV | 0 | 0 | 18750 | 18720.49 | Yes | Yes | Yes
ONG | UNDP | ODS phase-out in China solvent sector: 2005 annual programme | Multi-Year | ASP | CPR | SOL | 45 | INV | 429 | N | O | I | TCA/CTC | 635 | 635 | 0 | 0 | 2005-04-01 | 2007-02-01 | 2006-04-01 | 2010-01-01 |  |  | 5680000 | 0 | 5680000 | 2686466 | 47.3% | 2993534 | 451 | 598706.8 | 426000 | 0 | 201484.95 | 224515.05 | 33.825 | The last payment for 12 provinces/cities certified as Ozone-Friendly for early phase-out completed. The last payment for three activities for combating Illegal trade/use completed. | [13 empty] | 2005 | Investment | 1602 | 1602 |  |  | yes | yes | yes
FIN | UNIDO | Preparation of a production phase-out plan in the fumigants sector (methyl bromide) | Individual | ASP | CPR | FUM | 45 | PRP | 430 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-12-01 | 2006-02-01 | 40000 | -31 | 39969 | 39969 | 100% | 0 | 0 |  | 3000 | -7 | 2993 | 0 | 0 | FIN | [13 empty] | 2005 | NON-INV
ONG | Italy | National phase-out of methyl bromide (phase II) | Multi-year | ASP | CPR | FUM | 46 | INV | 431 | A | O | I | MBR | 534 | 88 | 0 |  | 2005-07-01 | 2007-03-01 | 2015-07-01 | 2015-07-01 |  |  | 4000000 | 0 | 4000000 | 2000569 | 50.01% | 1999431 | 1999431 | 1999431 | 470000 | 0 | 235066.8575 | 234933.1425 | 234933.1425 | Equipment procurement for the tobacco seedling sector was undertaken, in time for the crop season 2008. Subcontract for the ongoing tranche was issued in November 2008 and the final report is expected in July 2009. | Multi-Year Current Tranche - Actual Consumption (ODP Tonnes) was submitted as "n.a." | 2005 | [11 empty] | 2005 | Investment | 446 |  | 0 | 0 | Yes
COM | IBRD | Process agent sector plan (phase I): 2005 annual programme | Multiyear | ASP | CPR | PAG | 46 | INV | 432 | N | O | I | CTC | 4556 | 4556 | 16171 | 16171 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-07-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | Fully completed and disbursed; 2005 targets met. | [13 empty] | 2005 | INV | 1454 | 1397.9 | 38686 | 33080 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phase-out in China: 2006 annual programme | Multiyear | ASP | CPR | HAL | 47 | INV | 433 | N | O | I | HAL | 6170 | 6170 | 10470 | 10470 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-11-01 |  | 11400000 | 0 | 11400000 | 11400000 | 100% | 0 | 0 | 0 | 855000 | 0 | 855000 | 0 | 0 | Annual program technically and financially completed. | [13 empty] | 2005 | INV | 1000 | 1000 | 1000 | 1000 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2006 annual programme | Multiyear | ASP | CPR | FOA | 47 | INV | 434 | N | O | I | CFC | 600 | 600 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 |  | 2008-10-01 |  | 3320000 | 0 | 3320000 | 3320000 | 100% | 0 | 0 | 0 | 282800 | 0 | 282800 | 0 | 0 | The four provincial CFC-11 phaseout contracts are under implementation. All funds under this AP has been disbursed to China as China has met all performance targets. | [13 empty] | 2005 | INV | 7000 | 7000 | 0 | 0 | Yes | Yes | Yes
ONG | UNDP | ODS phase-out in China solvent sector: 2006 annual programme | Multi-Year | ASP | CPR | SOL | 47 | INV | 435 | N | O | I | TCA/CTC | 85 | 85 | 0 | 0 | 2005-11-01 |  | 2006-12-01 | 2010-12-01 |  |  | 5055000 | 0 | 5055000 | 0 | 0% | 5055000 | 0 | 1011000 | 379125 | 0 | 0 | 379125 | 0 | The conversions at remaining 2 enterprises with 4.3 ODP tons achieved in 2008. The disbursement for 2006 TCA phase-out contracts completed. Two training workshops under the joint sub-project with China Custom for Monitoring the Illegal Trade held in April and October; and equipments to verify the ODS trade purchased and applied in local custom. | [13 empty] | 2005 | Investment | 974 | 974 |  |  | yes | yes | yes
COM | UNIDO | Sector plan for methyl bromide production sector (first tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 436 | A | O | I | MBR | 0 | 0 | 231 | 231 | 2005-11-01 | 2006-06-01 | 2008-12-01 |  | 2008-12-01 |  | 3000000 | 0 | 3000000 | 2666061 | 88.87% | 333939 | 294500 | 290000 | 225000 | 0 | 199955 | 25045 | 22088 | Final report due to Dec 2008, final payment released, USD 39,439 will be available for auditing of Phase II, III and IV. The project completed in Dec 2008. | [13 empty] | 2005 | INV |  |  | 570.6 | 540 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production (first tranche) | Multiyear | ASP | CPR | PAG | 47 | INV | 437 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2007-09-01 |  | 15000000 | 0 | 15000000 | 15000000 | 100% | 0 | 0 | 0 | 1125000 | 0 | 1125000 | 0 | 0 | 2006 AP, made up of this project and CPR/PAG/48/INV/440, is under implementation. | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0
ONG | Japan | Refrigeration servicing sector CFC phase-out plan (second tranche) | Multi-Year | ASP | CPR | REF | 47 | INV | 438 | A | O | I | CFC | 511 | 511 | 0 |  | 2005-11-01 | 2006-11-01 | 2006-12-01 | 2007-12-01 |  |  | 3000000 | 0 | 3000000 | 709004 | 23.63% | 2290996 | 137100 | 1000000 | 390000 | 0 | 92171 | 297829 | 17823 | Revised annual implementation plan was approved by 45th ExCom in Apr 2005. The second tranche (Japanese contribution) was approved by 47th ExCom in Nov 2005. Institution and trainers were selected for training of trainers workshops. In 2006, training of t |  | 2005 | [12 empty] | investment
ONG | USA | CFCs, CTC and halon accelerated phase-out-plan (second tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 439 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 | 2009-12-01 |  |  | 5000000 | 0 | 5000000 | 0 | 0% | 5000000 | 5000000 | 5000000 | 375000 | 0 | 0 | 375000 | 375000 | Ongoing. | [15 empty] | 1000 | 1000 | 8400 | 7289 | Yes
COM | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 440 | N | O | I | CTC | 0 | 0 | 6642 | 6642 | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2007-04-01 |  | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 | 0 | 1200000 | 0 | 1200000 | 0 | 0 | Allowed CTC production in 2006 revised taking into account the new PA II Agreement and APP agreement. A total max. allowable sum of production and imports of CTC was 28,662 ODP tons. Consumption for PAI will be kept as the same level as 2005. Phaseout target met and will be verified in early 2007. Two disbursements of 2006 AP made in 2006. | [13 empty] | 2006 | INV | 493 | 461.4 | 28662 | 28476.22 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 441 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-12-01 | 2007-04-01 |  | 2007-12-01 |  | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 | 0 | 750000 | 0 | 750000 | 0 | 0 | Under implementation. | [13 empty] | 2006 | INV | 6945 | 5825.2 | 0 | 0 | Yes | Yes | Yes
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2006-2007 | Multi-Year | ASP | CPR | OTH | 48 | INV | 442 | A | O | I | CFC | 150 | 150 |  |  | 2006-04-01 | 2007-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-05-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 |  | 112500 | 0 | 112500 | 0 | 0 | Financial completion in May 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2006 | INV | 150 | 150 |  |  | Yes | Yes | Yes
COM | IBRD | Sector plan for CFC production phase-out: 2006 annual programme | Multiyear | ASP | CPR | PRO | 48 | INV | 443 | N | O | I | CFC | 0 | 0 | 5250 | 5250 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-04-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 | 0 | 975000 | 0 | 975000 | 0 | 0 | CFC production phaseout target for 2006 has been met. The Bank will verify 2006 CFC production early 2007. Two tranches were disbursed in 2006. | [13 empty] | 2006 | INV | 0 | 0 | 13500 | 13498 | Yes | Yes | Yes
COM | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | CPR | SEV | 50 | INS | 444 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 |  | 390000 | 0 | 390000 | 389587 | 99.89% | 413 | 0 | 330.4 | 29250 | 0 | 29219.025 | 30.975 | 0 | The designed activities under the project completed in 2008. The policy and enforcement actions strengthened. The public awareness improved. The sustainability of early phase-out enhanced. | [13 empty] | 2006 | Non-Investment
COM | IBRD | Sector plan for halon phase-out in China: 2007 annual programme | Multiyear | ASP | CPR | HAL | 50 | INV | 445 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-10-01 | 2007-11-01 |  | 2008-10-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | One TA activity is under implementation: Shenyan Fire Research Institute was selected as a beneficiary to study integrated control technology for various halon alternatives and automatic fire detection systems combined and the contract was signed in December 31, 2008. All funds under this AP has been disbursed from the Bank to China in 2008. | [13 empty] | 2007 | INV | 1000 | 1000 | 1000 | 1000 | Yes | Yes | Yes
ONG | UNDP | ODS phase-out in China solvent sector: 2007 annual programme | Multi-Year | ASP | CPR | SOL | 50 | INV | 446 | N | O | I | TCA/CTC | 85 | 85 | 0 | 0 | 2006-11-01 |  | 2008-12-01 | 2010-12-01 |  |  | 5480000 | 0 | 5480000 | 0 | 0% | 5480000 | 0 | 1096000 | 411000 | 0 | 0 | 411000 | 0 | Workshop organized May 2008 to attract interested enterprises to participate TCA phase-out activities. 1 enterprise completed the project, with 1.8 ODP tons achieved in 2008 and remaining ODP tones to be reflected in 2009. Disbursements will be reflected as soon as disbursements of previous phase will be exhausted as they are managed as one programme. The sub-project, Local Environment Protection Bureaus (EPBs) Capacity Building for Compliance with the Montreal Protocol, implemented smoothly. The 19 EPBs initiated the data survey; established or revised the local regulations on controlling ODS production, consumption, transportation and distribution; enhanced the public awareness on ozone protection etc. The first payment to 19 EPBs completed. Disbursement will be reflected when previous tranches depleted. | [13 empty] | 2006 | Investment | 339 | 339 |  |  | yes | yes | yes
ONG | IBRD | Phase-out of CFC consumption in the pharmaceutical aerosol sector (2007-2008 biennial programme) | One off phaseout | ASP | CPR | ARS | 51 | INV | 447 | N | O | I | CFC | 485.1 | 0 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2011-03-01 | 2011-03-01 |  |  | 6000000 | 0 | 6000000 | 1500000 | 25% | 4500000 | 4500000 | 2250000 | 450000 | 0 | 112500 | 337500 | 337500 | Under implementation. The first tranch of disbursement has been made from the Bank to China. | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0
COM | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2007 annual programme | Multiyear | ASP | CPR | PAG | 51 | INV | 448 | N | O | I | CTC | 0 | 0 | 6642 | 6642 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 | 0 | 375000 | 0 | 375000 | 0 | 0 | Activities under this annual program have been completed. Disbursement has been completed. | [13 empty] | 2007 | INV | 501 | 482 | 18738 | 13438 | Yes | Yes | Yes
COM | IBRD | Sector plan for CFC production phase-out: 2007 annual programme | Multiyear | ASP | CPR | PRO | 51 | INV | 449 | N | O | I | CFC | 0 | 0 | 6100 | 6100 | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-03-01 |  | 24000000 | 0 | 24000000 | 24000000 | 100% | 0 | 0 | 0 | 1800000 | 0 | 1800000 | 0 | 0 | Completed. CFC phaseout targets in 2007 met. | [13 empty] | 2007 | INV | 0 | 0 | 7400 | 6289.04 | Yes | Yes | Yes
COM | UNIDO | Refrigeration servicing sector CFC phase-out plan (third tranche) | Multi-Year | ASP | CPR | REF | 51 | INV | 450 | A | O | I | CFC | 782 | 782 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-12-01 |  | 700000 | 0 | 700000 | 325500 | 46.5% | 374500 | 374500 | 300000 | 52500 | 0 | 24412.5 | 28087.5 | 28087.5 | Project completed in Dec 2008. | [13 empty] | 2007 | INV | 2997 | 2997 |  |  | Yes | Yes | Yes
FIN | UNIDO | National phase-out of methyl bromide (phase II, second tranche) | Multi-Year | ASP | CPR | FUM | 52 | INV | 451 | A | O | I | MBR | 65.2 | 65.2 |  |  | 2007-07-01 | 2008-02-01 | 2008-07-31 |  | 2008-09-01 | 2008-09-01 | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | Project completed in Sep 2008. Financial completion in Sep 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2007 | INV | 570.6 | 389.3 |  |  | Yes | N/A | N/A
COM | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2007 annual programme | Multiyear | ASP | CPR | PAG | 52 | INV | 452 | N | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-07-01 |  | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 | 0 | 750000 | 0 | 750000 | 0 | 0 | Actitities under this annual program have been completed, and the funding has been fully disbursed. | [13 empty] | 2007 | INV | 6945 | 5176 | 0 | 0 | Yes | Yes | Yes
ONG | UNIDO | Refrigeration servicing sector CFC phase-out plan (fourth tranche) | Multi-Year | ASP | CPR | REF | 53 | INV | 453 | A | O | I | CFC | 793 | 0 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 | 2009-11-01 |  |  | 700000 | 0 | 700000 | 202800 | 28.97% | 497200 | 201000 | 200000 | 52500 | 0 | 15210 | 37290 | 15075 | During 2008 the training of technicians has continued and technicians were provided with recovery and service tools. Training centers for the domestic and industrial refrigeration were established and additional training of service technicians and purchase of equipment for the technicians as well as continued monitoring of activities is planned for 2009 and onwards. | [13 empty] | 2007 | INV | 2997 | 2997 |  |  | Yes | Yes | Yes
ONG | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2007 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 454 | N | O | I | CFC | 551 | 551 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 | 2009-11-30 |  |  | 2676000 | 0 | 2676000 | 1503000 | 56.17% | 1173000 | 1173000 | 1173000 | 240840 | 0 | 135270 | 105570 | 105570 | Under implementation. The limits given in the PU foam/APP agreement for national CFC-11 consumption and CFC-11 consumption in the foam sector were both met. 24 individual contracts (7 contracts signed in 2007 and 17 contracts signed 2008) accounting for 746.239 tons of CFC-11 phaseout have been signed with total grant of US$ 2,176,961.14. The 2007 phaseout target of 551 tons has also been met. | [13 empty] | 2006 | INV | 400 | 400 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2008 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 455 | N | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 | 2009-11-30 |  |  | 1767000 | 0 | 1767000 | 1263500 | 71.51% | 503500 | 503500 | 503500 | 159030 | 0 | 113715 | 45315 | 45315 | There will be no phaseout contract to be signed for the 2008 Annual Program. Most of the funding for the 2008 AP has been committed to CFC-11 phaseout contracts signed for the previous APs. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 | Yes | No | No
ONG | IBRD | Sector plan for halon phase-out in China: 2008 annual programme | Multiyear | ASP | CPR | HAL | 53 | INV | 456 | N | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 | 2010-12-01 |  |  | 300000 | 0 | 300000 | 150000 | 50% | 150000 | 150000 | 150000 | 22500 | 0 | 11250 | 11250 | 11250 | Under implementation. Two tranches of disbursement have been made. One TA activity is under implementation: Shenyan Fire Research Institute was selected as a beneficiary to study integrated control technology for various halon alternatives and automatic fire detection systems combined and the contract was signed in December 31, 2008. | [13 empty] | 2007 | INV | 1000 | 1000 | 1000 | 1000 | Yes | No | No
ONG | UNDP | ODS phase-out in China solvent sector: 2008 annual programme | Multi-Year | ASP | CPR | SOL | 53 | INV | 457 | N | O | I | TCA | 85 | 85 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 |  |  | 1480000 | 0 | 1480000 | 0 | 0% | 1480000 | 0 | 296000 | 111000 | 0 | 0 | 111000 | 0 | Signed contract with 11 enterprises verified eligible to participate in TCA phase-out sub-project with 28.9 ODP tones phase-out to be achieved in 2009 and 2010. The first payment completed. Disbursement will be reflected when previous tranches depleted. | [13 empty] | 2007 | Investment | 254 |  |  |  | Latest | Latest | Latest
ONG | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2008 annual programme | Multiyear | ASP | CPR | PAG | 54 | INV | 458 | N | O | I | CTC | 0 | 0 | 10594 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2009-03-31 |  |  | 3000000 | 0 | 3000000 | 1500000 | 50% | 1500000 | 1500000 | 1500000 | 225000 | 0 | 112500 | 112500 | 112500 | Ongoing as scheduled. Two disbursements from the Bank to China have been made. | [13 empty] | 2007 | INV | 493 | 483 | 8188.7 | 3835 | Yes | Yes | Yes
ONG | IBRD | Sector plan for CFC production phase-out: 2008 annual programme | Multiyear | ASP | CPR | PRO | 54 | INV | 459 | N | O | I | CFC | 0 | 0 | 6850 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2009-03-31 |  |  | 7500000 | 0 | 7500000 | 3750000 | 50% | 3750000 | 3750000 | 3750000 | 562500 | 0 | 281250 | 281250 | 281250 | Under implementation. Two tranches of disbursement have been made. | [13 empty] | 2007 | INV | 0 | 0 | 550 | 548 | Yes | Yes | Yes
ONG | UNDP | Preparation of a HCFC phase-out management plan: industrial and commercial refrigeration sub-sectors | Individual | ASP | CPR | PHA | 55 | PRP | 460 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 604000 | 0 | 604000 | 0 | 0% | 604000 | 0 | 604000 | 45300 | 0 | 0 | 45300 | 0 | Approved at 55th ExCom. TOR and work plan for all activities finalized. Interaction meetings with the sector working group and industry representatives held during two missions in 2008. Recruitment of national expert entity is in process. Initial expenditures reflected under CPR-464. | [13 empty] | 2008 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan: solvent sector | Individual | ASP | CPR | PHA | 55 | PRP | 461 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 432000 | 0 | 432000 | 0 | 0% | 432000 | 0 | 432000 | 32400 | 0 | 0 | 32400 | 0 | Approved at 55th ExCom. TOR and work plan for all activities finalized. Interaction meetings with the sector working group and industry representatives held during two missions in 2008. Recruitment of national expert entity is in process. Initial expenditures reflected under CPR-464. | [13 empty] | 2008 | Investment
ONG | UNIDO | National phase-out of methyl bromide (phase II, third tranche) | Multi-Year | ASP | CPR | FUM | 55 | INV | 462 | A | O | I | MBR | 124.6 | 124.6 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-07-01 |  |  | 1800000 | 0 | 1800000 | 180000 | 10% | 1620000 | 1620000 | 1620000 | 135000 | 0 | 13500 | 121500 | 121500 | Equipment procurement for the tobacco seedling sector was undertaken, in time for the crop season 2008. Subcontract for the ongoing tranche was issued in November 2008 and the final report is expected in July 2009. | [13 empty] | 2008 | INV | 390 | 380 |  |  | Yes | No | No
ONG | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2008 annual programme | Multiyear | ASP | CPR | PAG | 55 | INV | 463 | N | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-07-31 |  |  | 10000000 | 0 | 10000000 | 5500000 | 55% | 4500000 | 4500000 | 4500000 | 750000 | 0 | 412500 | 337500 | 337500 | Ongoing as scheduled. Two disbursement from the Bank to China have been made. | [13 empty] | 2007 | INV | 6945 | 6945 | 0 | 0 | Yes | No | No
ONG | UNDP | Preparation of an overarching HPMP strategy | Individual | ASP | CPR | PHA | 55 | PRP | 464 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-08-01 | 2009-07-01 | 2010-04-01 |  |  | 360000 | 0 | 360000 | 22868 | 6.352% | 337132 | 0 | 337132 | 27000 | 0 | 1715.1 | 25284.9 | 0 | Approved at 55th ExCom. TOR and work plan for all activities finalized. Meetings with the working group held during two missions in 2008. Recruitment of national expert entity is in process. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan: refrigeration servicing sub-sector | RMP | ASP | CPR | PHA | 55 | PRP | 465 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2010-12-10 |  |  | 375000 | 0 | 375000 | 173432.12 | 46.25% | 201567.88 | 0 | 201567.88 | 48750 | 0 | 22546.1756 | 26203.8244 | 0 | The initial mission to the country on 27-29 October 2008, and agreement reached on the work plan, as well as the survey forms with the indsutry associations and FECO/MEP. The SSFA was drafted and finalized for signautre by December 2008. UNEP also participated the first coordination meeting organized by China during 9-10 | [13 empty] | 2008
ONG | UNIDO | Preparation of a HCFC phase-out management plan (XPS foam sector) | Individual | ASP | CPR | PHA | 55 | PRP | 466 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 84000 | 0 | 84000 | 0 | 0% | 84000 | 0 | 15000 | 6300 | 0 | 0 | 6300 | 0 | Organization of expert meeting on technologies. | UNIDO is only cooperating agency together with UNDP in this sector, while GTZ has the lead. UNIDO provided its contributions to the preparation of the TOR already in November 2008. In addition, during the IA coordination meeting held in December 2008 in Beijing, it was agreed that UNIDO's scope of activities would be focusing on providing expertise for the review and the selection of alternative technologies including organization of expert group meetings on this subject. UNIDO was informed by MEP/FECO and GTZ that the kick-off meeting for the subject sector would be held 14 May 2009 only. Work on legislation is not part of UNIDO's scope of activities. | [12 empty] | 2008 | NON-INV
ONG | IBRD | Preparation of a HCFC phase-out management plan: HCFC production sector |  | ASP | CPR | PHA | 55 | PRP | 467 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 | 2010-07-01 |  |  | 473300 | 0 | 473300 | 0 | 0% | 473300 | 473300 | 331310 | 35498 | 0 | 0 | 35498 | 35498 | Ongoing as scheduled. The overall TOR for preparing the HCFC production phaseout sector plan has been agreed in Sept. 2008. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of a HCFC phase-out management plan: polyurethane foam sector |  | ASP | CPR | PHA | 55 | PRP | 468 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-12-31 | 2010-07-01 |  |  | 685900 | 0 | 685900 | 137180 | 20% | 548720 | 548720 | 480130 | 51443 | 0 | 10288.6 | 41154.4 | 41154.4 | Ongoing as scheduled. The overall TOR for preparing the HCFC sector-based phaseout plan in the PU foam sector was agreed in Sept. 2008. The first disbursement to China was made in Nov. 2008. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
ONG | Germany | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 469 | A | O | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2008-09-01 | 2009-07-01 | 2010-07-01 |  |  | 201369 | 0 | 201369 | 21500 | 10.68% | 179869 | 0 | 95600 | 26178 | 0 | 2795.0032 | 23382.9968 | 0 | Meetings with the Chinese partner took place and the activity plan has been finalized. A financial contribution contract has been prepared which will start early 2009. At this time (May 09) dedicated staff and consultants are working on the surveys, other data gathering and the structure of the plan. The questionnaire is agreed with MEP/FECO, legislation and regulatory work will be discussed during June 2009 in China with MEP/FECO.
ONG | UNIDO | Preparation of a HCFC phase-out management plan (Room air-conditioning sector) | Individual | ASP | CPR | PHA | 55 | PRP | 470 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2010-04-01 |  |  | 500000 | 0 | 500000 | 127796 | 25.56% | 372204 | 6090 | 140000 | 37500 | 0 | 9585 | 27915 | 457 | Inception workshop for the HPMP preparation took place in December 2008 with the participation of all implementing and bilateral agencies involved in the China HPMP. Detailed plan of action has been agreed upon with at least 2 coordination meetings per year. UNIDO's sub-contract with MEP/FECO was sigend end November 2008. | UNIDO made a sub-contract with MEP/FECO and the first payment has already been released. Although UNDP is in charge of the HPMP preparation and is responsible for the legislation component, UNIDO's sub-contract with MEP/FECO did include activities related to legislation and policy development. Drafting of sectoral level policy and regulatory framework of HCFC phase-out in the room air conditioning sector and its adoption by an expert seminar is expected by end 2009. UNIDO is responsible for the investment component for the RAC sector. Planned completion date is based on the plan of action approved by MEP/FECO at the interagency coordination meeting in December 2009. Each HPMP component has to be coordinated and since China is by far the biggest HCFC consumer among A5 countries, one year for the completion of the HPMP was not realistic. | [12 empty] | 2008 | NON-INV
ONG | UNDP | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 471 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 84000 | 0 | 84000 | 0 | 0% | 84000 | 0 | 84000 | 6300 | 0 | 0 | 6300 | 0 | Approved at 55th ExCom. GTZ is lead agency and UNDP and UNIDO are cooperating agencies. The proposals for distribution of work between the three agencies is under consideration by FECO. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan: enabling components | RMP | ASP | CPR | PHA | 55 | PRP | 472 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2010-12-10 |  |  | 100000 | 0 | 100000 | 70000 | 70% | 30000 | 0 | 30000 | 13000 | 0 | 9100 | 3900 | 0 | The initial mission to the country on 27-29 October 2008, and agreement reached on the work plan. The SSFA was drafted and finalized for signautre by December 2008. UNEP also participated the first cooridation meeting organized by China during 9-10 December 2008. | [13 empty] | 2008
ONG | UNIDO | Sector plan for phase-out of CFCs consumption in MDI sector | Individual | ASP | CPR | ARS | 56 | INV | 473 | A | O | I | CFC | 322.5 | 0 |  |  | 2008-11-01 |  | 2013-12-31 | 2013-12-01 |  |  | 13500000 | 0 | 13500000 | 0 | 0% | 13500000 | 0 | 1500000 | 1012500 | 0 | 0 | 1012500 | 0 | The sector plan for the entire phase out of CFCs in the MDI sector in China was approved at the 56th ExCom Meeting. Implementation modalities have been agreed upon in December 2008. Terms of Reference are under preparation and it is expected that a subcontract will be signed with the Chinese counterpart in 2nd Quarter 2009. | [13 empty] | 2008 | INV
ONG | UNIDO | Refrigeration servicing sector CFC Phase-out Plan (fifth tranche) | Multi-Year | ASP | CPR | REF | 56 | INV | 474 | A | O | I | CFC | 680 | 0 |  |  | 2008-11-01 | 2008-12-01 | 2009-11-30 | 2010-12-01 |  |  | 700000 | 0 | 700000 | 206018 | 29.43% | 493982 | 0 | 200000 | 52500 | 0 | 15451 | 37049 | 0 | During 2008 the training of technicians has continued and technicians were provided with recovery and service tools. Training centers for the domestic and industrial refrigeration were established and additional training of service technicians and purchase of equipment for the technicians as well as continued monitoring of activities is planned for 2009 and onwards. | [13 empty] | 2008 | INV | 2317 | 2137 |  |  | Not yet confirmed | No | No
ONG | UNIDO | Sector plan for methyl bromide production sector (second tranche) | Multi-Year | ASP | CPR | PRO | 56 | INV | 475 | A | O | I |  | 0 | 0 | 214 |  | 2008-11-01 |  | 2011-11-30 | 2011-11-01 |  |  | 3000000 | 0 | 3000000 | 0 | 0% | 3000000 | 2700000 | 300000 | 225000 | 0 | 0 | 225000 | 202500 | Note: maximum MB production quota of 390 ODP tonnes (2008) confirmed. MB production audit and supplementary verification of the MB feedstock use, both for the period 2005 to 2007, completed. Production data are in line with those agreed at the 47th ExCom. | [13 empty] | 2008 | INV |  |  | 390 | 380.5 | Yes | No | No
ONG | UNEP | Awareness/outreach activities on HCFC phase-out and its challenges during HPMP preparatory phase | Individual | ASP | CPR | SEV | 56 | TAS | 476 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-31 | 2010-12-31 |  |  | 140000 | 0 | 140000 | 0 | 0% | 140000 | 0 | 140000 | 18200 | 0 | 0 | 18200 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | CPR | SEV | 56 | INS | 477 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-01 | 2010-12-01 |  |  | 390000 | 0 | 390000 | 0 | 0% | 390000 | 0 | 78000 | 29250 | 0 | 0 | 29250 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
ONG | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2009 annual programme | Multiyear | ASP | CPR | FOA | 56 | INV | 478 | N | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 1767000 | 0 | 1767000 | 0 | 0% | 1767000 | 1767000 | 883500 | 159030 | 0 | 0 | 159030 | 159030 | Ongoing as scheduled. | [13 empty] | 2008 | INV | 0 | 0 | 0 | 0
ONG | UNDP | ODS phase-out in China solvent sector: 2009 annual programme | Multi-Year | ASP | CPR | SOL | 56 | INV | 479 | N | O | I | TCA | 84 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 1480000 | 0 | 1480000 | 0 | 0% | 1480000 | 0 | 592000 | 111000 | 0 | 0 | 111000 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | IBRD | Strategy for gradual phase-out of 1,1,1-trichloroethane (TCA) production (second stage programme) | Multiyear | ASP | CPR | PRO | 56 | INV | 480 | N | O | I | TCA | 0 | 0 | 79 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 700000 | 0 | 700000 | 0 | 0% | 700000 | 700000 | 350000 | 52500 | 0 | 0 | 52500 | 52500 | Ongoing as scheduled. | [13 empty] | 2007 | INV | 0 | 0 | 79 | 79 | Yes | No | No
ONG | IBRD | Sector plan for halon phase-out in China: 2009 annual programme | Multiyear | ASP | CPR | HAL | 56 | INV | 481 | N | O | I | HAL | 1000 | 0 | 1500 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 100000 | 50000 | 7500 | 0 | 0 | 7500 | 7500 | Ongoing as scheduled. | [13 empty] | 2008 | INV | 1000 | 0 | 0 | 0 | No | No | No
FIN | UNEP | Country programme preparation | Individual | EUR | CRO | SEV | 16 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | EUR | CRO | SEV | 20 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 101200 | 0 | 101200 | 101200 | 100% | 0 | 0 | 0 | 13156 | 0 | 13156 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | EUR | CRO | FOA | 21 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -686 | 29314 | 29314 | 100% | 0 | 0 |  | 3900 | -95 | 3805 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Oriolik Co. flexible polyurethane foam plant | Individual | EUR | CRO | FOA | 22 | INV | 4 | A | O | I | CFC | 25 | 25 |  |  | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-11-01 | 2000-07-01 | 110780 | -24 | 110756 | 110756 | 100% | 0 | 0 |  | 14401 | -26 | 14375 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Pliva D.D. | Individual | EUR | CRO | ARS | 22 | INV | 5 | A | O | I | CFC | 10.6 | 10.6 |  |  | 1997-05-01 | 1997-10-01 | 1998-08-01 |  | 2000-10-01 | 2001-12-01 | 89779 | -2344 | 87435 | 87435 | 100% | 0 | 0 |  | 11671 | -323 | 11348 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | CRO | REF | 24 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-02-01 | 1999-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (tobacco, tomatoes) | Individual | EUR | CRO | FUM | 24 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Two alternatives to the use of methyl bromide in tobacco production; namely: solarization plus bio-fumigation, the use of low-dose chemicals, and non-soil cultivation, in combination with an integrated pest management programme | Individual | EUR | CRO | FUM | 25 | DEM | 8 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-09-01 | 2000-08-01 |  | 2001-05-01 | 2003-03-01 | 288200 | -28165 | 260035 | 260035 | 100% | 0 | 0 |  | 37466 | -3715 | 33751 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | EUR | CRO | REF | 28 | TRA | 9 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2003-02-01 | 2003-07-01 | 70000 | -1483 | 68517 | 68517 | 100% | 0 | 0 |  | 9100 | -207 | 8893 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | EUR | CRO | REF | 28 | TAS | 10 | A | O | I | CFC | 15 | 15 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2003-10-01 | 289910 | -3739 | 286171 | 286171 | 100% | 0 | 0 |  | 37688 | -545 | 37143 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | CRO | SEV | 29 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2001-12-01 |  | 2002-03-01 | 2003-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 | 0 | 0 | 8710 | 0 | 8710 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNIDO | Refrigerant management plan: customs training | RMP | EUR | CRO | REF | 28 | TRA | 12 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 2001-04-01 | 2001-08-01 |  | 2002-06-01 | 2003-07-01 | 38250 | -2227 | 36023 | 36023 | 100% | 0 | 0 |  | 4973 | -297 | 4676 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the tobacco fumigation sector | Individual | EUR | CRO | FUM | 33 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -16341 | 13659 | 13659 | 100% | 0 | 0 |  | 3900 | -2127 | 1773 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Phase out of methyl bromide in tobacco seedlings | Individual | EUR | CRO | FUM | 35 | INV | 14 | A | O | I | MBR | 16.2 | 16.2 |  |  | 2001-12-01 | 2002-07-01 | 2007-01-01 |  | 2006-12-01 | 2007-12-01 | 476833 | -5789 | 471044 | 471044 | 100% | 0 | 0 |  | 61988 | -752 | 61236 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2001 | INV
FIN | Sweden | Assistance to prepare an RMP update | Individual | EUR | CRO | REF | 36 | PRP | 15 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2004-03-04 | 2004-04-04 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0 | At the 36th meeting in March 2002 Sweden received approval for assisting the Government of Croatia in updating their Refrigerant Management Plan (RMP Update). International and National consultants were contracted in June 2002. A survey of current ODS consumption and use in the servicing sector were conducted followed by a desk study and sector review. Due to ExCom decision regarding Terminal Phase-out Management Plans (TPMP) the Update was submitted in January 2003 as a TPMP, with Sweden as co-implementing agency and UNIDO as lead Implementing Agency, and approved at the 39th ExCom meeting. |  | 2002 | [11 empty] | 2002
TRF | Germany | Project preparation for phasing out ODS use in Pliva Pharmaceuticals | Individual | EUR | CRO | ARS | 36 | PRP | 16 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-04-01 | 16500 | -16500 | 0 |  |  | 0 | 0 | 0 | 2145 | -2145 | 0 | 0 | 0 | Project was offset against Germany contributions at the 39th meeting. Project funds have been transferred to the Croatia Halon project preparation project.
FIN | UNEP | Renewal of institutional strengthening projects (Phase III) | Individual | EUR | CRO | SEV | 36 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-06-01 | 2004-04-01 |  | 2004-12-04 | 2007-05-01 | 87900 | 0 | 87900 | 87900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | Sweden | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | TAS | 18 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-09-03 | 2004-12-01 |  | 2005-06-01 | 2005-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 |  |  | 3450 | 0 | 3450 | 0 | 0 | Annual report submitted and approved at the 42nd ExCom meeting. |  | 2003 | [11 empty] | 2003
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | EUR | CRO | HAL | 39 | PRP | 19 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2004-07-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 | 0 | 0 | 2145 | 0 | 2145 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
COM | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | INV | 20 | A | O | I | CFC | 0 | 33 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2005-04-01 |  | 184000 | 0 | 184000 | 174254 | 94.7% | 9746 | 9300 | 9000 | 13800 | 0 | 13069 | 731 | 698 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2003 |  | 98 | 88.7 |  |  | Yes | Yes | Yes
FIN | UNEP | Extension of institutional strengthening project | Individual | EUR | CRO | SEV | 41 | INS | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2006-12-01 | 2008-05-01 | 87707 | 0 | 87707 | 87706.58 | 100% | 0.42 | 0 | 0.42 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNIDO | Terminal phase-out management plan: 2004 annual implementation programme | Multi-Year | EUR | CRO | PHA | 42 | TAS | 22 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 |  | 48300 | 0 | 48300 | 38958 | 80.66% | 9342 | 8000 | 9000 | 3623 | 0 | 2922 | 701 | 600 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2004 | INV | 98 | 78.2 |  |  | Yes | Yes | Yes
FIN | Sweden | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | CRO | PHA | 42 | TAS | 23 | A | O | I |  | 0 |  | 0 |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-12-01 | 2005-12-01 | 24700 | 0 | 24700 | 24700 | 100% | 0 |  |  | 1853 | 0 | 1853 | 0 | 0 | Annual report submitted and approved at the 46th ExCom meeting. |  | 2004 | [11 empty] | 2004
FIN | Germany | Sectoral phase-out programme: establishment of a halon bank | Individual | EUR | CRO | HAL | 43 | TAS | 24 | A | O | I | HAL | 30.1 | 30.1 | 0 |  | 2004-07-01 | 2005-01-01 | 2007-07-01 |  | 2008-10-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Having identified an enterprise, tender for Halonbank equipment has been finalized in december 2007, equipment will be delivered in May 2008. Project completed. PCR was submitted in December 2008.
FIN | UNIDO | Training and awareness workshop in the solvents (CTC) sector | Individual | EUR | CRO | SOL | 45 | TAS | 25 | A | O | I | CTC | 2.3 | 2.3 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN | [13 empty] | 2005 | INV
COM | UNIDO | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 26 | A | O | I | CFC | 20 | 20 |  |  | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2007-12-01 |  | 35000 | 0 | 35000 | 30026 | 85.79% | 4974 | 0 | 4000 | 2625 | 0 | 2252 | 373 | 0 | The project is expected to be financially completed in 2009. | [13 empty] | 2005 | INV | 65 | 43.5 |  |  | Yes | Yes | Yes
FIN | Sweden | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 27 | A | O | I | CFC | 13 | 13 | 0 |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-06-06 | 2006-06-01 | 21500 | 0 | 21500 | 21500 | 100% | 0 | 0 | 0 | 1613 | 0 | 1613 | 0 | 0 | The assistance to Croatia in the implementation of the TPMP was jointly implemented by UNIDO and Sweden, with UNIDO as the lead implementing agency. During 2004 and 2005, the national ODS regulation (By-law) was revised and adopted. The reclamation equipment was delivered during autumn 2004. A mission took place in March 2005. The IC participated in the training of the reclamation facilities in October 2005. The SEI and the IC met with UNIDO in Vienna in September 2005 to discuss some outstanding issues. In March 2006 SEI received the final report from the national consultant/PMU. |  | 2005 | [11 empty] | 2005
COM | UNEP | Extension of institutional strengthening project (phase V) | Individual | EUR | CRO | SEV | 47 | INS | 28 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 0 | 2008-04-01 |  | 2008-11-01 |  | 87707 | 0 | 87707 | 70033.78 | 79.85% | 17673.22 | 17707 | 17673.22 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008 | [13 empty] | 2005 | Non Investment
COM | UNIDO | Terminal CFC phase-out management plan (4th tranche) | Multi-Year | EUR | CRO | PHA | 49 | TAS | 29 | A | O | I | CFC | 43.1 | 43.1 |  |  | 2006-07-01 | 2008-02-01 | 2008-12-01 |  | 2008-12-01 |  | 20200 | 0 | 20200 | 10000 | 49.5% | 10200 | 10200 | 10000 | 1515 | 0 | 750 | 765 | 765 | Project completed in Dec 2008. | [13 empty] | 2006 | INV | 21.9 | 0 |  |  | Yes | Yes | Yes
COM | UNIDO | Monitoring and verification audit report | Individual | EUR | CRO | PHA | 52 | TAS | 30 | A | O | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-01-31 |  | 2008-09-01 |  | 20000 | 0 | 20000 | 14924 | 74.62% | 5076 | 1500 | 1500 | 1800 | 0 | 1343 | 457 | 135 | The verification audit was completed in September 2008, which was noted at the subsequent 56th ExCom Mtg. Project completed in Sep 2008. | [13 empty] | 2007 | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | CRO | PHA | 55 | PRP | 31 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 | 2009-07-01 |  |  | 150000 | 0 | 150000 | 6876 | 4.584% | 143124 | 18177 | 60000 | 11250 | 0 | 516 | 10734 | 1363 | Inception workshop for the HPMP preparation took place beginning December 2008. The University of Zagreb was sub-contracted to undertake a detailed HCFC survey. | HCFC legislation is already in place. Second stakeholders' workshop is planned for 28 May 2009. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | EUR | CRO | SEV | 56 | INS | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2011-01-31 | 2011-01-31 |  |  | 87707 | 0 | 87707 |  | 0% | 87707 | 0 | 87707 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNDP | Country programme preparation | Individual | LAC | CUB | SEV | 08 | CPG | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 20000 | -5000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 2600 | -650 | 1950 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of OTOZ | Individual | LAC | CUB | SEV | 10 | INS | 2 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-10-01 | 2000-12-01 | 172000 | -5 | 171995 | 171995 | 100% | 0 | 0 | 0 | 22360 | -1 | 22359 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Development of an ODS phase out strategy in the refrigeration sector | RMP-Component | LAC | CUB | REF | 13 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-07-01 |  | 1997-09-01 | 1998-12-01 | 30000 | -10000 | 20000 | 20000 | 100% | 0 | 0 | 0 | 3900 | -1300 | 2600 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | CUB | REF | 15 | TAS | 4 | A | O | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-12-01 |  | 1997-09-01 | 1998-12-01 | 169000 | -5167 | 163833 | 163833 | 100% | 0 | 0 | 0 | 21970 | -672 | 21298 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 22 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Umbrella project for elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Empco-Mincin and Segere-Sime "Dionisio Rodrigues" | Individual | LAC | CUB | REF | 23 | INV | 6 | A | O | I | CFC | 3.2 | 3.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-06-01 | 2002-03-01 | 119505 | -9086 | 110419 | 110419 | 100% | 0 | 0 | 0 | 15536 | -1181 | 14355 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of an investment project (hospitals) in the commercial refrigeration sector | Individual | LAC | CUB | REF | 24 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-02-14 | 2001-07-01 | 50000 | -1874 | 48126 | 48126 | 100% | 0 | 0 |  | 6500 | -253 | 6247 | 0 | 0 | FIN |  |  |  | 1999-04-01
FIN | UNIDO | Preparation of a phase out project (tobacco) | Individual | LAC | CUB | FUM | 24 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-01-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | Canada | Project preparation for development of a refrigerant management plan | Individual | LAC | CUB | REF | 25 | PRP | 9 | A | O | I |  | 0 |  | 0 |  | 1998-07-01 | 1999-06-01 | 1999-01-01 |  | 1999-09-01 | 2000-09-01 | 22600 | 0 | 22600 | 22600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Although previous reports indicated all funds had been disbursed in 2002, US $2,600 were found to be left-over and were returned to the MLF. See letter to Sectretariat. |  | 1998 | [11 empty] | 1998 | Non-Inv.
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | CUB | SEV | 26 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14907 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1998 | Non-Investment
FIN | UNIDO | Phasing out methyl bromide in the tobacco sector | Individual | LAC | CUB | FUM | 26 | INV | 11 | A | O | I | MBR | 48 | 48 |  |  | 1998-11-01 | 1999-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-12-01 | 1673324 | -294 | 1673030 | 1673030 | 100% | 0 | 0 |  | 194066 | -324 | 193742 | 0 | 0 | FIN
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practice | RMP | LAC | CUB | REF | 29 | TRA | 12 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 10400 | 0 | 10400 | 0 |  | 2650 technicians trained. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: training programme for customs officers | RMP | LAC | CUB | REF | 29 | TRA | 13 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | 667 customs officers trained. ODS Import database system established. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation and enforcement of regulations on ODSs | RMP | LAC | CUB | REF | 29 | TAS | 14 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  | 0 | 2600 | 0 | 2600 | 0 |  | Policy workshop held May 2002. ODS regulations updated. Project errouneously reported as completed in 2003. Completion officially reported by Cuba in 2004 |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: recovery and recycling of CFC-12 in the MAC sector (amendment to the RMP) | RMP | LAC | CUB | REF | 30 | TAS | 15 | A | O | I | CFC | 8 |  | 0 |  | 2000-03-01 | 2001-11-01 | 2002-04-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project erroneously reported as completed in 2003. Additional (final) training took place in 2004. Insufficient data to determine ODP phase-out. However, RMP as a whole is deemed to have contributed to a reduction in the servicing sector of about 90 ODP |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 33 | PRP | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Renewal of the institutional strengthening under Montreal Protocol (phase III) | Individual | LAC | CUB | SEV | 34 | INS | 17 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2003-08-01 |  | 2003-09-01 | 2004-12-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14907 | 0 | 14907 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2001 | Non-Investment
FIN | UNDP | Phaseout of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | Individual | LAC | CUB | ARS | 34 | INV | 18 | A | O | I | CFC | 28.2 | 28.2 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-05-01 |  | 2006-12-01 | 2008-04-01 | 124220 | 0 | 124220 | 124220 | 100% | 0 | 0 | 0 | 16149 | 0 | 16149 | 0 | 0 | Completed in 2006. Financially completed in 2008. | [13 empty] | 2001 | Investment
FIN | UNDP | Development of MDI transition strategies | Individual | LAC | CUB | ARS | 36 | TAS | 19 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2004-03-01 | 2008-08-01 | 30000 | -5998 | 24002 | 24002 | 100% | 0 | 0 | 0 | 3900 | -780 | 3120.26 | -0.26 | 0 | Completed in 2004. Financially completed in 2008. | [13 empty] | 2002 | Non-Investment
FIN | UNDP | Project preparation in the MDI sector | Individual | LAC | CUB | ARS | 36 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 30000 | 20000 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3900 | 1500 | 5400 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | Germany | Preparation of a CFC phase out management plan | Individual | LAC | CUB | PHA | 37 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-07-01 | 2004-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project preparation lead to project approval at 43rd Excom | [13 empty] | 2002
FIN | UNDP | Extension of the institutional strengthening project (phase 4) | Individual | LAC | CUB | SEV | 40 | INS | 22 | N | T | I | No_ODP | 12.3 | 12.3 | 0 | 0 | 2003-07-01 | 2003-10-01 | 2005-07-01 |  | 2006-12-01 | 2008-08-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2006. Financially completed in 2008. | [13 empty] | 2003 | Non-Investment
ONG | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | CUB | ARS | 41 | INV | 23 | N | O | I | CFC | 109.1 | 99 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2006-09-01 | 2009-07-01 |  |  | 5960000 | 0 | 5960000 | 4504108 | 75.57% | 1455892 | 0 | 582356.8 | 447000 | 0 | 337808.1 | 109191.9 | 0 | Equipment installation and commissioning took longer than expected and some pieces such as mixing vessels seals and pumps had to be replaced. This delayed the completion of the project. Industrial batches and completion of the project are expected to take place during the fist half of 2009 | [10 empty] | 2008-03-01 |  |  | 2003 | Investment
FIN | UNIDO | Project preparation to eliminate methyl bromide consumption (horticulture) | Individual | LAC | CUB | FUM | 43 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 | 2006-09-01 | 30000 | -1068 | 28932 | 28932 | 100% | 0 | 0 |  | 2250 | -80 | 2170 | 0 | 0 | FIN | [14 empty] | NON-INV
TRF | Germany | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 25 | A | O | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-04-01 | 120000 | -76547 | 43453 | 43453 | 100% | 0 | 0 | 0 | 15600 | -9951 | 5649 | 0 | 0 | Technicians studied retrofit systems and potentials and prepared a syllabus on emission reduction; conversion of one cold room to R409; Preparation to retrofit 15 commercial refrigeration systems; development and printing of 1000 retrofit manuals and emis
FIN | Canada | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 26 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2008-01-08 | 2008-01-08 | 400000 | 0 | 400000 | 400000 | 100% | 0 |  | 0 | 52000 | 0 | 52000 | 0 |  | First phase of R&R equipment shipped in May 2005. Public awareness activities initiated in 2005 are continuing and include the production of technical pamphlets, videos, TV commercials, education workshops etc.. 2nd phase of R&R equipment and retrofit tools delivered in November 2007. 3rd phase completed in January 2008. Note that target and consumption indicated under columns BB and BC are for 2005. |  | 2004 | [11 empty] | 2004 | Investment | 312 | 208.5 |  |  | Yes
TRF | France | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 27 | A | O | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-06-01 | 200000 | -119681 | 80319 | 80319 | 100% | 0 |  | 0 | 26000 | -15559 | 10441.47 | -0.47 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project remaining budget and activities was transferred to UNDP in Apr 06.
ONG | UNIDO | Total phase-out of methyl bromide in soil, substrate, storage and structure fumigation | Individual | LAC | CUB | FUM | 44 | INV | 29 | A | O | I | MBR | 24.1 | 24.1 |  |  | 2004-12-01 | 2005-07-01 | 2008-12-01 | 2009-06-01 |  |  | 537763 | 0 | 537763 | 474464 | 88.23% | 63299 | 26916 | 20000 | 40332 | 0 | 35585 | 4747 | 2019 | Equipment including soil fumigation equipment was purchased and delivered in 2008. Training programme is ongoing and the project is planned to be complete in June 2009. | [13 empty] | 2004 | INV
TRF | Germany | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 30 | A | O | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-04-01 | 116000 | -116000 | 0 | 0 |  | 0 | 0 | 0 | 15080 | -15080 | 0 | 0 | 0 | see remarks under MLF No. CUB/PHA/43/TAS/25. Transfer to UNDP completed.
TRF | France | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 31 | A | O | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-06-01 | 200000 | -200000 | 0 | 0 |  | 0 |  | 0 | 26000 | -26000 | 0 | 0 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project was transferred to UNDP in Apr 06.
ONG | Canada | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 32 | A | O | I | CFC | 30 |  | 0 |  | 2005-04-01 | 2008-01-08 | 2007-04-01 | 2009-06-09 |  |  | 62000 | 0 | 62000 | 21000 | 33.87% | 41000 |  | 41000 | 8060 | 0 | 8060 | 0 |  | Some funds from 2005 implementation plan were combined with remaining funds from 2004 plan to complete the 3rd phase of equipment procurement for the project. Remaining funds from 2005 plan will be used for a final procurement of tools, for which a contract was signed in January 2009. Note that target and consumption indicated under columns BB and BC are for 2006. |  | 2005 | [11 empty] | 2005 | Investment | 260 | 239.5 |  |  | Yes
COM | UNDP | National ODS phase-out plan for CFCs: 2005 annual implementation plan - UNDP Portion | Multi-Year | LAC | CUB | PHA | 45 | INV | 33 | N | O | I | CFC | 30 | 30 | 0 | 0 | 2005-04-01 | 2007-07-01 | 2006-04-01 |  | 2007-12-01 |  | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 18750 | 0 | 18750 | 0 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment | 331 | 331 |  |  | Yes | Yes | yes
COM | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | CUB | SEV | 47 | INS | 34 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-11-01 | 2007-12-01 |  | 2008-03-01 |  | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2008. The Institutional Strengthening project for Cuba has enabled the Government to continue the successful implementation of Montreal Protocol in the country. During 2008 the NOU continued its monitoring of the country's compliance status with the Montreal Protocol through data collection and monitoring of ODS consumption. Cuba has a strong public awareness programme thanks to the support of the Institutional Project. | [13 empty] | 2005 | Non-Investment
TRF | Canada | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 35 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2008-12-01 |  |  | 2007-03-01 | 196871 | -196871 | 0 | 0 |  | 0 |  | 0 | 25593 | -25593 | 0 | 0 |  | Project was transferred to UNDP at ExCom 51 (March 2007). Therefore there is no planned date of completion. Progress report for 2007 will show adjustment of funding approved. |  | 2005 | [11 empty] | 2005 | Non-Inv.
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 36 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2008-12-01 | 2010-01-01 |  |  | 787482 | 196871 | 984353 | 103978 | 10.56% | 880375 | 0 | 176075 | 59061 | 17718 | 8110.2276 | 68668.7724 | 0 | Four Chillers have been installed in Cuba, and they will start running in early 2009. Five additional Chillers were procured in 2008 and will be installed in 2009. Project was delayed because of a hurricane that caused severe damage on Chillers sites. | [13 empty] | 2005 | Non-Investment
ONG | UNDP | National ODS phase-out plan for CFCs: balance of the 2004 and 2005 annual programmes (France and Germany) | Multi-Year | LAC | CUB | PHA | 48 | INV | 37 | N | O | I | CFC | 79.7 | 79.7 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 | 2009-07-01 |  |  | 512228 | 0 | 512228 | 254280 | 49.64% | 257948 | 0 | 103179.2 | 38417 | 0 | 19070.9504 | 19346.0496 | 0 | The commercial retrofit programme represents the main activity in the NPP. The programme is on-going. A large procurement process was completed in the end of 2008, and the goods will be delivered in early 2009. Training of refrigeration technicians continues under the NPP. | [13 empty] | 2006 | Investment | 150.9 | 150.9 |  |  | Yes | Yes | yes
ONG | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | CUB | SEV | 53 | INS | 38 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 | 2010-01-01 |  |  | 149066 | 0 | 149066 | 21782 | 14.61% | 127284 | 0 | 25456.8 | 11180 | 0 | 1633.6573 | 9546.3427 | 0 | See above comments for CUB-34. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | National ODS phase-out plan for CFCs: 2006 and 2007 annual implementation plans | Multi-Year | LAC | CUB | PHA | 53 | INV | 39 | N | O | I | CFC | 166.2 | 40 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-01-01 |  |  | 641000 | 0 | 641000 | 0 | 0% | 641000 | 0 | 128200 | 48075 | 0 | 0 | 48075 | 0 | See CUB 37 for more details. | [13 empty] | 2007 | Investment | 54.7 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CUB | PHA | 56 | PRP | 40 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme | Individual | EUR | CYP | SEV | 22 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-05-01 |  | 1997-05-01 | 1997-05-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | AFR | DJI | SEV | 30 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-07-01 | 2007-01-01 | 60000 | -34200 | 25800 | 25800 | 100% | 0 | 0 | 0 | 7800 | -4446 | 3354 | 0 | 0 | Project financially completed. | $9,000 plus $1170 returned ExCom 37 $25,200 plus $3276 returned ExCom 46 | [5 empty] | 2002-07-01 | [6 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | DJI | REF | 36 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
COM | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | DJI | REF | 37 | TAS | 3 | A | O | I | CFC | 1.6 | 1.6 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2007. | [13 empty] | 2002 | Investment
COM | UNEP | Implementation of the RMP: customs training | Individual | AFR | DJI | REF | 37 | TRA | 4 | A | O | I | CFC | 2.1 | 2.1 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 |  | 33100 | 0 | 33100 | 21125.54 | 63.82% | 11974.46 | 11974.07 | 11974.46 | 4303 | 0 | 2746.3202 | 1556.6798 | 1556.6291 | Project completed | [13 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: training in good practices of refrigeration | Individual | AFR | DJI | REF | 37 | TRA | 5 | A | O | I | CFC | 4.8 | 4.8 | 0 | 0 | 2002-07-01 | 2004-08-01 | 2003-08-01 |  | 2006-12-01 |  | 74200 | 0 | 74200 | 41026.7 | 55.29% | 33173.3 | 22149.96 | 33173.3 | 9646 | 0 | 5333.471 | 4312.529 | 2879.4948 | Project completed | [13 empty] | 2002 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | DJI | SEV | 37 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-08-01 |  | 2006-04-01 | 2007-04-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNDP | Implementation of the RMP: recovery and recycling | RMP-Component | AFR | DJI | REF | 37 | TAS | 7 | A | O | I | CFC | 8.8 | 8.8 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 |  | 136463 | 0 | 136463 | 135739 | 99.47% | 724 | 0 | 579.2 | 17740 | 0 | 17646.07 | 93.93 | 0 | Completed in 2007. | [13 empty] | 2002 | Investment
COM | UNEP | Implementation of the RMP: assistance to establish legislation | Individual | AFR | DJI | REF | 37 | TRA | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2003-08-01 |  | 2004-04-04 |  | 9000 | 0 | 9000 | 0 | 0% | 9000 | 9000 | 9000 | 1170 | 0 | 0 | 1170 | 1170 | Project completed | [13 empty] | 2002 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | DJI | SEV | 48 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2008-04-01 | 2009-04-01 |  |  | 78000 | 0 | 78000 | 59874.57 | 76.76% | 18125.43 | 18125 | 18125.43 | 0 | 0 | 0 | 0 | 0 | Implementation of ISP on going satisfactorily. NOU coodrinating implementation of TPMP with UNEP and UNDP. Awareness activities were carried out targetting decision makers and majors stakeholders to promote enforcement of ODS regulations. | [13 empty] | 2006 | Non Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | DJI | PHA | 48 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2006 | Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | DJI | PHA | 48 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-03-01 |  | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project completed in March 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-year | AFR | DJI | PHA | 53 | TAS | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-03-01 | 2009-03-01 |  |  | 80000 | 0 | 80000 | 47945.69 | 59.93% | 32054.31 | 20980 | 32054.31 | 10400 | 0 | 6232.9397 | 4167.0603 | 2727.4 | MoU with the country was signed in March 2008. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | DJI | PHA | 53 | INV | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2009-12-01 |  |  | 147000 | 0 | 147000 | 0 | 0% | 147000 | 0 | 58800 | 13230 | 0 | 0 | 13230 | 0 | Consultant mission took place in August 2008 and further to this specifications for international purchase of equipment were finalized and posted. Bids have been received, a supplier selected and it is expected that tools, equipment and gas will arrive in country first quarter of 2009. Contract for reinforcement of training center has been prepared and should be put in place to coincide with arrival of equipment. In view of slow disbursements, 2nd tranche to be submitted later in 2009. | [13 empty] | 2007 | Investment | 3.2 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DJI | PHA | 55 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | MOU sent to Country for Signature | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | DMI | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-08-01 |  | 1998-09-01 | 1999-07-01 | 40000 | -16000 | 24000 | 24000 | 100% | 0 | 0 | 0 | 5200 | -2080 | 3120 | 0 | 0 | Project financially completed. | $16,000 plus $2080 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Custom training | Individual | LAC | DMI | REF | 26 | TRA | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2003-06-01 | 2000-11-02 |  | 2006-04-01 | 2008-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training of trainers in good refrigerant management practices | Individual | LAC | DMI | REF | 26 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-11-02 |  | 2006-06-01 | 2008-12-01 | 20000 | 0 | 20000 | 17000 | 85% | 3000 | 0 | 0 | 2600 | 0 | 2210 | 390 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 1998 | Non Investment
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | DMI | SEV | 26 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-07-01 | 2001-12-01 |  | 2004-02-01 | 2005-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | DMI | SEV | 42 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-12-01 | 2007-04-01 | 13000 | 0 | 13000 | 12999.64 | 100% | 0.36 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Preparation of refrigerant management plan | RMP | LAC | DMI | REF | 44 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2006-08-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | LAC | DMI | SEV | 45 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-10-01 | 2008-01-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
ONG | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 9 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2009-12-01 | 2009-12-01 |  |  | 40000 | 0 | 40000 | 5060 | 12.65% | 34940 | 0 | 13976 | 3600 | 0 | 455.4 | 3144.6 | 0 | Based on the needs assessment, tools and equipment was procured. It will be delivered in early 2009. Training of technicians. 2nd and 3rd tranche approved at 56th ExCom | [13 empty] | 2006 | Investment | 0.7 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-12-01 | 2009-12-01 |  |  | 35000 | 0 | 35000 | 26923.8 | 76.93% | 8076.2 | 7000 | 8076.2 | 4550 | 0 | 3500.094 | 1049.906 | 910 | Main achievements are: 1) Control legislation on ODS has been passed and is being enforced, 2) Temporary office space and secretarial support is been provided for the Association of Refrigeration and Air-Conditioning, Association registered 3) Needs-assessment, procurement of equipment and design of refrofit incentive scheme are being carried out. 4) Training of customs officers is being organized, Senoir Customs officer attended regional workshop for Prevention of illegal trade in ODS 5) Senior technician attended regional workshop in Alternative ozone friendly technologies 6).A regional expert was recruited to assist in the preparation of annual reports and advise UNEP and UNDP on the developments and needs of country.The agreement for this project expired and some activities implemented. Currently this accord is in the signature process. | [13 empty] | 2006 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | DMI | SEV | 50 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DMI | SEV | 56 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project recently approved. UNEP is working on the signature of the funding agreement (SSFA) for project implementation. Final payment, Terminal and financial reports of current IS phase being prepared and expected for 2009 2nd quarter. | [13 empty] | 2008
ONG | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2010-03-01 |  |  | 66000 | 0 | 66000 | 0 | 0% | 66000 | 0 | 66000 | 8580 | 0 | 0 | 8580 | 0 | Project recently approved. UNEP is working on the signature of the funding agreement (SSFA) for project implementation. | [13 empty] | 2008
ONG | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 57000 | 0 | 57000 | 0 | 0% | 57000 | 0 | 22800 | 5130 | 0 | 0 | 5130 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | DOM | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1996-03-01 |  | 1995-07-01 | 1995-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | USA | Project preparation in commercial refrigeration |  | LAC | DOM | REF | 17 | PRP | 2 | A | O | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1995-09-01 | 1995-09-01 | 19000 | 0 | 19000 | 19000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | USA | Demonstration project in MACs |  | LAC | DOM | REF | 17 | DEM | 3 | A | O | I |  | 0 | 10 | 0 |  | 1995-07-01 | 1995-09-01 | 1996-12-01 |  | 1997-12-01 | 1999-10-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | UNEP | Establishment of the National Commission for the Ozone (Cogo) | Individual | LAC | DOM | SEV | 17 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1998-10-01 |  | 2000-02-01 | 2001-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | Project financially completed. |  |  | 1998-10-01 | [10 empty] | 1995 | Non Investment
FIN | USA | Demonstration project in commercial refrigeration (food storage, distribution and retailing) |  | LAC | DOM | REF | 18 | DEM | 5 | A | O | I |  | 0 | 7 | 0 |  | 1995-11-01 | 1995-11-01 | 1996-12-01 |  | 1998-02-01 | 1999-10-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | UNDP | Demonstration project in commercial refrigeration (food storage, distribution and retailing) | RMP-Component | LAC | DOM | REF | 18 | TAS | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-04-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1995 | Non-Investment
FIN | UNDP | Project preparation assistance in foams and refrigeration | Individual | LAC | DOM | SEV | 18 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | DOM | REF | 21 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Fabrica de Refrigeradores Comerciales, C.A. (Farco) | Individual | LAC | DOM | REF | 22 | INV | 9 | A | O | I | CFC | 31.8 | 31.8 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-11-01 | 2000-07-01 | 423209 | -2883 | 420326 | 420326 | 100% | 0 | 0 | 0 | 55017 | -375 | 54642 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sub-sector | Individual | LAC | DOM | REF | 22 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Metalgas S.A. by replacement with HCFC-141b and HFC-134a respectively | Individual | LAC | DOM | REF | 24 | INV | 11 | A | O | I | CFC | 20.8 | 20.8 | 0 | 0 | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 1999-12-01 | 2001-12-01 | 316368 | -3741 | 312627 | 312627 | 100% | 0 | 0 | 0 | 41128 | -486 | 40642 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for one project in commercial refrigeration subsector | Individual | LAC | DOM | REF | 24 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | DOM | REF | 25 | TAS | 13 | A | O | I | CFC | 37.4 | 37.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 441482 | -49014 | 392468 | 392468 | 100% | 0 | 0 | 0 | 57393 | -6372 | 51021 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | LAC | DOM | REF | 25 | TRA | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-03 |  | 2003-06-01 | 2005-01-01 | 38000 | -10000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 4940 | -1300 | 3640 | 0 | 0 | Project financially completed. | $25,000 plus $3,250 PSC returned ExCom 46 | [12 empty] | 1998 | Non Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | DOM | REF | 25 | TAS | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-01-01 | 2000-08-01 |  | 2003-09-01 | 2003-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Industria Continental, C.A. by replacement with HCFC-141b and HFC 134a respectively | Individual | LAC | DOM | REF | 25 | INV | 16 | A | O | I | CFC | 19.9 | 19.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-03-01 | 303200 | -2802 | 300398 | 300398 | 100% | 0 | 0 | 0 | 39416 | -364 | 39052 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | LAC | DOM | REF | 25 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-02-02 |  | 2001-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. |  |  |  |  | 2000-12-01 | [8 empty] | 1998 | Non Investment
FIN | UNIDO | Preparation of a demonstration project (tobacco, curcubits, flowers, tomatoes) | Individual | LAC | DOM | FUM | 25 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: alternatives to the use of methyl bromide: soil pasteurization (steam), non soil cultivation, solarization with biofumigation and low dose chemicals all in combination with IPM system | Individual | LAC | DOM | FUM | 26 | DEM | 19 | A | O | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2002-03-01 | 2003-05-01 | 324500 | -699 | 323801 | 323801 | 100% | 0 | 0 |  | 42185 | -158 | 42027 | 0 | 0 | FIN
FIN | UNDP | Preparation of a project in the general foam subsector | Individual | LAC | DOM | FOA | 27 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Paredomi (Paneles Refrigerados Dominicanos, C.A.) | Individual | LAC | DOM | FOA | 29 | INV | 21 | A | O | I | CFC | 60.7 | 60.7 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-04-01 | 2003-09-01 | 177670 | 0 | 177670 | 177670 | 100% | 0 | 0 | 0 | 23097 | 0 | 23097 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Espumas del Cibao | Individual | LAC | DOM | FOA | 29 | INV | 22 | A | O | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2002-11-01 | 89712 | -1048 | 88664 | 88664 | 100% | 0 | 0 | 0 | 11663 | -136 | 11527 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | DOM | SEV | 29 | INS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 103000 | 0 | 103000 | 103000 | 100% | 0 | 0 | 0 | 13390 | 0 | 13390 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Poquinsa (Poliuretano Químico Indutrial, S.A.) | Individual | LAC | DOM | FOA | 29 | INV | 24 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 24920 | 0 | 24920 | 24920 | 100% | 0 | 0 | 0 | 3240 | 0 | 3240 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | DOM | FUM | 30 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -9183 | 15817 | 15817 | 100% | 0 | 0 | 0 | 3250 | -1194 | 2056.21 | -0.21 | 0 | Project financially completed. | $9,183 plus $1,194 PSC returned ExCom 43 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | DOM | FOA | 33 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | DOM | FOA | 36 | PRP | 27 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2005-07-01 | 2006-06-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 975 | 0 | 975 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the solvent sector | Individual | LAC | DOM | SOL | 36 | PRP | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Preparation of investment activities of the RMP | Individual | LAC | DOM | REF | 36 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNIDO | Preparation of a phase-out project in the fumigants (methyl bromide) sector for TPO-soil fumigation | Individual | LAC | DOM | FUM | 36 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2004-03-01 | 30000 | -2722 | 27278 | 27278 | 100% | 0 | 0 |  | 3900 | -359 | 3541 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNEP | Policy and technical assistance | Individual | LAC | DOM | SEV | 37 | TAS | 31 | A | O | I | CFC | 0.8 | 0.8 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2006-06-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNDP | National halon bank management plan development | Individual | LAC | DOM | HAL | 38 | TAS | 32 | N | O | I | Halon | 3 | 3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2007-12-01 |  | 40000 | 0 | 40000 | 33505 | 83.76% | 6495 | 0 | 5196 | 5200 | 0 | 4355.65 | 844.35 | 0 | Completed in 2007. | [13 empty] | 2002 | Investment
ONG | UNIDO | Phase-out of methyl bromide in melon, flowers and tobacco | Individual | LAC | DOM | FUM | 38 | INV | 33 | A | O | I | MBR | 141 | 141 |  |  | 2002-11-01 | 2003-01-01 | 2006-12-01 | 2009-06-01 |  |  | 922900 | 0 | 922900 | 673238 | 72.95% | 249662 | 135573 | 50000 | 111519 | 0 | 84056 | 27463 | 14913 | During 2008 technical support was provided to the flower sector on the use of steaming and in horticulture in general. In 2009 additional training will be provided and the project is expected to be complete in June 2009. | [13 empty] | 2002 | INV
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | DOM | SEV | 39 | INS | 34 | A | T | I | CFC | 17.1 | 17.1 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2006-11-01 | 2007-04-01 | 134333 | -1 | 134332 | 134333 | 100% | -1 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 1 returned to ExCom 54 | [12 empty] | 2003 | Non Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | DOM | PHA | 42 | PRP | 35 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-05-01 | 2006-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 563 | 0 | 563 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: 2005 annual implementation programme | Multi-Year | LAC | DOM | PHA | 45 | INV | 36 | N | O | I | CFC | 41.3 | 41.3 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-12-01 |  | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment | 311.2 | 311.2 |  |  | yes | yes | yes
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DOM | SEV | 48 | INS | 37 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-12-01 |  | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. During this year main achievements concentrate in the following areas: UNIDO´s methyl bromide terminal project, the halon bank, implementation of the TPMP and public awareness as well as strengthening of links with government institutions. In the case of methyl bromide, a national law was launched that prohibits imports of methyl bromide for agricultural use. By the time the report was submitted, the country reports O consumption of this substance. With regards to the halon bank, only the purchase of the supplementary equipment is pending. The international bid is already open for this purpose. In relation to the TPMP, training courses continue either for customs agents or for refrigeration technicians (131 and 80 respecively were certified this year). Finally, 3 agreemens were signed; 2 with key government institutions (National Institutes of Biotechnology and for Professional Training) and one with local UNDP. In terms of public awareness, a magazine and a set of brochures around the achievements of the country for the last 11 years, were published. | [13 empty] | 2006 | Non Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (second tranche) | Multi-Year | LAC | DOM | PHA | 48 | INV | 38 | N | O | I | CFC | 171 | 171 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-07-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Completed in 2008. See DOM-40 for details. | [13 empty] | 2006 | Investment | 81 | 81 |  |  | yes | yes | yes
ONG | UNDP | National halon bank management plan update | Individual | LAC | DOM | HAL | 51 | TAS | 39 | N | O | I | Halons | 1.2 | 0 | 0 | 0 | 2007-03-01 |  | 2011-01-01 | 2011-01-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 4000 | 1800 | 0 | 0 | 1800 | 0 | Current and future demand (critical uses) has been determined. Remaining pending equipment in the process of being procured. | [13 empty] | 2007 | Non-Investment
COM | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (third tranche) | Multi-Year | LAC | DOM | PHA | 51 | INV | 40 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-01-01 | 2009-03-01 |  | 2008-12-01 |  | 400000 | 0 | 400000 | 360538 | 90.13% | 39462 | 0 | 31569.6 | 30000 | 0 | 27040.35 | 2959.65 | 0 | Completed in 2008. 500 refrigeration technicians were training in good refrigeration practices. Additional equipment was procured for R&R in MAC and Commercial. The use of HC in Domestic Refrigeration was promoted under the Domestic Refrigeration Programme. All current uses of solvents assessed and alternatives provided to the users. Tranche operationally completed and all activities continued in 2008 plan. Accounts to be settled in 2009. | [13 empty] | 2007 | Investment | 53 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (fourth tranche) | Multi-Year | LAC | DOM | PHA | 54 | INV | 41 | N | O | I | CFC | 28 | 0 | 0 | 0 | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 211600 | 0 | 211600 | 0 | 0% | 211600 | 0 | 42320 | 15870 | 0 | 0 | 15870 | 0 | Continuation of DOM 40. See above. | [13 empty] | 2008 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | DOM | PHA | 55 | PRP | 42 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | Local and international consultants have been identified. The inception workshop is expected to take place in early 2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | DOM | SEV | 56 | INS | 43 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 134333 | 0 | 134333 | 0 | 0% | 134333 | 0 | 134333 | 0 | 0 | 0 | 0 | 0 | Project recently approved. Agreement for project implementation has been recently signed and first fund disbursement already processed. The country is currently producing A7 data report for 2008 and is updated with earlier reports. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | DRC | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. |  |  |  | 1999-03-01 | [9 empty] | 1995 | Non Investment
FIN | UNEP | Creation of an Ozone Office | Individual | AFR | DRC | SEV | 27 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2003-06-01 | 2000-04-01 |  | 2000-12-01 | 2004-04-01 | 32270 | 0 | 32270 | 32270 | 100% | 0 | 0 | 0 | 4195.1 | 0 | 4195.1 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
COM | UNEP | Assistance in developing the RMP project proposal | Individual | AFR | DRC | REF | 32 | TAS | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2002-01-01 |  | 2003-12-01 |  | 60000 | -4805 | 55195 | 35195 | 63.76% | 20000 | 0 | 20000 | 7800 | -625 | 4575.35 | 2599.65 | 0 | Project completed | $ 4,805 plus $ 625 returned from ExCom 48 | [6 empty] | 2003-12-01 | [5 empty] | 2000 | Non Investment
FIN | UNEP | Institutional strengthening project | Individual | AFR | DRC | SEV | 32 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-09-01 | 2005-12-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 | 0 | 8390.2 | 0 | 8390.2 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | DRC | FOA | 33 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Complast SPRL | Individual | AFR | DRC | FOA | 35 | INV | 6 | A | O | I | CFC | 38 | 38 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-11-01 | 2007-03-01 | 190820 | 0 | 190820 | 190820 | 100% | 0 | 0 | 0 | 24807 | 0 | 24807 | 0 | 0 | Completed in 2006. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slastock foam by conversion to methylene chloride at M.K. SPRL | Individual | AFR | DRC | FOA | 35 | INV | 7 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-04-01 | 149800 | 0 | 149800 | 149567 | 99.84% | 233 | 0 | 0 | 19474 | 0 | 19443.71 | 30.29 | 0 | Completed in 2005. Financially completed in 2008. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in recovery and recycling refrigeration sector | Individual | AFR | DRC | REF | 36 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock sector | Individual | AFR | DRC | FOA | 36 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
COM | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Bek SPRL by convesion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 10 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-09-01 |  | 2005-12-01 |  | 165670 | 0 | 165670 | 131404 | 79.32% | 34266 | 0 | 27412.8 | 21537 | 0 | 17082.52 | 4454.48 | 0 | Completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Ekanawe SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 11 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 75490 | 0 | 75490 | 75490 | 100% | 0 | 0 | 0 | 9814 | 0 | 9813.7 | 0.3 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Sokamo SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 12 | A | O | I | CFC | 21 | 21 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 69920 | 0 | 69920 | 69920 | 100% | 0 | 0 | 0 | 9090 | 0 | 9089.6 | 0.4 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | DRC | REF | 39 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
FIN | UNDP | Formulation of terminal project in the foam sector | Individual | AFR | DRC | FOA | 39 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
COM | UNEP | Implementation of the RMP: training programme for technicians in the refrigeration sector | Individual | AFR | DRC | REF | 41 | TRA | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-10-01 |  | 2006-12-01 |  | 115000 | 0 | 115000 | 107050.69 | 93.09% | 7949.31 | 0 | 7949.31 | 14950 | 0 | 13916.5897 | 1033.4103 | 0 | Project completed | [13 empty] | 2003 | Non Investment
COM | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | DRC | REF | 41 | TAS | 16 | N | O | I | CFC | 13.1 | 13.1 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-12-01 |  | 437102 | 0 | 437102 | 221682 | 50.72% | 215420 | 0 | 172336 | 32783 | 0 | 16626.3275 | 16156.6725 | 0 | Completed in 2008. Contracts with centers have been signed (3 in Kinshasa one in Lower Congo) and each has been equipped. Workshops held. For first semester of operation ending 31 December 863kg have been recovered of which 500kg have been recycled. 200kg were returned to technicians as per their requests. Balance due to outstanding invoices to be settled in 2009. | [13 empty] | 2003 | Investment
COM | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | DRC | REF | 41 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2006-12-01 |  | 40000 | 0 | 40000 | 21045.4 | 52.61% | 18954.6 | 18955 | 18954.6 | 5200 | 0 | 2735.902 | 2464.098 | 2464.15 | Project completed | [13 empty] | 2003 | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | DRC | REF | 41 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 109000 | 0 | 109000 | 108792.4 | 99.81% | 207.6 | 0 | 0 | 14170 | 0 | 14143.012 | 26.988 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNDP | Terminal umbrella project for the foam sector | Individual | AFR | DRC | FOA | 41 | INV | 19 | N | O | I | CFC | 123 | 123 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 |  | 640820 | 0 | 640820 | 581442 | 90.73% | 59378 | 10000 | 47502.4 | 48062 | 0 | 43608.6037 | 4453.3963 | 750.0078 | Completed in 2007. | [13 empty] | 2003 | Investment
COM | UNIDO | Preparation of a phase-out plan in the solvents (CTC) sector | Individual | AFR | DRC | SOL | 45 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2007-04-01 |  | 30000 | 0 | 30000 | 28395 | 94.65% | 1605 | 512 | 700 | 2250 | 0 | 2130 | 120 | 38 | The project will be financially completed upon disbursement of unliquidated obligations. | This project is PRP one. Consumption figure for 2008 is not yet available. | [12 empty] | 2005 | NON-INV
FIN | UNDP | Project preparation for refrigeration end-user | Individual | AFR | DRC | REF | 45 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-07-01 | 2006-12-01 | 16870 | 0 | 16870 | 16870 | 100% | 0 | 0 | 0 | 1265 | 0 | 1265 | 0 | 0 | Completed in 2006. Financially completed in 2006. | [13 empty] | 2005 | Investment
COM | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | DRC | SEV | 46 | INS | 22 | A | T | I | CFC | 5.2 | 5.2 | 0 | 0 | 2005-07-01 | 2007-01-01 | 2007-07-01 |  | 2007-07-01 |  | 64540 | 0 | 64540 | 14766.9 | 22.88% | 49773.1 | 49773 | 49773.1 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2005 | Non Investment
ONG | UNEP | National CFC phase-out plan (first tranche) | Multi-year | AFR | DRC | PHA | 49 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-12-31 | 2009-07-01 |  |  | 143750 | 0 | 143750 | 140340.37 | 97.63% | 3409.63 | 3410 | 3409.63 | 18688 | 0 | 18244.2481 | 443.7519 | 443.3 | 149 practitioners have been trained and certified in 2008. 163 Customs Officers have been trained in 2008. 3 refrigerant identifiers have been purchased in 2008 | [13 empty] | 2006 | Non Investment
ONG | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | AFR | DRC | PHA | 49 | INV | 24 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 |  | 2007-12-01 | 2010-01-01 |  |  | 193750 | 0 | 193750 | 0 | 0% | 193750 | 0 | 38750 | 14531 | 0 | 0 | 14531 | 0 | Two missions took place in 2008, the last one being in December. Administrative coordinator and national consultants have been hired. Specifications for purchase of tools, equipment and gas have been prepared and an international bidding process is scheduled to close mid January 2009. A national bidding process has been completed and equipment should be available by mid-year. 19 end user applications are being finalized by the national consultant and will be evaluated by Int. Consultants when received. Visit to provinces will identify additional ones. MDI project has been launched and high level meetings to adopt strategy and legislation are scheduled early 2009. Second tranche to be approved at 57th ExCom. | [13 empty] | 2006 | Investment | 51.5 |  |  |  | Latest | Latest | Latest
ONG | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (first phase) | Multi-year | AFR | DRC | SOL | 51 | INV | 25 | A | O | I | CTC-TCA | 8.9 |  | 0 |  | 2007-03-01 | 2008-04-01 | 2008-03-01 | 2009-12-01 |  |  | 288440 | 0 | 288440 | 18350 | 6.362% | 270090 | 1201 | 200000 | 37497 | 0 | 2385.5 | 35111.5 | 156.13 | The procurement of equipment for 6 identified counterparts is in progress. Offers received and will be jointly evaluated with Ozone office, Kinshasa. It is envisaged that the equipment will be delivered and installed in the 3rd quarter 2009. |  | 2007 | [11 empty] | 2007 | Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | DRC | SEV | 52 | INS | 26 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-06-30 | 2009-06-30 |  |  | 64540 | 0 | 64540 | 19570.16 | 30.32% | 44969.84 | 15630 | 44969.84 | 0 | 0 | 0 | 0 | 0 | NOU DRC continued the implementation of NPOP training actitivities for refrigeration technicians, Customs officers, Officers of the Office Conglais du Controle and Environment inspectors.The NOU coodinated the implementation of investment projects under t | [13 empty] | 2007 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DRC | PHA | 55 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for Signature | [13 empty] | 2008
ONG | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (second phase) | Multi-year | AFR | DRC | SOL | 56 | INV | 28 | A | O | I | CTC-TCA | 11.7 |  | 0 |  | 2008-11-01 |  | 2009-11-01 | 2009-12-01 |  |  | 144220 | 0 | 144220 |  | 0% | 144220 |  | 120000 | 18749 | 0 | 0 | 18749 | 0 | The procurement of equipment for 6 identified counterparts is in progress. Offers received and will be jointly evaluated with Ozone office, Kinshasa. It is envisaged that the equipment will be delivered and installed in the 3rd quarter 2009. |  | 2008 | [11 empty] | 2008 | Investment
FIN | UNEP | Country programe preparation | Individual | ASP | DRK | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 1996-10-01 | 1997-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Establishment of a National Ozone Cell | Individual | ASP | DRK | SEV | 21 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 2000-02-01 |  | 2000-12-01 | 2003-06-01 | 142560 | 0 | 142560 | 142560 | 100% | 0 | 0 | 0 | 18532.8 | 0 | 18532.8 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNIDO | Project formulation of investment projects in all sectors | Individual | ASP | DRK | SEV | 21 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 2000-10-01 | 2001-07-01 | 70000 | -1720 | 68280 | 68280 | 100% | 0 | 0 |  | 9100 | -238 | 8862 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | DRK | FUM | 23 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-01-01 | 2001-07-01 | 15000 | 8050 | 23050 | 23050 | 100% | 0 | 0 |  | 1950 | 1042 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 23 | INV | 5 | A | O | I | CTC | 110 | 110 |  |  | 1997-11-01 | 1999-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-07-01 | 311922 | 0 | 311922 | 311922 | 100% | 0 | 0 |  | 40550 | 0 | 40550 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Hamhung Foam Factory, Hamgyong South Province | Individual | ASP | DRK | FOA | 23 | INV | 6 | A | O | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 102680 | -2145 | 100535 | 100535 | 100% | 0 | 0 |  | 13348 | -299 | 13049 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Pyongyang Foam Plant | Individual | ASP | DRK | FOA | 23 | INV | 7 | A | O | I | CFC | 83 | 83 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 103570 | -1984 | 101586 | 101586 | 100% | 0 | 0 |  | 13464 | -279 | 13185 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Chongjin Foam Factory, Hamgyong North Province | Individual | ASP | DRK | FOA | 23 | INV | 8 | A | O | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 103670 | -72 | 103598 | 103598 | 100% | 0 | 0 |  | 13477 | -31 | 13446 | 0 | 0 | FIN
FIN | UNIDO | Non-investment project: promotion and information transfer of alternatives to the use of methyl bromide in the preparation of seedbeds for the cultivation of rice and maize | Individual | ASP | DRK | FUM | 25 | TAS | 9 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 1999-07-01 |  | 1999-11-01 | 2001-03-01 | 27500 | -153 | 27347 | 27347 | 100% | 0 | 0 |  | 3575 | -25 | 3550 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvent to vapour at Pyongyang September 18 Bearings Factory | Individual | ASP | DRK | SOL | 26 | INV | 10 | A | O | I | CTC | 121 | 121 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 1081024 | -2425 | 1078599 | 1078599 | 100% | 0 | 0 |  | 128913 | -455 | 128458 | 0 | 0 | FIN
FIN | UNIDO | Conversion of remaining metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 26 | INV | 11 | A | O | I | CTC | 168 | 168 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2001-12-01 | 2002-12-01 | 490157 | -2198 | 487959 | 487959 | 100% | 0 | 0 |  | 63720 | -386 | 63334 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from CTC solvent to TCE vapour degreasing at Ceramic Tools Factory (CTF) | Individual | ASP | DRK | SOL | 28 | INV | 12 | A | O | I | CTC | 19.8 | 19.8 |  |  | 1999-07-01 | 2000-08-01 | 2000-08-01 |  | 2001-12-01 | 2002-12-01 | 206657 | 0 | 206657 | 206657 | 100% | 0 | 0 |  | 26865 | 0 | 26865 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening | Individual | ASP | DRK | SEV | 32 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-08-01 | 2003-01-01 |  | 2003-10-01 | 2003-12-01 | 95040 | 0 | 95040 | 95040 | 100% | 0 | 0 | 0 | 12355.2 | 0 | 12355.2 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNIDO | Preparation for four projects in the solvent (CTC) sector | Individual | ASP | DRK | SOL | 33 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-10-01 |  | 2002-12-01 | 2003-05-01 | 70000 | -17 | 69983 | 69983 | 100% | 0 | 0 |  | 9100 | -17 | 9083 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNEP | Development of a refrigerant management plan | RMP | ASP | DRK | REF | 35 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2002-08-01 |  | 2003-06-01 | 2005-05-01 | 60000 | -13466 | 46534 | 46534 | 100% | 0 | 0 | 0 | 7800 | -1751 | 6049.42 | -0.42 | 0 | Project financially completed. | $17,650 plus $2,295 PSC returned ExCom 46; $ -4184 plus $ -544 returned from ExCom 48 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Preparation of country programme update | Individual | ASP | DRK | SEV | 36 | CPG | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2003-04-01 |  | 2003-10-01 | 2005-05-01 | 30000 | -684 | 29316 | 29315.61 | 100% | 0.39 | 0 | 0.39 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $684 returned ExCom 46 | [12 empty] | 2002 | Non Investment
FIN | UNIDO | Closure of ODS production plant | Multi-Year | ASP | DRK | PRO | 36 | INV | 17 | A | O | R | CFC | 0 | 0 | 500 | 500 | 2002-03-01 | 2002-10-01 | 2003-03-01 |  | 2002-10-01 | 2003-05-01 | 1344350 | 0 | 1344350 | 1344350 | 100% | 0 | 0 |  | 67217 | 0 | 67217 | 0 | 0 | FIN | [13 empty] | 2002 | INV |  |  | 0 | 0 | Yes | Yes | Yes
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride to aqueous cleaning techniques at the Gumsong Tractor Factory (GST) | Individual | ASP | DRK | SOL | 36 | INV | 18 | A | O | I | CTC | 198 | 198 |  |  | 2002-03-01 | 2002-06-01 | 2004-09-01 |  | 2004-12-01 | 2006-05-01 | 1932207 | 0 | 1932207 | 1932207 | 100% | 0 | 0 |  | 222543 | -1 | 222542 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion of cleaning processes from CTC to aqueous and solvent cleaning techniques at Huichon February 26 Factory (HUI) | Individual | ASP | DRK | SOL | 37 | INV | 19 | A | O | I | CTC | 209 | 209 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-12-01 | 2006-05-01 | 1945477 | -950 | 1944527 | 1944527 | 100% | 0 | 0 |  | 224002 | -443 | 223559 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Conversion of methyl chloroform and CTC to non-ODS solvent cleaning in the plating workshop of the Taedong-gang Television Factory (PTV), Taedong-gang District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 20 | A | O | I | CTC | 59.8 | 59.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-06-01 | 2006-07-01 | 597886 | -4408 | 593478 | 593478 | 100% | 0 | 0 |  | 75767 | -484 | 75283 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Conversion of Cleaning Processes from CTC to perchloroethylene cleaning at the galvanising workshop of the Pyongyang Illuminating Fixtures Factory (PIF) | Individual | ASP | DRK | SOL | 38 | INV | 21 | A | O | I | CTC | 29.7 | 29.7 |  |  | 2002-11-01 | 2004-06-01 | 2004-06-01 |  | 2004-12-01 | 2006-09-01 | 230172 | -59 | 230113 | 230113 | 100% | 0 | 0 |  | 29922 | -7 | 29915 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Conversion of cleaning processes from CTC (formerly methyl chloroform) to perchloroethylene cleaning at the Plating Workshop (PLT) of the refrigeration factory of the 5 October Automation Complex, Pyongchon District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 22 | A | O | I | CTC | 69.3 | 69.3 |  |  | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2006-05-01 | 508068 | -1981 | 506087 | 506087 | 100% | 0 | 0 |  | 65887 | -306 | 65581 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of investment projects in the solvents, process agents and fumigants sector (CTC) | Individual | ASP | DRK | MUS | 39 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 40000 | -22 | 39978 | 39978 | 100% | 0 | 0 |  | 3000 | -6 | 2994 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Preparation of investment projects in the refrigeration sector (CFC) | Individual | ASP | DRK | REF | 39 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 20000 | -267 | 19733 | 19733 | 100% | 0 | 0 |  | 1500 | -22 | 1478 | 0 | 0 | FIN | [13 empty] | 2003
COM | UNEP | Monitoring the activities in the refrigeration servicing subsector | Individual | ASP | DRK | REF | 40 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 |  | 10000 | 0 | 10000 | 5000 | 50% | 5000 | 0 | 5000 | 1300 | 0 | 650 | 650 | 0 | Project completed | [13 empty] | 2003 | Non Investment
FIN | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (first tranche) | Multi-Year | ASP | DRK | REF | 40 | INV | 26 | A | O | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-10-01 | 2004-07-01 |  | 2004-12-01 | 2008-07-01 | 384000 | 0 | 384000 | 384000 | 100% | 0 | 0 |  | 28800 | 0 | 28800 | 0 | 0 | Financial completion in Jul 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2003 |  | 56 | 56 |  |  | N/A | N/A | N/A
FIN | UNEP | Training of refrigeration service technicians in good servicing practices | Individual | ASP | DRK | REF | 40 | TRA | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 | 2008-12-01 | 70000 | -2171 | 67829 | 67829 | 100% | 0 | 0 | 0 | 9100 | -282 | 8817.77 | 0.23 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Assistance for the development of a licensing system and training of customs officers | Individual | ASP | DRK | REF | 40 | TRA | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-08-01 | 2006-01-01 | 50000 | -5486 | 44514 | 44514 | 100% | 0 | 0 | 0 | 6500 | -713 | 5786.82 | 0.18 | 0 | Project financially completed. | $ 5,486 plus $ 713 returned to ExCom 52 | [12 empty] | 2003 | Non Investment
FIN | UNIDO | Provision of basic tools for the registered service workshops | RMP Update | ASP | DRK | REF | 40 | TAS | 29 | A | O | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-09-01 | 2006-09-01 | 100000 | -10480 | 89520 | 89520 | 100% | 0 | 0 |  | 9000 | -943 | 8057 | 0 | 0 | FIN | [13 empty] | 2003
ONG | UNIDO | Plan for terminal phase-out of CTC (first tranche) | Multi-Year | ASP | DRK | PHA | 41 | INV | 30 | A | O | I | CTC | 0 | 613.8 |  |  | 2003-12-01 | 2004-02-01 | 2004-12-01 | 2009-06-01 |  |  | 3500000 | 0 | 3500000 | 3492768 | 99.79% | 7232 | 0 | 1 | 262500 | 0 | 261958 | 542 | 0 | As per ExCom Decision 55/12 UNIDO was requested to sell equipment specified in the decision and report back to the 57th ExCom. UNIDO has sold the 11 reactors and a corresponding report was submitted to the 57th ExCom Mtg. | [10 empty] | 2006-12-01 |  |  | 2003 | INV | 2200 | 2198.9 |  |  | Yes | Yes | Yes
COM | UNEP | Extension of institutional strengthening project: phase 2 | Individual | ASP | DRK | SEV | 41 | INS | 31 | A | T | I | CFC | 10.2 | 9.8 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 |  | 123552 | 0 | 123552 | 94105 | 76.17% | 29447 | 0 | 29447 | 0 | 0 | 0 | 0 | 0 | project completed | [13 empty] | 2003 | Non Investment
ONG | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (second tranche) | Multi-Year | ASP | DRK | REF | 42 | INV | 32 | A | O | I | CFC | 56 | 56 |  |  | 2004-04-01 | 2004-08-01 | 2005-12-01 | 2009-06-01 |  |  | 981011 | 0 | 981011 | 917085 | 93.48% | 63926 | 0 | 60000 | 73576 | 0 | 68781 | 4795 | 0 | Remaining equipment for the conversion of the compressor factory is being ordered. Procurement of additional safety equipment is planned. The project is expected to be complete in June 2009. | [13 empty] | 2004 | INV | 56 | 24.5 |  |  | N/A | N/A | N/A
FIN | UNIDO | Closure of ODS production plant: verification of complete closure of all CFC-11 and CFC-12 production facilities (second tranche) | Multi-Year | ASP | DRK | PRO | 42 | INV | 33 | A | O | I | CFC | 0 | 0 | 1250 | 1250 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2004-06-01 | 2004-12-01 | 733700 | 0 | 733700 | 733700 | 100% | 0 | 0 |  | 36685 | 0 | 36685 | 0 | 0 | FIN | [13 empty] | 2003 | INV |  |  | 0 | 0 | Yes | Yes | Yes
FIN | UNEP | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2005-11-01 | 2006-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNIDO | Plan for terminal phase-out of CTC (third tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 35 | A | O | I | CTC | 1441.4 | 597.7 |  |  | 2005-07-01 | 2006-04-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | Project completed in Jul 2008. Financial completion in Jul 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2005 | INV | 0 | 0 |  |  | Yes | Yes | Yes
FIN | UNIDO | Plan for terminal phase-out of CTC (second tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 36 | A | O | I | CTC | 0 | 0 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 1000000 | -157 | 999843 | 999843 | 100% | 0 | 0 |  | 75000 | -12 | 74988 | 0 | 0 | Project completed in Jul 2008. Financial completion in Jul 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2005 | INV | 192.8 | 191.4 |  |  | Yes | Yes | Yes
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 38 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-12-01 | 2006-12-01 | 15000 | -11196 | 3804 | 3804 | 100% | 0 | 0 |  | 1125 | -840 | 285 | 0 | 0 | FIN | [13 empty] | 2005 | NON-INV
COM | UNEP | Implementation of the NPP: regulations, training programme and monitoring (first tranche) | Multi-year | ASP | DRK | PHA | 47 | TAS | 39 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2008-07-01 |  | 234600 | 0 | 234600 | 174393.53 | 74.34% | 60206.47 | 0 | 60206.47 | 30498 | 0 | 22671.1589 | 7826.8411 | 0 | Project completed in July 2008 | [13 empty] | 2005 | Non Investment
ONG | UNIDO | Implementation of the NPP: recovery and recycling | Individual | ASP | DRK | PHA | 47 | TAS | 40 | A | O | I | CFC | 192.7 | 163.7 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 | 2009-12-01 |  |  | 536000 | 0 | 536000 | 357126 | 66.63% | 178874 | 2341 | 50000 | 40200 | 0 | 26784 | 13416 | 176 | Recovery and recycling equipment was purchased and additional tools and equipment are under procurement. The project is expected to be complete in December 2009. | [13 empty] | 2005 | INV | 177 | 91.8 |  |  | Yes | Yes | Yes
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | DRK | SEV | 47 | INS | 41 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-12-01 |  | 123552 | 0 | 123552 | 123552 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2005 | Non Investment
FIN | UNIDO | Preparation of a process agent terminal umbrella project | Individual | ASP | DRK | PAG | 48 | PRP | 42 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-05-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN | [13 empty] | 2006 | NON-INV
FIN | UNIDO | Closure of ODS production plant (third tranche) | Multi-Year | ASP | DRK | PRO | 49 | INV | 43 | A | O | I |  | 0 | 0 | 2530 | 2530 | 2006-07-01 | 2006-11-01 | 2008-12-01 |  | 2006-12-01 | 2008-04-01 | 488750 | 0 | 488750 | 488750 | 100% | 0 | 0 |  | 24438 | 0 | 24438 | 0 | 0 | Financial completion in Apr 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2006 | INV |  |  | 0 | 0 | Yes | Yes | Yes
COM | UNEP | Implementation of the NPP: regulations, training programme and monitoring (second tranche) | Multi-year | ASP | DRK | PHA | 49 | TAS | 44 | A | O | I | CFC | 54 | 54 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-12-01 |  | 2008-03-01 |  | 163400 | 0 | 163400 | 10000 | 6.12% | 153400 | 0 | 153400 | 21242 | 0 | 1300 | 19942 | 0 | Project completed in March 2008 | [13 empty] | 2006 | Non Investment
COM | UNIDO | Plan for terminal phase-out of CTC (fourth tranche) | Multi-Year | ASP | DRK | PHA | 49 | INV | 45 | A | O | I | CTC | 100 | 100 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 |  | 500000 | 0 | 500000 | 495930 | 99.19% | 4070 | 0 | 1 | 37500 | 0 | 37195 | 305 | 0 | The entire equipment was installed in DPRK for the all solvent cleaning projects, two fumigation projects and two pilot process agent plants, for the two remaining ones, which did not receive GL reactors, an option of "closure" projects is being considered according to the Decision of ExCom on alternative project solutions and the project is to be submitted by end of 2009 to the 59th ExCom. No CTC is used any longer in DPRK. Remaining project funds are planned to be spent for organization of a process agent training workshop (April 2009) and a study tour to China (May 2009) to get acquainted with ODS -free process agent projects. | [13 empty] | 2006 | INV | 92.8 | 0 |  |  | Yes | Yes | Yes
COM | UNIDO | Supplementary plan for terminal phase-out of CTC as process agent | Individual | ASP | DRK | PAG | 49 | INV | 46 | A | O | I | CTC | 229.9 | 229.9 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 |  | 884399 | 0 | 884399 | 24541 | 2.775% | 859858 | 850000 | 850000 | 66330 | 0 | 1841 | 64489 | 63750 | The project equipment was delivered and installed. The project completed in Dec 2008. | [13 empty] | 2006 | INV
ONG | UNEP | Implementation of the NPP: regulations, training programme and monitoring (third tranche) | Multi-Year | ASP | DRK | PHA | 51 | TAS | 47 | A | O | I | CFC | 18 | 0 |  |  | 2007-03-01 |  | 2008-03-01 | 2009-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 100000 | 13000 | 0 | 0 | 13000 | 0 | Project scheduled for completion in December 2009 | [13 empty] | 2007 | Non Investment
COM | UNIDO | Plan for terminal phase-out of CTC (fifth tranche) | Multi-Year | ASP | DRK | PHA | 52 | INV | 48 | A | O | I | CTC | 15 | 15 |  |  | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-12-01 |  | 284840 | 0 | 284840 | 172383 | 60.52% | 112457 | 112318 | 110000 | 21363 | 0 | 12929 | 8434 | 8424 | The entire equipment was installed in DPRK for the all solvent cleaning projects, two fumigation projects and two pilot process agent plants, for the two remaining ones, which did not receive GL reactors, an option of "closure" projects is being considered according to the Decision of ExCom on alternative project solutions and the project is to be submitted by end of 2009 to the 59th ExCom. No CTC is used any longer in DPRK. Remaining project funds are planned to be spent for organization of a process agent training workshop (April 2009) and a study tour to China (May 2009) to get acquainted with ODS -free process agent projects. | [13 empty] | 2007 | INV | 37.8 | 0 |  |  | Yes | Yes | Yes
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | DRK | SEV | 53 | INS | 49 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 130000 | 0 | 130000 | 0 | 0% | 130000 | 0 | 130000 | 0 | 0 | 0 | 0 | 0 | Project newly approved in the 53rd ExCom. For country's agreement. Issue on transfer of funds still remain. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Implementation of the NPP: regulations, training programme and monitoring (fourth tranche) | Multi-Year | ASP | DRK | PHA | 54 | TAS | 50 | A | O | I | CFC | 19 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-31 | 2009-03-31 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 2600 | 0 | 0 | 2600 | 0 | Customs training: 200 trained in 2008 (8 3-day training workshops) Refrigeration technicians training: 200 technicians trained in 2008 (8 3-day training workshops) enforcement measures for laws and regulations of ODS phase out and awareness education: 1) Developed a policy measure to mandate “all education agencies related with the CFC/HCFC refrigerant and refrigeration equipment to incorporate the concept of ozone layer protection in their curriculum”, presented to SPC and MLEP for the permission. 2). The code of good practices is under circulation for completion 3) Broadcasted TV cartoon “Ozzy Ozone” on the “World Environment Day” 3) Prepared Ozone session and broadcasted TV material “On Ozone and its damage to human health” in the National Workshop on the Occasion of “World Environment Day” in June 5 2008. 4) Mr. Kim Chol, the head of PMU office had an interview with “Pyongyang Times” in August on the activities to protect ozone layer conducted by DPR Korea. Published the Newsletter of Ozone Action in DPR Korea on half year basis. NOU and PMU visited the workshops to monitor the CFCs recovered or recycled in the service workshops. They also reviewed the reports of the service workshops on the operation of R&R machines | [13 empty] | 2008
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | DRK | PHA | 55 | PRP | 51 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 | 2009-07-01 |  |  | 50000 | 0 | 50000 | 8086 | 16.17% | 41914 | 5492 | 15000 | 3750 | 0 | 606 | 3144 | 412 | National consultants and international experts were recruited. | National consultants are working on the HCFC survey. Upon completion of the survey, workshop will be organized. National consultant(s) will be assigned to work on HCFC-legislation. | [12 empty] | 2008 | NON-INV
ONG | UNIDO | Plan for terminal phase-out of CTC (6th tranche) | Multi-Year | ASP | DRK | PHA | 55 | INV | 52 | A | O | I | CTC | 77.8 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 3004 | 90000 | 7500 | 0 | 0 | 7500 | 225 | The entire equipment was installed in DPRK for the all solvent cleaning projects, two fumigation projects and two pilot process agent plants, for the two remaining ones, which did not receive GL reactors, an option of "closure" projects is being considered according to the Decision of ExCom on alternative project solutions and the project is to be submitted by end of 2009 to the 59th ExCom. No CTC is used any longer in DPRK. Remaining project funds are planned to be spent for organization of a process agent training workshop (April 2009) and a study tour to China (May 2009) to get acquainted with ODS -free process agent projects. | [13 empty] | 2008 | INV | 37.8 | 0 |  |  | Yes | No | No
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | ECU | SEV | 04 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 92031 | -5365 | 86666 | 86666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation for the conversion of six aerosol plants from CFC-12 to LPG |  | LAC | ECU | ARS | 06 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 300000 | -300000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Training programme for the Montreal Protocol Project Implementation Unit | Individual | LAC | ECU | SEV | 06 | TRA | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-12-01 |  | 1994-06-01 | 1997-12-01 | 100000 | 40000 | 140000 | 140000 | 100% | 0 | 0 | 0 | 13000 | 5200 | 18200 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
CLO | IBRD | Country programme preparation | Individual | LAC | ECU | SEV | 06 | CPG | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 76100 | -76100 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | ECU | SEV | 06 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 95026 | 76203 | 171229 | 171229 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation for the reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants (Indurama, Durex, Ecasa) |  | LAC | ECU | FOA | 06 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Technical assistance in aerosol project preparation |  | LAC | ECU | ARS | 08 | PRP | 7 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-04-01 |  | 1993-04-01 | 1993-04-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Feasibility study for reduction of CFC-11 in rigid polyurethane foam insulation for refrigerators using water/CO2 formulation |  | LAC | ECU | FOA | 08 | PRP | 8 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 41000 | 50000 | 91000 | 91000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $50,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Support for country programme preparation |  | LAC | ECU | SEV | 07 | CPG | 9 | A | O | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-09-01 |  | 1993-09-01 | 1993-09-01 | 50000 | 6000 | 56000 | 56000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $6,000 credited against 1993 contributions (11th Meeting).
FIN | IBRD | Reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants: Indurama, Durex, and Ecasa | Individual | LAC | ECU | FOA | 09 | INV | 10 | N | O | I | CFC | 51 | 126.4 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1994-03-01 |  | 1995-11-01 | 1997-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprises have used funds to completely phaseout CFC-11 through adoption of HCFC-141b. PCR completed. |  |  | 1995-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening | Individual | LAC | ECU | SEV | 09 | INS | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1997-05-01 | 1997-08-01 | 204000 | -33327 | 170673 | 170673 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Public awareness campaign has been successfully carried out. Ozone Team actively supporting project implementation. |  |  | 1997-06-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of 18 aerosol plants to hydrocarbon propellants (Laboratorios Windsor (60 ton CFC/year), Pro Quim (6 ton), Jabonería Nacional (50 ton), Camposa (5 ton) and 14 other plants (169 ton) | Individual | LAC | ECU | ARS | 09 | INV | 12 | N | O | I | CFC | 290 | 82 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-09-01 | 1995-10-01 | 697000 | -365172 | 331828 | 331828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A complete phaseout in the aerosol sector has been achieved through this project component. All small aerosol producers have agreed to have their cans filled by Windsor Laboratories, Ecuador's largest aerosol filler. Balance to be returned to MF by Nov/99. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ECU | SEV | 09 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 68000 | 13231 | 81231 | 81231 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Assistance in implementation of country programme |  | LAC | ECU | SEV | 11 | CPG | 14 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | IBRD | Supervision of project implementation (approved at the 9th ExCom Meeting) |  | LAC | ECU | SEV | 12 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 15197 | 45197 | 45197 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY95. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Halon-1211 management plan |  | LAC | ECU | HAL | 13 | TAS | 16 | A | O | I |  | 5.5 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
CLO | UNIDO | Preparation of an investment project in a plant (Elasta) for the production of polyurethane flexible foam for automotive industry | Individual | LAC | ECU | SEV | 17 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1995-09-01 |  |  | 1999-12-01 | 15000 | -9243 | 5757 | 5757 | 100% | 0 | 0 |  | 1950 | -1203 | 747 | 0 | 0 | CLO
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ECU | SEV | 16 | PRP | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 56745 | 0 | 56745 | 56745 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY97. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | ECU | SEV | 21 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Ongoing. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | LAC | ECU | SEV | 04 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 40386 | -22201 | 18185 | 18185 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector for cut flowers and tobacco |  | LAC | ECU | FUM | 24 | PRP | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam, refrigeration and halon sectors |  | LAC | ECU | SEV | 24 | PRP | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-31 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 49000 | 0 | 49000 | 49000 | 100% | 0 | 0 |  | 6370 | 0 | 6370 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | Individual | LAC | ECU | FUM | 26 | TAS | 23 | N | O | I | MBR | 15 | 0 | 0 | 0 | 1998-11-01 | 2003-12-01 | 2005-11-01 | 2009-06-01 |  |  | 244244 | 0 | 244244 | 204525.75 | 83.74% | 39718.25 | 39718.25 | 39000 | 31751.72 | 0 | 26588.34 | 5163.38 | 5163.38 | First round of testing completed Sep 08 and final report issued. Highly satisfactory results obtained with the application of the alternative substance (Agrocelhone) in terms of securing the same level of production, size and quality of the plants and flowers and effectively controlling pests such as nematodes. Second round testing will take place to re-confirm results starting Feb 09 (to follow the planting cycle) and will be completed by Jun 09. Additional testing will not negatively impact compliance as GoE is committed to controlling MB imports as reflected in its action plan. (Rectification of previous year report: amount of Agrocelhone imported in 2007 was 450 lts.) | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the fabrication of flexible foams by replacement with methylene chloride at an automobile and furniture component manufacturing plant belonging to Elasto S.A. | Individual | LAC | ECU | FOA | 26 | INV | 24 | N | O | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-06-01 |  | 2002-10-01 | 2002-11-01 | 187286 | 0 | 187286 | 187286 | 100% | 0 | 0 |  | 24347.18 | 0 | 24347.18 | 0 | 0 | Project successfully completed in both physical and financial terms, and total funding disbursed. PCR under preparation. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacing CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Indurama S.A. | Individual | LAC | ECU | REF | 26 | INV | 25 | N | O | I | CFC | 28.38 | 28.38 | 0 | 0 | 1998-11-01 | 2002-09-01 | 2001-06-01 |  | 2002-09-01 | 2002-09-01 | 174792 | 0 | 174792 | 174792 | 100% | 0 | 0 |  | 22722.96 | 0 | 22722.96 | 0 | 0 | ODS free production started Jun. 02. Project successfully completed in both physical and financial terms and all funds disbursed. PCR is under preparation. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Ecuatoriana de Artefactos S.A. (ECASA) | Individual | LAC | ECU | REF | 26 | INV | 26 | N | O | I | CFC | 15.73 | 15.73 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-02-01 |  | 2001-11-30 | 2002-03-01 | 188545 | 0 | 188545 | 188545 | 100% | 0 | 0 |  | 24510.85 | 0 | 24510.85 | 0 | 0 | Project successfully completed both in physical and financial terms, and all funding disbursed. PCR under preparation. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the foam and commercial refrigeration sectors |  | LAC | ECU | SEV | 27 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | LAC | ECU | SEV | 28 | INS | 28 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2001-12-01 | 2001-08-01 |  | 2004-04-01 | 2004-04-01 | 97300 | 0 | 97300 | 97300 | 100% | 0 | 0 |  | 12649 | 0 | 12649 | 0 | 0 | NOU (MICIP) activities included work on the regulatory side, seeing thru a resolution that sets up import quotas for ODS in order to comply with the Protocol's control measures and additional agreed targets with ExCom. Public awareness activities included a series of seminars in schools in different regions of the country. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector |  | LAC | ECU | FUM | 33 | PRP | 29 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-11-01 | 2001-12-01 |  | 2002-11-01 | 2002-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | MeBr phaseout plan for the rose plant nursery sector approved at the 38th ExCom. | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation of a national CFC phase-out plan |  | LAC | ECU | SEV | 36 | PRP | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | NCPP submitted and approved at the 41st ExCom. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technology change for the phase-out of methyl bromide in the rose plant nursery sector | Individual | LAC | ECU | FUM | 38 | INV | 31 | N | O | I | MBR | 37.2 | 37.2 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2005-11-01 |  | 2005-01-01 | 2005-02-01 | 597945 | 0 | 597945 | 597945 | 100% | 0 | 0 |  | 75774 | 0 | 75774 | 0 | 0 | Project completed. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: first tranche | Multiyear | LAC | ECU | PHA | 41 | INV | 32 | N | O | I | CFC | 11 | 11 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2005-04-01 |  | 777326 | 0 | 777326 | 777326 | 100% | 0 | 0 | 0 | 58299.45 | 0 | 58299.44 | 0.01 | 0.01 | NCPP advancing satisfactorily and country has been meeting its CFC consumption commitments. To date, $1,053,319.94 has been disbursed and an additional $167,598 is committed (i.e. contracts signed) and expected to be disbursed by mid-09. Program to replace chillers is underway. | [13 empty] | 2003 | INV | 235 | 143 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | LAC | ECU | SEV | 42 | INS | 33 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-02-01 | 2007-03-01 | 176800 | 0 | 176800 | 176800 | 100% | 0 | 0 |  | 13260 | 0 | 13260 | 0 | 0 | IS completed. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of a methyl bromide project |  | LAC | ECU | FUM | 45 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-12-01 | 2009-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 25000 | 10000 | 1875 | 0 | 0 | 1875 | 1875 | Preparation is postponed while new alternative is tested. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a TCA phase-out project |  | LAC | ECU | SOL | 45 | PRP | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2005-12-01 |  | 2006-02-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 1500 | 0 | 1500 | 0 | 0 | Results from the survey and seminar carried out in Jan 06 show that there is not enough consumption of TCA in the country, and remaining consumers are changing technologies on their own. A project will not be presented to MLF. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | LAC | ECU | PHA | 45 | INV | 36 | N | O | I | CFC | 85 | 85 | 0 | 0 | 2005-04-01 | 2008-10-01 | 2006-04-01 | 2009-06-01 |  |  | 439319 | 0 | 439319 | 276000 | 62.82% | 163319 | 163319 | 163319 | 32349 | 0 | 20323.1 | 12025.9 | 12025.9 | NCPP advancing satisfactorily and country has been meeting its CFC consumption commitments. To date, $1,053,319.94 has been disbursed and an additional $167,598 is committed (i.e. contracts signed) and expected to be disbursed by mid-09. Program to replace chillers is underway. | [13 empty] | 2005 | INV | 150 | 133 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | LAC | ECU | PHA | 49 | INV | 37 | N | O | I | CFC | 70 | 70 | 0 | 0 | 2006-07-01 |  | 2007-12-01 | 2009-06-01 |  |  | 227410 | 0 | 227410 | 0 | 0% | 227410 | 227410 | 167598 | 17055 | 0 | 0 | 17055 | 17055 | NCPP advancing satisfactorily and country has been meeting its CFC consumption commitments. As the tranche was newly approved, there has been no disbursement to date. Program to replace chillers is under implementation. | [13 empty] | 2005 | INV | 80 | 63 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Extension of institutional strengthening project (phase IV, first year) | Individual | LAC | ECU | SEV | 51 | INS | 38 | N | T | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 | 2009-04-30 |  |  | 88400 | 0 | 88400 | 60000 | 67.87% | 28400 | 28400 | 28400 | 6630 | 0 | 4500 | 2130 | 2130 | The objective of the ISP is to continue implementing the NCPP and enact supporting regulations to ensure sustainable phaseout. This entailed continued efforts to ratify the Beijing Amendment by contacting members of the recently established National Assembly; monitoring compliance with the Protocols control measures and ExCom agreement; enforcement of the licensing system to control the import and export of ODS; continued implementation of the Action Plan to return to compliance with MeBr consumption; and continuation of the Ozone Protection Awareness Campaign in Radio, Newspaper and Television to maintain phase-out momentum of the different ODS consuming sectors, as well as to identify the remaining ODS users in the country. | [13 empty] | 2006 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | LAC | ECU | PHA | 52 | INV | 39 | N | O | I | CFC | 38 | 0 | 0 | 0 | 2007-07-01 |  | 2008-07-31 | 2009-06-01 |  |  | 227411 | 0 | 227411 | 0 | 0% | 227411 | 227411 | 167598.24 | 17056 | 0 | 0 | 17056 | 17056 | NCPP advancing satisfactorily and country has been meeting its CFC consumption commitments. To date, $1,053,319.94 has been disbursed and an additional $167,598 is committed (i.e. contracts signed) and expected to be disbursed by mid-09. Program to replace chillers is underway. | [13 empty] | 2007 | INV | 42 | 28 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Preparation of a HCFC phase-out management plan |  | LAC | ECU | PHA | 55 | PRP | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 | 2010-09-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 150000 | 85000 | 11250 | 0 | 0 | 11250 | 11250 | Preparation activities have not initiated. The Bank's LAC Region will implement HCFC phase-out projects over the next years, however new projects will be designed and developed at the regional level, involving several countries under a more strategic approach and reducing administrative costs. Therefore, the Bank will not be involved in the preparation and implementation of projects at the country level. Given that Ecuador is interested in developing the HCFH phase, the transfer of the preparation funds to another implementing agency is recommended. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | LAC | ECU | PHA | 56 | INV | 41 | N | O | I | CFC | 42 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-01 |  |  | 18334 | 0 | 18334 | 0 | 0% | 18334 | 18334 | 18334 | 1375 | 0 | 0 | 1375 | 1375 | NCPP advancing satisfactorily and country has been meeting its CFC consumption commitments. As the tranche was newly approved, there has been no disbursement to date. Program to replace chillers is under implementation. | [13 empty] | 2007 | INV | 42 | 0 | 0 | 0 |  | No | No
ONG | IBRD | Extension of institutional strengthening project (phase IV, second year) | Individual | LAC | ECU | SEV | 56 | INS | 42 | N | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-09-30 | 2009-09-30 |  |  | 88400 | 0 | 88400 | 0 | 0% | 88400 | 88400 | 80000 | 6630 | 0 | 0 | 6630 | 6630 | Newly approved. | [13 empty] | 2007 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | AFR | EGY | SEV | 04 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 68981 | 28539 | 97520 | 97520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Study tours for officials from the Ministry of the Environment, and pre-feasibility study | Individual | AFR | EGY | SEV | 04 | TRA | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-02-01 |  | 1992-06-01 | 1997-12-01 | 51000 | -6910 | 44090 | 44090 | 100% | 0 | 0 | 0 | 6630 | -898 | 5732 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | EGY | SEV | 06 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 227827 | -219155 | 8672 | 8672 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of investment projects | Individual | AFR | EGY | SEV | 06 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1993-09-01 | 2003-04-01 | 100000 | 319 | 100319 | 100319 | 100% | 0 | 0 | 0 | 13000 | 41 | 13041 | 0 | 0 | Completed in 1993. Financially completed in 2003. | [13 empty] | 1992 | Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of flexible polyurethane foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 08 | INV | 5 | A | O | I | CFC | 121 | 121 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1993-10-01 |  | 1994-01-01 | 2003-04-01 | 497000 | 3489 | 500489 | 500489 | 100% | 0 | 0 | 0 | 64610 | 454 | 65064 | 0 | 0 | Completed in 1994. Financially completed in 2003. | [13 empty] | 1992 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacturing of moulded, flexible, semi-rigid and rigid polyurethane foam at Taki-Vita factory | Individual | AFR | EGY | FOA | 08 | INV | 6 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1995-04-01 | 2003-04-01 | 293950 | 58550 | 352500 | 352500 | 100% | 0 | 0 | 0 | 38214 | 7612 | 45826 | 0 | 0 | Completed in 1995. Financially completed in 2003. | [13 empty] | 1992 | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of moulded polyurethane foams at Technopol Egypt SAE | Individual | AFR | EGY | FOA | 08 | INV | 7 | A | O | I | CFC | 55 | 55 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-04-01 | 2003-04-01 | 645000 | 31211 | 676211 | 676211 | 100% | 0 | 0 | 0 | 83850 | 4057 | 87907 | 0 | 0 | Completed in 1994. Financially completed in 2003. | [13 empty] | 1992 | Investment
FIN | IBRD | Conversion of refrigeration compressor manufacturing to HFC-134a at MISR Compressors Manufacturing Co. (MCMC) | Individual | AFR | EGY | REF | 08 | INV | 8 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1994-03-01 |  | 1997-07-01 | 2000-11-01 | 2800000 | -950000 | 1850000 | 1850000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Savings of $250,000 to be returned to the 36th ExCom. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC in refrigeration at Koldair Company | Individual | AFR | EGY | REF | 08 | INV | 9 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-01-01 | 2003-04-01 | 272000 | -21979 | 250021 | 250021 | 100% | 0 | 0 | 0 | 35360 | -2857 | 32503 | 0 | 0 | Completed in 1994. Financially completed in 2003. | [13 empty] | 1992 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at Al-Sharif Plastic Factories | Individual | AFR | EGY | FOA | 09 | INV | 10 | A | O | I | CFC | 75 | 75 | 0 | 0 | 1993-03-01 | 1998-12-01 | 1994-06-01 |  | 2001-12-01 | 2003-04-01 | 498000 | -22472 | 475528 | 475528 | 100% | 0 | 0 | 0 | 64740 | -2921 | 61819 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1993 | Investment
FIN | UNIDO | Preparatory assistance for elimination of CFCs in manufacturing foams at Advechems and El Fateh | Individual | AFR | EGY | REF | 09 | TAS | 11 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-08-01 | 1998-08-01 | 50000 | -9289 | 40711 | 40711 | 100% | 0 | 0 |  | 6500 | -1216 | 5284 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 in manufacture of molded foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 09 | INV | 12 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1993-11-01 | 2003-04-01 | 275000 | 9431 | 284431 | 284431 | 100% | 0 | 0 | 0 | 35750 | 1226 | 36976 | 0 | 0 | Completed in 1993. Financially completed in 2003. | [13 empty] | 1993 | Investment
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | EGY | SEV | 09 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112200 | -69976 | 42224 | 42224 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Institutional strengthening unit for the Montreal Protocol related activities | Individual | AFR | EGY | SEV | 10 | INS | 14 | N | T | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1996-05-01 |  | 1996-12-01 | 2000-07-01 | 263450 | 0 | 263450 | 263450 | 100% | 0 | 0 |  | 34249 | 0 | 34249 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded flexible polyurethane foam at Modern Building Carpentry Co. (Mobica) | Individual | AFR | EGY | FOA | 10 | INV | 15 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 434000 | 0 | 434000 | 434000 | 100% | 0 | 0 | 0 | 56420 | 0 | 56420 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNIDO | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at (ADVECHEMS) | Individual | AFR | EGY | FOA | 10 | INV | 16 | A | O | I | CFC | 196 | 183.3 |  |  | 1993-06-01 | 1994-03-01 | 1994-06-01 |  | 1994-12-01 | 2000-12-01 | 904000 | 0 | 904000 | 904000 | 100% | 0 | 0 |  | 117520 | -44 | 117476 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded rigid polyurethane foam at Cairo Light Industries Co. (Olympic Electric) | Individual | AFR | EGY | FOA | 10 | INV | 17 | A | O | I | CFC | 75 | 75 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-12-01 |  | 1995-11-01 | 2000-12-01 | 940000 | -28084 | 911916 | 911916 | 100% | 0 | 0 | 0 | 122200 | -3651 | 118549 | 0 | 0 | Completed in 1995. Financially completed in 2000. | [13 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of rigid polyurethane foam (PUF) at Specialized Engineering Contracting Co. | Individual | AFR | EGY | FOA | 11 | INV | 18 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1994-12-01 | 1998-12-01 | 85000 | -5398 | 79602 | 79602 | 100% | 0 | 0 | 0 | 11050 | -702 | 10348 | 0 | 0 | Completed in 1994. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam at Alex Foam (formerly Dekheila Chemical Industries Co.) | Individual | AFR | EGY | FOA | 11 | INV | 19 | A | O | I | CFC | 130 | 130 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1995-11-01 | 1998-12-01 | 650000 | -82388 | 567612 | 567612 | 100% | 0 | 0 | 0 | 84500 | -10710 | 73790 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam (PUF) at Horse Foam Co. | Individual | AFR | EGY | FOA | 11 | INV | 20 | A | O | I | CFC | 120 | 120 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-08-01 |  | 1997-03-01 | 2000-07-01 | 385000 | -107636 | 277364 | 277364 | 100% | 0 | 0 | 0 | 50050 | -13993 | 36057 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1993 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | FOA | 11 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-01-01 |  | 1994-12-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of flexible polyurethane foam at Foam Industrial and Hyma | Individual | AFR | EGY | FOA | 12 | INV | 22 | A | O | I | CFC | 170 | 170 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-06-01 |  | 1997-03-01 | 2000-07-01 | 525000 | -11898 | 513102 | 513102 | 100% | 0 | 0 | 0 | 68250 | -1547 | 66703 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Technical assistance to prepare a national halon action plan and project development | Individual | AFR | EGY | HAL | 12 | TAS | 23 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-01-01 |  | 1997-03-01 | 1998-12-01 | 25000 | 1730 | 26730 | 26730 | 100% | 0 | 0 | 0 | 3250 | 225 | 3475 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [13 empty] | 1994 | Non-Investment
FIN | IBRD | Preparation of investment projects in the commercial and industrial refrigeration (1994) |  | AFR | EGY | REF | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | -18884 | 6116 | 6116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | AFR | EGY | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC free-technology in the manufacture of rigid molded and miscellaneous PUF at 5 plants: Tiba Air, Egat Company, Solar Energy Company, Ismailia Aluminum Company, and Fu Tech Company | Individual | AFR | EGY | FOA | 12 | INV | 26 | A | O | I | CFC | 44.2 | 44.2 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-03-01 | 1997-11-01 | 870000 | -107668 | 762332 | 762332 | 100% | 0 | 0 | 0 | 113100 | -13997 | 99103 | 0 | 0 | Completed in 1997. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at Scib Chemical Company | Individual | AFR | EGY | FOA | 12 | INV | 27 | A | O | I | CFC | 12.4 | 12.4 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1995-11-01 | 2003-02-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 2003. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at El Fateh | Individual | AFR | EGY | FOA | 12 | INV | 28 | A | O | I | CFC | 59 | 59 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2002-03-01 | 2003-01-01 | 496000 | -1 | 495999 | 495999 | 100% | 0 | 0 | 0 | 64480 | 0 | 64480 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  | 1997-09-01 | [10 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at Industrial Engineering Company for Construction and Development (Icon) | Individual | AFR | EGY | FOA | 12 | INV | 29 | A | O | I | CFC | 51 | 51 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1999-10-01 | 2001-12-01 | 498000 | 0 | 498000 | 498000 | 100% | 0 | 0 | 0 | 64740 | 0 | 64740 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology Reftruck Company | Individual | AFR | EGY | REF | 12 | INV | 30 | A | O | I | CFC | 25.1 | 25.1 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1998-09-01 | 2002-11-01 | 385000 | -2692 | 382308 | 382308 | 100% | 0 | 0 | 0 | 50050 | -350 | 49700 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC free-technology at Misr Panel (Egyptian Company for Cold Storage Industries) | Individual | AFR | EGY | REF | 12 | INV | 31 | A | O | I | CFC | 74.4 | 74.4 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2001-03-01 | 2002-03-01 | 636000 | 0 | 636000 | 636000 | 100% | 0 | 0 | 0 | 82680 | 0 | 82680 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  |  | 1997-09-01 | [10 empty] | 1994 | Investment
FIN | UNIDO | Phasing out ODS at the refrigerator plants of Delta Industrial Co. | Individual | AFR | EGY | REF | 13 | INV | 32 | A | O | I | CFC | 97 | 117 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1997-05-01 | 2000-07-01 | 2611986 | -133089 | 2478897 | 2478897 | 100% | 0 | 0 |  | 339558 | -17812 | 321746 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Electrostar for Refrigeration Co. | Individual | AFR | EGY | REF | 13 | INV | 33 | A | O | I | CFC | 46 | 51 |  |  | 1994-07-01 | 1995-02-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1450585 | -13996 | 1436589 | 1436589 | 100% | 0 | 0 |  | 188576 | -2115 | 186461 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in production of household refrigeration at additional four companies | Individual | AFR | EGY | REF | 13 | PRP | 34 | A | O | I |  | 0 | 0 |  |  | 1994-07-01 | 1994-10-01 | 1994-10-01 |  | 1995-08-01 | 1998-08-01 | 15000 | 3364 | 18364 | 18364 | 100% | 0 | 0 |  | 1950 | 437 | 2387 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Kiriazi Refrigerators Manufacturing Co. | Individual | AFR | EGY | REF | 13 | INV | 35 | A | O | I | CFC | 137 | 137 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1643040 | -52934 | 1590106 | 1590106 | 100% | 0 | 0 |  | 213595 | -7209 | 206386 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacturing of rigid PUF at seven enterprises: GMC, Petrojet, Modern Products, Cairo General Contractors Co., Egyptian Solar Energy, Tawifika, Helwan | Individual | AFR | EGY | FOA | 15 | INV | 36 | A | O | I | CFC | 69 | 69 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 2000-12-01 | 2002-11-01 | 780000 | -292655 | 487345 | 487345 | 100% | 0 | 0 | 0 | 101400 | -38045 | 63355 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-07-01 | [9 empty] | 1994 | Investment
FIN | UNIDO | Phasing out ODS at Helwan Company for Metallic Appliances domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 38 | A | O | I | CFC | 7.5 | 7.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 644239 | -29419 | 614820 | 614820 | 100% | 0 | 0 |  | 83751 | -3951 | 79800 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Super Bosh Factory domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 39 | A | O | I | CFC | 13 | 13 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 760066 | -34709 | 725357 | 725357 | 100% | 0 | 0 |  | 98809 | -4662 | 94147 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Islamic Company for Industrialization (Siltal) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 40 | A | O | I | CFC | 26 | 26 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 866633 | -39576 | 827057 | 827057 | 100% | 0 | 0 |  | 112662 | -5315 | 107347 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Société Mondiale pour Refroidissement (Alaska) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 41 | A | O | I | CFC | 55 | 55 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 1518606 | -69349 | 1449257 | 1449257 | 100% | 0 | 0 |  | 197419 | -9314 | 188105 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at International Co. for Refrigeration and Appliances (Iberna) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 42 | A | O | I | CFC | 19 | 19 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 852738 | -38941 | 813797 | 813797 | 100% | 0 | 0 |  | 110856 | -5230 | 105626 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at El Nasr Company for Electric and Electronic Apparatus (Philips) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 43 | A | O | I | CFC | 22.5 | 22.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 854690 | -39030 | 815660 | 815660 | 100% | 0 | 0 |  | 111110 | -5242 | 105868 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Royal Engineering, Co. | Individual | AFR | EGY | REF | 15 | INV | 44 | A | O | I | CFC | 20.3 | 20.3 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 539000 | -1790 | 537210 | 537210 | 100% | 0 | 0 | 0 | 70070 | -233 | 69837 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Port Said Metal Work, Co. (MOG) | Individual | AFR | EGY | REF | 15 | INV | 45 | A | O | I | CFC | 11.8 | 11.8 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1999-10-01 | 2003-02-01 | 484000 | 0 | 484000 | 484000 | 100% | 0 | 0 | 0 | 62920 | 0 | 62920 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [9 empty] | 1994 | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF at El-Tawil Manufacturing Company | Individual | AFR | EGY | FOA | 15 | INV | 46 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-12-01 |  |  | 2000-12-01 | 121000 | -91977 | 29023 | 29023 | 100% | 0 | 0 | 0 | 15730 | -11957 | 3773 | 0 | 0 | Canceled in 1999. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation of investment projects (1995) |  | AFR | EGY | SEV | 16 | PRP | 47 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 65623 | 0 | 65623 | 65623 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The reconnaissance mission reported that the scope of refrigeration-sector projects would be limited to recovery and recycling activities. Project identification was then undertaken. This activity is now completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible molded PUF and integral skin foam at El Shabrawi | Individual | AFR | EGY | FOA | 18 | INV | 48 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 1999-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at United Investment Corporation Inc. | Individual | AFR | EGY | REF | 18 | INV | 49 | A | O | I | CFC | 48.7 | 48.7 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1999-11-01 | 2003-11-01 | 493350 | -32495 | 460855 | 460855 | 100% | 0 | 0 | 0 | 64136 | -4224 | 59912 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refcat Compnay Inc. | Individual | AFR | EGY | REF | 18 | INV | 50 | A | O | I | CFC | 26.8 | 26.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 2000-12-01 | 409000 | -19 | 408981 | 408981 | 100% | 0 | 0 | 0 | 53170 | -3 | 53167 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
CLO | UNIDO | Conversion of cleaning processes from CFC-113 to Aqueous Cleaning at Optica | Individual | AFR | EGY | SOL | 18 | INV | 51 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-06-01 |  |  | 1996-06-01 | 12043 | -12043 | 0 | 0 |  | 0 | 0 |  | 1566 | -1566 | 0 | 0 | 0 | CLO
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to non-ODS cleaning at 3 electronic companies | Individual | AFR | EGY | SOL | 18 | INV | 52 | A | O | I | CFC TCA | 13.7 | 13.7 |  |  | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-10-01 | 1998-11-01 | 227203 | 0 | 227203 | 227203 | 100% | 0 | 0 |  | 29536 | 0 | 29536 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from CFC-113 and 1,1,1 TCA to semi-aqueous cleaning at Arab International Optronics | Individual | AFR | EGY | SOL | 18 | INV | 53 | A | O | I | CFC TCA | 2.1 | 2.1 |  |  | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1999-12-01 | 2000-03-01 | 48533 | 0 | 48533 | 48533 | 100% | 0 | 0 |  | 6309 | 0 | 6309 | 0 | 0 | FIN |  |  |  | 1999-07-01
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Siltal | Individual | AFR | EGY | SOL | 18 | INV | 54 | A | O | I | TCA | 2 | 2 |  |  | 1995-11-01 | 1997-11-01 | 1996-06-01 |  | 1998-10-01 | 2000-07-01 | 48784 | -419 | 48365 | 48365 | 100% | 0 | 0 |  | 6342 | -65 | 6277 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | SEV | 18 | PRP | 55 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1995 | Investment
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Technopol | Individual | AFR | EGY | SOL | 19 | INV | 56 | A | O | I | TCA | 6 | 6 |  |  | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2000-05-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282 | 0 | 16282 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to cleaning in perchloroethylene at Abbasol | Individual | AFR | EGY | SOL | 19 | INV | 57 | A | O | I | TCA | 8 | 8 |  |  | 1996-05-01 | 1998-10-01 | 1997-05-01 |  | 1998-12-01 | 1999-07-01 | 154544 | 0 | 154544 | 154544 | 100% | 0 | 0 |  | 20091 | 0 | 20091 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at El-Mohandes | Individual | AFR | EGY | REF | 20 | INV | 58 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 |  | 2000-06-01 | [8 empty] | 1996 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Amiral | Individual | AFR | EGY | REF | 20 | INV | 59 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-06-01 | 1998-09-01 |  |  | 2003-11-01 | 160000 | -70081 | 89919 | 89919 | 100% | 0 | 0 | 0 | 20800 | -9111 | 11689 | 0 | 0 | Canceled in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [10 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | EGY | FOA | 21 | PRP | 60 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 40000 | -7520 | 32480 | 32480 | 100% | 0 | 0 | 0 | 5200 | -978 | 4222 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNIDO | Institutional strengthening project for the Montreal Protocol related activities (Phase II) | Individual | AFR | EGY | SEV | 21 | INS | 61 | N | T | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1999-02-01 |  | 1998-12-01 | 1999-09-01 | 43900 | 132009 | 175909 | 175909 | 100% | 0 | 0 |  | 5707 | 17125 | 22832 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector | Individual | AFR | EGY | SOL | 21 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-07-01 | 1997-06-01 |  | 2000-07-01 | 2000-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNIDO | Preparatory assistance for phase out of ODS in the production of household refrigerators at Electrostar & Kiriazi | Individual | AFR | EGY | REF | 09 | TAS | 63 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-03-01 | 1998-08-01 | 50000 | 6602 | 56602 | 56602 | 100% | 0 | 0 |  | 6500 | 858 | 7358 | 0 | 0 | FIN
FIN | UNDP | Phaseout of the remaining ODS consumption in the foam sector (11 enterprises) | Individual | AFR | EGY | FOA | 22 | INV | 64 | A | O | I | CFC | 319 | 319 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 2005-01-01 | 2007-01-01 | 1672000 | -18136 | 1653864 | 1653864 | 100% | 0 | 0 | 0 | 217360 | -2358 | 215002 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  |  |  |  | 2000-12-01 | [8 empty] | 1997 | Investment
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | EGY | SEV | 04 | PRP | 65 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 131065 | -51944 | 79121 | 79121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | UNDP | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and curcubits) | Individual | AFR | EGY | FUM | 24 | PRP | 66 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 1998-07-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 1998. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation to prepare one halon sector programme | Individual | AFR | EGY | HAL | 24 | PRP | 67 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 2000-10-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | Germany | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and cucurbits) | Individual | AFR | EGY | FUM | 25 | PRP | 68 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1998-12-01 |  | 1998-08-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Implementation of the demonstration | [13 empty] | 1998
FIN | Germany | Four alternatives to the use of methyl bromide in horticulture (strawberries, tomatoes, cucurbits) | Individual | AFR | EGY | FUM | 26 | DEM | 69 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-12-01 | 2001-03-01 | 308000 | -81000 | 227000 | 227000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted. Balance was offset against German contribution at the 40th Meeting.
FIN | Germany | Application of methyl bromide alternatives in grain storage | Individual | AFR | EGY | FUM | 26 | DEM | 70 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted. | [13 empty] | 1995
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | EGY | REF | 27 | PRP | 71 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 1999-09-01 | 2002-01-01 | 28700 | 0 | 28700 | 28700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 27 | PRP | 72 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2001-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Phase III: Institutional Strengthening Project for the Montreal Protocol Related Activities | Individual | AFR | EGY | SEV | 27 | INS | 73 | N | T | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 2001-04-01 |  | 2001-11-01 | 2002-05-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | -1 | 22749 | 0 | 0 | FIN
FIN | Germany | Implementation of the RMP: modification of legal provisions and information system | RMP | AFR | EGY | REF | 29 | TAS | 74 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | UNIDO was subcontracted. Project completed. Draft PCR submitted in September 2005. | [13 empty] | 1997
FIN | Germany | Implementation of the RMP: establishing a national recovery and recycling network | Individual | AFR | EGY | REF | 29 | TAS | 75 | A | O | I | CFC | 100 | 100 | 0 |  | 1999-11-01 | 2000-04-01 | 2002-12-01 |  | 2007-12-01 | 2008-10-01 | 599500 | 0 | 599500 | 599500 | 100% | 0 | 0 | 0 | 77935 | 0 | 77935 | 0 | 0 | Project is completed. A final monitoring and evaluation workshop was organized with NOU in August 2007 to establish a network for monitoring in the whole country. PCR was approved by NOU and was sent to MLF in October 2008.
FIN | Germany | Implementation of the RMP: implementation of measures to address the informal sector | RMP | AFR | EGY | REF | 29 | TAS | 76 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 252500 | 0 | 252500 | 252500 | 100% | 0 | 0 | 0 | 32825 | 0 | 32825 | 0 | 0 | Unido was subcontracted, training courses have been carried out successfully. Project completed. Draft PCR submitted in September 2005. | [13 empty] | 1997
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | EGY | FUM | 30 | PRP | 77 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-12-01 | 2003-05-01 | 25000 | -858 | 24142 | 24142 | 100% | 0 | 0 |  | 3250 | -116 | 3134 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 30 | PRP | 78 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-12-01 | 2001-04-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | -1 | 1949 | 0 | 0 | FIN
FIN | UNIDO | Conversion of TCA used for the formulation of degreasing and contact cleaners and crack detectors to new formulations with special hydrocarbons and heavy chlorinated ester at Sien | Individual | AFR | EGY | SOL | 28 | INV | 79 | A | O | I | TCA | 9 | 9 |  |  | 1999-07-01 | 2000-11-01 | 2000-08-01 |  | 2002-06-01 | 2003-10-01 | 231435 | 0 | 231435 | 231435 | 100% | 0 | 0 |  | 30087 | -34 | 30053 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at Maasara Co. for engineering industries | Individual | AFR | EGY | SOL | 31 | INV | 80 | A | O | I | TCA | 10.7 | 10.7 |  |  | 2000-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-12-01 | 2004-03-01 | 294950 | 0 | 294950 | 294950 | 100% | 0 | 0 |  | 38344 | -4 | 38340 | 0 | 0 | FIN
COM | UNDP | Halon management bank programme | Individual | AFR | EGY | HAL | 32 | TAS | 81 | N | O | I | Halon | 754 | 754 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2004-01-01 |  | 2007-12-01 |  | 405000 | 0 | 405000 | 401106 | 99.04% | 3894 | 0 | 3115.2 | 52650 | 0 | 52143.78 | 506.22 | 0 | Completed in 2007. | [13 empty] | 2000 | Investment
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | AFR | EGY | FUM | 33 | PRP | 82 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-12-01 | 2003-05-01 | 30000 | -528 | 29472 | 29472 | 100% | 0 | 0 |  | 3900 | -75 | 3825 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Renewal of institutional strengthening project (phase IV) | Individual | AFR | EGY | SEV | 34 | INS | 83 | N | T | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-12-01 | 175000 | -8670 | 166330 | 166330 | 100% | 0 | 0 |  | 22750 | -1161 | 21589 | 0 | 0 | FIN | [13 empty] | 2001 | NON-INV
TRF | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | AFR | EGY | REF | 36 | PRP | 84 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Transferred in 2003. | [13 empty] | 2002 | Investment
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | EGY | PHA | 36 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-04-01 | 2003-09-01 |  | 2005-12-01 | 2006-12-01 | 75000 | -33 | 74967 | 74967 | 100% | 0 | 0 |  | 9750 | -4 | 9746 | 0 | 0 | FIN | [13 empty] | 2002 | INV
ONG | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation | Individual | AFR | EGY | FUM | 38 | INV | 86 | A | O | I | MBR | 185.6 | 185.6 |  |  | 2002-11-01 | 2003-09-01 | 2009-11-01 | 2009-06-01 |  |  | 2750592 | 0 | 2750592 | 2085183 | 75.81% | 665409 | 346121 | 400000 | 312565 | 0 | 239370 | 73195 | 38073 | Equipment already purchased and installed. A big training programme in grafting has started in November 2008. The first phase is being almost completed. A second phase has been submitted for approval to the ExCom. The project is expected to be completed in Jun 2009. | [13 empty] | 2002 | INV
FIN | UNIDO | Extension of institutional strengthening project | Individual | AFR | EGY | SEV | 40 | INS | 87 | N | T | I |  | 18.9 | 18.9 |  |  | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-08-01 | 228323 | -1 | 228322 | 228322 | 100% | 0 | 0 |  | 17125 | -1 | 17124 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2003
COM | UNIDO | Terminal solvent sector umbrella project | Individual | AFR | EGY | SOL | 44 | INV | 89 | A | O | I | CFC CTC TCA | 41 | 41 |  |  | 2004-12-01 | 2005-02-01 | 2006-06-01 |  | 2007-12-01 |  | 778464 | 0 | 778464 | 772619 | 99.25% | 5845 | 3674 | 3500 | 58385 | 0 | 57946 | 439 | 276 | The project will be financially completed upon disbursement of unliquidated obligations. | [11 empty] | 2007-07-01 |  | 2004 | INV
FIN | UNIDO | Preparation of a MDI phase-out plan (CFC) | Individual | AFR | EGY | ARS | 45 | PRP | 90 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 50000 | -337 | 49663 | 49663 | 100% | 0 | 0 |  | 3750 | -25 | 3725 | 0 | 0 | Financial completion in May 2008. Refund was reported to 55th ExCom, Jul 2008. FIN. | [13 empty] | 2005 | NON-INV
COM | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | AFR | EGY | PHA | 46 | INV | 91 | A | O | I | CFC | 190 | 190 |  |  | 2005-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 |  | 1000000 | 0 | 1000000 | 969957 | 97% | 30043 | 30000 | 29000 | 75000 | 0 | 72747 | 2253 | 2250 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2005 | INV | 822 | 821.2 |  |  | Yes | Yes | Yes
ONG | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | AFR | EGY | ARS | 50 | INV | 92 | A | O | I | CFC | 159.5 | 0 |  |  | 2006-11-01 | 2007-01-01 | 2009-12-01 | 2010-12-01 |  |  | 5899000 | 0 | 5899000 | 630232 | 10.68% | 5268768 | 2883777 | 2000000 | 442425 | 0 | 47267 | 395158 | 216283 | In 2008 UNIDO has procured filling equipment for the two Egyptian companies, ADCO and EIPICO. The selection of the technology provider has been completed in November 2008. The pilot batches of the first MDI are being planned to achieve by Dec 2009. The project completion date is December 2010. | [13 empty] | 2006 | INV
ONG | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | AFR | EGY | PHA | 50 | INV | 93 | A | O | I | CFC | 182 | 0 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 | 2009-03-01 |  |  | 1200000 | 0 | 1200000 | 837636 | 69.8% | 362364 | 352070 | 150000 | 90000 | 0 | 62823 | 27177 | 26405 | The implementation activities under this tranche will be completed at the end of March 2009. | [13 empty] | 2006 | INV | 595 | 593.6 |  |  | Yes | Yes | Yes
COM | UNIDO | Extension of institutional strengthening project (phase VI) | Individual | AFR | EGY | SEV | 51 | INS | 94 | N | T | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-12-01 |  | 2008-12-01 |  | 228323 | 0 | 228323 | 151540 | 66.37% | 76783 | 49162 | 76000 | 17124 | 0 | 11366 | 5758 | 3687 | Progress reports received as of December 2008 and the project completed in Dec 2008. | [13 empty] | 2007 | NON-INV
ONG | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | AFR | EGY | PHA | 54 | INV | 95 | A | O | I | CFC | 100 | 41 |  |  | 2008-04-01 | 2008-11-01 | 2009-03-31 | 2009-09-01 |  |  | 600000 | 0 | 600000 | 8911 | 1.485% | 591089 | 0 | 150000 | 45000 | 0 | 668 | 44332 | 0 | The comments raised in the report of the senior evaluation officer on the implementation of the NPP in Egypt were considered carefully. Based on that an expedited plan of action for implementation of the third tranche was agreed upon between EEAA and UNIDO. The project should be completed by Sep 2009. | [13 empty] | 2008 | INV | 113 | 113 |  |  | Not yet confirmed | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | EGY | PHA | 55 | PRP | 96 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 195000 | 0 | 195000 | 9876 | 5.065% | 185124 | 12010 | 30000 | 14625 | 0 | 741 | 13884 | 901 | National experts for policy and regulatory issues as well as the solvent, foam and refrigeration sectors were recruited in October 2008 . The first results of the survey are expected in March 2009. The inception workshop is planned to take place in early February 2009. | Nominations for the national experts were received promptly. The NOU and EEAA are showing a high level of responsiveness with regard to the HCFC phase out. | [12 empty] | 2008 | NON-INV
ONG | UNIDO | Extension of the institutional strengthening projects (phase VII) | Individual | AFR | EGY | SEV | 56 | INS | 97 | N | T | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2011-03-31 | 2010-12-01 |  |  | 228323 | 0 | 228323 | 0 | 0% | 228323 | 0 | 20000 | 17124 | 0 | 0 | 17124 | 0 | The project will be initiated once the previous phase is fully implemented, expected date for new subcontract will be March 2009. | [13 empty] | 2008 | NON-INV
ONG | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation except in date use | Individual | AFR | EGY | FUM | 56 | INV | 98 | A | O | I | MBR | 184.2 | 0 |  |  | 2008-11-01 |  | 2013-11-30 | 2013-11-01 |  |  | 1934994 | 0 | 1934994 | 0 | 0% | 1934994 | 0 | 300000 | 145125 | 0 | 0 | 145125 | 0 | Completion of Phase 1 of this Project was completed in 2008 while the second phase was approved at the 56th ExCom Meeting. In 2009 additional equipment is going to be purchased for three horticulture companies and training will be provided in grafting. | [13 empty] | 2008 | INV
FIN | UNEP | Country programme preparation | Individual | LAC | ELS | SEV | 16 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-06-01 |  | 1997-03-01 | 1999-01-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 5200 | -650 | 4550 | 0 | 0 | Project financially completed. | $ 5,000 plus $ 650 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNDP | Project preparation in the refrigeration sectors | Individual | LAC | ELS | REF | 21 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 45000 | -3239 | 41761 | 41761 | 100% | 0 | 0 | 0 | 5850 | -421 | 5429 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Prado, S.A. de C.V. | Individual | LAC | ELS | REF | 22 | INV | 3 | A | O | I | CFC | 22.4 | 22.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-06-01 | 2001-12-01 | 306229 | 0 | 306229 | 306229 | 100% | 0 | 0 | 0 | 39810 | 0 | 39810 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNEP | Area of Policies for the Protection of the Ozone Layer (institutional strengthening) | Individual | LAC | ELS | SEV | 22 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 2000-05-01 |  | 2001-06-01 | 2001-12-01 | 66900 | 0 | 66900 | 66900 | 100% | 0 | 0 | 0 | 8697 | 0 | 8697 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
CLO | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | ELS | FOA | 24 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | ELS | REF | 25 | TAS | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2002-01-01 | 2000-08-01 |  | 2003-06-01 | 2005-10-01 | 10500 | -1035 | 9465 | 9465 | 100% | 0 | 0 | 0 | 1365 | -135 | 1230 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1998 | Non-Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | LAC | ELS | REF | 25 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 2000-02-02 |  | 2001-12-01 | 2003-07-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 | 0 | 0 | 5070 | 0 | 5070 | 0 | 0 | Project financially completed. |  |  |  |  | 2000-12-01 | [8 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | LAC | ELS | REF | 25 | TRA | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-03 |  | 2004-03-01 | 2005-02-01 | 38000 | -14300 | 23700 | 23700 | 100% | 0 | 0 | 0 | 4940 | -1859 | 3081 | 0 | 0 | Project financially completed. | $14,300 plus $ 1,859 returned ExCom 46 | [12 empty] | 1998 | Non Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | ELS | REF | 25 | TAS | 9 | A | O | I | CFC | 36.3 | 36.3 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-05-01 | 403925 | -26048 | 377877 | 377877 | 100% | 0 | 0 | 0 | 52510 | -3386 | 49124 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | ELS | SEV | 32 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-03-01 | 2004-05-01 | 44600 | 0 | 44600 | 44600 | 100% | 0 | 0 | 0 | 5798 | 0 | 5798 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | LAC | ELS | REF | 37 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-11-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 2275 | 0 | 2275 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | ELS | SEV | 38 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 | 2006-10-01 | 57980 | 0 | 57980 | 57980 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNDP | RMP update: technical assistance for the refrigeration sector | Individual | LAC | ELS | REF | 42 | TAS | 13 | N | O | I | CFC | 172.5 | 172.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 |  | 231700 | 0 | 231700 | 231699 | 100% | 1 | 0 | 0.8 | 20853 | 0 | 20852.91 | 0.09 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment
COM | UNDP | RMP update: technical assistance for certification and licensing of refrigeration technicians | Individual | LAC | ELS | REF | 42 | TRA | 14 | N | O | I | CFC | 57.6 | 57.6 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 |  | 77300 | 0 | 77300 | 77299 | 100% | 1 | 0 | 0.8 | 6957 | 0 | 6956.91 | 0.09 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment
COM | UNDP | RMP update: monitoring programme | Individual | LAC | ELS | REF | 42 | TAS | 15 | N | O | I | CFC | 30.5 | 30.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2008-04-01 |  | 41000 | 0 | 41000 | 40515 | 98.82% | 485 | 7 | 388 | 3690 | 0 | 3646.35 | 43.65 | 0.63 | Completed in 2008. Continuous monitoring took place of RMP update activities through the national consultant visiting technical workshops and providing technical assistance. | [13 empty] | 2004 | Investment
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | ELS | SEV | 44 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-06-01 |  | 60000 | 0 | 60000 | 39606 | 66.01% | 20394 | 0 | 20394 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | ELS | FUM | 45 | TAS | 18 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-09-01 | 2007-12-01 | 40000 | -2757 | 37243 | 37243 | 100% | 0 | 0 |  | 3600 | -248 | 3352 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | NON-INV
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | ELS | PHA | 48 | PRP | 19 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 |  | 30000 | 0 | 30000 | 25169 | 83.9% | 4831 | 4830 | 4831 | 2250 | 0 | 1887.675 | 362.325 | 362.25 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Extension of institutional strengthening project (year 1 of phase V) | Individual | LAC | ELS | SEV | 52 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-09-30 | 2009-09-30 |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | During this period, the following activities were carried out: 1) Information on ODS imports was successfully gathered and served as basis for a new legislation proposal. 2) The process for the acquisition of CFC free refrigeration systems was successfully concluded and equipment was delivered to 10 hospitals and upgraded in 3 shrimp boats from the National Chamber of Fisheries and Agriculture, 3) Annual report on 2007 figures was sent to Ozone Secretariat, 4)The staff from the Ministry of Environment and Natural Resources was trained by an international expert on customs and ODS imports. 5) IS phase VI was recently approved. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | ELS | PHA | 53 | INV | 21 | N | O | I | CFC | 16 | 13 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 | 2009-11-01 |  |  | 230000 | 0 | 230000 | 22587 | 9.82% | 207413 | 108218 | 82965.2 | 17250 | 0 | 1694.025 | 15555.975 | 8116.35 | 1 "drop in" seminar with 29 participants. 1 seminar on refrigerant blends with 150 participants. 1 train the trainers on retrofit with 29 participants. Tools and equipment that will be delivered in 2009 in the process of being procured. Second tranche to be submitted at 57th ExCom. | [13 empty] | 2007 | Investment | 46 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | ELS | PHA | 53 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2008-11-30 | 2009-06-01 |  |  | 20000 | 0 | 20000 | 13674.75 | 68.37% | 6325.25 | 0 | 6325.25 | 2600 | 0 | 1777.7175 | 822.2825 | 0 | One Train-the-trainers seminar was carried out, along with a Manufacturer’s seminar. 10 technical seminars are still under implementation, 2,000 posters, 2,000 brochures, and 2,000 technical cards are being printed along with , 100 tool sets. The License System has been re-designed, including corrective measures, 4 planning, stocktaking and training meetings have been completed and border campaigns re-designed. Regular formal monitoring exercises are being carried out on a quarterly basis and the results are being discussed and acted upon during the corresponding management meeting. 2008 Annual Implementation Report will be presented at the 57th ExCom Meeting. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ELS | PHA | 55 | PRP | 23 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | Local and international consultants have been identified. The inception workshop is expected to take place in early 2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Extension of institutional strengthening project (year 2 of phase V) | Individual | LAC | ELS | SEV | 56 | INS | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Project recently approved. Agreement for project implementation has been recently signed and first fund disbursement already processed. The country is currently producing A7 data report for 2008 and is updated with earlier reports. | [13 empty] | 2008
ONG | UNEP | Project preparation for a country programme/refrigerant management plan | Individual | AFR | EQG | SEV | 49 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-03-01 | 2007-07-31 | 2009-04-01 |  |  | 60000 | 0 | 60000 | 14878.38 | 24.8% | 45121.62 | 35000 | 45121.62 | 7800 | 0 | 1934.1894 | 5865.8106 | 4550 | Draft NPP was finalized by end of December 2008 awaiting submission to the 57th ExCom | [13 empty] | 2006 | Non Investment
ONG | UNEP | Start-up of institutional strengthening project | Individual | AFR | EQG | SEV | 49 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-12-01 | 2007-07-31 | 2009-03-31 |  |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ISP help support the establishment of the NOU and facilitated preparation of CP/NPP. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | EQG | PHA | 56 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Project newly approved | [13 empty] | 2008
CLO | UNDP | Project preparation of the investment components of the RMP | Individual | AFR | ERI | REF | 47 | PRP | 1 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  |  | 2007-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. | [13 empty] | 2005 | Investment
COM | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | ERI | SEV | 47 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2008-02-01 |  | 40000 | 0 | 40000 | 38000 | 95% | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | Project completed in February 2008 | [13 empty] | 2005 | Non Investment
FIN | UNEP | Country programme/RMP project preparation | RMP | AFR | ERI | SEV | 47 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 40000 | 0 | 40000 | 38000 | 95% | 2000 | 0 | 0 | 5200 | 0 | 4940 | 260 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 2005 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | TAS | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2010-03-31 | 2010-03-31 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 100000 | 13000 | 0 | 0 | 13000 | 0 | Impementation not yet started due to lack of ODS Regulations. CAP assisting country to approve ODS Regulations | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | INV | 5 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 |  | 2010-03-31 | 2010-03-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 50000 | 9000 | 0 | 0 | 9000 | 0 | As per the ExCom’s decision, no funding can be released until the confirmation of the report of the licensing system to the Ozone Secretariat had been received by the Fund Secretariat. Despite several follow-ups by UNEP and UNIDO the above confirmation has not yet been received. Thus, no activities could be implemented. | [13 empty] | 2008 | INV | 4.2 | 4.2 |  |  | Not yet confirmed | N/A | N/A
ONG | UNEP | Institutional strengthening (phase I) | Individual | AFR | ERI | SEV | 54 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2010-03-31 | 2010-03-31 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | MOU for implementation agreed with the country. First payment awaiting for the country to submit reports for the previous IS phase | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ERI | PHA | 55 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU signed with the country awaiting first payment. Country identified national experts for the survey, finalised HCFC survey questionnaire and TORs for the survey and drafting of HPMP | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | ETH | SEV | 16 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-09-25 | 1996-06-01 |  | 1996-12-01 | 1996-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
CLO | UNDP | Project preparation assistance | Individual | AFR | ETH | SEV | 17 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1997-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1997. | [13 empty] | 1995 | Investment
FIN | UNEP | Establishment of national ozone cell for the implementation of Montreal Protocol in Ethiopia | Individual | AFR | ETH | SEV | 20 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-01-01 | 1999-11-01 | 60500 | 0 | 60500 | 60500 | 100% | 0 | 0 | 0 | 7865 | 0 | 7865 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | [10 empty] | 1996 | Non Investment
TRF | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 23 | TRA | 4 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-01-01 | 1999-12-01 |  |  | 2000-03-01 | 93490 | -93490 | 0 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | Project transferred to UNEP at ExCom 30
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ETH | REF | 23 | PRP | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 1999-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation | [13 empty] | 1998
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ETH | REF | 26 | TAS | 6 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-10-01 | 2005-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. RMP update approved in dec 2004 | [13 empty] | 2000
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | ETH | SEV | 29 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 40300 | 0 | 40300 | 40300 | 100% | 0 | 0 | 0 | 5239 | 0 | 5239 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | ETH | FUM | 30 | TAS | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -7326 | 17674 | 17674 | 100% | 0 | 0 | 0 | 3250 | -952.38 | 2297.62 | 0 | 0 | Project financially completed. | $ 7,326 plus $ 952 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 30 | TRA | 9 | A | O | I | CFC | 11.1 | 11.1 | 0 | 0 | 2000-03-01 | 2001-11-01 | 2003-06-01 |  | 2003-06-01 | 2007-07-01 | 82735 | -24380 | 58355 | 58355 | 100% | 0 | 0 | 0 | 10755 | -3169 | 7586.15 | -0.15 | 0 | Project financially completed. | $ 24,380 plus $ 3,169 PSC returned ExCom 46 | [12 empty] | 2000 | Non Investment
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ETH | REF | 37 | PRP | 10 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom | [13 empty] | 1998
COM | UNEP | Extension of institutional strengthening project for a one year period (phase 3) | Individual | AFR | ETH | SEV | 39 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2006-12-05 |  | 26216 | 0 | 26216 | 18246 | 69.6% | 7970 | 0 | 7970 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2003 | Non Investment
COM | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | ETH | SEV | 41 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 0 | 2005-12-01 |  | 2008-12-01 |  | 26216 | 0 | 26216 | 12978 | 49.5% | 13238 | 0 | 13238 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. The NOU submitted all pending IS reports covering the period 2004-2008. The NOU conducted Customs training workshop for twenty Custom Officers to equip them to implement the Customs tariff Amendment No. 3, which encourages the import of ODS alternatives by lowering the tax in favour of the alternatives.The NOU distributed practical training equipment for good practices of Refrigerator Maintenance to training colleges. The NOU conducted awareness activities and distributed information about the accelerated phase-out of HCFC to relevant government and non-governmental agencies. Explanatory documents about the Montreal Protocol and its obligations prepared in Amharig language (local language) were distributed to relevant agencies in order to lobby for support for the ratification of the amendments to the Montreal Protocol. The NOU celebrated the 2008 Ozone day and organized seminars for members of the parliament, representatives of regional environmental agencies and schools. | [13 empty] | 2003 | Non Investment
ONG | France | Implementation of the RMP update | RMP Update | AFR | ETH | REF | 44 | TAS | 14 | A | O | I | CFC | 12.3 |  | 0 |  | 2004-12-01 | 2005-11-01 | 2007-12-01 | 2009-12-01 |  |  | 91300 | 0 | 91300 | 53200 | 58.27% | 38100 |  | 38100 | 11869 | 0 | 6916 | 4953 |  | The French contribution is implemented by GTZ-Proklima. The project is being implemented slowly mainly because of the delay in approval of the ODS regulations which delays the customs officers training and delaying compeltion of the project.
CLO | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | AFR | ETH | SOL | 45 | TAS | 15 | A | O | I | CTC TCA | 5.4 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  |  | 2007-12-01 | 40000 | -35474 | 4526 | 4526 | 100% | 0 | 0 |  | 3600 | -3193 | 407 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. CLO. | [13 empty] | 2005 | INV
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ETH | SEV | 50 | INS | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2008-11-01 | 2010-03-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | The MOU for this phase was sent to the NOU for signing in 2008 | [13 empty] | 2006 | Non Investment
ONG | France | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ETH | PHA | 51 | PRP | 17 | A | O | I |  | 0 |  | 0 |  | 2007-03-01 | 2008-12-01 | 2008-03-01 | 2009-07-01 |  |  | 30000 | 0 | 30000 | 17600 | 58.67% | 12400 |  | 12400 | 3900 | 0 | 2288 | 1612 |  | The French contribution is implemented by GTZ-Proklima. Ethiopia still lacks ODS regualtions a prerequisite for the TPMP project. The survey under the project is near completion but it is unclear whether Ethiopia will have regulations in time for a TPMP approval.
ONG | UNIDO | Project preparation in the fumigant sector (flowers) | Individual | AFR | ETH | FUM | 54 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2010-12-01 |  |  | 35000 | 0 | 35000 | 60 | 0.1714% | 34940 | 0 | 1 | 2625 | 0 | 5 | 2620 | 0 | Approved on the understanding that funding would not be disbursed until the Government had reported its Article 7 data for 2006 and had ratified the London Amendment, pursuant to decision 51/19; and that no further funding would be considered until such time as an official commitment, in writing, to ratify the Copenhagen Amendment to the Montreal Protocol had been received by the Secretariat from the Government. | [13 empty] | 2008 | NON-INV
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ETH | PHA | 56 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU for implementation agreed with the country. NOU identified experts to undertake the HCFC survey and drafting of HPMP and the NOU drafted the HCFC survey questinnaire and the HPMP template | [13 empty] | 2008
FIN | Germany | Promoting compliance with the Montreal Protocol in countries with economies in transition (Croatia and Romania) | Individual | EUR | EUR | SEV | 28 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2001-08-01 | 2003-10-01 | 67800 | -6900 | 60900 | 60900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 2002
FIN | Hungary | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 2 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 41145 | 0 | 41145 | 41145 | 100% | 0 |  |  | 5349 | 0 | 5349 | 0
FIN | Slovak Republic | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 3 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 14622 | 0 | 14622 | 14622 | 100% | 0 |  |  | 1901 | 0 | 1901 | 0
FIN | Czech Republic | Regional network for 10 article 5 countries in Eastern Europe and Central Asia (jointly implemented with Hungary, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 4 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 58487 | 0 | 58487 | 58487 | 100% | 0 |  |  | 7603 | 0 | 7603 | 0
FIN | UNEP | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and the Slovak Republic) | Individual | EUR | EUR | SEV | 39 | TAS | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 | 2006-02-01 | 53666 | 0 | 53666 | 53666 | 100% | 0 | 0 | 0 | 6976.58 | 0 | 6976.58 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
ONG | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers (Croatia, Macedonia, Romania, and Serbia and Montenegro) | Individual | EUR | EUR | REF | 47 | DEM | 6 | A | O | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 | 2009-04-01 |  |  | 1069074 | 0 | 1069074 | 571762 | 53.48% | 497312 | 311129 | 300000 | 80181 | 0 | 42882 | 37299 | 23335 | All 8 chillers in Romania, Macedonia, Croatia and Montenegro have been delivered and installed. Two chillers in Serbia have been delivered and installed. UNIDO is waiting for the Secretariat's approval to disburse funding for the remaining two chillers in Serbia. Project will be completed in April 2009. | [13 empty] | 2005 | INV
FIN | UNEP | Country programme preparation | Individual | ASP | FIJ | SEV | 4 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -2165 | 22835 | 22835 | 100% | 0 | 0 | 0 | 3250 | -281.45 | 2968.55 | 0 | 0 | Project financially completed. | $ 2,165 plus $ 281 PSC returned ExCom 41 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | FIJ | SEV | 12 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1997-03-01 |  | 2000-07-01 | 2001-12-01 | 65890 | 0 | 65890 | 65890 | 100% | 0 | 0 | 0 | 8565.7 | 0 | 8565.7 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | FIJ | REF | 21 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1999-11-01 | 2002-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | 1999-05-01 | [9 empty] | 1997 | Non Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | ASP | FIJ | REF | 29 | TAS | 4 | A | O | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2007-02-01 | 96755 | -500 | 96255 | 96255 | 100% | 0 | 0 | 0 | 12578 | -65 | 12513 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 1999 | Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | FIJ | SEV | 29 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2001-12-01 |  | 2002-05-01 | 2007-03-01 | 43930 | 0 | 43930 | 43930 | 100% | 0 | 0 | 0 | 5711 | 0 | 5710.9 | 0.1 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Train the trainer programme for refrigeration service technicians | Individual | ASP | FIJ | REF | 29 | TRA | 6 | A | O | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-02 |  | 2003-01-01 | 2004-10-01 | 70500 | -24500 | 46000 | 46000 | 100% | 0 | 0 | 0 | 9165 | -3185 | 5980 | 0 | 0 | Project financially completed. | $ 24,500 plus $ 3,185 returned to ExCom 46 |  |  |  |  | 2002-12-02 | [7 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | FIJ | REF | 29 | TRA | 7 | A | O | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-02 |  | 2004-07-01 | 2008-12-01 | 42500 | 0 | 42500 | 40689 | 95.74% | 1811 | 0 | 0 | 5525 | 0 | 5289.57 | 235.43 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [5 empty] | 2002-12-02 | [7 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | ASP | FIJ | SEV | 37 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2004-08-01 | 2008-12-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | FIJ | SEV | 44 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Development of a total ODS phase out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-11-01 | 2006-03-01 | 15000 | -83 | 14917 | 14917 | 100% | 0 | 0 | 0 | 1950 | -11 | 1939.21 | -0.21 | 0 | Project financially completed. | $ 83 plus $11 returned to ExCom 51 | [12 empty] | 2005 | Non Investment
COM | UNDP | Project preparation for complete ODS phase-out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2006-07-01 |  | 16870 | 0 | 16870 | 10000 | 59.28% | 6870 | 0 | 6870 | 1265 | 0 | 749.8518 | 515.1482 | 0 | Completed in 2006. | [13 empty] | 2005 | Investment
ONG | UNEP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2008-12-01 | 2009-12-01 |  |  | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 | 0 | 8450 | 0 | 8450 | 0 | 0 | Fiji has finalised code of practices for fumigation including phosphine have been finalised after review. Solar tent has been installed and has faced certain operational difficulties due to excessive heat generation. Design modifications for addressing excessive heat generation has been undertaken during the year. Final project report on MB phaseout activities is under preparation. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase IV- year 2) | Individual | ASP | FIJ | SEV | 47 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNDP | Implementation of the TPMP (investment component) | One-off-Phaseout | ASP | FIJ | PHA | 47 | TAS | 15 | N | O | I | CFC | 0.5 | 0.5 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Completed in 2008. Seven customs trainings were conducted in 2008 with participation of 44 customs officers. To date, more than 1,000 participants have been trained in this programme. Out of this, 577 have been issued License to handle controlled substances. Twelve new sets of refrigeration recovery equipment were purchased in 2008, of which 9 sets were distributed around Fiji and 1 to be used for demonstration purposes in GPR workshops. Two sets will be distributed early 2009. Legal Consultants submitted final ODS Legislation Review in October. The Final Consultation meeting with stakeholders was held from 18 - 20 November 2008 and final payments were issued to Munroy Leys for their submission of the final draft. | [12 empty] | 2009-12-01 | 2005 | Investment
ONG | UNEP | Implementation of the TPMP (non-investment component) | Individual | ASP | FIJ | PHA | 47 | TAS | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2009-12-01 | 2009-12-01 |  |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | 2008 workplan prepared and submitted to UNEP. The NOU plans to complete policy review of ODS Act and ODS Regulation. Amendment of the ODS regulations 2000 to include licensing of exports of ODS and equipment containing ODS will be introduced by end of 2008. TPMP Implementation: 108 technicians trained in 2008 under the training programme for customs officer, 19 officers in 2008 were trained; For 2007 to 2008: 118 new registered for license to store controlled substances, 390 renewals for license to handles controlled substances, 45 new registered applicants for permit to store controlled substances, 224 renewals for permit to store controlled substances and 39 number of imports approved; The country continues to strengthen their awareness activities by organizing Ozone events such as International Ozone Day, seminars to public and schools, etc. They distributed ozone related awareness materials such as information booklets, posters, calendars, t-shirts, pens, notebook, etc. | [13 empty] | 2005 | Non Investment
ONG | UNDP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 17 | N | O | I | MeBr | 2.1 | 0 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2008-12-01 | 2010-12-01 |  |  | 50000 | 0 | 50000 | 22945 | 45.89% | 27055 | 0 | 5411 | 4500 | 0 | 2065.05 | 2434.95 | 0 | The control system was returned replaced in the kiln, however there continues to be design issues that has resulted in further melt downs of the solar tent. The supplier was working on providing a solution to this. It is expected that another trial will be done in 2009. | [13 empty] | 2005 | Non-Investment
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | FIJ | SEV | 50 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-11-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008 & financially completed. TPMP Implementation: 108 technicians trained in 2008; under the training programme for customs officer, 19 officers in 2008 were trained; For 2007 to 2008: 118 new registered for license to store controlled substances, 390 renewals for license to handles controlled substances, 45 new registered applicants for permit to store controlled substances, 224 renewals for permit to store controlled substances and 39 number of imports approved; The country continues to strengthen their awareness activities by organizing Ozone events such as International Ozone Day, seminars to public and schools, etc. They distributed ozone related awareness materials such as information booklets, posters, calendars, t-shirts, pens, notebook, etc. | [13 empty] | 2006 | Non Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | FIJ | PHA | 55 | PRP | 19 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | National experts to be recruited in Q1-2009. Project inception workshop planned by mid 2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | FIJ | SEV | 56 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-11-30 | 2010-11-30 |  |  | 60000 | 0 | 60000 | 7841 | 13.07% | 52159 | 0 | 52159 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | FSM | REF | 36 | TAS | 1 | A | O | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 | 2009-06-01 |  |  | 10000 | 0 | 10000 | 2983 | 29.83% | 7017 | 0 | 7017 | 1300 | 0 |  | 1300 | 1300 | Regulations passed by Executive in September 2008, and waiting for endorsment by the legislature. |  | 2002
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | FSM | REF | 36 | TAS | 2 | A | O | I |  | 0.7 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 |  | 2008-06-01 |  | 26000 | 0 | 26000 | 21083 | 81.09% | 4917 | 0 | 4917 | 3380 | 0 |  | 3380 | 3380 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | FSM | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 |  | 34000 | 0 | 34000 | 31238.87 | 91.88% | 2761.13 | 0 | 2761.13 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2002 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | FSM | SEV | 49 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 |  | 2007-03-31 |  | 2008-07-01 |  | 11333 | 0 | 11333 | 0 | 0% | 11333 | 0 | 11333 | 0 | 0 | 0 | 0 | 0 | Project completed in July 2008. | [13 empty] | 2006 | Non Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GAB | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-29 | 1995-12-01 |  | 1997-05-01 | 1997-06-01 | 10000 | 33000 | 43000 | 43000 | 100% | 0 | 0 | 0 | 1300 | 4290 | 5590 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | GAB | REF | 21 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-11-01 | 2002-03-01 | 20000 | -5395 | 14605 | 14605 | 100% | 0 | 0 | 0 | 2600 | -701 | 1899 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNEP | Creation of a National Ozone Technical Group | Individual | AFR | GAB | SEV | 22 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2001-12-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 | 0 | 5928 | 0 | 5928 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme in the refrigeration sector | Individual | AFR | GAB | REF | 26 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-09-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Customs training | Individual | AFR | GAB | REF | 26 | TRA | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2003-12-01 | 2005-01-01 | 31000 | -10000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 4030 | -1300 | 2730 | 0 | 0 | Project financially completed. | $ 10,000 plus $ 1,300 returned ExCom 46 | [12 empty] | 1998 | Non Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 26 | TAS | 6 | A | O | I | CFC | 12.2 | 12.2 | 0 | 0 | 1998-11-01 | 2001-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 232470 | -36306 | 196164 | 196164 | 100% | 0 | 0 | 0 | 30221 | -4720 | 25501 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GAB | REF | 26 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2002-01-01 | 2000-12-01 |  | 2003-07-01 | 2003-08-01 | 12100 | -1600 | 10500 | 10500 | 100% | 0 | 0 | 0 | 1573 | -208 | 1365 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | GAB | SEV | 32 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-03 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | GAB | REF | 37 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | AFR | GAB | SEV | 37 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2005-02-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 41 | TAS | 11 | N | O | I | CFC | 3.3 | 3.3 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2007-07-01 |  | 60277 | 0 | 60277 | 60277 | 100% | 0 | 0 | 0 | 5425 | 0 | 5425 | 0 | 0 | Completed in 2007. | [13 empty] | 2003 | Investment
FIN | UNEP | Implementation of the RMP: customs training programme ( phase II) | Individual | AFR | GAB | REF | 41 | TRA | 12 | A | O | I | CFC | 2.7 | 2.7 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 50000 | 0 | 50000 | 48014.53 | 96.03% | 1985.47 | 0 | 0 | 6500 | 0 | 6241.8889 | 258.1111 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 2003 | Non Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | GAB | REF | 41 | TRA | 13 | A | O | I | CFC | 1.9 | 1.9 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | GAB | REF | 41 | TAS | 14 | N | O | I | CFC | 0.8 | 0.8 | 0 | 0 | 2003-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 |  | 15000 | 0 | 15000 | 14228 | 94.85% | 772 | 0 | 617.6 | 1350 | 0 | 1280.52 | 69.48 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | GAB | SEV | 44 | INS | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 |  | 60000 | 0 | 60000 | 48015.53 | 80.03% | 11984.47 | 11984 | 11984.47 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | GAB | PHA | 48 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-07-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2006 | Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAB | PHA | 48 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 0 | 2007-04-01 |  | 2008-05-01 |  | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project completed in May 2008. | [13 empty] | 2006 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAB | SEV | 50 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | TAS | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-31 | 2009-07-31 |  |  | 65000 | 0 | 65000 | 41568.23 | 63.95% | 23431.77 | 16000 | 23431.77 | 8450 | 0 | 5403.8699 | 3046.1301 | 2080 | Purchase of training equipment done in March 2008 | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | INV | 21 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 | 2009-07-01 |  |  | 50000 | 0 | 50000 | 20593 | 41.19% | 29407 | 0 | 11762.8 | 4500 | 0 | 1853.37 | 2646.63 | 0 | Consultant mission was carried out end 2008. Bidding process for purchase of equipment has been completed and equipment, tools and refrigerant gas have arrived in country. Main retrofit centre in Libreville has been identified and preparation for retrofit demonstration project is ongoing. Two other centres should be set up early 2009, one in Port Gentil, one in Franceville. Second tranche to be approved at 57th ExCom. | [13 empty] | 2007 | Investment | 1.5 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GAB | PHA | 55 | PRP | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for Signature | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GAB | SEV | 56 | INS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-31 | 2010-12-31 |  |  | 60000 | 0 | 60000 | 454.05 | 0.7567% | 59545.95 | 0 | 59545.95 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | GAM | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-06-01 |  | 1995-10-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | GAM | SEV | 19 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-09-01 | 2000-09-01 | 42200 | 0 | 42200 | 42200 | 100% | 0 | 0 | 0 | 5486 | 0 | 5486 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Training of customs officers | Individual | AFR | GAM | SEV | 19 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  | 2002-10-01 | 2003-10-01 | 9500 | 0 | 9500 | 9500 | 100% | 0 | 0 | 0 | 1235 | 0 | 1235 | 0 | 0 | Project financially completed. |  |  | 1997-12-01 | [10 empty] | 1996 | Non Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | GAM | FOA | 21 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-05-01 | 2002-03-01 | 20000 | -6548 | 13452 | 13452 | 100% | 0 | 0 | 0 | 2600 | -851 | 1749 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNIDO | Refrigeration recovery and recycling scheme | RMP | AFR | GAM | REF | 22 | TAS | 5 | A | O | I | CFC | 7.7 | 7.7 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 68000 | -243 | 67757 | 67757 | 100% | 0 | 0 |  | 8840 | -45 | 8795 | 0 | 0 | FIN
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Karan Foam Manufacturing Ltd. | Individual | AFR | GAM | FOA | 22 | INV | 6 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 63500 | -2619 | 60881 | 60881 | 100% | 0 | 0 | 0 | 8255 | -340 | 7915 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | AFR | GAM | REF | 23 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Refrigerant management plan: Policy development and related information dissemination | Individual | AFR | GAM | REF | 29 | TAS | 8 | A | O | I | CFC | 3.2 | 3.2 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2000-12-02 |  | 2002-10-01 | 2003-10-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Training programme for technicians in good refrigeration practices | Individual | AFR | GAM | REF | 29 | TRA | 9 | A | O | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-06-02 |  | 2002-10-01 | 2003-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | GAM | SEV | 30 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | Germany | Project preparation for additional activities for Gambia RMP | RMP | AFR | GAM | REF | 32 | PRP | 11 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2004-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project completed and resultant RMP update is being implemented. | [13 empty] | 1998
COM | Germany | Implementation of the RMP update: phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | GAM | REF | 37 | TAS | 12 | A | O | I |  | 11.2 | 11.2 | 0 |  | 2002-07-01 | 2003-03-01 | 2005-01-01 |  | 2007-09-01 |  | 76700 | 0 | 76700 | 76670 | 99.96% | 30 | 0 | 0 | 9971 | 0 | 9967.1 | 3.9 | 0 | Project completed and PCR submitted. | [13 empty] | 1998
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | GAM | SEV | 41 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2006-03-01 | 2007-03-01 | 36573 | 0 | 36573 | 36573 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | GAM | SEV | 48 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 |  | 60000 | 0 | 60000 | 59971 | 99.95% | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | Project completed in April 2008 | [13 empty] | 2006 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAM | PHA | 49 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-31 |  | 2007-08-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | GAM | PHA | 49 | PRP | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2007-12-01 |  | 12000 | 0 | 12000 | 11760 | 98% | 240 | 0 | 240 | 900 | 0 | 882 | 18 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | GAM | PHA | 53 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 93000 | 0 | 93000 | 89999.68 | 96.77% | 3000.32 | 3000 | 3000.32 | 12090 | 0 | 11699.9584 | 390.0416 | 390 | First tranche successfully completed. Country conducted trainings for customs officers, refrigeration technicians, reviewed ODS Regulations, curricula for customs training school and technicians scholl. second tranche approved during 57th ExCom | [13 empty] | 2007 | Non Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | GAM | PHA | 53 | INV | 18 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2008-12-01 |  | 99500 | 0 | 99500 | 74353 | 74.73% | 25147 | 0 | 20117.6 | 8955 | 0 | 6691.77 | 2263.23 | 0 | Completed in 2008. National expert recruited. International expert recruited with a mission in August 2008. In August, 20 technicians were trained in refrigerant safe handling and retrofitting techniques. Equipment bidding finalized. Equipment to arrive in Q1-2009. Four companies accepted to convert or replace their equipment. More applications to be processed after 2nd tranche approval expected at 57th ExCom. Final invoices will be settled in 2009. | [13 empty] | 2007 | Investment | 3.6 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAM | SEV | 54 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-31 | 2010-03-31 |  |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 40500 | 40500 | 0 | 0 | 0 | 0 | 0 | The country signed the SSFA in May 2008 and the first disbursement was made in August 2008. The NOU conducted various sub-projects such as training of 145 refrigeration technicians and 50 Custom Enforcement officers. The NOU also implemented an incentive scheme for end users. The country celebrated the national ozone day with series of events. The NOU conducted awareness programmes and distributed ozone brochures, organized radio and TV programmes for the general public and essay competitions for schools. The Association of Refrigeration Technicians as well as other stakeholders have significantly contributed to the reduction of the consumption of Ozone Depleting substances in the Gambia. | [13 empty] | 2008
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GAM | PHA | 55 | PRP | 20 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Prepared prodoc & TORs and held discussions on them. Prodoc is expected to be signed in Q1-2009. activities to be launched in Q2-2009. | [13 empty] | 2008 | Investment
COM | UNEP | Establishment of ozone unit | Individual | AFR | GBS | SEV | 39 | INS | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2004-04-01 |  | 2004-07-01 |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2003 | Non Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | GBS | REF | 39 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2003 | Investment
COM | UNEP | Formulation of the country programme/RMP | RMP | AFR | GBS | SEV | 39 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-07-01 |  | 60000 | 0 | 60000 | 27173 | 45.29% | 32827 | 0 | 32827 | 7800 | 0 | 3532.49 | 4267.51 | 0 | Project completed | [13 empty] | 2003 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening project) | Individual | AFR | GBS | SEV | 43 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 0 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: monitoring of the activities in the RMP | Individual | AFR | GBS | REF | 43 | TAS | 5 | A | O | I | CFC | 1 | 0 | 0 | 0 | 2004-07-01 |  | 2007-07-01 |  | 2008-12-01 |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 20000 | 2600 | 0 | 0 | 2600 | 2600 | Project completed in December 2008 | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: training for customs officials, police, coast guards, border guards and commercial inspectors | Individual | AFR | GBS | REF | 43 | TRA | 6 | A | O | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2006-07-01 |  | 2007-12-01 |  | 70000 | 0 | 70000 | 54038 | 77.2% | 15962 | 14006 | 15962 | 9100 | 0 | 7024.94 | 2075.06 | 1820.78 | Project completed | [13 empty] | 2004 | Non Investment
ONG | UNDP | Implementation of the RMP: technical assistance project for MAC and refrigeration service and end-user sub-sectors | RMP-Component | AFR | GBS | REF | 43 | TAS | 7 | N | O | I | CFC | 14.3 | 2 | 0 | 0 | 2004-07-01 |  | 2006-07-01 | 2010-01-01 |  |  | 282900 | 0 | 282900 | 0 | 0% | 282900 | 0 | 56580 | 21218 | 0 | 0 | 21218 | 0 | International consultant mission took place early Sept 08. Bids for purchase of equipment were reviewed and supplier selected. Equipment expected to arrive in the country by mid-2009. Project document has been revised to reflect the current realities of the country (strengthening of a Reference Centre, equipment, end user incentives). The signature of this document has been delayed due to a change of Minister at the end of 2008 but this should take place early 2009 and remaining activities under the project should be carried out during 2009. | [13 empty] | 2004 | Investment
COM | UNEP | Implementation of the RMP: training for refrigeration technicians | Individual | AFR | GBS | REF | 43 | TRA | 8 | A | O | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 |  | 70000 | 0 | 70000 | 44014.4 | 62.88% | 25985.6 | 25360 | 25985.6 | 9100 | 0 | 5721.872 | 3378.128 | 3296.8 | Project completed | [13 empty] | 2004 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | GBS | SEV | 50 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 | 2009-12-01 |  |  | 60000 | 0 | 60000 | 30080 | 50.13% | 29920 | 0 | 29920 | 0 | 0 | 0 | 0 | 0 | The NOU coordinated the implementation of the delayed inestment (end-users) activities under the RMP. NOU also coodinated preparation of TPMP with UNEP and UNDP. Consultations were held with major stakeholders to promote the enforcement of UEMOA sub-region | [13 empty] | 2006 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GBS | PHA | 50 | PRP | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 |  | 30000 | 0 | 30000 | 30000.4 | 100% | -0.4 | 0 | -0.4 | 3900 | 0 | 3900.052 | -0.052 | 0 | Project completed in December 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GBS | PHA | 56 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-03-31 | 2010-03-31 |  |  | 62500 | 0 | 62500 | 0 | 0% | 62500 | 0 | 62500 | 8125 | 0 | 0 | 8125 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | EUR | GEO | SEV | 23 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1997-11-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training in monitoring and controlling of ODS | Individual | EUR | GEO | REF | 23 | TRA | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-01-01 | 1998-02-01 |  | 2005-06-01 | 2006-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | GEO | SEV | 23 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 2000-12-01 |  | 2001-05-01 | 2001-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | EUR | GEO | REF | 23 | TAS | 4 | A | O | I | CFC | 3.7 | 3.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 106750 | -2348 | 104402 | 104402 | 100% | 0 | 0 | 0 | 13878 | -305 | 13573 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training of trainers in the refrigeration servicing sector | Individual | EUR | GEO | REF | 23 | TRA | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-11-01 | 1998-11-02 |  | 2001-11-01 | 2006-12-01 | 50000 | -9800 | 40200 | 40200 | 100% | 0 | 0 | 0 | 6500 | -1274 | 5226 | 0 | 0 | Project financially completed. | $ 9,800 plus $ 1,274 PSC returned to ExCom 46 | [12 empty] | 1997 | Non Investment
FIN | Canada | Promoting compliance with the Montreal Protocol in countries with economies in transition (CEITs) | Individual | EUR | GEO | SEV | 27 | TAS | 6 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-03-01 |  | 2001-10-01 | 2002-06-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | GEO | FUM | 30 | TAS | 7 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-01-01 | 2004-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | GEO | SEV | 32 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-08-01 | 2003-01-01 |  | 2003-02-01 | 2003-12-01 | 46700 | 0 | 46700 | 46700 | 100% | 0 | 0 | 0 | 6071 | 0 | 6071 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | EUR | GEO | FUM | 33 | PRP | 9 | A | O | I | MBR | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-05-01 | 2003-05-01 | 30000 | -1001 | 28999 | 28999 | 100% | 0 | 0 |  | 3900 | -136 | 3764 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Implementation of the RMP: incentive programme for the end-users in the commercial/industrial refrigeration and refrigerated transport sub-sectors | RMP-Component | EUR | GEO | REF | 35 | TAS | 10 | N | O | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2005-01-01 |  | 2005-01-01 | 2007-06-01 | 101000 | -553 | 100447 | 100447 | 100% | 0 | 0 | 0 | 13130 | -72 | 13058 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | EUR | GEO | REF | 35 | TAS | 11 | N | O | I | No_ODP | 2.3 | 2.3 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2007-12-01 |  | 2005-12-01 | 2007-06-01 | 16350 | 0 | 16350 | 16350 | 100% | 0 | 0 | 0 | 2126 | 0 | 2126 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Non-Investment
FIN | UNEP | Implementation of the RMP: training programme in the refrigeration sector (phase III) | Individual | EUR | GEO | REF | 35 | TRA | 12 | A | O | I | CFC | 2.8 | 2.8 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2003-01-01 |  | 2005-11-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
COM | UNIDO | Technical assistance for the phase-out of methyl bromide for soil fumigation | Individual | EUR | GEO | FUM | 37 | TAS | 13 | A | O | I | MBR | 6 | 6 |  |  | 2002-07-01 | 2003-02-01 | 2006-08-01 |  | 2006-12-01 |  | 220000 | 0 | 220000 | 219043 | 99.56% | 957 | 530 | 500 | 28600 | 0 | 28476 | 124 | 69 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2002 | NON-INV
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | EUR | GEO | SEV | 39 | INS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2004-12-01 | 2008-12-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNIDO | Preparation of a national halon bank | Individual | EUR | GEO | HAL | 44 | PRP | 16 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-09-01 | 15000 | -1438 | 13562 | 13562 | 100% | 0 | 0 |  | 1125 | -108 | 1017 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2004
FIN | UNIDO | Preparation of structure in fumigation of commodities in mill factories and grain storage | Individual | EUR | GEO | FUM | 44 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 30000 | -62 | 29938 | 29938 | 100% | 0 | 0 |  | 2250 | -5 | 2245 | 0 | 0 | FIN | [13 empty] | 2004
COM | UNEP | Extension of the institutional strengthening project: phase IV | Individual | EUR | GEO | SEV | 45 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-04-01 |  | 60667 | 0 | 60667 | 52442.07 | 86.44% | 8224.93 | 133.34 | 8224.93 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2005 | Non Investment
FIN | Sweden | Assistance to prepare a terminal phase-out management plan | Individual | EUR | GEO | PHA | 47 | PRP | 19 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-01-30 | 2006-12-01 |  | 2006-12-06 | 2006-12-06 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | In December 2005 at the 47th Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a Terminal phase-out management plan in Georgia. The final TPMP was submitted to the 50th ExCom meeting and approved. The TPMP is implemented by UNDP as sole implementing agency. |  | 2005 | [11 empty] | 2005
ONG | UNIDO | Technical assistance for the elimination of methyl bromide in grain and storage facilities | Individual | EUR | GEO | FUM | 47 | INV | 20 | A | O | I | MBR | 7.2 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 | 2009-12-01 |  |  | 225500 | 0 | 225500 | 87782 | 38.93% | 137718 | 29279 | 40000 | 20295 | 0 | 7900 | 12395 | 2635 | A second training session was organized and equipment installation was completed in 2008. Training activities are ongoing and the project is expected to be complete in December 2009. | [13 empty] | 2005 | INV
FIN | UNIDO | Halon banking management programme | Individual | EUR | GEO | HAL | 47 | TAS | 21 | A | O | I | HAL | 42.5 | 42.5 |  |  | 2005-11-01 | 2006-08-01 | 2008-12-01 |  | 2008-01-01 | 2008-09-01 | 64930 | -603 | 64327 | 64327 | 100% | 0 | 0 |  | 5844 | -55 | 5789 | 0 | 0 | Project completed in Jan 2008. Financial completion in Sep 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2005 | INV
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | EUR | GEO | PHA | 50 | INV | 22 | N | O | I | CFC | 4.8 | 4.8 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2009-11-01 |  | 2008-12-01 |  | 216180 | 0 | 216180 | 195616 | 90.49% | 20564 | 0 | 16451.2 | 16214 | 0 | 14671.6524 | 1542.3476 | 0 | Completed in 2008. Code of Practice developed, discussed with stakeholders, and approved July 2008. Three vocational schools supported by training materials, manuals and training software developed in Georgian language. Specialized trainings arranged for vocational school instructors. In class training provided. Training equipment purchased and transferred to schools. Service equipment purchased and distributed to service companies backed up with two training sessions. Reclaim equipment and GC purchased with training delivered by supplier in October 2008. Handbook on technologies developed in Georgian language. | [13 empty] | 2006 | Investment | 8.2 | 8.2 |  |  | Yes | Yes | yes
TRF | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 51 | INS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-03-01 |  | 2009-03-01 |  |  | 2007-12-01 | 60667 | -60667 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project transferred | [13 empty] | 2007 | Non Investment
ONG | UNDP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 52 | INS | 24 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-03-01 | 2009-04-01 |  |  | 60667 | 0 | 60667 | 36321 | 59.87% | 24346 | 0 | 9738.4 | 4550 | 0 | 2724.06 | 1825.94 | 0 | NOU coordinates the work of TPMP, Halons and MBr, and HPMP programmes, and workshops. Customs awareness training arranged. National experts contracted to assist with ODS data collection and verification for 2006/07. Reporting to MFLS and Ozone Secretariat carried out. Awareness raising supported through leaflets, meetings in schools, vocational schools and universities, TV casts, drawing contests and technical dictionary for technicians. Additional training sessions held with respect to safe refrigerant handling, leak detection and labeling. Web-page of NOU developed. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | GEO | PHA | 53 | INV | 25 | N | O | I | CFC | 3.4 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-01-01 |  |  | 108820 | 0 | 108820 | 0 | 0% | 108820 | 0 | 21764 | 8162 | 0 | 0 | 8162 | 0 | Project ongoing. Demonstration component prepared for launch in Q1-2009. Three companies selected to participate in the programme. Activities to start in Q1-2009. MDI element to start in Q1-Q2-2009. | [13 empty] | 2007 | Investment | 3.4 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | GEO | PHA | 55 | PRP | 26 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Prepared prodoc & TORs and held discussions on them. Prodoc's signature expected in Q1-2009. Activities to start in Q2-2009. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GHA | SEV | 4 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
TRF | UNDP | Refrigeration training programme for servicing technicians | RMP-Component | AFR | GHA | REF | 04 | TRA | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-06-01 |  |  | 1993-06-01 | 99000 | -93800 | 5200 | 5200 | 100% | 0 | 0 | 0 | 12870 | -12194 | 676 | 0 | 0 | Transferred in 1993. Financially completed in 1993. | [13 empty] | 1991 | Non-Investment
FIN | UNDP | Technical assistance for technology transfer for phase-out of CFC-11 in flexible foam | Individual | AFR | GHA | FOA | 08 | TAS | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1994-10-01 |  | 1995-06-01 | 1997-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Improved servicing and maintenance within the refrigeration sector | RMP-Component | AFR | GHA | REF | 08 | TAS | 4 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-04-01 | 1998-12-01 | 328000 | 0 | 328000 | 328000 | 100% | 0 | 0 | 0 | 42640 | 0 | 42640 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [13 empty] | 1992 | Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | GHA | SEV | 08 | INS | 5 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 160000 | 23200 | 183200 | 183200 | 100% | 0 | 0 | 0 | 20800 | 3016 | 23816 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1992 | Non-Investment
FIN | UNEP | Implementation of train the trainer programme and national demonstration programme | Individual | AFR | GHA | REF | 10 | TRA | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 1995-12-01 | 1999-04-01 | 99000 | 0 | 99000 | 99000 | 100% | 0 | 0 | 0 | 12870 | 0 | 12870 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNDP | Umbrella project for continuation of CFC free-technology in the manufacture of flexible polyurethane foam at Ashanti, Latex Foam, Nsawam and Prestige Foam | Individual | AFR | GHA | FOA | 12 | INV | 7 | A | O | I | CFC | 316 | 316 | 0 | 0 | 1994-03-01 | 1997-12-01 | 1994-12-01 |  | 2000-06-01 | 2001-12-01 | 345000 | -53650 | 291350 | 291350 | 100% | 0 | 0 | 0 | 44850 | -6974 | 37876 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-08-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | GHA | SEV | 20 | INS | 8 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-12-01 | 1999-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1996 | Non-Investment
FIN | IBRD | Country programme preparation |  | AFR | GHA | SEV | 04 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 29362 | -11448 | 17914 | 17914 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
COM | UNDP | Renewal of the institutional strengthening project | Individual | AFR | GHA | SEV | 26 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 |  | 107000 | -7725 | 99275 | 99275 | 100% | 0 | 0 | 0 | 13910 | -1004 | 12906 | 0 | 0 | Completed in 2000. | [13 empty] | 1998 | Non-Investment
FIN | France | Technical assistance in air conditioning |  | AFR | GHA | REF | 27 | TAS | 11 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-01-18 | 2000-04-01 |  | 2001-04-02 | 2001-04-01 | 31500 | -5121 | 26379 | 26379.2079 | 100% | -0.20792 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le Ghana a présenté avec l'aide du PNUD un projet utilisant les 50% restant dans le cadre du Plan de Gestion des Réfrigérants. Il n'est donc plus possible de présenter de projets avant 2007 dans ce pays.
FIN | UNDP | Implementation of the RMP: Mobile air conditioning recovery and recycling of CFC-12 | RMP-Component | AFR | GHA | REF | 32 | TAS | 12 | A | O | I | CFC | 7.7 | 7.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-12-01 | 2006-10-01 | 98902 | -45 | 98857 | 98857 | 100% | 0 | 0 | 0 | 12857 | -6 | 12851 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 2000 | Investment
FIN | UNEP | Implementation of the RMP: Customs training programme | Individual | AFR | GHA | REF | 32 | TRA | 13 | A | O | I | CFC | 6.3 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2003-01-01 | 2007-04-01 | 81000 | -18194 | 62806 | 62806 | 100% | 0 | 0 | 0 | 10530 | -2365 | 8164.78 | 0.22 | 0 | Project financially completed. | $ 18,194 plus $ 2,365 returned ExCom 46 |  |  |  |  | 2003-06-03 | [7 empty] | 2000 | Non Investment
COM | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | AFR | GHA | REF | 32 | TAS | 14 | N | O | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2006-01-01 |  | 2006-12-01 |  | 198000 | 0 | 198000 | 196581 | 99.28% | 1419 | 0 | 1135.2 | 25740 | 0 | 25555.53 | 184.47 | 0 | Completed in 2006. | [13 empty] | 2000 | Non-Investment
COM | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | AFR | GHA | SEV | 32 | INS | 15 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2003-02-01 |  | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 2003. | [13 empty] | 2000 | Non-Investment
COM | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GHA | REF | 32 | TAS | 16 | N | O | I | CFC | 1.2 | 1.2 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2007-12-01 |  | 15455 | 0 | 15455 | 4198 | 27.16% | 11257 | 0 | 9005.6 | 2009 | 0 | 545.6993 | 1463.3007 | 0 | Completed in 2007. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation in soil fumigation (curcubits) | Individual | AFR | GHA | FUM | 33 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
COM | UNDP | Training programme for terminal phase-out of methyl bromide use, excluding QPS applications | One-off-Phaseout | AFR | GHA | FUM | 37 | TRA | 18 | N | O | I | MeBr | 6.3 | 6.3 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 |  | 2006-12-01 |  | 101550 | -799 | 100751 | 100751 | 100% | 0 | 0 | 0 | 13202 | -104 | 13097.63 | 0.37 | 0 | Completed in 2006. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Renewal of institutional strengthening (phase 5) | Individual | AFR | GHA | SEV | 38 | INS | 19 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 |  | 139100 | -860 | 138240 | 138240 | 100% | 0 | 0 | 0 | 18083 | -112 | 17971.2 | -0.2 | 0 | Completed in 2004. | [13 empty] | 2002 | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GHA | SEV | 43 | INS | 20 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2006-07-01 |  | 2006-12-01 | 2008-08-01 | 139100 | -272 | 138828 | 138828 | 100% | 0 | 0 | 0 | 10433 | -20 | 10412.6 | 0.4 | 0 | Completed in 2006. Financially Completed in 2008. | [13 empty] | 2004 | Non-Investment
FIN | UNDP | Technical assistance for the CTC sector | Individual | AFR | GHA | SOL | 44 | TAS | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 20000 | -284 | 19716 | 19716 | 100% | 0 | 0 | 0 | 1800 | -26 | 1774.44 | -0.44 | 0 | Completed in 2006. Financially Completed in 2008. | [13 empty] | 2004 | Non-Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | GHA | PHA | 47 | PRP | 23 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-08-01 | 30000 | -609 | 29391 | 29391 | 100% | 0 | 0 | 0 | 2250 | -46 | 2204.32 | -0.32 | 0 | Completed in 2006. Financially Completed in 2008. | [13 empty] | 2005 | Investment
COM | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GHA | PHA | 50 | INV | 24 | N | O | I | CFC | 12.2 | 12.2 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2009-11-01 |  | 2008-11-01 |  | 204394 | 0 | 204394 | 204394 | 100% | 0 | 0 | 0 | 15330 | 0 | 15330 | 0 | 0 | Completed in 2008. See GHA-26 for status. | [13 empty] | 2006 | Investment | 17.5 | 17.5 |  |  | Yes | Yes | No
COM | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GHA | SEV | 50 | INS | 25 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 |  | 139100 | 0 | 139100 | 131591 | 94.6% | 7509 | 0 | 6007.2 | 10433 | 0 | 9869.798 | 563.202 | 0 | Completed in 2008. Ozone Office fully operational and implementing activities according to action plan. New phase approved at 56th ExCom meeting. | [13 empty] | 2006 | Non-Investment
ONG | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GHA | PHA | 53 | INV | 26 | N | O | I | CFC | 5.3 | 5 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 | 2009-11-01 |  |  | 140500 | 0 | 140500 | 104670 | 74.5% | 35830 | 0 | 14332 | 10538 | 0 | 7850.6225 | 2687.3775 | 0 | A detailed progress report was submitted at the 56th ExCom meeting in which the excellent progress was reported related to the awareness activities, refrigeration training and certification programme, the customs training, the MAC R&R Wayside Technicians programme, the retrofit programme in Commercial Refr and MAC sectors. All activities scheduled to be completed by Nov 2009. | [13 empty] | 2007 | Investment | 5.3 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GHA | PHA | 55 | PRP | 27 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Approved at 55th ExCom, initial visit undertaken in 2008 to initiate activities, discuss survey forms, draft prodoc and TORs. Inception workshop to take place after survey conducted, scheduled for June 2009. Interest in possible climate links expressed. HPMP to be submitted 4Q2008. | [13 empty] | 2008 | Investment
ONG | UNDP | MDI transition strategy | Individual | AFR | GHA | ARS | 56 | TAS | 28 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-05-01 | 2010-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 6000 | 2700 | 0 | 0 | 2700 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | GHA | SEV | 56 | INS | 29 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-01 | 2010-11-01 |  |  | 139100 | 0 | 139100 | 0 | 0% | 139100 | 0 | 27820 | 10433 | 0 | 0 | 10433 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
FIN | UNEP | Regional workshop for Arabic speaking countries | Individual | GLO | GLO | SEV | 4 | TRA | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-12-01 |  | 1991-12-01 | 1992-12-01 | 246000 | -104000 | 142000 | 142000 | 100% | 0 | 0 | 0 | 31980 | -13520 | 18460 | 0 | 0 | Project financially completed. | $ 104,000 plus $ 13,520 PSC returned ExCom 41 | [12 empty] | 1994 | Non Investment
FIN | UNEP | Information exchange and technology transfer (1991-1992) | Individual | GLO | GLO | SEV | 4 | TAS | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-12-01 |  | 1993-06-01 | 1993-12-01 | 526000 | 0 | 526000 | 526000 | 100% | 0 | 0 | 0 | 68380 | 0 | 68380 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
FIN | UNEP | Advisory group meeting (1991) | Individual | GLO | GLO | SEV | 4 | TAS | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-03-01 | 1992-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
FIN | IBRD | Administration, coordination, financial, legal (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 320000 | -34564 | 285436 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in the Middle East | RMP-Component | GLO | GLO | REF | 06 | TRA | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1992-12-01 |  | 1996-06-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in MAC | RMP-Component | GLO | GLO | REF | 06 | TAS | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1998-01-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in refrigeration sector | RMP-Component | GLO | GLO | REF | 06 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1994-02-01 |  | 1994-09-01 | 1997-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in flexible polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in solvents | Individual | GLO | GLO | SOL | 06 | TAS | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in halons | Individual | GLO | GLO | HAL | 06 | TAS | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-01-01 |  | 1994-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Three national policy workshops | Individual | GLO | GLO | SEV | 06 | TRA | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1996-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Two study-tours for officials and industry representatives | Individual | GLO | GLO | SEV | 06 | TRA | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1998-04-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Participation at workshops and key metings | Individual | GLO | GLO | SEV | 06 | TRA | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-10-01 |  | 1995-09-01 | 1997-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNEP | OzonAction Information Clearing-house (1992) | Individual | GLO | GLO | SEV | 6 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 430000 | 0 | 430000 | 430000 | 100% | 0 | 0 | 0 | 55900 | 0 | 55900 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Preparation of technical documents and newsletter | Individual | GLO | GLO | SEV | 6 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 320000 | 0 | 320000 | 320000 | 100% | 0 | 0 | 0 | 41600 | 0 | 41600 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in the Middle East | Individual | GLO | GLO | HAL | 06 | TRA | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-02-01 |  | 1993-12-01 | 1997-12-01 | 60000 | -20988 | 39012 | 39012 | 100% | 0 | 0 | 0 | 7800 | -2728 | 5072 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in the Middle East/Africa | Individual | GLO | GLO | FOA | 06 | TRA | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-12-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -14413 | 38087 | 38087 | 100% | 0 | 0 | 0 | 6825 | -1874 | 4951 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial and industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 06 | TRA | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Technical assistance in rigid polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-01-01 |  | 1993-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNEP | Support to training activities by UNEP | Individual | GLO | GLO | SEV | 6 | TRA | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1994-03-01 | 1994-12-01 | 365000 | 0 | 365000 | 365000 | 100% | 0 | 0 | 0 | 47450 | 0 | 47450 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Advisory group meeting (1992) | Individual | GLO | GLO | SEV | 6 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-02-01 |  | 1993-03-01 | 1993-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Travel (1992) | Individual | GLO | GLO | SEV | 6 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | IBRD | Administration, coordination, financial, legal (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1347550 | -396573 | 950977 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Technical assistance in aerosol sector | Individual | GLO | GLO | ARS | 06 | TAS | 24 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-02-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Procurement of 40 halon recycling machines for demonstration | Individual | GLO | GLO | HAL | 07 | DEM | 25 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-09-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | Germany | Support to attend the Alternatives to CFC and Halons Technologies and Substances conference | Individual | GLO | GLO | SEV | 07 | TRA | 26 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-10-01 | 1992-10-01 |  | 1992-10-01 | 1994-10-01 | 18378 | 0 | 18378 | 18378 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | UNDP | Global halon project | Individual | GLO | GLO | HAL | 08 | TAS | 27 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1995-10-01 |  | 1997-12-01 | 1999-05-01 | 345133 | 0 | 345133 | 345133 | 100% | 0 | 0 | 0 | 44867 | 0 | 44867 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Global MAC project | RMP-Component | GLO | GLO | REF | 08 | TAS | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1995-10-01 |  | 1995-12-01 | 1997-12-01 | 318584 | 0 | 318584 | 318584 | 100% | 0 | 0 | 0 | 41416 | 0 | 41416 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Global refrigeration project | Individual | GLO | GLO | REF | 08 | TAS | 29 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 60000 | -6681 | 53319 | 53319 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The original Global Refrigeration project is completed. The final activity, the preparation of a template for the domestic refrigeration sector utilizing hydrocarbon refrigerant, has been completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Regional workshops in halon-1211 training |  | GLO | GLO | HAL | 08 | TRA | 30 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 429000 | 0 | 429000 | 429000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | IBRD | Global solvent project |  | GLO | GLO | SOL | 08 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 260000 | 21754 | 281754 | 281754 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is completed Final report to be issued shortly. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Preparation of training material for aerosol sector | Individual | GLO | GLO | ARS | 9 | TAS | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Support to networking activities | Individual | GLO | GLO | SEV | 9 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1993-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Aerosol training workshop | Individual | GLO | GLO | ARS | 9 | TRA | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Support to other national training activities | Individual | GLO | GLO | SEV | 9 | TRA | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Development of a training strategy | Individual | GLO | GLO | SEV | 9 | TRA | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | International halon bank clearing-house function | Individual | GLO | GLO | HAL | 9 | TAS | 37 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-05-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
CLO | IBRD | Preparation of investment projects (1993) |  | GLO | GLO | SEV | 09 | PRP | 38 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1995-03-01 |  |  | 1993-12-01 | 455000 | -455000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Travel (1993) | Individual | GLO | GLO | SEV | 9 | TAS | 39 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Advisory group meeting (1993) | Individual | GLO | GLO | SEV | 9 | TAS | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Preparation of training material for refrigeration sector | Individual | GLO | GLO | REF | 9 | TAS | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Information Exchange Clearing-house System (1993) | Individual | GLO | GLO | SEV | 9 | TAS | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-06-01 | 1996-07-01 | 705000 | 0 | 705000 | 705000 | 100% | 0 | 0 | 0 | 91650 | 0 | 91650 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 43 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1179000 | -309745 | 869355 | -100 | -100 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Global aerosol project | Individual | GLO | GLO | ARS | 10 | TAS | 44 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-12-01 |  | 1995-12-01 | 1995-12-01 | 350000 | -196423 | 153577 | 153577 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Global Aerosol Phase I report has been received and is under consideration. It is most likely that the Phase II component will be implemented by UNEP. Discussions have been initiated. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 10 | TRA | 45 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 | 0 | 5642 | 0 | 5642 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNIDO | Strategy for phasing out of ODS in low ODS-consuming countries | Individual | GLO | GLO | REF | 11 | TAS | 46 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-09-01 | 1994-11-01 |  | 1996-06-01 | 1998-08-01 | 100000 | -159 | 99841 | 99841 | 100% | 0 | 0 |  | 13000 | -41 | 12959 | 0 | 0 | FIN
FIN | UNEP | Updating OAIC diskette and on-line system (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 47 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-21 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Outreach at conferences and workshops (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 48 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-16 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Information dissemination (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 49 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-20 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 380000 | 0 | 380000 | 380000 | 100% | 0 | 0 | 0 | 49400 | 0 | 49400 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Sectoral data collection (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 50 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1997-03-01 | 1999-02-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 | 0 | 27950 | 0 | 27950 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Quality review technology catalogs | Individual | GLO | GLO | SEV | 12 | TAS | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-04-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 52 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1418963 | -47607 | 1371356 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Information papers and fact sheets for evaluation of technical options to replace ODS | Individual | GLO | GLO | SEV | 12 | TAS | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1999-12-01 | 2000-01-01 | 60000 | -3500 | 56500 | 56500 | 100% | 0 | 0 | 0 | 7800 | -455 | 7345 | 0 | 0 | Project financially completed. | $ 3,500 plus $ 455 PSC returned ExCom 33 |  |  | 1998-12-01 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Translation of the "Protecting the Ozone Layer" sectoral technical brochures | Individual | GLO | GLO | SEV | 12 | TAS | 54 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-09-01 | 1999-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Halon bank management information collection and dissemination (1994) | Individual | GLO | GLO | HAL | 12 | TAS | 55 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Halon bank management case study logbook | Individual | GLO | GLO | HAL | 12 | TAS | 56 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1998-07-01 | 1995-03-01 |  | 2001-10-01 | 2001-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | 1999-03-01 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Translate the halon management: banking for the future information kit | Individual | GLO | GLO | HAL | 12 | TAS | 57 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1996-03-01 | 1999-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Informal Advisory Group meeting (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 58 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-20 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Ad hoc Group meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 59 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Meeting of the consultants (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-04 | 1995-03-01 |  | 1995-07-01 | 1995-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Travel (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNIDO | Joint UNIDO/UNEP preparation of country programmes | Individual | GLO | GLO | SEV | 12 | TAS | 62 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1996-06-01 | 1998-08-01 | 75000 | -3155 | 71845 | 71845 | 100% | 0 | 0 |  | 9750 | -425 | 9325 | 0 | 0 | FIN
FIN | UNDP | Safety pre-assessment and post-assessment of foam and solvent projects implemented by UNDP | Individual | GLO | GLO | FOA | 12 | TAS | 63 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 3000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3250 | 390 | 3640 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Non-Investment
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | SOL | 12 | PRP | 64 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | REF | 12 | PRP | 65 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | ARS | 12 | PRP | 66 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 349931 | -349931 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Query-response service (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 67 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | OzonAction newsletter and special supplements (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 68 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNDP | Analysis and formulation of a halon action plan and phase out strategy for small consuming countries | Individual | GLO | GLO | HAL | 13 | TAS | 69 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Non-Investment
FIN | UNEP | Support to national training activities (1994) | Individual | GLO | GLO | SEV | 13 | TRA | 70 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1996-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNDP | Determination of cost-effective phase-out approaches for enterprises with relatively small ODS use in foams | Individual | GLO | GLO | FOA | 14 | TAS | 71 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-09-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Non-Investment
FIN | UNEP | Update the OAIC diskette version (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 72 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Translation of "Training Manual on Good Practices in Refrigeration" and "Training Manual on Chillers and Refrigerant Management" into Chinese, French and Spanish | Individual | GLO | GLO | REF | 16 | TRA | 73 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-25 | 1995-09-01 |  | 1997-12-01 | 1999-04-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 | 0 | 34320 | 0 | 34320 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Information papers and fact sheets to assist evaluation of technical options to replace ODS (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 74 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Develop sector specific videos | Individual | GLO | GLO | SEV | 16 | TAS | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-05-31 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Update Technology Sourcebooks and quality review updated material | Individual | GLO | GLO | SEV | 16 | TAS | 76 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Project financially completed. |  |  |  | 1999-07-01 |  |  | 2002-04-01 | [6 empty] | 1995 | Non Investment
FIN | UNEP | Disseminate information (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 78 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 | 0 | 31850 | 0 | 31850 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Provide direct query-response service (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 79 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-20 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 80 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-12 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Halon bank management query response, information collection and dissemination (1995) | Individual | GLO | GLO | HAL | 16 | TAS | 81 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-20 | 1995-07-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Collect sectoral data from worldwide sources (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 82 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-08-28 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 | 0 | 23400 | 0 | 23400 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Informal advisory group meeting (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 83 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Meeting of halon bank managers | Individual | GLO | GLO | HAL | 16 | TAS | 84 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-21 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Development of a "self-help" guide for small halon-consuming countries | Individual | GLO | GLO | HAL | 16 | TAS | 85 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-08-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | 1999-03-01 | [9 empty] | 1995 | Non Investment
FIN | UNEP | Dissemination of the existing halon banking awareness flyer | Individual | GLO | GLO | HAL | 16 | TAS | 86 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-09-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Completion of "Recommendations for a Code of Good Practice in Refrigeration" for Article 5 countries | Individual | GLO | GLO | REF | 16 | TAS | 87 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1995-09-01 |  | 1998-07-01 | 1999-04-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 | 0 | 4940 | 0 | 4940 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Ad hoc group meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 88 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-03 | 1996-03-01 |  | 1997-06-01 | 1999-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Travel (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 89 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-09-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNDP | Global MACs project: Phase 2 | RMP-Component | GLO | GLO | REF | 18 | TAS | 90 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1997-11-01 |  | 1999-05-01 | 2004-01-01 | 500000 | -1 | 499999 | 499999 | 100% | 0 | 0 | 0 | 65000 | 0 | 65000 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  |  |  | 1999-07-01 | [9 empty] | 1995 | Non-Investment
FIN | UNEP | Produce sector-specific video for aerosol sector | Individual | GLO | GLO | ARS | 19 | TAS | 91 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1996-12-01 |  | 1999-12-01 | 2000-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | 1999-03-01 | [9 empty] | 1996 | Non Investment
FIN | IBRD | OORG workshops and meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 92 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 183399 | 0 | 183399 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Produce a video on methyl bromide alternatives | Individual | GLO | GLO | FUM | 19 | TAS | 93 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-03-01 | 2000-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. |  |  |  | 1999-03-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Develop technical brochure on methyl bromide | Individual | GLO | GLO | FUM | 19 | TRA | 94 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Provide halon bank management query response, information collection and dissemination | Individual | GLO | GLO | HAL | 19 | TAS | 95 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 | 0 | 3770 | 0 | 3770 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Guidelines for the establishment of recovery and recycling systems and related legislation for low volume ODS consuming countries | Individual | GLO | GLO | REF | 19 | TAS | 96 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2000-06-01 | 2000-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed. |  |  |  | 1999-07-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Training modules for national training courses on good practices in refrigeration | Individual | GLO | GLO | REF | 19 | TRA | 97 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | 1999-07-01 |  |  | 2002-06-01 | [6 empty] | 1996 | Non Investment
FIN | UNEP | Prepare guidance to assist hotel industry in LVCs to avoid, replace, or eliminate ODS | Individual | GLO | GLO | REF | 19 | TRA | 98 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1996-12-01 |  | 1998-04-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 19 | TAS | 99 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-04-01 | 1999-01-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Collect sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 19 | TAS | 100 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-12-01 | 1999-01-01 | 104500 | 0 | 104500 | 104500 | 100% | 0 | 0 | 0 | 13585 | 0 | 13585 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Provide direct query-response service (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 101 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 6240 | 0 | 6240 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Support to national activities | Individual | GLO | GLO | SEV | 19 | TAS | 102 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-05-01 | 1999-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Ad hoc Group meetings | Individual | GLO | GLO | SEV | 19 | TAS | 103 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Deliver OAIC-DV and other OzonAction Programme information through World Wide Web home page site on a one year trial basis | Individual | GLO | GLO | SEV | 19 | TAS | 104 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 | 0 | 1885 | 0 | 1885 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Continue to maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 19 | TAS | 105 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Prepare an inventory and assessment of environmentally sound and economically viable technologies and know-how conducive to phase out of ODS | Individual | GLO | GLO | SEV | 19 | TAS | 106 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 2000-12-01 | 1996-08-01 |  | 2004-04-01 | 2005-12-01 | 50000 | -27500 | 22500 | 22500 | 100% | 0 | 0 | 0 | 6500 | -3575 | 2925 | 0 | 0 | Project financially completed. | $ 27,500 plus $ 3,575 returned ExCom 46 |  |  | 2000-03-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Travel (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special suplements | Individual | GLO | GLO | SEV | 19 | TAS | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 | 0 | 31850 | 0 | 31850 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Prepare information papers and case studies | Individual | GLO | GLO | SEV | 19 | TRA | 109 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 2001-09-01 | 2001-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 | 0 | 0 | 5980 | 0 | 5980 | 0 | 0 | Project financially completed. |  |  |  | 1999-03-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 110 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 3120 | 0 | 3120 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Produce handbook on technology options especially for SMEs | Individual | GLO | GLO | SEV | 19 | TRA | 111 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-11-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. |  |  |  | 1999-07-01 | [9 empty] | 1996 | Non Investment
CLO | UNEP | Training modules on management of ODS phase-out in SMEs | Individual | GLO | GLO | SEV | 19 | TAS | 112 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  |  | 2006-12-01 | 40000 | -19000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 5200 | -2470 | 2730 | 0 | 0 | Project cancelled | $ 19,000 plus $ 2,470 returned to ExCom 52 |  |  | 1999-12-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Disseminate information | Individual | GLO | GLO | SEV | 19 | TRA | 113 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-05-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Training modules on policy design and setting up of legislation | Individual | GLO | GLO | SEV | 19 | TRA | 114 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Provide International Halon Bank Management International Clearinghouse services | Individual | GLO | GLO | HAL | 21 | TAS | 115 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Study on drop-in substitutes for domestic refrigeration | Individual | GLO | GLO | REF | 21 | TAS | 116 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1999-08-01 | 2000-06-01 | 80000 | -21000 | 59000 | 59000 | 100% | 0 | 0 | 0 | 10400 | -2730 | 7670 | 0 | 0 | Project financially completed. | $ 21,000 plus $ 2,730 PSC returned ExCom 32 |  |  | 1999-05-01 | [9 empty] | 1995 | Non Investment
FIN | IBRD | IFC concessional financing study |  | GLO | GLO | SEV | 21 | PRP | 117 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 21 | TAS | 118 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 | 0 | 44200 | 0 | 44200 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Provide direct query-response service (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 119 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 21 | TAS | 120 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-02-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 21 | TAS | 121 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-01-01 |  | 1997-12-01 | 1999-01-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 | 0 | 0 | 43550 | 0 | 43550 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Advisory and expert group meetings | Individual | GLO | GLO | SEV | 21 | TAS | 122 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 123 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Travel (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 124 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Update the OAIC diskette version including "Simple Search" versions of prioritized OzonAction publications | Individual | GLO | GLO | SEV | 21 | TAS | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-10-01 | 2000-06-01 | 63000 | -15400 | 47600 | 47600 | 100% | 0 | 0 | 0 | 8190 | -2002 | 6188 | 0 | 0 | Project financially completed. | $15400 plus $2002 PSC returned ExCom 32 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Deliver OzonAction newsletter and other information through the World Wide Web home page | Individual | GLO | GLO | SEV | 21 | TAS | 126 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Update existing technical brochure series to include 1994/95 TOC data | Individual | GLO | GLO | SEV | 21 | TAS | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 2001-01-01 | 2002-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Develop awareness materials for 1999 freeze to support national initiatives on awareness raising | Individual | GLO | GLO | SEV | 21 | TAS | 128 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Translate prioritized OzonAction Programme documents into French and Spanish | Individual | GLO | GLO | SEV | 21 | TAS | 129 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1997-12-01 |  | 1998-12-01 | 1999-08-01 | 40000 | -1191 | 38809 | 38809 | 100% | 0 | 0 | 0 | 5200 | -154.83 | 5045.17 | 0 | 0 | Project financially completed. | $1191 plus $155 PSC returned ExCom 30 | [12 empty] | 1998 | Non Investment
FIN | UNEP | Develop a handbook on the practical use of policy instruments | Individual | GLO | GLO | SEV | 21 | TAS | 130 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-11-01 | 1997-12-01 |  | 2003-06-01 | 2005-12-01 | 50000 | -10000 | 40000 | 40000 | 100% | 0 | 0 | 0 | 6500 | -1300 | 5200 | 0 | 0 | Project financially completed. | $ 50,000 plus $ 6,500 returned ExCom 46 |  |  | 1999-07-01 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 21 | TAS | 131 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Preparation of refrigerant management plans/country programmes for VLVC/LVC | Individual | GLO | GLO | SEV | 22 | CPG | 132 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1997-12-01 |  | 2002-03-01 | 2007-01-01 | 200000 | -73040 | 126960 | 126960 | 100% | 0 | 0 | 0 | 26000 | -9495 | 16504.8 | 0.2 | 0 | Project financially completed. | $ 73,040 plus $ 9,495 returned ExCom 46 |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
FIN | UNDP | Preparation of refrigerant management plans (Bahamas, Bangladesh, Botswana, Dominican Republic, El Salvador, Gabon, Mozambique, Niger, Lesotho, Trinidad and Tobago) | Individual | GLO | GLO | REF | 22 | PRP | 133 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 140000 | -2 | 139998 | 139998 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNIDO | Development of Refrigeration Management Plans | Individual | GLO | GLO | REF | 22 | PRP | 134 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1997-12-01 |  | 2001-04-01 | 2001-09-01 | 60000 | -23740 | 36260 | 36260 | 100% | 0 | 0 |  | 7800 | -3094 | 4706 | 0 | 0 | FIN |  |  |  | 1999-02-01
CLO | IBRD | Initial work programme for 1991 | Individual | GLO | GLO | SEV | 04 | TAS | 135 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 500000 | -500000 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 23 | TAS | 136 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-08-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | Switzerland | International workshop on potential for hydrocarbon-based refrigerant as replacements in existing domestic and small commercial refrigeration appliances | Individual | GLO | GLO | REF | 23 | TRA | 137 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1997-12-01 |  | 1997-09-01 | 1997-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1997
FIN | Germany | Information video: working safely with hydrocarbons in domestic and small scale commercial refrigeration | Individual | GLO | GLO | REF | 23 | TRA | 138 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1998-08-01 |  | 2001-01-01 | 2002-12-01 | 322050 | 0 | 322050 | 322050 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Dec 2003 | [13 empty] | 2002
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 23 | TAS | 139 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 | 0 | 14560 | 0 | 14560 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Update the OAIC diskette version (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 140 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 23 | TAS | 141 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 | 0 | 44200 | 0 | 44200 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Provide direct query-response service (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 142 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through World Wide Web home page site | Individual | GLO | GLO | SEV | 23 | TAS | 143 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Advisory and expert group meetings (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 144 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -10000 | 65000 | 65000 | 100% | 0 | 0 | 0 | 9750 | -1300 | 8450 | 0 | 0 | Project financially completed. | $ 10,000 plus $ 1,300 PSC returned ExCom 32 | [12 empty] | 1994 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (1998) | Individual | GLO | GLO | HAL | 23 | TAS | 145 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 | 0 | 11570 | 0 | 11570 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Travel (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 146 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -2950 | 72050 | 72050 | 100% | 0 | 0 | 0 | 9750 | -383 | 9366.5 | 0.5 | 0 | Project financially completed. | $ 2,950 plus $ 383 PSC returned ExCom 33 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 23 | TAS | 147 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-07-01 | 347000 | -1750 | 345250 | 345250 | 100% | 0 | 0 | 0 | 45110 | -227.5 | 44882.5 | 0 | 0 | Project financially completed. | $ 1,750 plus $,228 PSC returned ExCom 30 | [12 empty] | 1994 | Non Investment
FIN | UNEP | Support to national activities (1998) | Individual | GLO | GLO | SEV | 23 | TRA | 148 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-10-01 |  | 1998-10-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
CLO | IBRD | Advance for project preparation as indicated in the 1998 business plan |  | GLO | GLO | SEV | 23 | PRP | 149 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 1998-12-01 | 275600 | -275600 | 0 | 0 |  | 0 | 0 |  | 35828 | -35828 | 0 | 0 | 0 | The resources allocated for this project were granted to The World Bank as an advance for project preparation for the Year 1998. During the 24th meeting the resources were taken out of the total project prepartion approvals. To indicate this transaction a negative entry with the same ID is created in 24th meeting. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Technical sourcebook of methyl bromide alternatives | Individual | GLO | GLO | FUM | 23 | TAS | 150 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-12-01 | 2002-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Handbook for NOUs reducing reliance on methyl bromide | Individual | GLO | GLO | FUM | 23 | TAS | 151 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1998-11-01 |  | 1999-02-01 | 1999-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 152 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Translate and print three guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 23 | TAS | 153 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 2002-12-01 | 2003-08-01 | 360000 | 0 | 360000 | 360000 | 100% | 0 | 0 | 0 | 46800 | 0 | 46800 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
CLO | UNDP | Advance for project preparation as indicated in the 1998 business plan | Individual | GLO | GLO | SEV | 23 | PRP | 154 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-03-01 |  |  | 1998-03-01 | 256000 | -256000 | 0 | 0 |  | 0 | 0 | 0 | 33280 | -33280 | 0 | 0 | 0 | Canceled in 1998. | [13 empty] | 1998 | Investment
FIN | UNEP | Compilation of legislations for regulatory authorities from Article 5 countries that discourage methyl bromide use and promote alternatives | Individual | GLO | GLO | FUM | 24 | TAS | 155 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Technical and institutional resources for methyl bromide alternatives projects | Individual | GLO | GLO | FUM | 24 | TAS | 156 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-10-01 |  | 1999-09-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Methyl bromide information kit | Individual | GLO | GLO | FUM | 24 | TAS | 157 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 1998-12-01 | 1999-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Data reporting handbook to provide information to Article 5 countries and assist them with their data reporting | Individual | GLO | GLO | SEV | 24 | TAS | 158 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-01-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNDP | Global MAC project: Phase III | RMP-Component | GLO | GLO | REF | 24 | TAS | 159 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2002-12-01 | 2003-12-01 | 250000 | -63356 | 186644 | 186644 | 100% | 0 | 0 | 0 | 32500 | -8236 | 24264 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | UNEP | Compilation of case studies on commercial, low-impact methyl bromide alternatives successfully implemented | Individual | GLO | GLO | FUM | 24 | TAS | 160 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | Germany | Travel expenses for participants to attend a regional workshop on methyl bromide alternatives for North African countries (Algeria, Egypt, Jordan, Lebanon, Morocco, Syria, Tunisia) | Individual | GLO | GLO | FUM | 25 | TRA | 161 | N | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-05-01 | 1999-06-01 |  | 1998-06-01 | 1999-07-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | UNEP | Deliver the OzonAction newsletter and other information through world wide web home page site (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 162 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 163 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 | 0 | 14560 | 0 | 14560 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 164 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 | 0 | 11570 | 0 | 11570 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Disseminate awareness materials, technical and policy information (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 165 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 | 0 | 44200 | 0 | 44200 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 26 | TAS | 166 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 26 | TAS | 167 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Provide direct query-response service (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 168 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Advisory and expert group meetings (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 169 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 75000 | -3500 | 71500 | 71500 | 100% | 0 | 0 | 0 | 9750 | -455 | 9295 | 0 | 0 | Project financially completed. | $ 3,500 plus $ 455 PSC returned ExCom 33 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 170 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 55000 | -6300 | 48700 | 48700 | 100% | 0 | 0 | 0 | 7150 | -819 | 6331 | 0 | 0 | Project financially completed. | $ 6,300 plus $ 819 PSC returned ExCom 31 | [12 empty] | 1996 | Non Investment
FIN | UNEP | Travel (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 171 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | Germany | Implementation of RMPs for 14 low volume consuming countries in eastern and southern Africa | RMP | GLO | GLO | REF | 26 | TAS | 172 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-11-01 | 2005-09-01 | 815000 | 0 | 815000 | 815000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All countries completed the activities under this project. PCR is to be submitted | [13 empty] | 2000
FIN | UNEP | Support to national activities for 1999 | Individual | GLO | GLO | SEV | 26 | TAS | 173 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 26 | TAS | 174 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 347000 | 0 | 347000 | 347000 | 100% | 0 | 0 | 0 | 45110 | 0 | 45110 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 175 | A | O | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  | 1999-12-01 | 2001-02-01 | 169000 | -169000 | 0 | 0 |  | 0 | 0 |  | 21970 | -21970 | 0 | 0 | 0 | FIN
CLO | UNDP | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 176 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-03-01 |  |  | 1999-03-01 | 299000 | -299000 | 0 | 0 |  | 0 | 0 | 0 | 38870 | -38870 | 0 | 0 | 0 | Canceled in 1999. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation advance |  | GLO | GLO | SEV | 26 | PRP | 177 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-03-31 | 1999-12-01 |  | 2000-12-01 | 1999-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Development of training manuals for extension workers | Individual | GLO | GLO | FUM | 27 | TRA | 178 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-02-01 | 50000 | -4000 | 46000 | 46000 | 100% | 0 | 0 | 0 | 6500 | -520 | 5980 | 0 | 0 | Project financially completed. | $ 4,000 plus $ 520 PSC returned ExCom 43 | [12 empty] | 1999 | Non Investment
FIN | UNEP | National farmer's training and establishment of Farmer's Field School (FFS) | Individual | GLO | GLO | FUM | 27 | TRA | 179 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-04-01 |  | 2001-12-01 | 2003-12-03 | 60000 | -4000 | 56000 | 56000 | 100% | 0 | 0 | 0 | 7800 | -520 | 7280 | 0 | 0 | Project financially completed. | $ 4,000 plus $ 520 PSC returned ExCom 43 | [12 empty] | 1999 | Non Investment
FIN | Canada | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 180 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-02-01 | 2000-04-01 |  | 2001-07-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | English version of manual completed in April 2001. Printing and dissemination has been completed. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | UNEP | Development of a handbook on standards and codes of good practice for halon sector | Individual | GLO | GLO | HAL | 27 | TAS | 181 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-09-01 | 2002-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Develop fact sheet describing win-win technology options relative to Kyoto and Montreal Protocols | Individual | GLO | GLO | SEV | 27 | TAS | 182 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2000-04-01 |  | 2002-12-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Update regulations to control ozone depleting substances | Individual | GLO | GLO | SEV | 27 | TAS | 183 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2001-09-01 | 2001-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | Finland | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 184 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2001-11-01 | 2002-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1999 |  |  |  | 2001-06-01
FIN | IBRD | Unallocated project preparation funds |  | GLO | GLO | SEV | 27 | PRP | 185 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 162000 | 0 | 162000 | 162000 | 100% | 0 | 0 |  | 21060 | 0 | 21060 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Update the OAIC CD-Rom | Individual | GLO | GLO | SEV | 29 | TAS | 186 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-01-01 | 2002-01-01 | 69300 | 0 | 69300 | 69300 | 100% | 0 | 0 | 0 | 9009 | 0 | 9009 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Preparation of how-to crop manual on adopting methyl bromide alternatives for cut flowers | Individual | GLO | GLO | FUM | 29 | TAS | 187 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2000-11-01 |  | 2001-12-01 | 2002-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Support to national activities (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 188 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNIDO | Project preparation advance for 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 189 | A | O | I |  | 0 | 0 |  |  | 1999-11-01 |  | 2000-04-01 |  | 2000-12-01 | 2003-05-01 | 170000 | -170000 | 0 | 0 |  | 0 | 0 |  | 22100 | -22100 | 0 | 0 | 0 | FIN
CLO | UNDP | Project preparation advance for the year 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 190 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2003-09-01 | 250000 | -250000 | 0 | 0 |  | 0 | 0 | 0 | 32500 | -32500 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
CLO | IBRD | Project preparation advance for 2000 |  | GLO | GLO | SEV | 29 | PRP | 191 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2000-03-01 | 357450 | -357450 | 0 | 0 |  | 0 | 0 |  | 46468.5 | -46468.5 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 192 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 29 | TAS | 193 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 117600 | 0 | 117600 | 117600 | 100% | 0 | 0 | 0 | 15288 | 0 | 15288 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Travel (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 194 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Diseminate awareness materials, technical and policy information (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 195 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 357000 | 0 | 357000 | 357000 | 100% | 0 | 0 | 0 | 46410 | 0 | 46410 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Provide international halon bank management information clearinghouse services (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 196 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 93450 | 0 | 93450 | 93450 | 100% | 0 | 0 | 0 | 12148.5 | 0 | 12148.5 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Provide direct query-response service (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 197 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 84000 | 0 | 84000 | 84000 | 100% | 0 | 0 | 0 | 10920 | 0 | 10920 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Complement for translation and printing of four guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 29 | TAS | 198 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2005-04-01 | 2007-07-01 | 120000 | -22000 | 98000 | 98000 | 100% | 0 | 0 | 0 | 15600 | -2860 | 12740 | 0 | 0 | Project financially completed. | $ 22,000 plus US$ 2,860 PSC returned to ExCom 55 |  |  |  |  | 2002-12-02 | [7 empty] | 1999 | Non Investment
FIN | UNEP | Advisory and expert group meetings (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 199 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 200 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2002-03-01 | 364000 | 0 | 364000 | 364000 | 100% | 0 | 0 | 0 | 47320 | 0 | 47320 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 201 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Deliver the OzonAction newsletter and other information through worldwide web home page site (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 202 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 26250 | 0 | 26250 | 26250 | 100% | 0 | 0 | 0 | 3412.5 | 0 | 3412.5 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
CLO | IBRD | Project preparation (unallocated) |  | GLO | GLO | SEV | 30 | PRP | 203 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of 6 projects in the recovery/recycling refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 204 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of 6 projects in the end-user commercial refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 205 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNEP | Organizing a global video competition on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 206 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2000-09-01 |  | 2002-11-01 | 2006-01-01 | 60000 | -42676 | 17324 | 17324 | 100% | 0 | 0 | 0 | 7800 | -5548 | 2252.12 | -0.12 | 0 | Project financially completed. | $26,684 plus $3,469 PSC returned ExCom 44. $ 15,992 plus $ 2,079 returned to ExCom 52 |  |  |  |  | 2001-10-01 | [7 empty] | 2000 | Non Investment
FIN | UNEP | Translation and printing of OzonAction documents into French, Spanish and Arabic | Individual | GLO | GLO | SEV | 30 | TAS | 207 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-05-01 | 2001-03-01 |  | 2001-12-01 | 2002-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Adapting existing audiovisual materials to promote control of illegal trade in ODS | Individual | GLO | GLO | SEV | 30 | TAS | 208 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2003-06-01 | 2003-10-01 | 50000 | -2353 | 47647 | 47647 | 100% | 0 | 0 | 0 | 6500 | -306 | 6194.11 | -0.11 | 0 | Project financially completed. | $ 2,353 plus $ 306 PSC returned ExCom 43 | [12 empty] | 2000 | Non Investment
FIN | UNEP | New awareness raising activities and materials for dissemination to the general public | Individual | GLO | GLO | SEV | 30 | TAS | 209 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-02-01 |  | 2001-12-01 | 2002-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Develop materials to educate children on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 210 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2004-07-01 | 2006-02-01 | 100000 | -10448 | 89552 | 89552 | 100% | 0 | 0 | 0 | 13000 | -1359 | 11641.76 | -0.76 | 0 | Project financially completed. | $ 9,321 plus $ 1,212 PSC returned to ExCom 52 | [6 empty] | 2003-07-01 | [5 empty] | 2000 | Non Investment
FIN | UNEP | Policy development assistance to prevent future methyl bromide growth in low methyl bromide-consuming countries | Individual | GLO | GLO | FUM | 30 | TAS | 211 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2001-05-31 | 2002-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | IBRD | Administration, coordination, financial, legal (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 212 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1450646 | 0 | 1450646 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | Canada | Translation, in French and Spanish, of the approved manual on Customs Officer Training on Substances that Deplete the Ozone Layer | Individual | GLO | GLO | SEV | 32 | TAS | 213 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2001-07-01 |  | 2002-02-01 | 2002-03-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 |  | 0 | 1440 | 0 | 1440 | 0 |  | Translation of manual into Spanish and French completed in early 2002. Both manuals were printed and disseminated in 2002. Project Completed. |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | UNEP | Provide international halon bank management information clearinghouse services in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 214 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Travel for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 215 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-12-02 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNIDO | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 216 | A | O | I |  | 0 | 0 |  |  | 2000-12-01 |  | 2001-12-01 |  | 2001-03-01 | 2001-03-01 | 139500 | -139500 | 0 | 0 |  | 0 | 0 |  | 18135 | -18135 | 0 | 0 | 0 | FIN
FIN | UNEP | Provide direct query-response service in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 217 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Global enabling activity for customs training | Individual | GLO | GLO | SEV | 32 | TRA | 218 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2002-03-01 | 2003-06-01 | 165400 | -13971 | 151429 | 151429 | 100% | 0 | 0 | 0 | 21502 | -1816.23 | 19685.77 | 0 | 0 | Project financially completed. | $ 13,971 plus $ 1,816 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Disseminate awareness material, technical, and policy information in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 219 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 346000 | -13916 | 332084 | 332084 | 100% | 0 | 0 | 0 | 44980 | -1809.08 | 43170.92 | 0 | 0 | Project financially completed. | $13,916 plus $ 1,809 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Deliver OzonAction Newsletter and other information through world wide web home page site in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 220 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Publish the OzonAction newsletter and special supplements in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 221 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 280000 | -5051 | 274949 | 274949 | 100% | 0 | 0 | 0 | 36400 | -656.63 | 35743.37 | 0 | 0 | Project financially completed. | $ 5,051 plus $ 657 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Support to national activities for 2001 | Individual | GLO | GLO | SEV | 32 | TRA | 222 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Advisory and expert group meetings for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 223 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 75000 | -7392 | 67608 | 67608 | 100% | 0 | 0 | 0 | 9750 | -960.96 | 8789.04 | 0 | 0 | Project financially completed. | $ 7,392 plus $ 961 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Regional awareness raising and South-South assistance | Individual | GLO | GLO | SEV | 32 | TAS | 224 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2001-12-01 |  | 2004-12-01 | 2006-01-01 | 191000 | -26212 | 164788 | 164788 | 100% | 0 | 0 | 0 | 24830 | -3408 | 21422.44 | -0.44 | 0 | Project financially completed. | $ 8212 plus $ 1068 returned to ExCom 50. $ 18,000 plus $ 2,340 returned to ExCom 52 | [6 empty] | 2003-07-01 | [5 empty] | 2000 | Non Investment
FIN | UNEP | Maintain contact database of experts and mailing list for OzonAction programme publications in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 225 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Conduct outreach at conferences and workshops in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 226 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 55000 | -5 | 54995 | 54995 | 100% | 0 | 0 | 0 | 7150 | -1 | 7149.35 | -0.35 | 0 | Project financially completed. | $ 5 plus $ 1 PSC returned ExCom 43 | [12 empty] | 2000 | Non Investment
CLO | UNDP | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 227 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2001-12-01 |  |  | 2001-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2001. | [13 empty] | 2001 | Investment
FIN | UNEP | Prioritized sectoral data from worldwide sources in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 228 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 121000 | 0 | 121000 | 121000 | 100% | 0 | 0 | 0 | 15730 | 0 | 15730 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Preparation of a booklet on data reporting for methyl bromide | Individual | GLO | GLO | SEV | 33 | TAS | 229 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2001-12-01 |  | 2001-11-01 | 2003-06-01 | 42500 | -2002 | 40498 | 40498 | 100% | 0 | 0 | 0 | 5525 | -260.26 | 5264.74 | 0 | 0 | Project financially completed. | $ 2,002 plus $260 PSC returned ExCom 41 | [12 empty] | 2001 | Non Investment
COM | UNEP | Study on development of ODS phase-out strategy for SMEs | Individual | GLO | GLO | SEV | 34 | TAS | 230 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-09-01 | 2002-12-01 |  | 2005-12-01 |  | 100000 | -10000 | 90000 | 30000 | 33.33% | 60000 | 0 | 60000 | 13000 | -1300 | 3900 | 7800 | 0 | Project completed | $ 10,000 plus $1,300 support costs returned to 54th ExCom meeeting. | [12 empty] | 2001 | Non Investment
FIN | UNEP | Global public awareness and education campaign to sustain the phase out (first tranche) | Individual | GLO | GLO | SEV | 34 | TAS | 231 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-01-01 | 2003-01-01 | 60000 | -11755 | 48245 | 48245.26 | 100% | -0.26 | 0 | -0.26 | 7800 | -1528.15 | 6271.8838 | -0.0338 | 0 | Project financially completed. | $ 5,810 plus $ 755 PSC returned ExCom 44 $ 5,945 plus $ 773 PSC returned ExCom 46 | [12 empty] | 2001 | Non Investment
CLO | UNEP | Development of tracking system for ODS and ODS-based equipment | Individual | GLO | GLO | SEV | 34 | TAS | 232 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2002-12-01 |  |  | 2005-03-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | This project was cancelled by ExCom 44 | $ 40,000 plus $ 5,200 PSC returned ExCom 45 | [12 empty] | 2001 | Non Investment
FIN | Japan | Workshop on concessional lending | Individual | GLO | GLO | SEV | 35 | TRA | 233 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-02 | 2002-12-01 |  | 2003-03-01 | 2006-07-01 | 75000 | 0 | 75000 | 57706 | 76.94% | 17294 | 0 | 0 | 9750 | 0 | 7502 | 2248 | 0 | Project financially completed in July 2006. |  | 2001
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 35 | PRP | 234 | A | O | I |  | 0 | 0 |  |  | 2001-12-01 |  | 2002-03-01 |  | 2002-03-01 | 2002-03-01 | 176250 | -176250 | 0 | 0 |  | 0 | 0 |  | 22913 | -22913 | 0 | 0 | 0 | FIN | [13 empty] | 2001 | INV
CLO | IBRD | Project preparation advance (2002) |  | GLO | GLO | SEV | 35 | PRP | 235 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2001-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 | [14 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
CLO | UNDP | Project preparation advance (2002) | Individual | GLO | GLO | SEV | 35 | PRP | 236 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2002-03-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2002. | [13 empty] | 2002 | Investment
FIN | UNEP | Compliance Assistance Programme: 2002 work programme: | Individual | GLO | GLO | SEV | 35 | TAS | 237 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2002-12-01 |  | 2002-12-01 | 2005-01-01 | 5351450 | -1500591 | 3850859 | 3850859 | 100% | 0 | 0 | 0 | 428116 | -120047 | 308068.72 | 0.28 | 0 | Project financially completed. | $ 50,000 transferred for 5 policy projects ExCom 37 / $1,265,686.30 plus $ 105,254.90 PSC returned Excom 41 / $176,842 plus $14,147 PSC returned Excom 44; $ ,8063 plus $ 645 returned from ExCom 48 | [12 empty] | 1991 | Non Investment
FIN | UNEP | Translation of OzonAction Publications into other UN languages | Individual | GLO | GLO | SEV | 36 | TAS | 238 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2002-11-01 |  | 2006-11-01 | 2007-12-01 | 93000 | -34067 | 58933 | 58933 | 100% | 0 | 0 | 0 | 12090 | -4429 | 7661.29 | -0.29 | 0 | Project financially completed. | $ 34,067 plus $ 4,429 PSC returned to ExCom 54 | [6 empty] | 2004-07-01 | [5 empty] | 2002 | Non Investment
FIN | IBRD | Unallocated project preparation |  | GLO | GLO | SEV | 36 | PRP | 239 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2002-12-01 | 180000 | -180000 | 0 | 0 |  | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 | [14 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | Israel | International methyl bromide compliance assistance workshop (Bahamas, Barbados, Bosnia, Congo, Ecuador, Ethiopia, Moldova, Mexico, and Zambia) | Individual | GLO | GLO | FUM | 37 | TRA | 240 | A | O | D |  | 0 |  | 0 |  | 2002-07-01 |  | 2003-03-01 |  | 2002-12-01 |  | 98300 | -64177 | 34123 | 34123 | 100% | 0 | 0 | 0 | 9830 | -5847 | 3983 | 0 | 0 | The workshop was completed as planned. The goals were achieved and feedback from participants was very positive. The numbers of participants were lower than the maximum potential cited in the proposal. Costs were lower than expected. Two countries, Bahamas and Barbados, did not send participants. Participants from Ethiopia did not arrive due to logistical problems. Please see extended summary for further details of workshop content and outputs. * In addition to estimated disbursement stated, there will be support costs at 10%. |  | 2002 | [11 empty] | 2002 | Non-Investment
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 37 | TAS | 241 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2005-12-01 | 2006-01-01 | 200000 | -33111 | 166889 | 166889 | 100% | 0 | 0 | 0 | 26000 | -4304 | 21695.57 | 0.43 | 0 | Project financially completed. | $ 33,000 plus $ 4,304 PSC returned to ExCom 52 | [7 empty] | 2004-12-01 |  |  |  |  | 2002 | Non Investment
FIN | UNEP | Compliance assistance programme: 2003 work programme | Individual | GLO | GLO | SEV | 38 | TAS | 242 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-07-01 | 5830885 | -466383 | 5364502 | 5364502 | 100% | 0 | 0 | 0 | 466471 | -37310.6646 | 429160.16 | 0.17537 | 0 | Project financially completed. | $ 173,035 plus $ 13,843 PSC returned ExCom 43 $ 293,348 plus $ 23,468 PSC returned ExCom 46 | [12 empty] | 2002 | Non Investment
FIN | UNDP | Core Unit Support (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 243 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2002 | Non-Investment
FIN | UNIDO | Core unit (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 244 | A | O | I |  | 0 | 0 |  |  | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | IBRD | Core unit (2003) |  | GLO | GLO | SEV | 38 | TAS | 245 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included support/travel of core staff; annual FI workshop and OORG meeting; attendance at ExCom and interagency mtgs; 15th MOP and UNEP regional meetings; and publication of MP case study and flyer. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | UNEP | Development of guidelines to promote safety an aerosol conversions | Individual | GLO | GLO | ARS | 39 | TAS | 246 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2003-12-01 | 2009-07-01 |  |  | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 | 0 | 6760 | 0 | 6760 | 0 | 0 | Electronic versions of remaining versions (French and Spanish) expected to be be online by July 2009. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 39 | TAS | 247 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-02-01 | 2004-04-01 |  | 2006-04-01 | 2007-12-01 | 200000 | -77956 | 122044 | 122044 | 100% | 0 | 0 | 0 | 26000 | -10134 | 15865.72 | 0.28 | 0 | Project financially completed. | $ 24,731 plus $ 3,215 returned to ExCom 52 $ 53,225 plus $ 6,919 PSC returned to ExCom 54 | [12 empty] | 2003 | Non Investment
COM | UNEP | Production of OzonAction Newsletter in Russian, translation of 4 refrigeration/customs training modules into Russian, and reprinting and updating existing publications | Individual | GLO | GLO | SEV | 39 | TAS | 248 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-03-01 |  | 2008-05-01 |  | 75000 | 0 | 75000 | 66785.04 | 89.05% | 8214.96 | 0 | 8214.96 | 9750 | 0 | 8682.0552 | 1067.9448 | 0 | Project completed in May 2008. The following documents have been translated into Russian and disseminated: - Ozone Protection, Climate Change, Energy Efficiency, Centro Galileo / UNEP, 2006 (electronically) - Ozzy Goes Farming, UNEP, 2006 (printed) - Ozzy Goes Polar, UNEP, 2007 (printed). All translation / outreach products produced under project GLO/SEV/39/TAS/248 can be downloaded from the OzonAction website or the ECA website: http://fr1.estis.net/sites/ecanetwork/default.asp?site=ecanetwork&page_id=24EAFBF9-6FDA-450A-B204-14D8EB95A01C" | [9 empty] | 2005-09-01 |  |  |  | 2003 | Non Investment
FIN | UNDP | Core Unit Support (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 249 | N | O | I | No-ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2003 | Non-Investment
FIN | UNIDO | Core unit (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 250 | A | O | I |  | 0 | 0 |  |  | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN | [13 empty] | 2003
FIN | IBRD | Core unit (2004) |  | GLO | GLO | SEV | 41 | TAS | 251 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of three MP events and development of select knowledge material. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Compliance assistance programme: 2004 budget | Individual | GLO | GLO | SEV | 41 | TAS | 252 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2004-12-01 |  | 2004-12-04 | 2006-12-01 | 6757900 | -190217 | 6567683 | 6567683 | 100% | 0 | 0 | 0 | 540632 | -15218 | 525414.64 | -0.64 | 0 | Project financially completed. | $ 141,359 plus $11,309 returned to ExCom 48 $ 48,858 plus $ 3,909 returned to ExCom 49 | [12 empty] | 2003 | Non Investment
FIN | Sweden | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 253 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-10-01 |  | 2006-02-01 | 2006-12-31 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | At the 41st meeting of the Executive Committee, the Government of Sweden in collaboration with the Government of Japan received approval for developing a Handbook related to the servicing sector. A Draft outline of the Handbook with a broader perspective in accordance with the ExCom decision was developed in March 04. Two consultants were recruited and a first full Draft was developed in Feb. 2005. The Draft was revised substantially twice before the text was sent for a review by UNEP/DTIE, Japan and the NOUs of Croatia and the Philippines in June 2005. Responses were received in Aug-Sept 2005. After taking into account the comments received, the layout and printing was organised. The printed version was received in February 2006 and the distribution to all NOUs and relevant agencies was organised by UNEP. The Handbook is available at the UNEP and SEI web pages for down load. |  | 2003 | [11 empty] | 2003
FIN | Japan | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 254 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2004-11-01 | 2004-11-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | PCR is expected to be submitted by Sweden Government in early autumn 2007. |  | 2003
COM | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 42 | TAS | 255 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-04-01 |  | 200000 | -26518 | 173482 | 167943.58 | 96.81% | 5538.42 | 5000 | 5538.42 | 26000 | -3447 | 21832.6654 | 720.3346 | 650 | Project completed. | $ 26,518 plus $ 3,447 PSC returned to ExCom 54 | [12 empty] | 2004 | Non Investment
FIN | UNDP | Initial start-up costs | Individual | GLO | GLO | SEV | 04 | TAS | 256 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1991-12-01 |  | 1992-12-01 | 2004-07-01 | 596500 | 0 | 596500 | 596500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1992. Financially completed in 2004. | [13 empty] | 2004 | Investment
FIN | UNIDO | Core unit budget for 2005 | Individual | GLO | GLO | SEV | 44 | TAS | 258 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN | [13 empty] | 2004
FIN | UNDP | Core unit (2005) | Individual | GLO | GLO | SEV | 44 | TAS | 259 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2004 | Non-Investment
FIN | UNEP | Compliance assistance programme: 2005 budget | Individual | GLO | GLO | SEV | 44 | TAS | 260 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-12-01 | 7157544 | -304536 | 6853008 | 6853007.84 | 100% | 0.16 | 0 | 0.16 | 572604 | -24363 | 548240.6272 | 0.3728 | 0 | Project financially completed. | $ 111,925 plus $ 8954 PSC returned to ExCom 50 US$ 101,599 plus US$ 8,128 PSC returned to ExCom 54 US$ 56,023 plus US$ 4,482 PSC returned to ExCom 55 US$ 34,989 plus US$ 2,799 PSC returned to ExCom 56 | [12 empty] | 2004 | Non Investment
FIN | IBRD | Core unit (2005) |  | GLO | GLO | SEV | 44 | TAS | 261 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
COM | UNEP | Assistance for regional awareness raising (2005) | Individual | GLO | GLO | SEV | 45 | TAS | 262 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2008-12-01 |  | 200000 | 0 | 200000 | 105750.85 | 52.88% | 94249.15 | 24991.39 | 94249.15 | 26000 | 0 | 13747.6105 | 12252.3895 | 3248.8807 | [14 empty] | 2005 | Non Investment
FIN | UNEP | Development of effective awareness materials | Individual | GLO | GLO | SEV | 45 | TAS | 263 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-01-01 | 2007-12-01 | 120000 | -13267 | 106733 | 106733 | 100% | 0 | 0 | 0 | 15600 | -1725 | 13875.29 | -0.29 | 0 | Project financially completed. | $ 13,267 plus $ 1,725 PSC returned to ExCom 54 | [12 empty] | 2005 | Non Investment
COM | UNEP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 264 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2007-02-01 |  | 40000 | 0 | 40000 | 31452.1 | 78.63% | 8547.9 | 0 | 8547.9 | 5200 | 0 | 4088.773 | 1111.227 | 0 | Project completed | [13 empty] | 2005 | Non Investment
FIN | UNIDO | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 265 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-08-01 | 2005-11-01 |  | 2006-06-01 | 2007-12-01 | 119000 | -640 | 118360 | 118360 | 100% | 0 | 0 |  | 8925 | -48 | 8877 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | NON-INV
COM | UNDP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 266 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2005-11-01 |  | 2005-12-01 |  | 122000 | 0 | 122000 | 121081 | 99.25% | 919 | 0 | 919 | 9150 | 0 | 9081.075 | 68.925 | 0 | Completed in 2005. | [13 empty] | 2005 | Investment
FIN | IBRD | Project preparation in the chiller sector and organization of a workshop |  | GLO | GLO | REF | 46 | PRP | 267 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2005-11-01 | 2005-11-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Chiller Workshop held Sep 05. Findings were used as a basis for development of IA chiller projects, including the Bank's Global Chiller Project. The Global Chiller Project was submitted for ExCom consideration in Nov 05 and US$6.88 million was approved out of the $15 million window. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Global chiller replacement project (China, India, Indonesia, Malaysia and Philippines) | Individual | GLO | GLO | REF | 47 | DEM | 268 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2013-12-01 | 2013-12-01 |  |  | 6884612 | 0 | 6884612 | 0 | 0% | 6884612 | 6884612 | 1200000 | 516346 | 0 | 0 | 516346 | 516346 | For India, appraisal mission conducted in Dec. 08. ERPA template was modified upon the request of the Coordinating Entity and now expected to be signed during negotiations in Apr 09. WB Board approval expected in Jun 09. For the Philippines, GEF Council approved the project for work program at US$2.6 million in Nov 08. PIN prepared for carbon finance and appraisal expected in May 09. For Jordan, Secretariat has given, indirectly, its no objection to the project approach in Nov 08. WB mission conducted in Dec 08 to prepare the project. Grant agreement is expected to be amended in Apr 09 to permit project start. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | Portugal | Communication and cooperation support to Portuguese speaking countries (Angola, Cape Verde, East Timor, Guinea Bissau, Mozambique and Sao Tome and Principe) | Individual | GLO | GLO | SEV | 47 | TAS | 269 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 | 2008-12-08 |  |  | 90000 | 0 | 90000 |  | 0% | 90000 |  | 90000 | 11700 | 0 | 0 | 11700 | 0
COM | UNEP | Compliance Assistance Programme: 2006 budget | Individual | GLO | GLO | SEV | 47 | TAS | 270 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 |  | 7770000 | -30227 | 7739773 | 7380705.41 | 95.36% | 359067.59 | 169503.07 | 218422 | 621600 | -2418 | 590456.4328 | 28725.5672 | 13560.2456 | Project financially completed. Balance to be returned to ExCom 57 | $ 30,227 plus $ 2,418 PSC returned to ExCom 55 | [12 empty] | 2005 | Non Investment
FIN | UNDP | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 271 | N | O | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1700000 | 0 | 1700000 | 0 | 0 | Completed in 2006. Financially completed in 2007. | [13 empty] | 2005 | Non-Investment
FIN | UNIDO | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 272 | A | O | I |  | 0 | 0 |  |  | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1700000 | 0 | 1700000 | 0 | 0 | FIN | [13 empty] | 2005
FIN | IBRD | Core unit budget (2006) |  | GLO | GLO | SEV | 47 | TAS | 273 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
COM | UNEP | Updating the customs training manual | Individual | GLO | GLO | SEV | 48 | TRA | 274 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 0 | 2007-04-01 |  | 2008-08-01 |  | 60000 | 0 | 60000 | 44298.77 | 73.83% | 15701.23 | 3340 | 15701.23 | 7800 | 0 | 5758.8401 | 2041.1599 | 434.2 | Project completed in August 2008. Dissemination done. Electronic version uploaded to the website. Translation into French and Spanish done | [13 empty] | 2006 | Non Investment
ONG | UNEP | Global technical assistance programme in the chiller sector | Individual | GLO | GLO | REF | 48 | TAS | 275 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 |  | 2009-04-01 | 2009-04-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 200000 | 26000 | 0 | 0 | 26000 | 0 | UNEP is still collecting information from industry and Implementing Agency sources. Still trying to identify cost-effective option for conference for last quarter of 2009. | [13 empty] | 2006 | Non Investment
COM | UNEP | Compliance Assistance Programme: 2007 budget | Individual | GLO | GLO | SEV | 50 | TAS | 276 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2007-12-01 |  | 8003000 | 0 | 8003000 | 7584577.77 | 94.77% | 418422.23 | 80959.13 | 247888 | 640240 | 0 | 606766.2216 | 33473.7784 | 6476.7304 | Project completed | [13 empty] | 2006 | Non Investment
FIN | UNIDO | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 277 | A | O | I |  | 0 | 0 |  |  | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1751000 | 0 | 1751000 | 0 | 0 | FIN | [13 empty] | 2006 | NON-INV
COM | UNDP | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 278 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1751000 | 0 | 1751000 | 0 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
FIN | IBRD | Core unit budget (2007) |  | GLO | GLO | SEV | 50 | TAS | 279 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-11-01 | 2007-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1580000 | -17251 | 1562749 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of one MP event and completion of reports and responses. Two pamphlets completed for the 20th MP Anniversary. | [13 empty] | 2007 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Assessment of CTC phase-out in the chlo-alkali sector | Individual | GLO | GLO | PHA | 52 | TAS | 280 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-07-01 | 2008-09-30 |  | 2008-06-01 | 2008-07-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Study completed and presented to the 55th ExCom. | [13 empty] | 2007 | Non-INV | 0 | 0 | 0 | 0
ONG | UNEP | Study on challenges associated with halon banking in developing countries | Individual | GLO | GLO | HAL | 52 | TAS | 281 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-31 | 2009-07-31 |  |  | 40000 | 0 | 40000 | 36000 | 90% | 4000 | 0 | 4000 | 5200 | 0 | 4680 | 520 | 0 | Consultant collected and reviewed extensive data from halon banks in close cooperation with HTOC Co-Chairs. Some residual data collection still ongoing. Preliminary findings and draft recommendations presented to HTOC meeting in March 2009. Document being drafted. Final document expected by July 2009. | [13 empty] | 2007 | Non Investment
ONG | UNEP | MDI regional workshops/CAP | Individual | GLO | GLO | ARS | 52 | TAS | 282 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2008-07-31 | 2009-07-31 |  |  | 200000 | 0 | 200000 | 123101.5 | 61.55% | 76898.5 | 6759.91 | 76898.5 | 16000 | 0 | 9848.12 | 6151.88 | 540.7928 | LAC: Sub-Regional Workshop on Phasing-Out CFC based Metered Dose Inhalers (MDI) for Latin American and Spanish Speaking Caribbean countries was aimed to provide participants with practical information to promote national awareness raising MDI programmes with stakeholders as well as to identify and address barriers that could impede the transition to CFC free MDIs, from the point of view of the health authorities. Agenda was focused on: Non-CFC based MDI technology, experience exchange on national strategies to substitute CFC in the MDI and MOP/ExCom decisions. Two participants per country attended the workshop, one from NOU and another from the Health sector. Furthermore, 50 people from private and public national stakeholders of Argentina attended the workshop, which contributed to reach national consensus on MDI strategy and investment projects in the sector. Multilateral Fund Secretariat representative, Deputy Director of Ozone Secretariat, ROAP RNC, UNDP MP Regional Officer and MTOC experts joined the workshop leaded by ROLAC/CAP team. Sub-Regional Workshop on Phasing-Out CFC based Metered Dose Inhalers (MDI) for the English Speaking Caribbean was aimed to create the capacity of the ozone units to design and implement effective strategies, well-adapted to local conditions to address the MDI transition situation. 13 National Ozone Officers and Assistants from 14 countries of the Caribbean participated in this Networking activity carried out in city of Georgetown, Guyana. Two Officers from UNDP and the Deputy Director of Ozone Secretariat. 6 international and regional experts gave their presentations, and discussions were held on: Measured Doses Inhalers technology; Chronic Respiratory Disease, and MOP issues. ASP: UNEP, in cooperation with other Implementing Agencies of the Multilateral Fund, have brought together government officers from National Ozone Unit and Public Health department, industries, asthma/COPD associations, NGOs, select industry representatives and MTOC members as resource persons to share their valuable experiences and perspective during the Regional Workshop on Phasing-out CFC MDIs held on 13-15 March 2008 in Langkawi, Malaysia back to back with the joint SA and SEAP Network Meeting. During the workshop, the main challenges and barriers affecting industry from expedited conversion to CFC free alternatives to CFC MDIs were discussed. Key elements, which are essential for the preparation and implementation of CFC MDI transition strategy, were discussed and identified. Particularly, inputs were provided for countries without CFC MDI manufacturing industries on awareness and information exchange and regulations needed for fast track adoption of CFC free alternatives. The workshop also had discussions on the uncertainty in the supply of pharmaceutical grade CFC and management strategy for pharmaceutical-grade CFC during 2008-2010 and beyond. During the workshop, discussions among the participants in some sessions had led to introduction of “Langkawi Declaration on Public-private Partnership on Phasing-out CFC Metered Dose Inhalers”. ECA: The ECA network conducted a thematic meeting on MDI transition strategies on 25 March 2008 in Tirana, Albania, back-to-back with the annual ECA network meeting. The resource persons included national health sector representatives as well as bilateral partners. The meeting was preceded by the collection of data concerning the availability and status of market introduction of non-CFC MDIs in ECA network countries and the agenda included the following sessions: Introduction / MDI meetings in other regions / ExCom document 51/39 / MDI situation in selected countries / technology developments / transition strategies & regulatory aspects / MDI quick start transition strategy for non-producing countries / road map towards the development of transition strategies. Meeting documents, presentations and detailed meeting recommendations are available from the ECA website: http://fr1.estis.net/sites/ecanetwork/default.asp?site=ecanetwork&page_id=8CCA0773-632D-47CC-BBDE-99599B7A15DA. Based on the recommendations of the ECA network meeting, 4 countries received further support to conduct national MDI stakeholder consultations involving health sector representatives and patients associations as part of the ECA work programme 2008/2009." | [13 empty] | 2007 | Non Investment
ONG | UNEP | Integrated enforcement training under the Montreal Protocol through green customs initiative | Individual | GLO | GLO | SEV | 52 | TAS | 283 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 |  | 2010-06-01 | 2011-06-01 |  |  | 62000 | 0 | 62000 | 0 | 0% | 62000 | 10000 | 62000 | 8060 | 0 | 0 | 8060 | 1300 | Green Customs E-learning module with WCO underway, activities on collection of case studies and GCI video in preparation. Regional and national workshops were delayed due to lack of co-financing from oher GCI partners in 2008. GCI has now secured co-funding from Green Customs Partners and bilateral support outside the MLF of approximately $300,000 for 2009. A funding proposal will be submitted to the 59th Excom requesting further funds. | [13 empty] | 2007 | Non Investment
COM | UNEP | Compliance Assistance Programme: 2008 budget | Individual | GLO | GLO | SEV | 53 | TAS | 284 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-12-31 |  | 2008-12-01 |  | 8243090 | 0 | 8243090 | 7435746.1257 | 90.21% | 807343.8743 | 797021.3993 | 807343.8743 | 659447 | 0 | 594859.6901 | 64587.3099 | 63761.7119 | Project completed in December 2008 | [13 empty] | 2007 | Non Investment
COM | UNDP | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 285 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1803530 | 0 | 1803530 | 0 | 0 | Completed in 2008. | [13 empty] | 2007 | Non-Investment
FIN | IBRD | Core unit budget (2008) |  | GLO | GLO | SEV | 53 | TAS | 286 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  | 2008-11-01 | 2008-11-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1614900 | 0 | 1614900 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting the MP annual workshop for FIs and staff; reconvening the OORG (with 2 meetings held in 2008); an analytical piece on HCFC and related side-event; commissioning of a "foam decision tree," for HCFC alternatives; completion of reports and responses and providing required data and information needed for preparing ExCom documentation. | [13 empty] | 2007 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 287 | A | O | I |  | 0 | 0 |  |  | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 | 2008-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1803530 | 0 | 1803530 | 0 | 0 | FIN | [13 empty] | 2007 | NON-INV
CLO | UNIDO | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 288 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 |  | 2008-07-01 |  |  | 2008-09-01 | 390000 | -390000 | 0 | 0 |  | 0 | 0 |  | 29250 | -29250 | 0 | 0 | 0 | Project cancelled in Sep 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2008 | NON-INV
CLO | UNDP | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 289 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-11-01 | 257000 | -257000 | 0 | 0 |  | 0 | 0 | 0 | 19275 | -19275 | 0 | 0 | 0 | Canceled in 2008. Advance on HPMP-work was returned at the 56th ExCom meeting. | [13 empty] | 2008 | Investment
CLO | UNEP | Advance for preparation of HPMPs | RMP | GLO | GLO | PHA | 54 | PRP | 290 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-12-01 | 408000 | -408000 | 0 | 0 |  | 0 | 0 | 0 | 53040 | -53040 | 0 | 0 | 0 | Project closed | US$ 408,000 plus US$ 53,040 returned to ExCom 56 | [12 empty] | 2008
ONG | IBRD | Development of strategy/methodology for ODS disposal |  | GLO | GLO | DES | 55 | TAS | 291 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-11-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 250000 | 225000 | 22500 | 0 | 0 | 22500 | 22500 | Consultant selection process initiated in Aug 08. Selection process expected to be completed in early 2009 and contract signed in Mar 09. Study inception report expected in Mar 09 and preliminary draft to be ready by Jun 09. Steering committee to guide study and methodology development or compilation for eventual recommendation to the ExCom is to be convened in Apr 09. Cooperation with Sweden on its case study in Russia initiated in late 2008. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
ONG | UNEP | Compliance Assistance Programme: 2009 budget | Individual | GLO | GLO | SEV | 56 | TAS | 292 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-31 | 2009-12-31 |  |  | 8490000 | 0 | 8490000 | 0 | 0% | 8490000 | 0 | 8490000 | 679200 | 0 | 0 | 679200 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNIDO | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 293 | A | O | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2009-12-31 | 2009-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1857636 | 0 | 0 | 1857636 | 0 | - | [13 empty] | 2008 | NON-INV
ONG | IBRD | Core unit budget (2009) |  | GLO | GLO | SEV | 56 | TAS | 294 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-31 | 2009-12-31 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1663347 | 0 | 0 | 1663347 | 1663347 | Activities to include travel to MP-related meetings; support of core unit staff; hosting of the MP annual workshop for FIs and staff as well as the new OORG meeting; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
ONG | UNDP | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 295 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-01 | 2009-12-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1857636 | 0 | 0 | 1857636 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
ONG | Israel | International methyl bromide compliance assistance workshop | Individual | GLO | GLO | FUM | 56 | TAS | 296 | A | O | D |  | 0 |  | 0 |  | 2008-11-01 |  | 2009-02-01 |  |  |  | 101200 | 0 | 101200 | 0 | 0% | 101200 | 0 | 0 | 13156 | 0 | 0 | 13156 | 0 | Not provided. | [13 empty] | 2008 | Non-Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GRN | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-08-01 |  | 1999-10-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
FIN | UNEP | Creation of a National Ozone Unit | Individual | LAC | GRN | SEV | 30 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2003-06-01 | 2003-04-01 |  | 2006-08-01 | 2007-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Train the trainer programme for refrigeration service technicians | Individual | LAC | GRN | REF | 30 | TRA | 3 | A | O | I | CFC | 2.2 | 2.2 |  | 0 | 2000-03-01 | 2000-12-01 | 2000-10-01 |  | 2007-01-01 | 2008-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 | 0 | 6760 | 0 | 6760 | 0 | 0 | Project financially completed. | [5 empty] | 2002-06-02 | [7 empty] | 2000 | Non Investment
COM | UNEP | Implementation of the RMP: Training of custom officers, ODS inspectorate and Ozone Unit staff | Individual | LAC | GRN | REF | 30 | TRA | 4 | A | O | I | CFC | 1.5 | 1.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2007-01-01 |  | 36700 | 0 | 36700 | 22913 | 62.43% | 13787 | 0 | 13787 | 4771 | 0 | 2978.69 | 1792.31 | 0 | Project completed | [5 empty] | 2002-12-02 | [7 empty] | 2000 | Non Investment
FIN | UNDP | Implementation of the RMP: National recovery recycling project | RMP-Component | LAC | GRN | REF | 30 | TAS | 5 | A | O | I | CFC | 1.4 | 1.4 | 0 | 0 | 2000-03-01 | 2002-06-01 | 2001-10-01 |  | 2002-12-01 | 2003-11-01 | 33400 | 0 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4342 | 0 | 4342 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNEP | Institutional strengthening project | Individual | LAC | GRN | SEV | 44 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | GRN | REF | 46 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-09-01 |  | 15000 | 0 | 15000 | 14663 | 97.75% | 337 | 337.02 | 337 | 1950 | 0 | 1906.19 | 43.81 | 43.8126 | Project completed | [13 empty] | 2005 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | LAC | GRN | PHA | 49 | TAS | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2007-12-31 | 2009-12-31 |  |  | 37000 | 0 | 37000 | 28922.27 | 78.17% | 8077.73 | 127.68 | 8077.73 | 4810 | 0 | 3759.8951 | 1050.1049 | 16.5984 | Total of 157customs officers. Two senoir customs officers attended regional workshop on Customs Enforcement. One senior customs officer attended regional workshop on ODS Illegal trade enforcement. Funds are to be realocated to new agreement, following receipt of financial and terminal reports and approval by UNEP as funding agreement expired in 2007. | [13 empty] | 2006 | Non Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | GRN | PHA | 49 | INV | 10 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 |  | 2007-12-01 | 2009-07-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 16000 | 3600 | 0 | 0 | 3600 | 0 | Equipment procured under the TPMP. An error in the process led to a delay in the delivery of equipment. Training activities were carried out. Stickers for reconverted equipment developed and given to technicians. Expenditures will be reflected in 2009. | [13 empty] | 2006 | Investment | 3 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | GRN | SEV | 50 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | First disbursement made in July 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | GRN | PHA | 55 | TAS | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-31 | 2009-12-31 |  |  | 48000 | 0 | 48000 | 16538.1 | 34.45% | 31461.9 | 23063.84 | 31461.9 | 6240 | 0 | 2149.953 | 4090.047 | 2998.2992 | Funding agreement (SSFA) recently signed with the country. First payment made. National experts identified and contracted to provide technical assistance. | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GRN | PHA | 55 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions and further arrangements are being set. Planning preparatoy meeting planned for March of 2009. | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan (second tranche) | Multi-year | LAC | GRN | PHA | 55 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-07-01 | 2010-07-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 10000 | 4500 | 0 | 0 | 4500 | 0 | See GRN-10 | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | GUA | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-23 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 | 0 | 3900 | 390 | 4290 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | GUA | SEV | 08 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 25000 | -13641 | 11359 | 11359 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | GUA | SEV | 09 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 47000 | -13488 | 33512 | 33512 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening: Establishment of COGO | Individual | LAC | GUA | SEV | 10 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-12-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 | 0 | 22360 | 0 | 22360 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | GUA | SEV | 11 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 30000 | 257 | 30257 | 30257 | 100% | 0 | 0 | 0 | 3900 | 34 | 3934 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | GUA | SEV | 12 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 55000 | -47098 | 7902 | 7902 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industria Metalurgica Centroamericana S.A. (Imca) | Individual | LAC | GUA | REF | 15 | INV | 7 | A | O | I | CFC | 4 | 4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-07-01 | 2000-07-01 | 155017 | -5823 | 149194 | 149194 | 100% | 0 | 0 | 0 | 20152 | -757 | 19395 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Refrigeradores de Guatemala S.A. (Refrigua) | Individual | LAC | GUA | REF | 15 | INV | 8 | A | O | I | CFC | 24.4 | 24.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1996-10-01 | 1999-12-01 | 194866 | 0 | 194866 | 194866 | 100% | 0 | 0 | 0 | 25333 | 0 | 25333 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1994 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | GUA | REF | 18 | TAS | 9 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-12-01 | 2002-03-01 | 256780 | -19649 | 237131 | 237131 | 100% | 0 | 0 | 0 | 33381 | -2554 | 30827 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | USA | Refrigeration: mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | GUA | REF | 19 | DEM | 10 | A | O | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 1998-08-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. |  | 1995 | 1997-12-01
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | GUA | FOA | 21 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1997 | Investment
FIN | UNIDO | Project formulation of demonstraton project in the methyl bromide sector | Individual | LAC | GUA | FUM | 21 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-03-01 | 1997-08-01 |  | 1999-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | GUA | REF | 21 | TRA | 13 | A | O | I | CFC | 68.3 | 68.3 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2001-12-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | GUA | SEV | 22 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2000-05-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNIDO | Demonstration project: four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization, and low-dose chemicals in combination with an IPM system | Individual | LAC | GUA | FUM | 22 | DEM | 15 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-07-01 | 440000 | -57777 | 382223 | 382223 | 100% | 0 | 0 |  | 57200 | -7590 | 49610 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at four enterprises (Exea S.A., Productos American Vitas S.A., Termomecanica S.A., Unirefri S.A.) | Individual | LAC | GUA | REF | 23 | INV | 16 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2002-03-01 | 212000 | -24132 | 187868 | 187868 | 100% | 0 | 0 | 0 | 27560 | -3137 | 24423 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Construservicios, Aplitex, and Fiberglas & Plasticos | Individual | LAC | GUA | FOA | 23 | INV | 17 | A | O | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 128500 | -15778 | 112722 | 112722 | 100% | 0 | 0 | 0 | 16705 | -2051 | 14654 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNEP | Implementation of the RMP: Custom officers training programme | Individual | LAC | GUA | REF | 27 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2000-10-02 |  | 2002-11-01 | 2003-11-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 4420 | 0 | 4420 | 0 | 0 | Project financially completed. | [5 empty] | 2001-12-01 | [7 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Code of good practices in refrigeration | Individual | LAC | GUA | REF | 27 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-02 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [5 empty] | 2001-12-01 | [7 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Licensing system | Individual | LAC | GUA | REF | 27 | TAS | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-02 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNIDO | Project preparation for the phase out of 800 tonnes in the methyl bromide sector (melon) | Individual | LAC | GUA | FUM | 29 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 1999-11-01 | 2002-04-01 | 2000-12-01 |  | 2002-12-01 | 2003-12-01 | 45000 | -1164 | 43836 | 43836 | 100% | 0 | 0 |  | 5850 | -160 | 5690 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | LAC | GUA | SEV | 28 | INS | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-12-01 | 2003-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. |  |  |  |  | 2002-06-01 | [8 empty] | 1999 | Non Investment
ONG | UNEP | Implementation of the RMP: establishment of licensing system | Individual | LAC | GUA | REF | 35 | TAS | 23 | A | O | I | CFC | 19.2 | 0 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 | 2009-06-01 |  |  | 23200 | 0 | 23200 | 23200 | 100% | 0 | 0 | 0 | 3016 | 0 | 3016 | 0 | 0 | Electronic ODS link between Customs and Ministry of Environment set-up completed. An inter institutional board to review ODS legislation was established. | [13 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: alternatives to the use of CFC-12 in the refrigeration sector | Individual | LAC | GUA | REF | 35 | TAS | 24 | A | O | I | CFC | 47.9 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 | 2009-03-01 |  |  | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 | 0 | 7540 | 0 | 7540 | 0 | 0 | More than 200 refrigeration technicians trained in alternative refrigerants. 16 visits to refrigerant suppliers to check stock of refrigerants and corresponding documents of license issued. Negotiations carried out to nclude the Good practices and ODS alternative technology at the piensum of the refrigeration tehcnician school. | [13 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | GUA | REF | 35 | TAS | 25 | A | O | I | CFC | 26.3 | 0 | 0 | 0 | 2001-12-01 | 2007-11-01 | 2007-12-01 | 2009-06-01 |  |  | 31800 | 0 | 31800 | 3411 | 10.73% | 28389 | 28389 | 28389 | 4134 | 0 | 443.43 | 3690.57 | 3690.57 | Interim progress and financial reports for each of the RMP components prepared by NOU. | [13 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: establishment and enforcement of legislation | Individual | LAC | GUA | REF | 35 | TAS | 26 | A | O | I | CFC | 51.2 | 0 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 | 2009-06-01 |  |  | 62000 | 0 | 62000 | 57661 | 93% | 4339 | 4339 | 4339 | 8060 | 0 | 7495.93 | 564.07 | 564.07 | Bi-monthly meeting between NOO and counterpart in Custom Officer carried out to check ODS imports and licenses issued. | [13 empty] | 2001 | Non Investment
ONG | UNEP | Implementation of the RMP: customs training programme | Individual | LAC | GUA | REF | 35 | TRA | 27 | A | O | I | CFC | 46.3 | 0 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2007-12-01 | 2009-03-01 |  |  | 56000 | 0 | 56000 | 56000 | 100% | 0 | 0 | 0 | 7280 | 0 | 7280 | 0 | 0 | 2 Refreshing Workshops on ODS control carried out for Custom Officers and 1 workshop for Officer of the Minister of Environment. A total of 82 officers trained in two days workshop. | [13 empty] | 2001 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | GUA | SEV | 35 | INS | 28 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-09-01 | 2004-01-01 |  | 2004-03-01 | 2007-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
COM | UNIDO | National phase out of methyl bromide | Individual | LAC | GUA | FUM | 38 | INV | 29 | A | O | I | MBR | 502.6 | 502.6 |  |  | 2002-11-01 | 2003-03-01 | 2008-11-01 |  | 2008-12-01 |  | 3257377 | 0 | 3257377 | 3058976 | 93.91% | 198401 | 68552 | 68000 | 368311 | 0 | 346487 | 21824 | 7541 | Agreement with melon farmers was reached for the implementation of the remaining funds during 2008. Continued with equipment procurement, installation and training. Project completed in Dec 2008. | Official data reported in 2008 was 173 ODP, less than the agreed data. | [12 empty] | 2002 | INV
ONG | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | LAC | GUA | SEV | 43 | INS | 30 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 | 2009-06-01 |  |  | 62400 | 0 | 62400 | 48606.24 | 77.89% | 13793.76 | 0 | 13793.76 | 0 | 0 | 0 | 0 | 0 | The NOU allowed the Goverment to manage all the activities for implementation of the Montreal Protocol in Guatemala, such as the timely and permanent monitoring with the country’s obligations, answering Secretariats queries and preparing ODS data report. NOU manages the ODS license system and attends international and regional Montreal Protocol meetings and workshops. NOU leaded the preparation and implementation of all approved projects under the Multilateral Fund, i.e. RMP, TPMP, MB phase-out. NOU currently preparing terminal progress and financial reports for undertaking ISP phase VI. | [13 empty] | 2004 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | GUA | PHA | 50 | PRP | 31 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-03-01 | 2007-11-01 |  | 2008-11-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2008. TPMP was successfully presented and approved to ExCom 56 | [13 empty] | 2006 | Investment
ONG | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUA | PHA | 50 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 | 2009-06-01 |  |  | 15000 | 0 | 15000 | 10000 | 66.67% | 5000 | 5000 | 5000 | 1950 | 0 | 1300 | 650 | 650 | TPMP resulting from this activity was approved at 56 ExCom meeting. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | LAC | GUA | SEV | 53 | INS | 33 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 |  |  | 124800 | 0 | 124800 | 0 | 0% | 124800 | 124800 | 124800 | 0 | 0 | 0 | 0 | 0 | Funding agreement (SSFA) has been signed in December 2008 and conditions are met for processing first disbursement. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | TAS | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2008-11-30 | 2009-11-30 |  |  | 33000 | 0 | 33000 | 0 | 0% | 33000 | 0 | 33000 | 4290 | 0 | 0 | 4290 | 0 | Project recently approved. Agreement for project implementation has been recently signed and first fund disbursement already processed. The country is currently producing A7 data report for 2008 and is updated with earlier reports. | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | INV | 35 | N | O | I | CFC | 5.9 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-01 | 2010-11-01 |  |  | 249000 | 0 | 249000 | 0 | 0% | 249000 | 0 | 49800 | 22410 | 0 | 0 | 22410 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | GUI | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-10-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | GUI | SEV | 18 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | GUI | REF | 21 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 2000-01-01 | 2001-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. |  |  |  | 1999-05-01 | [9 empty] | 1997 | Non Investment
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | AFR | GUI | FOA | 21 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -8983 | 11017 | 11017 | 100% | 0 | 0 |  | 2600 | -1170 | 1430 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | GUI | REF | 22 | TAS | 5 | A | O | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-01 | 80780 | 0 | 80780 | 80780 | 100% | 0 | 0 |  | 10501 | 0 | 10501 | 0 | 0 | FIN
FIN | UNEP | Implementation of the RMP: Training for customs officers | Individual | AFR | GUI | REF | 30 | TRA | 6 | A | O | I | CFC | 6.7 | 6.7 | 0 | 0 | 2000-03-01 | 2001-03-01 | 2001-04-01 |  | 2003-03-01 | 2007-06-01 | 42500 | -23512 | 18988 | 18988 | 100% | 0 | 0 | 0 | 5525 | -3057 | 2468.44 | -0.44 | 0 | Project financially completed. | $ 23,512 plus $ 3,057 PSC returned ExCom 46 |  |  |  |  | 2003-03-03 | [7 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Train the trainer programme in the refrigeration servicing sector | Individual | AFR | GUI | REF | 30 | TRA | 7 | A | O | I | CFC | 10.5 | 10.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2002-09-01 | 2003-09-01 | 66500 | 0 | 66500 | 66500 | 100% | 0 | 0 | 0 | 8645 | 0 | 8645 | 0 | 0 | Project financially completed. | [5 empty] | 2002-12-02 | [7 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | GUI | SEV | 28 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-11-01 | 2001-12-12 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333.29 | 0 | 4333.29 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | GUI | SEV | 34 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 | 0 | 4333.29 | 0 | 4333.29 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNEP | Preparation of a country programme/RMP | RMP | AFR | GUI | REF | 39 | PRP | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2004-11-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | GUI | SEV | 41 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333.25 | 100% | -0.25 | 0 | -0.25 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment components) | Individual | AFR | GUI | REF | 42 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
COM | UNEP | Implementation of the RMP: customs officers training in monitoring and control of ODS (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 12 | A | O | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-04-01 |  | 2006-12-01 |  | 25000 | 0 | 25000 | 13006 | 52.02% | 11994 | 11993.84 | 11994 | 3250 | 0 | 1690.78 | 1559.22 | 1559.1992 | Project completed | [13 empty] | 2005 | Non Investment
FIN | UNEP | Implementation of the RMP: training programme for refrigeration technicians (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 13 | A | O | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-10-01 |  | 2006-12-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNEP | Implementation of the RMP: monitoring the activities of the RMP | Individual | AFR | GUI | REF | 45 | TAS | 14 | A | O | I | CFC | 3.1 | 3.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2005 | Non Investment
COM | UNDP | Implementation of the RMP: recovery and recycling programme (phase II) | RMP-Component | AFR | GUI | REF | 45 | TAS | 15 | N | O | I | CFC | 7.9 | 7.9 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2007-04-01 |  | 2007-10-01 |  | 49890 | 0 | 49890 | 43879 | 87.95% | 6011 | 0 | 4808.8 | 4490 | 0 | 3949.022 | 540.978 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GUI | PHA | 49 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-31 |  | 2008-07-31 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed in July 2008 after submission of TPMP document | [13 empty] | 2006 | Non Investment
COM | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | GUI | PHA | 49 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2008-06-01 |  | 15000 | 0 | 15000 | 12112 | 80.75% | 2888 | -28 | 1 | 1125 | 0 | 908 | 217 | -2 | Project completed in Jun 2008. | [13 empty] | 2006 | NON-INV
ONG | UNEP | Extension of the institutional strengthening project: (phase V) | Individual | AFR | GUI | SEV | 50 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NOU Coordinated the enforcement of ODS regulations, complete the remaining RMP activities, coordinated the preparation and implementation of a TPMP, coordinated awareness raising activities through various media, and reported ODS Consumption data. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-12-31 | 2009-12-31 |  |  | 74000 | 0 | 74000 | 50000 | 67.57% | 24000 | 20000 | 24000 | 9620 | 0 | 6500 | 3120 | 2600 | MoU for the implementation of the TPMP signed by the country in October 2008 and First payment done in November 2008. | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | INV | 20 | A | O | I | CFC | 1.4 | 0 |  |  | 2008-07-01 |  | 2009-12-31 | 2009-12-01 |  |  | 140000 | 0 | 140000 | 0 | 0% | 140000 | 0 | 30000 | 12600 | 0 | 0 | 12600 | 0 | Technical specification for equipment purchase has been prepared and once UNIDO received the confirmation of NOU the bidding will start. The second tranche is expected to be submitted in 2009. | [13 empty] | 2008 | INV | 2.9 | 2.9 |  |  | Not yet confirmed | N/A | N/A
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GUI | PHA | 56 | PRP | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 20000 | 85000 | 11050 | 0 | 0 | 11050 | 2600 | Project newly approved | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project: (phase VI) | Individual | AFR | GUI | SEV | 56 | INS | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-31 | 2010-12-31 |  |  | 60000 | 0 | 60000 | 13452 | 22.42% | 46548 | 0 | 46548 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | GUY | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-02-26 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 5200 | -650 | 4550 | 0 | 0 | Project financially completed. | $ 5,000 plus $ 650 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNIDO | ODS phase out at a domestic refrigeration plant (Guyana Refrigeration Ltd.) | Individual | LAC | GUY | REF | 17 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1995-09-01 |  | 1998-01-01 | 1999-08-01 | 15000 | -659 | 14341 | 14341 | 100% | 0 | 0 |  | 1950 | -89 | 1861 | 0 | 0 | FIN
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | GUY | REF | 21 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-12-01 | 30000 | -4000 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3900 | -520 | 3380 | 0 | 0 | Project financially completed. | $ 4,000 plus $ 520 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Creation of the National Ozone Action Unit | Individual | LAC | GUY | SEV | 23 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 2000-11-01 |  | 2001-08-01 | 2007-03-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 | 0 | 8450 | -205 | 8450 | -205 | 0 | Project financially completed. | $ 0 plus $ 205 returned to ExCom 49 | [12 empty] | 1997 | Non Investment
FIN | UNIDO | Phasing out ODS at Guyana Refrigerator Ltd., Guyana (GRL) | Individual | LAC | GUY | REF | 23 | INV | 5 | A | O | I | CFC | 7.2 | 7.2 |  |  | 1997-11-01 | 1998-08-01 | 1999-06-01 |  | 2001-04-01 | 2002-09-01 | 461000 | 0 | 461000 | 461000 | 100% | 0 | 0 |  | 59930 | -6 | 59924 | 0 | 0 | FIN
FIN | UNEP | Implementation of the refrigerant management plan: Training of trainers for good refrigeration servicing practices | Individual | LAC | GUY | REF | 23 | TRA | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 2001-04-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training on monitoring and control of ODS and ODS using equipment | Individual | LAC | GUY | REF | 23 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-06-01 |  | 2003-08-01 | 2003-09-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 | 0 | 2080 | 0 | 2080 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | Canada | Implementation of the RMP: national recovery and recycling programme | RMP | LAC | GUY | REF | 23 | TAS | 8 | A | O | I | CFC | 6.5 |  | 0 |  | 1997-11-01 | 1998-04-01 | 2000-12-01 |  | 2003-05-01 | 2003-05-01 | 73450 | 0 | 73450 | 73450 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completion Report submitted. |  | 1997 | [11 empty] | 1997 | Non-Inv.
COM | UNEP | Renewal of institutional strengthening project | Individual | LAC | GUY | SEV | 34 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2005-02-01 | 2003-08-01 |  | 2008-09-01 |  | 43400 | 0 | 43400 | 38896.64 | 89.62% | 4503.36 | 0 | 4503.36 | 5642 | 0 | 5056.5632 | 585.4368 | 0 | Project completed in Sept 2008 | [13 empty] | 2001 | Non Investment
COM | UNEP | Implementation of the RMP: assistance for implementation of additional activities in the RMP | Individual | LAC | GUY | REF | 35 | TAS | 10 | A | O | I | CFC | 45.2 | 45.2 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 |  | 2008-01-01 |  | 65500 | 0 | 65500 | 65500 | 100% | 0 | 0 | 0 | 8515 | 0 | 8515 | 0 | 0 | Project completed in January 2008 | [13 empty] | 2001 | Non Investment
ONG | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUY | PHA | 48 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 | 2009-06-01 |  |  | 15000 | 0 | 15000 | 14935.83 | 99.57% | 64.17 | 63.84 | 64.17 | 1950 | 0 | 1941.6579 | 8.3421 | 8.2992 | Licensing system completed. Ratification of Beijing completed. Country conducted one training for customs officials. Institutionalised Training of technicians at the Government technical school. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | GUY | PHA | 48 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 |  | 15000 | 0 | 15000 | 14988 | 99.92% | 12 | 0 | 12 | 1125 | 0 | 1124.1 | 0.9 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | GUY | SEV | 48 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2008-04-01 | 2009-05-01 |  |  | 56333 | 0 | 56333 | 45066.4 | 80% | 11266.6 | 11266.6 | 11266.6 | 0 | 0 | 0 | 0 | 0 | The IS project has assisted the Ozone unit in the implementation of various outreach activiteis such as a number of exhibitons through out the country, the participation in television shows, publication of articles in newspapers and visits to secondary schools. The local association of refrigeration technicians (GARVA) has assisted the NOU by promoting the creation of incentives suchas duty exemptions and reductions for ozone-friendly technologies, 2007 ODS reports were submitted to UNEP and OS. Joint work between GARVA and customs agency is undergoing to execute training programmes accross the country. Ratification of the Beijing amendment took place in June 2008. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | GUY | PHA | 53 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2009-03-01 | 2009-12-01 |  |  | 58000 | 0 | 58000 | 34800 | 60% | 23200 | 23200 | 23200 | 7540 | 0 | 4524 | 3016 | 3016 | Achievements under this agreement include: 1) Sustained management for compliance for Annex A Group I CFCs, maintaining zero imports 2) Successful coordination of the implementation of the TPMP along with national stakeholders and UNEP and UNDP as implementing agencies 3) Various awareness-building activities in schools, beaches and general public, incorporating climate change as vehicle of extending the outreach programmes and activities 4) Sustained communication with key stakeholders for the tourism investment sectors thereby ensuring zero imports of Methyl Bromide and including for Plant Quarantine and pre-shipment. This is also done for Halons. 5) Began process of sensitising national stakeholders on HCFC phase out. 6)New assistant NOO recruited. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | GUY | PHA | 53 | INV | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 | 2010-01-01 |  |  | 124000 | 0 | 124000 | 1541 | 1.243% | 122459 | 0 | 24491.8 | 11160 | 0 | 138.69 | 11021.31 | 0 | Limited progress. Project Documents was signed and Project Coordinator was hired. In the process of preparing training activities and carrying out the needs assessment for the procurement of tools and equipment. | [13 empty] | 2007 | Investment | 8 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GUY | PHA | 55 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions for project implementation and further arrangements are being settled to formalize funding agreement (SSFA). First regional planning meeting set for March 2009. | [13 empty] | 2008
FIN | UNEP | Preparation of country programme | Individual | LAC | HAI | SEV | 32 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-04-01 |  | 2003-07-01 | 2005-06-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 | 0 | 7800 | -3770 | 4030 | 0 | 0 | Project financially completed. | $ 9,000 plus $1,170 PSC returned ExCom 44 $ 20,000 plus $ 2,600 PSC retuned ExCom 46 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | HAI | REF | 36 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | HAI | SEV | 38 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-07-01 | 2003-12-01 |  | 2004-08-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
ONG | UNDP | Implementation of the refrigerant management plan: recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | HAI | REF | 39 | TAS | 4 | A | O | I | CFC | 88.6 | 33 | 0 | 0 | 2003-04-01 | 2007-04-01 | 2006-04-01 | 2010-01-01 |  |  | 220256 | 0 | 220256 | 36433 | 16.54% | 183823 | 0 | 36764.6 | 19823 | 0 | 3278.9634 | 16544.0366 | 0 | International and local consultants have been hired for the implementation of the revised RMP update in Haiti. International Expert mission was programmed twice in 2008, but had to be cancelled in the last moment. Training activities and procurement of basic tools for technicians in informal sector is expected to begin in early 2009. | [13 empty] | 2003 | Investment
COM | UNEP | Implementation of the refrigerant management plan: train the technicians on good practices in refrigeration | Individual | LAC | HAI | REF | 39 | TRA | 5 | A | O | I | CFC | 29.9 | 29.9 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2008-12-01 |  | 74200 | 0 | 74200 | 74200 | 100% | 0 | 0 | 0 | 9646 | 0 | 9646 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2003 | Non Investment
ONG | UNDP | Implementation of the refrigerant management plan: monitoring the activities in the RMP | RMP-Component | LAC | HAI | REF | 39 | TAS | 6 | N | O | I | CFC | 11.8 | 8 | 0 | 0 | 2003-04-01 | 2008-02-01 | 2006-04-01 | 2010-01-01 |  |  | 29400 | 0 | 29400 | 12029 | 40.91% | 17371 | 0 | 3474.2 | 2646 | 0 | 1082.61 | 1563.39 | 0 | Local Consultant hired to support the implementation of activities under the R&R component in the RMP update. | [13 empty] | 2003 | Non-Investment
ONG | UNEP | Implementation of the refrigerant management plan: training for customs officers | Individual | LAC | HAI | REF | 39 | TRA | 7 | A | O | I | CFC | 13.3 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-04-01 | 2009-12-01 |  |  | 33100 | 0 | 33100 | 19307.2 | 58.33% | 13792.8 | 0 | 13792.8 | 4303 | 0 | 2509.936 | 1793.064 | 0 | Total of 157 customs officers. Two senior customs officers attended regional workshop on Customs Enforcement. One senior customs officer attended regional workshop on ODS Illegal trade enforcement. Funds are to be realocated to new agreement, following receipt of financial and terminal reports and approval by UNEP as funding agreement expired in 2007. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase I, years 2 and 3) | Individual | LAC | HAI | SEV | 43 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-09-01 | 2008-12-01 | 100000 | 0 | 100000 | 99999.75 | 100% | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | HAI | SEV | 50 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 | 2009-03-01 |  |  | 100000 | 0 | 100000 | 80000 | 80% | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | The country is in the process of producing first progress report, which is expected for 2nd quarter 2009. | [13 empty] | 2006 | Non Investment
COM | UNEP | Sectoral phase-out programme: Establishing a halon management plan | Individual | LAC | HAI | HAL | 50 | TAS | 10 | A | O | I | Halon | 1.5 | 1.5 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2009-11-01 |  | 2008-11-01 |  | 25000 | 0 | 25000 | 16000 | 64% | 9000 | 0 | 9000 | 3250 | 0 | 2080 | 1170 | 0 | Project completed in November 2008. National report received and approved by UNEP in November of 2008. Terminal and financial reports are being prepared and expected for 2009 2nd quarter. | [13 empty] | 2006 | Non Investment
ONG | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | HAI | PHA | 54 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-01 | 2009-07-01 |  |  | 15000 | 0 | 15000 | 4992 | 33.28% | 10008 | 6500 | 10008 | 1125 | 0 | 374.4 | 750.6 | 487.5 | First mission of International expert to Haiti in December 2008. Return visit expected in Apr 09. TPMP is expected to be submitted for the consideration of ExCom 58. | [13 empty] | 2008 | Investment
ONG | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | HAI | PHA | 54 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-31 | 2009-07-31 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 12000 | 15000 | 1950 | 0 | 0 | 1950 | 1560 | TPMP resulting from this project will be submitted to 58th ExCom meeting. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | HON | SEV | 13 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-28 | 1995-10-01 |  | 1996-06-01 | 1999-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit Cell for the institutional strengthening programme | Individual | LAC | HON | SEV | 20 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1999-10-01 |  | 2001-06-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | [10 empty] | 1996 | Non Investment
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | HON | FOA | 21 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1998-04-01 | 1997-05-01 |  | 2000-12-01 | 2001-09-01 | 30000 | -11403 | 18597 | 18597 | 100% | 0 | 0 |  | 3900 | -1486 | 2414 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | HON | REF | 24 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-11-01 | 2000-07-01 | 30000 | -7251 | 22749 | 22749 | 100% | 0 | 0 |  | 3900 | -947 | 2953 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | LAC | HON | REF | 28 | TRA | 5 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2002-04-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 38250 | 0 | 38250 | 38250 | 100% | 0 | 0 |  | 4973 | 0 | 4973 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | LAC | HON | REF | 28 | TRA | 6 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | LAC | HON | REF | 28 | TAS | 7 | A | O | I | CFC | 14.2 | 14.2 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 245900 | -951 | 244949 | 244949 | 100% | 0 | 0 |  | 31967 | -174 | 31793 | 0 | 0 | FIN | [5 empty] | 2003-06-01
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | HON | SEV | 32 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-05-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | LAC | HON | FUM | 33 | PRP | 9 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-03-01 | 2002-04-01 |  | 2002-11-01 | 2003-05-01 | 30000 | -482 | 29518 | 29518 | 100% | 0 | 0 |  | 3900 | -69 | 3831 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Phase-out of methyl bromide in melon and banana production sector and tobacco seedling | Individual | LAC | HON | FUM | 37 | INV | 10 | A | O | I | MBR | 213 | 213 |  |  | 2002-07-01 | 2002-11-01 | 2008-12-01 |  | 2006-12-01 | 2007-09-01 | 1977454 | -6 | 1977448 | 1977448 | 100% | 0 | 0 |  | 227519 | 0 | 227519 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2002 | INV
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | HON | SEV | 40 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-07-01 | 2005-07-01 |  | 2005-07-01 | 2007-02-01 | 57200 | -1 | 57199 | 57199 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 1 returned to ExCom 51 | [12 empty] | 2003 | Non Investment
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | HON | REF | 41 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2008-12-01 | 15000 | 0 | 15000 | 14371.92 | 95.81% | 628.08 | 0 | 0 | 1950 | 0 | 1868.3496 | 81.6504 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 2003 | Non Investment
FIN | UNDP | Preparation of the RMP update proposal | RMP-Component | LAC | HON | REF | 41 | PRP | 13 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-09-01 | 15000 | 0 | 15000 | 13000 | 86.67% | 2000 | 0 | 0 | 1125 | 0 | 975 | 150 | 0 | Completed in 2005. Financially Completed in 2008. | [13 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance programme for the promotion of good practices and recovery and recycling | RMP-Component | LAC | HON | REF | 44 | TAS | 15 | N | O | I | CFC | 138.6 | 101 | 0 | 0 | 2004-12-01 | 2007-11-01 | 2007-12-01 | 2009-11-01 |  |  | 150000 | 0 | 150000 | 108946 | 72.63% | 41054 | 0 | 16421.6 | 13500 | 0 | 9805.14 | 3694.86 | 0 | Equipment successfully delivered to beneficiary workshops. This included training to the beneficiaries. In the process of procuring spare parts for existing and new equipment. Additional equipment / spares awaited for in 2009. | [13 empty] | 2004 | Investment
ONG | UNEP | Implementation of the RMP: programme for certification and licensing of refrigeration technicians | Individual | LAC | HON | REF | 44 | TRA | 16 | A | O | I | CFC | 86.9 | 0 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2007-12-01 | 2009-06-01 |  |  | 94000 | 0 | 94000 | 79400 | 84.47% | 14600 | 14600 | 14600 | 12220 | 0 | 10322 | 1898 | 1898 | Internal changes within the training institute (INFOP) have derived in unexpected delays. Consequently a request for the MOU's extension has been agreed. Training in the southern regions of the country has been implemented and currently reaching a total of 960 technicians certified. Further courses will take place in the cities of Trujillo, Tela and Olanchito, reaching a total of 1200 technicians trained. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: programme for prevention of illegal ODS trade | Individual | LAC | HON | REF | 44 | TAS | 17 | A | O | I | CFC | 21.3 | 0 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 | 2009-06-01 |  |  | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 | 0 | 2990 | 0 | 2990 | 0 | 0 | Custom training refreshing courses are part of the agreement with INFOP. Administrative delays inside the training institution have forced the counterpart to reprogramme trainings on illegal trade in the main cities of the country. UNEP continues to encourage project implementation and assists country by providing information through its networks and e-fora focused on illegal trade prevention. NOU continues to monitor and assist customs check-points already identfied as main spots for illegal CFC trade. Notwithstanding, recent confiscations have taken place in the cities of Ceiba and Trujillo, places where this kind of operations was inexistent, thus reflecting the change in strategies followed by companies attempting to avoid customs controls. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP: programme for permanent monitoring of the RMP | Individual | LAC | HON | REF | 44 | TAS | 18 | A | O | I | CFC | 35.1 | 0 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 | 2009-06-01 |  |  | 38000 | 0 | 38000 | 30000 | 78.95% | 8000 | 0 | 8000 | 4940 | 0 | 3900 | 1040 | 0 | With regards to monitoring and follow up of the network of recycling and recovery (R&R), NOU visited the 95% of 120 technicians and workshops belonging to such Network. Interim progress and financial reports for each of the RMP components received. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | HON | SEV | 45 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-05-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | HON | SEV | 50 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 | 2009-06-01 |  |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | Through the IS project the NOU has gained support among national stakeholders and other government institutions. Important achievements are the ratification of amendments under the Montreal Protocol, the establishment of strategic alliances with key government institutions like the Special Environment Prosecution Agency and the Border Police for complying with the policies regulating Ozone Depleting Substances (ODS), import controls and the prohibition of imports of ODS-based equipment. Furthermore, they have fostered public awareness in the country by including the international ozone day celebration within the environmental dates to celebrate in the country, as well as promoting the ozone protection issue at education centers with the support of the private sector. Finally, Honduras is in compliance with their commitments under the Montreal Protocol according to the MB Action Plan approved by MOP 16 and Montreal Protocol Annex A and B phase-out goals. NOU is in charge of overall design of Montreal Protocol implementation at country level, attending international and regional meetings, preparing ODS reports and preparing answers to Secretariats and Implementing Agencies | [13 empty] | 2006 | Non Investment
FIN | UNIDO | National methyl bromide phase-out plan, phase II (first tranche) | Multi-Year | LAC | HON | FUM | 50 | INV | 21 | A | O | I | MBR | 31.8 | 31.8 |  |  | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-09-01 | 2008-12-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 45000 | 0 | 45000 | 0 | 0 | The tranche was completed and funding request with a detailed report for the third tranche is being submitted to the 56th ExCom. The second tranche is also almost fully implemented. Project completed in Sep 2008. Financial completion in Dec 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2006 | INV | 295.8 | 295.8 |  |  | Yes | N/A | N/A
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 22 | A | O | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-09-01 | 2008-09-01 | 15000 | -95 | 14905 | 14905 | 100% | 0 | 0 |  | 1125 | -7 | 1118 | 0 | 0 | Project completed in Sep 2008. Financial completion in Sep 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2007 | NON-INV
COM | UNEP | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 |  | 15000 | 0 | 15000 | 11500 | 76.67% | 3500 | 1000 | 3500 | 1950 | 0 | 1495 | 455 | 130 | Project completed in March 2008. Disbursements of funds available at country level per submission of progress and finance reports. TPMP project document was submitted to MFS and approved at the 55th ExCom meeting. | [13 empty] | 2007 | Non Investment
ONG | UNIDO | National methyl bromide phase-out plan, phase II (second tranche) | Multi-Year | LAC | HON | FUM | 53 | INV | 24 | A | O | I | MBR | 47.5 | 47.5 |  |  | 2007-11-01 | 2007-12-01 | 2008-11-30 | 2009-09-01 |  |  | 800000 | 0 | 800000 | 444026 | 55.5% | 355974 | 250263 | 355900 | 60000 | 0 | 33302 | 26698 | 18770 | First tranche has been completed. The second tranche is almost completed. A second set of equipment for grafting (including a new set of trays) and a laboratory was purchased for Suragroh. A laboratory for Excosur and Agrolibano was also purchased. A equipment for bioantagonist production for Agrolibano. All the equipment has been installed and commissioned, the production cycle started and the equipment is fully operational. The project is planned to be completed in Sep 2009. A total of 47.5 tonnes were eliminated. | [13 empty] | 2007 | INV | 255 | 214.2 |  |  | Yes | N/A | N/A
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | HON | PHA | 55 | PRP | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-07-31 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 10000 | 35000 | 4550 | 0 | 0 | 4550 | 1300 | Preliminary discussions for HCFC survey, identification of country needs and further arrangements are being set. Funding agreement (SSAF) currently being negotiated with the country. | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | INV | 26 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-12-31 | 2009-12-01 |  |  | 301000 | 0 | 301000 | 712 | 0.2365% | 300288 | 0 | 250000 | 22575 | 0 | 53 | 22522 | 0 | The project is being implemented with two different approaches. On one side, an experienced national consultant is working on the searching of the remaining CFC consumption and providing alternatives for the phase out. On the other hand, the technical institution is being trained in the drop in with hydrocarbon which will be implemented as core of the project, recovering the CFC and feeding the R&R system. The project is expected to be completed in December 2009. | [13 empty] | 2008 | INV | 39.7 | 23.4 |  |  | Yes | N/A | N/A
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | TAS | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 | 2009-12-31 |  |  | 146000 | 0 | 146000 | 0 | 0% | 146000 | 105000 | 146000 | 18980 | 0 | 0 | 18980 | 13650 | Funding agreement (SSFA) signed in December 2008. A mission to the country was carried out by UNEP and UNIDO officers in order to define the first POA of the project. | [13 empty] | 2008
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | HON | PHA | 55 | PRP | 28 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 115000 | 0 | 115000 | 3192 | 2.776% | 111808 | 862 | 90000 | 8625 | 0 | 239 | 8386 | 65 | The survey of HCFC is being carried out by a national institution with the coordination of NOU. An international consultant has been contracted for the preparation of the project document. The project is planned to be submitted to the first ExCom in 2010. | The consultant is leading the preparation of the HPMP, guiding the survey and the NOU in legislation and other issues. This consultant is expected to prepare the final document. The preparation is a team work and the consultant is leading the team. The initial workshop will take place in June. The NOU is working on the legislation with the support of another consultant. | [12 empty] | 2008 | NON-INV
ONG | UNIDO | National methyl bromide phase-out plan, phase II (third tranche) | Multi-Year | LAC | HON | FUM | 56 | INV | 29 | A | O | I | MBR | 23.9 | 0 |  |  | 2008-11-01 |  | 2009-11-30 | 2010-07-01 |  |  | 300000 | 0 | 300000 | 0 | 0% | 300000 | 0 | 150000 | 22500 | 0 | 0 | 22500 | 0 | The implementation activities under this tranche focusing on training components will continue in 2009. | [13 empty] | 2008 | INV | 207.5 | 181.8 |  |  | Yes | N/A | N/A
FIN | UNDP | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 54000 | -12931 | 41069 | 41069 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation advance I (1993) |  | ASP | IDS | SEV | 09 | PRP | 3 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. 14 subproject proposals were prepared. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | IDS | SEV | 09 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 206000 | 1805 | 207805 | 207805 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection and Ozone Depleting Substances Phase-out Unit | Individual | ASP | IDS | SEV | 10 | INS | 5 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 1997-06-01 | 2003-04-01 | 314780 | 0 | 314780 | 314780 | 100% | 0 | 0 | 0 | 40921 | 0 | 40921 | 0 | 0 | Completed in 1997. Financially completed in 2003. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 11 | PRP | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1994-11-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | IBRD | Elimination of CFC-11/12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Tulus Bakti Sempurna | Individual | ASP | IDS | FOA | 11 | INV | 7 | N | O | I | CFC | 95 | 95 | 0 | 0 | 1993-11-01 | 1997-01-01 | 1994-11-01 |  | 1998-09-01 | 1998-12-01 | 416000 | -22725 | 393275 | 393275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Intitri Muliatama | Individual | ASP | IDS | FOA | 11 | INV | 8 | N | O | I | CFC | 119 | 119 | 0 | 0 | 1993-11-01 | 1996-12-01 | 1994-11-01 |  | 1998-09-01 | 1998-09-01 | 387000 | -62963 | 324037 | 324037 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Dasa Windu Agung | Individual | ASP | IDS | FOA | 11 | INV | 9 | N | O | I | CFC | 122 | 122 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1995-04-01 |  | 1998-08-01 | 1998-08-01 | 1733000 | 0 | 1733000 | 1733000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Run commercially. Technical audit had been completed and equipment disposal had been carried out. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Safety and technical programme to assist manufacturers of hydrocarbon propelled aerosol products | Individual | ASP | IDS | ARS | 11 | TAS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-07-01 | 1995-11-01 |  | 1998-11-01 | 1998-11-01 | 238000 | -18915 | 219085 | 219085 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities on Work program had been completed. Technical audit has been carried out. Draft PCR has been submitted. Remaining grant returned to trust fund. Project completed and closed. 3% agency fee incl. |  |  | 1997-06-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance programme for small CFC users in the flexible polyurethane foam sector | Individual | ASP | IDS | FOA | 11 | TAS | 11 | N | O | I | CFC | 100 | 286 | 0 | 0 | 1993-11-01 | 1996-11-01 | 1995-11-01 |  | 1998-05-01 | 1998-05-01 | 1600000 | -1987 | 1598013 | 1598013 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project technically and financial completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Foamindo Industri Uretan | Individual | ASP | IDS | FOA | 11 | INV | 12 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1993-11-01 | 1998-01-01 | 1994-11-01 |  | 2002-04-01 | 2002-04-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in Apr. 02. Draft PCR submitted to WB for review. |  |  | 1997-12-01 |  | 2000-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Completion of processing of investment projects approved at the 11th ExCom Meeting |  | ASP | IDS | SEV | 12 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 128899 | 43396 | 172295 | 172295 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation and processing complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IDS | SEV | 12 | TRA | 14 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-07-01 | 1995-03-01 |  | 1998-08-01 | 1998-08-01 | 50000 | -701 | 49299 | 49299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TA Uppindo project is closed. PCR submitted. 3% agency fee incl. |  |  | 1997-12-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IDS | SEV | 12 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-30 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 117312 | -81569 | 35743 | 35743 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Erlangga Trimanunggal Kusumah | Individual | ASP | IDS | FOA | 13 | INV | 16 | N | O | I | CFC | 100 | 100 | 0 | 0 | 1994-07-01 | 1997-10-01 | 1995-07-01 |  | 2002-04-01 | 2002-04-01 | 379000 | 0 | 379000 | 379000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project was completed in April 2002. Draft PCR has been submitted to WB for review. |  |  | 1997-12-01 |  | 2000-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out investment project preparation (1994) |  | ASP | IDS | SEV | 13 | PRP | 17 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-08 | 1996-08-01 |  | 1996-08-01 | 1996-08-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Royal Abadi Sejahtera | Individual | ASP | IDS | FOA | 13 | INV | 18 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-06-01 | 1997-06-01 | 237500 | -3846 | 233654 | 233654 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Positive Foam Industry | Individual | ASP | IDS | FOA | 15 | INV | 19 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1994-12-01 | 1997-10-01 | 1995-12-01 |  | 2002-04-01 | 2002-04-01 | 449000 | 0 | 449000 | 449000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in April 2002. Draft PCR had been submitted to WB for review. |  |  | 1997-12-01 |  | 2000-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Multi Karya Makmur | Individual | ASP | IDS | FOA | 15 | INV | 20 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 2003-06-01 | 2003-07-01 | 123700 | -768 | 122932 | 122932.14 | 100% | -0.14 | -0.14 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1997-12-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene and polystyrene foam sheet at PT Inter Foamindosentra | Individual | ASP | IDS | FOA | 15 | INV | 21 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 1998-09-01 | 2000-10-01 | 390000 | -154145 | 235855 | 235855 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. Balance returned to the MLF at the 33rd ExCom. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Sharp Yasonta, Indonesia | Individual | ASP | IDS | REF | 15 | INV | 22 | N | O | I | CFC | 172.7 | 172.7 | 0 | 0 | 1994-12-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 1998-05-01 | 346000 | 502910 | 848910 | 848910.25 | 100% | -0.25 | -0.25 |  | 0 | 78000 | 78000 | 0 | 0 | PCR has been submitted. Project is physically and financially completed. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Lippo Melco Manufacturing | Individual | ASP | IDS | REF | 15 | INV | 23 | N | O | I | CFC | 47.02 | 47.02 | 0 | 0 | 1994-12-01 | 1996-12-01 | 1998-10-01 |  | 1998-06-01 | 1999-03-01 | 382000 | 234452.23 | 616452.23 | 616452.23 | 100% | 0 | 0 |  | 0 | 32455.02 | 32455.42 | -0.4 | -0.4 | Conversion of refrigerant to 134a is finished. Technical audit done on Feb. '98. Completed ODS phaseout in Jun. '98. Disposal plan was carried out in Nov. 19, '98. IOC has been disbursed. Project is technically and financially closed. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Project formulation for phasing out ODS in small and medium scale industries | Individual | ASP | IDS | SEV | 15 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-01-01 | 2002-05-01 | 80000 | -2803 | 77197 | 77197 | 100% | 0 | 0 |  | 10400 | -380 | 10020 | 0 | 0 | FIN |  |  | 1997-12-01 | 1999-02-01
CLO | UNDP | Elimination of the use of 111 TCA and CFC-113 in the manufacture of metal and plastic motorcycle parts at PT KGD Indonesia, Inc. | Individual | ASP | IDS | SOL | 15 | INV | 25 | A | O | R | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1996-02-01 |  |  | 1997-05-01 | 88000 | -88000 | 0 | 0 |  | 0 | 0 | 0 | 11440 | -11440 | 0 | 0 | 0 | Canceled in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Elimination of ODS used in the manufacturing of household refrigerators at P.T. Sanyo Industries Indonesia, Jakarta | Individual | ASP | IDS | REF | 15 | INV | 26 | N | O | I | CFC | 72.3 | 72.3 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1998-12-01 |  | 1998-03-01 | 1998-12-01 | 558000 | -30847.24 | 527152.76 | 527152.76 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project is completed. PCR had been submitted, project is closed. Unused funds returned to 32nd meeting. 3% agency fee incl. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination in production of halon-1211 fire protection extinguishers at Dahlia Cahaya, Bayu Sentosa Agung and Chubb Lips | Individual | ASP | IDS | HAL | 15 | INV | 27 | N | O | I | HAL | 465 | 682.4 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1995-12-01 |  | 1997-11-01 | 1997-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PCR has been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance in solvent, halon and refrigeration sectors | Individual | ASP | IDS | SEV | 15 | PRP | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-03-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Reduction of CFC-12 emission during service of MAC by use of recycling equipment | Individual | ASP | IDS | REF | 15 | TAS | 29 | N | O | I | CFC | 41 | 41 | 0 | 0 | 1994-12-01 | 2000-03-01 | 1996-12-01 |  | 2002-04-01 | 2002-04-01 | 327000 | -51593.01 | 275406.99 | 275406.99 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Draft PCR submitted to the Bank. Savings are to be returned to the MLF. |  |  | 1997-12-01 | 2000-01-01 | 2001-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Musimassejahtera Abadi | Individual | ASP | IDS | FOA | 15 | INV | 30 | N | O | I | CFC | 114 | 50 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  |  | 2000-12-01 | 390000 | -356351 | 33649 | 33649 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled at 31st meeting and $154,145 returned at the 32nd meeting. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IDS | SEV | 16 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 108824 | 0 | 108824 | 108824 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF foam for cold storage at P.T. Fibrindo Carsa Pratama | Individual | ASP | IDS | FOA | 17 | INV | 32 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1995-07-01 | 1997-03-01 | 1996-06-01 |  | 1997-12-01 | 2000-07-01 | 55000 | -5382 | 49618 | 49618 | 100% | 0 | 0 | 0 | 7150 | -700 | 6450 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | Australia | Indonesian ODS control policy | Individual | ASP | IDS | SEV | 17 | TAS | 33 | A | O | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-05-01 | 1996-01-01 |  | 1996-01-01 | 1996-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for coolers/thermoware at P.T. Perdana Merah Delima | Individual | ASP | IDS | FOA | 18 | INV | 34 | A | O | R | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 1999-12-01 | 173000 | -1 | 172999 | 172999 | 100% | 0 | 0 | 0 | 22490 | 0 | 22490 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | UNIDO | Phasing out of ODS at P.T. Air Tech. Co. Ltd. | Individual | ASP | IDS | REF | 18 | INV | 35 | A | O | I | CFC | 30.1 | 30.1 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-05-01 | 409850 | 0 | 409850 | 409850 | 100% | 0 | 0 |  | 53281 | 0 | 53281 | 0 | 0 | FIN
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. Topjaya Antariksa Electronics | Individual | ASP | IDS | REF | 18 | INV | 36 | N | O | I | CFC | 51 | 69 | 0 | 0 | 1995-11-01 | 1996-11-01 | 2002-12-02 |  | 1998-05-01 | 2000-02-01 | 702000 | -2674 | 699326 | 699326 | 100% | 0 | 0 |  | 91260 | -347 | 90913 | 0 | 0 | Project is completed. PCR has been submitted. Unused fund is returned to 32nd Ex.Com. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. National Gobel (Nabel) | Individual | ASP | IDS | REF | 18 | INV | 37 | N | O | I | CFC | 90 | 100.57 | 0 | 0 | 1995-11-01 | 1996-07-01 | 2000-12-01 |  | 1998-03-01 | 2000-03-01 | 856500 | 0 | 856500 | 856500 | 100% | 0 | 0 |  | 111345 | 0 | 111345 | 0 | 0 | Project is completed. PCR has been submitted. |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning processes from 1.1.1 TCA to aqueous cleaning at PT INTI (Industri Telekomunikasi Indonesia) | Individual | ASP | IDS | SOL | 18 | INV | 38 | N | O | I | TCA | 0.97 | 1 | 0 | 0 | 1995-11-01 | 1996-07-01 | 1996-11-01 |  | 1996-06-01 | 1996-08-01 | 37380 | 0 | 37380 | 37380 | 100% | 0 | 0 |  | 4859.4 | 0 | 4859.4 | 0 | 0 | Project is completed and closed. PCR submitted. |  |  | 1996-08-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Garuda Indonesia | Individual | ASP | IDS | SOL | 18 | INV | 39 | N | O | I | TCA | 0.86 | 2.67 | 0 | 0 | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-11-01 | 1998-11-01 | 33264 | -169 | 33095 | 33095 | 100% | 0 | 0 |  | 4324.32 | -21.97 | 4302.35 | 0 | 0 | The project is completed. Technical audit has been done with satisfactory result. PCR had been submitted. Project is closed. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Markindo Theco | Individual | ASP | IDS | SOL | 18 | INV | 40 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 1999-03-01 | 83200 | -83200 | 0 | 0 |  | 0 | 0 |  | 10816 | -10816 | 0 | 0 | 0 | CANCELLED. Funds returned to 27th meeting. |  |  | 1997-12-01 | 1996-11-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 18 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 18 | PRP | 42 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Investment project for phasing out ODS at PT Naviri Kencana Perdana | Individual | ASP | IDS | FOA | 19 | INV | 43 | A | O | I | CFC | 47.8 | 47.8 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 377382 | -402 | 376980 | 376980 | 100% | 0 | 0 |  | 49060 | -130 | 48930 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Alpine Cool | Individual | ASP | IDS | FOA | 20 | INV | 44 | A | O | I | CFC | 13.9 | 13.9 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 84000 | -268 | 83732 | 83732 | 100% | 0 | 0 | 0 | 10920 | -35 | 10885 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1996 | Investment
CLO | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene foam sheet at PT. Toha Kencana Mas | Individual | ASP | IDS | FOA | 20 | INV | 45 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-10-01 |  |  | 1999-07-01 | 109930 | -109930 | 0 | 0 |  | 0 | 0 |  | 14290.9 | -14291 | 0 | -0.1 | -0.1 | Project is cancelled. Funds returned to 28th meeting. |  |  | 1997-12-01 | 1997-10-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at PT Dithon Urethane | Individual | ASP | IDS | FOA | 20 | INV | 46 | A | O | I | CFC | 16.5 | 16.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-02-01 | 2000-07-01 | 184000 | -295 | 183705 | 183705 | 100% | 0 | 0 | 0 | 23920 | -38 | 23882 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Mentari Metal Pratama | Individual | ASP | IDS | FOA | 20 | INV | 47 | A | O | I | CFC | 8.8 | 8.8 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-09-01 |  | 1999-11-01 | 2001-12-01 | 47000 | -693 | 46307 | 46307 | 100% | 0 | 0 | 0 | 6110 | -90 | 6020 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Goldstar Astra Electronics (GSA) | Individual | ASP | IDS | REF | 20 | INV | 48 | N | O | I | CFC | 38.1 | 35.04 | 0 | 0 | 1996-10-01 | 1998-02-01 | 1999-04-01 |  | 1999-12-01 | 2001-03-01 | 512730 | -163820 | 348910 | 348910.32 | 100% | -0.32 | -0.32 |  | 66654.9 | -21297 | 45358 | -0.1 | -0.1 | Project is technically and financially closed. IOC has been disbursed. Balance returned to the MLF at the 35th ExCom. |  |  | 1999-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at PT Cahaya Biru Sakti | Individual | ASP | IDS | SOL | 20 | INV | 50 | N | O | I | TCA | 18.2 | 18.2 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1998-06-01 | 2000-10-01 | 700700 | -125383 | 575317 | 575317 | 100% | 0 | 0 |  | 91091 | -16299.79 | 74791.21 | 0 | 0 | Project completed and PCR submitted Jan. 01. |  |  | 1997-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of tobacco expansion process from CFC-11 to carbon dioxide at PT Hanjaya Mandal Sampoerna and P.T. Djarum | Individual | ASP | IDS | OTH | 21 | INV | 51 | N | O | I | CFC | 90 | 54 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1999-02-01 |  | 1997-06-01 | 1998-08-01 | 1214000 | -607000 | 607000 | 607000 | 100% | 0 | 0 |  | 157820 | -78910 | 78910 | 0 | 0 | PT Sampoerna - grant was fully disbursed. Completed technical audit and disposal plan. PCR has been submitted and project is closed. PT Djarum - steam-based technology proposed was refused, project cancelled. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Samsung Maspion Indonesia (SMI) | Individual | ASP | IDS | REF | 21 | INV | 52 | N | O | I | CFC | 104.3 | 98.24 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1999-08-01 |  | 2001-10-01 | 2001-11-01 | 537226 | -320243 | 216983 | 216983 | 100% | 0 | 0 |  | 69839.38 | -41632 | 28206.97 | 0.41 | 0.41 | Enterprise decided not to proceed to c-pentane due to current unfavorable economic conditions causing a high upfront investment costs for technology, and stopped at HCFC-141b. Disposal of old equipment done and IOC disbursed. Unused funds returned to the MLF at 35th and 36th Meetings. PCR under preparation. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | IDS | REF | 21 | PRP | 53 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1997 | Investment
FIN | UNIDO | Project formulation of investment projects in the aerosol and foam sectors | Individual | ASP | IDS | SEV | 21 | PRP | 54 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 2000-10-01 | 2001-07-01 | 20000 | -4478 | 15522 | 15522 | 100% | 0 | 0 |  | 2600 | -585 | 2015 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 21 | PRP | 55 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 179000 | -150000 | 29000 | 29000 | 100% | 0 | 0 |  | 23270 | -19500 | 3770 | 0 | 0 | For IDS/SEV/21/PRP/55 $179,000 was approved of which $29,000 was expensed, and the remaining $150,000 was transferred to Indonesia PPA III. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 at PT Winnerfoam Abadi | Individual | ASP | IDS | FOA | 22 | INV | 56 | A | O | I | CFC | 40 | 40 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 79472 | -1287 | 78185 | 78185 | 100% | 0 | 0 |  | 10331 | -183 | 10148 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Panca Duta foam industry | Individual | ASP | IDS | FOA | 22 | INV | 57 | A | O | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2001-12-01 | 86955 | -621 | 86334 | 86334 | 100% | 0 | 0 |  | 11304 | -98 | 11206 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at PT Elastino Satyajaya flexible polyurethane foam plant | Individual | ASP | IDS | FOA | 22 | INV | 58 | A | O | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 75943 | 0 | 75943 | 75943 | 100% | 0 | 0 |  | 9873 | -5 | 9868 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at P.T. Jalur Sejuk | Individual | ASP | IDS | REF | 22 | INV | 59 | A | O | I | CFC | 30.85 | 30.85 |  |  | 1997-05-01 | 1997-09-01 | 1998-11-01 |  | 1999-06-01 | 2001-07-01 | 171470 | 0 | 171470 | 171470 | 100% | 0 | 0 |  | 22291 | -17 | 22274 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at Plysindo Inter Mouldi (PIM) | Individual | ASP | IDS | FOA | 22 | INV | 60 | A | O | I | CFC | 4.5 | 4.5 | 0 | 0 | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1997-09-01 | 2001-12-01 | 75870 | -1848 | 74022 | 74022 | 100% | 0 | 0 | 0 | 9863 | -240 | 9623 | 0 | 0 | Completed in 1997. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | Individual | ASP | IDS | ARS | 22 | INV | 61 | N | O | I | CFC | 460 | 460 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1999-06-01 |  | 2005-05-01 | 2004-10-01 | 1175340 | 0 | 1175340 | 1175340 | 100% | 0 | 0 |  | 152794 | 0 | 152794 | 0 | 0 | Project financially and physically completed. |  |  |  | 2000-06-01 |  | 2002-06-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IDS | SEV | 16 | PRP | 62 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 50000 | -32695 | 17305 | 17305 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF insulated products at UD Samrow Foam | Individual | ASP | IDS | FOA | 23 | INV | 63 | A | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-10-01 | 2001-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of an investment project for phasing out ODS at three enterprises including the companies Nirwana and P.T. Success | Individual | ASP | IDS | SEV | 23 | PRP | 64 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-10-01 | 2001-07-01 | 10000 | 9025 | 19025 | 19025 | 100% | 0 | 0 |  | 1300 | 1169 | 2469 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC -free technology in the manufacture of rigid polyurethane foam (panels, blocks) at PT Aneka Cool Citratama | Individual | ASP | IDS | FOA | 23 | INV | 65 | A | O | I | CFC | 32.7 | 32.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 232225 | -10678 | 221547 | 221547 | 100% | 0 | 0 | 0 | 30189 | -1388 | 28801 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at C.V. Kulkasindo | Individual | ASP | IDS | REF | 23 | INV | 66 | A | O | I | CFC | 9.4 | 9.4 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 136000 | -18594 | 117406 | 117406 | 100% | 0 | 0 | 0 | 17680 | -2417 | 15263 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at PT Dilihan Glory | Individual | ASP | IDS | FOA | 23 | INV | 67 | A | O | I | CFC | 13.1 | 13.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 102200 | -14362 | 87838 | 87838 | 100% | 0 | 0 | 0 | 13286 | -1867 | 11419 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray foam) at PT Ferrarindo Multi Sarana | Individual | ASP | IDS | FOA | 23 | INV | 68 | A | O | I | CFC | 7.7 | 7.7 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-07-01 | 32900 | -316 | 32584 | 32584 | 100% | 0 | 0 | 0 | 4277 | -41 | 4236 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector (tobacco, tomatoes, pepper) | Individual | ASP | IDS | FUM | 23 | PRP | 69 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 1998-09-01 | 2001-07-01 | 10000 | 17659 | 27659 | 27659 | 100% | 0 | 0 |  | 1300 | 2290 | 3590 | 0 | 0 | FIN
CLO | UNDP | Conversion to CFC-free techology in the manufacture of rigid PUF insulated thermoware at PT Langgeng Makmur Plastic Industry Ltd. | Individual | ASP | IDS | FOA | 23 | INV | 70 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 142000 | -142000 | 0 | 0 |  | 0 | 0 | 0 | 18460 | -18460 | 0 | 0 | 0 | Canceled in 1999. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded and integral skin PUF at PT Archigramma | Individual | ASP | IDS | FOA | 23 | INV | 71 | A | O | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 106625 | -14881 | 91744 | 91744 | 100% | 0 | 0 | 0 | 13861 | -1935 | 11926 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Maspion | Individual | ASP | IDS | REF | 23 | INV | 72 | N | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2000-11-01 | 136890 | -11703 | 125187 | 125187.38 | 100% | -0.38 | -0.38 |  | 17796 | -1521.39 | 16274.31 | 0.3 | 0.3 | Project completed. Disposal of old equipment has been carried out. PCR will be submitted January 2001. Project is closed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polethylene foam sheet at PT. Tara Guna Foam | Individual | ASP | IDS | FOA | 23 | INV | 73 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1997-11-01 | 2001-10-01 | 1999-12-01 |  | 2001-12-01 | 2002-10-01 | 287700 | -34630.97 | 253069.03 | 253069.03 | 100% | 0 | 0 |  | 37401 | -4502.03 | 32898.97 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  |  | 2001-02-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Porkka Indonesia | Individual | ASP | IDS | REF | 23 | INV | 74 | N | O | I | CFC | 3.96 | 3.96 | 0 | 0 | 1997-11-01 | 2000-10-01 | 1999-12-01 |  | 1998-08-01 | 2001-03-01 | 58517 | -9377 | 49140 | 49140 | 100% | 0 | 0 |  | 7607 | -1219.01 | 6387.99 | 0 | 0 | Project completed and PCR to be submitted Mar. 02. Savings returned to the 35th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT. Irc Inoac Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 75 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2003-04-01 | 412900 | -412900 | 0 | 0 |  | 0 | 0 |  | 53677 | -53677 | 0 | 0 | 0 | Cancelled - 38th ExCom | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT Sea Horse Maspion Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 76 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 532200 | -532200 | 0 | 0 |  | 0 | 0 |  | 69186 | -63864 | 5322 | 0 | 0 | Project cancelled at the 35th ExCom and funds to be returned at the 36th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 77 | N | O | I | CFC | 954 | 954 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2007-01-01 | 2007-03-01 | 4060640 | -467626.72 | 3593013.28 | 3593013.28 | 100% | 0 | 0 |  | 527883 | -60791.46 | 467091.54 | 0 | 0 | Project is physically and financially completed |  |  |  |  | 2001-02-01 | 2002-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance programme for SMEs for flexible polyurethane foam at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 78 | N | O | I | CFC | 370 | 370 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2005-04-01 | 2005-12-01 | 3538400 | -1983523.96 | 1554876.04 | 1554876.04 | 100% | 0 | 0 |  | 459992 | -257858.12 | 202133.88 | 0 | 0 | Project completed. |  |  |  |  | 2001-02-01 | 2002-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of commercial refrigeration units at PT Wahana Derby Sejati | Individual | ASP | IDS | REF | 23 | INV | 79 | N | O | I | CFC | 10.28 | 10.28 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1997-11-01 | 1998-07-01 | 139233 | -77613 | 61620 | 61620 | 100% | 0 | 0 |  | 18100 | -10089.69 | 8010.31 | 0 | 0 | Project completed, PCR submitted Mar. 99 and balance returned to the 32nd ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IDS | SEV | 23 | INS | 80 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 208650 | -265 | 208385 | 208385 | 100% | 0 | 0 | 0 | 27125 | -34 | 27091 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1997 | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF spray insulation at Karya Cipta Semesta | Individual | ASP | IDS | FOA | 23 | INV | 81 | A | O | I | CFC | 16.4 | 16.4 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-12-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 8840 | 0 | 8840 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded PUF at Ciptaindah Jokindo | Individual | ASP | IDS | FOA | 23 | INV | 82 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 77125 | -58 | 77067 | 77067 | 100% | 0 | 0 | 0 | 10026 | -7 | 10019 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IDS | REF | 24 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | IDS | FOA | 24 | PRP | 84 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation in the halon recycling sector |  | ASP | IDS | HAL | 24 | PRP | 85 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray foam) at PT Sentras Varitima | Individual | ASP | IDS | FOA | 25 | INV | 86 | A | O | I | CFC | 18.1 | 18.1 | 0 | 0 | 1998-07-01 | 1999-07-01 | 2000-08-01 |  | 2000-07-01 | 2002-03-01 | 125000 | -5780 | 119220 | 119220 | 100% | 0 | 0 | 0 | 16250 | -751 | 15499 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Supply conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Gaya Teknik | Individual | ASP | IDS | REF | 25 | INV | 88 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-12-01 | 147880 | -2358 | 145522 | 145522 | 100% | 0 | 0 | 0 | 19224 | -306 | 18918 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Converstion to CFC-free technology in the manufacture of rigid polyurethane spray foam at Metal Tunggal Prakarsamandiri | Individual | ASP | IDS | FOA | 25 | INV | 89 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2002-10-01 | 43330 | 0 | 43330 | 43330 | 100% | 0 | 0 | 0 | 5633 | 0 | 5633 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Aneka Froze Citratama | Individual | ASP | IDS | REF | 25 | INV | 90 | A | O | I | CFC | 13.1 | 13.1 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 174255 | -17790 | 156465 | 156465 | 100% | 0 | 0 | 0 | 22653 | -2313 | 20340 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Converstion to CFC-free technolgoy in the manufacture of rigid polyurethane spray foam at Karya Sempati Sarana | Individual | ASP | IDS | FOA | 25 | INV | 91 | A | O | I | CFC | 8.8 | 8.8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2004-01-01 | 45550 | 0 | 45550 | 45550 | 100% | 0 | 0 | 0 | 5922 | 0 | 5922 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of CFC-11 and CFC-12/R-502 to HCFC-141b (foam) and HFC-134a/R404a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at P.T. Intermas Pacific | Individual | ASP | IDS | REF | 25 | INV | 92 | A | O | I | CFC | 17.9 | 17.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 209300 | -20993 | 188307 | 188307 | 100% | 0 | 0 | 0 | 27209 | -2729 | 24480 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at PT Hanaria Indah | Individual | ASP | IDS | FOA | 26 | INV | 93 | A | O | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 101352 | -18169 | 83183 | 83183 | 100% | 0 | 0 | 0 | 13176 | -2362 | 10814 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in store products (rice, coffee and corn) | Individual | ASP | IDS | FUM | 26 | DEM | 94 | A | O | I |  | 0 | 0 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-12-01 | 2003-10-01 | 332200 | -5985 | 326215 | 326215 | 100% | 0 | 0 |  | 43186 | -845 | 42341 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated panels at P.T. Panendra Sejati | Individual | ASP | IDS | FOA | 26 | INV | 95 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 156600 | -46830 | 109770 | 109770 | 100% | 0 | 0 | 0 | 20358 | -6088 | 14270 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Indoklima Sarana Engineering | Individual | ASP | IDS | FOA | 26 | INV | 96 | A | O | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 212193 | -43243 | 168950 | 168950 | 100% | 0 | 0 | 0 | 27585 | -5622 | 21963 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Laksana | Individual | ASP | IDS | FOA | 26 | INV | 97 | A | O | I | CFC | 21.3 | 21.3 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-11-01 | 2004-01-01 | 122885 | -3 | 122882 | 122882 | 100% | 0 | 0 | 0 | 15975 | 0 | 15975 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Mekar Armada Jaya | Individual | ASP | IDS | FOA | 26 | INV | 98 | A | O | I | CFC | 24.9 | 24.9 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 149357 | -6055 | 143302 | 143302 | 100% | 0 | 0 | 0 | 19416 | -787 | 18629 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Tesaguna Sejati | Individual | ASP | IDS | REF | 26 | INV | 99 | A | O | I | CFC | 9.7 | 9.7 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 147900 | 0 | 147900 | 147900 | 100% | 0 | 0 | 0 | 19227 | 0 | 19227 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Trisakti | Individual | ASP | IDS | FOA | 26 | INV | 100 | A | O | I | CFC | 11.1 | 11.1 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2003-03-01 | 80037 | -6557 | 73480 | 73480 | 100% | 0 | 0 | 0 | 10405 | -852 | 9553 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Mentari Adi Fayar | Individual | ASP | IDS | FOA | 26 | INV | 101 | A | O | I | CFC | 22.4 | 22.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-01-01 | 2004-01-01 | 111517 | 0 | 111517 | 111517 | 100% | 0 | 0 | 0 | 14497 | 0 | 14497 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Herry Alter's | Individual | ASP | IDS | REF | 26 | INV | 102 | A | O | I | CFC | 32.4 | 32.4 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 438060 | -15658 | 422402 | 422402 | 100% | 0 | 0 | 0 | 56948 | -2036 | 54912 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at Irama Sejuk Santosa | Individual | ASP | IDS | FOA | 26 | INV | 103 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 54800 | -4604 | 50196 | 50196 | 100% | 0 | 0 | 0 | 7124 | -599 | 6525 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 3 enterprises: Bali Cool, Centrum Cool and Ever Cool | Individual | ASP | IDS | REF | 26 | INV | 104 | A | O | I | CFC | 15.2 | 15.2 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 231800 | -1729 | 230071 | 230071 | 100% | 0 | 0 | 0 | 30134 | -225 | 29909 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, CFC-12 to HFC-134a and R-502 to R-404A technology in the manufacture of commercial refrigeration equipment at PT Algron | Individual | ASP | IDS | REF | 26 | INV | 105 | A | O | I | CFC | 10.4 | 10.4 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-11-01 | 158210 | 0 | 158210 | 158210 | 100% | 0 | 0 | 0 | 20567 | 0 | 20567 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated boxes at P.T. Polidaya Fiberindo Indah | Individual | ASP | IDS | FOA | 26 | INV | 106 | A | O | I | CFC | 9.3 | 9.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 72800 | -8363 | 64437 | 64437 | 100% | 0 | 0 | 0 | 9464 | -1087 | 8377 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | IDS | HAL | 27 | TAS | 107 | N | O | I | HAL | 972 | 972 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2003-04-01 |  | 2007-01-01 | 2007-06-01 | 486200 | -11076.12 | 475123.88 | 475123.88 | 100% | 0 | 0 |  | 63206 | -1439.9 | 61766.1 | 0 | 0 | Project is physically and financially completed | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam sector |  | ASP | IDS | FOA | 27 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IDS | FOA | 27 | PRP | 109 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2002-01-01 | 2003-05-01 | 50000 | -177 | 49823 | 49823 | 100% | 0 | 0 |  | 6500 | -33 | 6467 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Nirwana in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 110 | A | O | I | CFC | 32.6 | 32.6 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 206911 | 0 | 206911 | 206911 | 100% | 0 | 0 |  | 26898 | -27 | 26871 | 0 | 0 | FIN
FIN | IBRD | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at CV Sumber Logam | Individual | ASP | IDS | FOA | 29 | INV | 111 | N | O | I | CFC | 12.1 | 12.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2001-12-01 | 2002-05-01 | 56118 | -30157 | 25961 | 25961 | 100% | 0 | 0 |  | 7295.34 | -3920.41 | 3374.93 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam, panels, blocks) at Tansri Gani | Individual | ASP | IDS | FOA | 29 | INV | 112 | A | O | I | CFC | 45.3 | 45.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2003-03-01 | 2005-09-01 | 354700 | -5045 | 349655 | 349655 | 100% | 0 | 0 | 0 | 46111 | -656 | 45455 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [6 empty] | 2003-07-01 | [6 empty] | 1999 | Investment
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Meta Presindo Utama in the manufacture of polyurethane integral skin and moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 113 | A | O | I | CFC | 21.8 | 21.8 |  |  | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 213603 | 0 | 213603 | 213603 | 100% | 0 | 0 |  | 27768 | -15 | 27753 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based systems and HCFC-141b in the manufacture of polyurethane foam for automotive and furniture applications at P.T. Yoska Prima Inti | Individual | ASP | IDS | FOA | 29 | INV | 114 | A | O | I | CFC | 49.5 | 49.5 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 368868 | -221866 | 147002 | 147002 | 100% | 0 | 0 | 0 | 47953 | -28843 | 19110 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
CLO | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at PT Sentra Sukses Selalu | Individual | ASP | IDS | FOA | 29 | INV | 115 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-04-01 | 539579 | -539579 | 0 | 0 |  | 0 | 0 |  | 69353.69 | -69353.69 | 0 | 0 | 0 | Cancelled - 38th ExCom | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (boxfoam and sprayfoam) at PT Intimas Chemindo | Individual | ASP | IDS | FOA | 29 | INV | 116 | N | O | I | CFC | 74.3 | 74.3 | 0 | 0 | 1999-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-03-01 | 2004-09-01 | 290294 | -163063.56 | 127230.44 | 127230.44 | 100% | 0 | 0 |  | 37738.22 | -21198.04 | 16539.96 | 0.22 | 0.22 | Project technically and financially completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at PT Dawamiba Engineering | Individual | ASP | IDS | FOA | 29 | INV | 117 | N | O | I | CFC | 31.6 | 31.6 | 0 | 0 | 1999-11-01 | 2001-11-01 | 2002-12-01 |  | 2003-06-01 | 2003-10-01 | 156500 | -2750 | 153750 | 153750 | 100% | 0 | 0 |  | 20345 | -357.5 | 19987.5 | 0 | 0 | Project technically and financially completed. PCR draft being finalized. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at Kimura Fiberglass | Individual | ASP | IDS | FOA | 29 | INV | 118 | N | O | I | CFC | 21.1 | 21.1 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2001-12-01 | 2002-07-01 | 69385 | -36556.41 | 32828.59 | 32828.59 | 100% | 0 | 0 |  | 9020.05 | -4752.34 | 4267.71 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown technology in the manufacturing of polyurethane integral skin shoe soles at P.T. Trias Rantai Mas | Individual | ASP | IDS | FOA | 31 | INV | 119 | A | O | I | CFC | 18.4 | 18.4 |  |  | 2000-07-01 | 2000-11-01 | 2003-01-01 |  | 2003-01-01 | 2003-12-01 | 141319 | 0 | 141319 | 141319 | 100% | 0 | 0 |  | 18371 | 0 | 18371 | 0 | 0 | FIN
FIN | IBRD | Phaseout of CFC-11 by conversion to water based technology and LCD technology in the manufacture of flexible moulded foam and to HCFC-141b in the manufacture of molded integral skin polyurethane foam at Anto Indo Foam | Individual | ASP | IDS | FOA | 31 | INV | 120 | N | O | I | CFC | 51.75 | 51.75 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-03-01 | 2003-10-01 | 249645 | -244 | 249401 | 249400.86 | 100% | 0.14 | 0.14 |  | 32453.85 | -32 | 32422.11 | -0.26 | -0.26 | Project technically and financially completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Extension of institutional strengthening project (Phase III) | Individual | ASP | IDS | SEV | 32 | INS | 121 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2003-01-01 |  | 2004-09-01 | 2006-08-01 | 208650 | -85 | 208565 | 208564 | 100% | 1 | 0 | 0 | 27125 | -11 | 27113.87 | 0.13 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2000 | Non-Investment
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 122 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -2204 | 22796 | 22796 | 100% | 0 | 0 |  | 3250 | -291 | 2959 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IDS | REF | 33 | PRP | 123 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 124 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | IBRD | Project preparation for 3 projects in the foam sector and one in the refrigeration sector |  | ASP | IDS | SEV | 33 | PRP | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at PT Kemenangan | Individual | ASP | IDS | FOA | 35 | INV | 126 | A | O | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 104817 | -2098 | 102719 | 102719 | 100% | 0 | 0 | 0 | 13626 | -273 | 13353 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (steel door) at PT Bostinco | Individual | ASP | IDS | FOA | 35 | INV | 127 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-01-01 |  | 2003-10-01 | 2004-05-01 | 88479 | 0 | 88479 | 88479 | 100% | 0 | 0 |  | 11502.27 | 0 | 11502.27 | 0 | 0 | Project physically and financially completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (cooler box products) at Dua Roda Industrial Co. | Individual | ASP | IDS | FOA | 35 | INV | 128 | N | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-05-01 | 2003-10-01 | 52457 | -5800 | 46657 | 46657 | 100% | 0 | 0 |  | 6819.41 | -754 | 6065.41 | 0 | 0 | Project physically and financially completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | Individual | ASP | IDS | FOA | 35 | INV | 129 | N | O | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2004-10-01 |  | 2005-12-01 | 2005-12-01 | 165201 | -20510.44 | 144690.56 | 144690.56 | 100% | 0 | 0 |  | 21476.13 | -2666.36 | 18809.77 | 0 | 0 | Project financially and technically completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (house ware products) at PT Maspion Plastic and Metal Industry | Individual | ASP | IDS | FOA | 35 | INV | 130 | N | O | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-11-01 | 2004-09-01 | 141723 | 0 | 141723 | 141723 | 100% | 0 | 0 |  | 18423.99 | 0 | 18423.99 | 0 | 0 | Project physically and financially completed | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Nikoteknik | Individual | ASP | IDS | REF | 35 | INV | 131 | A | O | I | CFC | 27.9 | 27.9 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 238903 | -19314 | 219589 | 219589 | 100% | 0 | 0 | 0 | 31057 | -2511 | 28546 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Sapporo Mestika | Individual | ASP | IDS | REF | 35 | INV | 132 | A | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 153768 | -4603 | 149165 | 149165 | 100% | 0 | 0 | 0 | 19990 | -598 | 19392 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Hatindo Metal Utama | Individual | ASP | IDS | REF | 35 | INV | 133 | A | O | I | CFC | 9.6 | 9.6 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2006-10-01 | 145894 | 0 | 145894 | 145894 | 100% | 0 | 0 | 0 | 18966 | 0 | 18966 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Leoindo Kreasi | Individual | ASP | IDS | REF | 35 | INV | 134 | A | O | I | CFC | 15.7 | 15.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 119394 | -4838 | 114556 | 114556 | 100% | 0 | 0 | 0 | 15521 | -629 | 14892 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Alfa Metalindo Agra | Individual | ASP | IDS | REF | 35 | INV | 135 | A | O | I | CFC | 9.7 | 9.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 146960 | -3500 | 143460 | 143460 | 100% | 0 | 0 | 0 | 19105 | -455 | 18650 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Gastro Gizi Sarana | Individual | ASP | IDS | REF | 35 | INV | 136 | A | O | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 221049 | -6055 | 214994 | 214994 | 100% | 0 | 0 | 0 | 28736 | -787 | 27949 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | IDS | REF | 36 | PRP | 137 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2740 | 17260 | 17260 | 100% | 0 | 0 | 0 | 2600 | -356 | 2244 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | ASP | IDS | REF | 36 | PRP | 138 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 35000 | -5430 | 29570 | 29570 | 100% | 0 | 0 | 0 | 4550 | -706 | 3844 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNIDO | Preparation of a phase-out project in the fumigant (methyl bromide) sector in TPO-grain fumigation | Individual | ASP | IDS | FUM | 36 | PRP | 139 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of a sector phase-out plan in process agents sector | Individual | ASP | IDS | PAG | 36 | PRP | 140 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-12-01 | 2004-12-01 | 60000 | -1890 | 58110 | 58110 | 100% | 0 | 0 |  | 7800 | -258 | 7542 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of integral skin automotive parts at PT Wulansari Raharja | Individual | ASP | IDS | FOA | 36 | INV | 141 | A | O | I | CFC | 10.8 | 10.8 |  |  | 2002-03-01 | 2004-02-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 101301 | -632 | 100669 | 100669 | 100% | 0 | 0 |  | 13169 | -103 | 13066 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | IBRD | Preparation of two sector plans in the aerosol sector and in the foam sector |  | ASP | IDS | SEV | 36 | PRP | 142 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Foam and aerosol proposals prepared and submitted to Excom. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid insulation foam parts at two companies: PT Morodadi Prima and PT Tentrem Industri Karosseri | Individual | ASP | IDS | FOA | 36 | INV | 143 | A | O | I | CFC | 25.5 | 25.5 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-11-01 | 2007-04-01 | 164947 | -567 | 164380 | 164380 | 100% | 0 | 0 |  | 21443 | -74 | 21369 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT Solindah Kita | Individual | ASP | IDS | FOA | 36 | INV | 144 | A | O | I | CFC | 48 | 48 |  |  | 2002-03-01 | 2002-08-01 | 2004-09-01 |  | 2005-12-01 | 2006-12-01 | 390760 | -5753 | 385007 | 385007 | 100% | 0 | 0 |  | 50799 | -748 | 50051 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Aneka Citra Refrigeratama Co. | Individual | ASP | IDS | FOA | 37 | INV | 145 | A | O | I | CFC-11 | 18.2 | 18.2 | 0 |  | 2002-07-01 | 2004-11-01 | 2004-09-01 |  | 2005-12-01 | 2006-03-01 | 142506 | -377 | 142129 | 142129 | 100% | 0 | 0 | 0 | 18526 | -49 | 18476.77 | 0.23 | 0 | Project completed. |  | 2002 | [12 empty] | investment
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Bina Teknik Co. | Individual | ASP | IDS | FOA | 37 | INV | 146 | A | O | I | CFC-11 | 22.8 |  | 0 |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2006-03-01 | 2006-03-01 | 117889 | -541 | 117348 | 117348 | 100% | 0 | 0 | 0 | 15326 | -70 | 15255.24 | 0.76 | 0 | Project completed in March 2006. |  | 2002 | [12 empty] | investment
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT. Accurai | Individual | ASP | IDS | FOA | 37 | INV | 147 | A | O | I | CFC | 50 | 50 |  |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2005-06-01 | 2006-09-01 | 523943 | -656 | 523287 | 523287 | 100% | 0 | 0 |  | 67634 | -72 | 67562 | 0 | 0 | FIN | [13 empty] | 2002 | INV
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (first tranche) | Multi-Year | ASP | IDS | REF | 37 | INV | 148 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-10-01 | 2002-12-01 |  | 2004-12-01 |  | 1288000 | 0 | 1288000 | 1288000 | 100% | 0 | 0 | 0 | 111920 | 0 | 111920 | 0 | 0 | Completed in 2004. | [8 empty] | 2004-12-01 |  |  |  |  | 2002 | Investment | 1141 | 1141 |  |  | Yes | Yes | yes
FIN | IBRD | Strengthening of import/export control | Individual | ASP | IDS | SEV | 37 | TAS | 149 | N | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2004-08-01 |  | 2006-12-01 | 2006-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Gov. of Indonesia made great progress in improving import licensing and quota system to monitor and control ODS import. Revised draft to existing regulation agreed upon by Ministry of Trade and other relevant government depts. New regulation adopted on June 22, 2006. Old regulation with provision that only one company can import ODS declared void. Standard Operating Procedures drafted to provide guidance for implementation of new regulation. Project completed. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Project to phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Ganesha Rattesko and Sindari Nusatama | Individual | ASP | IDS | FOA | 38 | INV | 150 | A | O | I | CFC | 52 | 52 |  |  | 2002-11-01 | 2003-12-01 | 2005-06-01 |  | 2005-12-01 | 2006-12-01 | 283490 | -101 | 283389 | 283389 | 100% | 0 | 0 |  | 36854 | -13 | 36841 | 0 | 0 | FIN | [13 empty] | 2002 | INV
COM | UNDP | Refrigeration sector phase-out plan: refrigeration servicing | Multi-Year | ASP | IDS | REF | 38 | INV | 151 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2005-12-01 |  | 2196758 | 0 | 2196758 | 2196758 | 100% | 0 | 0 | 0 | 195708 | 0 | 195708 | 0 | 0 | Completed in 2005. | [13 empty] | 2002 | Investment | 1072 | 1072 |  |  | Yes | Yes | yes
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Delta Atlantik and Samudra Plastics | Individual | ASP | IDS | FOA | 38 | INV | 152 | A | O | I | CFC | 18.8 | 18.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2004-11-01 | 2006-05-01 | 146388 | 0 | 146388 | 146388 | 100% | 0 | 0 |  | 19030 | -10 | 19020 | 0 | 0 | FIN | [13 empty] | 2002 | INV
COM | IBRD | Refrigeration sector phase-out plan: MAC servicing sector | Multiyear | ASP | IDS | REF | 38 | INV | 153 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 1369800 | 0 | 1369800 | 1369800 | 100% | 0 | 0 | 0 | 121962 | 0 | 121962 | 0 | 0 | 2003 annual plan completed successfully. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector ( 2nd tranche) | Multi-Year | ASP | IDS | REF | 40 | INV | 154 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2003-07-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 52900 | 0 | 52900 | 0 | 0 | Completed in 2004. | [13 empty] | 2003 | Investment | 841 | 841 |  |  | Yes | Yes | yes
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (balance of second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 155 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-06-01 |  | 1600000 | 0 | 1600000 | 1600000 | 100% | 0 | 0 | 0 | 141100 | 0 | 141100 | 0 | 0 | Completed in 2006. | [13 empty] | 2003 | Investment | 841 | 841 |  |  | Yes | Yes | yes
COM | IBRD | Sector phase-out plan for elimination of CFCs in the refrigeration (MAC servicing) sector: 2004 annual programme | Multiyear | ASP | IDS | REF | 41 | INV | 156 | N | O | I | CFC | 110 | 110 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 |  | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 | 0 | 119937 | 0 | 119937 | 0 | 0 | 2004 annual plan completed sucessfully. | [13 empty] | 2003 | INV | 695 | 695 | 0 | 0 | Yes | Yes | Yes
COM | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (servicing) sector (second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 157 | N | O | I | CFC | 200 | 200 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2004-12-01 |  | 2006-12-01 |  | 1805987 | 0 | 1805987 | 1805987 | 100% | 0 | 0 | 0 | 160939 | 0 | 160939 | 0 | 0 | Completed in 2006. | [10 empty] | 2006-12-01 |  |  | 2003 | Investment | 872 | 872 |  |  | Yes | Yes | yes
TRF | Canada | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 41 | INV | 158 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 |  | 2007-12-01 |  |  | 2004-12-01 | 350000 | -350000 | 0 | 0 |  | 0 |  | 0 | 45500 | -45500 | 0 | 0 |  | Project transferred to UNIDO. |  | 2003 | [11 empty] | 2003 | Non-Inv.
COM | UNDP | Extension of institutional strengthening project | Individual | ASP | IDS | SEV | 41 | INS | 159 | N | T | I | No_ODP | 22.4 | 22.4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 |  | 271245 | 0 | 271245 | 270542 | 99.74% | 703 | 0 | 562.4 | 20343 | 0 | 20290.276 | 52.724 | 0 | Completed in 2006. | [13 empty] | 2003 | Non-Investment
FIN | IBRD | Phase-out of residual CFCs in the foam sector (advancement) | Multiyear | ASP | IDS | FOA | 42 | INV | 160 | N | O | I | CFC | 130 | 130 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-12-01 | 100000 | 1625000 | 1725000 | 1725000 | 100% | 0 | 0 |  | 7500 | 121875 | 129375 | 0 | 0 | Project is physically and financially completed | [13 empty] | 2003 | INV | 222.2 | 222 | 0 | 0 | Yes | Yes | Yes
COM | UNIDO | Plan for terminal phase-out of ODS in the solvent sector | Individual | ASP | IDS | SOL | 44 | INV | 162 | A | O | I | CFC CTC TCA | 100.5 | 100.5 |  |  | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-10-01 |  | 1464733 | 0 | 1464733 | 1438205 | 98.19% | 26528 | 26520 | 26520 | 108974 | 0 | 107000 | 1974 | 1973 | Last package of equipment was delivered and commissioned. Final non investment activities of PMU were completed. Project completed in Oct 2008. | [13 empty] | 2004 | INV
COM | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 163 | N | O | I | CFC | 300 | 300 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-12-01 |  | 1762000 | 0 | 1762000 | 1762000 | 100% | 0 | 0 | 0 | 156900 | 0 | 156900 | 0 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment | 541 | 541 |  |  | Yes | Yes | yes
COM | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 164 | N | O | I | CFC | 300 | 300 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-12-01 |  | 500000 | 0 | 500000 | 58952 | 11.79% | 441048 | 441048 | 352838.4 | 43400 | 0 | 5117.0336 | 38282.9664 | 38282.9664 | Completed in 2008. R&R Equipment distributed to both servicing and training establishments. Additional equipment for 243 sets procured. | [13 empty] | 2004 | Investment | 572 | 572 |  |  | Yes | Yes | yes
COM | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (third tranche) | Multiyear | ASP | IDS | REF | 44 | INV | 165 | N | O | I | CFC | 110 | 110 | 0 | 0 | 2004-12-01 | 2006-11-01 | 2005-12-01 |  | 2005-12-01 |  | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 | 0 | 119937 | 0 | 119937 | 0 | 0 | 2005 consumption reduction target was achieved. | [13 empty] | 2004 | INV | 585 | 585 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives | Multiyear | ASP | IDS | ARS | 44 | INV | 166 | N | O | I | CFC | 70 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-05-01 | 2009-12-01 |  |  | 371910 | 0 | 371910 | 291542 | 78.39% | 80368 | 80368 | 80368 | 27893 | 0 | 21865.45 | 6027.55 | 6027.55 | Potential beneficiaries have been indentified and procurement process for safety equipment is being conducted. One company received the safety equipment, while 5 others expected to receive it in 2009. Safety booklet prepared by consultant is being reviewed by NOU and to be completed by Mar 09. Project activities expected to be completed by end-2009. | [13 empty] | 2003 | INV | 0 | 0 | 0 | 0
COM | UNDP | National strategy for phasing out the use of CFC in the aerosol: conversion from CFC to hydrocarbon aerosol propellants at P.T Yulia | Individual | ASP | IDS | ARS | 44 | INV | 167 | N | O | I | CFC | 80 | 80 | 0 | 0 | 2004-12-01 | 2005-11-01 | 2005-12-01 |  | 2006-06-01 |  | 224000 | 0 | 224000 | 181887 | 81.2% | 42113 | 0 | 33690.4 | 13440 | 0 | 10913.22 | 2526.78 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment
COM | UNIDO | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 44 | INV | 168 | A | O | I | MBR | 37.8 | 37.8 |  |  | 2004-12-01 | 2005-04-01 | 2007-12-01 |  | 2008-09-01 |  | 350000 | 0 | 350000 | 349628 | 99.89% | 372 | 360 | 300 | 26250 | 0 | 26222 | 28 | 27 | Project completed in Sep 2008. | [13 empty] | 2004 | INV
COM | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IDS | SEV | 45 | TAS | 169 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 |  | 114679 | 0 | 114679 | 97560 | 85.07% | 17119 | 0 | 13695.2 | 10321 | 0 | 8780.3064 | 1540.6936 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. Activities completed and all accounts settled. | [13 empty] | 2005 | Non-Investment
FIN | IBRD | Project preparation funds for the development of a phase-out plan for the MDI sector |  | ASP | IDS | ARS | 46 | PRP | 170 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-09-01 | 2006-07-01 |  | 2008-11-01 | 2008-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | TA for an MDI strategy submitted and approved at the 56th ExCom. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
COM | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IDS | SEV | 47 | INS | 171 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2007-12-01 |  | 2007-12-01 |  | 271245 | 0 | 271245 | 271144 | 99.96% | 101 | 0 | 80.8 | 20343 | 0 | 20335.4251 | 7.5749 | 0 | Completed in 2007. | [13 empty] | 2005 | Non-Investment
COM | IBRD | Phase-out of residual CFCs in the foam sector (second tranche) | Multiyear | ASP | IDS | FOA | 48 | INV | 172 | N | O | I | CFC | 130 | 130 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2008-12-01 |  | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 | 0 | 78750 | 0 | 78750 | 0 | 0 | Investment part of the project completed and 36 foam enterprises have been funded under the Sector Plan with a phaseout of 335.2 MT of CFC-11. Monitoring and capacity building activities will be continued in 2009. | [13 empty] | 2005 | INV | 196 | 196 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fourth tranche) | Multiyear | ASP | IDS | REF | 48 | INV | 173 | N | O | I | CFC | 110 | 110 | 0 | 0 | 2006-04-01 | 2008-12-01 | 2007-04-01 |  | 2008-12-01 |  | 126800 | 0 | 126800 | 126800 | 100% | 0 | 0 | 0 | 10092 | 0 | 10092 | 0 | 0 | Investment part of the project completed. A network with local government has been established aiming to create a monitoring program. Remaining funds reallocated for a follow-up training workshop, to support a regional training center, capacity building and monitoring of the MAC recycling program in the region. | [13 empty] | 2005 | INV | 475 | 475 | 0 | 0 | Yes | Yes | Yes
ONG | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 174 | N | O | I | CFC | 300 | 300 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 | 2009-12-01 |  |  | 750000 | 0 | 750000 | 152580 | 20.34% | 597420 | 178079 | 238968 | 67500 | 0 | 13732.2 | 53767.8 | 16027.11 | Equipment installation and commissioning took place for 7 additional enterprises endorsed in 2006. Technical assistance activities carried out and 2 additional regulations issued. Some disbursement will be reflected in 2009. | [13 empty] | 2006 | Investment | 241 | 241 |  |  | Latest | Latest | Latest
COM | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 175 | N | O | I | CFC | 300 | 300 | 0 | 0 | 2006-04-01 |  | 2007-04-01 |  | 2008-12-01 |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 226790 | 200000 | 21300 | 0 | 0 | 21300 | 19322.508 | Completed in 2008. Decree executed May 2007 on the Regulation for Technical Guidance and Competence for Retrofitting and Recovery/Recycling. During 2006/2007, about 2,296 technicians received training. | [13 empty] | 2006 | Investment | 250 | 250 |  |  | Yes | Yes | yes
ONG | IBRD | Phase-out of residual CFCs in the foam sector (third tranche) | Multiyear | ASP | IDS | FOA | 51 | INV | 176 | N | O | I | CFC | 156 | 156 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 | 2009-12-01 |  |  | 147564 | 0 | 147564 | 19164 | 12.99% | 128400 | 128400 | 128400 | 11067 | 0 | 1437.26 | 9629.74 | 9629.74 | Investment part of the project completed and 36 foam enterprises have been funded under the Sector Plan with a phaseout of 335.2 MT of CFC-11. Monitoring and capacity building activities will be continued in 2009. | [13 empty] | 2006 | INV | 66 | 66 | 0 | 0 | Yes | Yes | Yes
ONG | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 177 | N | O | I | CFC | 300 | 300 | 0 | 0 | 2007-03-01 |  | 2009-03-01 | 2010-01-01 |  |  | 217000 | 0 | 217000 | 0 | 0% | 217000 | 0 | 43400 | 19530 | 0 | 0 | 19530 | 0 | Enforcement of revised regulation continued in 2007 including coordination meetings between KLH, Ministries of Trade, Industry and Customs to streamline enforcement. | [13 empty] | 2007 | Investment | 0 |  |  |  | Latest | Latest | Latest
ONG | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fifth tranche) | Multiyear | ASP | IDS | REF | 51 | INV | 178 | N | O | I | CFC | 110 | 110 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 | 2009-12-01 |  |  | 125800 | 0 | 125800 | 24447 | 19.43% | 101353 | 101353 | 101353 | 10002 | 0 | 1943.71 | 8058.29 | 8058.29 | Investment part of the project completed. A network with local government has been established aiming to create a monitoring program. Remaining funds reallocated for a follow-up training workshop, to support a regional training center, capacity building and monitoring of the MAC recycling program in the region as well as a campaign to promote use of 3R equipment. | [13 empty] | 2006 | INV | 475 | 475 | 0 | 0 | Yes | No | No
ONG | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 179 | N | O | I | CFC | 322 | 300 | 0 | 0 | 2007-03-01 |  | 2009-03-01 | 2010-01-01 |  |  | 159555 | 0 | 159555 | 0 | 0% | 159555 | 0 | 31911 | 13160 | 0 | 0 | 13160 | 0 | 148 sets of refrigeration servicing equipment and 100 sets of refrigerant identifiers procured. 34 end-users completed conversions under the pilot retrofitting/replacement demonstration programme. Technical assistance activities conducted. Disbursements will be reflected as soon as disbursements of previous phase will be exhausted as they are managed as one programme. | [13 empty] | 2007 | Investment | 0 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IDS | SEV | 53 | INS | 180 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 | 2009-11-01 |  |  | 271245 | 0 | 271245 | 11726 | 4.323% | 259519 | 0 | 103807.6 | 20343 | 0 | 879.4338 | 19463.5662 | 0 | Monitoring of implementation of ongoing plans, policy and regulatory actions, awareness and information dissemination activities are all ongoing. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (sixth tranche) | Multi-Year | ASP | IDS | REF | 54 | INV | 181 | N | O | I | CFC | 241 | 241 | 0 | 0 | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 181000 | 0 | 181000 | 0 | 0% | 181000 | 0 | 36200 | 16290 | 0 | 0 | 16290 | 0 | Certificates of completions and handover protocols issued to all enterprises who participated in the project and completed conversions. Government issued decree to ban import of CFCs from 01 January 2008. | [13 empty] | 2008 | Investment
ONG | IBRD | Phase-out of residual CFCs in the foam sector (fourth tranche) | Multiyear | ASP | IDS | FOA | 54 | INV | 182 | N | O | I | CFC | 66 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-31 | 2010-06-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 35000 | 5000 | 2625 | 0 | 0 | 2625 | 2625 | Monitoring and evaluation activities as well as capacity building for local government will continue into 2010 and are expected to be completed by June 2010. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 |  | No | No
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | IDS | PHA | 55 | PRP | 183 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 173750 | 0 | 173750 | 0 | 0% | 173750 | 0 | 173750 | 13031 | 0 | 0 | 13031 | 0 | Approved at 55th ExCom. Sector technical working groups and national HPMP coordination group constituted. Preparation for inception workshop in February 2009 in cooperation with ASHRAE Indonesia. | [13 empty] | 2008 | Investment
ONG | IBRD | Technical assistance to implement national transition strategy to CFC-free MDI | Multi-Year Partial Phase-out | ASP | IDS | ARS | 56 | TAS | 184 | N | O | I | CFC | 16.3 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-31 | 2010-12-31 |  |  | 155000 | 0 | 155000 | 0 | 0% | 155000 | 155000 | 85000 | 13950 | 0 | 0 | 13950 | 13950 | Implementation plan, including project schedule has been reviewed by MDI team and will be finalised by Mar 09. TOR for national consultant is being prepared by NOU. | [13 empty] | 2006 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Assistance in project preparation in all sectors | Individual | ASP | IND | SEV | 08 | PRP | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 100000 | -18339 | 81661 | 81661 | 100% | 0 | 0 | 0 | 13000 | -2384 | 10616 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IND | SEV | 08 | INS | 2 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-06-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 430600 | -1671 | 428929 | 428929 | 100% | 0 | 0 | 0 | 55978 | -217 | 55761 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IND | SEV | 09 | CPG | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1993-11-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1993 | Non-Investment
FIN | IBRD | User-sector pre-investment studies |  | ASP | IND | SEV | 09 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 400000 | 11292 | 411292 | 411292 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Feasibility study for recovery/recycling of CFC refrigerants | RMP | ASP | IND | REF | 10 | TAS | 5 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-02-01 | 1993-10-01 |  | 1998-06-01 | 1999-08-01 | 55000 | -42920 | 12080 | 12080 | 100% | 0 | 0 |  | 7150 | -5582 | 1568 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phasing out ODS in the unorganized sector | Individual | ASP | IND | SEV | 10 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-05-01 | 1993-10-01 |  | 1999-12-01 | 2000-09-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Project formulation for the conversion of electronic cleaning processes from CFC-113/alcohol blended and 1,1,1 trichlorethane to non-CFC cleaning | Individual | ASP | IND | SOL | 10 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-10-01 | 1993-10-01 |  | 1998-12-01 | 2000-07-01 | 74000 | -332 | 73668 | 73668 | 100% | 0 | 0 |  | 9620 | -58 | 9562 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | IBRD | Substitution of CFC-11 refrigerant by HCFC-123 in centrifugal chillers (Blue Star) | Individual | ASP | IND | REF | 10 | INV | 8 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1993-06-01 | 1995-07-01 | 1996-06-01 |  | 1997-12-01 | 1997-12-01 | 567000 | -146504 | 420496 | 420496 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Shriram Industries | Individual | ASP | IND | REF | 10 | INV | 9 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 1997-07-01 | 685000 | -309549 | 375451 | 375451 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aero Pharma aerosol conversion | Individual | ASP | IND | ARS | 11 | INV | 10 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1993-11-01 | 1996-08-01 | 1994-11-01 |  | 2000-10-01 | 1998-06-01 | 62520 | 0 | 62520 | 62520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | No change in previous status |  |  | 1997-03-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Survey of ODS use in the small scale (including tiny) and informal sectors, data base generation and ODS transition management planning | Individual | ASP | IND | SEV | 11 | TAS | 11 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-11-01 | 1994-05-01 |  | 1996-12-01 | 2001-12-01 | 120000 | -11230 | 108770 | 108770 | 100% | 0 | 0 | 0 | 15600 | -1460 | 14140 | 0 | 0 | Completed in 1996. Financially completed in 2001. | [13 empty] | 1993 | Non-Investment
FIN | IBRD | Modification of CFC-12 MAC manufacturing for HFC-134a at Subros Ltd. | Individual | ASP | IND | REF | 11 | INV | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1995-11-01 |  | 1998-11-01 | 2003-05-01 | 1710000 | -55496 | 1654504 | 1654504 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at UB Petroproducts Ltd. | Individual | ASP | IND | FOA | 11 | INV | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1999-02-01 | 1996-11-01 |  | 1999-08-01 | 2000-08-01 | 200000 | 291817 | 491817 | 491817.37 | 100% | -0.37 | -0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-04-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at Manali Petrochemical Ltd. | Individual | ASP | IND | FOA | 11 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1997-02-01 | 1996-11-01 |  | 1998-01-01 | 2000-08-01 | 219000 | 211348 | 430348 | 430347.63 | 100% | 0.37 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-04-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor designs for refrigeration and appliances from CFC-12 to HFC-134a at Kirloskar Copeland Ltd. | Individual | ASP | IND | REF | 12 | INV | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1998-03-01 |  | 1999-03-01 | 1999-11-01 | 547900 | -16905 | 530995 | 530994.85 | 100% | 0.15 | 0.15 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-03-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of the use of CFC in the manufacture of extruded polyethylene foam sheet at Camphor and Allied Products Ltd. | Individual | ASP | IND | FOA | 12 | INV | 16 | A | O | R | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1995-12-01 | 1994-09-01 |  | 1995-12-01 | 1997-12-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF panels at Sunpra Ltd. | Individual | ASP | IND | FOA | 12 | INV | 17 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 414000 | -43773 | 370227 | 370227 | 100% | 0 | 0 | 0 | 53820 | -5690 | 48130 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Eagle Flasks Industries Ltd. | Individual | ASP | IND | FOA | 12 | INV | 18 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1995-03-01 |  | 1996-09-01 | 2000-12-01 | 365000 | -3745 | 361255 | 361255 | 100% | 0 | 0 | 0 | 47450 | -487 | 46963 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 12 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IND | SEV | 12 | PRP | 20 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-12-31 | 1994-12-01 |  | 1996-12-01 | 1996-12-01 | 430000 | -241165 | 188835 | 188835 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects for India ODS II (1994) |  | ASP | IND | SEV | 12 | PRP | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 70837 | -6037 | 64800 | 64800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IND | SEV | 12 | TRA | 22 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-03-01 | 1995-03-01 | 345000 | -239292 | 105708 | 105708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation advance of $345,000 to IDBI has been cleared by the Bank to support the preparation of subprojects to be processed thru the umbrella grant agreement. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 as blowing agent in polyurethane foam systems with low and non-ODS materials at Expanded Incorporation | Individual | ASP | IND | FOA | 13 | INV | 23 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1997-04-01 | 1998-07-01 |  | 2000-09-01 | 2000-09-01 | 502130 | -8064 | 494066 | 494066 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 open-type compressor designs for use with HCFC-22 refrigerant at Freezeking Industries Pvt., Ltd. | Individual | ASP | IND | REF | 13 | INV | 24 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1997-07-01 |  | 1999-11-01 | 2000-12-01 | 240500 | -25806 | 214694 | 214694.04 | 100% | -0.04 | -0.04 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents aqueous cleaning at ITI Mankapur | Individual | ASP | IND | SOL | 13 | INV | 25 | A | O | I | CFC | 34 | 48.8 |  |  | 1994-07-01 | 1996-06-01 | 1996-01-01 |  | 1996-10-01 | 2000-12-01 | 610160 | 0 | 610160 | 610160 | 100% | 0 | 0 |  | 79321 | -2 | 79319 | 0 | 0 | FIN
FIN | IBRD | ODS phase-out in sterilization and siliconisation of disposable syringes and needle at Hindustan Syringes and Medical Devices Private Ltd., Haryana | Individual | ASP | IND | SOL | 13 | INV | 26 | N | O | I | CFC | 53.2 | 56 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1996-12-01 | 1998-09-01 | 481000 | -22298 | 458702 | 458702 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase out of CFC-11 in the manufacture of phenolic foam at Bakelite Hylam Ltd. | Individual | ASP | IND | FOA | 13 | INV | 27 | A | O | I | CFC | 58 | 58 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1998-11-01 | 1999-12-01 | 367000 | 0 | 367000 | 367000 | 100% | 0 | 0 | 0 | 47710 | 0 | 47710 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1994 | Investment
FIN | UNDP | Demonstration and evaluation of alternative technology for halon fire protection system and technical assistance for sectoral strategy for ODS phase out | Individual | ASP | IND | HAL | 13 | DEM | 28 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-01 | 1997-07-01 |  | 1999-12-01 | 2003-02-01 | 309000 | -44111 | 264889 | 264889 | 100% | 0 | 0 | 0 | 40170 | -5734 | 34436 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-06-01 | [9 empty] | 1994 | Non-Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | IND | FOA | 13 | TAS | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1998-07-01 | 1995-07-01 |  | 1999-12-01 | 2003-05-01 | 200000 | -1396 | 198604 | 198604 | 100% | 0 | 0 | 0 | 26000 | -182 | 25818 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non-Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of polyurethane foam at U-Foam Private Ltd. | Individual | ASP | IND | FOA | 13 | INV | 30 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1997-11-01 | 2000-12-01 | 328500 | -77822 | 250678 | 250678 | 100% | 0 | 0 | 0 | 42705 | -10117 | 32588 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | Canada | Initiative to help phase out the release of ODS by Asian SMEs | Individual | ASP | IND | SEV | 15 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1996-02-01 | 1996-02-01 | 109780 | 0 | 109780 | 109780 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | [10 empty] | 1994 | Non-Inv.
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | IND | SEV | 16 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 24065 | 0 | 24065 | 24065 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IND | SEV | 16 | PRP | 33 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 355246 | 0 | 355246 | 355246 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible slabstock PUF at Duroflex Coir Industries P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 34 | N | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1997-01-01 |  | 1997-08-01 | 1998-03-01 | 100800 | -7422 | 93378 | 93378 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF at Industrial Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 35 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1997-08-01 | 1997-06-01 | 320000 | -9500 | 310500 | 310500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Arts (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 36 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-05-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Ashish Plastics P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 37 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible polyurtehane foams at Karnataka Consumer Products Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 38 | N | O | I | CFC | 27 | 27 | 0 | 0 | 1995-07-01 | 1999-06-01 | 1997-01-01 |  | 2000-03-01 | 2001-07-01 | 253200 | -103341 | 149859 | 149859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1998-12-01 | 1999-09-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of moulded PUF at Madras Polymoulds (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 39 | N | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1997-10-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 167700 | -57255 | 110445 | 110445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-12-01 | 1999-01-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Plastics Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 40 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 456500 | -81683 | 374817 | 374817 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Polyplas (India) Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 41 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 236000 | -52332 | 183668 | 183668 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Panorama Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 42 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Polynate Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 43 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-02-01 | 2001-10-01 | 278000 | -1057 | 276943 | 276943 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | 1999-02-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Sree Precoated Steels Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 44 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1997-01-01 |  |  | 1999-11-01 | 224000 | -224000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled |  |  | 1998-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Vikram Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 45 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 236000 | -52312 | 183688 | 183688 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Tranquil Rubber Sales Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 46 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1998-04-01 | 2000-07-01 | 215250 | -79521 | 135729 | 135729 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Real Polymers | Individual | ASP | IND | FOA | 17 | INV | 47 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  | 1998-09-01 | 1998-07-01 | 276200 | -51275 | 224925 | 224925 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of PUF moldings at Vijayjyot Seats Ltd. | Individual | ASP | IND | FOA | 17 | INV | 48 | N | O | I | CFC | 49 | 49 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1998-09-01 | 1999-12-01 | 335500 | -25979 | 309521 | 309521 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF automotive seats at Polyflex (India) P. Ltd. | Individual | ASP | IND | FOA | 17 | INV | 49 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1998-03-01 | 1997-01-01 |  | 1998-09-01 | 2002-01-01 | 222400 | -6000 | 216400 | 216400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 17 | DEM | 50 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1995-07-01 | 181550 | -181550 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project implementation has been transferred to UNDP. |  |  | 1996-06-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Alfa Foams (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 51 | N | O | I | CFC | 19 | 19 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1997-10-01 | 2000-11-01 | 219900 | -27875 | 192025 | 192025.49 | 100% | -0.49 | -0.49 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Blue Star Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 52 | N | O | I | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1998-06-01 | 2000-12-01 | 224000 | -55898 | 168102 | 168102 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | UNIDO | Preparation of umbrella project for ODS phase out in the Aerosol sector (small-scale industries) | Individual | ASP | IND | ARS | 18 | PRP | 53 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-05-01 |  |  | 1997-06-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | IBRD | Phase out of CFCs in the manufacture of integral skin PUF moldings at Pfeda Synthetics (P) Ltd. | Individual | ASP | IND | FOA | 18 | INV | 54 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-05-01 |  | 1998-04-01 | 1999-09-01 | 335728 | -14893 | 320835 | 320834.93 | 100% | 0.07 | 0.07 |  | 43644.64 | -1936.09 | 41708.55 | 0 | 0 | Complete. |  |  | 1997-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at Bharat Seats Ltd. | Individual | ASP | IND | FOA | 18 | INV | 55 | N | O | R | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-03-01 |  | 1993-07-01 | 1996-12-01 | 514563 | -563 | 514000 | 514000 | 100% | 0 | 0 |  | 66893.19 | -73.19 | 66820 | 0 | 0 | Complete. |  |  | 1993-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at PUR Polyurethane Products P. Ltd. | Individual | ASP | IND | FOA | 18 | INV | 56 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2002-03-01 | 2005-01-01 | 187864 | -41523 | 146341 | 146341 | 100% | 0 | 0 |  | 24422.32 | -5397.99 | 19024.33 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 1997-12-01 | 1999-02-01 | 2000-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFCs in the manufacture of extruded polyethylene foam at Kunstoff Polymers Ltd. | Individual | ASP | IND | FOA | 18 | INV | 57 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1997-02-01 | 239320 | -239320 | 0 | 0 |  | 0 | 0 |  | 31111.6 | -31111.6 | 0 | 0 | 0 | Cancelled |  |  | 1997-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Shroff Textiles Ltd. | Individual | ASP | IND | FOA | 18 | INV | 58 | N | O | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1998-05-01 | 1997-05-01 |  | 2000-06-01 | 2001-01-01 | 197200 | 0 | 197200 | 197200 | 100% | 0 | 0 |  | 25636 | 0 | 25636 | 0 | 0 | Project completed and PCR submitted |  |  | 1997-12-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of rigid PUF products at SDC Polyurethane Products Ltd. | Individual | ASP | IND | FOA | 18 | INV | 59 | N | O | I | CFC | 24 | 24 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1997-05-01 |  | 1998-06-01 | 2000-07-01 | 160971 | 0 | 160971 | 160970.73 | 100% | 0.27 | 0.27 |  | 20926.23 | 0 | 20926.19 | 0.04 | 0.04 | Project completed and PCR submitted. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from halon-1211 to ABC dry chemical power (ABC-DCP) and carbon dioxide (CO2) in portable extinguishers at Real Value Appliances Ltd. | Individual | ASP | IND | HAL | 18 | INV | 60 | N | O | I | HAL | 462 | 462 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 2003-07-01 | 251736 | -251736 | 0 | 0 |  | 0 | 0 |  | 32725.68 | -32725.68 | 0 | 0 | 0 | Project cancelled at the 39th ExCom. |  |  | 1998-06-01 |  | 2000-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Meghdoot Refrigeration Industries | Individual | ASP | IND | REF | 18 | INV | 61 | N | O | I | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-01-01 | 2000-07-01 | 164590 | -5660 | 158930 | 158929.9 | 100% | 0.1 | 0.1 |  | 21396.7 | -735.8 | 20660.9 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-08-01 | 1999-05-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna & Co. | Individual | ASP | IND | REF | 18 | INV | 62 | N | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-06-01 | 2001-06-01 | 147020 | -11574 | 135446 | 135446 | 100% | 0 | 0 |  | 19112.6 | -1504.62 | 17607.98 | 0 | 0 | Project completed and PCR submitted |  |  | 1997-08-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna Engineers P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 63 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2001-04-01 | 2003-10-01 | 202790 | -81830 | 120960 | 120960 | 100% | 0 | 0 |  | 26362.7 | -10637.87 | 15725.13 | -0.3 | -0.3 | Project completed. |  |  | 1997-08-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Friz-Tech P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 64 | N | O | I | CFC | 12 | 11.5 | 0 | 0 | 1995-11-01 | 1997-11-01 | 1997-05-01 |  | 2000-03-01 | 2002-07-01 | 132920 | 0 | 132920 | 132920 | 100% | 0 | 0 |  | 17279.6 | 0 | 17279.6 | 0 | 0 |  |  |  | 1997-08-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of electronic cleaning processes for ODS solvents to non-clean and hydrocarbon cleaning technologies at ERL-Bangalore | Individual | ASP | IND | SOL | 18 | INV | 65 | A | O | I | CFC TCA | 16.4 | 16.4 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2000-12-01 | 192421 | -1899 | 190522 | 190522 | 100% | 0 | 0 |  | 25015 | -286 | 24729 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to no-clean and aqueous photo resist developing and stripping technologies at ITI Palakkad | Individual | ASP | IND | SOL | 18 | INV | 66 | A | O | I | CFC TCA | 15 | 15 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1998-08-01 | 235744 | 5652 | 241396 | 241396 | 100% | 0 | 0 |  | 30647 | 734 | 31381 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 18 | PRP | 67 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | ASP | IND | SEV | 18 | PRP | 68 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 19 | DEM | 69 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-09-01 | 1997-06-01 |  | 2001-11-01 | 2002-03-01 | 0 | 168783 | 168783 | 168783 | 100% | 0 | 0 | 0 | 0 | 21942 | 21942 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  |  | 1998-04-01 | [10 empty] | 1996 | Non-Investment
CLO | UNDP | Phase out of CFCs in the manufacture of cold cured molded PUF products at Autofit P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 70 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 103125 | -103125 | 0 | 0 |  | 0 | 0 | 0 | 13406 | -13406 | 0 | 0 | 0 | Canceled in 1998. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plastic Products | Individual | ASP | IND | FOA | 19 | INV | 71 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2000-12-01 | 2002-03-01 | 96000 | -889 | 95111 | 95111 | 100% | 0 | 0 | 0 | 12480 | -116 | 12364 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-06-01 | [9 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products in Inalsa Ltd. | Individual | ASP | IND | FOA | 19 | INV | 72 | A | O | I | CFC | 28.9 | 28.9 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2000-12-01 | 123000 | -4222 | 118778 | 118778 | 100% | 0 | 0 | 0 | 15990 | -549 | 15441 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products at Omkar PUF Insulation | Individual | ASP | IND | FOA | 19 | INV | 73 | A | O | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 59000 | -151 | 58849 | 58849 | 100% | 0 | 0 | 0 | 7670 | -20 | 7650 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of cold cured molded and integral skin PUF products at Kaygee Foams P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 74 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 217250 | -1198 | 216052 | 216052 | 100% | 0 | 0 | 0 | 28243 | -156 | 28087 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Mahavir Enterprises | Individual | ASP | IND | FOA | 19 | INV | 75 | A | O | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 2000-08-01 | 2001-12-01 | 94500 | -220 | 94280 | 94280 | 100% | 0 | 0 | 0 | 12285 | -28 | 12257 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  |  | 1999-07-01 | [9 empty] | 1996 | Investment
FIN | UNDP | Phase out of the CFCs in the manufacture of cold cured molded and integral skin PUF products at Preto Foams | Individual | ASP | IND | FOA | 19 | INV | 76 | A | O | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-11-01 | 2000-12-01 | 167100 | -17268 | 149832 | 149832 | 100% | 0 | 0 | 0 | 21723 | -2245 | 19478 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | IBRD | Phase-out of CFCs in the manufacture of molded PUF automotive seat cushions at Roloforms Polymer Ltd. | Individual | ASP | IND | FOA | 19 | INV | 77 | N | O | I | CFC | 26 | 26 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-03-01 | 162400 | -38657 | 123743 | 123743 | 100% | 0 | 0 |  | 21112 | -5025.41 | 16086.59 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-01-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF insulated thermoware at Asha Handicrafts (formerly Asian Advertisers) | Individual | ASP | IND | FOA | 19 | INV | 78 | A | O | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 122500 | -6656 | 115844 | 115844 | 100% | 0 | 0 | 0 | 15925 | -865 | 15060 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured and integral skin PUF moldings at Amit Polyseats Ltd. | Individual | ASP | IND | FOA | 19 | INV | 79 | A | O | I | CFC | 19.3 | 19.3 | 0 | 0 | 1996-05-01 | 1996-10-01 | 1997-11-01 |  | 1997-06-01 | 2000-07-01 | 243000 | -28744 | 214256 | 214256 | 100% | 0 | 0 | 0 | 31590 | -3737 | 27853 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF spray insulation at Beardsell Ltd. | Individual | ASP | IND | FOA | 19 | INV | 80 | A | O | I | CFC | 21.2 | 21.2 | 0 | 0 | 1996-05-01 | 2000-05-01 | 1997-11-01 |  | 2000-11-01 | 2002-03-01 | 129000 | -19305 | 109695 | 109695 | 100% | 0 | 0 | 0 | 16770 | -2510 | 14260 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-12-01 | [9 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF products at Lloyd Insulations and Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 81 | A | O | I | CFC | 76.7 | 76.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-09-01 | 2000-12-01 | 500000 | -35883 | 464117 | 464117 | 100% | 0 | 0 | 0 | 65000 | -4665 | 60335 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Meenakshi Polymers Pvt. Ltd. | Individual | ASP | IND | FOA | 19 | INV | 82 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1996-11-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 214000 | -38836 | 175164 | 175164 | 100% | 0 | 0 | 0 | 27820 | -5049 | 22771 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Punjab Scooters Ltd. | Individual | ASP | IND | FOA | 19 | INV | 83 | A | O | I | CFC | 39 | 39 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 312200 | -23972 | 288228 | 288228 | 100% | 0 | 0 | 0 | 40586 | -3116 | 37470 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF products at Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 84 | N | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2001-03-01 | 140190 | -26 | 140164 | 140164 | 100% | 0 | 0 |  | 18224.7 | -3.38 | 18221.32 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF for insulated thermoware at Arihant Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 85 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 146450 | -146450 | 0 | 0 |  | 0 | 0 |  | 19038.5 | -19038.5 | 0 | 0 | 0 | Cancelled. |  |  | 1998-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Plast | Individual | ASP | IND | FOA | 19 | INV | 86 | N | O | I | CFC | 21 | 21 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 141320 | -546 | 140774 | 140773.84 | 100% | 0.16 | 0.16 |  | 18372 | -70.98 | 18301.02 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 87 | N | O | I | CFC | 17.4 | 17.4 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 129420 | 0 | 129420 | 129420 | 100% | 0 | 0 |  | 16824.6 | 0 | 16824.6 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Wimco Pen Co. | Individual | ASP | IND | FOA | 19 | INV | 88 | N | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 119290 | -4225 | 115065 | 115065 | 100% | 0 | 0 |  | 15507.7 | -549.25 | 14958.45 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | 1999-03-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rabi-Run Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 89 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 2001-01-01 | 2002-09-01 | 142622 | -2428 | 140194 | 140194.28 | 100% | -0.28 | -0.28 |  | 18541 | -315.64 | 18225.36 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 1998-02-01 |  | 2000-06-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Seepra Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 90 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1998-08-01 | 1999-12-01 | 171910 | -10400 | 161510 | 161510 | 100% | 0 | 0 |  | 22348 | -1352 | 20996 | 0 | 0 | Complete. |  |  | 1998-02-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Shakti Fabricators | Individual | ASP | IND | REF | 19 | INV | 91 | N | O | I | CFC | 13.5 | 13.5 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 2001-11-01 | 2003-10-01 | 159230 | -926 | 158304 | 158304 | 100% | 0 | 0 |  | 20699.9 | -120.42 | 20579.58 | -0.1 | -0.1 | Project completed. |  |  | 1998-02-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Chandra Frig Co. P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 92 | N | O | I | CFC | 9.4 | 4.8 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  |  | 2004-04-01 | 130984 | -64197 | 66787 | 66787.07 | 100% | -0.07 | -0.07 |  | 17028 | -8346 | 8682.32 | -0.32 | -0.32 | Project cancelled at the 42nd ExCom and balance returned at the 43rd ExCom. Bank has requested FI to examine the SGA to find out appropriate course of action for recuperation of equipment. Process underway. |  |  | 1998-02-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rockwell Devices P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 93 | N | O | I | CFC | 18 | 18 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-07-01 | 2000-09-01 | 181004 | -9611 | 171393 | 171392.74 | 100% | 0.26 | 0.26 |  | 23530.52 | -1249.43 | 22281.09 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sethia Appliances P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 94 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 2000-08-01 | 173384 | -6586 | 166798 | 166798.3 | 100% | -0.3 | -0.3 |  | 22540 | -856.18 | 21683.82 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to semi-aqueous cleaning and no-clean soldering technologies at ITI, Bangalore | Individual | ASP | IND | SOL | 19 | INV | 95 | A | O | I | CFC TCA | 7 | 7 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1996-12-01 | 1999-08-01 | 107954 | -808 | 107146 | 107146 | 100% | 0 | 0 |  | 14034 | -127 | 13907 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Amar Enterprises | Individual | ASP | IND | FOA | 20 | INV | 96 | A | O | I | CFC | 16.2 | 16.2 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 120000 | -57 | 119943 | 119943 | 100% | 0 | 0 | 0 | 15600 | -7 | 15593 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plast | Individual | ASP | IND | FOA | 20 | INV | 97 | A | O | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 71000 | -104 | 70896 | 70896 | 100% | 0 | 0 | 0 | 9230 | -13 | 9217 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Cottage Industries | Individual | ASP | IND | FOA | 20 | INV | 98 | A | O | I | CFC | 7.8 | 7.8 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 61000 | -2047 | 58953 | 58953 | 100% | 0 | 0 | 0 | 7930 | -266 | 7664 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at K.B. Poly Industries P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 99 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 149000 | -19595 | 129405 | 129405 | 100% | 0 | 0 | 0 | 19370 | -2547 | 16823 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Deccan Engineering Enterprises | Individual | ASP | IND | FOA | 20 | INV | 100 | A | O | I | CFC | 8.3 | 8.3 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 64000 | -3303 | 60697 | 60697 | 100% | 0 | 0 | 0 | 8320 | -429 | 7891 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of EPE foam products at Vora Cork Industries | Individual | ASP | IND | FOA | 20 | INV | 101 | A | O | I | CFC | 39.6 | 39.6 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 2003-07-01 | 2005-09-01 | 264500 | -52153 | 212347 | 212347 | 100% | 0 | 0 | 0 | 34385 | -6780 | 27605 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  |  |  | 1999-09-01 | [9 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Best Plastronics P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 102 | A | O | I | CFC | 19.5 | 19.5 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 129000 | -35002 | 93998 | 93998 | 100% | 0 | 0 | 0 | 16770 | -4550 | 12220 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [9 empty] | 1996 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at Krishna Fabrications Ltd. | Individual | ASP | IND | FOA | 20 | INV | 103 | A | O | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 164000 | -21543 | 142457 | 142457 | 100% | 0 | 0 | 0 | 21320 | -2801 | 18519 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | FOA | 20 | INV | 104 | N | O | I | CFC | 568 | 568 | 0 | 0 | 1996-10-01 | 1999-01-01 | 1999-02-01 |  | 1999-07-01 | 2003-10-01 | 2691570 | -27265 | 2664305 | 2664305 | 100% | 0 | 0 |  | 349904.1 | -3544.45 | 346359.55 | 0.1 | 0.1 | Project completed. |  |  |  | 2000-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Supercold Refrigeration Systems P. Ltd. | Individual | ASP | IND | REF | 20 | INV | 105 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1996-10-01 | 2000-12-01 | 1998-04-01 |  | 2001-04-01 | 2002-05-01 | 133770 | -3495 | 130275 | 130275 | 100% | 0 | 0 |  | 17390.1 | -454.35 | 16935.75 | 0 | 0 | Enterprise has submitted the draft PCR which will be sent to the Bank by April 15, 2003. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Murali Refrigeration and Engineering Co. | Individual | ASP | IND | REF | 20 | INV | 106 | N | O | I | CFC | 9 | 9 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-04-01 |  | 1999-06-01 | 2000-10-01 | 126485 | -1539 | 124946 | 124945.52 | 100% | 0.48 | 0.48 |  | 16443.05 | -200.07 | 16242.98 | 0 | 0 | Project completed and PCR submitted | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening project for the phaseout of ODSs under the Montreal Protocol: Phase II | Individual | ASP | IND | SEV | 20 | INS | 107 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1999-03-01 | 1999-12-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 1999. Financially completed in 1999. | [13 empty] | 1996 | Non-Investment
FIN | IBRD | Project preparation in the refrigeration sector |  | ASP | IND | REF | 21 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1998-06-01 | 1998-06-01 | 243000 | 0 | 243000 | 243000 | 100% | 0 | 0 |  | 31590 | 0 | 31590 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | IND | SEV | 21 | PRP | 109 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-11-01 | 2000-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigeration Components and Accessories | Individual | ASP | IND | REF | 22 | INV | 110 | N | O | I | CFC | 9.5 | 9.5 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 125370 | -75182.45 | 50187.55 | 50187.55 | 100% | 0 | 0 |  | 16298.1 | -9773.72 | 6524.38 | 0 | 0 | Project financially completed and balance funds returned. |  |  |  |  | 2000-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam chemical systems at Polymermann (Asia) P.Ltd. | Individual | ASP | IND | FOA | 22 | INV | 111 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2003-11-01 | 385000 | -4930 | 380070 | 380070 | 100% | 0 | 0 | 0 | 50050 | -641 | 49409 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-07-01 | [9 empty] | 1997 | Investment
FIN | IBRD | Elimination of 1,1,1 TCA from the precision cleaning processes at Modi Xerox | Individual | ASP | IND | SOL | 22 | INV | 112 | N | O | I | TCA | 6.07 | 6.07 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1998-06-01 | 1998-01-01 | 130819 | -25985 | 104834 | 104834 | 100% | 0 | 0 |  | 17006.47 | -3378.05 | 13628.42 | 0 | 0 | Complete. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Stella Industries aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 113 | N | O | I | CFC | 105 | 105 | 0 | 0 | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-09-01 | 1998-09-01 | 269175 | 0 | 269175 | 269175 | 100% | 0 | 0 |  | 34992.75 | 0 | 34992.75 | 0 | 0 | Project completed. PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Accra Pack India Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 114 | N | O | I | CFC | 52 | 52 | 0 | 0 | 1997-05-01 | 1999-02-01 | 1998-06-01 |  | 2001-07-01 | 2002-04-01 | 129690 | -7545 | 122145 | 122145 | 100% | 0 | 0 |  | 16859.7 | -980.85 | 15878.85 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  |  | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Ultra Tech Specialty Chemicals Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 115 | A | O | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-09-01 | [9 empty] | 1997 | Investment
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Pranav Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 116 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 2002-03-01 | 2002-12-01 | 944914 | -90669 | 854245 | 854245 | 100% | 0 | 0 |  | 122838.82 | -11786.97 | 111051.85 | 0 | 0 | Draft PCR submitted to ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Texas Enterprises aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 117 | A | O | I | CFC | 31.2 | 31.2 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 70000 | -4903 | 65097 | 65097 | 100% | 0 | 0 | 0 | 9100 | -637 | 8463 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [9 empty] | 1997 | Investment
FIN | UNDP | Aerol Formulations aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 118 | A | O | I | CFC | 31 | 31 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -791 | 68659 | 68659 | 100% | 0 | 0 | 0 | 9029 | -103 | 8926 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [9 empty] | 1997 | Investment
FIN | IBRD | My Fair Lady aerosol conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 119 | N | O | I | CFC | 59.4 | 59.4 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1998-06-01 |  | 2000-12-01 | 2002-09-01 | 113975 | -16195 | 97780 | 97780.37 | 100% | -0.37 | -0.37 |  | 14816.75 | -2105.35 | 12711.4 | 0 | 0 | PCR finalized and submitted to ExCom. |  |  |  | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Standard Refrigeration Appliances | Individual | ASP | IND | REF | 22 | INV | 120 | N | O | I | CFC | 18.8 | 18.8 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-11-01 |  | 2000-08-01 | 2000-12-01 | 170180 | -166 | 170014 | 170014 | 100% | 0 | 0 |  | 22123.4 | -21.58 | 22101.82 | 0 | 0 | Project completed and PCR submitted | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Sanden Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 121 | N | O | I | CFC | 8.36 | 8.36 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2002-03-01 | 2002-04-01 | 490820 | -111557 | 379263 | 379263 | 100% | 0 | 0 |  | 63806.6 | -14502.41 | 49304.19 | 0 | 0 | Draft PCR submitted to the ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sheetal Engineering Works P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 122 | N | O | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-02-01 | 2001-06-01 | 127630 | -28297 | 99333 | 99333 | 100% | 0 | 0 |  | 16591.9 | -3678.61 | 12913.29 | 0 | 0 | Project completed. PCR will be submitted January 2001. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Hindustan Refrigeration Industries | Individual | ASP | IND | REF | 22 | INV | 123 | N | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 132320 | -81327 | 50993 | 50993 | 100% | 0 | 0 |  | 17201.6 | -10572.51 | 6629.09 | 0 | 0 | Project financially completed and balance funds returned. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 124 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 147300 | -95904.45 | 51395.55 | 51395.55 | 100% | 0 | 0 |  | 19149 | -12467.58 | 6681.42 | 0 | 0 | Project financially completed and balance funds returned. |  |  |  |  | 2000-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Maharaja International Ltd. | Individual | ASP | IND | REF | 22 | INV | 125 | N | O | I | CFC | 59.8 | 59.8 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-11-01 |  | 2004-01-01 | 2005-01-01 | 510000 | -261775.31 | 248224.69 | 248224.69 | 100% | 0 | 0 |  | 66300 | -34030.79 | 32269.21 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [5 empty] | 2001-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HCF-134a refrigerant at Voltas Ltd. | Individual | ASP | IND | REF | 22 | INV | 126 | N | O | I | CFC | 379.83 | 379.83 | 0 | 0 | 1997-05-01 | 2000-07-01 | 2001-12-01 |  | 2003-11-01 | 2005-01-01 | 2724378 | -1093985 | 1630393 | 1630393 | 100% | 0 | 0 |  | 354169.14 | -142218 | 211951 | 0.14 | 0.14 | Project financially completed and balance funds returned. |  |  |  | 1999-11-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects for submission in 1997 and 1998 |  | ASP | IND | REF | 22 | PRP | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Blowkings | Individual | ASP | IND | FOA | 22 | INV | 128 | A | O | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 132000 | -14394 | 117606 | 117606 | 100% | 0 | 0 | 0 | 17160 | -1871 | 15289 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | ASP | IND | SEV | 22 | PRP | 129 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Delta Foams Engineering Co. | Individual | ASP | IND | FOA | 22 | INV | 130 | A | O | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 2001-12-01 | 85000 | -15226 | 69774 | 69774 | 100% | 0 | 0 | 0 | 11050 | -1979 | 9071 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Polar Enterprises | Individual | ASP | IND | REF | 22 | INV | 131 | N | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1999-09-01 | 2001-07-01 | 138190 | -189 | 138001 | 138001 | 100% | 0 | 0 |  | 17964.7 | -24.57 | 17940.13 | 0 | 0 | Project completed and PCR submitted | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Super Urethane Products P. Ltd. | Individual | ASP | IND | FOA | 22 | INV | 132 | A | O | I | CFC | 39.1 | 39.1 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 284000 | -36532 | 247468 | 247468 | 100% | 0 | 0 | 0 | 36920 | -4749 | 32171 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam in small and medium-sized enterprises (SMEs) | Individual | ASP | IND | FOA | 22 | INV | 133 | A | O | I | CFC | 290 | 290 | 0 | 0 | 1997-05-01 | 1997-12-01 | 2000-06-01 |  | 2001-12-01 | 2003-03-01 | 1404000 | -79 | 1403921 | 1403921 | 100% | 0 | 0 | 0 | 182520 | -10 | 182510 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 2000-06-01 | [9 empty] | 1997 | Investment
FIN | IBRD | Conversion of refrigerator manufacture to cyclopentane foam blowing agent and to HCF-134a refrigerant at Videocon Appliances Ltd. | Individual | ASP | IND | REF | 22 | INV | 134 | N | O | I | CFC | 351.7 | 351.7 | 0 | 0 | 1997-05-01 | 1999-10-01 | 1999-11-01 |  | 2001-12-01 | 2002-08-01 | 1835115 | 524053.41 | 2359168.41 | 2359168.41 | 100% | 0 | 0 |  | 238564.95 | 61500.14 | 300065.09 | 0 | 0 | Project physically completed in 2001, however, was not reported as such by FI in time for the 2001 progress report. Subsequent draft PCR has confirmed correct date of completion. |  |  |  | 1999-11-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Aerosols D'Asia Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 135 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -2379 | 67071 | 67071 | 100% | 0 | 0 | 0 | 9029 | -309 | 8720 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [9 empty] | 1997 | Investment
FIN | UNDP | Asian Aerosols Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 136 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 90890 | -7767 | 83123 | 83123 | 100% | 0 | 0 | 0 | 11816 | -1010 | 10806 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-09-01 | [9 empty] | 1997 | Investment
FIN | IBRD | Attarwala and Co. Pvt. Ltd. aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 137 | N | O | I | CFC | 30.6 | 30.6 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2002-12-01 | 2005-01-01 | 134250 | -12102 | 122148 | 122148 | 100% | 0 | 0 |  | 17452.5 | -1573.26 | 15879.24 | 0 | 0 | Project financially completed and balance funds returned to ExCom. PCR submitted. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Aero Pack Products aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 138 | A | O | I | CFC | 20.4 | 20.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-04-01 | 69450 | 0 | 69450 | 69450 | 100% | 0 | 0 | 0 | 9029 | 0 | 9029 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-09-01 | [9 empty] | 1997 | Investment
FIN | IBRD | Aero Industries aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 139 | N | O | I | CFC | 27.6 | 27.6 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 1999-05-01 | 121735 | -3903 | 117832 | 117832 | 100% | 0 | 0 |  | 15825.55 | -507.39 | 15318.16 | 0 | 0 | Project completed and PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | UNDP | Meenakshi aerosol and cosmetics conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 140 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1998-06-01 |  |  | 1998-07-01 | 98940 | -98940 | 0 | 0 |  | 0 | 0 | 0 | 12862 | -12862 | 0 | 0 | 0 | Canceled in 1998. | [13 empty] | 1997 | Investment
FIN | IBRD | Aeropres aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 141 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 2000-10-01 | 146860 | -4040 | 142820 | 142819.81 | 100% | 0.19 | 0.19 |  | 19091.8 | -525.2 | 18566.6 | 0 | 0 | Project completed and PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IND | SEV | 16 | PRP | 142 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Nissan Thermoware P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 143 | A | O | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 111000 | -706 | 110294 | 110294 | 100% | 0 | 0 | 0 | 14430 | -92 | 14338 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Aarkay Industries | Individual | ASP | IND | REF | 23 | INV | 144 | N | O | I | CFC | 19.8 | 19.8 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 135798 | 15128 | 150926 | 150926 | 100% | 0 | 0 |  | 17654 | 1967 | 19621 | 0 | 0 | PCR is being finalized for submission in 2003. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Saikrupa Industries | Individual | ASP | IND | REF | 23 | INV | 145 | N | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 125618 | 10524 | 136142 | 136142 | 100% | 0 | 0 |  | 16330.34 | 1368.12 | 17698.46 | 0 | 0 | PCR is being finalized for submission in 2003. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Viral Corporation | Individual | ASP | IND | FOA | 23 | INV | 146 | A | O | I | CFC | 11.8 | 11.8 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 84000 | -2736 | 81264 | 81264 | 100% | 0 | 0 | 0 | 10920 | -356 | 10564 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible moulded cold-cured and integral skin PU foam at Venus Auto P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 147 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 137250 | -1155 | 136095 | 136095 | 100% | 0 | 0 | 0 | 17843 | -150 | 17693 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at Siddhi Polymer P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 148 | A | O | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 75250 | -737 | 74513 | 74513 | 100% | 0 | 0 | 0 | 9783 | -96 | 9687 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured moulded and integral skin at Shri Krishna Polyurethane Industries P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 149 | A | O | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-08-01 | 2002-11-01 | 192875 | -486 | 192389 | 192389 | 100% | 0 | 0 | 0 | 25074 | -63 | 25011 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Reliable Rotomoulders P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 150 | A | O | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 63000 | -769 | 62231 | 62231 | 100% | 0 | 0 | 0 | 8190 | -100 | 8090 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Panna International | Individual | ASP | IND | FOA | 23 | INV | 151 | A | O | I | CFC | 9.7 | 9.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1998-12-01 | 2000-12-01 | 48000 | -19370 | 28630 | 28630 | 100% | 0 | 0 | 0 | 6240 | -2518 | 3722 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sarkar Refrigeration Industries | Individual | ASP | IND | REF | 23 | INV | 152 | N | O | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-06-01 |  | 2000-11-01 | 2002-06-01 | 117100 | -1955 | 115145 | 115145 | 100% | 0 | 0 |  | 15223 | -287 | 14936 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  |  | 2000-09-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Malanpur Entech P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 153 | A | O | I | CFC | 18.9 | 18.9 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 148000 | -12388 | 135612 | 135612 | 100% | 0 | 0 | 0 | 19240 | -1610 | 17630 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of integral skin PUF products at Legend Interiors | Individual | ASP | IND | FOA | 23 | INV | 154 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 124000 | -14125 | 109875 | 109875 | 100% | 0 | 0 | 0 | 16120 | -1836 | 14284 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at K. J. Polymers P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 155 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 127550 | -353 | 127197 | 127197 | 100% | 0 | 0 | 0 | 16582 | -46 | 16536 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bluplast Corporation | Individual | ASP | IND | FOA | 23 | INV | 156 | A | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Alaska Industries | Individual | ASP | IND | FOA | 23 | INV | 157 | A | O | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 128000 | -18370 | 109630 | 109630 | 100% | 0 | 0 | 0 | 16640 | -2388 | 14252 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at Ras Polybuild Products P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 158 | A | O | I | CFC | 17.7 | 17.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 128000 | -136 | 127864 | 127864 | 100% | 0 | 0 | 0 | 16640 | -18 | 16622 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of an investment project for phasing out ODS in the refrigeration sector (project under identification | Individual | ASP | IND | REF | 23 | PRP | 159 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2002-05-01 | 25000 | 24369 | 49369 | 49369 | 100% | 0 | 0 |  | 3250 | 3158 | 6408 | 0 | 0 | FIN
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Sidwal Refrigeration Industries P. Ltd. | Individual | ASP | IND | REF | 23 | INV | 160 | N | O | I | CFC | 11.7 | 14.1 | 0 | 0 | 1997-11-01 | 1999-10-01 | 1999-06-01 |  | 2000-09-01 | 2002-05-01 | 169744 | 5038 | 174782 | 174782 | 100% | 0 | 0 |  | 22067 | 655.32 | 22722.32 | 0 | 0 | [15 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation for 3 projects in the aerosol sector | Individual | ASP | IND | ARS | 24 | PRP | 161 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-06-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNIDO | Preparation investment projects in the solvent (CFC 113) sector at Harbans Lal Mahotra & Sons Ltd. Calcutta | Individual | ASP | IND | SOL | 24 | PRP | 162 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 25000 | -177 | 24823 | 24823 | 100% | 0 | 0 |  | 3250 | -28 | 3222 | 0 | 0 | FIN
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Steelage Industries Limited Minimax Division/ Chennai | Individual | ASP | IND | HAL | 24 | INV | 163 | A | O | I | Halon | 116 | 116 | 0 | 0 | 1998-03-01 | 2000-05-01 | 2000-04-01 |  | 2002-01-01 | 2003-04-01 | 131915 | -41454 | 90461 | 90461 | 100% | 0 | 0 | 0 | 17149 | -5389 | 11760 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation to prepare 10 projects in the foam sector | Individual | ASP | IND | FOA | 24 | PRP | 164 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vijay Fire Protection Systems Ltd. | Individual | ASP | IND | HAL | 24 | INV | 165 | A | O | I | Halon | 292 | 292 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 219152 | 0 | 219152 | 219152 | 100% | 0 | 0 | 0 | 28490 | 0 | 28490 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 5 halon extinguisher projects | Individual | ASP | IND | HAL | 24 | PRP | 166 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Sunder Chemical | Individual | ASP | IND | ARS | 24 | INV | 167 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 59892 | -3617 | 56275 | 56275 | 100% | 0 | 0 | 0 | 7786 | -470 | 7316 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Nitin Fire Protection Industries Ltd., Bombay | Individual | ASP | IND | HAL | 24 | INV | 168 | A | O | I | Halon | 212 | 212 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 165818 | 0 | 165818 | 165818 | 100% | 0 | 0 | 0 | 21556 | 0 | 21556 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IND | REF | 24 | PRP | 169 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of production halon-1211 fire extinguishers at Atkins, New Delhi | Individual | ASP | IND | HAL | 24 | INV | 170 | A | O | I | Halon | 37 | 37 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2001-05-01 | 2002-03-01 | 54760 | -739 | 54021 | 54021 | 100% | 0 | 0 | 0 | 7119 | -96 | 7023 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Sara-Chem Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 171 | A | O | I | CFC | 23.3 | 23.3 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 89164 | -29723 | 59441 | 59441 | 100% | 0 | 0 | 0 | 11591 | -3864 | 7727 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Maja Cosmetics Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 172 | A | O | I | CFC | 31.3 | 31.3 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 125240 | -705 | 124535 | 124535 | 100% | 0 | 0 | 0 | 16281 | -92 | 16189 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Spray Products | Individual | ASP | IND | ARS | 24 | INV | 173 | A | O | I | CFC | 16.8 | 16.8 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 65486 | -2975 | 62511 | 62511 | 100% | 0 | 0 | 0 | 8513 | -387 | 8126 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Aerosol conversion at Chem-Verse Consultants | Individual | ASP | IND | ARS | 24 | INV | 174 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 67324 | -1872 | 65452 | 65452 | 100% | 0 | 0 | 0 | 8752 | -243 | 8509 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at New Age Industries, Bombay | Individual | ASP | IND | HAL | 24 | INV | 175 | A | O | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 132248 | -292 | 131956 | 131956 | 100% | 0 | 0 | 0 | 17192 | -38 | 17154 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vimal Industrial Safety Equipment Corporation Baroda, Gujrat | Individual | ASP | IND | HAL | 24 | INV | 176 | A | O | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 186152 | 0 | 186152 | 186152 | 100% | 0 | 0 | 0 | 24200 | 0 | 24200 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Ashoka Engineering Co., New Delhi | Individual | ASP | IND | HAL | 24 | INV | 177 | A | O | I | Halon | 34 | 34 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 50320 | 0 | 50320 | 50320 | 100% | 0 | 0 | 0 | 6542 | 0 | 6542 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation in the refrigeration, solvent and halon production sectors |  | ASP | IND | SEV | 24 | PRP | 178 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Aerosol Conversion at Midas Care Pharmaceuticals | Individual | ASP | IND | ARS | 24 | INV | 179 | A | O | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 110880 | -2729 | 108151 | 108151 | 100% | 0 | 0 | 0 | 14414 | -355 | 14059 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sandeep Refrigeration | Individual | ASP | IND | REF | 25 | INV | 180 | N | O | I | CFC | 9.9 | 9.9 | 0 | 0 | 1998-07-01 | 1999-08-01 | 2000-08-01 |  | 2000-08-01 | 2001-04-01 | 107684 | -773 | 106911 | 106911 | 100% | 0 | 0 |  | 13998.92 | -100.49 | 13898.43 | 0 | 0 | Project completed and PCR submitted | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS solvents to heat cleaning technologies and ODS free solvent coating at Malhotra Shaving Products Ltd. | Individual | ASP | IND | SOL | 25 | INV | 181 | A | O | I | CFC | 13.6 | 13.6 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-01-01 | 255112 | 0 | 255112 | 255112 | 100% | 0 | 0 |  | 33165 | 0 | 33165 | 0 | 0 | FIN
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Prashant Refrigeration Appliances | Individual | ASP | IND | REF | 25 | INV | 182 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 1999-12-01 | 104058 | -104058 | 0 | 0 |  | 0 | 0 |  | 13527.54 | -13528 | 0 | -0.46 | -0.46 | Project has been cancelled. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of domestic refrigerators at BPL Refrigeration Ltd. | Individual | ASP | IND | REF | 25 | INV | 183 | N | O | I | CFC | 136 | 136 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2001-08-01 |  | 2002-12-01 | 2005-01-01 | 722906 | 302123 | 1025029 | 1025029 | 100% | 0 | 0 |  | 93977.78 | 35611.19 | 129588.97 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam at Puff Insulators | Individual | ASP | IND | FOA | 26 | INV | 184 | A | O | I | CFC | 10.6 | 10.6 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-11-01 | 2002-03-01 | 83150 | 0 | 83150 | 83150 | 100% | 0 | 0 | 0 | 10810 | 0 | 10810 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and integral skin foam products to water blown systems in flexible molded polyurethane foam at Joti Foam Pr | Individual | ASP | IND | FOA | 26 | INV | 185 | A | O | I | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 174290 | -287 | 174003 | 174003 | 100% | 0 | 0 | 0 | 22658 | -37 | 22621 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated termoware at Jaypee Technoplast P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 186 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 139860 | -966 | 138894 | 138894 | 100% | 0 | 0 | 0 | 18182 | -126 | 18056 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Sintex Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 187 | A | O | D | CFC | 10.9 | 10.9 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-11-01 | 2003-04-01 | 62980 | -1589 | 61391 | 61391 | 100% | 0 | 0 | 0 | 8187 | -207 | 7980 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at National Flask Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 188 | A | O | I | CFC | 36.9 | 36.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-08-01 | 2002-03-01 | 203870 | -16186 | 187684 | 187684 | 100% | 0 | 0 | 0 | 26503 | -2104 | 24399 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at Jayson Industries | Individual | ASP | IND | FOA | 26 | INV | 189 | A | O | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 88900 | -840 | 88060 | 88060 | 100% | 0 | 0 | 0 | 11557 | -109 | 11448 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC -141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Duab International | Individual | ASP | IND | FOA | 26 | INV | 190 | A | O | I | CFC | 13.4 | 13.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-12-01 | 2001-12-01 | 104490 | 0 | 104490 | 104490 | 100% | 0 | 0 | 0 | 13584 | 0 | 13584 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS to heat cleaning technologies and ODS free solvent coating at Lal Malhotra & Sons Ltd. | Individual | ASP | IND | SOL | 26 | INV | 191 | A | O | I | CFC | 16 | 16 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 308899 | 0 | 308899 | 308899 | 100% | 0 | 0 |  | 40157 | -8 | 40149 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Galaxy FRP P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 192 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 144808 | -1805 | 143003 | 143003 | 100% | 0 | 0 | 0 | 18825 | -235 | 18590 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam insulated thermoware at Ajay Corrugating and Plastics P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 193 | A | O | I | CFC | 10.3 | 10.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 80805 | 0 | 80805 | 80805 | 100% | 0 | 0 | 0 | 10505 | 0 | 10505 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Preparation of ten projects in general foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 194 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | UNIDO | Preparation of investment project in the solvent sector | Individual | ASP | IND | SOL | 27 | PRP | 195 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-07-20 | 2000-11-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam in situ and spray insulation at P.K. Construction Co. | Individual | ASP | IND | FOA | 27 | INV | 196 | A | O | D | CFC | 10.6 | 10.6 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 1999-12-01 | 2001-12-01 | 74172 | -3275 | 70897 | 70897 | 100% | 0 | 0 | 0 | 9642 | -426 | 9216 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ganga Thermoware | Individual | ASP | IND | FOA | 27 | INV | 197 | A | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 78864 | -5388 | 73476 | 73476 | 100% | 0 | 0 | 0 | 10252 | -700 | 9552 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bansal Plastic Industries | Individual | ASP | IND | FOA | 27 | INV | 198 | A | O | I | CFC | 20.4 | 20.4 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 68829 | -6240 | 62589 | 62589 | 100% | 0 | 0 | 0 | 8948 | -811 | 8137 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Renewal of Institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol : Phase 3 | Individual | ASP | IND | SEV | 27 | INS | 199 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2001-04-01 |  | 2001-08-01 | 2002-01-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Preparation of five projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 27 | PRP | 200 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of two projects in aerosol sector | Individual | ASP | IND | ARS | 27 | PRP | 201 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Baba Insulator | Individual | ASP | IND | FOA | 27 | INV | 202 | A | O | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 59096 | -10468 | 48628 | 48628 | 100% | 0 | 0 | 0 | 7682 | -1361 | 6321 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | IBRD | Preparation of projects in the refrigeration, solvent and CFC-halon production sectors |  | ASP | IND | SEV | 27 | PRP | 203 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Whirlpool of India Ltd. | Individual | ASP | IND | REF | 27 | INV | 204 | N | O | I | CFC | 200.6 | 200.6 | 0 | 0 | 1999-03-01 | 2002-12-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 675165 | -276756 | 398409 | 398409 | 100% | 0 | 0 |  | 84268.15 | -39407.54 | 44860.61 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at R.S. Insulators | Individual | ASP | IND | FOA | 27 | INV | 205 | A | O | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 54800 | -10912 | 43888 | 43888 | 100% | 0 | 0 | 0 | 7124 | -1419 | 5705 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of seven projects in rigid foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 206 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Shree Nath Plastics | Individual | ASP | IND | FOA | 27 | INV | 207 | A | O | I | CFC | 13.9 | 13.9 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 61370 | -7114 | 54256 | 54256 | 100% | 0 | 0 | 0 | 7978 | -925 | 7053 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Cascade Counsel Ltd. New Delhi | Individual | ASP | IND | HAL | 28 | INV | 208 | A | O | I | Halon | 54 | 54 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79920 | 0 | 79920 | 79920 | 100% | 0 | 0 | 0 | 10390 | 0 | 10390 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Bharat Engineering Works, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 209 | A | O | I | Halon | 49.5 | 49.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 73260 | -7751 | 65509 | 65509 | 100% | 0 | 0 | 0 | 9524 | -1008 | 8516 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Varivar Plast Products P., Ltd. | Individual | ASP | IND | FOA | 28 | INV | 210 | A | O | I | CFC | 12.3 | 12.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 96184 | -1 | 96183 | 96183 | 100% | 0 | 0 | 0 | 12504 | 0 | 12504 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Supertek International | Individual | ASP | IND | FOA | 28 | INV | 211 | A | O | I | CFC | 10.6 | 10.6 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 83202 | 0 | 83202 | 83202 | 100% | 0 | 0 | 0 | 10816 | 0 | 10816 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Standard Electric Appliances | Individual | ASP | IND | FOA | 28 | INV | 212 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 78136 | 0 | 78136 | 78136 | 100% | 0 | 0 | 0 | 10158 | 0 | 10158 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC at Vimsons Aerosol by substituting with HAPs | Individual | ASP | IND | ARS | 28 | INV | 213 | A | O | I | CTC/CFC | 18.2 | 18.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-03-01 | 2002-11-01 | 66500 | -18505 | 47995 | 47995 | 100% | 0 | 0 | 0 | 8645 | -2406 | 6239 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at O.K. Industries | Individual | ASP | IND | FOA | 28 | INV | 214 | A | O | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 66227 | -2012 | 64215 | 64215 | 100% | 0 | 0 | 0 | 8610 | -262 | 8348 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Primrose Multiplast P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 215 | A | O | D | CFC | 9.6 | 9.6 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 117105 | -1131 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15224 | -147 | 15077 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Zenith Fire Services, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 216 | A | O | I | Halon | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 53280 | -3309 | 49971 | 49971 | 100% | 0 | 0 | 0 | 6926 | -430 | 6496 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | IBRD | Phaseout of use of carbon tetrachloride as process agent in the production of endosulphan by Excel Industries Limited | Individual | ASP | IND | PAG | 28 | INV | 217 | N | O | I | CTC | 375 | 375 | 0 | 0 | 1999-07-01 | 2000-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-03-01 | 366000 | 0 | 366000 | 366000 | 100% | 0 | 0 |  | 47580 | 0 | 47580 | 0 | 0 | PCR to be finalized and submitted in 2003. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to CFC-free technology in the manufacture of rigid polyurethane foam chemical systems at Shivathene Linopack | Individual | ASP | IND | FOA | 28 | INV | 218 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 209000 | -16227 | 192773 | 192773 | 100% | 0 | 0 | 0 | 27170 | -2110 | 25060 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Devisons P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 219 | A | O | I | CFC | 15.3 | 15.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 114940 | -5215 | 109725 | 109725 | 100% | 0 | 0 | 0 | 14942 | -678 | 14264 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Extinguisher production and elimination of its consumption of virgin halon-1301 at New Fire Engineers Pvt. Ltd. Mumbai | Individual | ASP | IND | HAL | 28 | INV | 220 | A | O | I | Halon | 120 | 120 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC by substituting HAPs at Syncaps | Individual | ASP | IND | ARS | 28 | INV | 221 | A | O | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2005-09-01 | 2007-01-01 | 161518 | -15270 | 146248 | 146248 | 100% | 0 | 0 | 0 | 20997 | -1985 | 19012 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher to ABC powder and CO2 units together with the use of recycled halon-1301 in lieu of virgin product at Standard Castings Pvt. Ltd. New Delhi, under the name of Pyrosafety | Individual | ASP | IND | HAL | 28 | INV | 222 | A | O | I | Halon | 64.1 | 64.1 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-11-01 | 92000 | -23084 | 68916 | 68916 | 100% | 0 | 0 | 0 | 11960 | -3001 | 8959 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 and CTC to processes based on IPA at Vidyut Metallics Ltd. (VML) | Individual | ASP | IND | SOL | 28 | INV | 223 | A | O | I | CFC CTC | 19.7 | 19.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2003-09-01 | 2004-06-01 | 225452 | -387 | 225065 | 225065 | 100% | 0 | 0 |  | 29309 | -97 | 29212 | 0 | 0 | FIN | [6 empty] | 2002-03-01
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Nav Texfeb P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 224 | A | O | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 163982 | -3561 | 160421 | 160421 | 100% | 0 | 0 | 0 | 21318 | -463 | 20855 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | UNIDO | Conversion of cleaning processes from TCA and CTC to non-ODS solvent cleaning technologies (trichloroethylene and alkozypropanol) at Videocon Group (VDC) | Individual | ASP | IND | SOL | 28 | INV | 225 | A | O | I | CTC TCA | 7.2 | 7.2 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2002-01-01 | 2003-03-01 | 234978 | -4 | 234974 | 234974 | 100% | 0 | 0 |  | 30547 | -49 | 30498 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at N.D. Plastics | Individual | ASP | IND | FOA | 28 | INV | 226 | A | O | I | CFC | 12.9 | 12.9 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2001-12-01 | 101289 | -802 | 100487 | 100487 | 100% | 0 | 0 | 0 | 13168 | -104 | 13064 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC by substituting with HAPs at Ruby Aerosols | Individual | ASP | IND | ARS | 28 | INV | 227 | A | O | I | CTC/CFC | 22.2 | 22.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2002-01-01 | 2005-11-01 | 45800 | -16 | 45784 | 45784 | 100% | 0 | 0 | 0 | 5954 | -2 | 5952 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ashoka Metals | Individual | ASP | IND | FOA | 28 | INV | 228 | A | O | I | CFC | 12.5 | 12.5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2002-03-01 | 68066 | -1587 | 66479 | 66479 | 100% | 0 | 0 | 0 | 8849 | -206 | 8643 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 28 small and medium-sized enterprises | Individual | ASP | IND | FOA | 28 | INV | 229 | A | O | I | CFC | 105.7 | 105.7 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2002-12-01 | 2005-09-01 | 699139 | -39114 | 660025 | 660025 | 100% | 0 | 0 | 0 | 86905 | -4862 | 82043 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 to IPA and xylene at Microraj Electronics PVT Ltd. & RCC (Sales) PVT ltd., Hyderabad (MRJ) | Individual | ASP | IND | SOL | 28 | INV | 230 | A | O | I | CFC | 4.3 | 4.3 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2001-11-01 | 2002-12-01 | 85431 | -431 | 85000 | 85000 | 100% | 0 | 0 |  | 11106 | -74 | 11032 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Tokyo Plast International, Ltd. | Individual | ASP | IND | FOA | 29 | INV | 231 | A | O | I | CFC | 30.5 | 30.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-06-01 | 2003-11-01 | 196394 | -37676 | 158718 | 158718 | 100% | 0 | 0 | 0 | 25531 | -4898 | 20633 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Santech Industries | Individual | ASP | IND | FOA | 29 | INV | 232 | A | O | I | CFC | 14.7 | 14.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 115101 | -9 | 115092 | 115092 | 100% | 0 | 0 | 0 | 14963 | -2 | 14961 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Saddle Poly Products P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 233 | A | O | I | CFC | 15.2 | 15.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 119087 | -44 | 119043 | 119043 | 100% | 0 | 0 | 0 | 15481 | -6 | 15475 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Coolwels Automobile Engineers | Individual | ASP | IND | FOA | 29 | INV | 234 | A | O | I | CFC | 15.8 | 15.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 133221 | -669 | 132552 | 132552 | 100% | 0 | 0 | 0 | 17319 | -87 | 17232 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Mayur Jugs P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 235 | A | O | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 119412 | -16905 | 102507 | 102507 | 100% | 0 | 0 | 0 | 15524 | -2198 | 13326 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Premium Mouldings and Pressings P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 236 | A | O | I | CFC | 17.7 | 17.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 138432 | -87 | 138345 | 138345 | 100% | 0 | 0 | 0 | 17996 | -11 | 17985 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crystal Electronics and Plastics | Individual | ASP | IND | FOA | 29 | INV | 237 | A | O | I | CFC | 18.3 | 18.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 123343 | -20723 | 102620 | 102620 | 100% | 0 | 0 | 0 | 16035 | -2695 | 13340 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
COM | IBRD | CFC production sector gradual phase-out project: 1999 annual programme | Multiyear | ASP | IND | PRO | 29 | INV | 238 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2000-11-01 |  | 2000-11-01 |  | 12000000 | 0 | 12000000 | 12000000 | 100% | 0 | 0 | 0 | 960000 | 0 | 960000 | 0 | 0 | Implemented | [14 empty] | INV | 0 | 0 | 22588 | 22411 | Yes | Yes | Yes
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at National Plastics | Individual | ASP | IND | FOA | 29 | INV | 239 | A | O | I | CFC | 36.2 | 36.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 212481 | -39605 | 172876 | 172876 | 100% | 0 | 0 | 0 | 27623 | -5149 | 22474 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Reactive Polymers Ltd. | Individual | ASP | IND | FOA | 29 | INV | 240 | A | O | I | CFC | 29.6 | 29.6 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 354175 | -56621 | 297554 | 297554 | 100% | 0 | 0 | 0 | 46043 | -7361 | 38682 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Jaiswal Industries | Individual | ASP | IND | FOA | 29 | INV | 241 | A | O | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 152070 | -14822 | 137248 | 137248 | 100% | 0 | 0 | 0 | 19769 | -1927 | 17842 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 24 SMEs | Individual | ASP | IND | FOA | 29 | INV | 242 | A | O | I | CFC | 97.7 | 97.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2003-04-01 | 2006-10-01 | 886584 | -127666 | 758918 | 758918 | 100% | 0 | 0 | 0 | 107524 | -8865 | 98659 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 1999 | Investment
FIN | UNDP | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | Individual | ASP | IND | HAL | 29 | TAS | 243 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2002-12-01 |  | 2005-12-01 | 2007-03-01 | 88000 | -3435 | 84565 | 84565 | 100% | 0 | 0 | 0 | 11440 | -447 | 10993 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Technical assistance for safety and technical programme to assist SME's manufacturing aerosol products (Phase I) | Individual | ASP | IND | ARS | 29 | TAS | 244 | A | O | I | CFC | 125 | 125 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2004-09-01 | 2008-04-01 | 155000 | -16537 | 138463 | 138463 | 100% | 0 | 0 | 0 | 20150 | -2150 | 18000 | 0 | 0 | Completed in 2004. Financially completed in 2008. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Delite Foam and Polymers | Individual | ASP | IND | FOA | 29 | INV | 245 | A | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 188832 | -2784 | 186048 | 186048 | 100% | 0 | 0 | 0 | 24548 | -362 | 24186 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Harjas Plastic and Metal Components P. Ltd. | Individual | ASP | IND | FOA | 29 | INV | 246 | A | O | I | CFC | 20.2 | 20.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-05-01 | 2003-07-01 | 246386 | -30539 | 215847 | 215847 | 100% | 0 | 0 | 0 | 32030 | -3970 | 28060 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | IBRD | Preparation of projects in the solvent general sector |  | ASP | IND | SOL | 30 | PRP | 247 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 30 | PRP | 248 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 20000 | -703 | 19297 | 19297 | 100% | 0 | 0 |  | 2600 | -95 | 2505 | 0 | 0 | FIN
FIN | IBRD | Preparation of projects in halon production sector |  | ASP | IND | PRO | 30 | PRP | 249 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of 6 projects in the integral skin foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 250 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of an umbrella project in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 251 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 252 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
FIN | UNEP | Develop policy and customs training strategies | Individual | ASP | IND | SEV | 30 | TAS | 253 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2003-04-01 | 2005-12-01 | 50000 | -22000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 6500 | -2860 | 3640 | 0 | 0 | Project financially completed. | $ 22,000 plus $ 2,860 PSC returned ExCom 46 | [12 empty] | 2000 | Non Investment
CLO | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 30 | PRP | 254 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
FIN | IBRD | Preparation of projects in the industrial and chiller refrigeration subsectors |  | ASP | IND | REF | 30 | PRP | 255 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at M/s Kooverji Devshi and Co. Pvt. Ltd., Mumbai | Individual | ASP | IND | HAL | 28 | INV | 256 | A | O | I | Halon | 25.5 | 25.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-05-01 | 2002-03-01 | 37740 | 0 | 37740 | 37740 | 100% | 0 | 0 | 0 | 4906 | 0 | 4906 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Fedders Lloyd Corporation Ltd. | Individual | ASP | IND | REF | 31 | INV | 257 | A | O | I | CFC | 21.2 | 21.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 257428 | -2616 | 254812 | 254812 | 100% | 0 | 0 | 0 | 33466 | -340 | 33126 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ramakrishna Moulders | Individual | ASP | IND | FOA | 31 | INV | 258 | A | O | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-12-01 | 2003-04-01 | 78479 | -1311 | 77168 | 77168 | 100% | 0 | 0 | 0 | 10202 | -170 | 10032 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at M-Plast | Individual | ASP | IND | FOA | 31 | INV | 259 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 93279 | -451 | 92828 | 92828 | 100% | 0 | 0 | 0 | 12126 | -59 | 12067 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Naorang Plast | Individual | ASP | IND | FOA | 31 | INV | 260 | A | O | I | CFC | 13.5 | 13.5 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 53171 | -563 | 52608 | 52608 | 100% | 0 | 0 | 0 | 6912 | -73 | 6839 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Sanjay Industries | Individual | ASP | IND | FOA | 31 | INV | 261 | A | O | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 99277 | -2381 | 96896 | 96896 | 100% | 0 | 0 | 0 | 12906 | -310 | 12596 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
COM | IBRD | CFC production sector gradual phase-out project: 2000 annual programme | Multiyear | ASP | IND | PRO | 31 | INV | 262 | N | O | I | CFC | 0 | 0 | 1882 | 1882 | 2000-07-01 | 2000-09-01 | 2000-12-01 |  | 2000-12-01 |  | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 | 0 | 880000 | 0 | 880000 | 0 | 0 | Annual Programme satisfactorily implemented with achievement of CY2000 CFC production reduction and disbursement targets. ODS (regulation & control) rules established along with quota order for production quota licenses for CFC-producing enterprises. | [13 empty] | 2000 | INV | 0 | 0 | 20706 | 20407 | Yes | Yes | Yes
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crown Industries | Individual | ASP | IND | FOA | 31 | INV | 263 | A | O | I | CFC | 22.5 | 22.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 113110 | -4382 | 108728 | 108728 | 100% | 0 | 0 | 0 | 14704 | -570 | 14134 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Formulation of CTC process cleaning agent project in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 264 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2002-03-01 | 2003-05-01 | 20000 | -261 | 19739 | 19739 | 100% | 0 | 0 |  | 2600 | -38 | 2562 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for SMEs in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 265 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2002-04-01 |  | 2003-06-01 | 2003-06-01 | 30000 | -29 | 29971 | 29971 | 100% | 0 | 0 |  | 3900 | -10 | 3890 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Blue Star Ltd., Thane | Individual | ASP | IND | SOL | 31 | INV | 266 | A | O | I | CTC | 6.6 | 6.6 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-12-01 | 2003-10-01 | 76027 | 0 | 76027 | 76027 | 100% | 0 | 0 |  | 9884 | 0 | 9884 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at sixteen enterprises | Individual | ASP | IND | FOA | 31 | INV | 267 | A | O | I | CFC | 211.1 | 211.1 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 1094567 | -75293 | 1019274 | 1019274 | 100% | 0 | 0 | 0 | 130402 | -8282 | 122120 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Enertech Engineering P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 268 | A | O | I | CFC | 15.8 | 15.8 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2004-01-01 | 123109 | -86 | 123023 | 123023 | 100% | 0 | 0 | 0 | 16004 | -11 | 15993 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Raipur Agencies | Individual | ASP | IND | FOA | 31 | INV | 269 | A | O | I | CFC | 16.3 | 16.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 144567 | -2814 | 141753 | 141753 | 100% | 0 | 0 | 0 | 18794 | -366 | 18428 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pyarelal Coir Products Ltd. | Individual | ASP | IND | FOA | 31 | INV | 270 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 167381 | -2886 | 164495 | 164495 | 100% | 0 | 0 | 0 | 21760 | -375 | 21385 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at R.H. Industries | Individual | ASP | IND | FOA | 31 | INV | 271 | A | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 153895 | -2700 | 151195 | 151195 | 100% | 0 | 0 | 0 | 20006 | -351 | 19655 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pinnacle Industries Ltd. | Individual | ASP | IND | FOA | 31 | INV | 272 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 186392 | 0 | 186392 | 186392 | 100% | 0 | 0 | 0 | 24231 | 0 | 24231 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Nindra Foams | Individual | ASP | IND | FOA | 31 | INV | 273 | A | O | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 148804 | -2244 | 146560 | 146560 | 100% | 0 | 0 | 0 | 19345 | -292 | 19053 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at SR Poly-steel P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 274 | A | O | I | CFC | 14.9 | 14.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 144299 | -1 | 144298 | 144298 | 100% | 0 | 0 | 0 | 18759 | 0 | 18759 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Enkay Foam P., Ltd. | Individual | ASP | IND | FOA | 31 | INV | 275 | A | O | I | CFC | 16.6 | 16.6 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 162339 | -4442 | 157897 | 157897 | 100% | 0 | 0 | 0 | 21104 | -577 | 20527 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Alka International Ltd. | Individual | ASP | IND | FOA | 31 | INV | 276 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 173155 | -6690 | 166465 | 166465 | 100% | 0 | 0 | 0 | 22510 | -870 | 21640 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Evershine Plastic Industry | Individual | ASP | IND | FOA | 31 | INV | 277 | A | O | I | CFC | 16.2 | 16.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 80060 | -2410 | 77650 | 77650 | 100% | 0 | 0 | 0 | 10408 | -313 | 10095 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | Canada | National halon management and banking programme | Halon Banking | ASP | IND | HAL | 32 | TAS | 278 | A | O | I | HAL | 197.2 | 197.2 | 0 |  | 2000-12-01 | 2002-10-02 | 2004-01-01 |  | 2007-03-01 | 2007-03-01 | 245700 | 0 | 245700 | 245700 | 100% | 0 |  | 0 | 24570 | 0 | 24570 | 0 |  | Halon reclamation facility established in 2003. Canadian component annd Australian component of project completed |  | 2000 | [11 empty] | 2000 | Investment
FIN | UNDP | Technical assistance to Ozone Cell, MOEF during the preparation of a refrigeration and air conditioning servicing sector strategy | RMP-Component | ASP | IND | REF | 32 | TAS | 279 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-07-01 | 2005-09-01 | 30000 | -3675 | 26325 | 26325 | 100% | 0 | 0 | 0 | 3900 | -478 | 3422 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Netplast Ltd. | Individual | ASP | IND | FOA | 32 | INV | 280 | A | O | I | CFC | 18 | 18 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-09-01 | 2005-09-01 | 177224 | -2199 | 175025 | 175025 | 100% | 0 | 0 | 0 | 23039 | -286 | 22753 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | Australia | National halon management and banking programme | Individual | ASP | IND | HAL | 32 | TAS | 281 | A | O | I | HAL | 197.2 | 197.2 | 0 | 0 | 2000-12-01 | 2002-02-01 | 2004-01-01 |  | 2007-05-01 | 2008-05-01 | 245700 | -24100 | 221600 | 221600 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed. |  | 2000
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sandlas Air-Con Systems P. Ltd. | Individual | ASP | IND | REF | 32 | INV | 282 | A | O | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 228517 | -9527 | 218990 | 218990 | 100% | 0 | 0 | 0 | 29707 | -1239 | 28468 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to trichloromethane at M/S Alpha Drugs India Ltd., Patiala | Individual | ASP | IND | PAG | 32 | INV | 283 | A | O | I | CTC | 69.7 | 69.7 |  |  | 2000-12-01 | 2001-11-01 | 2002-06-01 |  | 2003-03-01 | 2004-04-01 | 145866 | -130 | 145736 | 145736 | 100% | 0 | 0 |  | 15453 | -38 | 15415 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Svis Labs Ltd., Ranipet | Individual | ASP | IND | PAG | 32 | INV | 284 | A | O | R | CTC | 54.2 | 54.2 |  |  | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 249547 | 0 | 249547 | 249547 | 100% | 0 | 0 |  | 25352 | -9 | 25343 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sun Steering Wheels, Ltd. | Individual | ASP | IND | FOA | 32 | INV | 285 | A | O | I | CFC | 15.6 | 15.6 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-02-01 | 2005-10-01 | 144379 | -2997 | 141382 | 141382 | 100% | 0 | 0 | 0 | 18769 | -390 | 18379 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 32 | INV | 286 | A | O | I | CFC | 53.5 | 53.5 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 789425 | -20719 | 768706 | 768706 | 100% | 0 | 0 | 0 | 96837 | -2279 | 94558 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Satya Deeptha Pharmaceuticals Ltd., Humnabad | Individual | ASP | IND | PAG | 32 | INV | 287 | A | O | I | CTC | 27.9 | 27.9 |  |  | 2000-12-01 | 2001-11-01 | 2002-07-01 |  | 2002-12-01 | 2004-12-01 | 260133 | -659 | 259474 | 259474 | 100% | 0 | 0 |  | 33817 | -139 | 33678 | 0 | 0 | FIN
FIN | Germany | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 288 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2004-04-05 | 2004-04-01 | 240200 | 0 | 240200 | 240200 | 100% | 0 | 0 | 0 | 31226 | 0 | 31226 | 0 | 0 | India's National CFC consumption Phase-Out Plan with special refeence to the Refrigeration Service Sector was approved at the 42nd ExCom (IND/REF/42/INV/369). | [13 empty] | 2002
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sawhney Seating Systems | Individual | ASP | IND | FOA | 32 | INV | 289 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-07-01 | 2005-09-01 | 241619 | -3124 | 238495 | 238495 | 100% | 0 | 0 | 0 | 31410 | -406 | 31004 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNIDO | Umbrella project for the conversion of three commercial refrigeration enterprises in New Delhi (Gaurav Controls, Thermoking and Western Engineering) | Individual | ASP | IND | REF | 32 | INV | 290 | A | O | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-01-01 | 2003-02-01 |  | 2004-08-01 | 2005-09-01 | 328894 | -49284 | 279610 | 279610 | 100% | 0 | 0 |  | 42756 | -6464 | 36292 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Doctors Organic Chemicals Ltd., Tanuku | Individual | ASP | IND | PAG | 32 | INV | 291 | A | O | I | CTC | 94.6 | 94.6 |  |  | 2000-12-01 | 2002-01-01 | 2002-06-01 |  | 2002-12-01 | 2003-12-01 | 288809 | -171 | 288638 | 288638 | 100% | 0 | 0 |  | 37545 | -82 | 37463 | 0 | 0 | FIN
FIN | Switzerland | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 292 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-04-01 | 2003-04-01 | 70796 | 0 | 70796 | 70796 | 100% | 0 | 0 | 0 | 9204 | 0 | 9204 | 0 | 0 |  |  | 2000
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IND | REF | 33 | PRP | 293 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the non-recycling halon sector | Individual | ASP | IND | HAL | 33 | PRP | 294 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2003-06-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 2001 | Investment
COM | IBRD | CFC production sector gradual phase-out project: 2001 annual programme | Multiyear | ASP | IND | PRO | 33 | INV | 295 | N | O | I | CFC | 0 | 0 | 1583 | 1583 | 2001-03-01 | 2001-04-30 | 2001-12-01 |  | 2001-12-01 |  | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 | 0 | 880000 | 0 | 880000 | 0 | 0 | Annual Programme satisfactorily implemented. | [13 empty] | 2001 | INV | 0 | 0 | 18824 | 18693 | Yes | Yes | Yes
CLO | UNDP | Project preparation in the foam sector | Individual | ASP | IND | FOA | 33 | PRP | 296 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | ASP | IND | FOA | 33 | PRP | 297 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | IND | ARS | 33 | PRP | 298 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IND | FOA | 33 | PRP | 299 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | IBRD | Project preparation in the MAC sector |  | ASP | IND | REF | 33 | PRP | 300 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-09-01 | 2001-12-01 |  | 2002-09-01 | 2002-09-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project submitted to and approved at the 38th ExCom. | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a sector plan for the process agent sector |  | ASP | IND | PAG | 33 | PRP | 301 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-31 | 2001-12-01 |  | 2003-04-01 | 2003-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Sector Plan completed and project document prepared for submission to the ExCom. | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Project preparation in the process agent (pharmaceutical) sector | Individual | ASP | IND | PAG | 33 | PRP | 302 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-10-01 |  | 2003-10-01 | 2004-09-01 | 70000 | -5813 | 64187 | 64187 | 100% | 0 | 0 |  | 9100 | -769 | 8331 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at M/S Benzo Chemical Industries, Tarapore | Individual | ASP | IND | PAG | 34 | INV | 303 | A | O | I | CTC | 23 | 23 |  |  | 2001-07-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 136786 | -3906 | 132880 | 132880 | 100% | 0 | 0 |  | 17782 | -508 | 17274 | 0 | 0 | FIN | [7 empty] | 2004-12-01 | [5 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at UNC Plast Industries | Individual | ASP | IND | FOA | 34 | INV | 304 | A | O | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2007-02-01 | 89607 | -1142 | 88465 | 88465 | 100% | 0 | 0 | 0 | 11649 | -148 | 11501 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Viking Engineers P. Ltd. | Individual | ASP | IND | FOA | 34 | INV | 305 | A | O | I | CFC | 13.3 | 13.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-10-01 | 144900 | -2745 | 142155 | 142155 | 100% | 0 | 0 | 0 | 18837 | -357 | 18480 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Engineering, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 306 | A | O | I | CTC | 14.5 | 14.5 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 240435 | 0 | 240435 | 240435 | 100% | 0 | 0 |  | 31257 | -19 | 31238 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Flexo Foam P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 307 | A | O | I | CFC | 19.4 | 19.4 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-04 | 2004-03-04 | 185241 | 0 | 185241 | 185241 | 100% | 0 | 0 |  | 24081 | 0 | 24081 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 | [11 empty] | 2001 | Investment
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Engineer Industries, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 308 | A | O | I | CTC | 20.2 | 20.2 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 238776 | 0 | 238776 | 238776 | 100% | 0 | 0 |  | 31041 | -9 | 31032 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Germany | Project preparation for the phase out of ODS use in the flexible molded foam sub-sector in 5 enterprises | Individual | ASP | IND | FOA | 34 | PRP | 309 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-10-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 2 resultant investment projects were submitted and approved in Mar-02 | [13 empty] | 2002
COM | UNDP | Renewal of institutional strengthening project (phase IV) | Individual | ASP | IND | SEV | 34 | INS | 310 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-09-01 | 2003-08-01 |  | 2004-03-01 |  | 287100 | 0 | 287100 | 285796 | 99.55% | 1304 | 0 | 1043.2 | 37323 | 0 | 37153.48 | 169.52 | 0 | Completed in 2004. | [13 empty] | 2001 | Non-Investment
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at Praddep Shetye Ltd., Alibagh | Individual | ASP | IND | PAG | 34 | INV | 311 | A | O | I | CTC | 133.9 | 133.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 279001 | -10 | 278991 | 278991 | 100% | 0 | 0 |  | 36270 | -1 | 36269 | 0 | 0 | FIN | [7 empty] | 2004-12-01 | [5 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Roome Plastics P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 312 | A | O | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 100546 | -2008 | 98538 | 98538 | 100% | 0 | 0 | 0 | 13071 | -261 | 12810 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to ethylene dichloride at Chiplun Fine Chemicals Ltd., Ratnagiri | Individual | ASP | IND | PAG | 34 | INV | 313 | A | O | I | CTC | 16.7 | 16.7 |  |  | 2001-07-01 | 2002-02-01 | 2003-02-01 |  | 2003-07-01 | 2004-09-01 | 155830 | 0 | 155830 | 155830 | 100% | 0 | 0 |  | 20258 | -2 | 20256 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at FDC Limited, Roha | Individual | ASP | IND | PAG | 34 | INV | 314 | A | O | I | CTC | 34.1 | 34.1 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2008-05-01 | 238371 | -191 | 238180 | 238180 | 100% | 0 | 0 |  | 30988 | -25 | 30963 | 0 | 0 | Financial completion in May 2008. Refund was reported to 55th ExCom, Jul 2008. FIN. | [13 empty] | 2001 | INV
FIN | IBRD | Halon production and consumption sector phase out plan | One off phaseout | ASP | IND | HAL | 34 | INV | 315 | N | O | I | HAL | 556 | 556 | 321 | 321 | 2001-07-01 | 2003-08-01 | 2002-08-01 |  | 2003-10-01 | 2008-01-01 | 2600000 | 0 | 2600000 | 2600000 | 100% | 0 | 0 | 0 | 234000 | 0 | 234000 | 0 | 0 | UNDP has confirmed that project has been completed. Final completion report still pending from UNDP. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at GRD Chemicals Ltd., Indore, M.P. | Individual | ASP | IND | PAG | 34 | INV | 316 | A | O | I | CTC | 17.9 | 17.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-04-01 | 127667 | 0 | 127667 | 127667 | 100% | 0 | 0 |  | 16597 | -9 | 16588 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Essa Aircons Ltd. | Individual | ASP | IND | FOA | 34 | INV | 317 | A | O | I | CFC | 13.9 | 13.9 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 108837 | -2996 | 105841 | 105841 | 100% | 0 | 0 | 0 | 14149 | -389 | 13760 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sutlej Coach Products P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 318 | A | O | I | CFC | 18 | 18 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-04 | 2004-09-04 | 187400 | 0 | 187400 | 187400 | 100% | 0 | 0 |  | 24362 | 0 | 24362 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in June 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 | [11 empty] | 2001 | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Malvika Polymers | Individual | ASP | IND | FOA | 34 | INV | 319 | A | O | I | CFC | 20 | 20 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-04 | 2004-03-04 | 196610 | 0 | 196610 | 196315 | 99.85% | 295 | 0 |  | 25559 | 0 | 25521 | 38 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 | [11 empty] | 2001 | Investment
FIN | IBRD | Conversion of chlorinated rubber manufacture from carbon tetrachloride to non-ODS process at Rishiroop Organics Pvt. Ltd. | Individual | ASP | IND | PAG | 34 | INV | 320 | N | O | I | CTC | 248.8 | 248.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-10-01 | 2005-01-01 | 2074300 | -109984 | 1964316 | 1964315.95 | 100% | 0.05 | 0.05 |  | 238173 | -12098.24 | 226074.76 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to HCF-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at 14 enterprises | Individual | ASP | IND | FOA | 34 | INV | 321 | A | O | I | CFC | 178.4 | 178.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-09-01 | 2005-11-01 | 759165 | -12566 | 746599 | 746599 | 100% | 0 | 0 | 0 | 93508 | -1382 | 92126 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at 17 small and medium-sized enterprises | Individual | ASP | IND | FOA | 34 | INV | 322 | A | O | I | CFC | 55.8 | 55.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-03-01 | 2004-12-01 | 417740 | 0 | 417740 | 417740 | 100% | 0 | 0 | 0 | 54306 | 0 | 54306 | 0 | 0 | Completed in 2004. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of commercial refrigeration equipment at 5 enterprises (Ahmedabad Low Temp, Kalkura Cooling Machines, Mechelec Steel Products, Polfrost Aircon and Shri Ambica Engineering) | Individual | ASP | IND | REF | 34 | INV | 323 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-11-01 | 2005-11-01 | 323627 | -7398 | 316229 | 316229 | 100% | 0 | 0 | 0 | 42072 | -962 | 41110 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Apollo Steelcrafts | Individual | ASP | IND | FOA | 34 | INV | 324 | A | O | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 76925 | -3129 | 73796 | 73796 | 100% | 0 | 0 | 0 | 10000 | -407 | 9593 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at SR Polymers and Printers | Individual | ASP | IND | FOA | 34 | INV | 325 | A | O | I | CFC | 19.6 | 19.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 95002 | -2970 | 92032 | 92032 | 100% | 0 | 0 | 0 | 12350 | -386 | 11964 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Caryaire Equipments India P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 326 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-07-01 | 2005-11-01 | 133509 | 0 | 133509 | 133509 | 100% | 0 | 0 | 0 | 17356 | 0 | 17356 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Coils Ltd., Palghar | Individual | ASP | IND | SOL | 34 | INV | 327 | A | O | I | CTC | 22.8 | 22.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 245024 | 0 | 245024 | 245024 | 100% | 0 | 0 |  | 31853 | -19 | 31834 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lear Insulation Engineering P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 328 | A | O | I | CFC | 10.6 | 10.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 82567 | -1581 | 80986 | 80986 | 100% | 0 | 0 | 0 | 10734 | -206 | 10528 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nandadeep Fibrotech P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 329 | A | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 88526 | -3278 | 85248 | 85248 | 100% | 0 | 0 | 0 | 11508 | -426 | 11082 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Nu-Foam Rubber Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 330 | A | O | I | CFC | 15.6 | 15.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2003-02-01 | 2005-10-01 | 160150 | -1115 | 159035 | 159035 | 100% | 0 | 0 | 0 | 20820 | -145 | 20675 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Poly Glass Fibre Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 331 | A | O | I | CFC | 17.1 | 17.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-03-01 | 2005-10-01 | 134238 | -2571 | 131667 | 131667 | 100% | 0 | 0 | 0 | 17451 | -334 | 17117 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Polyrub Industries | Individual | ASP | IND | FOA | 34 | INV | 332 | A | O | I | CFC | 12.5 | 12.5 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 97953 | -3144 | 94809 | 94809 | 100% | 0 | 0 | 0 | 12734 | -409 | 12325 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Prince Plastoware Ltd. | Individual | ASP | IND | FOA | 34 | INV | 333 | A | O | I | CFC | 9.4 | 9.4 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2004-08-01 |  | 2002-06-01 | 2003-11-01 | 74010 | -3392 | 70618 | 70618 | 100% | 0 | 0 | 0 | 9621 | -441 | 9180 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Solvay Moulding P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 334 | A | O | I | CFC | 26.1 | 26.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-07-01 | 2005-09-01 | 196885 | -15868 | 181017 | 181017 | 100% | 0 | 0 | 0 | 25595 | -2063 | 23532 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bhatia Plastics | Individual | ASP | IND | FOA | 34 | INV | 335 | A | O | I | CFC | 11.1 | 11.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-03-01 | 2005-10-01 | 87070 | -5398 | 81672 | 81672 | 100% | 0 | 0 | 0 | 11319 | -702 | 10617 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Oto Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 336 | A | O | I | CFC | 12.7 | 12.7 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-04 | 2004-03-04 | 139716 | 0 | 139716 | 139335 | 99.73% | 381 | 0 |  | 18163 | 0 | 18116 | 47 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 | [11 empty] | 2001 | Investment
FIN | IBRD | Conversion of domestic refrigerator manufacture to either R600a or HFC-134a refrigerant at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | REF | 30 | INV | 337 | N | O | I | CFC | 71.7 | 71.7 | 0 | 0 | 2000-03-01 | 2003-07-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 2050000 | -250684.64 | 1799315.36 | 1799315.36 | 100% | 0 | 0 |  | 235500 | -28798.16 | 206701.84 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [13 empty] | 1999 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to cyclohexane at Amoli Organics Ltd., Mumbai | Individual | ASP | IND | PAG | 35 | INV | 338 | A | O | I | CTC | 38.5 | 38.5 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-08-01 | 2007-01-01 | 385367 | -1454 | 383913 | 383913 | 100% | 0 | 0 |  | 50098 | -189 | 49909 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at fourteen enterprises | Individual | ASP | IND | REF | 35 | INV | 339 | A | O | I | CFC | 68 | 68 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2003-11-01 | 2005-10-01 | 960097 | -5024 | 955073 | 955073 | 100% | 0 | 0 | 0 | 115611 | -553 | 115058 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ice-Make Refrigeration | Individual | ASP | IND | REF | 35 | INV | 340 | A | O | I | CFC | 12.4 | 12.4 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-12-01 | 157305 | -1232 | 156073 | 156073 | 100% | 0 | 0 | 0 | 20450 | -160 | 20290 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Konark Refrigeration Appliances P., Ltd. | Individual | ASP | IND | REF | 35 | INV | 341 | A | O | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-09-01 | 182684 | -1327 | 181357 | 181357 | 100% | 0 | 0 | 0 | 23749 | -173 | 23576 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 35 | INV | 342 | A | O | I | CFC | 56.5 | 56.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2007-03-01 | 726448 | -9086 | 717362 | 717362 | 100% | 0 | 0 | 0 | 89909 | -999 | 88910 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNEP | Overall strategy for the solvent sector to support the phaseout of ODS in SMEs | Individual | ASP | IND | SOL | 35 | TAS | 343 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2003-12-01 |  | 2005-06-01 | 2007-07-01 | 169000 | -10140 | 158860 | 158860 | 100% | 0 | 0 | 0 | 21970 | -1318 | 20651.8 | 0.2 | 0 | Project financially completed. | $ 10,140 plus $ 1,318 PSC returned to ExCom 50 | [12 empty] | 2001 | Non Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | ASP | IND | REF | 36 | PRP | 344 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356 | 2244 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the aerosol sector | Individual | ASP | IND | ARS | 36 | PRP | 345 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -473 | 2777 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 36 | PRP | 346 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-04-01 |  | 2003-09-01 | 2004-09-01 | 30000 | -4889 | 25111 | 25111 | 100% | 0 | 0 |  | 3900 | -641 | 3259 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of an investment project in the solvent (CFC-113) sector | Individual | ASP | IND | SOL | 36 | PRP | 347 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-04-01 | 2004-04-01 | 30000 | -479 | 29521 | 29521 | 100% | 0 | 0 |  | 3900 | -68 | 3832 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | ASP | IND | FOA | 36 | PRP | 348 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 40000 | -6328 | 33672 | 33672 | 100% | 0 | 0 | 0 | 5200 | -823 | 4377 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Country programme update | Individual | ASP | IND | SEV | 36 | CPG | 349 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-09-01 | 2003-10-01 |  | 2006-07-01 | 2007-03-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 2006. Financially completed in 2007. | [8 empty] | 2004-12-01 |  |  |  |  | 2002 | Non-Investment
FIN | Germany | Conversion from CFC-11 to water-based technology at Precision Engineering Tools and Components | Individual | ASP | IND | FOA | 36 | INV | 350 | A | O | I | CFC | 22 | 22 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-05 | 2006-06-01 | 200282 | -26 | 200256 | 200256 | 100% | 0 | 0 | 0 | 26037 | -3 | 26034 | 0 | 0 | Project has been completed. PCR submitted in 2006. Remaining funds will be returned. | [8 empty] | 2004-12-01 |  |  |  |  | 1998
FIN | Germany | Conversion from CFC-11 to water-based technology at Pramukh Poly-Products | Individual | ASP | IND | FOA | 36 | INV | 351 | A | O | I | CFC | 27 | 27 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-05 | 2006-06-01 | 224812 | -9 | 224803 | 224803 | 100% | 0 | 0 | 0 | 29226 | -1 | 29225 | 0 | 0 | Project has been completed. PCR submitted in 2006 | [8 empty] | 2004-12-01 |  |  |  |  | 1998
COM | IBRD | CFC production sector gradual phase-out project: 2002 annual programme | Multiyear | ASP | IND | PRO | 36 | INV | 352 | N | O | I | CFC | 0 | 0 | 1883 | 1883 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 | 0 | 480000 | 0 | 480000 | 0 | 0 | Completed. | [13 empty] | 2002 | INV | 0 | 0 | 16941 | 16890 | Yes | Yes | Yes
COM | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (first tranche) | Multi-Year | ASP | IND | FOA | 37 | INV | 353 | N | O | I | CFC | 162.5 | 162.5 | 0 | 0 | 2002-07-01 | 2003-11-01 | 2003-12-01 |  | 2004-12-01 |  | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Completed in 2004. | [13 empty] | 2002 | Investment | 639 | 639 |  |  | Yes | Yes | yes
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Navdeep Engineering, Palghar | Individual | ASP | IND | SOL | 38 | INV | 354 | A | O | I | CTC | 53.9 | 53.9 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-12-01 | 2007-01-01 | 661842 | -1087 | 660755 | 660755 | 100% | 0 | 0 |  | 82803 | -120 | 82683 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | IBRD | Project preparation funds for CTC production closure plan |  | ASP | IND | PRO | 38 | PRP | 355 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed and submitted to ExCom. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
COM | UNDP | Plan for phase out of CFCs in the refrigeration manufacturing sector (first tranche) | Multi-Year | ASP | IND | REF | 38 | INV | 356 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2004-11-01 |  | 2006-07-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 172971 | 0 | 172971 | 0 | 0 | Completed in 2006. | [13 empty] | 2002 | Investment | 428 | 428 |  |  | Yes | Yes | yes
FIN | IBRD | Complete phase out of CFC-12 to non-ODS technology (HFC-134a) for manufacturing of mobile air-conditioners (MACs) at Subros Limited (phase II) | Individual | ASP | IND | REF | 38 | INV | 357 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-11-01 |  | 2003-11-01 | 2005-01-01 | 1181693 | -83277 | 1098416 | 1098416 | 100% | 0 | 0 |  | 222895 | -15708 | 207187.01 | -0.01 | -0.01 | Project financially completed and balance funds returned. PCR submitted to ExCom. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | UNDP | Terminal umbrella project in the aerosol sector | Individual | ASP | IND | ARS | 38 | INV | 358 | A | O | I | CTC/CFC | 132.5 | 132.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-11-01 |  | 2007-03-01 |  | 583000 | 0 | 583000 | 513531 | 88.08% | 69469 | 0 | 55575.2 | 74130 | 0 | 65296.832 | 8833.168 | 0 | Completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNIDO | Plan for phase-out of CFCs in the refrigeration (manufacturing) sector | Multi-Year | ASP | IND | REF | 38 | INV | 359 | A | O | I | CFC | 40 | 59 |  |  | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2006-11-01 | 2007-12-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 65000 | 0 | 65000 | 0 | 0 | FIN | [13 empty] | 2002 | INV | N/A | N/A |  |  | N/A | N/A | N/A
CLO | UNIDO | Preparation of an investment project in the fumigant sector | Individual | ASP | IND | FUM | 39 | PRP | 360 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2004-07-01 | 2004-04-01 |  |  | 2005-12-01 | 35000 | -34038 | 962 | 962 | 100% | 0 | 0 |  | 2625 | -2553 | 72 | 0 | 0 | CLO | [13 empty] | 2003
COM | IBRD | CFC production sector gradual phase-out: 2003 annual programme | Multiyear | ASP | IND | PRO | 39 | INV | 361 | N | O | I | CFC | 0 | 0 | 1883 | 1883 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-04-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | Implemented. | [13 empty] | 2003 | INV | 0 | 0 | 15058 | 15014 | Yes | Yes | Yes
FIN | UNIDO | Conversion of CFC-113 as cleaning solvent to TCE at Bharat Electronics Limited (BEL), Bangalore | Individual | ASP | IND | SOL | 40 | INV | 362 | A | O | I | CFC | 16 | 16 |  |  | 2003-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-12-01 | 2006-12-01 | 151291 | -684 | 150607 | 150607 | 100% | 0 | 0 |  | 13616 | -61 | 13555 | 0 | 0 | FIN | [13 empty] | 2003
COM | IBRD | CTC phase-out plan for the consumption and production sectors (first tranche) | Multiyear | ASP | IND | PHA | 40 | INV | 363 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-07-01 |  | 5000000 | 3520843 | 8520843 | 8520843 | 100% | 0 | 0 | 0 | 375000 | 264063 | 639063 | 0 | 0 | Tranche is completed. | [13 empty] | 2003 | INV | 0 | 0 | 0 | 0
COM | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 364 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-03-01 | 2004-12-01 |  | 2006-12-01 |  | 476536 | 0 | 476536 | 476536 | 100% | 0 | 0 | 0 | 43243 | 0 | 43243 | 0 | 0 | Completed in 2006. | [10 empty] | 2006-12-01 |  |  | 2003 | Investment | 288 | 288 |  |  | Yes | Yes | yes
COM | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (second tranche) | Multi-Year | ASP | IND | FOA | 41 | INV | 365 | N | O | I | CFC | 210 | 210 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-07-01 |  | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 | 0 | 153500 | 0 | 153500 | 0 | 0 | Completed in 2006. | [13 empty] | 2003 | Investment | 429 | 429 |  |  | Yes | Yes | yes
COM | UNIDO | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 366 | A | O | I | CFC | 67 | 77 |  |  | 2003-12-01 | 2006-10-01 | 2005-12-01 |  | 2007-03-01 |  | 173200 | 0 | 173200 | 170831 | 98.63% | 2369 | 29 | 1 | 19052 | 0 | 18791 | 261 | 3 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2003 | INV | N/A | N/A |  |  | N/A | N/A | N/A
COM | UNDP | Extension of institutional strengthening project: phase 5 | Individual | ASP | IND | SEV | 41 | INS | 367 | N | T | I | No_ODP | 30.8 | 30.8 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-07-01 |  | 373230 | 0 | 373230 | 370310 | 99.22% | 2920 | 0 | 2336 | 27992 | 0 | 27773.002 | 218.998 | 0 | Completed in 2006. | [13 empty] | 2003 | Non-Investment
COM | UNDP | MDI Transitional Strategy | Individual | ASP | IND | ARS | 41 | TAS | 368 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2008-07-01 |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 24000 | 2250 | 0 | 0 | 2250 | 0 | Completed in 2008. The MDI Transition Strategy was completed and submitted as part of the overall MDI project to the 56th ExCom meeting in November 2008. Funds will therefore be returned in 2009. | [13 empty] | 2003 | Non-Investment
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 369 | A | O | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2006-04-06 | 2006-04-06 | 414370 | 0 | 414370 | 414370 | 100% | 0 | 0 | 0 | 53868 | 0 | 53868 | 0 | 0 | The project infrastructure has been successfully established and all activites as per the the annual working plan have been accomplished. | [15 empty] | 964 |  | 3389 | 2368
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 370 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-03-31 | 2005-03-31 | 353020 | 0 | 353020 | 353020 | 100% | 0 | 0 | 0 | 45893 | 0 | 45893 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2004: Four new training cells have been established and a Training of Trainers Wokshop was held for 12 particpants. With this, 13 training cells provided in 2004 standard training programs for refrigeration service technicians. | 2004 | [11 empty] | 2004
COM | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 371 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-11-01 | 2005-04-01 |  | 2006-06-01 |  | 277200 | 0 | 277200 | 277200 | 100% | 0 | 0 | 0 | 20790 | 0 | 20790 | 0 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment | 219 | 219 |  |  | Yes | Yes | yes
COM | IBRD | CFC production sector gradual phase-out: 2004 annual programme | Multiyear | ASP | IND | PRO | 42 | INV | 372 | N | O | I | CFC | 0 | 0 | 1832 | 1832 | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2005-01-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | Completed. | [13 empty] | 2004 | INV | 0 | 0 | 13176 | 13069 | Yes | Yes | Yes
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multiyear | ASP | IND | PHA | 42 | INV | 373 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 |  | 9180112 | 0 | 9180112 | 9180112 | 100% | 0 | 0 | 0 | 688508 | 0 | 688508 | 0 | 0 | Planned 2006 disbursement was held back due to a policy issue emanating from the 2005 verification report regarding stockpiles of CTC for feedstock use in future years. As the issue was resolved by the Parties at the end of 2006, full disbursement of this tranche will be made in the first half of 2007. | [13 empty] | 2003 | INV | 0 | 0 | 0 | 0
COM | France | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 374 | A | O | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2008-07-01 |  | 1000000 | 0 | 1000000 | 562524 | 56.25% | 437476 |  | 437476 | 85000 | 0 | 47814.54 | 37185.46 |  | The French contribution is implemented by GTZ-Proklima. All activities planned under this tranche have been accomplished. | [10 empty] | 2007-04-01
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 375 | A | O | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-07 | 2007-12-07 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned with the funds from this tranche have been accomplished. | [15 empty] | 708 |  | 708
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year Partial | ASP | IND | PHA | 42 | INV | 376 | N | O | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2005-11-01 | 2005-04-01 | 2007-09-01 |  |  | 2500000 | 0 | 2500000 | 1901645 | 76.07% | 598355 |  | 598355 | 280000 | 0 | 247214 | 32786 | 0 | Pre-shipment inspection of equipment at manufacturing site completed in April 2006, equipment delivered to respective plant sites end 2006. Installation and commissioning to be initiated upon completion of civil works 2Q2007 | [10 empty] | 2006-11-01
FIN | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-year | ASP | IND | REF | 42 | TAS | 377 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2007-06-01 | 256300 | 0 | 256300 | 256300 | 100% | 0 | 0 | 0 | 33319 | 0 | 33319 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 379 | N | O | I | CFC | 158 | 158 | 0 | 0 | 2004-12-01 | 2006-03-01 | 2005-12-01 |  | 2006-06-01 |  | 277050 | 0 | 277050 | 277050 | 100% | 0 | 0 | 0 | 20779 | 0 | 20779 | 0 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment | 206.2 | 206.2 |  |  | Yes | Yes | yes
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 380 | A | O | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2006-01-01 | 2005-12-01 |  | 2006-04-06 | 2006-04-06 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | All activities as per the annual working plan have been accomplished. | [15 empty] | 964 |  | 3389 | 2368
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 381 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-03-31 | 2006-03-31 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2005: In the operational year 05-06 the following number of technicians are trained: a) in Standard RSE programs: 1685 participants b) Mobile Air-Conditioning programs 130 participants c) Open Type compressor programs: 64 partic | 2005 | [11 empty] | 2005
COM | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-year | ASP | IND | REF | 44 | TAS | 382 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-04-01 |  | 256300 | 0 | 256300 | 133606.9 | 52.13% | 122693.1 | 0 | 122693.1 | 33319 | 0 | 17368.897 | 15950.103 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (third tranche) | Multi-Year | ASP | IND | REF | 44 | INV | 383 | N | O | I | CFC | 141 | 141 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2006-12-01 |  | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 21621 | 0 | 21621 | 0 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment | 0 |  |  |  | Latest | Latest | Latest
COM | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (third tranche) | Multi-Year | ASP | IND | FOA | 44 | INV | 384 | N | O | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-12-01 |  | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment | 0 |  |  |  | Latest | Latest | Latest
ONG | UNIDO | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 385 | A | O | I | CTC | 733 | 733 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 | 2009-07-01 |  |  | 3500000 | 0 | 3500000 | 2946055 | 84.17% | 553945 | 397670 | 70000 | 262500 | 0 | 220954 | 41546 | 29825 | The finalization of ongoing project is in progress. SHES assessment is being arranged. The project is expected to be completed in jul 2009. | [13 empty] | 2005 | INV | 173 | 173 |  |  | Yes | Yes | Yes
COM | IBRD | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multiyear | ASP | IND | PHA | 45 | INV | 386 | N | O | I | CTC | 6158 | 9848 | 9827 | 9896 | 2005-04-01 | 2007-04-01 | 2006-04-01 |  | 2006-07-01 |  | 399045 | 0 | 399045 | 399045 | 100% | 0 | 0 | 0 | 29928 | 0 | 29928 | 0 | 0 | 2005 verification of CTC production and consumption completed as scheduled. Levels of CTC production and consumption in 2005, excluding the quantity stockpiled for feedstock use in the following years, are well under the agreed targets. | [13 empty] | 2005 | INV | 1726 | 1726 | 1726 | 1726 | Yes | Yes | Yes
ONG | France | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 387 | A | O | I | CTC | 1385 |  | 0 |  | 2005-04-01 | 2008-01-01 | 2006-04-01 | 2009-07-01 |  |  | 1000000 | 0 | 1000000 | 306950 | 30.7% | 693050 |  | 693050 | 85000 | 0 | 26090.75 | 58909.25 |  | The French contribution is implemented by GTZ-Proklima. During 2009 the main focus of activities will be on training and technical assistance/information dissemination to industries. Eligible enterprises for investment support are also being assessed. The funds from this tranche will be spent during the implementation of the annual working plan 2009. | [10 empty] | 2008-04-01
COM | Germany | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 388 | A | O | I | CTC | 970 |  | 0 |  | 2005-04-01 | 2006-01-01 | 2006-07-01 |  | 2008-12-07 |  | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan. | [15 empty] | 708 |  | 708
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 389 | N | O | I | CTC | 533 |  | 0 |  | 2005-04-01 |  | 2008-04-01 | 2007-09-01 |  |  | 2500000 | 0 | 2500000 |  | 0% | 2500000 |  | 1000000 | 280000 | 0 |  | 280000 | 0 | POs issued end 2006 for safety and ancillary equipment, remaining equipment to be procured early 2007 with expected delivery end of 2Q2007.
COM | IBRD | CFC production sector gradual phase-out: 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 45 | INV | 390 | N | O | I | CFC | 0 | 0 | 1882 | 1882 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-04-01 |  | 5850000 | 0 | 5850000 | 5850000 | 100% | 0 | 0 | 0 | 438750 | 0 | 438750 | 0 | 0 | Completed. | [13 empty] | 2005 | INV | 0 | 0 | 11294 | 11263.48 | Yes | Yes | Yes
COM | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IND | SEV | 45 | TAS | 391 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 |  | 183486 | 0 | 183486 | 166627 | 90.81% | 16859 | 0 | 13487.2 | 16514 | 0 | 14996.6661 | 1517.3339 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IND | SEV | 47 | INS | 392 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2008-12-01 |  | 373230 | 0 | 373230 | 359973 | 96.45% | 13257 | 2615 | 10605.6 | 27992 | 0 | 26997.7339 | 994.2661 | 196.1232 | Completed in 2008. Monitoring and management of implementation of all ongoing phase-out plans and activities. Active participation in Ozone Officers network meetings as well as ExCom, OEWG and MOP meetings. Public awareness and information dissemination activities. | [13 empty] | 2005 | Non-Investment
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 393 | A | O | I | CFC | 0 |  | 0 |  | 2005-11-01 | 2006-01-01 | 2006-12-01 |  | 2007-04-07 | 2007-04-07 | 105090 | 0 | 105090 | 105090 | 100% | 0 | 0 | 0 | 13662 | 0 | 13662 | 0 | 0 | All activities as per the annual working plan have been accomplished. | [15 empty] | 964 |  | 3389 | 2368
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 394 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2007-03-31 | 2007-03-31 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2006: In the operational year 06-07 the following number of technicians are trained: a) in Standard RSE programs: 1810 participants b) Mobile Air-Conditioning programs 238 participants c) Open Type compressor programs: 55 partic | 2006 | [11 empty] | 2006
ONG | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 395 | N | O | I | CFC | 414 | 414 | 0 | 0 | 2005-11-01 | 2007-01-01 | 2006-12-01 | 2009-12-01 |  |  | 1332377 | 0 | 1332377 | 705706 | 52.97% | 626671 | 56452 | 250668.4 | 112417 | 0 | 59542.7206 | 52874.2794 | 4763.0397 | The distribution of equipment kits and mini-reclaim units procured in 2007 continued during 2008 and is now completed. | [13 empty] | 2005 | Investment | 157 | 157 |  |  | Yes | Yes | yes
COM | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-year | ASP | IND | REF | 47 | TAS | 396 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2006-12-01 |  | 2007-04-01 |  | 85000 | 0 | 85000 | 70173.83 | 82.56% | 14826.17 | 0 | 14826.17 | 11050 | 0 | 9122.5979 | 1927.4021 | 0 | Project completed | [13 empty] | 2005 | Non Investment
COM | IBRD | CFC production sector gradual phase-out: 2006 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 397 | N | O | I | CFC | 0 | 0 | 3389 | 3389 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | AP completed. | [13 empty] | 2006 | INV | 0 | 0 | 7342 | 6964 | Yes | Yes | Yes
COM | IBRD | CFC production sector gradual phase-out: balance from the 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 398 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-05-01 | 2007-04-01 |  | 2008-07-01 |  | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Implemented and tranches disbursed. | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0
ONG | France | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 399 | A | O | I | CTC | 0 |  | 0 |  | 2006-07-01 |  | 2007-07-01 | 2009-12-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 |  | 500000 | 85000 | 0 | 0 | 85000 |  | The French contribution is implemented by GTZ-Proklima. The funds from this tranche have been earmarked for investment support. Eligible enterprises have already been assessed, approval by the Government of India is pending.
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multiyear | ASP | IND | PHA | 49 | INV | 400 | N | O | I | CTC | 232 | 232 | 232 | 232 | 2006-07-01 | 2007-11-01 | 2007-07-01 |  | 2007-07-01 |  | 9556267 | 0 | 9556267 | 9556267 | 100% | 0 | 0 | 0 | 716720 | 0 | 716720 | 0 | 0 | The 2006 Verification of CTC production and consumption will be carried out during the first quarter of 2007. The verification report will be submitted to the ExCom in July 2007. | [13 empty] | 2006 | INV | 1147 | 1129 | 1147 | 1129 | Yes | Yes | Yes
COM | Germany | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 401 | A | O | I | CTC | 0 |  | 0 |  | 2006-07-01 | 2008-01-01 | 2007-07-01 |  | 2008-12-01 |  | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan. | [15 empty] | 708 |  | 708
ONG | UNIDO | CTC phase-out for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 402 | A | O | I | CTC | 347 | 347 | 347 |  | 2006-07-01 | 2007-06-01 | 2007-07-01 | 2009-07-01 |  |  | 399046 | 0 | 399046 | 99668 | 24.98% | 299378 | 46196 | 100000 | 29928 | 0 | 7475 | 22453 | 3465 | The finalization of ongoing project is in progress. SHES assessment is being arranged. The project is expected to be completed in jul 2009. | [13 empty] | 2006 | INV | 60 | 60 |  |  | Yes | Yes | Yes
ONG | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 403 | N | O | I | CFC | 138 | 138 | 0 | 0 | 2006-11-01 |  | 2008-06-01 | 2010-03-01 |  |  | 167860 | 0 | 167860 | 0 | 0% | 167860 | 0 | 33572 | 12590 | 0 | 0 | 12590 | 0 | Additional refrigeration servicing equipment kits and mini-reclaim units procured and distributed. | [13 empty] | 2006 | Investment | 74.5 |  |  |  | Latest | Latest | Latest
COM | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 404 | A | O | I | CFC | 358 | 358 | 0 |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2008-04-08 |  | 436200 | 0 | 436200 | 436200 | 100% | 0 | 0 | 0 | 56706 | 0 | 56706 | 0 | 0 | All activities as per the annual working plan have been accomplished. | [15 empty] | 964 |  | 3389 | 2368
COM | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-year | ASP | IND | REF | 50 | TAS | 405 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2008-04-01 |  | 85000 | 0 | 85000 | 20632 | 24.27% | 64368 | 0 | 64368 | 11050 | 0 | 2682.16 | 8367.84 | 0 | Project complted in April 2008. One training for SISI officers on ODS regulations was conducted in June-07 at Hyderabad. Twenty SISI officers from around 20 states participated in the workshop. Contract in developing the on-line system has been issued. The consultant will start the work | [13 empty] | 2006 | Non Investment
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 406 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-11-01 |  | 2008-03-31 | 2008-03-31 | 367140 | 0 | 367140 | 367140 | 100% | 0 | 0 | 0 | 47728 | 0 | 47728 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2007: In the operational year 07-08 the following number of technicians are trained: a) in Standard RSE programs: 1880 participants b) Mobile Air-Conditioning programs 275 participants c) Open Type compressor programs: 113 partic. | 2007 | [11 empty] | 2007
COM | IBRD | CFC production sector gradual phase-out: 2007 annual implementation plan | Multiyear | ASP | IND | PRO | 51 | INV | 407 | N | O | I | CFC | 0 | 0 | 3953 | 3953 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2008-04-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 | 0 | 450000 | 0 | 450000 | 0 | 0 | AP completed. | [13 empty] | 2007 | INV | 0 | 0 | 3389 | 2346.68 | Yes | Yes | Yes
COM | IBRD | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multiyear | ASP | IND | PHA | 52 | INV | 408 | N | O | I | CTC | 420 | 420 | 420 | 420 | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-07-01 |  | 4020938 | 0 | 4020938 | 4020938 | 100% | 0 | 0 | 0 | 301570 | 0 | 301570 | 0 | 0 | Verification exercise of CTC production and consumption for 2007 undertaken in Feb 08. Audit team noted that there was greater cooperation from feedstock users in sharing information during verification. It was confirmed that there were no diversions of CTC stockpiles to non- feedstock applications, no exports and no imports of CTC for non-feedstock applications. Therefore, as per the MP definition, consumption in 2007 is equal to 707 ODP tons and is within the target of 708 ODP tons as per agreement. | [13 empty] | 2007 | INV | 708 | 707 | 708 | 707 | Yes | Yes | Yes
ONG | France | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 409 | A | O | I | CTC | 0 |  | 0 |  | 2007-07-01 |  | 2008-07-01 | 2009-12-01 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 |  | 500000 | 85000 | 0 | 0 | 85000 |  | The French contribution is implemented by GTZ-Proklima. The funds from this tranche have been earmarked for investment support. Eligible enterprises have already been assessed, approval by the Government of India is pending.
ONG | Germany | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 410 | A | O | I | CTC | 0 |  | 0 |  | 2007-07-01 | 2008-12-01 | 2008-07-01 | 2010-12-07 |  |  | 300000 | 0 | 300000 | 25235 | 8.412% | 274765 | 0 | 274765 | 57500 | 0 | 4836.7083 | 52663.2917 | 0 | Activities for this tranche are in sequence with completion of the activities from the previous tranches in the textiles sector (training, information dissemination workshops, technical advisories). | [15 empty] | 708 |  | 708
COM | UNDP | Project preparation for a MDI investment project | Individual | ASP | IND | ARS | 52 | PRP | 411 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2008-07-01 |  | 100000 | 0 | 100000 | 76381 | 76.38% | 23619 | 829 | 23619 | 7500 | 0 | 5728.575 | 1771.425 | 62.175 | Completed in 2008. UNDP mission including MDI international technical expert took place in April 2008 to visit all participating MDI manufacturers. The MDI investment project was prepared in cooperation with the industry and submitted to the 56th ExCom in November 2008, (including the transition strategy) where it was approved. Final invoices still to be settled in 2009. | [13 empty] | 2007 | Investment
ONG | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | IND | SEV | 54 | INS | 416 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 373230 | 0 | 373230 | 0 | 0% | 373230 | 0 | 74646 | 27992 | 0 | 0 | 27992 | 0 | Continuation of IND-392. | [13 empty] | 2008 | Non-Investment
ONG | IBRD | CFC production sector gradual phase-out: 2008 annual implementation plan | Multiyear | ASP | IND | PRO | 54 | INV | 417 | N | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 | 2009-07-01 |  |  | 6000000 | 0 | 6000000 | 3510000 | 58.5% | 2490000 | 2490000 | 2490000 | 450000 | 0 | 263250 | 186750 | 186750 | CFC Accelerated Phaseout Agreement supersedes this Annual Implementation Plan. As India chose to accelerate CFC production stop as of 1 Aug 08, a half-yearly audit was not undertaken by the Government. Instead a national audit will be commissioned in Jan 09, followed by a Bank audit in Feb 09. TA activites proceeding satisfactorily, with additional targeted awareness and training programs in collaboration with GTZ and UNEP. Producer compensation disbursements in 2008 deferred to 2009. | [13 empty] | 2007 | INV | 0 | 0 | 690 | 690 | Yes | No | No
ONG | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 418 | A | O | I |  | 3.2 |  | 0 |  | 2008-04-01 | 2008-09-01 | 2009-03-01 | 2009-03-31 |  |  | 81141 | 0 | 81141 | 70593 | 87% | 10548 | 10548 | 10548 | 10548 | 0 | 5696 | 4852 | 4852 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2008: In the operational year 08-09 the following number of technicians are trained: a) in Standard RSE programs: 1716 participants | 2008 | [11 empty] | 2008
ONG | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 419 | N | O | I | CFC | 70.3 | 60 | 0 | 0 | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 47881 | 0 | 47881 | 0 | 0% | 47881 | 0 | 9576.2 | 3591 | 0 | 0 | 3591 | 0 | It was decided by the NCCOPP Core Group that a one-off information brochure/flyer would be produced advising CFC users of the impending shut-down of CFC production from August 2008 and also for establishing sustainable infrastructures in the sector. | [13 empty] | 2008 | Investment
ONG | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-year | ASP | IND | REF | 54 | TAS | 420 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-31 | 2009-03-31 |  |  | 19900 | 0 | 19900 | 6054.7 | 30.43% | 13845.3 | 0 | 13845.3 | 2587 | 0 | 787.111 | 1799.889 | 0 | Additional training programme conducted by NACEN in 2008; - Chennai 23-24 October 2008, 22 officers were trained - Mumbai 10-11 November, 2008, 21 officers were trained - New Delhi 17-18 November, 2008, 35 officers were trained - Bangalore 19-20 November, 2008, 35 officers were trained. Bangalore 19-20 November, 2008, 19 officers were trained; Hyderabad 11-12 December, 2008, 24 officers were trained; Kanpur 11-12 December, 2008, 22 officers were trained; Kolkata, 11-12 December, 2008, 19 officers were trained; Vadodara, 23-23 December, 2008, 31 officers were trained; Patna 29-30 December, 2008, 23 officers were trained; 4 Modules have been prepared and both NACEN and UNEP have given their comments. | [13 empty] | 2008
ONG | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 421 | A | O | I | CFC | 73.5 | 73.5 | 0 |  | 2008-04-01 | 2008-07-01 | 2009-03-01 | 2010-07-01 |  |  | 101078 | 0 | 101078 | 74052 | 73.26% | 27026 | 0 | 27026 | 13140 | 0 | 9626.6574 | 3513.3426 | 0 | All activities as per the annual working plan have been accomplished. Pending activities are the completion of the final verification report and distribution of the remaining equipment.
ONG | IBRD | CTC phase-out plan for the consumption and production sectors: 2008 annual programme | Multiyear | ASP | IND | PHA | 55 | INV | 422 | N | O | I | CTC | 440 | 0 | 440 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-07-31 |  |  | 3211875 | 0 | 3211875 | 2300000 | 71.61% | 911875 | 911875 | 911875 | 240891 | 0 | 172500.26 | 68390.74 | 68390.74 | CY2008 verification of CTC production and consumption will be carried out during the first quarter of 2009. Verification report will be submitted to the ExCom in Jul 09. | [13 empty] | 2007 | INV | 269 | 269 | 269 | 269 | Yes | No | No
ONG | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | IND | ARS | 56 | INV | 423 | N | O | I | CFC | 564.6 | 0 | 0 | 0 | 2008-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 8082267 | 0 | 8082267 | 0 | 0% | 8082267 | 0 | 1616453.4 | 606170 | 0 | 0 | 606170 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | Italy | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs |  | ASP | IND | ARS | 56 | INV | 424 | N | O | I | CFC | 139.7 | 0 | 0 |  | 2008-11-01 |  | 2013-11-01 | 2013-11-01 |  |  | 2000000 | 0 | 2000000 |  | 0% | 2000000 |  |  | 230000 | 0 |  | 230000 |  | Funds recently approved in Nov 2007 and implementation to be initiated.
ONG | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | IND | ARS | 56 | TAS | 425 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2013-11-30 | 2013-11-30 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 120000 | 15600 | 0 | 0 | 15600 | 0 | Project newly approved | [13 empty] | 2008
ONG | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 426 | A | O | I | CFC | 0 |  | 0 |  | 2008-11-01 |  | 2009-11-01 | 2010-07-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Funds will be disbursed for stakeholder consultations and participation in planning workshops. A representative survey in the servicing sector as per the original plan submitted to the 55th and 56th ExCom cannot be carried out as the cost for such a survey is much higher than the allocated budget for Germany under the HPMP preparation. UNDP as the lead implementing agency will undertake a more general survey in the country, data on the servicing sector will be collected during stakeholder consultations with manufacturers, industry associations and selected servicing enterprises. Legislation/regulation aspects will also be taken into account during the stakeholder consultations. During a recent meeting between the Ozone Cell and the implementing agencies it has been planned to submit the HPMP to the 61st ExCom in July 2010. Hence the planned date of completion of IND/PHA/56/PRP/426 is July 2010
ONG | UNIDO | Preparation of a HCFC phase-out management plan (transportation refrigeration and air-conditioning sectors) | Individual | ASP | IND | PHA | 56 | PRP | 427 | A | O | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2009-11-30 | 2009-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 30000 | 5250 | 0 | 0 | 5250 | 0 | TOR for the preparation of HPMP, stage 1 component has been developed and submitted to the ozone cell. | UNIDO is only cooperating agency and is responsible for the transportation refrigeration and air-conditioning sector. Work on legislation is part of the lead agency's assignments. | [12 empty] | 2008 | NON-INV
ONG | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 428 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 113750 | 0 | 113750 | 0 | 0% | 113750 | 0 | 113750 | 8531 | 0 | 0 | 8531 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IND | PHA | 56 | PRP | 429 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2010-12-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNDP | Preparation of a HCFC phase-out management plan (fire fighting and solvent sectors) | Individual | ASP | IND | PHA | 56 | PRP | 430 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 1500 | 0 | 0 | 1500 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (foam sector) | Individual | ASP | IND | PHA | 56 | PRP | 431 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 105000 | 0 | 105000 | 0 | 0% | 105000 | 0 | 105000 | 7875 | 0 | 0 | 7875 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (air conditioning sector) | Individual | ASP | IND | PHA | 56 | PRP | 432 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 125000 | 0 | 125000 | 0 | 0% | 125000 | 0 | 125000 | 9375 | 0 | 0 | 9375 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (refrigeration sector) | Individual | ASP | IND | PHA | 56 | PRP | 433 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 80000 | 6000 | 0 | 0 | 6000 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNDP | Study to determine production and consumption of ODS | Individual | ASP | IRA | SEV | 04 | TAS | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 30350 | 0 | 30350 | 30350 | 100% | 0 | 0 | 0 | 3946 | 0 | 3946 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
CLO | IBRD | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1993-06-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
CLO | IBRD | Preparation of investment projects (1992) |  | ASP | IRA | SEV | 06 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  |  | 1992-12-01 | 40000 | -39579 | 421 | 421 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening | Individual | ASP | IRA | SEV | 08 | INS | 5 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-12-01 | 2000-12-01 | 200200 | 0 | 200200 | 200200 | 100% | 0 | 0 | 0 | 26026 | 0 | 26026 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | IRA | SEV | 08 | PRP | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-11-01 | 1993-10-01 |  | 1995-03-01 | 1997-12-01 | 17935 | 0 | 17935 | 17935 | 100% | 0 | 0 | 0 | 2332 | 0 | 2332 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1992 | Investment
FIN | UNIDO | Preparatory assistance for phase out of ODS in domestic refrigeration industry | Individual | ASP | IRA | REF | 09 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-06-01 |  | 1996-05-01 | 1998-08-01 | 50000 | 13633 | 63633 | 63633 | 100% | 0 | 0 |  | 6500 | 1772 | 8272 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase-out CFC-11 and CFC-12 | Individual | ASP | IRA | REF | 11 | INV | 8 | A | O | I | CFC | 757 | 757 |  |  | 1993-11-01 | 1994-12-01 | 1995-11-01 |  | 1997-12-01 | 2002-09-01 | 3228395 | 5674963 | 8903358 | 8903358 | 100% | 0 | 0 |  | 419691 | 735911 | 1155602 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phase-out of CFC-11 and CFC-12 in the commercial and small domestic refrigeration industry | Individual | ASP | IRA | REF | 15 | PRP | 9 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector | Individual | ASP | IRA | SEV | 17 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-08-01 | 32065 | 698 | 32763 | 32763 | 100% | 0 | 0 |  | 4168 | 91 | 4259 | 0 | 0 | FIN
FIN | UNIDO | DBL project Iran. Phasing out CFC-11 through conversion of rigid PU-foam manufactured with the technique of continuous lamination at Fabis, Iran Steel, Mammoth Tehran, F.M., and Urethane Systems | Individual | ASP | IRA | FOA | 17 | INV | 11 | A | O | I | CFC | 1200 | 1200 |  |  | 1995-07-01 | 1995-12-01 | 1997-07-01 |  | 1998-12-01 | 2003-05-01 | 2571250 | 0 | 2571250 | 2571250 | 100% | 0 | 0 |  | 334263 | -361 | 333902 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Movalled Home Appliances Co. | Individual | ASP | IRA | REF | 18 | INV | 12 | A | O | I | CFC | 70 | 70 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 607732 | -1500 | 606232 | 606231.7394 | 100% | 0.2606 | 0 |  | 79005 | -320 | 78685 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Machine Manufacturing Co. | Individual | ASP | IRA | REF | 18 | INV | 13 | A | O | I | CFC | 62 | 62 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 608605 | -1737 | 606868 | 606867.5278 | 100% | 0.4722 | 0 |  | 79119 | -351 | 78768 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Lorestan Refrigerator Manufacturing Industries | Individual | ASP | IRA | REF | 18 | INV | 14 | A | O | I | CFC | 94 | 94 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 615018 | -1793 | 613225 | 613225.4118 | 100% | -0.4118 | 0 |  | 79952 | -359 | 79593 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Gadook Industries, Co. | Individual | ASP | IRA | REF | 18 | INV | 15 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 373838 | -944 | 372894 | 372894.3966 | 100% | -0.3966 | 0 |  | 48599 | -200 | 48399 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Faritz, Iran | Individual | ASP | IRA | REF | 18 | INV | 16 | A | O | I | CFC | 109 | 109 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 612504 | -1822 | 610682 | 610682.2582 | 100% | -0.2582 | 0 |  | 79626 | -363 | 79263 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Monark Co. | Individual | ASP | IRA | REF | 18 | INV | 17 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 369939 | -859 | 369080 | 369079.6662 | 100% | 0.3338 | 0 |  | 48092 | -188 | 47904 | 0 | 0 | FIN
FIN | France | Project preparation/technical assistance for MAC recycling and training in good servicing practices |  | ASP | IRA | REF | 20 | PRP | 18 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1997-08-01 | 1997-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | UNIDO | Project formulation in the commercial refrigeration sector (remaining enterprises), compressors and the foam sector | Individual | ASP | IRA | SEV | 21 | PRP | 19 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -8 | 6492 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Safoam Co. | Individual | ASP | IRA | FOA | 22 | INV | 20 | A | O | I | CFC | 120 | 120 |  |  | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 2002-12-01 | 2003-12-01 | 487125 | 0 | 487125 | 487125 | 100% | 0 | 0 |  | 63326 | -85 | 63241 | 0 | 0 | FIN |  |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Urethane Systems Company (USC) | Individual | ASP | IRA | FOA | 22 | INV | 21 | A | O | I | CFC | 110 | 110 |  |  | 1997-05-01 | 2001-09-01 | 1998-06-01 |  | 2003-03-01 | 2004-02-01 | 487125 | -4690 | 482435 | 482435 | 100% | 0 | 0 |  | 63326 | -709 | 62617 | 0 | 0 | FIN |  |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 from flexible slabstock foam manufacturing at Shizar Co. | Individual | ASP | IRA | FOA | 22 | INV | 22 | A | O | I | CFC | 120 | 120 |  |  | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2003-12-01 | 2004-12-01 | 487125 | 0 | 487125 | 487125 | 100% | 0 | 0 |  | 63326 | 0 | 63326 | 0 | 0 | FIN |  |  |  | 2000-11-01
FIN | France | Project preparation and technical assistance in the solvent sector |  | ASP | IRA | SOL | 23 | PRP | 23 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | UNIDO | Phasing out ODS at Electro Steel Co. | Individual | ASP | IRA | REF | 23 | INV | 24 | A | O | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 898159 | -20754 | 877405 | 877405 | 100% | 0 | 0 |  | 116761 | -2879 | 113882 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Chavan Manufacturing Company | Individual | ASP | IRA | REF | 23 | INV | 25 | A | O | I | CFC | 41.8 | 41.8 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-03-01 | 527802 | 0 | 527802 | 527802 | 100% | 0 | 0 |  | 68614 | 0 | 68614 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Saran Co. | Individual | ASP | IRA | REF | 23 | INV | 26 | A | O | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 2002-06-01 | 2003-10-01 | 458663 | -2976 | 455687 | 455687 | 100% | 0 | 0 |  | 59626 | -481 | 59145 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector for phasing out ODS at three enterprises including Bahaman Plastic | Individual | ASP | IRA | FOA | 23 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-06-01 |  | 2000-09-01 | 2001-07-01 | 10000 | -2561 | 7439 | 7439 | 100% | 0 | 0 |  | 1300 | -334 | 966 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Zagross II Co. | Individual | ASP | IRA | REF | 23 | INV | 28 | A | O | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 444858 | -3734 | 441124 | 441124 | 100% | 0 | 0 |  | 57832 | -577 | 57255 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Mashhad Foam | Individual | ASP | IRA | FOA | 23 | INV | 29 | A | O | I | CFC | 90 | 90 |  |  | 1997-11-01 | 1999-01-01 | 1998-12-01 |  | 2003-12-01 | 2004-12-01 | 503330 | -1856 | 501474 | 501474 | 100% | 0 | 0 |  | 65433 | -345 | 65088 | 0 | 0 | FIN |  |  |  | 2000-11-01
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IRA | SEV | 23 | INS | 30 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-08-01 | 1999-12-01 |  | 2002-05-01 | 2003-11-01 | 133470 | 0 | 133470 | 133470 | 100% | 0 | 0 | 0 | 17351 | 0 | 17351 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1997 | Non-Investment
FIN | France | Set up of a national programme of recovery and recycling CFC-12 (pilot project in Tehran) |  | ASP | IRA | REF | 23 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1999-10-12 | 1998-12-01 |  | 2004-12-01 | 2004-12-01 | 345923 | 0 | 345923 | 242768.0348 | 70.18% | 103154.9652 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed; balance returned at the 57th meeting.
FIN | France | Projects preparation and technical assistance in the halon sector |  | ASP | IRA | HAL | 23 | PRP | 32 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 1999-07-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | IRA | FUM | 23 | PRP | 33 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | France | Conversion to non-CFC facilities of 4 companies producing cars and wagons equipped with MAC-umbrella project |  | ASP | IRA | REF | 24 | INV | 34 | A | O | I |  | 0 |  | 0 |  | 1998-03-01 | 2000-02-22 | 1999-04-01 |  | 2002-06-01 | 2008-09-01 | 138600 | 0 | 138600 | 103129.2625 | 74.41% | 35470.7375 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. | [6 empty] | 2002-06-01
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at Sobouhi Refrigeration | Individual | ASP | IRA | REF | 26 | INV | 35 | A | O | I | CFC | 30.4 | 30.4 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 237847 | -23768 | 214079 | 214079 | 100% | 0 | 0 |  | 30920 | -3134 | 27786 | 0 | 0 | FIN
FIN | France | Small and medium enterprises study |  | ASP | IRA | SEV | 26 | TAS | 36 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 2002-05-01 | 1999-12-01 |  | 2005-04-01 | 2005-04-01 | 75000 | 0 | 75000 | 20000 | 26.67% | 55000 |  | 0 | 0 | 0 | 0 | 0 |  | Closed as per decision 45/12, financial closure to be finalised. | [6 empty] | 2002-12-01
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b in manufacture of commercial refrigeration equipment at Yazd Arg Metal, Yazd Sardin and Shervin Electric | Individual | ASP | IRA | REF | 26 | INV | 37 | A | O | I | CFC | 62.2 | 62.2 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2003-02-01 | 743990 | -95365 | 648625 | 648625 | 100% | 0 | 0 |  | 91839 | -10603 | 81236 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 27 | PRP | 38 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -1807 | 18193 | 18193 | 100% | 0 | 0 |  | 2600 | -239 | 2361 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IRA | FOA | 27 | PRP | 39 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 18000 | -1160 | 16840 | 16840 | 100% | 0 | 0 |  | 2340 | -154 | 2186 | 0 | 0 | FIN
FIN | UNDP | Preparation of four projects in the integral skin foam subsector | Individual | ASP | IRA | FOA | 27 | PRP | 40 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of three projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 27 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and domestic refrigeration at the Sherkate Sanayee Emerson (Emerson Co). | Individual | ASP | IRA | REF | 28 | INV | 42 | A | O | I | CFC | 45.8 | 45.8 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-05-01 | 343873 | -10039 | 333834 | 333834 | 100% | 0 | 0 |  | 44703 | -1373 | 43330 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Foroughmanesh Co. | Individual | ASP | IRA | REF | 28 | INV | 43 | A | O | I | CFC | 35.8 | 35.8 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 399803 | -13456 | 386347 | 386347 | 100% | 0 | 0 | 0 | 51974 | -1749 | 50225 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Tahvieh Garm va Sard Co. | Individual | ASP | IRA | REF | 28 | INV | 44 | A | O | I | CFC | 20.5 | 20.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-02-01 | 278659 | -13367 | 265292 | 265292 | 100% | 0 | 0 | 0 | 36226 | -1738 | 34488 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b AND cfc-12 TO hfc-134A in commercial refrigeration at the second group of Iranian Commercial Refrigeration Manufacturers | Individual | ASP | IRA | REF | 28 | INV | 45 | A | O | I | CFC | 42.5 | 42.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-09-01 | 309966 | -1621 | 308345 | 308345 | 100% | 0 | 0 |  | 40296 | -275 | 40021 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Movaledsarma Co. (Zagross 1) | Individual | ASP | IRA | REF | 28 | INV | 46 | A | O | I | CFC | 77.6 | 77.6 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2004-01-01 | 816698 | -12094 | 804604 | 804604 | 100% | 0 | 0 | 0 | 99837 | -1331 | 98506 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Broudati Ghandil Iran (Ghandil Co.) | Individual | ASP | IRA | REF | 28 | INV | 47 | A | O | I | CFC | 27.5 | 27.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 335423 | -3923 | 331500 | 331500 | 100% | 0 | 0 |  | 43605 | -578 | 43027 | 0 | 0 | FIN
FIN | France | Conversion to ODS-free technology at Dorcharkh Company |  | ASP | IRA | SOL | 28 | INV | 48 | A | O | I | CTC | 11 | 11 | 0 |  | 1999-07-01 | 2001-08-22 | 2001-08-01 |  | 2002-12-01 | 2008-10-01 | 157276 | 0 | 157276 | 161561 | 102.7% | -4285 | 0 | 0 | 7864 | 0 | 7864 | 0 |  | Project completed. Approval value is corrected to reflect 5% support costs.
ONG | France | Halon management programme | Halon Banking | ASP | IRA | HAL | 28 | TAS | 49 | A | O | I |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-21 | 2003-08-01 | 2009-12-01 |  |  | 511175 | 0 | 511175 | 102149.2553 | 19.98% | 409025.7447 |  | 350000 | 0 | 0 | 0 | 0 |  | Results of 62 questionnaires: estimated total annual stock and consumption in 2008: 10 MT of halon 1211 and 117 MT of halon 1301.Information and Control Centre selected. MOU prepared and signed with the Fire-fighting organisation of Teheran, which will be the Operator of the R&R centre. Selection of a local consultant to advise the NOU on the establishment of the Information and Control centre, training and servicing needs and on the equipment needs for the R&R centre. International tender organised beginning of 2009.
ONG | UNIDO | Phasing out ODS in manufacturing of flexible PU slabstock foam through the use of liquid CO2 blowing technology at Bahman Plastic Co. | Individual | ASP | IRA | FOA | 28 | INV | 50 | A | O | I | CFC | 83 | 83 |  |  | 1999-07-01 | 2000-11-01 |  |  |  |  | 485929 | 0 | 485929 | 435548 | 89.63% | 50381 | 45000 | 1 | 63171 | 0 | 56621 | 6550 | 5850 | No progress was reported by the ozone office nor the counterpart until the end of December 2008. According to the decision of the 56th ExCom, the project should be cancelled. | [5 empty] | 2002-06-01
COM | UNIDO | Replacement of CFC-12 refrigerant by HFC-134a at Iran Compressor Manufacturing Company (ICMC) | Individual | ASP | IRA | REF | 28 | INV | 51 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2008-08-01 |  | 1076148 | 84000 | 1160148 | 1129655 | 97.37% | 30493 | 23978 | 6000 | 128376 | 9240 | 134262 | 3354 | 2638 | Project completed in Aug 2008.
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Saiwan Sannat Co. | Individual | ASP | IRA | REF | 29 | INV | 52 | A | O | I | CFC | 14.9 | 14.9 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-03-01 | 200709 | 0 | 200709 | 200709 | 100% | 0 | 0 |  | 26092 | 0 | 26092 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Sanaayee Toulidy Bard Co. | Individual | ASP | IRA | REF | 29 | INV | 53 | A | O | I | CFC | 16.4 | 16.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 205529 | 0 | 205529 | 205529 | 100% | 0 | 0 |  | 26719 | 0 | 26719 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Minavand Refrigeration Company | Individual | ASP | IRA | REF | 29 | INV | 54 | A | O | I | CFC | 13.4 | 13.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 176777 | -3308 | 173469 | 173469 | 100% | 0 | 0 |  | 22981 | -466 | 22515 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 tgo HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Electro Shargh Mazandaran Co. | Individual | ASP | IRA | REF | 29 | INV | 55 | A | O | I | CFC | 28.2 | 28.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 301715 | -31900 | 269815 | 269815 | 100% | 0 | 0 | 0 | 39223 | -4147 | 35076 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardkaran Industrial Manufacturing Co. | Individual | ASP | IRA | REF | 29 | INV | 56 | A | O | I | CFC | 25.3 | 25.3 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2002-03-01 | 2003-11-01 | 155405 | -6082 | 149323 | 149323 | 100% | 0 | 0 | 0 | 20203 | -791 | 19412 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
COM | UNIDO | Phasing out of the important non critical, non-essential use of methyl bromide for post-harvest treatment | Individual | ASP | IRA | FUM | 29 | INV | 57 | A | O | I | MBR | 12.4 | 12.4 |  |  | 1999-11-01 | 2000-04-01 | 2001-12-01 |  | 2006-12-01 |  | 260698 | 0 | 260698 | 244950 | 93.96% | 15748 | 355 | 300 | 33891 | 0 | 31844 | 2047 | 46 | The project is expected to be financially completed in 2009.
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Khozestan Technique Co. | Individual | ASP | IRA | REF | 29 | INV | 58 | A | O | I | CFC | 9.6 | 9.6 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-04-01 | 132041 | -1 | 132040 | 132040 | 100% | 0 | 0 | 0 | 17165 | 0 | 17165 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Forouzan Yakhchal Company (Forouzan Ref. Co.) | Individual | ASP | IRA | REF | 29 | INV | 59 | A | O | I | CFC | 16.7 | 16.7 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 192704 | -5358 | 187346 | 187346 | 100% | 0 | 0 |  | 25052 | -736 | 24316 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Electro Sard Azna Co,. | Individual | ASP | IRA | REF | 29 | INV | 60 | A | O | I | CFC | 18.7 | 18.7 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 191061 | -33421 | 157640 | 157640 | 100% | 0 | 0 | 0 | 24838 | -4345 | 20493 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 30 | PRP | 61 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-05-01 | 2003-02-01 | 30000 | -108 | 29892 | 29892 | 100% | 0 | 0 |  | 3900 | -20 | 3880 | 0 | 0 | FIN
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 62 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855 | 3045 | 0 | 0 | Completed in 2000. Financially completed in 2006. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of 3 projects in the domestic refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 63 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Prepare 2 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 64 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HCFC-134a technology in the manufacture of commercial refrigeration equipment at Behsarma Co. | Individual | ASP | IRA | REF | 28 | INV | 65 | A | O | I | CFC | 34.5 | 34.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 455593 | -13588 | 442005 | 442005 | 100% | 0 | 0 | 0 | 59227 | -1766 | 57461 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fadak Refrigeration Industries | Individual | ASP | IRA | REF | 31 | INV | 66 | A | O | I | CFC | 17.3 | 17.3 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-11-01 | 2003-11-01 | 258937 | 0 | 258937 | 258937 | 100% | 0 | 0 | 0 | 33662 | 0 | 33662 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial and domestic refrigeration equipment at Jaleh & Segin Co. | Individual | ASP | IRA | REF | 31 | INV | 67 | A | O | I | CFC | 23.6 | 23.6 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 322309 | 0 | 322309 | 322309 | 100% | 0 | 0 | 0 | 41900 | 0 | 41900 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at MH Seyed Salaki Co. | Individual | ASP | IRA | REF | 31 | INV | 68 | A | O | I | CFC | 9.8 | 9.8 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 141590 | 0 | 141590 | 141590 | 100% | 0 | 0 | 0 | 18407 | 0 | 18407 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at Sanayee Broudati Partou Sard Tawan (Barez-Himalia) and Sanayee Broudati Himalia (Himalia) | Individual | ASP | IRA | REF | 31 | INV | 69 | A | O | I | CFC | 36.09 | 36.09 |  |  | 2000-07-01 | 2000-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-06-01 | 377544 | -3754 | 373790 | 373790 | 100% | 0 | 0 |  | 49081 | -565 | 48516 | 0 | 0 | FIN
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Baharanfarr Co. | Individual | ASP | IRA | REF | 31 | INV | 70 | A | O | I | CFC | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-01-01 | 2003-08-01 |  |  | 2002-11-01 | 208070 | -207415 | 655 | 655 | 100% | 0 | 0 | 0 | 27049 | -26964 | 85 | 0 | 0 | Canceled in 2002. Financially completed in 2002. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fereidooni Refrigerant Industries | Individual | ASP | IRA | REF | 31 | INV | 71 | A | O | I | CFC | 10.4 | 10.4 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-11-01 | 157454 | 0 | 157454 | 157454 | 100% | 0 | 0 | 0 | 20469 | 0 | 20469 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | ASP | IRA | REF | 31 | PRP | 72 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-04-01 | 2002-01-01 |  | 2002-08-01 | 2003-02-01 | 70000 | -1431 | 68569 | 68569 | 100% | 0 | 0 |  | 9100 | -200 | 8900 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Rashestan Co. | Individual | ASP | IRA | FOA | 31 | INV | 73 | A | O | I | CFC | 70 | 70 |  |  | 2000-07-01 | 2001-04-01 | 2003-01-01 |  | 2005-07-01 | 2005-12-01 | 539882 | 0 | 539882 | 539882 | 100% | 0 | 0 |  | 69387 | -79 | 69308 | 0 | 0 | FIN
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | IRA | SEV | 32 | INS | 74 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-08-01 | 2004-01-01 | 133470 | -25 | 133445 | 133445 | 100% | 0 | 0 | 0 | 17351 | -3 | 17347.75 | 0.25 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2000 | Non-Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nobough Industrial Co. | Individual | ASP | IRA | FOA | 32 | INV | 75 | A | O | I | CFC | 31.8 | 21 | 0 | 0 | 2000-12-01 | 2002-01-01 | 2004-01-01 |  |  | 2003-07-01 | 248736 | -198081 | 50655 | 50655 | 100% | 0 | 0 | 0 | 32336 | -25751 | 6585 | 0 | 0 | Canceled in 2003. Financially completed in 2006. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to n-pentane technology in the manufacture of integral skin polyurethane foam products at Iran Polyurethane Manufacturing Co. | Individual | ASP | IRA | FOA | 32 | INV | 76 | A | O | I | CFC | 51.8 | 51.8 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-08-01 | 2003-11-01 | 796230 | 0 | 796230 | 796230 | 100% | 0 | 0 | 0 | 97585 | 0 | 97585 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 77 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
CLO | UNIDO | Project preparation in soil fumigation | Individual | ASP | IRA | FUM | 33 | PRP | 78 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  |  | 2003-05-01 | 25000 | -19845 | 5155 | 5155 | 100% | 0 | 0 |  | 3250 | -2581 | 669 | 0 | 0 | CLO | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 79 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNIDO | Project preparation in the solvent (CTC) sector | Individual | ASP | IRA | SOL | 33 | PRP | 80 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2005-12-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | -2 | 2598 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 81 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Yakhchalsazi Yazd Co. | Individual | ASP | IRA | REF | 34 | INV | 82 | A | O | I | CFC | 30 | 30 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 248646 | -43159 | 205487 | 205487 | 100% | 0 | 0 | 0 | 32324 | -5611 | 26713 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the domestic refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Rezvan Co. | Individual | ASP | IRA | REF | 34 | INV | 84 | A | O | I | CFC | 13.2 | 13.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 182182 | -34099 | 148083 | 148083 | 100% | 0 | 0 | 0 | 23684 | -4433 | 19251.07 | -0.07 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Electro Ara Co. | Individual | ASP | IRA | REF | 34 | INV | 85 | A | O | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-06-01 | 2007-02-01 | 178784 | -45309 | 133475 | 133475 | 100% | 0 | 0 | 0 | 23242 | -5890 | 17352 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Boloorin Yazd Refrigerator Co. | Individual | ASP | IRA | REF | 34 | INV | 86 | A | O | I | CFC | 20.5 | 20.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2005-09-01 | 212320 | -37255 | 175065 | 175065 | 100% | 0 | 0 | 0 | 27602 | -4843 | 22759 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Sarmaye Sepahan Co. | Individual | ASP | IRA | REF | 34 | INV | 87 | A | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 148525 | 0 | 148525 | 148525 | 100% | 0 | 0 | 0 | 19308 | 0 | 19308 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded and integral skin polyurethane foams at Abre Sanati Iran | Individual | ASP | IRA | FOA | 34 | INV | 88 | A | O | I | CFC | 47.5 | 47.5 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2005-11-01 | 344407 | -7956 | 336451 | 336451 | 100% | 0 | 0 | 0 | 44773 | -1034 | 43739 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Mersun Co. | Individual | ASP | IRA | REF | 34 | INV | 89 | A | O | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 162891 | -25194 | 137697 | 137697 | 100% | 0 | 0 | 0 | 21176 | -3275 | 17901 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ideal Sardsir Co. | Individual | ASP | IRA | REF | 34 | INV | 90 | A | O | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 187907 | -13311 | 174596 | 174596 | 100% | 0 | 0 | 0 | 24428 | -1730 | 22698 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parsa Sazan Co. | Individual | ASP | IRA | REF | 34 | INV | 91 | A | O | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 212845 | -60001 | 152844 | 152844 | 100% | 0 | 0 | 0 | 27670 | -7800 | 19870 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Zenoz Sanaat Co. | Individual | ASP | IRA | REF | 34 | INV | 92 | A | O | I | CFC | 10.2 | 10.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2003-12-01 | 140036 | 0 | 140036 | 140036 | 100% | 0 | 0 | 0 | 18205 | 0 | 18205 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Part | Individual | ASP | IRA | REF | 34 | INV | 93 | A | O | I | CFC | 8.2 | 8.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2005-10-01 | 114770 | 0 | 114770 | 114770 | 100% | 0 | 0 | 0 | 14920 | 0 | 14920 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sepand Afroz Co. | Individual | ASP | IRA | REF | 34 | INV | 94 | A | O | I | CFC | 12.6 | 12.6 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 172881 | -13071 | 159810 | 159810 | 100% | 0 | 0 | 0 | 22475 | -1699 | 20776 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Yakhchalsazi Anzabi Co. | Individual | ASP | IRA | REF | 34 | INV | 95 | A | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 138935 | -17 | 138918 | 138918 | 100% | 0 | 0 | 0 | 18062 | -2 | 18060 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at General Industries | Individual | ASP | IRA | REF | 34 | INV | 96 | A | O | I | CFC | 31.1 | 31.1 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 428197 | 0 | 428197 | 428197 | 100% | 0 | 0 | 0 | 55666 | 0 | 55666 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ghaynar Khazar Co. | Individual | ASP | IRA | REF | 34 | INV | 97 | A | O | I | CFC | 16.8 | 16.8 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-11-01 | 2003-11-01 | 191092 | -30740 | 160352 | 160352 | 100% | 0 | 0 | 0 | 24842 | -3996 | 20846 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the Takran Mobbarad Co. | Individual | ASP | IRA | REF | 34 | INV | 98 | A | O | I | CFC | 9.6 | 9.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 119864 | -2915 | 116949 | 116949 | 100% | 0 | 0 |  | 15582 | -403 | 15179 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ojan Cooling Industries | Individual | ASP | IRA | REF | 34 | INV | 99 | A | O | I | CFC | 7.5 | 7.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2004-01-01 | 110863 | 0 | 110863 | 110863 | 100% | 0 | 0 | 0 | 14412 | 0 | 14412 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Hanzad Co. | Individual | ASP | IRA | REF | 34 | INV | 100 | A | O | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2007-03-01 | 199627 | -28424 | 171203 | 171203 | 100% | 0 | 0 | 0 | 25952 | -3695 | 22257 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Tehran Shirak | Individual | ASP | IRA | REF | 34 | INV | 101 | A | O | I | CFC | 20.5 | 20.5 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2005-09-01 | 202836 | -1649 | 201187 | 201187 | 100% | 0 | 0 |  | 26369 | -256 | 26113 | 0 | 0 | FIN | [13 empty] | 2000 | INV
FIN | UNIDO | Preparation of 12 investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 102 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 15000 | -403 | 14597 | 14597 | 100% | 0 | 0 |  | 1950 | -55 | 1895 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Donyaye Mojdeh | Individual | ASP | IRA | REF | 34 | INV | 103 | A | O | I | CFC | 15.4 | 15.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2004-09-01 | 191020 | -2225 | 188795 | 188795 | 100% | 0 | 0 |  | 24833 | -329 | 24504 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Zarifan Mashad | Individual | ASP | IRA | REF | 34 | INV | 104 | A | O | I | CFC | 22 | 22 |  |  | 2001-07-01 | 2002-03-01 | 2003-12-01 |  | 2004-06-01 | 2005-12-01 | 200550 | -1183 | 199367 | 199367 | 100% | 0 | 0 |  | 26072 | -195 | 25877 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Novin Enjemad | Individual | ASP | IRA | REF | 34 | INV | 105 | A | O | I | CFC | 10.1 | 10.1 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 138702 | -1665 | 137037 | 137037 | 100% | 0 | 0 |  | 18031 | -244 | 17787 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | ASP | IRA | FOA | 34 | PRP | 106 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-03-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 20000 | -840 | 19160 | 19160 | 100% | 0 | 0 |  | 2600 | -113 | 2487 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Roshan Ind. Group | Individual | ASP | IRA | REF | 34 | INV | 107 | A | O | I | CFC | 18.6 | 18.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 203960 | -5201 | 198759 | 198759 | 100% | 0 | 0 |  | 26515 | -717 | 25798 | 0 | 0 | FIN | [13 empty] | 2000 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Avaj Sarma Co. | Individual | ASP | IRA | REF | 34 | INV | 108 | A | O | I | CFC | 15.2 | 15.2 |  |  | 2001-07-01 | 2001-11-01 | 2004-08-01 |  | 2004-06-01 | 2005-08-01 | 176477 | -534 | 175943 | 175943 | 100% | 0 | 0 |  | 22942 | -106 | 22836 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sana Commercial Co. | Individual | ASP | IRA | REF | 34 | INV | 109 | A | O | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 156286 | -367 | 155919 | 155919 | 100% | 0 | 0 | 0 | 20317 | -48 | 20269 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Golsarma Co. | Individual | ASP | IRA | REF | 34 | INV | 110 | A | O | I | CFC | 28.3 | 28.3 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 230066 | -13115 | 216951 | 216951 | 100% | 0 | 0 | 0 | 29909 | -1705 | 28204 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Arjah Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 111 | A | O | I | CFC | 27.4 | 27.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2005-06-01 | 2006-09-01 | 209425 | -304 | 209121 | 209121 | 100% | 0 | 0 |  | 27225 | -39 | 27186 | 0 | 0 | FIN | [13 empty] | 2000 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Shagayegh Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 112 | A | O | I | CFC | 10 | 10 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 137985 | -514 | 137471 | 137471 | 100% | 0 | 0 | 0 | 17938 | -67 | 17871 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Gasso Co. | Individual | ASP | IRA | REF | 34 | INV | 113 | A | O | I | CFC | 11.7 | 11.7 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 158232 | -4811 | 153421 | 153421 | 100% | 0 | 0 |  | 20570 | -657 | 19913 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Iranogharb | Individual | ASP | IRA | FOA | 34 | INV | 114 | A | O | I | CFC | 62 | 62 | 0 |  | 2001-07-01 | 2001-08-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 386260 | 0 | 386260 | 386260 | 100% | 0 | 0 | 0 | 50214 | 0 | 50214 | 0 | 0 | Project completed except for the certificate of destruction which is still outstanding. PCR was prepared and forwarded to the country for comment.. | [13 empty] | 2002
FIN | UNIDO | Phasing out ODS in the manufacture of flexible slab stock foam through the use of LCD blowing technology at Abre Shomal Co. | Individual | ASP | IRA | FOA | 35 | INV | 115 | A | O | I | CFC | 90.4 | 90.4 |  |  | 2001-12-01 | 2002-06-01 | 2003-07-01 |  | 2004-03-01 | 2005-08-01 | 552148 | -50609 | 501539 | 501539 | 100% | 0 | 0 |  | 70736 | -5654 | 65082 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Esfanj Jajerood foam company | Individual | ASP | IRA | FOA | 35 | INV | 116 | A | O | I | CFC | 89 | 89 | 0 |  | 2001-12-01 | 2001-01-01 | 2003-05-01 |  | 2004-12-01 | 2007-12-01 | 499299 | 0 | 499299 | 499299 | 100% | 0 | 0 | 0 | 64909 | 0 | 64909 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sandalisazi Esfanje Ghalebi Iran | Individual | ASP | IRA | FOA | 35 | INV | 117 | A | O | I | CFC | 22.4 | 22.4 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2007-02-01 | 188820 | -7749 | 181071 | 181071 | 100% | 0 | 0 | 0 | 24547 | -1007 | 23540 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector in 5 companies | Individual | ASP | IRA | FOA | 35 | PRP | 118 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2001-01-01 | 2003-01-01 |  | 2002-09-01 | 2002-12-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 5 projects submitted and approved in Jul-02.
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Abbaspour Co. | Individual | ASP | IRA | REF | 35 | INV | 119 | A | O | I | CFC | 9.7 | 9.7 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 144206 | -741 | 143465 | 143465 | 100% | 0 | 0 |  | 18747 | -126 | 18621 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Moradi Company | Individual | ASP | IRA | REF | 35 | INV | 120 | A | O | I | CFC | 6.4 | 6.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-03-01 | 82400 | -2031 | 80369 | 80369 | 100% | 0 | 0 |  | 10712 | -281 | 10431 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Bouran Saz Karaj (Kohsar Co.) | Individual | ASP | IRA | REF | 35 | INV | 121 | A | O | I | CFC | 9.6 | 9.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 120526 | -2024 | 118502 | 118502 | 100% | 0 | 0 |  | 15668 | -287 | 15381 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Sherkate Taavoni 435 (Khorsandi Co.) | Individual | ASP | IRA | REF | 35 | INV | 122 | A | O | I | CFC | 5.4 | 5.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 82107 | -1871 | 80236 | 80236 | 100% | 0 | 0 |  | 10674 | -260 | 10414 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alborz Neishabour | Individual | ASP | IRA | REF | 35 | INV | 123 | A | O | I | CFC | 16 | 16 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2005-08-01 | 189669 | -4567 | 185102 | 185102 | 100% | 0 | 0 |  | 24657 | -632 | 24025 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at the Ariz Pooyaye Sanat (Ariz Co.) | Individual | ASP | IRA | REF | 35 | INV | 124 | A | O | I | CFC | 7.6 | 7.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 86365 | -3752 | 82613 | 82613 | 100% | 0 | 0 |  | 11227 | -504 | 10723 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Yaghoubali Bazdid Vahdat (Isun Co.) | Individual | ASP | IRA | REF | 35 | INV | 125 | A | O | I | CFC | 10.5 | 10.5 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 131605 | -2900 | 128705 | 128705 | 100% | 0 | 0 |  | 17109 | -404 | 16705 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Darvish Mohamad Nazari Company (Jahan Nama) | Individual | ASP | IRA | REF | 35 | INV | 126 | A | O | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-05-01 | 139970 | -140 | 139830 | 139830 | 100% | 0 | 0 |  | 18196 | -47 | 18149 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Borna Sanat Arak | Individual | ASP | IRA | REF | 35 | INV | 127 | A | O | I | CFC | 8 | 8 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2007-05-01 | 108238 | -802 | 107436 | 107436 | 100% | 0 | 0 |  | 14071 | -104 | 13967 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sard Va Garm | Individual | ASP | IRA | REF | 35 | INV | 128 | A | O | I | CFC | 8.4 | 8.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 125350 | -4570 | 120780 | 120780 | 100% | 0 | 0 |  | 16296 | -619 | 15677 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardintous Co. | Individual | ASP | IRA | REF | 35 | INV | 129 | A | O | I | CFC | 10.3 | 10.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 145879 | -281 | 145598 | 145598 | 100% | 0 | 0 |  | 18964 | -66 | 18898 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Gostar Co. | Individual | ASP | IRA | REF | 35 | INV | 130 | A | O | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 100384 | -3803 | 96581 | 96581 | 100% | 0 | 0 |  | 13050 | -514 | 12536 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Alireza Abdolrezazadeh Co. | Individual | ASP | IRA | REF | 35 | INV | 131 | A | O | I | CFC | 7.7 | 7.7 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 116646 | -327 | 116319 | 116319 | 100% | 0 | 0 | 0 | 15164 | -43 | 15121 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Garm Iran Co. | Individual | ASP | IRA | REF | 35 | INV | 132 | A | O | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2006-10-01 | 153447 | -30506 | 122941 | 122941 | 100% | 0 | 0 | 0 | 19948 | -3966 | 15982 | 0 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2001 | Investment
COM | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Ghotb Jonoub Industrial Group | Individual | ASP | IRA | REF | 35 | INV | 133 | A | O | I | CFC | 14.6 | 14.6 | 0 | 0 | 2001-12-01 | 2004-06-01 | 2004-07-01 |  | 2006-04-01 |  | 170125 | 0 | 170125 | 167514 | 98.47% | 2611 | 0 | 2088.8 | 22116 | 0 | 21776.5738 | 339.4262 | 0 | Completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Havasaz Manufacturing and Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 134 | A | O | I | CFC | 24.5 | 24.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 252294 | -19021 | 233273 | 233273 | 100% | 0 | 0 | 0 | 32798 | -2473 | 30325 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Mehran Sard, Co. | Individual | ASP | IRA | REF | 35 | INV | 135 | A | O | I | CFC | 17.7 | 17.7 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 144715 | -1097 | 143618 | 143618 | 100% | 0 | 0 | 0 | 18813 | -143 | 18670 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parto Shiva Sanaat | Individual | ASP | IRA | REF | 35 | INV | 136 | A | O | I | CFC | 23.9 | 23.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2007-01-01 | 283948 | -36625 | 247323 | 247323 | 100% | 0 | 0 | 0 | 36913 | -4761 | 32152 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Sain Electric Co. | Individual | ASP | IRA | REF | 35 | INV | 137 | A | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 152024 | -32223 | 119801 | 119801 | 100% | 0 | 0 | 0 | 19763 | -4189 | 15574 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Boroudati Maleki | Individual | ASP | IRA | REF | 35 | INV | 138 | A | O | I | CFC | 17.9 | 17.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2006-06-01 | 215052 | -178 | 214874 | 214874 | 100% | 0 | 0 | 0 | 27957 | -23 | 27934 | 0 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Fan, Co. | Individual | ASP | IRA | REF | 35 | INV | 139 | A | O | I | CFC | 20.8 | 20.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-10-01 | 267075 | -26729 | 240346 | 240346 | 100% | 0 | 0 | 0 | 34720 | -3475 | 31245 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Tehran Sardsazi Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 140 | A | O | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 125244 | 0 | 125244 | 125244 | 100% | 0 | 0 | 0 | 16282 | 0 | 16282 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 141 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -85 | 1215 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 2 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 142 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -85 | 1215 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 4 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 143 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 6 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 144 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNEP | Preparation of country programme update | Individual | ASP | IRA | SEV | 36 | CPG | 145 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 26250 | -3250 | 23000 | 23000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 3,250 returned ExCom 46 | [12 empty] | 2002 | Non Investment
FIN | UNIDO | Preparation of 3 umbrella investment projects in the commercial and domestic refrigeration sector | Individual | ASP | IRA | REF | 36 | PRP | 146 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 30000 | -2109 | 27891 | 27891 | 100% | 0 | 0 |  | 3900 | -280 | 3620 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNDP | Project preparation in the manufacturing of refrigeration equipment sector (terminal phase-out) | Individual | ASP | IRA | REF | 36 | PRP | 147 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 35000 | -5431 | 29569 | 29569 | 100% | 0 | 0 | 0 | 4550 | -706 | 3844 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNIDO | Formulation of two umbrella investment projects in the rigid and flexible foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 148 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2003-10-01 | 2004-07-01 | 35000 | -557 | 34443 | 34443 | 100% | 0 | 0 |  | 4550 | -80 | 4470 | 0 | 0 | FIN | [13 empty] | 2002 | INV
COM | UNIDO | Phasing out of ODS in the manufacture of flexible slabstock foam through the use of LCD blowing technology at Esfanj Shirvan Co. | Individual | ASP | IRA | FOA | 37 | INV | 149 | A | O | I | CFC | 91.1 | 91.1 |  |  | 2002-07-01 | 2002-11-01 | 2004-03-01 |  | 2008-12-01 |  | 373515 | 0 | 373515 | 299515 | 80.19% | 74000 | 74000 | 74000 | 48557 | 0 | 38937 | 9620 | 9620 | Project completed in Dec 2008. | [8 empty] | 2005-06-01 |  |  |  |  | 2002 | INV
FIN | Germany | Conversion from CFC-11 to pentane technology in the manufacture of integral skin PU foam at Jahad Tahghihat Group | Individual | ASP | IRA | FOA | 37 | INV | 150 | A | O | I | CFC | 23 | 23 | 0 |  | 2002-07-01 | 2002-10-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 335249 | 0 | 335249 | 335249 | 100% | 0 | 0 | 0 | 43582 | 0 | 43582 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Abre Baspar foam company | Individual | ASP | IRA | FOA | 37 | INV | 151 | A | O | I | CFC | 77 | 77 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 387174 | 0 | 387174 | 387174 | 100% | 0 | 0 | 0 | 50333 | 0 | 50333 | 0 | 0 | Equipment has been delivered and installed, certificate of destruction was signed. Project is completed. PCR has been submitted for comment to the country.
COM | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded PU foam at Sanayeh Dashboard Iran | Individual | ASP | IRA | FOA | 37 | INV | 152 | A | O | I | CFC | 22 | 22 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2007-12-01 |  | 185632 | 0 | 185632 | 143632 | 77.37% | 42000 | 0 | 0 | 24132 | 0 | 18672.0362 | 5459.9638 | 0 | NOU acknowledged destruction of old equipment in December 2007. PCR was sent to NOU in Nov-2008, still waiting for approval. Funds of USD 42.000 will be returned to MLFS.
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Nikou Esfandj | Individual | ASP | IRA | FOA | 37 | INV | 153 | A | O | I | CFC | 18.6 | 18.6 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 228310 | 0 | 228310 | 228310 | 100% | 0 | 0 | 0 | 29680 | 0 | 29680 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Project preparation for the development of a foam sector strategy | Individual | ASP | IRA | FOA | 37 | PRP | 154 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  | 2002-12-01 | 2003-12-01 | 51850 | 0 | 51850 | 51850 | 100% | 0 | 0 | 0 | 6741 | 0 | 6741 | 0 | 0 | Project preparation lead to sector phase out strategy, included in NPOP approved at 41st ExCom.
COM | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Yakhchavan Co. | Individual | ASP | IRA | FOA | 37 | INV | 155 | A | O | I | CFC | 73.6 | 73.6 |  |  | 2002-07-01 | 2002-11-01 | 2005-03-01 |  | 2005-12-01 |  | 531838 | 0 | 531838 | 524645 | 98.65% | 7193 | 0 | 1 | 68502 | 0 | 67711 | 791 | 0 | Financial completion in Dec 2008. | [13 empty] | 2002 | INV
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Phira Khodro | Individual | ASP | IRA | FOA | 37 | INV | 156 | A | O | I | CFC | 20.2 | 20.2 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 158166 | 0 | 158166 | 158166 | 100% | 0 | 0 | 0 | 20562 | 0 | 20562 | 0 | 0 | Project is completed. PCR was signed by NOU in June 2007 and submitted by end 2007.
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | IRA | SEV | 38 | INS | 157 | N | T | I | No_ODP | 14.3 | 14.3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2005-12-01 | 2007-06-01 | 173511 | -1407 | 172104 | 172104 | 100% | 0 | 0 | 0 | 22556 | -183 | 22373.53 | -0.53 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2002 | Non-Investment
FIN | UNIDO | Preparation of investment projects in the solvent sector (CTC/TCA) | Individual | ASP | IRA | SOL | 39 | PRP | 158 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 750 | 0 | 750 | 0 | 0 | FIN | [13 empty] | 2003
FIN | Germany | Preparation of a national CFC phase-out plan | Individual | ASP | IRA | PHA | 39 | PRP | 159 | A | O | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-04-01 | 2004-04-01 |  | 2003-11-01 | 2003-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 3120 | 0 | 3120 | 0 | 0 | National Phase Out Plan has been submitted and appproved at the 41th meeting
FIN | Germany | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 160 | A | O | I | CFC | 0 |  | 0 |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 | 694124 | 946405 | 1640529 | 1640529 | 100% | 0 | 0 | 0 | 76354 | 104105 | 180459 | 0 | 0 | Activity progressed according to plan. So far, a total of 1500 ODP tons have been replaced with CFC-free technology. All of the funds have been disbursed and the targeted ODP phase out has been achieved. The tranche is completed, all outstanding certificates of destruction were handed in by december 2007. | [15 empty] | 578.7
ONG | UNEP | National CFC phase-out plan: first tranche | Multi-year | ASP | IRA | PHA | 41 | TAS | 161 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 | 2009-12-01 |  |  | 140253 | 0 | 140253 | 140253.35 | 100% | -0.35 | 0 | -0.35 | 18232.89 | 0 | 18232.9355 | -0.0455 | 0 | Regulation and Policy Support: The licensing system/quota has been approved by the National Ozone Committee, which has been empowered to take such decisions. It is more like an administrative order. A sub committee has been formed to review the existing regulatory and policy measures and to propose new amendments to the existing regulations in order to improve the enforcement of the key components of the Licensing System. Decisions made by the sub-committee and their reports are being sent for the confirmation and enforcement by the relevant line-ministries. The present penalties for any violation from the approved amendments to the regulations are being enforced under the legal framework as stipulated in the Comprehensive Legislation Plan (CLP). The existing in place licensing system was approved by the National Ozone Committee to be applied to control import of HCFCs. As the first step towards enforcement of the licensing system for the import/export of HCFCs in the country, the National Ozone Committee approved at its meeting of 28 December 2008 to have the Statistics Forms for the National Ozone Unit (for import) completed by the Ministry of Commerce and the Customs Department at the time of registration and import of HCFCs into the country and return the completed forms back to the National Ozone Unit on a regular basis for its record. First Stakeholder Consultation Meeting on Illegal Trade of ODS and ODS Containing Products, 14 June 2008, Tehran-Iran The meeting was attended by 54 representatives (managers and officers) from the Customs Department, Ministry of Commerce, Supreme Council of the Free Trade Zones, Task Force to Combat Smuggling of Goods, Provincial Ozone Cells as well as members of Policy & Enforcement Centre: Annual quota allocation base on the criteria adopted and approved by the legal sub-committee of the National Ozone Committee; Close coordination with EC on iPIC; · Close coordination with importers and Commerce Ministry; · Close coordination with Customs Department; · Close coordination with the Regional Enforcement Network (REN) on illegal control of ODS and ODS containing products; · The database on illegal trade is available in Farsi now and was the basis of the workshop organized on 26th September 2008 with the provincial Ozone Officers; · Provincial Ozone Officers were provided with necessary trainings in a one day workshop on the application of IT in ODS monitoring; · There is good coordination with the Customs Department and the Ministry of Commerce. The database is in the National Ozone Unit of the Department of Environment and linked online to the provincial ozone cells. The database is scheduled to be linked to other relevant line-ministries (the Customs Department and the Ministry of Commerce).; · The Enforcement Officer in coordination with the National Ozone Unit and Customs Department has held one workshop on illegal trade issues and intends organizing similar workshops on a regular basis. The Refrigeration Industries Association has also been involved in assisting the National Ozone Unit in addressing illegal trade issues. This follows the PPP model developed by UNEP CAP on involving industry in the fight against illegal trade. | [13 empty] | 2003 | Non Investment
FIN | UNIDO | National CFC phase-out plan (first tranche of implementation plan 2004) | Multi-Year | ASP | IRA | PHA | 41 | INV | 162 | A | O | I | CFC | 274.1 | 274.1 |  |  | 2003-12-01 | 2004-03-01 | 2005-04-01 |  | 2005-12-01 | 2007-12-01 | 361840 | 2104066 | 2465906 | 2465906 | 100% | 0 | 0 |  | 27138 | 157805 | 184943 | 0 | 0 | FIN | [13 empty] | 20032004 | INV | N/A | N/A |  |  | N/A | N/A | N/A
COM | France | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 163 | A | O | I | CFC | 0 | 59.4 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 |  | 1006620 | 0 | 1006620 | 1006620 | 100% | 0 |  | 0 | 110728 | 0 | 110728 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | UNIDO | Preparation of investment projects in the solvent sector CTC/TCA | Individual | ASP | IRA | SOL | 42 | PRP | 164 | A | O | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -110 | 14890 | 14890 | 100% | 0 | 0 |  | 1125 | -8 | 1117 | 0 | 0 | FIN | [13 empty] | 2004 | NON-INV
COM | UNDP | National CFC phase-out plan: first tranche | Multi-Year | ASP | IRA | PHA | 42 | INV | 165 | N | O | I | CFC | 56 | 56 | 0 | 0 | 2004-04-01 | 2005-05-01 | 2007-04-01 |  | 2007-12-01 |  | 770000 | 0 | 770000 | 758043 | 98.45% | 11957 | 0 | 9565.6 | 57750 | 0 | 56853.225 | 896.775 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment | 56 |  |  |  | Latest | Latest | Latest
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IRA | SEV | 44 | INS | 167 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-03-01 | 2007-06-01 | 86755 | -1313 | 85442 | 85442 | 100% | 0 | 0 | 0 | 6507 | -98 | 6408.6 | 0.4 | 0 | Completed in 2006. Financially completed in 2007. | [13 empty] | 2004 | Non-Investment
FIN | UNIDO | Preparatory assistance in methyl bromide (soil fumigation in olive tree nurseries) | Individual | ASP | IRA | FUM | 44 | PRP | 168 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 9830 | -1250 | 8580 | 8580 | 100% | 0 | 0 |  | 737 | -93 | 644 | 0 | 0 | FIN | [13 empty] | 2004
FIN | Germany | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 169 | A | O | I | CFC | 108.7 | 108.7 | 0 |  | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2007-12-01 | 2007-12-01 | 479044 | 0 | 479044 | 479044 | 100% | 0 | 0 | 0 | 52695 | 0 | 52695 | 0 | 0 | Funds have been disbursed for the conversion of additional manufacturers in the foam sector. Certificates of destruction were handed in by Dec-2008. | [15 empty] | 578.7
FIN | UNIDO | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 170 | A | O | I | CFC | 115.5 | 115.5 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 742449 | -52 | 742397 | 742397 | 100% | 0 | 0 |  | 55684 | -4 | 55680 | 0 | 0 | Financial completion in May 2008. Refund was reported to 55th ExCom, Jul 2008. FIN. | [13 empty] | 2005 | INV | N/A | N/A |  |  | N/A | N/A | N/A
ONG | France | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 171 | A | O | I | CFC | 91.4 | 94.3 | 0 |  | 2005-04-01 | 2007-04-01 | 2007-04-01 | 2009-06-01 |  |  | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 55000 | 0 | 55000 | 0 |  | The French contribution is implemented by GTZ-Proklima. Funds of this tranche were disbursed for the purchase of the equipment tendered in 2007 (see first tranche). The 180 units were delivered to Iran in Dec-2007. 160 of the 180 units were distributed by Dec-2008, remaining 20 units will be disbursed until June 2009. Monitoring of workshops will be continued.
COM | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IRA | SEV | 45 | TAS | 172 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 |  | 68807 | 0 | 68807 | 58536 | 85.07% | 10271 | 0 | 8216.8 | 6193 | 0 | 5268.5548 | 924.4452 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
FIN | UNIDO | Preparation of an MDI project | Individual | ASP | IRA | ARS | 47 | PRP | 173 | A | O | I |  |  | 0 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2008-04-01 | 2008-09-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 5250 | 0 | 5250 | 0 | 0 | Project completed in Apr 2008. Financial completion in Sep 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2005 | NON-INV
FIN | UNDP | Extension of institutional strengthening project (phase V, year 2) | Individual | ASP | IRA | SEV | 47 | INS | 174 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-03-01 | 2008-09-01 | 86756 | 0 | 86756 | 86687 | 99.92% | 69 | 0 | 0 | 6507 | 0 | 6501.8248 | 5.1752 | 0 | Completed in 2007. Financially Completed in 2008. | [13 empty] | 2005 | Non-Investment
COM | UNIDO | Total phase-out of methyl bromide in soil fumigation in olive seedings, fruit trees, nurseries and others | Individual | ASP | IRA | FUM | 47 | INV | 175 | A | O | I | MBR | 14.4 | 14.4 |  |  | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2008-12-01 |  | 227950 | 0 | 227950 | 218903 | 96.03% | 9047 | 133 | 100 | 20516 | 0 | 19701 | 815 | 12 | Equipments were purchased and training provided. The project completed in Dec 2008. | [13 empty] | 2005 | INV
COM | Germany | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 176 | A | O | I | CFC | 294.5 | 294.5 | 0 |  | 2006-04-01 | 2006-10-05 | 2007-04-01 |  | 2008-08-01 |  | 1007124 | 0 | 1007124 | 1007124 | 100% | 0 | 0 | 0 | 110784 | 0 | 110784 | 0 | 0 | Funds have been disbursed for the conversion of manufacturers in the foam sector. Certificates of destruction will be collected and handed in during 2009. | [15 empty] | 578.7
COM | UNIDO | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 177 | A | O | I | CFC | 19.4 | 19.4 |  |  | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 |  | 66224 | 0 | 66224 | 65675 | 99.17% | 549 | 0 | 1 | 4967 | 0 | 4926 | 41 | 0 | Financial completion in Dec 2008. | [13 empty] | 2006 | INV | N/A | N/A |  |  | N/A | N/A | N/A
FIN | UNIDO | Preparation of a phase-out plan in the solvent sector | Individual | ASP | IRA | SOL | 48 | PRP | 178 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-07-01 | 2007-04-01 |  | 2006-12-01 | 2007-05-01 | 15000 | -512 | 14488 | 14488 | 100% | 0 | 0 |  | 1125 | -38 | 1087 | 0 | 0 | FIN | [13 empty] | 2006 | NON-INV
COM | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | IRA | SEV | 50 | INS | 179 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-07-01 |  | 86755 | 0 | 86755 | 86690 | 99.93% | 65 | 0 | 52 | 6507 | 0 | 6502.1247 | 4.8753 | 0 | Completed in 2008. Effective monitoring of NPP to ensure meeting targets of Agreement. Special efforts to monitor and coordinating implementation of solvent sector plan to return to compliance on CTC and TCA. Policy actions and public awareness activities undertaken | [13 empty] | 2006 | Non-Investment
ONG | UNIDO | Terminal solvent sector umbrella project | Individual | ASP | IRA | SOL | 50 | INV | 180 | A | O | I | CTC TCA | 52.7 | 52.7 |  |  | 2006-11-01 | 2007-11-01 | 2008-02-01 | 2009-12-01 |  |  | 856478 | 0 | 856478 | 417893 | 48.79% | 438585 | 318065 | 340000 | 64236 | 0 | 31342 | 32894 | 23855 | The CTC/TCA phase out has been achieved at the 6 Iranian companies. All the equipment has been procured in 2007-2008 and installed. Technical monitoring activities like two solvent training workshops and publication of solvent leaflets are planned to be conducted in 2009. The project completion date is December 2009. | Under the licensing system, the NOU reduced the quota for the import of CTC to zero as from 1st January 2008 to remain in compliance with its commitments to the country's "Action Plan" for the control of import and consumption of CTC and TCA. Eventually, according to import data released by the Iranian Customs Administration for 2008, no CTC was imported into the country during this year. | [12 empty] | 2006 | INV
ONG | Germany | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | INV | 181 | A | O | I | CFC | 250.3 | 250.3 | 0 |  | 2007-03-01 | 2007-04-01 | 2008-03-01 | 2009-04-01 |  |  | 920868 | 0 | 920868 | 720868 | 78.28% | 200000 | 0 | 200000 | 101295 | 0 | 79295.1042 | 21999.8958 | 0 | 4 tenders were contracted and production started. 2 machines were ready for delivery by end of 2008. The installation of all 4 machines is planned in 2009. | [15 empty] | 578.7
COM | UNIDO | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | TRA | 182 | A | O | I |  | 0 | 66.6 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-04-01 |  | 36179 | 0 | 36179 | 34285 | 94.76% | 1894 | 173 | 100 | 2713 | 0 | 2571 | 142 | 13 | Project completed in Apr 2008. | [13 empty] | 2007 | INV | N/A | N/A |  |  | N/A | N/A | N/A
ONG | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | ASP | IRA | ARS | 52 | INV | 183 | A | O | I | CFC | 96.4 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2010-09-30 | 2010-12-01 |  |  | 3529508 | -232750 | 3296758 | 8061 | 0.2445% | 3288697 | 1554241 | 1500000 | 264713 | -17456 | 605 | 246652 | 116568 | In 2008 UNIDO has procured filling equipment for the Iranian company Sina Darou. The selection of the technology provider has been completed in November 2008. The pilot batches of the first MDI are being planned to achieve by Dec 2009. The project completion date is December 2010. | [13 empty] | 2007 | INV
ONG | UNEP | National transition strategy for the phase-out of CFC propellants in MDIs | Individual | ASP | IRA | ARS | 52 | TAS | 184 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-03-01 | 2010-09-30 | 2010-09-30 |  |  | 70000 | 0 | 70000 | 63000 | 90% | 7000 | 0 | 7000 | 9100 | 0 | 8190 | 910 | 0 | The MOU content agreed by the country in January 2008. The fomat for UNEP changed to SSFA. SSFA was agreed to with the country and has been signed. Two National CFC MDI phaseout awareness workshops proposed to be held - one was held in March 2009. The second one is proposed to be held in the 3rd or 4th quarter of 2009. Information on regulations implementation including CFC consumption controls for MDI manufacturing shared with the country during the year 2008 and consultations on this were held in March 2009. | [13 empty] | 2007 | Non Investment
COM | UNDP | Extension of the institutional strengthening project (phase VI, second year) | Individual | ASP | IRA | SEV | 53 | INS | 185 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 |  | 86756 | 0 | 86756 | 60101 | 69.28% | 26655 | 0 | 21324 | 6507 | 0 | 4507.7828 | 1999.2172 | 0 | Completed in 2008. Monitoring of NPP, policy actions, public information and awareness actions. Strengthening provincial level environment units for implementing MP-related regulations. Phase 7 approved at 56th ExCom. | [13 empty] | 2007 | Non-Investment
ONG | Germany | National CFC phase-out plan: 2008 annual implementation programme | Multi-Year | ASP | IRA | PHA | 54 | INV | 186 | A | O | I | CFC | 195.7 | 72.9 | 0 |  | 2008-04-01 | 2008-04-01 | 2009-03-01 | 2009-03-01 |  |  | 729846 | 0 | 729846 | 203056.68 | 27.82% | 526789.32 | 0 | 526789.32 | 80283 | 0 | 22336.2181 | 57946.7819 | 0 | 1 more foam company was selected, monitoring, awareness and training activities were continued.
ONG | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | IRA | SEV | 56 | INS | 187 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-01 | 2010-12-01 |  |  | 173511 | 0 | 173511 | 0 | 0% | 173511 | 0 | 34702.2 | 13013 | 0 | 0 | 13013 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 188 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 113750 | 0 | 113750 | 0 | 0% | 113750 | 0 | 113750 | 8531 | 0 | 0 | 8531 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IRA | PHA | 56 | PRP | 189 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project. Consultant for preparation of UNEP component engaged | [13 empty] | 2008
ONG | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 190 | A | O | I | HCFC | 0 |  | 0 |  | 2008-11-01 |  | 2009-11-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | The stakeholder and first Interagency meeting was organized in Mar-2009. In 2008 only some research activities on subsector background were done. Together with the lead agency GTZ will review existing legislation and regulations and will make some comments and proposals to the NOU during 2009.
ONG | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | IRQ | SEV | 54 | INS | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2010-03-31 | 2009-06-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Comprehensive training programme for 35 national experts was conducted and relevant information was disseminated | [13 empty] | 2008
ONG | UNEP | Preparation of country programme and national phase-out plan | RMP | ASP | IRQ | PHA | 55 | PRP | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-06-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 60000 | 7800 | 0 | 0 | 7800 | 7800 | Country contract signed, CP/NPP national teams formulated and data gathered for the project document development | [13 empty] | 2008
ONG | UNIDO | Preparation of country programme and national phase-out plan. | Individual | ASP | IRQ | PHA | 55 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2009-12-01 |  |  | 40000 | 0 | 40000 | 6122 | 15.3% | 33878 | 10896 | 30000 | 3600 | 0 | 551 | 3049 | 981 | A training workshop for Iraqi national experts was organized in Beirut in September 2008. The data collection wil be completed in February 2009. The NPP project will be submitted to the 58th meeting of the Executive Committee. | [13 empty] | 2008 | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | IRQ | PHA | 55 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 60 | 0.2% | 29940 | 0 | 10000 | 2250 | 0 | 5 | 2245 | 0 | Indicative data on the consumption of the HCFCs was collected. Data will be reported to the Ozone Secretariat by the middle of February. Remaining funds for the HPMP preparation will be requested at the 57th meeting of the ExCom. | The initial workshop will be planned upon approval of the additional funding for the HPMP preparation. Work on ODS related legislation is ongoing by the Government of Iraq. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | AFR | IVC | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-03-01 | 1994-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1690 | 0 | 1690 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening (establishment of the Ozone Secretariat) | Individual | AFR | IVC | SEV | 13 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-01-01 | 1997-07-01 |  | 1998-10-01 | 1999-07-01 | 122810 | -300 | 122510 | 122510 | 100% | 0 | 0 | 0 | 15965.3 | -39 | 15926.3 | 0 | 0 | Project financially completed. | $ 300 plus $ 39 PSC returned ExCom 31 | [12 empty] | 1996 | Non Investment
FIN | UNEP | Training for refrigeration and air conditioning technicians | Individual | AFR | IVC | REF | 13 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-04 | 1995-07-01 |  | 1997-03-01 | 1999-04-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
CLO | UNIDO | Project formulation for the ODS phase-out in the refrigeration sector | Individual | AFR | IVC | REF | 16 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  |  | 1999-11-01 | 15000 | -84 | 14916 | 14916 | 100% | 0 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | CLO
FIN | UNIDO | ODS phase-out of a foam producing plant (Fabrique Ivoirienne de mousse et amemblement) and 2 aerosol fillers (Sicobel and Gandoor) | Individual | AFR | IVC | SEV | 17 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-02-01 | 1995-09-01 |  | 1996-10-01 | 1998-08-01 | 10000 | -388 | 9612 | 9612 | 100% | 0 | 0 |  | 1300 | -52 | 1248 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at F.I.M.A. flexible polyurethane foam plant | Individual | AFR | IVC | FOA | 19 | INV | 6 | A | O | I | CFC | 53.1 | 53.1 |  |  | 1996-05-01 | 1997-09-01 | 1997-07-01 |  | 1997-12-01 | 2001-03-01 | 85087 | -246 | 84841 | 84841 | 100% | 0 | 0 |  | 11061 | -49 | 11012 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Parfumerie Gandour D.A.F. | Individual | AFR | IVC | ARS | 20 | INV | 7 | A | O | I | CFC | 66 | 66 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-10-01 | 106061 | 0 | 106061 | 106061 | 100% | 0 | 0 |  | 13788 | 0 | 13788 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Sicobel | Individual | AFR | IVC | ARS | 20 | INV | 8 | A | O | I | CFC | 20.8 | 20.8 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-09-01 | 59171 | -453 | 58718 | 58718 | 100% | 0 | 0 |  | 7692 | -71 | 7621 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | France | Refrigeration management plan preparation |  | AFR | IVC | REF | 21 | PRP | 9 | A | O | I |  | 0 |  | 0 |  | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1998-03-01 | 1998-03-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
CLO | France | Implementation of the RMP | RMP | AFR | IVC | REF | 24 | TAS | 10 | A | O | I | CFC | 24.8 |  | 0 |  | 1998-03-01 | 1999-10-16 | 2000-04-01 |  |  | 2009-04-01 | 227650 | 0 | 227650 | 31436.2872 | 13.81% | 196213.7128 |  | 0 | 0 | 0 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
FIN | UNIDO | Preparation of an investment project in the domestic refrigeration (hydrocarbon) sector for Serti | Individual | AFR | IVC | REF | 24 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-10-01 | 2000-12-01 | 20000 | -10918 | 9082 | 9082 | 100% | 0 | 0 |  | 2600 | -1421 | 1179 | 0 | 0 | FIN |  |  |  | 1999-06-01
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | IVC | SEV | 26 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-08-10 | 2000-12-01 |  | 2004-04-01 | 2004-12-01 | 81800 | 0 | 81800 | 81800 | 100% | 0 | 0 | 0 | 10634 | 0 | 10634 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
CLO | UNIDO | Preparation of a project for stored commodities (cocoa beans) | Individual | AFR | IVC | FUM | 27 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | France | Documentary on traffic in second-hand refrigerators |  | AFR | IVC | REF | 27 | TAS | 14 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-04-01 | 2000-06-01 |  | 1999-07-01 | 1999-07-01 | 12000 | -2381 | 9619 | 9619 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Project preparation for projects in commercial refrigeration production facilities |  | AFR | IVC | REF | 37 | PRP | 15 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 1999-12-16 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 15000 | -1636 | 13364 | 13364 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. A study on a replacement programme for centrifugal chillers was completed in 2002. It was followed by a proposal on the phase out of CFC emissions in centrifugal chillers through energy related activities. Balance returned at the 57th ExCom.
CLO | France | Implementation of the refrigerant management plan: monitoring the activities of the RMP and set up of an import/export licensing system | RMP | AFR | IVC | REF | 37 | TAS | 16 | A | O | I | CFC | 188.7 |  | 0 |  | 2002-07-01 |  | 2004-08-01 |  |  | 2009-04-01 | 49500 | -49500 | 0 | 0 |  | 0 |  | 0 | 4950 | -4950 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
TRF | France | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 37 | INV | 17 | A | O | I | CFC | 0 |  | 0 |  | 2002-07-01 |  | 2006-08-01 |  |  | 2009-04-01 | 1000000 | -1000000 | 0 | 0 |  | 0 |  | 0 | 100000 | -100000 | 0 | 0 |  | Project transferred to UNIDO per decision 57/xx(f).
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector | Individual | AFR | IVC | FUM | 39 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-11-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | -198 | 9802 | 9802 | 100% | 0 | 0 |  | 750 | -16 | 734 | 0 | 0 | FIN | [13 empty] | 2003
COM | UNIDO | Phase-out the use of methyl bromide commodities and storage fumigation | Individual | AFR | IVC | FUM | 42 | INV | 19 | A | O | I | MBR | 8.5 | 8.5 |  |  | 2004-04-01 | 2004-04-01 | 2006-10-01 |  | 2008-12-01 |  | 222210 | 0 | 222210 | 188699 | 84.92% | 33511 | 46 | 33477 | 19999 | 0 | 16983 | 3016 | 4 | Project completed in Dec 2008. | [13 empty] | 2004 | INV
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | IVC | SEV | 43 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-09-01 | 2005-07-01 |  | 2005-11-01 | 2007-08-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | AFR | IVC | ARS | 44 | PRP | 22 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -1832 | 13168 | 13168 | 100% | 0 | 0 |  | 1125 | -137 | 988 | 0 | 0 | FIN | [13 empty] | 2004
ONG | UNIDO | Phase-out of CFC-12 in the manufacture of cosmetics aerosols (deodorants) by conversion to hydrocarbon aerosol propellant (HAP) at COPACI, Abidjan (terminal aerosol sector project) | Individual | AFR | IVC | ARS | 46 | INV | 23 | A | O | I | CFC | 43.4 | 0 |  |  | 2005-07-01 | 2005-10-01 | 2007-09-01 |  |  |  | 110428 | 0 | 110428 | 1077 | 0.9753% | 109351 | 0 | 1 | 9939 | 0 | 97 | 9842 | 0 | The project will be cancelled. | [13 empty] | 2005 | INV
FIN | UNEP | Extension of the institutional strengthening project (phase III, year 2) | Individual | AFR | IVC | SEV | 48 | INS | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | IVC | PHA | 48 | PRP | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 15000 | 0 | 15000 | 14990.93 | 99.94% | 9.07 | 0 | 9.07 | 1950 | 0 | 1948.8209 | 1.1791 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
COM | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | IVC | PHA | 48 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2008-04-01 |  | 15000 | 0 | 15000 | 14985 | 99.9% | 15 | 0 | 1 | 1125 | 0 | 1124 | 1 | 0 | Project completed in Apr 2008. Financial completion in Dec 2008. | [13 empty] | 2006 | NON-INV
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | IVC | SEV | 53 | INS | 27 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-30 | 2009-11-30 |  |  | 106340 | 0 | 106340 | 101 | 0.09498% | 106239 | 0 | 106239 | 0 | 0 | 0 | 0 | 0 | MoU sent to the country in October 2008 and payment pending on required reports | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | TAS | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-31 | 2010-03-31 |  |  | 173000 | 0 | 173000 | 118047.76 | 68.24% | 54952.24 | 50000 | 54952.24 | 22490 | 0 | 15346.2088 | 7143.7912 | 6500 | Five workshops have been carried out and helped to train about 165 Customs officers and other enforcement officers | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | INV | 29 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-11-01 | 2010-03-31 | 2009-12-01 |  |  | 162000 | 0 | 162000 | 7580 | 4.679% | 154420 | 17 | 50000 | 12150 | 0 | 569 | 11581 | 1 | Project implementation activities have been coordinated with the NOU and UNEP. The scope of equipment has been identified and the bidding has started. | [13 empty] | 2008 | INV | 44.1 | 44.1 |  |  | Not yet confirmed | N/A | N/A
FIN | UNEP | Country programme preparation | Individual | LAC | JAM | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-06-26 | 1995-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | JAM | SEV | 14 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | JAM | REF | 18 | TAS | 3 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1997-05-01 | 2000-12-01 | 172465 | -13366 | 159099 | 159099 | 100% | 0 | 0 | 0 | 22420 | -1738 | 20682 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNEP | Institutional strengthening through creation of a National Ozone Unit | Individual | LAC | JAM | SEV | 20 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-05-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | [10 empty] | 1996 | Non Investment
FIN | UNDP | Project preparation in the aerosol, foam and refrigeration sectors | Individual | LAC | JAM | SEV | 21 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 30000 | -16175 | 13825 | 13825 | 100% | 0 | 0 | 0 | 3900 | -2103 | 1797 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at West Indies Synthetics Company, Ltd (Wisynco) | Individual | LAC | JAM | FOA | 22 | INV | 6 | A | O | I | CFC | 81.6 | 81.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 1998-12-01 | 2000-12-01 | 596000 | -3008 | 592992 | 592992 | 100% | 0 | 0 | 0 | 77480 | -391 | 77089 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | USA | MAC demonstration project |  | LAC | JAM | REF | 23 | DEM | 7 | A | O | I | CFC | 9.6 |  | 0 |  | 1997-11-01 | 1998-02-01 | 1998-12-01 |  | 1999-06-01 | 2000-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Equipment delivered and training conducted in March 99, with follow-up mission in June 1999. Final report will be submitted June 2000. |  | 1997
FIN | UNIDO | Preparation of a phase out project (tobacco fumigation) | Individual | LAC | JAM | FUM | 24 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-09-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | JAM | REF | 24 | PRP | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-02-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
CLO | UNIDO | Demonstration project - alternatives to the use of methyl bromide in structural and commodity fumigation | Individual | LAC | JAM | FUM | 26 | DEM | 10 | A | O | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  |  | 2001-07-01 | 102850 | -102850 | 0 | 0 |  | 0 | 0 |  | 13371 | -13371 | 0 | 0 | 0 | CLO
FIN | Canada | Implementation of the RMP: training of trainers in refrigeration and certification of technicians | RMP | LAC | JAM | REF | 27 | TRA | 11 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-10-01 |  | 2000-08-01 | 2001-03-02 | 50850 | 0 | 50850 | 50850 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Phase 1 (train-the trainer) completed 7-11 June 1999. Phase 2 completed in June 2000. Monitoring and evaluation completed August 2000. | PCR submitted to Secretariat | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: customs officers training programme | RMP | LAC | JAM | REF | 27 | TRA | 12 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-10-01 |  | 2001-11-01 | 2001-12-01 | 54240 | 0 | 54240 | 54240 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Legislation finalized in July 99. Phase 1 -train-the-trainer- completed June 2000, Phase 2 completed in Nov. 2000, Monitoring and evaluation completed in Nov. 2001. | PCR submitted to Secretariat. | 1999 |  |  |  | 2001-12-01 | [7 empty] | 1999 | Non-Inv.
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | JAM | SEV | 29 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-01-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | JAM | REF | 30 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2002-05-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | JAM | SEV | 35 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-08-01 | 2004-10-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | Canada | Terminal phase-out management plan for CFCs: training and recovery and recycling | One-off Phase-out | LAC | JAM | PHA | 37 | TAS | 16 | A | O | I | CFC | 57.5 | 57.5 | 0 |  | 2002-07-01 | 2002-09-01 | 2006-01-01 |  | 2006-03-06 | 2006-03-06 | 240000 | 0 | 240000 | 240000 | 100% | 0 |  | 0 | 31200 | 0 | 31200 | 0 |  | All activities completed by end of 2005. Final monitoring reports received in March 2006. Jamaica provided comprehensive report on R&R activities. |  | 2002 | [11 empty] | 2002 | Non-Inv.
COM | UNDP | Terminal phase-out management plan for CFCs: retrofitting/replacement programme | Individual | LAC | JAM | PHA | 37 | TAS | 17 | N | O | I | CFC | 2 | 2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2006-01-01 |  | 2007-12-01 |  | 140000 | 0 | 140000 | 135511 | 96.79% | 4489 | 0 | 3591.2 | 18200 | 0 | 17616.43 | 583.57 | 0 | Completed in 2007. | [13 empty] | 2002 | Non-Investment
FIN | UNDP | Formulation of the solvent sectoral phase out plan | Individual | LAC | JAM | SOL | 39 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2003 | Investment
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | JAM | SEV | 40 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-01-01 | 2007-01-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNDP | Technical assistance umbrella project to phase out ODS solvent use | Individual | LAC | JAM | SOL | 42 | TAS | 20 | N | O | I | TCA | 0.8 | 0.8 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2006-12-01 |  | 25000 | 0 | 25000 | 21861 | 87.44% | 3139 | 0 | 2511.2 | 2250 | 0 | 1967.49 | 282.51 | 0 | Completed in 2006. | [13 empty] | 2004 | Non-Investment
FIN | Canada | Project preparation for the phase-out of methyl bromide |  | LAC | JAM | FUM | 43 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2005-09-01 | 2005-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 1125 | 0 | 1125 | 0 |  | Project proposal completed in September 2005, submitted and approved at ExCom 47. |  | 2004 | [11 empty] | 2004 | Non-Inv.
ONG | Canada | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | JAM | FUM | 47 | TAS | 22 | A | O | I | MBR | 1.2 |  | 0 |  | 2005-11-01 | 2006-09-06 | 2007-12-01 | 2009-06-01 |  |  | 55530 | 0 | 55530 | 32417 | 58.38% | 23113 |  | 18684 | 7219 | 0 | 6643 | 576 |  | Training workshop on alternative (Eco2Fume) and IPM with international trainer conducted in October 2006 for fumigators in Jamaica. From 2007 to end of 2008, group of trainers completed field training exercies (delays were previously reported and explained). These trainers will conduct Phase 2 training from April -May 2009. Note that it is expected that the project will be completed with savings of about $4,400. |  | 2005 | [10 empty] | 2009-04-01 | 2005 | Investment
COM | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | JAM | SEV | 47 | INS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2008-02-01 |  | 2008-06-01 |  | 60000 | 0 | 60000 | 60000.4 | 100% | -0.4 | 0 | -0.4 | 0 | 0 | 0 | 0 | 0 | Project completed in June 2008. Country submitted progress reports accordingly. During this period, major achievements were done through several outreach activities, reaching the private sector and general public. In addition, two projects were managed by the NOO: the Methyl Bromide Phase out project, implemented by Environment Canada and the TPMP, carried out by UNDP. The NOO continues to manage zero importation of Annex A Group 1 CFCs through the enforcement of the ODS Licensing System. In accordance with national laws, no permits are issued for the importation of this group of substances. The NOO continued to monitor that legislative control is sustained. All payments for this project have been processed, terminal reports and renewal request were received during May 2008. The renewal was approved two months later. | [13 empty] | 2005 | Non Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | JAM | PHA | 55 | PRP | 24 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Local and international consultants have been identified. The inception workshop is expected to take place in early 2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | JAM | SEV | 55 | INS | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2010-11-30 | 2010-11-30 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | Agreement for project implementation has been recently signed and first fund disbursement already processed. The country is currently producing A7 data report for 2008 and is updated with earlier reports. | [13 empty] | 2008
FIN | UNDP | Technical assistance and pre-feasibility study in aerosol sector | Individual | ASP | JOR | ARS | 04 | TAS | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 | 0 | 3770 | 0 | 3770 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | JOR | SEV | 04 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 24464 | -21052 | 3412 | 3412 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | JOR | SEV | 06 | CPG | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 70000 | -17005 | 52995 | 52995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Feasibility study on deodorization of local gas as a CFC substitute in cosmetics | Individual | ASP | JOR | ARS | 06 | TAS | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
TRF | IBRD | Reduction of CFC-11 in rigid insulation foams in domestic and commercial refrigerators | Individual | ASP | JOR | FOA | 07 | INV | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transferred project to UNIDO. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  | 1994-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC use in flexible foam at International Foam Industries Co. Ltd. | Individual | ASP | JOR | FOA | 07 | INV | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Company moved to the Sudan. |  |  | 1994-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technology transfer and engineering support | Individual | ASP | JOR | FOA | 07 | TAS | 7 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1995-01-01 | 1994-06-01 |  | 1996-06-01 | 1998-05-01 | 73000 | 0 | 73000 | 73000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed for Phase-1 ODS projects. It is part of a line-of-grant approval. The project was carried out as part of IS project. To avoid double counting, disbursement was claimed under the IS project approved at the 7th Meeting. |  |  | 1994-06-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in flexible foam at Kolaghassi Foam and Mattress Factory Co. | Individual | ASP | JOR | FOA | 07 | INV | 8 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-12-01 | 1998-05-01 | 172800 | -3904.84 | 168895.16 | 168895.16 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in air conditioning, commercial and domestic refrigeration (1992) |  | ASP | JOR | REF | 07 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-06-30 | 1996-06-01 |  | 1992-12-01 | 1992-12-01 | 500000 | -445139 | 54861 | 54861 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Recovery and recycling of CFC-12 in refrigeration equipment and maintenance procedures and recycling in halon systems | Individual | ASP | JOR | REF | 07 | DEM | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. UNIDO took over. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Policy and monitoring measures | Individual | ASP | JOR | SEV | 07 | INS | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1995-12-01 |  | 1997-06-01 | 1997-06-01 | 100000 | 70000 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PIU fully operational. Total funding of $170,000 was disbursed. |  |  | 1997-06-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | LPG purification at Jordan Refinery Company | Individual | ASP | JOR | ARS | 07 | INV | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1995-06-01 |  | 1998-01-01 | 1998-05-01 | 805000 | 0 | 805000 | 805000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in aerosol at Household and Toiletries | Individual | ASP | JOR | ARS | 07 | INV | 13 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1995-06-01 |  | 1998-04-01 | 1998-05-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in aerosol at Haddad and Sons Inc. | Individual | ASP | JOR | ARS | 07 | INV | 14 | N | O | I | CFC | 85 | 85 | 0 | 0 | 1992-06-01 | 1995-08-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 214200 | 0 | 214200 | 214200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | JOR | SEV | 09 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123200 | -38647 | 84553 | 84553 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment project for phase out of ODS in selected industries in the refrigeration and air-conditioning sector | Individual | ASP | JOR | REF | 10 | PRP | 16 | A | O | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1993-10-01 |  | 1994-12-01 | 1998-08-01 | 90000 | -14930 | 75070 | 75070 | 100% | 0 | 0 |  | 11700 | -1956 | 9744 | 0 | 0 | FIN
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | JOR | SEV | 12 | PRP | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 72900 | 6579 | 79479 | 79479 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | ODS phase out at National Refrigeration Co. (NRC) | Individual | ASP | JOR | REF | 13 | INV | 18 | A | O | I | CFC | 14.3 | 19.3 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-07-01 | 813887 | -29 | 813858 | 813858 | 100% | 0 | 0 |  | 105805 | -171 | 105634 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Household Appliance Manufacturing Co. (HAMCO) | Individual | ASP | JOR | REF | 13 | INV | 19 | A | O | I | CFC | 21.2 | 21.2 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 775602 | 0 | 775602 | 775602 | 100% | 0 | 0 |  | 100828 | -19 | 100809 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Middle East Electrical Industries Co. Ltd. | Individual | ASP | JOR | REF | 13 | INV | 20 | A | O | I | CFC | 16.6 | 23 |  |  | 1994-07-01 | 1994-12-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 883153 | -51 | 883102 | 883102 | 100% | 0 | 0 |  | 114810 | -189 | 114621 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for investment projects in commercial refrigeration, air-conditioning, foam and halon sectors | Individual | ASP | JOR | SEV | 15 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 50000 | -827 | 49173 | 49173 | 100% | 0 | 0 |  | 6500 | -118 | 6382 | 0 | 0 | FIN |  |  | 1997-07-01 | 1999-02-01
FIN | IBRD | Umbrella project for conversion to CFC-free technology at three flexible polyurethane foam factories at Arab Foam, Jordan Plastics, National Foam | Individual | ASP | JOR | FOA | 15 | INV | 22 | N | O | I | CFC | 114 | 114 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-09-01 |  | 2002-12-01 | 2003-12-01 | 368500 | 0 | 368500 | 368500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-10-01 | 1999-04-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | JOR | SEV | 16 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 64680 | 0 | 64680 | 64680 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at Five Star Polyurethane Foam Factory | Individual | ASP | JOR | FOA | 17 | INV | 24 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-02-01 | 1996-04-01 |  | 1998-03-01 | 1998-05-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | JOR | SEV | 18 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project preparation is completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Industrial Petrochemical Co. Ltd. (JIPCO) | Individual | ASP | JOR | ARS | 20 | INV | 26 | N | O | I | CFC | 98 | 98 | 0 | 0 | 1996-10-01 | 2002-12-01 | 1997-10-01 |  | 2003-10-01 | 2003-12-01 | 102855 | 0 | 102855 | 102855 | 100% | 0 | 0 |  | 13371.15 | 0 | 13371.15 | 0 | 0 | Project completed. |  |  |  | 2000-12-01 |  | 2002-03-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Antiseptics and Detergents Ind. Co. Ltd. (JADICO) | Individual | ASP | JOR | ARS | 20 | INV | 27 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1996-10-01 | 1999-03-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 65720 | 0 | 65720 | 65720 | 100% | 0 | 0 |  | 8543.6 | 0 | 8543.6 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Chemical Products Co. Ltd. (JCPCO) | Individual | ASP | JOR | ARS | 20 | INV | 28 | N | O | I | CFC | 61 | 61 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 203328 | 0 | 203328 | 203328 | 100% | 0 | 0 |  | 26432.64 | 0 | 26432.64 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC at Abdin Industrial Est.Co. | Individual | ASP | JOR | REF | 20 | INV | 29 | A | O | I | CFC | 10.4 | 21.5 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1997-12-01 | 2000-07-01 | 116928 | -636 | 116292 | 116292 | 100% | 0 | 0 |  | 15201 | -107 | 15094 | 0 | 0 | FIN
FIN | IBRD | Renewal of institutional strengthening | Individual | ASP | JOR | SEV | 22 | INS | 30 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1999-05-01 |  | 1999-05-01 | 1999-06-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | PIU fully operational. Funds were fully disbursed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polysterene at Al Hussam | Individual | ASP | JOR | FOA | 22 | INV | 31 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1999-12-01 | 1999-06-01 |  | 2001-02-01 | 2002-01-01 | 347855 | 0 | 347855 | 347855 | 100% | 0 | 0 |  | 45221.15 | 0 | 45221.15 | 0 | 0 | Project completed. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF (box foam) at Baybars | Individual | ASP | JOR | FOA | 22 | INV | 32 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1997-05-01 | 2001-12-01 | 1998-11-01 |  | 2002-12-01 | 2003-12-01 | 112500 | 0 | 112500 | 112500 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Project completed. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the original country programme |  | ASP | JOR | SEV | 22 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-31 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | 1999-06-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | ASP | JOR | SEV | 04 | PRP | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 25079 | 47196 | 72275 | 72275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFCs at the Ihsan & Tahseen Baalbaki Co. | Individual | ASP | JOR | REF | 23 | INV | 35 | A | O | I | CFC | 66.5 | 66.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-06-01 | 2001-12-01 | 545103 | -5327 | 539776 | 539776 | 100% | 0 | 0 |  | 70863 | -803 | 70060 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | JOR | FUM | 23 | PRP | 36 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-03-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (miscellaneous applications) at Fathei Abu Arja | Individual | ASP | JOR | FOA | 23 | INV | 37 | N | O | I | CFC | 105.4 | 105.4 | 0 | 0 | 1997-11-01 | 1999-12-01 | 2000-12-01 |  | 1999-12-01 | 2004-08-01 | 824869 | -7968 | 816901 | 816901 | 100% | 0 | 0 |  | 107233 | -1035.84 | 106197.13 | 0.03 | 0.03 | FAA project is technically and financially completed. There is no more ODS used in production. Baseline equipment modified so as to fit the new alternative of 141-b. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and halon recycling sectors |  | ASP | JOR | SEV | 24 | PRP | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | JOR | REF | 24 | PRP | 39 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-05-01 | 2000-12-01 | 30000 | -3410 | 26590 | 26590 | 100% | 0 | 0 |  | 3900 | -449 | 3451 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation and optimal use of soil fumigants in combination with an integrated pest management | Individual | ASP | JOR | FUM | 25 | DEM | 40 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-10-01 | 2000-08-01 |  | 2001-12-01 | 2003-08-01 | 385000 | -64217 | 320783 | 320783 | 100% | 0 | 0 |  | 50050 | -8414 | 41636 | 0 | 0 | FIN
FIN | Germany | Comprehensive approach to disseminate soil solarization technology for methyl bromide substitution | Individual | ASP | JOR | FUM | 26 | DEM | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-08-01 | 2002-01-01 | 232789 | 0 | 232789 | 232789 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completion report submitted | [13 empty] | 1998
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at six Jordanian companies | Individual | ASP | JOR | REF | 26 | INV | 42 | A | O | I | CFC | 25.1 | 25.1 |  |  | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 1999-12-01 | 2002-09-01 | 305764 | -4822 | 300942 | 300942 | 100% | 0 | 0 |  | 39749 | -689 | 39060 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in manufacture of commercial refrigeration equipment at Maurice al-Deek Co. | Individual | ASP | JOR | REF | 26 | INV | 43 | A | O | I | CFC | 25.7 | 25.7 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 336233 | -7042 | 329191 | 329191 | 100% | 0 | 0 |  | 43710 | -983 | 42727 | 0 | 0 | FIN
FIN | IBRD | Preparation of project in the aerosol and halon recycling sectors |  | ASP | JOR | SEV | 27 | PRP | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2000-01-01 |  | 1999-12-01 | 1999-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 |  | 650 | 0 | 650 | 0 | 0 | Completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 27 | PRP | 45 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 1999-12-01 | 2001-03-01 | 5000 | -693 | 4307 | 4307 | 100% | 0 | 0 |  | 650 | -91 | 559 | 0 | 0 | FIN
FIN | France | Technical assistance in air-conditioning |  | ASP | JOR | REF | 27 | TAS | 46 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-23 | 2000-04-01 |  | 2002-06-01 | 2002-06-01 | 42000 | -31575 | 10425 | 10424.9065 | 100% | 0.093509 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le rapport d'enquête a été achevé. D'un commun accord avec le Gouvernement jordanien, le projet sera transféré à la Banque Mondiale. | [5 empty] | 2001-11-01
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | ASP | JOR | REF | 28 | TRA | 47 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2001-08-01 |  | 2002-10-01 | 2004-03-01 | 70000 | -654 | 69346 | 69346 | 100% | 0 | 0 |  | 9100 | -99 | 9001 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | ASP | JOR | REF | 28 | TRA | 48 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-07-01 | 2003-06-01 | 38250 | -187 | 38063 | 38063 | 100% | 0 | 0 |  | 4973 | -33 | 4940 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: technical assistance and support to develop regulations for ODS to implement the Environment law of 1999 | RMP | ASP | JOR | REF | 28 | TAS | 49 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-03-01 | 2002-07-01 | 20000 | -2979 | 17021 | 17021 | 100% | 0 | 0 |  | 2600 | -391 | 2209 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | ASP | JOR | REF | 28 | TAS | 50 | A | O | I | CFC | 19.1 | 19.1 |  |  | 1999-07-01 | 2001-09-01 | 2001-08-01 |  | 2004-06-01 | 2005-09-01 | 311950 | -2650 | 309300 | 309300 | 100% | 0 | 0 |  | 40554 | -409 | 40145 | 0 | 0 | FIN | [5 empty] | 2002-12-01
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | ASP | JOR | SEV | 28 | INS | 51 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-08-01 | 1999-08-01 |  | 2001-07-01 | 2001-07-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | IS tranche completed and full funding dibursed. |  |  |  |  | 2000-12-01 | [9 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Third Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 52 | A | O | I | CFC | 16.8 | 17.74 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 243764 | -79664 | 164100 | 164100 | 100% | 0 | 0 |  | 31689 | -10390 | 21299 | 0 | 0 | FIN
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | JOR | HAL | 29 | TAS | 53 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2003-12-01 |  | 2007-12-01 | 2008-01-01 | 382250 | 0 | 382250 | 382250 | 100% | 0 | 0 | 0 | 49693 | 0 | 49693 | 0 | 0 | The halon recycling center has been completed and is operational. Consistent with ExCom policies, no newly produced halons will be allowed to be imported. The ban will be enforced thru the existing import lincensing system. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | Germany | Complete phase-out of the use of methyl bromide in Jordan | Individual | ASP | JOR | FUM | 29 | INV | 54 | A | O | I | MBR | 180 | 140.5 | 0 |  | 1999-11-01 | 2000-03-01 | 2014-12-01 | 2015-12-01 |  |  | 3063000 | 0 | 3063000 | 2197850 | 71.75% | 865150 | 0 | 170000 | 398190 | 0 | 285720.5 | 112469.5 | 0 | Jordan imported 45 metric tons in 2008, which is on target under Jordan's phase-down schedule.
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigertion equipment at Al-Arghawin & Marka commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 29 | INV | 55 | A | O | I | CFC | 27.4 | 27.4 |  |  | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 255203 | -9070 | 246133 | 246133 | 100% | 0 | 0 |  | 33176 | -1229 | 31947 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | ASP | JOR | ARS | 30 | PRP | 56 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-08-01 | 2001-04-01 |  | 2001-01-01 | 2002-05-01 | 20000 | -7413 | 12587 | 12587 | 100% | 0 | 0 |  | 2600 | -966 | 1634 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 30 | PRP | 57 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-04-01 | 2001-04-01 |  | 2002-12-01 | 2003-08-01 | 20000 | -1759 | 18241 | 18241 | 100% | 0 | 0 |  | 2600 | -232 | 2368 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (CFC-113) sector | Individual | ASP | JOR | SOL | 30 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2002-12-01 | 2003-06-01 | 25000 | -2455 | 22545 | 22545 | 100% | 0 | 0 |  | 3250 | -324 | 2926 | 0 | 0 | FIN
FIN | IBRD | Project preparation of projects in the aerosol sector |  | ASP | JOR | ARS | 30 | PRP | 59 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam general sector |  | ASP | JOR | FOA | 30 | PRP | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the halon non-recycling |  | ASP | JOR | HAL | 30 | PRP | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Second Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 62 | A | O | I | CFC | 25.8 | 25.8 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2000-08-01 | 2002-09-01 | 278950 | -2424 | 276526 | 276526 | 100% | 0 | 0 |  | 36264 | -373 | 35891 | 0 | 0 | FIN
FIN | IBRD | Substitution of CFC-12 for HAPs for perfumes and cosmetics at the aerosol plant Abu Shakra Factory | Individual | ASP | JOR | ARS | 31 | INV | 63 | N | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-08-01 | 2003-11-01 | 76676 | 0 | 76676 | 76676 | 100% | 0 | 0 |  | 9967.88 | 0 | 9967.88 | 0 | 0 | Enterprise has ceased using CFCs. Project conversion is completed. Remaining amount of the grant has been requested and payment process initiated. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | Individual | ASP | JOR | ARS | 31 | INV | 64 | N | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2005-02-01 | 2005-02-01 | 49539 | 0 | 49539 | 49539 | 100% | 0 | 0 |  | 6440.07 | 0 | 6440.07 | 0 | 0 | Project completed. | [7 empty] | 2003-06-01 | [5 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in production commercial refrigeration equipment at the medium size commercial refrigerator manufacturers (Jordan Catering Supplies, El-Shami, and Nedal Raja Al-Dwaik companies) in Jordan | Individual | ASP | JOR | REF | 31 | INV | 65 | A | O | I | CFC | 34.72 | 34.72 |  |  | 2000-07-01 | 2000-10-01 | 2003-08-01 |  | 2002-12-01 | 2004-09-01 | 469525 | -33258 | 436267 | 436267 | 100% | 0 | 0 |  | 61038 | -4413 | 56625 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at Fourth Group of small size Jordanian Commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 31 | INV | 66 | A | O | I | CFC | 23.1 | 23.07 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 270034 | -18831 | 251203 | 251203 | 100% | 0 | 0 |  | 35104 | -2499 | 32605 | 0 | 0 | FIN
FIN | IBRD | Country programme update | Individual | ASP | JOR | SEV | 31 | CPG | 67 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-09-01 | 2001-04-01 |  | 2002-09-01 | 2002-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | CP update submitted to the 38th ExCom. | [13 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Jordan Tunisian Chemical Company | Individual | ASP | JOR | ARS | 32 | INV | 68 | A | O | I | CFC | 12 | 12 |  |  | 2000-12-01 | 2001-10-01 | 2003-03-01 |  | 2002-12-01 | 2003-10-01 | 52800 | -23 | 52777 | 52777 | 100% | 0 | 0 |  | 6864 | -14 | 6850 | 0 | 0 | FIN
FIN | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | Individual | ASP | JOR | HAL | 32 | INV | 69 | N | O | I | HAL | 421.8 | 421.8 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-03-01 |  | 2008-01-01 | 2008-12-01 | 563000 | 0 | 563000 | 563000 | 100% | 0 | 0 | 0 | 71930 | 0 | 71930 | 0 | 0 | Project completed. PCR under preparation. | [7 empty] | 2003-06-01 | [5 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Project preparation in the commercial refrigeration (umbrella project) sector | Individual | ASP | JOR | REF | 33 | PRP | 70 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-04-01 |  | 2002-07-01 | 2003-09-01 | 20000 | -477 | 19523 | 19523 | 100% | 0 | 0 |  | 2600 | -66 | 2534 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in the production of commercial refrigeration equipment at the second medium-size commercial refrigerator manufacturers group (Abu Azmi, Hasouni Refrigeration and Majdi) | Individual | ASP | JOR | REF | 34 | INV | 71 | A | O | I | CFC | 26.4 | 26.4 |  |  | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-07-01 | 2005-09-01 | 342652 | -5429 | 337223 | 337223 | 100% | 0 | 0 |  | 44545 | -776 | 43769 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at 6th group of SMEs (Abu-Khalaf, Al-Taghwa, Farough Refrigeration, Dawudiah Workshop, Makka Refrigeration and Teck-Tack workshop) | Individual | ASP | JOR | REF | 34 | INV | 72 | A | O | I | CFC | 24.4 | 24.4 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 286523 | -5667 | 280856 | 280856 | 100% | 0 | 0 |  | 37248 | -795 | 36453 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | IBRD | Renewal of the institutional strengthening project |  | ASP | JOR | SEV | 34 | INS | 73 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 133333 | -20000 | 113333 | 113333 | 100% | 0 | 0 |  | 17333.29 | -2600 | 14733.29 | 0 | 0 | Final activities of this IS tranche completed. NOU supervised ongoing projects, organized Ozone Day and conducted public awareness. | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacturing commercial refrigeration equipment at 5th group of SMEs (Abdoulah Factory, Emad Addin Al- Sareegy, Ma-nna, Al-Mansour, Al-Ostath, Raed) | Individual | ASP | JOR | REF | 34 | INV | 74 | A | O | I | CFC | 26 | 26 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 244954 | -5781 | 239173 | 239173 | 100% | 0 | 0 |  | 31844 | -801 | 31043 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the King Hussein Workshop, Zarqa | Individual | ASP | JOR | SOL | 34 | INV | 75 | A | O | I | TCA | 6.4 | 6.4 |  |  | 2001-07-01 | 2002-12-01 | 2003-02-01 |  | 2003-12-01 | 2004-10-01 | 191316 | 0 | 191316 | 191316 | 100% | 0 | 0 |  | 24871 | 0 | 24871 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the Royal Jordanian Air Force | Individual | ASP | JOR | SOL | 37 | INV | 76 | A | O | I | TCA | 10.4 | 10.4 |  |  | 2002-07-01 | 2003-11-01 | 2004-08-01 |  | 2005-12-01 | 2007-01-01 | 342757 | -17 | 342740 | 342740 | 100% | 0 | 0 |  | 44558 | -2 | 44556 | 0 | 0 | FIN | [13 empty] | 2002 | INV
ONG | IBRD | National ODS phase out plan: aerosol, foam, MAC service and solvent sectors | One off phaseout | ASP | JOR | PHA | 38 | INV | 77 | N | O | I |  | 157.7 | 144.44 | 0 | 0 | 2002-11-01 | 2005-11-01 | 2009-11-01 | 2009-11-01 |  |  | 590000 | 0 | 590000 | 583000 | 98.81% | 7000 | 7000 | 7000 | 74900 | 0 | 74011.35 | 888.65 | 888.65 | All investment work has been undertaken, including that implemented by UNIDO. All other activities implemented except for training. Remaining phaseout is for the servicing and solvents sectors. | [13 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | National ODS phase out plan: commercial manufacturing and servicing and transport refrigeration | One-off Phase Out | ASP | JOR | PHA | 38 | INV | 78 | A | O | I | CFC | 41 | 41 |  |  | 2002-11-01 | 2003-06-01 | 2009-12-01 |  | 2006-12-01 | 2007-12-01 | 410000 | -2466 | 407534 | 407534 | 100% | 0 | 0 |  | 53300 | -321 | 52979 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2002 | INV
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | JOR | SEV | 40 | INS | 79 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-06-01 | 2005-07-01 |  | 2005-06-01 | 2005-06-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | Phase 6 of the IS project completed. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening project (phase VI) | Individual | ASP | JOR | SEV | 46 | INS | 80 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-31 | 147320 | 0 | 147320 | 147320 | 100% | 0 | 0 |  | 11049 | 0 | 11049 | 0 | 0 | IS Phase VI is completed. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of institutional strengthening project (phase VII) | Individual | ASP | JOR | SEV | 52 | INS | 81 | N | T | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-07-01 | 2009-07-01 |  |  | 147333 | 0 | 147333 | 104350.07 | 70.83% | 42982.93 | 42982.93 | 42982.93 | 11050 | 0 | 7826.27 | 3223.73 | 3223.73 | Activities continue as planned including control of illegal ODS trade, implementation and enforcement of the quota system, management of the licensing system for controlling ODS import and export. Other ongoing work includes, public awareness, monitoring of converted enterprises and follow-up on a labelling system for new products using ozone friendly substances. In 2008, the NOU focused on preparing the chiller replacement project and winding down the implementation of its NOPP. GoJ actively participated in 54-56th ExCom meetings and the OEWG/20th MOP. | [13 empty] | 2007 | Non-INV | 0 | 0 | 0 | 0
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | JOR | PHA | 55 | PRP | 82 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-12-01 |  |  | 150000 | 0 | 150000 | 5247 | 3.498% | 144753 | 0 | 60000 | 11250 | 0 | 394 | 10856 | 0 | Contracts were issued for the preparation of the survey. Stake holders workshop will be organized and the HPMP is expected to be submitted at the 59th ExCom. | Subcontract for the preparation of the HPMP includes: • Assistance for policy and legislation; • Survey of HCFCs use and analysis of data collectes; • Consultation with national stackeholders in the data collection and analysis. Regarding the policy aspect, the contractor is requested to assess and analyze the institutional framework, legislation, licensing and quota system regulating consumption of ozone depleting substances in Jordan with particular focus on HCFCs. The contractor is also requested to assess the current national policies on climate change, chemical management and energy policies, as well as the CFCs phase out activities and lessons learned from previous ODS phase-out activities. Expected outputs: assessment of the current status of legislation and recommendations on necessary institutional and regulatory improvements to facilitate a smooth compliance with the HCFCs phase out obligations. | [12 empty] | 2008 | NON-INV
ONG | UNIDO | Preparation of a demonstration project for the conversion of HCFC to non-HCFC technology in the manufacturing of mini-split units at Petra Engineering | Individual | ASP | JOR | REF | 56 | PRP | 83 | A | O | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2009-11-30 | 2009-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 25000 | 3000 | 0 | 0 | 3000 | 0 | First draft of the project document is prepared and the HPMP is expected to be submitted at the 58th ExCom. | [13 empty] | 2008 | NON-INV
FIN | UNEP | Formulation of national phase out strategy | Individual | ASP | KAM | SEV | 35 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2005-01-01 | 60000 | -433 | 59567 | 59566.82 | 100% | 0.18 | 0 | 0.18 | 7800 | -56 | 7743.6866 | 0.3134 | 0 | Project financially completed. | $ 433 plus $ 56 PSC returned to ExCom 49 | [12 empty] | 2001 | Non Investment
FIN | UNDP | Formulation of investment components of the RMP | Individual | ASP | KAM | REF | 36 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 15000 | -1844 | 13156 | 13156 | 100% | 0 | 0 | 0 | 1950 | -240 | 1710 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | KAM | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | KAM | REF | 39 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
COM | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant and awareness and incentive programme for the MAC sub-sector | RMP-Component | ASP | KAM | REF | 41 | TAS | 5 | N | O | I | CFC | 56.2 | 56.2 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 |  | 625000 | 0 | 625000 | 624733 | 99.96% | 267 | 0 | 213.6 | 46875 | 0 | 46854.975 | 20.025 | 0 | Completed in 2007. | [13 empty] | 2003 | Investment
FIN | UNEP | Implementation of the RMP: refrigeration and air-conditioning technicians training programme | Individual | ASP | KAM | REF | 41 | TRA | 6 | A | O | I | CFC | 11.7 | 11.7 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-03-01 | 130000 | -54 | 129946 | 129946 | 100% | 0 | 0 | 0 | 16900 | -7 | 16892.98 | 0.02 | 0 | Project financially completed. | $ 54 plus $ 7 PSC returned to ExCom 54 | [12 empty] | 2003 | Non Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | KAM | REF | 41 | TRA | 7 | A | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-03-01 | 85000 | -199 | 84801 | 84801 | 100% | 0 | 0 | 0 | 11050 | -26 | 11024.13 | -0.13 | 0 | Project financially completed. | $ 199 plus $ 26 returned to ExCom 51 | [12 empty] | 2003 | Non Investment
FIN | UNEP | Implementation of the RMP: implementation support and monitoring | Individual | ASP | KAM | REF | 41 | TAS | 8 | A | O | I | CFC | 4.5 | 4.5 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | ASP | KAM | SEV | 41 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-01-01 | 2006-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | KAM | FUM | 46 | TAS | 10 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 30000 | -2430 | 27570 | 27570 | 100% | 0 | 0 |  | 2700 | -219 | 2481 | 0 | 0 | Financial completion in Sep 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2005 | NON-INV
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | KAM | SEV | 47 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan | Individual | ASP | KAM | PHA | 50 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 |  | 15000 | 0 | 15000 | 5440 | 36.27% | 9560 | 0 | 9560 | 1125 | 0 | 408 | 717 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | KAM | PHA | 50 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-09-01 | 2008-01-01 | 15000 | -11 | 14989 | 14989.5 | 100% | -0.5 | 0 | -0.5 | 1950 | -1 | 1948.635 | 0.365 | 0 | Project financially completed. | $ 11 plus $ 1 returned to ExCom 56 | [12 empty] | 2006 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | KAM | SEV | 53 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 | 2009-11-01 |  |  | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Conducted Train-the-Trainer Workshop on Good Practices in Refrigeration on 5-9 May 2008 with 37 participants. 6 training workshops were planned and organized between May – December 2008 with the total 223 additional technicians.Conducted Training-the-Trainer Workshop on Controlling and Monitoring of ODS during 28-30 May 2008 with 29 participants. 6 training workshops were planned and organized between May – December 2008, with the similar model for 208 different customs and Camcontrol officers were trained. Organized meeting with steering committee on 28 April 2008 to review the possibility of any cross-border trade, international trend of illegal trade of ODS and discuss measures to reduce the illegal trade in Cambodia. NOU has conducted 4 awareness training workshops between August – December 2008, to educate the stakeholders to understand the effectiveness of the ozone layer on the human health and environment, and what have been done for the implementation of Montreal Protocol in Cambodia | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-year | ASP | KAM | PHA | 53 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Conducted Train-the-Trainer Workshop on Good Practices in Refrigeration on 5-9 May 2008 with 37 participants. 6 training workshops were planned and organized between May – December 2008 with the total 223 additional technicians. Conducted Training-the-Trainer Workshop on Controlling and Monitoring of ODS during 28-30 May 2008 with 29 participants. 6 training workshops were planned and organized between May – December 2008, with the similar model for 208 different customs and Camcontrol officers were trained. Organized meeting with steering committee on 28 April 2008 to review the possibility of any cross-border trade, international trend of illegal trade of ODS and discuss measures to reduce the illegal trade in Cambodia. NOU has conducted 4 awareness training workshops between August – December 2008, to educate the stakeholders to understand the effectiveness of the ozone layer on the human health and environment, and what have been done for the implementation of Montreal Protocol in Cambodia. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-Year | ASP | KAM | PHA | 53 | INV | 16 | N | O | I | CFC | 3.5 | 2 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 | 2010-01-01 |  |  | 195000 | 0 | 195000 | 51434 | 26.38% | 143566 | 0 | 28713.2 | 14625 | 0 | 3857.55 | 10767.45 | 0 | In 2008 RFP were completed for all equipment and put out for tender. It is expected that in the second quarter 2009 all equipment will be delivered. 974 cars were retrofitted and approximately 2.6 tons of CFC-12 were recovered, recycled and reused. However, due to inadequate awareness programmes, car owners are unaware of the new change in incentive cost for retrofitting. Card retrofitting progress is slow. As the sub-decree on ODS management has been put in place since 2005; the licensing system for ODS import export is in place and running smoothly. Establishment of a Refrigeration Association is in progress. | [13 empty] | 2007 | Investment | 13.5 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KAM | PHA | 55 | PRP | 17 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 1875 | 0 | 0 | 1875 | 0 | Experts to be recruited in Q1-2009. Project inception workshop planned by mid 2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KAM | PHA | 55 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-07-31 |  |  | 125000 | 0 | 125000 | 100000 | 80% | 25000 | 0 | 25000 | 16250 | 0 | 13000 | 3250 | 0 | The SSFA was signed on December 2008. | [13 empty] | 2008
FIN | UNDP | Country programme preparation | Individual | AFR | KEN | SEV | 06 | CPG | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-07-01 |  | 1994-06-01 | 1997-12-01 | 25000 | -2270 | 22730 | 22730 | 100% | 0 | 0 | 0 | 3250 | -295 | 2955 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | KEN | SEV | 09 | INS | 3 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-06-01 | 2005-09-01 | 175000 | -34 | 174966 | 174966 | 100% | 0 | 0 | 0 | 22750 | -4 | 22746 | 0 | 0 | Completed in 1998. Financially completed in 2005. | [13 empty] | 1993 | Non-Investment
TRF | UNDP | Demonstration and training unit for maintenance and recharge of refrigeration and air conditioning equipment | RMP-Component | AFR | KEN | REF | 04 | TRA | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1993-06-01 |  |  | 1993-06-01 | 115100 | -105248 | 9852 | 9852 | 100% | 0 | 0 | 0 | 14963 | -13682 | 1281 | 0 | 0 | Transferred in 1993. Financially completed in 1993. | [13 empty] | 1991 | Non-Investment
FIN | UNEP | Support to a national workshop on refrigeration | Individual | AFR | KEN | REF | 10 | TRA | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 2001-07-01 | 2001-07-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1993 | Non Investment
FIN | UNIDO | CFC-phase out project at Kenya Cold Storages Ltd. and subsidiary companies: Hall Equatorial, Premier Refrigeration and Engineering, Refrigeration Services | Individual | AFR | KEN | REF | 11 | INV | 6 | A | O | I | CFC | 40.8 | 40.8 |  |  | 1993-11-01 | 1996-12-01 | 1997-03-01 |  | 1998-12-01 | 2001-07-01 | 380875 | 123140 | 504015 | 504015 | 100% | 0 | 0 |  | 49514 | 15904 | 65418 | 0 | 0 | FIN
FIN | UNIDO | Identification and preparation of projects in the solvents and aerosols sectors | Individual | AFR | KEN | SEV | 17 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1995-11-01 |  | 1998-03-02 | 1999-08-01 | 15000 | -938 | 14062 | 14062 | 100% | 0 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFCs at Aesthetics Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 10 | A | O | I | CFC | 107 | 107 |  |  | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | -1 | 7149 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mirage Industries Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 11 | A | O | I | CFC | 51 | 51 |  |  | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 47250 | -371 | 46879 | 46879 | 100% | 0 | 0 |  | 6143 | -58 | 6085 | 0 | 0 | FIN
CLO | Australia | Replacement of methyl bromide with non ozone depleting substances in grain storage | Individual | AFR | KEN | FUM | 21 | DEM | 12 | A | O | D |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-07-01 |  |  | 2000-06-01 | 232834 | -91869 | 140965 | 140965 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | 1996
FIN | IBRD | Country programme preparation |  | AFR | KEN | SEV | 04 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 31498 | -22816 | 8682 | 8682 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of ODS cleaning processes from TCA to aqueous cleaning and cleaning in TCE at Kenyan Railways Central Workshop | Individual | AFR | KEN | SOL | 23 | INV | 14 | A | O | I | TCA | 6 | 6 |  |  | 1997-11-01 | 1998-08-01 | 1998-12-01 |  | 1999-12-01 | 2002-09-01 | 205524 | 0 | 205524 | 205524 | 100% | 0 | 0 |  | 26718 | 0 | 26718 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | AFR | KEN | FUM | 23 | PRP | 15 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | KEN | REF | 23 | PRP | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1998
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in cut-flowers at Kenya Agricultural Research Institute - KARI | Individual | AFR | KEN | FUM | 24 | DEM | 17 | A | O | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-10-01 | 2000-04-01 |  | 2003-03-01 | 2004-03-01 | 328900 | -2958 | 325942 | 325942 | 100% | 0 | 0 |  | 42757 | -452 | 42305 | 0 | 0 | FIN
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | KEN | SEV | 25 | INS | 18 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-12-01 | 2003-10-01 | 116667 | 0 | 116667 | 116667 | 100% | 0 | 0 | 0 | 15167 | 0 | 15167 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | KEN | REF | 26 | TAS | 19 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. TPMP approved in Dec 2004 | [13 empty] | 2000
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | AFR | KEN | FUM | 26 | DEM | 20 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-05-01 | 1999-12-01 |  | 2007-06-01 | 2007-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998 | [11 empty] | 1998 | Non-Inv.
CLO | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | AFR | KEN | FUM | 30 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-05-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | KEN | FUM | 30 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9392 | 15608 | 15608 | 100% | 0 | 0 | 0 | 3250 | -1221 | 2029.04 | -0.04 | 0 | Project financially completed. | $ 9,392 plus $ 1,221 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | Germany | Development of an investment project for the phase out of methyl bromide in vegetable production | Individual | AFR | KEN | FUM | 30 | PRP | 23 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-08-01 | 2000-12-01 |  | 2002-11-01 | 2003-09-01 | 13360 | 0 | 13360 | 13360 | 100% | 0 | 0 | 0 | 1737 | 0 | 1737 | 0 | 0 | Project initially blocked by 30th ExCom Decision on Kenya. Work completed November 2002. Investtment project approved at 39th ExCom. | [13 empty] | 1997
FIN | Germany | Recovery and recycling project | Individual | AFR | KEN | REF | 28 | TAS | 24 | A | O | I | CFC | 8.5 | 5 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2001-08-01 |  | 2004-05-01 | 2004-10-01 | 98725 | 0 | 98725 | 98725 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to the 44th Excom. | [13 empty] | 2001
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | AFR | KEN | SEV | 32 | INS | 25 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2005-09-01 | 116667 | -234 | 116433 | 116433 | 100% | 0 | 0 | 0 | 15167 | -30 | 15137 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Non-Investment
FIN | Germany | Project preparation for the solvent sector | Individual | AFR | KEN | SOL | 35 | PRP | 26 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-05-02 | 2003-07-01 |  | 2002-11-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed , investment project being implemented | [13 empty] | 1998
FIN | Germany | Project preparation for the RMP update | RMP Update | AFR | KEN | REF | 36 | TAS | 27 | A | O | I |  | 203.6 |  | 0 |  | 2002-03-01 | 2003-06-01 | 2003-03-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A TPMP developed through the preparation process was approved at the 44th ExCom | [13 empty] | 1998
FIN | UNDP | Project preparation in the soil fumigant sector (cut flowers) | Individual | AFR | KEN | FUM | 36 | PRP | 28 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2002 | Investment
FIN | UNEP | Policy and technical assistance | Individual | AFR | KEN | SEV | 37 | TAS | 29 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2005-12-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | AFR | KEN | SEV | 38 | INS | 30 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2006-12-01 | 151667 | -204 | 151463 | 151463 | 100% | 0 | 0 | 0 | 19717 | -27 | 19689.71 | 0.29 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2002 | Non-Investment
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flower component (first tranche) | Multi-Year | AFR | KEN | FUM | 38 | INV | 31 | A | O | I | MeBr | 10 | 10 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  |  | 2007-11-01 | 510660 | 0 | 510660 | 508208 | 99.52% | 2452 | 0 | 0 | 66173 | 0 | 65855.2618 | 317.7382 | 0 | Transferred in 2007. Balance to be returned in 2009. | [9 empty] | 2005-07-01 |  |  |  | 2002 | Investment | 63 | 63 |  |  | Yes | Yes | yes
COM | Germany | Conversion of TCA based cleaning process to non-ODS alternatives at the Kenya Power and Lighting Company | Individual | AFR | KEN | SOL | 39 | INV | 32 | A | O | I | TCA | 1.9 | 1 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2004-10-01 |  | 2007-12-01 |  | 85800 | 0 | 85800 | 82688 | 96.37% | 3112 | 0 | 0 | 11154 | 0 | 10749.44 | 404.56 | 0 | Project completed and PCR will be submitted in 2009. Remaining funds will be returned to the secretariat. | [13 empty] | 2002
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (first tranche) | Multi-Year | AFR | KEN | FUM | 39 | INV | 33 | A | O | I | MBR | 5 | 8 | 0 |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-04-01 | 2006-04-06 | 287247 | 0 | 287247 | 287247 | 100% | 0 | 0 | 0 | 37342 | 0 | 37342 | 0 | 0 | During 2004 the project staff was completed, a demonstration facility was set up in cooperation with the University of Nairobi, a very successful demonstration of substrates as alternative to MB was held at this facility. In sectors and areas where viable | 96 in 2004 | [12 empty] | 1997 |  | 96 | 41.06 |  |  | Yes
COM | UNDP | Project preparation for the formulation of solvent sectoral phase-out plan | Individual | AFR | KEN | SOL | 42 | PRP | 34 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2007-09-01 |  | 20000 | 0 | 20000 | 18150 | 90.75% | 1850 | 0 | 1850 | 1500 | 0 | 1361.25 | 138.75 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment
COM | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (second tranche) | Multi-Year | AFR | KEN | FUM | 42 | INV | 35 | A | O | I | MBR | 12 | 14.7 | 0 |  | 2004-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-12-06 |  | 172347 | 0 | 172347 | 172347 | 100% | 0 | 0 | 0 | 22405 | 0 | 22405 | 0 | 0 | Second tranche approved at 42nd ExCom. During 2005 technology transfer activities continued through agreements with farms for the adoption of alternatives such as substrates, IPM and chemicals such as metham sodium. Practical demonstrations and training w | 63 in 2006 | [14 empty] | 63 | 34.2 |  |  | Yes
FIN | France | Terminal CFCs phase-out management plan (first tranche) | Multi-Year | AFR | KEN | PHA | 44 | INV | 37 | A | O | I | CFC | 45.1 | 53 | 0 |  | 2004-12-01 | 2007-08-01 | 2005-12-01 |  | 2008-05-01 | 2008-07-01 | 215914 | 0 | 215914 | 215914 | 100% | 0 |  | 0 | 28069 | 0 | 28069 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed and tranche 2 requested and approved. | [10 empty] | 2007-06-01
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation (second tranche) | Multi-Year | AFR | KEN | FUM | 44 | INV | 38 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-11-01 | 306396 | -306396 | 0 | 0 |  | 0 | 0 | 0 | 22980 | -22980 | 0 | 0 | 0 | Transferred in 2007. | [13 empty] | 2004 | Investment | 53 | 53 |  |  | Yes | Yes | yes
TRF | UNDP | Extension of institutional strengthening project (phase V) | Individual | AFR | KEN | SEV | 44 | INS | 39 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  |  | 2007-07-01 | 151667 | 0 | 151667 | 150881 | 99.48% | 786 | 0 | 0 | 11375 | 0 | 11316.0501 | 58.9499 | 0 | Transferred in 2007. Balance to be returned in 2009. | [13 empty] | 2004 | Non-Investment
TRF | UNDP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 50 | INS | 39 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  |  | 2007-12-01 | 75833 | -75833 | 0 | 0 |  | 0 | 0 | 0 | 5688 | -5688 | 0 | 0 | 0 | Transferred in 2007. | [13 empty] | 2006 | Non-Investment
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flowers (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 40 | A | O | I | MeBr | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2009-12-01 |  |  | 2007-11-01 | 204263 | -204263 | 0 | 0 |  | 0 | 0 | 0 | 15320 | -15320 | 0 | 0 | 0 | Transferred in 2007. | [13 empty] | 2006 | Investment | 32 |  |  |  | Latest | Latest | Latest
ONG | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 41 | A | O | I | MBR | 12 | 9.7 | 0 |  | 2006-11-01 | 2007-01-01 | 2009-12-01 | 2009-12-09 |  |  | 114898 | 0 | 114898 | 102550 | 89.25% | 12348 | 0 | 12348 | 14937 | 0 | 13331.7321 | 1605.2679 | 0 | During 2008 further written agreements were made between the project and individual farms for the adoption of alternatives. Training workshops and practical demonstrations continued with extensionists, growers and students. The project is focussing on the small number of remaining MB users, preventing new uses, and carrying out activities to improve the sustainabilty of alternatives. | 29 in 2008 / 17.4 in 2007 | [14 empty] | 29 | 17.4
COM | UNEP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 52 | INS | 42 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2007-11-01 |  | 2008-11-01 |  | 75833 | 0 | 75833 | 75833 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008. and another phase approved during 55th Ex-com | [13 empty] | 2007 | Non Investment
ONG | UNIDO | Technology transfer leading to methyl bromide phase-out in soil fumigation | Individual | AFR | KEN | FUM | 53 | INV | 43 | A | O | I | MBR | 21 | 0 |  |  | 2007-11-01 | 2008-02-01 | 2010-11-01 | 2009-12-01 |  |  | 510659 | 0 | 510659 | 275861 | 54.02% | 234798 | 60527 | 150000 | 38300 | 0 | 20690 | 17610 | 4540 | During 2008 a UNIDO mission was undertaken to transfer the project team from UNDP to UNIDO and to discuss the plan of action. Most items were purchased and the training programme is underway. Progress report was submitted to the Executive Committee. | [13 empty] | 2007 | INV
ONG | France | Terminal CFCs phase-out management plan (second tranche) | Multi-Year | AFR | KEN | PHA | 54 | INV | 44 | A | O | I | CFC | 20 |  | 0 |  | 2008-04-01 | 2008-10-01 | 2009-03-01 | 2009-08-01 |  |  | 297000 | 0 | 297000 | 83041 | 27.96% | 213959 |  | 213959 | 38610 | 0 | 10795.33 | 27814.67 |  | 4 customs trainings have been conducted, recovery cylinders for the implementation of the incentive scheme have been purchased.
ONG | UNEP | Extension of the institutional strengthening project (2nd year of phase VI) | Individual | AFR | KEN | SEV | 55 | INS | 45 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-06-30 | 2009-06-30 |  |  | 75833 | 0 | 75833 | 37917 | 50% | 37916 | 37916 | 37916 | 0 | 0 | 0 | 0 | 0 | MOU signed with country and implementation of activities going well. NOU established a unit for licensing sytem, conducted training for customs officers and refrigerations technicnians. Produced awareness materials | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | ASP | KIR | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 2600 | -910 | 1690 | 0 | 0 | Project financially completed. | $ 7,000 plus $ 910 PSC returned ExCom 41 |  |  | 1999-10-01 | [9 empty] | 1995 | Non Investment
COM | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | KIR | REF | 36 | TAS | 2 | A | O | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 |  | 10000 | 0 | 10000 | 2983 | 29.83% | 7017 | 0 | 7016.7017 | 1300 | 0 | 0 | 1300 | 1300 | Environment Act passed August 2007 and the Customs Tariff Act amended so licensing system now in place. Customs training workshop complete. Project will be completed when the regional strategy as a whole is completed. |  | 2002
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | KIR | REF | 36 | TAS | 3 | A | O | I |  | 0.4 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 |  | 18000 | 0 | 18000 | 13456 | 74.76% | 4544 | 0 | 4544 | 2340 | 0 | 0 | 2340 | 2340 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | KIR | SEV | 36 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | KIR | SEV | 49 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 |  | 2007-03-31 |  | 2008-12-01 |  | 7666 | 0 | 7666 | 0 | 0% | 7666 | 0 | 7666 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. UNEP is discussing the closure of the Regional Strategy and has requested SPREP to disburse all remaining IS funding to the country. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | KIR | SEV | 53 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008. First disbursement will start after country receive final payment of previous IS phase from SPREP. | [13 empty] | 2007 | Non Investment
FIN | UNEP | Preparation of country programme | Individual | ASP | KUW | SEV | 30 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-06-01 |  | 2002-07-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Institutional strengthening and capacity building | Individual | ASP | KUW | SEV | 37 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-03-01 | 2005-08-01 |  | 2006-01-01 | 2008-12-01 | 121520 | 0 | 121520 | 121520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers in monitoring of ODS | Individual | ASP | KUW | REF | 37 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-01-01 |  | 2004-12-01 | 2006-12-01 | 53445 | 0 | 53445 | 53445 | 100% | 0 | 0 | 0 | 6947.85 | 0 | 6947.85 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme on good refrigerant management practices and hydrocarbon (HC) refrigerants safe handling | Individual | ASP | KUW | REF | 37 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-09-01 | 2004-08-01 | 2009-11-01 |  |  | 95325 | 0 | 95325 | 64485 | 67.65% | 30840 | 0 | 30840 | 12392.25 | 0 | 8383.05 | 4009.2 | 0 | All training activities completed since 2007, the only remaining activitiy is one workshop on HC safe handling is to be conducted in 2009 | [13 empty] | 2002 | Non Investment
COM | UNIDO | Implementation of the RMP: national recovery and recycling | RMP Update | ASP | KUW | REF | 37 | TAS | 5 | A | O | I | CFC | 64 | 64 |  |  | 2002-07-01 | 2003-07-01 | 2005-08-01 |  | 2006-12-01 |  | 448816 | 0 | 448816 | 446375 | 99.46% | 2441 | 0 | 1 | 22441 | 35905 | 58029 | 317 | 0 | Financial completion in Dec 2008. | [13 empty] | 2002 | INV
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | KUW | REF | 37 | TAS | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2005-12-01 | 2005-08-01 | 2009-12-01 |  |  | 27000 | 0 | 27000 | 17000.4 | 62.96% | 9999.6 | 10000 | 9999.6 | 3510 | 0 | 2210.052 | 1299.948 | 1300 | Activities in 2008 included evaluating outcomes of the completed training and monitoring operation of distributed R&R equipment. Final report and completion planned for 2009 | [13 empty] | 2002 | Non Investment
ONG | UNIDO | Preparation of a halon phase-out plan | Individual | ASP | KUW | HAL | 45 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2007-01-01 | 2006-04-01 | 2009-06-01 |  |  | 25000 | 0 | 25000 | 20760 | 83.04% | 4240 | 0 | 2000 | 1875 | 0 | 1557 | 318 | 0 | According to Para. 77 of ExCom Decision 53/12, the NOU was requested to identify the institution to host halon banking equipment. Up to date, no official nomination was received by UNIDO. | [13 empty] | 2005 | NON-INV
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | KUW | SEV | 47 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 105320 | 0 | 105320 | 105320 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNIDO | Preparation of a terminal phase-out management project | Individual | ASP | KUW | PHA | 48 | PRP | 9 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-07-01 | 2008-08-01 | 25000 | -2 | 24998 | 24998 | 100% | 0 | 0 |  | 1875 | 0 | 1875 | 0 | 0 | Financial completion in Aug 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2006 | NON-INV
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | ASP | KUW | PHA | 52 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 |  | 2008-11-01 | 2009-11-01 |  |  | 240000 | 0 | 240000 | 0 | 0% | 240000 | 0 | 240000 | 31200 | 0 | 0 | 31200 | 0 | Work-plan with country and UNIDO was set, procurement of training equipment is made, national task-forces and committee under establishment and delay is due to the change of the ODS Officer | [13 empty] | 2007 | Non Investment
ONG | UNIDO | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | ASP | KUW | PHA | 52 | INV | 11 | A | O | I | CFC | 15 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-11-01 | 2009-06-01 |  |  | 220000 | 0 | 220000 | 21923 | 9.965% | 198077 | 147841 | 40000 | 19800 | 0 | 1973 | 17827 | 13306 | Recovery and recycling equipment were procured. Material for training on MAC retrofits was developed. The scheme for the implementation of a MAC retrofit incentive programme was agreed upon. The project is expected to be completed by June 2009. | [13 empty] | 2007 | INV | 70 | 70 |  |  | Yes | N/A | N/A
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | KUW | SEV | 53 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 | 2009-11-01 |  |  | 105320 | 0 | 105320 | 23470 | 22.28% | 81850 | 63320 | 81850 | 0 | 0 | 0 | 0 | 0 | This is ongoing ISP Phase with Kuwait and first and second payments disbursed as per schedule, following submission of all reports as per SSFA. | [13 empty] | 2007 | Non Investment
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | KUW | PHA | 55 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 10000 | 5250 | 0 | 0 | 5250 | 0 | UNEP is in the process of recruiting national experts to collect the required data. The first stakeholder workshop will take place in March 2009. | Legislation related matters are part of the responsibility of UNEP. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KUW | PHA | 55 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 125000 | 0 | 125000 | 0 | 0% | 125000 | 0 | 125000 | 16250 | 0 | 0 | 16250 | 0 | Work-plan agreed with country and UNIDO, contractual arrangements and survey started in 2009 | [13 empty] | 2008
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | ASP | KYR | REF | 37 | TAS | 1 | A | O | I | CFC | 1.8 | 1.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-08-01 |  | 2006-12-01 | 2008-03-01 | 16500 | 0 | 16500 | 16499 | 99.99% | 1 | 0 | 0 | 2145 | 0 | 2144.87 | 0.13 | 0 | Completed in 2006. Financially completed in 2008. | [13 empty] | 2002 | Non-Investment
FIN | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | KYR | REF | 37 | TAS | 2 | A | O | I | CFC | 20.6 | 20.6 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-07-01 |  | 2007-12-01 | 2008-04-01 | 187242 | 0 | 187242 | 185783 | 99.22% | 1459 | 0 | 0 | 24341 | 0 | 24151.79 | 189.21 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2002 | Non-Investment
COM | UNEP | Implementation of the RMP: training for customs excise and personnel involved in the monitoring of ODS/equipment | Individual | EUR | KYR | REF | 37 | TRA | 3 | A | O | I | CFC | 8.3 | 8.3 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2005-06-01 |  | 74910 | 0 | 74910 | 66244 | 88.43% | 8666 | 0 | 8666 | 9738.3 | 0 | 8611.72 | 1126.58 | 0 | Project completed | [13 empty] | 2002 | Non Investment
FIN | UNDP | Implementation of the RMP: national programme for refrigerant recovery and recycling | RMP-Component | ASP | KYR | REF | 37 | TAS | 4 | A | O | I | CFC | 20.4 | 20.4 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2003-10-01 | 2007-03-01 | 185175 | -1006 | 184169 | 184168 | 100% | 1 | 0 | 0 | 24073 | -131 | 23941.62 | 0.38 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2002 | Investment
COM | UNEP | Establishment of the Ozone Unit | Individual | EUR | KYR | SEV | 37 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-10-01 | 2005-08-01 |  | 2004-12-01 |  | 133650 | 0 | 133650 | 129002 | 96.52% | 4648 | 0 | 4648 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | EUR | KYR | REF | 37 | TRA | 6 | A | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2003-08-01 |  | 2005-08-01 |  | 97900 | 0 | 97900 | 84982 | 86.8% | 12918 | 0 | 12918 | 12727 | 0 | 11047.66 | 1679.34 | 0 | Project completed | [13 empty] | 2002 | Non Investment
FIN | UNEP | Country programme | Individual | EUR | KYR | SEV | 37 | CPG | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2002-07-01 |  | 2002-07-01 | 2002-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNDP | Technical assistance project to install alternatives and phase-out methyl bromide | One-off-Phaseout | ASP | KYR | FUM | 41 | TAS | 8 | N | O | I | MeBr | 14.2 | 14.2 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2008-12-01 |  | 2007-12-01 |  | 300000 | 0 | 300000 | 299593 | 99.86% | 407 | 0 | 325.6 | 22500 | 0 | 22469.475 | 30.525 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | EUR | KYR | SEV | 44 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNDP | Project preparation of a terminal phase-out management plan | Individual | ASP | KYR | PHA | 47 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-04-01 |  | 30000 | 0 | 30000 | 29092 | 96.97% | 908 | 0 | 908 | 2250 | 0 | 2181.9 | 68.1 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment
COM | UNIDO | Halon phase-out programme | Individual | EUR | KYR | HAL | 48 | TAS | 12 | A | O | I | HAL | 2.4 | 2.4 |  |  | 2006-04-01 | 2006-12-01 | 2009-04-01 |  | 2008-12-01 |  | 50000 | 0 | 50000 | 36219 | 72.44% | 13781 | 3493 | 3400 | 4500 | 0 | 3260 | 1240 | 314 | Project completed in Dec 2008. | [13 empty] | 2006 | INV
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | EUR | KYR | SEV | 50 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 |  | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008 | [13 empty] | 2006 | Non Investment
COM | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | ASP | KYR | PHA | 50 | INV | 14 | N | O | I | CFC | 1 | 1 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2009-11-01 |  | 2008-12-01 |  | 194000 | 0 | 194000 | 168640 | 86.93% | 25360 | 0 | 20288 | 14550 | 0 | 12648 | 1902 | 0 | Completed in 2008. Equipment arrived and distributed. A series of workshops held. One end-user company applied for grants and approved. MDI component is in advanced stage. Second tranche approved at 55th ExCom. | [13 empty] | 2006 | Investment | 7 |  |  |  | Latest | Latest | Latest
COM | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | KYR | PHA | 50 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-07-01 |  | 142600 | 0 | 142600 | 119415.99 | 83.74% | 23184.01 | 0 | 23184.01 | 18538 | 0 | 15524.0787 | 3013.9213 | 0 | Project completed in July 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | KYR | SEV | 55 | INS | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-01-31 | 2009-01-31 |  |  | 115830 | 0 | 115830 | 46000 | 39.71% | 69830 | 69830 | 69830 | 0 | 0 | 0 | 0 | 0 | SSFA signed by both parties. NOU is implementing second tranche of TPMP accoridng to annual work plan. NOU actively participating in the ECA network activities. | [13 empty] | 2008
ONG | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | KYR | PHA | 55 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 65100 | 0 | 65100 | 0 | 0% | 65100 | 65100 | 65100 | 8463 | 0 | 0 | 8463 | 8463 | SSFA signed by both parties. Activities are being coordinated with UNDP and ongoing according to annual work plan. | [13 empty] | 2008
ONG | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-year | ASP | KYR | PHA | 55 | INV | 18 | N | O | I | CFC | 1 | 1 | 0 | 0 | 2008-07-01 |  | 2010-07-01 | 2010-07-01 |  |  | 63000 | 0 | 63000 | 0 | 0% | 63000 | 0 | 12600 | 4725 | 0 | 0 | 4725 | 0 | Project ongoing. NOU/UNDP planned finalization of MDI and end-user work in Q2-Q3-2009. | [13 empty] | 2008 | Investment
ONG | UNEP | TPMP verification report | Individual | EUR | KYR | PHA | 55 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 2600 | 0 | 0 | 2600 | 0 | Activities are planned for last quarter of 2009. This is linked to completion of currently ongoing second annual tranche of TPMP. | [13 empty] | 2008
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KYR | PHA | 55 | PRP | 20 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Prepared prodoc & TORs and held discussions on them. Prodoc signed. National experts to be recruited in Q1-2009. Project inception workshop planned in Q2-2009. | [13 empty] | 2008 | Investment
FIN | UNEP | Regional workshop for Latin America and the Caribbean | Individual | LAC | LAC | SEV | 4 | TRA | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-05-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in Latin America | Individual | LAC | LAC | FOA | 06 | TRA | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | 1312 | 53812 | 53812 | 100% | 0 | 0 | 0 | 6825 | 171 | 6996 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in Latin America | Individual | LAC | LAC | HAL | 06 | TRA | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1994-06-01 | 1997-12-01 | 60000 | -15158 | 44842 | 44842 | 100% | 0 | 0 | 0 | 7800 | -1971 | 5829 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Latin America | RMP-Component | LAC | LAC | REF | 06 | TRA | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1995-11-01 | 1994-02-01 |  | 1995-11-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Latin America | Individual | LAC | LAC | REF | 06 | TRA | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1992-09-01 | 1997-12-01 | 40000 | -16953 | 23047 | 23047 | 100% | 0 | 0 | 0 | 5200 | -2204 | 2996 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | USA | Follow-up to regional halon-1211 workshop |  | LAC | LAC | HAL | 08 | TRA | 6 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | UNEP | Support to regional network for OzonAction/ODS focal points | Individual | LAC | LAC | SEV | 9 | TAS | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-03-01 | 2000-12-01 | 130000 | -9000 | 121000 | 121000 | 100% | 0 | 0 | 0 | 16900 | -1170 | 15730 | 0 | 0 | Project financially completed. | $ 9,000 plus $ 1,170 PSC returned ExCom 31 | [12 empty] | 1999 | Non Investment
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1994) | Individual | LAC | LAC | SEV | 12 | TAS | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-26 | 1995-03-01 |  | 1995-03-01 | 2000-12-01 | 224000 | -14500 | 209500 | 209500 | 100% | 0 | 0 | 0 | 29120 | -1885 | 27235 | 0 | 0 | Project financially completed. | $ 14,500 plus $ 1,885 PSC returned ExCom 31 | [12 empty] | 1997 | Non Investment
FIN | USA | Project preparation for low consuming countries |  | LAC | LAC | REF | 13 | PRP | 9 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNEP | Regional workshop on non-CFC technologies for domestic refrigerator manufacturing industries | Individual | LAC | LAC | REF | 15 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-05-01 |  | 1995-05-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1995) | Individual | LAC | LAC | SEV | 16 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-05-01 | 1996-03-01 |  | 1995-08-01 | 2000-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on technology assessment in refrigeration | Individual | LAC | LAC | REF | 16 | TAS | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-01-01 | 1996-03-01 |  | 1999-05-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | 1999-05-01 | [9 empty] | 1995 | Non Investment
FIN | UNEP | Regional workshop on methyl bromide for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-24 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNDP | Methyl bromide data collection for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TAS | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 1998-12-01 | 57700 | 0 | 57700 | 57700 | 100% | 0 | 0 | 0 | 7501 | 0 | 7501 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Non-Investment
FIN | UNDP | Regional Latin America demonstration project in recovery of ODS in MACs: Phase I (Argentina, Colombia) | RMP-Component | LAC | LAC | REF | 18 | TAS | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1999-05-01 | 207000 | 0 | 207000 | 207000 | 100% | 0 | 0 | 0 | 26910 | 0 | 26910 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1995 | Non-Investment
FIN | USA | Project preparation in MAC and refrigerated transport in Central American and the Caribbean |  | LAC | LAC | REF | 19 | PRP | 16 | A | O | I |  | 0 |  | 0 |  | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1998-02-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Final report submitted in June 1998. |  | 1995 | 1997-05-01
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for Latin America and Caribbean | Individual | LAC | LAC | SEV | 19 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-04-01 | 1999-04-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 | 0 | 13650 | 0 | 13650 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Networking and Training in Latin American Region Network (including English-speaking Caribbean) | Individual | LAC | LAC | SEV | 19 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299000 | -57167 | 241833 | 241833 | 100% | 0 | 0 | 0 | 38870 | -7431.71 | 31438.29 | 0 | 0 | Project financially completed. | $ 57,167 plus $ 7,432 PSC returned ExCom 30 | [12 empty] | 1994 | Non Investment
FIN | UNEP | Latin American Region Network (1997) | Individual | LAC | LAC | SEV | 21 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 380000 | -38093 | 341907 | 341907 | 100% | 0 | 0 | 0 | 49400 | -4952.09 | 44447.91 | 0 | 0 | Project financially completed. | $ 38,093 plus $ 4,952 PSC returned ExCom 30 | [12 empty] | 1998 | Non Investment
FIN | UNEP | Latin America Region Networks for LAC South, LAC Central, and Caribbean (1998) | Individual | LAC | LAC | SEV | 23 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 399000 | -53324 | 345676 | 345676 | 100% | 0 | 0 | 0 | 51870 | -6932.12 | 44937.88 | 0 | 0 | Project financially completed. | $ 53,324 plus $ 6,932 PSC returned ExCom 30 | [12 empty] | 1994 | Non Investment
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for the Caribbean region | Individual | LAC | LAC | SEV | 23 | TRA | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-11-01 |  | 1998-06-01 | 1999-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) in Central America: El Salvador, Honduras, Nicaragua and Panama |  | LAC | LAC | REF | 24 | DEM | 27 | A | O | I |  | 0 |  | 0 |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-06-01 | 2000-07-01 | 569000 | 0 | 569000 | 569000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training and equipment were provided in El Salvador, Honduras, Nicaragua and Panama in April - May 1999. Final report will be submitted in June 2000.
FIN | Canada | Development of a regional halon bank management plan for the English-speaking Caribbean (Bahamas, Barbados, Grenada, Guyana, Jamaica, and Trinidad and Tobago) | Halon Banking | LAC | LAC | HAL | 26 | TAS | 28 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-10-01 | 2000-06-01 |  | 2005-12-01 | 2006-03-06 | 177410 | 0 | 177410 | 177410 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Establishment of halon clearing house in Trinidad and promotional brochure completed in 2005. All 6 countries finished their halon surveys. All project activities completed. Last payment to UNEP to reimburse University of West Indies for halon clearing |  | 1998 | [11 empty] | 1998 | Non-Inv.
FIN | UNEP | Latin America Region Network (South America, Central America and the Caribbean) | Individual | LAC | LAC | SEV | 26 | TAS | 29 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-12-01 | 2000-12-01 | 399000 | -55099 | 343901 | 343901 | 100% | 0 | 0 | 0 | 51870 | -7162.87 | 44707.13 | 0 | 0 | Project financially completed. | $ 55,099 plus $ 7,163 PSC returned ExCom 37 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Regional training workshop on policy development | Individual | LAC | LAC | FUM | 27 | TRA | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-03-01 |  | 2000-04-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
CLO | UNIDO | Preparation of a demonstration project for broccoli, cucurbits, tobacco, seed beds, grain fumigation in El Salvador, Honduras and Nicaragua | Individual | LAC | LAC | FUM | 27 | PRP | 31 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  |  | 2001-12-01 | 40000 | -29186 | 10814 | 10814 | 100% | 0 | 0 |  | 5200 | -3796 | 1404 | 0 | 0 | CLO
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | LAC | LAC | FUM | 27 | TRA | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-12-03 | 80000 | -4000 | 76000 | 76000 | 100% | 0 | 0 | 0 | 10400 | -520 | 9880 | 0 | 0 | Project financially completed. | $ 4,000 plus $ 520 PSC returned ExCom 43 | [12 empty] | 1999 | Non Investment
FIN | UNEP | Latin America and the Caribbean regional networks (South America, Central America, Caribbean) (2000) | Individual | LAC | LAC | SEV | 29 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 418950 | -30000 | 388950 | 388950 | 100% | 0 | 0 | 0 | 54463.5 | -3900 | 50563.5 | 0 | 0 | Project financially completed. | $ 30,000 plus 3,900 returned ExCom 46 | [12 empty] | 1999 | Non Investment
CLO | UNEP | Development of regional halon banking management plan for the Latin American region (Dominican Republic, El Salvador, Chile, Colombia and Peru) | Individual | LAC | LAC | HAL | 29 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2001-06-01 |  |  | 2002-07-01 | 174000 | -174000 | 0 | 0 |  | 0 | 0 | 0 | 22620 | -22620 | 0 | 0 | 0 | Project was cancelled by 37th ExCom. | $ 174,000 plus $ 22,620 PSC returned ExCom 38 | [12 empty] | 1997 | Non Investment
FIN | UNEP | South American, Central American and the Caribbean regional networks (2001) | Individual | LAC | LAC | SEV | 32 | TAS | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 429000 | -17257 | 411743 | 411743 | 100% | 0 | 0 | 0 | 55770 | -2243.41 | 53526.59 | 0 | 0 | Project financially completed. | $ 17,257 plus $ 2,243 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector in the Caribbean, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | LAC | REF | 47 | DEM | 36 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 | 2009-06-01 |  |  | 1000000 | 0 | 1000000 | 0 | 0% | 1000000 | 0 | 400000 | 75000 | 0 | 0 | 75000 | 0 | 1 expert mission to Jamaica (with other funds) to assess the developed financial scheme. Limited number of CFC based chillers found in the four countries. Discussions with countries will take place in 2009 to decide how to adjust project objectives. | [13 empty] | 2005 | Investment
FIN | Spain | Policy assistance to support the methyl bromide phase-out with special focus in Guatemala and Honduras | Individual | LAC | LAC | FUM | 47 | TAS | 37 | A | O | I | MBR | 0 |  | 0 |  | 2005-11-01 | 2006-02-01 | 2007-12-01 | 2007-07-01 |  | 2008-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 |  | 10400 |  | This Project was approved on ExCom 47th, December 2005. First contacts for money transfer were initiated on December 2005. During 2006 and 2007 all funds were disbursed. PCR is suposed to be ready in May 2008 and financial completion in June 2008.
ONG | Canada | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 38 | A | O | I |  | 0 |  | 0 |  | 2007-03-01 | 2008-09-08 | 2008-03-01 | 2009-12-01 |  |  | 50000 | 0 | 50000 | 20000 | 40% | 30000 |  | 30000 | 6500 | 0 | 2600 | 3900 |  | Delays were encountered in consolidating a work plan due to the large number of project stakeholders and negotating MOUs. In 2008, network meeting with custom officers focal points took place and study on illegal trade in the region was initiated. Draft study completed in early 2009 and is under review. See narrative progress report. |  | 2007 | [11 empty] | 2007 | Non-Inv.
ONG | UNEP | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 39 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-02-01 | 2008-03-01 | 2009-10-01 |  |  | 80000 | 0 | 80000 | 35127.68 | 43.91% | 44872.32 | 44872.77 | 44872.32 | 10400 | 0 | 4566.5984 | 5833.4016 | 5833.4601 | Second Steering committee Held in March of 2008. Contract Extablsihed with Env. Can. to allow UNEP to implement the conponents of Env. Canada, REgional consultant selected. REgional workshop held Dec. 2008 | [13 empty] | 2007 | Non Investment
ONG | Spain | Technical assistance to introduce chemical alternatives in countries which have rescheduled methyl bromide phase out plan (Argentina and Uruguay) | Individual | LAC | LAC | FUM | 54 | TAS | 40 | A | O | I | MBR | 0 |  | 0 |  | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 147400 | 0 | 147400 |  | 0% | 147400 |  |  | 19162 | 0 |  | 19162 |  | The project is going well, they are in the process of establish some trials with new chemicals in one of the countries (Uruguay) and they expect to do the same in Argentina in a few months.
FIN | UNEP | Country programme preparation | Individual | ASP | LAO | SEV | 27 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-07-01 |  | 2001-07-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit for implementing the phase-out of ODS under the Montreal Protocol | Individual | ASP | LAO | SEV | 34 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-08-01 | 2006-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
ONG | France | Implementation of the RMP: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II) | RMP | ASP | LAO | REF | 34 | TRA | 3 | N | O | I |  | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-04 | 2004-08-01 | 2009-06-01 |  |  | 78750 | 0 | 78750 | 56900 | 72.25% | 21850 |  | 21000 | 10237 | 0 | 7396.6387 | 2840.3613 |  | Lao has reported an error concerning the training of technicians in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). The amount of expenses made for these 2 lines were inserted under LAO/REF/34/TRA/03. It therefore looked in error as if the budget foreseen for the training of trainers had been exceeded. Training of technicians sessions will therefore be organized and carried out on the remaining budget at the beginning of 2009.
ONG | France | Implementation of the RMP: customs training programme | RMP | ASP | LAO | REF | 34 | TRA | 4 | N | O | I |  | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-01 | 2003-08-01 | 2009-06-01 |  |  | 81542 | 0 | 81542 | 66000 | 80.94% | 15542 |  | 15000 | 10600 | 0 | 8579.6277 | 2020.3723 |  | The target number of customs officers to be trained has not been met yet because the organisation of the training sessions was delayed.
FIN | Sweden | Implementation of the RMP: development of import/export licensing system | Individual | ASP | LAO | REF | 34 | TAS | 5 | A | O | I |  | 1.6 |  | 0 |  | 2001-07-01 | 2002-11-01 | 2002-09-01 |  | 2005-12-01 | 2005-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Swedish contribution in Lao PDR consists of technical assistance to prepare an import/export licensing system. International and national consultants were contracted in April 2002. After an initial delay in the signing of agreement and data collection the project is completed, we are only awaiting Lao PDR’s approval of the final report. The Decree for the "Control of the Import-Export and Consumption of ODS" was signed late 2003. A regulation for how the new Decree shall be implemented has been developed and the regulation was signed by the Minister in November 2004. SEI and the IC gave a number of suggestions on drafts on the regulation during 2004. An information brochure to all importers informing them about the licensing system was finalized during 2005. |  | 2001 | [11 empty] | 2001
ONG | France | Implementation of the RMP: recovery and recycling, training and demonstration project (complement) | RMP | ASP | LAO | REF | 34 | TAS | 6 | N | O | I |  | 1.2 |  | 0 |  | 2001-07-01 | 2006-03-07 | 2004-08-01 | 2009-06-01 |  |  | 40800 | 0 | 40800 | 40800 | 100% | 0 |  | 0 | 2040 | 0 | 2040 | 0 |  | Lao has reported an error concerning this activity in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). With the 2 budgets combined, 3 sets of R&R equipment have been bought and handed over to three institutions, 21 sets of basic servicing equipment were bought, and the training of trainers included sessions on best practices, MAC and R&R. Furthermore, a recovery and recycling machine was built locally as part of a university training course.
COM | UNEP | Implementation of the RMP: Monitoring the activities contained in the RMP | Individual | ASP | LAO | REF | 34 | TAS | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 |  | 17500 | -42 | 17458 | 5000 | 28.64% | 12458 | 0 | 12458 | 2275 | -5 | 650 | 1620 | 0 | Project completed | $ 42 plus $ 5 returned to ExCom 54 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | LAO | FOA | 36 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356 | 2244 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | France | Technical assistance for country programme and refrigerant management plan preparation |  | ASP | LAO | SEV | 27 | CPG | 9 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-07 | 2000-12-01 |  | 2001-02-01 | 2001-02-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Le Plan de gestion des réfriférants a été approuvé en même temps que le Programme de pays à la 34ème réunion du Comité Exécutif. Project completed.
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) in the manufacture of flexible polyurethane foam (box) at Prasert Foam Co., Ltd. | Individual | ASP | LAO | FOA | 38 | INV | 10 | A | O | I | CFC | 16.3 | 16.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-08-01 | 2005-11-01 | 139343 | 0 | 139343 | 139343 | 100% | 0 | 0 | 0 | 18115 | 0 | 18114.59 | 0.41 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Formulation of a terminal phase out project in the foam sector | Individual | ASP | LAO | FOA | 39 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | LAO | SEV | 43 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
CLO | UNDP | Conversion from CFC-11 in the manufacture of boxfoam (FPF) and insulated containers (RPF) in Prasert Sofa Shop Co., Ltd. | Individual | ASP | LAO | FOA | 44 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-12-01 | 184660 | -184660 | 0 | 0 |  | 0 | 0 | 0 | 16619 | -16619 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. | [13 empty] | 2004 | Investment
CLO | UNDP | Project preparation for foam multiple sub-sectors | Individual | ASP | LAO | FOA | 45 | PRP | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  |  | 2006-12-01 | 22493 | 0 | 22493 | 22493 | 100% | 0 | 0 | 0 | 1687 | 0 | 1687 | 0 | 0 | Canceled in 2006. Financially completed in 2006. | [13 empty] | 2005 | Investment
FIN | France | Project preparation for a terminal phase-out management plan for CFCs |  | ASP | LAO | PHA | 49 | PRP | 16 | A | O | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2007-05-14 | 2007-07-01 |  | 2008-02-01 | 2009-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Project completed. TPMP approved by 54th ExCom.
COM | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | LAO | SEV | 50 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2008-11-01 |  | 2008-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008 | [13 empty] | 2006 | Non Investment
ONG | France | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | LAO | PHA | 54 | INV | 18 | A | O | I | CFC | 0 |  | 0 |  | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 181500 | 0 | 181500 |  | 0% | 181500 |  | 150000 | 23595 | 0 | 0 | 23595 |  | The start-off was delayed because activities need to be completed under the RMP.
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | LAO | PHA | 55 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 19500 | 0 | 0 | 19500 | 0 | Draft agreement was prepared and submitted to the country in March 2009 due to Lao PDR internal reorganization of the ozone focal point under the Ministry of Water Resource and Environment. | [13 empty] | 2008
ONG | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | LAO | SEV | 56 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | ASP | LEB | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-28 | 1995-07-01 |  | 1996-05-01 | 1995-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNIDO | Project formulation for phase out of ODS in aerosol sector (Cosmaline Industries S.A.) | Individual | ASP | LEB | ARS | 16 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -8784 | 6216 | 6216 | 100% | 0 | 0 |  | 1950 | -1143 | 807 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for phase out of ODS in the refrigeration sector (Weather-mate and OPACO Ltd.) | Individual | ASP | LEB | REF | 16 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1997-08-01 | 1995-07-01 |  | 1997-12-01 | 2000-12-01 | 15000 | -1497 | 13503 | 13503 | 100% | 0 | 0 |  | 1950 | -197 | 1753 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for the phase out of ODS in the foam sector in 2 plants (Ets. Henri Abdallah and Nasri Karam) | Individual | ASP | LEB | FOA | 16 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-07-01 |  | 1997-03-01 | 1998-08-01 | 20000 | -7358 | 12642 | 12642 | 100% | 0 | 0 |  | 2600 | -959 | 1641 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of CFCs at Cosmaline Industries s.a.al. | Individual | ASP | LEB | ARS | 19 | INV | 5 | A | O | I | CFC | 87.7 | 87.7 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-07-01 | 212500 | 0 | 212500 | 212500 | 100% | 0 | 0 |  | 27625 | 0 | 27625 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Zeeni's Trading Agency | Individual | ASP | LEB | ARS | 19 | INV | 6 | A | O | I | CFC | 212 | 212 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 361900 | -9467 | 352433 | 352433 | 100% | 0 | 0 |  | 47047 | -1303 | 45744 | 0 | 0 | FIN
FIN | France | Projects preparation and technical assistance in the foam sector |  | ASP | LEB | FOA | 19 | TAS | 7 | A | O | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-08-01 | 1996-09-01 | 20000 | -495 | 19505 | 19505 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNDP | Creation of an Ozone Unit | Individual | ASP | LEB | SEV | 19 | INS | 8 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 2000-05-01 |  | 2000-12-01 | 2002-03-01 | 179000 | -63 | 178937 | 178937 | 100% | 0 | 0 | 0 | 23270 | -8 | 23262 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1996 | Non-Investment
FIN | UNIDO | Phasing out of CFC-11 at Nasri Karam and Sons | Individual | ASP | LEB | FOA | 20 | INV | 9 | A | O | I | CFC | 22 | 22 |  |  | 1996-10-01 | 1997-07-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 100109 | -106 | 100003 | 100003 | 100% | 0 | 0 |  | 13014 | -34 | 12980 | 0 | 0 | FIN
FIN | France | Conversion to non-CFC technology in the manufacture of polyurethane flexible molded foam at Meuble Mode Sarl |  | ASP | LEB | FOA | 20 | INV | 10 | A | O | I | CFC | 9 | 9 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-03-01 | 55700 | -235 | 55465 | 55465 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Furniture and Plastic Sarl (FAP) |  | ASP | LEB | FOA | 20 | INV | 11 | A | O | I | CFC | 28 | 28 | 0 |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 2000-09-01 | 2000-12-01 | 128700 | 0 | 128700 | 128700 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Plastiflex Sarl |  | ASP | LEB | FOA | 20 | INV | 12 | A | O | I | CFC | 42 | 42 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-03-01 | 1999-08-01 | 154000 | -7224 | 146776 | 146776 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Merza Foam Sarl |  | ASP | LEB | FOA | 20 | INV | 13 | A | O | I | CFC | 45 | 45 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-04-01 | 108172 | -950 | 107222 | 107222 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to non-CFC technology in the manufacture of rigid foam (sandwich panels) at Kilzi and Co. Sarl |  | ASP | LEB | FOA | 20 | INV | 14 | A | O | I | CFC | 22.5 | 22.5 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-11-01 | 1999-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis. |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Fomaco Sarl |  | ASP | LEB | FOA | 20 | INV | 15 | A | O | I | CFC | 26 | 26 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-09-01 | 1999-12-01 | 154000 | -2258 | 151742 | 151742 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Project preparation for the commercial refrigeration sector |  | ASP | LEB | REF | 20 | PRP | 16 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation to establish a CFC and HCFC recovery and recycling centre |  | ASP | LEB | REF | 20 | PRP | 17 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | UNIDO | Phasing out CFC-11 at Ets. Henri Abdallah P.F.M. | Individual | ASP | LEB | FOA | 21 | INV | 18 | A | O | I | CFC | 16.6 | 16.6 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 81291 | -583 | 80708 | 80708 | 100% | 0 | 0 |  | 10568 | -93 | 10475 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Lebanese Modern Industrial and Trading Co. | Individual | ASP | LEB | REF | 22 | INV | 19 | A | O | I | CFC | 135 | 135 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1999-12-01 | 2002-10-01 | 1313121 | -65527 | 1247594 | 1247594 | 100% | 0 | 0 |  | 170706 | -8776 | 161930 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | ASP | LEB | REF | 23 | TRA | 20 | A | O | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1999-06-01 |  | 2000-10-01 | 2000-12-01 | 52668 | 0 | 52668 | 52668 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en octobre 2000
ONG | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | ASP | LEB | REF | 23 | TAS | 21 | A | O | I | CFC | 62 |  | 0 |  | 1997-11-01 |  | 1998-12-01 | 2009-12-01 |  |  | 425289 | 0 | 425289 | 0 | 0% | 425289 |  | 300000 | 0 | 0 | 0 | 0 |  | The financial agreement was at last signed in 2008. Activities are however delayed. |  |  |  |  | 2002-11-01
FIN | France | Conversion of refrigeration industrial facilities |  | ASP | LEB | REF | 23 | INV | 22 | A | O | I | CFC | 10.4 | 10.4 | 0 |  | 1997-11-01 | 1999-01-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 166605 | -13443 | 153162 | 153162 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé
FIN | UNDP | Project preparation for one methyl bromide alternative demonstration project | Individual | ASP | LEB | FUM | 25 | PRP | 23 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-08-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Demonstration project of alternative to methyl bromide for soil fumigation (greenhouse) | Individual | ASP | LEB | FUM | 26 | DEM | 24 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 328200 | -2958 | 325242 | 325242 | 100% | 0 | 0 | 0 | 42666 | -385 | 42281 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | Germany | Training in improved operations, service and maintenance for refrigeration technicians in using hydrocarbons | Individual | ASP | LEB | REF | 26 | TRA | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-09-01 | 2002-01-01 | 49500 | -8197 | 41303 | 41303 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | [13 empty] | 1999
CLO | Germany | Project preparation and technical assistance at Arnatoury S.A.R.L., Sin-El-Fil | Individual | ASP | LEB | ARS | 26 | PRP | 26 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented | Funds to be offset against future german approvals | [12 empty] | 2000
FIN | UNDP | Preparation of project in the foam subsector | Individual | ASP | LEB | FOA | 27 | PRP | 27 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of four projects in the aerosol sector | Individual | ASP | LEB | ARS | 27 | PRP | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
COM | France | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers |  | ASP | LEB | REF | 28 | TAS | 29 | A | O | I |  | 0 |  | 0 |  | 1999-07-01 | 2000-03-23 | 2002-02-01 |  | 2001-08-01 |  | 45750 | 0 | 45750 | 24784 | 54.17% | 20966 |  | 0 | 0 | 0 | 0 | 0 |  | The study was completed and a draft report was handed over to the NOU (08/2001). Remaining activities could be carried out at the same time than the R&R project.Project completed.
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at International Cosmetic Manufacturing Co. (Incoma), SAL | Individual | ASP | LEB | ARS | 28 | INV | 30 | A | O | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 158582 | -5069 | 153513 | 153513 | 100% | 0 | 0 | 0 | 20616 | -659 | 19957 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | Germany | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers | RMP | ASP | LEB | REF | 28 | TAS | 31 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2001-11-01 | 2003-10-01 | 37550 | -3 | 37547 | 37547 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | [13 empty] | 2001
FIN | UNDP | Group SME's project for the conversion to CFC-free technology in manufacturer of aerosol at Zahdreddine Trade and Manufacturing Sarl (ZTME), at Societe Nouvelle pour le Commerce et l'Industrie (SNCI) | Individual | ASP | LEB | ARS | 29 | INV | 32 | A | O | I | CFC | 50.7 | 50.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2004-09-01 | 2005-10-01 | 314092 | -1547 | 312545 | 312545 | 100% | 0 | 0 | 0 | 40832 | -201 | 40631 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141B and CFC-12 to HFC-134a in the manufacture of commercial refrigeration at the first group of Lebanese Commercial Refrigerator Manufacturers | Individual | ASP | LEB | REF | 29 | INV | 33 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2000-07-01 | 2002-09-01 | 258006 | -8773 | 249233 | 249233 | 100% | 0 | 0 |  | 33541 | -1192 | 32349 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Farjallah Co. | Individual | ASP | LEB | REF | 29 | INV | 34 | A | O | I | CFC | 20.1 | 20.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-07-01 | 200046 | 0 | 200046 | 200046 | 100% | 0 | 0 | 0 | 26006 | 0 | 26006 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosols at Societe Nougeaim PMOSAL | Individual | ASP | LEB | ARS | 28 | INV | 35 | A | O | I | CFC | 54 | 54 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 147333 | -2643 | 144690 | 144690 | 100% | 0 | 0 | 0 | 19153 | -344 | 18809 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the second group of Lebanese commercial refrigeration manufacturers | Individual | ASP | LEB | REF | 31 | INV | 36 | A | O | I | CFC | 15.66 | 15.66 |  |  | 2000-07-01 | 2000-09-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 203191 | -1043 | 202148 | 202148 | 100% | 0 | 0 |  | 26415 | -177 | 26238 | 0 | 0 | FIN
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | ASP | LEB | SEV | 31 | INS | 37 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2003-07-01 | 2004-12-01 | 119300 | 0 | 119300 | 119300 | 100% | 0 | 0 | 0 | 15509 | 0 | 15509 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2000 | Non-Investment
FIN | UNIDO | Project preparation of two umbrella investment projects in the commercial refrigeration sector, covering six SME factories each | Individual | ASP | LEB | REF | 31 | PRP | 38 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1076 | 18924 | 18924 | 100% | 0 | 0 |  | 2600 | -144 | 2456 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the third group of Lebanese commercial refrigerator manufacturers | Individual | ASP | LEB | REF | 31 | INV | 39 | A | O | I | CFC | 15.8 | 15.8 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 208498 | -8133 | 200365 | 200365 | 100% | 0 | 0 |  | 27105 | -1099 | 26006 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two umbrella projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 33 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-01-01 | 2002-04-01 |  | 2002-07-01 | 2003-06-01 | 15000 | -229 | 14771 | 14771 | 100% | 0 | 0 |  | 1950 | -33 | 1917 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | LEB | FOA | 33 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 12000 | -1934 | 10066 | 10066 | 100% | 0 | 0 | 0 | 1560 | -251 | 1309 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | ASP | LEB | FUM | 33 | PRP | 42 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 2001 | Investment
FIN | UNIDO | Project preparation in the fumigants (strawberries) sector | Individual | ASP | LEB | FUM | 33 | PRP | 43 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -904 | 29096 | 29096 | 100% | 0 | 0 |  | 3900 | -123 | 3777 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 44 | A | O | I | MBR | 6 | 6 |  |  | 2001-07-01 | 2002-04-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | FIN | [13 empty] | 2001 | INV | 44.4 | 44.4 |  |  | Yes | N/A | N/A
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 4th group of enterprises | Individual | ASP | LEB | REF | 34 | INV | 45 | A | O | I | CFC | 18.8 | 18.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2004-06-01 | 2005-12-01 | 279672 | -9510 | 270162 | 270162 | 100% | 0 | 0 |  | 36357 | -1292 | 35065 | 0 | 0 | FIN | [13 empty] | 2001 | INV
COM | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 46 | N | O | I | MeBr | 25.8 | 25.8 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-12-01 |  | 2004-12-01 |  | 800000 | 0 | 800000 | 800000 | 100% | 0 | 0 | 0 | 98000 | 0 | 98000 | 0 | 0 | Completed in 2004. | [13 empty] | 2001 | Investment | 186.1 | 186.1 |  |  | Yes | N/A | Yes
CLO | UNIDO | Preparation of 2 umbrella investment projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 36 | PRP | 47 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO | [13 empty] | 2002 | INV
FIN | UNDP | Preparation of a CFC terminal programme | Individual | ASP | LEB | PHA | 36 | PRP | 48 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-12-01 | 2007-03-01 | 15000 | -3601 | 11399 | 11399 | 100% | 0 | 0 | 0 | 1950 | -468 | 1482 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNDP | Country programme update | Individual | ASP | LEB | SEV | 36 | CPG | 49 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2003-12-01 | 2004-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 | 0 | 4875 | 0 | 4875 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Renewal of institutional strengthening project (Phase 3) | Individual | ASP | LEB | SEV | 37 | INS | 50 | N | T | I | No_ODP | 12.8 | 12.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-12-01 |  | 155090 | 0 | 155090 | 154111 | 99.37% | 979 | 0 | 783.2 | 20162 | 0 | 20034.43 | 127.57 | 0 | Completed in 2004. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (second tranche) | Multi-Year | ASP | LEB | FUM | 38 | INV | 51 | N | O | I | MeBr | 31.8 | 31.8 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2004-12-01 |  | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 76000 | 0 | 76000 | 0 | 0 | Completed in 2004. | [13 empty] | 2002 | Investment | 124.3 | 124.3 |  |  | Yes | N/A | Yes
FIN | UNIDO | Phase-out of methyl bromide (strawberries): release of second tranche | Multi-Year | ASP | LEB | FUM | 38 | INV | 52 | A | O | I | MBR | 10.1 | 10.1 |  |  | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 | 2007-12-01 | 421946 | 0 | 421946 | 421946 | 100% | 0 | 0 |  | 54853 | 0 | 54853 | 0 | 0 | FIN | [13 empty] | 2002 | INV | 34.3 | 34.3 |  |  | Yes | N/A | N/A
COM | UNDP | Sector phase-out of methyl bromide in vegetable, cut flower and tobacco production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 53 | N | O | I | MeBr | 54 | 54 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-06-01 |  | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Completed in 2006. | [13 empty] | 2003 | Investment | 70.3 | 70.3 |  |  | Yes | N/A | Yes
COM | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 54 | A | O | I | MBR | 14.2 | 25.3 |  |  | 2003-12-01 | 2005-07-01 | 2004-12-01 |  | 2008-12-01 |  | 450000 | 0 | 450000 | 367358 | 81.64% | 82642 | 35004 | 50000 | 33750 | 0 | 27552 | 6198 | 2625 | Project completed Dec 2008: . | [13 empty] | 2003 | INV | 20.1 | 24.3 |  |  | No | N/A | N/A
FIN | UNDP | Project preparation for the formulation of a CFC phase-out plan | Individual | ASP | LEB | PHA | 42 | PRP | 55 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2004-12-01 | 2005-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 | 0 | 1200 | 0 | 1200 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2004 | Investment
COM | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (first tranche) | Multi-Year | ASP | LEB | PHA | 44 | INV | 57 | N | O | I | CFC | 55 | 55 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 |  | 1061420 | 0 | 1061420 | 1061420 | 100% | 0 | 0 | 0 | 79607 | 0 | 79607 | 0 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment | 417 | 417 |  |  | Yes | Yes | yes
COM | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fourth tranche) | Multi-Year | ASP | LEB | FUM | 44 | INV | 58 | N | O | I | MeBr | 36 | 36 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2005-12-01 |  | 2008-12-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Completed in 2008. Activities resumed post-2006 conflict. Agreement was revised at 52nd ExCom Meeting Training and interactions with individual farmers and farmers associations took place to identify type and quantities of alternative supplies. Awareness raising and outreaching activities as well as monitoring and evaluation activities were successfully conducted. | [13 empty] | 2004 | Investment | 34.3 | 34.3 |  |  | Yes | N/A | Yes
COM | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | LEB | SEV | 44 | INS | 59 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-06-01 |  | 155090 | 0 | 155090 | 152255 | 98.17% | 2835 | 0 | 2268 | 11632 | 0 | 11419.3704 | 212.6296 | 0 | Completed in 2007. | [13 empty] | 2004 | Non-Investment
COM | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | LEB | SEV | 45 | TAS | 60 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-09-01 | 2006-12-01 |  | 2008-08-01 |  | 45872 | 0 | 45872 | 39024 | 85.07% | 6848 | 0 | 5478.4 | 4128 | 0 | 3511.7517 | 616.2483 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
ONG | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 61 | N | O | I | MeBr | 34.3 | 17 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-03-01 | 2009-07-01 |  |  | 210000 | 57300 | 267300 | 120814 | 45.2% | 146486 | 0 | 58594.4 | 15750 | 4298 | 9061.05 | 10986.95 | 0 | Activities resumed post-2006 conflict for new season in cut flower sector, with remaining quantities of Agrocelhone distributed to farmers, achieving phase out of 17.04 ODP tones of MeBr. Only limited number of pools were constructed for floating trays techniques in tobacco sector, due extraordinary stormy weather, no tangible results achieved yet. Further disbursements will be reflected in 2009. | [13 empty] | 2005 | Investment | 0 |  |  |  | Latest | Latest | Latest
ONG | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 62 | A | O | I | MBR | 9 | 5.51 |  |  | 2005-11-01 | 2008-02-01 | 2006-12-01 | 2009-03-01 |  |  | 42504 | 4900 | 47404 | 35025 | 73.89% | 12379 | 9865 | 11000 | 3188 | 368 | 2627 | 929 | 740 | USD 4,900 was approved as financial loss during war at the 54th ExCom. National expert contract as well as site-engineers to ensure full implementation of the alternative technologies has been extended by end of 2008. The reports related to the 2008 MeBr consumption phase-out were not yet received.The project is completed, however there are still few public awareness publications as well as monitoring activities on-going by 1st quarter 2009. | [13 empty] | 2005 | INV | 9 | 3.5 |  |  | Yes | N/A | N/A
COM | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (second and third tranches) | Multi-Year | ASP | LEB | PHA | 48 | INV | 63 | N | O | I | CFC | 287 | 287 | 0 | 0 | 2006-04-01 | 2008-01-01 | 2007-04-01 |  | 2008-12-01 |  | 865000 | 0 | 865000 | 320750 | 37.08% | 544250 | 0 | 435400 | 64875 | 0 | 24056.25 | 40818.75 | 0 | Completed in 2008. Most of the investment activities in various manufacturing sectors completed. Servicing sector activities continued. 22 sets of refrigerant identifiers procured and distributed. 60 sets MAC R&R units procured and are under distribution. Some of these expenditures to be reflected in 2009. | [13 empty] | 2006 | Investment | 75 | 75 |  |  | Yes | Yes | yes
COM | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | LEB | SEV | 50 | INS | 64 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 |  | 155090 | 0 | 155090 | 110836 | 71.47% | 44254 | 0 | 35403.2 | 11632 | 0 | 8312.8787 | 3319.1213 | 0 | Completed in 2008. Extensive monitoring and management of NPMP activities continued and special efforts were taken to restart activities following the post conflict conditions of July 2006. Public awareness undertaken. Follow-up phase 6 approved at 56th ExCom. While late payments to be processed in 2009, project operationally completed. | [13 empty] | 2006 | Non-Investment
ONG | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fourth tranche) | Multi-Year | ASP | LEB | PHA | 53 | INV | 65 | N | O | I | CFC | 40 | 40 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 40000 | 7500 | 0 | 0 | 7500 | 0 | See note above | [13 empty] | 2007 | Investment | 35 |  |  |  | Latest | Latest | Latest
ONG | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fifth tranche) | Multi-year | ASP | LEB | PHA | 55 | INV | 66 | N | O | I | CFC | 35 | 33 | 0 | 0 | 2008-07-01 |  | 2010-07-01 | 2010-07-01 |  |  | 65000 | 0 | 65000 | 0 | 0% | 65000 | 0 | 13000 | 4875 | 0 | 0 | 4875 | 0 | See note above | [13 empty] | 2008 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | LEB | PHA | 55 | PRP | 67 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 137250 | 0 | 137250 | 0 | 0% | 137250 | 0 | 137250 | 10294 | 0 | 0 | 10294 | 0 | Review of existing baseline information in progress. TOR and prodoc is under finalization. | [13 empty] | 2008 | Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | LEB | SEV | 56 | INS | 68 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-03-01 | 2009-03-01 |  |  | 155090 | 0 | 155090 | 0 | 0% | 155090 | 0 | 62036 | 11632 | 0 | 0 | 11632 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
FIN | UNEP | Country programme preparation | Individual | AFR | LES | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-05-25 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | LES | SEV | 20 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1999-10-01 |  | 1999-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  | 2000-03-01 | [10 empty] | 1996 | Non Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | LES | REF | 21 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-06-01 | 2002-03-01 | 20000 | -2704 | 17296 | 17296 | 100% | 0 | 0 | 0 | 2600 | -352 | 2248 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | LES | REF | 22 | TAS | 4 | A | O | I | CFC | 3.6 | 3.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2000-12-01 | 56095 | 0 | 56095 | 56095 | 100% | 0 | 0 | 0 | 7292 | 0 | 7292 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | LES | REF | 26 | TAS | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-11-01 | 2004-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted TPMP submitted and approved at 41st Excom | [13 empty] | 1999
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | LES | SEV | 29 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-12-01 |  | 2005-04-01 | 2007-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | -1515 | 2600 | -1515 | 0 | Project financially completed. | $ 0 plus $ 1,515 returned to ExCom 49 | [12 empty] | 1999 | Non Investment
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | LES | REF | 37 | PRP | 7 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed, TPMP approved at 41st Excom | [13 empty] | 1998
FIN | Germany | Terminal CFC phase-out management plan (first tranche) | Multi-Year | AFR | LES | PHA | 41 | INV | 8 | A | O | I | CFC | 0.6 | 0.8 | 0 |  | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2005-03-05 | 2005-06-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Second tranche was requested for the TPMP. | [13 empty] | 2002 |  | 1.4 | 1.2 |  |  | Yes
FIN | Germany | Terminal CFC phase-out management plan (second tranche) | Multi-Year | AFR | LES | PHA | 45 | INV | 9 | A | O | I | CFC | 0.6 | 0.6 | 0 |  | 2005-04-01 | 2005-04-01 | 2006-04-01 |  | 2007-12-01 | 2008-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | 3rd tranche was requested and approved. | [15 empty] | 0.8 | 0 |  |  | Yes
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LES | SEV | 45 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-03-07 | 2007-04-01 |  | 2008-02-01 |  | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in February 2008. | [13 empty] | 2005 | Non Investment
ONG | Germany | Terminal CFC phase-out management plan (third tranche) | Multi-Year | AFR | LES | PHA | 50 | INV | 10 | A | O | I | CFC | 1.4 | 1.4 | 0 |  | 2006-11-01 | 2007-05-01 | 2007-11-01 | 2009-10-01 |  |  | 17300 | 0 | 17300 | 11700 | 67.63% | 5600 | 0 | 5600 | 2249 | 0 | 1521 | 728 | 0 | NOU underwent a change in personnel and that delayed all activities. However the last remaining funds are now being used for the incentive scheme and purchasing of training equipment for the centres. | [15 empty] | 0 | 0 |  |  | Yes
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | LES | SEV | 53 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | MOU signed with country and awaiting payment. Activities delayed due to change of Ozone Officer | [13 empty] | 2007 | Non Investment
FIN | UNIDO | Preparation of country programme | Individual | AFR | LIB | SEV | 27 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 80000 | -3440 | 76560 | 76560 | 100% | 0 | 0 |  | 10400 | -463 | 9937 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the Refrigeration sector | Individual | AFR | LIB | REF | 30 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2003-07-01 | 2004-04-01 | 20000 | -550 | 19450 | 19450 | 100% | 0 | 0 |  | 2600 | -76 | 2524 | 0 | 0 | FIN
COM | UNIDO | Phasing out ODS in the production of refrigerators and freezers at Electrical Household Appliance Manufacturing | Individual | AFR | LIB | REF | 32 | INV | 3 | A | O | I | CFC | 53.4 | 53.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-06-01 |  | 2004-03-01 |  | 558113 | 0 | 558113 | 365013 | 65.4% | 193100 | 191573 | 190000 | 71392 | 1 | 47452 | 23941 | 23773 | The project will be financially completed upon disbursement of unliquidated obligations.
ONG | UNIDO | Creation of the National Ozone Unit | Individual | AFR | LIB | SEV | 32 | INS | 4 | N | T | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-12-01 | 2004-01-01 | 2009-06-01 |  |  | 157000 | 0 | 157000 | 88198 | 56.18% | 68802 | 68800 | 68000 | 20410 | 0 | 11466 | 8944 | 8944 | The progress reports were received as of December 2008. The project will be completed as planned.
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Sebha Unit | Individual | AFR | LIB | FOA | 32 | INV | 5 | A | O | I | CFC | 26 | 19 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  |  | 2008-04-01 | 128097 | -106916 | 21181 | 21181 | 100% | 0 | 0 | 0 | 16653 | -13899 | 2754 | 0 | 0 | Canceled in 2005. Financially completed in 2008. Balance returned in 2009. | [13 empty] | 2000 | Investment
COM | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Garabouli Unit | Individual | AFR | LIB | FOA | 32 | INV | 6 | A | O | I | CFC | 40.3 | 40.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-12-01 |  | 109810 | 0 | 109810 | 109502 | 99.72% | 308 | 0 | 246.4 | 14275 | 0 | 14234.9608 | 40.0392 | 0 | Completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Electrical Household Appliance-Tajura by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | LIB | FOA | 32 | INV | 7 | A | O | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2005-12-01 | 2008-04-01 | 119802 | -7675 | 112127 | 112127 | 100% | 0 | 0 | 0 | 15574 | -998 | 14576 | 0 | 0 | Completed in 2005. Financially completed in 2008. | [13 empty] | 2000 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Ben Ghazi Unit | Individual | AFR | LIB | FOA | 32 | INV | 8 | A | O | I | CFC | 31.4 | 31.4 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2007-04-01 | 2008-03-01 | 124860 | 0 | 124860 | 124763 | 99.92% | 97 | 0 | 0 | 16232 | 0 | 16219.3898 | 12.6102 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | LIB | FOA | 32 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2000-12-01 | 2001-12-01 |  | 2001-03-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | LIB | FOA | 33 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | -1934 | 23066 | 23066 | 100% | 0 | 0 | 0 | 3250 | -251 | 2999 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
CLO | UNIDO | Project preparation in the commercial refrigeration sector | Individual | AFR | LIB | REF | 33 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 |  | 2002-04-01 |  |  | 2003-06-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO | [13 empty] | 2001 | INV
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Essadek | Individual | AFR | LIB | FOA | 34 | INV | 12 | A | O | I | CFC | 32 | 32 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2007-03-01 | 129109 | 0 | 129109 | 129109 | 100% | 0 | 0 | 0 | 16784 | 0 | 16784 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Hilal Africa | Individual | AFR | LIB | FOA | 34 | INV | 13 | A | O | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2008-04-01 | 113727 | 0 | 113727 | 113704 | 99.98% | 23 | 0 | 0 | 14785 | 0 | 14782.0099 | 2.9901 | 0 | Completed in 2005. Financially completed in 2008. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate El Hani | Individual | AFR | LIB | FOA | 35 | INV | 14 | A | O | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-10-01 | 112440 | 0 | 112440 | 112440 | 100% | 0 | 0 | 0 | 14617 | 0 | 14617 | 0 | 0 | Completed in 2005. Financially completed in 2008. | [13 empty] | 2001 | Investment
COM | UNDP | Phase out of CFC-11 by conversion to liquid carbon dioxide (LCD) in the manufacture of flexible polyurethane foam at El Houria Unit Plant | Individual | AFR | LIB | FOA | 35 | INV | 15 | A | O | I | CFC | 96 | 96 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-08-01 |  | 520405 | 0 | 520405 | 470518 | 90.41% | 49887 | 0 | 39909.6 | 67245 | 0 | 60798.7681 | 6446.2319 | 0 | Completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Ali Sannoga | Individual | AFR | LIB | FOA | 35 | INV | 16 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2007-03-01 | 125640 | 0 | 125640 | 125640 | 100% | 0 | 0 | 0 | 16333 | 0 | 16333 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 6 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 |  | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-12-01 | 2007-03-01 | 20000 | -9146 | 10854 | 10854 | 100% | 0 | 0 | 0 | 2600 | -1189 | 1411 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | AFR | LIB | REF | 36 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-06-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 20000 | -722 | 19278 | 19278 | 100% | 0 | 0 |  | 2600 | -98 | 2502 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | National phase-out plan | Individual | AFR | LIB | SEV | 38 | PRP | 21 | A | O | I | CFC | 0 | 0 |  |  | 2002-11-01 | 2003-09-01 | 2003-12-01 |  | 2005-06-01 | 2006-08-01 | 40000 | -468 | 39532 | 39532 | 100% | 0 | 0 |  | 5200 | -61 | 5139 | 0 | 0 | FIN | [13 empty] | 2002 | INV
COM | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | LIB | PHA | 41 | INV | 22 | A | O | I | CFC | 150 | 150.4 |  |  | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-08-01 |  | 1500000 | 0 | 1500000 | 1499979 | 100% | 21 | 0 | 1 | 112500 | 1 | 112498 | 3 | 0 | Financial completion in Dec 2008. | [13 empty] | 2003 | INV | 461 | 459 |  |  | Yes | Yes | Yes
FIN | UNIDO | Preparation of a halon phase-out plan | Individual | AFR | LIB | HAL | 45 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 25000 | -264 | 24736 | 24736 | 100% | 0 | 0 |  | 1875 | -20 | 1855 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | NON-INV
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector (methyl bromide) | Individual | AFR | LIB | FUM | 45 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-11-01 | 15000 | -1137 | 13863 | 13863 | 100% | 0 | 0 |  | 1125 | -85 | 1040 | 0 | 0 | FIN | [13 empty] | 2005 | NON-INV
ONG | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | AFR | LIB | PHA | 45 | INV | 25 | A | O | I | CFC | 124 | 124 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 | 2009-12-01 |  |  | 720000 | 0 | 720000 | 487207 | 67.67% | 232793 | 48621 | 80000 | 54000 | 0 | 36541 | 17459 | 3647 | Technical specification on the package of servicing equipment for 50 service shops has been prepared and consented with NOU. Procurement is in progress, offers are evaluated. Delivery expected in the first Q 2009. | [13 empty] | 2005 | INV | 176 | 176 |  |  | Yes | Yes | Yes
ONG | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | AFR | LIB | HAL | 47 | TAS | 26 | A | O | I | HAL | 653.9 | 0 |  |  | 2005-11-01 | 2006-09-01 | 2008-12-01 | 2010-01-01 |  |  | 343500 | 0 | 343500 | 169 | 0.0492% | 343331 | 0 | 20000 | 25763 | 0 | 13 | 25750 | 0 | The initially identified entity to host halon banking equipment failed to obtain approval by the Ministry of Industry. New entity (iron & steel company) has been suggested and its suitability is being verified. | We have not yet received the official Article 7 data of the country. | [12 empty] | 2005 | INV
ONG | UNIDO | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others | Multi-Year | AFR | LIB | FUM | 47 | INV | 27 | A | O | I | MBR | 56 | 21 |  |  | 2005-11-01 | 2006-04-01 | 2009-12-01 | 2009-12-01 |  |  | 743000 | 0 | 743000 | 111918 | 15.06% | 631082 | 514223 | 600000 | 55725 | 0 | 8394 | 47331 | 38567 | The second tranche of the MY-project has been approved by the 56th ExCom as Spanish Bilateral. The agreement with Spain is completed and the funds are going to be transferred to UNIDO soon. A team of 4 national experts was recruited and are implementing the agreed activities. In particular, a greenhouse for the introduction of the grafting technology is under installation and its completion is expected in time for the 2009 cropping season. In the meantime, training of the people responsible for the management of the grafting unit is ongoing. Furthermore, training activities will be addressed to growers on how to cultivate grafted plants. Field training to the growers and technician is also expected in 2009 on the proper use of solarization, in combination with chemical substances. Distribution of plastic, insect nets, grafted seedlings, chemical substances (e.g. Metham Na, nematicides, etc.) will be distributed to the growers. | [13 empty] | 2005 | INV | 96 | 96 |  |  | Yes | N/A | N/A
ONG | UNIDO | National ODS phase-out plan: 3rd tranche | Multi-Year | AFR | LIB | PHA | 54 | INV | 28 | A | O | I | CFC | 176 | 11.6 |  |  | 2008-04-01 |  | 2009-03-31 | 2010-07-01 |  |  | 277947 | 0 | 277947 | 0 | 0% | 277947 | 0 | 12000 | 20846 | 0 | 0 | 20846 | 0 | Training of service technicians to be organized after delivery of equipment. | [13 empty] | 2008 | INV | 11.6 | 11.6 |  |  | Yes | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | LIB | PHA | 55 | PRP | 29 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 7505 | 8.829% | 77495 | 3454 | 20000 | 6375 | 0 | 563 | 5812 | 259 | Contracts were issued for the preparation of the survey. Stake holders workshop will be organized for the preparation of the HPMP. | Job description of the national expert for the preparation of the HPMP includes: • Assistance for policy and legislation; • Survey of HCFCs use and analysis of data collectes; • Consultation with national stackeholders in the data collection and analysis. Regarding the policy aspect, the consultant is requested to assess and analyze the institutional framework, legislation, licensing and quota system regulating consumption of ozone depleting substances in Libya with particular focus on HCFCs. The expert is also requested to assess the current national policies on climate change, chemical management and energy policies, as well as the CFCs phase out activities and lessons learned from previous ODS phase-out activities. Expected outputs: assessment of the current status of legislation and recommendations on necessary institutional and regulatory improvements to facilitate a smooth compliance with the HCFCs phase out obligations. | [12 empty] | 2008 | NON-INV
ONG | Spain | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others (second tranche) | Multi-Year | AFR | LIB | FUM | 56 | INV | 30 | A | O | I | MBR | 55 |  | 0 |  | 2008-11-01 |  | 2010-11-01 | 2010-11-01 |  |  | 500000 | 0 | 500000 |  | 0% | 500000 |  |  | 65000 | 0 |  | 65000 |  | We are in the process to transfer the US$ 500,000 to UNIDO for the implementation of the project, they expect to start the implementation in may 2009, they will report pogress at the end of 2009
FIN | UNEP | Country programme preparation | Individual | AFR | LIR | SEV | 27 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2000-07-01 |  | 2003-09-01 | 2008-12-01 | 50000 | 0 | 50000 | 33000 | 66% | 17000 | 14500 | 0 | 6500 | 0 | 4290 | 2210 | 1885 | Project financially completed. Balance to be returned to ExCom 57 | [7 empty] | 2003-12-01 | [5 empty] | 1999 | Non Investment
FIN | UNEP | Establishment of the ozone unit | Individual | AFR | LIR | SEV | 41 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2007-12-01 | 127820 | 0 | 127820 | 127820 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | Germany | Implementation of the RMP: training of trainers in code of good refrigeration practices and establishment of national refrigeration demonstration centre | Individual | AFR | LIR | REF | 41 | TRA | 3 | A | O | I |  | 13 | 13 | 0 |  | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2008-12-01 |  | 119460 | 0 | 119460 | 119460 | 100% | 0 | 0 | 0 | 15530 | 0 | 15530 | 0 | 0 | A total of 32 technician training courses have been completed throughout the country. Additional tools were purchased for the National Refriegration demonstration centre in Monrovia | [13 empty] | 2002
ONG | Germany | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector and recovery and recycling | RMP Update | AFR | LIR | REF | 41 | TAS | 4 | A | O | I | CFC | 10.1 | 10.1 | 0 |  | 2003-12-01 | 2005-06-01 | 2006-12-01 | 2009-10-01 |  |  | 92400 | 0 | 92400 | 85320 | 92.34% | 7080 | 0 | 7080 | 12012 | 0 | 11091.6 | 920.4 | 0 | Follow up of the R&R project including purchase of storage cylinders for R502 collected through the incentive scheme. Exchange of info within the industry | [13 empty] | 2002
ONG | Germany | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP Update | AFR | LIR | REF | 41 | TAS | 5 | A | O | I | CFC | 11.7 | 0.5 | 0 |  | 2003-12-01 | 2005-04-01 | 2008-12-01 | 2009-06-01 |  |  | 107350 | 0 | 107350 | 105000 | 97.81% | 2350 | 0 | 2350 | 13996 | 0 | 13689.6134 | 306.3866 | 0 | Incentive scheme was initiated with several companies coming forward. Under the project1731.6 kgs of R502 and 113kgs of R12 phased out through retrofits of cold rooms and the project is coming to an end. | [13 empty] | 2002
COM | Germany | Implementation of the RMP: MAC recovery/recycling of CFC-12 | Individual | AFR | LIR | REF | 41 | TAS | 6 | A | O | I | CFC | 6.8 | 3 | 0 |  | 2003-12-01 | 2005-04-01 | 2006-12-01 |  | 2008-12-01 |  | 61858 | 0 | 61858 | 61858 | 100% | 0 | 0 | 0 | 8042 | 0 | 8042 | 0 | 0 | Project has been completed with MAC associations being created and R&R units being shared among with MAC garages.
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | LIR | REF | 41 | TRA | 7 | A | O | I | CFC | 4.4 | 4.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-06-01 | 2008-12-01 | 40040 | 0 | 40040 | 37651 | 94.03% | 2389 | 0 | 0 | 5205 | 0 | 4894.63 | 310.37 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 2003 | Non Investment
ONG | Germany | Implementation of the RMP: monitoring the activities in the RMP | RMP Update | AFR | LIR | REF | 41 | TAS | 8 | A | O | I |  | 1.7 | 0 | 0 |  | 2003-12-01 | 2003-12-01 | 2006-12-01 | 2009-07-01 |  |  | 15455 | 0 | 15455 | 12000 | 77.64% | 3455 | 0 | 3455 | 2009 | 0 | 1559.8835 | 449.1165 | 0 | A national consultant is monitoring the activities in the country and providing back up to the NOU. The consultant has been very helpful for the implementation of the incentive scheme | [13 empty] | 2002
COM | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | LIR | PHA | 49 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2006-07-01 |  | 2007-12-01 |  | 12000 | 0 | 12000 | 11383 | 94.86% | 617 | 0 | 617 | 900 | 0 | 853.725 | 46.275 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | LIR | PHA | 49 | PRP | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-31 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | LIR | SEV | 51 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2009-03-01 | 2009-03-01 |  |  | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The NOU continued the effective monitoring of activities under the Recovery and Recycling program and the Commercial and Industry Incentive Program, which is nearing a successful completion by end of first quarter 2009. The NOU coordinated several activities under TPMP which included Training-of-trainer’s workshop for selected Customs Officers; Training-of-trainer’s workshop in Ghana in for servicing with hydrocarbon refrigerant; purchased and distributed additional five refrigerant identifiers to the Bureau of Customs and Excise; and the establishment of TPMP Monitoring unit. The NOU undertook a joint Customs- NOU Border Tours of various Customs Border Points around the country to assess the level of progress made in the enforcement of ODS Regulations. Posters listing banned ODS and ozone friendly refrigerants were also distributed during the tours at these border points. The NOU assisted the Liberian Refrigeration Union in supervising the first inauguration of the officers of the Union. The NOU celebrated the Ozone Day with several activities including organizing, on the eve of the Ozone day, a one-day seminar with teachers of various schools in and around Monrovia, in collaboration with the Ministry of Education; distribution of awareness materials such as ozone posters, T-Shirts, tracks, etc. The NOU was represented and participated in the 2008 Ozone officers’ Network Meetings in Cairo Egypt and Benin. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | LIR | PHA | 53 | TAS | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 131500 | 0 | 131500 | 124999.53 | 95.06% | 6500.47 | 6500 | 6500.47 | 17095 | 0 | 16249.9389 | 845.0611 | 845 | First tranche successfully completed, country conducted trainings for customs officers, refrigeration technicians, reviewed ODS Regulations, curricula for customs training school and technicians scholl.second tranche approved during the 57th Ex-com | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | LIR | PHA | 53 | INV | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 | 2009-11-01 |  |  | 104000 | 0 | 104000 | 32590 | 31.34% | 71410 | 0 | 28564 | 9360 | 0 | 2933.1 | 6426.9 | 0 | Project ongoing. National experts recruited. International expert recruited with a mission fielded in August 2008. A training workshop for 12 technicians was held in August 2008 to cover safe handling of refrigerants and retrofitting techniques. Equipment bidding finalized. Equipment expected in Q1-2009. Delays experienced with supplier. 4 companies participated in end-user incentive programme. Four more applications are being prepared and will be processed in Q1-Q2-2009. Second tranche to be approved at 57th ExCom. | [13 empty] | 2007 | Investment | 8.4 |  |  |  | Latest | Latest | Latest
FIN | France | Country programme preparation |  | AFR | MAG | SEV | 21 | CPG | 1 | A | O | D |  | 0 |  | 0 |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-09-01 | 1999-12-01 | 40000 | -3019 | 36981 | 36981 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Implementation of the RMP: training of personnel in charge of control and monitoring of imports of ODS |  | AFR | MAG | REF | 29 | TRA | 2 | A | O | I | CFC | 4.4 | 3.2 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2003-06-01 | 2005-01-01 | 26000 | 0 | 26000 | 25148.9362 | 96.73% | 851.0638 |  | 0 | 1300 | 0 | 1257 | 43 |  | Project completed.
FIN | France | Implementation of the RMP: training of trainers and refrigeration technicians in good service practices |  | AFR | MAG | REF | 29 | TRA | 3 | A | O | I | CFC | 7.8 | 5.7 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2004-08-01 | 2005-01-01 | 46200 | 0 | 46200 | 44680.8511 | 96.71% | 1519.1489 |  | 0 | 2310 | 0 | 2234.0426 | 75.9574 |  | Project completed.
FIN | UNEP | Creation of a Ozone Unit | Individual | AFR | MAG | SEV | 29 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2004-07-01 | 2007-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | France | Implementation of the RMP: set up a national recovery and recycling network |  | AFR | MAG | REF | 29 | TAS | 5 | A | O | I | CFC | 13.9 | 10.2 | 0 |  | 1999-11-01 | 2002-05-30 | 2002-12-01 |  | 2004-08-01 | 2005-01-01 | 82700 | 0 | 82700 | 70804.8191 | 85.62% | 11895.1809 |  | 0 | 4135 | 0 | 3540 | 595 |  | Project completed.
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MAG | SEV | 43 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2008-12-01 | 60700 | 0 | 60700 | 60700.01 | 100% | -0.01 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | AFR | MAG | REF | 44 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2005-12-01 |  | 2005-06-01 | 2007-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | AFR | MAG | FUM | 45 | TAS | 9 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 |  | 40000 | 0 | 40000 | 37808 | 94.52% | 2192 | 0 | 1 | 3600 | 0 | 3403 | 197 | 0 | The project is expected to be financially completed in 2009. | [13 empty] | 2005 | NON-INV
FIN | UNEP | Implementation of the RMP: training of customs officers and other officers to control and follow-up of ODS and its containers | Individual | AFR | MAG | REF | 47 | TRA | 10 | A | O | I | CFC | 3.7 | 3.7 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Implementation of the RMP: training of maintenance technicians including small craftsmen of informal sector | Individual | AFR | MAG | REF | 47 | TRA | 11 | A | O | I | CFC | 4.2 | 4.2 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
ONG | France | Implementation of the RMP: recovery and recycling component | RMP | AFR | MAG | REF | 47 | TAS | 12 | A | O | I | CFC | 6.8 |  | 0 |  | 2005-11-01 | 2008-03-04 | 2007-06-01 | 2009-06-01 |  |  | 40500 | 0 | 40500 | 28350 | 70% | 12150 |  | 12150 | 5265 | 0 | 3685.5 | 1579.5 |  | The R&R strategy has been finalised and discussed in details with the local consultant who will assist the NOU to monitor the project.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAG | PHA | 49 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-11-01 | 2007-07-31 |  | 2007-07-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | MAG | SEV | 49 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-07-01 | 2008-06-30 | 2009-06-30 |  |  | 60700 | 0 | 60700 | 47854.53 | 78.84% | 12845.47 | 12175 | 12845.47 | 0 | 0 | 0 | 0 | 0 | The NOU Coordinated the implementation of the TPMP update with UNEP and UNIDO The NOU organized awareness raising activities through the local media and production of awarenss material. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 | 2009-07-01 |  |  | 133000 | 0 | 133000 | 123362.29 | 92.75% | 9637.71 | 1136.78 | 9637.71 | 17290 | 0 | 16037.0977 | 1252.9023 | 147.7814 | Four training workshops have been carried out in May-June 2008. A total of 20 trainers and 160 practitioners have been trained and certified. 25 toolkits were purchased | [13 empty] | 2007 | Non Investment
COM | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | INV | 16 | A | O | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-01 |  | 2008-11-01 |  | 78000 | 0 | 78000 | 75487 | 96.78% | 2513 | 2503 | 2000 | 7020 | 0 | 6794 | 226 | 225 | Project completed in Nov 2008. | [13 empty] | 2007 | INV | 2.3 | 2.3 |  |  | Yes | N/A | N/A
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MAG | PHA | 55 | PRP | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for signature | [13 empty] | 2008
ONG | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 87000 | 0 | 87000 | 0 | 0% | 87000 | 0 | 87000 | 11310 | 0 | 0 | 11310 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | INV | 19 | A | O | I | CFC CTC | 2.4 | 0 |  |  | 2008-11-01 |  | 2009-11-30 | 2009-11-01 |  |  | 47000 | 0 | 47000 | 0 | 0% | 47000 | 0 | 40000 | 4230 | 0 | 0 | 4230 | 0 | The Plan of Action for the implementation of the seccond tranche was reviewed with the Government. Terms of reference for the supply of equipment were prepared and are under review by the Government. The project is expected to be completed in November 2009. | [13 empty] | 2008 | INV | 2.3 | 0.8 |  |  | Yes | N/A | N/A
FIN | UNDP | Training in MAC sector | RMP-Component | ASP | MAL | REF | 04 | TRA | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-10-01 | 1993-12-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Country programme preparation | Individual | ASP | MAL | SEV | 04 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 16294 | -8287 | 8007 | 8007 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | MAL | SEV | 04 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 38289 | 5307 | 43596 | 43596 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Servicing, maintenance and recovery of portable extinguishers (halon-1211) and training programme | Individual | ASP | MAL | HAL | 06 | INV | 4 | N | O | I | HAL | 900 | 900 | 0 | 0 | 1992-02-01 | 1996-03-01 | 1993-02-01 |  | 1998-09-01 | 2002-04-01 | 720000 | -1150 | 718850 | 718850 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conservation, leakage control and recycling of CFC-12 and demonstration project in MAC sector | Individual | ASP | MAL | REF | 06 | TAS | 5 | N | O | D | CFC | 370 | 370 | 0 | 0 | 1992-02-01 | 1994-03-01 | 1992-12-01 |  | 1997-06-01 | 1997-07-01 | 910000 | -1845 | 908155 | 908155 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-08-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | MAL | SEV | 06 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | -65592 | 54408 | 54408 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $54,408 and expenditure of $35,201 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $89,609 and entry for country program removed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Support to a sub-regional workshop on halon and halon bank management | Individual | ASP | MAL | HAL | 9 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-01-01 | 1994-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNDP | Institutional strengthening in relation to projects on reduction of ozone depleting substances | Individual | ASP | MAL | SEV | 09 | INS | 8 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-12-01 | 2003-04-01 | 322520 | -15703 | 306817 | 306817 | 100% | 0 | 0 | 0 | 41928 | -2041 | 39887 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [13 empty] | 1993 | Non-Investment
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | MAL | SEV | 09 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 28200 | 916 | 29116 | 29116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | MAL | SEV | 10 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 75000 | -58343 | 16657 | 16657 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam sheet at Jumaya Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 10 | INV | 11 | A | O | R | CFC | 150 | 150 | 0 | 0 | 1993-06-01 | 1993-12-01 | 1994-12-01 |  | 1993-12-01 | 1997-12-01 | 235811 | 62 | 235873 | 235873 | 100% | 0 | 0 | 0 | 30655 | 8 | 30663 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 10 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-12-01 |  | 1994-03-01 | 1997-12-01 | 50000 | 4438 | 54438 | 54438 | 100% | 0 | 0 | 0 | 6500 | 577 | 7077 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | UNDP | National ODS conference | Individual | ASP | MAL | SEV | 10 | TRA | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-07-01 |  | 1993-07-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1993 | Non-Investment
FIN | USA | Conference on the elimination of ozone depleting solvents |  | ASP | MAL | SOL | 11 | TRA | 14 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Key Asset Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 15 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-11-01 |  | 1995-02-01 | 1998-12-01 | 690000 | -15755 | 674245 | 674245 | 100% | 0 | 0 | 0 | 89700 | -2048 | 87652 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane insulation foam at Insafoam Insulation Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 16 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 310000 | -3393 | 306607 | 306607 | 100% | 0 | 0 | 0 | 40300 | -441 | 39859 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Island Resources Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 17 | A | O | I | TCA/CFC | 16.5 | 16.5 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-04-01 | 1998-12-01 | 230000 | -14204 | 215796 | 215796 | 100% | 0 | 0 | 0 | 29900 | -1846 | 28054 | 0 | 0 | Completed in 1994. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Conversion of metal cleaning processes from trichloroethane solvents to non-ODS organic solvents at Ngai Cheong Metal Industries | Individual | ASP | MAL | SOL | 11 | INV | 18 | A | O | I | TCA | 2 | 2 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-11-01 |  | 1995-04-01 | 1998-12-01 | 63480 | 0 | 63480 | 63480 | 100% | 0 | 0 | 0 | 8252 | 0 | 8252 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Main Plant | Individual | ASP | MAL | SOL | 11 | INV | 19 | A | O | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-10-01 |  | 1994-05-01 | 1998-12-01 | 113570 | -2661 | 110909 | 110909 | 100% | 0 | 0 | 0 | 14764 | -346 | 14418 | 0 | 0 | Completed in 1994. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Port Klang Plant | Individual | ASP | MAL | SOL | 11 | INV | 20 | A | O | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-10-01 |  | 1995-04-01 | 1998-12-01 | 173280 | 25992 | 199272 | 199272 | 100% | 0 | 0 | 0 | 22526 | 3379 | 25905 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polysterene and polyethylene foam sheet at Associated Air-Pack Industries, Sdb. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 21 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 234000 | 17126 | 251126 | 251126 | 100% | 0 | 0 | 0 | 30420 | 2226 | 32646 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of polyurethane insulated panel at Cycle World Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 22 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-03-01 |  | 1997-06-01 | 2000-12-01 | 353000 | -1 | 352999 | 352999 | 100% | 0 | 0 | 0 | 45890 | 0 | 45890 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-12 in the manufacture of EPS/EPE foam sheet at Pulai Lamipak Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 23 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1994-12-01 |  | 1996-08-01 | 2002-03-01 | 355000 | -17066 | 337934 | 337934 | 100% | 0 | 0 | 0 | 46150 | -2219 | 43931 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin, spoiler and moulded flexible foam at P.U. Tech Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 24 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 198000 | 0 | 198000 | 198000 | 100% | 0 | 0 | 0 | 25740 | 0 | 25740 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin polyurethane foam at P.U. Mate Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 25 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 113000 | -9294 | 103706 | 103706 | 100% | 0 | 0 | 0 | 14690 | -1208 | 13482 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam at Pexafoam Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 26 | A | O | I | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 2003-09-01 | 195000 | -5077 | 189923 | 189923 | 100% | 0 | 0 | 0 | 25350 | -660 | 24690 | 0 | 0 | Completed in 1995. Financially completed in 2003. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at N.L.Y. Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 27 | A | O | I | CFC | 55 | 55 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 130000 | -14651 | 115349 | 115349 | 100% | 0 | 0 | 0 | 16900 | -1905 | 14995 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the integral circuit lead frame cleaning processes at San Matech Sdn. Bhd. | Individual | ASP | MAL | SOL | 12 | INV | 28 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-07-01 |  |  | 1995-07-01 | 141000 | -141000 | 0 | 0 |  | 0 | 0 | 0 | 18330 | -18330 | 0 | 0 | 0 | Canceled in 1995. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of home refrigerators at Sharp Roxy Appliance Corp. | Individual | ASP | MAL | REF | 12 | INV | 29 | A | O | D | CFC | 65 | 65 | 0 | 0 | 1994-03-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 962000 | -103353 | 858647 | 858647 | 100% | 0 | 0 | 0 | 125060 | -13436 | 111624 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Safety and technical programme to aid manufacturers of aerosol products | Individual | ASP | MAL | ARS | 12 | TAS | 30 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1996-03-01 |  | 1995-12-01 | 2001-12-01 | 145700 | -40377 | 105323 | 105323 | 100% | 0 | 0 | 0 | 18941 | -5249 | 13692 | 0 | 0 | Completed in 1995. Financially completed in 2001. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 12 | PRP | 31 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | MAL | SEV | 12 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 35815 | 12744 | 48559 | 48559 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase-out of the use of CFC in the manufacture of flexible polyurethane foam (slabstock) at small scale producers | Individual | ASP | MAL | FOA | 12 | INV | 33 | A | O | I | CFC | 80 | 80 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-03-01 |  | 1998-08-01 | 2000-12-01 | 1045000 | -55552 | 989448 | 989448 | 100% | 0 | 0 | 0 | 135850 | -7222 | 128628 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Up-date country programme | Individual | ASP | MAL | SEV | 12 | CPG | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program up-date is complete. Final document submitted to the Bank and the Government on 4/30/95. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of 111 TCA in the automobile bumper cleaning processes at Perusahaan Otomobil National Bhd. (Proton) | Individual | ASP | MAL | SOL | 12 | INV | 35 | A | O | I | TCA | 20 | 20 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1995-12-01 |  | 1995-04-01 | 1998-12-01 | 700439 | -59344 | 641095 | 641095 | 100% | 0 | 0 | 0 | 91057 | -7715 | 83342 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | MAL | SEV | 12 | PRP | 36 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 66610 | 2803 | 69413 | 69413 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at United Refrigerator Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 37 | A | O | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-12-01 | 2003-07-01 | 351200 | -11852 | 339348 | 339348 | 100% | 0 | 0 | 0 | 45656 | -1541 | 44115 | 0 | 0 | Completed in 1997. Financially completed in 2003. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane foam panels for cold storage at Wong Brothers Electrical and Refrigeration Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 38 | A | O | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1999-03-01 | 2001-12-01 | 299000 | -1 | 298999 | 298999 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-05-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Eversoft Foam Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 39 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1996-12-01 | 1998-12-01 | 185000 | -1 | 184999 | 184999 | 100% | 0 | 0 | 0 | 24050 | 0 | 24050 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Nian Aik Foam Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 40 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 245000 | -53100 | 191900 | 191900 | 100% | 0 | 0 | 0 | 31850 | -6903 | 24947 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid panels for commercial refrigerators at Pangkat Refrigeration Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 41 | A | O | I | CFC | 20 | 20 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 210000 | -6736 | 203264 | 203264 | 100% | 0 | 0 | 0 | 27300 | -876 | 26424 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of refrigeration products at Oyl Appliances | Individual | ASP | MAL | REF | 13 | INV | 42 | A | O | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-12-01 |  | 1997-12-01 | 2002-03-01 | 625100 | -38549 | 586551 | 586551 | 100% | 0 | 0 | 0 | 81263 | -5011 | 76252 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of polyurethane foam for pipe insulation at Allied Foam Insulation | Individual | ASP | MAL | FOA | 13 | INV | 43 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 276000 | -2955 | 273045 | 273045 | 100% | 0 | 0 | 0 | 35880 | -384 | 35496 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at Phoenix Base Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 44 | A | O | I | CFC | 61 | 61 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-06-01 |  | 1995-02-01 | 1998-12-01 | 165000 | 12784 | 177784 | 177784 | 100% | 0 | 0 | 0 | 21450 | 1662 | 23112 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at Lian Pang Refrigerator and Electrical Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 45 | A | O | I | CFC | 12.5 | 12.5 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-07-01 |  | 1998-10-01 | 2003-09-01 | 201100 | -1 | 201099 | 201099 | 100% | 0 | 0 | 0 | 26143 | 0 | 26143 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam for use as imitation wood at Saferay (M) SDN BHD | Individual | ASP | MAL | FOA | 15 | INV | 46 | A | O | I | CFC | 11 | 11 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1997-06-01 | 1998-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Completed in 1997. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of pipe insulation at Ricwil Sdn Bhd | Individual | ASP | MAL | FOA | 15 | INV | 47 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 118000 | -13464 | 104536 | 104536 | 100% | 0 | 0 | 0 | 15340 | -1750 | 13590 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of moulded and flexible PU foams at Dream Products Snd. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 48 | A | O | D | CFC | 15 | 15 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-11-01 |  | 1998-09-01 | 2000-07-01 | 66500 | -154 | 66346 | 66346 | 100% | 0 | 0 | 0 | 8645 | -20 | 8625 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels at Rigid Foam Industries, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 49 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1997-12-01 | 2000-07-01 | 335000 | -3198 | 331802 | 331802 | 100% | 0 | 0 | 0 | 43550 | -416 | 43134 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels and shipyard insulation works at Leading Refrigeration and Engineering, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 50 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 214000 | -13246 | 200754 | 200754 | 100% | 0 | 0 | 0 | 27820 | -1722 | 26098 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | IBRD | Substitution of CFC-12 and CFC-11 with HFC-134a and HCFC-141b respectively and elimination of the use of 1.1.1. TCA in household refrigerator manufacturing at Matsuchita Electric Co. (Melcom) | Individual | ASP | MAL | REF | 15 | INV | 51 | N | O | D |  | 99.73 | 99.73 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1997-12-01 |  | 1996-01-01 | 1997-08-01 | 1276500 | -4307 | 1272193 | 1272193 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. $5,096.82 will be returned. |  |  | 1996-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 15 | PRP | 52 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Conversion project at Argon Malaysia, Sdn. Bhd | Individual | ASP | MAL | ARS | 15 | INV | 53 | N | O | I | CFC | 38 | 38 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-12-01 |  | 1997-08-01 | 1997-08-01 | 131200 | 0 | 131200 | 131200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | Project preparation in the halon sector |  | ASP | MAL | HAL | 15 | PRP | 54 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-06-01 |  | 1995-06-01 | 1996-06-01 | 45000 | -28116 | 16884 | 16884 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | IBRD | Conversion of the aerosol filling plant Kontrak Manufacturing Services Sdn. Bhd. | Individual | ASP | MAL | ARS | 15 | INV | 55 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-12-01 |  | 1998-10-01 | 1998-11-01 | 618000 | 0 | 618000 | 618000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase out of the use of CFC in the manufacture of rigid PU panels at Shaga Cooling Technology | Individual | ASP | MAL | FOA | 15 | INV | 56 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1996-10-01 | 2000-12-01 | 190000 | -12498 | 177502 | 177502 | 100% | 0 | 0 | 0 | 24700 | -1625 | 23075 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | MAL | SEV | 16 | PRP | 57 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 206488 | 0 | 206488 | 206488 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation of subprojects which was initiated in 1994 is complete resulting in 11 proposals. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | MAL | SEV | 16 | PRP | 58 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 12258 | 0 | 12258 | 12258 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This budget is being utilized to supervise the MACs and halon Recover and Recycling projects approved for Malaysia in 1993. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS in the process of EPE/EPS foam sheet at Star Foam Paper Products Sdn. Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 59 | N | O | I | CFC | 66 | 66 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-07-01 |  | 2000-10-01 | 2002-03-01 | 295000 | -43111 | 251889 | 251889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Safety audit cannot be performed as enterprise out of business due to economic slowdown. Given this subproject was physically completed many years ago and the enterprise cannot recover its business, DOE and the Bank decided safety audit cannot be done and PCR should be sent to ExCom after receiving endorsement letter from the Government. |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to hydrocarbon technology in the manufacture of aerosol products at Maya Chemical Industries Sdn., Bhd. | Individual | ASP | MAL | ARS | 17 | INV | 60 | A | O | R | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 37808 | 0 | 37808 | 37808 | 100% | 0 | 0 | 0 | 4915 | 0 | 4915 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured PUF molded products at Urethane Technologies Sdn., Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 61 | A | O | D | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-07-01 |  | 1997-12-01 | 2000-12-01 | 199000 | -7010 | 191990 | 191990 | 100% | 0 | 0 | 0 | 25870 | -911 | 24959 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to non-ozone depleting organic solvents in Ban Seng Lee Industries Sdn. Bhd. | Individual | ASP | MAL | SOL | 17 | INV | 62 | N | O | D | TCA | 3.36 | 3.36 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1996-07-01 | 1996-09-01 | 108400 | 0 | 108400 | 108400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1996-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Tenco Industries Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 63 | N | O | D | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-11-01 |  | 1996-03-01 | 1997-03-01 | 79200 | 0 | 79200 | 79200 | 100% | 0 | 0 |  | 10296 | 0 | 10296 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Alloychem Malaysia Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 64 | A | O | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2001-12-01 | 2003-11-01 | 99500 | -13228 | 86272 | 86272 | 100% | 0 | 0 | 0 | 12935 | -1720 | 11215 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Artwright Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 65 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2002-03-01 | 90320 | 0 | 90320 | 90320 | 100% | 0 | 0 | 0 | 11742 | 0 | 11742 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured/integral skin PUF molded at Muda Murni Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 66 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2000-12-01 | 236500 | -52362 | 184138 | 184138 | 100% | 0 | 0 | 0 | 30745 | -6807 | 23938 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of molded/integral skin PUF at Bristol Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 67 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-02-01 | 2000-07-01 | 123400 | -475 | 122925 | 122925 | 100% | 0 | 0 | 0 | 16042 | -61 | 15981 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Sze Chuan Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 68 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | ASP | MAL | FOA | 18 | PRP | 69 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-02-01 |  | 1999-02-01 | 2000-07-01 | 40000 | -35 | 39965 | 39965 | 100% | 0 | 0 |  | 5200 | -13 | 5187 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at TM Cooling Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 70 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam decorative products at Florafoam Marketing Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 71 | A | O | D | CFC | 23 | 23 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1997-06-01 | 2000-12-01 | 152000 | -1 | 151999 | 151999 | 100% | 0 | 0 | 0 | 19760 | 0 | 19760 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Converson of production of portable fire extinguishers at Eversafe | Individual | ASP | MAL | HAL | 18 | INV | 72 | A | O | D | Halon | 574 | 574 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 2002-03-01 | 179586 | -4214 | 175372 | 175372 | 100% | 0 | 0 | 0 | 23346 | -548 | 22798 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | UNDP | Umbrella project for elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration at 4 small enterprises: Lim Yew, Exquisite, FMC, Noblelane | Individual | ASP | MAL | REF | 18 | INV | 73 | A | O | I | CFC | 44.8 | 44.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2001-12-01 | 2003-04-01 | 680000 | -49438 | 630562 | 630562 | 100% | 0 | 0 | 0 | 88400 | -6427 | 81973 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1997-10-01 | [10 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Sanyo Industries (Malaysia) Berhad | Individual | ASP | MAL | REF | 18 | INV | 74 | A | O | I | CFC | 13.4 | 13.4 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 183260 | -1 | 183259 | 183259 | 100% | 0 | 0 | 0 | 23824 | 0 | 23824 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | IBRD | Phase out of CFC-12 MAC system production equipment and conversion to HFC-134a MAC system manufacturing in Nippondenso Capital Sdn. Bhd. | Individual | ASP | MAL | REF | 18 | INV | 75 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-03-01 | 1999-11-01 |  | 1998-11-01 | 1998-12-01 | 2232718 | -420628.19 | 1812089.81 | 1812089.81 | 100% | 0 | 0 |  | 290253.34 | -30624.23 | 259629.11 | 0 | 0 | Project completed. Disbursement figure in 1999 and 2000 progress reports is incorrect. Additional balance to be returned to 37th ExCom. |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-12 MAC manufacturing equipment and conversion to HFC-134a MAC system manufacturing at APM Air Conditioners Sdn., Bhd. | Individual | ASP | MAL | REF | 18 | INV | 76 | N | O | I |  | 5 | 5 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1999-11-01 |  | 2001-12-01 | 2002-10-01 | 1181553 | -150254.79 | 1031298.21 | 1031298.21 | 100% | 0 | 0 |  | 153601.89 | -19533.15 | 134068.74 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Balance to be returned at the 39th ExCom. |  |  | 1997-12-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Reduction of the consumption of ODSs in the commercial air-conditioning sector via training, recovery and recycling of CFC-11 and CFC-12 in chillers at Mashrae | Individual | ASP | MAL | REF | 18 | TAS | 77 | N | O | I | CFC | 105 | 4.45 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1996-11-01 |  | 2000-11-01 | 2002-10-01 | 824078 | -118061 | 706017 | 706017 | 100% | 0 | 0 |  | 107130.14 | -15347.93 | 91782.21 | 0 | 0 | Final PCR not submitted to ExCom as DOE and the Bank requested MASHRAE and CETEC to revise PCR to ensure that information accurately reflects the actual nature of this project including lessons learned. Actual ODP phaseout low because many chiller owners decided to replace the CFC unit with the new non-CFC unit instead of using the facility. |  |  | 1997-12-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | France | Phasing out the use of CFC-113 in the electronics industry through the technical promotion of no clean processes |  | ASP | MAL | SOL | 18 | INV | 78 | A | O | D |  | 0 |  | 0 |  | 1995-11-01 |  | 1996-11-01 |  |  | 1997-11-01 | 226600 | -226600 | 0 | 0 |  | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet annulé
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at AE Technology Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 79 | N | O | R | TCA | 17 | 16.8 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1995-08-01 | 1996-09-01 | 56893 | 0 | 56893 | 56893.2 | 100% | -0.4 | -0.4 |  | 7396.09 | 0 | 7396.11 | -0.02 | -0.02 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Mondial Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 80 | N | O | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 2001-03-01 | 144447 | -144447 | 0 | 0 |  | 0 | 0 |  | 18778.11 | -18778.11 | 0 | 0 | 0 | Project cancelled. |  |  | 1997-07-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Widetech | Individual | ASP | MAL | SOL | 18 | INV | 81 | N | O | I | TCA | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-09-01 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 398418 | 0 | 398418 | 398418 | 100% | 0 | 0 |  | 51794.34 | 0 | 51794.34 | 0 | 0 | Project completed. |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at Eng Teknologi Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 82 | N | O | I | TCA | 3.4 | 3.36 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-11-01 |  | 1998-09-01 | 1999-02-01 | 117379 | 0 | 117379 | 117378.6 | 100% | 0.4 | 0.4 |  | 15259.27 | 0 | 15259.21 | 0.06 | 0.06 | Project completed. |  |  | 1997-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 18 | PRP | 83 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 18000 | -4 | 17996 | 17996 | 100% | 0 | 0 | 0 | 2340 | -1 | 2339 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 18 | PRP | 84 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
COM | UNDP | Umbrella project to phase out ODS at SMEs in the aerosol sector | Individual | ASP | MAL | ARS | 19 | INV | 85 | A | O | I | CFC | 250 | 250 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1998-04-01 |  | 2005-12-01 |  | 1486660 | 0 | 1486660 | 1315527 | 88.49% | 171133 | 0 | 136906.4 | 193266 | 0 | 171018.687 | 22247.313 | 0 | Completed in 2005. |  |  |  | 1999-07-01 |  | 2001-12-01 | [7 empty] | 1996 | Investment
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane refrigerator panels at Penang Trading Co. | Individual | ASP | MAL | FOA | 19 | INV | 86 | N | O | I | CFC | 10.5 | 10.5 | 0 | 0 | 1996-05-01 | 2000-02-01 | 2000-05-01 |  | 2001-12-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents since Nov. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank in 02. The Bank is waiting for certificate of destruction from DOE before issuing an approval letter |  |  | 1997-05-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufactue of polyurethane cold-room insulation panels/truck container panels at Kejuruteraan Transfreeze Sdn Bhd | Individual | ASP | MAL | FOA | 19 | INV | 87 | N | O | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 2000-02-01 | 1997-05-01 |  | 2001-11-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phrase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents as of Dec. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank Mar. 02. These both projects has two funding parts that are ICC and contingency. |  |  | 1997-05-01 | 1999-06-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology for the manufacture of flexible polyurethane foam at Nite Beauty Industries | Individual | ASP | MAL | FOA | 19 | INV | 88 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-06-01 | 1999-12-01 | 36875 | 0 | 36875 | 36875 | 100% | 0 | 0 | 0 | 4794 | 0 | 4794 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC -free technology for the manufacture of flexible polyurethane foam at Far East Foam Industries | Individual | ASP | MAL | FOA | 19 | INV | 89 | A | O | I | CFC | 41.2 | 41.2 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-09-01 | 2001-12-01 | 209000 | -2275 | 206725 | 206725 | 100% | 0 | 0 | 0 | 27170 | -296 | 26874 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | IBRD | Phase-out of CFC-12 MAC manufacturing equipment and conversion of HFC-134a MAC manufacturing equipment at UCM Industrial Corporation Berhad | Individual | ASP | MAL | REF | 19 | INV | 90 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-05-01 | 2000-05-01 |  | 2000-08-01 | 2002-10-01 | 1468797 | -263251 | 1205546 | 1205546 | 100% | 0 | 0 |  | 190943.61 | -34222.63 | 156720.98 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Savings to be returned at the 39th ExCom. |  |  | 1997-12-01 |  | 2000-03-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 20 | INS | 91 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-10-01 |  | 1998-10-01 | 2003-04-01 | 215000 | -5523 | 209477 | 209477 | 100% | 0 | 0 | 0 | 27950 | -718 | 27232 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1996 | Non-Investment
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 21 | PRP | 92 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0 | Completed. |  |  |  | 1999-06-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | MAL | SEV | 21 | PRP | 93 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2004-12-01 | 100000 | -34365 | 65635 | 65635 | 100% | 0 | 0 | 0 | 13000 | -4467 | 8533 | 0 | 0 | Completed in 1998. Financially Completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Amstrad | Individual | ASP | MAL | FOA | 22 | INV | 94 | A | O | I | CFC | 13.9 | 13.9 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 108800 | -86 | 108714 | 108714 | 100% | 0 | 0 | 0 | 14144 | -11 | 14133 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-06-01 | [9 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Anchor Profit Sdn Bhd | Individual | ASP | MAL | FOA | 22 | INV | 95 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 | 0 | 17030 | 0 | 17030 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Rollbond | Individual | ASP | MAL | FOA | 22 | INV | 96 | A | O | I | CFC | 22.2 | 22.2 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 155500 | 0 | 155500 | 155500 | 100% | 0 | 0 | 0 | 20215 | 0 | 20215 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | France | No clean process improvement training for electronic assemblers who phased out the use of CFC-113 |  | ASP | MAL | SOL | 22 | TRA | 97 | A | O | D |  | 0 |  | 0 |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-04-01 | 1999-04-01 | 192423 | 25462 | 217885 | 217885 | 100% | 0 |  |  | 0 | 1500 | 1500 | 0 |  | Projet achevé. PCR soumis
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at RCA Group | Individual | ASP | MAL | FOA | 22 | INV | 98 | A | O | I | CFC | 41.9 | 41.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2000-12-01 | 284500 | -12922 | 271578 | 271578 | 100% | 0 | 0 | 0 | 36985 | -1680 | 35305 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CT Foam | Individual | ASP | MAL | FOA | 23 | INV | 99 | A | O | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 236000 | 0 | 236000 | 236000 | 100% | 0 | 0 | 0 | 30680 | 0 | 30680 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNIDO | Phasing out ODS at Summer Technologies Sdn. Bhd. | Individual | ASP | MAL | FOA | 23 | INV | 100 | A | O | I | CFC | 12.1 | 12.1 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 89407 | 0 | 89407 | 89407 | 100% | 0 | 0 |  | 11623 | 0 | 11623 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Kean Chong Industries Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 101 | A | O | I | CFC | 16.3 | 16.3 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-11-23 | 107819 | 0 | 107819 | 107819 | 100% | 0 | 0 |  | 14016 | 0 | 14016 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Visdamax Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 102 | A | O | I | CFC | 18.5 | 18.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 139959 | 0 | 139959 | 139959 | 100% | 0 | 0 |  | 18195 | 0 | 18195 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufature of polyurethane foam at Kwang Tai Refrigeration | Individual | ASP | MAL | REF | 23 | INV | 103 | A | O | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-04-01 | 316000 | -9988 | 306012 | 306012 | 100% | 0 | 0 | 0 | 41080 | -1298 | 39782 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free techology in the manufacture of polyurethane foam at Hi Tech Insulation | Individual | ASP | MAL | FOA | 23 | INV | 104 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2002-03-01 | 96815 | -3942 | 92873 | 92873 | 100% | 0 | 0 | 0 | 12586 | -512 | 12074 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Heng Huat Furniture | Individual | ASP | MAL | FOA | 23 | INV | 105 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 269500 | 0 | 269500 | 269500 | 100% | 0 | 0 | 0 | 35035 | 0 | 35035 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Frank Chee | Individual | ASP | MAL | FOA | 23 | INV | 106 | A | O | I | CFC | 28 | 28 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 174350 | 0 | 174350 | 174350 | 100% | 0 | 0 | 0 | 22666 | 0 | 22666 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at OAL Enterprise | Individual | ASP | MAL | FOA | 23 | INV | 107 | A | O | I | CFC | 7.4 | 7.4 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 58300 | -19611 | 38689 | 38689 | 100% | 0 | 0 | 0 | 7579 | -2549 | 5030 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 24 | PRP | 108 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project (timber) | Individual | ASP | MAL | FUM | 24 | PRP | 109 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-11-01 | 2004-12-01 | 30000 | -983 | 29017 | 29017 | 100% | 0 | 0 | 0 | 3900 | -128 | 3772 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNIDO | Preparation of investment projects in the foam sector (rigid polyurethane) for Chon Son, Ngui Soon, Ming Soon, Yon Tuck | Individual | ASP | MAL | FOA | 24 | PRP | 110 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 20000 | -205 | 19795 | 19795 | 100% | 0 | 0 |  | 2600 | -31 | 2569 | 0 | 0 | FIN
FIN | UNDP | Conversion to LCD technology in the manufacture of polyurethane foam at Tenaga | Individual | ASP | MAL | FOA | 25 | INV | 111 | A | O | I | CFC | 23 | 23 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 308800 | 0 | 308800 | 308800 | 100% | 0 | 0 | 0 | 40144 | 0 | 40144 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the insulation of GRP fish boxes and flotation buoys at C.C. Chong Co. | Individual | ASP | MAL | FOA | 26 | INV | 112 | A | O | I | CFC | 4.5 | 4.5 |  |  | 1998-11-01 | 1999-03-01 | 2000-06-01 |  | 2000-05-01 | 2001-09-01 | 34583 | 0 | 34583 | 34583 | 100% | 0 | 0 |  | 4496 | -1 | 4495 | 0 | 0 | FIN
FIN | UNIDO | The replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Ming Soon Enterprise Sdn. Bhd. | Individual | ASP | MAL | FOA | 26 | INV | 113 | A | O | I | CFC | 6.2 | 6.23 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-02-01 | 2002-09-01 | 48799 | 0 | 48799 | 48799 | 100% | 0 | 0 |  | 6344 | -8 | 6336 | 0 | 0 | FIN
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | MAL | SEV | 26 | INS | 114 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-05-01 | 215000 | -36884 | 178116 | 178116 | 100% | 0 | 0 | 0 | 27950 | -4795 | 23155 | 0 | 0 | Completed in 2000. Financially completed in 2005. | [13 empty] | 1998 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Minply | Individual | ASP | MAL | FOA | 26 | INV | 115 | A | O | I | CFC | 16.5 | 16.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 158050 | -3297 | 154753 | 154753 | 100% | 0 | 0 | 0 | 20547 | -429 | 20118 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Grorich | Individual | ASP | MAL | FOA | 26 | INV | 116 | A | O | I | CFC | 32.9 | 32.9 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 174150 | 0 | 174150 | 174150 | 100% | 0 | 0 | 0 | 22640 | 0 | 22640 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Preparation of two projects in commercial refrigeration subsector | Individual | ASP | MAL | REF | 27 | PRP | 117 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | UNIDO | Preparation of three investment projects in the foam sector (rigid polyrethane) | Individual | ASP | MAL | FOA | 27 | PRP | 118 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 25000 | -47 | 24953 | 24953 | 100% | 0 | 0 |  | 3250 | -11 | 3239 | 0 | 0 | FIN
FIN | UNDP | Preparation of three projects in rigid foam subsector | Individual | ASP | MAL | FOA | 27 | PRP | 119 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Yong Tuck Refrigerators Trading Co. | Individual | ASP | MAL | FOA | 27 | INV | 120 | A | O | I | CFC | 8 | 8 |  |  | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2000-06-01 | 2001-09-01 | 61735 | -643 | 61092 | 61092 | 100% | 0 | 0 |  | 8026 | -97 | 7929 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 in the manufacture of cold room panels and insulation slabs by conversion to HCFC-141b at PKL Insulation | Individual | ASP | MAL | FOA | 28 | INV | 121 | A | O | I | CFC | 8.1 | 8.1 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-12-01 | 2003-07-01 | 57019 | -1434 | 55585 | 55585 | 100% | 0 | 0 | 0 | 7412 | -186 | 7226 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and blocks) at Polyedge Trading | Individual | ASP | MAL | FOA | 28 | INV | 122 | A | O | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2002-02-01 |  | 2000-12-01 | 2001-12-01 | 80650 | 0 | 80650 | 80650 | 100% | 0 | 0 | 0 | 10485 | 0 | 10485 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | UNDP | Retroactive project for phasing-out ODS consumption in the manufacture of cold room panels by conversion to HCFC-141b at FMCP Sdn. Bhd. | Individual | ASP | MAL | FOA | 28 | INV | 123 | A | O | R | CFC | 12.2 | 12.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-07-01 | 2001-12-01 | 45557 | 0 | 45557 | 45557 | 100% | 0 | 0 | 0 | 5922 | 0 | 5922 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phase out CFC-11 consumption by conversion to HCFC-141b AT Perniagaan Hower in the manufacture of sandwich panels | Individual | ASP | MAL | FOA | 28 | INV | 124 | A | O | I | CFC | 5.3 | 5.3 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 41499 | -87 | 41412 | 41412 | 100% | 0 | 0 |  | 5395 | -20 | 5375 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology at Automated Plastic System Sdn. Bhd. in the manufacture of insulated fishing boxes | Individual | ASP | MAL | FOA | 28 | INV | 125 | A | O | I | CFC | 5.2 | 5.2 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-01-01 | 2001-12-01 | 40716 | 0 | 40716 | 40716 | 100% | 0 | 0 |  | 5293 | 0 | 5293 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 and R502 consumption at Thermo Cooling Engineering, Sdn. Bhd. | Individual | ASP | MAL | REF | 28 | INV | 126 | A | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 46502 | -1900 | 44602 | 44602 | 100% | 0 | 0 | 0 | 6045 | -247 | 5798 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phase out CFC-11 consumption at Chong Brother Group of Companies | Individual | ASP | MAL | FOA | 28 | INV | 127 | A | O | I | CFC | 27.6 | 27.6 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 216108 | 0 | 216108 | 216108 | 100% | 0 | 0 |  | 28094 | -21 | 28073 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 and CFC-12 and R-502 in the manufacture of commercial refrigerators by conversion HCFC-141b, HCFC-22 and HFC-404a at Gai Hin Refrigeration Sdn. Bhd. | Individual | ASP | MAL | REF | 29 | INV | 128 | A | O | I | CFC | 41 | 41 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 354147 | -16712 | 337435 | 337435 | 100% | 0 | 0 | 0 | 46039 | -2173 | 43866 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
COM | UNDP | Alternatives to the use of methyl bromide on Malaysian timbers | Individual | ASP | MAL | FUM | 29 | DEM | 129 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2006-07-01 |  | 230000 | 0 | 230000 | 221922 | 96.49% | 8078 | 0 | 6462.4 | 29900 | 0 | 28849.86 | 1050.14 | 0 | Completed in 2006. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Masterfoam Products | Individual | ASP | MAL | FOA | 29 | INV | 130 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 208900 | 0 | 208900 | 208900 | 100% | 0 | 0 | 0 | 27157 | 0 | 27157 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible polyurethane foam at Kemas Mekar Sdn Bhd | Individual | ASP | MAL | FOA | 29 | INV | 131 | A | O | I | CFC | 23.3 | 23.3 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 385900 | -11270 | 374630 | 374630 | 100% | 0 | 0 | 0 | 50167 | -1465 | 48702 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | IBRD | Project preparation for MACs and compressors project category |  | ASP | MAL | REF | 30 | PRP | 132 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 30 | PRP | 133 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -9678 | 20322 | 20322 | 100% | 0 | 0 | 0 | 3900 | -1258 | 2642 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | MAL | REF | 30 | PRP | 134 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 20000 | -4121 | 15879 | 15879 | 100% | 0 | 0 | 0 | 2600 | -537 | 2063 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | IBRD | Preparation of projects in the solvent sector and a national CFC phase out programme |  | ASP | MAL | SEV | 27 | PRP | 135 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0 | Ongoing | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam and to LCD technology in the manufacture of flexible molded foam at Sy Heng Huat | Individual | ASP | MAL | FOA | 31 | INV | 136 | A | O | I | CFC | 46.2 | 46.2 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-01-01 | 2003-11-01 | 272235 | 0 | 272235 | 272235 | 100% | 0 | 0 | 0 | 35391 | 0 | 35391 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to LCD and water-based technology in the manufacture of flexible molded foam at Unique Field | Individual | ASP | MAL | FOA | 31 | INV | 137 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 109990 | 0 | 109990 | 109990 | 100% | 0 | 0 | 0 | 14299 | 0 | 14299 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible molded foam at Pointray | Individual | ASP | MAL | FOA | 31 | INV | 138 | A | O | I | CFC | 24.3 | 24.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 130896 | -27 | 130869 | 130869 | 100% | 0 | 0 | 0 | 17016 | -4 | 17012 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNIDO | Preparation of three investment projects in the rigid foam sector | Individual | ASP | MAL | FOA | 31 | PRP | 139 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2001-07-01 |  | 2002-01-01 | 2003-05-01 | 20000 | -740 | 19260 | 19260 | 100% | 0 | 0 |  | 2600 | -100 | 2500 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at eleven small and sedium-sized enterprises | Individual | ASP | MAL | REF | 32 | INV | 140 | A | O | I | CFC | 64.8 | 64.8 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 960658 | -29788 | 930870 | 930870 | 100% | 0 | 0 | 0 | 115672 | -3276 | 112396 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at three enterprises (SKE Fookmei, Master Shanghai Turnparts and Maltar Industries) | Individual | ASP | MAL | REF | 32 | INV | 141 | A | O | I | CFC | 34.9 | 34.9 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-11-01 | 2005-09-01 | 505184 | -12891 | 492293 | 492293 | 100% | 0 | 0 | 0 | 65570 | -1418 | 64152 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
COM | UNDP | Extension of the institutional strengthening project (Phase IV) | Individual | ASP | MAL | SEV | 32 | INS | 142 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2005-03-01 |  | 215000 | 0 | 215000 | 204006 | 94.89% | 10994 | 0 | 8795.2 | 27950 | 0 | 26520.78 | 1429.22 | 0 | Completed in 2005. | [13 empty] | 2000 | Non-Investment
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Composites Truck Body Sdn., Bhd. | Individual | ASP | MAL | FOA | 34 | INV | 143 | A | O | I | CFC | 8.1 | 8.1 |  |  | 2001-07-01 | 2002-12-01 | 2004-02-01 |  | 2003-12-01 | 2003-12-01 | 63280 | -129 | 63151 | 63151 | 100% | 0 | 0 |  | 8226 | -29 | 8197 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigerating equipment at Tung Kiong Factories Sdn. Bhd. | Individual | ASP | MAL | REF | 32 | INV | 143 | A | O | I | CFC | 18.9 | 18.9 |  |  | 2000-12-01 | 2001-10-01 | 2003-07-01 |  | 2003-03-01 | 2004-05-01 | 202075 | -503 | 201572 | 201572 | 100% | 0 | 0 |  | 26270 | -107 | 26163 | 0 | 0 | FIN
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC 134a in the manufacturing of MAC system at Sanden International (M) Sdn., Bhd. | Individual | ASP | MAL | REF | 34 | INV | 144 | N | O | R | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-02-01 | 2003-01-01 |  | 2002-08-01 | 2003-02-01 | 807280 | -15079 | 792201 | 792201 | 100% | 0 | 0 |  | 48440 | -904.74 | 47535.26 | 0 | 0 | Project fully completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | MAL | PHA | 35 | INV | 145 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 1799940 | 0 | 1799940 | 1799940 | 100% | 0 | 0 | 0 | 140395 | 0 | 140395 | 0 | 0 | 2002 phaseout targets achieved. Implementation of project activities under this tranche completed since Dec 03. A balance of $403,729 from MAC investment project will be reallocated to MAC sector in 2007. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation in the soil fumigant sector | Individual | ASP | MAL | FUM | 36 | PRP | 146 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-11-01 | 10000 | -947 | 9053 | 9053 | 100% | 0 | 0 | 0 | 1300 | -123 | 1177 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
COM | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | MAL | PHA | 37 | INV | 147 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-12-01 | 2003-08-01 |  | 2003-08-01 |  | 2969065 | 0 | 2969065 | 2969065 | 100% | 0 | 0 | 0 | 259216 | 0 | 259216 | 0 | 0 | 3,827 technicians from 3,480 certified MAC service workshops trained and registered. Additional training conducted for the 169 R&R machines provided. Financial subsidy of MAC tools will be delivered by Apr 09. Train-the trainer program for ten Public Authorized Training Centers completed. For RSS sector, 1,221 technicians from 969 workshops trained and certified. As of Dec 08, a total of 506 vouchers of basic tools and 101 vouchers of R&R machines distributed. It is expected that investment part of the program will be completed by mid-2009. | [13 empty] | 2002 | INV | 1910.5 | 1671.4 | 0 | 0 | Yes | Yes | Yes
COM | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 38 | INS | 148 | N | T | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 |  | 279500 | 0 | 279500 | 262367 | 93.87% | 17133 | 0 | 13706.4 | 36335 | 0 | 34107.71 | 2227.29 | 0 | Completed in 2005. | [13 empty] | 2002 | Non-Investment
COM | IBRD | National CFC phase-out plan: 2003 annual work programme | Multiyear | ASP | MAL | PHA | 40 | INV | 149 | N | O | I | CFC | 292 | 292 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-12-01 |  | 2013100 | 0 | 2013100 | 2013100 | 100% | 0 | 0 | 0 | 169179 | 0 | 169179 | 0 | 0 | 3,827 technicians from 3,480 certified MAC service workshops trained and registered. Additional training conducted for the 169 R&R machines provided. Financial subsidy of MAC tools will be delivered by Apr 09. Train-the trainer program for ten Public Authorized Training Centers completed. For RSS sector, 1,221 technicians from 969 workshops trained and certified. As of Dec 08, a total of 506 vouchers of basic tools and 101 vouchers of R&R machines distributed. It is expected that investment part of the program will be completed by mid-2009. | [13 empty] | 2003 | INV | 1618.5 | 1471.9 | 0 | 0 | Yes | Yes | Yes
FIN | UNDP | Project preparation for the formulation of fumigant methyl bromide | Individual | ASP | MAL | FUM | 42 | PRP | 150 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-01-01 | 2006-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
ONG | UNDP | Technical assistance programme to install alternatives and phase-out all remaining non-QPS uses of methyl bromide | Individual | ASP | MAL | FUM | 43 | TAS | 151 | N | O | I | MeBr | 8.7 | 4 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2007-12-01 | 2010-12-01 |  |  | 200000 | 0 | 200000 | 91103 | 45.55% | 108897 | 0 | 21779.4 | 18000 | 0 | 8199.27 | 9800.73 | 0 | In 2008, work continued on moving this project forward. There were a number of taskforce meetings. Additionally the consultant for the project demonstration on soil and post harvest treatment was selected and the detailed protocol for treatments for both soil and post harvest treatment is 80% completed. The final trials did not occur in 2008 as planned and have been rescheduled to 2009. | [13 empty] | 2004 | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | MAL | SEV | 44 | INS | 153 | N | T | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2008-07-01 |  | 279500 | 0 | 279500 | 279500 | 100% | 0 | 0 | 0 | 20963 | 0 | 20963 | 0 | 0 | Completed in 2008. Implementation of activities for the year 2008 included activities related to awareness raising; Hiring of 5 enforcement officers - contracting done UNDP and publishing a knowledge product on Ozone for local and international consumption in collaboration with UNDP. Phase 7 of the IS-programme took over these activities (see below). | [13 empty] | 2004 | Non-Investment
COM | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | MAL | PHA | 44 | INV | 154 | N | O | I | CFC | 430 | 430 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 |  | 1688300 | 0 | 1688300 | 1688300 | 100% | 0 | 0 | 0 | 143947 | 0 | 143947 | 0 | 0 | 3,827 technicians from 3,480 certified MAC service workshops trained and registered. Additional training conducted for the 169 R&R machines provided. Financial subsidy of MAC tools will be delivered by Apr 09. Train-the trainer program for ten Public Authorized Training Centers completed. For RSS sector, 1,221 technicians from 969 workshops trained and certified. As of Dec 08, a total of 506 vouchers of basic tools and 101 vouchers of R&R machines distributed. It is expected that investment part of the program will be completed by mid-2009. | [13 empty] | 2004 | INV | 1188.5 | 1139.9 | 0 | 0 | Yes | Yes | Yes
COM | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | MAL | SEV | 45 | TAS | 155 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 |  | 91743 | 0 | 91743 | 78048 | 85.07% | 13695 | 0 | 10956 | 8257 | 0 | 7024.4306 | 1232.5694 | 0 | Completed in 2008. Final invoices pertaining to survey settled. | [13 empty] | 2005 | Non-Investment
COM | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | MAL | PHA | 47 | INV | 156 | N | O | I | CFC | 470.8 | 470.8 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2008-12-01 |  | 1208300 | 0 | 1208300 | 1208300 | 100% | 0 | 0 | 0 | 100747 | 0 | 100747 | 0 | 0 | 3,827 technicians from 3,480 certified MAC service workshops trained and registered. Additional training conducted for the 169 R&R machines provided. Financial subsidy of MAC tools will be delivered by Apr 09. Train-the trainer program for ten Public Authorized Training Centers completed. For RSS sector, 1,221 technicians from 969 workshops trained and certified. As of Dec 08, a total of 506 vouchers of basic tools and 101 vouchers of R&R machines distributed. It is expected that investment part of the program will be completed by mid-2009. | [13 empty] | 2005 | INV | 717.7 | 671.6 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | MAL | PHA | 49 | INV | 157 | N | O | I | CFC | 120 | 120 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 | 2009-12-01 |  |  | 1013300 | 0 | 1013300 | 212253.97 | 20.95% | 801046.03 | 801046.03 | 801046.03 | 83197 | 0 | 17427.11 | 65769.89 | 65769.89 | 3,827 technicians from 3,480 certified MAC service workshops trained and registered. Additional training conducted for the 169 R&R machines provided. Financial subsidy of MAC tools will be delivered by Apr 09. Train-the trainer program for ten Public Authorized Training Centers completed. For RSS sector, 1,221 technicians from 969 workshops trained and certified. As of Dec 08, a total of 506 vouchers of basic tools and 101 vouchers of R&R machines distributed. It is expected that investment part of the program will be completed by mid-2009. | [13 empty] | 2006 | INV | 597.7 | 535.3 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | MAL | PHA | 52 | INV | 158 | N | O | I | CFC | 88.3 | 88.3 | 0 | 0 | 2007-07-01 |  | 2008-07-31 | 2009-12-01 |  |  | 275000 | 0 | 275000 | 0 | 0% | 275000 | 275000 | 275000 | 24750 | 0 | 0 | 24750 | 24750 | 3,827 technicians from 3,480 certified MAC service workshops trained and registered. Additional training conducted for the 169 R&R machines provided. Financial subsidy of MAC tools will be delivered by Apr 09. Train-the trainer program for ten Public Authorized Training Centers completed. For RSS sector, 1,221 technicians from 969 workshops trained and certified. As of Dec 08, a total of 506 vouchers of basic tools and 101 vouchers of R&R machines distributed. It is expected that investment part of the program will be completed by mid-2009. | [13 empty] | 2007 | INV | 508.7 | 287.4 | 0 | 0 | Yes | Yes | No
ONG | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | MAL | SEV | 53 | INS | 159 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 | 2010-01-01 |  |  | 279500 | 0 | 279500 | 146489 | 52.41% | 133011 | 0 | 26602.2 | 20963 | 0 | 10986.9371 | 9976.0629 | 0 | RSS and MAC workshops were carried out. Publication and awareness-raising materials were extensively produced and distributed. Trainings for end-users on recycling and CFC recovery were conducted. Training workshops with Malaysia Royal Customs were carried out, emphasizing on control on importation of ODS and usage, prevention of illegal trade and also the use of Refrigerant Identifier at custom entry point. Seminars on phasing-out CFC based MDI's were carried out in collaboration with National Pharmaceutical Control Bureau. Seminars on HCFC were conducted to raise awareness among the industries. An inception workshop was organized to kick-start the preparation of the HPMP. | [13 empty] | 2007 | Non-Investment
ONG | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | MAL | PHA | 55 | INV | 160 | N | O | I | CFC | 89 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 275000 | 0 | 275000 | 0 | 0% | 275000 | 275000 | 275000 | 24750 | 0 | 0 | 24750 | 24750 | 3,827 technicians from 3,480 certified MAC service workshops trained and registered. Additional training conducted for the 169 R&R machines provided. Financial subsidy of MAC tools will be delivered by Apr 09. Train-the trainer program for ten Public Authorized Training Centers completed. For RSS sector, 1,221 technicians from 969 workshops trained and certified. As of Dec 08, a total of 506 vouchers of basic tools and 101 vouchers of R&R machines distributed. It is expected that investment part of the program will be completed by mid-2009. | [13 empty] | 2007 | INV | 419.7 | 0 | 0 | 0 |  | No | No
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | MAL | PHA | 55 | PRP | 161 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 173750 | 0 | 173750 | 0 | 0% | 173750 | 0 | 173750 | 13031 | 0 | 0 | 13031 | 0 | TOR and prodoc finalized. HPMP inception workshop held in December 2008. Recruitment of national expert entities is in progress. | [13 empty] | 2008 | Investment
FIN | UNEP | Complement for country programme preparation | Individual | AFR | MAR | SEV | 9 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-06-01 |  | 1993-06-01 | 1993-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ozone depleting substances | Individual | AFR | MAR | SEV | 10 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-08-01 | 1996-06-01 |  | 2004-12-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1993 | Non Investment
FIN | UNDP | Aerosol conversion at Compagnie Manufacturiere de Produits Cosmetiques Ltee. | Individual | AFR | MAR | ARS | 12 | INV | 3 | A | O | D | CFC | 25 | 25 | 0 | 0 | 1994-03-01 | 1996-06-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 62150 | 0 | 62150 | 62150 | 100% | 0 | 0 | 0 | 8080 | 0 | 8080 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Preparation of projects in the refrigeration and foam sectors | Individual | AFR | MAR | REF | 12 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Blyfridge Ltd. | Individual | AFR | MAR | REF | 15 | INV | 5 | A | O | I | CFC | 2 | 2 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 197208 | -20442 | 176766 | 176766 | 100% | 0 | 0 | 0 | 25637 | -2658 | 22979 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at A.H. Bahemia | Individual | AFR | MAR | REF | 15 | INV | 6 | A | O | I | CFC | 2.7 | 2.7 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 213500 | -25495 | 188005 | 188005 | 100% | 0 | 0 | 0 | 27755 | -3314 | 24441 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
TRF | UNDP | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | RMP-Component | AFR | MAR | REF | 17 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1996-07-01 |  |  | 1999-07-01 | 176350 | -162281 | 14069 | 14069 | 100% | 0 | 0 | 0 | 22926 | -21096 | 1830 | 0 | 0 | Transferred in 1999. Financially completed in 1999. |  |  |  | 1999-07-01 | [9 empty] | 1995 | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MAR | REF | 23 | PRP | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1998-03-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1998
FIN | Germany | Project preparation and technical assistance at Chem Tech | Individual | AFR | MAR | ARS | 26 | PRP | 9 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2001-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MAR | REF | 26 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted TPMP approved at 41st Excom | [13 empty] | 1999
FIN | Germany | Investment project for phasing out CFCs at Chem Tech-Stella Industries, Port Louis | Individual | AFR | MAR | ARS | 27 | INV | 11 | A | O | I | CFC | 16 | 16 | 0 | 0 | 1999-03-01 | 1999-03-01 | 1999-11-01 |  | 2001-06-01 | 2002-01-01 | 90400 | 0 | 90400 | 90400 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | Funds to be offset against future german approvals |  |  |  | 2000-12-01 | [8 empty] | 2000
FIN | Germany | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | Individual | AFR | MAR | REF | 28 | TAS | 12 | A | O | I | CFC | 8 | 5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-06-01 |  | 2005-12-01 | 2006-09-01 | 183377 | -3647 | 179730 | 179730.3 | 100% | -0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Certification of R&R center. Follow-up evaluation of the performance of recycling center. Recommendation that the training institue should cooperate with the local gas dealer in utilizing the facility. PCR was submitted in 2006.
FIN | Germany | Project preparation for the phase out of methyl bromide use | Individual | AFR | MAR | FUM | 37 | PRP | 13 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2002-10-01 | 2003-12-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 | 0 | 0 | 1430 | 0 | 1430 | 0 | 0 | A project proposal was prepared but not accepted by the beneficiary. Assistance of beneficiary will now be unter the TPMP approved at 41st ExCom. | [13 empty] | 1997
FIN | Germany | Project preparation for a CFC terminal phase out management plan | Individual | AFR | MAR | REF | 37 | PRP | 14 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. TPMP approved at 41st Excom
FIN | Germany | Implementation of an ODS terminal phase out management plan (first tranche) | Multi-Year | AFR | MAR | PHA | 41 | INV | 15 | A | O | I | CFC | 0 | 2.6 | 0 |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-10-05 | 2006-04-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | 2 Hydrocarbon trainings have been conducted. NOU started the process of converting the New Court House through a subsidy scheme provided under the project. Next tranche has been approved. | [13 empty] | 2002 |  | 4 | 4 |  |  | Yes
FIN | Germany | Implementation of an ODS terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAR | PHA | 45 | INV | 16 | A | O | I | CFC | 2 | 2 | 0 |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2007-12-01 | 2008-04-01 | 62030 | 0 | 62030 | 62030 | 100% | 0 | 0 | 0 | 8064 | 0 | 8064 | 0 | 0 | 2nd tranche was approved. | [15 empty] | 2 | 0 |  |  | Yes
COM | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | MAR | SEV | 45 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-04-01 |  | 2007-11-01 |  | 60000 | 0 | 60000 | 24025.87 | 40.04% | 35974.13 | 35987 | 35974.13 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2005 | Non Investment
ONG | Germany | Implementation of an ODS terminal phase-out management plan (third tranche) | Multi-Year | AFR | MAR | PHA | 50 | INV | 18 | A | O | I | CFC | 2 | 2 | 0 |  | 2006-11-01 | 2007-03-01 | 2007-12-01 | 2009-08-01 |  |  | 40000 | 0 | 40000 | 34000 | 85% | 6000 | 0 | 6000 | 5200 | 0 | 4420 | 780 | 0 | Due to the amendment of the MP to phase out HCFCs, the chiller conversion was stalled. However the buildings are now being converted to NH3 and the funds will be utlised for engineering requirements at these buildings. | [15 empty] | 0 | 0 |  |  | Yes
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MAR | SEV | 53 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | MOU for implementation agreed with the country. First payment awaiting for the country to submit reports for the previous IS phase | [13 empty] | 2007 | Non Investment
ONG | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | MAR | PHA | 55 | PRP | 20 | A | O | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 | 2009-12-01 |  |  | 75000 | 0 | 75000 | 2100 | 2.8% | 72900 | 0 | 72900 | 9750 | 0 | 273 | 9477 | 0 | HCFC survey is being planned. However progress has been slow. Planning stage has involved developing a questionnaire. Discussions also involved on who the NOU should hire for the survey with the final decision form the govt to use NOU staff to conduct the survey. Now that this is done, the survey is to start in May 2009.
FIN | UNEP | Country programme preparation | Individual | ASP | MAS | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 5200 | -3250 | 1950 | 0 | 0 | Project financially completed. | $ 25,000 plus $ 3,250 PSC returned ExCom 46 |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | MAS | REF | 36 | TAS | 2 | A | O | I |  | 0.8 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 |  | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 0 | 3380 | 3380 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | MAS | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-08-01 |  | 34000 | 0 | 34000 | 33178 | 97.58% | 822 | 0 | 822 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2002 | Non Investment
COM | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | MAS | REF | 36 | TAS | 4 | A | O | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 |  | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 0 | 1040 | 1040 | MAS regulations established. Customs training workshop held April 2005. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | MAS | SEV | 50 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2008-11-01 |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008. UNEP is discussing the closure of the Regional Strategy and has requested SPREP to disburse all remaining IS funding to the country. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | ASP | MAS | SEV | 53 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008. First disbursement will start after country receive final payment of previous IS phase from SPREP. | [13 empty] | 2007 | Non Investment
FIN | UNEP | Country programme preparation | Individual | EUR | MAT | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-06-01 |  | 1995-07-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | France | Country programme preparation |  | AFR | MAU | SEV | 13 | CPG | 1 | A | O | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-07-01 | 1995-07-01 |  | 1995-07-01 | 1995-09-01 | 44000 | -2580 | 41420 | 39771 | 96.02% | 1649 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Balance returned at 57th ExCom.
FIN | France | Institutional strengthening project proposal |  | AFR | MAU | SEV | 14 | INS | 2 | A | T | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 1999-12-01 | 1999-12-01 | 38874 | -12891 | 25983 | 25983 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Training and awareness of personnel involved in the task of codifying and identifying ODS and ODS-containing material |  | AFR | MAU | SEV | 14 | TRA | 3 | A | O | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-10-01 | 1995-09-01 |  | 1996-11-01 | 1996-12-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | La formation a eu lieu du 02 au 04 novembre 1996. Project completed.
FIN | France | Training of refrigeration technicians |  | AFR | MAU | REF | 14 | TRA | 4 | A | O | D |  | 0 |  | 0 |  | 1994-09-01 | 1997-07-01 | 1995-09-01 |  | 1999-06-01 | 1999-08-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 1997-05-01
FIN | France | Conversion of CFC-based commercial refrigeration installations in the fishing industry |  | AFR | MAU | REF | 14 | TAS | 5 | A | O | D | CFC | 2 |  | 0 |  | 1994-09-01 | 1999-07-01 | 1996-09-01 |  | 2000-11-01 | 2000-12-01 | 106900 | -7378 | 99522 | 99521.8666 | 100% | 0.13336 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  |  |  | 2000-06-01
COM | UNEP | Development of an RMP | Individual | AFR | MAU | REF | 33 | PRP | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2003-12-01 |  | 2003-12-01 |  | 60000 | 0 | 60000 | 21919.4 | 36.53% | 38080.6 | 0 | 38080.6 | 7800 | 0 | 2849.522 | 4950.478 | 0 | Project completed | [13 empty] | 2001 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | MAU | SEV | 33 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2004-01-01 | 2003-04-01 |  | 2004-01-01 | 2007-01-01 | 25900 | 0 | 25900 | 25900 | 100% | 0 | 0 | 0 | 3367 | -7 | 3367 | -7 | 0 | Project financially completed. | $ 0 plus $ 7 PSC returned to ExCom 49 | [12 empty] | 2001 | Non Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | MAU | REF | 39 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
FIN | UNEP | Implementation of the RMP: training programme for customs excise | Individual | AFR | MAU | REF | 41 | TRA | 9 | A | O | I | CFC | 1.6 | 1.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2007-12-01 | 2008-12-01 | 39800 | 0 | 39800 | 38731 | 97.31% | 1069 | 0 | 0 | 5174 | 0 | 5035.03 | 138.97 | 0 | Project financially completed. Balance to be returned to ExCom 57 | [13 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians | Individual | AFR | MAU | REF | 41 | TRA | 10 | A | O | I | CFC | 2.6 | 2.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2005-07-01 |  | 2007-12-01 |  | 65000 | 0 | 65000 | 29660.03 | 45.63% | 35339.97 | 20000 | 35339.97 | 8450 | 0 | 3855.8039 | 4594.1961 | 2600 | Project completed | [13 empty] | 2003 | Non Investment
COM | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | MAU | REF | 41 | TAS | 11 | N | O | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 |  | 100995 | 0 | 100995 | 100299 | 99.31% | 696 | 0 | 556.8 | 9090 | 0 | 9027.3569 | 62.6431 | 0 | Completed in 2007. | [13 empty] | 2003 | Investment
COM | UNDP | Implementation of the RMP: awareness and incentive programme for MAC, commercial and industrial end-users | RMP-Component | AFR | MAU | REF | 41 | TAS | 12 | N | O | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Completed in 2007. | [13 empty] | 2003 | Non-Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | MAU | REF | 41 | TAS | 13 | A | O | I | CFC | 1.2 | 1.2 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | 0 | 30000 | 29166 | 97.22% | 834 | 0 | 0 | 3900 | 0 | 3791.58 | 108.42 | 0 | Project financially completed. Balances to be returned to ExCom 57 | [13 empty] | 2003 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MAU | SEV | 43 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 33670 | 0 | 33670 | 33670 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MAU | PHA | 48 | PRP | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2006 | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAU | PHA | 48 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | AFR | MAU | SEV | 49 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2008-06-30 | 2009-12-30 |  |  | 60000 | 0 | 60000 | 44626.44 | 74.38% | 15373.56 | 961.59 | 15373.56 | 0 | 0 | 0 | 0 | 0 | Second payment done in October 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MAU | PHA | 53 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 96000 | 0 | 96000 | 63893.37 | 66.56% | 32106.63 | 27000 | 32106.63 | 12480 | 0 | 8306.1381 | 4173.8619 | 3510 | Training activities started in November 2008 | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MAU | PHA | 53 | INV | 19 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 34000 | 7650 | 0 | 0 | 7650 | 0 | Consultant mission organized in 2008. International bidding process to close on 15 February 09 and it is expected that equipment purchased could arrive in country by mid-2009. Second consultant mission has been requested and will be timed to coincide with official inauguration of the 2 excellence centers identified (Nouakchott and Nouadhibou). Contracts with these have already been signed and are set up to start as soon as equipment arrives. Charges will be reflected in 2009. Second tranche to be approved at 57th ExCom. | [13 empty] | 2007 | Investment | 3 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MAU | PHA | 55 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for signature | [13 empty] | 2008
FIN | UNIDO | Preparation of a Country Programme | Individual | EUR | MDN | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-08-01 | 1995-12-01 |  | 1996-12-01 | 1998-08-01 | 80000 | -7780 | 72220 | 72220 | 100% | 0 | 0 |  | 10400 | -1026 | 9374 | 0 | 0 | FIN
FIN | UNIDO | Preparation of projects in the refrigeration, aerosol and foam sector | Individual | EUR | MDN | SEV | 18 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-01-01 | 1996-03-01 |  | 2000-12-01 | 2002-05-01 | 30000 | -3675 | 26325 | 26325 | 100% | 0 | 0 |  | 3900 | -483 | 3417 | 0 | 0 | FIN |  |  | 1997-07-01 | 1999-02-01
FIN | UNIDO | Phasing out of CFCs at the refrigerator plant of Frinko | Individual | EUR | MDN | REF | 20 | INV | 3 | A | O | I | CFC | 104 | 104 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1998-12-01 | 2001-12-01 | 1081724 | -556 | 1081168 | 1081168 | 100% | 0 | 0 |  | 140624 | -295 | 140329 | 0 | 0 | FIN
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | MDN | SEV | 20 | INS | 4 | N | T | I |  | 0 | 0 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-08-01 | 2001-07-01 | 152900 | 0 | 152900 | 152900 | 100% | 0 | 0 |  | 19877 | -25 | 19852 | 0 | 0 | FIN |  |  | 1999-10-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 5 | A | O | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2002-09-01 | 520125 | -4895 | 515230 | 515230 | 100% | 0 | 0 |  | 67616 | -742 | 66874 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from manufacturing of rigid PU sandwich panels at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 6 | A | O | I | CFC | 67.6 | 67.6 |  |  | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1997-12-01 | 2002-05-01 | 284236 | -6661 | 277575 | 277575 | 100% | 0 | 0 |  | 36951 | -923 | 36028 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | EUR | MDN | REF | 24 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 30000 | -4462 | 25538 | 25538 | 100% | 0 | 0 |  | 3900 | -585 | 3315 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in methyl bromide (tobacco, pepper, tomatoes) | Individual | EUR | MDN | FUM | 25 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - three alternatives to the use of methyl bromide: non-soil cultivation, biofumigation and low dose chemicals in tobacco and horticultural production | Individual | EUR | MDN | FUM | 26 | DEM | 9 | A | O | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-04-01 | 2003-05-01 | 259600 | -558 | 259042 | 259042 | 100% | 0 | 0 |  | 33748 | -126 | 33622 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | MDN | REF | 28 | TAS | 10 | A | O | I | CFC | 13.5 | 13.5 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2002-02-01 | 2003-12-01 | 220044 | -43661 | 176383 | 176383 | 100% | 0 | 0 |  | 28606 | -5713 | 22893 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | MDN | REF | 28 | TRA | 11 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-06-01 |  | 2002-03-01 | 2003-05-01 | 70000 | -6146 | 63854 | 63854 | 100% | 0 | 0 |  | 9100 | -812 | 8288 | 0 | 0 | FIN
FIN | UNIDO | Institutional strengthening for Montreal Protocol related activities, Phase II | Individual | EUR | MDN | SEV | 30 | INS | 12 | N | T | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 101950 | 0 | 101950 | 101950 | 100% | 0 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | EUR | MDN | ARS | 30 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2001-07-01 | 15000 | -2425 | 12575 | 12575 | 100% | 0 | 0 |  | 1950 | -318 | 1632 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | MDN | FUM | 30 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -499 | 19501 | 19501 | 100% | 0 | 0 |  | 2600 | -69 | 2531 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers | RMP | EUR | MDN | REF | 28 | TRA | 15 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-03-01 |  | 2002-03-01 | 2003-05-01 | 37180 | -6973 | 30207 | 30207 | 100% | 0 | 0 |  | 4833 | -912 | 3921 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in tobacco seedling and horticulture production sector | Individual | EUR | MDN | FUM | 32 | INV | 16 | A | O | I | MBR | 27.2 | 27.2 |  |  | 2000-12-01 | 2001-10-01 | 2006-01-01 |  | 2004-12-01 | 2006-05-01 | 1075207 | -3327 | 1071880 | 1071880 | 100% | 0 | 0 |  | 128273 | -553 | 127720 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of CFC 11/12 in the manufacture of aerosols by conversion to HFC and hydrocarbon propellants at Alkaloid A.D. | Individual | EUR | MDN | ARS | 32 | INV | 17 | A | O | I | CFC | 25 | 25 |  |  | 2000-12-01 | 2001-12-01 |  |  |  |  | 110000 | 0 | 110000 | 99467 | 90.42% | 10533 | 0 | 1 | 14300 | 0 | 12931 | 1369 | 0 | Although the project was cancelled, the ODP phase out of 25.0 tonnes achieved. Financial completion in Dec 2008.
FIN | UNIDO | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MDN | SEV | 35 | INS | 18 | N | T | I |  | 0 | 0 |  |  | 2001-12-01 | 2002-08-01 | 2004-01-01 |  | 2004-07-01 | 2005-09-01 | 101950 | 0 | 101950 | 101950 | 100% | 0 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Technical assistance in preparation of the national halon management plan | Individual | EUR | MDN | HAL | 37 | TAS | 19 | A | O | I | HAL | 32.1 | 32.1 |  |  | 2002-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-05-01 | 2004-02-01 | 25000 | -8 | 24992 | 24992 | 100% | 0 | 0 |  | 3250 | -6 | 3244 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project: phase IV | Individual | EUR | MDN | SEV | 42 | INS | 20 | N | T | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-05-01 | 132347 | 0 | 132347 | 132347 | 100% | 0 | 0 |  | 9926 | 0 | 9926 | 0 | 0 | FIN | [13 empty] | 2004 | NON-INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | MDN | PHA | 45 | INV | 21 | A | O | I | CFC | 10 | 10 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-11-01 | 2007-12-01 | 154210 | -134 | 154076 | 154076 | 100% | 0 | 0 |  | 11566 | -10 | 11556 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | INV | 25 | 11.83 |  |  | Yes | N/A | N/A
COM | UNIDO | Extension of the institutional strengthening project (phase V) | Individual | EUR | MDN | SEV | 48 | INS | 22 | N | T | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2008-04-01 |  | 2008-12-01 |  | 132347 | 0 | 132347 | 115619 | 87.36% | 16728 | 6096 | 16000 | 9926 | 0 | 8671 | 1255 | 457 | Project completed in Dec 2008. | [13 empty] | 2006 | NON-INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | EUR | MDN | PHA | 50 | INV | 23 | A | O | I | CFC | 5 | 5 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-11-01 | 2008-07-01 | 79871 | -123 | 79748 | 79748 | 100% | 0 | 0 |  | 5990 | -9 | 5981 | 0 | 0 | Financial completion in Jul 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2006 | INV | 15 | 6.98 |  |  | Yes | N/A | N/A
COM | UNIDO | Terminal phase-out management plan for CFCs (third tranche) | Multi-Year | EUR | MDN | PHA | 53 | INV | 24 | A | O | I | CFC | 5 | 5 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 |  | 2008-11-01 |  | 15000 | 0 | 15000 | 8813 | 58.75% | 6187 | 360 | 6000 | 1125 | 0 | 661 | 464 | 27 | Project completed in Nov 2008. | [13 empty] | 2007 | INV | 10 | 10 |  |  | Yes | N/A | N/A
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MDN | PHA | 55 | PRP | 25 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-08-01 |  |  | 85000 | 0 | 85000 | 6256 | 7.36% | 78744 | 36266 | 7000 | 6375 | 0 | 469 | 5906 | 2720 | Contract on HPMP preparation has been awarded. | All components of the HPMP preparation are covered under the sub-contract including work on legislation. | [12 empty] | 2008 | NON-INV
ONG | UNIDO | Terminal phase-out management plan for CFCs (fourth tranche) | Multi-Year | EUR | MDN | PHA | 56 | INV | 26 | A | O | I | CFC | 5 | 0 |  |  | 2008-11-01 |  | 2009-11-30 | 2009-11-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 13000 | 1125 | 0 | 0 | 1125 | 0 | Monitoring and reporting activities on the import control and utilization of R&R equipment and operation of R&R centers and training centers are progressing according to NOU schedules. New contract to be signed in the first Q of 2009. | [13 empty] | 2008 | INV | 5 | 0 |  |  | Yes | N/A | N/A
FIN | UNEP | Country programme preparation | Individual | ASP | MDV | SEV | 4 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -5500 | 19500 | 19500 | 100% | 0 | 0 | 0 | 3250 | -715 | 2535 | 0 | 0 | Project financially completed. | $ 5,500 plus $ 715 PSC returned ExCom 41 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | MDV | SEV | 12 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1997-03-01 |  | 2002-05-01 | 2005-12-01 | 41250 | 0 | 41250 | 41250 | 100% | 0 | 0 | 0 | 5362.5 | 0 | 5362.5 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non Investment
FIN | UNEP | Development of RMP | RMP | ASP | MDV | REF | 30 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-04-01 |  | 2002-09-01 | 2003-09-01 | 30000 | -1849 | 28151 | 28151 | 100% | 0 | 0 | 0 | 3900 | -240.37 | 3659.63 | 0 | 0 | Project financially completed. | $ 1,849 plus $ 240 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | MDV | SEV | 37 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2004-08-01 |  | 2004-10-01 | 2005-12-01 | 35753 | 0 | 35753 | 35753 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
ONG | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | MDV | REF | 38 | TAS | 5 | A | O | I | CFC | 2.3 | 1 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-05-01 | 2010-12-01 |  |  | 115000 | 0 | 115000 | 26644 | 23.17% | 88356 | 0 | 17671.2 | 14950 | 0 | 3463.72 | 11486.28 | 0 | Constant changes in the NOU in 2008 prevented signature of contracts with end-users. It is expected this will be resolved in 2009 | [13 empty] | 2002 | Non-Investment
COM | UNEP | Implementation of the RMP: monitoring and review | Individual | ASP | MDV | REF | 38 | TAS | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-08-01 |  | 15000 | 0 | 15000 | 1043.73 | 6.958% | 13956.27 | 0 | 13956.27 | 1950 | 0 | 135.6849 | 1814.3151 | 0 | Project completed | [13 empty] | 2002 | Non Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MDV | REF | 38 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-07-01 | 2008-12-01 | 35000 | 0 | 35000 | 33000 | 94.29% | 2000 | 0 | 0 | 4550 | 0 | 4290 | 260 | 0 | Project financially completed. Balances to be returned to ExCom 57 | [13 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: training of customs officials and the Ozone Unit staff | Individual | ASP | MDV | REF | 38 | TRA | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2005-05-01 |  | 2005-11-01 |  | 35000 | 0 | 35000 | 28612 | 81.75% | 6388 | 0 | 6388 | 4550 | 0 | 3719.56 | 830.44 | 0 | Project completed | [13 empty] | 2002 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | MDV | SEV | 44 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2005-11-01 | 2007-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | MDV | SEV | 50 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008. Several Stakeholder meetings have been conducted throughout the year 2008. - Meeting conducted regarding banning of import of CFCs, Halons, Methyl Bromide and Bromochloromethane in January 2008. No CFCs have been imported to the Maldives from the year 2008. Stakeholder workshop regarding phase out of CFC based MDIs was held in March 2008. A new National Ozone Committee was established in 2008 to coordinate all activities under the Montreal Protocol. Several public awareness activities, including workshops, development and distribution of awareness materials were carried out throughout the year 2008. An “Ozone Awareness Stamp set” was released on the occasion of the International Ozone Day 2008. An Ozone Resource Corner was opened in the library of Environment Research Centre /National Ozone Unit. UNEP DTIE’s Publication “the Ozone Story” was translated and released to the general public on the Ozone Day 2008. Children’s evening: A children evening was held in Male, including colorful and informative activities and games for children. Several Television and Radio programs were also conducted in 2008. These included TV quiz programs asking questions related to ozone, Broadcasting an English and Dhivehi song regarding ozone through TV and radio stations, Interviews, News reports, and Programs for public questions and answers. | [13 empty] | 2006 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | MDV | PHA | 50 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-11-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | MDV | PHA | 50 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 |  | 15000 | 0 | 15000 | 6560 | 43.73% | 8440 | 0 | 8440 | 1125 | 0 | 492 | 633 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | MDV | PHA | 53 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 | 2009-03-01 |  |  | 80000 | 0 | 80000 | 79999.53 | 100% | 0.47 | 0 | 0.47 | 10400 | 0 | 10399.9389 | 0.0611 | 0 | Several Stakeholder meetings have been conducted throughout the year 2008. This includes the meetings conducted regarding banning of import of CFCs, Halons, Methyl Bromide and Bromochloromethane in January 2008. Stakeholder workshop regarding phase out of CFC based MDIs was held in March 2008. This workshop was conducted with the technical assistance of UNEP ROAP, National Asthma Council of Australia and Sri Lanka. 5 units of refrigerant identifiers were procured by UNEP and received by the Maldivian Government in 2008. Several public awareness activities, including workshops, development and distribution of awareness materials were carried out throughout the year 2008. Activities under the TPMP were regularly monitored by the NOU staff with assistance of Maldives Customs through a licensing system. Ban of CFCs and other gases have been implemented and fully monitored since January 2008. There have been no reports of illegal trade. In addition other regulations that have been put in place in the previous years have also been monitored and enforced. These include ban of vehicles older than 5 years, ban of CFC based equipment, Quota order for ODS use, requiring end-users to obtain approval of the National Ozone Cell to procure ODS. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | MDV | PHA | 53 | INV | 15 | N | O | I | CFC | 0.7 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 17000 | 7650 | 0 | 0 | 7650 | 0 | No Progress in 2008 due to non signature of the ProDoc by the Government. UNDP followed up with the country office to try to resolve this issue, but there was constant changes in the NOU which made this task difficult. | [13 empty] | 2007 | Investment | 0.7 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | MDV | PHA | 55 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-31 | 2010-12-31 |  |  | 85000 | 0 | 85000 | 63000 | 74.12% | 22000 | 0 | 22000 | 11050 | 0 | 8190 | 2860 | 0 | Project newly approved in the 55th ExCom.Country's agreement in process. Issue on transfer of funds still remain. | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | MDV | SEV | 56 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project in November 2008. The agreement with the country was signed in December 2008. | [13 empty] | 2008
FIN | IBRD | Country programme preparation | Individual | LAC | MEX | SEV | 04 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 36061 | 26194 | 62255 | 62255 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | MEX | SEV | 04 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 68164 | 35178 | 103342 | 103342 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of terms of reference for investment projects identified in the country programme | Individual | LAC | MEX | SEV | 04 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1993-12-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 2277 | 52277 | 52277 | 100% | 0 | 0 | 0 | 6500 | 296 | 6796 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1991 | Investment
FIN | IBRD | Safety programme in aerosol plant and recycling training and demonstration project in MAC | Individual | LAC | MEX | MUS | 04 | TRA | 4 | N | O | I | CFC | 0 | 36 | 0 | 0 | 1991-06-01 | 1996-02-01 | 1992-11-01 |  | 1996-04-01 | 1996-04-01 | 180000 | -126208 | 53792 | 53792 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-05-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of projects identified in the country programme | Individual | LAC | MEX | MUS | 05 | INV | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1996-11-01 |  | 1996-12-01 | 1997-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Demonstration programme in CFC recovery and recycling of the Instituto Mexicano del Seguro Social (IMSS) refrigeration equipment | Individual | LAC | MEX | REF | 05 | DEM | 6 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-12-01 | 1992-11-01 |  | 1996-12-01 | 1996-12-01 | 499918 | 0 | 499918 | 499918 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Training of Quimobasicos personnel in the use of CFC recovery and recycling equipment | Individual | LAC | MEX | REF | 05 | TRA | 7 | N | O | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1992-11-01 |  |  | 1996-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. |  |  | 1996-12-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recovery and recycling of refrigeration equipment in Monterrey City (Climas Jiménez) | Individual | LAC | MEX | REF | 05 | TAS | 8 | N | O | I | CFC | 4 | 0.3 | 0 | 0 | 1991-11-01 | 1995-10-01 | 1992-11-01 |  | 1994-06-01 | 1995-12-01 | 29328 | 0 | 29328 | 29328 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 with HFC-134a refrigerant in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | REF | 05 | INV | 9 | N | O | I | CFC | 13 | 13 | 0 | 0 | 1991-11-01 | 1995-08-01 | 1992-11-01 |  | 1995-12-01 | 1995-12-01 | 211543 | 0 | 211543 | 211543 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b foam blowing in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 10 | N | O | I | CFC | 25 | 25 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-09-01 | 494500 | 0 | 494500 | 494500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-113 used as a cleaning agent in the manufacturing of optical frames at Styloptic, S.A. | Individual | LAC | MEX | SOL | 05 | INV | 11 | N | O | I | CFC | 3.2 | 0.72 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-06-01 | 79299 | 0 | 79299 | 79299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery, reclaim and recycling of CFC-113 and methylchloroform through Química Omega S.A. plant | Individual | LAC | MEX | SOL | 05 | INV | 12 | N | O | I |  | 183.3 | 183.3 | 0 | 0 | 1991-11-01 | 1995-02-01 | 1992-11-01 |  | 1995-11-01 | 1995-11-01 | 295302 | 0 | 295302 | 295302 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-11-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recovery and recycling programme through Quimobasicos, S.A. | Individual | LAC | MEX | REF | 05 | TAS | 13 | N | O | I | CFC | 140 | 260 | 0 | 0 | 1991-11-01 | 1994-10-01 | 1992-11-01 |  | 1994-07-01 | 1994-12-01 | 222540 | 0 | 222540 | 222540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The annual rate of ODS phaseout has been determined and has exceeded phaseout expectations, resulting in a phase out of 260 tons of CFC phaseout. Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparatory study on halons, inventory, and proposals for revisions of existing standards | Individual | LAC | MEX | HAL | 06 | TAS | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1994-04-01 |  | 1995-09-01 | 1998-12-01 | 25000 | 2223 | 27223 | 27223 | 100% | 0 | 0 | 0 | 3250 | 289 | 3539 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | MEX | SEV | 06 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 292076 | -223980 | 68096 | 68096 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $60,082 and expenditure of $8,014 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $68,096 and entry for country program removed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Institutional strengthening |  | LAC | MEX | SEV | 07 | INS | 16 | A | T | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 285000 | 65000 | 350000 | 350000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. US $65,000 against 1994 contributions (15th meeting)
FIN | USA | Support for country programme preparation and development of project proposals |  | LAC | MEX | SEV | 07 | PRP | 17 | A | O | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-06-01 | 145000 | 136000 | 281000 | 281000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $136,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Assistance to country programme and investment projects preparation |  | LAC | MEX | SEV | 08 | CPG | 18 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Chiller hands-on training |  | LAC | MEX | REF | 08 | TRA | 19 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 81000 | 259000 | 340000 | 340000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $259,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Mexican solvents programme to reduce CFC-113 and methyl chloroform |  | LAC | MEX | SOL | 08 | TRA | 20 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 360000 | 138000 | 498000 | 498000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $138,000 credited against 1993 contributions (11th Meeting).
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | MEX | SEV | 09 | PRP | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123400 | -65386 | 58014 | 58014 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 11 | PRP | 22 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | IBRD | Supervision of project implementation (1994) |  | LAC | MEX | SEV | 12 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -35085 | 64915 | 64915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | MEX | SEV | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 52286 | -44858 | 7428 | 7428 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Bank is evaluating its activities in the country. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | USA | Cancun chiller workshop |  | LAC | MEX | REF | 13 | TRA | 25 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Pilot sectoral study and action plan in commercial refrigeration |  | LAC | MEX | REF | 13 | TAS | 26 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 410000 | -139742 | 270258 | 270258 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Demonstration project in MAC |  | LAC | MEX | REF | 13 | DEM | 27 | A | O | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Project preparation |  | LAC | MEX | SOL | 13 | PRP | 28 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 450000 | -119143 | 330857 | 330857 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 14 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-12-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Ensambladora de Refrigeradores (Enresa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 30 | A | O | I | CFC | 47 | 47 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 867033 | -51481 | 815552 | 815552 | 100% | 0 | 0 | 0 | 112714 | -6693 | 106021 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Astral (Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 31 | A | O | I | CFC | 344 | 344 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 2439932 | -80899 | 2359033 | 2359033 | 100% | 0 | 0 | 0 | 317191 | -10517 | 306674 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at (Comasa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 32 | A | O | D | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-12-01 |  | 1995-11-01 | 1998-12-01 | 1188724 | -152860 | 1035864 | 1035864 | 100% | 0 | 0 | 0 | 154534 | -19872 | 134662 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
CLO | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at Fabricacion de Compresores S.A. (Facosa, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 33 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-06-01 |  |  | 1996-05-01 | 584000 | -581001 | 2999 | 2999 | 100% | 0 | 0 | 0 | 75920 | -75530 | 390 | 0 | 0 | Canceled in 1996. Financially completed in 1996. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Supermatic, S.A. (Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 34 | A | O | I | CFC | 366 | 366 | 0 | 0 | 1994-12-01 | 1996-03-01 | 1996-06-01 |  | 1997-04-01 | 2000-12-01 | 2017517 | -5120 | 2012397 | 2012397 | 100% | 0 | 0 | 0 | 262277 | -666 | 261611 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Estufas y Refrigeradores Nacionales S.A. (Erna, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 35 | A | O | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-09-01 | 2000-12-01 | 1038309 | -49630 | 988679 | 988679 | 100% | 0 | 0 | 0 | 134980 | -6452 | 128528 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of 1,1,1 TCA from the precision cleaning processes at Lucas Diesel | Individual | LAC | MEX | SOL | 15 | INV | 36 | A | O | D | TCA | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-06-01 |  | 1997-07-01 | 1999-12-01 | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 21840 | 0 | 21840 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-113 from the textile cleaning processes at Procesadora y Revitalizadora | Individual | LAC | MEX | SOL | 15 | INV | 37 | A | O | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-09-01 |  | 1996-08-01 | 2000-12-01 | 71337 | -1889 | 69448 | 69448 | 100% | 0 | 0 | 0 | 9274 | -246 | 9028 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | MEX | SEV | 16 | PRP | 38 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 71744 | 0 | 71744 | 71744 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 17 | PRP | 39 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1996-11-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Extension of institutional strengthening | Individual | LAC | MEX | SEV | 17 | INS | 40 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-12-01 |  | 1996-10-01 | 2003-11-01 | 47500 | 47500 | 95000 | 95000 | 100% | 0 | 0 | 0 | 6175 | 6175 | 12350 | 0 | 0 | Completed in 1996. Financially completed in 2003. | [13 empty] | 1995 | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Paneles | Individual | LAC | MEX | FOA | 18 | INV | 41 | A | O | I | CFC | 81 | 81 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1997-08-01 | 2000-12-01 | 100000 | -5098 | 94902 | 94902 | 100% | 0 | 0 | 0 | 13000 | -663 | 12337 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels at Galvamet, S.A. de C.V. | Individual | LAC | MEX | FOA | 18 | INV | 42 | A | O | D | CFC | 88.7 | 88.7 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1996-04-01 | 1998-12-01 | 195500 | -6004 | 189496 | 189496 | 100% | 0 | 0 | 0 | 25415 | -781 | 24634 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Recovery of CFC-12 servicing of domestic refrigeration at Vitromatic Comercial y Servicios Integrados | RMP-Component | LAC | MEX | REF | 18 | TAS | 43 | N | O | I | CFC | 76 | 76 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1997-10-01 | 2002-12-01 | 352610 | -47579 | 305031 | 305031 | 100% | 0 | 0 | 0 | 45839 | -6185 | 39654 | 0 | 0 | Completed in 1997. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | UNIDO | Preparation of investment projects | Individual | LAC | MEX | SEV | 18 | PRP | 44 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-08-01 |  | 1997-09-01 | 2000-07-01 | 50000 | -477 | 49523 | 49523 | 100% | 0 | 0 |  | 6500 | -72 | 6428 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 18 | PRP | 45 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels and doors at Multypanel | Individual | LAC | MEX | FOA | 19 | INV | 46 | A | O | I | CFC | 306 | 306 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-08-01 | 2001-12-01 | 428000 | -85789 | 342211 | 342211 | 100% | 0 | 0 | 0 | 55640 | -11153 | 44487 | 0 | 0 | Completed in 1997. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) - Group project (10 enterprises) | Individual | LAC | MEX | FOA | 19 | INV | 47 | A | O | I | CFC | 100 | 100 | 0 | 0 | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1998-11-01 | 2001-08-01 | 507500 | -43764 | 463736 | 463736 | 100% | 0 | 0 | 0 | 65975 | -5689 | 60286 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Carmovil | Individual | LAC | MEX | FOA | 20 | INV | 48 | A | O | I | CFC | 14.6 | 14.6 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 80500 | -1092 | 79408 | 79408 | 100% | 0 | 0 | 0 | 10465 | -142 | 10323 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Umbrella project for conversion to CFC-free technology in the manufacture of polyurethane shoe soles (seven enterprises) | Individual | LAC | MEX | FOA | 20 | INV | 49 | A | O | I | CFC | 95 | 95 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 2001-08-01 | 2003-04-01 | 1201590 | -3434 | 1198156 | 1198156 | 100% | 0 | 0 | 0 | 156207 | -446 | 155761 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1996 | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODSs under the Montreal Protocol | Individual | LAC | MEX | SEV | 20 | INS | 50 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-10-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1996 | Non-Investment
FIN | IBRD | Project preparation |  | LAC | MEX | SEV | 21 | PRP | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation in the foam and solvent sectors | Individual | LAC | MEX | SEV | 21 | PRP | 52 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 52000 | -2539 | 49461 | 49461 | 100% | 0 | 0 | 0 | 6760 | -330 | 6430 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | LAC | MEX | SEV | 22 | PRP | 53 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Acsa | Individual | LAC | MEX | FOA | 22 | INV | 54 | A | O | I | CFC | 94.4 | 94.4 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 597000 | -1890 | 595110 | 595110 | 100% | 0 | 0 | 0 | 77610 | -245 | 77365 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Industrias Pol-Rym S.A. de C.V., (IPR) | Individual | LAC | MEX | FOA | 22 | INV | 55 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1998-11-01 |  | 1998-11-01 | 2001-12-01 | 421500 | -4909 | 416591 | 416591 | 100% | 0 | 0 | 0 | 54795 | -638 | 54157 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Tecnopolimeros | Individual | LAC | MEX | FOA | 22 | INV | 56 | A | O | I | CFC | 54.4 | 54.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2002-11-01 | 359000 | -1642 | 357358 | 357358 | 100% | 0 | 0 | 0 | 46670 | -213 | 46457 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-06-01 | [9 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Termopuertos | Individual | LAC | MEX | FOA | 22 | INV | 57 | A | O | D | CFC | 10 | 10 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-07-01 | 2000-12-01 | 78300 | -2557 | 75743 | 75743 | 100% | 0 | 0 | 0 | 10179 | -332 | 9847 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | LAC | MEX | FUM | 22 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-07-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | MEX | SEV | 22 | TAS | 59 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1998-05-01 |  | 1998-05-01 | 2001-12-01 | 60000 | -1400 | 58600 | 58600 | 100% | 0 | 0 | 0 | 7800 | -182 | 7618 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1997 | Non-Investment
FIN | IBRD | CFC-11 phase out at Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 60 | N | O | I | CFC | 15.6 | 13 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-12-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Gigante 1 | Individual | LAC | MEX | REF | 05 | INV | 61 | N | O | I | CFC | 38 | 5 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1997-09-01 | 1997-09-01 | 496380 | 0 | 496380 | 496380 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Aurrera 1 | Individual | LAC | MEX | REF | 05 | INV | 62 | N | O | I | CFC | 44 | 22.2 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Gigante 2 | Individual | LAC | MEX | REF | 05 | INV | 63 | N | O | I | CFC | 18 | 0 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1997-06-01 |  | 1998-10-01 | 1998-10-01 | 278070 | 0 | 278070 | 278070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Chedraui stores | Individual | LAC | MEX | REF | 05 | INV | 64 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1996-08-01 | 1996-08-01 | 228120 | 0 | 228120 | 228120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Aurrera 2 | Individual | LAC | MEX | REF | 05 | INV | 65 | N | O | I | CFC | 22 | 11.8 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technolog in the manufacture of rigid foam at Valsa Panel | Individual | LAC | MEX | FOA | 23 | INV | 66 | A | O | D | CFC | 24 | 24 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1998-07-01 | 2000-12-01 | 92000 | -312 | 91688 | 91688 | 100% | 0 | 0 | 0 | 11960 | -41 | 11919 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNIDO | Phasing out of CFCs at Criotec S.A. | Individual | LAC | MEX | REF | 23 | INV | 67 | A | O | R | CFC | 16 | 16 |  |  | 1997-11-01 | 1998-09-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 240794 | 0 | 240794 | 240794 | 100% | 0 | 0 |  | 31303 | 0 | 31303 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Torrey S.A. | Individual | LAC | MEX | REF | 23 | INV | 68 | A | O | I | CFC | 15.1 | 15.1 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 228165 | -4430 | 223735 | 223735 | 100% | 0 | 0 |  | 29661 | -622 | 29039 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at group project Pumex | Individual | LAC | MEX | FOA | 23 | INV | 69 | A | O | I | CFC | 167.7 | 167.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 1133881 | -20532 | 1113349 | 1113349 | 100% | 0 | 0 | 0 | 147405 | -2669 | 144736 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNIDO | Phasing out of CFCs at Nieto S.A. | Individual | LAC | MEX | REF | 23 | INV | 70 | A | O | R | CFC | 24.6 | 24.6 |  |  | 1997-11-01 | 1998-06-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 353976 | 0 | 353976 | 353976 | 100% | 0 | 0 |  | 46017 | 0 | 46017 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin foam at Air Design | Individual | LAC | MEX | FOA | 23 | INV | 71 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 80500 | -1178 | 79322 | 79322 | 100% | 0 | 0 | 0 | 10465 | -153 | 10312 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid foam (spray) and integral skin foam at Con Espuma | Individual | LAC | MEX | FOA | 23 | INV | 72 | A | O | I | CFC | 11.4 | 11.4 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 96100 | -2230 | 93870 | 93870 | 100% | 0 | 0 | 0 | 12493 | -290 | 12203 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Group Project (Orca) | Individual | LAC | MEX | FOA | 23 | INV | 73 | A | O | I | CFC | 190 | 190 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-11-01 | 1471500 | -154071 | 1317429 | 1317429 | 100% | 0 | 0 | 0 | 191295 | -20029 | 171266 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNIDO | Phasing out of CFCs at Vendo S.A. | Individual | LAC | MEX | REF | 23 | INV | 74 | A | O | R | CFC | 16.5 | 16.5 |  |  | 1997-11-01 | 1999-03-01 | 1998-10-01 |  | 1998-12-01 | 1999-07-01 | 248524 | 0 | 248524 | 248524 | 100% | 0 | 0 |  | 32308 | 0 | 32308 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for phasing out ODS at several small enterprises in the commercial refrigeration | Individual | LAC | MEX | REF | 23 | PRP | 75 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-06-01 |  | 1999-11-01 | 2001-03-01 | 20000 | -49 | 19951 | 19951 | 100% | 0 | 0 |  | 2600 | -11 | 2589 | 0 | 0 | FIN
FIN | UNDP | Project preparation for a halon sector phase out programme | Individual | LAC | MEX | HAL | 24 | PRP | 76 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-12-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation in the commercial refrigeration (end users) conversion projects |  | LAC | MEX | REF | 24 | PRP | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Manufacture of complete heat exchanger systems for air conditioning equipment that use HFC-134a at Climas de Mexico | Individual | LAC | MEX | REF | 24 | INV | 78 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 2000-05-01 | 2000-05-01 | 2359812 | 0 | 2359812 | 2359812 | 100% | 0 | 0 |  | 306775.56 | 0 | 306775.56 | 0 | 0 | Project completed. Indirect phaseout of 110.5 MT. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation for 5 projects in the foam sector | Individual | LAC | MEX | FOA | 24 | PRP | 79 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for 2 methyl bromide (flowers and crop storage) alternative demonstration projects | Individual | LAC | MEX | FUM | 24 | PRP | 80 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide in the cultivation of tomatoes, strawberries, tobacco, melons and cut flowers | Individual | LAC | MEX | FUM | 25 | DEM | 81 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-08-01 |  | 2004-12-01 | 2006-05-01 | 790350 | -13975 | 776375 | 776375 | 100% | 0 | 0 |  | 102746 | -1977 | 100769 | 0 | 0 | FIN
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid foam for refrigeration systems at Refrigeración Rodríguez | Individual | LAC | MEX | FOA | 25 | INV | 82 | A | O | I | CFC | 34.9 | 34.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 132650 | -31006 | 101644 | 101644 | 100% | 0 | 0 | 0 | 17245 | -4031 | 13214 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Renewal of institutional strengthening project | Individual | LAC | MEX | SEV | 25 | INS | 83 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-07-01 |  | 2000-07-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | UNDP | Conversion to water-based technology in the manufacture of integral skin foam at Moldecor, S.A. de C.V. | Individual | LAC | MEX | FOA | 25 | INV | 84 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2000-04-01 | 2001-12-01 | 86500 | -845 | 85655 | 85655 | 100% | 0 | 0 | 0 | 11245 | -110 | 11135 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Plasticos Tecnicos Mexicanos (PTM) in the manufacture of commercial refrigeration equipment | Individual | LAC | MEX | REF | 25 | INV | 85 | A | O | I | CFC | 50.6 | 50.6 |  |  | 1998-07-01 | 1998-11-01 | 2000-01-01 |  | 1999-12-01 | 2002-09-01 | 398439 | 0 | 398439 | 398439 | 100% | 0 | 0 |  | 51797 | -1 | 51796 | 0 | 0 | FIN
ONG | UNDP | Alternatives to methyl bromide for structural fumigation in Mexico | Individual | LAC | MEX | FUM | 26 | DEM | 86 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 | 2009-04-01 |  |  | 498300 | 0 | 498300 | 330533 | 66.33% | 167767 | 0 | 67106.8 | 64779 | 0 | 42969.29 | 21809.71 | 0 | Limited progress in 2008. A needs assessment was made regarding Technical Assistance needed in order to successfully close the project in early 2009. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Group Project Valcom (Uriel, Limas, Tecknipol, Anzaldua, and Negrete) | Individual | LAC | MEX | FOA | 26 | INV | 87 | A | O | I | CFC | 44.3 | 44.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-08-01 | 2002-11-01 | 314961 | -3630 | 311331 | 311331 | 100% | 0 | 0 | 0 | 40945 | -472 | 40473 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | MEX | REF | 27 | PRP | 88 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 15000 | -2159 | 12841 | 12841 | 100% | 0 | 0 |  | 1950 | -283 | 1667 | 0 | 0 | FIN
FIN | UNDP | Preparation of three projects in the foam sector | Individual | LAC | MEX | FOA | 27 | PRP | 89 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-07-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNIDO | Phasing out CFC-11 with cyclopentane and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators of Metaplus S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 90 | A | O | I | CFC | 20.1 | 20.1 |  |  | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-12-01 | 2004-04-01 | 303094 | -1405 | 301689 | 301689 | 100% | 0 | 0 |  | 39402 | -245 | 39157 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators at Refrigeracion Duran S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 91 | A | O | I | CFC | 15.1 | 15.1 |  |  | 2000-03-01 | 2000-09-01 | 2001-10-01 |  | 2002-07-01 | 2003-10-01 | 112985 | 0 | 112985 | 112985 | 100% | 0 | 0 |  | 14688 | -3 | 14685 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the rigid foam sector | Individual | LAC | MEX | FOA | 30 | PRP | 92 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-04-01 |  | 2001-10-01 | 2003-03-01 | 30000 | -838 | 29162 | 29162 | 100% | 0 | 0 |  | 3900 | -115 | 3785 | 0 | 0 | FIN
FIN | IBRD | Preparation of projects in the commercial refrigeration sector |  | LAC | MEX | REF | 30 | PRP | 93 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | MEX | FOA | 30 | PRP | 94 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UK | Chiller concessional lending pilot project | Individual | LAC | MEX | REF | 28 | INV | 95 | N | O | I | CFC | 5 | 7.8 | 0 |  | 1999-07-01 | 2001-02-22 | 2004-02-01 |  | 2004-03-01 |  | 565000 | 0 | 565000 | 565000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Phase I is completed and accomplished its objectives improving expected results: Twelve chillers were financed instead of the ten expected, with an additional two chillers financed from accumulated funds. 7.8 ODP tons were eliminated instead of 5 tons as expected. Disbursements have been made on schedule with 100% disbursement achieved in August 2002. 100% of building owners that participated in the program have made their monthly repayment on time. Energy savings were 36% higher than proposed. The project will be completed in March 2004. | [14 empty] | Investment
FIN | UNDP | Foam phaseout sector strategy | Individual | LAC | MEX | FOA | 31 | TAS | 96 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-01-01 |  | 2001-12-01 | 2004-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 31 | INS | 97 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-08-01 | 2003-11-01 | 190000 | -45584 | 144416 | 144416 | 100% | 0 | 0 | 0 | 24700 | -5926 | 18774 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b or water-blown technology in rigid polyurethane foam (spray) and to water based formulations in integral skin foam at Comsisa | Individual | LAC | MEX | FOA | 31 | INV | 98 | A | O | I | CFC | 68.7 | 68.7 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2003-08-01 |  | 2003-10-01 | 2004-01-01 | 424050 | 0 | 424050 | 424050 | 100% | 0 | 0 | 0 | 55127 | 0 | 55127 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | MEX | REF | 31 | TAS | 99 | A | O | I | CFC | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2002-05-01 |  | 2004-06-01 | 2004-12-01 | 100000 | -294 | 99706 | 99706 | 100% | 0 | 0 |  | 13000 | -59 | 12941 | 0 | 0 | FIN | [7 empty] | 2003-12-01
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | LAC | MEX | REF | 33 | PRP | 100 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2004-04-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -3 | 6497 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the recycling halon sector | Individual | LAC | MEX | HAL | 33 | PRP | 101 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Airtemp | Individual | LAC | MEX | REF | 34 | INV | 102 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-01-01 |  | 2001-11-30 | 2002-03-01 | 1651430 | 0 | 1651430 | 1651430 | 100% | 0 | 0 |  | 191657.3 | 0 | 191657.3 | 0 | 0 | Project successfully completed both physically and financially and all funding disbursed. PCR is under preparation and expected to be submitted in early 2003. Planned and indirect phaseout should be 60 tons on the basis of 1.1 kg installed per unit plus 2 kg of additional service charges (adding up to 3.1 kg per unit). | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | UNDP | Foam sector ODS phaseout plan (first trnache) | Individual | LAC | MEX | FOA | 35 | INV | 103 | N | O | I | CFC | 145 | 145 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2003-07-01 |  | 2004-11-01 |  | 833150 | 0 | 833150 | 833150 | 100% | 0 | 0 | 0 | 101647 | 0 | 101647 | 0 | 0 | Completed in 2004. | [13 empty] | 2000 | Investment
COM | UNDP | National halon management and banking programme | Individual | LAC | MEX | HAL | 35 | TAS | 104 | A | O | I | Halon | 230 | 230 | 0 | 0 | 2001-12-01 | 2002-08-01 | 2005-01-01 |  | 2007-12-01 |  | 500000 | 0 | 500000 | 444492 | 88.9% | 55508 | 0 | 44406.4 | 65000 | 0 | 57783.96 | 7216.04 | 0 | Completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the storage fumigant sector | Individual | LAC | MEX | FUM | 36 | PRP | 105 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | IBRD | Project preparation in the MAC sector |  | LAC | MEX | REF | 36 | PRP | 106 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-04-01 | 2003-07-01 | 25000 | -20000 | 5000 | 5000 | 100% | 0 | 0 |  | 3250 | -2600 | 650 | 0 | 0 | Project preparation commenced, however, upon further inspection at the enterprise, enterprise was determined ineligible. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of a sectoral phase-out plan in refrigeration | Individual | LAC | MEX | REF | 36 | PRP | 107 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-04-01 | 2005-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | -1 | 3899 | 0 | 0 | FIN | [13 empty] | 2002 | INV
CLO | UNIDO | Preparation of a sectoral phase-out plan in the solvents sector | Individual | LAC | MEX | SOL | 36 | PRP | 108 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-07-01 |  |  | 2003-05-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | CLO | [13 empty] | 2002 | INV
FIN | UNIDO | Renewal of the institutional strengthening project for the phase out of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 37 | INS | 109 | N | T | I |  | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2002-08-01 |  | 2003-12-01 | 2005-03-01 | 0 | 50040 | 50040 | 50040 | 100% | 0 | 0 |  | 0 | 6495 | 6495 | 0 | 0 | FIN | [14 empty] | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | MEX | SEV | 37 | INS | 110 | N | T | I | CFC | 20.4 | 20.4 |  |  | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2005-03-01 | 2006-05-01 | 247000 | -4309 | 242691 | 242691 | 100% | 0 | 0 |  | 32110 | -610 | 31500 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
FIN | UNDP | Preparation of the country programme update | Individual | LAC | MEX | SEV | 38 | CPG | 111 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-10-01 | 48046 | -17955 | 30091 | 30091 | 100% | 0 | 0 | 0 | 6246 | -2334 | 3911.98 | 0.02 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Non-Investment
FIN | UNIDO | Closure of CFC production facilities of the company Quimobasicos | Individual | LAC | MEX | PRO | 38 | PRP | 112 | A | O | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-06-01 | 2004-04-01 | 38000 | -286 | 37714 | 37714 | 100% | 0 | 0 |  | 4940 | -45 | 4895 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector (methyl bromide) | Individual | LAC | MEX | FUM | 39 | PRP | 113 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-01-01 | 2005-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | -3 | 3747 | 0 | 0 | FIN | [13 empty] | 2003
CLO | UNIDO | Preparation of investment projects in the solvent sector (TCA) | Individual | LAC | MEX | SOL | 39 | PRP | 114 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  |  | 2004-06-01 | 30000 | -18965 | 11035 | 11035 | 100% | 0 | 0 |  | 2250 | -1424 | 826 | 0 | 0 | CLO | [13 empty] | 2003
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (first tranche) | Multi-Year | LAC | MEX | PRO | 40 | INV | 115 | A | O | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-11-01 | 2004-03-01 |  | 2005-06-01 | 2006-12-01 | 5300000 | 0 | 5300000 | 5300000 | 100% | 0 | 0 |  | 397500 | 0 | 397500 | 0 | 0 | FIN | [13 empty] | 2003 |  |  |  | 12355 | 8694 | Yes | Yes | Yes
FIN | IBRD | Sterilization group project to replace CFC-12 technology-based sterilization equipment by alternative technologies in the hospital medical sterilization sector | Individual | LAC | MEX | STE | 40 | INV | 115 | N | O | I | CFC | 14.5 | 19.94 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2005-07-01 |  | 2006-06-01 | 2006-06-01 | 288700 | -22568 | 266132 | 266132 | 100% | 0 | 0 |  | 21653 | -1692.64 | 19960.36 | 0 | 0 | Umbrella project is now completed. | [13 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for the conversion of CFC-11, CFC-12 and CFC-113 into HFC, HCFC, HFE for technical aerosols at Tecnosol, Envatec and Dimmex | Individual | LAC | MEX | ARS | 41 | INV | 116 | N | O | I | CFC | 57.3 | 63.98 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2006-12-01 |  | 2006-03-01 | 2006-03-01 | 252340 | 0 | 252340 | 252340 | 100% | 0 | 0 |  | 18925.5 | 0 | 18925.5 | 0 | 0 | Umbrella project is now completed. | [13 empty] | 2003 | INV | 0 | 0 | 0 | 0
COM | UNDP | Foam sector ODS phase-out plan (second tranche) | Individual | LAC | MEX | FOA | 42 | INV | 117 | N | O | D | CFC | 192 | 192 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2007-12-01 |  | 1109120 | 0 | 1109120 | 1030122 | 92.88% | 78998 | 0 | 63198.4 | 83184 | 0 | 77259.15 | 5924.85 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment
COM | Spain | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 118 | A | O | I | MBR | 107.2 | 0 | 0 |  | 2004-04-01 | 2005-10-01 | 2006-10-01 |  | 2008-12-01 |  | 707965 | 0 | 707965 | 454721 | 64.23% | 253244 | 53467 | 190000 | 87876 | 0 | 59113.73 | 28762.27 | 6786.95 | COMPLETED PROJECT. Completion report (PCR) prepared and submited | [13 empty] | 2004 | Investment
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (second tranche) | Multi-Year | LAC | MEX | PRO | 42 | INV | 119 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-05-01 | 2005-04-01 |  | 2005-06-01 | 2006-12-01 | 10700000 | 0 | 10700000 | 10700000 | 100% | 0 | 0 |  | 802500 | 0 | 802500 | 0 | 0 | FIN | [13 empty] | 2004 | INV |  |  | 12355 | 8044 | Yes | Yes | Yes
COM | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | MEX | PHA | 42 | INV | 120 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-01 |  | 3517000 | 0 | 3517000 | 3508848 | 99.77% | 8152 | 2163 | 5000 | 263775 | 0 | 263164 | 611 | 162 | The project is expected to be financially completed in 2009. | [10 empty] | 2006-12-01 |  |  | 2003 | INV | 4403 | 3208.44 |  |  | Yes | Yes | Yes
FIN | UNIDO | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 121 | A | O | I | MBR | 36.9 | 132.9 |  |  | 2004-04-01 | 2004-11-01 | 2006-10-01 |  | 2006-12-01 | 2008-06-01 | 207035 | -1912 | 205123 | 205123 | 100% | 0 | 0 |  | 18633 | -172 | 18461 | 0 | 0 | Financial completion in Jun 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2003 | INV
ONG | Canada | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 122 | A | O | I | MBR | 18.2 |  | 0 |  | 2004-04-01 | 2006-09-06 | 2006-10-01 | 2009-03-09 |  |  | 190000 | 0 | 190000 | 188000 | 98.95% | 2000 |  | 2000 | 24700 | 0 | 18525 | 6175 |  | This project is implemented by UNDP on behalf of Canada. Project was nearly completed by end of 2008 with 10 companies successfully completing alternative fumigations techniques. Pending activities including final reports were completed by March 2009. |  | 2004 | [10 empty] | 2008-06-01 | 2004 | Investment
ONG | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | MEX | PHA | 45 | INV | 123 | A | O | I | CFC | 100 | 100 |  |  | 2005-04-01 | 2006-05-01 | 2007-04-01 | 2010-12-01 |  |  | 4478000 | -200000 | 4278000 | 3286568 | 76.82% | 991432 | 205773 | 250000 | 335850 | -15000 | 246493 | 74357 | 15433 | USD 200,000 was transferred to MLF at the 54th ExCom as an adjustment to the MDI project from the original amount of USD 4,478,000. The project was ongoing in the balance list which was taken out and same amount was reduced in the approved funding. Equipment for 14 R&R centers were purchased. These centers were put into operation in 2008. In 2009 additional training of technicians and phase out in the end-user sector is planned. Monitoring of implementation and verification of performance is continuing until end 2010 to ensure sustainability. | [13 empty] | 2005 | INV | 2205 | 1604 |  |  | Yes | Yes | Yes
FIN | IBRD | National CFC phase-out plan: 2005 work programme | Multiyear | LAC | MEX | PHA | 45 | INV | 124 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2007-04-01 |  | 2006-02-01 | 2006-02-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | Project completed | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Extension of institutional strengthening project: phase VII | Individual | LAC | MEX | SEV | 45 | INS | 125 | N | T | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-08-01 | 2008-08-01 | 247000 | 0 | 247000 | 247000 | 100% | 0 | 0 |  | 18525 | 0 | 18525 | 0 | 0 | Financial completion in Aug 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2005 | NON-INV
COM | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: third tranche | Multi-Year | LAC | MEX | PRO | 45 | INV | 126 | A | O | I | CFC | 0 | 0 | 5616 | 5616 | 2005-04-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 |  | 4000000 | 0 | 4000000 | 3999437 | 99.99% | 563 | 115 | 100 | 300000 | 0 | 299958 | 42 | 9 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2005 | INV |  |  | 6739 | 5201 | Yes | Yes | Yes
COM | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | MEX | SEV | 45 | TAS | 127 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 |  | 114679 | 0 | 114679 | 97560 | 85.07% | 17119 | 0 | 13695.2 | 10321 | 0 | 8780.3064 | 1540.6936 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
ONG | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: fourth tranche | Multi-Year | LAC | MEX | PRO | 47 | INV | 128 | A | O | I | CFC | 0 | 0 | 6739 | 6739 | 2005-11-01 | 2006-01-01 | 2009-12-01 | 2009-12-01 |  |  | 11850000 | 0 | 11850000 | 11760444 | 99.24% | 89556 | 0 | 30000 | 888750 | 0 | 882033 | 6717 | 0 | At the 56th ExCom it was decided that no further external audit is required. Further monitoring, policy and awareness measures will be implemented in 2009. | [13 empty] | 2005 | INV |  |  | 0 | 0 | Yes | Yes | Yes
FIN | UNIDO | Preparation of a process agent project | Individual | LAC | MEX | PAG | 48 | PRP | 129 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -94 | 29906 | 29906 | 100% | 0 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | Financial completion in Jun 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2006 | NON-INV
COM | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | MEX | PHA | 50 | INV | 130 | A | O | I | CFC | 400 | 400 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-07-01 |  | 299500 | 0 | 299500 | 291855 | 97.45% | 7645 | 7641 | 7000 | 22463 | 0 | 21889 | 574 | 573 | Project completed in Jul 2008. | [13 empty] | 2006 | INV | 150 | 0 |  |  | Yes | Yes | Yes
COM | UNIDO | Project preparation in the fumigant sector | Individual | LAC | MEX | FUM | 51 | PRP | 131 | A | O | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-08-01 |  | 60000 | 0 | 60000 | 59491 | 99.15% | 509 | 35 | 1 | 4500 | 0 | 4462 | 38 | 3 | Project completed in Aug 2008. | [13 empty] | 2007 | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase VIII) | Individual | LAC | MEX | SEV | 52 | INS | 132 | N | T | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2009-07-31 | 2009-06-01 |  |  | 247000 | 0 | 247000 | 154065 | 62.37% | 92935 | 332 | 48000 | 18525 | 0 | 11555 | 6970 | 25 | National experts contracts were extended by Jun 2009 and the project will be completed. | [13 empty] | 2007 | NON-INV
ONG | UNIDO | Umbrella project for terminal phase-out of CTC | Individual | LAC | MEX | PAG | 52 | INV | 133 | A | O | I | CTC | 87.3 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-31 | 2010-01-01 |  |  | 1518094 | 0 | 1518094 | 20373 | 1.342% | 1497721 | 1466350 | 800000 | 113857 | 0 | 1528 | 112329 | 109976 | The equipment procurement has been done and is being now manufactured. Its installation is planned for October 2009. Mexichem company will not import CTC from 1 January 2009, but will use CTC from stock until conversion is completed. The project is expected to be completed in January 2010. | We were informed by the NOU that the CTC imports in 2008 were higher than 9.376 ODP tonnes due to the technical difficulties faced duting project implementation and the serious difficulty to get CTC in the international market during the first years of the implementation of the project. It is to be noted that the overall consumption was below the total consumption allowed by the Decision of the MOP, the only difference is the year of compliance. In 2006 the imports were zero MT and in 2008 the imports were around 80 MT. With respect to the difficulties faced during project implementation, the first bidding for the acquisition of the equipment was not successful due to the costs, that were significantly higher than the original budget. This resulted in a delay in the acquisition process and in the project execution. Also it is important to empasize that the alternative solution selected is technologically complex and took more time for its analysis and definition. Furthermore, offered delivery time of the required equipment was not less than 9 months. Mexichem Company will use CTC from their stocks during the procurement and installation process of new equipment. Should the company run out of its CTC stocks, it is confirmed that no more CTC would be imported for that purpose. | [12 empty] | 2007 | INV
FIN | UNIDO | Project preparation for a MDI project, including the development of a national transitional strategy for the sector | Individual | LAC | MEX | ARS | 52 | PRP | 134 | A | O | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-04-01 | 2008-07-01 | 50000 | -275 | 49725 | 49725 | 100% | 0 | 0 |  | 3750 | -21 | 3729 | 0 | 0 | Project completed in Apr 2008. Financial completion in Jul 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2007 | NON-INV
ONG | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | MEX | ARS | 53 | INV | 135 | A | O | I | CFC | 97 | 0 |  |  | 2007-11-01 | 2008-04-01 | 2010-01-31 | 2010-12-01 |  |  | 2630503 | 0 | 2630503 | 404523 | 15.38% | 2225980 | 929174 | 1000000 | 197288 | 0 | 30339 | 166949 | 69688 | In 2008 UNIDO has procured filling equipment for the Mexican company Salus. The selection of the technology provider has been completed in November 2008. The pilot batches of the first MDI are being planned to achieve by Dec 2009. The project completion date is December 2010. | [13 empty] | 2007 | INV
ONG | UNIDO | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 136 | A | O | I | MBR | 130 | 0 |  |  | 2008-04-01 | 2008-06-01 | 2014-03-31 | 2014-03-01 |  |  | 2000000 | 0 | 2000000 | 266991 | 13.35% | 1733009 | 47119 | 500000 | 150000 | 0 | 20024 | 129976 | 3534 | Project started its implementation in April 2008. Agreements with the farmers have been signed. TOR for five greenhouses in accordance with the agreements were prepared, bidding completed and delivery of the first two greenhouses is expected before June 2009. 2008 consumption was lower than stipulated in the agreement. | [13 empty] | 2008 | INV | 895 | 874.8 |  |  | Yes | N/A | N/A
ONG | Italy | National methyl bromide phase-out plan (first tranche) | Multi-year | LAC | MEX | FUM | 54 | INV | 137 | A | O | I | MBR | 70 |  | 0 |  | 2008-04-01 |  | 2014-03-01 | 2014-03-01 |  |  | 1000000 | 0 | 1000000 |  | 0% | 1000000 |  | 500000 | 120000 | 0 | 0 | 120000 | 0 | Project started its implementation in April 2008. Agreements with the farmers have been signed. TOR for five greenhouses in accordance with the agreements were prepared, bidding completed and delivery of the first two greenhouses is expected before June 2009. 2008 consumption was lower than stipulated in the agreement. |  | 2008 | [11 empty] | 2008 | Investment | 70 | 70
ONG | Canada | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 138 | A | O | I | MBR | 20 |  | 0 |  | 2008-04-01 |  | 2014-03-01 | 2012-03-14 |  |  | 500000 | 0 | 500000 | 0 | 0% | 500000 |  | 220000 | 58527 | 0 | 0 | 58527 |  | Initiation of project was awaiting completion of technical assistance project (MEX/FUM/42/TAS/122) which was delayed for reasons previously reported. Activities now expected to start in mid-2009. |  | 2008 | [11 empty] | 2008 | Investment | 895 | 840.3 |  |  | Yes
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 139 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 104250 | 0 | 104250 | 1272 | 1.22% | 102978 | 292 | 30000 | 7819 | 0 | 95 | 7724 | 22 | Preparation of HPMP, workshop and survey are progressing. | Bidding was successfully completed for the HPMP preparation and contract was awarded. Initial workshop took place in January 2009. Work on legislation is part of the sub-contract. | [12 empty] | 2008 | NON-INV
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 140 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 69500 | 0 | 69500 | 0 | 0% | 69500 | 0 | 69500 | 5213 | 0 | 0 | 5213 | 0 | International and Local consultant hired to do / update the HCFC survey in the Foam Sector. | [13 empty] | 2008 | Investment
ONG | UNDP | Pilot project for validation of methyl formate in microcellular polyurethane applications (phase I) | Individual | LAC | MEX | FOA | 56 | TAS | 141 | N | O | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-06-01 | 2009-12-01 |  |  | 291500 | 0 | 291500 | 0 | 0% | 291500 | 0 | 116600 | 21862 | 0 | 0 | 21862 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
FIN | UNEP | Country programme preparation | Individual | AFR | MLI | SEV | 19 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-05-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | MLI | REF | 24 | PRP | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Institutional strengthening project for Mali | Individual | AFR | MLI | SEV | 24 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | France | Project preparation in the foam sector (Fofy) |  | AFR | MLI | FOA | 25 | PRP | 4 | A | O | I |  | 0 |  | 0 |  | 1998-07-01 | 1998-08-01 | 1999-01-01 |  | 1998-09-01 | 1998-11-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Fofy Industrie |  | AFR | MLI | FOA | 26 | INV | 5 | A | O | I | CFC | 19.5 | 19.5 | 0 |  | 1998-11-01 | 2000-01-27 | 2000-12-01 |  | 2001-12-18 | 2001-12-18 | 151000 | 0 | 151000 | 150999.9781 | 100% | 0.021858 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | UNEP | Refrigerant management plan: Assistance in drafting ODS-related legislation | Individual | AFR | MLI | REF | 29 | TAS | 6 | A | O | I | CFC | 2.7 | 2.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-02 |  | 2002-07-01 | 2003-08-01 | 10980 | 0 | 10980 | 10980 | 100% | 0 | 0 | 0 | 1427.4 | 0 | 1427.4 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Training programme for customs officers | Individual | AFR | MLI | REF | 29 | TRA | 7 | A | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-02 |  | 2003-12-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [5 empty] | 2003-03-03 | [7 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: Train the trainers programme in the refrigeration servicing sector | Individual | AFR | MLI | REF | 29 | TRA | 8 | A | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-02 |  | 2002-05-01 | 2005-01-01 | 60000 | -18414 | 41586 | 41586 | 100% | 0 | 0 | 0 | 7800 | -2393.82 | 5406.18 | 0 | 0 | Project financially completed. | $ 18,414 plus $ 2,394 PSC returned ExCom 46 |  |  |  |  | 2002-12-02 | [7 empty] | 1999 | Non Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 32 | TAS | 9 | A | O | I | CFC | 25.3 | 25.3 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-12-01 | 2004-01-01 | 102658 | -3518 | 99140.3 | 99140 | 100% | 0.3 | 0 | 0 | 13346 | -457 | 12888.761 | 0.239 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the refrigerant management plan | RMP-Component | AFR | MLI | REF | 32 | TAS | 10 | A | O | I | No_ODP | 3.8 | 3.8 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2005-07-01 | 2007-03-01 | 15455 | -237 | 15218 | 15218 | 100% | 0 | 0 | 0 | 2009 | -31 | 1978 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2000 | Non-Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | MLI | SEV | 35 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-03-01 | 2007-06-01 | 46667 | 0 | 46667 | 46667 | 100% | 0 | 0 | 0 | 6066.71 | 0 | 6066.71 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNIDO | Preparation of an awareness workshop in the methyl bromide sector | Individual | AFR | MLI | FUM | 36 | TRA | 12 | A | O | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-03 |  | 2003-07-01 | 2004-04-01 | 30000 | -596 | 29404 | 29404 | 100% | 0 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
COM | UNEP | Preparation of the refrigerant management plan update | RMP update | AFR | MLI | REF | 43 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2005-07-01 |  | 2005-11-01 |  | 10000 | 0 | 10000 | 0 | 0% | 10000 | 0 | 10000 | 1300 | 0 | 0 | 1300 | 0 | Project completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | MLI | SEV | 44 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-04 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNDP | Implementation of the RMP update: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 45 | TAS | 16 | N | O | I | CFC | 12.3 | 12.3 | 0 | 0 | 2005-04-01 | 2007-09-01 | 2007-04-01 |  | 2007-12-01 |  | 50000 | 0 | 50000 | 48610 | 97.22% | 1390 | 0 | 1112 | 4500 | 0 | 4374.9 | 125.1 | 0 | Completed in 2007. | [13 empty] | 2005 | Non-Investment
FIN | UNEP | Implementation of the RMP update: training programme for customs officers (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 17 | A | O | I | CFC | 7.3 | 7.3 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2007-09-01 | 2008-12-01 | 29546 | 0 | 29546 | 29545.97 | 100% | 0.03 | 0 | 0.03 | 3841 | 0 | 3840.9761 | 0.0239 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNEP | Implementation of the RMP update: training programme for refrigeration service technicians (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 18 | A | O | I | CFC | 6.1 | 6.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2008-12-01 |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2005 | Non Investment
COM | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | AFR | MLI | REF | 45 | TAS | 19 | A | O | I | CFC | 4.9 | 4.9 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2005 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLI | PHA | 48 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-02-01 |  | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project completed in February 2008. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MLI | PHA | 48 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 |  | 12000 | 0 | 12000 | 10738 | 89.48% | 1262 | 0 | 1262 | 900 | 0 | 805.35 | 94.65 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | MLI | SEV | 50 | INS | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 |  | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008 and IS phase V ongoing | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 120000 | 0 | 120000 | 114412.14 | 95.34% | 5587.86 | 1014.55 | 5587.86 | 15600 | 0 | 14873.5782 | 726.4218 | 131.8915 | Training of 104 technicians from August to December 2008 | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | INV | 24 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 | 2009-11-01 |  |  | 172000 | 0 | 172000 | 15801 | 9.187% | 156199 | 142153 | 62479.6 | 12900 | 0 | 1185.075 | 11714.925 | 10661.475 | Two consultant missions took place in 2008. International bidding process has been completed and equipment arrival expected early 2009. Contract with Excellence center signed as well as with storage centre. Both are ready to start operations when equipment arrives. Second tranche to be approved at 57th ExCom. | [13 empty] | 2007 | Investment | 16.2 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLI | PHA | 55 | PRP | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for signature | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | MLI | SEV | 56 | INS | 26 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-31 | 2010-12-31 |  |  | 60677 | 0 | 60677 | 0 | 0% | 60677 | 0 | 60677 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | MLW | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-05-01 | 1993-05-01 |  | 1994-03-01 | 1994-12-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3900 | -650 | 3250 | 0 | 0 | Project financially completed. | $ 5,000 plus $ 650 PSC returned ExCom 41 | [12 empty] | 1991 | Non Investment
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | MLW | SEV | 12 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1997-03-01 |  | 1998-10-01 | 1999-10-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 | 0 | 10010 | 0 | 10010 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | MLW | REF | 17 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | MLW | SEV | 18 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 | 0 | 910 | 0 | 910 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MLW | REF | 19 | TAS | 5 | A | O | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -311 | 106009 | 106009 | 100% | 0 | 0 | 0 | 13822 | -40 | 13782 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 21 | PRP | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 22 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MLW | REF | 23 | PRP | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1998
FIN | UNDP | Project preparation for a methyl bromide (tobacco) alternative demonstration project | Individual | AFR | MLW | FUM | 24 | PRP | 9 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-02-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNEP | Request for renewal of institutional strengthening | Individual | AFR | MLW | SEV | 25 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-06-01 |  | 2000-12-01 | 2003-12-01 | 51350 | 0 | 51350 | 51350 | 100% | 0 | 0 | 0 | 6675.5 | 0 | 6675.5 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MLW | REF | 26 | TAS | 11 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted | [13 empty] | 2000
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Robry Ltd. | Individual | AFR | MLW | FOA | 26 | INV | 12 | A | O | I | CFC | 33 | 33 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 156500 | -17548 | 138952 | 138952 | 100% | 0 | 0 | 0 | 20345 | -2281 | 18064 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 1998 | Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | MLW | FUM | 30 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9242 | 15758 | 15758 | 100% | 0 | 0 | 0 | 3250 | -1201.46 | 2048.54 | 0 | 0 | Project financially completed. | $ 9,242 plus $ 1,201 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | MLW | SEV | 31 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-01-01 | 2005-12-01 | 51300 | 0 | 51300 | 51300 | 100% | 0 | 0 | 0 | 6669 | 0 | 6669 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
COM | UNDP | Phaseout of all non-essential and non-QPS methyl bromide (release of first tranche) | Multi-Year | AFR | MLW | FUM | 32 | DEM | 15 | N | O | I | MeBr | 19.3 | 19.3 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2001-12-01 |  | 2001-12-01 |  | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2001. | [13 empty] | 2000 | Investment | 109.7 | 109.7 |  |  | Yes | N/A | Yes
COM | UNDP | Second payment under the national programme for the phaseout of all non-essential and non-quarantine and pre-shipment applications of methyl bromide | Multi-Year | AFR | MLW | FUM | 34 | INV | 16 | N | O | I | MeBr | 20.9 | 20.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2002-08-01 |  | 2004-12-01 |  | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Completed in 2004. | [13 empty] | 2001 | Investment | 90 | 90 |  |  | Yes | N/A | Yes
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | MLW | REF | 37 | PRP | 17 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2004-05-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP approved in June 04
COM | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (release of third tranche) | Multi-Year | AFR | MLW | FUM | 40 | INV | 18 | N | O | I | MeBr | 41.1 | 41.1 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 |  | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 56250 | 0 | 56250 | 0 | 0 | Completed in 2004. | [13 empty] | 2003 | Investment | 49.3 | 49.3 |  |  | Yes | N/A | Yes
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | MLW | SEV | 41 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | Germany | Implementation of the RMP update: refrigeration and air-conditioning sector | Individual | AFR | MLW | REF | 43 | TAS | 20 | A | O | I |  | 49 | 0 | 0 |  | 2004-07-01 | 2004-10-01 | 2007-07-01 |  | 2007-12-01 |  | 100000 | 0 | 100000 | 99439 | 99.44% | 561 | 0 | 0 | 13000 | 0 | 12927.07 | 72.93 | 0 | Project completed. PCR was submitted in September 2008. Remaining funds will be returned to the secretariat.
COM | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (fourth tranche) | Multi-Year | AFR | MLW | FUM | 43 | INV | 21 | N | O | I | MeBr | 29.7 | 29.7 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 |  | 849824 | 0 | 849824 | 806482 | 94.9% | 43342 | 0 | 34673.6 | 63737 | 0 | 60486.3398 | 3250.6602 | 0 | Completed in 2006. | [13 empty] | 2004 | Investment | 0 | 0 |  |  | Yes | N/A | yes
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | MLW | SEV | 47 | INS | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2007-12-01 |  | 2007-12-01 | 2008-01-01 | 66733 | 0 | 66733 | 66733.41 | 100% | -0.41 | 0 | -0.41 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLW | PHA | 50 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-02-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MLW | PHA | 53 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 95000 | 0 | 95000 | 70000.16 | 73.68% | 24999.84 | 25000 | 24999.84 | 12350 | 0 | 9100.0208 | 3249.9792 | 3250 | First tranche successfully completed, country conducted trainings for customs officers, refrigeration technicians, reviewed ODS Regulations, curricula for customs training school and technicians scholl.second tranche approved during the 57th Ex-com | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLW | PHA | 53 | INV | 25 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 | 2009-11-01 |  |  | 125500 | 0 | 125500 | 23430 | 18.67% | 102070 | 57004 | 40828 | 11295 | 0 | 2108.7 | 9186.3 | 5130.36 | Project ongoing. National expert recruited. International expert recruited with a mission fielded in July 2008. Training for 17 technicians from various training centers held at that time in safe refrigerant handling and retrofitting techniques. Equipment bidding finalized. Equipment expected in Q1-2009. End-user incentives advertised through direct contacts with companies. It is expected that applications to be received in Q1-2009. Second tranche to be approved at 57th ExCom. | [13 empty] | 2007 | Investment | 8.7 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | MLW | SEV | 53 | INS | 26 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 | 2009-11-01 |  |  | 66733 | 0 | 66733 | 53575.57 | 80.28% | 13157.43 | 0 | 13157.43 | 0 | 0 | 0 | 0 | 0 | MOU signed with the country, NOU implemenmted activities including trainings for customs officeers, refrigeration technicians, production of awareness materials and successfully hosting sub-regional workshop for refrigeration technicians on retrofitting | [13 empty] | 2007 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLW | PHA | 55 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU signed with the country awaiting first payment. Country identified national experts for the survey, finalised HCFC survey questionnaire and TORs for the survey and drafting of HPMP | [13 empty] | 2008
COM | UNIDO | Project preparation for a country programme and a terminal phase-out plan | Individual | EUR | MOG | SEV | 51 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-04-01 |  | 40000 | 0 | 40000 | 38349 | 95.87% | 1651 | 1030 | 1000 | 3600 | 0 | 3451 | 149 | 93 | Project completed in Apr 2008. | [13 empty] | 2007 | NON-INV
COM | UNIDO | Establishment of the ozone unit | Individual | EUR | MOG | SEV | 51 | INS | 2 | N | T | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-12-01 |  | 30000 | 0 | 30000 | 21614 | 72.05% | 8386 | 8257 | 8000 | 2250 | 0 | 1621 | 629 | 619 | Project completed in Dec 2008. | [13 empty] | 2007 | NON-INV
ONG | UNIDO | Terminal phase-out plan for CFCs (first tranche) | Multi-Year | EUR | MOG | PHA | 53 | INV | 3 | A | O | I | CFC | 3 | 0 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 | 2009-12-01 |  |  | 175000 | 0 | 175000 | 38588 | 22.05% | 136412 | 35156 | 30000 | 13125 | 0 | 2894 | 10231 | 2637 | The implementation of the project started. The implementation modalities have been agreed upon. Equipment for training purposes was purchased. Project Management Unit was established and trained. | [13 empty] | 2007 | INV | 5.2 | 3.5 |  |  | Yes | N/A | N/A
ONG | UNIDO | Institutional strengthening project (Phase I) | Individual | EUR | MOG | SEV | 55 | INS | 4 | N | T | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-06-30 | 2010-06-01 |  |  | 60000 | 0 | 60000 | 1457 | 2.428% | 58543 | 375 | 20000 | 4500 | 0 | 109 | 4391 | 28 | National experts contracts were issued under the new phase as of end December 2008 for the year 2009. | [13 empty] | 2008 | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MOG | PHA | 55 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 30000 | 6375 | 0 | 0 | 6375 | 0 | National and International experts were selected for the preparation of HPMP. | Initial workshop is planned for July/August 2009, after the completion of the survey. Review of legislation is part of the survey. Most aspects of the HPMP are covered by the contract. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | MOL | SEV | 25 | INS | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2002-07-01 | 2004-05-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | EUR | MOL | REF | 25 | TAS | 2 | A | O | I | CFC | 21.9 | 21.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2002-05-01 | 2002-11-01 | 254150 | -304 | 253846 | 253846 | 100% | 0 | 0 | 0 | 33040 | -40 | 33000 | 0 | 0 | Completed in 2002. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Train the trainers programme for good practices in the refrigeration sector | Individual | EUR | MOL | REF | 25 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-09-01 | 1999-08-01 |  | 2003-12-01 | 2005-12-01 | 66000 | -11000 | 55000 | 55000 | 100% | 0 | 0 | 0 | 8580 | -1430 | 7150 | 0 | 0 | Project financially completed. | $ 11,000 plus $ 1,430 PSC returned ExCom 46 |  |  |  | 2001-06-01 | [8 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training on monitoring and control of CFC and CFC using equipment | Individual | EUR | MOL | REF | 25 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2001-06-01 | 1999-08-01 |  | 2004-12-01 | 2008-01-01 | 66550 | -7349 | 59201 | 59201 | 100% | 0 | 0 | 0 | 8651.5 | -955 | 7696.13 | 0.37 | 0 | Project financially completed. | $ 7,349 plus $ 955 returned at ExCom 53 |  |  |  | 2002-01-01 | [8 empty] | 1998 | Non Investment
FIN | UNEP | Country programme | Individual | EUR | MOL | SEV | 25 | CPG | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 1998-07-01 |  | 1998-07-01 | 1998-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 38508 | Non Investment
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | MOL | FUM | 30 | TAS | 6 | A | O | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-04-01 | 2004-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed in April 2004. PCR submitted |  | 2000 | [11 empty] | 2000 | Non-Inv.
FIN | UNEP | Renewal of institutional strengthening projects (Phase II) | Individual | EUR | MOL | SEV | 36 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2004-04-01 |  | 2004-07-01 | 2007-06-01 | 69334 | 0 | 69334 | 69334.29 | 100% | -0.29 | 0 | -0.29 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Project preparation for the RMP proposal | RMP-Component | EUR | MOL | REF | 41 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MOL | SEV | 43 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-03-01 | 2007-03-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | EUR | MOL | REF | 44 | TAS | 11 | A | O | I | CFC | 6.4 | 6.4 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-04-01 |  | 19885 | 0 | 19885 | 15651.09 | 78.71% | 4233.91 | 0 | 4233.91 | 2585 | 0 | 2034.6417 | 550.3583 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNDP | Implementation of the RMP: technical assistance programme | RMP-Component | EUR | MOL | REF | 44 | TAS | 12 | N | O | I | CFC | 55.9 | 55.9 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 |  | 173495 | 0 | 173495 | 173492 | 100% | 3 | 0 | 2.4 | 15615 | 0 | 15614.73 | 0.27001 | 0 | Completed in 2007. | [13 empty] | 2004 | Investment
COM | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | EUR | MOL | FUM | 45 | TAS | 13 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 |  | 30000 | 0 | 30000 | 28162 | 93.87% | 1838 | 0 | 1 | 2700 | 0 | 2535 | 165 | 0 | The project is expected to be financially completed in 2009. | [13 empty] | 2005 | NON-INV
COM | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | MOL | SEV | 48 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2008-04-01 |  | 69334 | 0 | 69334 | 59392.9 | 85.66% | 9941.1 | 0 | 9941.1 | 0 | 0 | 0 | 0 | 0 | Project completed in April 2008 | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | EUR | MOL | PHA | 48 | PRP | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-11-01 | 2007-04-01 |  | 2007-12-01 |  | 12000 | 0 | 12000 | 9619 | 80.16% | 2381 | 0 | 2381 | 900 | 0 | 721.425 | 178.575 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | EUR | MOL | PHA | 48 | PRP | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2008-04-01 |  | 18000 | 0 | 18000 | 10040.31 | 55.78% | 7959.69 | 0 | 7959.69 | 2340 | 0 | 1305.2403 | 1034.7597 | 0 | Project completed in April 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-year | EUR | MOL | PHA | 52 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 | 2009-12-01 |  |  | 74500 | 0 | 74500 | 69004.2 | 92.62% | 5495.8 | 0 | 5495.8 | 9685 | 0 | 8970.546 | 714.454 | 0 | SSFA drafted and cleared by both Parties. Signature expected during first half of 2009. | [13 empty] | 2007 | Non Investment
COM | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | MOL | PHA | 52 | INV | 18 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-07-01 |  | 2008-11-01 |  | 152500 | 0 | 152500 | 137868 | 90.41% | 14632 | 0 | 11705.6 | 11438 | 0 | 10340.552 | 1097.448 | 0 | Completed in 2008. Equipment arrived. National and international experts recruited. Upon request from NOU, alternative technology and international standards workshop arranged in November 2008 (21 engineers and technicians attended). 10 companies received grants for technological conversions. Second tranche approved at 56th ExCom. | [13 empty] | 2007 | Investment | 10 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | MOL | SEV | 54 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-07-31 | 2010-07-31 |  |  | 69334 | 0 | 69334 | 8505.39 | 12.27% | 60828.61 | 60828.2 | 60828.61 | 0 | 0 | 0 | 0 | 0 | SSFA signed by both parties. NOU is implementing second and final tranche of TPMP accoridng to annual work plan. NOU actively participating in the ECA network activities. NOU hosted sub-regional ECA contact group meeting on implementation of TPMPs in Dec. 2008. | [13 empty] | 2008
ONG | UNDP | MDI transition strategy | Individual | EUR | MOL | ARS | 54 | TAS | 20 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2009-09-01 | 2010-01-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 6000 | 2700 | 0 | 0 | 2700 | 0 | Prodoc signed. NOU advised that the start of MDI programme planned for Q1-2009. | [13 empty] | 2008 | Non-Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | MOL | PHA | 55 | PRP | 21 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Project document signed and, administratively, project is starting up. National experts to be recruited in Q1-2009. Project start-up visit planned in Q1-2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 140500 | 0 | 140500 | 0 | 0% | 140500 | 0 | 140500 | 18265 | 0 | 0 | 18265 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | INV | 23 | N | O | I | CFC | 10 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 152500 | 0 | 152500 | 0 | 0% | 152500 | 0 | 61000 | 11438 | 0 | 0 | 11438 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme formulation | Individual | ASP | MON | SEV | 20 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | 1999-05-01 | [9 empty] | 1996 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | ASP | MON | SEV | 28 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-08-01 |  | 2002-08-01 | 2003-09-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Train the trainer programme for refrigeration service technicians | Individual | ASP | MON | REF | 32 | TRA | 3 | A | O | I | CFC | 2.4 | 2.4 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-03 |  | 2003-10-01 | 2005-01-01 | 65970 | -15423 | 50547 | 50546.91 | 100% | 0.09 | 0 | 0.09 | 8576 | -2004 | 6571.0983 | 0.9017 | 0 | Project financially completed. | $ 1,886 plus $245 PSC returned ExCom 44 $ 13,529 plus $1759 PSC retuned ExCom 46 $ 8 plus returned to ExCom 49 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | MON | REF | 32 | TRA | 4 | A | O | I | CFC | 2.8 | 2.8 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-03 |  | 2003-06-01 | 2003-06-01 | 77200 | -15003 | 62197 | 62197.12 | 100% | -0.12 | 0 | -0.12 | 10036 | -1950.39 | 8085.6256 | -0.0156 | 0 | Project financially completed. | $ 5,003 plus $ 650 PSC returned ExCom 44 $ 10,000 plus $ 1300 returned ExCom 46 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | MON | REF | 33 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | MON | REF | 35 | TAS | 6 | A | O | I | CFC | 3.9 | 3.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2005-11-01 | 108600 | 0 | 108600 | 108600 | 100% | 0 | 0 | 0 | 14118 | 0 | 14118 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | ASP | MON | SEV | 36 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | MON | SEV | 43 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-07-01 | 2007-07-01 | 57200 | -2 | 57198 | 57198 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 2 returned to ExCom 55 | [12 empty] | 2004 | Non Investment
COM | Japan | Preparation of a terminal phase-out management plan | Individual | ASP | MON | PHA | 45 | PRP | 9 | A | O | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2005-10-01 |  | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 4407 | 0 | 4407 | 0 | 0
ONG | Japan | Terminal phase-out management plan: first tranche | Multi-Year | ASP | MON | PHA | 47 | INV | 10 | N | O | I | CFC | 0.7 |  | 0 |  | 2005-11-01 | 2006-07-01 | 2007-12-01 | 2009-08-01 |  |  | 150000 | 0 | 150000 | 137758.75 | 70.44% | 12241.25 | 0 | 12241 | 19500 | 0 | 19500 | 0 | 0 | From January to February 2006, a candidate staff member of the PMU was selected and sent to Japan to participate in the training course of JICA. In March 2006, MOU was signed between UNEP, cooperating implementing agency, and the Government of Mongolia. The 1st tranche activities have been mostly completed. | [15 empty] | 4 |  | 0 | 0 | Yes
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | MON | SEV | 50 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-06-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in June 2008 & financially completed. TPMP Implementation: Four Customs Training Workshops were conducted wherein 292 officers were trained; o Two Technicians Training Workshops were conducted · Ministerial decree to ban the import of CTC/TCA/MeBr and other ODSs was approved by Government resolution # 95 in 11 of April 2007. Mongolia hosted in June 2007 the Regional Enforcement Network on ‘’Partnering with private sector for preventing environmental crime Combating Illegal Trade for Compliance with the Montreal Protocol in the Asia Pacific Region’’. The country strengthened their awareness campaign by organizing Ozone events such as International Ozone Day, symposium etc. They distributed information booklets, posters, calendars, leaflets, etc. And distributed the translated and edited the Ozone education package with the involvement of TUNZA Mongolian Youth volunteers. The country also organized National Ozone quiz and the winner participated in the first organized Regional Ozone Quiz. | [13 empty] | 2006 | Non Investment
ONG | Japan | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | MON | PHA | 53 | INV | 12 | A | O | I |  | 1.5 |  | 0 |  | 2007-11-01 |  | 2009-11-01 |  |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 |  |  | 7150 | 0 |  | 7150
ONG | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | MON | SEV | 55 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2010-12-01 | 2010-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Follow up of the bi-lateral dialogue with China was conducted during the network meetings in April and September 2008. In 2008, 3 training progamme workshops for technicians were conducted with a total of 120 refrigeration technicians from over 10 companies that are members of the Mongolian Refrigeration Association (MRA) participated in the training workshops. The trainings were conducted by MRA and NOU. A roundtable discussion on stockpiling was conducted on 26 March and 23 May 2008. Numerous awareness programme were held and materials produced such as 1. Posters dedicated to the International Ozone Day 2008 were prepared and published. “Ozone Action in Mongolia” newsletter has also been published and distributed. 2. Two workshops for journalists on ozone layer protection were organized in April and September 2008.3. TV programme on the ozone issues was broadcasted 3-4 times through Mongolian National Television and TV5 channels in April, September and October. On the International Day of Preservation of Ozone Layer on 16 September 2008, a press conference on ozone layer protection was conducted. 4. “A Handbook for Environmental Journalist” was developed in cooperation with Environmental University ECO ASIA. 5.Quiz competition on ozone layer and climate change was organized among the school children, students and the members of TUNZA Mongolia on 2 September 2008. 6. Youth campaign titled “For protection of ozone layer” was organized during the 4th Tunza Neayen Conference. | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MON | PHA | 55 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-31 | 2010-07-31 |  |  | 85000 | 0 | 85000 | 60000 | 70.59% | 25000 | 0 | 25000 | 11050 | 0 | 7800 | 3250 | 0 | Initial mission to the country by the Activity Leader on 20-23 March 2008. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | MOR | SEV | 19 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-05-01 |  | 1996-05-01 | 1996-05-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | France | Project preparation for the formulation of a project to implement a recycling network for CFC-11, CFC-12 and HCFC-22 |  | AFR | MOR | REF | 19 | PRP | 2 | A | O | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1996-11-01 |  | 1997-04-01 | 1997-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé.
FIN | UNEP | Creation of Ozone Unit | Individual | AFR | MOR | SEV | 19 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1999-05-01 |  | 2004-07-01 | 2007-02-01 | 179000 | 0 | 179000 | 179000 | 100% | 0 | 0 | 0 | 23270 | 0 | 23270 | 0 | 0 | Project financially completed. |  |  | 1999-12-01 | [10 empty] | 1996 | Non Investment
FIN | UNDP | Phase out of CFCs in the manufacture of integral skin and cold cured molded PUF products at Maghreb Elastoplast | Individual | AFR | MOR | FOA | 20 | INV | 4 | A | O | D | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1997-09-01 | 2000-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | France | Technical assistance on alternative technologies for cold storage facilities |  | AFR | MOR | REF | 20 | TAS | 5 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1999-10-01 | 1999-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MOR | FOA | 21 | PRP | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 80000 | -13195 | 66805 | 66805 | 100% | 0 | 0 | 0 | 10400 | -1715 | 8685 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNIDO | Project formulation of investment projects in domestic refrigeration and methyl bromide sectors | Individual | AFR | MOR | SEV | 21 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-06-01 |  | 1999-09-01 | 2000-12-01 | 22150 | -1502 | 20648 | 20648 | 100% | 0 | 0 |  | 2880 | -200 | 2680 | 0 | 0 | FIN |  |  |  | 1999-02-01
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richbond S.A. | Individual | AFR | MOR | FOA | 22 | INV | 8 | A | O | I | CFC | 150 | 150 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-06-01 |  |  | 2004-12-01 | 470625 | -40036 | 430589 | 430589 | 100% | 0 | 0 | 0 | 61181 | -5205 | 55976 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation | Individual | AFR | MOR | SEV | 22 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Dolidol | Individual | AFR | MOR | FOA | 22 | INV | 10 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 1999-06-01 |  |  | 2003-12-01 | 475822 | -61553 | 414269 | 414269 | 100% | 0 | 0 | 0 | 61857 | -8002 | 53855 | 0 | 0 | Canceled in 2001. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNIDO | Demonstration project - four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization and low-dose chemicals in combination with an integrated pesticide management system | Individual | AFR | MOR | FUM | 22 | DEM | 11 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 2000-12-01 | 2002-08-01 | 487300 | -7238 | 480062 | 480062 | 100% | 0 | 0 |  | 63349 | -1040 | 62309 | 0 | 0 | FIN
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Sodiflex and Tiznit Plastic S.A. | Individual | AFR | MOR | FOA | 23 | INV | 12 | A | O | I | CFC | 85 | 85 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2005-09-01 | 517300 | -5023 | 512277 | 512277 | 100% | 0 | 0 | 0 | 67249 | -653 | 66596.01 | -0.01 | 0 | Canceled in 2004. Financially completed in 2005. | [13 empty] | 1997 | Investment
CLO | UNDP | Phase out of CFC in the manufacture fo flexible foam (slabstock) at Salidor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 13 | A | O | I | CFC | 48 | 48 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richdor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 14 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 62300 | 0 | 62300 | 62300 | 100% | 0 | 0 | 0 | 8099 | 0 | 8099 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam at Panaf Isolation S.A. | Individual | AFR | MOR | FOA | 23 | INV | 15 | A | O | I | CFC | 17.5 | 17.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-09-01 | 2001-12-01 | 137000 | -3191 | 133809 | 133809 | 100% | 0 | 0 | 0 | 17810 | -415 | 17395 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Molen Industrie S.A. | Individual | AFR | MOR | FOA | 23 | INV | 16 | A | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-12-01 | 1999-12-01 |  | 2002-06-01 | 2003-11-01 | 56070 | 0 | 56070 | 56070 | 100% | 0 | 0 | 0 | 7289 | 0 | 7289 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1997 | Investment
ONG | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | AFR | MOR | REF | 23 | TAS | 17 | A | O | I | CFC | 22 |  | 0 |  | 1997-11-01 |  | 1998-12-01 | 2009-12-01 |  |  | 355867 | 0 | 355867 | 4398.3921 | 1.236% | 351468.6079 |  | 100000 | 0 | 0 | 0 | 0 |  | This project encounters implementation difficulties as no institution accepts to host the R&R center. |  |  |  |  | 2002-11-01
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | AFR | MOR | REF | 23 | TRA | 18 | A | O | D |  | 0 |  | 0 |  | 1997-11-01 | 1999-02-01 | 1998-06-01 |  | 2000-12-01 | 2000-12-01 | 53361 | 0 | 53361 | 53361 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Mousse d'Or S.A. | Individual | AFR | MOR | FOA | 23 | INV | 19 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 280350 | 0 | 280350 | 280350 | 100% | 0 | 0 | 0 | 36446 | 0 | 36446 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector for Allom du Nord and others | Individual | AFR | MOR | REF | 24 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-09-01 | 2001-03-01 | 15000 | -4090 | 10910 | 10910 | 100% | 0 | 0 |  | 1950 | -534 | 1416 | 0 | 0 | FIN
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | AFR | MOR | FOA | 24 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1998 | Investment
CLO | UNDP | Conversion to LCD technology in the manufacture of flexible foam (slabstock) to replace CFC-11 at Bonbino Confort | Individual | AFR | MOR | FOA | 25 | INV | 22 | A | O | I | CFC | 90 | 90 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  |  | 2004-12-01 | 490200 | 0 | 490200 | 490200 | 100% | 0 | 0 | 0 | 63726 | 0 | 63726 | 0 | 0 | Canceled in 2004. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to HCFC-141b/water technology in the manufacture of rigid polyurethane spray foam at Batcomar S.A. | Individual | AFR | MOR | FOA | 25 | INV | 23 | A | O | I | CFC | 9.2 | 9.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-07-01 | 2002-03-01 | 72000 | -10826 | 61174 | 61174 | 100% | 0 | 0 | 0 | 9360 | -1407 | 7953 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Alom du Nord | Individual | AFR | MOR | REF | 25 | INV | 24 | A | O | I | CFC | 7.7 | 7.7 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-04-01 | 2002-09-01 | 99402 | -12788 | 86614 | 86614 | 100% | 0 | 0 |  | 12922 | -1680 | 11242 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Batinox | Individual | AFR | MOR | REF | 25 | INV | 25 | A | O | I | CFC | 4.5 | 4.5 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-05-01 | 2002-09-01 | 32920 | -341 | 32579 | 32579 | 100% | 0 | 0 |  | 4280 | -51 | 4229 | 0 | 0 | FIN
FIN | Germany | Three alternatives to the use of methyl bromide: enemy plants, organic amendments and grafting on resistant rootstocks in combination with an integrated pest management system in tomatoes and curcubits | Individual | AFR | MOR | FUM | 26 | DEM | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 2001-10-10 | 2003-10-01 | 229523 | 0 | 229523 | 229523 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to 41st ExCom | [13 empty] | 1997
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Smifam | Individual | AFR | MOR | REF | 26 | INV | 27 | A | O | I | CFC | 4.9 | 4.9 |  |  | 1998-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-04-01 | 2002-09-01 | 62447 | -2267 | 60180 | 60180 | 100% | 0 | 0 |  | 8118 | -307 | 7811 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (bananas) | Individual | AFR | MOR | FUM | 27 | PRP | 28 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -482 | 14518 | 14518 | 100% | 0 | 0 |  | 1950 | -66 | 1884 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (flowers) | Individual | AFR | MOR | FUM | 27 | PRP | 29 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -148 | 14852 | 14852 | 100% | 0 | 0 |  | 1950 | -22 | 1928 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | MOR | REF | 27 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-09-01 | 1999-12-01 |  | 2001-04-01 | 2001-10-01 | 7000 | -1517 | 5483 | 5483 | 100% | 0 | 0 |  | 910 | -198 | 712 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | MOR | ARS | 27 | PRP | 31 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -7939 | 12061 | 12061 | 100% | 0 | 0 |  | 2600 | -1035 | 1565 | 0 | 0 | FIN
COM | UNEP | Preparation of a refrigerant management plan | RMP | AFR | MOR | REF | 27 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-04-01 |  | 2007-12-01 |  | 30000 | 0 | 30000 | 25016 | 83.39% | 4984 | 0 | 4984 | 3900 | 0 | 3252.08 | 647.92 | 0 | Project completed | [13 empty] | 1999 | Non Investment
FIN | UNIDO | Conversion of HCFC-141b technology (rigid foam) and HFC-134a (refrigeration) in the manufacture of domestic refrigerators and freezers at Manar | Individual | AFR | MOR | REF | 29 | INV | 33 | A | O | R | CFC | 38.6 | 38.6 |  |  | 1999-11-01 | 2000-04-01 | 2000-07-01 |  | 1999-12-01 | 2000-11-01 | 434183 | 0 | 434183 | 434183 | 100% | 0 | 0 |  | 26051 | 0 | 26051 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Siafmo | Individual | AFR | MOR | REF | 29 | INV | 34 | A | O | I | CFC | 8.7 | 8.7 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 126240 | -3250 | 122990 | 122990 | 100% | 0 | 0 |  | 16411 | -448 | 15963 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Mafidec | Individual | AFR | MOR | REF | 29 | INV | 35 | A | O | I | CFC | 5.6 | 5.6 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 117360 | -7879 | 109481 | 109481 | 100% | 0 | 0 |  | 15257 | -1047 | 14210 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Sonyafroid | Individual | AFR | MOR | REF | 29 | INV | 36 | A | O | I | CFC | 13.1 | 13.1 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 275895 | -2567 | 273328 | 273328 | 100% | 0 | 0 |  | 35866 | -390 | 35476 | 0 | 0 | FIN
COM | France | Phase-out of methyl bromide use in the cut flower and banana production |  | AFR | MOR | FUM | 29 | INV | 37 | A | O | I | MBR | 61 |  | 0 |  | 1999-11-01 | 2001-05-29 | 2003-12-01 |  | 2008-07-01 |  | 1006652 | 0 | 1006652 | 928212.3142 | 92.21% | 78439.6858 |  | 78400 | 120732 | 0 | 111324.3992 | 9407.6008 |  | This project was implemented through UNIDO and is completed. Accounts are to be settled. | [6 empty] | 2005-04-01
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic commercial refrigeration equiment at Comafro | Individual | AFR | MOR | REF | 29 | INV | 38 | A | O | I | CFC | 6.5 | 6.5 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 134750 | -1142 | 133608 | 133608 | 100% | 0 | 0 |  | 17518 | -177 | 17341 | 0 | 0 | FIN
FIN | UNIDO | Preparation of phase-out project in the methyl bromide sector | Individual | AFR | MOR | FUM | 30 | PRP | 39 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -260 | 29740 | 29740 | 100% | 0 | 0 |  | 3900 | -40 | 3860 | 0 | 0 | FIN
FIN | Germany | Project preparation/technical assistance in the halon sector | Individual | AFR | MOR | HAL | 31 | PRP | 40 | A | O | I |  | 0 |  | 0 |  | 2000-07-01 | 2000-08-01 | 2001-01-01 |  | 2004-12-04 | 2005-06-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project proposal completed and with consent of NOU transferred to UNIDO for implementation. | [13 empty] | 1998
FIN | UNIDO | Phase out of methyl bromide for soil fumigation in strawberry production | Individual | AFR | MOR | FUM | 32 | INV | 41 | A | O | I | MBR | 155 | 155 |  |  | 2000-12-01 | 2001-01-01 | 2006-01-01 |  | 2007-12-01 | 2008-12-01 | 2189729 | 0 | 2189729 | 2189729 | 100% | 0 | 0 |  | 250870 | 0 | 250870 | 0 | 0 | Financial completion in Dec 2008. FIN: Total disbursement = Total approval.
COM | France | Technical assistance for cold storage equipment (training and demonstration project) |  | AFR | MOR | REF | 32 | TAS | 42 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2004-01-16 | 2003-01-01 |  | 2005-08-01 |  | 114337 | 0 | 114337 | 114405.1702 | 100.1% | -68.1702 |  | 0 | 5717 | 0 | 5720.4086 | -3.4086 |  | Project completed
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Interfer by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 43 | A | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 78973 | 0 | 78973 | 78973 | 100% | 0 | 0 | 0 | 10266 | 0 | 10266 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Engequife by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 44 | A | O | I | CFC | 7.2 | 7.2 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 56391 | -146 | 56245 | 56245 | 100% | 0 | 0 | 0 | 7331 | -19 | 7312 | 0 | 0 | Completed in 2003. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (first tranche) | Multi-Year | AFR | MOR | FUM | 34 | INV | 44 | A | O | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-10-01 | 2002-12-01 |  | 2005-09-01 | 2008-09-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 52000 | 0 | 52000 | 0 | 0 | Financial completion in Sep 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2001 | INV | 355.8 | 355.8 |  |  | Yes | N/A | N/A
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Climatisation et Froid Loudaya (CFL) | Individual | AFR | MOR | REF | 35 | INV | 45 | A | O | I | CFC | 15 | 15 |  |  | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 177312 | -847 | 176465 | 176465 | 100% | 0 | 0 |  | 23051 | -147 | 22904 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at First Clim Co. | Individual | AFR | MOR | REF | 35 | INV | 46 | A | O | I | CFC | 9 | 9 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 135258 | -980 | 134278 | 134278 | 100% | 0 | 0 |  | 17584 | -156 | 17428 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Etablissement Lahdar | Individual | AFR | MOR | REF | 35 | INV | 47 | A | O | I | CFC | 7.4 | 7.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 101451 | -1363 | 100088 | 100088 | 100% | 0 | 0 |  | 13189 | -198 | 12991 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Country programme update | Individual | AFR | MOR | SEV | 38 | CPG | 48 | A | O | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-12-01 | 2005-05-01 | 40000 | -1747 | 38253 | 38253 | 100% | 0 | 0 |  | 5200 | -235 | 4965 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MOR | SEV | 43 | INS | 49 | A | T | I | CFC | 12.8 | 0 | 0 | 0 | 2004-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the terminal umbrella group of commercial refrigeration manufactures. | Individual | AFR | MOR | REF | 43 | INV | 50 | A | O | I | CFC | 18.4 | 18.4 |  |  | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 359864 | 0 | 359864 | 359864 | 100% | 0 | 0 |  | 26990 | 0 | 26990 | 0 | 0 | FIN | [13 empty] | 2004 | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (balance of the first tranche) | Multi-Year | AFR | MOR | FUM | 44 | INV | 52 | A | O | I | MBR | 34.1 | 34.1 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-12-01 | 607513 | -236 | 607277 | 607277 | 100% | 0 | 0 |  | 45563 | -17 | 45546 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2004 | INV | 355.8 | 355.8 |  |  | Yes | N/A | N/A
FIN | UNIDO | Training and awareness workshop in the solvent and process agents (CTC & TCA ) sectors | Individual | AFR | MOR | SOL | 45 | TAS | 53 | A | O | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -591 | 39409 | 39409 | 100% | 0 | 0 |  | 3600 | -53 | 3547 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | INV
COM | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (third tranche) | Multi-Year | AFR | MOR | FUM | 47 | INV | 54 | A | O | I | MBR | 39 | 39 |  |  | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2008-12-01 |  | 1670995 | 0 | 1670995 | 1543642 | 92.38% | 127353 | 119705 | 119000 | 125325 | 0 | 115773 | 9552 | 8978 | Project completed in Dec 2008. | [13 empty] | 2005 | INV | 316.8 | 316.8 |  |  | Yes | N/A | N/A
COM | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fourth tranche) | Multi-Year | AFR | MOR | FUM | 50 | INV | 55 | A | O | I | MBR | 56.4 | 56.4 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-12-01 |  | 411633 | 0 | 411633 | 224190 | 54.46% | 187443 | 186003 | 150000 | 30872 | 0 | 16814 | 14058 | 13950 | Project completed in Dec 2008. | [13 empty] | 2006 | INV | 260.4 | 260.4 |  |  | Yes | N/A | N/A
COM | UNIDO | Project preparation for a methyl bromide phase-out plan (green beans and cucumber) | Individual | AFR | MOR | FUM | 51 | PRP | 56 | A | O | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-03-01 |  | 2008-06-01 |  | 35000 | 0 | 35000 | 34867 | 99.62% | 133 | 0 | 1 | 2625 | 0 | 2615 | 10 | 0 | Project completed in Jun 2008. | [13 empty] | 2007 | NON-INV
ONG | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MOR | SEV | 53 | INS | 57 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 | 2009-11-01 |  |  | 156000 | 0 | 156000 | 44230.13 | 28.35% | 111769.87 | 76500 | 111769.87 | 0 | 0 | 0 | 0 | 0 | NOU has been effective in coordinating implementation of remaining investment activities with UNIDO. NOU continued awarenss raising activities through dissemission of material and celebration of the International Ozone day. | [13 empty] | 2007 | Non Investment
ONG | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fifth tranche) | Multi-Year | AFR | MOR | FUM | 53 | INV | 58 | A | O | I | MBR | 78 | 68.4 |  |  | 2007-11-01 | 2008-02-01 | 2008-11-30 | 2009-03-01 |  |  | 424381 | 0 | 424381 | 343416 | 80.92% | 80965 | 54254 | 50000 | 31829 | 0 | 25756 | 6073 | 4069 | Project implemented according to workplan. In 2008 the expected reduction of consumption of methyl bromide is 68.4 ODP tonnes - 144 metric tonnes of MeBr. | [13 empty] | 2007 | INV | 182.4 | 182.4 |  |  | Yes | N/A | N/A
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | MOR | PHA | 55 | PRP | 59 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-12-01 |  |  | 150000 | 0 | 150000 | 5486 | 3.657% | 144514 | 435 | 70000 | 11250 | 0 | 411 | 10839 | 33 | National experts contracts were issued. Kick-off meeting under organization. | National consuntants hired for the preparation of the HPMP. The assignments include: • Assistance for policy and legislation; • Survey of HCFCs use and analysis of data collectes; • Consultation with national stackeholders in the data collection and analysis. Regarding the consultant hired for policy and legislation, main task is to assess and analyze the institutional framework, legislation, licensing and quota system regulating consumption of ozone depleting substances in Morocco with particular focus on HCFCs. Furthermore, the consultant is requested to assess the current national policies on climate change, chemical management and energy policies, as well as the CFCs phase out activities and lessons learned from previous ODS phase-out activities. Expected outputs: assessment of the current status of legislation and recommendations on necessary institutional and regulatory improvements to facilitate a smooth compliance with the HCFCs phase out obligations. | [12 empty] | 2008 | NON-INV
ONG | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (sixth tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 60 | A | O | I | MBR | 182.4 | 0 |  |  | 2008-11-01 |  | 2010-11-30 | 2010-11-01 |  |  | 398427 | 0 | 398427 | 0 | 0% | 398427 | 0 | 50000 | 29882 | 0 | 0 | 29882 | 0 | The project was approved at the 56th ExCom in Nov 2008 and will be implemented according to work plan. | [13 empty] | 2008 | INV | 96 | 96 |  |  | Not yet confirmed | N/A | N/A
ONG | UNIDO | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 61 | A | O | I | MBR | 35 | 0 |  |  | 2008-11-01 | 2008-12-01 | 2012-11-30 | 2012-11-01 |  |  | 690000 | 0 | 690000 | 13302 | 1.928% | 676698 | 0 | 300000 | 51750 | 0 | 998 | 50752 | 0 | The 2009 and 2010 action plans were agreed during a mission on the project site and a kick off stakeholder meeting. The national institution responsible for the project implementation was selected (APEFEL) and the contract with the center is under finalization. Among other, the following activities will be implemented in 2009: • Development of composting and biofumigation plant at CTT • Development of grafting technology for melon and other cucurbits at the existing grafting centers • Devote one green house at the CTT where necessary trials and demonstration activities will be organized. This activity will be carry-out in partnership with INRA • Organize a study tour to grafting and composting centers and technology providers to select the best technologies for Morocco. Results from that experience will give information on the establishment of a composting plant at the CTT (2009) and on how to spread the technology within the country (year 2010) | [13 empty] | 2008 | INV | 106.2 | 106.2 |  |  | Not yet confirmed | N/A | N/A
ONG | Italy | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-year | AFR | MOR | FUM | 56 | INV | 62 | A | O | I | MBR | 15 |  | 0 |  | 2008-11-01 |  | 2012-11-01 | 2012-11-01 |  |  | 310000 | 0 | 310000 |  | 0% | 310000 |  | 50000 | 40300 | 0 | 0 | 40300 | 0 | The 2009 and 2010 action plans were agreed during a mission on the project site and a chick off stakeholder meeting. The national institution responsible for the project implementation was selected (APEFEL) and the contract with the center is under finalization. Among other, the following activities will be implemented in 2009: • Development of composting and biofumigation plant at CTT • Development of grafting technology for melon and other cucurbits at the existing grafting centers • Devote one green house at the CTT where necessary trials and demonstration activities will be organized. This activity will be carry-out in partnership with INRA • Organize a study tour to grafting and composting centers and technology providers to select the best technologies for Morocco. Results from that experience will give information on the establishment of a composting plant at the CTT (2009) and on how to spread the technology within the country (year 2010) |  | 2008 | [11 empty] | 2008 | Investment | 260.9 | 260.9
FIN | UNEP | Country programme preparation | Individual | AFR | MOZ | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNIDO | Preparation of projects in commercial refrigeration | Individual | AFR | MOZ | REF | 15 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-08-01 | 1998-08-01 | 15000 | -1697 | 13303 | 13303 | 100% | 0 | 0 |  | 1950 | -223 | 1727 | 0 | 0 | FIN
FIN | UNEP | Institutional strengthening | Individual | AFR | MOZ | SEV | 15 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1997-12-01 |  | 2003-12-01 | 2005-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 12012 | 0 | 12012 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
CLO | UNIDO | Phasing out of CFCs at INDATEC/Industria de aplicacoes technico-domesticas Ltd. | Individual | AFR | MOZ | REF | 18 | INV | 4 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1997-03-01 |  |  | 2002-04-01 | 581515 | -246871 | 334644 | 334644 | 100% | 0 | 0 |  | 75597 | -32162 | 43435 | 0 | 0 | CLO |  |  | 1997-12-01 | 1999-11-01
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | MOZ | REF | 21 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -1643 | 18357 | 18357 | 100% | 0 | 0 | 0 | 2600 | -214 | 2386 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MOZ | REF | 22 | TAS | 6 | A | O | I | CFC | 6.9 | 6.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 115809 | -138 | 115671 | 115671 | 100% | 0 | 0 | 0 | 15055 | -18 | 15037 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MOZ | REF | 26 | TAS | 7 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved. | [13 empty] | 2000
CLO | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (tobacco) | Individual | AFR | MOZ | FUM | 27 | PRP | 8 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 1999 | Investment
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | MOZ | REF | 37 | PRP | 9 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | MOZ | SEV | 41 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-03-01 | 2005-12-01 |  | 2007-01-01 | 2008-12-01 | 80080 | 0 | 80080 | 80080 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
ONG | France | Refrigerant management plan update | RMP Update | AFR | MOZ | REF | 44 | TAS | 12 | A | O | I | CFC | 15.5 |  | 0 |  | 2004-12-01 | 2005-12-13 | 2007-12-01 | 2009-07-01 |  |  | 104512 | 0 | 104512 | 84600 | 80.95% | 19912 |  | 19912 | 13587 | 0 | 10998.3562 | 2588.6438 |  | The French contribution is implmented by GTZ PROKLIMA. With the approval of the ODS regulations the NOU could start on customs trainings. 2 customs trainings have so far been conducted. Necessary equipment including all identifiers are now available for use.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MOZ | PHA | 50 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-11-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MOZ | SEV | 50 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2008-11-01 | 2009-03-01 |  |  | 80800 | 0 | 80800 | 66817.35 | 82.69% | 13982.65 | 10100 | 13982.65 | 0 | 0 | 0 | 0 | 0 | MOU signed with country. Country approved ODS Regulations, prepared TPMP, conducted trainings for customs officers and refrigeration technicians, produced and distributed awareness materials and celebrated Ozone Day. Project completed and new phase approv | [13 empty] | 2006 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MOZ | PHA | 55 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | MOU signed with the country awaiting first payment. Country identified national experts for the survey, finalised HCFC survey questionnaire and TORs for the survey and drafting of HPMP | [13 empty] | 2008
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 75000 | 9750 | 0 | 0 | 9750 | 0 | New in 2008 and implementation started in 2009 | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | INV | 15 | N | O | I | CFC | 2.3 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-01 | 2010-11-01 |  |  | 100500 | 0 | 100500 | 0 | 0% | 100500 | 0 | 20100 | 9045 | 0 | 0 | 9045 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MYA | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-09 | 1995-06-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. |  |  |  | 1999-05-01 | [9 empty] | 1994 | Non Investment
ONG | UNEP | Establishment of the national Ozone Cell for implementing the phase out of ODSs under the Montreal Protocol | Individual | ASP | MYA | SEV | 29 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2007-07-01 | 2002-12-01 | 2009-12-01 |  |  | 76000 | 0 | 76000 | 20000 | 26.32% | 56000 | 0 | 56000 | 9880 | 0 | 2600 | 7280 | 0 | UNEP had a high level mission on Feb 2009 wherein plans for 2009 activities were discussed; Organise a sub regional Ozone Day in Myanmar on 16th September 2009 and invite NOOs of neighbouring countries India, China, Thailand, Bangladesh and Laos for this celebration to bolster south south initiatives for Myanmar. 2. Back to back UNIDO will organise a refresher training for technicians from their funds. 3. CAP to organise a customs training.4. San Win to visit Bangkok office for two days on way to GC for his capacity building. | [13 empty] | 1999 | Non Investment
COM | UNEP | Preparation of a refrigerant management plan | RMP | ASP | MYA | REF | 29 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2000-12-01 |  | 2005-04-01 |  | 30000 | 0 | 30000 | 5134 | 17.11% | 24866 | 0 | 24866 | 3900 | 0 | 667.42 | 3232.58 | 0 | Project completed | [13 empty] | 1999 | Non Investment
CLO | UNDP | Formulation of the investment components of theRMP | Individual | ASP | MYA | REF | 39 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  |  | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
ONG | UNEP | Implementation of the RMP: preparation of ozone regulations for control of ODSs | Individual | ASP | MYA | REF | 45 | TAS | 5 | A | O | I | CFC | 5.2 | 0 | 0 | 0 | 2005-04-01 | 2008-05-01 | 2005-11-01 | 2009-12-01 |  |  | 13000 | 0 | 13000 | 12999.53 | 100% | 0.47 | 0 | 0.47 | 1690 | 0 | 1689.9389 | 0.0611 | 0 | Myanmar signed the MOU in February 2008 | [13 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring implementation of the RMP | Individual | ASP | MYA | REF | 45 | TAS | 6 | A | O | I | CFC | 8.8 | 0 | 0 | 0 | 2005-04-01 | 2008-03-01 | 2008-04-01 | 2009-12-01 |  |  | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 2860 | 0 | 2860 | 0 | 0 | MOU was finally signed by NCEA in February 2008. NCEA requested the fund to be transfered during April 2008 to coincide with their fiscal year calendar. The national workshop is tentatively scheduled during June 2008. | [13 empty] | 2005 | Non Investment
FIN | UNIDO | Implementation of the RMP: establishing conversion practice of domestic refrigerators | Individual | ASP | MYA | REF | 45 | TAS | 7 | A | O | I | CFC | 32.1 | 32.1 |  |  | 2005-04-01 | 2005-10-01 | 2006-10-01 |  | 2007-11-01 | 2008-07-01 | 80000 | -15 | 79985 | 79985 | 100% | 0 | 0 |  | 7200 | -1 | 7199 | 0 | 0 | Financial completion in Jul 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2005 | INV
ONG | UNEP | Preparation of a terminal phase-out management plan | RMP | ASP | MYA | PHA | 55 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2008-12-31 | 2009-12-31 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UNEP had a high level mission on Feb 2009 wherein plans for 2009 activities were discussed; Organise a sub regional Ozone Day in Myanmar on 16th September 2009 and invite NOOs of neighbouring countries India, China, Thailand, Bangladesh and Laos for this celebration to bolster south south initiatives for Myanmar. 2. Back to back UNIDO will organise a refresher training for technicians from their funds. 3. CAP to organise a customs training.4. San Win to visit Bangkok office for two days on way to GC for his capacity building. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | NAM | SEV | 15 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-04-01 | 1996-03-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of a National Ozone Office | Individual | AFR | NAM | SEV | 18 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 2000-02-01 | 2001-12-12 | 61765 | 0 | 61765 | 61765 | 100% | 0 | 0 | 0 | 8029.45 | 0 | 8029.45 | 0 | 0 | Project financially completed. |  |  | 1998-11-01 | [10 empty] | 1995 | Non Investment
FIN | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | NAM | REF | 20 | TRA | 3 | A | O | I | CFC | 5.4 | 5.4 | 0 |  | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-10-01 | 1999-10-01 | 103440 | 0 | 103440 | 103440 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1997
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | NAM | REF | 23 | PRP | 4 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1999
FIN | Germany | Recuperation and recycling of CFC-12 integrated with the introduction of hydrocarbon technology in the service sector | Individual | AFR | NAM | REF | 24 | TAS | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-06-01 |  | 1998-06-01 | 2000-01-01 | 34400 | -244 | 34156 | 34156 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted | [13 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | NAM | REF | 26 | TAS | 6 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. TPMP approved in Dec 2003 | [13 empty] | 2001
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | NAM | SEV | 31 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 41177 | 0 | 41177 | 41177 | 100% | 0 | 0 | 0 | 5353.01 | 0 | 5353.01 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | NAM | PHA | 37 | PRP | 8 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-09-01 | 2004-08-01 | 50250 | 0 | 50250 | 50250 | 100% | 0 | 0 | 0 | 6533 | 0 | 6533 | 0 | 0 | Project completed and TPMP approved at 41st Excom | [13 empty] | 1998
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | NAM | SEV | 41 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 53530 | 0 | 53530 | 53530 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | Germany | Terminal phase-out management plan for CFCs | Multi-Year | AFR | NAM | PHA | 41 | INV | 10 | A | O | I | CFC | 9 | 10.5 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 | 2008-05-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Namibia continues to maintain zero imports in keeping with the TPMP targets. In 2007, 3 additional customs training were organised to maintain vigilance and update the ASCUYDA ++ system. Incentive scheme is being implemented successfully with 42 cold rooms being retrofitted mainly at hospitals and schools (hostels). A total of 312 kgs of ODS has been phased out | [10 empty] | 2006-12-06 |  |  | 2002 |  | 8 | 0 |  |  | Yes
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | NAM | SEV | 47 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 |  | 60000 | 0 | 60000 | 53689.58 | 89.48% | 6310.42 | 6310.36 | 6310.42 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2005 | Non Investment
ONG | Germany | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | NAM | PHA | 50 | INV | 12 | A | O | I | CFC | 3 | 3 | 0 |  | 2006-11-01 | 2007-04-01 | 2008-11-01 | 2009-06-01 |  |  | 92500 | 0 | 92500 | 87600 | 94.7% | 4900 | 0 | 4900 | 12025 | 0 | 11388 | 637 | 0 | Project is very near completion last conversions under the incentive scheme are being completed. A total of 78 conversions were done | [15 empty] | 0 | 0 |  |  | Yes
ONG | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NAM | SEV | 53 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 19500.38 | 32.5% | 40499.62 | 40500 | 40499.62 | 0 | 0 | 0 | 0 | 0 | MOU signed with country, NOU implemented activities including conducting trainings for customs officers, refrigeration technicians and produced awareness materials | [13 empty] | 2007 | Non Investment
ONG | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | NAM | PHA | 55 | PRP | 14 | A | O | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 | 2009-10-01 |  |  | 30000 | 0 | 30000 | 27435 | 91.45% | 2565 | 0 | 2565 | 3900 | 0 | 3566.55 | 333.45 | 0 | HCFC survey countrywide has been started. 8 consultants have been hired for this task. The regulations are being currently reviewed by legal experts and recommendations would be taken forward.
COM | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NAU | REF | 44 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2008-12-01 |  | 8000 | 0 | 8000 | 6000 | 75% | 2000 | 0 | 2000 | 1040 | 0 | 780 | 260 | 0 | Project completed in December 2008. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NAU | SEV | 44 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NAU | REF | 44 | TAS | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-07 |  | 14000 | 0 | 14000 | 7123 | 50.88% | 6877 | 0 | 6877 | 1820 | 0 | 925.99 | 894.01 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NAU | SEV | 50 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2008-11-01 |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008. UNEP is discussing the closure of the Regional Strategy and has requested SPREP to disburse all remaining IS funding to the country. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | NAU | SEV | 53 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008. First disbursement will start after country receive final payment of previous IS phase from SPREP. | [13 empty] | 2007 | Non Investment
FIN | UNEP | Country programme preparation | Individual | ASP | NEP | SEV | 19 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | ASP | NEP | REF | 24 | PRP | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-06-01 | 2000-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Establishment of an Ozone Unit | Individual | ASP | NEP | SEV | 26 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-10 | 2001-12-01 |  | 2002-05-01 | 2003-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 | 0 | 8060 | 0 | 8060 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNDP | Preparation of a refrigeration recovery and recycling project | Individual | ASP | NEP | REF | 27 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-07-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | UNDP | Project preparation in the commercial refrigeration subsector | Individual | ASP | NEP | REF | 27 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2001-12-01 | 20000 | -15000 | 5000 | 5000 | 100% | 0 | 0 | 0 | 2600 | -1950 | 650 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | UNEP | Refrigerant management plan: policy development and related information dissemination | Individual | ASP | NEP | REF | 28 | TAS | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-08-03 |  | 2001-12-01 | 2002-10-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 | 0 | 0 | 780 | 0 | 780 | 0 | 0 | Project financially completed. | [5 empty] | 2001-12-01 | [7 empty] | 1999 | Non Investment
FIN | UNDP | Implementation of the RMP: monitoring activities included in the RMP | RMP-Component | ASP | NEP | REF | 28 | TAS | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2005-01-01 | 2002-02-01 |  | 2005-12-01 | 2007-03-01 | 8894 | -3328 | 5566 | 5565 | 99.98% | 1 | 0 | 0 | 1156 | -433 | 722.8701 | 0.1299 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | ASP | NEP | REF | 28 | TAS | 8 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2003-10-01 | 2003-11-01 | 88577 | -1 | 88576 | 88576 | 100% | 0 | 0 | 0 | 11515 | 0 | 11515 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNEP | Refrigerant management plan: training of trainers in refrigeration | Individual | ASP | NEP | REF | 28 | TRA | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-02-03 |  | 2004-03-01 | 2004-10-01 | 70000 | -29000 | 41000 | 41000 | 100% | 0 | 0 | 0 | 9100 | -3770 | 5330 | 0 | 0 | Project financially completed. | $ 29,000 plus $ 3,770 PSC returned Excom 46 | [12 empty] | 1999 | Non Investment
FIN | UNEP | Refrigerant management plan: training in monitoring and control of CFC and establishment of import/export licensing system | Individual | ASP | NEP | REF | 28 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2001-08-02 |  | 2004-07-01 | 2006-02-01 | 44400 | -19400 | 25000 | 25000 | 100% | 0 | 0 | 0 | 5772 | -2522 | 3250 | 0 | 0 | Project financially completed. | $ 19,400 plus $ 2,522 returned to ExCom 52 |  |  |  |  | 2002-12-02 | [7 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | NEP | SEV | 37 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-08-01 | 2007-06-01 | 53733 | 0 | 53733 | 53733 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Project preparation for the refrigerant management plan update | Individual | ASP | NEP | REF | 43 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2005-07-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | NEP | SEV | 44 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Implementation of the RMP: assistance to remain in compliance with the Montreal Protocol | Individual | ASP | NEP | REF | 44 | TAS | 15 | A | O | I | CFC | 5.4 | 5.42 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2007-12-01 |  | 2008-01-01 | 2008-10-01 | 51440 | 0 | 51440 | 51440 | 100% | 0 | 0 | 0 | 6687.2002 | 0 | 6687.2 | 0.00019531 | 0 | Project complted in May 2008 & financially completed. NOU initiated discussion with Indian Ozone Cell on border dialogue and agreed that the dialogue would be organized in the second half of 2008. · NOU maintained the inventory of the seized CFCs and visited the site in January 2008 - Final reports (progress report and expenditure reports) received | [13 empty] | 2004 | Non Investment
ONG | UNDP | Implementation of the RMP: recovery and recycling, retrofit and their monitoring | RMP-Component | ASP | NEP | REF | 44 | TAS | 16 | N | O | I | CFC | 12.1 | 4 | 0 | 0 | 2004-12-01 |  | 2007-12-01 | 2010-01-01 |  |  | 57495 | 0 | 57495 | 0 | 0% | 57495 | 13912 | 11499 | 5175 | 0 | 0 | 5175 | 1252.1889 | Procurement of some of the equipment has been completed in 2008 with the remainder to be completed in early 2009. | [13 empty] | 2004 | Investment
FIN | UNEP | Technical assistance in CTC management | Individual | ASP | NEP | SOL | 47 | TAS | 17 | A | O | I | CTC | 0.9 | 0.9 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-01-01 | 2008-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project completed in December 2008. Another awareness programme was organized in November 2007 and widely press release on CTC was published in December 2007. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | NEP | SEV | 50 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2008-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008. TPMP Implementation: - Three workshops were organized on good practices in refrigeration wherein 97 technicians were trained. - One workshop was organized for customs officers selected from the main entry points identified wherein 35 officers were trained | [13 empty] | 2006 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | NEP | PHA | 50 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-07 | 2007-11-01 |  | 2008-01-01 | 2008-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed in January 2008 & financially completed | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | NEP | PHA | 50 | PRP | 20 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-07-01 |  | 15000 | 0 | 15000 | 4854 | 32.36% | 10146 | 0 | 10146 | 1125 | 0 | 364.05 | 760.95 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | NEP | PHA | 52 | TAS | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-04-01 | 2008-07-01 | 2009-12-01 |  |  | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | The technicians training workshop on good practices was organized in Pokhara during 19-21 January 2008 with 47 participants from this region. Two more technicians training workshops on good practices were organized separately during 17-20 September 2008 and 26-28 October 2008 with 50 technicians trained. The train-the-trainer workshop was organized mainly focusing on retrofitting with HC alternative during 13-15 May 2008 in Katmandu with 30 Participants. Prof. Agarwal from India conducted the training under south-south cooperation between Nepal and India. Support the Nepal Refrigeration and Electro Mechanical Association organized its General Assembly on 15 January 2008 and released a booklet with technical information of alternatives, phaseout situation, HCFC phaseout schedule etc as well as contact details of its full members. Public awareness meeting among the workshop stakeholders from different parts of the country was organized on Ozone Day 2008 in Pokhara. MDI workshop was organized on 22nd October 2008 in which 50 participants participated. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | NEP | PHA | 52 | INV | 22 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 |  | 2009-07-01 | 2010-07-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 15000 | 6750 | 0 | 0 | 6750 | 0 | The TPMP project document was signed in September 2008. The equipment list and detail specification has been developed and will be put for tender in 2009. | [13 empty] | 2007 | Investment | 12 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | NEP | PHA | 55 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2010-12-01 |  |  | 85000 | 0 | 85000 | 60000 | 70.59% | 25000 | 0 | 25000 | 11050 | 0 | 7800 | 3250 | 0 | Newly approved project. Country is also actively pursuing ratification of Copenhangen Amendment. | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | NEP | SEV | 56 | INS | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | Newly approved project in Nov 2008. The agreement with the country was signed in December 2008. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | NER | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1994-12-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Creation of an Ozone Secretariat | Individual | AFR | NER | SEV | 15 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1997-12-01 |  | 1999-05-01 | 1999-10-01 | 74800 | 0 | 74800 | 74800 | 100% | 0 | 0 | 0 | 9724 | 0 | 9724 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | NER | REF | 21 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-03-01 | 2002-03-01 | 20000 | -3085 | 16915 | 16915 | 100% | 0 | 0 | 0 | 2600 | -401 | 2199 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | NER | SEV | 26 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-28 | 2000-12-01 |  | 2001-06-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the RMP: Customs officers training programme | Individual | AFR | NER | REF | 27 | TAS | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-08-01 | 2000-10-02 |  | 2003-12-01 | 2005-02-01 | 63000 | -24000 | 39000 | 39000 | 100% | 0 | 0 | 0 | 8190 | -3120 | 5070 | 0 | 0 | Project financially completed. | $ 24,000 plus $ 3,120 PSC returned Excom 46 | [12 empty] | 1999 | Non Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | NER | REF | 27 | TAS | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 2002-01-01 | 2001-04-01 |  | 2004-12-01 | 2005-11-01 | 15455 | -3305 | 12150 | 12150 | 100% | 0 | 0 | 0 | 2009 | -430 | 1579 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 1999 | Non-Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | NER | REF | 27 | TAS | 7 | A | O | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2001-04-01 |  | 2003-08-01 | 2003-10-01 | 87603 | -8661 | 78942 | 78942 | 100% | 0 | 0 | 0 | 11388 | -1126 | 10262 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNEP | Implementation of the RMP: Train the trainers programme in the refrigeration sector | Individual | AFR | NER | REF | 27 | TAS | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-10-02 |  | 2002-05-01 | 2003-05-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 | 0 | 5395 | 0 | 5395 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | NER | SEV | 33 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | NER | REF | 37 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-11-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNEP | Policy and technical assistance | Individual | AFR | NER | SEV | 37 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2003-08-01 |  | 2004-01-01 | 2007-01-01 | 10000 | -1995 | 8005 | 8005 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 1,995 returned to ExCom 50 | [12 empty] | 2002 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | NER | SEV | 41 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Implementation of the RMP update: training for customs technicians | Individual | AFR | NER | REF | 42 | TRA | 13 | A | O | I | CFC | 66 | 6.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2007-04-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Implementation of the RMP update: train the trainer programme for refrigeration service technicians | Individual | AFR | NER | REF | 42 | TRA | 14 | A | O | I | CFC | 14.6 | 14.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-10-01 |  | 2006-12-01 | 2008-06-01 | 55747 | 0 | 55747 | 54246.48 | 97.31% | 1500.52 | 0 | 0 | 7247 | 0 | 7052.0424 | 194.9576 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Implementation of the RMP update: monitoring of the activities | Individual | AFR | NER | REF | 42 | TAS | 15 | A | O | I | CFC | 6 | 6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2006-04-01 |  | 2007-04-01 | 2007-12-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 | 0 | 2990 | 0 | 2990 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NER | SEV | 47 | INS | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
TRF | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 48 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 |  | 2007-04-01 |  |  | 2007-12-01 | 12000 | -12000 | 0 | 0 |  | 0 | 0 | 0 | 900 | -900 | 0 | 0 | 0 | Transferred in 2007. | [13 empty] | 2006 | Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | NER | PHA | 48 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-11-01 |  | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project completed in November 2008 after submission of TPMP document | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | NER | SEV | 53 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 | 2009-11-01 |  |  | 64827 | 0 | 64827 | 20382.43 | 31.44% | 44444.57 | 43900 | 44444.57 | 0 | 0 | 0 | 0 | 0 | First payment done in March 2008 | [13 empty] | 2007 | Non Investment
COM | UNIDO | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 53 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2008-12-01 |  | 12000 | 0 | 12000 | 4142 | 34.52% | 7858 | 1327 | 1000 | 900 | 0 | 311 | 589 | 100 | Project completed in Dec 2008. | [13 empty] | 2007 | NON-INV
ONG | UNEP | Terminal phase out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | TAS | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2010-03-31 | 2010-03-31 |  |  | 81000 | 0 | 81000 | 55999.53 | 69.14% | 25000.47 | 25000 | 25000.47 | 10530 | 0 | 7279.9389 | 3250.0611 | 3250 | Signature of the MoU for the implementation of the TPMP in September 2008 | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | INV | 21 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 |  | 2010-03-31 | 2010-03-01 |  |  | 131000 | 0 | 131000 | 0 | 0% | 131000 | 2991 | 70000 | 11790 | 0 | 0 | 11790 | 269 | Implementation modalities have been agreed upon. Technical specifications for equipment purchase were prepared and agreed upon with UNEP and NOU. The procurement process was initiated and the delivery of equipment is expected in 2nd/3rd Quarter 2009. | [13 empty] | 2008 | INV | 4.8 | 4.8 |  |  | Not yet confirmed | N/A | N/A
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | NER | PHA | 55 | PRP | 22 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 5440 | 6.4% | 79560 | 17 | 20000 | 6375 | 0 | 408 | 5967 | 1 | National expert was contracted and National survey is on-going for the preparation of the HPMP. | The job description of the consultant addresses survey of the existing legislation and needed measures to extend its provisions on HCFCs. The organization of the workshop is under preparation , the activity will take place in June 2009 | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | LAC | NIC | SEV | 13 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-22 | 1995-10-01 |  | 1996-11-01 | 1999-03-01 | 40000 | -3825 | 36175 | 36175 | 100% | 0 | 0 | 0 | 5200 | -497.25 | 4702.75 | 0 | 0 | Project financially completed. | $ 3,825 plus $ 497 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNIDO | Project formulation of investment projects in the refrigeration sector | Individual | LAC | NIC | REF | 21 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-08-01 |  | 1998-05-01 | 2001-12-01 | 50000 | -8349 | 41651 | 41651 | 100% | 0 | 0 |  | 6500 | -1094 | 5406 | 0 | 0 | FIN
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | NIC | SEV | 22 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2002-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. |  |  |  | 2000-05-01 | [9 empty] | 1997 | Non Investment
CLO | UNIDO | Preparation of refrigerant management plan | Individual | LAC | NIC | REF | 24 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 |  | 1999-04-01 |  |  | 2001-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Fogel S.A. in the manufacture of commercial refrigeration equipment | Individual | LAC | NIC | REF | 25 | INV | 5 | A | O | R | CFC | 9.6 | 9.6 |  |  | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 1999-12-01 | 2001-03-01 | 130027 | 0 | 130027 | 130027 | 100% | 0 | 0 |  | 16904 | -22 | 16882 | 0 | 0 | FIN
COM | Finland | Implementation of the RMP: assistance in the design of policies and regulations | Individual | LAC | NIC | REF | 25 | TAS | 6 | A | O | I | CFC | 12.8 |  | 0 |  | 1998-07-01 | 2001-09-01 | 2000-07-01 |  | 2005-12-01 |  | 225430 | 0 | 225430 | 148575 | 65.91% | 76855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1998
FIN | UNIDO | Preparation of a project for the phase-out of methyl bromide soil fumigation | Individual | LAC | NIC | FUM | 34 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-05-01 | 2003-12-01 | 30000 | -27242 | 2758 | 2758 | 100% | 0 | 0 |  | 3900 | -3542 | 358 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | NIC | SEV | 31 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2002-08-01 |  | 2003-09-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | NIC | SEV | 39 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-10-01 | 2005-04-01 |  | 2007-03-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Preparation of the RMP update proposal | RMP update | LAC | NIC | REF | 41 | PRP | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2004-12-01 |  | 2005-02-01 | 2007-01-01 | 15000 | -900 | 14100 | 14100 | 100% | 0 | 0 | 0 | 1950 | -117 | 1833 | 0 | 0 | Project financially completed. | $ 900 plus $ 117 returned to ExCom 50 | [12 empty] | 2003 | Non Investment
FIN | UNDP | Preparation of the RMP update proposal (investment component) | RMP-Component | LAC | NIC | REF | 41 | PRP | 10 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-11-01 | 15000 | 0 | 15000 | 14964 | 99.76% | 36 | 0 | 0 | 1125 | 0 | 1122.3 | 2.7 | 0 | Completed in 2005. Financially Completed in 2008. | [13 empty] | 2003 | Investment
COM | UNDP | Project preparation for the formulation of transitional strategy for aerosol inhalant drug products | Individual | LAC | NIC | ARS | 42 | PRP | 11 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-07-01 | 2005-04-01 |  | 2008-03-01 |  | 30000 | 0 | 30000 | 29956 | 99.85% | 44 | 0 | 44 | 2250 | 0 | 2246.7 | 3.3 | 0 | Completed in 2008. MDI transitional strategy was presented to ExCom 56. | [13 empty] | 2004 | Investment
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | NIC | FUM | 45 | TAS | 12 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | -275 | 29725 | 29725 | 100% | 0 | 0 |  | 2700 | -25 | 2675 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | NON-INV
COM | UNDP | Implementation of the RMP update: incentive programme to promote good practices in refrigeration | RMP-Component | LAC | NIC | REF | 45 | TAS | 13 | N | O | I | CFC | 35.2 | 35.2 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment
ONG | UNEP | Implementation of the RMP update: licensing and certification system for refrigeration technicians | Individual | LAC | NIC | REF | 45 | TRA | 14 | A | O | I | CFC | 16.6 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2008-04-01 | 2009-06-01 |  |  | 40000 | 0 | 40000 | 35000 | 87.5% | 5000 | 5000 | 5000 | 5200 | 0 | 4550 | 650 | 650 | A total of 270 technicians have been certified in 13 training courses along this year by the national training institution called CECNA. Second disbursement was issued and funds available at country level per submission of progress and finance report. | [13 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP update: programme for prevention of illegal CFC trade | Individual | LAC | NIC | REF | 45 | TAS | 15 | A | O | I | CFC | 6.2 | 0 | 0 | 0 | 2005-04-01 | 2007-03-01 | 2008-04-01 | 2009-06-01 |  |  | 15000 | 0 | 15000 | 9000 | 60% | 6000 | 6000 | 6000 | 1950 | 0 | 1170 | 780 | 780 | Coordination meeting among NOU and other Minsitries were held. ODS new Decree is being prepared in order to incorporate enfrocement lesson learnts as well as all ODS. Second disbursement was issued and funds availalble at country level per submission of progress and finance reports. | [13 empty] | 2005 | Non Investment
ONG | UNEP | Implementation of the RMP update: monitoring the activities of the RMP | Individual | LAC | NIC | REF | 45 | TAS | 16 | A | O | I | CFC | 12.4 | 0 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2008-04-01 | 2009-06-01 |  |  | 30000 | 0 | 30000 | 28935 | 96.45% | 1065 | 0 | 1065 | 3900 | 0 | 3761.55 | 138.45 | 0 | Cleaner Prdouction Center of Nicaragua was contracted to develop a market study about remainign CFC use and consumption, which was delivered to the Government authorities to assess and include in its monitoring and control system. Second disbursement released and funds available country level to afford 2008 activities. Interim progress and financial reports for each of the RMP components received. | [13 empty] | 2005 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | NIC | PHA | 49 | PRP | 18 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-07-01 |  | 2008-09-01 |  | 15000 | 0 | 15000 | 13958 | 93.05% | 1042 | 240 | 1042 | 1125 | 0 | 1046.85 | 78.15 | 18 | Completed in 2008. TPMP was successfully presented and approved to ExCom 56 | [13 empty] | 2006 | Investment
ONG | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | NIC | PHA | 49 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-06-01 | 2007-07-31 | 2009-03-31 |  |  | 15000 | 0 | 15000 | 7750 | 51.67% | 7250 | 7250 | 7250 | 1950 | 0 | 1007.5 | 942.5 | 942.5 | TPMP resulting from this activity was approved at 56 ExCom meeting. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | NIC | SEV | 49 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-06-30 | 2009-09-30 |  |  | 60000 | 0 | 60000 | 24012.69 | 40.02% | 35987.31 | 12000 | 35987.31 | 0 | 0 | 0 | 0 | 0 | Support from the IS project has been mainly in the areas of public awareness, assistance to government stakeholders and strengthening links with institutions and other Montreal Protocol Party. In relation to outreach activities, the NOU carried out an artistic project of a mural around the ozone layer which was exhibited during the celebrations of the World Environment Day, and several interviews for TV newscast were held on the Ozone Layer Day. The NOO has attended several international and regional meetings. As a result, Nicaragua was recently postulated in a position within the structures of the Montreal Protocol, gaining further representation at the Implementation Committee for Latin America. Finally the IS project has assisted in the work of other project such as the RMP/TPMP and prepared ODS data reporting. | [13 empty] | 2006 | Non Investment
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | NIC | PHA | 55 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 2853 | 3.356% | 82147 | 683 | 82000 | 6375 | 0 | 214 | 6161 | 51 | The survey of HCFC is being carried out by a national institution (National Cleaner Production Centre) in coordination with the NOU. An international consultant has been contracted for the preparation of the project document. The project is planned to be submitted at the first ExCom in 2010. | The consultant is leading the preparation of the HPMP, guiding the survey and the NOU in legislation and other issues. The initial workshop was carried out in April. The NOU is working on the legislation with the support of another consultant. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 130000 | 0 | 130000 | 0 | 0% | 130000 | 0 | 130000 | 16900 | 0 | 0 | 16900 | 0 | Project recently approved. Preliminary discussions for project implementation and further arrangements are being set. Funding agreement (SSFA) currently being negotiated with the country. A mission to the country was carried out by UNEP officers in order to define the first POA of the project. | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | INV | 23 | N | O | I | CFC | 3.7 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-01 | 2010-11-01 |  |  | 320000 | 0 | 320000 | 0 | 0% | 320000 | 0 | 64000 | 24000 | 0 | 0 | 24000 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNDP | National seminar on industry and protection of the ozone layer | Individual | AFR | NIR | SEV | 04 | TRA | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-11-01 |  | 1992-12-01 | 1997-12-01 | 49650 | -23201 | 26449 | 26449 | 100% | 0 | 0 | 0 | 6455 | -3016 | 3439 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Country programme preparation (1991) | Individual | AFR | NIR | SEV | 04 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-02-01 |  | 1991-12-01 | 1991-12-01 | 129981 | -44959 | 85022 | 85022 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1992) | Individual | AFR | NIR | SEV | 06 | CPG | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 271255 | -214838 | 56417 | 56417 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1992) |  | AFR | NIR | SEV | 06 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 144078 | -144078 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1993) |  | AFR | NIR | SEV | 09 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1994-03-01 |  |  | 1993-12-01 | 62500 | -62500 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening | Individual | AFR | NIR | SEV | 09 | INS | 6 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-01-01 | 1996-03-01 |  | 2001-01-01 | 2003-09-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1993 | Non-Investment
FIN | UNIDO | Preparation of CFC phase out strategy for refrigeration and A/C industries and services | Individual | AFR | NIR | REF | 11 | TAS | 7 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1999-12-01 | 2000-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  |  | 1999-12-01
CLO | IBRD | Preparation of investment projects (1994) |  | AFR | NIR | SEV | 12 | PRP | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | AFR | NIR | SEV | 17 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNIDO | Phasing out of CFCs at Debo Industries Ltd. Nigeria | Individual | AFR | NIR | REF | 18 | INV | 10 | A | O | I | CFC | 52 | 52 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1048053 | 0 | 1048053 | 1048053 | 100% | 0 | 0 |  | 136247 | -44 | 136203 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Thermocool Eng. Co. Ltd. | Individual | AFR | NIR | REF | 18 | INV | 11 | A | O | I | CFC | 82 | 82 |  |  | 1995-11-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1465750 | 0 | 1465750 | 1465750 | 100% | 0 | 0 |  | 190548 | -10 | 190538 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Royal Foam Products | Individual | AFR | NIR | FOA | 20 | INV | 12 | A | O | D | CFC | 43 | 43 | 0 | 0 | 1996-10-01 | 1998-08-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 34000 | -600 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4420 | -78 | 4342 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Teju Industries Limited | Individual | AFR | NIR | FOA | 20 | INV | 13 | A | O | D | CFC | 47 | 47 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-10-01 | 2003-01-01 | 75000 | -6859 | 68141 | 68141 | 100% | 0 | 0 | 0 | 9750 | -892 | 8858 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam for thermoware in Eleganza Industries Ltd. at Ikeja, Lagos | Individual | AFR | NIR | FOA | 20 | INV | 14 | A | O | I | CFC | 48.3 | 48.3 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 314000 | -4065 | 309935 | 309935 | 100% | 0 | 0 | 0 | 40820 | -528 | 40292 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Sara Products Limited | Individual | AFR | NIR | FOA | 20 | INV | 15 | A | O | D | CFC | 27.7 | 27.7 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1999-07-01 | 2001-12-01 | 107000 | -2075 | 104925 | 104925 | 100% | 0 | 0 | 0 | 13910 | -270 | 13640 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | NIR | FOA | 21 | PRP | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | IBRD | Country programme preparation (1993) | Individual | AFR | NIR | SEV | 09 | CPG | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 35100 | -11028 | 24072 | 24072 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1994) | Individual | AFR | NIR | SEV | 12 | CPG | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 150000 | -143520 | 6480 | 6480 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1995) | Individual | AFR | NIR | SEV | 16 | CPG | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1997-06-01 | 1997-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | AFR | NIR | SEV | 04 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 82821 | -82821 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Winco Foam Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 21 | A | O | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 117200 | -321 | 116879 | 116879 | 100% | 0 | 0 | 0 | 15236 | -42 | 15194 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Bajabure Industrial Complex Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 22 | A | O | I | CFC | 32.3 | 32.3 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2002-11-01 | 135400 | -11117 | 124283 | 124283 | 100% | 0 | 0 | 0 | 17602 | -1445 | 16157 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Elico Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 23 | A | O | I | CFC | 25.7 | 25.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 133900 | -13658 | 120242 | 120242 | 100% | 0 | 0 | 0 | 17407 | -1776 | 15631 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Mouka Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 24 | A | O | I | CFC | 30.3 | 30.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2004-01-01 | 143600 | -3462 | 140138 | 140138 | 100% | 0 | 0 | 0 | 18668 | -450 | 18218 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Safa Foam Products (Nig) Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 25 | A | O | I | CFC | 24.4 | 24.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-12-01 |  | 2003-08-01 | 2006-10-01 | 146400 | 0 | 146400 | 146400 | 100% | 0 | 0 | 0 | 19032 | 0 | 19032 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manuyfacture of rigid PUF insulation products at Aluminium Manufacturing Company of Nigeria Plc (Alumaco) | Individual | AFR | NIR | FOA | 23 | INV | 26 | A | O | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-12-01 |  | 2001-11-01 | 2002-11-01 | 38000 | -400 | 37600 | 37600 | 100% | 0 | 0 | 0 | 4940 | -52 | 4888 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for thermoware in 3 enterprises of the Eleganza Group (Eleganza Cooler and Household Industries Ltd., Eleganza Ceramics and Cooler Industries Ltd.) | Individual | AFR | NIR | FOA | 23 | INV | 27 | A | O | I | CFC | 73.8 | 73.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 568000 | -25762 | 542238 | 542238 | 100% | 0 | 0 | 0 | 73840 | -3349 | 70491 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Ugochukwu Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 28 | A | O | I | CFC | 118.6 | 118.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-07-01 | 2002-11-01 | 407600 | 0 | 407600 | 407600 | 100% | 0 | 0 | 0 | 52988 | 0 | 52988 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF spray insulation at Polyurethane Manufacturers Ltd. (Polyma) | Individual | AFR | NIR | FOA | 23 | INV | 29 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2004-01-01 | 80500 | -339 | 80161 | 80161 | 100% | 0 | 0 | 0 | 10465 | -44 | 10421 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at A.G. Leventis | Individual | AFR | NIR | REF | 26 | INV | 30 | A | O | I | CFC | 19.1 | 19.1 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2003-03-01 | 2004-04-01 | 190420 | 0 | 190420 | 190420 | 100% | 0 | 0 |  | 24755 | 0 | 24755 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Orbit Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 31 | A | O | I | CFC | 25.1 | 25.1 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-07-01 | 2003-11-01 | 135200 | -1 | 135199 | 135199 | 100% | 0 | 0 | 0 | 17576 | 0 | 17576 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Olufoam and Plastic Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 32 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1998-11-01 | 2001-10-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 84600 | 0 | 84600 | 84600 | 100% | 0 | 0 | 0 | 10998 | 0 | 10998 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [7 empty] | 2003-12-01 | [5 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Okin Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 33 | A | O | I | CFC | 25.3 | 25.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-11-01 | 2002-11-01 | 133200 | 0 | 133200 | 133200 | 100% | 0 | 0 | 0 | 17316 | 0 | 17316 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Marta Industries (Nig.) Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 34 | A | O | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 130600 | -1299 | 129301 | 129301 | 100% | 0 | 0 | 0 | 16978 | -169 | 16809 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Confidence Products and Services Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 35 | A | O | I | CFC | 27.3 | 27.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 142300 | -1210 | 141090 | 141090 | 100% | 0 | 0 | 0 | 18499 | -157 | 18342 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Chemical and Wire Manufacturers Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 36 | A | O | I | CFC | 37.1 | 37.1 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-01-01 | 2003-11-01 | 164500 | 0 | 164500 | 164500 | 100% | 0 | 0 | 0 | 21385 | 0 | 21385 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [7 empty] | 2003-07-01 | [5 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Bodefoam Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 37 | A | O | I | CFC | 35.3 | 35.3 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 136400 | 0 | 136400 | 136400 | 100% | 0 | 0 | 0 | 17732 | 0 | 17732 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Group Enterprises Nig. Ltd. (Polly Foam) | Individual | AFR | NIR | FOA | 26 | INV | 38 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 128900 | -2349 | 126551 | 126551 | 100% | 0 | 0 | 0 | 16757 | -305 | 16452 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pesaco Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 39 | A | O | I | CFC | 23.4 | 23.4 | 0 | 0 | 1998-11-01 | 2000-08-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 126400 | 0 | 126400 | 126400 | 100% | 0 | 0 | 0 | 16432 | 0 | 16432 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at New Ltd. | Individual | AFR | NIR | REF | 26 | INV | 40 | A | O | I | CFC | 20.9 | 20.9 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2003-05-01 | 361770 | 0 | 361770 | 361770 | 100% | 0 | 0 |  | 47030 | 0 | 47030 | 0 | 0 | FIN
FIN | UNDP | Project preparation | Individual | AFR | NIR | FOA | 26 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Yinka-Oba Foam Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 42 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2003-08-01 | 2005-10-01 | 185300 | -629 | 184671 | 184671 | 100% | 0 | 0 | 0 | 24089 | -82 | 24007 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Universal Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 43 | A | O | I | CFC | 30.6 | 30.6 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-11-01 | 135300 | 0 | 135300 | 135300 | 100% | 0 | 0 | 0 | 17589 | 0 | 17589 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at Kolinton Technical Industries | Individual | AFR | NIR | REF | 26 | INV | 44 | A | O | I | CFC | 39.5 | 39.5 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2003-12-01 | 2004-06-01 | 674348 | -902 | 673446 | 673446 | 100% | 0 | 0 |  | 84178 | -216 | 83962 | 0 | 0 | FIN
FIN | UNDP | Preparation of three projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 45 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at United Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 46 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1999-07-01 | 2001-10-01 | 2002-02-01 |  | 2003-08-01 | 2007-01-01 | 137310 | -6098 | 131212 | 131212 | 100% | 0 | 0 | 0 | 17850 | -793 | 17057 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Tinuola Bay Industries Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 47 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-09-01 | 2003-09-01 | 119410 | 0 | 119410 | 119410 | 100% | 0 | 0 | 0 | 15523 | 0 | 15523 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Soesons Ltd. | Individual | AFR | NIR | REF | 28 | INV | 48 | A | O | I | CFC | 16.1 | 16.1 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-08-01 | 221353 | 0 | 221353 | 221353 | 100% | 0 | 0 |  | 28776 | 0 | 28776 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Diamond Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 49 | A | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2001-11-01 | 2002-11-01 | 112150 | 0 | 112150 | 112150 | 100% | 0 | 0 | 0 | 14580 | 0 | 14580 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to liquid carbon dioxide blown technology in the manufacture of molded flexible polyurethane foam at Automotive Component Industries Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 50 | A | O | I | CFC | 37 | 37 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 204761 | 0 | 204761 | 204761 | 100% | 0 | 0 | 0 | 26619 | 0 | 26619 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Onward Electrical Industry Ltd. | Individual | AFR | NIR | REF | 28 | INV | 51 | A | O | I | CFC | 10.7 | 10.7 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2003-12-01 | 2004-04-01 | 146927 | 0 | 146927 | 146927 | 100% | 0 | 0 |  | 19101 | 0 | 19101 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at United Technologies Ltd. | Individual | AFR | NIR | REF | 28 | INV | 52 | A | O | I | CFC | 9.6 | 9.6 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-12-01 | 130579 | 0 | 130579 | 130579 | 100% | 0 | 0 |  | 16975 | -6 | 16969 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration equipment at De Johnson Ltd. | Individual | AFR | NIR | REF | 29 | INV | 53 | A | O | I | CFC | 9 | 9 |  |  | 1999-11-01 | 2000-09-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 123816 | 0 | 123816 | 123816 | 100% | 0 | 0 |  | 16096 | 0 | 16096 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration at Austin-Laz & Co. Ltd | Individual | AFR | NIR | REF | 29 | INV | 54 | A | O | I | CFC | 11.6 | 11.6 |  |  | 1999-11-01 | 2000-10-01 | 2001-06-01 |  | 2002-08-01 | 2003-07-01 | 147181 | 0 | 147181 | 147181 | 100% | 0 | 0 |  | 19134 | 0 | 19134 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Rubez (Nig.) Ltd. (Current Foam) | Individual | AFR | NIR | FOA | 29 | INV | 55 | A | O | I | CFC | 21.9 | 21.9 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2002-12-01 |  | 2003-08-01 | 2005-11-01 | 89803 | -65 | 89738 | 89738 | 100% | 0 | 0 | 0 | 11674 | -8 | 11666 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1999 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafco Industries Limited | Individual | AFR | NIR | FOA | 29 | INV | 56 | A | O | I | CFC | 34.2 | 34.2 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-12-01 | 2006-06-01 | 58559 | 0 | 58559 | 58559 | 100% | 0 | 0 | 0 | 7613 | 0 | 7613 | 0 | 0 | Completed in 2002. Financially completed in 2006. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Vono Products PLC | Individual | AFR | NIR | FOA | 29 | INV | 57 | A | O | I | CFC | 56.5 | 56.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 173782 | 0 | 173782 | 173782 | 100% | 0 | 0 | 0 | 22592 | 0 | 22592 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride blown technology in the manufacture of flexible polyurethane foam at Betaday Industries Ltd. | Individual | AFR | NIR | FOA | 29 | INV | 58 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 104495 | -1 | 104494 | 104494 | 100% | 0 | 0 | 0 | 13584 | 0 | 13584 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to mehtylene chloride in the manufacture of flexible polyurethane foam at Vito Company (Nig.) Ltd., Victory Foam | Individual | AFR | NIR | FOA | 29 | INV | 59 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 133560 | -188 | 133372 | 133372 | 100% | 0 | 0 | 0 | 17363 | -25 | 17338 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of seven projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 60 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-04-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNIDO | Preparation of investment project in the aerosols sector | Individual | AFR | NIR | ARS | 30 | PRP | 61 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2000-10-01 | 2001-09-01 | 25000 | -9266 | 15734 | 15734 | 100% | 0 | 0 |  | 3250 | -1208 | 2042 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | NIR | REF | 30 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-02-01 | 2002-09-01 | 25000 | -2212 | 22788 | 22788 | 100% | 0 | 0 |  | 3250 | -292 | 2958 | 0 | 0 | FIN
FIN | UNDP | Preparation of 8 projects in the general foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 63 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2006. | [13 empty] | 2000 | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 64 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Sokoto Foam Factory (Nig.) Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 65 | A | O | I | CFC | 26.1 | 26.1 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-12-01 | 2005-09-01 | 141421 | -4328 | 137093 | 137093 | 100% | 0 | 0 | 0 | 18385 | -563 | 17822 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manfuacture of flexible slabstock foam by conversion to methylene chloride at Abeokuta Commercial and Industrial Co. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 66 | A | O | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 118468 | -382 | 118086 | 118086 | 100% | 0 | 0 | 0 | 15401 | -50 | 15351 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Celplas Industries Limited | Individual | AFR | NIR | FOA | 31 | INV | 67 | A | O | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-11-01 | 2002-12-01 | 215325 | 0 | 215325 | 215325 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Completed in 2002. Financially completed in 2002. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Climax Ind. Ltd. (Ely Foam) | Individual | AFR | NIR | FOA | 31 | INV | 68 | A | O | I | CFC | 29.7 | 29.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 173362 | -575 | 172787 | 172787 | 100% | 0 | 0 | 0 | 22537 | -75 | 22462 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Wappah Foam Limited | Individual | AFR | NIR | FOA | 31 | INV | 69 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 130081 | -4 | 130077 | 130077 | 100% | 0 | 0 | 0 | 16911 | -1 | 16910 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 2000 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafa Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 70 | A | O | I | CFC | 34.2 | 34.2 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-12-01 | 2006-10-01 | 124667 | -9881 | 114786 | 114786 | 100% | 0 | 0 | 0 | 16207 | -1285 | 14922 | 0 | 0 | Completed in 2002. Financially completed in 2006. | [13 empty] | 2000 | Investment
FIN | UNIDO | Replacement of refrigerant CFC=12 withHFC-134a, and foam flowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration equipment at Bosmak Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 71 | A | O | I | CFC | 10.8 | 10.8 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2003-10-01 | 2004-06-01 | 154245 | -420 | 153825 | 153825 | 100% | 0 | 0 |  | 20052 | -86 | 19966 | 0 | 0 | FIN
FIN | UNDP | Technical assistance to prepare a refrigeration management plan (RMP) | RMP-Component | AFR | NIR | REF | 32 | TAS | 72 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2003-01-01 |  | 2002-12-01 | 2003-11-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2000 | Non-Investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Eastern Wrought Iron Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 73 | A | O | I | CFC | 27.1 | 27.1 | 0 |  | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2004-11-01 | 2006-05-01 | 109345 | -3207 | 106138 | 106138 | 100% | 0 | 0 | 0 | 14215 | -417 | 13798 | 0 | 390 | Operationally completed November 2004. COC issued. Final revision issued but unspent balance and corresponding support cost still to be returned in 2007. |  | 2000 | [12 empty] | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Mac-Vico (Nig.) Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 74 | A | O | I | CFC | 28.4 | 28.4 | 0 |  | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-07-01 | 2003-10-01 | 105209 | 0 | 105209 | 105209 | 100% | 0 | 0 | 0 | 13677 | 0 | 13677 | 0 | 0 | Operationally completed July 2003, financially completed October 2003 |  | 2000 | [12 empty] | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Martchem Industries Limited (at 2 plants) by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 75 | A | O | I | CFC | 38.4 | 38.4 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2003-03-01 | 2003-10-01 | 175121 | 0 | 175121 | 175121 | 100% | 0 | 0 | 0 | 22766 | 0 | 22766 | 0 | 0 | Operationally and financially completed 2003 |  | 2000 | [12 empty] | investment
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Coldcare Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 76 | A | O | I | CFC | 11.4 | 11.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-12-01 | 2003-12-01 | 173200 | 0 | 173200 | 173200 | 100% | 0 | 0 |  | 22516 | 0 | 22516 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Akocen Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 77 | A | O | I | CFC | 12.1 | 12.1 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2003-10-01 | 157894 | 0 | 157894 | 157894 | 100% | 0 | 0 |  | 20526 | 0 | 20526 | 0 | 0 | FIN
CLO | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 78 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 79 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNIDO | Project preparation for three projects in the commercial refrigeration sector | Individual | AFR | NIR | REF | 33 | PRP | 80 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1718 | 18282 | 18282 | 100% | 0 | 0 |  | 2600 | -227 | 2373 | 0 | 0 | FIN | [13 empty] | 2001 | INV
CLO | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 81 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 82 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Atuchukwu Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 83 | A | O | I | CFC | 22.2 | 22.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 118488 | -1 | 118487 | 118487 | 100% | 0 | 0 | 0 | 15403 | 0 | 15403 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Apaco Foam and Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 84 | A | O | I | CFC | 27.7 | 27.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 147018 | 0 | 147018 | 147018 | 100% | 0 | 0 | 0 | 19112 | 0 | 19112 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Gasfa Industries Nig., Ltd. (Meka Foam) | Individual | AFR | NIR | FOA | 34 | INV | 85 | A | O | I | CFC | 40.5 | 40.5 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2003-08-01 | 2005-09-01 | 238843 | -9895 | 228948 | 228948 | 100% | 0 | 0 | 0 | 31050 | -1286 | 29764 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Adig Plastics Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 86 | A | O | I | CFC | 14.3 | 14.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-04-01 | 112050 | 0 | 112050 | 112050 | 100% | 0 | 0 | 0 | 14567 | 0 | 14567 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | AFR | NIR | HAL | 34 | PRP | 87 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 19420 | 0 | 19420 | 19420 | 100% | 0 | 0 | 0 | 2525 | 0 | 2525 | 0 | 0 | Project proposal submitted and approved by MF (37th ExCom). | [13 empty] | 1998
FIN | UNDP | Phasing out CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Rima Foam Products Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 88 | A | O | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-06-01 | 119036 | -582 | 118454 | 118454 | 100% | 0 | 0 | 0 | 15475 | -76 | 15399 | 0 | 0 | Completed in 2002. Financially completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Harmony Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 89 | A | O | I | CFC | 22.3 | 22.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2005-11-01 | 126531 | -13568 | 112963 | 112963 | 100% | 0 | 0 | 0 | 16449 | -1764 | 14685 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | NIR | FUM | 34 | TAS | 90 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -16990 | 8010 | 8010 | 100% | 0 | 0 | 0 | 3250 | -2208.7 | 1041.3 | 0 | 0 | Project financially completed. | $ 16,990 plus $ 2,209 PSC returned ExCom 44 | [12 empty] | 2001 | Non Investment
CLO | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Global Plastic Industries, Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 91 | A | O | I | CFC | 4.7 | 4.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  |  | 2005-09-01 | 36801 | -3512 | 33289 | 33289 | 100% | 0 | 0 | 0 | 4784 | -457 | 4327 | 0 | 0 | Canceled in 2004. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bibafoam Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 92 | A | O | I | CFC | 26 | 26 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-10-01 | 114685 | 0 | 114685 | 114685 | 100% | 0 | 0 | 0 | 14909 | 0 | 14909 | 0 | 0 | Completed in 2002. Financially completed in 2006. | [13 empty] | 2001 | Investment
COM | UNDP | Renewal of institutional strengthening project (phase II) | Individual | AFR | NIR | SEV | 34 | INS | 93 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-08-01 |  | 200000 | 0 | 200000 | 199149 | 99.57% | 851 | 0 | 680.8 | 26000 | 0 | 25889.37 | 110.63 | 0 | Completed in 2003. | [13 empty] | 2001 | Non-Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bamako Industrial, Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 94 | A | O | I | CFC | 24 | 24 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2005-11-01 | 114510 | -3460 | 111050 | 111050 | 100% | 0 | 0 | 0 | 14886 | -450 | 14436 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Agric Services (Nig.), Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 95 | A | O | I | CFC | 43.7 | 43.7 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-08-01 | 2005-10-01 | 239160 | -263 | 238897 | 238897 | 100% | 0 | 0 | 0 | 31091 | -34 | 31057 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2001 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) technology in the manufacture of flexible polyurethane at ten box-foam enterprises in Lagos area | Individual | AFR | NIR | FOA | 35 | INV | 96 | A | O | I | CFC | 199.2 | 199.2 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2007-02-01 | 1062808 | 0 | 1062808 | 1062808 | 100% | 0 | 0 | 0 | 126909 | 0 | 126909 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Polade | Individual | AFR | NIR | REF | 35 | INV | 97 | A | O | I | CFC | 8.3 | 8.3 |  |  | 2001-12-01 | 2002-03-01 | 2004-05-01 |  | 2004-06-01 | 2005-03-01 | 70382 | 0 | 70382 | 70382 | 100% | 0 | 0 |  | 9150 | -4 | 9146 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Ristian | Individual | AFR | NIR | REF | 35 | INV | 98 | A | O | I | CFC | 11 | 11 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2004-06-01 | 2005-12-01 | 143729 | -706 | 143023 | 143023 | 100% | 0 | 0 |  | 18685 | -122 | 18563 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2001 | INV
FIN | UNDP | Preparation of a refrigerant management plan | Individual | AFR | NIR | REF | 36 | PRP | 99 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-11-01 | 40000 | -1 | 39999 | 39999 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2002 | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | AFR | NIR | FOA | 36 | PRP | 100 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNIDO | Preparation of a sectoral phase-out plan in solvents | Individual | AFR | NIR | SOL | 36 | PRP | 101 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-06-01 | 2004-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | -8 | 9092 | 0 | 0 | FIN | [13 empty] | 2002 | INV
COM | UNDP | Country programme update | Individual | AFR | NIR | SEV | 36 | CPG | 102 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-10-01 |  | 2007-12-01 |  | 241493 | 0 | 241493 | 231075 | 95.69% | 10418 | 0 | 8334.4 | 31394 | 0 | 30039.75 | 1354.25 | 0 | Completed in 2007. | [13 empty] | 2002 | Non-Investment
FIN | Germany | Sectoral phase-out programme: establishing a halon bank | Individual | AFR | NIR | HAL | 37 | TAS | 103 | A | O | I | HAL | 285.3 | 285.3 | 0 |  | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2007-08-01 | 2008-10-01 | 499000 | 0 | 499000 | 499000 | 100% | 0 | 0 | 0 | 64870 | 0 | 64870 | 0 | 0 | Project is completed. PCR has been submitted to the MLF in October 2008.
COM | Japan | Assistance for a national information, education and communication campaign for compliance with the Montreal Protocol | Individual | AFR | NIR | SEV | 38 | TAS | 104 | A | O | I | CFC | 5.6 |  | 0 |  | 2002-11-01 | 2004-12-01 | 2003-11-01 | 2007-12-01 | 2008-10-01 |  | 68000 | 0 | 68000 | 7100 | 10.44% | 60900 | 25000 | 60900 | 8840 | 0 | 923 | 7917 | 3250 | The national stakeholders’ workshop for IEC (Information, education and communication) campaign was held on 5-6 October, 2006 in Abuja. Based on the outcome of the workshop, the Government of Nigeria and UNEP is finalizing the strategy and the action plan |  | 2002
FIN | UNIDO | National CFC phase-out plan: refrigeration manufacturing | Multi-Year | AFR | NIR | PHA | 38 | INV | 105 | A | O | I | CFC | 42.9 | 42.9 |  |  | 2002-11-01 | 2003-03-01 | 2005-06-01 |  | 2006-03-01 | 2008-09-01 | 682386 | 0 | 682386 | 682386 | 100% | 0 | 0 |  | 82521 | 0 | 82521 | 0 | 0 | Financial completion in Sep 2008. FIN: Total disbursement = Total approval. | [7 empty] | 2005-06-01 | [5 empty] | 2002 | INV | N/A | N/A |  |  | N/A | N/A | N/A
COM | UNDP | National CFC phase-out plan: foam sector and refrigeration servicing sector (first tranche) | Multi-Year | AFR | NIR | PHA | 38 | INV | 106 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2006-12-01 |  | 5013929 | 0 | 5013929 | 5013929 | 100% | 0 | 0 | 0 | 449318 | 0 | 449318 | 0 | 0 | Completed in 2006. | [9 empty] | 2005-12-01 |  |  |  | 2002 | Investment | 2388.8 | 2388.8 |  |  | Yes | Yes | Yes
COM | UNDP | Extension of institutional strengthening project | Individual | AFR | NIR | SEV | 40 | INS | 107 | N | T | I | No_ODP | 21.5 | 21.5 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 |  | 260000 | 0 | 260000 | 259900 | 99.96% | 100 | 0 | 80 | 19500 | 0 | 19492.5 | 7.5 | 0 | Completed in 2006. | [13 empty] | 2003 | Non-Investment
COM | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | NIR | PHA | 41 | INV | 108 | N | O | I | CFC | 830 | 830 | 0 | 0 | 2003-12-01 | 2007-03-01 | 2004-12-01 |  | 2007-12-01 |  | 2976827 | 0 | 2976827 | 2976827 | 100% | 0 | 0 | 0 | 264834 | 0 | 264834 | 0 | 0 | Completed in 2007. | [13 empty] | 2003 | Investment | 1543.5 | 1543.5 |  |  | Yes | Yes | yes
FIN | UNIDO | National CFC phase-out plan (aerosol sector) | Multi-Year | AFR | NIR | PHA | 41 | INV | 109 | A | O | I | CFC | 57.9 | 57.9 |  |  | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2008-03-01 | 2008-06-01 | 255000 | -2 | 254998 | 254998 | 100% | 0 | 0 |  | 33150 | 0 | 33150 | 0 | 0 | Project completed in Mar 2008. Financial completion in Jun 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2003 | INV | N/A | N/A |  |  | N/A | N/A | N/A
FIN | UNIDO | Terminal ODS phase out umbrella project in the solvent sector (first tranche) | Multi-Year | AFR | NIR | SOL | 43 | INV | 110 | A | O | I | CTC | 152.1 | 152.1 |  |  | 2004-07-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-05-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 39750 | 0 | 39750 | 0 | 0 | FIN | [13 empty] | 2004 | INV | 198 | 197.85 |  |  | Yes | Yes | Yes
COM | UNDP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | NIR | PHA | 44 | INV | 112 | N | O | I | CFC | 850.7 | 850.7 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-09-01 |  | 2077141 | 0 | 2077141 | 688868 | 33.16% | 1388273 | 1388273 | 1110618.4 | 183863 | 0 | 60976.7643 | 122886.2357 | 122886.2357 | Completed in 2008. See NIR-117 for short status. | [13 empty] | 2004 | Investment | 956.4 |  |  |  | Latest | Latest | Latest
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (2nd tranche) | Multi-Year | AFR | NIR | SOL | 46 | INV | 113 | A | O | I | CTC TCA | 0 | 0 |  |  | 2005-07-01 | 2005-11-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 23775 | 0 | 23775 | 0 | 0 | Financial completion in Sep 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2005 | INV | 45.9 | 0 |  |  | Yes | Yes | Yes
COM | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | NIR | SEV | 48 | INS | 114 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2007-12-01 |  | 260000 | 0 | 260000 | 259805 | 99.92% | 195 | 0 | 156 | 19500 | 0 | 19485.375 | 14.625 | 0 | Completed in 2007. | [13 empty] | 2006 | Non-Investment
COM | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (3rd tranche) | Multi-Year | AFR | NIR | PHA | 49 | INV | 115 | A | O | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-11-01 | 2007-07-01 |  | 2007-12-01 |  | 425000 | 0 | 425000 | 401879 | 94.56% | 23121 | 20593 | 20000 | 31875 | 0 | 30141 | 1734 | 1544 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2006 | INV | 45.9 | 0 |  |  | Yes | Yes | Yes
ONG | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (fourth tranche) | Multi-Year | AFR | NIR | SOL | 52 | INV | 116 | A | O | I | CTC | 45.9 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2010-01-01 | 2010-12-01 |  |  | 303200 | 0 | 303200 | 159600 | 52.64% | 143600 | 25396 | 40000 | 22740 | 0 | 11970 | 10770 | 1905 | In 2008 solvents were purchased, equipment was distributed and training of the national staff was conducted. In 2009 workshop for small-scale solvent users is under preparation. A team of national experts will be recruited to provide technical assistance to solvent users. Public awareness activities are continued. Enforcement of the legislation is planned. | [13 empty] | 2007 | INV | 23 | 0 |  |  | Yes | Yes | Yes
ONG | UNDP | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | AFR | NIR | PHA | 54 | INV | 117 | N | O | I | CFC | 1179.8 | 1162 | 0 | 0 | 2008-04-01 |  | 2010-03-01 | 2010-03-01 |  |  | 1286303 | 0 | 1286303 | 0 | 0% | 1286303 | 315352 | 257260.6 | 111407 | 0 | 0 | 111407 | 27312.7096 | Detailed progress report submitted at 57th ExCom. Remaining CFC-12 only 17.5 ODP tones, which is remarkable. Programme now making good progress. OPIAMU continued its day to day monitoring operations. For foams, phase-II almost completed and specs for equipment for phase-III finalized but PO to be placed in early 2009. Training of customs officers and technicians continued, R&R equipment purchased and distributed. Incentive programme for comm. ref. initiated and awareness workshop carried out. More numeric summary data is available at the UNMFS web-based database system. Next funding tranche to be approved in April 2009. | [13 empty] | 2008 | Investment
ONG | UNDP | Extension of the institutional strengthening project (phase V) | Individual | AFR | NIR | SEV | 54 | INS | 118 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2010-03-01 | 2010-03-01 |  |  | 260000 | 0 | 260000 | 43533 | 16.74% | 216467 | 2956 | 43293.4 | 19500 | 0 | 3264.975 | 16235.025 | 221.7 | 2-year extension approved in Apt 08. Ozone Office fully operational and implementing activities according to action plan. New phase approved at 56th ExCom meeting. | [13 empty] | 2008 | Non-Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | NIR | PHA | 55 | PRP | 119 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Approved at 55th ExCom, initial visit undertaken in 2008 to initiate activities, discuss survey forms, draft prodoc and TORs. Inception workshop to take place in May 2009. HPMP to be submitted 4Q2008. | [13 empty] | 2008 | Investment
ONG | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 120 | A | O | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2009-11-30 | 2009-11-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 12000 | 1500 | 0 | 0 | 1500 | 0 | Meeting with national stake holders, the government and UNDP (lead agency) is being coordinated. | UNIDO is only cooperating implementing agency and is in charge of the refrigeration and A/C manufacturing sector. Work on legislation is the responsibility of the lead implementing agency, UNDP. | [12 empty] | 2008 | NON-INV
ONG | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 121 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2010-04-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 0 | 45000 | 3375 | 0 | 0 | 3375 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NIU | SEV | 44 | INS | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-06-01 | 2007-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NIU | REF | 44 | TAS | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-07 |  | 14000 | 0 | 14000 | 10723 | 76.59% | 3277 | 0 | 3277 | 1820 | 0 | 1393.99 | 426.01 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NIU | REF | 44 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  | 2008-12-01 |  | 8000 | 0 | 8000 | 0 | 0% | 8000 | 0 | 8000 | 1040 | 0 | 0 | 1040 | 0 | Project completed in December 2008 | [13 empty] | 2004 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NIU | SEV | 50 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 |  | 15000 | 0 | 15000 | 10100 | 67.33% | 4900 | 0 | 4900 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | NIU | SEV | 53 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 | 2009-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008. First disbursement will start after country receive final payment of previous IS phase from SPREP. | [13 empty] | 2007 | Non Investment
FIN | UNIDO | Country programme preparation | Individual | ASP | OMA | SEV | 29 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-12-01 | 2002-05-01 | 80000 | -1455 | 78545 | 78545 | 100% | 0 | 0 |  | 10400 | -205 | 10195 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the RMP: Training of trainers in good refrigerant management practices | RMP Update | ASP | OMA | REF | 34 | TRA | 2 | A | O | I | CFC | 80 | 80 |  |  | 2001-07-01 | 2002-06-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 178000 | -1359 | 176641 | 176641 | 100% | 0 | 0 |  | 23140 | -213 | 22927 | 0 | 0 | FIN | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Institutional Strengthening/Support to the National Ozone Unit in Oman | Individual | ASP | OMA | SEV | 32 | INS | 2 | N | T | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2005-12-01 | 2006-02-01 | 79000 | 0 | 79000 | 79000 | 100% | 0 | 0 |  | 10270 | -1 | 10269 | 0 | 0 | FIN
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | ASP | OMA | HAL | 34 | PRP | 3 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-09-01 | 2002-01-01 |  | 2003-07-03 | 2003-12-01 | 17000 | 0 | 17000 | 17000 | 100% | 0 | 0 | 0 | 2210 | 0 | 2210 | 0 | 0 | Int.consultant visited Oman, nat. consultants identified, Implemenation of the projects will be done by World Bank on request of Oman, results transferred to WB Jul-03. WB TAS-Project approved 41st ExCom. | [13 empty] | 1998
FIN | UNIDO | Implementation of the RMP: Customs training programme | RMP Update | ASP | OMA | REF | 34 | TRA | 4 | A | O | I | CFC | 18.9 | 18.9 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-09-01 | 42000 | -4469 | 37531 | 37531 | 100% | 0 | 0 |  | 5460 | -589 | 4871 | 0 | 0 | FIN | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | OMA | REF | 34 | TAS | 5 | A | O | I | CFC | 9 | 9 |  |  | 2001-07-01 | 2007-03-01 | 2004-08-01 |  | 2007-12-01 | 2008-09-01 | 20000 | -196 | 19804 | 19804 | 100% | 0 | 0 |  | 2600 | -25 | 2575 | 0 | 0 | Financial completion in Sep 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Implementation of the RMP: Recovery and recycling project | RMP Update | ASP | OMA | REF | 34 | TAS | 6 | A | O | I | CFC | 103.3 | 103.3 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2005-12-01 | 2007-12-01 | 230000 | -502 | 229498 | 229498 | 100% | 0 | 0 |  | 29900 | -65 | 29835 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2001 | INV
FIN | UNEP | Policy and technical assistance | Individual | ASP | OMA | SEV | 37 | TAS | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2006-02-01 | 2008-12-01 | 10000 | 0 | 10000 | 9948 | 99.48% | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. Balances to be returned to ExCom 57 | [13 empty] | 2002 | Non Investment
TRF | IBRD | Halon consumption phase-out through a technical assistance programme and a halon recycling | Halon Banking | ASP | OMA | HAL | 41 | TAS | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 |  |  | 2005-07-01 | 64600 | -64600 | 0 | 0 |  | 0 | 0 |  | 5814 | -5814 | 0 | 0 | 0 | Project transferred to UNIDO at the 46th ExCom. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Awareness workshop and training on methyl bromide alternatives | Individual | ASP | OMA | FUM | 44 | TRA | 10 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-09-01 | 2007-10-01 | 35000 | -2078 | 32922 | 32922 | 100% | 0 | 0 |  | 3150 | -187 | 2963 | 0 | 0 | FIN | [13 empty] | 2004 | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvent sector (CTC) | Individual | ASP | OMA | SOL | 45 | TAS | 11 | A | O | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 3150 | 0 | 3150 | 0 | 0 | Financial completion in May 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2005 | INV
ONG | UNIDO | Halon consumption phase-out through a technical assistance programme and a halon recycling | Individual | ASP | OMA | HAL | 46 | TAS | 12 | A | O | I | HAL | 6.85 | 0 |  |  | 2005-07-01 | 2007-02-01 | 2006-12-01 | 2009-05-01 |  |  | 64600 | 0 | 64600 | 13005 | 20.13% | 51595 | 23004 | 15000 | 5814 | 0 | 1170 | 4644 | 2070 | International bidding for R&R equipment completed and purchase order issued. Equipment to be procured locally is being coordinated. | [11 empty] | 2008-02-01 |  | 2005 | NON-INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | OMA | PHA | 46 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2007-03-01 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN | [13 empty] | 2005 | NON-INV
COM | UNIDO | Renewal of institutional strengthening support (phase II) | Individual | ASP | OMA | SEV | 46 | INS | 14 | N | T | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-03-01 | 2007-07-01 |  | 2007-12-01 |  | 68467 | 0 | 68467 | 58121 | 84.89% | 10346 | 10346 | 10346 | 5135 | 0 | 4359 | 776 | 776 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2005 | NON-INV
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | OMA | PHA | 52 | INV | 15 | A | O | I | CFC | 10 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2009-12-31 | 2009-04-01 |  |  | 305800 | 0 | 305800 | 128599 | 42.05% | 177201 | 57709 | 100000 | 22935 | 0 | 9645 | 13290 | 4328 | The equipment was delivered. Training on good practices was completed. Material for the training on chiller retrofits was developed. The training is expected to take place in February 2009. Project is expected to be completed by April 2009 and the second tranche will be submitted accordingly. | [13 empty] | 2007 | INV | 25 | 8.5 |  |  | Yes | N/A | N/A
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | OMA | PHA | 55 | PRP | 16 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 9200 | 10000 | 7500 | 0 | 0 | 7500 | 690 | National experts were recruited to carry out the survey. The first stakeholder consultation workshop will take place in March 2009. | Legislation related matters are part of the responsibility of UNEP. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | OMA | PHA | 55 | PRP | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-07-31 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 50000 | 6500 | 0 | 0 | 6500 | 0 | Survey on HCFC use conducted as part of UNIDO contract with the local institution, first coordination workshop for all stakeholders planned for early 2009 | [13 empty] | 2008
ONG | UNIDO | Renewal of institutional strengthening support (phase III) | Individual | ASP | OMA | SEV | 56 | INS | 18 | N | T | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2010-11-30 | 2010-11-01 |  |  | 68467 | 0 | 68467 | 0 | 0% | 68467 | 0 | 10000 | 5135 | 0 | 0 | 5135 | 0 | Project has been approved by the 56th ExCom. Working plan for 2009 has been agreed as of December 2008. | [13 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | ASP | PAK | SEV | 9 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1996-06-01 | 1996-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | IBRD | Project identification and preparation (1993) |  | ASP | PAK | SEV | 11 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 100000 | -91044 | 8956 | 8956 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Strategy for ODS phase out in refrigeration industry | Individual | ASP | PAK | REF | 12 | TAS | 3 | A | O | I |  | 0 | 0 |  |  | 1994-03-01 | 1995-08-01 | 1994-06-01 |  | 1998-03-01 | 2000-07-01 | 50000 | -232 | 49768 | 49768 | 100% | 0 | 0 |  | 6500 | -40 | 6460 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | PAK | SEV | 12 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 133191 | -38871 | 94320 | 94320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | PAK | SEV | 14 | INS | 5 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 2001-12-01 | 2003-05-01 | 259000 | -4042 | 254958 | 254958 | 100% | 0 | 0 | 0 | 33670 | -525 | 33145 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non-Investment
FIN | IBRD | Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group: (Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Industries Ltd., Procon En) | Individual | ASP | PAK | FOA | 17 | INV | 6 | N | O | I | CFC | 205 | 205 | 0 | 0 | 1995-07-01 | 1999-08-01 | 1997-01-01 |  | 2005-02-01 | 2006-07-01 | 1247330 | -1030 | 1246300 | 1246300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-05-01 | 1999-09-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded and rigid PUF at Razi Sons | Individual | ASP | PAK | FOA | 18 | INV | 7 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1995-11-01 | 1999-04-01 | 1997-05-01 |  | 2002-11-01 | 2003-08-01 | 493262 | 0 | 493262 | 493262 | 100% | 0 | 0 |  | 64124.06 | 0 | 64124.06 | 0 | 0 | Project and draft PCR completed. |  |  | 1998-12-01 | 1999-09-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1995) |  | ASP | PAK | SEV | 16 | PRP | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 143009 | 0 | 143009 | 143009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at the Chest Freezer Factory of Riaz Electric Co. Ltd. | Individual | ASP | PAK | REF | 19 | INV | 9 | A | O | I | CFC | 48.2 | 48.2 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-12-01 | 2005-12-01 | 822987 | -4083 | 818904 | 818904 | 100% | 0 | 0 |  | 106988 | -699 | 106289 | 0 | 0 | FIN |  |  | 1997-10-01 | 1999-12-01
FIN | UNIDO | Phasing out ODS at the refrigerator and chest freezer plants of Pak Elektron Ltd. (PEL) | Individual | ASP | PAK | REF | 19 | INV | 10 | A | O | I | CFC | 68 | 68 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-10-01 | 2006-05-01 | 1210295 | -67215 | 1143080 | 1143080 | 100% | 0 | 0 |  | 157338 | -8973 | 148365 | 0 | 0 | FIN |  |  | 1997-10-01 | 1999-12-01
CLO | IBRD | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agenct and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | Individual | ASP | PAK | REF | 19 | INV | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1999-11-01 | 257650 | -257650 | 0 | 0 |  | 0 | 0 |  | 33494.5 | -33494.5 | 0 | 0 | 0 | Subproject cancelled. |  |  | 1998-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 21 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of ODS coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Hyderabad | Individual | ASP | PAK | SOL | 22 | INV | 13 | A | O | I | CFC | 18.9 | 18.9 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 1999-12-01 | 2002-09-01 | 321172 | -3201 | 317971 | 317971 | 100% | 0 | 0 |  | 41752 | -481 | 41271 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning and coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Lahore | Individual | ASP | PAK | SOL | 22 | INV | 14 | A | O | I | CFC | 40.7 | 40.7 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2002-06-01 | 2003-06-01 | 510162 | 0 | 510162 | 510162 | 100% | 0 | 0 |  | 66321 | -37 | 66284 | 0 | 0 | FIN
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the country programme |  | ASP | PAK | FOA | 22 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-30 | 1998-05-01 |  | 1997-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Synthetic Products Enterprises (Pvt) Ltd. (SPEL) | Individual | ASP | PAK | FOA | 23 | INV | 16 | N | O | I | CFC | 13.6 | 13.6 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-01-01 | 2003-10-01 | 160625 | -23796.5 | 136828.5 | 136828.5 | 100% | 0 | 0 |  | 20881 | -3093.5 | 17787.5 | 0 | 0 | Project completed and PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at the freezer factory of Hirra Farooq's (Pvt) Ltd. | Individual | ASP | PAK | REF | 23 | INV | 17 | A | O | I | CFC | 31.2 | 31.2 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 2003-08-01 | 2003-12-01 | 521580 | -3110 | 518470 | 518470 | 100% | 0 | 0 |  | 67805 | -511 | 67294 | 0 | 0 | FIN
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kold Kraft Ltd. | Individual | ASP | PAK | REF | 23 | INV | 18 | N | O | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-12-01 | 2003-02-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0 | Project completed and PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | Individual | ASP | PAK | REF | 23 | INV | 19 | N | O | I | CFC | 117.6 | 117.6 | 0 | 0 | 1997-11-01 | 2004-07-01 | 2000-03-01 |  | 2006-12-01 | 2006-12-01 | 841750 | 0 | 841750 | 841750 | 100% | 0 | 0 |  | 109428 | 0 | 109428 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 23 | INV | 20 | N | O | I | CFC | 239.6 | 239.6 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2006-10-01 | 2006-10-01 | 1600000 | -209475 | 1390525 | 1390525 | 100% | 0 | 0 |  | 208000 | -27231.75 | 180768.25 | 0 | 0 | Project completed. | [5 empty] | 2001-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Singer Pakistan Ltd. | Individual | ASP | PAK | REF | 23 | INV | 21 | N | O | I | CFC | 17.8 | 17.8 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2004-07-01 | 2005-02-01 | 205893 | 0 | 205893 | 205893 | 100% | 0 | 0 |  | 26766 | 0 | 26766 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible moulded, rigid foam) at Diamond Group of Industries | Individual | ASP | PAK | FOA | 23 | INV | 22 | N | O | I | CFC | 64.1 | 64.1 | 0 | 0 | 1997-11-01 | 2001-09-01 | 2000-03-01 |  | 2005-02-01 | 2007-06-01 | 563339 | 0 | 563339 | 563339 | 100% | 0 | 0 |  | 73234 | 0 | 73234 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 24 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 |  | 8190 | 0 | 8190 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | ASP | PAK | FUM | 24 | PRP | 24 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-12-01 | 1999-04-01 |  | 2000-01-01 | 2000-07-01 | 30000 | -21118 | 8882 | 8882 | 100% | 0 | 0 |  | 3900 | -2747 | 1153 | 0 | 0 | FIN
FIN | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 25 | INV | 25 | N | O | I | CFC | 105.65 | 105.65 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2000-08-01 |  | 2006-10-01 | 2006-10-01 | 718900 | -161848 | 557052 | 557052 | 100% | 0 | 0 |  | 93457 | -21040.24 | 72416.76 | 0 | 0 | Project completed. | [5 empty] | 2001-12-01 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Dawlance P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 26 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 477894 | -477894 | 0 | 0 |  | 0 | 0 |  | 62126.22 | -62126.33 | 0 | -0.11 | -0.11 | Project cancelled at the 33rd ExCom Meeting. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of refrigeration equipment at United Refrigeration Industries Ltd. | Individual | ASP | PAK | REF | 25 | INV | 27 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 457815 | -457815 | 0 | 0 |  | 0 | 0 |  | 59515.95 | -59515.95 | 0 | 0 | 0 | Project cancelled at the 33rd ExCom Meeting. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC134a in the manufacture of commercial refrigeration equipment at Shadman Electronic Industries P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 28 | N | O | I | CFC | 15.53 | 15.53 | 0 | 0 | 1998-07-01 | 2000-10-01 | 2000-08-01 |  | 2002-11-01 | 2003-02-01 | 236936 | 0 | 236936 | 236936 | 100% | 0 | 0 |  | 30801.68 | 0 | 30801.68 | 0 | 0 | Project completed and PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 through conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane slabstock foam at United Foam Industries | Individual | ASP | PAK | FOA | 26 | INV | 29 | N | O | I | CFC | 28.6 | 28.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-12-01 | 2002-01-01 | 178200 | 0 | 178200 | 178200 | 100% | 0 | 0 |  | 23166 | 0 | 23166 | 0 | 0 | Project completed and PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 through conversion to water based technology in the manufacture of flexible molded polyurethane foam at Saleem Automotive Industries Ltd. | Individual | ASP | PAK | FOA | 26 | INV | 30 | N | O | I | CFC | 2.5 | 2.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-06-01 |  | 1999-03-01 | 2000-12-01 | 33875 | -2272 | 31603 | 31603 | 100% | 0 | 0 |  | 4403.75 | -295.35 | 4108.4 | 0 | 0 | Project completed, PCR submitted June 2000. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a in the manufacture of domestic refrigeration equipment at Refrigerators Manufacturing Company Pakistan Ltd. | Individual | ASP | PAK | REF | 26 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-31 | 127804 | -127804 | 0 | 0 |  | 0 | 0 |  | 16614.52 | -16614.52 | 0 | 0 | 0 | Project cancelled at the 35th ExCom Meeting. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | PAK | REF | 27 | PRP | 32 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-03-01 | 1999-12-01 |  | 2003-07-01 | 2003-10-01 | 30000 | -2206 | 27794 | 27794 | 100% | 0 | 0 |  | 3900 | -292 | 3608 | 0 | 0 | FIN | [5 empty] | 2001-12-01
FIN | IBRD | Preparation of projects in the foam and refrigeration sectors |  | ASP | PAK | SEV | 27 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | Individual | ASP | PAK | FOA | 29 | INV | 34 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1999-11-01 | 2004-09-01 | 2001-12-01 |  | 2005-06-01 | 2005-09-01 | 279280 | -5612.86 | 273667.14 | 273667.14 | 100% | 0 | 0 |  | 36306.4 | -729.68 | 35576.72 | 0 | 0 | Project completed. | [6 empty] | 2003-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam flexible sub-sector |  | ASP | PAK | REF | 30 | PRP | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration sector (railway) |  | ASP | PAK | REF | 30 | PRP | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam |  | ASP | PAK | FOA | 30 | PRP | 37 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 |  | 1560 | 0 | 1560 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | PAK | SEV | 18 | PRP | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | Individual | ASP | PAK | REF | 32 | INV | 39 | N | O | I | CFC | 19.7 | 19.7 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-08-01 | 2006-02-01 | 176681 | 0 | 176681 | 176681 | 100% | 0 | 0 |  | 22968.53 | 0 | 22968.53 | 0 | 0 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Mumtaz Engineers | Individual | ASP | PAK | REF | 32 | INV | 40 | N | O | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-11-01 | 2007-06-01 | 204736 | -21870.06 | 182865.94 | 182865.94 | 100% | 0 | 0 |  | 26615.68 | -2843.1 | 23772.9 | -0.32 | -0.32 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Project preparation for four projects in the solvent (CTC) sector | Individual | ASP | PAK | SOL | 33 | PRP | 41 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | -7022 | 22978 | 22978 | 100% | 0 | 0 |  | 3900 | -918 | 2982 | 0 | 0 | FIN | [13 empty] | 2001 | INV
COM | UNIDO | Conversion of carbon tetrachloride as process solvent to 1,2-dichloroethane at Himont Chemicals Ltd. | Individual | ASP | PAK | PAG | 35 | INV | 42 | A | O | I | CTC | 80 | 80 |  |  | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2008-10-01 |  | 485701 | 0 | 485701 | 474245 | 97.64% | 11456 | 4061 | 11000 | 63141 | 0 | 61652 | 1489 | 528 | Final installations, commissioning and converted technology was done. Project completed in Oct 2008. | [13 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the production of domestic refrigeration equipment at Ideal Appliances, Ltd. | Individual | ASP | PAK | REF | 35 | INV | 43 | A | O | I | CFC | 12.9 | 12.9 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2004-07-01 | 2005-09-01 | 173101 | -1342 | 171759 | 171759 | 100% | 0 | 0 |  | 22503 | -210 | 22293 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | PAK | SEV | 35 | INS | 44 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2004-01-01 |  | 2004-01-01 | 2007-06-01 | 172666 | -102 | 172564 | 172564 | 100% | 0 | 0 | 0 | 22447 | -13 | 22433.7 | 0.3 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Non-Investment
FIN | UNIDO | Preparation of two projects in the solvents sector | Individual | ASP | PAK | SOL | 36 | PRP | 45 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 20000 | -639 | 19361 | 19361 | 100% | 0 | 0 |  | 2600 | -87 | 2513 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | IBRD | Assistance for the country programme update | Individual | ASP | PAK | SEV | 36 | CPG | 46 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | CPU submitted and approved at the 41st ExCom Meeting. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Riaz Electric Ltd., Lahore | Individual | ASP | PAK | SOL | 37 | INV | 47 | A | O | I | CTC | 10 | 10 |  |  | 2002-07-01 | 2004-10-01 | 2004-08-01 |  | 2005-12-01 | 2006-12-01 | 122078 | -665 | 121413 | 121413 | 100% | 0 | 0 |  | 15870 | -86 | 15784 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Preparation of investment projects in the solvents sector (CTC/TCA) | Individual | ASP | PAK | SOL | 39 | PRP | 48 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 25000 | -807 | 24193 | 24193 | 100% | 0 | 0 |  | 1875 | -63 | 1812 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector | Individual | ASP | PAK | FUM | 39 | PRP | 49 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2004-04-01 | 2004-06-01 | 30000 | -9323 | 20677 | 20677 | 100% | 0 | 0 |  | 2250 | -702 | 1548 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Preparation of a phase-out plan in the refrigeration sector (CFC manufacturing) | Individual | ASP | PAK | REF | 39 | PRP | 50 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 | 2005-05-01 | 20000 | -168 | 19832 | 19832 | 100% | 0 | 0 |  | 1500 | -15 | 1485 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) and methyl chloroform (MCF) to tetrachloroethylene (PER) and water in combination with partial process modification at Hirra Farooq Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 51 | A | O | I | CTC MCF | 37.5 | 37.5 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 246493 | -536 | 245957 | 245957 | 100% | 0 | 0 |  | 22184 | -48 | 22136 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC), methyl chloroform (MCF) and CFC-113 to tetrachloroethylene (PER) and water in combination with process modification at Breeze Frost Industries Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 52 | A | O | I | CTC MCF CFC | 33.2 | 33.2 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 282056 | -204 | 281852 | 281852 | 100% | 0 | 0 |  | 21254 | -15 | 21239 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Project preparation for a halon sector phase-out plan | Individual | ASP | PAK | HAL | 40 | PRP | 53 | A | O | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2003-12-01 | 2004-12-01 | 22000 | -780 | 21220 | 21220 | 100% | 0 | 0 |  | 1650 | -61 | 1589 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNDP | Extension of institutional strengthening project: phase 3 | Individual | ASP | PAK | SEV | 41 | INS | 54 | N | T | I | No_ODP | 18.6 | 18.6 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-11-01 | 224467 | 0 | 224467 | 221991 | 98.9% | 2476 | 0 | 0 | 16835 | 0 | 16649.3003 | 185.6997 | 0 | Completed in 2005. Financially Completed in 2008. | [13 empty] | 2003 | Non-Investment
FIN | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | ASP | PAK | HAL | 41 | TAS | 55 | A | O | I | HAL | 24.2 | 24.2 |  |  | 2003-12-01 | 2004-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 209400 | -786 | 208614 | 208614 | 100% | 0 | 0 |  | 18846 | -71 | 18775 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2003 | INV
COM | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (first tranche) | Multi-Year | ASP | PAK | REF | 41 | TAS | 56 | A | O | I | CFC | 36 | 36 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2004-12-01 |  | 191000 | 0 | 191000 | 186528 | 97.66% | 4472 | 4472 | 4000 | 14325 | 0 | 13990 | 335 | 335 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2003 | INV | 614 | 578 |  |  | Yes | N/A | N/A
COM | UNIDO | Sector phase-out plan of CTC | Multi-Year | ASP | PAK | PHA | 41 | INV | 57 | A | O | I | CTC | 100 | 109.7 |  |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-07-01 |  | 1200000 | 0 | 1200000 | 1196085 | 99.67% | 3915 | 3345 | 3345 | 90000 | 0 | 89706 | 294 | 251 | The project will be financially completed upon disbursement of unliquidated obligations. | [10 empty] | 2006-07-01 |  |  | 20022003 | INV | 61.9 | 148.5 |  |  | No | Yes | No
FIN | IBRD | Phase-out of the use of CFCs in remaining foam enterprises: Pakistan Insulation, Simpson Wire, HEPCO, Indus Plastic, Workman and Thermocraft Engineering | Individual | ASP | PAK | FOA | 41 | INV | 58 | N | O | I | CFC | 106.9 | 106.9 | 0 | 0 | 2003-12-01 | 2005-11-01 | 2006-01-01 |  | 2006-12-01 | 2007-06-01 | 658973 | -12331 | 646642 | 646642 | 100% | 0 | 0 |  | 49423 | -801 | 48622 | 0 | 0 | Project completed. | [13 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of the use of CFC-11 and CFC-12 in the manufacture of refrigeration equipment at Dawlance, United Refrigeration, Ice Age and at 29 small enterprises | Individual | ASP | PAK | REF | 42 | INV | 59 | N | O | I | CFC | 181.3 | 181.3 | 0 | 0 | 2004-04-01 | 2005-08-01 | 2007-04-01 |  | 2006-12-01 | 2007-06-01 | 1126855 | -49164 | 1077691 | 1077691 | 100% | 0 | 0 |  | 84514 | -3195 | 81319 | 0 | 0 | Project completed. | [13 empty] | 2003 | INV | 0 | 0 | 0 | 0
COM | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (second tranche) | Multi-Year | ASP | PAK | REF | 44 | TAS | 61 | A | O | I | CFC | 80 | 80 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-05-01 |  | 534200 | 0 | 534200 | 521267 | 97.58% | 12933 | 12341 | 12353 | 40065 | 0 | 39095 | 970 | 926 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2004 | INV | 379 | 350 |  |  | Yes | N/A | N/A
COM | UNIDO | Sector phase-out plan of CTC (second tranche) | Multi-Year | ASP | PAK | PHA | 44 | INV | 62 | A | O | I | CTC | 326.5 | 326.5 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-07-01 |  | 1300000 | 0 | 1300000 | 1273858 | 97.99% | 26142 | 14348 | 14348 | 97500 | 0 | 95539 | 1961 | 1076 | The project is expected to be financially completed in 2009. | [13 empty] | 2004 | INV | 41.8 | 41.8 |  |  | Yes | Yes | Yes
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | PAK | FUM | 45 | TAS | 63 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 30000 | -7149 | 22851 | 22851 | 100% | 0 | 0 |  | 2700 | -643 | 2057 | 0 | 0 | Financial completion in May 2008. Refund was reported to 54th ExCom, Apr 2008. FIN. Refund was reported to 55th ExCom, Jul 2008. FIN. | [13 empty] | 2005 | NON-INV
COM | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (third tranche) | Multi-Year | ASP | PAK | REF | 47 | INV | 64 | A | O | I | CFC | 80 | 80 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 |  | 2008-09-01 |  | 414300 | 0 | 414300 | 412850 | 99.65% | 1450 | 1140 | 1000 | 31073 | 0 | 30964 | 109 | 86 | Project completed in Sep 2008. | [13 empty] | 2005 | INV | 79 | 49 |  |  | Yes | N/A | N/A
COM | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | PAK | SEV | 51 | INS | 65 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-03-01 | 2009-04-01 |  | 2008-09-01 |  | 112233 | 0 | 112233 | 112233 | 100% | 0 | 0 | 0 | 8418 | 0 | 8418 | 0 | 0 | Completed in 2008. Ban on import of CFC-based compressors was imposed in July 2008 under the new Trade Policy 2008-09. Although not obligatory under the provisions of the Montreal Protocol, Pakistan is the only country in the region which has taken this initiative voluntarily. After training of the customs officials to curb ODS illegal trade, the customs authorities seized smuggled CFC-12. Federal Board of Revenue (Revenue Division) was requested to auction the consignments through eligible CFC importers. The project phased out over 91% import and consumption of ODS and is successfully heading towards 100% phase out target. | [13 empty] | 2007 | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase IV, second year) | Individual | ASP | PAK | SEV | 53 | INS | 66 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-10-01 | 2008-11-01 | 2009-11-01 |  |  | 112234 | 0 | 112234 | 61501 | 54.8% | 50733 | 0 | 20293.2 | 8418 | 0 | 4612.8216 | 3805.1784 | 0 | Activities have continued from PAK/SEV/51/INS/65 in 2008. Phase 5 to be approved at 57th ExCom. | [13 empty] | 2007 | Non-Investment
ONG | UNIDO | Sector phase-out plan of CTC (third tranche) | Multi-Year | ASP | PAK | PHA | 54 | INV | 67 | A | O | I | CTC | 62.5 | 17 |  |  | 2008-04-01 | 2008-10-01 | 2009-03-31 | 2009-12-01 |  |  | 245665 | 0 | 245665 | 37239 | 15.16% | 208426 | 26890 | 50000 | 25924 | 0 | 3930 | 21994 | 2838 | Public awareness activities continued. Purchasing of equipment for three metal cleaning companies was finalized. Commissioning is being finalized. Identification of institutions to be provided with equipment for training and technology demonstration has been organized. Import control and reporting is progressing. | [13 empty] | 2008 | INV | 15 | 0 |  |  | Yes | No | No
COM | UNDP | Project preparation for a MDI investment project | Individual | ASP | PAK | ARS | 54 | PRP | 68 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-11-01 |  | 60000 | 0 | 60000 | 16135 | 26.89% | 43865 | 28769 | 43865 | 4500 | 0 | 1210.125 | 3289.875 | 2157.675 | Completed in 2008. The Project has been prepared and was submitted and approved at the 56th ExCom. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | PAK | PHA | 55 | PRP | 69 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-31 | 2009-07-31 |  |  | 60000 | 0 | 60000 | 20000 | 33.33% | 40000 | 0 | 40000 | 7800 | 0 | 2600 | 5200 | 0 | Agreement prepared pending signature | [13 empty] | 2008
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | PAK | PHA | 55 | PRP | 70 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 90000 | 0 | 90000 | 60 | 0.06667% | 89940 | 0 | 30000 | 6750 | 0 | 5 | 6745 | 0 | Survey is organized in collaboration with UNEP. Investment activities will be prepared based on preliminary results of the survey. | Planning of completion was made on the basis and assumption that UNEP survey would proceed in due course. Legislation on import control of ODS is in place. HCFC-specific amendments may be introduced as appropriate in due course. | [12 empty] | 2008 | NON-INV
ONG | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | PAK | ARS | 56 | INV | 71 | N | O | I | CFC | 83.8 | 0 | 0 | 0 | 2008-11-01 |  | 2011-11-01 | 2011-11-01 |  |  | 449996 | 0 | 449996 | 0 | 0% | 449996 | 0 | 89999.2 | 33750 | 0 | 0 | 33750 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | PAK | ARS | 56 | TAS | 72 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2011-11-30 | 2011-11-30 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 70000 | 9100 | 0 | 0 | 9100 | 0 | Newly approved project. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | PAN | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | -3000 | 27000 | 27000 | 100% | 0 | 0 | 0 | 3900 | -390 | 3510 | 0 | 0 | Project financially completed. | $ 6,000 plus $ 780 PSC returned ExCom 41 ($ 3,000 plus $ 390 PSC added ExCom 11) | [12 empty] | 1992 | Non Investment
FIN | UNEP | Institutional strengthening: Establishment of COGO | Individual | LAC | PAN | SEV | 10 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-04-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 | 0 | 0 | 22425 | 0 | 22425 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1993 | Non Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 11 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | USA | Technical assistance in halon-1211 |  | LAC | PAN | HAL | 13 | TAS | 4 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 120000 | -42445 | 77555 | 77555 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible and rigid polyurethane foam at Plastifoam, S.A., Profomsa, and Thermofoam, S.A. | Individual | LAC | PAN | FOA | 13 | INV | 5 | A | O | I | CFC | 26 | 26 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1999-08-01 | 2002-10-01 | 155000 | -13140 | 141860 | 141860 | 100% | 0 | 0 | 0 | 20150 | -1708 | 18442 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PAN | REF | 18 | TAS | 6 | A | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-07-01 | 2003-11-01 | 172465 | -10608 | 161857 | 161857 | 100% | 0 | 0 | 0 | 22420 | -1379 | 21041 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 18 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAN | FOA | 21 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2637 | 12363 | 12363 | 100% | 0 | 0 | 0 | 1950 | -343 | 1607 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
CLO | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at Productos Moldeados America S.R. Ltda. (Plasticos Modernos) | Individual | LAC | PAN | FOA | 22 | INV | 9 | A | O | I | CFC | 16.2 | 16 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2003-11-01 | 339296 | -213326 | 125970 | 125970 | 100% | 0 | 0 | 0 | 44108 | -27732 | 16376 | 0 | 0 | Canceled in 2003. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNEP | Development of refrigerant management plans | RMP | LAC | PAN | REF | 24 | PRP | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
COM | Finland | Implementation of the RMP: monitoring and evaluation of the RMP | Individual | LAC | PAN | REF | 29 | TAS | 11 | A | O | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2008-12-01 |  | 33000 | 0 | 33000 | 6800 | 20.61% | 26200 | 0 | 29200 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. |  | 2001
COM | Finland | Implementation of the RMP: training programme for custom officers | Individual | LAC | PAN | REF | 29 | TRA | 12 | A | O | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2003-05-01 | 2001-06-01 |  | 2007-12-01 |  | 70000 | 0 | 70000 | 29978 | 42.83% | 40022 | 379 | 48185 | 0 | 0 | 0 | 0 | 0 | Project completed. Balances to be returned after all pending payments have been recorded |  | 2001 |  |  |  | 2002-12-01
COM | UNEP | Refrigerant management plan: Training and certification programme in refrigeration | Individual | LAC | PAN | REF | 29 | TRA | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2008-12-01 |  | 126200 | 0 | 126200 | 50000 | 39.62% | 76200 | 0 | 76200 | 16406 | 0 | 6500 | 9906 | 0 | Project completed in December 2008 | [13 empty] | 1999 | Non Investment
COM | UNEP | Refrigerant management plan: Monitoring on assistance to develop legislation | Individual | LAC | PAN | REF | 29 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2002-12-01 |  | 2008-12-01 |  | 10000 | 0 | 10000 | 6000 | 60% | 4000 | 0 | 4000 | 1300 | 0 | 780 | 520 | 0 | Project completed in December 2008 | [13 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PAN | SEV | 31 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2002-08-01 |  | 2002-12-01 | 2004-10-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNIDO | Preparation of an awareness workshop on methyl bromide | Individual | LAC | PAN | FUM | 36 | TRA | 16 | A | O | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-10-01 | 2003-12-01 | 30000 | -5344 | 24656 | 24656 | 100% | 0 | 0 |  | 3900 | -700 | 3200 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
COM | UNEP | Renewal of institutional strengthening (phase 3) | Individual | LAC | PAN | SEV | 38 | INS | 17 | A | T | I | CFC | 12.4 | 12.4 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2007-01-01 |  | 149500 | 0 | 149500 | 47139 | 31.53% | 102361 | 0 | 102361 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2002 | Non Investment
FIN | UNDP | Project preparation for update of refrigerant management plan (investment components) | Individual | LAC | PAN | REF | 40 | PRP | 18 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2003 | Investment
FIN | UNEP | Project preparation for refrigerant management plan update | RMP update | LAC | PAN | REF | 40 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-03-01 | 2004-07-01 |  | 2004-10-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAN | SEV | 44 | INS | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2009-12-01 |  |  | 149500 | 0 | 149500 | 0 | 0% | 149500 | 0 | 149500 | 0 | 0 | 0 | 0 | 0 | NOU has been undertaking all the activities for compliance with the Montreal Protocol, such as timely and permanent monitoring of ODS trade , ODS data reporting with both Secretariats and Implementing Agencies, supporting customs office in training and enforcement activities. NOU is also supervising the implementation of the TPMP. | [13 empty] | 2004 | Non Investment
COM | UNDP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | INV | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-04-01 | 2005-12-01 |  | 2008-12-01 |  | 250152 | 0 | 250152 | 250152 | 100% | 0 | 0 | 0 | 18762 | 0 | 18762 | 0 | 0 | Completed in 2008. A total of 100 cold stores at embarkations have been converted under the NPP in Panama. Kit of good practices and training was provided to technicians servicing the fishery sector. 250 kits of good practice in the process of being procured and will be delivered in early 2009. 1 training seminar of technicians conducted in 2008 with more to follow in 2009. Additional equipment for the reconversion programme for the fishery sector in the process of being procured. | [13 empty] | 2004 | Investment | 168.4 | 168.4 |  |  | Yes | Yes | yes
ONG | UNEP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 | 2009-12-01 |  |  | 25000 | 0 | 25000 | 8287.54 | 33.15% | 16712.46 | 0 | 16712.46 | 3250 | 0 | 1077.3802 | 2172.6198 | 0 | Agreement signed with counterpart. Work plan discussed and approved. Unit for illegal prevention established within Customs Office. Nearly 100 customs officers trained among current and newcomers in all regional customs offices. | [13 empty] | 2004 | Non Investment
ONG | UNDP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-Year | LAC | PAN | PHA | 47 | INV | 24 | N | O | I | CFC | 36.5 | 36.5 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 | 2010-01-01 |  |  | 238000 | 0 | 238000 | 17695 | 7.435% | 220305 | 0 | 44061 | 17850 | 0 | 1327.125 | 16522.875 | 0 | See PAN-22. | [13 empty] | 2005 | Investment | 131.95 | 131.95 |  |  | Yes | Yes | yes
ONG | UNEP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-year | LAC | PAN | PHA | 47 | TRA | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 | 2009-03-01 |  |  | 15000 | 0 | 15000 | 900 | 6% | 14100 | 0 | 14100 | 1950 | 0 | 117 | 1833 | 0 | Unit for illegal prevention established within Customs Office. Nearly 100 customs officers trained among current and newcomers in all regional customs offices. | [13 empty] | 2005 | Non Investment
ONG | UNDP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-Year | LAC | PAN | PHA | 50 | INV | 26 | N | O | I | CFC | 66 | 66 | 0 | 0 | 2006-11-01 |  | 2008-11-01 | 2010-07-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 40000 | 15000 | 0 | 0 | 15000 | 0 | See PAN-22. Tranches 4 & 5 approved at 56th ExCom. | [13 empty] | 2006 | Investment | 65.95 |  |  |  | Latest | Latest | Latest
ONG | UNEP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-year | LAC | PAN | PHA | 50 | TAS | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 | 2010-03-01 |  |  | 10000 | 0 | 10000 | 0 | 0% | 10000 | 0 | 10000 | 1300 | 0 | 0 | 1300 | 0 | New draft agreement is under consideration of counterpart. Customs Office has been upgraded to the Ministerial level and re-structuring of units and personnel are undergoing. | [13 empty] | 2006 | Non Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PAN | PHA | 55 | PRP | 28 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | International consultants identified for the HPMP preparation. HPMP launch is expected to take place in early 2009. | [13 empty] | 2008 | Investment
ONG | UNDP | National phase-out plan for Annex A (Group I) substances (fourth and fifth tranches) | Multi-Year | LAC | PAN | PHA | 56 | INV | 29 | N | O | I | CFC | 66 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 255000 | 0 | 255000 | 0 | 0% | 255000 | 0 | 102000 | 19125 | 0 | 0 | 19125 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PAR | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-10-01 |  | 1996-10-01 | 1999-05-01 | 43000 | -4000 | 39000 | 39000 | 100% | 0 | 0 | 0 | 5590 | -520 | 5070 | 0 | 0 | Project financially completed. | $ 4,000 plus $ 520 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | LAC | PAR | SEV | 21 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 2000-02-01 |  | 2001-07-01 | 2001-12-01 | 66300 | 0 | 66300 | 66300 | 100% | 0 | 0 | 0 | 8619 | 0 | 8619 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAR | FOA | 22 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of polyurethane foam at Superspuma Del Paraguay SAIC, Suenolar, La Asuncena, and Industrias Cel | Individual | LAC | PAR | FOA | 23 | INV | 4 | A | O | I | CFC | 55.5 | 55.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-10-01 | 405600 | -118208 | 287392 | 287392 | 100% | 0 | 0 | 0 | 52728 | -15367 | 37361 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | LAC | PAR | REF | 27 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-10-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
COM | UNEP | Implementation of the RMP: Monitoring and control of ODS and ODS based equipment, and training of customs officers and other inspection officers | Individual | LAC | PAR | REF | 32 | TAS | 6 | A | O | I | CFC | 15.2 | 15.2 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2001-12-03 |  | 2008-12-01 |  | 44920 | 0 | 44920 | 34931.44 | 77.76% | 9988.56 | 0 | 9988.56 | 5839.6 | 0 | 4541.0872 | 1298.5128 | 0 | Project completed in December 2008. Audit reports received. Last disbursement issued. Coordination workshops and meetings among NOU, Customs and other enforcement authorities carried out to agree guidelines for implementing Decree No. 12685/0899). The system for importing ODSs is functioning through the following steps: (a) The importer introduces a request to register as an ODS importer with the NOU only once. (b) When applicable, the importer makes a formal import request together with a pro-forma invoice at the NOU office. (c) The importer’s request is verified against his assigned quota and corresponding imports for the year, if applicable, the request is approved and the fee for import of ODS or ODS containing equipment is calculated for payment and granting of corresponding import license. (d) The importer then files the import request along with the trade import license at the customs office. (e) The customs computerized system “Sofia” requires the import license for any ODS or ODS-containing equipment and the processing customs officer has to introduce the license number assigned by the NOU and manually verifies that it corresponds with the list of assigned licenses thus authorizing the shipment. (f) At the port of entry, incoming merchandise related to ODS is systematically passed through what is called the “red channel” which requires physical inspection. The NOU officers are called to the port in order to inspect the merchandise with the ODS identifiers. (g) Each ODS importer must present the report of ODS imports for the previous license (“licensing returns”), along with copy of all related documentation (invoices, bills of lading, etc.) to the NOU, in order to request a new ODS import license. (h) Once a year the NOU requests the customs records of ODS imports in order to use as cross-check reference with the imports reported by the importers. | [5 empty] | 2003-06-03 | [7 empty] | 2000 | Non Investment
COM | UNEP | Implementation of the RMP: Train of trainers and training of refrigeration service technicians | Individual | LAC | PAR | REF | 32 | TRA | 7 | A | O | I | CFC | 56.7 | 56.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-12-03 |  | 2008-12-01 |  | 168020 | 0 | 168020 | 124363.38 | 74.02% | 43656.62 | 8500 | 43656.62 | 21842.6 | 0 | 16167.2394 | 5675.3606 | 1105 | Project Completed in December 2008. Audit reports received. Consultant has prepared a check list of sector needs for tools kits to be purchased at the TPMP. | [13 empty] | 2000 | Non Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recyling of CFC-12 refrigerant | RMP-Component | LAC | PAR | REF | 32 | TAS | 8 | A | O | I | CFC | 96.3 | 96.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2004-12-01 | 2005-11-01 | 285158 | -8351 | 276807 | 276807 | 100% | 0 | 0 | 0 | 37071 | -1086 | 35985 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | PAR | SEV | 32 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-01-01 | 2004-09-01 | 44200 | 0 | 44200 | 44200 | 100% | 0 | 0 | 0 | 5746 | 0 | 5746 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
COM | UNEP | Implementation of the RMP: Policy dialogue programme on complementary policy and enforcement | Individual | LAC | PAR | REF | 32 | TAS | 10 | A | O | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2001-09-02 |  | 2008-12-01 |  | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project completed in December 2008. Audit reports received. Last disbursement issued. Coordination workshops and meetings among NOU, Customs and other national authorities carried out to promote the approval of ODS license system reviewed. Finally, August 2008, Decree No. 12685/08 was issued. The new decree establishes: 1) the Secretariat of the Environment as the authority for implementation of the ODS regulations, 2) controls over imports and exports of all ODSs controlled under the Montreal Protocol, 3) the operating mechanisms for the “ODS Import / Export Licensing System”, 4) controls over the imports and exports of ODS-containing equipment, 5) controls over commercialization of ODSs, and 6) sanctions for non-compliance. | [13 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | PAR | REF | 33 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Terminal umbrella project to phase out CFC-11 and CFC-12 consumption in the manufacture of commercial refrigeration equipment by replacement with HCFC-141b and HFC-134a at 11 SMEs | Individual | LAC | PAR | REF | 34 | INV | 12 | A | O | I | CFC | 7.4 | 7.4 | 0 | 0 | 2001-07-01 | 2001-11-01 | 2005-02-01 |  | 2005-12-01 | 2007-03-01 | 410379 | -27448 | 382931 | 382931 | 100% | 0 | 0 | 0 | 53349 | -3568 | 49781 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2001 | Investment
ONG | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | PAR | SEV | 39 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2005-04-01 | 2009-07-01 |  |  | 57460 | 0 | 57460 | 24631.78 | 42.87% | 32828.22 | 32828 | 32828.22 | 0 | 0 | 0 | 0 | 0 | NOU facilitated the Govement to manage all the activities for implementation of the Montreal Protocol in the country, such as the timely and permanent monitoring with the country’s MP obligations, ODS data reporting, maintain communication with both Secretariats and Implementing Agencies. Also, leaded the follow up of approval of the new ODS legal regime in the country. NOU play also an important role in project implementation (i.e. preparing reports and documents for audits, meeting IAs and Goverment requirements to sign TPMP funding agreements and to hire national consultants). | [13 empty] | 2003 | Non Investment
COM | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | PAR | SOL | 45 | TAS | 14 | N | O | I | TCA/CTC | 2.4 | 2.4 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-12-01 |  | 30000 | 0 | 30000 | 15343 | 51.14% | 14657 | 0 | 11725.6 | 2700 | 0 | 1380.87 | 1319.13 | 0 | Completed in 2008. During 2008 additional work was done by the local consultant in order to complete the technical assistance started in 2007 to users of CTC on laboratory applications. The project is operationally completed. Final payment to local consultant to be done in 2009. | [11 empty] | 2008-01-01 |  | 2005 | Non-Investment
ONG | Spain | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | PAR | FUM | 47 | TAS | 15 | A | O | I | MBR | 0.2 |  | 0 |  | 2005-11-01 | 2007-07-07 | 2007-12-01 | 2009-07-01 |  |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 |  | 5200 |  | This Project was approved on ExCom 47th, December 2005. 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only signature of PCR is remaining and expectd by Jul 09. . 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only PCR remain for signature that is expected on July 2009.
COM | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | PAR | PHA | 47 | PRP | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-04-01 |  | 30000 | 0 | 30000 | 22551 | 75.17% | 7449 | 0 | 7449 | 2250 | 0 | 1691.325 | 558.675 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | INV | 17 | N | O | I | CFC | 68.7 | 0 | 0 | 0 | 2007-03-01 |  | 2010-12-01 | 2010-12-01 |  |  | 160000 | 0 | 160000 | 0 | 0% | 160000 | 0 | 32000 | 12000 | 0 | 0 | 12000 | 0 | In late 2007 a review of the legal framework related to ODS initiated in order to improve ODS imports/exports control. This review culminated with the adoption a new regulatory decree in August 2008. In April 2008, workshops on the control of imports and exports of ODS were conducted to train SEAM and Customs staff on the procedures to issue permits for the import and export of ODS and the corresponding control measures. In June 2008, the project coordinator was hired and an action plan and timeline for project implementation was prepared. First activities including the procurement of equipment for technicians started, however disbursements will only be reflected in 2009 when purchase order is issued. | [13 empty] | 2007 | Investment | 31.6 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-12-01 | 2010-12-01 |  |  | 80000 | 0 | 80000 | 48000.38 | 60% | 31999.62 | 32000 | 31999.62 | 10400 | 0 | 6240.0494 | 4159.9506 | 4160 | Project execution started in 2008. Coordinator hired to support NOU with project management. TPMP launching workshop carried out. Institutional contacts have been made with main stakeholders of the refrigeration sector in the country to agree cooperation agreements. In addition, the international bidding process is already in place for the purchase of R/R equipment. In order to further enhance the application of the reviewed license system (Decree No. 12685/0899, two agreements are being made with the National Customs Office and the Faculty of Chemistry of the National University of Asuncion. Interim progress and financial reports for each of the TPMP components received. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAR | SEV | 53 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 3172 | 60000 | 0 | 0 | 0 | 0 | 0 | Funding agreement (SSFA) signed | [13 empty] | 2007 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | PAR | PHA | 55 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-12-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions for HCFC survey, identification of country needs and further arrangements are being set. Funding agreement (SSFA) currently being negotiated with the country. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | PER | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1995-07-01 | 1995-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 | 0 | 6890 | 0 | 6890 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 13 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1996-07-01 |  | 1995-09-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Alfa S.A. | Individual | LAC | PER | REF | 15 | INV | 3 | A | O | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-09-01 | 2000-12-01 | 252727 | -567 | 252160 | 252160 | 100% | 0 | 0 | 0 | 32855 | -74 | 32781 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-02-01 | [9 empty] | 1994 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Andina Industrial S.A. | Individual | LAC | PER | REF | 15 | INV | 4 | A | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  |  | 2002-06-01 | 229816 | -75350 | 154466 | 154466 | 100% | 0 | 0 | 0 | 29876 | -9795 | 20081 | 0 | 0 | Canceled in 2000. Financially completed in 2002. |  |  | 1997-09-01 | [10 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coldex S.A. | Individual | LAC | PER | REF | 15 | INV | 5 | A | O | I | CFC | 67.4 | 67.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1998-01-01 | 2000-12-01 | 748966 | -102197 | 646769 | 646769 | 100% | 0 | 0 | 0 | 97366 | -13286 | 84080 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Lenche S.A. (Inlensa) | Individual | LAC | PER | REF | 15 | INV | 6 | A | O | I | CFC | 6 | 6 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 2002-09-01 | 2003-11-01 | 201443 | -29670 | 171773 | 171773 | 100% | 0 | 0 | 0 | 26188 | -3857 | 22331 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  | 1997-12-01 | [10 empty] | 1994 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Reunidas S.A. (Inresa) | Individual | LAC | PER | REF | 15 | INV | 7 | A | O | D | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1996-06-01 |  |  | 2003-01-01 | 267641 | -91077 | 176564 | 176564 | 100% | 0 | 0 | 0 | 34793 | -11840 | 22953 | 0 | 0 | Canceled in 1999. Financially completed in 2003. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrial Selva S.A. (Indusel) | Individual | LAC | PER | REF | 15 | INV | 8 | A | O | I | CFC | 34.9 | 34.9 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2002-03-01 | 412098 | -331 | 411767 | 411767 | 100% | 0 | 0 | 0 | 53573 | -43 | 53530 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-12 in the production of polystyrene foam at Productos Moldeados America SR, Ltd. (Promola) | Individual | LAC | PER | FOA | 17 | INV | 9 | A | O | D | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1998-11-01 | 1999-12-01 | 294960 | 0 | 294960 | 294960 | 100% | 0 | 0 | 0 | 38345 | 0 | 38345 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | UNIDO | Project preparation assistance in solvent sector | Individual | LAC | PER | SOL | 17 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -8097 | 21903 | 21903 | 100% | 0 | 0 |  | 3900 | -1057 | 2843 | 0 | 0 | FIN |  |  |  | 1999-01-01
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | PER | SEV | 17 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1998-10-01 |  | 2000-08-01 | 2001-08-01 | 154000 | 0 | 154000 | 154000 | 100% | 0 | 0 | 0 | 20020 | 0 | 20020 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Non Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 18 | PRP | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-03-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Master Service, S.A. | Individual | LAC | PER | REF | 19 | INV | 13 | A | O | I | CFC | 9.4 | 9.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-02-01 | 2002-04-01 | 140000 | -10839 | 129161 | 129161 | 100% | 0 | 0 | 0 | 18200 | -1409 | 16791 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest feezers at Compañia Peruana de Máquinas para Coser S.A. (Copemaco) | Individual | LAC | PER | REF | 19 | INV | 14 | A | O | I | CFC | 12.9 | 12.9 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 193834 | 0 | 193834 | 193834 | 100% | 0 | 0 | 0 | 25198 | 0 | 25198 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers and refrigerators at Formetal | Individual | LAC | PER | REF | 19 | INV | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  |  | 2001-12-01 | 118000 | -64335 | 53665 | 53665 | 100% | 0 | 0 | 0 | 15340 | -8364 | 6976 | 0 | 0 | Canceled in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Col-Frio S.A. | Individual | LAC | PER | REF | 19 | INV | 16 | A | O | I | CFC | 11.7 | 11.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 175000 | -468 | 174532 | 174532 | 100% | 0 | 0 | 0 | 22750 | -61 | 22689 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PER | REF | 19 | TAS | 17 | A | O | I | CFC | 28.6 | 28.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 2001-12-01 | 2003-04-01 | 342695 | -53108 | 289587 | 289587 | 100% | 0 | 0 | 0 | 44550 | -6904 | 37646 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1996 | Investment
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Faber Castell | Individual | LAC | PER | SOL | 20 | INV | 18 | A | O | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-11-01 | 1997-10-01 |  | 1998-09-01 | 2000-12-01 | 16409 | -4827 | 11582 | 11582 | 100% | 0 | 0 |  | 2133 | -630 | 1503 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Carbolan | Individual | LAC | PER | SOL | 20 | INV | 19 | A | O | I | TCA | 0.4 | 0.4 |  |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 31457 | -7307 | 24150 | 24150 | 100% | 0 | 0 |  | 4089 | -954 | 3135 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Papeles Industriales | Individual | LAC | PER | SOL | 20 | INV | 20 | A | O | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-12-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 47953 | -957 | 46996 | 46996 | 100% | 0 | 0 |  | 6234 | -134 | 6100 | 0 | 0 | FIN
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | PER | REF | 21 | TRA | 21 | A | O | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2002-12-01 | 2003-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | LAC | PER | FUM | 24 | PRP | 22 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2000-06-01 | 2002-12-01 | 25000 | -863 | 24137 | 24137 | 100% | 0 | 0 | 0 | 3250 | -112 | 3138 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNEP | Implementation of the RMP: Custom officers training programme | Individual | LAC | PER | REF | 27 | TRA | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2004-05-04 | 2005-12-01 | 34000 | -13000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 4420 | -1690 | 2730 | 0 | 0 | Project financially completed. | $ 13,000 plus $ 1,690 PSC returned Excom 46 |  |  |  | 2001-12-01 | [8 empty] | 1999 | Non Investment
FIN | UNDP | Preparation of a project in general foam subsector | Individual | LAC | PER | FOA | 27 | PRP | 24 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNEP | Implementation of the RMP: Support for a licensing system | Individual | LAC | PER | REF | 27 | TAS | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-02 |  | 2002-02-01 | 2003-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Implementation of the RMP: Code of good practices in refrigeration | Individual | LAC | PER | REF | 27 | TAS | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2002-02-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
COM | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PER | SEV | 29 | INS | 27 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2002-06-01 |  | 102700 | 0 | 102700 | 57990 | 56.47% | 44710 | 0 | 44710 | 13351 | -5812 | 7538.7 | 0.3 | 0 | Project completed | $ 0 returned plus $ 5,812 returned to ExCom 49 | [12 empty] | 1999 | Non Investment
FIN | UNDP | Phase-out of methyl bromide in soil fumigation | One-off-Phaseout | LAC | PER | FUM | 31 | INV | 28 | N | O | I | MeBr | 4 | 4 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-11-01 | 209770 | 0 | 209770 | 209770 | 100% | 0 | 0 | 0 | 27270 | 0 | 27270 | 0 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2000 | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | PER | FOA | 33 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Foam sector ODS phaseout plan (covering 5 enterprises: Molflex; Zetaflex; EMSA; Metusa; Polishoes) | Individual | LAC | PER | FOA | 35 | INV | 30 | A | O | I | CFC | 33.8 | 33.8 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2006-12-01 | 2008-04-01 | 325277 | 0 | 325277 | 324662 | 99.81% | 615 | 0 | 0 | 42286 | 0 | 42206.05 | 79.95 | 0 | Completed in 2006. Financially completed in 2008. | [13 empty] | 2001 | Investment
ONG | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | PER | SEV | 37 | INS | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2004-08-01 | 2010-12-01 |  |  | 133510 | 0 | 133510 | 0 | 0% | 133510 | 0 | 133510 | 0 | 0 | 0 | 0 | 0 | NOU carried out all activities for compliance with the Montreal Protocol. Timely and permanent monitoring of ODS consumption, data reporting and submission to both Secretariats and Implementing Agencies. NOU play also an important role in the preparation of the TPMP (i.e. reports and documents, meetings and missions, data gathering, national consultations, strategy development, etc.) | [13 empty] | 2002 | Non Investment
FIN | UNEP | Preparation of the refrigerant management plan update proposal | RMP Update | LAC | PER | REF | 37 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-02-01 | 2003-08-01 |  | 2004-07-01 | 2008-12-01 | 15000 | -3000 | 12000 | 12000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 3,000 returned to ExCom 52 | [12 empty] | 2002 | Non Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | LAC | PER | REF | 39 | PRP | 33 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2003 | Investment
ONG | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | LAC | PER | REF | 43 | TAS | 34 | A | O | I | CFC | 30.9 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2007-12-01 | 2009-06-01 |  |  | 40000 | 0 | 40000 | 15000 | 37.5% | 25000 | 8000 | 25000 | 5200 | 0 | 1950 | 3250 | 1040 | Progress and financial reports submitted on Dec-2008 by national consultant. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP update: refrigeration technicians certification and licensing system | Individual | LAC | PER | REF | 43 | TAS | 35 | A | O | I | CFC | 66.4 | 0 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 | 2009-06-01 |  |  | 86000 | 0 | 86000 | 45116.67 | 52.46% | 40883.33 | 30000 | 40883.33 | 11180 | 0 | 5865.1671 | 5314.8329 | 3900 | Agreements with training and accreditation institutions signed. Three workshops and 120 technicians trained. 33 more workshops involving nearly 1,000 are programmed to be completed in third quarter of 2009. | [13 empty] | 2004 | Non Investment
ONG | UNEP | Implementation of the RMP update: technical assistance for prevention of illegal CFC trade | Individual | LAC | PER | REF | 43 | TAS | 36 | A | O | I | CFC | 20.1 | 0 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 | 2009-06-01 |  |  | 26000 | 0 | 26000 | 6000 | 23.08% | 20000 | 10000 | 20000 | 3380 | 0 | 780 | 2600 | 1300 | 25 new customs officers trained. Review of current legislation and further training to a broader audience (agents, police, prosecutor, etc) will take place in first quarter of 2009 | [13 empty] | 2004 | Non Investment
ONG | UNDP | Implementation of the RMP update: technical assistance for the refrigeration sector | RMP-Component | LAC | PER | REF | 43 | TAS | 37 | N | O | I | CFC | 94.9 | 94.9 | 0 | 0 | 2004-07-01 | 2007-02-01 | 2007-12-01 | 2009-07-01 |  |  | 123000 | 0 | 123000 | 101466 | 82.49% | 21534 | 0 | 8613.6 | 11070 | 0 | 9131.94 | 1938.06 | 0 | During 2008 the RMP in Peru continued implementation. Activities completed include the purchase of parts and equipment for the R & R network along with their distribution thought workshops. More technicians were found than expected. The full distribution should be concluded in 2009 along with the final purchase of additional equipment to also be distributed. Agreements were reached with various different capacity building institutions (GAMOR, CONCORDIA SENATI) so as to provide training to a minimum of 1200 technicians in 36 courses. | [13 empty] | 2004 | Investment
ONG | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | PER | PHA | 50 | PRP | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 | 2009-06-01 |  |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | TPMP resulting from this activity was approved at 55 ExCom meeting. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | PER | PHA | 50 | PRP | 39 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-12-01 |  | 15000 | 0 | 15000 | 12600 | 84% | 2400 | 0 | 2400 | 1125 | 0 | 945 | 180 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PER | PHA | 55 | PRP | 40 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-09-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | Approved at 55th ExCom. Maintained initial discussions with NOU on the activities to be included in the preparation of the HPMP. Launching event programmed for March 2009 | [13 empty] | 2008 | Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | PER | PHA | 55 | INV | 41 | N | O | I | CFC | 15 | 0 | 0 | 0 | 2008-07-01 |  | 2010-12-01 | 2010-12-01 |  |  | 183500 | 0 | 183500 | 0 | 0% | 183500 | 0 | 36700 | 13763 | 0 | 0 | 13763 | 0 | Approved at 55th ExCom. Project document sent to the country for signatures, and work plan agreed. Substantive activities to start in 2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PER | PHA | 55 | TAS | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-12-31 | 2010-12-31 |  |  | 77500 | 0 | 77500 | 0 | 0% | 77500 | 0 | 77500 | 10075 | 0 | 0 | 10075 | 0 | Draft funding agreement (SSFA) is under consideration by Ministry of Industry. Internal discussions are undergoing regarding the designation of focal point for Multilateral Environmental Agreeements, including Montreal Protocol, due to the recent creation of the Ministry of Environment. | [13 empty] | 2008
FIN | IBRD | Country programme preparation | Individual | ASP | PHI | SEV | 04 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 19952 | 17415 | 37367 | 37367 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Training programme in the refrigeration sector | RMP-Component | ASP | PHI | REF | 04 | TRA | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-04-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 64000 | -1707 | 62293 | 62293 | 100% | 0 | 0 | 0 | 8320 | -222 | 8098 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | PHI | SEV | 04 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 10826 | 39489 | 50315 | 50315 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | PHI | SEV | 06 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-08-12 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 400000 | -6325 | 393675 | 393675 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. Balance of funds returned to Multilateral Fund. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | PHI | SEV | 06 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 100000 | -57260 | 42740 | 42740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Country programme preparation | Individual | ASP | PHI | SEV | 08 | CPG | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 39820 | 39820 | 79640 | 79640 | 100% | 0 | 0 | 0 | 5177 | 5177 | 10354 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Concepcion Industries | Individual | ASP | PHI | REF | 09 | INV | 7 | N | O | I | CFC | 40.8 | 78.3 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-05-01 |  | 1998-10-01 | 1999-02-01 | 790000 | -46000 | 744000 | 744000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Full-production with C-pentane - Oct. 21, 1998. PCR was endorsed to WB on 01/12/99. Grant fund fully disbursed. No ODS eqpt. Dismantled - High pressure foam machine was used even at the start of operation. |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Sanyo Philippines | Individual | ASP | PHI | REF | 09 | INV | 8 | N | O | D | CFC | 12.6 | 23.9 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-03-01 |  | 1996-11-01 | 1999-01-01 | 660000 | -37061 | 622939 | 622939 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Phase 2 completed 11/96 - adoption of HCFC 141b foam. PCR was endorsed to WB on 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 12/19/95 |  |  | 1997-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Transunion (formerly called Federal Electric Company) | Individual | ASP | PHI | REF | 09 | INV | 9 | N | O | I | CFC | 6.6 | 26.4 | 0 | 0 | 1993-03-01 | 1997-09-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 770000 | -204218.75 | 565781.25 | 565781.34 | 100% | -0.09 | -0.09 |  | 0 | 0 | 0 | 0 | 0 | Full production with C-pentane - Oct.1, 1998. PCR was endorsed to WB on 2/2/99. Date ODS Eqpt. Dismantled - 12/02/98. All safety equipmpent and other items are installed and operational. Total grant fund disbursed is $547,732.15 only (excluding FI fees). Completed revision of PCR's Table 5. Revised PCR submitted to WB on 10 Jan |  |  | 1997-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Instititional strengthening for Ozone Desk Operations | Individual | ASP | PHI | SEV | 09 | INS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-12-01 | 2002-05-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed physically and financially. |  |  | 1998-06-01 | 1999-12-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to semi-aqueous and aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 11 | N | O | D |  | 85.7 | 85.7 | 0 | 0 | 1993-03-01 | 1996-08-01 | 1993-09-01 |  | 1995-09-01 | 1998-07-01 | 790000 | 0 | 790000 | 790000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 8/16/96 |  |  | 1995-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to low-emission processing and organic solvents at Pacific Semiconductors, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1996-10-01 | 710000 | -710000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise decided not to proceed with project. Project cancelled. |  |  | 1993-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at Electronic Assemblies, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 13 | N | O | I | CFC | 4 | 4.16 | 0 | 0 | 1993-03-01 | 1996-04-01 | 1993-09-01 |  | 1997-02-01 | 1998-07-01 | 710000 | -34141 | 675859 | 675859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 6/11/96 |  |  | 1997-02-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at Integrated Microelectronic, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 14 | N | O | D | CFC | 14.6 | 14.6 | 0 | 0 | 1993-03-01 | 1997-08-01 | 1993-09-01 |  | 1997-12-01 | 1998-12-01 | 430000 | -72997.88 | 357002.12 | 357002.12 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/20/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 5/19/98 |  |  | 1996-07-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to semi-aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 15 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1997-02-01 | 70000 | -70000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise is no longer eligible for grant funding. Project cancelled. | [14 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Information exchange programme | Individual | ASP | PHI | SEV | 09 | TAS | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-11-01 |  |  | 1993-11-01 | 200000 | -200000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Funds transferred to UNEP for its implementation at the request of the Govt. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance for the financial institution | Individual | ASP | PHI | SEV | 09 | TAS | 17 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-08-01 | 1994-03-01 |  | 2000-04-01 | 2000-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project and PCR completed. |  |  | 1998-06-01 | 1999-12-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of tobacco fluffing process to carbon dioxide at Fortune Tobacco corporation | Individual | ASP | PHI | OTH | 09 | INV | 18 | N | O | I | CFC | 350 | 350 | 0 | 0 | 1993-03-01 | 1996-05-01 | 1995-03-01 |  | 1999-08-01 | 2000-08-01 | 4720000 | -267640 | 4452360 | 4452360 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully completed on Dec. 30, 1999. Decommissioning of the G -13 Plant was done from Jan. 10 to May 7, 2000. PCR was endorsed to WB on August 2, 2000. Grant fund fully disbursed. |  |  | 1997-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Philippines Appliance Corporation (Philacor) | Individual | ASP | PHI | REF | 09 | INV | 19 | N | O | I | CFC | 240 | 240 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1997-05-01 |  | 1998-04-01 | 1999-02-01 | 1770000 | 0 | 1770000 | 1770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR was endorsed to WB on 10/20/98. Date ODS Eqpt. Dismantled - 12/19/95. Grant fund fully disbursed. |  |  | 1998-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | PHI | SEV | 09 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 194550 | -129221 | 65329 | 65329 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 11 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-07-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | UNDP | Survey of ODS usage, data base generation and technical assistance for ODS phase-out for small-scale enterprises | Individual | ASP | PHI | SEV | 11 | TAS | 22 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1996-09-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1993 | Non-Investment
FIN | UNEP | Information exchange programme | Individual | ASP | PHI | SEV | 11 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1995-12-01 |  | 2000-12-01 | 2003-07-01 | 200000 | -1488 | 198512 | 198512 | 100% | 0 | 0 | 0 | 26000 | -193.44 | 25806.56 | 0 | 0 | Project financially completed. | $1,488 plus $ 193 PSC returned ExCom 41 | [12 empty] | 1993 | Non Investment
CLO | IBRD | User-sector project identification and preparation (1993) |  | ASP | PHI | SEV | 11 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  |  | 1994-12-01 | 150000 | -150000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | PHI | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 136027 | -93678 | 42349 | 42349 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-use at small manufacturers of flexible foam | Individual | ASP | PHI | FOA | 12 | INV | 26 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1999-12-01 | 2003-04-01 | 745000 | -262154 | 482846 | 482846 | 100% | 0 | 0 | 0 | 96850 | -34080 | 62770 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-07-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the residual use of CFC in the manufacture of extruded polystyrene foam sheet in 3 companies: Concept Packaging Co., Amtes Co., and Q.C. Styropackaging Co. | Individual | ASP | PHI | FOA | 12 | INV | 27 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-12-01 | 1995-03-01 |  | 1997-12-01 | 1999-05-01 | 505000 | -230578 | 274422 | 274422 | 100% | 0 | 0 | 0 | 65650 | -29975 | 35675 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Nikkon Industrial Corporation | Individual | ASP | PHI | FOA | 12 | INV | 28 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-09-01 | 1998-12-01 | 315000 | -46523 | 268477 | 268477 | 100% | 0 | 0 | 0 | 40950 | -6048 | 34902 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1994 | Investment
CLO | IBRD | Preparation of investment projects (1994) |  | ASP | PHI | SEV | 12 | PRP | 29 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 94900 | -94900 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase out of CFC in the manufacture of flexible polyurethane foam at Foamcraft Incorporated | Individual | ASP | PHI | FOA | 13 | INV | 31 | A | O | I | CFC | 90 | 90 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1998-05-01 | 2001-12-01 | 185000 | -19094 | 165906 | 165906 | 100% | 0 | 0 | 0 | 24050 | -2482 | 21568 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of polyurethane insulated building elements at Metal Forming Co. | Individual | ASP | PHI | FOA | 13 | INV | 32 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 305000 | -16698 | 288302 | 288302 | 100% | 0 | 0 | 0 | 39650 | -2171 | 37479 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase out of CFC in the manufacture of commercial refrigerators and ice boxes at Unimagna Philippines, Inc. | Individual | ASP | PHI | REF | 13 | INV | 33 | A | O | I | CFC | 29.5 | 29.5 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 1015700 | -54324 | 961376 | 961376 | 100% | 0 | 0 | 0 | 132041 | -7062 | 124979 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of the residual use of CFC in the manufacture of extruded polystyrene foam sheet at Styrotech Co. | Individual | ASP | PHI | FOA | 13 | INV | 34 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 60000 | -2297 | 57703 | 57703 | 100% | 0 | 0 | 0 | 7800 | -299 | 7501 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 15 | PRP | 35 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1994-12-01 | 1995-12-01 |  | 1996-03-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | PHI | SEV | 16 | PRP | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-12-31 | 1996-12-01 | 169937 | -70000 | 99937 | 99937 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Residual phaseout of CFCs in the manufacture of flexible polyurethane (slabstock) at Mandaue Foam Industries Inc. | Individual | ASP | PHI | FOA | 17 | INV | 37 | A | O | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-12-01 |  | 1997-06-01 | 2000-07-01 | 217000 | -9332 | 207668 | 207668 | 100% | 0 | 0 | 0 | 28210 | -1213 | 26997 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Umbrella project for the conversion of production of portable halon fire extinguishers of members companies of Fire Protectors Federation Inc. | Individual | ASP | PHI | HAL | 18 | INV | 38 | N | O | I | Halon | 77 | 77 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 2000-09-01 | 2003-04-01 | 114108 | -8935 | 105173 | 105173 | 100% | 0 | 0 | 0 | 14834 | -1161 | 13673 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-06-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Matsushita Electric Philippines Corporation (Mepco) | Individual | ASP | PHI | REF | 18 | INV | 39 | A | O | R | CFC | 47 | 47 | 0 | 0 | 1995-11-01 | 1996-06-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 112244 | -4513 | 107731 | 107731 | 100% | 0 | 0 | 0 | 14592 | -587 | 14005 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNIDO | Preparation of a recovery and recycling project in the refrigeration sector | Individual | ASP | PHI | REF | 18 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-01-01 |  | 1997-11-01 | 1998-08-01 | 15000 | 543 | 15543 | 15543 | 100% | 0 | 0 |  | 1950 | 71 | 2021 | 0 | 0 | FIN
FIN | USA | MACs servicing demonstration project |  | ASP | PHI | REF | 18 | DEM | 41 | A | O | I | CFC | 11 |  | 0 |  | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1999-09-01 | 1999-09-01 | 285500 | 0 | 285500 | 285500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | UNDP is working with the Government of the Philippines to complete the project. |  | 1995 | 1997-05-01
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 18 | PRP | 42 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | UNDP | Phaseout of the use of CFCs in the manufacture of PU foam for insulation and structural purposes at Himalaya Mfg. Corp. | Individual | ASP | PHI | FOA | 19 | INV | 43 | A | O | D | CFC | 17 | 17 | 0 | 0 | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 101000 | -4879 | 96121 | 96121 | 100% | 0 | 0 | 0 | 13130 | -634 | 12496 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | UNDP | Umbrella project for conversion from CFC-11 foam blowing agent into HCFC-141b, and CFC-12 and R-502 refrigerants into HFC-134a and HFC-404a at Gomeco, Chee Puck and Well Built | Individual | ASP | PHI | REF | 19 | INV | 44 | N | O | I | CFC | 28 | 28 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1998-04-01 |  | 2000-09-01 | 2003-04-01 | 156475 | -38769 | 117706 | 117706 | 100% | 0 | 0 | 0 | 20342 | -5040 | 15302 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-06-01 | [9 empty] | 1996 | Investment
FIN | IBRD | Philacor, Concepcion, Sanyo and Transunion -- Engineering Design and Assistance for the Use of HFC-134a Refrigerant in Household Refrigerators | Individual | ASP | PHI | REF | 19 | INV | 45 | N | O | I | CFC | 91.9 | 27.1 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1998-01-01 |  | 1998-05-01 | 1999-03-01 | 952000 | -485520 | 466480 | 466480 | 100% | 0 | 0 |  | 123760 | -58262.73 | 65497.27 | 0 | 0 | Project completed - HFC 134a refrigeration systems. PCRs endorsed to WB on 12/1/99. Grant fund fully disbursed. Philacor's Calamba Plant is not covered with grant funding. |  |  | 1998-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFC-113, 1,1,1 trichloroethane (TCA), CFC-11 and CFC-12 at multiple corporations that manufacture special formulations for various industrial markets | Individual | ASP | PHI | SOL | 19 | INV | 46 | N | O | I | TCA/CFC | 53.6 | 53.6 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1998-06-01 | 2003-09-01 | 642800 | -181667 | 461133 | 461133 | 100% | 0 | 0 | 0 | 83564 | -23617 | 59947 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1996 | Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | PHI | REF | 21 | PRP | 47 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 2000-12-01 | 35000 | -4264 | 30736 | 30736 | 100% | 0 | 0 | 0 | 4550 | -554 | 3996 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at PU Rigid Insulation Contractor | Individual | ASP | PHI | FOA | 22 | INV | 48 | N | O | I | CFC | 24.2 | 24.2 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1999-06-01 |  | 1999-12-01 | 2003-11-01 | 189290 | -14221 | 175069 | 175069 | 100% | 0 | 0 | 0 | 24608 | -1849 | 22759 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNIDO | National CFC recovery and recycling scheme | RMP | ASP | PHI | REF | 22 | TAS | 49 | A | O | I | CFC | 60 | 60 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2002-05-01 | 557500 | -49 | 557451 | 557451 | 100% | 0 | 0 |  | 72475 | -121 | 72354 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at MBA Urethane Products Contractor | Individual | ASP | PHI | FOA | 22 | INV | 50 | N | O | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 1999-12-01 | 2003-08-01 | 113574 | -22017 | 91557 | 91557 | 100% | 0 | 0 | 0 | 14765 | -2862 | 11903 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Soutech | Individual | ASP | PHI | FOA | 23 | INV | 51 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 1999-12-01 | 2003-04-01 | 326750 | -1799 | 324951 | 324951 | 100% | 0 | 0 | 0 | 42478 | -234 | 42244 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | UNDP | Umbrella project: Conversion to CFC-free technology in small CFC consuming enterprises using CFC in the manufacture of rigid polyurethane foam (Ashlar Industrial Corporation, Alen International, Zegal | Individual | ASP | PHI | FOA | 23 | INV | 52 | N | O | I | CFC | 5.1 | 5.1 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 39930 | -13985 | 25945 | 25945 | 100% | 0 | 0 | 0 | 5191 | -1818 | 3373 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Azkcon Refrigeration Industries, Inc. | Individual | ASP | PHI | REF | 23 | INV | 53 | A | O | I | CFC | 18.9 | 18.9 | 0 |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2005-04-01 | 370258 | -75353 | 294905 | 294905 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is completed, PCR drafted by UNDP for completion and submission by GTZ. Remaining balance and interest (USD 75.353) has been returned in Dec-04 to GTZ to be reported and returned to MLF at the 45th ExCom. | [13 empty] | 1992
FIN | UNDP | Project preparation to prepare the second and final phase for phaseout of ODS by solvent blenders | Individual | ASP | PHI | SOL | 24 | PRP | 54 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 | 1999-11-01 | 25000 | -22120 | 2880 | 2880 | 100% | 0 | 0 | 0 | 3250 | -2876 | 374 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | ASP | PHI | FUM | 25 | PRP | 55 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 1999-08-01 |  | 2000-12-01 | 2004-12-01 | 30000 | -358 | 29642 | 29642 | 100% | 0 | 0 | 0 | 3900 | -47 | 3853 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNDP | Elimination of CFC-113, l,l,l trichloroethane and CFC-12 at multiple corporations that manufacture special formulations for industrial markets (Ariad Industrial Co., Cloisonne, Redisol, Rodler) | Individual | ASP | PHI | SOL | 25 | INV | 56 | A | O | I | TCA/CFC | 18.4 | 18.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2003-04-01 | 334600 | -93314 | 241286 | 241286 | 100% | 0 | 0 | 0 | 43498 | -12131 | 31367 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Demonstration, training and policy development on alternatives to methyl bromide for banana soil fumigation | Individual | ASP | PHI | FUM | 26 | DEM | 57 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-07-01 | 2003-07-01 | 231000 | -214534 | 16466 | 16466 | 100% | 0 | 0 | 0 | 30030 | -27889 | 2141 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1998 | Investment
CLO | UNIDO | Preparation of investment project in the aerosol sector | Individual | ASP | PHI | ARS | 27 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | Sweden | Preparation of a government strategy to reduce and eliminate the use of CFC refrigerants for servicing and installations on-site | Individual | ASP | PHI | REF | 29 | PRP | 59 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2002-08-01 | 2002-11-01 | 141400 | 0 | 141400 | 141400 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Detailed discussions with the Philippine authority in charge, Department of Environment and Natural Resources (DENR), on the implementation took place May 2000. International and local consultants were contracted and in November 2000, the first meeting with the involved authorities and the private sector was conducted. The political situation in the Philippines during 2001 caused the project a delay. A RMP outline was adopted in October 2001. During 2002 the project was merged into a NCPP together with the WB. The NCPP was submitted jointly and approved in December 2002 with Sweden as co-implementing agency for TA activities related to the servicing sector. |  | 1999 | [11 empty] | 1999
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | ASP | PHI | FOA | 30 | PRP | 60 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 15000 | -3091 | 11909 | 11909 | 100% | 0 | 0 | 0 | 1950 | -401 | 1549 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | ASP | PHI | FUM | 30 | TAS | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -8880 | 16120 | 16120 | 100% | 0 | 0 | 0 | 3250 | -1154 | 2095.6 | 0.4 | 0 | Project financially completed. | $ 8,880 plus $ 1,154 PSC returned ExCom 43 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of PUF foam at RGC Foam Group (Polyfoam/Uratex) | Individual | ASP | PHI | FOA | 18 | INV | 62 | A | O | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1997-05-01 |  | 1997-06-01 | 2000-07-01 | 650000 | -3624 | 646376 | 646376 | 100% | 0 | 0 | 0 | 84500 | -471 | 84029 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | IBRD | Renewal of institutional strengthening |  | ASP | PHI | SEV | 28 | INS | 63 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-05-01 | 2002-05-01 | 139333 | 0 | 139333 | 139333 | 100% | 0 | 0 |  | 18113 | 0 | 18113 | 0 | 0 | Phase II completed and IS renewal approved at the 36th ExCom. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture or rigid polyurethane foam (sprayfoam) at Prescon Construction and Development | Individual | ASP | PHI | FOA | 31 | INV | 64 | N | O | I | CFC | 31.7 | 31.7 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-10-01 |  | 2002-09-01 | 2005-04-01 | 187926 | -25246 | 162680 | 162680 | 100% | 0 | 0 | 0 | 24430 | -3282 | 21148 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | IBRD | Preparation of a national CFC phaseout plan |  | ASP | PHI | PHA | 35 | PRP | 65 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2001-12-31 | 2002-12-01 |  | 2002-11-01 | 2002-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Completed. NCPP approved at the 38th ExCom. | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Training programme for customs officials and other key stakeholders | Individual | ASP | PHI | REF | 35 | TRA | 66 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2005-12-01 | 2006-11-01 | 170250 | -3588 | 166662 | 166662 | 100% | 0 | 0 | 0 | 22132.5 | -466 | 21666.06 | 0.44 | 0 | Project financially completed. | $ 3,588 plus $ 466 returned to ExCom 52 | [12 empty] | 2001 | Non Investment
FIN | IBRD | Renewal of institutional strengthening project (Phase III) |  | ASP | PHI | SEV | 36 | INS | 67 | N | O | I | CFC | 14.97 | 14.97 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2004-12-01 | 2005-01-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 23547.29 | 0 | 23547.29 | 0 | 0 | Phase III completed and IS renewal approved at the 42nd ExCom. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | Sweden | National CFC phase out plan: servicing sector (first tranche) | Multi-Year | ASP | PHI | PHA | 38 | TAS | 68 | A | O | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-02-03 | 2003-12-01 | 2010-03-31 |  |  | 152400 | 0 | 152400 | 152400 | 100% | 0 |  |  | 11316 | 0 | 11316 | 0 | 0 | On CFC recovery it was determined that the reclamation facility with the objective of reclaiming refrigerants for reuse is not technically and financially viable mainly because of the level and nature of refrigerant being recovered (lower levels and most critically mixed (contaminated)). The third party audit confirms this finding. Therefore, the project is considering a business model for an alternative to the original Reclamation Scheme. The idea would be to collect recovered refrigerant from the shops, transfer the recovered refrigerant using an industrial grade R&R machine into a storage tank and return the cylinders to the shops so that they can continue employing good practice and recovering refrigerant. Exploratory meetings with Treatment, Storage and Disposal Facilities will be conducted to discuss the alternative model in early 2009 if the Philippine Association of Refrigerant Importers, Inc. (PARII), the original partner in the reclamation scheme, decides not to participate in an alternative scheme. DENR and PARII are currently considering different options (as proposed during the WB mission in Nov 2008) on how to pursue with the reclamation scheme. To assist PARII to decide what option makes the most business sense, it was has been agreed that it would collect specific data, including projected operating costs (staff, collection costs, etc.) and the estimated levels of refrigerant that can be recovered. After that, DENR will add its data on the cost of analyzing the composition of recovered refrigerant and send it all to the World Bank. The Bank will then develop a business model to help PARII determine whether it would be financially viable and profitable to venture into this type of activity. To our understanding, PARII have not yet been able to make a decision to this end. Hence, the analysis and discussions on the viability of the reclamation facility has been very time consuming and has unfortunately led to further delays in the NCPP implementation. The new planned date for completion has therefore been revised to March 2010. |  | 2002 | [11 empty] | 2002 | [5 empty] | Yes
COM | IBRD | National CFC phase out plan: manufacturing sector (first tranche) | Multiyear | ASP | PHI | PHA | 38 | INV | 69 | N | O | I |  | 89.3 | 89.3 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 2858473 | 0 | 2858473 | 2302924.02 | 80.56% | 555548.98 | 555548.98 | 555183 | 248663 | 0 | 200334.93 | 48328.07 | 48328.07 | LBP facilitating finalization of PCRs for Primefoam, Qualifoam and Kooler Industries. Blutherm signed SGA with LBP in Jul 08 however a site visit showed that enterprise had still not secured ownership of its new site nor obtained necessary permits and initiated infrastructure work. Subproject will be cancelled in early 2009 if site ownership is not secured. For MAC inspection requirement, database of registered vehicles is in operation and being utilized nationwide. As of the end of 2008, about 90% vouchers (2,278) were paid. Remaining vouchers for payment to be made once suppliers comply with original qualification specs. Third party audit of voucher scheme started in Q4 2008 and to be completed in early 2009. Findings will be utilized along with WB review to propose final actions in NCPP implementation. DENR will also conduct monitoring of voucher grantees not yet monitored. Due to country-wide contamination of refrigerants, the reclamation scheme will be redesigned in 2009 to focus on collection and storage for eventual destruction. | [13 empty] | 2002 | INV | 1960 | 1422.4 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Preparation of a methyl bromide phase-out plan |  | ASP | PHI | FUM | 39 | PRP | 70 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | Meetings and workshops with Fertilizer and Pesticide Authority, a TWG and affected groups prior conducted. MBr consumption survey forwarded to Ozone Secretariat to support countrys request to lift potential non-compliance status. Proposed National MBr Strategy approved at the 45th ExCom. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan (manufacturing sector): 2004 annual programme | Multiyear | ASP | PHI | PHA | 41 | INV | 71 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 |  | 1877418 | 0 | 1877418 | 1626917.78 | 86.66% | 250500.22 | 250500.22 | 250500.22 | 160968 | 0 | 139490.35 | 21477.65 | 21477.65 | LBP facilitating finalization of PCRs for Primefoam, Qualifoam and Kooler Industries. Blutherm signed SGA with LBP in Jul 08 however a site visit showed that enterprise had still not secured ownership of its new site nor obtained necessary permits and initiated infrastructure work. Subproject will be cancelled in early 2009 if site ownership is not secured. For MAC inspection requirement, database of registered vehicles is in operation and being utilized nationwide. As of the end of 2008, about 90% vouchers (2,278) were paid. Remaining vouchers for payment to be made once suppliers comply with original qualification specs. Third party audit of voucher scheme started in Q4 2008 and to be completed in early 2009. Findings will be utilized along with WB review to propose final actions in NCPP implementation. DENR will also conduct monitoring of voucher grantees not yet monitored. Due to country-wide contamination of refrigerants, the reclamation scheme will be redesigned in 2009 to focus on collection and storage for eventual destruction. | [13 empty] | 2003 | INV | 1810 | 1389.8 | 0 | 0 | Yes | Yes | Yes
ONG | Sweden | National CFC phase-out plan servicing sector: 2004 annual programme | Multi-Year | ASP | PHI | PHA | 41 | TAS | 72 | A | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-07-01 | 2004-12-01 | 2010-03-31 |  |  | 166134 | 0 | 166134 | 77615 | 46.72% | 88519 | 88519 | 55000 | 12952 | 0 | 12952 | 0 | 0 | See remarks above. |  | 2003 | [8 empty] | 2006-12-01 |  | 2009-03-31 | 2003 | [5 empty] | Yes
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | PHI | SEV | 42 | INS | 73 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2005-05-01 | 90566 | 0 | 90566 | 90566 | 100% | 0 | 0 |  | 6792 | 0 | 6792 | 0 | 0 | First half of Phase IV of the IS project completed. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | PHI | PHA | 44 | INV | 75 | N | O | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 |  | 2160071 | 0 | 2160071 | 2159875.69 | 99.99% | 195.31 | 195.31 | 195.31 | 186006 | 0 | 185989.18 | 16.82 | 16.82 | LBP facilitating finalization of PCRs for Primefoam, Qualifoam and Kooler Industries. Blutherm signed SGA with LBP in Jul 08 however a site visit showed that enterprise had still not secured ownership of its new site nor obtained necessary permits and initiated infrastructure work. Subproject will be cancelled in early 2009 if site ownership is not secured. For MAC inspection requirement, database of registered vehicles is in operation and being utilized nationwide. As of the end of 2008, about 90% vouchers (2,278) were paid. Remaining vouchers for payment to be made once suppliers comply with original qualification specs. Third party audit of voucher scheme started in Q4 2008 and to be completed in early 2009. Findings will be utilized along with WB review to propose final actions in NCPP implementation. DENR will also conduct monitoring of voucher grantees not yet monitored. Due to country-wide contamination of refrigerants, the reclamation scheme will be redesigned in 2009 to focus on collection and storage for eventual destruction. | [13 empty] | 2004 | INV | 1509 | 1014.2 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Technical assistance for a national methyl bromide phase-out strategy | One off phaseout | ASP | PHI | FUM | 44 | TAS | 76 | N | O | I | MBR | 9 | 9 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-12-01 | 2009-06-01 |  |  | 330000 | 0 | 330000 | 247266.39 | 74.93% | 82733.61 | 82733.61 | 75000 | 24750 | 0 | 18544.97 | 6205.03 | 6205.03 | All PMU staff and consultants hired. Conditional registration for ECO2FUME, a potential MB substitute for stored commodity and QPS fumigation, granted by FPA. MB monitoring and control through the CAIP, Permit to Purchase and reporting system established. Admin. fines imposed to violators under the "No Permit No Sale" policy. Spot inspection of MB stakeholders in 5 regions conducted. Post-monitoring of flourmills sector accomplished. Assessed flourmill sector needs and feasibility of assistance to ease transition and build confidence in non-MB pest management. Database programmer for MB monitoring database hired, program to be made functional by 2009. Results of evaluation of bids for verification audit submitted. Meeting with MB importers on MB label review conducted. Mass distribution of informative materials on MB phaseout completed. | [13 empty] | 2004 | INV | 0 | 0 | 0 | 0
ONG | Sweden | National CFC phase-out plan servicing sector: 2005 annual programme | Multi-Year | ASP | PHI | PHA | 44 | TAS | 77 | A | O | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-12-07 | 2007-12-01 | 2009-12-01 |  |  | 40000 | 0 | 40000 | 34707 | 86.77% | 5293 | 5293 | 5293 | 2000 | 0 | 2000 | 0 | 0 | See remarks above. |  | 2004 | [11 empty] | 2004 | [5 empty] | Yes
FIN | IBRD | Extension of the institutional strengthening project (phase IV, second year) | Individual | ASP | PHI | SEV | 45 | INS | 78 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2006-05-01 | 90567 | 0 | 90567 | 90567 | 100% | 0 | 0 |  | 6793 | 0 | 6793 | 0 | 0 | Second half of Phase IV of the IS project completed. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | PHI | PHA | 47 | INV | 79 | N | O | I | CFC | 149 | 149 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 | 2010-03-01 |  |  | 2873197 | 0 | 2873197 | 925102.7 | 32.2% | 1948094.3 | 1948094.3 | 928088.24 | 248588 | 0 | 80039.56 | 168548.44 | 168548.44 | LBP facilitating finalization of PCRs for Primefoam, Qualifoam and Kooler Industries. Blutherm signed SGA with LBP in Jul 08 however a site visit showed that enterprise had still not secured ownership of its new site nor obtained necessary permits and initiated infrastructure work. Subproject will be cancelled in early 2009 if site ownership is not secured. For MAC inspection requirement, database of registered vehicles is in operation and being utilized nationwide. As of the end of 2008, about 90% vouchers (2,278) were paid. Remaining vouchers for payment to be made once suppliers comply with original qualification specs. Third party audit of voucher scheme started in Q4 2008 and to be completed in early 2009. Findings will be utilized along with WB review to propose final actions in NCPP implementation. DENR will also conduct monitoring of voucher grantees not yet monitored. Due to country-wide contamination of refrigerants, the reclamation scheme will be redesigned in 2009 to focus on collection and storage for eventual destruction. | [13 empty] | 2005 | INV | 1360 | 603.4 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | PHI | SEV | 48 | INS | 80 | N | T | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 | 2008-12-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 | 0 | 13585 | 0 | 13585 | 0 | 0 | Phase V completed and IS renewal approved at the 54th ExCom. | [13 empty] | 2006 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | PHI | PHA | 51 | INV | 81 | N | O | I | CFC | 907 | 907 | 0 | 0 | 2007-03-01 | 2007-12-01 | 2008-03-01 | 2010-03-01 |  |  | 337717 | 0 | 337717 | 97717 | 28.93% | 240000 | 240000 | 240000 | 20795 | 0 | 6016.94 | 14778.06 | 14778.06 | LBP facilitating finalization of PCRs for Primefoam, Qualifoam and Kooler Industries. Blutherm signed SGA with LBP in Jul 08 however a site visit showed that enterprise had still not secured ownership of its new site nor obtained necessary permits and initiated infrastructure work. Subproject will be cancelled in early 2009 if site ownership is not secured. For MAC inspection requirement, database of registered vehicles is in operation and being utilized nationwide. As of the end of 2008, about 90% vouchers (2,278) were paid. Remaining vouchers for payment to be made once suppliers comply with original qualification specs. Third party audit of voucher scheme started in Q4 2008 and to be completed in early 2009. Findings will be utilized along with WB review to propose final actions in NCPP implementation. DENR will also conduct monitoring of voucher grantees not yet monitored. Due to country-wide contamination of refrigerants, the reclamation scheme will be redesigned in 2009 to focus on collection and storage for eventual destruction. | [13 empty] | 2006 | INV | 453 | 171.3 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | PHI | PHA | 54 | INV | 82 | N | O | I | CFC | 53 | 53 | 0 | 0 | 2008-04-01 |  | 2009-03-31 | 2010-03-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 110000 | 50000 | 5500 | 0 | 0 | 5500 | 5500 | LBP facilitating finalization of PCRs for Primefoam, Qualifoam and Kooler Industries. Blutherm signed SGA with LBP in Jul 08 however a site visit showed that enterprise had still not secured ownership of its new site nor obtained necessary permits and initiated infrastructure work. Subproject will be cancelled in early 2009 if site ownership is not secured. For MAC inspection requirement, database of registered vehicles is in operation and being utilized nationwide. As of the end of 2008, about 90% vouchers (2,278) were paid. Remaining vouchers for payment to be made once suppliers comply with original qualification specs. Third party audit of voucher scheme started in Q4 2008 and to be completed in early 2009. Findings will be utilized along with WB review to propose final actions in NCPP implementation. DENR will also conduct monitoring of voucher grantees not yet monitored. Due to country-wide contamination of refrigerants, the reclamation scheme will be redesigned in 2009 to focus on collection and storage for eventual destruction. | [13 empty] | 2007 | INV | 400 | 0 | 0 | 0 |  | No | No
ONG | IBRD | Extension of institutional strengthening project (phase VI) | Individual | ASP | PHI | SEV | 54 | INS | 83 | N | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-31 | 2010-03-31 |  |  | 181133 | 0 | 181133 | 38257.69 | 21.12% | 142875.31 | 142875.31 | 105000 | 13585 | 0 | 2869.33 | 10715.67 | 10715.67 | Accomplishments in 2008 include continuation of the implementation of the ODS licensing system on import and trade; monitoring of CFC importers and traders of ODS including warehouse inspection, provision of assistance to the EMB and its Regional Offices in enforcement through spot inspections and issuance of Notices of Violation in cases involving sale of CFCs to manufacturing firms and non registration of ODS dealers; development of OPLAN CFC aimed at the confiscation of unregistered/illegally imported CFCs found in the market; coordination of consultation meetings for the Chiller Energy Efficiency Project; host seminar on ODS phase-out projects and promotion of alternatives for the private sector; host seminar-orientation on regulations on ODS; conduct of Ozone-Network meetings in 6 regions where Local Awareness Plans were prepared and discussed by O-Net members; continuation of information, education and communication (IEC) campaign targeting local government units, schools, and partner agencies; production and distribution of IEC materials; and spearheading ozone month celebration activities. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | PHI | PHA | 55 | PRP | 84 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 | 2010-09-01 |  |  | 195000 | 0 | 195000 | 0 | 0% | 195000 | 195000 | 100000 | 14625 | 0 | 0 | 14625 | 14625 | Project preparation activities will start in the first quarter of 2009. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | PNG | SEV | 13 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-02-14 | 1995-10-01 |  | 1996-05-01 | 1999-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
COM | UNEP | Creation of an Ozone Unit | Individual | ASP | PNG | SEV | 19 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1999-05-01 |  | 2003-12-01 |  | 45800 | 0 | 45800 | 21085 | 46.04% | 24715 | 0 | 24715 | 5954 | 0 | 2741.05 | 3212.95 | 0 | Project completed |  |  |  | 1999-05-01 | [9 empty] | 1996 | Non Investment
TRF | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | PNG | REF | 21 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-09-01 |  |  | 1998-07-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Project transferred | $ 30,000 plus $ 3,900 PSC returned ExCom 25 |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
FIN | Germany | Project preparation for the development of an ODS phase out action plan | Individual | ASP | PNG | PHA | 36 | PRP | 4 | A | O | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | TPMP for PNG has been approved at the 39th ExCom | [13 empty] | 1998
FIN | Germany | Terminal phase-out management plan for ODS (1st tranche) | Multi-Year | ASP | PNG | PHA | 39 | INV | 5 | A | O | I | CFC | 18 | 30.8 | 0 |  | 2003-04-01 | 2003-08-01 | 2005-12-01 |  | 2006-07-01 | 2006-12-01 | 480000 | 0 | 480000 | 480000 | 100% | 0 | 0 | 0 | 59700 | 0 | 59700 | 0 | 0 | PNG has successfully completed the 1st Action Plan of the TPMP and the country's consumption is well below the TPMP reduction targets. | [13 empty] | 2002 |  | 17 | 15.37 |  |  | Yes
FIN | Germany | Extension of institutional strengthening project | Individual | ASP | PNG | SEV | 41 | INS | 6 | N | O | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-06-01 | 2005-12-01 |  | 2006-03-01 | 2006-06-01 | 39693 | 0 | 39693 | 39693 | 100% | 0 | 0 | 0 | 5160 | 0 | 5160 | 0 | 0 | ISP completed successfully. | [13 empty] | 2002
FIN | Germany | Extension of the institutional strengthening project (phase III) | Individual | ASP | PNG | SEV | 48 | INS | 7 | A | O | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-05-01 | 2008-04-01 |  | 2008-04-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | ISP completed successfully.
ONG | Germany | Terminal phase-out management plan for ODS (2nd tranche) | Multi-Year | ASP | PNG | PHA | 48 | INV | 8 | A | O | I | CFC | 17 | 4.5 | 0 |  | 2006-04-01 | 2006-08-01 | 2008-12-01 | 2009-10-01 |  |  | 220000 | 0 | 220000 | 185455 | 84.3% | 34545 | 0 | 34545 | 27300 | 0 | 23013.2795 | 4286.7205 | 0 | PNG has been in compliance with its reductions targets but this has required some extensive customs trainings in 2008 including follow ups with improters. Additionally the incentive scheme is being implemented. Project should be completed in 2009. | [15 empty] | 0 | 0 |  |  | Yes
ONG | Germany | Extension of the institutional strengthening project (phase IV) | Individual | ASP | PNG | SEV | 54 | INS | 9 | A | O | I |  | 0 |  | 0 |  | 2008-04-01 | 2008-07-01 | 2010-03-01 | 2010-03-01 |  |  | 60000 | 0 | 60000 | 12100 | 20.17% | 47900 | 0 | 27800 | 7800 | 0 | 1573 | 6227 | 0 | NOU continues ot function, some offcie equipment was required and purchased under the ISP. Additional data reporting and awareness activities on ozone issues continue.
FIN | UNEP | Country programme preparation | Individual | AFR | PRC | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  | 1995-07-01 | 1996-07-01 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | PRC | SEV | 17 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 2000-12-01 | 2001-12-12 | 62920 | 0 | 62920 | 62920 | 100% | 0 | 0 | 0 | 8179.6 | 0 | 8179.6 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Non Investment
FIN | UNDP | Project preparation assistance in recovery and recycling of refrigerant, foam and halon sectors | Individual | AFR | PRC | SEV | 18 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | PRC | REF | 20 | TAS | 4 | A | O | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 1998-10-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 201200 | -13880 | 187320 | 187320 | 100% | 0 | 0 | 0 | 26156 | -1804 | 24352 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  | 1998-10-01 | [10 empty] | 1996 | Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | PRC | REF | 27 | PRP | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-12 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | PRC | SEV | 32 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 41950 | 0 | 41950 | 41950 | 100% | 0 | 0 | 0 | 5453.5 | 0 | 5453.5 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Assistance for information-sharing | Individual | AFR | PRC | REF | 32 | TAS | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-01-02 |  | 2003-12-01 | 2005-02-01 | 16000 | -2967 | 13033 | 13032.55 | 100% | 0.45 | 0 | 0.45 | 2080 | -385.71 | 1694.2315 | 0.0585 | 0 | Project financially completed. | $ 2,967 plus 386 returned ExCom 46 | [12 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation in the refrigeration sector | Individual | AFR | PRC | REF | 34 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-09-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNEP | Implementation of the RMP: Customs training programme | Individual | AFR | PRC | REF | 32 | TRA | 9 | A | O | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-12-01 |  | 2003-12-01 | 2005-01-01 | 69400 | -25378 | 44022 | 44021.75 | 100% | 0.25 | 0 | 0.25 | 9022 | -3299.14 | 5722.8275 | 0.0325 | 0 | Project financially completed. | $ 25,378 plus $ 3,299 returned ExCom 46 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | PRC | SEV | 39 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2005-12-01 | 54531 | 0 | 54531 | 54531 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | PRC | REF | 41 | TAS | 11 | N | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 2003-12-01 | 2006-07-01 | 2006-12-01 |  | 2008-12-01 |  | 118078 | 0 | 118078 | 54142 | 45.85% | 63936 | 1433 | 51148.8 | 10627 | 0 | 4872.7708 | 5754.2292 | 128.9698 | Completed in 2008. Amount of refrigerant that can be recycled exceeded capacity of existing centers, and NOU therefore requested additional R&R equipment. Remaining funds used for national consultant, local travel and replacement of R&R equipment. For some reason the expenditures related to equipment did not make it into the 2008 accounts and will be reflected in 2009. | [13 empty] | 2003 | Investment
COM | UNEP | Extensionl of the institutional strengthening project (phase IV) | Individual | AFR | PRC | SEV | 45 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-04-01 |  | 60000 | 0 | 60000 | 36060.97 | 60.1% | 23939.03 | 0 | 23939.03 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2005 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | PRC | PHA | 48 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2007-12-01 |  | 12000 | 0 | 12000 | 167 | 1.392% | 11833 | 0 | 11833 | 900 | 0 | 12.525 | 887.475 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | PRC | PHA | 48 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-11-01 |  | 18000 | 0 | 18000 | 17991 | 99.95% | 9 | 0 | 9 | 2340 | 0 | 2338.83 | 1.17 | 0 | Project completed in November 2008 after submission of TPMP document | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | PRC | SEV | 51 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-07-01 | 2009-03-01 | 2009-03-01 |  |  | 60000 | 0 | 60000 | 33056.81 | 55.09% | 26943.19 | 26943 | 26943.19 | 0 | 0 | 0 | 0 | 0 | NOU Congo organised training sessions and awareness raising campaigns in Brazzaville and Pointe Noire including celebration of International ozone day through the local media. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | TAS | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-31 | 2010-03-31 |  |  | 68000 | 0 | 68000 | 45024.13 | 66.21% | 22975.87 | 19000 | 22975.87 | 8840 | 0 | 5853.1369 | 2986.8631 | 2470 | Signature of the MoU for the implementation of the TPMP in October 2008 | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | INV | 17 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-07-01 | 2010-03-31 | 2010-03-01 |  |  | 50000 | 0 | 50000 | 1856 | 3.712% | 48144 | 0 | 30000 | 4500 | 0 | 167 | 4333 | 0 | Technical specification for equipment purchase was prepared and upon clearance of the NOU procurement process will start. | [13 empty] | 2008 | INV | 3.4 | 3.4 |  |  | Not yet confirmed | N/A | N/A
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | PRC | PHA | 55 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU send to Country for signing | [13 empty] | 2008
FIN | UNIDO | Preparation of the Country Programme | Individual | ASP | QAT | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
COM | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | QAT | REF | 34 | TAS | 2 | A | O | I | CFC | 3.7 | 3.7 |  |  | 2001-07-01 | 2006-03-01 | 2004-08-01 |  | 2007-12-01 |  | 20000 | 0 | 20000 | 16608 | 83.04% | 3392 | 622 | 600 | 2600 | 0 | 2159 | 441 | 81 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Institutional Strengthening Project: Creation of the National Ozone Unit | Individual | ASP | QAT | SEV | 27 | INS | 2 | N | T | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-11-01 | 2002-04-01 |  | 2004-10-01 | 2005-12-01 | 68450 | -4279 | 64171 | 64171 | 100% | 0 | 0 |  | 8899 | -570 | 8329 | 0 | 0 | FIN | [5 empty] | 2002-04-01
FIN | UNIDO | Implementation of RMP: National recovery and recycling project | RMP Update | ASP | QAT | REF | 34 | TAS | 3 | A | O | I | CFC | 54.1 | 54.1 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2006-12-01 | 2007-12-01 | 295000 | -35 | 294965 | 294965 | 100% | 0 | 0 |  | 38350 | -5 | 38345 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2001 | INV
FIN | UNIDO | Implementation of the RMP: Training of customs and Ozone Unit in monitoring and control of ODS | RMP Update | ASP | QAT | REF | 34 | TRA | 4 | A | O | I | CFC | 9.2 | 9.2 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 50000 | -2501 | 47499 | 47499 | 100% | 0 | 0 |  | 6500 | -335 | 6165 | 0 | 0 | FIN | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Implementation of RMP: Training of trainers and technicians training in good refrigerant management practices | RMP Update | ASP | QAT | REF | 34 | TRA | 5 | A | O | I | CFC | 19.3 | 19.3 |  |  | 2001-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-12-01 | 2006-03-01 | 105000 | -5978 | 99022 | 99022 | 100% | 0 | 0 |  | 13650 | -798 | 12852 | 0 | 0 | FIN | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase 2 | Individual | ASP | QAT | SEV | 41 | INS | 6 | N | T | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2006-09-01 | 2008-05-01 | 44500 | -1215 | 43285 | 43285 | 100% | 0 | 0 |  | 3338 | -92 | 3246 | 0 | 0 | Financial completion in May 2008. Refund was reported to 54th ExCom, Apr 2008. FIN. Refund was reported to 55th ExCom, Jul 2008. FIN. | [13 empty] | 2003 | NON-INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | QAT | PHA | 46 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-10-01 | 2006-07-01 |  | 2007-12-01 | 2007-12-01 | 30000 | -97 | 29903 | 29903 | 100% | 0 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project (phase II, second year funding) | Individual | ASP | QAT | SEV | 49 | INS | 8 | N | T | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-01-01 | 2007-07-01 | 2009-06-01 |  |  | 44500 | 0 | 44500 | 1247 | 2.802% | 43253 | 37909 | 20000 | 3338 | 0 | 94 | 3244 | 2843 | The delay is due to the long signature process in the country and delays in reporting under UNIDO's ongoing contract. National expert for the PMU was selected in April 2008 and his contract was issued. However, its has not yet been returned to UNIDO countersigned. Progress reports as welll as country programme progress reports were requested to the NOU for the years 2006 - 2007. | [13 empty] | 2006 | NON-INV
ONG | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | INV | 9 | A | O | I | CFC | 3 | 0 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 | 2009-07-01 |  |  | 242500 | 0 | 242500 | 33262 | 13.72% | 209238 | 72586 | 70000 | 18188 | 0 | 2495 | 15693 | 5444 | Equipment for investment and non-investment activities were procured by UNIDO. Material for training on the retrofitting of MACs and domestic refrigeration was prepared. Training will take place in the first quarter of 2009. | [13 empty] | 2007 | INV | 12 | 12 |  |  | Not yet confirmed | N/A | N/A
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-03-01 | 2009-03-01 |  |  | 65000 | 0 | 65000 | 0 | 0% | 65000 | 0 | 65000 | 8450 | 0 | 0 | 8450 | 0 | [14 empty] | 2007 | Non Investment
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | QAT | PHA | 55 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 10000 | 4125 | 0 | 0 | 4125 | 0 | The identification of national experts/consutancy firms to carry out the survey is in process. The first stakeholder consultation workshop will take place in March 2009. | Legislation related matters are part of the responsibility of UNEP. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | QAT | PHA | 55 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | Work-plan agreed with country and UNIDO, contractual arrangements and survey started in 2009 | [13 empty] | 2008
FIN | UNIDO | Preparation of Country Programme | Individual | EUR | ROM | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1995-07-01 | 1998-08-01 | 80000 | -23457 | 56543 | 56543 | 100% | 0 | 0 |  | 10400 | -3061 | 7339 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 at refrigerator plant at mechanical enterprises SADU and ARCTIC | Individual | EUR | ROM | REF | 15 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-04-01 | 1995-06-01 |  | 1996-07-01 | 1998-08-01 | 50000 | -4907 | 45093 | 45093 | 100% | 0 | 0 |  | 6500 | -647 | 5853 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS at Spumotim flexible foam plant | Individual | EUR | ROM | FOA | 16 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1996-05-01 | 15000 | 132 | 15132 | 15132 | 100% | 0 | 0 |  | 1950 | 17 | 1967 | 0 | 0 | FIN
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | ROM | SEV | 17 | INS | 4 | N | T | I |  | 0 | 0 |  |  | 1995-07-01 | 1997-12-01 | 1998-07-01 |  | 2003-12-01 | 2005-01-01 | 168443 | -80350 | 88093 | 88093 | 100% | 0 | 0 |  | 21898 | -10464 | 11434 | 0 | 0 | FIN |  |  | 1999-03-01 | 2000-01-01
FIN | UNIDO | Phasing out of CFCs at FARMEC SA | Individual | EUR | ROM | ARS | 18 | INV | 5 | A | O | I | CFC | 730 | 730 |  |  | 1995-11-01 | 1996-09-01 | 1997-11-01 |  | 1998-12-01 | 2001-07-01 | 895880 | -29399 | 866481 | 866481 | 100% | 0 | 0 |  | 116464 | -4000 | 112464 | 0 | 0 | FIN
FIN | UNIDO | Phase out ODS at the domestic refrigeration factory Arctic S.A. | Individual | EUR | ROM | REF | 18 | INV | 6 | A | O | R | CFC | 206 | 206.7 |  |  | 1995-11-01 | 1996-10-01 | 1997-05-01 |  | 1997-05-01 | 2000-07-01 | 1095300 | -48009 | 1047291 | 1047291 | 100% | 0 | 0 |  | 142389 | -6457 | 135932 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the domestic and commercial refrigeration sector | Individual | EUR | ROM | REF | 18 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-05-01 |  | 1999-03-01 | 2000-07-01 | 20000 | -808 | 19192 | 19192 | 100% | 0 | 0 |  | 2600 | -109 | 2491 | 0 | 0 | FIN |  |  |  | 1999-03-01
CLO | UNIDO | Conversion of commercial refrigeration equipment to phase out CFC-12, HCFC-502 and CFC-11 at Technofrig S.A. | Individual | EUR | ROM | REF | 19 | INV | 8 | A | O | I | CFC | 6.92 | 6.92 |  |  | 1996-05-01 | 1997-03-01 | 1999-06-01 |  |  | 2000-07-01 | 297768 | -255677 | 42091 | 42091 | 100% | 0 | 0 |  | 38710 | -33247 | 5463 | 0 | 0 | CLO |  |  | 1999-07-01
FIN | UNIDO | Phasing out of CFC-11 at S.C. Spumotim S.A. | Individual | EUR | ROM | FOA | 20 | INV | 9 | A | O | I | CFC | 30 | 30 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1997-12-01 | 2000-07-01 | 142293 | -83 | 142210 | 142210 | 100% | 0 | 0 |  | 18498 | -40 | 18458 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 and CFC-12 in the production of domestic refrigerators and replacing them by cyclopentane and HFC-134a at Ratmil, Uzine Mecanica Sadu | Individual | EUR | ROM | REF | 20 | INV | 10 | A | O | I | CFC | 73.3 | 73.3 |  |  | 1996-10-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2002-05-01 | 937859 | 0 | 937859 | 937859 | 100% | 0 | 0 |  | 121922 | 0 | 121922 | 0 | 0 | FIN
FIN | Austria | Establishment of a training centre for commercial refrigeration service technicians at Comservice S.A. |  | EUR | ROM | REF | 20 | TRA | 11 | A | O | I |  | 10 |  |  |  | 1996-10-01 |  | 1997-10-01 |  | 1999-02-01 | 1999-05-01 | 116628 | 0 | 116628 | 116628 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 1996
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | EUR | ROM | FUM | 23 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-03-01 | 2001-07-01 | 10000 | -780 | 9220 | 9220 | 100% | 0 | 0 |  | 1300 | -103 | 1197 | 0 | 0 | FIN |  |  |  | 1999-09-01
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | EUR | ROM | FOA | 23 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-05-01 | 2001-07-01 | 10000 | 1667 | 11667 | 11667 | 100% | 0 | 0 |  | 1300 | 214 | 1514 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | ROM | REF | 24 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 30000 | -1043 | 28957 | 28957 | 100% | 0 | 0 |  | 3900 | -142 | 3758 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC 11 and CFC-12 in the manufacture of extruded polyethylene and polystyrene foams through the use of butane as a blowing agent at Romcarbon, S.A. | Individual | EUR | ROM | FOA | 27 | INV | 15 | A | O | I | CFC | 132.4 | 132.4 |  |  | 1999-03-01 | 2000-04-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 516512 | 0 | 516512 | 516512 | 100% | 0 | 0 |  | 66816 | -11 | 66805 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | ROM | REF | 28 | TAS | 16 | A | O | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 373840 | 0 | 373840 | 373840 | 100% | 0 | 0 |  | 48599 | -69 | 48530 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | EUR | ROM | REF | 28 | TRA | 17 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-10-01 |  | 2002-08-01 | 2003-10-01 | 23100 | -1349 | 21751 | 21751 | 100% | 0 | 0 |  | 3003 | -180 | 2823 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | ROM | FUM | 30 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 10000 | -322 | 9678 | 9678 | 100% | 0 | 0 |  | 1300 | -44 | 1256 | 0 | 0 | FIN
COM | Italy | Phase out of methyl bromide in horticulture | Individual | EUR | ROM | FUM | 34 | INV | 19 | A | O | I | MBR | 93.9 | 93.9 | 0 |  | 2001-07-01 | 2002-02-26 | 2005-08-01 |  | 2006-12-01 |  | 630517 | 0 | 630517 | 628240 | 99.64% | 2277 |  |  | 79357 | 0 | 79030 | 327 | 0 | Financial completion in Aug 2007. Return of funds recorded at the 57th ExCom Mtg. The subject project was approved at the level of US$ 630,517 + US$ 79,357 agency support costs. Thus, the total approved funding was US$ 709,874. However, the Government of Italy transferred to UNIDO US$ 711,372.79, which is US$ 1,498.79 higher than the originally approved amount. That is the reason why it seems that there is a negative balance. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 | [11 empty] | 2001 | Investment
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | ROM | REF | 28 | TRA | 19 | A | O | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2001-01-01 | 2001-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Country programme update | Individual | EUR | ROM | SEV | 36 | CPG | 20 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-01-01 | 2004-04-01 | 60000 | -356 | 59644 | 59644 | 100% | 0 | 0 |  | 7800 | -59 | 7741 | 0 | 0 | FIN | [13 empty] | 2002 | NON-INV
FIN | UNIDO | Preparation of investment projects in the solvent sector | Individual | EUR | ROM | SOL | 39 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-10-01 | 2005-05-01 | 15000 | -785 | 14215 | 14215 | 100% | 0 | 0 |  | 1125 | -61 | 1064 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Terminal umbrella project for the phase-out of ODS solvents | Individual | EUR | ROM | SOL | 41 | INV | 22 | A | O | I | CTC | 11.1 | 11.1 |  |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-12-01 | 2007-05-01 | 220615 | -6247 | 214368 | 214368 | 100% | 0 | 0 |  | 19855 | -562 | 19293 | 0 | 0 | FIN | [13 empty] | 2003 | INV
FIN | UNIDO | Project preparation: CFC phase-out plan (aerosol and refrigeration) | Individual | EUR | ROM | PHA | 42 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2006-10-01 |  | 2005-08-01 | 2005-08-01 | 10000 | -1012 | 8988 | 8988 | 100% | 0 | 0 |  | 750 | -77 | 673 | 0 | 0 | FIN | [13 empty] | 2004 | NON-INV
FIN | Sweden | Assistance to prepare the national CFC phase-out plan (refrigeration servicing sector) | Individual | EUR | ROM | PHA | 43 | PRP | 24 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-04-01 | 2005-07-01 | 59400 | 0 | 59400 | 59400 | 100% | 0 |  |  | 7722 | 0 | 7722 | 0 | 0 | In July 2004, at the 43rd Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a national CFC phase-out plan for the servicing sector in Romania. After recruitment of consultants a mission was held in November 2004. The NCPP was prepared during the autumn 2004 and was approved at the 45th ExCom meeting in April 2005. |  | 2004 | [11 empty] | 2004
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of pharmaceutical aerosols by conversion to HFC-134a propellant at MEBRA, Brasov (terminal aerosol sector project) | Individual | EUR | ROM | ARS | 44 | INV | 26 | A | O | I | CFC | 46.5 | 46.5 |  |  | 2004-12-01 | 2005-07-01 | 2007-02-01 |  | 2006-06-01 | 2007-09-01 | 204776 | -640 | 204136 | 204136 | 100% | 0 | 0 |  | 18430 | -58 | 18372 | 0 | 0 | FIN | [13 empty] | 2004 | INV
FIN | UNIDO | Preparation of a terminal umbrella project to phase out CTC | Individual | EUR | ROM | SOL | 44 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 20000 | -900 | 19100 | 19100 | 100% | 0 | 0 |  | 1500 | -67 | 1433 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2004
FIN | UNIDO | Preparation of a closure project in the production of CFC/CTC/MBR | Individual | EUR | ROM | PRO | 45 | PRP | 28 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-12-01 | 25000 | -3848 | 21152 | 21152 | 100% | 0 | 0 |  | 1875 | -289 | 1586 | 0 | 0 | FIN | [13 empty] | 2005 | NON-INV
COM | UNIDO | Extension of institutional strengthening project: phase II | Individual | EUR | ROM | SEV | 45 | INS | 29 | N | T | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2007-04-01 |  | 2007-12-01 |  | 145984 | 0 | 145984 | 137873 | 94.44% | 8111 | 4169 | 8000 | 10949 | 0 | 10340 | 609 | 313 | The project is expected to be financially completed in 2009. | [13 empty] | 2005 | NON-INV
COM | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | INV | 30 | A | O | I | CFC | 14.6 | 40 |  |  | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-03-01 |  | 159050 | 0 | 159050 | 125772 | 79.08% | 33278 | 15223 | 10000 | 11929 | 0 | 9433 | 2496 | 1142 | During 2008 considerable progress was made and 82 % of the funds have already been committed. In June 2008 a new local consultant was hired by UNIDO to serve as PMU. She participated in the joint UNIDO/SEI mission to Bucharest at the end of June 2008. | [13 empty] | 2005 | INV | 220 | 180.2 |  |  | Yes | Yes | Yes
ONG | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-11-01 | 2007-04-01 | 2009-12-31 |  |  | 119500 | 0 | 119500 | 27908 | 23.35% | 91592 | 91592 | 60000 | 15535 | 0 | 3000 | 12535 | 12535 | Since mid 2008 there has been one person working at the PMU which has meant that substantial progress has been under the project. The planned date of completion is still December 2009 which might be a challange as the project is still suffering from a long delay. Training of trainers at the vocational schools was held in Sep 2008; a draft law has been prepared and is expected to be approved in June; the Working Group has discussed the draft decision on licensing/certification system and this will now be sent for approval: the first version of the National Code of Practice was launched in March 2009; preparations are ongoing for the work to establish a reclamation scheme; preparations are also ongoing for the training of the workforce. UNIDO, SEI and the IC had a mission to Bucharest in March 2009 during which the time plan for the project was updated. |  | 2005 | [8 empty] | 2008-12-31 |  |  | 2005 | [5 empty] | Yes
COM | UNIDO | Sector plan for production sector | Multi-Year | EUR | ROM | PRO | 47 | INV | 32 | A | O | I | MBR | 0 | 0 | 5 | 5 | 2005-11-01 | 2006-04-01 | 2006-07-01 |  | 2006-12-01 |  | 3200000 | 0 | 3200000 | 3108719 | 97.15% | 91281 | 0 | 50000 | 240000 | 0 | 233154 | 6846 | 0 | Financial completion may be delayed by few months. Any unspent balance will be returned to the MLF. | [13 empty] | 2005 | INV |  |  | 175 | 30.9 | Yes | Yes | Yes
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | ROM | HAL | 48 | PRP | 33 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-04-01 | 15000 | -571 | 14429 | 14429 | 100% | 0 | 0 |  | 1125 | -43 | 1082 | 0 | 0 | FIN | [13 empty] | 2006 | NON-INV
ONG | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | ROM | PHA | 48 | INV | 34 | A | O | I | CFC | 35.8 | 10.4 |  |  | 2006-04-01 | 2006-11-01 | 2007-04-01 | 2009-12-01 |  |  | 236750 | 0 | 236750 | 21348 | 9.017% | 215402 | 0 | 40000 | 17756 | 0 | 1601 | 16155 | 0 | In June 2008 a joint mission with Sweden was undertaken. Update of the vocational schools was initiated, while in July and August 2008 the PMU carried out a survey of schools educating students in refrigeration and air-conditions. The training of teachers took place in September 2008 and two teachers from each of the seven schools identified in the survey participated in the training. | [13 empty] | 2006 | INV | 146.8 | 85.25 |  |  | Yes | Yes | Yes
COM | UNIDO | Sector plan for production sector (second tranche) | Multi-Year | EUR | ROM | PRO | 50 | INV | 35 | A | O | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2007-06-01 |  | 900000 | 0 | 900000 | 668593 | 74.29% | 231407 | 100000 | 130000 | 67500 | 0 | 50144 | 17356 | 7500 | Financial completion may be delayed by few months. Any unspent balance will be returned to the MLF. | [13 empty] | 2006 | INV |  |  | 170 | 13 | Yes | Yes | Yes
ONG | UNIDO | Terminal phase-out management plan of CTC production/consumption for process agent uses | Individual | EUR | ROM | PAG | 50 | INV | 36 | A | O | I | CTC | 120.5 | 50 |  |  | 2006-11-01 | 2007-06-01 | 2007-11-01 | 2009-12-01 |  |  | 1389800 | 0 | 1389800 | 64737 | 4.658% | 1325063 | 736265 | 730000 | 104235 | 0 | 4855 | 99380 | 55220 | The process design was already made by UNIDO. The project equipment has been procured. Three bidding have been conducted by UNIDO to identify a local consultancy company to make a plant design documentation needed for plant registration by Romanian authorities concerned. However, for the time being UNIDO has not found such a company. It was agreed with Romanian authorities to change the TOR-scope of the work to include all the remaining activities: Plant design, equipment installation, piping, etc. and carry out a new bidding. UNIDO mission to Romania has taken place in October 2008 to re-write the TOR for new bidding. A partial phase out of 50 ODP tonnes achieved. The project is planned to be completed in Dec 2009. | [13 empty] | 2006 | INV
COM | UNIDO | Halon management programme | Individual | EUR | ROM | HAL | 50 | TAS | 37 | A | O | I | HAL | 3.5 | 3.5 |  |  | 2006-11-01 | 2007-11-01 | 2008-11-01 |  | 2008-06-01 |  | 32500 | 0 | 32500 | 32053 | 98.62% | 447 | 0 | 1 | 2925 | 0 | 2885 | 40 | 0 | Project completed in Jun 2008. | [13 empty] | 2006 | INV
ONG | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | ROM | PHA | 51 | INV | 38 | A | O | I | CFC | 14.9 | 14.9 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 2953 | 9.843% | 27047 | 0 | 10000 | 2250 | 0 | 221 | 2029 | 0 | In June 2008 a joint mission with Sweden was undertaken. Update of the vocational schools was initiated, while in July and August 2008 the PMU carried out a survey of schools educating students in refrigeration and air-conditions. The training of teachers took place in September 2008 and two teachers from each of the seven schools identified in the survey participated in the training. | [13 empty] | 2007 | INV | 33.2 | 0 |  |  | Yes | Yes | Yes
FIN | UNIDO | Sector plan for production sector (third tranche) | Multi-Year | EUR | ROM | PRO | 52 | INV | 39 | A | O | I | CTC | 0 | 0 | 170 | 170 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2007-12-01 | 2008-07-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 75000 | 0 | 75000 | 0 | 0 | Financial completion in Jul 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2007 | INV |  |  | 170 | 0 | Yes | Yes | Yes
ONG | UNIDO | Sector plan for production sector (fourth tranche) | Multi-Year | EUR | ROM | PRO | 53 | INV | 40 | A | O | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 | 2009-12-01 |  |  | 1200000 | 0 | 1200000 | 1100000 | 91.67% | 100000 | 0 | 20000 | 90000 | 0 | 82500 | 7500 | 0 | The fourth tranche of the sector plan for production sector was approved in view of the progress already achieved in establishing the CTC incinerator in Chimcomplex and the completion of the removal of the capability to produce CTC at Oltchim. Since the CTC production has already been closed, UNIDO is continuing with the monitoring activities and annual verification audits. | [13 empty] | 2007 | INV |  |  | 0 | 0 | Yes | No | No
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | RWA | SEV | 35 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2007-03-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 6500 | -4550 | 1950 | 0 | 0 | Project financially completed. | $ 35,000 plus $ 4,550 returned ExCom 46 | [12 empty] | 2001 | Non Investment
FIN | UNDP | Formulation of a refrigerant management plan | Individual | AFR | RWA | REF | 36 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2003-04-01 |  | 2005-01-01 | 2007-03-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | RWA | REF | 39 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2003 | Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 41 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2007-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 64600 | 0 | 64600 | 64599.99 | 100% | 0.01 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | AFR | RWA | REF | 41 | TRA | 6 | A | O | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 |  | 50000 | 0 | 50000 | 14495.81 | 28.99% | 35504.19 | 14461 | 35504.19 | 6500 | 0 | 1884.4553 | 4615.5447 | 1879.93 | Project completed | [13 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | RWA | REF | 41 | TRA | 7 | A | O | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 |  | 50000 | 0 | 50000 | 9732 | 19.46% | 40268 | 11482 | 40268 | 6500 | 0 | 1265.16 | 5234.84 | 1492.66 | Project completed | [13 empty] | 2003 | Non Investment
COM | UNDP | Implementation of the RMP: refrigeration manufacturing and centralized recovery and recycling of refrigerants | RMP-Component | AFR | RWA | REF | 41 | TAS | 8 | N | O | I | CFC | 12.9 | 12.9 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-12-01 |  | 118758 | 0 | 118758 | 101116 | 85.14% | 17642 | 0 | 14113.6 | 10688 | 0 | 9100.2527 | 1587.7473 | 0 | Completed in 2008. The R&R scheme is in place. Last R&R workshop to transfer rights to private sector was planned by the Government in Q1-2009. The project is operationally completed. | [13 empty] | 2003 | Investment
COM | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | RWA | REF | 41 | TAS | 9 | A | O | I | CFC | 2.2 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 |  | 2008-12-01 |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 2600 | 0 | 0 | 2600 | 0 | Project completed in December 2008 | [13 empty] | 2003 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | RWA | PHA | 48 | PRP | 10 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 |  | 12000 | 0 | 12000 | 8194 | 68.28% | 3806 | 0 | 3806 | 900 | 0 | 614.55 | 285.45 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | RWA | PHA | 48 | PRP | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2007-04-01 |  | 2008-11-01 |  | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | Project completed in November 2008 after submission of TPMP document | [13 empty] | 2006 | Non Investment
COM | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | RWA | SEV | 50 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2008-12-01 |  | 60000 | 0 | 60000 | 20087.69 | 33.48% | 39912.31 | 27000 | 39912.31 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. New IS phase approved | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | RWA | PHA | 53 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 110000 | 0 | 110000 | 79999.69 | 72.73% | 30000.31 | 30000 | 30000.31 | 14300 | 0 | 10399.9597 | 3900.0403 | 3900 | First tranche successfully completed. Country conducted trainings for customs officers, refrigeration technicians, reviewed ODS Regulations, curricula for customs training school and technicians scholl.Second tranche approved during 57th Ex-com | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | RWA | PHA | 53 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-11-01 | 2009-11-01 | 2010-01-01 |  |  | 124500 | 0 | 124500 | 2814 | 2.26% | 121686 | 0 | 24337.2 | 11205 | 0 | 253.26 | 10951.74 | 0 | Project ongoing. International expert recruited with a mission fielded in November 2008. Action plan developed. Equipment specifications developed. Equipment is expected in Q2-2009 through air freight due small size of lots (retrofit tools). NOU/UNDP prepared documentation for end-user programme and four companies attracted to participate. During the mission in November, international expert visited four companies to verify baseline technology data to aid NOU in finalizing grant documentation. More applications expected in Q1/2-2009 | [13 empty] | 2007 | Investment | 4.6 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | RWA | PHA | 55 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU signed with the country awaiting first payment. Country identified national experts for the survey, finalised HCFC survey questionnaire and TORs for the survey and drafting of HPMP | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | ASP | SAM | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-18 | 1995-06-01 |  | 1997-05-01 | 1999-02-01 | 35000 | -4850 | 30150 | 30150 | 100% | 0 | 0 | 0 | 4550 | -630.5 | 3919.5 | 0 | 0 | Project financially completed. | $ 4,850 plus $ 631 PSC returned ExCom 30 | [12 empty] | 1997 | Non Investment
FIN | UNEP | Establishment of the National Ozone Committee | Individual | ASP | SAM | SEV | 22 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-04-01 | 2000-06-01 |  | 2003-04-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the RMP: Training of customs officials and NOU staff | Individual | ASP | SAM | REF | 32 | TRA | 3 | A | O | I | CFC | 2 | 2 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-06-03 |  | 2003-09-01 | 2003-12-01 | 53500 | -9474 | 44026 | 44026 | 100% | 0 | 0 | 0 | 6955 | -1232 | 5723.38 | -0.38 | 0 | Project financially completed. | $ 9,474 plus $ 1,232 PSC returned ExCom 43 |  |  |  |  | 2003-06-03 | [7 empty] | 2000 | Non Investment
FIN | UNEP | Implementation of the RMP: Training of refrigeration service technicians | Individual | ASP | SAM | REF | 32 | TRA | 4 | A | O | I | CFC | 1.8 | 1.8 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-02-02 |  | 2002-10-01 | 2003-10-01 | 48800 | -5864 | 42936 | 42936 | 100% | 0 | 0 | 0 | 6344 | -762.32 | 5581.68 | 0 | 0 | Project financially completed. | $ 5,864 plus $ 762 PSC returned ExCom 41 |  |  |  |  | 2002-12-02 | [7 empty] | 2000 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | SAM | SEV | 25 | PRP | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-12-01 |  | 2000-12-01 | 2002-06-01 | 0 | 30000 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 3900 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase 2) | Individual | ASP | SAM | SEV | 39 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2005-04-01 |  | 2006-01-01 |  | 26000 | 0 | 26000 | 17971 | 69.12% | 8029 | 0 | 8029 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2003 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | SAM | SEV | 47 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | SAM | PHA | 50 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-06-01 | 2008-09-01 | 30000 | 0 | 30000 | 29999.55 | 100% | 0.45 | 0 | 0.45 | 3900 | 0 | 3899.9415 | 0.0585 | 0 | Project completed in June 2008 & financially completed | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | SAM | SEV | 53 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Samoa Refrigeration Association has been established. Its members consisted of owner/senior technicians from servicing workshops and instructors from Samoa Institute of Technology. The SREA had regular meetings with the NOU during 2008 and they were involved in assisting the NOU to conduct training and implement other activities under the TPMP. There was one training workshop for enforcement officers organized on 26 November 2008 with 32 participants. There were two trainings organized and conducted for the technicians on June and Cemceber 2008 with 42 participants trained.The National Ozone Day was held on 28th February 2008 with the main focus being on the total phase out of ozone depleting substances in Samoa. Presentations on the Ozone Layer Depletion, technical information and display boards were presented to the public. The NOU have also been assisting School field trips and student researches. Articles are presented in the local Newspapers and talkback shows on televisions and radio stations have been conducted by the NOU and will be continuous throughout this year. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 | 2009-03-01 |  |  | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | The Samoa Refrigeration Association has been established. Its members consisted of owner/senior technicians from servicing workshops and instructors from Samoa Institute of Technology. The SREA had regular meetings with the NOU during 2008 and they were involved in assisting the NOU to conduct training and implement other activities under the TPMP. There was one training workshop for enforcement officers organized on 26 November 2008 with 32 participants. There were two trainings organized and conducted for the technicians on June and Cemceber 2008 with 42 participants trained.The National Ozone Day was held on 28th February 2008 with the main focus being on the total phase out of ozone depleting substances in Samoa. Presentations on the Ozone Layer Depletion, technical information and display boards were presented to the public. The NOU have also been assisting School field trips and student researches. Articles are presented in the local Newspapers and talkback shows on televisions and radio stations have been conducted by the NOU and will be continuous throughout this year. | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | INV | 11 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-11-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 0 | 9000 | 4050 | 0 | 0 | 4050 | 0 | The TPMP implementation started in mid 2008 due to delayed signing of the agreement between the Government and UNEP/UNDP. One of the major challenges was delay in procurement, but this was resolved in 2008. Disbursements to commence in 2009. Second tranche to be approved at 57th ExCom. | [13 empty] | 2007 | Investment
COM | UNIDO | Preparation of a country programme/national phase-out plan | Individual | ASP | SAU | SEV | 49 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-09-01 | 2008-01-01 |  | 2007-12-01 |  | 65000 | 0 | 65000 | 61730 | 94.97% | 3270 | 0 | 1 | 4875 | 0 | 4630 | 245 | 0 | Financial completion in Dec 2008. | [13 empty] | 2006 | NON-INV
ONG | UNEP | Institutional strengthening (establishment of Ozone Unit) | Individual | ASP | SAU | SEV | 53 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2010-11-01 | 2010-11-01 |  |  | 300000 | 0 | 300000 | 0 | 0% | 300000 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | This is new ISP with Saudi Arabia and project document has been signed with country, based on which first payment was disbursed and so far we are waiting for submission of country progress report and cash advance. | [13 empty] | 2007 | Non Investment
ONG | UNIDO | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | INV | 3 | A | O | I | CFC | 269.7 | 0 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 | 2009-12-01 |  |  | 1287000 | 0 | 1287000 | 82533 | 6.413% | 1204467 | 577844 | 550000 | 96525 | 0 | 6190 | 90335 | 43338 | All equipment were procured in 2008 and delivery is expected in 1st Quarter 2009. Two technical assistance workshops were organized for the manufacturing sectors. In addition UNIDO contracted a company for the establishment of a data base for reporting and monitoring of the NPP implementation. | [13 empty] | 2007 | INV | 532 | 532 |  |  | Not yet confirmed | No | No
ONG | UNEP | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | TAS | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-03-01 | 2009-03-01 |  |  | 364500 | 0 | 364500 | 0 | 0% | 364500 | 0 | 364500 | 47385 | 0 | 0 | 47385 | 0 | National committees formulated and detailed work-plan developed in coordination with UNIDO, launching workshop organized, training equipment procurement is ongoing. Contractual arrangements and funds disbursement start in 2009 | [13 empty] | 2007 | Non Investment
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SAU | PHA | 55 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 130000 | 0 | 130000 | 0 | 0% | 130000 | 0 | 30000 | 9750 | 0 | 0 | 9750 | 0 | The identification of national experts/consutancy firms to carry out the survey is in process. The first stakeholder consultation workshop will take place in April 2009. | Legislation related matters are part of the responsibility of UNEP. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SAU | PHA | 55 | PRP | 6 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 65000 | 0 | 65000 | 0 | 0% | 65000 | 0 | 65000 | 8450 | 0 | 0 | 8450 | 0 | Work-plan agreed with country and UNIDO, contractual arrangements and survey started in 2009 | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | SEN | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1993-11-01 | 1993-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1690 | 0 | 1690 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Ozone Focal Point | Individual | AFR | SEN | SEV | 11 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1996-11-01 |  | 1997-12-01 | 1999-09-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22750 | 0 | 22750 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Expansion and upgrading of statistics networks for customs | Individual | AFR | SEN | SEV | 11 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1994-10-01 | 1994-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Training and upgrading for repair technicians | Individual | AFR | SEN | REF | 11 | TRA | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-11-01 |  | 1994-12-01 | 1995-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 | 0 | 7540 | 0 | 7540 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | AFR | SEN | FOA | 18 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 | 0 |  | 1300 | -73 | 1227 | 0 | 0 | FIN
FIN | France | Project preparation for projects in the hotel and fisheries industries and recycling |  | AFR | SEN | REF | 19 | PRP | 6 | A | O | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1996-12-01 | 10000 | -248 | 9752 | 9752 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Training of technicians in domestic refrigeration and air conditioning |  | AFR | SEN | REF | 21 | TRA | 7 | A | O | I |  | 0 |  | 0 |  | 1997-02-01 | 1998-01-01 | 1997-08-01 |  | 1998-03-01 | 1998-06-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | SEN | REF | 22 | TAS | 8 | A | O | I | CFC | 36.12 | 36.12 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-03-01 | 136250 | 0 | 136250 | 136250 | 100% | 0 | 0 |  | 17713 | 0 | 17713 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEN | SEV | 23 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-02-01 | 2000-02-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 | 0 | 15210 | 0 | 15210 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | SEN | REF | 24 | PRP | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 2000-12-01 | 2001-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNIDO | Preparation of a demonstration project (tobacco, peanuts) | Individual | AFR | SEN | FUM | 25 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-01-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide used in peanut seed fumigation in Novasen Ltd. | Individual | AFR | SEN | FUM | 26 | INV | 12 | A | O | I | MBR | 0.7 | 0.7 |  |  | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-02-01 | 62945 | -3226 | 59719 | 59719 | 100% | 0 | 0 |  | 8183 | -432 | 7751 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEN | SEV | 29 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-12-01 |  | 2001-12-01 | 2003-12-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 | 0 | 15210 | 0 | 15210 | 0 | 0 | Project financially completed. | [13 empty] | 1999 | Non Investment
FIN | Switzerland | Implementation of the RMP: demonstration project to retrofit domestic refrigerators for the use of hydrocarbon refrigerant | RMP | AFR | SEN | REF | 33 | TAS | 14 | A | O | I |  | 47 | 0 | 0 | 0 | 2001-03-01 | 2003-07-01 | 2001-11-01 |  | 2004-03-01 | 2004-06-01 | 71230 | 0 | 71230 | 71230 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2001
FIN | UNEP | Implementation of the RMP: Activities for supporting and monitoring the RMP | Individual | AFR | SEN | REF | 33 | TAS | 15 | A | O | I | CFC | 29.4 | 29.4 | 0 | 0 | 2001-03-01 | 2001-07-01 | 2003-12-01 |  | 2002-05-01 | 2003-06-01 | 44500 | -37 | 44463 | 44463 | 100% | 0 | 0 | 0 | 5785 | -4.81 | 5780.19 | 0 | 0 | Project financially completed. | $ 37 plus $ 5 PSC returned ExCom 41 | [12 empty] | 2001 | Non Investment
FIN | UNIDO | Implementation of the RMP: Refrigerant recovery and recycling scheme | RMP Update | AFR | SEN | REF | 33 | TAS | 16 | A | O | I | CFC | 56.1 | 56.1 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2003-03-01 | 2004-04-01 | 85000 | -1970 | 83030 | 83030 | 100% | 0 | 0 |  | 11050 | -273 | 10777 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | SEN | FUM | 34 | TAS | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -9000 | 16000 | 16000 | 100% | 0 | 0 | 0 | 3250 | -1170 | 2080 | 0 | 0 | Project financially completed. | $ 9,000 plus $ 1,170 PSC returned ExCom 44 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Renewal of institutional strengthening projects (Phase IV) | Individual | AFR | SEN | SEV | 36 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 5 | Individual | AFR | SEN | SEV | 41 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | SEN | SEV | 47 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 152100 | 0 | 152100 | 152100.19 | 100% | -0.19 | 0 | -0.19 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SEN | PHA | 48 | PRP | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2008-11-01 |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed in November 2008. TPMP approved in July 2007 | [13 empty] | 2006 | Non Investment
COM | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | SEN | PHA | 48 | PRP | 22 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-04-01 |  | 15000 | 0 | 15000 | 11957 | 79.71% | 3043 | 3041 | 3000 | 1125 | 0 | 897 | 228 | 228 | Project completed in Apr 2008. | [13 empty] | 2006 | NON-INV
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | SEN | PHA | 52 | TAS | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2008-07-01 | 2009-04-01 |  |  | 109500 | 0 | 109500 | 108500 | 99.09% | 1000 | 1000 | 1000 | 14235 | 0 | 14105 | 130 | 130 | Organization of 8 refrigeration training( 400 technicians trained) and 8 Customs training ( 198 officers trained) between June and November 2008. | [13 empty] | 2007 | Non Investment
ONG | Italy | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | SEN | PHA | 52 | INV | 24 | A | O | I |  | 0 |  | 0 |  | 2007-07-01 | 2008-06-01 | 2008-07-01 | 2009-12-01 |  |  | 220000 | 0 | 220000 | 26323 | 11.96% | 193677 | 69625 | 70000 | 28600 | 0 | 3421.99 | 25178.01 | 9051.25 | The equipment (refrigerant identifiers) for training programme of customs officers have been procured and delivered to the country. The equipment for TPMP component 3 of additional training for refrigeration technicians has been procured, delivered and distributed among end users. | Multi-Year Current Tranche - Actual Consumption (ODP Tonnes) was submitted as "n.a." | 2007 | [11 empty] | 2007 | Investment | 26.14 |  | 0 | 0 | n.a.
ONG | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | SEN | SEV | 53 | INS | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-30 | 2009-11-30 |  |  | 152100 | 0 | 152100 | 121600.38 | 79.95% | 30499.62 | 30500 | 30499.62 | 0 | 0 | 0 | 0 | 0 | First pyment done in March 2008 | [13 empty] | 2007 | Non Investment
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SEN | PHA | 55 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 81 | 0.09529% | 84919 | 1308 | 20000 | 6375 | 0 | 6 | 6369 | 98 | National expert was contracted and National survey is on-going for HPMP preparation. | The job description of the consultant addresses survey of the existing legislation and needed measures to extend its provisions on HCFCs. The organization of the workshop is under preparation, dates are to be established in cooperation with NOU in the period June - July 2009 | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | AFR | SEY | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1994-07-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | SEY | SEV | 13 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-03-01 | 1997-07-01 |  | 2000-07-01 | 2000-07-01 | 31900 | 0 | 31900 | 31900 | 100% | 0 | 0 | 0 | 4147 | 0 | 4147 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non Investment
FIN | UNIDO | Preparation of a project proposal for setting up a national refrigerant recovery and recycling centre, National Halon Bank | Individual | AFR | SEY | REF | 15 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1998-01-01 | 2000-07-01 | 15000 | -10846 | 4154 | 4154 | 100% | 0 | 0 |  | 1950 | -1411 | 539 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SEY | REF | 23 | PRP | 4 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-03-01 | 2001-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SEY | REF | 26 | TAS | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. RMP Update ongoing | [13 empty] | 1999
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEY | SEV | 31 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2002-08-01 |  | 2004-12-01 | 2005-12-01 | 21267 | 0 | 21267 | 21267 | 100% | 0 | 0 | 0 | 2764.71 | 0 | 2764.71 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SEY | REF | 37 | PRP | 7 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-07-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved | [13 empty] | 2001
FIN | Germany | Phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | SEY | REF | 40 | TAS | 8 | A | O | I |  | 2.4 | 2.4 | 0 |  | 2003-07-01 | 2003-10-01 | 2006-12-01 |  | 2006-12-01 | 2007-10-01 | 41607 | 0 | 41607 | 41607 | 100% | 0 | 0 | 0 | 5409 | 0 | 5409 | 0 | 0 | PCR has been submitted in October 2007. | [13 empty] | 2002
COM | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SEY | SEV | 44 | INS | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
FIN | France | Project preparation for a terminal phase-out management plan |  | AFR | SEY | PHA | 49 | PRP | 11 | A | O | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2006-09-01 | 2007-07-01 |  | 2007-03-01 | 2007-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 2600 | 0 | 2600 | 0 |  | The French contribution is implemented by GTZ. Project completed
ONG | France | Terminal ODS phase-out management plan (first tranche) | Multi-Year | AFR | SEY | PHA | 51 | INV | 12 | A | O | I | CFC | 0 | 0 | 0 |  | 2007-03-01 | 2007-06-01 | 2009-03-01 | 2009-06-01 |  |  | 120000 | 0 | 120000 | 95200 | 79.33% | 24800 |  | 24800 | 15600 | 0 | 12376 | 3224 |  | The French contribution is implmented by GTZ PROKLIMA. The project is beimg implemented at a slower pace than expected largely. currently assisting with the phasing out of some halons that were discovered. In addition activities on trainings is ongoing for both customs and technicains. Incenitve scheme has led to the conversion of some commercial cooling equipment in the hotel industry.
ONG | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SEY | SEV | 53 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2011-03-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | MOU signed with country, awaiting payment to be made | [13 empty] | 2007 | Non Investment
ONG | France | Terminal ODS phase-out management plan (second tranche) | Multi-Year | AFR | SEY | PHA | 55 | INV | 14 | A | O | I | CFC | 0 |  | 0 |  | 2008-07-01 |  | 2009-03-01 | 2009-10-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 |  | 60000 | 7800 | 0 | 0 | 7800 |  | The French contribution is implemented by GTZ-Proklima. Delayed implementation because funds still remain under the 1st tranche.
COM | UNEP | Formulation of national phase out strategy | Individual | AFR | SIL | SEV | 35 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-08-01 |  | 2003-12-01 |  | 40000 | 0 | 40000 | 15000 | 37.5% | 25000 | 0 | 25000 | 5200 | 0 | 1950 | 3250 | 0 | Project completed | [13 empty] | 2001 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SIL | SEV | 36 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2003-12-03 | 2004-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SIL | SEV | 41 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 85800 | 0 | 85800 | 85800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: training of trainers in code of good refrigeration practices/establishment of national refrigeration demonstration centre | Individual | AFR | SIL | REF | 41 | TRA | 4 | A | O | I | CFC | 18.2 | 18.2 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2006-12-01 |  | 2008-12-07 |  | 119460 | 0 | 119460 | 79996.74 | 66.97% | 39463.26 | 39463 | 39463.26 | 15530 | 0 | 10399.5762 | 5130.4238 | 5130.19 | Project completed in December 2008 | [13 empty] | 2003 | Non Investment
ONG | UNDP | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector, and recovery and recycling project | RMP-Component | AFR | SIL | REF | 41 | TAS | 5 | N | O | I | CFC | 14.1 | 0 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 | 2010-01-01 |  |  | 92400 | 0 | 92400 | 27170 | 29.4% | 65230 | 4650 | 13046 | 8316 | 0 | 2445.3 | 5870.7 | 418.5 | Legislation past in Jul 2008. Activities resumed through a mission by international expert in December 2008. Plan of actions developed and being effective. Additional progress to be achieved in 2009 | [13 empty] | 2003 | Investment
ONG | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | SIL | REF | 41 | TAS | 6 | N | O | I | CFC | 16.4 | 0 | 0 | 0 | 2003-12-01 |  | 2008-12-01 | 2010-01-01 |  |  | 107350 | 0 | 107350 | 0 | 0% | 107350 | 0 | 21470 | 9662 | 0 | 0 | 9662 | 0 | See SIL-05. | [13 empty] | 2003 | Non-Investment
ONG | UNDP | Implementation of the RMP: MAC recovery/recycling of CFC-12 | RMP-Component | AFR | SIL | REF | 41 | TAS | 7 | N | O | I | CFC | 9.4 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2010-01-01 |  |  | 61858 | 0 | 61858 | 0 | 0% | 61858 | 0 | 12371.6 | 5567 | 0 | 0 | 5567 | 0 | See SIL-05. | [13 empty] | 2003 | Investment
COM | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | SIL | REF | 41 | TRA | 8 | A | O | I | CFC | 6.4 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2008-01-01 |  | 41840 | 0 | 41840 | 32014.06 | 76.52% | 9825.94 | 9754 | 9825.94 | 5439 | 0 | 4161.8278 | 1277.1722 | 1268.02 | Project completed in January 2008 | [13 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | SIL | REF | 41 | TAS | 9 | A | O | I | CFC | 2.4 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 |  | 2008-02-01 |  | 15455 | 0 | 15455 | 0 | 0% | 15455 | 15455 | 15455 | 2009 | 0 | 0 | 2009 | 2009.15 | Project completed in February 2008. and awaiting for final report to close the project | [13 empty] | 2003 | Non Investment
COM | UNDP | Project preparation for a halon sectoral phase-out plan | Individual | AFR | SIL | HAL | 45 | PRP | 10 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2006-12-01 |  | 16870 | 0 | 16870 | 8962 | 53.12% | 7908 | 0 | 7908 | 1265 | 0 | 672.0172 | 592.9828 | 0 | Completed in 2006. | [13 empty] | 2005 | Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | SIL | SEV | 47 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2007-01-01 | 2008-12-01 | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
ONG | UNEP | Methyl bromide communication programme | Individual | AFR | SIL | FUM | 47 | TAS | 12 | A | O | I | MB | 0.4 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 | 2009-12-01 |  |  | 50000 | 0 | 50000 | 35000.16 | 70% | 14999.84 | 15000 | 14999.84 | 6500 | 0 | 4550.0208 | 1949.9792 | 1950 | The NOU continued the implementation of FFS and in collaboration with the National Farmer’s Association and the Crop Protection Department conducted a training workshop on alternatives to methyl bromide for soil and post harvest fumigation. The workshop targeted twenty extension workers and farmers who would then serve as trainers. An awareness raising workshop for decision makers on ozone layer depletion and methyl bromide and its alternative was organized for fifty Parliamentarians and heads of Government Departments to generate support for imposing a control system on the importation of the pesticide for use in the agricultural sector. This led to the ratification of the ODS Regulation and the establishment of licenses and quota systems. The NOU conducted awareness raising workshop programmes on radio and TV for stakeholders and the general public on the protection of the ozone layer and Methyl Bromide alternatives. | [13 empty] | 2005 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SIL | PHA | 48 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-12-01 |  | 18000 | 0 | 18000 | 13014.34 | 72.3% | 4985.66 | 4986 | 4985.66 | 2340 | 0 | 1691.8642 | 648.1358 | 648.18 | Project completed in December 2008. . TPMP was approved during the 57th Ex-com | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | SIL | PHA | 48 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 |  | 2008-12-01 |  | 12000 | 0 | 12000 | 10639 | 88.66% | 1361 | 0 | 1361 | 900 | 0 | 797.925 | 102.075 | 0 | Completed in 2008. International expert recruited and a mission fielded in December 2008. TPMP submitted and expected to be approved at 57th ExCom. | [13 empty] | 2006 | Investment
ONG | UNDP | Technical assistance for awareness raising in the halon sector | Individual | AFR | SIL | HAL | 51 | TAS | 15 | N | O | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 |  | 2008-09-01 | 2010-01-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 3000 | 1350 | 0 | 0 | 1350 | 0 | Project document signed. Arrangements are in place, as agreed with the Government, to launch the awareness raising project in Q1/2009. | [13 empty] | 2007 | Non-Investment
COM | UNEP | Extension of institutional strengthening project (phase II, 2nd year) | Individual | AFR | SIL | SEV | 51 | INS | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-03-01 |  | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in March 2008 | [13 empty] | 2007 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | SIL | SEV | 54 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-31 | 2010-03-31 |  |  | 85800 | 0 | 85800 | 25950 | 30.24% | 59850 | 59850 | 59850 | 0 | 0 | 0 | 0 | 0 | IS renewal for Phase III was approved in April 2008. The country signed the SSFA in May 2008 and first disbursement was made in August 2008. The NOU established contact with the naval Wing of the Sierra Leone Arm Forces together with the Customs and Excise Department of the Ministry of Finance and Economic Development. The purpose of this collaboration was to establish an intergovernmental team that will develop strategies to combat illegal trade of ozone depleting substances. The NOU also conveyed a meeting with the Sierra Leone Fire Force and the association of Architects to discuss issue of Architectural design and compartmentalization to identify alternatives to the use of halon in fire fighting. A workshop for decision makers which included Parliamentarians, Directors and professional heads of Departments and Permanent Secretaries was conducted on ozone layer protection and ODS. This led to the ratification of the ODS Regulation and the establishment of licenses and quota systems. An awareness workshop was also organized for officers of the Ministry of Foreign Affairs and International Cooperation and the Ministry of Justice and the Law Officers Department. This facilitated the preparation and ratification of the ODS regulation by Parliament. The NOU conducted awareness workshop on Green Customs Initiative for fifty Custom Officers. Twenty trainers were trained in alternative to methyl bromide for soil and post harvest fumigation. Good refrigeration practices were taught in the Department of refrigeration engineering of the Government Technical Institute. The NOU celebrated the Ozone Day and conducted a number of awareness raising activities such as school essay competition, radio and TV programmes. | [13 empty] | 2008
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SIL | PHA | 56 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Project newly approved | [13 empty] | 2008
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1993) | Individual | EUR | SLO | SEV | 11 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  | 1994-12-01 | 1994-12-01 | 50000 | -50000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | SLO | SEV | 11 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-03-01 |  | 1994-03-01 | 1994-03-01 | 100000 | -100000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | SLO | SEV | 12 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -22085 | 77915 | 77915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A workshop held on project preparation and processing procedures earlier in the year has helped the preparation of 8 subprojects in the refrigeration, foam, aerosol and solvents sectors. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1994) | Individual | EUR | SLO | SEV | 12 | CPG | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SOA | PHA | 55 | PRP | 1 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2010-07-01 |  |  | 195000 | 0 | 195000 | 0 | 0% | 195000 | 0 | 1 | 14625 | 0 | 0 | 14625 | 0 | Meeting with the NOU is planned for 1st Quarter 2009. | The responsible Ministry is planning to present the internal review of the legislation beginning of June 2009. In case required, revision of the legislation will be part of the sub contract. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | ASP | SOI | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 2600 | -910 | 1690 | 0 | 0 | Project financially completed. | $ 7,000 plus $ 910 PSC returned ExCom 41 |  |  | 1999-12-01 | [9 empty] | 1995 | Non Investment
COM | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | SOI | REF | 36 | TAS | 2 | A | O | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | Prohibited Import and Export Order and Restricted Import and Export Order made June 2007. Customs training workship complete. Project will be complete when the regional strategy as a whole is completed. |  | 2002
COM | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | SOI | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2006-06-01 |  | 20250 | 0 | 20250 | 12150 | 60% | 8100 | 0 | 8100 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2002 | Non Investment
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | SOI | REF | 36 | TAS | 4 | A | O | I |  | 1.4 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 |  | 34000 | 0 | 34000 | 23351 | 68.68% | 10649 | 0 | 10649 | 4420 | 0 | 0 | 4420 | 4420 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | SOI | SEV | 49 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 |  | 2007-12-31 |  | 2008-12-01 |  | 6833 | 0 | 6833 | 0 | 0% | 6833 | 0 | 6833 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | SOI | SEV | 53 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008. | [13 empty] | 2007 | Non Investment
ONG | UNEP | Formulation of national phase out strategy | Individual | AFR | SOM | SEV | 35 | TAS | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2002-08-01 | 2009-12-01 |  |  | 60000 | 0 | 60000 | 35098 | 58.5% | 24902 | 0 | 24902 | 7800 | 0 | 4562.74 | 3237.26 | 0 | No activity in 2008 but CAP team assisted NOU Somalia in preparation of Action Plan as requested by ImpCom. Resubmission of CP planned for 58 ExCom | [7 empty] | 2003-12-01 | [5 empty] | 2001 | Non Investment
FIN | UNDP | Formulation of refrigerant management plan | Individual | AFR | SOM | REF | 36 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2005-11-01 | 2005-12-01 | 15000 | -14659 | 341 | 341 | 100% | 0 | 0 | 0 | 1950 | -1906 | 44 | 0 | 0 | Completed in 2005. Financially completed in 2005. | [13 empty] | 2002 | Investment
COM | UNEP | Establishment of the Ozone Unit | Individual | AFR | SOM | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2008-12-01 |  | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008 with preparation and submission of Action Plan to ImpCom. | [13 empty] | 2002 | Non Investment
ONG | UNEP | Establishment of the National Ozone Committee (institutional strengthening) | Individual | AFR | SOM | SEV | 44 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2009-12-01 |  |  | 26000 | 0 | 26000 | 0 | 0% | 26000 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | MOU signed in December 2008 | [13 empty] | 2004 | Non Investment
FIN | UNDP | Country programme preparation | Individual | ASP | SRL | SEV | 06 | CPG | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-09-01 |  | 1994-03-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | SRL | SEV | 12 | INS | 2 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1997-03-01 |  | 1997-10-01 | 2003-09-01 | 154680 | 0 | 154680 | 154680 | 100% | 0 | 0 | 0 | 20108 | 0 | 20108 | 0 | 0 | Completed in 1997. Financially completed in 2003. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | SRL | SEV | 14 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-06-01 |  | 1996-06-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Associated Electrical Corporation (AEC) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 4 | A | O | I | CFC | 7.3 | 7.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1998-08-01 | 2000-12-01 | 250114 | -912 | 249202 | 249202 | 100% | 0 | 0 | 0 | 32515 | -119 | 32396 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Glacio Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 5 | A | O | I | CFC | 6.8 | 6.8 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 239500 | -26843 | 212657 | 212657 | 100% | 0 | 0 | 0 | 31135 | -3490 | 27645 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-08-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Regnis (Lanka) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 6 | A | O | I | CFC | 6.3 | 6.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 284324 | -18407 | 265917 | 265917 | 100% | 0 | 0 | 0 | 36962 | -2393 | 34569 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at International Cosmetic Ltd. (ICL) | Individual | ASP | SRL | ARS | 18 | INV | 7 | A | O | I | CFC | 5 | 5 | 0 | 0 | 1995-11-01 | 1997-04-01 | 1996-11-01 |  | 2001-08-01 | 2003-11-01 | 38968 | -5599 | 33369 | 33369 | 100% | 0 | 0 | 0 | 5066 | -728 | 4338 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-08-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | ASP | SRL | REF | 20 | TAS | 8 | A | O | I | CFC | 31.2 | 31.2 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1999-12-01 | 2001-12-01 | 352400 | -1472 | 350928 | 350928 | 100% | 0 | 0 | 0 | 45812 | -191 | 45621 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1996 | Investment
CLO | IBRD | Country programme preparation |  | ASP | SRL | SEV | 04 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 23339 | -23339 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | SRL | SEV | 23 | INS | 10 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-11-01 | 1999-12-01 |  | 1999-12-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 1999. Financially completed in 2003. | [13 empty] | 1997 | Non-Investment
FIN | UNDP | Project preparation for one project in the solvent sector | Individual | ASP | SRL | SOL | 24 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Project preparation assistance for the methyl bromide sector | Individual | ASP | SRL | FUM | 25 | PRP | 12 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-06-01 | 2004-12-01 | 25000 | -1090 | 23910 | 23910 | 100% | 0 | 0 | 0 | 3250 | -142 | 3108 | 0 | 0 | Completed in 1999. Financially completed in 2004. | [13 empty] | 1998 | Investment
COM | UNDP | Alternatives to methyl bromide for eradication of tea nematodes in Sri Lanka | Individual | ASP | SRL | FUM | 27 | DEM | 13 | A | O | I | MeBr | 3.9 | 3.9 | 0 | 0 | 1999-03-01 | 2000-07-01 | 2001-04-01 |  | 2007-10-01 |  | 310200 | 0 | 310200 | 302252 | 97.44% | 7948 | 0 | 6358.4 | 40326 | 0 | 39292.76 | 1033.24 | 0 | Completed in 2007. | [13 empty] | 1999 | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase III) | Individual | ASP | SRL | SEV | 29 | INS | 14 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2002-02-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 1999 | Non-Investment
ONG | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration | RMP-Component | ASP | SRL | REF | 32 | TAS | 15 | N | O | I | CFC | 5 | 3 | 0 | 0 | 2000-12-01 | 2002-04-01 | 2006-01-01 | 2010-01-01 |  |  | 250000 | 0 | 250000 | 48805 | 19.52% | 201195 | 0 | 40239 | 32500 | 0 | 6344.65 | 26155.35 | 0 | Advertisements for calling application published. Information about users of CFC based refrigeration equipment collected. | [13 empty] | 2000 | Non-Investment
COM | UNEP | Implementation of the RMP: Customs training programme | Individual | ASP | SRL | REF | 32 | TRA | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-02 | 2003-01-03 |  | 2005-04-01 |  | 87000 | 0 | 87000 | 45367 | 52.15% | 41633 | 0 | 41633 | 11310 | 0 | 5897.71 | 5412.29 | 0 | Project completed | [13 empty] | 2000 | Non Investment
COM | UNEP | Implementation of the RMP: Train the trainers and training of refrigeration service technicians including | Individual | ASP | SRL | REF | 32 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-02 | 2003-12-02 |  | 2004-09-01 |  | 219000 | -38504 | 180496 | 146992 | 81.44% | 33504 | 0 | 33504 | 28470 | -5005 | 19108.96 | 4356.04 | 0 | Project completed | $ 22,003 plus $ 2,860 PSC returned to ExCom 50 $ 16,501 plus $ 2,145 PSC returned to ExCom 54 | [12 empty] | 2000 | Non Investment
COM | UNDP | Implementation of the RMP: monitoring the activities included in the RMP | RMP-Component | ASP | SRL | REF | 32 | TAS | 18 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2008-12-01 |  | 15455 | 0 | 15455 | 13169 | 85.21% | 2286 | 0 | 1828.8 | 2009 | 0 | 1711.8422 | 297.1578 | 0 | Completed in 2008. The survey on use of Recovery & Recycling equipment distributed under RMP was continued and the data of recovery was recorded. Also a survey on the use of Recovery & Recycling equipment distributed under RMP was carried out. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Preparation of a terminal programme in the fumigant sector | Individual | ASP | SRL | FUM | 36 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2002-11-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -473 | 2777 | 0 | 0 | Completed in 2002. Financially completed in 2005. | [13 empty] | 2002 | Investment
COM | UNDP | Renewal of institutional strengthening project (Phase 4) | Individual | ASP | SRL | SEV | 37 | INS | 20 | N | T | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-08-01 |  | 134056 | 0 | 134056 | 131378 | 98% | 2678 | 0 | 2142.4 | 17427 | 0 | 17079.14 | 347.86 | 0 | Completed in 2004. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Methyl bromide phase-out for all remaining uses excluding QPS applications | One-off-Phaseout | ASP | SRL | FUM | 38 | TAS | 21 | N | O | I | MeBr | 3.3 | 3.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-11-01 |  | 2007-10-01 |  | 130000 | 0 | 130000 | 129998 | 100% | 2 | 0 | 1.6 | 16900 | 0 | 16899.74 | 0.26 | 0 | Completed in 2007. | [9 empty] | 2005-11-01 |  |  |  | 2002 | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | SRL | SEV | 43 | INS | 22 | N | T | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-12-01 | 2008-10-01 | 134056 | 0 | 134056 | 134042 | 99.99% | 14 | 0 | 0 | 10054 | 0 | 10052.95 | 1.05 | 0 | Completed in 2006. Financially Completed in 2008. | [13 empty] | 2004 | Non-Investment
COM | UNEP | National compliance action plan: enhancement of national capacity to monitor trade and prevent illegal trade of ODS | Individual | ASP | SRL | PHA | 43 | TRA | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2009-12-01 |  | 2008-12-01 |  | 135000 | 0 | 135000 | 134999.78 | 100% | 0.22 | 0 | 0.22 | 17550 | 0 | 17549.9714 | 0.0286 | 0 | Project completed in December 2008. Availability of trained 452 customs and enforcement officers under the implementation of National Compliance Action Plan (NCAP); Establishment of Enforcement/Information Centre at the Customs House under Department of Customs; All the awareness materials produced by NOU, are given to the center, which makes it easy to customs officers and the general public to obtain any information required; New internal circular for Sri Lanka customs on ODS issues: New guidelines made regarding import and export of ODS “NOU online ODS Data base system” incorporated with the Sri Lanka Custom and Import and Export Control Department, developed mainly for the purpose of combating the illegal imports of ODS , for regulating the ODS licensing system with the pertinent government institutions and for accessing ODS import data correctly and easily. The Government of Sri Lanka took a decision to phase out CFCs by the year 2008 in order to comply with the Montreal Protocol obligation. The Coordinating Committee for implementing the Montreal Protocol organized a media conference with Hon. Minister Patali Champika Ranawaka, the minister of Ministry of Environment and Natural Resources on 30th August 2007 at Grand Oriental Hotel, Colombo. This conference was covered by all national Media. Awareness materials developed and widely distributed to customs offices, borders and public; Also, established a strong relationship with press people on a regular media update regarding the ban on the import of ODS and other general awareness programme on the implementation of Montreal Protocol. ODS Task Force: up to the year 2008, 9 meeting were held respectively on 14.01.2004, 28.05.2004, 16.11.2004, 25.01.2005, 25.05.2005, 09.03.2006, 13.06.2006, 12. 02.2007 &4th August 2008; Due to this ODS Task Force, it has become easy to take decisions and actions on prevention of illegal imports of ODS; and to build a very good relationship between customs, NOU and other relevant government authorities. A new regulation (No. 1533/16 dated 25.01.2008) for the Repairing Maintaining or Installation Centers of Refrigerators, and Air-conditioners. | [13 empty] | 2004 | Non Investment
ONG | UNEP | National compliance action plan: halon bank management | Individual | ASP | SRL | PHA | 43 | TAS | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-06-01 | 2009-12-01 | 2009-12-01 |  |  | 40000 | 0 | 40000 | 25014.69 | 62.54% | 14985.31 | 0 | 14985.31 | 5200 | 0 | 3251.9097 | 1948.0903 | 0 | The NOU conducted the second National Halon Workshop held on 27th August 2008. The purpose of this workshop is to discuss the possibilities of maintaining a virtual Halon Bank for critical use requirement and introduce and discus in detail about ozone friendly fire fighting technologies. Conducting this kind of Workshop is one of the obligations in the Halon Bank Management Programme that was approved for Sri Lanka to be fulfilled. Therefore special attention was given to emphasis the importance to Halon Users to update their knowledge. The workshop was attended by Present Halon Users, Fire Officers of Defence sectors, Fire Officers of Fire Departments attached to Municipal Councils in Sri Lanka and Members of Fire Engineering Traders Association. | [11 empty] | 2007-12-01 |  | 2004 | Non Investment
COM | UNEP | National compliance action plan: extension training of the established refrigeration technicians | Individual | ASP | SRL | PHA | 43 | TRA | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2007-12-01 |  | 2008-12-01 |  | 174600 | 0 | 174600 | 172102.91 | 98.57% | 2497.09 | 0 | 2497.09 | 22698 | 0 | 22373.3783 | 324.6217 | 0 | Project completed in December 2008. There were a total of 1,779 refrigeration technicians trained under the NCAP. A total of 3,524 participants attended the awareness session for technicians organized back to back with the training programme. Establishment of Certificate System which issued to technicians after their participation in the training programmes. Establishment of Training Centre which facilities are available to conduct technicians training programme and awareness sessions. | [13 empty] | 2004 | Non Investment
ONG | Japan | National compliance action plan: incentive programme for commercial and industrial refrigeration end-users | One-off Phase-out | ASP | SRL | PHA | 43 | TAS | 26 | A | O | I | CFC | 5 |  | 0 |  | 2004-07-01 |  | 2005-12-01 | 2009-12-01 |  |  | 144000 | 0 | 144000 | 1844.1 | 1.281% | 142155.9 |  | 8000 | 18720 | 0 | 0 | 18720 |  | 1) One incentive payment was approved to Lanka Canneries Ltd. (fruit processing company). The amount approved was approximately US$ 965.00, which is 65% of the estimated cost of the retrofitting. The agreement was signed on 13th March 2009. Lanka Canneries Ltd. has already commenced the retrofitting of two refrigeration systems. 2) The technical evaluation of another application is almost finished and will be able to sign the agreement expectedly within the first week of May. 3) The NOU is currently in communication with a government-run milk processing factory to look into the possibility of their applying for the incentive programme in relation to the conversion of milk chilling plants which are located in the North and East areas of Sri Lanka. |  | 2004 | [8 empty] | 2007-12-01
ONG | Japan | National compliance action plan: MAC recovery/recycling and retrofit | One-off Phase-out | ASP | SRL | PHA | 43 | TAS | 27 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2006-12-01 | 2005-12-01 | 2009-12-01 |  |  | 123000 | 0 | 123000 | 65269.51 | 53.06% | 57730.49 |  | 57730 | 15990 | 0 | 0 | 15990 |  | 1) After the original programme target to retrofit 200 government vehicles were achieved on 3rd June 2008 with 203 vehicles retrofitted, the retrofitting programme have been continued, using the balance of approximately US$ 22,000. In 2008, 156 vehicles have been retrofitted in total, with the total number of retrofitted vehicles as of 31st December 2008 standing at 267. 299 vehicles have been retrofitted as of 31st March 2009. 2) A local consultant and the monitoring officer made on-site visits of MAC workshops which have been granted equipment in 2007. |  | 2004
ONG | Japan | National compliance action plan: recovery and recycling programme | One-off Phase-out | ASP | SRL | PHA | 43 | TAS | 28 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2008-10-01 | 2006-12-01 | 2009-12-01 |  |  | 290400 | 0 | 290400 | 132323.51 | 45.57% | 158076.49 |  | 158076 | 37752 | 0 | 0 | 37752 |  | 1) UNDP local office in Colombo published a newspaper advertisement on 22nd March 2009 inviting global suppliers to bid for the supply of recovery/recycling equipment. The bid were closed on 10th April 2009 and 4 bids were received. The NOU is making arrangements to appoint the Technical Evaluation Committee for the evaluation of bids received. 2) A local consultant and the monitoring officer visited refrigeration workshops which have been granted equipment in 2007 and in 2008. 3) The collection of data on the refrigerant recovery using the granted equipment was made (cf. the table below on Page 3). |  | 2004
ONG | Japan | National compliance action plan: monitoring the activities proposed in the plan | One-off Phase-out | ASP | SRL | PHA | 43 | TAS | 29 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2009-12-01 | 2009-12-01 |  |  | 108000 | 0 | 108000 | 35795.07 | 33.14% | 72204.93 |  | 72205 | 14040 | 0 | 0 | 14040 |  | 1) Continuation of the survey on the use of recovery & recycling equipment that has been distributed under RMP / NCAP. 2) A monitoring officer is stationed at the NOU on a regular basis to communicate with the ozone officer and different NOU officers in charge of individual project components, compiling the records of financial expenditure and implementation progress. On a monthly basis, the “project budget details” table and the “progress details” table, among other things, are updated. |  | 2004
COM | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SRL | SEV | 45 | TAS | 30 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 |  | 36697 | 0 | 36697 | 31219 | 85.07% | 5478 | 0 | 4382.4 | 3303 | 0 | 2809.9397 | 493.0603 | 0 | Completed in 2008. Final invoices pertaining to survey settled. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | SRL | SEV | 50 | INS | 31 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 |  | 2008-11-01 |  | 134056 | 0 | 134056 | 127464 | 95.08% | 6592 | 0 | 5273.6 | 10054 | 0 | 9559.6098 | 494.3902 | 0 | Completed in 2008. In 2008 the phase 6 of IS completed the second half of the action plan. Relevant data on ODS consumption collected and reported to MLF and Ozone secretariat. Awareness creation campaigns carried out and awareness creation materials printed and distributed. Two coordinating committee meetings held. International Ozone Day celebrated with awareness raising materials distributed. | [13 empty] | 2006 | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | SRL | SEV | 55 | INS | 32 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-12-01 | 2010-12-01 |  |  | 134056 | 0 | 134056 | 0 | 0% | 134056 | 0 | 26811.2 | 10054 | 0 | 0 | 10054 | 0 | Taking over activities from SRL-31 as soon as funds depleted. Ozone Unit fully operational as reflected in IS progress report and action plan. | [13 empty] | 2008 | Non-investment
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | SRL | PHA | 55 | PRP | 33 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 112250 | 0 | 112250 | 0 | 0% | 112250 | 0 | 112250 | 8419 | 0 | 0 | 8419 | 0 | Initiated prodoc & TORs Experts to be recruited in Q1-2009. Project inception workshop planned by mid 2009. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SRL | PHA | 55 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-12-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 25000 | 3250 | 0 | 0 | 3250 | 0 | Consultations are underway for National consultation appointment for UNEP component - UNDP is the lead agency. Launch workshop expected in May / June 2009. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | STK | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-12-01 | 1999-12-01 | 35000 | -12500 | 22500 | 22500 | 100% | 0 | 0 | 0 | 4550 | -1625 | 2925 | 0 | 0 | Project financially completed. | $12,500 plus $ 1,625 returned ExCom 30 | [12 empty] | 2001 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | LAC | STK | SEV | 21 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 2000-02-01 |  | 2006-09-01 | 2007-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | STK | REF | 21 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-09-01 | 1998-03-01 |  | 1998-03-01 | 1999-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | Canada | Implementation of the RMP including training programmes for refrigeration technicians and customs officers, assistance in the design of policies and regulations and recovery and recycling | RMP | LAC | STK | REF | 24 | TAS | 4 | A | O | I | CFC | 2 |  | 0 |  | 1998-03-01 | 1999-05-01 | 2001-03-01 |  | 2006-03-06 | 2006-03-06 | 124300 | 0 | 124300 | 124300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | R&R workshop and customs training were delayed because legislation not yet place. However legislation was adopted in early 2004 and R&R project was completed. Phase I Customs Training also implemented. Final reports by country received in February 2006, |  | 1998 | [11 empty] | 1998 | Non-Inv.
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STK | SEV | 42 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-08-01 | 2005-04-01 |  | 2007-08-01 | 2008-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | LAC | STK | REF | 44 | PRP | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-03-01 | 2008-12-01 | 15000 | -2312 | 12688 | 11539.68 | 90.95% | 1148.32 | 0 | 0 | 1950 | -301 | 1500.1584 | 148.8416 | 0 | Project completed. Balances to be returned to ExCom 57 | $ 2,312 plus $ 301 returned at ExCom 52 | [12 empty] | 2004 | Non Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | STK | SEV | 47 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2008-12-01 | 2009-12-01 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | First disbursement made in February 2008 | [13 empty] | 2005 | Non Investment
ONG | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 9 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 |  | 2009-12-01 | 2009-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 20000 | 4500 | 0 | 0 | 4500 | 0 | Equipment and tools (kit of good practices) procured. Will be delivered in early 2009. Expenditures to be reflected in 2009. Tranches 2 & 3 approved at 56th ExCom meeting. | [13 empty] | 2006 | Investment | 1.9 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2009-12-01 | 2009-12-01 |  |  | 40000 | 0 | 40000 | 24998.43 | 62.5% | 15001.57 | 0 | 15001.57 | 5200 | 0 | 3249.7959 | 1950.2041 | 0 | A national consultant has been contracted to work with the NOO, UNEP and UNDP for the implementation , monitoring and reporting on the TPMP. Customs training completed. Bejing admendment ratified. Interim committee for the association established. Two customs officials and the national ozone officer and assistant NOO attended a Regional Workshop for the Prevention and Control of Illegal Trade in Ozone Depleting Substances and Dependent Technologies. Senior Technician attended regional meeting for longer term alternatives. MLF approved second and third phases at the 56th ExCom. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Technical assistance to phase out the use of methyl bromide | Individual | LAC | STK | FUM | 50 | TAS | 11 | A | O | I | MB | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 | 2009-06-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 14713.4 | 20000 | 2600 | 0 | 0 | 2600 | 1912.742 | The international bid for the acquisition of equipment has concluded. The equipment has been purchased and sent to the country. Currently the shipment is at port and arrangements are being made to get clearance from the customs office to the importer's warehouse. Training on the use of the equipment is expected for 2009 2nd quarter. | [12 empty] | 2008-12-01 | 2006 | Non Investment
ONG | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | TAS | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2010-03-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 0 | 90000 | 11700 | 0 | 0 | 11700 | 0 | Project recently approved. Funding agreement is being negotiated with the country. | [13 empty] | 2008
ONG | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | INV | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 22000 | 4950 | 0 | 0 | 4950 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STK | PHA | 56 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2010-03-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Project recently approved. Funding agreement is being negotiated with the country. Regional preparatory meeting to be held in March of 2009. | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | STL | SEV | 13 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-10-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNEP | Development of a refrigeration management plan | RMP | LAC | STL | REF | 21 | PRP | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-03-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 | 0 | 0 | 1950 | -130 | 1820 | 0 | 0 | Project financially completed. | $ 1,000 plus $ 130 PSC returned ExCom 30 | [12 empty] | 1994 | Non Investment
FIN | UNEP | Establishment of an Ozone Cell | Individual | LAC | STL | SEV | 21 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 2000-02-01 |  | 2000-08-01 | 2001-08-01 | 36580 | 0 | 36580 | 36580 | 100% | 0 | 0 | 0 | 4755.4 | 0 | 4755.4 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | Canada | Implementation of the RMP | RMP | LAC | STL | REF | 23 | TAS | 4 | A | O | I | CFC | 3 |  | 0 |  | 1997-11-01 | 1998-03-01 | 2000-12-01 |  | 2003-12-01 | 2003-12-01 | 146900 | 0 | 146900 | 146900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | All activities completed. Project Completion Report is currently being drafted. |  | 1997 | [11 empty] | 1997 | Non-Inv.
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | STL | SEV | 30 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2002-04-01 |  | 2002-06-01 | 2003-07-01 | 24400 | 0 | 24400 | 24400 | 100% | 0 | 0 | 0 | 3172 | 0 | 3172 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | Canada | Preparation of update of refrigerant management plan | Individual | LAC | STL | REF | 35 | PRP | 6 | A | O | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-07-01 |  | 2003-11-01 | 2003-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 |  | 0 | 975 | 0 | 975 | 0 |  | RMP Update was completed and project was submitted in Nov. 2003. |  | 2000 | [11 empty] | 2001 | Non-Inv.
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | STL | SEV | 37 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-06-01 | 2005-12-01 | 31200 | 0 | 31200 | 31200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | Canada | Implementation of the RMP update | RMP Update | LAC | STL | REF | 41 | TAS | 8 | A | O | I |  | 7.1 | 7.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2007-05-01 | 2008-12-08 | 73450 | 0 | 73450 | 73328 | 99.83% | 122 |  | 0 | 9549 | 0 | 9533 | 16 |  | Project completed. 71 refrigeration technicians trained. Public service announcements were developed and broadcasted. Retrofit demonstration workshops concluded, including demonstrations of AC and vehicle retrofits. R&R equipment distributed. Though financial completion was previously reported to be May 2007, it was subsequently found that $122 were remaining. This amount, plus $16 in support costs, is to be returned to the Fund at the 58th ExCom Meeting. |  | 2003 | [11 empty] | 2003 | Non-Inv.
COM | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | LAC | STL | SEV | 43 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-10-01 | 2006-07-01 |  | 2007-04-01 |  | 31200 | 0 | 31200 | 30800 | 98.72% | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
FIN | Canada | Project preparation for a TPMP |  | LAC | STL | PHA | 48 | PRP | 10 | A | O | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-09-06 | 2007-04-01 |  | 2007-04-01 | 2008-07-08 | 30000 | -7000 | 23000 | 23000 | 100% | 0 |  | 0 | 3900 | -910 | 2990 | 0 |  | TPMP proposal completed and submitted in April 2007 for ExCom 52. Not all funds were used. Remaining funds returned to Fund. |  | 2006 | [11 empty] | 2006 | Non-Inv.
ONG | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | STL | SEV | 49 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2008-07-31 | 2009-07-31 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Terminal report and request of renewal submitted in May 2008. Project completion expected for 2009 first quarter. During the period from June 2006 to July 2008, St Lucia advanced in the implementation of the Institutional Strengthening Project. In particular, the NOO continued initiating actions to provide a suitable climate in Saint Lucia for the expeditious phase out of ODS. Also St. Lucia received, collect, analyse and disseminate information on the issues involved in ozone layer protection. Objectives were achieved in the following matters: Licensing system implemented and monitored; Import Quotas being issued by the Licensing Department of the Ministry of Commerce; Legislation being reviewed to adjust to the accelerated phase out of HCFCs. | [13 empty] | 2006 | Non Investment
ONG | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (first tranche) | Multi-Year | LAC | STL | PHA | 52 | INV | 12 | A | O | I | CFC | 0 |  | 0 |  | 2007-07-01 | 2007-09-01 | 2009-07-01 | 2009-07-01 |  |  | 156000 | 0 | 156000 | 131663 | 84.4% | 24337 |  | 23664 | 20280 | 0 | 9663 | 10617 |  | TPMP implementation began in Oct. 2007. R&R equipment and tools to be delivered in March 2008 and has now been distributed. Project monitoring and evaluation mechanism has been established, technicians training and customs training were undertaken. Legal framework for R&AC Association and revised MP regulations has been completed but is awaiting official government approval. See first tranche report. |  | 2007 | [11 empty] | 2007 | Investment | 1.2 | 0 |  |  | Yes
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STL | PHA | 55 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions for project imiplementation and further arrangements are being set. | [13 empty] | 2008
ONG | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | LAC | STL | SEV | 55 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2010-07-31 | 2010-07-31 |  |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | Agreement for project implementation has been recently signed and first fund disbursement already processed. The country is currently producing A7 data report for 2008 and is updated with earlier reports. | [13 empty] | 2008
ONG | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (second tranche) | Multi-Year | LAC | STL | PHA | 56 | INV | 15 | A | O | I | CFC | 1.2 |  | 0 |  | 2008-11-01 |  | 2009-11-01 | 2010-03-01 |  |  | 49000 | 0 | 49000 | 0 | 0% | 49000 |  | 40000 | 6370 | 0 | 0 | 6370 |  | Project approved in Nov. 2008. Agreement for project is under development; expect initiation mid-2009. |  | 2008 | [11 empty] | 2008 | Investment | 1.2 | 0 |  |  | Yes
FIN | UNEP | Preparation of country programme and refrigerant management plan | Individual | AFR | STP | SEV | 36 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2007-12-01 | 30000 | -3538 | 26462 | 26462 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 3,538 returned to ExCom 52 | [12 empty] | 2002 | Non Investment
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | STP | SEV | 38 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | STP | REF | 39 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-06-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2003 | Investment
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | STP | SEV | 44 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 |  | 2006-06-01 | 2008-12-01 | 40000 | 0 | 40000 | 39999.73 | 100% | 0.27 | 0 | 0.27 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: assistance for development of a licensing system | Individual | AFR | STP | REF | 44 | TAS | 6 | A | O | I |  | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-06-01 |  | 2006-12-01 |  | 20000 | 0 | 20000 | 15000 | 75% | 5000 | 5000 | 5000 | 2600 | 0 | 1950 | 650 | 650 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: training programme for custom officers | Individual | AFR | STP | REF | 44 | TRA | 7 | A | O | I |  | 0.7 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 |  | 45000 | 0 | 45000 | 21399 | 47.55% | 23601 | 23601 | 23601 | 5850 | 0 | 2781.87 | 3068.13 | 3068.13 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | STP | REF | 44 | TRA | 8 | A | O | I |  | 0.9 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2006-12-01 |  | 2008-12-01 |  | 55000 | 0 | 55000 | 17067 | 31.03% | 37933 | 20032 | 37933 | 7150 | 0 | 2218.71 | 4931.29 | 2604.16 | Project completed in December 08 | [13 empty] | 2004 | Non Investment
COM | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | STP | REF | 44 | TAS | 9 | A | O | I |  | 0.3 | 0 | 0 | 0 | 2004-12-01 | 0 | 2007-12-01 |  | 2007-12-07 |  | 20000 | 0 | 20000 | 9999.73 | 50% | 10000.27 | 10000 | 10000.27 | 2600 | 0 | 1299.9649 | 1300.0351 | 1300 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | STP | REF | 44 | TAS | 10 | N | O | I | CFC | 1.8 | 1.8 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2006-12-01 |  | 2008-12-01 |  | 110000 | 0 | 110000 | 95179 | 86.53% | 14821 | 0 | 11856.8 | 9900 | 0 | 8566.11 | 1333.89 | 0 | Completed in 2008. Remaining funds used for national consultant, local travel and replacement of broken R&R equipment and spares. Some outstanding invoices remaining and accounts to be closed in 2009. | [13 empty] | 2004 | Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | STP | SEV | 50 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-12-01 | 2009-12-01 |  |  | 60666 | 0 | 60666 | 19665.53 | 32.42% | 41000.47 | 40999 | 41000.47 | 0 | 0 | 0 | 0 | 0 | Slow disbursement rate but NOU operation. 1st payment made in Oct 2008 | [13 empty] | 2006 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | STP | PHA | 50 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-06-01 |  | 30000 | 0 | 30000 | 29992 | 99.97% | 8 | 0 | 8 | 3900 | 0 | 3898.96 | 1.04 | 0 | Project completed in June 2008 after submission of TPMP document | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | LAC | STP | PHA | 54 | TAS | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-31 | 2010-03-31 |  |  | 54000 | 0 | 54000 | 45008.53 | 83.35% | 8991.47 | 4000 | 8991.47 | 7020 | 0 | 5851.1089 | 1168.8911 | 520 | MOU sent to Country for Signature | [13 empty] | 2008
ONG | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | STP | PHA | 54 | INV | 14 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-08-01 | 2010-03-31 | 2010-03-01 |  |  | 66000 | 0 | 66000 | 21851 | 33.11% | 44149 | 7426 | 44000 | 5940 | 0 | 1967 | 3973 | 668 | Equipment and tools required for the drop in were purchased. The project activities started with the training of technicians in the use of hydrocarbon as drop-in and the CFC in domestic refrigerators are being replaced by hydrocarbon. A national consultant is coordinating the project activities. Three technicians from technical institute and refrigeration association were trained in Portugal on the recovery and recycling issues and technology. The planned completion date is March 2010. | [13 empty] | 2008 | INV | 0.7 | 0.2 |  |  | Yes | N/A | N/A
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | STP | PHA | 55 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-07-31 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU sent to Country for signature | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | LAC | STV | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-08-01 |  | 1998-05-01 | 1999-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training of trainers for good practices in refrigeration | Individual | LAC | STV | REF | 25 | TRA | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Implementation of the refrigerant management plan: Monitoring and control of ODS and ODS based equipment | Individual | LAC | STV | REF | 25 | TRA | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2004-03-01 | 2000-02-01 |  | 2005-02-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Creation of the National Ozone Unit | Individual | LAC | STV | SEV | 25 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-04-22 | 2001-06-01 |  | 2004-03-01 | 2005-12-01 | 30300 | 0 | 30300 | 30300 | 100% | 0 | 0 | 0 | 3939 | 0 | 3939 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 42 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-03-01 | 2005-04-01 |  | 2005-03-01 | 2005-12-01 | 13130 | 0 | 13130 | 13130 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2004 | Non Investment
COM | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | STV | REF | 44 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2005-12-01 |  | 2005-11-01 |  | 20000 | 0 | 20000 | 13019.95 | 65.1% | 6980.05 | 0 | 6980.05 | 2600 | 0 | 1692.5935 | 907.4065 | 0 | Project completed | [13 empty] | 2004 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 45 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2008-03-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in March 2008 & financially completed. UNON advised that they have received and approved all reports required for Closure, | [13 empty] | 2005 | Non Investment
ONG | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-Year | LAC | STV | PHA | 47 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 | 2009-12-01 |  |  | 67000 | 0 | 67000 | 57770.08 | 86.22% | 9229.92 | 5000 | 9229.92 | 8710 | 0 | 7510.1104 | 1199.8896 | 650 | New project activities were reprogrammed and signed off through a new funding agreement (SSFA) signed with the country, therefore, first disbursement was issued and funds available at country level. Currently, final financial reports are being prepared to allow for project closure. Completed Establishment of an Association of Refrigeration Technicians. Develop and published Code of Good Practice. Commencement of training in Good Practices, Recovery, Recycling and Reuse of Refrigerants and Retrofitting, including the use of Drop-in replacements for fixed and MAC systems; Draft Amendment of the Montreal Protocol Regulations to require licensing of technicians; senior customs officer attended regional workshop on ODS illegal trade prevention, senior technician attended regional workshop on longer term alternative technologies . | [13 empty] | 2005 | Non Investment
COM | UNDP | Terminal phase out management plan for CFCs (first phase) | Multi-Year | LAC | STV | PHA | 47 | INV | 11 | N | O | I | CFC | 1.3 | 1.3 | 0 | 0 | 2005-11-01 | 2007-08-01 | 2006-12-01 |  | 2008-12-01 |  | 101000 | 0 | 101000 | 79148 | 78.36% | 21852 | 0 | 17481.6 | 9090 | 0 | 7123.32 | 1966.68 | 0 | Completed in 2008. Kit of good practice (tools and equipment) procured and delivered to beneficiary technicians and workshops. Additional training was provided by local expert. Accounts will be settled in 2009, but remaining activities under tranches 2&3 approved at the 56th ExCom. | [13 empty] | 2005 | Investment | 2.1 |  |  |  | Latest | Latest | Latest
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | STV | SEV | 50 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2008-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 48000 | 80% | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | Second Payment issued and available at country level per submission of progress and finance reports. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STV | PHA | 55 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions for project implementation and further arrangements are being settled to formalize funding agreement (SSFA). Regional preparatory planning meeting scheduled for March 2009. | [13 empty] | 2008
ONG | UNEP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | TAS | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2010-12-01 |  |  | 28000 | 0 | 28000 | 0 | 0% | 28000 | 0 | 28000 | 3640 | 0 | 0 | 3640 | 0 | Project recently approved. Funding agreement is being negotiated with the country. Draft SSFA sent to country for review. | [13 empty] | 2008
ONG | UNDP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | INV | 15 | N | O | I | CFC | 0.8 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 27000 | 0 | 27000 | 0 | 0% | 27000 | 0 | 10800 | 2430 | 0 | 0 | 2430 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SUD | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1994-03-01 | 1994-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | SUD | SEV | 12 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1997-03-01 |  | 1999-07-01 | 1999-12-01 | 168300 | 0 | 168300 | 168300 | 100% | 0 | 0 | 0 | 21879 | 0 | 21879 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non Investment
FIN | UNIDO | Preparation of investment projects in the refrigeration, aerosol and foam sectors | Individual | AFR | SUD | SEV | 14 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-03-01 | 1995-01-01 |  | 1998-04-01 | 1999-08-01 | 50000 | -5442 | 44558 | 44558 | 100% | 0 | 0 |  | 6500 | -717 | 5783 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Sudanese Cosmetics and Household Products | Individual | AFR | SUD | ARS | 18 | INV | 4 | A | O | I | CFC | 281.5 | 281.5 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 497613 | -297 | 497316 | 497316 | 100% | 0 | 0 |  | 64690 | -141 | 64549 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Patra Foam Co. flexible polyurethane foam plant | Individual | AFR | SUD | FOA | 19 | INV | 5 | A | O | I | CFC | 16 | 16 |  |  | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1997-12-01 | 2000-04-01 | 72227 | 0 | 72227 | 72227 | 100% | 0 | 0 |  | 9390 | -1 | 9389 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of ODS at three small domestic refrigerator factories in Sudan (Coldair Refrigerator Factory, Modern Refrigerator + Metal furniture Co., Sheet Metal Industries Co. Refrigerator Factory) | Individual | AFR | SUD | REF | 19 | INV | 6 | A | O | I | CFC | 7.28 | 7.3 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 2002-03-01 | 2003-05-01 | 100000 | -13637 | 86363 | 86363 | 100% | 0 | 0 |  | 13000 | -1791 | 11209 | 0 | 0 | FIN |  |  | 1997-08-01
FIN | UNIDO | Preparation of Refrigerant Management Plan | Individual | AFR | SUD | REF | 23 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 1998-12-01 | 2000-04-01 | 10000 | 16173 | 26173 | 26173 | 100% | 0 | 0 |  | 1300 | 2097 | 3397 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | SUD | ARS | 27 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 25000 | -7393 | 17607 | 17607 | 100% | 0 | 0 |  | 3250 | -965 | 2285 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | AFR | SUD | REF | 28 | TRA | 9 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2002-06-01 |  | 2003-12-01 | 2003-12-01 | 70000 | -510 | 69490 | 69490 | 100% | 0 | 0 |  | 9100 | -81 | 9019 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | AFR | SUD | REF | 28 | TAS | 10 | A | O | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2004-08-01 | 2006-09-01 | 350000 | -1732 | 348268 | 348268 | 100% | 0 | 0 |  | 45500 | -225 | 45275 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | AFR | SUD | REF | 28 | TRA | 11 | A | O | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2001-08-01 | 2001-02-01 |  | 2002-10-01 | 2004-09-01 | 38250 | -1916 | 36334 | 36334 | 100% | 0 | 0 |  | 4973 | -257 | 4716 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | SUD | SEV | 28 | INS | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-12-01 | 2001-12-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 | 0 | 0 | 14586 | 0 | 14586 | 0 | 0 | Project financially completed. |  |  |  |  | 2001-06-01 | [8 empty] | 1999 | Non Investment
FIN | UNIDO | Phasing out of CFCs at Tag Cosmetics Ltd. | Individual | AFR | SUD | ARS | 28 | INV | 13 | A | O | I | CFC | 45.1 | 45.1 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2002-07-01 | 2002-12-01 | 131718 | 0 | 131718 | 131718 | 100% | 0 | 0 |  | 17123 | -8 | 17115 | 0 | 0 | FIN
COM | UNEP | Renewal of institutional strengthening project | Individual | AFR | SUD | SEV | 34 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-12-01 |  | 112200 | 0 | 112200 | 43696 | 38.94% | 68504 | 0 | 68504 | 14586 | 0 | 5680.48 | 8905.52 | 0 | Project completed | [13 empty] | 2001 | Non Investment
FIN | UNIDO | Preparation of investment projects in the domestic/commercial refrigeration sector | Individual | AFR | SUD | REF | 39 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-09-01 | 2004-04-01 |  | 2005-04-01 | 2005-08-01 | 20000 | -345 | 19655 | 19655 | 100% | 0 | 0 |  | 1500 | -28 | 1472 | 0 | 0 | FIN | [13 empty] | 2003
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | SUD | PHA | 41 | PRP | 15 | A | O | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 70000 | -294 | 69706 | 69706 | 100% | 0 | 0 |  | 5250 | -30 | 5220 | 0 | 0 | FIN | [13 empty] | 2003 | INV
ONG | UNEP | Extension of institutional strengthening: phase IV | Individual | AFR | SUD | SEV | 42 | INS | 16 | A | T | I | CFC | 12.1 | 0 | 0 | 0 | 2004-04-01 |  | 2006-04-01 | 2009-06-01 |  |  | 145860 | 0 | 145860 | 0 | 0% | 145860 | 0 | 145860 | 0 | 0 | 0 | 0 | 0 | The NOU conducted Training of service technicians which has become a routine practice under the current NPP in Sudan. About 200 technicians were trained under this programme in 2008. All investment projects have been completed and there is no CFC consumption in the manufacturing sectors. During the reporting period, regular visits to converted factories were made to ensure that no CFCs are being used. Training/recycling centres and selected workshops were also visited for encouragement, data collection and control purposes. By putting newly established centres in operation as well as via cooperation with other partners in the National Committee, NOU has stepped forward in extending its monitoring and enforcement activities beyond the borders of Khartoum State. The NOU celebrated the Ozone Day and conducted a number of awareness raising activities such as lectures, group briefings, radio and TV programmes as well as interviews and articles in the Sudanese newspapers. The NOU participated in national and international meetings on Ozone issue; in particular, the NOU participated in the 54th, 55th and 56th Meetings of the Executive committee of the MF for the Implementation of the MP and the 28th Meetings of the Open-ended Working Group. | [13 empty] | 2004 | Non Investment
COM | UNIDO | National CFC/CTC phase-out plan (first tranche) | Multi-Year | AFR | SUD | PHA | 44 | INV | 18 | A | O | I | CFC CTC | 16.77 | 71.77 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 |  | 499480 | 0 | 499480 | 472944 | 94.69% | 26536 | 26536 | 26536 | 37461 | 0 | 35471 | 1990 | 1990 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2004 | INV | 200.3 | 185.3 |  |  | Yes | Yes | Yes
COM | UNIDO | National CFC/CTC phase-out plan (second tranche) | Multi-Year | AFR | SUD | PHA | 50 | INV | 19 | A | O | I | CFC | 70.3 | 70.3 |  |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2007-12-01 |  | 220000 | 0 | 220000 | 216919 | 98.6% | 3081 | 3056 | 3000 | 16500 | 0 | 16269 | 231 | 229 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2006 | INV | 130.3 | 120 |  |  | Yes | Yes | Yes
ONG | UNIDO | National CFC/CTC phase-out plan (third tranche) | Multi-Year | AFR | SUD | PHA | 53 | INV | 20 | A | O | I | CFC | 65 | 0 |  |  | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-12-01 |  |  | 220000 | 0 | 220000 | 11132 | 5.06% | 208868 | 0 | 70000 | 16500 | 0 | 835 | 15665 | 0 | Two training courses organized to train 16 technical teachers/trainers from the staff operating R&R centers. Upgrade of National R&R scheme including training of staff on business administration including accounting. Technical specification to purchase service equipment for newly identified/certified training centers will be prepared. National consultant to help NOU and coordinate implementation activities was recruited. | [13 empty] | 2007 | INV | 45 | 44.8 |  |  | Yes | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SUD | PHA | 55 | PRP | 21 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 60 | 0.2% | 29940 | 0 | 25000 | 2250 | 0 | 5 | 2245 | 0 | Terms of Reference for an institution to undertake the survey have been prepared. Recruitment is in progress and offers to be received by end of January 2009. | The workshop is planned to take place as soon as initial information is collected. Legislation on import control of ODS is in place. HCFC-specific amendments may be introduced as appropriate in due course. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Preparation of country programme | Individual | LAC | SUR | SEV | 30 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-06-01 |  | 2003-08-01 | 2005-05-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 6500 | -4550 | 1950 | 0 | 0 | Project financially completed. | $ 25,000 plus $ 3,250 PSC returned ExCom 44 $ 10,000 plus $ 1,300 PSC returned ExCom 46 | [6 empty] | 2003-07-01 | [5 empty] | 2000 | Non Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | SUR | REF | 36 | PRP | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. | [13 empty] | 2002 | Investment
ONG | UNEP | Institutional strengthening and capacity building: establishment of the Ozone Unit | Individual | LAC | SUR | SEV | 41 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 | 2009-06-01 |  |  | 110000 | 0 | 110000 | 95297.43 | 86.63% | 14702.57 | 0 | 14702.57 | 0 | 0 | 0 | 0 | 0 | Country has to submit final financial, inventory of non-expendable equipment and final progress reports to allow completion of the project | [13 empty] | 2003 | Non Investment
COM | UNEP | Implementation of the RMP: development and strengthening of policy and regulatory framework for acceleration of compliance with the Montreal Protocol | Individual | LAC | SUR | REF | 41 | TAS | 4 | A | O | I | CFC | 1.5 | 1.5 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-01-01 |  | 20000 | 0 | 20000 | 18137.56 | 90.69% | 1862.44 | 0 | 1862.44 | 2600 | 0 | 2357.8828 | 242.1172 | 0 | Project completed | [13 empty] | 2003 | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers and other relevant stakeholders in monitoring of ODS | Individual | LAC | SUR | REF | 41 | TRA | 5 | A | O | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-10-01 | 2008-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNEP | Implementation of the RMP: training of trainers in good practices of refrigeration | Individual | LAC | SUR | REF | 41 | TRA | 6 | A | O | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-07-01 |  | 2007-12-01 | 2008-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 2003 | Non Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | LAC | SUR | REF | 42 | PRP | 7 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2005. Financially completed in 2006. | [13 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: technical assistance for the MAC and refrigeration service sectors | RMP-Component | LAC | SUR | REF | 44 | TAS | 9 | N | O | I | CFC | 23 | 21 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2007-06-01 | 2010-01-01 |  |  | 300430 | 0 | 300430 | 28842 | 9.6% | 271588 | 0 | 54317.6 | 22532 | 0 | 2163.126 | 20368.874 | 0 | One mission by international expert to place in 2008. Training was given to national experts. Procurement of equipment and tools completed, and the two winning companies will deliver the equipment in early 2009. | [13 empty] | 2004 | Investment
ONG | UNDP | Implementation of the RMP: monitoring the activities within the RMP | RMP-Component | LAC | SUR | REF | 44 | TAS | 10 | N | O | I | CFC | 2 | 1 | 0 | 0 | 2004-12-01 |  | 2007-06-01 | 2010-01-01 |  |  | 25750 | 0 | 25750 | 0 | 0% | 25750 | 0 | 5150 | 2318 | 0 | 0 | 2318 | 0 | See SUR-09 above. | [13 empty] | 2004 | Non-Investment
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | SUR | SEV | 50 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 | 2009-11-01 |  |  | 73333 | 0 | 73333 | 29333.2 | 40% | 43999.8 | 43999.8 | 43999.8 | 0 | 0 | 0 | 0 | 0 | First disbursment was realized in February 2008. Country achieved zero consumption of CFCs. | [13 empty] | 2006 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | SUR | PHA | 50 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 |  | 15000 | 0 | 15000 | 11796.72 | 78.64% | 3203.28 | 0 | 3203.28 | 1950 | 0 | 1533.5736 | 416.4264 | 0 | Project completed in December 2008. TPMP resulting from this activity was approved at 56th ExCom meeting. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | SUR | PHA | 50 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2007-11-01 |  | 2008-12-01 |  | 15000 | 0 | 15000 | 12500 | 83.33% | 2500 | 0 | 2500 | 1125 | 0 | 937.5 | 187.5 | 0 | Completed in 2008. TPMP was successfully presented and approved at ExCom 56 | [13 empty] | 2006 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | SUR | PHA | 55 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Preliminary discussions for project implementation and further arrangements are being settled to formalize funding agreement (SSFA). Planning preparatory meeting set for March 2009. | [13 empty] | 2008
ONG | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-06-30 | 2010-06-30 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 100000 | 13000 | 0 | 0 | 13000 | 0 | Project recently approved. Funding agreement is being negotiated with the country. Draft SSFA sent to country for review. | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | INV | 16 | N | O | I | CFC | 6.2 | 0 | 0 | 0 | 2008-11-01 |  | 2010-06-01 | 2010-06-01 |  |  | 125000 | 0 | 125000 | 0 | 0% | 125000 | 0 | 25000 | 11250 | 0 | 0 | 11250 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SWA | SEV | 12 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-09 | 1995-06-01 |  | 1994-12-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration production at FridgeMaster | Individual | AFR | SWA | REF | 15 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 25000 | -13308 | 11692 | 11692 | 100% | 0 | 0 |  | 3250 | -1733 | 1517 | 0 | 0 | FIN
FIN | UNEP | Institutional strengthening | Individual | AFR | SWA | SEV | 15 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1998-12-01 |  | 2003-12-01 | 2007-02-01 | 67320 | 0 | 67320 | 67320 | 100% | 0 | 0 | 0 | 8751.6 | 0 | 8751.6 | 0 | 0 | Project financially completed. |  |  | 1998-03-01 | [10 empty] | 1994 | Non Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SWA | REF | 23 | PRP | 4 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SWA | REF | 26 | TAS | 5 | A | O | I | CFC | 4 | 1.5 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 90375 | 0 | 90375 | 90375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted. RMP update ongoing | [13 empty] | 2001
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SWA | REF | 37 | PRP | 6 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2003-08-03 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. RMP update approved at 41st Excom
COM | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | SWA | SEV | 41 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2007-12-01 |  | 58344 | 0 | 58344 | 51885.51 | 88.93% | 6458.49 | 0 | 6458.49 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2003 | Non Investment
ONG | Germany | Implementation of the RMP update | RMP Update | AFR | SWA | REF | 41 | TAS | 8 | A | O | I |  | 20.9 | 20.9 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 | 2009-10-01 |  |  | 74295 | 0 | 74295 | 70000 | 94.22% | 4295 | 0 | 4295 | 9658 | 0 | 9099.6702 | 558.3298 | 0 | Additional workshop on the licensing system and training of customs officers was conducted. However once again there is no ozone officier in Swaziland and so work has come to a standstill | [13 empty] | 2002
COM | UNDP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 9 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2008-11-01 |  | 2008-12-01 |  | 15000 | 0 | 15000 | 9909 | 66.06% | 5091 | 0 | 5091 | 1125 | 0 | 743.175 | 381.825 | 0 | Completed in 2008. International expert fielded with a visit in July 2008. TPMP document developed, submitted and approved by ExCom at its 56th meeting in November 2008. | [13 empty] | 2007 | Investment
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SWA | SEV | 53 | INS | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 | 2009-11-01 |  |  | 60000 | 0 | 60000 | 19500.38 | 32.5% | 40499.62 | 40500 | 40499.62 | 0 | 0 | 0 | 0 | 0 | First payment made in March, 2008. NOU prepared TPMP and conducted trainings for cutsoms officers and Refrigertaion technicians | [13 empty] | 2007 | Non Investment
COM | UNEP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2008-11-30 |  | 2008-11-30 |  | 15000 | 0 | 15000 | 14999.76 | 100% | 0.24 | 0 | 0.24 | 1950 | 0 | 1949.9688 | 0.0312 | 0 | Project completed in November 2008. TPMP was approved during the 56th Ex-com | [13 empty] | 2007 | Non Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | TAS | 11 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-30 | 2010-11-30 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 75000 | 9750 | 0 | 0 | 9750 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | INV | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-11-01 | 2010-11-01 |  |  | 81500 | 0 | 81500 | 0 | 0% | 81500 | 0 | 16300 | 7335 | 0 | 0 | 7335 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SWA | PHA | 56 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | ASP | SYR | SEV | 4 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-11-01 | 1993-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration industry | Individual | ASP | SYR | SEV | 09 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-11-01 | 1993-09-01 |  | 1994-12-01 | 1996-05-01 | 35000 | -5 | 34995 | 34995 | 100% | 0 | 0 |  | 4550 | -8 | 4542 | 0 | 0 | FIN
FIN | UNIDO | Support to strengthening the General Commission for Environmental Affairs to implement Montreal Protocol related activities | Individual | ASP | SYR | SEV | 10 | INS | 3 | N | T | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 2002-11-01 | 2003-06-01 | 235180 | -15273 | 219907 | 219907 | 100% | 0 | 0 |  | 30573 | -2030 | 28543 | 0 | 0 | FIN |  |  | 1997-07-01 | 1999-10-01
FIN | UNIDO | Phasing out of CFCs at Al Hafez Refrigeration Co. | Individual | ASP | SYR | REF | 13 | INV | 4 | A | O | I | CFC | 106.7 | 100.7 |  |  | 1994-07-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 2001-05-01 | 2883277 | 0 | 2883277 | 2883277 | 100% | 0 | 0 |  | 374826 | 0 | 374826 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFC at Penguin (Syrian Batric Co.) | Individual | ASP | SYR | REF | 15 | INV | 5 | A | O | I | CFC | 82.3 | 77.3 |  |  | 1994-12-01 | 1996-01-01 | 1996-06-01 |  | 1996-12-01 | 2000-12-01 | 1719900 | -1241 | 1718659 | 1718659 | 100% | 0 | 0 |  | 223587 | -515 | 223072 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC in manufacturing of refrigerators at Krayem Int. Co. | Individual | ASP | SYR | REF | 15 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -711 | 14289 | 14289 | 100% | 0 | 0 |  | 1950 | -95 | 1855 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 from the manufacturing of pre-fabricated sandwich panels at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 15 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -1404 | 13596 | 13596 | 100% | 0 | 0 |  | 1950 | -185 | 1765 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for phasing out of CFC-11 from the sub sector of flexible foams manufacturing | Individual | ASP | SYR | FOA | 15 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | UNIDO | Phasing out CFC at Barada General Co. for Metallic Industry | Individual | ASP | SYR | REF | 15 | INV | 9 | A | O | I | CFC | 109 | 97 |  |  | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-12-01 | 2001-07-01 | 989650 | -95593 | 894057 | 894057 | 100% | 0 | 0 |  | 128655 | -12612 | 116043 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | ASP | SYR | ARS | 18 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-05-01 |  | 1998-05-01 | 1999-08-01 | 25000 | -746 | 24254 | 24254 | 100% | 0 | 0 |  | 3250 | -102 | 3148 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs from Manufacturing of domestic and commercial refrigerators at Krayem Brothers Co. | Individual | ASP | SYR | REF | 18 | INV | 11 | A | O | I | CFC | 89 | 89 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1998-12-01 | 2002-09-01 | 1071575 | -13558 | 1058017 | 1058017 | 100% | 0 | 0 |  | 139305 | -1981 | 137324 | 0 | 0 | FIN
CLO | UNIDO | Preparation of an investment project in recovery and recycling sector | Individual | ASP | SYR | REF | 18 | PRP | 12 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-01-01 |  |  | 2001-07-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  | 1998-12-01 | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Gaston Banna & Sons Co. | Individual | ASP | SYR | ARS | 19 | INV | 13 | A | O | I | CFC | 104 | 104 |  |  | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 1998-12-01 | 2000-04-01 | 299500 | 0 | 299500 | 299500 | 100% | 0 | 0 |  | 38935 | 0 | 38935 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Dakkak Co. flexible polyurethane foam plant | Individual | ASP | SYR | FOA | 19 | INV | 14 | A | O | I | CFC | 17 | 17 |  |  | 1996-05-01 | 1996-10-01 | 1997-05-01 |  | 1998-12-01 | 2001-11-01 | 96553 | 0 | 96553 | 96553 | 100% | 0 | 0 |  | 12552 | -17 | 12535 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 19 | INV | 15 | A | O | I | CFC | 65 | 65 |  |  | 1996-05-01 | 1996-11-01 | 1997-09-01 |  | 1998-12-01 | 2001-07-01 | 644600 | -9228 | 635372 | 635372 | 100% | 0 | 0 |  | 83798 | -1331 | 82467 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Careesse Cosmetics | Individual | ASP | SYR | ARS | 21 | INV | 16 | A | O | I | CFC | 185 | 185 |  |  | 1997-02-01 | 1997-06-01 | 1998-04-01 |  | 1998-12-01 | 2000-12-01 | 272621 | -1208 | 271413 | 271413 | 100% | 0 | 0 |  | 35441 | -213 | 35228 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Abdul Karim Sbei | Individual | ASP | SYR | FOA | 21 | INV | 17 | A | O | I | CFC | 61.7 | 61.7 |  |  | 1997-02-01 | 1997-06-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 92256 | -1984 | 90272 | 90272 | 100% | 0 | 0 |  | 11993 | -276 | 11717 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Walid and Nabil Rankousi Ltd. | Individual | ASP | SYR | FOA | 21 | INV | 18 | A | O | I | CFC | 38.7 | 38.7 |  |  | 1997-02-01 | 1998-11-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 86782 | -2175 | 84607 | 84607 | 100% | 0 | 0 |  | 11282 | -301 | 10981 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | ASP | SYR | FOA | 21 | PRP | 19 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-06-01 |  | 2000-12-01 | 2002-09-01 | 10000 | -362 | 9638 | 9638 | 100% | 0 | 0 |  | 1300 | -49 | 1251 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al Yaman | Individual | ASP | SYR | ARS | 22 | INV | 20 | A | O | I | CFC | 95 | 95 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2002-08-01 | 216128 | -2737 | 213391 | 213391 | 100% | 0 | 0 |  | 28097 | -400 | 27697 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ahmed Ali Harsho Sons Co. | Individual | ASP | SYR | ARS | 22 | INV | 21 | A | O | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-12-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 175328 | -3796 | 171532 | 171532 | 100% | 0 | 0 |  | 22793 | -529 | 22264 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Taki Eddin & Co. | Individual | ASP | SYR | ARS | 22 | INV | 22 | A | O | I | CFC | 118.8 | 118.8 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 244203 | 0 | 244203 | 244203 | 100% | 0 | 0 |  | 31746 | -44 | 31702 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Laboratories Kosmeto | Individual | ASP | SYR | ARS | 23 | INV | 23 | A | O | I | CFC | 59.9 | 59.9 |  |  | 1997-11-01 | 1998-10-01 | 1999-02-01 |  | 1999-10-01 | 2001-11-01 | 175062 | -1772 | 173290 | 173290 | 100% | 0 | 0 |  | 22758 | -266 | 22492 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Dina Cosmetics | Individual | ASP | SYR | ARS | 23 | INV | 24 | A | O | I | CFC | 70 | 70 |  |  | 1997-11-01 | 1998-10-01 | 1999-08-01 |  | 2000-07-01 | 2001-12-01 | 228477 | -456 | 228021 | 228021 | 100% | 0 | 0 |  | 29702 | -106 | 29596 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Akal Factory | Individual | ASP | SYR | FOA | 23 | INV | 25 | A | O | I | CFC | 101 | 101 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 2002-10-01 | 2004-04-01 | 510130 | 0 | 510130 | 510130 | 100% | 0 | 0 |  | 66317 | -26 | 66291 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of at least three investment projects in the aerosol sector for phasing out ODS at three enterprises including Nweylati | Individual | ASP | SYR | ARS | 23 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2001-05-01 | 10000 | 4480 | 14480 | 14480 | 100% | 0 | 0 |  | 1300 | 579 | 1879 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | SYR | FUM | 23 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | SYR | REF | 23 | PRP | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNIDO | Preparation of investment projects for NPD in Damascus and others in rigid foam sector | Individual | ASP | SYR | FOA | 24 | PRP | 29 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-04-01 | 2002-09-01 | 15000 | -238 | 14762 | 14762 | 100% | 0 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN |  |  |  | 1999-09-01
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in horticulture and commodities fumigation | Individual | ASP | SYR | FUM | 24 | DEM | 30 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 2001-05-01 | 2003-05-01 | 509850 | -33283 | 476567 | 476567 | 100% | 0 | 0 |  | 66281 | -4425 | 61856 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mariza Co. | Individual | ASP | SYR | ARS | 25 | INV | 31 | A | O | I | CFC | 90 | 90 |  |  | 1998-07-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 207652 | -3210 | 204442 | 204442 | 100% | 0 | 0 |  | 26995 | -460 | 26535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU slabstock foam through the use of CO2 blowing technology at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 26 | INV | 32 | A | O | I | CFC | 96 | 96 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2001-12-01 | 2003-12-01 | 543918 | 0 | 543918 | 543918 | 100% | 0 | 0 |  | 69831 | -3 | 69828 | 0 | 0 | FIN | [5 empty] | 2001-12-01
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ammar Industrial Establishment | Individual | ASP | SYR | REF | 26 | INV | 33 | A | O | I | CFC | 56 | 56 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 331080 | -222 | 330858 | 330858 | 100% | 0 | 0 | 0 | 43040 | -29 | 43011 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNIDO | Phasing out CFC-11 in the manufacture of flexible PU slabstock foam through the use of methylene chloride as blowing agent at Chaar Bros Co. | Individual | ASP | SYR | FOA | 26 | INV | 34 | A | O | I | CFC | 50 | 50 |  |  | 1998-11-01 | 1999-02-01 | 2000-04-01 |  | 2000-05-01 | 2001-07-01 | 98248 | -79 | 98169 | 98169 | 100% | 0 | 0 |  | 12772 | -30 | 12742 | 0 | 0 | FIN
FIN | France | Project preparation in the commercial refrigeration sector |  | ASP | SYR | REF | 26 | PRP | 35 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 25000 | -8828 | 16172 | 16172 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | UNIDO | Phasing out CFCs at Al-Fajer Co. | Individual | ASP | SYR | ARS | 26 | INV | 36 | A | O | I | CFC | 44 | 44 |  |  | 1998-11-01 | 1999-10-01 | 2000-04-01 |  | 2000-06-01 | 2001-07-01 | 169985 | -1059 | 168926 | 168926 | 100% | 0 | 0 |  | 22098 | -172 | 21926 | 0 | 0 | FIN
FIN | France | Technical assistance in the air-conditioning sector |  | ASP | SYR | REF | 26 | TAS | 37 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 30000 | -4018 | 25982 | 25982 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of domestic and commercial refrigeration equipment and foam sandwich panels at Ahmad Al-Hafez Al-Waha Refrigerator Co. | Individual | ASP | SYR | REF | 26 | INV | 38 | A | O | I | CFC | 28.2 | 28.2 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 330486 | 0 | 330486 | 330486 | 100% | 0 | 0 | 0 | 42963 | 0 | 42963 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at El-Effendi Refrigerator Plant | Individual | ASP | SYR | REF | 26 | INV | 39 | A | O | I | CFC | 13.3 | 13.3 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2007-01-01 | 182802 | -25050 | 157752 | 157752 | 100% | 0 | 0 | 0 | 23764 | -3256 | 20508 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 1998 | Investment
FIN | UNIDO | Project preparation of investment projects in the domestic refrigeration sector | Individual | ASP | SYR | REF | 27 | PRP | 40 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2002-09-01 | 20000 | -2856 | 17144 | 17144 | 100% | 0 | 0 |  | 2600 | -375 | 2225 | 0 | 0 | FIN
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 41 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1999 | Investment
CLO | UNDP | Preparation of one project in the flexible foam subsector | Individual | ASP | SYR | FOA | 27 | PRP | 42 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2004-01-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2001. | [13 empty] | 1999 | Investment
FIN | UNDP | Preparation of three projects in the domestic refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 43 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNIDO | Project preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 27 | PRP | 44 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-07-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 8000 | -1359 | 6641 | 6641 | 100% | 0 | 0 |  | 1040 | -178 | 862 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Golden Penguin Co. | Individual | ASP | SYR | REF | 28 | INV | 45 | A | O | I | CFC | 18.4 | 18.4 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 247481 | -52260 | 195221 | 195221 | 100% | 0 | 0 |  | 32173 | -6834 | 25339 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Ihsan Co. | Individual | ASP | SYR | REF | 28 | INV | 46 | A | O | I | CFC | 37.4 | 37.4 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-01-01 | 2003-05-01 | 497250 | -16958 | 480292 | 480292 | 100% | 0 | 0 | 0 | 64643 | -2205 | 62438 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
ONG | UNEP | Refrigerant management plan: Training programme for custom officials | Individual | ASP | SYR | REF | 29 | TRA | 47 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-03 | 2009-12-01 |  |  | 72600 | 0 | 72600 | 10000 | 13.77% | 62600 | 0 | 62600 | 9438 | 0 | 1300 | 8138 | 0 | All project activities completed, only disbursement of final payments under country contract is pending | [5 empty] | 2002-12-02 | [7 empty] | 1999 | Non Investment
COM | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarkisian Refrigerators |  | ASP | SYR | REF | 29 | INV | 48 | A | O | I | CFC | 3.8 |  | 0 |  | 1999-11-01 | 2007-03-21 | 2002-12-01 |  | 2007-12-10 |  | 57783 | 0 | 57783 | 57783 | 100% | 0 |  | 0 | 2889 | 0 | 2889 | 0 |  | Project completed.
ONG | UNEP | Refrigerant management plan: Training for trainers and refrigeration technician on good service practices | Individual | ASP | SYR | REF | 29 | TRA | 49 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2002-12-01 | 2009-12-01 |  |  | 201300 | 0 | 201300 | 129664 | 64.41% | 71636 | 0 | 71636 | 26169 | 0 | 16856.32 | 9312.68 | 0 | All project activities completed, only disbursement of final payments under country contract is pending | [13 empty] | 1999 | Non Investment
FIN | France | Development of a halon banking management plan |  | ASP | SYR | HAL | 29 | TAS | 50 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2004-04-21 | 2000-05-01 |  | 2001-05-01 | 2004-04-21 | 10736 | 0 | 10736 | 10736 | 100% | 0 |  |  | 536 | 0 | 536 | 0 |  | Project completed.
FIN | UNEP | Refrigerant management plan: Assistance for the establishment of regulations and legislation | Individual | ASP | SYR | REF | 29 | TAS | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-03 |  | 2002-06-01 | 2007-01-01 | 25500 | -10000 | 15500 | 15500 | 100% | 0 | 0 | 0 | 3315 | -1300 | 2015 | 0 | 0 | Project financially completed. | $ 10,000 plus $ 1,300 PSC returned ExCom 46 | [12 empty] | 1999 | Non Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigerarion equipment at seven enterprises | Individual | ASP | SYR | REF | 29 | INV | 52 | A | O | I | CFC | 51.9 | 51.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2003-08-01 | 2005-09-01 | 743419 | -20056 | 723363 | 723363 | 100% | 0 | 0 | 0 | 91776 | -2206 | 89569.93 | 0.07 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 1999 | Investment
CLO | France | Conversion from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Shoukairi and Co. |  | ASP | SYR | REF | 29 | INV | 53 | A | O | I | CFC | 2.5 |  | 0 |  | 1999-11-01 |  | 2002-12-01 |  |  | 2008-07-01 | 33359 | -33359 | 0 | 0 |  | 0 |  | 0 | 1668 | -1668 | 0 | 0 |  | Project cancelled (Decision 55/4)
FIN | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Bashar Refrigerators |  | ASP | SYR | REF | 29 | INV | 54 | A | O | I | CFC | 3.2 | 3.2 | 0 |  | 1999-11-01 | 2005-02-15 | 2002-12-01 |  | 2005-02-01 | 2005-10-01 | 49113 | 0 | 49113 | 47497.8723 | 96.71% | 1615.1277 |  | 0 | 2456 | 0 | 2375.2321 | 80.7679 |  | Project completed. Balance returned at 57th ExCom.
FIN | Germany | Development of halon banking management plan | Halon banking | ASP | SYR | HAL | 29 | TAS | 55 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2000-05-01 |  | 2000-05-01 | 2002-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 | 0 | 0 | 1396 | 0 | 1396 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 2001
COM | France | CFC emission reduction in central air conditioning |  | ASP | SYR | REF | 29 | INV | 56 | A | O | I | CFC | 0.9 |  | 0 |  | 1999-11-01 | 2006-09-03 | 2002-06-01 |  | 2006-12-29 |  | 143000 | 0 | 143000 | 106383 | 74.39% | 36617 |  | 0 | 7150 | 0 | 5319.15 | 1830.85 |  | Project completed.
CLO | UNIDO | Preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 30 | PRP | 57 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 30 | PRP | 58 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570 | 2030 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
COM | Germany | Implementation of the RMP: national recovery and recycling network | Individual | ASP | SYR | REF | 30 | TAS | 59 | A | O | I | CFC | 120 | 120 | 0 |  | 2000-03-01 | 2000-11-01 | 2002-04-01 |  | 2008-05-01 |  | 742146 | 0 | 742146 | 742146 | 100% | 0 | 0 | 0 | 96479 | 0 | 96479 | 0 | 0 | All activities which were planned for 2007 (report, guide book version) were finalized and remaining project funds were allocated for additional halon bank equipment. The project activities are completed and PCR and will be sent to MLF in 2009.
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Alaman Co. | Individual | ASP | SYR | REF | 28 | INV | 60 | A | O | I | CFC | 15.9 | 15.9 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 215910 | -36884 | 179026 | 179026 | 100% | 0 | 0 |  | 28068 | -4832 | 23236 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to cyclopenthane in the production of rigid foam panels at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 31 | INV | 61 | A | O | I | CFC | 61.1 | 61.1 |  |  | 2000-07-01 | 2001-04-01 | 2002-08-01 |  | 2004-10-01 | 2005-04-01 | 426104 | 0 | 426104 | 426104 | 100% | 0 | 0 |  | 55394 | -46 | 55348 | 0 | 0 | FIN | [7 empty] | 2003-11-01
FIN | UNIDO | Preparation of a project in the flexible foam sector | Individual | ASP | SYR | FOA | 31 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-12-01 | 2003-05-01 | 20000 | -27 | 19973 | 19973 | 100% | 0 | 0 |  | 2600 | -8 | 2592 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a project in the fumigant (methyl bromide) sector for grain fumigation | Individual | ASP | SYR | FUM | 31 | PRP | 63 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2001-07-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -5357 | 14643 | 14643 | 100% | 0 | 0 |  | 2600 | -699 | 1901 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Al-Wattar Home Appliances Co. | Individual | ASP | SYR | REF | 31 | INV | 64 | A | O | I | CFC | 18.9 | 18.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-05-01 | 2004-01-01 | 235860 | 0 | 235860 | 235860 | 100% | 0 | 0 | 0 | 30662 | 0 | 30662 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Assalam Refrigerator Co. | Individual | ASP | SYR | REF | 31 | INV | 65 | A | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 144309 | 0 | 144309 | 144309 | 100% | 0 | 0 | 0 | 18760 | 0 | 18760 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alfa Refrigerators Co. | Individual | ASP | SYR | REF | 31 | INV | 66 | A | O | I | CFC | 8.7 | 8.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-03-01 | 114461 | -2201 | 112260 | 112260 | 100% | 0 | 0 | 0 | 14880 | -286 | 14594 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2000 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Dolphin Refrigerators | Individual | ASP | SYR | REF | 31 | INV | 67 | A | O | I | CFC | 8.4 | 8.4 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 113045 | 0 | 113045 | 113045 | 100% | 0 | 0 | 0 | 14696 | 0 | 14696 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b in the production of rigid foam panels at Bassam Baghdan | Individual | ASP | SYR | FOA | 32 | INV | 68 | A | O | I | CFC | 16.4 | 16.4 |  |  | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2005-12-01 | 2006-12-01 | 126862 | -2164 | 124698 | 124698 | 100% | 0 | 0 |  | 16492 | -281 | 16211 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Raed Refrigeration | Individual | ASP | SYR | REF | 32 | INV | 69 | A | O | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-09-01 | 2005-11-01 | 211800 | 0 | 211800 | 211800 | 100% | 0 | 0 | 0 | 27534 | 0 | 27534 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2000 | Investment
FIN | Germany | Project preparation/technical assistance in soil fumigants (methyl bromide) | Individual | ASP | SYR | FUM | 32 | PRP | 70 | A | O | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2001-09-01 | 2002-03-01 | 37200 | 0 | 37200 | 37200 | 100% | 0 | 0 | 0 | 4836 | 0 | 4836 | 0 | 0 | Project preparation led to project proposal for implementation, which was not accepted because of quantities of illegal MB. Syria is currently complying with its obligations. Only 8 ODP tons will still be eligeable in the future. | [13 empty] | 1997
FIN | UNIDO | Phase-out o fCFC-11 and 12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Badran and Co. | Individual | ASP | SYR | ARS | 32 | INV | 71 | A | O | I | CFC | 15.6 | 15.6 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 68640 | 0 | 68640 | 68640 | 100% | 0 | 0 |  | 8923 | -3 | 8920 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Mahmoud Hamida | Individual | ASP | SYR | ARS | 32 | INV | 72 | A | O | I | CFC | 10.5 | 10.5 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 46200 | 0 | 46200 | 46200 | 100% | 0 | 0 |  | 6006 | -3 | 6003 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 and 12 in the manufacture of hair sprays by conversion to hydrocarbon propellant at Khadji and Zahka | Individual | ASP | SYR | ARS | 32 | INV | 73 | A | O | I | CFC | 11 | 11 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 48400 | -31 | 48369 | 48369 | 100% | 0 | 0 |  | 6292 | -14 | 6278 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of insecticides by conversion to hydrocarbon propellant at Cheikh Ghazal Insecticide Plant | Individual | ASP | SYR | ARS | 32 | INV | 74 | A | O | I | CFC | 36 | 36 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 87298 | -770 | 86528 | 86528 | 100% | 0 | 0 |  | 11349 | -118 | 11231 | 0 | 0 | FIN
COM | UNIDO | Renewal of institutional strengthening (Phase II) | Individual | ASP | SYR | SEV | 33 | INS | 75 | N | T | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-12-01 | 2003-04-01 |  | 2006-12-01 |  | 195000 | 0 | 195000 | 191883 | 98.4% | 3117 | 3069 | 3000 | 25350 | 0 | 24945 | 405 | 399 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2001 | NON-INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al-Muzayek | Individual | ASP | SYR | FOA | 34 | INV | 76 | A | O | I | CFC | 33.7 | 33.7 |  |  | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-12-01 | 2004-12-01 | 106789 | 0 | 106789 | 106789 | 100% | 0 | 0 |  | 13883 | -9 | 13874 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Germany | Establishing a halon bank and umbrella project for 63 manufacturers | Individual | ASP | SYR | HAL | 34 | TAS | 77 | A | O | I | HAL | 284.5 | 284.5 | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2005-12-05 | 2007-12-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 | 0 | 20930 | 0 | 20930 | 0 | 0 | Project is completed. PCR was submitted in 2007. | [13 empty] | 1998
FIN | France | Establishing a halon bank and umbrella project for 63 manufacturers |  | ASP | SYR | HAL | 34 | TAS | 78 | A | O | I | HAL | 284.5 |  | 0 |  | 2001-07-01 | 2004-04-21 | 2004-08-01 |  | 2004-04-21 | 2005-01-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 |  | 0 | 8050 | 0 | 8050 | 0 |  | Project completed.
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Refrigeration House Co. | Individual | ASP | SYR | REF | 34 | INV | 79 | A | O | I | CFC | 17.5 | 17.5 | 0 | 0 | 2001-07-01 | 2002-11-01 | 2004-08-01 |  | 2003-09-01 | 2007-01-01 | 253653 | 0 | 253653 | 253653 | 100% | 0 | 0 | 0 | 32975 | 0 | 32975 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2001 | Investment
FIN | UNIDO | Phase-out of the use of methyl bromide in grain storage (first tranche) | Multi-Year | ASP | SYR | FUM | 34 | INV | 80 | A | O | I | MBR | 5 | 5 |  |  | 2001-07-01 | 2002-08-01 | 2002-12-01 |  | 2006-12-01 | 2008-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Financial completion in Dec 2008. | [7 empty] | 2005-12-01 | [5 empty] | 2001 | INV | 99 | 99 |  |  | Yes | N/A | N/A
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Saad Refrigeration | Individual | ASP | SYR | REF | 35 | INV | 81 | A | O | I | CFC | 20.1 | 20.1 | 0 | 0 | 2001-12-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 | 2006-06-01 | 166323 | -8826 | 157497 | 157497 | 100% | 0 | 0 | 0 | 21622 | -1147 | 20475 | 0 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2001 | Investment
FIN | UNIDO | Preparation of an investment project in the extruded polystyrene foam sector | Individual | ASP | SYR | FOA | 36 | PRP | 82 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 15000 | -80 | 14920 | 14920 | 100% | 0 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | FIN | [13 empty] | 2002 | INV
CLO | UNIDO | Preparation of an investment project in the domestic refrigeration sector | Individual | ASP | SYR | REF | 36 | PRP | 83 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 |  | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO | [13 empty] | 2002 | INV
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | SYR | REF | 36 | PRP | 84 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-09-01 | 2007-03-01 | 20000 | -6865 | 13135 | 13135 | 100% | 0 | 0 | 0 | 2600 | -892 | 1708 | 0 | 0 | Completed in 2002. Financially completed in 2007. | [13 empty] | 2002 | Investment
CLO | UNIDO | Preparation of a national ODS phase-out plan | Individual | ASP | SYR | PHA | 36 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-10-01 |  |  | 2003-05-01 | 60000 | -56845 | 3155 | 3155 | 100% | 0 | 0 |  | 7800 | -7390 | 410 | 0 | 0 | CLO | [13 empty] | 2002 | INV
ONG | UNDP | Sector phase out plan for CFCs in the refrigeration manufacturing sector (except domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 86 | A | O | I | CFC | 246.2 | 231 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-12-01 | 2009-07-01 |  |  | 1665188 | 0 | 1665188 | 1052966 | 63.23% | 612222 | 0 | 244888.8 | 191422 | 0 | 121043.9047 | 70378.0953 | 0 | Agreement reached with foam equipment supplier reached regarding balance payment. All equipment is already commissioned. Completion documentation targeted for issuance in 2009. Some 2008 invoices still to be settled in 2009. | [13 empty] | 2002 | Investment
FIN | UNIDO | Plan for elimination of CFCs in the refrigeration manufacturing sector (domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 87 | A | O | I | CFC | 51 | 51 |  |  | 2002-11-01 | 2003-06-01 | 2004-11-01 |  | 2006-12-01 | 2007-12-01 | 353100 | -527 | 352573 | 352573 | 100% | 0 | 0 |  | 40590 | -61 | 40529 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2002 | INV
FIN | UNIDO | Phasing out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polystyrene (EPS) foam for packing purposes at Shanko and Partners Co. | Individual | ASP | SYR | FOA | 38 | INV | 88 | A | O | I | CFC | 16 | 16 |  |  | 2002-11-01 | 2003-11-01 | 2005-06-01 |  | 2004-08-01 | 2004-12-01 | 132200 | 0 | 132200 | 132200 | 100% | 0 | 0 |  | 17186 | -23 | 17163 | 0 | 0 | FIN | [13 empty] | 2002 | INV
ONG | UNIDO | Phase-out of methyl bromide in grain storage (second tranche) | Multi-Year | ASP | SYR | FUM | 41 | INV | 89 | A | O | I | MBR | 29.8 | 29.8 |  |  | 2003-12-01 | 2005-02-01 | 2004-12-01 | 2009-12-01 |  |  | 351725 | 0 | 351725 | 329659 | 93.73% | 22066 | 3314 | 19000 | 26379 | 0 | 24724 | 1655 | 249 | Phosphine generators, other equipment for the PH3 application and necessary training have been delivered. Purchase of additional equipment and contract to national experts to be extended in 2009. | [9 empty] | 2006-12-01 |  |  |  | 2003 | INV | 65.7 | 65.7 |  |  | Yes | N/A | N/A
COM | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SYR | SEV | 45 | TAS | 90 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 |  | 45872 | 0 | 45872 | 39024 | 85.07% | 6848 | 0 | 5478.4 | 4128 | 0 | 3511.7517 | 616.2483 | 0 | Completed in 2008. HCFC reports submitted at 52nd ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
ONG | UNIDO | Extension of institutional strengthening: phase III | Individual | ASP | SYR | SEV | 45 | INS | 91 | N | T | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2007-04-01 | 2009-12-01 |  |  | 203823 | 0 | 203823 | 128732 | 63.16% | 75091 | 4737 | 15000 | 15287 | 0 | 9655 | 5632 | 355 | Up-dated working plan has been agreed with the NOU to speed-up the implementation and complete the project as scheduled. National experts contracts extension have been achieved. | [13 empty] | 2005 | NON-INV
COM | UNIDO | Preparation of CFC-phase-out plan including methyl bromide | Individual | ASP | SYR | PHA | 45 | PRP | 92 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-12-01 |  | 70000 | 0 | 70000 | 68100 | 97.29% | 1900 | 0 | 1 | 5250 | 0 | 5108 | 142 | 0 | Financial completion in Dec 2008. | [13 empty] | 2005 | NON-INV
ONG | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers | Individual | ASP | SYR | REF | 47 | DEM | 93 | A | O | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 | 2009-04-01 |  |  | 585961 | 0 | 585961 | 232404 | 39.66% | 353557 | 324573 | 300000 | 43947 | 0 | 17430 | 26517 | 24343 | The chillers at Le Meridien were installed in November/December 2008. The retrofitting of chillers at El-Basel Hospital is in process. The project should be completed in April 2009. | [13 empty] | 2005 | INV
ONG | UNIDO | Phase-out methyl bromide in grain fumigation (third tranche) | Multi-Year | ASP | SYR | FUM | 47 | INV | 94 | A | O | I | MBR | 70.2 | 12 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 | 2010-07-01 |  |  | 432414 | 0 | 432414 | 153291 | 35.45% | 279123 | 199649 | 50000 | 32431 | 0 | 11497 | 20934 | 14974 | Phosphine generators, other equipment for the PH3 application and necessary training have been delivered. Purchase of additional equipment and contract to national experts to be extended in 2009. | [13 empty] | 2005 | INV | 0 | 0 |  |  | Yes | N/A | N/A
ONG | UNIDO | Methyl bromide national phase-out plan (soil fumigation) | Individual | ASP | SYR | FUM | 49 | TAS | 95 | A | O | I | MBR | 48 | 21 |  |  | 2006-07-01 | 2007-12-01 | 2010-07-01 | 2010-07-01 |  |  | 240000 | 0 | 240000 | 8566 | 3.569% | 231434 | 76673 | 70000 | 21600 | 0 | 771 | 20829 | 6901 | National institution was selected and contracted. Grafted plants were distributed to farmers. Purchase of additional equipment, contract to national experts and additional training to farmers to be provided in 2009. | The General Commission for Scientific Agricultural Research (GCSAR) was selected by UNIDO in January 2008 as main national executor. However, due to changes in the management of the institution, additional time was necessary for the internal approval of the activities. GCSAR was therefore able to start the assignment for the execution of the subcontract in August 2008. The first progress report is expected by June 2009. Furthermore, UNIDO will undertake a mission to the project in the same month (June 2008) to verify the proper execution of the programme. | [12 empty] | 2006 | INV
ONG | UNIDO | National CFC phase-out plan for Syria (first tranche) | Multi-Year | ASP | SYR | PHA | 49 | INV | 96 | A | O | I | CFC | 100 | 34.3 |  |  | 2006-07-01 | 2006-10-01 | 2008-07-01 | 2009-12-01 |  |  | 430000 | 0 | 430000 | 122994 | 28.6% | 307006 | 147316 | 30000 | 32250 | 0 | 9225 | 23025 | 11049 | The bidding for the equipment is repeated and is under way. Receipt of offers is expected end Fenruary 2009. All other activities are implemented as planned. | [13 empty] | 2006 | INV | 869.7 | 541.2 |  |  | Yes | Yes | Yes
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SYR | PHA | 55 | PRP | 97 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 136250 | 0 | 136250 | 60 | 0.04404% | 136190 | 30000 | 30000 | 10219 | 0 | 5 | 10214 | 2250 | Contracts were issued for the preparation of the survey. Stake holders workshop will be organized and the HPMP is expected to be submitted at the 59th ExCom. | Subcontract for the preparation of the HPMP includes: • Assistance for policy and legislation; • Survey of HCFCs use and analysis of data collectes; • Consultation with national stackeholders in the data collection and analysis. Regarding the policy aspect, the contractor is requested to assess and analyze the institutional framework, legislation, licensing and quota system regulating consumption of ozone depleting substances in Syria with particular focus on HCFCs. The contractor is also requested to assess the current national policies on climate change, chemical management and energy policies, as well as the CFCs phase out activities and lessons learned from previous ODS phase-out activities. Expected outputs: assessment of the current status of legislation and recommendations on necessary institutional and regulatory improvements to facilitate a smooth compliance with the HCFCs phase out obligations. | [12 empty] | 2008 | NON-INV
ONG | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | ASP | SYR | PHA | 56 | INV | 98 | A | O | I | CFC | 328.7 | 0 |  |  | 2008-11-01 |  | 2009-11-30 | 2009-11-01 |  |  | 170000 | 0 | 170000 | 0 | 0% | 170000 | 0 | 30000 | 12750 | 0 | 0 | 12750 | 0 | The country’s monitoring system is under establishment. The component "Update of the vocational schools" is ongoing. | [13 empty] | 2008 | INV | 207.2 | 207.2 |  |  | Not yet confirmed | No | No
FIN | IBRD | Country programme preparation | Individual | ASP | THA | SEV | 04 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 30909 | 220344 | 251253 | 251253 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Training of Government technical staff | Individual | ASP | THA | SEV | 04 | TRA | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 50000 | 3785 | 53785 | 53785 | 100% | 0 | 0 | 0 | 6500 | 492 | 6992 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | THA | SEV | 04 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 32476 | 11678 | 44154 | 44154 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | THA | SEV | 06 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-08 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 390000 | -40 | 389960 | 389960 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed and closed. Balance returned to Multilateral Fund. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | THA | SEV | 06 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | 12195 | 132195 | 132195 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Thai-Airways non-ODS metal cleaning |  | ASP | THA | SOL | 07 | PRP | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-12-01 | 1994-06-01 |  | 1994-12-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1994-12-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recycling in MAC | Individual | ASP | THA | REF | 07 | TAS | 7 | N | O | I | CFC | 250 | 86.93 | 0 | 0 | 1992-06-01 | 1999-01-01 | 1994-12-01 |  | 2003-12-01 | 2004-03-01 | 900000 | -74881 | 825119 | 825119 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-05-01 | 1999-12-01 | 2001-12-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | Follow-up activities of the USA/Thailand/Japan conference on conservation, containment and alternatives |  | ASP | THA | SOL | 08 | TAS | 8 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 203000 | -67000 | 136000 | 136000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection Unit | Individual | ASP | THA | SEV | 09 | INS | 9 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-12-01 | 1996-03-01 |  | 2002-01-01 | 2003-05-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  | 1997-12-01 | [10 empty] | 1993 | Non-Investment
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | THA | SEV | 09 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 190000 | -10781 | 179219 | 179219 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 10 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-06-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | IBRD | Conversion to wet media blasting and aqueous cleaning solvents at Hana (BKK) Co., Ltd. | Individual | ASP | THA | SOL | 10 | INV | 12 | N | O | D |  | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-03-01 |  | 1993-12-01 | 1997-08-01 | 1010000 | -232835 | 777165 | 777165 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at GSS Array | Individual | ASP | THA | SOL | 10 | INV | 13 | N | O | D | CFC | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1994-03-01 |  | 1993-12-01 | 1997-05-01 | 316000 | -41204 | 274796 | 274796 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at Saha Union's Sriracha facility | Individual | ASP | THA | SOL | 10 | INV | 14 | N | O | R | CFC | 27.2 | 21.76 | 0 | 0 | 1993-06-01 | 1996-06-01 | 1994-03-01 |  | 1993-05-01 | 1997-05-01 | 2573000 | -472605 | 2100395 | 2100395 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at Thai Heat Exchange Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 15 | N | O | I | TCA | 11 | 11 | 0 | 0 | 1993-06-01 | 1998-08-01 | 1994-03-01 |  | 1998-08-01 | 1998-08-01 | 268000 | -14000 | 254000 | 254000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-08-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at C.I. Group Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 16 | N | O | R | TCA | 12.7 | 12.7 | 0 | 0 | 1993-06-01 | 1998-05-01 | 1994-03-01 |  | 1995-12-01 | 1998-05-01 | 277000 | 0 | 277000 | 277000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 17 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-02-01 | 823000 | -131273 | 691727 | 691727 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Kang Yong Electric Co. Ltd. (Kye) | Individual | ASP | THA | REF | 10 | INV | 18 | N | O | R | CFC | 109 | 109 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1997-12-01 | 1140000 | -256628 | 883372 | 883372 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 19 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-01-01 | 1864000 | -1269071 | 594929 | 594929 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Hitachi Consumer Products Co. Ltd. | Individual | ASP | THA | REF | 10 | INV | 20 | N | O | D | CFC | 132 | 132 | 0 | 0 | 1993-06-01 | 1997-08-01 | 1996-06-01 |  | 1996-12-01 | 1998-10-01 | 553000 | 128861 | 681861 | 681861 | 100% | 0 | 0 |  | 0 | 32939.53 | 32939.53 | 0 | 0 | Project completed. Phase I was financially completed in Aug '97. Phase II was financially completed in Oct. '98. |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 21 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-09-01 | 1996-06-01 |  | 1997-01-01 | 1996-11-01 | 989000 | -330207 | 658793 | 658793 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 22 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-01-01 | 1996-06-01 |  | 1995-12-01 | 1997-01-01 | 686000 | -85630 | 600370 | 600370 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b as a foam blowing agent at Technic Foam, Ltd. | Individual | ASP | THA | FOA | 10 | INV | 23 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1993-06-01 | 1999-09-01 | 1993-12-01 |  | 2000-01-01 | 2000-06-01 | 174000 | 0 | 174000 | 174000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR approved by the WB in Jun/2000. |  |  | 1997-12-01 | 1999-08-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | THA | SEV | 10 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 150000 | -104309 | 45691 | 45691 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | UNDP | Elimination of CFC-114 in the manufacture of extruded polystyrene foam sheet and profiles at Thermaflex Insulation Asia Co. Ltd. | Individual | ASP | THA | FOA | 11 | INV | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-07-01 |  |  | 2001-07-01 | 220000 | -220000 | 0 | 0 |  | 0 | 0 | 0 | 28600 | -28600 | 0 | 0 | 0 | Canceled in 1995. | [13 empty] | 1993 | Investment
FIN | UNDP | Elimination of the use of CFC-12 and CFC-114 in the manufacture of extruded low density polyethylene foam sheet at Mic-Cell Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 27 | A | O | I | CFC | 44 | 44 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-11-01 | 2001-12-01 | 339500 | -1726 | 337774 | 337774 | 100% | 0 | 0 | 0 | 44135 | -225 | 43910 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1994 | Investment
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | THA | SEV | 12 | PRP | 28 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 129433 | 3256 | 132689 | 132689 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Umbrella Grant Agreement signed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFC in the manufacture of laminated rigid polyurethane foam insulation panels at Modular Compound Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 29 | A | O | I | CFC | 30 | 30 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1996-12-01 | 2000-12-01 | 508000 | -3349 | 504651 | 504651 | 100% | 0 | 0 | 0 | 66040 | -435 | 65605 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at 2 companies (Tahi Poly Seal Material Industries Co. Ltd, and Food Box Co. Ltd.): Phase I | Individual | ASP | THA | FOA | 12 | INV | 30 | A | O | R | CFC | 100 | 100 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1995-03-01 |  | 1995-02-01 | 2000-12-01 | 455000 | -2639 | 452361 | 452361 | 100% | 0 | 0 | 0 | 59150 | -343 | 58807 | 0 | 0 | Completed in 1995. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of laminated rigid polyurethane foam for insulation panels at Henger Panel | Individual | ASP | THA | FOA | 12 | INV | 31 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-06-01 | 2000-12-01 | 257500 | -509 | 256991 | 256991 | 100% | 0 | 0 | 0 | 33475 | -66 | 33409 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | THA | SEV | 12 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 81302 | -68062 | 13240 | 13240 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination in the use of CFC in the manufacture of commercial refrigerators at Sanden Refrigerator Co. Ltd. | Individual | ASP | THA | REF | 13 | INV | 33 | A | O | I | CFC | 21 | 21 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1998-06-01 | 1999-12-01 | 533800 | 0 | 533800 | 533800 | 100% | 0 | 0 | 0 | 69394 | 0 | 69394 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1994 | Investment
FIN | IBRD | Conversion of electronic cleaning processes from CFC-113 to high-purity water cleaning at Team Tronics, Co. Ltd. | Individual | ASP | THA | SOL | 13 | INV | 34 | N | O | I | CFC | 12 | 11.5 | 0 | 0 | 1994-07-01 | 1998-05-01 | 1995-01-01 |  | 1999-08-01 | 1999-09-01 | 221760 | 0 | 221760 | 221760 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-12-01 | 1999-02-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible polyurethane foam at Lucky Group | Individual | ASP | THA | FOA | 13 | INV | 35 | A | O | I | CFC | 187 | 187 | 0 | 0 | 1994-07-01 | 1997-12-01 | 1995-07-01 |  | 1999-11-01 | 2003-07-01 | 605000 | -1836 | 603164 | 603164 | 100% | 0 | 0 | 0 | 78650 | -239 | 78411 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  |  |  | 1999-06-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at Ponsri | Individual | ASP | THA | FOA | 13 | INV | 36 | A | O | I | CFC | 125 | 125 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1995-07-01 |  | 1996-06-01 | 2002-03-01 | 340000 | -6035 | 333965 | 333965 | 100% | 0 | 0 | 0 | 44200 | -784 | 43416 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1994 | Investment
FIN | IBRD | Production of HFC-134a MAC parts at Nippodenso | Individual | ASP | THA | REF | 13 | INV | 37 | N | O | R | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1997-03-01 | 1995-07-01 |  | 1993-12-01 | 1997-03-01 | 141500 | 0 | 141500 | 141500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Safety and technical assistance programme to manufacturers of aerosol products | Individual | ASP | THA | ARS | 15 | TAS | 38 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1998-08-01 | 2002-03-01 | 127000 | -20 | 126980 | 126980 | 100% | 0 | 0 | 0 | 16510 | -3 | 16507 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1994 | Non-Investment
FIN | UNDP | Project preparation assistance in foam, halon and aerosol sectors | Individual | ASP | THA | SEV | 15 | PRP | 39 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | IBRD | Phase-out of ODS solvents at Thai Airways | Individual | ASP | THA | SOL | 15 | INV | 40 | N | O | I | CFC | 6 | 0 | 0 | 0 | 1994-12-01 | 1998-12-01 | 1996-06-01 |  | 1999-12-01 | 1999-12-01 | 463900 | -32600 | 431300 | 431300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-12-01 | 1999-04-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF cold cured mouldings, integral skin mouldings and rigid PUF articles at Thai Union PU Co. Ltd. | Individual | ASP | THA | FOA | 15 | INV | 41 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1996-12-01 | 2000-12-01 | 525000 | -72931 | 452069 | 452069 | 100% | 0 | 0 | 0 | 68250 | -9481 | 58769 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF slabstock and cold cured mouldings st Somboon Paisarn 85 Company Ltd. | Individual | ASP | THA | FOA | 15 | INV | 42 | A | O | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-11-01 |  | 1998-11-01 | 2000-12-01 | 225000 | -5000 | 220000 | 220000 | 100% | 0 | 0 | 0 | 29250 | -650 | 28600 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | THA | SEV | 16 | PRP | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1997-12-01 | 1997-12-01 | 267138 | 0 | 267138 | 267138 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of the use of CFCs in the manufacture of flexible PUF slabstock at Karn Yang Yeen Yong Industry Ltd. | Individual | ASP | THA | FOA | 15 | INV | 44 | A | O | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-11-01 |  | 1999-04-01 | 2000-12-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 | 0 | 22100 | 0 | 22100 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-06-01 | [9 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Packserv Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 45 | A | O | D | CFC | 155 | 155 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 474705 | -1221 | 473484 | 473484 | 100% | 0 | 0 | 0 | 61712 | -159 | 61553 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Sanit & Sons Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 46 | A | O | I | CFC | 194 | 194 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 2000-04-01 | 2002-03-01 | 582100 | 0 | 582100 | 582100 | 100% | 0 | 0 | 0 | 75673 | 0 | 75673 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  |  | 1999-09-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUF foam for thermoware at Krieng Thavorn Containers Co. Ltd. | Individual | ASP | THA | FOA | 18 | INV | 47 | A | O | I | CFC | 65 | 65 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 430000 | -32154 | 397846 | 397846 | 100% | 0 | 0 | 0 | 55900 | -4180 | 51720 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | IBRD | Conversion of plastic lens cleaning processes from CFC-113 and 1,1,1 TCA to aqueous cleaning at Crystal Lens Corporation Ltd. | Individual | ASP | THA | SOL | 18 | INV | 48 | N | O | R |  | 1.86 | 1.86 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-05-01 |  | 1996-12-01 | 1998-08-01 | 39830 | 0 | 39830 | 39830 | 100% | 0 | 0 |  | 5177.9 | 0 | 5177.9 | 0 | 0 | Project completed. |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 18 | PRP | 49 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 2002-05-01 | 3000 | 0 | 3000 | 3000 | 100% | 0 | 0 | 0 | 390 | 0 | 390 | 0 | 0 | Completed in 1996. Financially completed in 2002. | [13 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 18 | PRP | 50 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUR foam for thermoware at Raengwa Standard Industry Co. Ltd. | Individual | ASP | THA | FOA | 19 | INV | 51 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-01-01 | 2000-12-01 | 181500 | -796 | 180704 | 180704 | 100% | 0 | 0 | 0 | 23595 | -103 | 23492 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1996 | Investment
CLO | IBRD | Phase out of CFC-11 in the manufacturing of equipment for the food and beverage industry at Siam Stainless Steel Co. Ltd. | Individual | ASP | THA | REF | 19 | INV | 52 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-09-01 |  |  | 1999-03-01 | 212900 | -212900 | 0 | 0 |  | 0 | 0 |  | 27677 | -27677 | 0 | 0 | 0 | Project cancelled. Funds returned to 27th meeting. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at BKJ Engineering Co. Ltd. (BKJ) | Individual | ASP | THA | SOL | 19 | INV | 53 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-02-01 |  |  | 1998-07-01 | 186487 | -186487 | 0 | 0 |  | 0 | 0 |  | 24243.31 | -24243 | 0 | 0.31 | 0.31 | Project cancellation |  |  | 1997-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of precision cleaning processes from CFC-113 to aqueous and alternative solvent cleaning and conversion of insulator applications from CFC-113 to perfluorocarbons at Thai CRT Co. Ltd. | Individual | ASP | THA | SOL | 19 | INV | 54 | N | O | R | CFC | 5 | 5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1996-05-01 |  | 1995-09-01 | 1997-05-01 | 99440 | 0 | 99440 | 99440 | 100% | 0 | 0 |  | 12927.2 | 0 | 12927.2 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Dacron Trade Co. | Individual | ASP | THA | FOA | 20 | INV | 55 | A | O | I | CFC | 47.6 | 47.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-11-01 | 2001-12-01 | 277800 | -19551 | 258249 | 258249 | 100% | 0 | 0 | 0 | 36114 | -2541 | 33573 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siam Matee | Individual | ASP | THA | FOA | 20 | INV | 56 | A | O | I | CFC | 33.9 | 33.9 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1998-09-01 |  | 1998-09-01 | 2001-12-01 | 198000 | -13801 | 184199 | 184199 | 100% | 0 | 0 | 0 | 25740 | -1794 | 23946 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1996 | Investment
FIN | IBRD | Elimination of ozone depleting substances used in the production of household refrigerators at A.P. National Co. Ltd. | Individual | ASP | THA | REF | 21 | INV | 57 | N | O | R | CFC | 54 | 54 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1998-02-01 |  | 1997-01-01 | 1997-12-01 | 311150 | 0 | 311150 | 311150 | 100% | 0 | 0 |  | 40449.5 | 0 | 40449.5 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 58 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1997-04-01 |  | 1997-01-01 | 1998-05-01 | 673680 | 224477 | 898157 | 898157 | 100% | 0 | 0 |  | 87578.4 | 29181.85 | 116760.25 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | THA | SEV | 21 | PRP | 59 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2001-12-01 | 100000 | -40377 | 59623 | 59623 | 100% | 0 | 0 | 0 | 13000 | -5249 | 7751 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 60 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1997-01-01 | 1997-10-01 | 808234 | -94003 | 714231 | 714231 | 100% | 0 | 0 |  | 105070.42 | 10323.11 | 115393.53 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 61 | N | O | R | CFC | 436 | 436 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1997-08-01 |  | 1997-01-01 | 1998-08-01 | 1467055 | -84285 | 1382770 | 1382770 | 100% | 0 | 0 |  | 190717.15 | -5722.05 | 184995.1 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 62 | N | O | R | CFC | 89 | 89 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1998-02-01 |  | 1997-01-01 | 1998-05-01 | 316957 | -19224 | 297733 | 297733 | 100% | 0 | 0 |  | 41204.41 | -1236.1 | 39968.31 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid and integral skin polyurethane foam at Bangkok Foam Group | Individual | ASP | THA | FOA | 22 | INV | 63 | A | O | I | CFC | 90.6 | 90.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2001-12-01 | 480500 | 0 | 480500 | 480500 | 100% | 0 | 0 | 0 | 62465 | 0 | 62465 | 0 | 0 | Completed in 2001. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Asia Container | Individual | ASP | THA | FOA | 22 | INV | 64 | A | O | I | CFC | 45 | 45 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1999-11-01 | 2000-12-01 | 199000 | 0 | 199000 | 199000 | 100% | 0 | 0 | 0 | 25870 | 0 | 25870 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Investment
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | THA | FUM | 22 | PRP | 65 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-12-01 |  | 1998-05-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siriphan | Individual | ASP | THA | FOA | 22 | INV | 66 | A | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-09-01 | 2001-12-01 | 215000 | -5001 | 209999 | 209999 | 100% | 0 | 0 | 0 | 27950 | -650 | 27300 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Ocean Plastics | Individual | ASP | THA | FOA | 22 | INV | 67 | A | O | I | CFC | 82 | 82 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 287000 | -16390 | 270610 | 270610 | 100% | 0 | 0 | 0 | 37310 | -2131 | 35179 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam at Chareon Porn | Individual | ASP | THA | FOA | 23 | INV | 68 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | -29 | 93471 | 93471 | 100% | 0 | 0 | 0 | 12155 | -4 | 12151 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam (boxfoam) at Thai International | Individual | ASP | THA | FOA | 23 | INV | 69 | A | O | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | 0 | 93500 | 93500 | 100% | 0 | 0 | 0 | 12155 | 0 | 12155 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Novochem | Individual | ASP | THA | FOA | 23 | INV | 70 | A | O | I | CFC | 19.7 | 19.7 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2002-08-01 | 2004-01-01 | 196600 | 0 | 196600 | 196600 | 100% | 0 | 0 | 0 | 25558 | 0 | 25558 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 1997 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane boxfoam at Nun Charoen | Individual | ASP | THA | FOA | 23 | INV | 71 | A | O | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 | 0 | 13650 | 0 | 13650 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1997 | Investment
CLO | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (panels) at Alcan Nikkei Thai Aluminum Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 72 | N | O | R |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-11-01 |  |  | 1999-11-01 | 36500 | -36500 | 0 | 0 |  | 0 | 0 |  | 4745 | -4745 | 0 | 0 | 0 | Project cancelled. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Can Asia Products Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 73 | N | O | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-11-01 |  | 1999-10-01 | 2000-06-01 | 84300 | 0 | 84300 | 84300 | 100% | 0 | 0 |  | 10959 | 0 | 10959 | 0 | 0 | Project completed. PCR submitted to the WB in May/2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in rigid sprayfoam applications at Thermobond Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 74 | N | O | I | CFC | 10.4 | 10.4 | 0 | 0 | 1997-11-01 | 1999-04-01 | 1999-11-01 |  | 1999-07-01 | 2000-04-01 | 81400 | -4613 | 76787 | 76787 | 100% | 0 | 0 |  | 10582 | -599.69 | 9982.31 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Century Plastics | Individual | ASP | THA | FOA | 23 | INV | 75 | A | O | D | CFC | 7.3 | 7.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2001-12-01 | 56750 | -2560 | 54190 | 54190 | 100% | 0 | 0 | 0 | 7378 | -333 | 7045 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Siam Chaicharoen Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 76 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 2000-04-01 | 2000-06-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat 30 June 2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at General Injection Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 77 | N | O | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-11-01 |  | 2000-06-01 | 2000-07-01 | 120580 | 0 | 120580 | 120580 | 100% | 0 | 0 |  | 15675 | 0 | 15675 | 0 | 0 | Project Completed. PCR submitted to the WB in Jun/2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Viriyakit Plastic Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 78 | N | O | I | CFC | 27.5 | 27.5 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-11-01 |  | 1999-02-01 | 1999-06-01 | 142700 | 0 | 142700 | 142700 | 100% | 0 | 0 |  | 18551 | 0 | 18551 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in rigid spray foam applications at P.U. Foam Insulation and Trading Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 79 | N | O | I | CFC | 58.1 | 58.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 1999-08-01 | 1999-09-01 | 225400 | 0 | 225400 | 225400 | 100% | 0 | 0 |  | 29302 | 0 | 29302 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of water coolers at Sirithana | Individual | ASP | THA | REF | 23 | INV | 80 | N | O | I | CFC | 8.06 | 8.06 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-05-01 |  | 1999-08-01 | 1999-12-01 | 122593 | 0 | 122593 | 122593 | 100% | 0 | 0 |  | 15937 | 0 | 15937 | 0 | 0 | Project completed. PCR submitted to the WB in Dec/1999. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Padriew Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 81 | N | O | I | CFC | 10.24 | 10.24 | 0 | 0 | 1997-11-01 | 1999-05-01 | 1999-05-01 |  | 1999-07-01 | 1999-08-01 | 135954 | 0 | 135954 | 135954 | 100% | 0 | 0 |  | 17674 | 0 | 17674 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of Water Coolers at Siam Cooler | Individual | ASP | THA | REF | 23 | INV | 82 | N | O | I | CFC | 26.38 | 12.38 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-05-01 |  | 2000-08-01 | 2000-09-01 | 186545 | -8258 | 178287 | 178286.83 | 100% | 0.17 | 0.17 |  | 24251 | -1073.54 | 23177.46 | 0 | 0 | Project completed. PCR submitted to the World Bank 4 September 2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | P-Tech Manuchem Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 83 | A | O | I | CFC | 37.3 | 37.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2001-12-01 | 115830 | -8432 | 107398 | 107398 | 100% | 0 | 0 | 0 | 15058 | -1096 | 13962 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | J.M.T. Laboratories Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 84 | A | O | I | CFC | 36.6 | 36.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2003-11-01 | 127920 | -5082 | 122838 | 122838 | 100% | 0 | 0 | 0 | 16630 | -661 | 15969 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1997 | Investment
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Sahakarn Intercool Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 85 | N | O | I | CFC | 5.7 | 5.7 | 0 | 0 | 1997-11-01 | 2000-03-01 | 1999-05-01 |  | 2000-07-01 | 2001-12-31 | 86697 | 0 | 86697 | 86697 | 100% | 0 | 0 |  | 11271 | 0 | 11271 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Treathaboon Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 86 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 1999-02-01 | 1999-12-01 | 177750 | -20563 | 157187 | 157187 | 100% | 0 | 0 |  | 23108 | -2673.19 | 20434.81 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation for 3 projects in the foam sector | Individual | ASP | THA | FOA | 24 | PRP | 87 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | IBRD | Project preparation in the foam, halon, commercial refrigeration (end users), and solvent sectors |  | ASP | THA | SEV | 24 | PRP | 88 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Project preparation for 4 projects in the aerosol sector | Individual | ASP | THA | ARS | 24 | PRP | 89 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to LCD technology (flexible) and water based technology (integral skin) in the manufacture of polyurethane foam at Duriflex | Individual | ASP | THA | FOA | 25 | INV | 90 | A | O | I | TCA/CFC | 21.2 | 21.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2001-12-01 | 278800 | -285 | 278515 | 278515 | 100% | 0 | 0 | 0 | 36244 | -37 | 36207 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion to low index/additive technology and methylene chloride in the manufacture of flexible polyurethane boxfoam at City Foam Co., Ltd. | Individual | ASP | THA | FOA | 25 | INV | 91 | A | O | I | CFC | 42 | 42 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2000-12-01 | 156100 | 0 | 156100 | 156100 | 100% | 0 | 0 | 0 | 20293 | 0 | 20293 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | IBRD | Terminal umbrella project to convert CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at 224 small and medium sized enterprises | Individual | ASP | THA | REF | 25 | INV | 92 | N | O | I | CFC | 173 | 186.1 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2002-12-01 |  | 2004-12-01 | 2006-07-01 | 750000 | 1717315 | 2467315 | 2467315 | 100% | 0 | 0 |  | 97500 | 208904 | 306404 | 0 | 0 | Project physically and financially completed. PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol | Individual | ASP | THA | SEV | 25 | INS | 93 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-07-01 | 2000-07-01 |  | 2003-04-01 | 2003-05-01 | 266667 | -225128 | 41539 | 41539 | 100% | 0 | 0 | 0 | 34667 | -29267 | 5400 | 0 | 0 | Completed in 2003. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | UNDP | Standard Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 94 | A | O | I | CFC | 41 | 41 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 138380 | -5000 | 133380 | 133380 | 100% | 0 | 0 | 0 | 17989 | -650 | 17339 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of cold store polyurethane panels at Somerville | Individual | ASP | THA | FOA | 25 | INV | 95 | N | O | I | CFC | 18.1 | 18.13 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2001-08-01 |  | 2000-03-01 | 2000-04-01 | 141957 | -21957 | 120000 | 120000 | 100% | 0 | 0 |  | 18454.41 | -2854.41 | 15600 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Mary Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 96 | A | O | I | CFC | 40 | 40 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 136400 | -4295 | 132105 | 132105 | 100% | 0 | 0 | 0 | 17732 | -558 | 17174 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide ingrain storage (rice, maize, tapioca, feed grains and pulses) | Individual | ASP | THA | FUM | 25 | DEM | 97 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-04-01 | 2000-08-01 |  | 2003-07-01 | 2004-12-01 | 280500 | -21687 | 258813 | 258813 | 100% | 0 | 0 |  | 36465 | -2873 | 33592 | 0 | 0 | FIN |  |  |  |  | 2001-12-01
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam at J.S. Industry Co. Ltd. | Individual | ASP | THA | FOA | 26 | INV | 98 | A | O | I | CFC | 93.2 | 93.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 418800 | -15974 | 402826 | 402826 | 100% | 0 | 0 | 0 | 54444 | -2077 | 52367 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Urethane | Individual | ASP | THA | FOA | 26 | INV | 99 | A | O | I | CFC | 17.5 | 17.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2001-12-01 | 2004-01-01 | 98645 | 0 | 98645 | 98645 | 100% | 0 | 0 | 0 | 12824 | 0 | 12824 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Suwan Polymer L.P. | Individual | ASP | THA | FOA | 26 | INV | 100 | A | O | I | CFC | 58 | 58 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 298370 | -1026 | 297344 | 297344 | 100% | 0 | 0 | 0 | 38788 | -133 | 38655 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Sahakij Comos L.P. | Individual | ASP | THA | FOA | 26 | INV | 101 | A | O | I | CFC | 48.7 | 48.7 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 255850 | -11488 | 244362 | 244362 | 100% | 0 | 0 | 0 | 33261 | -1493 | 31768 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at P. Chongcharoen | Individual | ASP | THA | FOA | 26 | INV | 102 | A | O | I | CFC | 24 | 24 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 130500 | -256 | 130244 | 130244 | 100% | 0 | 0 | 0 | 16965 | -33 | 16932 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lohr Trade and Consulting PTS Ltd. | Individual | ASP | THA | FOA | 26 | INV | 103 | A | O | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 93210 | -137 | 93073 | 93073 | 100% | 0 | 0 | 0 | 12117 | -18 | 12099 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | IBRD | Programme to reduce the usage of CFC-11 and CFC-12 in chiller servicing by replacing CFC-based chillers with HFC-134a and HCFC-123 chillers at Electricity Generating Authority (EGAT) | Individual | ASP | THA | REF | 26 | INV | 104 | N | O | I | CFC | 13.2 | 13.2 | 0 | 0 | 1998-11-01 |  | 2002-12-01 |  | 2003-09-01 | 2005-04-01 | 2475000 | -2475000 | 0 | 0 |  | 0 | 0 |  | 282250 | -145520.83 | 136729.17 | 0 | 0 | Project completed. Funding of $1,198,947 was disbursed for replacing 17 chillers with the understanding that it would be paid back once energy savings were achieved. $1,198,947 was paid back in full by Thailand in 2007 directly to the Bank and was received as "other income." That amount was subsequently deducted by the Treasurer in new approvals at the 54th ExCom. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam (flexible molded, integral skin) at World Plaster/Europlan Furniture Co. | Individual | ASP | THA | FOA | 26 | INV | 105 | A | O | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 135800 | -5000 | 130800 | 130800 | 100% | 0 | 0 | 0 | 17654 | -650 | 17004 | 0 | 0 | Completed in 1999. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ohm Intertrade L.P. | Individual | ASP | THA | FOA | 26 | INV | 106 | A | O | I | CFC | 19 | 19 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2002-03-01 | 146350 | -6393 | 139957 | 139957 | 100% | 0 | 0 | 0 | 19026 | -831 | 18195 | 0 | 0 | Completed in 1999. Financially completed in 2002. | [13 empty] | 1998 | Investment
FIN | IBRD | Preparation of projects in the foam, halon, commercial refrigeration end-use and solvent sectors |  | ASP | THA | SEV | 27 | PRP | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 | 0 |  | 18330 | 0 | 18330 | 0 | 0 | Ongoing | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.E. Containers Supply Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 108 | N | O | I | CFC | 29 | 29 | 0 | 0 | 1999-03-01 | 2000-06-01 | 1999-04-01 |  | 2000-09-01 | 2000-10-01 | 181883 | -8750 | 173133 | 173133 | 100% | 0 | 0 |  | 23644.79 | -1137.5 | 22507.29 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. | [14 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from CFC-11 to water blown and HCFC-141b technology in the manufacture of rigid foam (spray) at Bangkok Integrated Trading Co. | Individual | ASP | THA | FOA | 27 | INV | 109 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-04-01 |  |  | 2001-12-31 | 117923 | -117923 | 0 | 0 |  | 0 | 0 |  | 15329.99 | -15329.99 | 0 | 0 | 0 | Project cancelled July 2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam M.P. Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 110 | N | O | I | CFC | 25.4 | 25.4 | 0 | 0 | 1999-03-01 | 2000-09-01 | 1999-04-01 |  | 2000-08-01 | 2000-10-01 | 164366 | -12500 | 151866 | 151866 | 100% | 0 | 0 |  | 21367.58 | -1625 | 19742.58 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat Nov. 2000. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam Steel International PLC | Individual | ASP | THA | FOA | 27 | INV | 111 | N | O | I | CFC | 27.1 | 27.1 | 0 | 0 | 1999-03-01 | 2001-08-01 | 2001-03-01 |  | 2001-05-01 | 2002-03-01 | 196981 | -200 | 196781 | 196781 | 100% | 0 | 0 |  | 25607.53 | -26 | 25581.53 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  |  |  | 2001-03-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid foam at Willich Sales & Contracting Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 112 | N | O | I | CFC | 16.05 | 16.05 | 0 | 0 | 1999-03-01 | 2001-03-01 | 1999-04-01 |  | 2001-08-01 | 2002-11-01 | 58630 | 0 | 58630 | 58630 | 100% | 0 | 0 |  | 7621.9 | 0 | 7621.9 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  |  |  | 2000-06-01 | [9 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of integral skin polyurethane foam and rigid moulded foam at Jennings Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 113 | N | O | I | CFC | 14.35 | 14.35 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-02-01 | 2001-10-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282.37 | 0 | 16282.37 | 0 | 0 | Project completed. PCR submitted to the WB in Sep. 01 | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparation of six projects in general foam subsector | Individual | ASP | THA | FOA | 27 | PRP | 114 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. | [13 empty] | 1999 | Investment
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Plastmate Industry Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 115 | N | O | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 2000-08-01 | 1999-04-01 |  | 2000-11-01 | 2000-11-01 | 80649 | -6500 | 74149 | 74149 | 100% | 0 | 0 |  | 10484.37 | -845 | 9639.37 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to HCFC-141b technology in the manufacture of commercial refrigerator and display cabinets at Makassan Metal Works | Individual | ASP | THA | FOA | 28 | INV | 116 | N | O | I | CFC | 9.3 | 9.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2001-05-01 | 2002-07-01 | 72819 | 0 | 72819 | 72819 | 100% | 0 | 0 |  | 9466.47 | 0 | 9466.47 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. | [5 empty] | 2004-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Thai Steel Door L.P. | Individual | ASP | THA | FOA | 28 | INV | 117 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2000. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to low index additive (LIA) technology in the manufacture of flexible polyurethane foam at P.T. Foam Chiengmai L.P. | Individual | ASP | THA | FOA | 28 | INV | 118 | A | O | I | CFC | 12.7 | 12.7 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79120 | 0 | 79120 | 79120 | 100% | 0 | 0 | 0 | 10286 | 0 | 10286 | 0 | 0 | Completed in 2000. Financially completed in 2002. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at S.K. Container Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 119 | A | O | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1999 | Investment
ONG | Sweden | Halon management programme, halon recovery, recycling and banking | Halon banking | ASP | THA | HAL | 29 | TAS | 120 | A | O | I |  | 135.9 |  | 0 |  | 1999-11-01 | 2004-11-01 | 2003-12-01 | 2009-12-31 |  |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | The project is now overall progressing well (after the initial delayed start-up and then project revision). There has been a slight delay in the component on the demonstration projects only. This is said to be due to the current financial and political uncertainty in Thailand which makes it more difficult to find interested enterprises. NPC has recently started implementation of the first six conversion demonstrations, while they continue their efforts to identify another six potential beneficiaries. Public awareness events are being organized to announce and document the start of these demonstrations. NPC, the NOU, and TMB have been coordinating on the dissemination of this information. The project is expected to be completed by Dec 2009. Sweden disbursed the full project amount to the WB already in year 2000. |  | 1999 | [11 empty] | 1999
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | THA | HAL | 29 | TAS | 121 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2006-12-01 | 2003-12-01 | 2009-12-01 |  |  | 220750 | 0 | 220750 | 11223.53 | 5.084% | 209526.47 | 209526.47 | 139394 | 28697.5 | 0 | 1459.05 | 27238.45 | 27238.45 | Four seminars in the year 2008 for private and government sectors were organized. Electronic clearinghouse set up on the halon website for halon exchange among the users and suppliers instead of physical halon banking. All remaining activities to be completed in 2009. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to LIA (flexible), to water-based technology (flexible molded, structural and integral skin) and HCFC-141b technology (rigid) at Great Foam Products, Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 122 | A | O | I | CFC | 22.1 | 22.1 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 231843 | -23 | 231820 | 231820 | 100% | 0 | 0 | 0 | 30140 | -3 | 30137 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.S. Plastic Container L.P. | Individual | ASP | THA | FOA | 29 | INV | 123 | A | O | I | CFC | 9.7 | 9.7 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 75951 | 0 | 75951 | 75951 | 100% | 0 | 0 | 0 | 9874 | 0 | 9874 | 0 | 0 | Completed in 2001. Financially completed in 2004. | [13 empty] | 1999 | Investment
FIN | France | No clean process improvement training for electronic assemblers |  | ASP | THA | SOL | 29 | TRA | 124 | A | O | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-01-18 | 2001-12-01 |  | 2002-12-01 | 2002-12-01 | 118140 | -2140 | 116000 | 116000 | 100% | 0 |  | 0 | 5907 | -107 | 5800 | 0 |  | Projet achevé
FIN | IBRD | Preparation of projects in halon non-recycling |  | ASP | THA | HAL | 30 | PRP | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | ASP | THA | FUM | 30 | TAS | 126 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -9096 | 15904 | 15904 | 100% | 0 | 0 | 0 | 3250 | -1182.48 | 2067.52 | 0 | 0 | Project financially completed. | $ 9,096 plus $ 1,182 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | IBRD | Preparation of projects in the rigid polyurethane subsector |  | ASP | THA | FOA | 30 | PRP | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | ASP | THA | SOL | 30 | PRP | 128 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 21 | PRP | 129 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 16250 | 0 | 16250 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of commercial refrigeration equipment at Arco Industry Co., Ltd | Individual | ASP | THA | FOA | 28 | INV | 130 | N | O | I | CFC | 16.8 | 16.32 | 0 | 0 | 1999-07-01 | 2001-12-31 | 2002-02-01 |  | 2001-09-01 | 2002-02-01 | 131544 | -3759 | 127785 | 127785 | 100% | 0 | 0 |  | 17100.72 | -488.67 | 16612.05 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. | [5 empty] | 2004-02-01 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | Individual | ASP | THA | FOA | 31 | INV | 131 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-05-01 | 2005-02-01 | 51795 | -14902 | 36893 | 36893 | 100% | 0 | 0 |  | 6733.35 | -1936.91 | 4796.09 | 0.35 | 0.35 | Project completed and PCR under review. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Siam Cargo Containers | Individual | ASP | THA | FOA | 31 | INV | 132 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-07-01 | 2005-03-01 | 2003-08-01 |  | 2004-08-01 | 2005-03-01 | 177741 | -79622 | 98119 | 98119 | 100% | 0 | 0 |  | 23106.33 | -10350.86 | 12755.47 | 0 | 0 | Project physically and financially completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (sprayfoam and blocks) at Isotech | Individual | ASP | THA | FOA | 32 | INV | 133 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2004-01-01 |  | 2001-11-01 | 2002-01-01 | 144943 | 0 | 144943 | 144943 | 100% | 0 | 0 |  | 18842.59 | 0 | 18842.59 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/World Bank. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | Individual | ASP | THA | HAL | 32 | INV | 134 | N | O | I | HAL | 436 | 717.4 | 0 | 0 | 2000-12-01 | 2003-10-01 | 2004-02-01 | 2009-12-01 |  |  | 568000 | 0 | 568000 | 238887 | 42.06% | 329113 | 329113 | 100000 | 72480 | 0 | 30483.32 | 41996.68 | 41996.68 | Halon management team conducted a survey of halon-1301 from 57 users and invited them to participate in a 12 firm conversion demo. project. According to proposed eligibility criteria stated in TOR, NOU had difficulty in finding interested users, thus criteria adjusted and 7 companies became interested to participate. However, 2 of 7 halon-1301 users have already converted without TA to develop an action plan. It is expected that the conversion of five remaining halon-1301 users will be completed by Dec. 09. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a methyl bromide phaseout strategy | Individual | ASP | THA | FUM | 33 | TAS | 135 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2003-12-01 | 2002-09-01 |  | 2004-12-01 | 2005-03-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Project preparation completed. Strategy approved at the 44th ExCom. | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol |  | ASP | THA | SEV | 35 | INS | 136 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-12-31 | 2003-07-01 |  | 2003-07-01 | 2004-12-01 | 0 | 225128 | 225128 | 225128 | 100% | 0 | 0 |  | 0 | 29267 | 29267 | 0 | 0 | Project was completed and a terminal report and extension request was submitted to ExCom in Jul. 03. Funding was advanced to cover costs which was not received until 43rd ExCom. | [13 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | THA | PHA | 35 | INV | 137 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2002-12-01 |  | 2002-12-01 |  | 540000 | 0 | 540000 | 540000 | 100% | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | Implementation of project activities under this tranche completed since 2004. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | THA | PHA | 37 | INV | 138 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2003-12-01 |  | 5194380 | 0 | 5194380 | 4934794 | 95% | 259586 | 259586 | 259586 | 459494 | 0 | 436531.06 | 22962.94 | 22962.94 | Implementation of MAC sector almost completed. Financial subsidy for additional 300 MAC basic tools underway and expected to be completed Apr. 09. Supply of 209 Refrigerant Identifiers to government expected to finish by Sep 09. Supply of 250 RIs to private inspection centers expected to finish in Oct 09. Disbursement for these subcomponents expected to begin in Jul 09. RSS Subproject: Procurement of 52 sets of R&R machines for government training centers expected to be finished Jun 09 and disbursement expected to begin in May 09. 11 series of training for service technicians completed in Dec. 08. This component is to be completed Apr 09. Financial subsidy for 1,350 servicing shops all over the country expected to be completed end 2009. | [13 empty] | 2002 | INV | 3107.5 | 2180 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | THA | SEV | 40 | INS | 139 | N | T | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-08-01 | 2005-08-01 | 346667 | 0 | 346667 | 346667 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Remaining budget was used for public awareness activities e.g. ozone road show, publications, etc. These PR activities were conducted to promote and ensure sustainable ODS phaseout. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: 2003 annual programme | Multiyear | ASP | THA | PHA | 41 | INV | 140 | N | O | I | CFC | 486 | 486 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-03-01 |  | 4011846 | 0 | 4011846 | 2825038 | 70.42% | 1186808 | 1186808 | 1186808 | 353066 | 0 | 248619.92 | 104446.08 | 104446.08 | Implementation of MAC sector almost completed. Financial subsidy for additional 300 MAC basic tools underway and expected to be completed Apr. 09. Supply of 209 Refrigerant Identifiers to government expected to finish by Sep 09. Supply of 250 RIs to private inspection centers expected to finish in Oct 09. Disbursement for these subcomponents expected to begin in Jul 09. RSS Subproject: Procurement of 52 sets of R&R machines for government training centers expected to be finished Jun 09 and disbursement expected to begin in May 09. 11 series of training for service technicians completed in Dec. 08. This component is to be completed Apr 09. Financial subsidy for 1,350 servicing shops all over the country expected to be completed end 2009. | [13 empty] | 2003 | INV | 2818.5 | 1870 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | THA | PHA | 42 | INV | 141 | N | O | I | CFC | 486 | 486 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 |  | 1315400 | 0 | 1315400 | 855981.36 | 65.07% | 459418.64 | 459418.64 | 459418.64 | 118386 | 0 | 77038.32 | 41347.68 | 41347.68 | Implementation of MAC sector almost completed. Financial subsidy for additional 300 MAC basic tools underway and expected to be completed Apr. 09. Supply of 209 Refrigerant Identifiers to government expected to finish by Sep 09. Supply of 250 RIs to private inspection centers expected to finish in Oct 09. Disbursement for these subcomponents expected to begin in Jul 09. RSS Subproject: Procurement of 52 sets of R&R machines for government training centers expected to be finished Jun 09 and disbursement expected to begin in May 09. 11 series of training for service technicians completed in Dec. 08. This component is to be completed Apr 09. Financial subsidy for 1,350 servicing shops across country expected to be completed end 2009. | [13 empty] | 2004 | INV | 2332.5 | 1320.1 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National methyl bromide phase-out plan (first tranche) | Multiyear | ASP | THA | FUM | 44 | INV | 143 | N | O | I | MBR | 58.7 | 58.7 | 0 | 0 | 2004-12-01 | 2006-12-01 | 2006-12-01 | 2009-12-01 |  |  | 546991 | 0 | 546991 | 253238.31 | 46.3% | 293752.69 | 293752.69 | 293752 | 41024 | 0 | 18992.72 | 22031.28 | 22031.28 | Development of Management Information System (MIS) is 80% completed and MIS training for plant quarantine stations is expected by Q1 of 2009. Lab for insect resistance control unit has been fully operational since Sep 08 and testing on resistance conducted across Thailand. Train-the-Trainer Workshop organized in May 2008 and training equipment will be procured in 2009. Investment components for MB users (type 1) and fumigators (type 3) are on-going. Financial assistance for storage facilities that do not have in-house fumigation will be conducted in 2009. | [13 empty] | 2004 | INV | 183.1 | 181.4 | 0 | 0 | Yes | Yes | N/a
ONG | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | THA | PHA | 45 | INV | 144 | N | O | I | CFC | 962.9 | 962.9 | 0 | 0 | 2005-04-01 |  | 2006-04-01 | 2009-12-01 |  |  | 1330400 | 0 | 1330400 | 0 | 0% | 1330400 | 1330400 | 1330400 | 111736 | 0 | 0 | 111736 | 111736 | Implementation of MAC sector was almost completed. Financial subsidy for additional 300 MAC basic tools are underway. It is expected that it will be completed by end of April 2009. Implementation of refrigeration servicing sector is progressing well. Eleven series of training for service technicians were completed in December 2008. It was plan that this component will be completed by mid of March 2009. Financial subsidy for the number of 1,350 servicing shops all over the country is expected to be completed by the end of 2009. | [13 empty] | 2005 | INV | 1370 | 1192.1 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Renewal of institutional strengthening project (phase IV) | Individual | ASP | THA | SEV | 46 | INS | 145 | N | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-09-01 | 2007-10-01 | 346668 | 0 | 346668 | 346668 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Phase IV of the IS project successfully completed. IS renewed at the 52nd ExCom. | [13 empty] | 2005 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2006 annual implementation plan | Multiyear | ASP | THA | PHA | 48 | INV | 146 | N | O | I | CFC | 243 | 243 | 0 | 0 | 2006-04-01 |  | 2007-04-01 | 2010-06-01 |  |  | 851600 | 0 | 851600 | 0 | 0% | 851600 | 851600 | 851600 | 68644 | 0 | 0 | 68644 | 68644 | Implementation of MAC sector was almost completed. Financial subsidy for additional 300 MAC basic tools are underway. It is expected that it will be completed by end of April 2009. Implementation of refrigeration servicing sector is progressing well. Eleven series of training for service technicians were completed in December 2008. It was plan that this component will be completed by mid of March 2009. Financial subsidy for the number of 1,350 servicing shops all over the country is expected to be completed by the end of 2009. | [13 empty] | 2006 | INV | 1126.6 | 453.7 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National methyl bromide phase-out plan (second tranche) | Multiyear | ASP | THA | FUM | 50 | INV | 147 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 | 2009-12-01 |  |  | 1412214 | 0 | 1412214 | 44696 | 3.165% | 1367518 | 1367518 | 1058778 | 105916 | 0 | 3352.19 | 102563.81 | 102563.81 | Development of Management Information System (MIS) is 80% completed and MIS training for plant quarantine stations is expected by Q1 of 2009. Lab for insect resistance control unit has been fully operational since Sep 08 and testing on resistance conducted across Thailand. Train-the-Trainer Workshop organized in May 2008 and training equipment will be procured in 2009. Investment components for MB users (type 1) and fumigators (type 3) are on-going. Financial assistance for storage facilities that do not have in-house fumigation will be conducted in 2009. | [13 empty] | 2006 | INV | 146.6 | 146 | 0 | 0 | Yes | Yes | N/a
ONG | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | THA | SEV | 52 | INS | 148 | N | T | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-06-30 | 2009-06-30 |  |  | 346668 | 0 | 346668 | 218672.49 | 63.08% | 127995.51 | 127995.51 | 127995 | 26000 | 0 | 16400.37 | 9599.63 | 9599.63 | PR activities conducted intensively to inform the public about the ban on imports of CFC and (virgin) halon in 2010. Capacity of NOU and government agencies has been continuously enhanced. NOU conducted a meeting with CFC importers to set import quota. Dept. of Customs continued monitoring CFC imports and seized 42.36 MT of smuggled ODS in 2008; NOU published a booklet to provide information on ozone layer protection, alternative technologies and regulations and distributed to 2,500 copies to schools and 80 government organizations; Consultant hired in Jun 08 to set up an MIS; Ozone Day celebrated with information dissemination thru various media. | [13 empty] | 2007 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: 2007 annual implementation plan | Multiyear | ASP | THA | PHA | 53 | INV | 149 | N | O | I | CFC | 209 | 209 | 0 | 0 | 2007-11-01 |  | 2009-11-30 | 2010-06-01 |  |  | 550000 | 0 | 550000 | 0 | 0% | 550000 | 550000 | 470487 | 49500 | 0 | 0 | 49500 | 49500 | Implementation of MAC sector almost completed. Financial subsidy for additional 300 MAC basic tools underway and expected to be completed Apr. 09. Supply of 209 Refrigerant Identifiers to government expected to finish by Sep 09. Supply of 250 RIs to private inspection centers expected to finish in Oct 09. Disbursement for these subcomponents expected to begin in Jul 09. RSS Subproject: Procurement of 52 sets of R&R machines for government training centers expected to be finished Jun 09 and disbursement expected to begin in May 09. 11 series of training for service technicians completed in Dec. 08. This component is to be completed Apr 09. Financial subsidy for 1,350 servicing shops all over the country expected to be completed end 2009. | [13 empty] | 2006 | INV | 917.6 | 300.7 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2008 annual implementation plan | Multiyear | ASP | THA | PHA | 55 | INV | 150 | N | O | I | CFC | 208 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-31 | 2010-11-01 |  |  | 550000 | 0 | 550000 | 0 | 0% | 550000 | 550000 | 50000 | 49500 | 0 | 0 | 49500 | 49500 | Implementation of MAC sector almost completed. Financial subsidy for additional 300 MAC basic tools underway and expected to be completed Apr. 09. Supply of 209 Refrigerant Identifiers to government expected to finish by Sep 09. Supply of 250 RIs to private inspection centers expected to finish in Oct 09. Disbursement for these subcomponents expected to begin in Jul 09. RSS Subproject: Procurement of 52 sets of R&R machines for government training centers expected to be finished Jun 09 and disbursement expected to begin in May 09. 11 series of training for service technicians completed in Dec. 08. This component is to be completed Apr 09. Financial subsidy for 1,350 servicing shops all over the country expected to be completed end 2009. | [13 empty] | 2007 | INV | 709.6 | 0 | 0 | 0 |  | No | No
ONG | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | THA | PHA | 55 | PRP | 151 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 | 2010-09-01 |  |  | 195000 | 0 | 195000 | 0 | 0% | 195000 | 195000 | 64980 | 14625 | 0 | 0 | 14625 | 14625 | Preparation of National HCFC phase-out project is underway. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
COM | UNEP | Institutional strengthening project (phase I) | Individual | EUR | TKM | SEV | 46 | INS | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-10-01 | 2008-07-01 |  | 2008-02-01 |  | 115693 | 0 | 115693 | 83278.81 | 71.98% | 32414.19 | 32414 | 32414.19 | 0 | 0 | 0 | 0 | 0 | Project completed in February 2008. Renewal requested at 54th ExCom meeting (April 2008). | [13 empty] | 2005 | Non Investment
ONG | UNIDO | Preparation of a project for the elimination of methyl bromide in the post harvest sector | Individual | EUR | TKM | FUM | 53 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 | 2009-09-01 |  |  | 20000 | 0 | 20000 | 1543 | 7.715% | 18457 | 1017 | 15000 | 1500 | 0 | 116 | 1384 | 76 | The project is under preparation and is planned for submission to the 2nd meeting in 2009. | The project will be submittted instead to the 3rd meeting of the ExCom in 2009 as recently decided by the government. By now 88% of the project funds have been disbursed. Planned date of completion is revised to September 2009. | [12 empty] | 2007 | NON-INV
ONG | UNEP | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 |  | 2009-12-01 |  |  | 92000 | 0 | 92000 | 35370 | 38.45% | 56630 | 55200 | 56630 | 0 | 0 | 0 | 0 | 0 | SSFA signed in July 2008. First installement paid in November due to banking difficulties by NOU with opening an account. Currently NOU is fully staffed and operational. Art 7 data and CP Progress report for 2007 have been submitted. NOU actively participating in the ECA network activities. NOU participated in the ECA network thematic meeting on implementation of TPMPs in Russian-speaking countries. NOU initiated preparation for ECA network meeting on ODS legislation to be held in March 2009 in Turkmenistan. | [13 empty] | 2008
ONG | UNIDO | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 4 | N | T | I |  | 0 | 0 |  |  | 2008-04-01 |  | 2009-03-31 | 2009-12-01 |  |  | 15000 | 0 | 15000 | 0 | 0% | 15000 | 0 | 15000 | 1125 | 0 | 0 | 1125 | 0 | The purchase of recovery equipment was proposed by the NOU. The specification is under preparation and planned for 2Q 2009. | [13 empty] | 2008 | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TKM | PHA | 55 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 | 2009-12-01 |  |  | 85000 | 0 | 85000 | 5502 | 6.473% | 79498 | 1957 | 50000 | 6375 | 0 | 413 | 5962 | 147 | Consultant was selected for HCFC survey and the workshop in process for HPMP preparation. | Yes. Draft proposal is to the National Assembly is in preparation. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | TLS | SEV | 56 | INS | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | TOG | SEV | 6 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-02-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1992 | Non Investment
FIN | UNEP | Establishment of the National Ozone Office | Individual | AFR | TOG | SEV | 23 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-07-01 | 2004-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNEP | Development of a refrigerant management plan | RMP | AFR | TOG | REF | 35 | PRP | 3 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-08-01 |  | 2002-10-01 | 2007-02-01 | 60000 | -20927 | 39073 | 39073 | 100% | 0 | 0 | 0 | 7800 | -2721 | 5079.49 | -0.49 | 0 | Project financially completed. | $ 20,927 plus $ 2,721 PSC returned ExCom 46 | [12 empty] | 2001 | Non Investment
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | TOG | REF | 36 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. | [13 empty] | 2002 | Investment
FIN | UNDP | Implementation of the RMP: monitoring of the activities included in the RMP | RMP-Component | AFR | TOG | REF | 38 | TAS | 5 | A | O | I | CFC | 1.3 | 1.3 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 |  | 2007-12-01 | 2008-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2007. Financially completed in 2008. | [13 empty] | 2002 | Non-Investment
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | AFR | TOG | SEV | 37 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-08-01 | 2007-02-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration sector | RMP-Component | AFR | TOG | REF | 38 | TAS | 6 | A | O | I | CFC | 9.7 | 9.7 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2006-11-01 |  | 2007-12-01 |  | 110000 | 0 | 110000 | 97964 | 89.06% | 12036 | 0 | 9628.8 | 14300 | 0 | 12735.32 | 1564.68 | 0 | Completed in 2007. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Implementation of the RMP: recovery and recycling of refrigerants | RMP-Component | AFR | TOG | REF | 38 | TAS | 7 | A | O | I | CFC | 13.3 | 13.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  | 2007-12-01 |  | 150000 | 0 | 150000 | 149404 | 99.6% | 596 | 0 | 476.8 | 19500 | 0 | 19422.52 | 77.48 | 0 | Completed in 2007. | [13 empty] | 2002 | Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | AFR | TOG | REF | 38 | TRA | 8 | A | O | I | CFC | 5.7 | 5.7 | 0 | 0 | 2002-11-01 | 2003-03-01 | 2004-05-01 |  | 2006-12-01 | 2007-02-01 | 64000 | 0 | 64000 | 64000 | 100% | 0 | 0 | 0 | 8320 | 0 | 8320 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
FIN | UNEP | Implementation of the RMP: training of customs officers | Individual | AFR | TOG | REF | 38 | TRA | 9 | A | O | I | CFC | 3.8 | 3.8 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-05-01 |  | 2006-12-01 | 2008-02-01 | 43500 | 0 | 43500 | 42497.3 | 97.69% | 1002.7 | 0 | 0 | 5655 | 0 | 5524.649 | 130.351 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | TOG | SEV | 44 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2006-12-01 |  | 2007-09-07 |  | 60667 | 0 | 60667 | 48208.4 | 79.46% | 12458.6 | 0 | 12458.6 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | TOG | PHA | 48 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-06-01 |  | 18000 | 0 | 18000 | 13000 | 72.22% | 5000 | 0 | 5000 | 2340 | 0 | 1690 | 650 | 0 | Project completed in June 2008 after submission of TPMP document | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | TOG | PHA | 48 | PRP | 13 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 |  | 12000 | 0 | 12000 | 8288 | 69.07% | 3712 | 0 | 3712 | 900 | 0 | 621.6 | 278.4 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | TOG | SEV | 50 | INS | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-09-01 | 2008-11-01 | 2009-11-01 |  |  | 60666 | 0 | 60666 | 25667.98 | 42.31% | 34998.02 | 0 | 34998.02 | 0 | 0 | 0 | 0 | 0 | First payment don in September 2008 | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | TAS | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-31 | 2010-03-31 |  |  | 89000 | 0 | 89000 | 62708.2 | 70.46% | 26291.8 | 26000 | 26291.8 | 11570 | 0 | 8152.066 | 3417.934 | 3380 | Training of 25 technicians as trainers in October 2008 | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | INV | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 | 2010-03-01 | 2010-03-01 |  |  | 95000 | 0 | 95000 | 261 | 0.2747% | 94739 | 0 | 18947.8 | 8550 | 0 | 23.49 | 8526.51 | 0 | Consultant mission carried out late 2008. Second bidding process for purchase of equipment to be closed Feb 09. Equipment, tools and refrigerant gas are expected to arrive in country 1st quarter 2009. Consultant mission planned to coincide with this and launch of the excellence centre and start of program for recovery systems. Expenditures will be reflected in 2009. Second tranche to be approved at 57th ExCom. | [13 empty] | 2008 | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | TOG | PHA | 56 | PRP | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | Project newly approved | [13 empty] | 2008
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | TOG | SEV | 56 | INS | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-31 | 2010-12-31 |  |  | 60666 | 0 | 60666 | 0 | 0% | 60666 | 0 | 60666 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TON | REF | 36 | TAS | 1 | A | O | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 | 2009-06-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | Regs have passed the Tongan Law Committee and now awaiting consideration by Cabinet. Plan of Action sent to Ozone Sec in April 2009. |  | 2002
COM | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TON | SEV | 36 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 |  | 19700 | 0 | 19700 | 11820 | 60% | 7880 | 0 | 7880 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2002 | Non Investment
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TON | REF | 36 | TAS | 3 | A | O | I |  | 0.9 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 |  | 30000 | 0 | 30000 | 20080 | 66.93% | 9920 | 0 | 9920 | 3900 | 0 | 0 | 3900 | 3900 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TON | SEV | 49 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 |  | 2007-03-31 |  | 2008-12-01 |  | 6566 | 0 | 6566 | 0 | 0% | 6566 | 0 | 6566 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TON | SEV | 53 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008 | [13 empty] | 2007 | Non Investment
FIN | UNDP | Training of Government technical staff and preliminary work on country programme | Individual | LAC | TRI | SEV | 04 | TRA | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1995-07-01 | 1997-12-01 | 53800 | 102 | 53902 | 53902 | 100% | 0 | 0 | 0 | 6994 | 13 | 7007 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
CLO | IBRD | Preparation of investment projects (1991) |  | LAC | TRI | SEV | 04 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 86843 | -86843 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Country programme preparation | Individual | LAC | TRI | SEV | 06 | CPG | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1995-07-01 | 1997-12-01 | 25000 | 1200 | 26200 | 26200 | 100% | 0 | 0 | 0 | 3250 | 156 | 3406 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | TRI | SEV | 20 | INS | 4 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 2000-12-01 | 2003-06-01 | 66000 | -5223 | 60777 | 60777 | 100% | 0 | 0 | 0 | 8580 | -679 | 7901 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  |  |  | 1999-12-01 | [9 empty] | 1996 | Non-Investment
FIN | UNDP | Project preparation in the aerosol, refrigeration and solvent sectors | Individual | LAC | TRI | SEV | 21 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 40000 | -4596 | 35404 | 35404 | 100% | 0 | 0 | 0 | 5200 | -597 | 4603 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1997 | Investment
CLO | IBRD | Country programme preparation |  | LAC | TRI | SEV | 04 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 107561 | -107561 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Implementation of the refrigerant management plan: Training the trainers of technicians in the refrigeration sector | Individual | LAC | TRI | REF | 23 | TRA | 7 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-02 |  | 2002-09-01 | 2003-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | USA | MAC demonstration project |  | LAC | TRI | REF | 23 | DEM | 8 | A | O | I | CFC | 10 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1999-05-01 | 2000-05-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1997
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | TRI | REF | 23 | TAS | 9 | A | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 213990 | -12116 | 201874 | 201874 | 100% | 0 | 0 | 0 | 27819 | -1575 | 26244 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNEP | Implementation of the refrigerant management plan: Training in monitoring and controlling of ODSs | Individual | LAC | TRI | REF | 23 | TRA | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-02-01 |  | 2002-04-01 | 2003-05-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 | 0 | 0 | 3445 | 0 | 3445 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNDP | Project preparation for 1 project in the aerosol sector | Individual | LAC | TRI | ARS | 24 | PRP | 11 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1998 | Investment
FIN | UNDP | Project to phaseout use of CFCs in aerosol filling at Hand Arnold Industries Limited (HAIL) | Individual | LAC | TRI | ARS | 25 | INV | 12 | A | O | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2004-12-01 | 2005-10-01 | 119570 | 0 | 119570 | 119570 | 100% | 0 | 0 | 0 | 15544 | 0 | 15544 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 1998 | Investment
COM | UNDP | Renewal of institutional strengthening (Phase II) | Individual | LAC | TRI | SEV | 32 | INS | 13 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 |  | 44000 | 0 | 44000 | 39243 | 89.19% | 4757 | 0 | 3805.6 | 5720 | 0 | 5101.59 | 618.41 | 0 | Completed in 2003. | [13 empty] | 2000 | Non-Investment
FIN | UNDP | Project preparation for the RMP update | Individual | LAC | TRI | REF | 38 | PRP | 14 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2002-12-01 | 2003-12-01 |  | 2003-07-01 | 2006-06-01 | 13500 | -3905 | 9595 | 9595 | 100% | 0 | 0 | 0 | 1755 | -508 | 1247 | 0 | 0 | Completed in 2003. Financially completed in 2006. | [13 empty] | 2002 | Investment
COM | UNDP | Extension of institutional strengthening project (phase 3) | Individual | LAC | TRI | SEV | 38 | INS | 15 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2006-12-01 |  | 57200 | 0 | 57200 | 53096 | 92.83% | 4104 | 0 | 3283.2 | 7436 | 0 | 6902.48 | 533.52 | 0 | Completed in 2006. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | LAC | TRI | PHA | 40 | INV | 16 | N | O | I | CFC | 42.9 | 42.9 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2006-03-01 |  | 2006-12-01 |  | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 16500 | 0 | 16500 | 0 | 0 | Completed in 2006. | [13 empty] | 2003 | Investment | 77 | 77 |  |  | Yes | Yes | yes
COM | UNDP | Extension of institutional strengthening project (phase IV) | Individual | LAC | TRI | SEV | 44 | INS | 18 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-05-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2008. Trinidad and Tobago is in compliance with its obligations under the Montreal Protocol. The NOU supports the implementation of the TPMP. Active public awareness campaign. The ODS licensing system is well functioning. | [13 empty] | 2004 | Non-Investment
ONG | Canada | Technical assistance to phase out the use of methyl bromide | Individual | LAC | TRI | FUM | 49 | TAS | 19 | A | O | I | MBR | 0.1 |  | 0 |  | 2006-07-01 |  | 2008-01-01 | 2009-07-09 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 |  | 0 | 3900 | 0 | 0 | 3900 |  | Canada will ask for cancellation of project at 58th meeting and return all related funds. Country NOU has agreed to cancellation as it has not been possible for government to sign agreement for over 18 months. |  | 2006 | [11 empty] | 2006 | Investment
COM | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | LAC | TRI | PHA | 49 | INV | 20 | N | O | I | CFC | 34.1 | 34.1 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2008-12-01 |  | 2008-12-01 |  | 240000 | 0 | 240000 | 121568 | 50.65% | 118432 | 0 | 94745.6 | 18000 | 0 | 9117.6 | 8882.4 | 0 | Completed in 2008. International workshop about new refrigerant blends in July 2008 with 50 participants marked the official closure of the TPMP in T&T. Most funds were spent, but final expenditures will be reflected in 2009. | [13 empty] | 2006 | Investment | 34.1 |  |  |  | Latest | Latest | Latest
ONG | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | TRI | SEV | 50 | INS | 21 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2008-11-01 | 2009-06-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 24000 | 4500 | 0 | 0 | 4500 | 0 | See phase 4 - activities continued in phase V. | [13 empty] | 2006 | Non-Investment
COM | UNDP | Audit for an ongoing terminal phase-out management plan | Individual | LAC | TRI | PHA | 51 | TAS | 22 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-10-01 | 2008-03-01 |  | 2008-12-01 |  | 20000 | 0 | 20000 | 12739 | 63.7% | 7261 | 0 | 5808.8 | 1500 | 0 | 955.425 | 544.575 | 0 | Completed in 2008. International expert mission to T&T in October 2008. Independent report will be submitted for the consideration of ExCom 57. Final invoices still to be settled in 2009. | [13 empty] | 2007 | Non-Investment | 0 |  |  |  | NA | NA | NA
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | TRI | PHA | 55 | PRP | 23 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 6375 | 0 | 0 | 6375 | 0 | Local and international consultants have been identified. The inception workshop is expected to take place in early 2009. | [13 empty] | 2008 | Investment
COM | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TTR | REF | 36 | TAS | 1 | A | O | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | Regulations established August 2004. Customs training workshop complete. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TTR | REF | 36 | TAS | 2 | A | O | I |  | 1.1 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 |  | 30000 | 0 | 30000 | 17484 | 58.28% | 12516 | 0 | 12516 | 3900 | 0 | 0 | 3900 | 3900 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TTR | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 |  | 34000 | 0 | 34000 | 26600 | 78.24% | 7400 | 0 | 7400 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2002 | Non Investment
COM | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TTR | SEV | 49 | INS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-07-01 |  | 2007-03-31 |  | 2008-12-01 |  | 11333 | 0 | 11333 | 0 | 0% | 11333 | 0 | 11333 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TTR | SEV | 53 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 | 2009-12-01 |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during February 2008. First disbursement will start after country receive final payment of previous IS phase from SPREP. | [13 empty] | 2007 | Non Investment
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | TUN | SEV | 04 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 64748 | -33533 | 31215 | 31215 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 04 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 58363 | 105240 | 163603 | 163603 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | TUN | SEV | 06 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 50000 | -27623 | 22377 | 22377 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical seminar and conversion to non-CFC technology in aerosol sector | Individual | AFR | TUN | ARS | 07 | INV | 4 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1993-06-01 |  | 1998-03-01 | 1998-06-01 | 239995 | 50000 | 289995 | 289995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998 |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance and demonstration of non-CFC technology in rigid and flexible foam production | Individual | AFR | TUN | FOA | 07 | INV | 5 | N | O | I | CFC | 45 | 45 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-02-01 |  | 1998-03-01 | 1998-06-01 | 218354.28 | 0 | 218354.28 | 218354.28 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of low-CFC and non-CFC in rigid foams in refrigeration insulation at Tabrid | Individual | AFR | TUN | FOA | 07 | INV | 6 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-06-01 |  | 1997-07-01 | 1998-06-01 | 258844 | 0 | 258844 | 258844 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final PCR provided in June 1998 |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Maintenance of domestic, commercial and industrial refrigeration systems | Individual | AFR | TUN | REF | 07 | TAS | 7 | N | O | I | CFC | 42 | 42 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1997-06-01 |  | 1997-12-01 | 1998-06-01 | 32836 | 300000 | 332836 | 332836 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR provided in June 1998 |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance for development of HFC-134a-based domestic refrigerators | Individual | AFR | TUN | REF | 08 | TAS | 8 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1995-04-01 |  | 1997-06-01 | 1998-06-01 | 404658.6 | 0 | 404658.6 | 404658.6 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of Governmnet actions (institutional strengthening) | Individual | AFR | TUN | SEV | 08 | INS | 9 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-07-01 | 1995-10-01 |  | 1998-06-01 | 1998-06-01 | 285312 | 0 | 285312 | 285312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | [11 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | TUN | SEV | 09 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 165800 | -3866 | 161934 | 161934 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | AFR | TUN | SEV | 12 | PRP | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 76296 | -26955 | 49341 | 49341 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | AFR | TUN | SEV | 16 | PRP | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 35000 | -3418 | 31582 | 31582 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment projects in the aerosol, foam, domestic refrigeration and solvent sectors | Individual | AFR | TUN | SEV | 17 | PRP | 13 | A | O | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1998-03-01 | 1999-08-01 | 30000 | -1697 | 28303 | 28303 | 100% | 0 | 0 |  | 3900 | -226 | 3674 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Jasminal Laboratories | Individual | AFR | TUN | ARS | 19 | INV | 14 | A | O | I | CFC | 86 | 86 |  |  | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1998-12-01 | 2001-03-01 | 210000 | -77 | 209923 | 209923 | 100% | 0 | 0 |  | 27300 | -53 | 27247 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Satem Parfums et Produits Cosmetiques | Individual | AFR | TUN | ARS | 19 | INV | 15 | A | O | I | CFC | 29 | 29 |  |  | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 119500 | 0 | 119500 | 119500 | 100% | 0 | 0 |  | 15535 | 0 | 15535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Meublatex | Individual | AFR | TUN | FOA | 19 | INV | 16 | A | O | I | CFC | 28 | 28 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-10-01 | 2000-07-01 | 105000 | -681 | 104319 | 104319 | 100% | 0 | 0 |  | 13650 | -110 | 13540 | 0 | 0 | FIN
FIN | UNIDO | Umbrella project to phase out ODS at the six small refrigerator manufacturers | Individual | AFR | TUN | REF | 19 | INV | 17 | A | O | I | CFC | 78.5 | 78.5 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 1997-05-01 | 2001-10-01 | 764557 | -124194 | 640363 | 640363 | 100% | 0 | 0 |  | 99392 | -16277 | 83115 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the aerosol, foam, solvents and methyl bromide sectors | Individual | AFR | TUN | SEV | 21 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 1999-05-01 | 2000-12-01 | 27150 | -1020 | 26130 | 26130 | 100% | 0 | 0 |  | 3530 | -138 | 3392 | 0 | 0 | FIN |  |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at CODIFA | Individual | AFR | TUN | ARS | 22 | INV | 19 | A | O | I | CFC | 60.25 | 60.25 |  |  | 1997-05-01 | 1997-09-01 | 1998-09-01 |  | 1999-12-01 | 2000-11-01 | 179986 | 0 | 179986 | 179986 | 100% | 0 | 0 |  | 23398 | 0 | 23398 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Alki S.A. | Individual | AFR | TUN | ARS | 22 | INV | 20 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 |  | 1998-09-01 |  |  | 1999-12-01 | 74565 | -74565 | 0 | 0 |  | 0 | 0 |  | 9693 | -9693 | 0 | 0 | 0 | CLO |  |  |  | 1999-03-01
FIN | UNIDO | Phasing out CFCs at Sogepar | Individual | AFR | TUN | ARS | 22 | INV | 21 | A | O | I | CFC | 18.15 | 18.15 |  |  | 1997-05-01 | 1998-11-01 | 1998-09-01 |  | 2000-01-01 | 2001-07-01 | 68833 | 0 | 68833 | 68833 | 100% | 0 | 0 |  | 8948 | -4 | 8944 | 0 | 0 | FIN
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 09 | CPG | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 8200 | 0 | 8200 | 8200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 at Sud Inter Mousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 23 | A | O | I | CFC | 102 | 102 |  |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 2001-12-01 | 2003-08-01 | 546920 | -271 | 546649 | 546649 | 100% | 0 | 0 |  | 71100 | -148 | 70952 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sotrapoc flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 24 | A | O | I | CFC | 20 | 20 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 90037 | -1704 | 88333 | 88333 | 100% | 0 | 0 |  | 11705 | -240 | 11465 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Parhycos, Sfax, Tunisia | Individual | AFR | TUN | ARS | 23 | INV | 25 | A | O | I | CFC | 10 | 10 |  |  | 1997-11-01 | 1999-04-01 | 1999-02-01 |  | 1999-12-01 | 2001-03-01 | 41195 | 0 | 41195 | 41195 | 100% | 0 | 0 |  | 5355 | -2 | 5353 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Polymousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 26 | A | O | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 104343 | -88 | 104255 | 104255 | 100% | 0 | 0 |  | 13565 | -33 | 13532 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project to phase out ODS at 7 manufacturers of commercial and domestic refrigerators (Chahed Refrigeration, Sogima, Sotiem, Rei, Frigo BAF, Societe Moderne Refrigeration, Frigo Technique) | Individual | AFR | TUN | REF | 23 | INV | 27 | A | O | I | CFC | 29 | 29 |  |  | 1997-11-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2001-03-01 | 374111 | -1034 | 373077 | 373077 | 100% | 0 | 0 |  | 48634 | -211 | 48423 | 0 | 0 | FIN
FIN | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 24 | PRP | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Alternatives to the use of methyl bromide in horticulture at Société Méditeranéene Fruitière | Individual | AFR | TUN | FUM | 24 | DEM | 29 | A | O | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 2001-02-01 | 2003-05-01 | 301730 | -11452 | 290278 | 290278 | 100% | 0 | 0 |  | 39225 | -1549 | 37676 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | AFR | TUN | REF | 24 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 1998-12-01 | 2000-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | IBRD | Phase out of ozone depleting substances (renewal of institutional strengthening) | Individual | AFR | TUN | SEV | 25 | INS | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-07-01 | 2000-07-01 |  | 2003-12-01 | 2003-12-01 | 186700 | 0 | 186700 | 186700 | 100% | 0 | 0 |  | 24271 | 0 | 24271 | 0 | 0 | Legislation was drafted, ongoing and completed projects monitored and public awareness campaign was continued. IS renewal requested and approved at the 39th ExCom. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to LCD technology in the manufacture of polyurethane flexible foam and HCFC-141b with water in polyurethane rigid foam at Sotim | Individual | AFR | TUN | FOA | 25 | INV | 32 | N | O | I | CFC | 95.3 | 95.3 | 0 | 0 | 1998-07-01 | 2000-11-01 | 2000-08-01 |  | 2004-12-01 | 2007-07-01 | 553400 | -131363.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 71942 | -17077.2 | 54864.79 | 0.01 | 0.01 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Supermousse | Individual | AFR | TUN | FOA | 26 | INV | 33 | N | O | I | CFC | 93.5 | 93.5 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2007-07-01 | 529490 | -107453.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 68243.9 | -13849.21 | 54394.68 | 0.01 | 0.01 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a project in the solvent sector |  | AFR | TUN | SOL | 27 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out of CFCs at Laboratoires Parcos | Individual | AFR | TUN | ARS | 28 | INV | 35 | A | O | I | CFC | 29.8 | 29.8 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2004-03-01 | 2004-09-01 | 76127 | -469 | 75658 | 75658 | 100% | 0 | 0 |  | 9897 | -77 | 9820 | 0 | 0 | FIN
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Coldeq by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 36 | N | O | I | CFC | 8.8 | 8.8 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 68917 | -4392 | 64525 | 64525 | 100% | 0 | 0 |  | 8959.21 | -570.96 | 8388.25 | 0 | 0 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Bafes by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 37 | N | O | I | CFC | 11.7 | 11.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 91477 | -5148 | 86329 | 86329 | 100% | 0 | 0 |  | 11892.01 | -669.24 | 11222.77 | 0 | 0 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe de Construction Industrialisee (SCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 38 | N | O | I | CFC | 8.3 | 8.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 64700 | -5970 | 58730 | 58730 | 100% | 0 | 0 |  | 8411 | -776.1 | 7634.9 | 0 | 0 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe Nouvelle de Coupe Industrielle (SNCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 39 | N | O | I | CFC | 20.3 | 20.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 156235 | -15623.5 | 140611.5 | 140611.5 | 100% | 0 | 0 |  | 20310.55 | -2031.06 | 18279.49 | 0 | 0 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Soften by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 40 | N | O | I | CFC | 7.5 | 7.5 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 59079 | -995.9 | 58083.1 | 58083.1 | 100% | 0 | 0 |  | 7680.27 | -129.47 | 7550.8 | 0 | 0 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | UNIDO | Project preparation in the fumigants (dates) sector | Individual | AFR | TUN | FUM | 33 | PRP | 41 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 | 2010-12-01 |  |  | 25000 | 0 | 25000 | 12190 | 48.76% | 12810 | 0 | 1 | 3250 | 0 | 1585 | 1665 | 0 | The MBTOC has not yet identified any alternatives applicable for the fumigation of palm dates. DEMO project is ongoing to identify potential alternatives. The project preparation will stem from the result of that project (results expected in 2010). | [13 empty] | 2001 | INV
CLO | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 36 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2003-07-01 | 10000 | -10000 | 0 | 0 |  | 0 | 0 |  | 1300 | -1300 | 0 | 0 | 0 | Project prep. cancelled at the 41st ExCom. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening project | Individual | AFR | TUN | SEV | 39 | INS | 43 | N | T | I | CFC | 20.2 | 20.2 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 | 242667 | 0 | 242667 | 242667 | 100% | 0 | 0 |  | 18200.03 | 0 | 18200.02 | 0.01 | 0.01 | Phase III IS completed and IS IV approved at the 48th ExCom. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of the country programme update | Individual | AFR | TUN | SEV | 42 | CPG | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2004-12-01 |  | 2006-07-01 | 2006-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 7200 | 0 | 7200 | 0 | 0 | CPU completed and National ODS Phaseout Plan approved at the 49th ExCom. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
COM | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | TUN | SOL | 45 | TAS | 45 | A | O | I | CTC | 0.9 | 0.9 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2007-12-01 |  | 50000 | 0 | 50000 | 28460 | 56.92% | 21540 | 6580 | 6500 | 4500 | 0 | 2561 | 1939 | 592 | The project is expected to be financially completed in 2009. | [11 empty] | 2007-06-01 |  | 2005 | INV
COM | IBRD | Extension of institutional strengthening project (phase IV) | Individual | AFR | TUN | SEV | 48 | INS | 46 | N | T | I | CFC | 20.05 | 20.05 | 0 | 0 | 2006-04-01 | 2008-11-01 | 2008-06-01 |  | 2008-12-01 |  | 247270 | 0 | 247270 | 202692 | 81.97% | 44578 | 44578 | 44578 | 18545 | 0 | 15201.69 | 3343.31 | 3343.31 | Phase 4 IS Project (2006-2008) successfully completed. Financial completion expected in Q1 2009. Phase 5 approved at the 55th ExCom. | [13 empty] | 2006 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National ODS phase-out plan (first tranche) | Multiyear | AFR | TUN | PHA | 49 | INV | 47 | N | O | I | CFC | 169.5 | 0 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2008-07-31 | 2009-07-01 |  |  | 790000 | 0 | 790000 | 57230 | 7.244% | 732770 | 732770 | 350000 | 59250 | 0 | 4292.25 | 54957.75 | 54957.75 | Consultants engaged for the foam, servicing, aerosol and halon sectors and work underway. Study on the aerosol sector completed and approved by the NOU. Seminars on project assistance in each sector will be held in early 2009. Verification audit to be completed in 2009. | [13 empty] | 2005 | INV | 172.5 | 17.7 | 0 | 0 |  | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | TUN | PHA | 55 | PRP | 48 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2009-12-01 |  |  | 150000 | 0 | 150000 | 6758 | 4.505% | 143242 | 0 | 50000 | 11250 | 0 | 507 | 10743 | 0 | Contracts were issued for the preparation of the survey. Stake holders workshop will be organized for the preparation of the HPMP. | Subcontract for the preparation of the HPMP includes: • Assistance for policy and legislation; • Survey of HCFCs use and analysis of data collectes; • Consultation with national stackeholders in the data collection and analysis. Regarding the policy aspect, the contractor is requested to assess and analyze the institutional framework, legislation, licensing and quota system regulating consumption of ozone depleting substances in Tunisia with particular focus on HCFCs. The contractor is also requested to assess the current national policies on climate change, chemical management and energy policies, as well as the CFCs phase out activities and lessons learned from previous ODS phase-out activities. Expected outputs: assessment of the current status of legislation and recommendations on necessary institutional and regulatory improvements to facilitate a smooth compliance with the HCFCs phase out obligations. | [12 empty] | 2008 | NON-INV
ONG | IBRD | Extension of institutional strengthening project (phase V) | Individual | AFR | TUN | SEV | 55 | INS | 49 | N | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-06-30 | 2010-06-30 |  |  | 247270 | 0 | 247270 | 0 | 0% | 247270 | 247270 | 160000 | 18545 | 0 | 0 | 18545 | 18545 | 2008 IS activities included the monitoring of enterprises that have converted operations; reporting 2007 data under Art. 7; collaboration with Customs and Ministry of Commerce; meeting with the National Ozone Committee to allocate ODS quotas; participation in various intl ozone meetings in March, April and July 2008; overseeing implementation of the NOPP; participation in two IA missions; preparation of monitoring and progress reports; and public awareness activities. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | EUR | TUR | SEV | 06 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1991-06-30 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 13515 | 55074 | 68589 | 68589 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | EUR | TUR | SEV | 06 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 217687 | -67459 | 150228 | 150228 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and recycling of CFC-12 at a refrigeration production plant | Individual | EUR | TUR | REF | 07 | TAS | 3 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1994-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and reclamation of CFC-12 from household refrigerators | Individual | EUR | TUR | REF | 07 | TAS | 4 | N | O | I | CFC | 1 | 0 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1994-06-01 |  | 1996-12-01 | 1997-03-01 | 400000 | -82919.94 | 317080.06 | 317080.06 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-06-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Demonstration activities in several sectors |  | EUR | TUR | SEV | 07 | PRP | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-10-01 | 1993-06-01 |  | 1999-12-01 | 2000-03-01 | 500000 | -18877 | 481123 | 481123 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3 demo projects in solvent sector are implemented. 8 demo projects in refrigeration sector completed as of December 31, 1998. 6 demo projects in foam sector is completed as of March 31, 1999. Individual PCRs submitted separately per project code. |  |  | 1997-07-01 | 1999-03-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening | Individual | EUR | TUR | SEV | 08 | INS | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-06-01 | 1997-06-01 |  | 2000-04-01 | 2000-04-01 | 300000 | -33157 | 266843 | 266843 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IS project extended to accommodate additional work program of ozone unit. |  |  | 1997-06-01 | 1999-12-01 | [10 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of non-ODS technologies in the production of domestic refrigerators at Arcelik A.S. | Individual | EUR | TUR | REF | 08 | INV | 7 | N | O | I | CFC | 750 | 750 | 0 | 0 | 1992-10-01 | 1994-05-01 | 1995-10-01 |  | 1996-06-01 | 1997-03-01 | 4900000 | -10484 | 4889516 | 4889516.31 | 100% | -0.62 | -0.62 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | TUR | SEV | 09 | PRP | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 140400 | 42164 | 182564 | 182564 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | EUR | TUR | SEV | 12 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | -8823 | 21177 | 21177 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for supervision on project implementation. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | TUR | SEV | 13 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-30 | 1995-07-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -79142 | 20858 | 20858 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment projects in ODS phase out in the foam sector | Individual | EUR | TUR | FOA | 15 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-04-01 | 2001-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -6 | 6494 | 0 | 0 | FIN |  |  | 1997-12-01 | 1999-02-01
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers and coolers at Klimasan Klima Sanayi ve Ticaret A.S. | Individual | EUR | TUR | REF | 15 | INV | 12 | N | O | I |  | 36.9 | 36.9 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1997-01-01 | 1996-12-01 | 690903 | 110665 | 801568 | 801568 | 100% | 0 | 0 |  | 0 | 16669.9 | 16669.9 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the world Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($128,230). |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PEG Profilo Elektrikli Gerecler Sanayii A.S. | Individual | EUR | TUR | REF | 15 | INV | 13 | N | O | I | CFC | 290 | 290 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1996-04-01 | 1996-03-01 | 1578000 | 257747 | 1835747 | 1835747.02 | 100% | -0.02 | -0.02 |  | 0 | 34340.02 | 34340 | 0.02 | 0.02 | The company has achieved 100% non-ODS production. The project is completed and the final report has been submitted to the World Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($264,154). |  |  | 1996-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Assan Demir ve Sac Sanayi A.S., Tuzla-Istanbul | Individual | EUR | TUR | FOA | 15 | INV | 14 | N | O | I | CFC | 180 | 250 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1998-04-01 | 1998-12-01 | 925000 | 0 | 925000 | 925000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | EUR | TUR | SEV | 16 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 43966 | 0 | 43966 | 43966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | EUR | TUR | SEV | 16 | PRP | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 80000 | -7373 | 72627 | 72627 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the mnufacture of rigid polyurethane foam isulation panels at Tek-iz Izolasyon ve Yapi Elemanlari Sanayii, Umnariye-Istanbul | Individual | EUR | TUR | FOA | 18 | INV | 17 | N | O | I | CFC | 155 | 177 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1996-11-01 |  | 1998-04-01 | 1998-07-01 | 729650 | 0 | 729650 | 729650 | 100% | 0 | 0 |  | 94854.5 | 0 | 94854.5 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | UNIDO | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Barlan Metal | Individual | EUR | TUR | FOA | 18 | INV | 18 | A | O | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  |  | 1997-09-01 | 804050 | -802115 | 1935 | 1935 | 100% | 0 | 0 |  | 104527 | -104276 | 251 | 0 | 0 | CLO
CLO | IBRD | Elimination of the use of CFCs in the manufacture of domestic refrigerators at Pekel Teknik Sanyi ve Ticaret A.S. | Individual | EUR | TUR | REF | 18 | INV | 19 | N | O | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-05-01 |  |  | 1996-10-01 | 500664 | -500664 | 0 | 0 |  | 0 | 0 |  | 65086.32 | -65086.32 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. |  |  | 1996-05-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 18 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Project preparation completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers, coolers, ice makers, and ice cream machines at UGUR Makinalari Sanayi ve Ticaret, A.S. | Individual | EUR | TUR | REF | 19 | INV | 21 | N | O | I | CFC | 64.3 | 64.3 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1999-03-01 | 1999-07-01 | 1166455 | 0 | 1166455 | 1166455 | 100% | 0 | 0 |  | 151639.15 | 0 | 151639.15 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  | 1998-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out of CFC-11 at Urosan Kimiya Sanayii A.S. | Individual | EUR | TUR | FOA | 20 | INV | 22 | A | O | I | CFC | 135 | 135 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1999-12-01 | 2002-04-01 | 643500 | -10955 | 632545 | 632545 | 100% | 0 | 0 |  | 83655 | -1555 | 82100 | 0 | 0 | FIN |  |  |  | 1999-04-01
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 21 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project preparation completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into carbon dioxide and water for flexible molded foam at Suntas Foam and Mattress Industry and Commerce, Inc. | Individual | EUR | TUR | FOA | 22 | INV | 24 | N | O | I | CFC | 9.05 | 12.06 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1996-09-01 | 1998-07-01 | 148613 | -5177 | 143436 | 143436 | 100% | 0 | 0 |  | 19319.69 | -579.54 | 18740.15 | 0 | 0 | The project (retroactive) was fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11, CFC-12 into cyclopentane and HFC-134a for commercial refrigeration at S.F.A. Sogutma Urunleri Sanayi Ve Tekstil Pazariama Ltd. Sti. | Individual | EUR | TUR | REF | 22 | INV | 25 | N | O | I |  | 25.9 | 25.9 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-02-01 |  | 1999-03-01 | 1999-12-01 | 389832 | 0 | 389832 | 389832 | 100% | 0 | 0 |  | 50678.16 | 0 | 50678.16 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Gumaksan | Individual | EUR | TUR | REF | 22 | INV | 26 | N | O | I | CFC | 2.3 | 2.3 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1998-06-01 |  | 1998-11-01 | 1999-01-01 | 35195 | 0 | 35195 | 35195 | 100% | 0 | 0 |  | 4575.35 | 0 | 4575.35 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Kulahcioglu | Individual | EUR | TUR | REF | 22 | INV | 27 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 1999-03-01 | 1999-06-01 | 60840 | 0 | 60840 | 60840 | 100% | 0 | 0 |  | 7909.2 | 0 | 7909.2 | 0 | 0 | The project is completed 100% non-CFC production started. Waiting for PCR. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into HCFC-141b at Teba | Individual | EUR | TUR | FOA | 22 | INV | 28 | N | O | I | CFC | 3.51 | 3.51 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1998-06-01 |  | 1998-11-01 | 1999-02-01 | 27468 | -104 | 27364 | 27364 | 100% | 0 | 0 |  | 3570.84 | -13.52 | 3557.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible slabstock foam at Safas | Individual | EUR | TUR | FOA | 23 | INV | 29 | N | O | I | CFC | 93.83 | 93.83 | 0 | 0 | 1997-11-01 | 1998-05-01 | 1999-03-01 |  | 1999-09-01 | 1999-12-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 68900 | 0 | 68900 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 at Isbir Termoset Plastic San. A.S., Ankara, Turkey | Individual | EUR | TUR | FOA | 23 | INV | 30 | A | O | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1999-03-01 | 1998-12-01 |  | 2001-04-01 | 2002-09-01 | 501350 | 0 | 501350 | 501350 | 100% | 0 | 0 |  | 65176 | -45 | 65131 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Go-Ya Sungar Ltd. Sti. | Individual | EUR | TUR | FOA | 23 | INV | 31 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-11-01 | 1998-12-01 |  |  | 2002-04-01 | 533400 | -313280 | 220120 | 220120 | 100% | 0 | 0 |  | 69342 | -40772 | 28570 | 0 | 0 | CLO
FIN | USA | MACs servicing demonstration project |  | EUR | TUR | REF | 23 | DEM | 32 | A | O | I | CFC | 12 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 2000-07-01 | 205000 | 0 | 205000 | 205000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery planned for May 99. |  | 1997
CLO | IBRD | Conversion from CFC-11 into all-water and HCFC-141b for integral skin foam at Polifleks Sentetik Maddeler Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 33 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 |  | 2000-04-01 |  |  | 1999-11-01 | 252558 | -252558 | 0 | 0 |  | 0 | 0 |  | 32832.54 | -32832.54 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. Funds will be returned at 34th Meeting. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the aerosol, foam and recycling sectors |  | EUR | TUR | SEV | 24 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment project in the rigid foam sub sector | Individual | EUR | TUR | FOA | 24 | PRP | 35 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-11-01 | 2001-05-01 | 15000 | -9583 | 5417 | 5417 | 100% | 0 | 0 |  | 1950 | -1247 | 703 | 0 | 0 | FIN |  |  |  | 1999-09-01
FIN | UNIDO | Preparation of a demonstration project (flowers, tobacco) | Individual | EUR | TUR | FUM | 24 | PRP | 36 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the foam sector (polyurethane) at Sungersan AS and Serra Sunger | Individual | EUR | TUR | FOA | 24 | PRP | 37 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1999-12-01 | 2000-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | IBRD | Conversion from CFC-11 into all-water for flexible slabstock foam at IDAS | Individual | EUR | TUR | FOA | 24 | INV | 38 | N | O | I | CFC | 37 | 37 | 0 | 0 | 1998-03-01 | 1999-02-01 | 2000-04-01 |  | 1998-11-01 | 1999-07-01 | 230510 | -373 | 230137 | 230137 | 100% | 0 | 0 |  | 29966.3 | -48.49 | 29917.81 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 for flexible molded, integral skin and rigid foam at Purplast | Individual | EUR | TUR | FOA | 24 | INV | 39 | N | O | I | CFC | 54 | 54 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2000-11-01 | 551101 | 0 | 551101 | 551101 | 100% | 0 | 0 |  | 71643.13 | 0 | 71643.13 | 0 | 0 | Project fully implemented, 100% non-CFC production started. PCR submitted Jan. 01. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible moulded foam at Elele Doseme Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 40 | N | O | I | CFC | 41.36 | 41.36 | 0 | 0 | 1998-03-01 | 1999-04-01 | 2000-10-01 |  | 1999-04-01 | 1999-07-01 | 311768 | 0 | 311768 | 311768 | 100% | 0 | 0 |  | 40529.84 | 0 | 40529.84 | 0 | 0 | 100% non-CFC production started. Draft PCR prepared. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC foam blowing agents in the production of polyurethane (PU) insulation panels, spray/in situ foam and one component foams at Izopoli Yapi Elemantari Taahhuet Sanayii ve Ticaret Lt | Individual | EUR | TUR | FOA | 24 | INV | 41 | N | O | I | CFC | 274 | 274 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2001-04-01 |  | 2000-05-01 | 2000-05-01 | 1141500 | 0 | 1141500 | 1141500 | 100% | 0 | 0 |  | 148395 | 0 | 148395 | 0 | 0 | Project completed. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible moulded and HCFC-141b for integral skin foam at EPS Entegre Poliuretan Sunger Ve Koltuk San Tic. Ltd. Sti. | Individual | EUR | TUR | FOA | 24 | INV | 42 | N | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 1998-03-01 | 1999-01-01 | 2000-04-01 |  | 1999-12-01 | 1999-12-01 | 188280 | -270 | 188010 | 188010 | 100% | 0 | 0 |  | 24476.4 | -35.12 | 24441.28 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 for flexible moulded, integral skin and rigid foam at Pimsa Poliuretan Imalat Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 43 | N | O | I | CFC | 57.9 | 57.9 | 0 | 0 | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 1999-07-01 | 2000-11-01 | 551501 | 0 | 551501 | 551501 | 100% | 0 | 0 |  | 71695.13 | 0 | 71695.13 | 0 | 0 | Installation completed. 100% non-CFC production started. PCR submitted. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into methylene chloride and dop for flexible molded hot cured foam at Teknik Malzeme | Individual | EUR | TUR | FOA | 24 | INV | 44 | N | O | I | CFC | 17.2 | 17.2 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 1998-06-01 | 1999-08-01 | 122443 | -22079 | 100364 | 100364 | 100% | 0 | 0 |  | 15917.59 | -2870.27 | 13047.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for commercial refrigeration terminal umbrella project |  | EUR | TUR | REF | 25 | PRP | 45 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0 | Completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticulture (tomatoes and cucumbers) and ornamental (carnations) crops | Individual | EUR | TUR | FUM | 25 | DEM | 46 | A | O | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-02-01 | 2000-08-01 |  | 2001-05-01 | 2002-12-01 | 314600 | -9324 | 305276 | 305276 | 100% | 0 | 0 |  | 40898 | -1275 | 39623 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of CO2 blowing technology at Serra Sunger | Individual | EUR | TUR | FOA | 25 | INV | 47 | A | O | I | CFC | 86 | 86 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-08-01 | 454358 | 0 | 454358 | 454358 | 100% | 0 | 0 |  | 59067 | -16 | 59051 | 0 | 0 | FIN
FIN | IBRD | Project preparation for methy bromide |  | EUR | TUR | FUM | 25 | PRP | 48 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for 17 enterprises for phaseout of ODS used as solvents | Individual | EUR | TUR | SOL | 25 | INV | 49 | N | O | I |  | 11.97 | 11.97 | 0 | 0 | 1998-07-01 | 2000-03-01 | 1999-08-01 |  | 2000-10-01 | 2000-10-01 | 415312 | -20098 | 395214 | 395214 | 100% | 0 | 0 |  | 53990.56 | -2612.77 | 51377.79 | 0 | 0 | Project implemented and 100% non-CFC production started. Awaiting PCR. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of an electronic defluxing process from ODS-solvent cleaning to hydrocarbon/surfactant (semi-aqueous) cleaning at Aselsan AS | Individual | EUR | TUR | SOL | 25 | INV | 50 | N | O | R | CFC | 3.9 | 3.9 | 0 | 0 | 1998-07-01 | 1999-02-01 | 1999-08-01 |  | 1995-10-01 | 1999-02-01 | 58517 | 0 | 58517 | 58517 | 100% | 0 | 0 |  | 7607.21 | 0 | 7607.21 | 0 | 0 | Company has achieved 100% non-ODS production. Project is completed and draft report submitted to the Bank. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 to isobutane in the manufacture of polyethylene foam tubing at Thermaflex-Form | Individual | EUR | TUR | FOA | 26 | INV | 51 | N | O | R | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1996-08-01 | 1999-06-01 | 124219 | 0 | 124219 | 124219 | 100% | 0 | 0 |  | 16148.47 | 0 | 16148.47 | 0 | 0 | Company started non-CFC production in mid-1996. Subgrant agreement signed in Feb/99. PCR submitted Jan. 01. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 in the manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Sungersan | Individual | EUR | TUR | FOA | 27 | INV | 52 | A | O | I | CFC | 78 | 78 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 467397 | 0 | 467397 | 467397 | 100% | 0 | 0 |  | 60762 | 0 | 60762 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU molded foam through the use of CO2 blosing technology at Sungersan, Bursa | Individual | EUR | TUR | FOA | 27 | INV | 53 | A | O | I | CFC | 30 | 30 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2002-05-01 | 327374 | 0 | 327374 | 327374 | 100% | 0 | 0 |  | 42559 | -9 | 42550 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects in the foam, commercial refrigeration, refrigeration/ recycling, halon, methyl bromide and a demonstration project for a national phase-out. |  | EUR | TUR | SEV | 27 | PRP | 54 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | Completed | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into low index additive (LIA) technology for flexible slabstock foam at Elta | Individual | EUR | TUR | FOA | 28 | INV | 55 | N | O | I | CFC | 21.3 | 21.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2001-08-01 |  | 2001-06-01 | 2001-10-01 | 130597 | -20000 | 110597 | 110597 | 100% | 0 | 0 |  | 16977.61 | -2600 | 14377.61 | 0 | 0 | Project fully implemented. 100% non-CFC production started. Awaiting PCR. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of alternatives to methyl bromide in protected strawberry, pepper and eggplant in East Mediterranean region and in strawberry in Aydm province of Turkey | Individual | EUR | TUR | FUM | 29 | INV | 56 | N | O | I | MBR | 50 | 50 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2003-07-01 | 2003-08-01 | 366440 | 0 | 366440 | 366440 | 100% | 0 | 0 |  | 47637.2 | 0 | 47637.2 | 0 | 0 | Project fully implemented. Alternatives to MeBr use in strawberry, pepper and eggplant production determined and results published. | [14 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of investment project in the flexible foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 57 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 15000 | -10124 | 4876 | 4876 | 100% | 0 | 0 |  | 1950 | -1317 | 633 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 58 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-09-01 | 2001-04-01 |  | 2002-03-01 | 2002-05-01 | 15000 | -941 | 14059 | 14059 | 100% | 0 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector (horticulture) | Individual | EUR | TUR | FUM | 30 | PRP | 59 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -787 | 29213 | 29213 | 100% | 0 | 0 |  | 3900 | -108 | 3792 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects in the aerosol sector |  | EUR | TUR | ARS | 30 | PRP | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of project proposal in the foam general sector |  | EUR | TUR | FOA | 30 | PRP | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects for the halon recycling |  | EUR | TUR | HAL | 30 | PRP | 62 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 15000 | -5000 | 10000 | 10000 | 100% | 0 | 0 |  | 1950 | -650 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane foam subsector |  | EUR | TUR | FOA | 30 | PRP | 63 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | EUR | TUR | SOL | 30 | PRP | 64 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane panels for thermal insulation for cold rooms and cold storages at Izotek | Individual | EUR | TUR | FOA | 28 | INV | 65 | A | O | I | CFC | 74.8 | 74.8 |  |  | 1999-07-01 | 2000-08-01 | 2001-08-01 |  | 2001-08-01 | 2002-09-01 | 430721 | -4807 | 425914 | 425914 | 100% | 0 | 0 |  | 55994 | -713 | 55281 | 0 | 0 | FIN
FIN | IBRD | Conversion from CFCs and MCF into HAPs and CO2 for technical aerosols at Beta | Individual | EUR | TUR | ARS | 31 | INV | 66 | N | O | I |  | 31.2 | 31.2 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2002-01-01 |  | 2001-01-01 | 2001-10-01 | 137456 | 0 | 137456 | 137456 | 100% | 0 | 0 |  | 8247 | 0 | 8247 | 0 | 0 | Project fully implemented and 100% non-CFC production started. Awaiting PCR. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
CLO | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 31 | PRP | 67 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 |  | 2001-07-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Espol Sunger Company | Individual | EUR | TUR | FOA | 31 | INV | 68 | A | O | I | CFC | 95 | 95 |  |  | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2004-02-01 | 2004-12-01 | 552297 | 0 | 552297 | 552297 | 100% | 0 | 0 |  | 70753 | -31 | 70722 | 0 | 0 | FIN
FIN | IBRD | Phase-out methyl bromide in the dried fig sector | Individual | EUR | TUR | FUM | 31 | INV | 69 | N | O | I | MBR | 30 | 30 | 0 | 0 | 2000-07-01 | 2001-06-02 | 2002-10-01 |  | 2006-06-01 | 2006-12-01 | 479040 | -1980.74 | 477059.26 | 477059.26 | 100% | 0 | 0 |  | 62275.2 | -257.5 | 62017.7 | 0 | 0 | Project completed both physically and financially. Currently, beneficiary uses CO2 and phosphine in fumigation. No more MeBr is in use. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and integral skin foams at Urosan | Individual | EUR | TUR | FOA | 32 | INV | 70 | N | O | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-03-01 | 2004-12-01 | 291641 | -815.56 | 290825.44 | 290825.44 | 100% | 0 | 0 |  | 37913.33 | -106.02 | 37807.31 | 0 | 0 | Project completed. | [7 empty] | 2004-01-01 | [5 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and HCFC-141b for integral skin foams at 11 enterprises (Erdogan Rurmenler; KarakayaCelik; Una Polyuretan; Iksan Ltd; Ak-Kom; Karsan; Goldsit; Buoflex; Gervener; Yaris Kabin; Hisarlar) | Individual | EUR | TUR | FOA | 32 | INV | 71 | N | O | I | CFC | 48.5 | 48.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-06-01 | 2005-07-01 | 398378 | -277445.52 | 120932.48 | 120932.48 | 100% | 0 | 0 |  | 51789.14 | -36067.98 | 15721.22 | -0.06 | -0.06 | Project completed and non-ODS production at all 5 participating companies underway. | [7 empty] | 2004-01-01 | [5 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology at Purtiz Co. in the manufacture of rigid polyurethane foam for insulating purposes | Individual | EUR | TUR | FOA | 32 | INV | 72 | A | O | I | CFC | 52.8 | 52.8 |  |  | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-07-01 | 2004-09-01 | 301094 | -139 | 300955 | 300955 | 100% | 0 | 0 |  | 39142 | -80 | 39062 | 0 | 0 | FIN
FIN | IBRD | Renewal of institutional strengthening | Individual | EUR | TUR | SEV | 32 | INS | 73 | N | T | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2007-12-01 | 2008-04-01 | 200000 | 0 | 200000 | 196359.49 | 98.18% | 3640.51 | 0 | 0 | 26000 | 0 | 25526.73 | 473.27 | 0 | All activities completed and project is physically and financially closed. | [13 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phase out of methyl bromide in protected tomato, cucumber and carnation crops (first tranche) | Multi-Year | EUR | TUR | FUM | 35 | INV | 74 | A | O | I | MBR | 29.2 | 29.2 |  |  | 2001-12-01 | 2002-08-01 | 2002-12-01 |  | 2003-12-01 | 2006-11-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | FIN | [13 empty] | 2001 | INV | 263 | 263 |  |  | Yes | N/A | N/A
FIN | IBRD | Total phase out of CFCs plan: 2001 and 2002 annual programmes | Multiyear | EUR | TUR | PHA | 35 | INV | 75 | N | O | I | CFC | 97 | 97 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2008-04-01 | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 | 0 | 295000 | 0 | 295000 | 0 | 0 | Project completed. | [13 empty] | 2001 | INV | 977 | 699 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | Individual | EUR | TUR | SOL | 35 | INV | 76 | N | O | I | TCA | 15.4 | 15.4 | 0 | 0 | 2001-12-01 | 2003-11-01 | 2004-01-01 |  | 2005-02-01 | 2005-12-01 | 518693 | -45479.16 | 473213.84 | 473213.84 | 100% | 0 | 0 |  | 67056.23 | -5538.18 | 61517.82 | 0.23 | 0.23 | All 16 projects completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation in the methyl bromide sector (storage of hazelnut) |  | EUR | TUR | FUM | 36 | PRP | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2004-12-01 | 40000 | -40000 | 0 | 0 |  | 0 | 0 |  | 5200 | -5200 | 0 | 0 | 0 | Due to reorganization of MARA and personnel changes following a newly elected government funding is returned while Gov. weighs its options on a way forward. | [13 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of a sectoral phase-out project in the solvents sector | Individual | EUR | TUR | SOL | 36 | PRP | 78 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-07-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -2 | 6498 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | IBRD | Total phase out of CFCs plan: 2003 annual programme | Multiyear | EUR | TUR | PHA | 38 | INV | 79 | N | O | I | CFC | 375 | 375 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2008-04-01 | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 | 0 | 175000 | 0 | 175000 | 0 | 0 | Project completed. | [13 empty] | 2002 | INV | 534 | 457.2 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | EUR | TUR | HAL | 38 | TAS | 80 | N | O | I | HAL | 118 | 118 | 0 | 0 | 2002-11-01 | 2008-04-01 | 2005-11-01 |  | 2007-12-01 | 2008-04-01 | 439250 | 0 | 439250 | 432258 | 98.41% | 6992 | 0 | 0 | 57102.5 | 0 | 56193.54 | 908.96 | 0 | Project completed. | [13 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Total phase-out of CFCs plan: 2004 annual programme | Multiyear | EUR | TUR | PHA | 41 | INV | 81 | N | O | I | CFC | 218 | 218 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2008-04-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 150000 | 0 | 150000 | 0 | 0 | Project completed. | [13 empty] | 2003 | INV | 316 | 258.2 | 0 | 0 | Yes | Yes | Yes
COM | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (second tranche) | Multi-Year | EUR | TUR | FUM | 41 | INV | 82 | A | O | I | MBR | 58 | 58 |  |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 |  | 1000000 | 0 | 1000000 | 997323 | 99.73% | 2677 | 2606 | 2606 | 75000 | 0 | 74799 | 201 | 195 | Project completed in Dec 2008. | [13 empty] | 2003 | INV | 147 | 223 |  |  | Yes | N/A | N/A
FIN | UNIDO | Terminal umbrella project for phase-out of remaining ozone depleting solvents | Individual | EUR | TUR | SOL | 41 | INV | 83 | A | O | I | CTC | 24 | 24 |  |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2005-12-01 | 2007-03-01 | 531644 | -52625 | 479019 | 479019 | 100% | 0 | 0 |  | 39873 | -3947 | 35926 | 0 | 0 | FIN | [13 empty] | 2003 | INV
FIN | IBRD | Total phase-out of CFCs plan: 2005 annual programme | Multiyear | EUR | TUR | PHA | 44 | INV | 85 | N | O | I | CFC | 150 | 166 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-04-01 | 750000 | 0 | 750000 | 315903.15 | 42.12% | 434096.85 | 0 | 0 | 45000 | 0 | 18954.18 | 26045.82 | 0 | Project completed. | [13 empty] | 2004 | INV | 150 | 132 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | EUR | TUR | SEV | 44 | INS | 86 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 260000 | 0 | 260000 | 236399.08 | 90.92% | 23600.92 | 0 | 0 | 19500 | 0 | 17729.93 | 1770.07 | 0 | Field work and information dissemination via workshops and other meetings carried out by MARA. Training programs and other project components all completed. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Total phase-out of CFCs plan: 2006 annual programme | Multiyear | EUR | TUR | PHA | 47 | INV | 87 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Project completed. | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0 | Yes | Yes | Yes
ONG | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (third and fourth tranches) | Multi-Year | EUR | TUR | FUM | 47 | INV | 88 | A | O | I | MBR | 147 | 147 |  |  | 2005-11-01 | 2006-06-01 | 2006-12-01 | 2009-07-01 |  |  | 1408844 | 0 | 1408844 | 948843 | 67.35% | 460001 | 403903 | 100000 | 105663 | 0 | 71163 | 34500 | 30293 | Final national workshop has been organized in May 2008 and training activities were completed by 3 study tours organized in summer 2008, mainly to share the implementation results and to assure sustainability of the chosen alternatives. | (a) The study tours addressed very specific technical issues related to the implemented alternatives. E.g. A group of 4 experts working with grafted plants in Turkey were addresing growing techniques issues for grafted plants, during a 4 days study visit at specialized locations in Italy. This is ensuring sustainability of the implemented alternatives. The 4 days visit in Italy was called "study tour" in the UNIDO report, however it involved only highly specialized experts that are effectively applying the MeBr alternatives in Turkey. Similar technical discussions with international experts in Nederland were organized for 3 experts involved in application of soiless cultivation as an alternative to MeBr. (b) Technical training on the application of selected MeBr alternatives is part of the technology transfer process of the project. The solution to address specifical technical issues through visiting specialized location where such alternatives are in place was more convenient both from financial point of view (in comparison to hiring an international consultant) and also from practicality point of view. | [12 empty] | 2005 | INV | 0 | 0 |  |  | Yes | N/A | N/A
FIN | IBRD | Total phase-out of CFCs plan: 2007 annual programme | Multiyear | EUR | TUR | PHA | 50 | INV | 89 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2007-12-01 | 2008-04-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Project completed. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Total phase-out of CFCs plan: Implementation status of 2007AP and verification report for CFC consumption for 2007 | Multiyear | EUR | TUR | PHA | 53 | INV | 90 | N | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 | 2009-07-01 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 30000 | 0 | 0 | 30000 | 30000 | Implementation status and verification report will be submitted in 2009. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 | Yes
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TUR | PHA | 55 | PRP | 91 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 195000 | 0 | 195000 | 60 | 0.03077% | 194940 | 0 | 50000 | 14625 | 0 | 5 | 14620 | 0 | National expert contracted for the HCFCs survey. First stakeholders consultation workshop agreed for January 2009. Project is expected to be completed beginning of 2010. | Initial stakeholders consultation meeting took place 29 January 2009. Establisment of new facilities which utilise ODSs (including HCFCs) is banned since 2006. ? Regulation to control of ozone depleting substance has been revised with a view to HCFCs and put into force on November 12th 2008. ? According to provisions of this regulation HCFC phasing out scheme started to be implemented at the beginning of 2009. Licensing (for importers and distributors) and permit system are in force for HCFCs. | [12 empty] | 2008 | NON-INV
FIN | UNEP | Country programme preparation | Individual | ASP | TUV | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 5200 | -3250 | 1950 | 0 | 0 | Project financially completed. | $ 25,000 plus $ 3,250 returned ExCom 46 |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TUV | REF | 36 | TAS | 2 | A | O | I |  | 0.1 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 | 2009-06-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5017 | 1040 | 0 | 0 | 1040 | 1040 | ODS Act passed in June 2008. Regulations being finalised. Customs training workshop scheduled for May 2009. |  | 2002
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TUV | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2002 | Non Investment
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TUV | REF | 36 | TAS | 4 | A | O | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 |  | 18000 | 0 | 18000 | 13375 | 74.31% | 4625 | 0 | 4624 | 2340 | 0 | 0 | 2340 | 2340 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
COM | UNEP | Extension of the institutional strengthening project (2nd year of phase II) | Individual | ASP | TUV | SEV | 50 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 |  | 7583 | 0 | 7583 | 66 | 0.8704% | 7517 | 0 | 7517 | 0 | 0 | 0 | 0 | 0 | Project completed in in November 2008. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (2nd year of phase II) | Individual | ASP | TUV | SEV | 56 | INS | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | Project newly approved | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | UGA | SEV | 4 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1994-06-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
ONG | UNEP | Institutional strengthening (establishment of the ODS unit) | Individual | AFR | UGA | SEV | 13 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1997-07-01 | 2009-06-01 |  |  | 64515 | 0 | 64515 | 15687 | 24.32% | 48828 | 0 | 48828 | 8386.95 | 0 | 2039.31 | 6347.64 | 0 | Due to loss of records subsequent to changes in government structures, NOU is requesting closure of the current phase of the ISP and request for a new approval to start afresh. |  |  |  | 1999-12-01 | [9 empty] | 1994 | Non Investment
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | UGA | REF | 17 | PRP | 3 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | UGA | SEV | 18 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | UGA | REF | 19 | TAS | 5 | A | O | I | CFC | 3.6 | 3.6 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 56000 | -17 | 55983 | 55983 | 100% | 0 | 0 | 0 | 7280 | -2 | 7278 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | UGA | REF | 23 | PRP | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | UGA | REF | 26 | TAS | 7 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved in Dec 2004
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | UGA | FUM | 30 | PRP | 8 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -560 | 29440 | 29440 | 100% | 0 | 0 |  | 3900 | -79 | 3821 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | UGA | FUM | 34 | INV | 8 | A | O | I | MBR | 30 | 30 |  |  | 2001-07-01 | 2002-10-01 | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 228800 | -797 | 228003 | 228003 | 100% | 0 | 0 |  | 29744 | -104 | 29640 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | UGA | REF | 37 | PRP | 9 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completetd. RMP update approved at 44th ExCom | [13 empty] | 2002
ONG | France | Implementation of the RMP update | RMP Update | AFR | UGA | REF | 44 | TAS | 11 | A | O | I | CFC | 10.9 |  | 0 |  | 2004-12-01 | 2005-07-01 | 2007-12-01 | 2009-10-01 |  |  | 75000 | 0 | 75000 | 54000 | 72% | 21000 |  | 21000 | 9750 | 0 | 7020 | 2730 |  | The French contribution is implemented by GTZ-Proklima. The project implemention was slow due to restructuring at the customs department and training centres. These have only recently been completed and now 2 additional technican trainings are to be conducted.
COM | France | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | UGA | PHA | 50 | PRP | 12 | A | O | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | The French contribution is implmented by GTZ; TPMP submitted at 55th ExCom. Project completed.
ONG | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | UGA | PHA | 55 | INV | 13 | A | O | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2008-12-01 | 2010-12-01 | 2010-12-01 |  |  | 152500 | 0 | 152500 | 11430 | 7.495% | 141070 |  | 141070 | 19825 | 0 | 1485.9 | 18339.1 |  | The French contribution is implemented by GTZ-Proklima. First technician trainings are being conducted. However the implementation is slow because activities still need to be completed under the RMP.
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | UGA | PHA | 56 | PRP | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 3900 | 0 | 0 | 3900 | 0 | MOU for implementation signed with the country. NOU identified experts to undertake the HCFC survey and drafting of HPMP and the NOU drafted the HCFC survey questinnaire and the HPMP template | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | URT | SEV | 11 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1996-07-01 | 1999-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production | Individual | AFR | URT | REF | 15 | PRP | 2 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-05-01 | 1996-05-01 | 10000 | -51 | 9949 | 9949 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in aerosol sector at Mansoor Daya | Individual | AFR | URT | ARS | 15 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 10000 | -1456 | 8544 | 8544 | 100% | 0 | 0 |  | 1300 | -191 | 1109 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | AFR | URT | SEV | 17 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1998-12-01 | 1999-12-01 | 47000 | 0 | 47000 | 47000 | 100% | 0 | 0 | 0 | 6110 | 0 | 6110 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | UNIDO | Phasing out of CFCs at Mansoor Daya Chemicals Ltd. | Individual | AFR | URT | ARS | 18 | INV | 5 | A | O | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1997-12-01 | 1999-08-01 | 417163 | -2138 | 415025 | 415025 | 100% | 0 | 0 |  | 54231 | -363 | 53868 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFCs at Tanzania Domestic Appliance Manufacturers Ltd. | Individual | AFR | URT | REF | 18 | INV | 6 | A | O | I | CFC | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1997-03-01 |  |  | 2002-12-01 | 592790 | -101002 | 491788 | 491788 | 100% | 0 | 0 |  | 77063 | -13232 | 63831 | 0 | 0 | CLO |  |  | 1997-12-01 | 1999-12-01
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | URT | SEV | 20 | INS | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1999-10-01 |  | 2004-12-01 | 2007-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 8580 | 0 | 8580 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | URT | REF | 22 | TAS | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2001-12-01 | 161554 | -153795 | 7759 | 7759 | 100% | 0 | 0 | 0 | 21002 | -19993 | 1009 | 0 | 0 | Canceled in 2000. Financially completed in 2001. | [13 empty] | 1997 | Investment
FIN | UNDP | Project preparation to formulate one flexible foam sector project | Individual | AFR | URT | FOA | 24 | PRP | 9 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. | [13 empty] | 1998 | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at H.K. Foam Ltd. | Individual | AFR | URT | FOA | 26 | INV | 10 | A | O | I | CFC | 2 | 2 | 0 | 0 | 1998-11-01 | 2003-01-01 | 2000-12-01 |  |  | 2003-11-01 | 113700 | -105743 | 7957 | 7957 | 100% | 0 | 0 | 0 | 14781 | -13747 | 1034 | 0 | 0 | Canceled in 2003. Financially completed in 2003. | [13 empty] | 1998 | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pan Africa Enterprises Ltd. | Individual | AFR | URT | FOA | 26 | INV | 11 | A | O | I | CFC | 35 | 0 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  |  | 2004-03-01 | 213800 | 0 | 213800 | 213800 | 100% | 0 | 0 | 0 | 27794 | 0 | 27794 | 0 | 0 | Canceled in 2002. Financially completed in 2004. | [13 empty] | 1998 | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | URT | REF | 26 | TAS | 12 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Plyfoam Limited | Individual | AFR | URT | FOA | 31 | INV | 13 | A | O | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-07-01 | 2002-07-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 175134 | 0 | 175134 | 175134 | 100% | 0 | 0 | 0 | 22767 | 0 | 22767 | 0 | 0 | Completed in 2004. Financially completed in 2006. | [13 empty] | 2000 | Investment
COM | Germany | Recovery and recycling of CFCs | Individual | AFR | URT | REF | 36 | TAS | 14 | A | O | I | CFC | 71.4 | 11.7 | 0 |  | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2008-08-01 |  | 164223 | 0 | 164223 | 154299 | 93.96% | 9924 | 0 | 0 | 21349 | 0 | 20058.8794 | 1290.1206 | 0 | Under the contract the only remaining activity is the construction of the recovery and recycling center. As the local partner cannot give a concrete date of finalization of the construction we suggested to declare the project completed and return the rest of the fund to the MLF. NOU agreed to the PCR in Nov-2008. PCR to be sent to MLF in Apr-2009. Funds will be returned to MLFS.
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | URT | REF | 37 | PRP | 15 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-06-05 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A RMP update was submitted by Tanzania in 2005
COM | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | URT | SEV | 44 | INS | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 |  | 57200 | 0 | 57200 | 23000 | 40.21% | 34200 | 32400 | 34200 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
ONG | France | Refrigerant management plan update | RMP Update | AFR | URT | REF | 46 | TAS | 18 | A | O | I | CFC | 68.3 |  | 0 |  | 2005-07-01 | 2005-09-05 | 2008-07-01 | 2009-10-01 |  |  | 157252 | 0 | 157252 | 116517 | 74.1% | 40735 |  | 40735 | 20443 | 0 | 15147.3878 | 5295.6122 |  | The French contribution is implemented by GTZ-Proklima. Customs trainings were conducted as well as additional trainings for monitoring and enforcement' officers from the govt.
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | URT | SEV | 50 | INS | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 |  | 60000 | 0 | 60000 | 53900 | 89.83% | 6100 | 0 | 6100 | 0 | 0 | 0 | 0 | 0 | Project completed in November 2008. New phase approved at 57th ExCom. Country prepared TPMP, implemented first tranche of TPMP. NOU conducted trainings for customs officers, refrigeration technicians, produced awareness materials and celebrated Ozone Day. | [13 empty] | 2006 | Non Investment
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | URT | PHA | 50 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-11-01 |  | 17000 | 0 | 17000 | 3000 | 17.65% | 14000 | 14000 | 14000 | 2210 | 0 | 390 | 1820 | 1820 | Project completed in November 2008. | [13 empty] | 2006 | Non Investment
COM | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | URT | PHA | 50 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 |  | 12000 | 0 | 12000 | 8760 | 73% | 3240 | 0 | 3240 | 900 | 0 | 657 | 243 | 0 | Completed in 2007. | [13 empty] | 2006 | Investment
ONG | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | TAS | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-31 | 2010-03-31 |  |  | 131000 | 0 | 131000 | 100000.38 | 76.34% | 30999.62 | 31000 | 30999.62 | 17030 | 0 | 13000.0494 | 4029.9506 | 4030 | First tranche being implemented, country conducted trainings for customs officers, refrigeration technicians, reviewed ODS Regulations, curricula for customs training school and technicians scholl. Inspectors from Tanzania Burea of Standards were trained | [13 empty] | 2008
ONG | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | INV | 23 | N | O | I | CFC | 15.9 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-01 | 2010-03-01 |  |  | 204000 | 0 | 204000 | 2814 | 1.379% | 201186 | 0 | 40237.2 | 15300 | 0 | 211.05 | 15088.95 | 0 | Project ongoing. International expert recruited. Mission fielded in December 2008. Plan of actions developed. Equipment specifications developed and advertised. More progress expected in Q1/2-2009. | [13 empty] | 2008 | Investment
FIN | UNDP | Consultant mission to assess technical assistance requirement | Individual | LAC | URU | SEV | 04 | TAS | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-10-01 |  | 1992-12-01 | 1997-12-01 | 13050 | 992 | 14042 | 14042 | 100% | 0 | 0 | 0 | 1697 | 129 | 1826 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | URU | SEV | 08 | CPG | 2 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 23894 | 1550 | 25444 | 25444 | 100% | 0 | 0 | 0 | 3106 | 202 | 3308 | 0 | 0 | Completed in 1993. Financially completed in 1997. | [13 empty] | 1992 | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | URU | SEV | 10 | INS | 3 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 173800 | 29000 | 202800 | 202800 | 100% | 0 | 0 | 0 | 22594 | 3770 | 26364 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Conservation and demonstration programme for domestic and commercial refrigeration and installation of recovery and recycling equipment | RMP-Component | LAC | URU | REF | 12 | TAS | 4 | N | O | I | CFC | 22 | 22 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1996-03-01 |  | 1996-12-01 | 2004-01-01 | 175000 | -96 | 174904 | 174904 | 100% | 0 | 0 | 0 | 22750 | -12 | 22738 | 0 | 0 | Completed in 1996. Financially completed in 2004. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | URU | SEV | 12 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -41688 | 58312 | 58312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at 7 plants (Aislaciones de Uruguay, Metalizadora Uruguaya, Thermopur, Kubal SA, Kalisay SA, J.C. Scarone, Eraton SA) | Individual | LAC | URU | FOA | 13 | INV | 6 | N | O | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-12-01 | 1999-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 | 0 | 86450 | 0 | 86450 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1994 | Investment
FIN | USA | Technical assistance in halon-1211 management |  | LAC | URU | HAL | 13 | TAS | 7 | A | O | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1994-09-01 |  | 1994-09-01 | 1994-09-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Project preparation assistance | Individual | LAC | URU | SEV | 13 | PRP | 8 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1995-01-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at 5 plants (Sudamtex del Uruguay, S.A., Ronit Ltd., Maxi, Divino S.A., Poliflex, Ltd.) | Individual | LAC | URU | FOA | 13 | INV | 9 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 2001-12-01 | 2003-08-01 | 200000 | -5109 | 194891 | 194891 | 100% | 0 | 0 | 0 | 26000 | -664 | 25336 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  |  |  | 1999-06-01 | [9 empty] | 1994 | Investment
CLO | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in thermal tanks at Tem, S.A. | Individual | LAC | URU | FOA | 15 | INV | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-08-01 |  |  | 1996-04-01 | 220300 | -220300 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Tem S.A. has closed down. The project was cancelled by the government on 4/29/96. Funds returned to Multilateral Fund 20th Meeting. |  |  | 1997-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in cold storage and substitution of CFC-12 used as refrigerant with HFC-134a at Colder S.R.L. | Individual | LAC | URU | REF | 15 | INV | 11 | N | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-08-01 |  | 1997-09-01 | 1998-08-01 | 325070 | 0 | 325070 | 325070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Company signed Subgrant Agreement in November '96. Implementation began in Fall /96. Product testing started in Fall /97. The project was completed in August 98. |  |  | 1997-12-01 | 1999-04-01 | [10 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foams used as insulation for refrigerators and substitution of CFC-12 used as refrigerant at Indurnor S.A. | Individual | LAC | URU | REF | 15 | INV | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-12-01 |  |  | 1999-07-01 | 448140 | -448140 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Indunor S.A. has closed down. The funds were returned to the Multilateral Fund on July 99 at the 28th Ex Com meeting |  |  | 1998-06-01 | 2000-01-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | Training in the halon sector |  | LAC | URU | HAL | 15 | TRA | 13 | A | O | I |  | 76.1 |  | 0 |  | 1994-12-01 | 1994-12-01 | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foam used as insulation in thermal tanks at Etchepare-Gil S.A. | Individual | LAC | URU | FOA | 15 | INV | 14 | N | O | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-08-01 |  | 1999-09-01 | 2000-01-01 | 235050 | 0 | 235050 | 235050 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project was technically completed by September 99 and financially completed in January 00. |  |  | 1997-09-01 | 1999-11-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | URU | SEV | 16 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 81278 | 0 | 81278 | 81278 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation is complete. Project is now under supervision. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Total aerosol sector phaseout project (technical assistance) | Individual | LAC | URU | ARS | 18 | TAS | 16 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1999-12-01 | 2001-12-01 | 54000 | -1 | 53999 | 53999 | 100% | 0 | 0 | 0 | 7020 | 0 | 7020 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [9 empty] | 1995 | Non-Investment
FIN | UNDP | Conversion of production of halon-1211 fire extinguishers at Tornay and Mori | Individual | LAC | URU | HAL | 18 | INV | 17 | N | O | I | Halon | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-05-01 |  | 1997-09-01 | 1999-12-01 | 38150 | 0 | 38150 | 38150 | 100% | 0 | 0 | 0 | 4960 | 0 | 4960 | 0 | 0 | Completed in 1997. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | UNDP | Transfer of technology and conversion of production of halon-1211 fire extinguishers at Izeta López Fire Company | Individual | LAC | URU | HAL | 18 | INV | 18 | N | O | I | Halon | 2.7 | 2.7 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-02-01 |  | 1996-12-01 | 1999-12-01 | 24225 | 0 | 24225 | 24225 | 100% | 0 | 0 | 0 | 3149 | 0 | 3149 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1995 | Investment
FIN | IBRD | Recovery and recycling of CFC-12 in maintenance workshops for industrial refrigeration equipment | Individual | LAC | URU | REF | 18 | TAS | 19 | N | O | I | CFC | 4 | 0 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-05-01 |  | 1999-10-01 | 2000-01-01 | 87647 | 0 | 87647 | 87647 | 100% | 0 | 0 |  | 11394.11 | 0 | 11394.11 | 0 | 0 | Implementation began in Fall'96. The funds were transferred to local UNDP office in September'97. During 1998 the equipment was purchased and the consultantwas paid. The equipment were distributed on March 99 . The project was completed by October 99. |  |  | 1997-06-01 | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 18 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project preparation completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Completing the elimination of CFC use in domestic refrigeration manufacturing by adoption of HCFC-141b as blowing agent and HFC-134a as refrigerant at Nevol S.A. | Individual | LAC | URU | REF | 19 | INV | 21 | N | O | I | CFC | 4.62 | 4.62 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-07-01 |  | 2000-02-01 | 1999-07-01 | 141512 | 0 | 141512 | 141512 | 100% | 0 | 0 |  | 18396.56 | 0 | 18396.56 | 0 | 0 | The project was completed in July 99 |  |  | 1997-07-01 | 1999-07-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 20 | INS | 22 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-10-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 116000 | 0 | 116000 | 116000 | 100% | 0 | 0 | 0 | 15080 | 0 | 15080 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1996 | Non-Investment
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 21 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project preparation completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Market survey to develop a country-wide scheme to phase out remaining ODS | Individual | LAC | URU | SEV | 22 | TAS | 24 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1998-07-01 | 1998-07-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0 | Time required for collecting and verifying consumption data was longer than originally anticipated. All disbursements have been made (US$ 23,000). Project completed. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | LAC | URU | REF | 23 | PRP | 25 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1998-11-01 |  | 1999-01-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1997 | Non Investment
FIN | UNIDO | Preparation of a demonstration project (tomatoes, cucumber, strawberries, flowers) | Individual | LAC | URU | FUM | 24 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 25 | INS | 27 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-07-01 | 2003-12-01 | 116000 | -19 | 115981 | 115981 | 100% | 0 | 0 | 0 | 15080 | -2 | 15078 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1998 | Non-Investment
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticultural crops (cucumbers and peppers), seedbeds and nurseries (vegetables, tobacco and forestry) | Individual | LAC | URU | FUM | 25 | DEM | 28 | A | O | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-06-01 | 299200 | -1381 | 297819 | 297819 | 100% | 0 | 0 |  | 38896 | -241 | 38655 | 0 | 0 | FIN
FIN | Canada | Implementation of the RMP: custom officers training programme | RMP | LAC | URU | REF | 27 | TRA | 29 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2003-06-01 | 2004-05-01 | 71190 | 0 | 71190 | 71190 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers programme in the refrigeration sector | RMP | LAC | URU | REF | 27 | TRA | 30 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2001-06-01 | 2002-03-01 | 63280 | 0 | 63280 | 63280 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Train-the-technicians workshop complete, 150 technicians trained. PCR submitted to Sect. |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation of a license/quota system for ODS | RMP | LAC | URU | REF | 27 | TAS | 31 | A | O | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2001-03-01 |  | 2001-11-01 | 2002-04-01 | 11300 | 0 | 11300 | 11300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed and licensing developed as planned. PCR Submitted to Sect |  | 1999 | [11 empty] | 1999 | Non-Inv.
FIN | IBRD | Preparation of an investment project in the domestic refrigeration sector |  | LAC | URU | REF | 30 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | [14 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of an investment project in the fumigants (methyl bromide) sector | Individual | LAC | URU | FUM | 30 | PRP | 33 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 25000 | -935 | 24065 | 24065 | 100% | 0 | 0 |  | 3250 | -126 | 3124 | 0 | 0 | FIN
FIN | IBRD | Terminal programme for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | Individual | LAC | URU | FOA | 31 | INV | 34 | N | O | I | CFC | 4.35 | 4.35 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2002-01-01 |  | 2003-05-01 | 2003-05-01 | 91300 | -80 | 91220 | 91220 | 100% | 0 | 0 |  | 11869 | -10 | 11858.6 | 0.4 | 0.4 | Project completed. | [13 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | UNIDO | Phase-out of methyl bromide in horticulture (tomatoes and cut flowers) | Individual | LAC | URU | FUM | 34 | INV | 35 | A | O | I | MBR | 24 | 15.4 |  |  | 2001-07-01 | 2002-02-01 | 2012-12-01 | 2012-12-01 |  |  | 469370 | 0 | 469370 | 469137 | 99.95% | 233 | 89 | 50 | 61018 | 0 | 60988 | 30 | 12 | Some test on Iodure methane, which could be a convincing alternative were finalized. The test with Iodure methane gave very good results. Monitoring of the phase out will be continued until the complete phase out is achieved. | According to the revised schedule approved by the 46th Excom,the consumption for the years 2007, 2009 should not be more than 8.9 ODP tons. In 2007, it was 8.4 and unofficial estimation suggests that for 2008 would be about 8.4 again. | [12 empty] | 2001 | INV
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | URU | SEV | 31 | INS | 35 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-07-01 | 2004-04-01 | 116000 | -196 | 115804 | 115804 | 100% | 0 | 0 | 0 | 15080 | -25 | 15055 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Non-Investment
COM | UNEP | Implementation of the RMP: Demonstration and training project for the use of hydrocarbons as refrigerants | Individual | LAC | URU | REF | 34 | TAS | 36 | A | O | I | CFC | 45.8 | 45.8 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2007-03-01 |  | 65000 | 0 | 65000 | 62169 | 95.64% | 2831 | 0 | 2831 | 8450 | 0 | 8081.97 | 368.03 | 0 | Project completed | [13 empty] | 2001 | Non Investment
ONG | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | LAC | URU | REF | 34 | TAS | 37 | N | O | I | CFC | 109.2 | 99 | 0 | 0 | 2001-07-01 | 2003-01-01 | 2007-08-01 | 2009-07-01 |  |  | 154934 | 0 | 154934 | 92865 | 59.94% | 62069 | 0 | 24827.6 | 20141 | 0 | 12072.1983 | 8068.8017 | 0 | Five out of the six companies completed the conversions. There is still one that could not comply with the requirements and a new candidate had to be identified during 2008, conversion expected to be completed in 2009. | [13 empty] | 2001 | Investment
FIN | UNDP | Development of an MDI transition strategy | Individual | LAC | URU | ARS | 36 | TAS | 38 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-12-01 | 2004-04-01 | 30000 | -2577 | 27423 | 27423 | 100% | 0 | 0 | 0 | 3900 | -335 | 3565 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Renewal of institutional strengthening project (Phase 5) | Individual | LAC | URU | SEV | 37 | INS | 39 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2006-01-01 |  | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 19604 | 0 | 19604 | 0 | 0 | Completed in 2006. | [13 empty] | 2002 | Non-Investment
ONG | UNDP | Transition strategy for the phase-out of CFCs use in MDIs | Individual | LAC | URU | ARS | 38 | TAS | 40 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2005-01-01 | 2009-12-01 | 2009-12-01 |  |  | 70000 | 0 | 70000 | 56995 | 81.42% | 13005 | 0 | 5202 | 9100 | 0 | 7409.35 | 1690.65 | 0 | During 2008, discussions continued with individual laboratories to discuss their plans for the replacement of CFC using MDIs with CFC-free alternatives. A workshop intended for patients was held in the City of Migues to help educate them on the change of propellant in the inhaler. Also during 2008 Uruguay presented the draft MDI transition strategy. | [13 empty] | 2002 | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | URU | SEV | 43 | INS | 41 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 |  | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Completed in 2007. | [13 empty] | 2004 | Non-Investment
ONG | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | URU | ARS | 43 | INV | 42 | N | O | I | CFC | 10 | 0 | 0 | 0 | 2004-07-01 | 2006-04-01 | 2007-07-01 | 2009-12-01 |  |  | 427023 | 0 | 427023 | 352070 | 82.45% | 74953 | 0 | 29981.2 | 32027 | 0 | 26405.4767 | 5621.5233 | 0 | Four out of the five formulas have been achieved, had pilot production and are currently in stability tests. The final one is expected to be completed on the first half of 2009. Project expected to be completed in December 2009. | [13 empty] | 2004 | Investment
COM | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | URU | SOL | 45 | TAS | 43 | N | O | I | TCA/CTC | 0.3 | 0.3 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 0 | Completed in 2007. | [13 empty] | 2005 | Non-Investment
COM | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | URU | PHA | 47 | PRP | 44 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-03-01 |  | 30000 | 0 | 30000 | 29982 | 99.94% | 18 | 0 | 18 | 2250 | 0 | 2248.65 | 1.35 | 0 | Completed in 2007. | [13 empty] | 2005 | Investment
ONG | UNDP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | URU | SEV | 49 | INS | 45 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-10-01 | 2009-05-01 |  |  | 150800 | 0 | 150800 | 83725 | 55.52% | 67075 | 0 | 26830 | 11310 | 0 | 6279.375 | 5030.625 | 0 | During 2008 the NOU successfully continued the implementation of projects in the remaining consumer sectors. On refrigeration, the implementation of the TPMP was accelerated, technicians received access to tools for good practices in servicing and several technicians trained in Good Practices of Refrigeration were hired in coordination with Refrigeration Technicians Association to disseminate conferences to emphasize the importance of reducing CFC emissions to the atmosphere with good practices. On the MDI conversion project the HFA equipment was successfully installed and formulation development started for 4 products. Upon consensus with the MDI importers, workshops were held in coordination and with the participation of the stakeholders for awareness rising. Meetings were also held with MDI users in coordination with manufacturers, importers, health authorities and specialist physicians. More information for the use of the seal “Ozono Amigo” (Friendly Ozone) was distributed upon request of interested parties and public awareness on Ozone Layer depletion was brought about through press conferences, publication of articles in mass media and the distribution of materials such as “20 Questions & Answers about the Ozone Layer Scientific Assessment about the Ozone Depletion” translated edited and published by the NOU. The NOU continued improving the automatization of the control system to implement the Decree that controls ODS imports and ban production, import and export of equipment and articles manufactured with or requiring CFC, and the imports of ODS. | [13 empty] | 2006 | Non-Investment
COM | UNDP | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | INV | 46 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 |  | 240000 | 0 | 240000 | 228983 | 95.41% | 11017 | 0 | 8813.6 | 18000 | 0 | 17173.725 | 826.275 | 0 | Completed in 2008. During 2008, Uruguay achieved the following results through the implementation of their TPMP; 22 Technicians/Teachers were trained in "Train the Trainers" workshop. 414 technicians were trained in the 2 workshops (6 courses each) on Good Practices in Refrigeration, held during the months of June and August . A total of 394 technicians have received their incentives package (tools) for good practices. During the month of September, courses were carried out on refrigerated transport and refrigeration in telecommunications (50 technicians) as well as on the use of ammonia as an alternate refrigerant. (50 technicians). Phase 2 approved at 56th ExCom. | [13 empty] | 2006 | Investment | 29.9 |  |  |  | Latest | Latest | Latest
ONG | Canada | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | TAS | 47 | A | O | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2008-01-09 | 2007-11-01 | 2009-07-09 |  |  | 160000 | 0 | 160000 | 143595 | 89.75% | 16405 |  | 16405 | 20800 | 0 | 11680 | 9120 |  | Activities were delayed due to delays in signing agreement. However, in 2008, substantial progress was made in training technicians on retrofit alternatives. Remaining activities related to enforcement expected to be completed by mid-2009. Target and consumption under BB and BC are for 2007. |  | 2006 | [11 empty] | 2006 | Investment | 29.9 | 29.3 |  |  | Yes
ONG | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | URU | PHA | 55 | PRP | 48 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-07-01 | 2010-04-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 0 | 150000 | 11250 | 0 | 0 | 11250 | 0 | Approved at 55th ExCom. Maintained initial discussions with NOU on the activities to be included in the preparation of the HPMP. Launching event programmed for April 2009 | [13 empty] | 2008 | Investment
ONG | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | URU | SEV | 56 | INS | 49 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-10-01 | 2010-10-01 |  |  | 150800 | 0 | 150800 | 0 | 0% | 150800 | 0 | 30160 | 11310 | 0 | 0 | 11310 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
ONG | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | INV | 50 | N | O | I | CFC | 69.7 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 48000 | 0 | 48000 | 0 | 0% | 48000 | 0 | 19200 | 3600 | 0 | 0 | 3600 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Investment
ONG | Canada | Terminal phase-out management plan for Annex A Group I Substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | TAS | 51 | A | O | I | CFC | 0 |  | 0 |  | 2008-11-01 |  | 2009-11-01 | 2010-03-10 |  |  | 42000 | 0 | 42000 | 0 | 0% | 42000 |  | 30000 | 5460 | 0 | 0 | 5460 |  | Project to be initiated in second quarter of 2009. Target and consumption under BB and BC are for 2008. |  | 2008 | [11 empty] | 2008 | Investment | 29.9 | 26.4 |  |  | Yes
FIN | UNEP | Country programme preparation | Individual | ASP | VAN | SEV | 17 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-06-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 2600 | -910 | 1690 | 0 | 0 | Project financially completed. | $ 7,000 plus $ 910 PSC returned ExCom 41 |  |  | 1999-12-01 | [9 empty] | 1995 | Non Investment
ONG | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | VAN | REF | 36 | TAS | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 | 2009-06-01 |  |  | 8000 | 0 | 8000 | 2983 | 37.29% | 5017 | 0 | 5016 | 1040 | 0 | 0 | 1040 | 1040 | Progress has stalled on drafting the regulations. Customs training workshop has not been held. |  | 2002
COM | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | VAN | SEV | 36 | INS | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2008-12-01 |  | 20250 | 0 | 20250 | 12250 | 60.49% | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008 | [13 empty] | 2002 | Non Investment
COM | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | VAN | REF | 36 | TAS | 4 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 |  | 26000 | 0 | 26000 | 14970 | 57.58% | 11030 | 0 | 11030 | 3380 | 0 | 0 | 3380 | 3380 | Participated in train-the-trainer workshops on “Good Practices in Refrigeration”. Project will be completed when the regional strategy as a whole is finalised. |  | 2002
ONG | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | VAN | SEV | 54 | INS | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-31 | 2009-12-31 |  |  | 6750 | 0 | 6750 | 0 | 0% | 6750 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | Draft Agreement was prepared and submitted to the country during December 2008. First disbursement will start after country receive final payment of previous IS phase from SPREP. | [13 empty] | 2008
FIN | UNDP | Technical assistance and training of servicing technicians in the refrigeration sector | RMP-Component | LAC | VEN | REF | 04 | TRA | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 30000 | -10980 | 19020 | 19020 | 100% | 0 | 0 | 0 | 3900 | -1427 | 2473 | 0 | 0 | Completed in 1992. Financially completed in 1997. | [13 empty] | 1991 | Non-Investment
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | VEN | SEV | 04 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 70419 | -57546 | 12873 | 12873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 06 | CPG | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 61591 | -36591 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | VEN | SEV | 06 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 107058 | 69729 | 176787 | 176787 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of a CFC-12 polystyrene foam production facility to use hydrocarbons as blowing agent at Plásticos Molanca | Individual | LAC | VEN | FOA | 07 | INV | 5 | N | O | I | CFC | 259 | 259 | 0 | 0 | 1992-06-01 | 1993-06-01 | 1993-06-01 |  | 1995-12-01 | 1996-04-01 | 1300000 | -38322 | 1261678 | 1261678.18 | 100% | -0.36 | -0.36 |  | 0 | 0 | 0 | 0 | 0 | ICR issued in May/96. The final project cost amounted to about US$2 million. The overrun was absorbed by enterprise. |  |  | 1995-03-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | USA | Technical assistance and demonstration project in CFC recycling in MAC |  | LAC | VEN | REF | 08 | DEM | 6 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1995-07-01 | 1998-09-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Assistance in country programme preparation |  | LAC | VEN | SEV | 08 | CPG | 7 | A | O | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto Venezolano de los Seguros Sociales | Individual | LAC | VEN | REF | 08 | INV | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1995-07-01 | 851000 | -851000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Cancelled. |  |  | 1994-04-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Clínica Atias, Hospitalización y Servicios | Individual | LAC | VEN | REF | 08 | INV | 9 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-10-01 | 1996-12-01 | 1994-04-01 |  | 1997-01-01 | 1997-02-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-01-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto de Prevencion Social del Médico | Individual | LAC | VEN | REF | 08 | INV | 10 | N | O | D | CFC | 2 | 2 | 0 | 0 | 1992-10-01 | 1995-12-01 | 1994-04-01 |  | 1995-09-01 | 1997-02-01 | 69000 | 0 | 69000 | 69000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Congreso de la Republica | Individual | LAC | VEN | REF | 08 | INV | 11 | N | O | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1998-05-01 | 65000 | -65000 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Retroactive project physically completed, but enterprise chose not to utilize MLF funds. Funds returned to MLF. |  |  | 1995-12-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Workshops for the recycling and banking of halons | Individual | LAC | VEN | HAL | 09 | TAS | 12 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26800 | -3700 | 23100 | 23100 | 100% | 0 | 0 | 0 | 3484 | -481 | 3003 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Institutional strengthening of FONDOIN | Individual | LAC | VEN | SEV | 09 | INS | 13 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1995-12-01 | 1998-12-01 | 329192 | 0 | 329192 | 329192 | 100% | 0 | 0 | 0 | 42795 | 0 | 42795 | 0 | 0 | Completed in 1995. Financially completed in 1998. | [13 empty] | 1993 | Non-Investment
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | VEN | SEV | 09 | PRP | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 156200 | 23305 | 179505 | 179505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Workshops for identification of projects in the refrigeration and air conditioning sector | Individual | LAC | VEN | REF | 09 | PRP | 15 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-12-01 | 1997-12-01 | 19800 | 0 | 19800 | 19800 | 100% | 0 | 0 | 0 | 2574 | 0 | 2574 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Investment
FIN | UNDP | Workshops on conversion and installation of new central air conditioning systems using non-ODS | RMP-Component | LAC | VEN | REF | 09 | TAS | 16 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26200 | -13000 | 13200 | 13200 | 100% | 0 | 0 | 0 | 3406 | -1690 | 1716 | 0 | 0 | Completed in 1994. Financially completed in 1997. | [13 empty] | 1993 | Non-Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in domestic refrigeration | RMP-Component | LAC | VEN | REF | 09 | TAS | 17 | A | O | I | CFC | 8 | 8 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1994-03-01 |  | 1996-12-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1993 | Investment
FIN | Canada | Technical assistance in halon sector | Halon Banking | LAC | VEN | HAL | 11 | TAS | 18 | A | O | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1997-11-01 |  | 1996-05-01 | 1996-05-01 | 414000 | -109500 | 304500 | 304500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1993 | 2000-01-01 | [10 empty] | 1993 | Non-Inv.
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a heat exchangers at Fabrica de Aparatos de Aire Acondicionado, S.A. (Faaca) | Individual | LAC | VEN | REF | 11 | INV | 19 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1995-11-01 |  | 1998-02-01 | 1998-02-01 | 3480000 | -380000 | 3100000 | 3100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a compressors and heat exchangers at Aire Acondicionado Integral, S.A. (Aaisa) | Individual | LAC | VEN | REF | 11 | INV | 20 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1996-09-01 |  | 1998-06-01 | 1998-10-01 | 620000 | 3800000 | 4420000 | 4420000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-09-01 | [11 empty] | INV | 0 | 0 | 0 | 0
FIN | UNDP | Finalization of the country programme | Individual | LAC | VEN | SEV | 11 | CPG | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1993 | Non-Investment
FIN | IBRD | Supervision of Faaca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -26845 | 20345 | 20345 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Aaisa project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -28772 | 18418 | 18418 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Plásticos Molanca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 83236 | 9685 | 92921 | 92921 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for finalizing project preparation and for project supervision. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of air conditioners project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 28665 | -22792 | 5873 | 5873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in MAC | RMP-Component | LAC | VEN | REF | 12 | DEM | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1997-12-01 | 13400 | 0 | 13400 | 13400 | 100% | 0 | 0 | 0 | 1742 | 0 | 1742 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Non-Investment
FIN | USA | Technical assistance in halon-1211 management |  | LAC | VEN | HAL | 13 | DEM | 27 | A | O | I | HAL | 2 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 31000 | 3000 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Demonstration project in MAC |  | LAC | VEN | REF | 13 | DEM | 28 | A | O | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1998-09-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | USA | Training in all ODS sectors in Venezuelan Military |  | LAC | VEN | SEV | 15 | TRA | 29 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 3500 | 43500 | 43500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Demonstration project in the refrigeration sector |  | LAC | VEN | REF | 15 | DEM | 30 | A | O | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1998-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | UNDP | Preparatory assistance for the domestic and commercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 15 | PRP | 31 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 40000 | 5445 | 45445 | 45445 | 100% | 0 | 0 | 0 | 5200 | 708 | 5908 | 0 | 0 | Completed in 1995. Financially completed in 1997. | [13 empty] | 1994 | Investment
FIN | UNDP | Pilot project for recovery and recycling of CFC-12 in MAC (Phase II) | RMP-Component | LAC | VEN | REF | 15 | TAS | 32 | A | O | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 1996-12-01 | 2000-12-01 | 220000 | -13204 | 206796 | 206796 | 100% | 0 | 0 | 0 | 28600 | -1717 | 26883 | 0 | 0 | Completed in 1996. Financially completed in 2000. | [13 empty] | 1994 | Investment
FIN | IBRD | Preparation/supervision of investment projects ODS V (Aaisa) (1995) |  | LAC | VEN | SEV | 16 | PRP | 33 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 22455 | 0 | 22455 | 22455 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is now complete. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (Faaca) (1995) |  | LAC | VEN | SEV | 16 | PRP | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 19121 | 0 | 19121 | 19121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I and II (1995) |  | LAC | VEN | SEV | 16 | PRP | 35 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 36430 | 0 | 36430 | 36430 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (central air chillers) (1995) |  | LAC | VEN | SEV | 16 | PRP | 36 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 23966 | 0 | 23966 | 23966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Preparatory assistance for the domestic and comercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 17 | PRP | 37 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-06-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Pinova, S.A. | Individual | LAC | VEN | REF | 17 | INV | 38 | A | O | I | CFC | 25 | 25 | 0 | 0 | 1995-07-01 | 1996-07-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 517500 | -149132 | 368368 | 368368 | 100% | 0 | 0 | 0 | 67275 | -19387 | 47888 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Conversion of CFC-12 to compressor production facilities at Vecomesa, S.A. to manufacture HFC-134a compressors | Individual | LAC | VEN | REF | 17 | INV | 39 | A | O | I | No_ODP | 0.7 | 0.7 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1999-12-01 | 2000-12-01 | 362000 | -193742 | 168258 | 168258 | 100% | 0 | 0 | 0 | 47060 | -25186 | 21874 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-07-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Industrias Nutal, C.A. | Individual | LAC | VEN | REF | 17 | INV | 40 | A | O | I | CFC | 14.5 | 14.5 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1997-01-01 |  | 2001-12-01 | 2002-03-01 | 123623 | 0 | 123623 | 123623 | 100% | 0 | 0 | 0 | 16071 | 0 | 16071 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  |  | 1997-12-01 |  | 2000-12-01 | [8 empty] | 1995 | Investment
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 18 | PRP | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-12-31 |  | 1996-12-31 | 1996-12-31 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project has been dropped in FY97. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Grupo Frigilux, C.A. | Individual | LAC | VEN | REF | 18 | INV | 42 | A | O | I | CFC | 46 | 46 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1997-05-01 |  | 1999-12-01 | 2000-12-01 | 953000 | -371693 | 581307 | 581307 | 100% | 0 | 0 | 0 | 123890 | -48320 | 75570 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-09-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coresmalt Valencia, C.A. | Individual | LAC | VEN | REF | 18 | INV | 43 | A | O | I | CFC | 65.5 | 65.5 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2000-09-01 | 2002-03-01 | 685330 | -6585 | 678745 | 678745 | 100% | 0 | 0 | 0 | 89093 | -856 | 88237 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  |  | 1997-12-01 | [10 empty] | 1995 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Manufacturera de Aparatos Domésticos, S.A. (Madosa) | Individual | LAC | VEN | REF | 18 | INV | 44 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1997-05-01 |  |  | 2001-12-01 | 230274 | -51266 | 179008 | 179008 | 100% | 0 | 0 | 0 | 29936 | -6665 | 23271 | 0 | 0 | Canceled in 1999. Financially completed in 2001. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | VEN | SEV | 18 | PRP | 45 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of refrigerated display cases and bottle coolers at Neve Industrial, C.A. | Individual | LAC | VEN | REF | 19 | INV | 46 | A | O | I | CFC | 7.5 | 7.5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2002-03-01 | 112100 | -3498 | 108602 | 108602 | 100% | 0 | 0 | 0 | 14573 | -455 | 14118 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  |  |  | 1999-07-01 | [9 empty] | 1996 | Investment
FIN | Canada | Halon recycling and bank management (Phase II) | Halon Banking | LAC | VEN | HAL | 19 | TAS | 47 | A | O | I |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1998-05-01 |  | 1998-05-01 | 1998-09-01 | 352220 | -69864 | 282356 | 282356 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented. Adjustment results from lower equipment prices and exchange rate fluctuations. |  | 1996 | 1997-06-01 | [10 empty] | 1996 | Non-Inv.
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Tecnocongeladores Venezolanos (Tecoven), C.A. | Individual | LAC | VEN | REF | 19 | INV | 48 | A | O | I | CFC | 13.2 | 13.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 190000 | -2599 | 187401 | 187401 | 100% | 0 | 0 | 0 | 24700 | -338 | 24362 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-07-01 | [9 empty] | 1996 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Hielomatic, C.A. | Individual | LAC | VEN | REF | 19 | INV | 49 | A | O | I | CFC | 11.1 | 11.1 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 2000-07-01 | 2001-12-01 | 162375 | -379 | 161996 | 161996 | 100% | 0 | 0 | 0 | 21109 | -49 | 21060 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  |  | 1998-04-01 | [10 empty] | 1996 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 20 | INS | 50 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 1998. Financially completed in 1999. | [13 empty] | 1996 | Non-Investment
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | VEN | FOA | 21 | PRP | 51 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 1998-12-01 | 2000-07-01 | 30000 | -927 | 29073 | 29073 | 100% | 0 | 0 |  | 3900 | -126 | 3774 | 0 | 0 | FIN
FIN | UNDP | Project preparation in commercial refrigeration recovery and recycling and in the production sector | Individual | LAC | VEN | SEV | 21 | PRP | 52 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-12-01 | 2000-12-01 | 155000 | -120000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 20150 | -15600 | 4550 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  |  |  | 1999-07-01 | [9 empty] | 1997 | Investment
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 21 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project has been dropped in FY97. | [14 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Phasing out ODS at Decocar | Individual | LAC | VEN | FOA | 22 | INV | 54 | A | O | I | CFC | 16.2 | 16.2 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2001-12-01 | 126614 | 0 | 126614 | 126614 | 100% | 0 | 0 |  | 16460 | -3 | 16457 | 0 | 0 | FIN
FIN | Canada | Implementation of a centralized reclamation plant for recovered refrigerants in the commercial refrigeration and air-conditioning sector | Individual | LAC | VEN | REF | 22 | TAS | 55 | A | O | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-06-01 | 1999-06-01 | 495285 | -6685 | 488600 | 488600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997 | [11 empty] | 1997 | Non-Inv.
FIN | UNIDO | Phasing out ODS at Veniber C.A. | Individual | LAC | VEN | FOA | 22 | INV | 56 | A | O | I | CFC | 21.6 | 21.6 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1998-12-01 | 2001-09-01 | 164592 | -62 | 164530 | 164530 | 100% | 0 | 0 |  | 21397 | -42 | 21355 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Daniven C.A. | Individual | LAC | VEN | FOA | 22 | INV | 57 | A | O | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2000-04-01 | 104030 | 0 | 104030 | 104030 | 100% | 0 | 0 |  | 13524 | -16 | 13508 | 0 | 0 | FIN
FIN | UNDP | Implementation of a recovery and reclamation of refrigerants | RMP-Component | LAC | VEN | REF | 22 | TAS | 58 | A | O | I | CFC | 172 | 172 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 2003-12-01 | 2003-12-01 | 931622 | -61553 | 870069 | 870069 | 100% | 0 | 0 | 0 | 121111 | -8002 | 113109 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  |  |  | 1999-06-01 | [9 empty] | 1997 | Investment
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 04 | CPG | 59 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 30313 | -27612 | 2701 | 2701 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNDP | Institutional strengthening of FONDOIN (renewal) | Individual | LAC | VEN | SEV | 17 | INS | 60 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 54900 | 54900 | 109800 | 109800 | 100% | 0 | 0 | 0 | 7137 | 7137 | 14274 | 0 | 0 | Completed in 1996. Financially completed in 1999. | [13 empty] | 1995 | Non-Investment
FIN | UNIDO | Phasing out ODS at Industrias Todos C.A., Caracas | Individual | LAC | VEN | FOA | 23 | INV | 61 | A | O | I | CFC | 17.8 | 17.8 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-19 | 137520 | 0 | 137520 | 137520 | 100% | 0 | 0 |  | 17878 | 0 | 17878 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane for Fanesi Barquisimeto | Individual | LAC | VEN | FOA | 24 | PRP | 62 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 10000 | -56 | 9944 | 9944 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 and CFC-12 withHCFC-141b and HFC-134a at INVITREL in the manufacture of commercial refrigeration equipment | Individual | LAC | VEN | REF | 25 | INV | 63 | A | O | I | CFC | 46.4 | 46.4 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2002-09-01 | 419094 | -1714 | 417380 | 417380 | 100% | 0 | 0 |  | 54482 | -309 | 54173 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC -11 with HCFC-141b at TECNOFRIGO in the production of rigid PU panels | Individual | LAC | VEN | FOA | 25 | INV | 64 | A | O | I | CFC | 9 | 9 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2001-01-01 | 2002-09-01 | 71946 | 0 | 71946 | 71946 | 100% | 0 | 0 |  | 9353 | -13 | 9340 | 0 | 0 | FIN |  |  |  |  | 2000-11-01
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 25 | INS | 65 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-07-01 | 2001-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Non-Investment
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Liderfrio in the production of rigid PU panels | Individual | LAC | VEN | FOA | 26 | INV | 66 | A | O | I | CFC | 13.9 | 13.9 |  |  | 1998-11-01 | 1999-12-01 | 2000-04-01 |  | 2000-12-01 | 2002-09-01 | 107850 | 0 | 107850 | 107850 | 100% | 0 | 0 |  | 14021 | -7 | 14014 | 0 | 0 | FIN
FIN | UNIDO | Workshop on alternatives to methyl bromide in tobacco cultivation | Individual | LAC | VEN | FUM | 27 | TRA | 67 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 1999-11-01 | 2001-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | -2 | 5198 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | LAC | VEN | FOA | 27 | PRP | 68 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-06-01 | 2001-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -2 | 1298 | 0 | 0 | FIN
CLO | UNDP | Preparation of one project in refrigeration MAC and compressors subsector | Individual | LAC | VEN | REF | 27 | PRP | 69 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1999. | [13 empty] | 1999 | Investment
FIN | UNIDO | Preparation of investment project in the foam sector (integral skin) | Individual | LAC | VEN | FOA | 27 | PRP | 70 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2002-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | LAC | VEN | REF | 27 | PRP | 71 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2000-10-01 | 2001-10-01 | 25000 | -325 | 24675 | 24675 | 100% | 0 | 0 |  | 3250 | -47 | 3203 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (polystyrene/ polyethylene) | Individual | LAC | VEN | FOA | 27 | PRP | 72 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -37 | 19963 | 19963 | 100% | 0 | 0 |  | 2600 | -9 | 2591 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Fricava C.A. | Individual | LAC | VEN | FOA | 27 | INV | 73 | A | O | I | CFC | 15.3 | 15.3 |  |  | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 115382 | 0 | 115382 | 115382 | 100% | 0 | 0 |  | 15000 | -10 | 14990 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by 100% water blown system in the production of moulded integral skin flexible PU foam at Fanesi | Individual | LAC | VEN | FOA | 27 | INV | 74 | A | O | I | CFC | 11.4 | 11.4 |  |  | 1999-03-01 | 1999-06-01 | 2000-08-01 |  | 2001-06-01 | 2002-12-01 | 157882 | 0 | 157882 | 157882 | 100% | 0 | 0 |  | 20525 | 0 | 20525 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the refrigeration/MACS and compressor sector | Individual | LAC | VEN | REF | 27 | PRP | 75 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2000-09-01 | 2002-09-01 | 20000 | -113 | 19887 | 19887 | 100% | 0 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at five commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 76 | A | O | I | CFC | 30.9 | 30.9 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 469140 | -64008 | 405132 | 405132 | 100% | 0 | 0 |  | 60988 | -8404 | 52584 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Novemeca in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 77 | A | O | I | CFC | 16.2 | 16.2 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2000-11-01 | 2002-09-01 | 69886 | -632 | 69254 | 69254 | 100% | 0 | 0 |  | 9085 | -96 | 8989 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Amerio Industrial S.A. in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 78 | A | O | I | CFC | 11.8 | 11.8 |  |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2001-07-01 | 2002-09-01 | 88039 | -173 | 87866 | 87866 | 100% | 0 | 0 |  | 11445 | -40 | 11405 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at three domestic refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 79 | A | O | I | CFC | 27 | 27 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 371705 | -75965 | 295740 | 295740 | 100% | 0 | 0 |  | 48322 | -9937 | 38385 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | LAC | VEN | FOA | 30 | PRP | 80 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-04-01 | 2002-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | VEN | REF | 30 | PRP | 81 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-06-01 | 2003-10-01 | 20000 | -124 | 19876 | 19876 | 100% | 0 | 0 |  | 2600 | -20 | 2580 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 at Fandec C.A. (EPSR Foam) | Individual | LAC | VEN | FOA | 28 | INV | 82 | A | O | I | CFC | 45 | 45 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2003-12-01 | 2004-07-01 | 290481 | 0 | 290481 | 290481 | 100% | 0 | 0 |  | 37763 | -15 | 37748 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 with HCFC-141b at Friobox in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 83 | A | O | I | CFC | 16.5 | 1.1 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  |  | 2003-05-01 | 128387 | -119558 | 8829 | 8829 | 100% | 0 | 0 |  | 16690 | -15544 | 1146 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Nevecor in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 84 | A | O | I | CFC | 36.4 | 36.4 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-11-01 | 2003-12-01 | 198374 | 0 | 198374 | 198374 | 100% | 0 | 0 |  | 25789 | -13 | 25776 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration sector (domestic/commercial) | Individual | LAC | VEN | REF | 31 | PRP | 85 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2002-05-01 |  | 2002-06-01 | 2003-05-01 | 30000 | -238 | 29762 | 29762 | 100% | 0 | 0 |  | 3900 | -37 | 3863 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | VEN | REF | 31 | TAS | 86 | A | O | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2002-12-01 | 2003-10-01 | 70000 | -2912 | 67088 | 67088 | 100% | 0 | 0 |  | 9100 | -392 | 8708 | 0 | 0 | FIN
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | VEN | SEV | 31 | INS | 87 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-12-01 | 2004-02-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2002. Financially completed in 2004. | [13 empty] | 2000 | Non-Investment
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at seven commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 32 | INV | 88 | A | O | I | CFC | 32.3 | 32.3 |  |  | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2005-05-01 | 2005-12-01 | 403590 | -84678 | 318912 | 318912 | 100% | 0 | 0 |  | 52467 | -11074 | 41393 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for two umbrella projects in the rigid foam sector | Individual | LAC | VEN | FOA | 33 | PRP | 89 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-12-01 | 20000 | -227 | 19773 | 19773 | 100% | 0 | 0 |  | 2600 | -34 | 2566 | 0 | 0 | FIN | [13 empty] | 2001 | INV
COM | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | Individual | LAC | VEN | SEV | 34 | TAS | 90 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2002-12-01 |  | 2005-12-01 |  | 80000 | 0 | 80000 | 35500 | 44.38% | 44500 | 0 | 44500 | 10400 | 0 | 4615 | 5785 | 0 | Project completed | [13 empty] | 2001 | Non Investment
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams (Umbrella No. 1: Frimac, Frizer, El Control, Incumaca, Frive, Lunger, Profibra, Recovenca, Refriven, Requiven, Tefiven and Vanger) | Individual | LAC | VEN | FOA | 34 | INV | 91 | A | O | I | CFC | 62.8 | 53.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2003-12-01 | 2005-02-01 | 438017 | -71323 | 366694 | 366694 | 100% | 0 | 0 |  | 56942 | -9347 | 47595 | 0 | 0 | FIN | [13 empty] | 2001 | INV
COM | UNEP | Training of customs officers | Individual | LAC | VEN | REF | 34 | TRA | 92 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-12-01 |  | 2005-12-01 |  | 120000 | -6164 | 113836 | 107836 | 94.73% | 6000 | 0 | 6000 | 15600 | -801 | 14018.68 | 780.32 | 0 | Project completed | $ 6,164 plus $ 801 PSC returned to ExCom 53 | [12 empty] | 2001 | Non Investment
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | LAC | VEN | PHA | 36 | PRP | 93 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-03-01 | 2003-07-01 |  | 2004-04-01 | 2004-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | -12 | 12338 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to water system as a blowing agent in the manufacture of flexible polyurethane foams at Manufacturas Enveta, C.A. Cumana | Individual | LAC | VEN | FOA | 36 | INV | 94 | A | O | I | CFC | 32 | 32 |  |  | 2002-03-01 | 2003-12-01 | 2004-03-01 |  | 2004-06-01 | 2004-12-01 | 198882 | 0 | 198882 | 198882 | 100% | 0 | 0 |  | 25855 | -15 | 25840 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | VEN | SEV | 37 | INS | 95 | N | T | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-07-01 | 285480 | -981 | 284499 | 284499 | 100% | 0 | 0 | 0 | 37112 | -127 | 36985.4 | -0.4 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2002 | Non-Investment
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid p.u. foams: Umbrella No. 2 project. | Individual | LAC | VEN | FOA | 38 | INV | 96 | A | O | I | CFC | 135.5 | 135.5 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-03-01 | 2006-05-01 | 851432 | -86779 | 764653 | 764653 | 100% | 0 | 0 |  | 103658 | -9679 | 93979 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | IBRD | Project preparation for the CFC production phase out project |  | LAC | VEN | PRO | 41 | PRP | 97 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2004-04-01 | 2004-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Project was prepared and subsequently approved at the 44th ExCom in Dec. 04. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | VEN | PHA | 42 | INV | 98 | A | O | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-09-01 | 2008-05-01 | 1895062 | 0 | 1895062 | 1895062 | 100% | 0 | 0 |  | 142130 | 0 | 142130 | 0 | 0 | Financial completion in May 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2003 | INV | 3262 | 2944.64 |  |  | Yes | Yes | Yes
COM | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | VEN | SEV | 43 | INS | 99 | N | T | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 |  | 285480 | 0 | 285480 | 285480 | 100% | 0 | 0 | 0 | 21411 | 0 | 21411 | 0 | 0 | Completed in 2007. | [13 empty] | 2004 | Non-Investment
COM | IBRD | Phased reduction and closure of the entire CFC production: 2004 annual programme | Multiyear | LAC | VEN | PRO | 44 | INV | 101 | N | O | I | CFC | 0 | 0 | 1487 | 1487 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 |  | 3300000 | 0 | 3300000 | 3300000 | 100% | 0 | 0 | 0 | 247500 | 0 | 247500 | 0 | 0 | Latest production audit for CY07 took place in Feb 08 - the 5th visit to PRODUVEN to audit and verify production close of CFC-11/12. Based on this onsite audit the following conclusions were drawn: There was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2007. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2007. | [13 empty] | 2004 | INV | 0 | 0 | 4400 | 3564.73 | Yes | Yes | Yes
COM | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | VEN | SEV | 45 | TAS | 102 | A | O | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 |  | 45872 | 0 | 45872 | 17963 | 39.16% | 27909 | 0 | 22327.2 | 4128 | 0 | 1616.482 | 2511.518 | 0 | Completed in 2008. HCFC reports submitted at 51st ExCom. All activities completed and accounts settled. | [13 empty] | 2005 | Non-Investment
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | LAC | VEN | SOL | 45 | TAS | 103 | A | O | I | TCA | 1.9 | 1.9 |  |  | 2005-04-01 | 2006-04-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -1005 | 38995 | 38995 | 100% | 0 | 0 |  | 3600 | -90 | 3510 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2005 | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | VEN | FUM | 45 | TAS | 104 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2008-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | Financial completion in Aug 2008. FIN: Total disbursement = Total approval. | [13 empty] | 2005 | NON-INV
COM | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | VEN | PHA | 45 | INV | 105 | A | O | I | CFC | 50.2 | 50.2 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2007-07-01 |  | 1631831 | 0 | 1631831 | 1060167 | 64.97% | 571664 | 416763 | 541615 | 122387 | 0 | 79513 | 42874 | 31257 | Financial completion may be delayed by few months. Any unspent balance will be returned to the MLF. | [10 empty] | 2007-12-01 |  |  | 2005 | INV | 400 | -120 |  |  | Yes | Yes | Yes
COM | IBRD | National CFC production closure plan (second tranche) | Multiyear | LAC | VEN | PRO | 46 | INV | 106 | N | O | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-04-01 |  | 8100000 | 0 | 8100000 | 8100000 | 100% | 0 | 0 | 0 | 607500 | 0 | 607500 | 0 | 0 | Latest production audit for CY07 took place in Feb 08 - the 5th visit to PRODUVEN to audit and verify production close of CFC-11/12. Based on this onsite audit the following conclusions were drawn: There was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2007. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2007. | [13 empty] | 2005 | INV | 0 | 0 | 2913 | 2451.4 | Yes | Yes | Yes
COM | IBRD | National CFC production closure plan (third tranche) | Multiyear | LAC | VEN | PRO | 48 | INV | 107 | N | O | I | CFC | 0 | 0 | 2931 | 2931 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 |  | 1750000 | 0 | 1750000 | 1714667 | 97.98% | 35333 | 35333 | 30000 | 131200 | 0 | 128551.03 | 2648.97 | 2648.97 | Latest production audit for CY07 took place in Feb 08 - the 5th visit to PRODUVEN to audit and verify production close of CFC-11/12. Based on this onsite audit the following conclusions were drawn: There was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2007. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2007. | [13 empty] | 2006 | INV | 0 | 0 | 2913 | 2876 | Yes | Yes | Yes
COM | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | VEN | SEV | 49 | INS | 108 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2008-07-01 |  | 2008-12-01 |  | 285480 | 0 | 285480 | 285479 | 100% | 1 | 0 | 0.8 | 21411 | 0 | 21410.925 | 0.075 | 0 | Completed in 2008. During 2008, awareness activities were organized at the Children's Museum. Within the Training Programme on Good Refrigeration Practices for technicians, 34 centers have been in operation; with 130 courses dictated to 1300 technicians. For the Recuperation, Regeneration and Reuse of ODS Programme, the centers have been selected; the supply of equipment has been planned and the centers are expected to begin operation in 2009. The study to replace domestic refrigerators for energy efficient refrigerators and for the elimination of CFC 12 was finalized, execution will begin in 2009. | [13 empty] | 2006 | Non-Investment
ONG | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | VEN | PHA | 51 | INV | 109 | A | O | I | CFC | 50 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 | 2009-12-01 |  |  | 2071831 | 0 | 2071831 | 368656 | 17.79% | 1703175 | 680034 | 1500000 | 155387 | 0 | 27649 | 127738 | 51003 | The recovery and recycling scheme is fully operational. A reclaiming equipment has been installed in the premises of PRODUVEN and is operating as part of the R&R system. At present 4395 refrigeration technicians have been trained and 3889 certified. The pilot plan is fully operational. A chiller program will be implemented based on incentive program and revolving funds. The data monitoring and reporting system, training and certification technician program will continue. | [13 empty] | 2007 | INV | 0 | -15 |  |  | Yes | Yes | Yes
ONG | IBRD | National CFC production closure plan (fourth tranche) | Multiyear | LAC | VEN | PRO | 52 | INV | 110 | N | O | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 | 2009-09-01 |  |  | 2300000 | 0 | 2300000 | 2200000 | 95.65% | 100000 | 100000 | 40000 | 172500 | 0 | 165000 | 7500 | 7500 | Latest production audit for CY07 took place in Feb 08 - the 5th visit to PRODUVEN to audit and verify production close of CFC-11/12. Based on this onsite audit the following conclusions were drawn: There was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2007. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2007. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 |  | Yes | Yes
COM | IBRD | National CFC production closure plan (fifth tranche) | Multiyear | LAC | VEN | PRO | 54 | INV | 111 | N | O | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2009-03-31 |  | 2008-12-01 |  | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 | 0 | 78700 | 0 | 78700 | 0 | 0 | Latest production audit for CY07 took place in Feb 08 - the 5th visit to PRODUVEN to audit and verify production close of CFC-11/12. Based on this onsite audit the following conclusions were drawn: There was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2007. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2007. Final verification report will be submitted to the 58th ExCom. | [13 empty] | 2007 | INV | 0 | 0 | 0 | 0 | Yes | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | VEN | PHA | 55 | PRP | 112 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2009-12-01 |  |  | 173750 | 0 | 173750 | 9619 | 5.536% | 164131 | 426 | 140000 | 13031 | 0 | 721 | 12310 | 32 | The survey of HCFC is being carried out by a national consultant in coordination with the NOU. An international consultant has been contracted for the preparation of the project document. The project is planned to be submitted to the third ExCom in 2009. | The consultant is leading the preparation of the HPMP, guiding the survey and the NOU in legislation and other issues. A group of national expert is cooperating in the survey of the different sectors. This consultant is expected to prepare the final document. The initial workshop will take place in June. The NOU is working on the legislation with the support of another consultant. | [12 empty] | 2008 | NON-INV
ONG | UNDP | Renewal of institutional strengthening project (phase IX) | Individual | LAC | VEN | SEV | 56 | INS | 113 | N | T | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2010-12-01 | 2010-12-01 |  |  | 285480 | 0 | 285480 | 0 | 0% | 285480 | 0 | 57096 | 21411 | 0 | 0 | 21411 | 0 | Newly approved in Nov 08. | [13 empty] | 2008 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | VIE | SEV | 12 | PRP | 1 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1994 | Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VIE | SEV | 13 | CPG | 2 | A | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-11-17 | 1995-10-01 |  | 1996-05-01 | 1996-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [13 empty] | 1994 | Non Investment
FIN | France | Country programme preparation |  | ASP | VIE | SEV | 13 | CPG | 3 | A | O | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-08-01 | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 30000 | -8965 | 21035 | 21035 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNIDO | Phasing out ODS at the Searefico and Searee industrial refrigeration plants of Seaprodex Co. | Individual | ASP | VIE | REF | 15 | INV | 4 | A | O | I | CFC | 40 | 40 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2000-07-01 | 497070 | -2690 | 494380 | 494380 | 100% | 0 | 0 |  | 64619 | -452 | 64167 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project proposals for the reduction of refrigerant emission and establishment of collection and reclaiming network in domestic refrigeration sector | Individual | ASP | VIE | REF | 15 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-09-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 15000 | -14776 | 224 | 224 | 100% | 0 | 0 |  | 1950 | -1921 | 29 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for reduction of refrigerant emissions and conversion of food processing and other industrial refrigeration and A/C equipment to suitable alternatives | Individual | ASP | VIE | REF | 15 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -11168 | 8832 | 8832 | 100% | 0 | 0 |  | 2600 | -1454 | 1146 | 0 | 0 | FIN
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Saigon Cosmetics Company | Individual | ASP | VIE | ARS | 17 | INV | 7 | A | O | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 1998-08-01 | 2000-12-01 | 238430 | -2439 | 235991 | 235991 | 100% | 0 | 0 | 0 | 30996 | -317 | 30679 | 0 | 0 | Completed in 1998. Financially completed in 2000. | [13 empty] | 1995 | Investment
FIN | UNEP | Establishment of the ozone unit (institutional strengthening) | Individual | ASP | VIE | SEV | 17 | INS | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 1999-04-01 | 1999-11-01 | 137280 | 0 | 137280 | 137280 | 100% | 0 | 0 | 0 | 17846.4 | 0 | 17846.4 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1995 | Non Investment
FIN | UNEP | Technology cooperation workshop for ODS elimination | Individual | ASP | VIE | SEV | 17 | TRA | 9 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1995-12-01 |  | 1996-06-01 | 1999-04-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | Project financially completed. | [13 empty] | 1995 | Non Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at Daso Company Ltd. | Individual | ASP | VIE | ARS | 18 | INV | 10 | A | O | I | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1999-12-01 | 2001-08-01 | 110340 | -320 | 110020 | 110020 | 100% | 0 | 0 | 0 | 14344 | -41 | 14303 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  |  |  | 1999-06-01 | [9 empty] | 1995 | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Cosmetics Producing and Trading Company (CP & T) | Individual | ASP | VIE | ARS | 18 | INV | 11 | A | O | I | CFC | 85 | 85 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 2002-05-01 | 2003-11-01 | 285120 | -2641 | 282479 | 282479 | 100% | 0 | 0 | 0 | 37066 | -343 | 36723 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  |  |  | 1999-09-01 | [9 empty] | 1995 | Investment
FIN | France | Technical assistance on alternative technologies for cold storage facilities and project preparation |  | ASP | VIE | REF | 20 | TAS | 12 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-09-01 | 1999-05-01 | 40000 | -5500 | 34500 | 34500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNDP | Demonstration project in CFC recycling and emissions reduction in the commercial refrigeration sector | RMP-Component | ASP | VIE | REF | 20 | DEM | 13 | A | O | I | CFC | 28.2 | 28.2 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1998-09-01 |  | 2002-12-01 | 2004-09-01 | 168216 | -10238 | 157978 | 157978 | 100% | 0 | 0 | 0 | 21868 | -1331 | 20537 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  |  |  | 2000-07-01 | [9 empty] | 1996 | Non-Investment
FIN | Australia | Demonstration project CFC recycling and emissions reduction in the commercial refrigeration sector | Individual | ASP | VIE | REF | 20 | DEM | 14 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1997-12-01 |  | 2001-12-01 | 1905-06-26 | 282687 | -42162 | 240525 | 240525 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed |  | 1996 | 1997-12-01
FIN | USA | MAC servicing demonstration project |  | ASP | VIE | REF | 20 | DEM | 15 | A | O | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-03-01 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 300000 | -159091 | 140909 | 140909 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Terminated. |  | 1996 | 1998-12-01
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | VIE | FUM | 22 | PRP | 16 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  |  | 1999-02-01
CLO | UNDP | Project preparation in the domestic refrigeration sub-sector | Individual | ASP | VIE | REF | 22 | PRP | 17 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-12-01 |  |  | 1998-07-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 | 0 | 3250 | -3250 | 0 | 0 | 0 | Canceled in 1998. | [13 empty] | 1997 | Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | VIE | REF | 23 | PRP | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-07-01 | 2002-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1997 | Non Investment
FIN | UNDP | Project preparation for one project in the aerosol sector | Individual | ASP | VIE | ARS | 24 | PRP | 19 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1998 | Investment
FIN | UNIDO | Alternatives to the use of methyl bromide on stacked bags of rice, grain in silos and timber on a warehouse under tarps at Vietnam Fumigation Company | Individual | ASP | VIE | FUM | 24 | DEM | 20 | A | O | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2003-12-01 | 2004-12-01 | 411180 | -9744 | 401436 | 401436 | 100% | 0 | 0 |  | 53453 | -1349 | 52104 | 0 | 0 | FIN
FIN | UNDP | Preparation of two projects in general foam subsector | Individual | ASP | VIE | FOA | 27 | PRP | 21 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. | [13 empty] | 1999 | Investment
FIN | France | CFC emission reductions in spinning halls air conditioning systems chillers (pilot project) |  | ASP | VIE | REF | 28 | INV | 22 | A | O | I | CFC | 3.6 | 3.6 | 0 |  | 1999-07-01 | 2001-06-12 | 2001-08-01 |  | 2002-12-31 | 2002-12-01 | 197340 | 0 | 197340 | 197340 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed | [6 empty] | 2002-12-01
FIN | UNIDO | Technical assistance in preparation of the national halon bank management programme | Individual | ASP | VIE | HAL | 29 | TAS | 23 | A | O | I | HAL | 37.1 | 37.1 |  |  | 1999-11-01 | 2000-09-01 | 2000-12-01 |  | 2003-01-01 | 2003-12-01 | 25000 | -7148 | 17852 | 17852 | 100% | 0 | 0 |  | 3250 | -933 | 2317 | 0 | 0 | FIN
FIN | UNDP | Preparation of a project in the foam general sector | Individual | ASP | VIE | FOA | 30 | PRP | 24 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -625 | 19375 | 19375 | 100% | 0 | 0 | 0 | 2600 | -81 | 2519 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of a project in the aerosol sector | Individual | ASP | VIE | ARS | 30 | PRP | 25 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 10000 | -2192 | 7808 | 7808 | 100% | 0 | 0 | 0 | 1300 | -285 | 1015 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of a project in the refrigeration recycling subsector | Individual | ASP | VIE | REF | 30 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 5000 | -1096 | 3904 | 3904 | 100% | 0 | 0 | 0 | 650 | -142 | 508 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 2000 | Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | ASP | VIE | SEV | 28 | INS | 27 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-06-01 | 2001-12-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 | 0 | 11897.6 | 0 | 11897.6 | 0 | 0 | Project financially completed. |  |  |  |  | 2001-06-01 | [8 empty] | 1999 | Non Investment
FIN | UNDP | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | Individual | ASP | VIE | ARS | 31 | INV | 28 | A | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2003-08-01 |  | 2005-06-01 | 2008-10-01 | 49720 | 0 | 49720 | 49720 | 100% | 0 | 0 | 0 | 6464 | 0 | 6464 | 0 | 0 | Completed in 2005. Financially completed in 2008. | [13 empty] | 2000 | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | VIE | REF | 33 | PRP | 29 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | ASP | VIE | SEV | 33 | INS | 30 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-08-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 | 0 | 11897.6 | 0 | 11897.6 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | VIE | ARS | 33 | PRP | 31 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | ASP | VIE | FOA | 33 | PRP | 32 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNEP | Implementation of the RMP: Workshop for finalisation of regulations | Individual | ASP | VIE | REF | 34 | TAS | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2001-10-01 |  | 2002-01-01 | 2003-06-01 | 4350 | 0 | 4350 | 4350 | 100% | 0 | 0 | 0 | 565.5 | 0 | 565.5 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
TRF | Australia | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | Individual | ASP | VIE | REF | 34 | TAS | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 290413 | -290413 | 0 | 0 |  | 0 | 0 | 0 | 37754 | -37754 | 0 | 0 | 0 | Transferred to UNDP- 35th ExCom |  | 2001
FIN | UNDP | Implementation of the RMP: MAC recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 34 | TAS | 35 | A | O | I | CFC | 5.8 | 5.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-01-01 | 50500 | 0 | 50500 | 50500 | 100% | 0 | 0 | 0 | 6565 | 0 | 6565 | 0 | 0 | Completed in 2003. Financially completed in 2007. | [13 empty] | 2001 | Non-Investment
FIN | UNEP | Implementation of the RMP: Train the trainer programme in the refrigeration servicing sector | Individual | ASP | VIE | REF | 34 | TRA | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2006-02-01 | 200000 | -40959 | 159041 | 159041 | 100% | 0 | 0 | 0 | 26000 | -5325 | 20675.33 | -0.33 | 0 | Project financially completed. | $ 40,959 plus $ 5,325 returned ExCom 46 | [12 empty] | 2001 | Non Investment
FIN | Poland | Implementation of the RMP: Customs training programme | RMP Update | ASP | VIE | REF | 34 | TAS | 37 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-01-01 |  | 2003-01-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Reason for delays in completion of Phase I of the Project was a delay in the payment of Polish contribution covering a cost of the project because of problems with national budget. Payment of outstanding contribution was confirmed through a letter of 21 March 2002 from the UN Office in Nairobi (CP/4040-01-71).
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | ASP | VIE | REF | 34 | TAS | 38 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-01-01 | 21600 | -242 | 21358 | 21358 | 100% | 0 | 0 | 0 | 2808 | -31 | 2777 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Non-Investment
FIN | UNDP | Implementation of the RMP: Programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 35 | TAS | 39 | A | O | I | CFC | 17 | 17 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2007-03-01 | 290413 | -22502 | 267911 | 267911 | 100% | 0 | 0 | 0 | 37754 | -2925 | 34829 | 0 | 0 | Completed in 2004. Financially completed in 2007. | [13 empty] | 2001 | Non-Investment
FIN | UNDP | Terminal umbrella project for the aerosol sector to phase-out ODS consumption in the manufacture of aerosols and perfumes by conversion to hydrocarbon propellant (Dong A and Thorakao Cosmetics Ltd.) | Individual | ASP | VIE | ARS | 37 | INV | 40 | A | O | I | CFC | 28.5 | 28.5 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-04-01 |  | 2005-06-01 | 2007-03-01 | 125400 | 0 | 125400 | 125400 | 100% | 0 | 0 | 0 | 16302 | 0 | 16302 | 0 | 0 | Completed in 2005. Financially completed in 2007. | [13 empty] | 2002 | Investment
FIN | IBRD | Preparation of a national CFC phase-out plan |  | ASP | VIE | PHA | 39 | PRP | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Project preparation completed and project approved at the 45th ExCom. | [13 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | ASP | VIE | SEV | 40 | INS | 42 | A | T | I | CFC | 9.8 | 10.2 | 0 | 0 | 2003-07-01 | 2004-01-04 | 2005-07-01 |  | 2005-07-01 | 2007-12-01 | 118976 | -20 | 118956 | 118956 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 20 plus returned to ExCom 50 | [12 empty] | 2003 | Non Investment
FIN | IBRD | Project preparation for methyl bromide phase-out plan |  | ASP | VIE | FUM | 44 | PRP | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2006-11-01 | 2006-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 4875 | 0 | 4875 | 0 | 0 | Project prepared, submitted and approved at the 50th ExCom Meeting. | [13 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC and halon phase-out plan (first tranche) | Multiyear | ASP | VIE | PHA | 45 | INV | 45 | N | O | I | CFC | 40 | 40 | 0 | 0 | 2005-04-01 | 2006-11-01 | 2007-04-01 |  | 2008-07-01 |  | 495537 | 0 | 495537 | 495537 | 100% | 0 | 0 | 0 | 37165 | 0 | 37165 | 0 | 0 | Final disbursement of this funding tranche was made in Mar 08. A total number of 641 service tool kits distributed and paid for. Part of the costs of the 641 service tool kits was covered by this first tranche. | [13 empty] | 2004 | INV | 258.7 | 241 | 0 | 0 | Yes | Yes | Yes
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | ASP | VIE | SEV | 46 | INS | 46 | A | T | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
ONG | IBRD | National CFC and halon phase-out plan (second tranche) | Multiyear | ASP | VIE | PHA | 49 | INV | 47 | N | O | I | CFC | 165 | 165 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 | 2010-07-01 |  |  | 586000 | 0 | 586000 | 445802.15 | 76.08% | 140197.85 | 140197.85 | 140197.85 | 43950 | 0 | 33435.16 | 10514.84 | 10514.84 | Training of service technicians and provision of service tool kits will be completed in 2009. All training centers that are part of the project have already incorporated good practices in refrigeration and MAC services into their main curriculum. All selected vehicle inspection centers have received refrigerant identifiers. A voluntary MAC inspection program will start in 2009. | [13 empty] | 2006 | INV | 218.5 | 148.7 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National phase-out plan of out methyl bromide (first tranche) | Multiyear | ASP | VIE | FUM | 50 | INV | 48 | N | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 | 2010-12-01 |  |  | 230000 | 0 | 230000 | 0 | 0% | 230000 | 230000 | 220000 | 17250 | 0 | 0 | 17250 | 17250 | A launch workshop for the methyl bromide sector plan was organized on 26 Nov 08. PMU has been established within the Plant Protection Department and will be fully operational in Jan. 09. Priority actions for 2009 include strenthenging of existing training centers to carry out training on MB alternatives, assessment of MB alternatives for soil fumigation applications, and policy and regulatory activities. | [13 empty] | 2005 | INV | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | VIE | SEV | 52 | INS | 49 | A | T | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-06-30 | 2009-06-30 |  |  | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RNC visited country in February 2008 to review IS implementation and discuss licensing system to monitor HCFC. o For 2008, CFC quota of 40 MT was issued to 6 importers. Audited CFC import was only 20.4 MT, much lower than allowable quota. No quota issued | [13 empty] | 2007 | Non Investment
ONG | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | VIE | PHA | 55 | PRP | 50 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 | 2010-09-01 |  |  | 195000 | 0 | 195000 | 0 | 0% | 195000 | 195000 | 100000 | 14625 | 0 | 0 | 14625 | 14625 | Project preparation activities will start in the first quarter of 2009. | [13 empty] | 2008 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC and halon phase-out plan (third tranche) | Multiyear | ASP | VIE | PHA | 55 | INV | 51 | N | O | I | CFC | 58.7 | 0 | 0 | 0 | 2008-07-01 |  | 2010-07-31 | 2010-07-31 |  |  | 178463 | 0 | 178463 | 0 | 0% | 178463 | 178463 | 50000 | 13385 | 0 | 0 | 13385 | 13385 | Training of service technicians and provision of service tool kits will be completed in 2009. All training centers that are part of the project have already incorporated good practices in refrigeration and MAC services into their main curriculum. All selected vehicle inspection centers have received refrigerant identifiers. A voluntary MAC inspection program will start in 2009. | [13 empty] | 2007 | INV | 58.7 | 20 | 0 | 0 | Yes | Yes | No
FIN | UNEP | Country programme preparation | Individual | ASP | YEM | SEV | 19 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Project financially completed. | [13 empty] | 1996 | Non Investment
FIN | UNEP | Establishment of a National Ozone Unit | Individual | ASP | YEM | SEV | 25 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-02-22 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Project financially completed. | [13 empty] | 1998 | Non Investment
CLO | UNIDO | Preparation of project in the foam sector | Individual | ASP | YEM | FOA | 27 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of project in the aerosol sector | Individual | ASP | YEM | ARS | 27 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2001-10-01 | 20000 | -2885 | 17115 | 17115 | 100% | 0 | 0 |  | 2600 | -379 | 2221 | 0 | 0 | FIN
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | YEM | REF | 27 | PRP | 5 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-12-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project financially completed. | [5 empty] | 2001-09-01 | [7 empty] | 1999 | Non Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | YEM | REF | 33 | PRP | 6 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2003-07-01 | 15000 | -1934 | 13066 | 13066 | 100% | 0 | 0 | 0 | 1950 | -251 | 1699 | 0 | 0 | Completed in 2002. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | ASP | YEM | REF | 33 | PRP | 7 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-07-01 | 2003-10-01 | 20000 | -3268 | 16732 | 16732 | 100% | 0 | 0 |  | 2600 | -428 | 2172 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Phase out of CFC-11, CFC-12 and CFC-114 in the manufacture of aerosols by conversion to hydrocarbon propellant at Arabia Felix Industries Ltd. | Individual | ASP | YEM | ARS | 34 | INV | 8 | A | O | R | CFC | 96.6 | 96.6 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-05-01 | 2005-12-01 | 366804 | -5910 | 360894 | 360894 | 100% | 0 | 0 |  | 34676 | -613 | 34063 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | Germany | Preparation for phase-out investment project for methyl bromide sector | Individual | ASP | YEM | FUM | 34 | PRP | 9 | A | O | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-05-01 | 2002-01-01 |  | 2003-12-01 | 2004-04-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project to reduce MB consumtion by 9.1 ODP tonnes approved at 41st ExCom.
FIN | UNIDO | Phase out of CFC-12 in the manufacture of aerosols by conversion to hydrocarbon propellant at Al-Thowra Industrial Complex | Individual | ASP | YEM | ARS | 34 | INV | 10 | A | O | I | CFC | 82.7 | 82.7 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-04-01 | 2004-09-01 | 179508 | 0 | 179508 | 179508 | 100% | 0 | 0 |  | 23336 | -33 | 23303 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Nagman Co. | Individual | ASP | YEM | REF | 35 | INV | 11 | A | O | I | CFC | 7.3 | 7.3 |  |  | 2001-12-01 | 2002-04-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 105641 | -1328 | 104313 | 104313 | 100% | 0 | 0 |  | 13733 | -194 | 13539 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Styrco | Individual | ASP | YEM | REF | 35 | INV | 12 | A | O | I | CFC | 6.1 | 6.1 |  |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 90231 | -1456 | 88775 | 88775 | 100% | 0 | 0 |  | 11730 | -208 | 11522 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNEP | Renewal of the institutional strengthening project | Individual | ASP | YEM | SEV | 35 | INS | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2003-12-01 | 2004-12-01 | 118000 | 0 | 118000 | 118000 | 100% | 0 | 0 | 0 | 15340 | 0 | 15340 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
CLO | UNIDO | Preparation of a terminal investment project in commercial refrigeration sector | Individual | ASP | YEM | REF | 36 | PRP | 14 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-04-01 |  |  | 2003-05-01 | 10000 | -2349 | 7651 | 7651 | 100% | 0 | 0 |  | 1300 | -307 | 993 | 0 | 0 | CLO | [13 empty] | 2002 | INV
COM | UNDP | Implementation of the RMP: national recovery and recycling programme for refrigerants in the commercial and MAC sectors | RMP-Component | ASP | YEM | REF | 37 | TAS | 15 | A | O | I | CFC | 220 | 220 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2007-12-01 |  | 1472730 | 0 | 1472730 | 1433154 | 97.31% | 39576 | 0 | 31660.8 | 172000 | 0 | 167378.2146 | 4621.7854 | 0 | Completed in 2007. | [13 empty] | 2002 | Investment
COM | UNEP | Implementation of the RMP: establishment of regulations and legislation | Individual | ASP | YEM | REF | 37 | TAS | 16 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2004-01-01 |  | 2006-12-01 |  | 25000 | 0 | 25000 | 20000 | 80% | 5000 | 0 | 5000 | 3250 | 0 | 2600 | 650 | 0 | Project completed | [13 empty] | 2002 | Non Investment
COM | UNEP | Implementation of the RMP: training programme on good practices in refrigeration | Individual | ASP | YEM | REF | 37 | TRA | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-04-01 | 2005-08-01 |  | 2008-12-01 |  | 189500 | 0 | 189500 | 179500 | 94.72% | 10000 | 10000 | 10000 | 24635 | 0 | 23335 | 1300 | 1300 | Project completed in December 2008. Training of the two phases and supply iof training equipment to 5 national training centers | [13 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | YEM | REF | 37 | TRA | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 | 2010-03-01 |  |  | 91825 | 0 | 91825 | 83325 | 90.74% | 8500 | 8500 | 8500 | 11937.25 | 0 | 10832.25 | 1105 | 1105 | Phase I of the training project is completed and phase II started. Delay in starting the project was due to the delay in establishing the comprehensive ODS legislation and its bylaws | [13 empty] | 2002 | Non Investment
ONG | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | YEM | REF | 37 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2007-10-01 | 2005-08-01 | 2009-12-01 |  |  | 57750 | 0 | 57750 | 25000 | 43.29% | 32750 | 32750 | 32750 | 7507.5 | 0 | 3250 | 4257.5 | 4257.5 | National monitoring teams are formulated under supervision of NOU, project will continue in 2009 to monitor remaining cutoms training and distribution of R&R equipment | [13 empty] | 2002 | Non Investment
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | ASP | YEM | SEV | 41 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 104000 | -391 | 103609 | 103609 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | $ 391 returned to ExCom 51 | [12 empty] | 2003 | Non Investment
COM | Germany | Technical assistance programme for the phase-out of methyl bromide in agriculture | Individual | ASP | YEM | FUM | 41 | TAS | 21 | A | O | I | MBR | 9.1 | 17.06 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2008-04-08 |  | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | 2008: 50 Rolls of thermal polyethylene sheets for Solar Fumigation were purchased. Farmers were identified that received the solarization sheets and were trained in the usage. More field visits to farmers promoting MB alternatives took place. A consulting meeting with 34 farmes was conducted. A Train of Trainers course for Custom Officers on controlling ODSs was held. All project activities were successfully completed. The PCR will be submitted in 2009. | [13 empty] | 1997
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | ASP | YEM | SOL | 45 | TAS | 22 | A | O | I | TCA | 0.2 | 0.2 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 35000 | -164 | 34836 | 34836 | 100% | 0 | 0 |  | 3150 | -15 | 3135 | 0 | 0 | FIN | [13 empty] | 2005 | INV
FIN | UNIDO | Preparation of a terminal umbrella project in refrigeration (CFC) | Individual | ASP | YEM | REF | 45 | PRP | 23 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2008-04-01 | 2008-09-01 | 30000 | -453 | 29547 | 29547 | 100% | 0 | 0 |  | 2250 | -34 | 2216 | 0 | 0 | Project completed in Apr 2008. Financial completion in Sep 2008. Refund was reported to 56th ExCom, Nov 2008. FIN. | [13 empty] | 2005 | NON-INV
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | YEM | SEV | 47 | INS | 24 | A | T | I | CFC | 8.6 | 8.6 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2005 | Non Investment
FIN | UNEP | Extension of the institutional strengthening project (phase IV-supplementary request) | Individual | ASP | YEM | SEV | 48 | INS | 25 | A | T | I | CFC | 5.4 | 0 | 0 | 0 | 2006-04-01 | 2006-06-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | [13 empty] | 2006 | Non Investment
ONG | UNEP | Project preparation for a national phase-out management plan | RMP | ASP | YEM | PHA | 50 | PRP | 26 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-04-01 | 2007-11-01 | 2009-11-01 |  |  | 50000 | 0 | 50000 | 40000.3 | 80% | 9999.7 | 10000 | 9999.7 | 6500 | 0 | 5200.039 | 1299.961 | 1300 | Country contract signed, international consultant recruited, country visit completed, information and data compilation completed, PD developed and submitted for the 57th ExCom | [13 empty] | 2006 | Non Investment
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | YEM | SEV | 53 | INS | 27 | A | T | I | CFC | 14 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 | 2009-11-01 |  |  | 170000 | 0 | 170000 | 60000 | 35.29% | 110000 | 110000 | 110000 | 0 | 0 | 0 | 0 | 0 | Project completed upon country submission of signed expenditure report, audited report and terminal report of full phase IV of Yemen ISP. Accordingly Phase V started as per schedule. | [13 empty] | 2007 | Non Investment
ONG | UNIDO | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | INV | 28 | A | O | I | CFC | 339.4 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-12-31 | 2009-12-01 |  |  | 1137500 | 0 | 1137500 | 9679 | 0.8509% | 1127821 | 255883 | 300000 | 85313 | 0 | 726 | 84587 | 19191 | The equipment for the refrigeration manufacturing and servicing components of the project were purchased at the end of December 2008. A specialized foam expert was recruited and visited Yemen in early December 2008 to assess the situation of the 10 commercial refrigeration companies and study the feasibility of implementing hydrocarbon technology. The Government is considering merging 5 companies and providing them with Hydrocarbon machinery, while the rest will be supplied with HCFC machinery. | UNIDO is in touch with the Secretariat to clarify whether a change in the agreement is needed. | [12 empty] | 2008 | INV | 269.4 | 269.4 |  |  | Not yet confirmed | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | YEM | PHA | 55 | PRP | 29 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 |  | 2009-07-31 | 2009-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 10000 | 5250 | 0 | 0 | 5250 | 0 | The identification of national experts/consutancy firms to carry out the survey is in process. The first stakeholder consultation workshop will take place in April 2009. | Legislation related matters are part of the responsibility of UNEP. | [12 empty] | 2008 | NON-INV
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | YEM | PHA | 55 | PRP | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-31 | 2009-07-31 |  |  | 125000 | 0 | 125000 | 18751 | 15% | 106249 | 0 | 106249 | 16250 | 0 | 2437.63 | 13812.37 | 0 | Work-plan agreed with country and UNIDO, contractual arrangements and survey started in 2009 | [13 empty] | 2008
ONG | UNEP | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | TAS | 31 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-12-31 | 2010-12-31 |  |  | 315000 | 0 | 315000 | 0 | 0% | 315000 | 195000 | 315000 | 40950 | 0 | 0 | 40950 | 25350 | Country contract signed, work-plan agreed and implmentation started (first disbursement took place Jan 09) | [13 empty] | 2008
ONG | Germany | Terminal phase-out of methyl bromide (first tranche, part 1) | Multi-Year | ASP | YEM | FUM | 56 | INV | 32 | A | O | I | MBR | 5.9 | 0 | 0 |  | 2008-11-01 |  | 2014-12-01 | 2014-12-01 |  |  | 109740 | 0 | 109740 | 0 | 0% | 109740 | 0 | 109740 | 13896 | 0 | 0 | 13896 | 0 | An activity plan for 2009 has been finalized and first activites are starting in 2009.
FIN | UNIDO | Country Programme preparation | Individual | EUR | YUG | SEV | 21 | CPG | 1 | A | O | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-08-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | IBRD | Country programme preparation |  | EUR | YUG | SEV | 04 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 20302 | -14877 | 5425 | 5425 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | EUR | YUG | SEV | 04 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 21432 | -21432 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | UNIDO | Preparation of an investment project in the refrigeration sector for phasing out ODS at Obod | Individual | EUR | YUG | REF | 23 | PRP | 4 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-07-01 | 1998-03-01 |  | 1999-12-01 | 2000-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -1 | 1299 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the solvent sector for phasing out ODS at Hemofarm | Individual | EUR | YUG | SOL | 23 | PRP | 5 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-02-01 | 2001-07-01 | 10000 | -2587 | 7413 | 7413 | 100% | 0 | 0 |  | 1300 | -338 | 962 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | YUG | REF | 24 | PRP | 6 | A | O | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-06-01 | 2000-03-31 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Creation of Ozone Secretariat | Individual | EUR | YUG | SEV | 25 | INS | 7 | N | T | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2004-10-01 | 2005-09-01 | 151500 | 0 | 151500 | 151500 | 100% | 0 | 0 |  | 19695 | -5 | 19690 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-113 as solvent for dyaliser cleaning by water and steam at Hemomed Ltd. | Individual | EUR | YUG | SOL | 26 | INV | 8 | A | O | R | CFC | 54.6 | 54.6 |  |  | 1998-11-01 | 1999-02-01 | 1999-06-01 |  | 1998-12-01 | 1999-09-01 | 608729 | 0 | 608729 | 608729 | 100% | 0 | 0 |  | 76960 | 0 | 76960 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | YUG | HAL | 33 | PRP | 9 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-04-01 | 2003-05-01 | 20000 | -82 | 19918 | 19918 | 100% | 0 | 0 |  | 2600 | -15 | 2585 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the flexible foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-04-01 | 15000 | -15 | 14985 | 14985 | 100% | 0 | 0 |  | 1950 | -5 | 1945 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | EUR | YUG | REF | 33 | PRP | 10 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 10000 | -2325 | 7675 | 7675 | 100% | 0 | 0 |  | 1300 | -304 | 996 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-09-01 | 15000 | -201 | 14799 | 14799 | 100% | 0 | 0 |  | 1950 | -29 | 1921 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at seven enterprises (Jugostroj, Frigozika, Prva Petoletka, EIAD, BS Inzenjering, Soko and Alfa Klima) | Individual | EUR | YUG | REF | 34 | INV | 12 | A | O | I | CFC | 59.6 | 59.6 |  |  | 2001-07-01 | 2001-11-01 | 2004-02-01 |  | 2003-12-01 | 2005-09-01 | 755162 | -19150 | 736012 | 736012 | 100% | 0 | 0 |  | 93068 | -2235 | 90833 | 0 | 0 | FIN | [13 empty] | 2001 | INV
COM | Italy | Replacement of CFC-11 with cyclopentane foam blowing agent and CFC-12 with HFC-134a refrigerant in the manufacture of domestic refrigerators and freezers at Obod Elektroindustria | Individual | EUR | YUG | REF | 34 | INV | 13 | A | O | I | CFC | 94.9 | 94.9 | 0 |  | 2001-07-01 | 2002-09-01 | 2003-10-01 |  | 2007-04-01 |  | 1683135 | 0 | 1683135 | 1592015 | 94.59% | 91120 |  |  | 180348 | 0 | 170324.55 | 10023.45 | 0 | Financial completion in Dec 2008. Return of funds recorded at the 57th ExCom Mtg. This project was approved at the level of US$ 1,683,135 + US$ 180,348 agency support costs. Thus, the total approved funding was US$ 1,863,483. However, UNIDO received from Italy only US$ 1,783,533.78, which is US$ 79,949.22 less than the originally approved amount. All remaining balances amounting to US$ 20,564 were returned by UNIDO. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 | [11 empty] | 2001 | Investment
COM | UNIDO | Phase out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim Co. | Individual | EUR | YUG | FOA | 35 | INV | 14 | A | O | I | CFC | 75 | 75 |  |  | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2006-12-01 |  | 475728 | 0 | 475728 | 378448 | 79.55% | 97280 | 95220 | 95000 | 61845 | 0 | 49198 | 12647 | 12379 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2001 | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Prva Iskra-Poliuretani | Individual | EUR | YUG | FOA | 35 | INV | 15 | A | O | I | CFC | 34.4 | 34.4 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-02-01 | 2004-12-01 | 100240 | -169 | 100071 | 100071 | 100% | 0 | 0 |  | 13031 | -42 | 12989 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Halon bank management programme | Individual | EUR | YUG | HAL | 35 | TAS | 16 | A | O | I | HAL | 370 | 370 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-12-01 | 2005-12-01 | 249700 | -4216 | 245484 | 245484 | 100% | 0 | 0 |  | 32461 | -599 | 31862 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | EUR | YUG | REF | 36 | PRP | 17 | A | O | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-07-01 | 2004-12-01 | 20000 | -119 | 19881 | 19881 | 100% | 0 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Umbrella refrigeration project 2, replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at three enterprises | Individual | EUR | YUG | REF | 37 | INV | 18 | A | O | I | CFC | 10.9 | 10.9 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-10-01 | 2005-12-01 | 150109 | -1869 | 148240 | 148240 | 100% | 0 | 0 |  | 19514 | -273 | 19241 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Conversion of CFC-12 to HFC-134a in the manufacture of open compressors at Prva Petoletka - Kocna Tehnika Co. | Individual | EUR | YUG | REF | 38 | INV | 19 | A | O | I | CFC | 2 | 2 |  |  | 2002-11-01 | 2003-06-01 | 2005-06-01 |  | 2006-06-01 | 2007-09-01 | 223412 | -44 | 223368 | 223368 | 100% | 0 | 0 |  | 29044 | -6 | 29038 | 0 | 0 | FIN | [13 empty] | 2002 | INV
FIN | UNIDO | Assistance to prepare a national CFC phase-out plan (manufacturing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2005-04-01 | 2005-09-01 | 40000 | -7481 | 32519 | 32519 | 100% | 0 | 0 |  | 3000 | -565 | 2435 | 0 | 0 | FIN | [13 empty] | 2003
FIN | Sweden | Assistance to prepare a national CFC phase-out plan (servicing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 21 | A | O | I |  | 0 |  | 0 |  | 2003-07-01 | 2003-12-03 | 2004-07-01 |  | 2004-07-01 | 2004-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | The assistance to Serbia and Montenegro (SEM) to develop a NCPP for the servicing sector was completed in a joint undertaking with UNIDO during the spring 2004 and the plan was approved in July 2004. |  | 2003 | [11 empty] | 2003
ONG | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 22 | A | O | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2005-03-01 | 2010-03-31 |  |  | 148000 | -88000 | 60000 | 18971 | 31.62% | 41029 | 41029 | 25000 | 19240 | -11440 | 1000 | 6800 | 6800 | The NCPP implementation was started with UNIDO as Lead Agency and Sweden as Cooperating Agency. Since the Swedish decision in 2006 to cease the bilateral window, UNIDO is the sole implementing agency, with Sweden supporting only through the already contracted Swedish consultants. The project has been severely delayed partly due to the difficulties in making the PMU operational. The split with Montenegro also slowed down activities for a while. A frequent change of staff at the NOU has also caused further delays. A new NOU manager was officially assigned as of Dec 2008. The two NOU staff (NOU manager and assistant) is currently working on the ToR for the PMU and hopefully they will have an operational PMU before the summer. The absence of NOU Manager for a long period and the fact that there is still no PMU in place has meant that there has been a severe lack of resources for the national implementation. They now seem to be underway with the recruitment of staff for the PMU but this means that the project need to have its planned date for completion revised. After discussions with UNIDO, we proposed a revised completion date for March 2010. |  | 2004 | [8 empty] | 2006-12-01 |  |  | 2003 | [5 empty] | Yes
ONG | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 23 | A | O | I | CFC | 2 | 0 |  |  | 2004-07-01 | 2004-08-01 | 2005-03-01 | 2009-06-01 |  |  | 474700 | 0 | 474700 | 393569 | 82.91% | 81131 | 33832 | 20000 | 35603 | 0 | 29518 | 6085 | 2537 | There is a delay in the completion of the aerosol project, which was caused by the change of the country’s management. In November 2008 nomination of the Ozone Officers has been officially received by UNIDO. UNIDO mission was undertaken in December 2008 to speed up the implementation and to agree on an accelerated work plan. | [10 empty] | 2006-07-01 |  |  | 2004 | INV | 410 | 282.82 |  |  | Yes | Yes | Yes
ONG | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | YUG | SEV | 44 | INS | 25 | N | T | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-07-01 | 2006-12-01 | 2009-12-01 |  |  | 131300 | 0 | 131300 | 24280 | 18.49% | 107020 | 1467 | 20000 | 9848 | 0 | 1821 | 8027 | 110 | Nomination of the ozone officer has been officialy received in November 2008. Mission took place in December 2008, working plan to speed-up the implementation has been received. The project will be completed 1st quarter of 2010, and extension is to be requested to MLF to the 59th ExCom. | [13 empty] | 2004 | NON-INV
ONG | UNIDO | Project preparation in the fumigants sector (methyl bromide) | Individual | EUR | YUG | FUM | 45 | PRP | 26 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 | 2009-12-01 |  |  | 25000 | 0 | 25000 | 15811 | 63.24% | 9189 | 0 | 1 | 1875 | 0 | 1186 | 689 | 0 | Discussions are underway with the government with a possible project preparation. | After assisting the country in establishing a baseline on methyl bromide consumption and reporting data accordingly. Since the country has reported zero MB consumption during the last two years, no investment project is envisaged. | [12 empty] | 2005 | NON-INV
COM | UNIDO | Project preparation for the terminal phase-out in the solvent sector (CTC) | Individual | EUR | YUG | SOL | 45 | PRP | 27 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2008-12-01 |  | 15000 | 0 | 15000 | 10587 | 70.58% | 4413 | 2886 | 2000 | 1125 | 0 | 794 | 331 | 216 | Project document was prepared, submitted and approved. Project completed in Dec 2008. | [13 empty] | 2005 | NON-INV
ONG | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | INV | 28 | A | O | I | cFC | 18 | 0 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 | 2009-12-01 |  |  | 759000 | 0 | 759000 | 62939 | 8.292% | 696061 | 10223 | 120000 | 56925 | 0 | 4720 | 52205 | 767 | UNIDO mission was undertaken in December 2008 to speed up the implementation and to agree on an accelerated work plan. | [13 empty] | 2005 | INV | 392 | 52.1 |  |  | Yes | Yes | Yes
TRF | Sweden | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | TAS | 29 | A | O | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 |  |  |  | 134000 | -134000 | 0 | 0 |  | 0 | 0 | 0 | 17420 | -17420 | 0 | 0 | 0 | This activity was transferred to UNIDO in 2006. |  | 2005 | [11 empty] | 2005
ONG | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | YUG | PHA | 50 | INV | 30 | A | O | I | CFC | 124 | 72 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 | 2010-07-01 |  |  | 1033344 | 0 | 1033344 | 153318 | 14.84% | 880026 | 355500 | 290000 | 77501 | 0 | 11499 | 66002 | 26663 | A partial phase out of 72 ODP tonnes achieved. Terms of reference to carry out conversion at foaming/extrusion part have been prepared, bidding organized, offers evaluated, contractor selected and contract awarded. Extrusion line to be received in the first Q of 2009. Purchase of equipment for thermoforming in progress. Local contract for pre-installation works and locally purchased instrumentation and services is under preparation. | [13 empty] | 2006 | INV | 85 | 52.1 |  |  | Yes | No | No
ONG | UNIDO | National CFC phase-out plan (third tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 51 | INV | 31 | A | O | I |  | 0 | 0 |  |  | 2007-03-01 |  | 2008-03-01 | 2010-12-01 |  |  | 222000 | 0 | 222000 | 0 | 0% | 222000 | 0 | 10000 | 16650 | 0 | 0 | 16650 | 0 | National Ozone Unit revitalized, Ozone officer appointed. Custom clearance for training equipment delayed due to cancellation of recruitment of training institution. New training institution will be selected in collaboration with the NOU. Training of Junior Adviser in Air Protection Unit took place, national project implementation team will be created. | [13 empty] | 2007 | INV | 268 | 233.8 |  |  | Yes | No | No
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | YUG | PHA | 55 | PRP | 32 | A | O | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2009-12-01 |  |  | 150000 | 0 | 150000 | 1392 | 0.928% | 148608 | 0 | 50000 | 11250 | 0 | 104 | 11146 | 0 | JD for national consultant was provided and recruitment of surveyor organized in cooperation with NOU. | Due to administrative restructuring, NOU staff has been officially appointed November 2008. Implementation has been initiated January 2009. Preliminary survey identifies already the needed amendments to introduce restrictions on placing on the market new technologies based on HCFCs. Licensing system is already covering the HCFCs imports/exports; financial tool is in place for HCFCs (mandatory fee as contribution to Environmental Fund of Serbia for HCFCs import) | [12 empty] | 2008 | NON-INV
ONG | Italy | Terminal CTC phase-out project | Individual | EUR | YUG | SOL | 56 | INV | 33 | A | O | I | CTC | 2.6 |  | 0 |  | 2008-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 49324 | 0 | 49324 |  | 0% | 49324 |  | 20000 | 6412 | 0 | 0 | 6412 | 0 | The project was approved at the 56th ExCom, held in November 2008. |  | 2008 | [11 empty] | 2008 | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | ZAM | SEV | 4 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Project financially completed. | [13 empty] | 1991 | Non Investment
FIN | UNEP | Institutional strengthening | Individual | AFR | ZAM | SEV | 9 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1999-12-01 | 2004-05-01 | 75600 | 0 | 75600 | 75600 | 100% | 0 | 0 | 0 | 9828 | 0 | 9828 | 0 | 0 | Project financially completed. |  |  |  | 1999-12-01 | [9 empty] | 1993 | Non Investment
FIN | UNIDO | Preparation of training and certification programmes for refrigeration technicians and preparation of investment projects for the refrigeration sector | Individual | AFR | ZAM | REF | 15 | TAS | 3 | A | O | I |  | 0 | 17.7 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-12-01 | 1999-08-01 | 82100 | -5625 | 76475 | 76475 | 100% | 0 | 0 |  | 10673 | -747 | 9926 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 17 | PRP | 4 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-03-01 |  | 1996-06-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 18 | PRP | 5 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. | [13 empty] | 1995 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | ZAM | REF | 19 | TAS | 6 | A | O | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -240 | 106080 | 106080 | 100% | 0 | 0 | 0 | 13822 | -31 | 13791 | 0 | 0 | Completed in 1997. Financially completed in 2000. | [13 empty] | 1996 | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZAM | REF | 23 | PRP | 7 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-05-02 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1999
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZAM | REF | 26 | TAS | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-05-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RMP completed, RMP update approved in 42nd Excom | [13 empty] | 2000
CLO | UNIDO | Preparation of a demonstration project (tobacco, flowers) | Individual | AFR | ZAM | FUM | 27 | PRP | 9 | A | O | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 30000 | -30000 | 0 | 0 |  | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | ZAM | FUM | 30 | TAS | 10 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9259 | 15741 | 15741 | 100% | 0 | 0 | 0 | 3250 | -1203.67 | 2046.33 | 0 | 0 | Project financially completed. | $ 9,259 plus $ 1,204 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ZAM | SEV | 30 | INS | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2004-08-01 | 2002-07-01 |  | 2004-12-01 | 2008-12-01 | 50400 | 0 | 50400 | 50400 | 100% | 0 | 0 | 0 | 6552 | 0 | 6552 | 0 | 0 | Project financially completed. | [13 empty] | 2000 | Non Investment
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ZAM | REF | 37 | PRP | 12 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-01-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved at the 42nd meeting | [13 empty] | 2002
ONG | Germany | Refrigerant management plan update: refrigeration and air conditioning sector | RMP Update | AFR | ZAM | REF | 42 | TAS | 13 | A | O | I |  | 23.3 | 23.3 | 0 |  | 2004-04-01 | 2004-07-01 | 2007-04-01 | 2009-10-01 |  |  | 136000 | 0 | 136000 | 132400 | 97.35% | 3600 | 0 | 3600 | 17680 | 0 | 17212 | 468 | 0 | Zambia has concentrated most of this year on developing the TPMP and no real progress was made under the RMP project. However workshop on enforcement of licensing system and the incenitve scheme were conducted.
ONG | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | ZAM | SEV | 44 | INS | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2006-12-01 | 2009-06-01 |  |  | 65520 | 0 | 65520 | 52416 | 80% | 13104 | 13104 | 13104 | 0 | 0 | 0 | 0 | 0 | MOU signed with country and implementated all the activities. NOU conducted training for customs officers and refrigerations technicnians. Produced awareness materials and celebrated Ozone day. | [13 empty] | 2004 | Non Investment
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | ZAM | SOL | 45 | TAS | 16 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 40000 | -1745 | 38255 | 38255 | 100% | 0 | 0 |  | 3600 | -157 | 3443 | 0 | 0 | Financial completion in May 2008. Refund was reported to 54th ExCom, Apr 2008. FIN. Refund was reported to 55th ExCom, Jul 2008. FIN. | [13 empty] | 2005 | NON-INV
COM | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | ZAM | PHA | 50 | PRP | 17 | A | O | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 |  | 30000 | 0 | 30000 | 22000 | 73.33% | 8000 | 8000 | 8000 | 3900 | 0 | 2860 | 1040 | 1040 | Project completed | [13 empty] | 2006 | Non Investment
ONG | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | TAS | 18 | A | O | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 | 2009-03-01 |  |  | 94000 | 0 | 94000 | 70000.39 | 74.47% | 23999.61 | 24000 | 23999.61 | 12220 | 0 | 9100.0507 | 3119.9493 | 3120 | First tranche successfully completed, country conducted trainings for customs officers, refrigeration technicians, reviewed ODS Regulations, curricula for customs training school and technicians school. Second tranche approved during the 57th Ex-com | [13 empty] | 2007 | Non Investment
ONG | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | INV | 19 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-01 | 2010-01-01 |  |  | 109000 | 0 | 109000 | 0 | 0% | 109000 | 55864 | 21800 | 9810 | 0 | 0 | 9810 | 5027.76 | Project ongoing. NOU/UNDP developed equipment specifications and launched bidding process. As of December 2009, Bidding process finalized, equipment expected in Q1-2009. Visit by international expert postponed by the Government until Q2- 2009 | [13 empty] | 2007 | Investment | 4.1 |  |  |  | Latest | Latest | Latest
COM | UNIDO | Project preparation in the fumigants sector (soil fumigation) | Individual | AFR | ZAM | FUM | 54 | PRP | 20 | A | O | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-09-01 | 2009-03-31 |  | 2008-12-01 |  | 35000 | 0 | 35000 | 19140 | 54.69% | 15860 | 15134 | 15134 | 2625 | 0 | 1436 | 1189 | 1135 | Project completed in Dec 2008. | [13 empty] | 2008 | NON-INV
ONG | UNIDO | Technical assistance for the total phase out of methyl bromide in tobacco, cut flowers, horticulture and post harvest uses | Individual | AFR | ZAM | FUM | 56 | INV | 21 | A | O | I | MBR | 7.4 | 0 |  |  | 2008-11-01 |  | 2011-11-30 | 2011-11-01 |  |  | 289548 | 0 | 289548 | 0 | 0% | 289548 | 0 | 70000 | 21716 | 0 | 0 | 21716 | 0 | Working arrangement on implementation modalities is under finalization between UNIDO and the government. In 2009 activities will be focused on training in the tobacco and horticulture sectors. Training will be organized and relevant equipment will be distributed to the farmers. | [13 empty] | 2008 | INV
ONG | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ZAM | PHA | 56 | PRP | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-30 | 2009-11-30 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 85000 | 11050 | 0 | 0 | 11050 | 0 | MOU signed with country in February and first payment being processed | [13 empty] | 2008
FIN | UNEP | Country programme preparation | Individual | AFR | ZIM | SEV | 9 | CPG | 1 | A | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project financially completed. | [13 empty] | 1993 | Non Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of an Ozone Office | Individual | AFR | ZIM | SEV | 13 | INS | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1997-07-01 |  | 1999-10-01 | 2000-12-01 | 171050 | 0 | 171050 | 171050 | 100% | 0 | 0 | 0 | 22236.5 | 0 | 22236.5 | 0 | 0 | Project financially completed. |  |  |  | 1999-05-01 | [9 empty] | 1994 | Non Investment
FIN | UNIDO | Preparation of investment projects in the refrigeration, air conditioning and recovery/recycling | Individual | AFR | ZIM | SEV | 14 | PRP | 3 | A | O | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-02-01 | 1995-03-01 |  | 1997-11-01 | 1999-08-01 | 40000 | -463 | 39537 | 39537 | 100% | 0 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN
FIN | UNIDO | CFC refrigerant recovery and reclaim project | RMP | AFR | ZIM | REF | 17 | TAS | 4 | A | O | I | CFC | 47 | 47 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-08-01 | 312300 | -143 | 312157 | 312157 | 100% | 0 | 0 |  | 40599 | -83 | 40516 | 0 | 0 | FIN
FIN | IBRD | Project preparation |  | AFR | ZIM | SEV | 18 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-31 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | [15 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ref-air Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 6 | N | O | I | CFC | 5.3 | 5.3 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2000-11-01 | 2000-11-01 | 43382 | 0 | 43382 | 43382 | 100% | 0 | 0 |  | 5639.66 | 0 | 5639.66 | 0 | 0 | Because of economic difficulties in Zimbabwe (including significant local currency devaluation and unavailability of forex), not much progress was made until CY00 and the project was completed by 11/00. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Commercial Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 7 | N | O | I | CFC | 6.9 | 6.9 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2001-08-01 | 2001-08-01 | 156636 | -15061 | 141575 | 141575 | 100% | 0 | 0 |  | 20363 | -1957.93 | 18405.07 | 0 | 0 | Project completed. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Capri Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 8 | N | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-10-01 |  | 1999-11-01 | 1999-11-01 | 106695 | 0 | 106695 | 106695 | 100% | 0 | 0 |  | 13870 | 0 | 13870 | 0 | 0 | CFC-11 portion completed 2/97 and CFC-12 portion completed 6/99, but because of the economic difficulties in Zimbabwe (including significant local currency devaluation) and the change of ownership of the company, not much progress was made during CY98. The project was completed in 08/99. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to cyclopentane as the blowing agent for foam insulation at Imperial Derby Refrigeration Ltd. | Individual | AFR | ZIM | REF | 20 | INV | 9 | N | O | I | CFC | 14 | 12.85 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-12-01 |  | 1996-03-01 | 2001-05-01 | 310000 | -88275 | 221725 | 221725 | 100% | 0 | 0 |  | 40300 | -11476 | 28824.25 | -0.25 | -0.25 | Project completed. Funds returned at the 35th ExCom. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ajax Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 10 | N | O | I | CFC | 3.5 | 3.5 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2001-10-01 |  | 1997-01-01 | 2001-08-01 | 61966 | 0 | 61966 | 61966 | 100% | 0 | 0 |  | 8056 | 0 | 8056 | 0 | 0 | Company taken over by Commercial Refrigeration and now treated as 2nd production line at Commercial. Project combined with that of Commercial Refrigeration as approved. Financial completion date is the same as Commercial. |  |  |  | 1999-12-01 | [10 empty] | INV | 0 | 0 | 0 | 0
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ZIM | FUM | 22 | PRP | 11 | A | O | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  |  | 1999-02-01
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZIM | REF | 23 | PRP | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation | [13 empty] | 1998
FIN | UNIDO | Demonstration project - Two alternatives to the use of methyl bromide in the production of tobacco drought-resistant seedlings: non-soil cultivation and low-dose chemicals | Individual | AFR | ZIM | FUM | 23 | DEM | 13 | A | O | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-11-01 |  | 2000-12-01 | 2002-09-01 | 370700 | -17402 | 353298 | 353298 | 100% | 0 | 0 |  | 48191 | -2335 | 45856 | 0 | 0 | FIN
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | AFR | ZIM | FUM | 24 | PRP | 14 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2003. | [13 empty] | 1998 | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZIM | REF | 26 | TAS | 15 | A | O | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-03 | 2004-07-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
CLO | Germany | Project preparation for phasing out of ODS at the domestic refrigeration factory Fridgemaster | Individual | AFR | ZIM | REF | 26 | PRP | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented. | Funds to be offset against future german approvals
FIN | UNDP | Alternatives to the use of methyl bromide on stacked bags of maize under gas proof PVC sheets and plastic cocoons (storage) | Individual | AFR | ZIM | FUM | 27 | DEM | 17 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 2000-12-01 | 2003-04-01 | 212850 | -10142 | 202708 | 202708 | 100% | 0 | 0 | 0 | 27671 | -1319 | 26352 | 0 | 0 | Completed in 2000. Financially completed in 2003. | [13 empty] | 1999 | Investment
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector (cut flowers) | Individual | AFR | ZIM | FUM | 30 | PRP | 18 | A | O | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -570 | 29430 | 29430 | 100% | 0 | 0 |  | 3900 | -80 | 3820 | 0 | 0 | FIN
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | AFR | ZIM | FUM | 30 | TAS | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -2765 | 22235 | 22235 | 100% | 0 | 0 | 0 | 3250 | -359 | 2890.55 | 0.45 | 0 | Project financially completed. | $ 2,765 plus $ 359 PSC returned ExCom 41 | [12 empty] | 2000 | Non Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | ZIM | SEV | 28 | INS | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-12-01 | 2003-06-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 | 0 | 14824.29 | 0 | 14824.29 | 0 | 0 | Project financially completed. |  |  |  |  | 2001-06-01 | [8 empty] | 1999 | Non Investment
COM | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | ZIM | FUM | 31 | INV | 21 | A | O | I | MBR | 132 | 132 |  |  | 2000-07-01 | 2001-03-01 | 2004-08-01 |  | 2006-12-01 |  | 904200 | 0 | 904200 | 893211 | 98.78% | 10989 | 6616 | 6600 | 109462 | 0 | 108253 | 1209 | 728 | The project will be financially completed upon disbursement of unliquidated obligations.
FIN | UNIDO | Project preparation in the fumigants (tobacco) sector | Individual | AFR | ZIM | FUM | 33 | PRP | 22 | A | O | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2002-12-01 | 2004-03-01 | 30000 | -600 | 29400 | 29400 | 100% | 0 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN | [13 empty] | 2001 | INV
FIN | UNDP | Project preparation in the fumigation storage sector | Individual | AFR | ZIM | FUM | 33 | PRP | 23 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. | [13 empty] | 2001 | Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | ZIM | SEV | 34 | INS | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2003-08-01 |  | 2004-07-01 | 2004-12-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 | 0 | 14824.29 | 0 | 14824.29 | 0 | 0 | Project financially completed. | [13 empty] | 2001 | Non Investment
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | ZIM | PHA | 37 | PRP | 25 | A | O | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-09-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 62760 | 0 | 62760 | 62760 | 100% | 0 | 0 | 0 | 8159 | 0 | 8159 | 0 | 0 | TPMP first tranche approved at 44th ExCom
FIN | UNDP | Project preparation for the re-formulation of solvent technical assistance | Individual | AFR | ZIM | SOL | 42 | PRP | 26 | A | O | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2006. Financially completed in 2006. | [13 empty] | 2004 | Investment
COM | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | ZIM | SEV | 43 | INS | 27 | A | T | I | CFC | 12.2 | 12.2 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-11-01 |  | 148242 | 0 | 148242 | 143038.27 | 96.49% | 5203.73 | 0 | 5203.73 | 0 | 0 | 0 | 0 | 0 | Project completed | [13 empty] | 2004 | Non Investment
FIN | Germany | Terminal phase-out management plan for CFCs (first tranche) | Individual | AFR | ZIM | PHA | 44 | INV | 29 | A | O | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2007-06-01 | 2007-10-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Project was completed and the 2nd tranche approved in March 2007
FIN | UNIDO | Project preparation in the fumigants (methyl bromide) sector (phase out in tobacco seedling) | Individual | AFR | ZIM | FUM | 45 | PRP | 30 | A | O | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2005-12-01 | 2005-12-01 | 15000 | -599 | 14401 | 14401 | 100% | 0 | 0 |  | 1125 | -47 | 1078 | 0 | 0 | FIN | [13 empty] | 2005 | NON-INV
CLO | UNDP | Project preparation for a fumigant (methyl bromide) project | Individual | AFR | ZIM | FUM | 45 | PRP | 31 | N | O | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 |  | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2006. | [13 empty] | 2005 | Investment
COM | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (first tranche) | Multi-Year | AFR | ZIM | FUM | 47 | INV | 32 | A | O | I | MBR | 50 | 50 |  |  | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 |  | 1862486 | 0 | 1862486 | 1859683 | 99.85% | 2803 | 2642 | 2000 | 139686 | 0 | 139476 | 210 | 198 | The project will be financially completed upon disbursement of unliquidated obligations. | [13 empty] | 2005 | INV | 180 | 155.4 |  |  | Yes | N/A | N/A
FIN | UNIDO | Project preparation in the fumigant sector (grain storage) | Individual | AFR | ZIM | FUM | 48 | PRP | 33 | A | O | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-08-01 | 2007-03-01 |  | 2006-12-01 | 2007-03-01 | 20000 | -806 | 19194 | 19194 | 100% | 0 | 0 |  | 1500 | -60 | 1440 | 0 | 0 | Refund was reported to 54th ExCom, Apr 2008. FIN. | [13 empty] | 2006 | NON-INV
ONG | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | ZIM | SEV | 50 | INS | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2008-11-01 | 2009-11-01 |  |  | 148242 | 0 | 148242 | 0 | 0% | 148242 | 0 | 148242 | 0 | 0 | 0 | 0 | 0 | MOU signed with country, awaiting payment to be made | [13 empty] | 2006 | Non Investment
ONG | UNDP | Technical assistance for the phase-out of ODS in the solvent/sterilant sector | Individual | AFR | ZIM | SOL | 50 | TAS | 35 | N | O | I | TCA/CTC | 3.9 | 0 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-05-01 | 2010-01-01 |  |  | 60000 | 0 | 60000 | 24535 | 40.89% | 35465 | 10070 | 7093 | 5400 | 0 | 2208.15 | 3191.85 | 906.3 | Project ongoing. National experts recruited. International expert recruited and fielded with a mission to Harare. Stakeholder workshop held in July 2008. Activities planned for 2008 and 2009. IT equipment and software upgrade planned as of December 31, 2008. | [13 empty] | 2006 | Non-Investment
COM | UNIDO | Total phase-out of methyl bromide used in grain fumigation | Individual | AFR | ZIM | FUM | 50 | INV | 36 | A | O | I | MBR | 10.2 | 10.2 |  |  | 2006-11-01 | 2007-01-01 | 2010-11-01 |  | 2008-12-01 |  | 192073 | 0 | 192073 | 152573 | 79.43% | 39500 | 33485 | 33000 | 17287 | 0 | 13732 | 3555 | 3014 | Project succesfully implemented. Project completed in Dec 2008. | [13 empty] | 2006 | INV
COM | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (second tranche) | Multi-Year | AFR | ZIM | FUM | 51 | INV | 37 | A | O | I | MBR | 120 | 120 |  |  | 2007-03-01 | 2007-11-01 | 2009-12-01 |  | 2008-12-01 |  | 1862486 | 0 | 1862486 | 1279888 | 68.72% | 582598 | 578098 | 578000 | 139686 | 0 | 95992 | 43694 | 43357 | Project is about to be completed. Last shipment of trays is expected in May 2009. Training activities were completed. | [13 empty] | 2007 | INV | 74.2 | 36 |  |  | Yes | N/A | N/A
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, first tranche) | Multi-Year | AFR | ZIM | PHA | 51 | INV | 38 | A | O | I |  | 25 | 25 | 0 |  | 2007-03-01 | 2007-04-01 | 2009-12-01 |  | 2008-07-01 | 2008-10-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | Phase completed and 3rd tranche approved | [15 empty] | 67.7 | 65 |  |  | yes
ONG | Germany | National phase-out of Annex A (Group I) substances (phase II, second tranche) | Multi-Year | AFR | ZIM | PHA | 54 | INV | 39 | A | O | I |  | 20 | 20 | 0 |  | 2008-04-01 | 2008-05-01 | 2009-03-01 | 2009-03-01 |  |  | 175000 | 0 | 175000 | 168000 | 96% | 7000 | 0 | 7000 | 22347 | 0 | 21453.12 | 893.88 | 0 | 5 Customs training, 7 technician training and 72 conversions under the incentive scheme were the main activities conducted