EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Sixtieth Meeting
Montreal, 12-15 April 2010

DRAFT DECISION ON AGENDA ITEM  9(d): INVESTMENT PROJECTS:

NATIONAL CFC PHASE-OUT PLAN IN BANGLADESH

(Submitted by the Informal Group)

The Executive Committee decided:

- To take note of the progress report on the implementation of the second to the fourth tranches of the national ODS phase-out plan in Bangladesh;

- To take note of the verification report on 2008 CFC consumption;

- To further note the fast track implementation of the project for the phase-out of CFCs used for the manufacturing of metered dose inhalers (MDIs) approved by the Executive Committee at its 52nd Meeting, which has resulted in the reduction of 46 ODP tonnes of CFCs so far;

- To apply the penalty clause in the Agreement between the Government of Bangladesh and the Executive Committee calculated, at 50 per cent of the amount for each of the fifth and sixth tranches being submitted to the Executive Committee for approval, for reasons of non-compliance with the Agreement, on the basis that not sufficient and timely regulatory controls on imports of CFCs for the refrigeration servicing sector have been applied to curtail consumption in this sector;

- Using the method outlined in sub-paragraph (c) above, to apply a total penalty of US $81,500 for the fifth and sixth tranches of the national ODS phase out plan for Bangladesh;

- To approve the fifth and sixth tranches of the national ODS phase-out plan for Bangladesh at a total funding level of US $55,000, plus agency support costs of US $4,125 for UNDP, and US $26,500, plus agency support costs of US $3,445, for UNEP, which took into account the penalty using the method outlined in sub-paragraph (c) above;

- To request the Government of Bangladesh and UNDP to submit to the 61st Meeting a detailed progress report on the implementation of the national ODS phase-out plan for Bangladesh; a comprehensive plan of action associated with the seventh and last tranche of the phase-out plan to sustain compliance with the Montreal Protocol targets in 2010 and beyond, and include extension of activities to address HCFC controls and reductions;

- To note that the maximum level of CFC consumption from 1 January 2010 was zero as stipulated in the Agreement, except for any essential uses of CFCs that the Parties might approved for Bangladesh for the production of MDIs.

-----