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MODIFICACIONES DEL PROGRAMA DE TRABAJO DEL PNUMA PARA 2021*









*El presente documento se publica para reflejar la eliminación de la solicitud de preparación del plan de aplicación de los HFC de Kigali (fase I) para Liberia, que se aprobó en la 87ª reunión. Para facilitar la consulta, se han resaltado los cambios en el documento.

COMENTARIOS Y RECOMENDACIÓN DE LA SECRETARÍA DEL FONDO
El PNUMA solicita la aprobación del Comité Ejecutivo de la cantidad de 3 455 511 $EUA, más unos gastos de apoyo al organismo de 200 930 $EUA para las modificaciones de su programa de trabajo de 2021 que se exponen en la tabla 1. La presentación se adjunta al presente documento.
Tabla 1: Modificaciones del programa de trabajo del PNUMA para 2021
	País
	Actividad/Proyecto
	Cantidad solicitada ($EUA)
	Cantidad recomendada ($EUA)

	SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL

	A1: Renovación de proyectos de fortalecimiento institucional

	Albania
	Renovación del proyecto de fortalecimiento institucional (fase X)
	139 776
	139 776

	Benín
	Renovación del proyecto de fortalecimiento institucional (fase XII)
	85 000
	85 000

	Bhután
	Renovación del proyecto de fortalecimiento institucional (fase IX)
	85 000
	85 000

	Camerún 
	Renovación del proyecto de fortalecimiento institucional (fase XIII)
	178 601
	178 601

	Comoras
	Renovación del proyecto de fortalecimiento institucional (fase XII)
	85 000
	85 000

	Islas Cook
	Renovación del proyecto de fortalecimiento institucional (fase VIII)
	85 000
	85 000

	Micronesia (Estados Federados de)
	Renovación del proyecto de fortalecimiento institucional (fase VIII)
	85 000
	85 000

	Guatemala
	Renovación del proyecto de fortalecimiento institucional (fase IX)
	159 744
	159 744

	Namibia
	Renovación del proyecto de fortalecimiento institucional (fase XI)
	85 000
	85 000

	Paraguay
	Renovación del proyecto de fortalecimiento institucional (fase X)
	85 000
	85 000

	San Vicente y las Granadinas
	Renovación del proyecto de fortalecimiento institucional (fase VIII)
	85 000
	85 000

	Senegal
	Renovación del proyecto de fortalecimiento institucional (fase XIV)
	194 689
	194 689

	Islas Salomón 
	Renovación del proyecto de fortalecimiento institucional (fase IX)
	85 000
	85 000

	Sudán
	Renovación del proyecto de fortalecimiento institucional (fase X)
	186 701
	186 701

	Timor-Leste
	Renovación del proyecto de fortalecimiento institucional (fase VI)
	85 000
	85 000

	Vanuatu
	Renovación del proyecto de fortalecimiento institucional (fase VIII)
	85 000
	85 000

	Subtotal para A1
	1 794 511
	1 794 511

	Gastos de apoyo al organismo
	0
	0

	Total para A1
	1 794 511
	1 794 511

	A2: Asistencia técnica para actividades de apoyo (decisión 79/46)

	India
	Actividades de apoyo para la reducción del HFC
	250 000
	250 000

	Subtotal para A2
	250 000
	250 000

	Gastos de apoyo al organismo
	17 500
	17 500

	Total para A2
	267 500
	267 500

	A3: Asistencia técnica para preparar un informe de verificación sobre el consumo de HCFC

	Botswana
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Djibouti
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Gambia
	Informe de verificación para la etapa II del PGEH 
	30 000
	30 000

	Guinea Bissau
	Informe de verificación para la etapa II del PGEH 
	30 000
	30 000

	República Democrática Popular Lao
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Mongolia
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Nepal
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Nicaragua
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Santo Tomé y Príncipe
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Zimbabwe
	Informe de verificación para la etapa II del PGEH
	30 000
	30 000

	Subtotal para A3
	300 000
	300 000

	Gastos de apoyo al organismo
	39 000
	39 000

	Total para A3
	339 000
	339 000

	A4: Preparación de proyectos para los planes de aplicación de la Enmienda de Kigali para los HFC (PAK)

	Camboya a
	Preparación de un PAK (etapa I)
	135 000
	135 000

	Chile b
	Preparación de un PAK (etapa I)
	20 000
	20 000

	Fiji b
	Preparación de un PAK (etapa I)
	35 000
	35 000

	Granada a
	Preparación de un PAK (etapa I)
	60 000
	60 000

	Lesotho c
	Preparación de un PAK (etapa I)
	91 000
	91 000

	Malawic
	Preparación de un PAK (etapa I)
	119 000
	119 000

	Namibiac 
	Preparación de un PAK (etapa I)
	119 000
	119 000

	República Árabe Siria c
	Preparación de un PAK (etapa I)
	154 000
	154 000

	Rwandac
	Preparación de un PAK (etapa I)
	91 000
	91 000

	Sierra Leonac
	Preparación de un PAK (etapa I)
	91 000
	91 000

	Uganda c
	Preparación de un PAK (etapa I)
	70 000
	70 000

	Viet Nam d
	Preparación de un PAK (etapa I)
	35 000
	35 000

	Zambiac
	Preparación de un PAK (etapa I)
	91 000
	91 000

	Subtotal para A4
	1 111 000
	1 111 000

	Gastos de apoyo al organismo
	144 430
	144 430

	Total para A4
	1 255 430
	1 255 430

	Gran total (A1, A2, A3, A4)
	3 656 441
	3 656 441


a PNUD como organismo de ejecución de cooperación 
b PNUD como organismo de ejecución director
c ONUDI como organismo de ejecución de cooperación
d Banco Mundial como organismo de ejecución director

SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL
A1: Renovación de proyectos de fortalecimiento institucional
Descripción de los proyectos
El PNUMA presentó solicitudes para la renovación de proyectos de fortalecimiento institucional de los países citados en la sección A1 de la tabla 1. La descripción de estos proyectos se presenta en el anexo I del presente documento.
Comentarios de la Secretaría
La Secretaría examinó las solicitudes de renovación de dieciséis proyectos de fortalecimiento institucional en nombre de los Gobiernos concernidos teniendo en cuenta las orientaciones y las decisiones pertinentes sobre admisibilidad y los niveles de financiación. Las solicitudes fueron doblemente verificadas comparándolas con los planes de trabajo originales para el fortalecimiento institucional de la fase anterior, los datos del programa del país y del artículo 7, el último informe sobre la aplicación del plan de gestión de la eliminación de los HCFC (PGEH), el informe sobre la marcha de las actividades del organismo y cualquier decisión pertinente de la Reunión de las Partes. Se observó que estos países han presentado los datos de sus programas de país de 2020 y cumplen con los objetivos de control en virtud del Protocolo de Montreal y su consumo anual de HCFC no supera el consumo anual máximo admisible indicado en sus Acuerdos del PGEH con el Comité Ejecutivo. Asimismo, las solicitudes presentadas incluían indicadores de desempeño para las actividades planificadas para la siguiente fase de los proyectos de fortalecimiento institucional, de acuerdo con la decisión 74/51(e).
La Secretaría tomó nota de la reciente situación política en Sudán y debatió con el PNUMA la ejecución de proyectos en el país. Se acordó que el PNUMA no desembolsaría ninguna financiación aprobada para Sudán hasta que el PNUMA haya presentado una carta a la Secretaría en la que se indique la posibilidad de que las actividades previstas pueden llevarse a cabo en el país.
Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de las solicitudes de renovación de proyectos de fortalecimiento institucional para Albania, Benín, Bhután, Camerún, Comoras, Islas Cook, Micronesia (Estados Federados de), Guatemala, Namibia, Paraguay, San Vicente y las Granadinas, Senegal, Islas Salomón, Sudán, Timor-Leste y Vanuatu con el nivel de financiación indicado en la sección A1 de la tabla 1 del presente documento, en el entendimiento de que el PNUMA no desembolsaría ninguna financiación aprobada para Sudán hasta que el PNUMA haya presentado una carta a la Secretaría indicando la posibilidad de que las actividades previstas pueden llevarse a cabo en el país. El Comité Ejecutivo puede considerar oportuno expresar a los Gobiernos mencionados anteriormente los comentarios que se presentan en el anexo II de este documento.
A2: Asistencia técnica para actividades de apoyo para la reducción de HFC 
Antecedentes 
De conformidad con la decisión 79/46[footnoteRef:2], el PNUMA presentó una solicitud de financiación para la realización de actividades de apoyo para la reducción de los HFC en India[footnoteRef:3], como se indica en la sección A2 de la tabla 1. [2:  El Comité Ejecutivo decidió, entre otras cosas, aprobar actividades de apoyo sobre la base de que los países dispondrían de flexibilidad para emprender una serie de actividades para cumplir sus obligaciones iniciales en virtud de la Enmienda de Kigali; las actividades de apoyo podrían consistir, entre otras cosas, en las siguientes: facilitar y apoyar la pronta ratificación de la Enmienda de Kigali; iniciar acuerdos de apoyo institucional; examinar los sistemas de concesión de licencias; presentar datos sobre los HFC; y actividades de demostración ajenas a la inversión.]  [3:  India ratificó la Enmienda de Kigali el 27 de septiembre de 2021.] 

Las actividades de apoyo consisten en: 
Desarrollo de una estrategia nacional para la aplicación de la Enmienda de Kigali que incluya un estudio sobre el consumo y la producción de HFC; evaluaciones sectoriales para diversas aplicaciones, como la refrigeración y el aire acondicionado, las espumas, los aerosoles y el sector de servicios; identificación de los requisitos para establecer la legislación y el marco político para la gestión de la reducción de los HFC; y coordinación entre las instituciones gubernamentales y las partes interesadas sobre las políticas y los planes de acción necesarios para la ratificación y aplicación de la Enmienda de Kigali; 
Revisión y actualización del marco normativo existente para apoyar los sistemas de concesión de licencias de importación y exportación de HFC y alternativas a los HFC; y desarrollo del marco para la notificación de datos sobre HFC y el sistema de concesión de licencias de HFC en consulta con las aduanas y las autoridades pertinentes; 
Evaluación de las prácticas y capacidades de los técnicos de mantenimiento en relación con el control de emisiones y el manejo de refrigerantes inflamables y tóxicos; evaluación del sistema existente de capacitación profesional y certificado de cualificación para los técnicos de mantenimiento de la refrigeración; y exámenes de las aplicaciones tecnológicas alternativas; y 
Programa de divulgación y sensibilización que incluye la elaboración de material informativo y la organización de tres talleres informativos para las partes interesadas y el público sobre la Enmienda de Kigali y sus implicaciones, la reducción de los HFC y la manipulación segura de las alternativas, así como la eficiencia energética y las opciones de refrigerantes inocuos para el clima.
Comentarios de la Secretaría 
La Secretaría examinó la solicitud para las actividades de apoyo y llegó a la conclusión de que cumplían todos los requisitos de la decisión 79/46, como se indica a continuación: 
El PNUMA presentó una carta de apoyo del Gobierno de la India; 
La propuesta de proyecto incluía una descripción de las actividades de apoyo, los arreglos institucionales, el desglose de los costos y el calendario de ejecución; y 
La ejecución del proyecto durará 18 meses. 
La financiación solicitada para la India era coherente con la decisión 79/46(c), y se calculó sobre la base del consumo básico de referencia de HCFC del país. 
Recomendación de la Secretaría 
La Secretaría recomienda la aprobación general de la solicitud de actividades de apoyo a la reducción de los HFC para la India, con el nivel de financiación indicado en la sección A2 de la tabla 1.
A3: Asistencia técnica para preparar un informe de verificación sobre el consumo de HCFC
Descripción del proyecto
El Comité Ejecutivo pidió a los organismos bilaterales y de ejecución pertinentes que incluyeran en las enmiendas de sus programas de trabajo respectivos para su presentación a la 88ª reunión, la financiación de la preparación de informes de verificación del consumo de HCFC para determinados países que operan al amparo del artículo 5. El PNUMA, como organismo de ejecución director, solicita financiación para la verificación de la etapa II de los planes de gestión de la eliminación de los HCFC (PGEH) de Botswana, Djibouti, Gambia, Guinea-Bissau, la República Democrática Popular Lao, Mongolia, Nepal, Nicaragua, Santo Tomé y Príncipe y Zimbabwe[footnoteRef:4]. [4:  Decisión 87/27 ] 

Comentarios de la Secretaría
La Secretaría advirtió que la financiación solicitada para estos 10 países era coherente con los fondos aprobados para verificaciones similares en reuniones anteriores. Observó además que el informe de verificación debe presentarse al menos 10 semanas antes de la reunión del Comité Ejecutivo correspondiente en la que se solicite el siguiente tramo de financiación del PGEH.
Recomendación de la Secretaría
La Secretaría recomienda la aprobación general para la preparación de informes de verificación para la etapa II de los PGEH para Botswana, Djibouti, Gambia, Guinea-Bissau, la República Democrática Popular Lao, Mongolia, Nepal, Nicaragua, Santo Tomé y Príncipe y Zimbabwe con el nivel de financiación indicado en la sección A3 de la tabla 1, entendiendo que el informe de verificación deberá presentarse al menos 10 semanas antes de la reunión del Comité Ejecutivo correspondiente en la que se solicite el siguiente tramo de financiación para el PGEH.
A4: Preparación de proyectos para los planes de aplicación de la Enmienda de Kigali para los HFC (PAK)
Descripción de proyectos
El PNUMA presentó solicitudes para la preparación de la etapa I de los PAK para 10 países que operan al amparo del artículo 5 como organismo de ejecución director, y para tres países como organismo de ejecución de cooperación con el PNUD como organismo de ejecución director para Chile y Fiji, y el Banco Mundial para Viet Nam, como se muestra en la sección A4 de la tabla 1. El PNUD, como organismo de ejecución director para Chile y Fiji y como organismo de ejecución de cooperación para Camboya y Granada, solicitó 340 000 $EUA, más unos gastos de apoyo al organismo por valor de 23 800 $EUA[footnoteRef:5];  la ONUDI, como organismo de ejecución de cooperación para Lesotho, Malawi, Namibia, Rwanda, Sierra Leona, la República Árabe Siria, Uganda y Zambia, solicitó 354 000 $EUA, más unos gastos de apoyo al organismo por valor de 24 780 $EUA[footnoteRef:6], y el Banco Mundial, como organismo de ejecución director para Viet Nam, solicitó 185 000 $EUA, más unos gastos de apoyo al organismo por valor de 12 950 $EUA, en sus enmiendas al programa de trabajo para 2021.  [5:  UNEP/OzL.Pro/ExCom/88/30]  [6:  UNEP/OzL.Pro/ExCom/88/32.] 

Comentarios de la Secretaría
Al examinar estas solicitudes, la Secretaría tuvo en cuenta las directrices para la preparación de los PAK contenidas en la decisión 87/50; las actividades propuestas para la preparación de proyectos y su conexión con las actividades de apoyo y otros proyectos relacionados con los HFC en los países pertinentes. La Secretaría señaló que las solicitudes de financiación están en consonancia con la decisión 87/50, y que el PNUMA, en su calidad de organismo de ejecución director, proporcionó una descripción de las actividades necesarias para la preparación de estrategias globales para los PAK de los 10 países, utilizando el formato para las solicitudes de preparación de proyectos para los PAK. Las propuestas incluían estimaciones de las importaciones de HFC y mezclas de HFC para todos los países, actividades para la preparación de proyectos, incluida la elaboración de una estrategia global; una encuesta nacional con las partes interesadas pertinentes sobre el consumo de HFC, el análisis del uso de HFC y alternativas, incluidas las estadísticas de importación y exportación de alternativas a las SAO; consultas para la preparación de una estrategia sobre la introducción de tecnologías de eficiencia energética en el mercado para siete países (Malawi, Namibia, Rwanda, Sierra Leona, República Árabe Siria, Uganda y Zambia); exámenes de las iniciativas, políticas y reglamentos nacionales pertinentes relacionados con la eliminación de los HCFC y la reducción de los HFC para cuatro países (Camboya, Granada, Malawi y Namibia); y reuniones de consulta para finalizar la estrategia global con diversas partes interesadas para todos los países[footnoteRef:7].  [7:  Decisión 87/50] 

El PNUMA aclaró que la preparación de proyectos para las estrategias generales de reducción de los HFC para los 11 países se basaría en las actividades realizadas en el marco de las actividades de apoyo, ya que éstas eran las primeras medidas relacionadas con la reducción de los HFC y habían contribuido a la ratificación de la Enmienda de Kigali. 
Tras este examen, la Secretaría señaló que todos los 13 países para los que el PNUMA solicitó financiación para la preparación de un plan de gestión de la reducción de los HFC han ratificado la Enmienda de Kigali[footnoteRef:8]; los países han proporcionado cartas de apoyo en las que indican su intención de adoptar medidas tempranas para la reducción de los HFC, y que la financiación solicitada se ajusta a la decisión 87/50. [8:  Fechas de ratificación (o aceptación) de la Enmienda de Kigali: Camboya, 8 de abril de 2021; Chile, 19 de septiembre de 2017; Fiji, 16 de junio de 2020; Granada, 29 de mayo de 2018; Lesotho, 7 de octubre de 2019; Liberia, 12 de julio de 2020; Malawi, 21 de noviembre de 2017; Namibia, 16 de mayo de 2019 A; Rwanda, 23 de mayo de 2017; Sierra Leona, 15 de junio de 2020; República Árabe Siria, 5 de abril de 2021; Uganda, 21 de junio de 2018; Viet Nam, 27 de septiembre de 2019 A; y Zambia, 15 de marzo de 2021.] 

Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de la preparación de proyectos para los planes de aplicación de la Enmienda de Kigali en relación con los HFC para Camboya, Chile, Fiji, Granada, Lesotho, Malawi, Namibia, Rwanda, Sierra Leona, la República Árabe Siria, Uganda, Viet Nam y Zambia con el nivel de financiación que figura en la sección A4 de la tabla 1.
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Annex I
INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:9] [9:  Data as at December 2020 are based on document UNEP/OzL.Pro/ExCom/88/12] 

Albania: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec‑01 & Nov‑02 & Jul‑05 
	151,200

	Phase II:
	Jul-06
	109,200

	Phase III:
	Apr-08
	109,200

	Phase IV:
	Jul-10
	109,200

	Phase V:
	Apr-12
	109,200

	Phase VI:
	May-14
	109,200

	Phase VII:
	May-16
	139,776

	Phase VIII:
	Nov-17
	139,776

	Phase IX:
	Dec-19
	139,776

		Total:
	1,116,528

	Amount requested for renewal (phase X) (US $):
	139,776

	Amount recommended for approval for phase X (US $): 
	139,776

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	139,776

	Date of approval of country programme:
	2003

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	6.0

	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.0

	Annex C, Group I (HCFCs)
	3.1

	Annex E (methyl bromide)
	0.0

		Total:
	3.1

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	2,752,153

	Amount disbursed (as at December 2020) (US $):
	2,279,609

	ODS to be phased out (as at July 2021) (ODP tonnes):
	72.4

	ODS phased out (as at December 2020) (ODP tonnes):
	71.8



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	716,932

	(b)
	Institutional strengthening:
	1,116,528

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	918,693

		Total:
	2,752,153

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase IX of the Institutional Strengthening (IS) project, the National Ozone Unit (NOU) of Albania implemented the revised ODS legislation. Article 7 and country programme data (including HFC consumption data) were submitted in a timely manner. The NOU coordinated activities under stages I and II of the HPMP. Several training sessions for service technicians and vocational schools were organized. Outreach materials and activities were produced and organized. Albania also celebrated World Ozone Day 2020, and participated in regional and global Montreal Protocol meetings. Of the 17 performance indicators proposed, 10 were fully achieved and 7 were partially achieved.
Plan of action
 The plan of action for the upcoming phase includes: continuing activities to adopt and implement legislation; building national capacity; monitoring and controlling the import and use of HCFCs and HFCs; facilitating access to alternative substances and technologies; continuing to train technicians in the RAC servicing sector, customs officers, and environment inspectors; supporting Albania’s compliance with Montreal Protocol obligations in partnership with public- and private-sector stakeholders; and conducting public awareness campaigns.
Benin: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-95
	50,000

	Phase II:
	Jul-99
	33,333

	Phase III:
	Mar-01
	33,333

	Phase IV:
	Jul-03
	43,333

	Phase V:
	Jul-06
	60,000

	Phase VI:
	Nov-08
	60,000

	Phase VII:
	Dec-10
	60,000

	Phase VIII:
	Dec-13
	60,000

	Phase IX:
	Nov-15
	85,000

	Phase X:
	Nov-17
	85,000

	Phase XI:
	Dec-19
	85,000

		Total:
	654,999

	Amount requested for renewal (phase XII) (US $):
	85,000

	Amount recommended for approval for phase XII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	23.8

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	13.49

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	13.49

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	2,642,926

	Amount disbursed (as at December 2020) (US $):
	2,359,295

	ODS to be phased out (as at July 2021) (ODP tonnes):
	80.0

	ODS phased out (as at December 2020) (ODP tonnes):
	75.2



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	578,027

	(b)
	Institutional strengthening:
	654,999

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,409,900

		Total:
	2,642,926

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase XI, the NOU of Benin submitted Article 7 and country programme data for 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Coordination meetings were held with the National Ozone Committee and with refrigerant importers and distributors. The NOU supervised the training of 556 RAC technicians and 203 enforcement officers. Information on the availability of HCFC alternatives, on ODS regulations and on decisions by the parties to the Montreal Protocol was disseminated to consumers and importers. Benin also celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. Of the 20 performance indicators proposed, 19 were fully achieved and one was partially achieved.
Plan of action
The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP; continuing to implement and enforce the HCFC licensing and quota system; providing information about annual quotas to importers; organizing meetings with refrigerant importers and distributors; finalizing the enabling activities project; and collecting data for timely reporting to the Ozone and Multilateral Fund Secretariats.
Bhutan: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-04 and Jul-05
	130,000

	Phase II:
	Nov-07
	60,000

	Phase III:
	Jul-09 & Jul-10
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Dec-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Jul-17
	85,000

	Phase VIII:
	May-19
	85,000

	Total:
	600,000

	Amount requested for renewal (phase IX) (US $):
	85,000

	Amount recommended for approval for phase IX (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2005

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

		Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.04

		Annex E, (methyl bromide)
	0.00

	Total:
	0.04

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,583,000

	Amount disbursed (as at December 2020) (US $):
	1,333,925

	ODS to be phased out (as at July 2021) (ODP tonnes):
	0.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.2



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	147,000

	(b)
	Institutional strengthening:
	600,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	836,000

		Total:
	1,583,000

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VIII, The NOU of Bhutan implemented and enforced the licensing and quota system for HCFC import/export and the licensing system for HFCs; provided regular training on the Montreal Protocol, the Kigali Amendment and enforcement activities to customs and other enforcement officers; implemented the Ozone Regulation to effectively monitor illegal trade of all ODS and HFCs; conducted workshops, in collaboration with UNEP, for technicians in the refrigeration and air-conditioning servicing sector in relation to the ratification of the Kigali Amendment; and coordinated the implementation of the HPMP. Of the 16 performance indicators proposed, 13 were fully achieved and three were partially achieved.
Plan of action
 The plan of action for the upcoming phase includes: focusing on continuous implementation of the HPMP and HFC phase-down; focusing on data collection and the quota system to meet HFC phase-down obligations; preparing for the monitoring of HFC consumption; preparing for additional enforcement to control HFCs; providing capacity-building for the servicing sector; and increasing the awareness of key stakeholders and market players.
Cameroon: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-93
	161,000

	Phase II:
	May-97
	107,000

	Phase III:
	Jul-99
	107,000

	Phase IV:
	Dec-03 & Dec-04
	139,532

	Phase V:
	Nov-05
	139,532

	Phase VI:
	Nov-07
	139,532

	Phase VII:
	Nov-09
	139,532

	Phase VIII:
	Nov-11
	139,532

	Phase IX:
	Dec-13
	139,532

	Phase X:
	Nov-15
	178,601

	Phase XI:
	Nov-17
	178,601

	Phase XII:
	Dec-19
	178,601

		Total:
	1,747,995

	Amount requested for renewal (phase XIII) (US $):
	178,601

	Amount recommended for approval for phase XIII (US $): 
	178,601

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	178,601

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2018

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	8.2

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	88.8

	(f)	Annex E (methyl bromide) (average 1995-1998)
	18.1

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	32.53

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	32.53

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	10,299,885

	Amount disbursed (as at December 2020) (US $):
	9,468,948

	ODS to be phased out (as at July 2021) (ODP tonnes):
	737.2

	ODS phased out (as at December 2020) (ODP tonnes):
	734.8



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	7,065,108

	(b)
	Institutional strengthening:
	1,747,995

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,486,782

		Total:
	10,299,885

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase XII, the NOU of Cameroon submitted Article 7 and country programme data for 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Coordination meetings were held with the National Ozone Committee and with the refrigeration association and importers. The Kigali amendment was ratified on 24 August 2021. The NOU also supervised the training of refrigeration and air-conditioning technicians and customs enforcement officers. Information on the availability of HCFC alternatives, on ODS regulations and on MOP decisions was disseminated to consumers and importers. Cameroon also celebrated International Ozone Day and participated in Montreal Protocol meetings. Of the 18 performance indicators proposed, 16 were fully achieved and two were partially achieved.
Plan of action
 The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP; continuing to implement the HCFC licensing and quota system, and providing information about annual quotas to importers; organizing annual stakeholder workshops to raise awareness on low-GWP HCFC alternatives; and collecting data for timely reporting to the Ozone and Multilateral Fund Secretariats.
Comoros: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-97
	27,800

	Phase II:
	Dec-00
	18,533

	Phase III:
	Apr-03
	24,093

	Phase IV:
	Apr-05
	60,000

	Phase V:
	Mar-07
	60,000

	Phase VI:
	Apr-09
	60,000

	Phase VII:
	Jul-11
	60,000

	Phase VIII:
	Jul-13
	60,000

	Phase IX:
	Nov-15
	85,000

	Phase X:
	Nov-17
	85,000

	Phase XI:
	Dec-19
	85,000

		Total:
	625,426

	Amount requested for renewal (phase XII) (US $):
	85,000

	Amount recommended for approval for phase XII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.1

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.05

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.05

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,456,426

	Amount disbursed (as at December 2020) (US $):
	1,309,130

	ODS to be phased out (as at July 2021) (ODP tonnes):
	2.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.4



Summary of activities and funds approved by the Executive Committee:

	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	75,000

	(b)
	Institutional strengthening:
	625,426

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	756,000

		Total:
	1,456,426

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase XI, Comoros submitted Article 7 and country programme data for 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Annual meetings were held with the National Ozone Committee. The NOU supervised the training of refrigeration and air-conditioning technicians, and customs enforcement officers. Information on the availability of HCFC alternatives, on ODS regulations and on MOP decisions was disseminated to consumers and importers. Comoros celebrated International Ozone Day and participated in network and Montreal Protocol meetings. Of the 19 performance indicators proposed, 17 were fully achieved, one was partially achieved and one was not achieved. 
Plan of action
The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP and the submission of stage II; continuing to implement the licensing and quota system for HCFCs and beginning to implement the HFC licensing system; organizing annual stakeholder workshops to raise awareness on low‑GWP HCFC alternatives; collecting gender-disaggregated data and taking the gender dimension into account in all activities; and collecting data for timely reporting to the Ozone and Multilateral Fund Secretariats.
Cook Islands: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-04 & Nov-06
	30,000

	Phase II:
	Nov-07 & Nov-09
	47,500

	Phase III:
	Dec-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	Dec-16
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	427,500

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2004

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.1

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.00

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.00

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	833,550

	Amount disbursed (as at December 2020) (US $):
	508,839

	ODS to be phased out (as at July 2021) (ODP tonnes):
	1.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	427,500

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	406,050

		Total:
	

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII, Cook Islands enforced the licensing system for HCFCs through monitoring of illegal trade; strengthened HFC trade controls based on recommendations from the verification of HCFC consumption; amended existing legislation; and undertook to control the import and export of HCFs as of January 2021, seeking to finalize the related regulation. The National Ozone Officer (NOO) worked in close collaboration with stakeholders to implement the Montreal Protocol and sustain compliance. Article 7 and country programme data were submitted to the Ozone and Multilateral Fund Secretariats. The NOU organized and delivered the World Ozone Day celebrations and participated in the regional network meetings. Of the 20 performance indicators proposed, 11 were fully achieved, six were partially achieved and three were not achieved.
Plan of action
 The plan of action for the upcoming phase includes: enforcing the HCFC and HCFC-based equipment ban and implementing the HFC licensing system, including the quota system; adopting and implementing individual HS codes (PACHS22) for HFCs and blends; submitting Article 7 and country programme data; engaging and coordinating with national stakeholders and the RAC association for the implementation of the HPMP; strengthening national capacity for the preparation of the HFC phase‑down; organizing World Ozone Day and developing awareness materials; and participating in meetings related to the Montreal Protocol. 
Micronesia (Federated States of): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	34,000

	Phase II:
	Jul-06 & Jul-09
	41,333

	Phase III:
	Jul-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	Dec-16
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	425,333

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.2

	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.09

	Annex E (methyl bromide)
	0.00

		Total:
	0.09

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	895,433

	Amount disbursed (as at December 2020) (US $):
	528,076

	ODS to be phased out (as at July 2021) (ODP tonnes):
	1.1

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



1.  Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	425,333

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	470,100

		Total:
	895,433

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII, Federated States of Micronesia sustained compliance through legislation, the licensing and quota system, monitoring and enforcement, capacity-building, the involvement of the RAC Association and awareness-raising activities. The ODS regulations were amended to expand their scope for controlling and monitoring HFC imports into the country and to establish the HFC licensing system, effective from February 2021. Article 7 and country programme data for 2019 and 2020 were reported to the Multilateral Fund and Ozone Secretariats. Of the 19 performance indicators proposed, 14 were fully achieved and five were partially achieved.
Plan of action
The plan of action for the upcoming phase includes: implementing the HCFC quota and licensing system and HFC licensing system, and setting up of the HFC quota system; adopting individual HS codes (PACHS22) for HFCs and blends in all States; submitting Article 7 and country programme data reports in a timely fashion; engaging the National Steering Committee and RAC Associations in the implementation of Montreal Protocol activities; coordinating with stakeholders for the implementation of the HPMP; organizing World Ozone Day celebrations and developing awareness materials; and participating in regional and international meetings. 

Guatemala: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jun-93
	172,000

	Phase II:
	May-97
	96,000

	Phase III:
	Jul-99
	96,000

	Phase IV:
	Dec-01
	96,000

	Phase V:
	Jul-04
	62,400

	Phase VI:
	Nov-07
	124,800

	Phase VII:
	Jul-10
	124,800

	Phase VIII:
	Jun-18
	159,744

		Total:
	931,744

	Amount requested for renewal (phase IX) (US $):
	159,744

	Amount recommended for approval for phase IX (US $): 
	159,744

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	159,744

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	8.3

	Annex E (methyl bromide) (average 1995-1998)
	400.7

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.0

	Annex C, Group I (HCFCs)
	4.0

	Annex E (methyl bromide)
	0.0

		Total:
	4.0

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	10,088,208

	Amount disbursed (as at December 2020) (US $):
	9,113,007

	ODS to be phased out (as at July 2021) (ODP tonnes):
	1,129.579006

	ODS phased out (as at December 2020) (ODP tonnes):
	1,117.9



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	6,882,044

	(b)
	Institutional strengthening:
	931,744

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,274,420

		Total:
	10,088,208

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase VIII, the NOO of Guatemala reported Article 7 and country programme data to the Multilateral Fund and Ozone Secretariats. The NOU coordinated HPMP activities and activities for the phase-out of methyl bromide. The NOO also coordinated ODS import/export controls with the General Direction of Customs and other enforcement authorities; conducted awareness-raising activities among ODS importers, suppliers, end-users and general public; and promoted good practices in refrigeration, technician certification and customs officer training. Guatemala also participated in meetings relating to the Montreal Protocol. Of the 29 performance indicators proposed, 25 were fully achieved, three were partially achieved and one was not achieved.
Plan of action
The plan of action for the upcoming phase includes: continuing to revise ODS legislation to fulfill the Kigali amendment requirements; strictly monitoring and controlling the imports and use of HCFCs/HFCs; and facilitating access to new alternative substances and technologies. The NOU will also promote ratification of the Kigali amendment and HFC phase-down; continue coordinating with customs for effective monitoring of international trade of controlled substances; engage stakeholders in HPMP implementation; and continue public awareness activities, as well as training of servicing technicians in the safe use of flammable refrigerants.
Namibia: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-95
	61,765

	Phase II:
	Jul-00
	41,177

	Phase III:
	Dec-03
	53,530

	Phase IV:
	Nov-05
	60,000

	Phase V:
	Nov-07
	60,000

	Phase VI:
	Nov-09
	60,000

	Phase VII:
	Apr-12
	60,000

	Phase VIII:
	Nov-14
	60,000

	Phase IX:
	Jul-17
	85,000

	Phase X:
	Dec-19
	85,000

		Total:
	626,472

	Amount requested for renewal (phase XI) (US $):
	85,000

	Amount recommended for approval for phase XI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	8.4

	Annex E, (methyl bromide) (average 1995-1998)
	0.8

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	o.74

	Annex E (methyl bromide)
	0.00

		Total:
	0.74

	Year of reported country programme implementation data:
	2020

	Summary of the project and country profile
	

	Amount approved for projects (as at July 2021) (US $):
	2,302,062

	Amount disbursed (as at December 2020) (US $):
	1,951,919

	ODS to be phased out (as at July 2021) (ODP tonnes):
	25.6

	ODS phased out (as at December 2020) (ODP tonnes):
	20.3



2. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,062,500

	(b)
	Institutional strengthening:
	626,472

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	613,090

		Total:
	2,302,062

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase X, The NOU of Namibia implemented ODS regulations through the enforcement of the licensing and quota system for HCFCs. The NOU completed the enabling activities project, embarked on an awareness programme, and conducted training for customs officers, clearing agents and refrigeration technicians and other stakeholders. The NOU assisted in amending the legislation to include control of HFC consumption in line with Kigali Amendment, which provided the opportunity to include an HFC licensing and quota system that is now operational. The NOU organized World Ozone Day and other awareness-raising activities, and conducted several training workshops and meetings using online platforms. Of the 16 performance indicators proposed, 15 were fully achieved and one was partially achieved.
Plan of action
The plan of action for the upcoming phase includes: continuing with the training programme for technicians in the refrigeration sector and customs officers/clearing agents for the enforcement of the ODS regulations; continuing the awareness-raising programme and the distribution of awareness materials to the industry and other stakeholders; continuing the timely submission of Article 7 and country programme implementation data to the Multilateral Fund and Ozone Secretariats; and attending regional and international meetings, workshops and events.
Paraguay: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Feb-97
	66,300

	Phase II:
	Dec-00
	44,200

	Phase III:
	Apr-03
	57,460

	Phase IV:
	Nov-07
	60,000

	Phase V:
	Jul-10
	60,000

	Phase VI:
	Apr-12
	60,000

	Phase VII:
	May-14
	60,000

	Phase VIII:
	Dec-16
	85,000

	Phase IX:
	Dec-18
	85,000

		Total:
	577,960

	Amount requested for renewal (phase X) (US $):
	85,000

	Amount recommended for approval for phase X(US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2021

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	18.0

	Annex E (methyl bromide)
	0.9

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	10.91

	Annex E (methyl bromide)
	0.00

		Total:
	10.91

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	4,210,637

	Amount disbursed (as at December 2020) (US $):
	3,341,267

	ODS to be phased out (as at July 2021) (ODP tonnes):
	345.1

	ODS phased out (as at December 2020) (ODP tonnes):
	340.4



3. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,588,524

	(b)
	Institutional strengthening:
	577,960

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,044,153

		Total:
	4,210,637

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Under phase IX, the NOU of Paraguay worked to achieve broad consensus on revised national ODS legislation. The NOU also submitted Article 7 and country programme implementation data in a timely manner for 2018, 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Several training sessions for service technicians and for customs officers were organized, and technical vocational schools were equipped with training equipment. The NOU produced several information and outreach materials and organized extensive World Ozone Day events in 2019 and 2020; organized the regional network meeting for Latin America in 2019 and participated in virtual network meetings. Of the 26 performance indicators proposed, 23 were fully achieved and three were partially achieved.
Plan of action
The plan of action for the upcoming tranche includes: continuing revision of ODS legislation in line with the Kigali Amendment; strictly monitoring and controlling the imports and use of HCFCs and HFCs, and facilitating access to and use of new alternative substances and technologies; continuing to coordination with customs to ensure effective surveillance of international trade; facilitating the involvement of main stakeholders; generating the mechanisms to reduce demand for equipment that works with HCFC; implementing a database of RAC technicians trained and certified in the handling of alternatives to HCFCs and HFCs; training servicing technicians in safety practices with flammable refrigerants; and continuing public awareness activities, especially with the education sector and with a gender focus, during the World Refrigeration Day, World Ozone Day celebrations and national events. 

Saint Vincent and the Grenadines: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-98
	30,300

	Phase II:
	Apr-04 & Apr-05
	43,130

	Phase III:
	Nov 06
	60,000

	Phase IV:
	Jul-09 & Dec-10
	60,000

	Phase V:
	Apr-12
	60,000

	Phase VI:
	Nov-14
	60,000

	Phase VII:
	Nov-17
	85,000

		Total:
	398,430

	Amount requested for renewal (phase VIII) (US $):
	85,000

	
Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.01

	Annex E (methyl bromide)
	0.00

		Total:
	0.01

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,348,354

	Amount disbursed (as at December 2020) (US $):
	1,063,097

	ODS to be phased out (as at July 2021) (ODP tonnes):
	2.3

	ODS phased out (as at December 2020) (ODP tonnes):
	2.2



4. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	252,115

	(b)
	Institutional strengthening:
	398,430

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	697,809

		Total:
	1,348,354

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII, the NOU of Saint Vincent and the Grenadines submitted 2020 country programme and Article 7 data despite challenges linked to the pandemic and the La Soufriere volcanic eruption. The NOU continued to promote low-GWP energy efficient technologies through information dissemination, and reviewed draft National Refrigerant Labelling Standards with support from the RAC Association and the National Steering Committee; conducted public awareness initiatives and provided training to servicing technicians in good practices and the use of alternative technologies. Of the 25 performance indicators proposed, 20 were fully achieved, five were partially achieved and five were not achieved. 
Plan of action
The plan of action for the upcoming phase includes: continuing to monitor and control the importation of refrigerants through testing and enforcement; continuing to develop national standards for the safe handling, transport and storage of refrigerants; implementing the revised regulations that include mandatory certification of technicians and the imposition of various fees including a licensing fee for all imports of non-ozone-friendly substances; and continuing public education and awareness activities. 


Senegal: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-93
	175,000

	Phase II:
	Nov-97
	117,000

	Phase III:
	Nov-99
	117,000

	Phase IV:
	Mar-02
	152,100

	Phase V:
	Dec-03
	152,100

	Phase VI:
	Nov-05
	152,100

	Phase VII:
	Nov-07
	152,100

	Phase VIII:
	Nov-09
	152,101

	Phase IX:
	Nov-11
	152,101

	Phase X:
	Dec-13
	152,101

	Phase XI:
	Nov-15
	194,689

	Phase XII:
	Nov-17
	194,689

	Phase XIII:
	Dec-19
	194,689

	Total:
	2,057,770

	Amount requested for renewal (phase XIV) (US $):
	194,689

	Amount recommended for approval for phase XIV (US $): 
	194,689

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	194,689

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	36.2

	(f)	Annex E (methyl bromide) (average 1995-1998)
	53.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	13.2

	(f)	Annex E (methyl bromide)
	0.0

	Total:
	13.2

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	4,496,195

	Amount disbursed (as at December 2020) (US $):
	3,929,827

	ODS to be phased out (as at July 2021) (ODP tonnes):
	196.3

	ODS phased out (as at December 2020) (ODP tonnes):
	148.1



5. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	747,945

	(b)
	Institutional strengthening:
	2,057,770

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,690,480

		Total:
	4,496,195

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Under phase XIII, the NOU of Senegal submitted Article 7 and country programme data to the Multilateral Fund and Ozone Secretariats. Coordination meetings were held with the National Ozone Committee and with industry association and RAC associations, and the NOU supervised the training of RAC technicians and customs and enforcement officers. Awareness activities were conducted, including the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on laws such as the control or ban of HCFC-based equipment, regulations and decisions by the Parties to the Montreal Protocol. Senegal celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. Of the 18 performance indicators proposed, 15 were fully achieved, two were partially achieved and one was not achieved. 
Plan of action
The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; continuing implementation of the licensing and quota system for HCFCs and providing information about annual quotas to importers; beginning the technician certification programme; continuing monitoring and evaluation; organizing annual stakeholder workshops to raise awareness on low‑GWP HCFC alternatives; collecting and reporting data to the Ozone and Multilateral Fund Secretariats; and undertaking national communication on the country’s reasons for ratifying the Kigali Amendment.
Solomon Islands: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	20,250

	Phase II:
	Jul-06 & Nov-07
	36,833

	Phase III:
	Nov-09 & Apr-10
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Nov-17
	85,000

	Phase VIII:
	May-19
	85,000

		Total:
	467,083

	Amount requested for renewal (phase IX) (US $):
	85,000

	Amount recommended for approval for phase IX (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	2.0

		Annex E, (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.08

		Annex E, (methyl bromide)
	0.00

		Total:
	0.08

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,160,333

	Amount disbursed (as at December 2020) (US $):
	706,680

	ODS to be phased out (as at July 2021) (ODP tonnes):
	3.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	467,083

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	693,250

		Total:
	1,160,333

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase VIII, the NOU of the Solomon Islands helped develop an online system to enhance effectiveness in tracking and monitoring of trade of controlled substances including HFCs. The NOU submitted Article 7 and country programme data to the Ozone Secretariat and Multilateral Fund Secretariats, conducted awareness-raising activities, and engaged stakeholders, the National Steering Committee and the RAC Association. The NOU continued to follow up on the ratification of the Kigali Amendment and began drafting legislation to include the mandatory control of HFCs. The NOU participated in meetings of the Montreal Protocol. Of the 20 performance indicators proposed, 14 were fully achieved, three were partially achieved and three were not achieved.
Plan of action
The plan of action for the upcoming phase includes: enacting the Ozone Layer Protection Regulation that controls HCFCs and HFCs, as well as working to launch the electronic licensing system for both HCFCs and HFCs; continuing joint inspections with the Customs Department and Solomon Islands Refrigeration and Air-conditioning Association (SIRAC) to monitor ODS trade; coordination and supporting the National ODS Steering Committee and RAC Association in the implementation of Montreal Protocol activities; continuing to raise awareness and organize World Ozone Day; participating in relevant Montreal Protocol meetings; and supporting ratification of the Kigali Amendment.
Sudan: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	168,300

	Phase II:
	Jul-99
	112,200

	Phase III:
	Jul-01
	112,200

	Phase IV:
	Apr-04
	145,860

	Phase V:
	Jul-09
	109,395

	Phase VI:
	Dec-10
	145,860

	Phase VII:
	Apr-13
	145,860

	Phase VIII:
	Apr-13
	186,701

	Phase IX:
	Jun-18
	186,701

		Total:
	1,313,077

	Amount requested for renewal (phase X) (US $):
	186,701

	Amount recommended for approval for phase X (US $): 
	186,701

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	186,701

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan (stage I):
	2012

	Date of approval of HCFC phase-out management plan (stage II):
	2015

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	52.7

	(f)	Annex E (methyl bromide) (average 1995-1998)
	3.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	10.59

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	10.59

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	9,146,045

	Amount disbursed (as at December 2020) (US $):
	6,748,784

	ODS to be phased out (as at July 2021) (ODP tonnes):
	678.1

	ODS phased out (as at December 2020) (ODP tonnes):
	662.9



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	6,148,108

	(b)
	Institutional strengthening:
	1,313,077

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,684,860

		Total:
	9,146,045

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase IX, the NOU of Sudan made progress towards ratification of the Kigali Amendment. The NOU implemented ODS regulations through the enforcement of the HCFC licensing and quota system. Regulations have been revised to include an HFC licensing system and HFC import control, pending approval by the relevant authorities. The NOU conducted awareness-raising activities on the Montreal Protocol and Ozone Day celebrations, and trained refrigeration technicians in the safe handling of low‑GWP alternatives. The Steering Committee and the Refrigeration Association were involved in the implementation of the Montreal Protocol activities. Of the 16 performance indicators proposed, nine were fully achieved, five were partially achieved and two were not achieved. 
Plan of action
The plan of action for the upcoming phase includes: enforcing the import licensing and quota system more rigorously; conducting a training programme for technicians in the refrigeration sector; continuing to encourage ratification of the Kigali Amendment; continuing to train customs officers to support the implementation and enforcement of ODS regulations; continuing to follow-up on the approval of revised ODS regulations, which include an HFC licensing system; continuing the awareness-raising programme; continuing to submit Article 7 and country programme data to the Multilateral Fund and Ozone Secretariats; and participating in meetings, workshops and events related to the Montreal Protocol.
Timor-Leste: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-08
	40,000

	Phase II:
	Jul-10 & Jul-11
	60,000

	Phase III:
	Apr-13
	60,000

	Phase IV:
	May-16
	85,000

	Phase V:
	Dec-19
	85,000

		Total:
	330,000

	Amount requested for renewal (phase VI) (US $):
	85,000

	Amount recommended for approval for phase VI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2009

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2017

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.1

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.5

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.15

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.15

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	994,700

	Amount disbursed (as at December 2020) (US $):
	723,178

	ODS to be phased out (as at July 2021) (ODP tonnes):
	0.0

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	161,800

	(b)
	Institutional strengthening:
	330,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	502,900

		Total:
	994,700

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
During phase V, the NOU of Timor-Leste continued to enforce the licensing and quota system in accordance with the Decree-Law No. No. 36/2012; it further strengthened collaboration with the Directorate General for Customs to enforce the HCFC licensing and quota system through the National Single Window System under ASYCUDA, which integrates the risk profiling for ODS control. The NOU worked closely with the importers, customs brokers and the Directorate General for Customs to strengthen national data reconciliation and reporting procedures. Article 7 and country programme data for 2019 and 2020 were submitted to the Multilateral Fund and Ozone Secretariats. The NOO also worked closely with the Steering Committee and RAC industries; organized public awareness activities and joined meetings on the Montreal Protocol. The Government continued to work with national stakeholders on the ratification of the Kigali Amendment. Of the 18 performance indicators proposed, 15 were fully achieved and three were partially achieved.
Plan of action
The plan of action for the upcoming phase includes: strictly enforcing of HCFC licensing and quota system through the National Single Window System; implementing the HFC import and export licensing system after approval of an amendment to the existing Decree-law and the setting of HFC quota allocation criteria to be implemented from 1 January 2024; strengthening the monitoring and reporting of ODS import and export; conducting capacity-building activities for enforcement officers and refrigeration technicians; continuing to follow-up on the internal process for ratification of the Kigali Amendment; ensuring the continuity of the awareness programme and information exchange including the celebration of the World Ozone Day; and promoting international and regional cooperation on the implementation of the Montreal Protocol. 
Vanuatu: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	20,250

	Phase II:
	Apr-08 & Nov-09
	39,250

	Phase III:
	Dec-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	Dec-16
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	409,500

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.00

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.00

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	944,100

	Amount disbursed (as at December 2020) (US $):
	600,492

	ODS to be phased out (as at July 2021) (ODP tonnes):
	0.28

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



6. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	409,500

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	534,600

	
	Total:
	944,100

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



[bookmark: _GoBack]Progress report
During phase VII, the Government of Vanuatu strengthened its licensing and quota system by changing from an annual license to a per-shipment license. Actions were carried out to facilitate Kigali Amendment implementation, including the HFC licensing system in force since February 2020 under the new OLP Act. Vanuatu fulfilled its Article 7 and country programme data reporting obligations for 2019 and 2020. The NOO promoted and supported the implementation of the national RAC certification scheme; organized public awareness activities, organized World Ozone Day celebrations, and joined the meetings on the Montreal Protocol. Of the 18 performance indicators proposed, 15 indicators were fully achieved, two were partially achieved and one was not achieved.
Plan of action
The plan of action for the upcoming phase includes: effectively implementing the HCFC and HFC licensing system, and creating the HFC quota system; implementing individual HS codes (PACHS22) for HFCs and blends; submitting Article 7 and country programme data in a timely fashion; actively engaging national stakeholders and the RAC Association in the implementation of Montreal Protocol; organizing the World Ozone Day celebrations and developing awareness materials; and participating in regional and international meetings. Moreover, the phase will strengthen national capacity to support Vanuatu in preparing for HFC phase-down.
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Anexo II 
OPINIONES PRELIMINARES EXPRESADAS POR EL COMITÉ EJECUTIVO SOBRE LA RENOVACIÓN DE PROYECTOS DE FORTALECIMIENTO INSTITUCIONAL PRESENTADOS A LA 88a REUNIÓN

Albania
1. El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional (fase IX) para Albania y tomó nota con beneplácito de que el Gobierno de Albania comunicó a la Secretaría del Ozono los datos de 2019 y 2020 que indican que el país cumple con el Protocolo de Montreal y los datos de ejecución del programa de país a la Secretaría del Fondo. El Comité tomó nota de que existe un sistema operativo de licencias de importación y exportación de SAO y de cuotas de HCFC, y que Albania también estableció un sistema de licencias de HFC. El Comité también tomó nota con beneplácito de que el país ha obtenido el apoyo de las partes interesadas a través del comité directivo y de las reuniones de consulta, y ha sensibilizado al público sobre la protección de la capa de ozono. Por lo tanto, el Comité confía en que Albania seguirá aplicando su plan de gestión de la eliminación de los HCFC y su proyecto de fortalecimiento institucional de manera oportuna y eficaz, a fin de preparar al país para cumplir y mantener la reducción del 67,5% de su consumo de referencia de HCFC en 2025.
Benín
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional (fase XI) para Benín y tomó nota con beneplácito de que el Gobierno de Benín comunicó a la Secretaría del Ozono los datos de 2019 y 2020 que indican que el país cumple con el Protocolo de Montreal y los datos de ejecución del programa de país a la Secretaría del Fondo. El Comité también tomó nota de que Benín ha adoptado algunas medidas importantes para eliminar su consumo de HCFC en la fase actual, en particular la aplicación de controles de importación de SAO mediante un sistema de licencias y cuotas y la capacitación de funcionarios de aduanas y técnicos de refrigeración. El Comité tomó nota con beneplácito de que el país alcanzó una reducción del 35% en el consumo de HCFC en 2020, según los requisitos del Protocolo de Montreal. El Comité aprecia enormemente los esfuerzos del Gobierno de Benín para reducir el consumo de HCFC y, por lo tanto, espera que, en los próximos dos años, Benín continúe la ejecución de su proyecto de fortalecimiento institucional con un éxito extraordinario para lograr y mantener el cumplimiento del Protocolo de Montreal.
Bhután
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para Bhután (fase IX) y reconoce con beneplácito los esfuerzos realizados por el país en la preparación y la aplicación del sistema de concesión de licencias de HFC, la ratificación de la Enmienda de Kigali y la presentación puntual de los informes de datos conforme al artículo 7 y al programa de país. El Comité también toma nota con beneplácito de que el país mantiene un sólido sistema de licencias y cuotas para los HCFC y está aplicando su sistema de licencias de importación para los HFC, lo que permitió a Bhután cumplir con sus obligaciones durante el período del informe. El Comité también toma nota de que el PGEH se está ejecutando según lo previsto, ya que el país ha alcanzado el objetivo de reducción del 35% para 2020 y ha completado con éxito la ejecución del proyecto de actividades de apoyo para la reducción de los HFC. Por lo tanto, el Comité confía en que Bhután continuará con las actividades relacionadas tanto con los proyectos como con las políticas, para cumplir los futuros objetivos del Protocolo de Montreal.


Camerún
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para Camerún (fase XII) y tomó nota con beneplácito de que Camerún comunicó los datos de importación de HCFC para 2020 en virtud del artículo 7 y la presentación de informes del programa de país a las Secretarías del Ozono y del Fondo Multilateral, datos que indican que el país cumple con el Protocolo de Montreal. El Comité también tomó nota de que Camerún ha adoptado algunas medidas importantes para eliminar su consumo de HCFC en la fase actual, en particular la aplicación de controles de importación de SAO mediante un sistema de licencias y cuotas y la capacitación de funcionarios de aduanas y técnicos de refrigeración. El Comité felicitó al Gobierno de Camerún por la ratificación de la Enmienda de Kigali en agosto de 2021. El Comité apreció los esfuerzos del Gobierno de Camerún para reducir el consumo de HCFC y, por lo tanto, espera que, en los próximos dos años, Camerún continúe con la exitosa ejecución de su proyecto de fortalecimiento institucional para lograr y mantener el cumplimiento del Protocolo de Montreal.
Comoras
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para Comoras (fase XI) y tomó nota con beneplácito de que Comoras comunicó los datos de importación de HCFC para 2019 y 2020 en virtud del artículo 7 y la presentación de informes del programa de país a las Secretarías del Ozono y del Fondo Multilateral, datos que indican que el país cumple con el Protocolo de Montreal. El Comité también tomó nota de que Comoras ha adoptado algunas medidas importantes para eliminar su consumo de HCFC, en particular la aplicación de controles de importación de SAO mediante un sistema de licencias y cuotas y la capacitación de funcionarios de aduanas y técnicos de refrigeración. El Comité tomó nota con beneplácito del establecimiento del sistema de licencias de HFC en las Comoras. El Comité aprecia asimismo los esfuerzos del Gobierno de Comoras para reducir el consumo de HCFC y espera que, en los próximos dos años, Comoras continúe la ejecución de su proyecto de fortalecimiento institucional con un éxito extraordinario para lograr y mantener el cumplimiento del Protocolo de Montreal.
Islas Cook
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para las Islas Cook (fase VIII) y tomó nota con beneplácito de que las Islas Cook comunicaron a las Secretarías del Ozono y del Fondo Multilateral los datos conforme al artículo 7 y al programa de país para 2019 y 2020, datos que indican que el país cumple con los requisitos de eliminación del Protocolo de Montreal. El Comité reconoció con aprecio que las Islas Cook han mantenido un consumo cero de SAO. El Comité también tomó nota con beneplácito de los esfuerzos de las Islas Cook por utilizar las lecciones aprendidas en la verificación del consumo de HCFC para seguir mejorando el sistema de concesión de licencias para controlar la importación y exportación de HFC, tal y como se refleja en el marco de la enmienda legal. El Comité espera que, en los próximos dos años, las Islas Cook continúen con la ejecución del proyecto fortalecimiento institucional con un éxito extraordinario para lograr y mantener el cumplimiento del Protocolo de Montreal.
Micronesia (Estados Federados de)
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para los Estados Federados de Micronesia (fase VII) y tomó nota con beneplácito de que los Estados Federados de Micronesia comunicaron a las Secretarías del Ozono y del Fondo Multilateral los datos conforme al artículo 7 y al programa de país para 2019 y 2020, datos que indican que el país cumple con los requisitos de eliminación del Protocolo de Montreal. El Comité tomó nota con beneplácito de la aplicación eficaz del sistema de licencias y cuotas para los HCFC, el establecimiento del sistema de licencias para los HFC y la coordinación con las partes interesadas pertinentes. El Comité elogió al Gobierno de los Estados Federados de Micronesia por lograr una reducción del consumo de HCFC superior al 35% en 2020. El Comité tomó nota con beneplácito del mayor nivel de sensibilización pública creado para informar a las principales partes interesadas y al público en general sobre la eliminación conforme al PGEH y las obligaciones de la Enmienda de Kigali. Por lo tanto, el Comité espera que, en los próximos dos años, el Gobierno de los Estados Federados de Micronesia continúe aplicando eficazmente la nueva normativa para seguir ejecutando el proyecto de fortalecimiento institucional con un éxito extraordinario para lograr y mantener el cumplimiento del Protocolo de Montreal.
Guatemala
El Comité Ejecutivo examinó el informe presentado con la solicitud del proyecto de fortalecimiento institucional para Guatemala (fase VIII) y tomó nota con beneplácito de que el Gobierno de Guatemala comunicó los datos de 2019 y 2020 a las Secretarías del Ozono y del Fondo Multilateral, datos que indican que el país está cumpliendo con el Protocolo de Montreal. El Comité también tomó nota de que Guatemala cuenta con un sistema operativo de licencias de importación y exportación de SAO y de cuotas de HCFC y ha incluido los HFC en el sistema de licencias. El Comité tomó nota de que Guatemala ha llevado a cabo con éxito actividades de sensibilización y divulgación sobre buenas prácticas de refrigeración y la manipulación segura de refrigerantes inflamables entre los técnicos de refrigeración y los usuarios finales y ha reforzado la relación con la Asociación de Técnicos de Refrigeración de Guatemala (ASFRIGUA). Además, el Comité tomó nota de que Guatemala está finalizando el proyecto de actividades de apoyo a la ratificación de la Enmienda de Kigali y ha realizado importantes avances hacia la ratificación. Por lo tanto, el Comité confía en que Guatemala ratificará pronto la Enmienda de Kigali y continuará la ejecución del proyecto de fortalecimiento institucional con un éxito extraordinario para lograr y mantener el cumplimiento del Protocolo de Montreal.
Namibia
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para Namibia (fase XI) y tomó nota con beneplácito de que Namibia comunicó puntualmente los datos del programa de país y del artículo 7 a las Secretarías del Fondo y del Ozono, datos que indican que el país cumple el Protocolo de Montreal y su Acuerdo con el Comité Ejecutivo. El Comité tomó nota de que Namibia ha adoptado medidas para abordar la eliminación de los HCFC, incluida la aplicación de un sistema de licencias y cuotas para los HCFC, y la capacitación de funcionarios de aduanas y técnicos de refrigeración. Además, el Comité tomó nota con beneplácito de la ratificación de la Enmienda de Kigali por parte del país en mayo de 2019, con el compromiso de actuar con prontitud en su aplicación. Por lo tanto, el Comité confía en que Namibia continuará su reducción progresiva del consumo de HCFC para alcanzar el objetivo del 67,5% para el 1 de enero de 2025 y cumplir con sus otras obligaciones en virtud del Protocolo de Montreal.
Paraguay
El Comité Ejecutivo examinó el informe presentado con la solicitud del proyecto de fortalecimiento institucional para Paraguay (fase X) y tomó nota con beneplácito de que Paraguay ha cumplido con sus obligaciones de presentación de datos en virtud del artículo 7 y de eliminación de los HCFC en el marco del Protocolo de Montreal, y de que existe un sistema operativo de concesión de licencias de importación y exportación de SAO y de cuotas de HCFC que incluye los HFC en el sistema de concesión de licencias. El Comité tomó nota además de que Paraguay presentó a la Secretaría los datos de ejecución del programa de país de manera oportuna. El Comité se congratuló de que el país haya capacitado a técnicos de refrigeración en buenas prácticas de refrigeración y en la manipulación segura de sustancias alternativas, haya obtenido el apoyo de las partes interesadas a través del comité directivo y se haya comprometido a formular normas y estándares para la manipulación segura de refrigerantes alternativos. El Comité también tomó nota de que Paraguay llevó a cabo reuniones de consulta y sensibilizó al público sobre la protección de la capa de ozono. Por lo tanto, el Comité confía en que Paraguay continuará ejecutando el proyecto de fortalecimiento institucional de manera eficaz para cumplir con los objetivos de eliminación de los HCFC para 2030 y en preparación para la reducción de los HFC.
San Vicente y las Granadinas
El Comité Ejecutivo examinó el informe presentado con la solicitud del proyecto de fortalecimiento institucional para San Vicente y las Granadinas (fase VII) y tomó nota con beneplácito de que el país ha comunicado la ejecución del programa de país para 2020 y los datos del artículo 7 a las Secretarías del Fondo Multilateral y del Ozono con antelación a los plazos establecidos. El Comité reconoció con beneplácito que el Gobierno de San Vicente y las Granadinas tiene un sistema de licencias y cuotas de HCFC bien estructurado y operativo que incluye la concesión de licencias de HFC. El Comité tomó nota con beneplácito de que el país ha adoptado medidas para iniciar la ratificación de la Enmienda de Kigali al Protocolo de Montreal. El Comité también tomó nota con beneplácito de los esfuerzos realizados por el Gobierno tras la erupción del volcán La Soufriere de abril de 2021. Por lo tanto, el Comité confía en que el Gobierno de San Vicente y las Granadinas continuará con las actividades relacionadas tanto con las políticas como con los proyectos, para garantizar que su consumo anual de HCFC no supere el consumo máximo permitido en el acuerdo del PGEH con el Comité Ejecutivo, y el país ratifique la Enmienda de Kigali.
Senegal
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para Senegal (fase XIV) y tomó nota con beneplácito de que Senegal comunicó a la Secretaría del Ozono los datos de 2019 y 2020 que indican que el país está cumpliendo con el Protocolo de Montreal. El Comité también tomó nota asimismo de que Senegal ha adoptado algunas medidas importantes para eliminar su consumo de HCFC en el periodo cubierto, en particular la aplicación de controles de importación de SAO mediante un sistema de licencias y cuotas y la capacitación de funcionarios de aduanas y técnicos de refrigeración. El Comité apreció los esfuerzos de Senegal para reducir el consumo de HCFC y tomó nota de que la reducción del 35% del consumo de HCFC se logró en 2020 de acuerdo con los requisitos del Protocolo de Montreal. El Comité espera que, en los próximos dos años, Senegal continúe con la ejecución de su proyecto de fortalecimiento institucional con éxito para seguir cumpliendo el Protocolo de Montreal.
Islas Salomón
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para las Islas Salomón (fase VIII) y tomó nota con beneplácito de que el país está haciendo lo necesario para cumplir las medidas de control del Protocolo de Montreal relacionadas con los HCFC y los HFC. El Comité tomó nota con beneplácito de que el país ha notificado la ejecución del programa de país de 2019 y 2020 y los datos del artículo 7 a las Secretarías del Fondo Multilateral y del Ozono. El Comité elogió al Gobierno de las Islas Salomón por la elaboración de un proyecto de ley sobre la protección de la capa de ozono que incluye el control obligatorio de los HFC y la transición a un sistema electrónico de licencias y cuotas. El Comité tomó nota de que las Islas Salomón aceleraron la ejecución del proyecto a pesar de las dificultades impuestas por la pandemia de Covid-19. El Comité también observó que el país cumplió con su obligación de reducción del 35% en virtud del Protocolo de Montreal en 2020. El Comité espera que, en la próxima fase del proyecto de fortalecimiento institucional, el Gobierno de las Islas Salomón complete la ratificación de la Enmienda de Kigali, apruebe el proyecto de ley sobre la protección de la capa de ozono y cumpla con los requisitos de presentación de informes.
Sudán
El Comité Ejecutivo examinó el informe presentado con la solicitud de renovación del proyecto de fortalecimiento institucional para Sudán (fase X) y tomó nota con beneplácito de que Sudán comunicó a las Secretarías del Fondo Multilateral y del Ozono los datos de ejecución del programa de país de 2018, 2019 y 2020 y los datos del artículo 7, datos que indican que el país cumple con el Protocolo de Montreal. El Comité reconoció que Sudán cuenta con un sistema operativo de licencias y cuotas de HCFC, ha llevado a cabo la capacitación de técnicos de refrigeración en la manipulación segura de alternativas de bajo potencial de calentamiento de la atmósfera (PCA) y ha realizado actividades de sensibilización. El Comité reconoció los esfuerzos del Gobierno de Sudán y, por lo tanto, confía en que Sudán continuará con las actividades relacionadas tanto con las políticas como con los proyectos, para que el país pueda reducir el consumo de HCFC y alcanzar la reducción del 67,5% requerida por el Protocolo de Montreal para el 1 de enero de 2025. El Comité también espera que la Enmienda de Kigali sea ratificada en la próxima fase.
Timor-Leste
El Comité Ejecutivo examinó el informe presentado con la solicitud del proyecto de fortalecimiento institucional para Timor-Leste (fase VI) y tomó nota con beneplácito de que el Gobierno de Timor-Leste comunicó los datos de 2019 y 2020 a las Secretarías del Ozono y del Fondo Multilateral, datos que indican que el país está cumpliendo con el Protocolo de Montreal. El Comité también tomó nota con beneplácito de que el país siguió reforzando su sistema de licencias y cuotas de HCFC a través del Sistema Nacional de Ventanilla Única, que mejoró el mecanismo existente para la recopilación y conciliación eficaces de datos, y que proporcionó informes de datos precisos. El Comité confía en que Timor-Leste siga ejecutando su proyecto de fortalecimiento institucional de manera oportuna y eficaz y que ratifique pronto la Enmienda de Kigali.
Vanuatu
El Comité Ejecutivo examinó el informe presentado con la solicitud del proyecto de fortalecimiento institucional (fase VIII) para Vanuatu y tomó nota con beneplácito de que Vanuatu comunicó a las Secretarías del Ozono y del Fondo Multilateral los datos del artículo 7 y del programa de país para 2019 y 2020, datos que indican que el país cumple con los requisitos de eliminación del Protocolo de Montreal. El Comité también tomó nota y apreció que Vanuatu haya adoptado medidas importantes para mantener la eliminación de su consumo de HCFC a través de la capacitación y la mejora de capacidades en sectores clave como los funcionarios encargados de hacer cumplir la ley (incluidos los funcionarios de aduanas) y la capacitación de los técnicos de mantenimiento de refrigeración y aire acondicionado. El Comité apreció los esfuerzos de Vanuatu para hacer cumplir el sistema de licencias de HCFC y la prohibición de equipos basados en HCFC, y para establecer el sistema de licencias de HFC, incluyendo el control obligatorio de equipos basados en HFC. El Comité elogió al Gobierno de Vanuatu por haber logrado una reducción del consumo de HCFC superior al 35%.
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