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执行蒙特利尔议定书
多边基金执行委员会
第九十七次会议
2025年12月1日至5日，蒙特利尔
临时议程 [footnoteRef:1] 项目6(a) [1:  UNEP/OzL.Pro/ExCom/97/1] 



根据2024年业务计划评估执行机构的绩效


背景

本文件由以下各节组成：
一.	定量绩效指标分析。本节对执行机构在2024年业务计划 [footnoteRef:2] 设定的绩效目标以及提交给第97次会议的进展和财务报告方面的绩效进行了定量评估；以及对八个绩效指标中的每一个进行趋势分析。 [2:  根据第41/93号决定通过并经第47/51号和第71/28号决定修订的绩效指标，以及第93次会议报告（UNEP/OzL.Pro/ExCom/93/105）附件X – XIII中为2024年业务计划通过的目标。] 


二.	定性绩效指标分析。本节根据国家臭氧机构官员提供的投入，对双边和执行机构的绩效进行了定性评估。

三.	秘书处的评论

四.	建议
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执行蒙特利尔议定书多边基金执行委员会的会前文件不妨碍文件印发后执行委员会可能作出的任何决定。
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一.	定量绩效指标分析 
表1列出了批准的目标、实现每个目标的进展衡量标准以及实现的目标数量。
表1. 2024年绩效指标目标和实现情况
	条目


	开发计划署
	环境规划署
	工发组织
	世界银行

	
	目标
	机构
实现
	秘书处
评估
	达到目标
	目标
	机构
实现
	秘书处
评估
	达到
目标
	目标
	机构
实现
	秘书处
评估
	达到
目标
	目标
	机构
实现
	秘书处
评估
	达到
目标

	批准的付款*
	38
	30
	30
	否
	86
	63
	76
	否
	43
	37
	36
	否
	4
	2
	2
	否

	批准的项目/活动
	33
	29
	29
	否
	119
	153
	122
	是
	56
	18
	40
	否
	4
	4
	4
	是

	支付的资金（百万美元）
	26.75
	18.74
	18.74
	否
	24.72
	24.01
	23.78
	否
	19.68
	19.79
	19.79
	是
	18.16
	26.41
	26.41
	是

	淘汰消耗臭氧层物质*
	271.84
	260.0
	260.0
	否
	198.99
	177.7
	173.8
	否
	468.43
	456.7
	456.7
	否
	5,446.1
	7,876.9
	5,443.7
	否

	活动的项目完成情况
	45
	41
	41
	否
	81
	82
	82
	是
	64
	34
	33
	否
	1
	6
	6
	是

	财务完成速度
	70% (48) 

	48
	48
	是
	12 个月
	5.8个月
	5.9个月
	是
	完成运营后的12个月
	12个月
	11.6个月
	是
	90% (7)
	57% (4)
	57% (4)
	否

	及时提交项目完成报告
	准时(1)
	准时(6)
	准时(2)
	是
	准时(5)
	准时(11)
	准时(11)
	是
	准时(4)
	准时
	准时(6)
	是
	0
	0
	0
	不适用

	及时提交进度报告
	准时
	准时
	准时
	是
	准时
	准时
	准时
	是
	准时
	准时
	准时
	是
	准时
	准时
	准时
	是

	实现的目标数
	
	
	
	3/8
	
	
	
	5/8
	
	
	
	4/8
	
	
	
	4/7


* “如果一个机构因另一个合作机构或牵头机构而无法提交付款”或“如果提交执行委员会审议的含氢氯氟烃淘汰管理计划因国家臭氧机构和机构无法控制的因素而未获批准”，该机构的目标将被降低。
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绩效加权评估
表2按秘书处的方法，按绩效指标列出2024年加权评估的结果。 
表2. 2024年执行机构绩效的加权评估
	条目
	权重
	开发计划署
	环境规划署
	工发组织
	世界银行

	
	
	实现的
目标%
	积分
	实现的
目标%
	积分
	实现的
目标%
	积分
	实现的
目标%*
	积分

	批准的付款
	10
	79
	8
	88
	9
	84
	8
	50
	5

	批准的项目/活动
	10
	88
	9
	103
	10
	71
	7
	100
	10

	支付的资金
	15
	70
	11
	96
	14
	101
	15
	145
	15

	淘汰消耗臭氧层物质

	25
	96
	24
	87
	22
	97
	24
	100
	25

	活动项目完成情况
	20
	91
	18
	101
	20
	52
	10
	600
	20

	财务完成速度
	10
	100
	10
	151
	10
	103
	10
	57
	7

	及时提交项目完成报告
	5
	200
	5
	220
	5
	150
	5
	不适用
	不适用

	及时提交进度报告
	5
	100
	5
	100
	5
	100
	5
	100
	7

	2024年评估
	100
	 
	90
	 
	95
	 
	84
	 
	89


*对于世界银行来说，“及时提交项目完成报告”的权重（5）已按比例分配给其他行政指标：“财务完成速度（3）”和“及时提交进度报告（2）”。获得的积分四舍五入到最接近的数字。

其它定量绩效指标分析
根据第41/93号决定，[footnoteRef:3] 附件一和附件二分别介绍了投资 [footnoteRef:4] 项目和非投资 [footnoteRef:5] 项目的历史分析。 [3:  请求秘书处在今后评价执行机构业绩时，根据趋势分析继续监测投资和非投资业绩指标。]  [4:  投资项目包括由项目代码指定的多年期协定。]  [5:  只有“资金支付”、“首次支付速度”和“项目完成速度”指标适用于非投资项目。] 

附件一显示，所有机构在2024年实现了淘汰消耗臭氧层物质的目标。开发计划署和世界银行实现了支付资金数额的目标，而工发组织实现了98%。开发计划署和工发组织实现了项目完成报告的目标，而世界银行没有2024年应提交的项目完成报告。2024年的交付速度和首次支付与前几年相似，反映了所有执行机构的历史表现。与2023年相比，开发计划署和工发组织的批准项目价值目标实现率有所提高，而世界银行的实现率有所下降。世界银行实现了淘汰消耗臭氧层物质的目标，开发计划署和工发组织也部分实现了这一目标。由于氟氯化碳和含氢氯氟烃的消耗臭氧潜能值存在差异，以及批准多年期协定而不是单个项目，“成本效益”和“项目筹备费用”指标对于任何趋势都没有定论。
附件二显示，开发计划署、环境规划署和工发组织实现了支付资金数额的目标；2024年所有执行机构的交付速度和首次支付速度与前几年相似。
二.	定性绩效指标分析
共处理了从93个第5条国家的国家臭氧机构收到的160 [footnoteRef:6] 份问卷，以评估双边和执行机构的定性绩效。 [6:  澳大利亚（1）、法国（1）、德国（8）、开发计划署（30）、环境规划署（73）、工发组织（44）和
世界银行（3）。] 

调查表包含三大类问题，必须对各机构在每一类中的绩效进行全面评估。
表3概述了国家臭氧机构对三大类别的总体评级。应该指出的是，一些国家臭氧机构没有提供一个或多个类别的总体评级，尽管它们确实对本文件附件三所列的个别问题做出了答复。表3显示，大多数总体评级是满意或以上；只有13个评级低于满意。
表3.按类别分列的双边和执行机构定性绩效总体评级
	类别
	高度满意
	满意
	不太满意
	不满意

	影响
	91
	37
	4
	1

	组织与合作
	73
	31
	3
	1

	技术援助/培训
	78
	41
	2
	2



除了对上述三个主要类别要求的总体评分外，调查表还包括31个单独的问题。国家臭氧机构对这些问题给出了118个低于满意的评级，详见附件三。
三.	秘书处的评论
已向各执行机构通报了2024年绩效定量评估的结果，结果显示，所有执行机构都实现了84%或更多的目标。
敬请执行委员会注意，与2023年相比，两个执行机构（开发计划署和环境规划署）2024年的绩效定量评估有所改善。
秘书处注意到，93个国家臭氧机构（2023年为88个）提交了定性评估。秘书处将从国家臭氧机构收到的评估发送给各自的双边和执行机构征求意见，重点是131个低于满意的评级（包括三大类别的13个低评级和个别问题的118个低评级）。
对于在定性评估中发现问题的所有国家（即“不太满意”或“不满意”的评级），各国家臭氧机构与双边和执行机构之间的对话已经完成；所有机构都报告说，在与各自国家臭氧机构的对话中商定了前进的道路，在大多数情况下，他们能够解决与不太满意的评级有关的问题。在这方面，敬请执行委员会赞赏地注意到，双边和执行机构努力与各自的国家臭氧机构就其服务被认为不太满意的领域进行公开和建设性的讨论，与有关国家臭氧机构的协商结果也令人满意。
四.	建议
敬请执行委员会：
注意：
根据文件UNEP/OzL.Pro/ExCom/97/9所载的2024年业务计划对执行机构的绩效进行评估；
所有执行机构对其2024年的绩效进行了定量评估，在100分制中至少为84分；
这一趋势分析表明，与2023年相比，2024年执行机构的某些指标的绩效没有改善； 
与2023年相比，两个执行机构（开发计划署和环境规划署）2024年的定量绩效有所改善；
赞赏地注意到，双边和执行机构努力与各自的国家臭氧机构就其服务被认为不太令人满意的领域进行公开和建设性的讨论，与有关国家臭氧机构的协商结果也令人满意；和
鼓励国家臭氧机构每年及时提交对协助其政府的双边和执行机构定性绩效的评估，注意到144个国家中有93个国家提交了2024年的评估，而2023年为88个。
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Annex I
INVESTMENT PROJECT PERFORMANCE BY AGENCY
(2001-2024)

	UNDP
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	ODS phased out
	99%
	92%
	100%
	79%
	91%
	85%
	100%
	86%
	100%
	N/A
	0%
	94%
	100%
	100%
	100%
	0%
	34%
	100%
	100%
	100%
	100%
	100%
	37%
	100%

	Funds disbursed
	95%
	77%
	64%
	100%
	96%
	66%
	76%
	98%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	97%
	97%
	100%
	100%
	100%
	100%
	100%
	64%
	100%

	Project completion reports
	86%
	87%
	100%
	97%
	79%
	30%
	82%
	74%
	100%
	54%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%

	Distribution among countries
	63%
	58%
	38%
	72%
	44%
	75%
	64%
	66%
	83%
	51%
	79%
	94%
	81%
	68%
	85%
	90%
	60%
	88%
	80%
	69%
	76%
	67%

	77%
	82%

	Value of projects approved
	100%
	99%
	65%
	73%
	82%
	83%
	77%
	100%
	100%
	38%
	87%
	100%
	87%
	89%
	91%
	100%
	80%
	79%
	85%
	81%
	80%
	78%
	57%
	84%

	ODS to be phased out
	96%
	77%
	44%
	89%
	70%
	100%
	100%
	100%
	100%
	100%
	92%
	61%
	100%
	29%
	83%
	84%
	84%
	96%
	97%
	93%
	95%
	98%
	82%
	96%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation 
(% of approvals)
	1.1%
	2.5%
	1.6%
	3.6%
	1.4%
	0.5%
	3.6%
	1.5%
	14.7%
	14.4%
	3.0%
	2.8%
	1.8%
	0.2%
	4.3%
	2.3%
	2.71%
	0.99%
	0.43%
	0.74%
	1.46%
	6.42%
	5.76%
	5.18%

	Cost-effectiveness ($/kg)
	8.3
	10.35
	7.1
	6.27
	8.24
	4.99
	5.76
	5.61
	6.09
	59.84
	146.85
	92.53
	56.92
	249.68
	70.89
	108.35
	184.95
	38.00
	45.41
	51.97
	51.22
	59.08
	14.18
	16.46

	Speed of first disbursement (months)
	12.84
	12.8
	12.8
	12.91
	12.9
	13.0
	13.1
	13.2
	13.4
	13.6 
	13.7
	13.7
	13.7
	13.7
	13.7
	13.6
	13.5
	13.6
	13.6
	13.6
	13.6
	13.6
	13.7
	13.7

	Speed of completion (months)
	33.6
	32.7
	32.4
	32.41
	32.9
	33.6
	33.9
	33.8
	33.9
	34.2 
	34.6
	34.9 
	34.9
	35.2
	35.1
	34.4
	35.6
	35.7 
	35.8
	35.7
	35.8
	35.9
	35.8
	35.9

	Net emissions due to delays (ODP tonnes)
	11,727
	9,023
	6,466
	3,607
	4,538
	6,619
	2,674
	1,312
	92
	113
	101
	520
	538
	248
	238
	-881
	416.3
	499.6
	426.1
	395.9
	268.4
	335.3
	480.9
	651.7

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNIDO
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	ODS phased out
	100%
	100%
	88%
	100%
	99%
	100%
	100%
	84%
	86%
	100%
	100%
	0%
	27%
	42%
	100%
	100%
	100%
	50%
	45%
	55%
	87%
	100%
	100%
	100%

	Funds disbursed
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	91%
	100%
	94%
	100%
	100%
	100%
	97%
	100%
	100%
	100%
	100%
	69%
	86%
	87%
	100%
	100%
	98%

	Project completion reports
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	84%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%

	Distribution among countries
	89%
	73%
	78%
	67%
	79%
	69%
	75%
	82%
	61%
	81%
	83%
	100%
	72%
	67%
	100%
	76%
	54%
	64%
	75%
	74%
	52%
	62%
	66%
	75%

	Value of projects approved
	99%
	97%
	68%
	82%
	100%
	100%
	92%
	100%
	59%
	78%
	100%
	79%
	88%
	64%
	93%
	71%
	73%
	57%
	73%
	85%
	52%
	90%
	77%
	100%

	ODS to be phased out
	100%
	100%
	37%
	89%
	100%
	47%
	91%
	100%
	100%
	100%
	36%
	81%
	21%
	36%
	100%
	82%
	61%
	71%
	82%
	86%
	84%
	70%
	96%
	97%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	Cost of project preparation (% of approvals)
	2.7%
	3.3%
	3.6%
	2%
	0.9%
	1.8%
	2.1%
	1.3%
	11.9%
	5.7%
	2.7%
	3.9%
	1.1%
	1.3%
	1.8%
	3.6%
	2.6%
	0.4%
	2.4%
	2.8%
	3.2%
	8.71%
	8.82%
	4.50%

	Cost-effectiveness ($/kg)
	5.67
	7.28
	9.79
	3.58
	3.10
	7.13
	6.51
	9.34
	3.26
	22.58
	187.59
	35.34
	186.02
	79.01
	56.02
	65.50
	53.61
	22.83
	119.38
	20.96
	27.80
	17.48
	11.09
	11.19

	Speed of first disbursement (months)
	9.29
	9.16
	9.2
	9.06
	8.97
	9.0
	8.9
	8.7
	8.7
	8.7 
	8.4
	8.6
	8.5
	8.6
	9.0
	8.9
	9.0
	9.2
	9.2
	9.2
	9.1
	9.3
	9.3
	9.2

	Speed of completion (months)
	29.85
	30.89
	31.7
	32.35
	32.98
	33.2
	33.5
	33.4
	33.7
	34.1 
	35.0
	35.9
	36.8
	38.3
	39.5
	40.2
	40.9
	41.1
	41.7
	42.4
	42.7
	42.4
	42.1
	42.5

	Net emissions due to delays (ODP tonnes)
	5,727
	5,960
	3,503
	13,035
	1,481
	3,864
	4,470
	3,431
	6,970
	8,918
	14,583
	17,144
	8,805
	9,939
	13,389
	6,906
	8,054.8
	7,971.7
	3,372.1
	8,137.3
	9,458.7
	8,112.8
	7,797.6
	870.5

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	World Bank
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	ODS phased out
	100%
	100%
	84%
	100%
	69%
	31%
	84%
	47%
	100%
	100%
	100%
	20%
	98%
	100%
	100%
	100%
	100%
	51%
	100%
	100%
	100%
	N/A
	66%
	100%

	Funds disbursed
	74%
	100%
	100%
	73%
	100%
	100%
	100%
	100%
	73%
	64%
	43%
	15%
	100%
	100%
	100%
	78%
	96%
	62%
	80%
	70%
	63%
	99%
	43%
	100%

	Project completion reports
	74%
	100%
	84%
	84%
	100%
	84%
	74%
	69%
	25%
	20%
	85%
	10%
	100%
	24%
	24%
	8%
	33%
	11%
	45%
	26%
	77%
	90%
	100%
	N/A

	Distribution among countries
	67%
	79%
	65%
	71%
	93%
	79%
	92%
	77%
	67%
	50%
	57%
	100%
	67%
	50%
	33%
	100%
	50%
	60%
	100%
	33%
	60%
	75%
	100%
	40%

	Value of projects approved
	92%
	100%
	82%
	94%
	83%
	87%
	83%
	93%
	98%
	3%
	93%
	29%
	93%
	72%
	100%
	39%
	29%
	95%
	46%
	26%
	77%
	80%
	100%
	90%

	ODS to be phased out
	72%
	91%
	65%
	59%
	100%
	66%
	93%
	35%
	100%
	89%
	11%
	7%
	25%
	11%
	100%
	50%
	74%
	69%
	100%
	84%
	95%
	99%
	100%
	100%

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Cost of project preparation (% of approvals)
	1.3%
	0.4%
	0.6%
	0.2%
	0.4%
	0.4%
	0.02%
	0.6%
	2.2%
	74.8%
	1.5%
	5.6%
	0.2%
	0.6%
	0.4%
	4.0%
	18.64%
	1.04%
	0.0%
	0.0%
	0.0%
	0.61%
	2.92%
	0.81%

	Cost-effectiveness ($/kg)
	3.85
	4.57
	6.12
	3.74
	1.04
	3.33
	3.29
	9.36
	1.43
	1.12
	545.23
	69.01
	118.26
	214.04
	19.84
	48.54
	52.66
	618.83
	177.65
	2.56
	4.55
	3.85
	18.29
	31.96

	Speed of first disbursement (months)
	25.33
	26.28
	26
	26.02
	25.7
	25.3
	25.0
	24.8
	24.8
	24.6 
	24.6
	24.7
	24.6
	24.6
	24.6
	24.6 
	24.5
	24.4 
	24.5
	24.4
	24.4
	24.4
	24.3

	24.2

	Speed of completion (months)
	40.09
	41.35
	41
	40.88
	40.7
	40.3
	40.2
	39.8
	39.8
	40.2 
	40.2
	40.2
	40.3
	40.8
	40.8
	40.8
	41.0
	40.1 
	41.2
	41.2
	41.2
	41.3
	41.2
	41.2

	Net emissions due to delays (ODP tonnes)
	21,539
	22,324
	18,021
	8,338
	4,843
	5,674
	2,316
	1,303
	182
	1,680
	801
	901
	901
	1,002
	275
	455
	249.9
	788.4
	812.98
	5.5
	74.8
	149.5
	146.9

	65.5
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NON-INVESTMENT PROJECT PERFORMANCE BY AGENCY
(2001-2024)

	UNDP
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	Funds disbursed
	93%
	61%
	100%
	100%
	100%
	92%
	100%
	100%
	100%
	100%
	100%
	84%
	88%
	100%
	47%
	82%
	100%
	100%
	100%
	100%
	100%
	100%
	100%
	100%

	Speed until first disbursement (months)
	12
	11.4
	11
	11.44
	11.5
	11.8
	11.7
	11.7
	11.8
	12.2
	11.8
	11.9
	11.9
	11.8
	12.0
	11.9
	11.8
	11.7
	11.8
	11.7
	11.7
	11.7
	11.6
	11.5

	Speed until project completion (months)
	36
	34.7
	35
	35.36
	35.4
	36.6
	37.3
	37.1
	37.3
	37.7
	37.1
	37.4
	37.2
	36.7
	36.3
	36.0
	36.8
	36.2
	36.1
	36.0
	36.0
	35.7
	35.7
	35.6

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNEP
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	Funds disbursed
	93%
	93%
	99%
	54%
	54%
	51%
	49%
	64%
	69%
	60%
	63%
	55%
	47%
	61%
	44%
	91%
	100%
	81%
	85%
	75%
	85%
	85%
	82%
	100%

	Speed until first disbursement (months)
	6.87
	7.3
	7.6
	8.49
	8.4
	8.4
	8.7
	9.0
	9.0
	9.5 
	9.6
	9.8
	9.8
	9.9
	10.1
	10.5
	10.5
	10.9
	10.9
	11.1
	11.6
	11.9
	12.2
	12.5

	Speed until project completion (months)
	29.66
	30.4
	31
	31.8
	32.4
	32.9
	33.2
	33.6
	32.9
	33.9 
	34.3
	34.4
	34.7
	35.3
	35.3
	36.1
	36.7
	36.7
	36.8
	36.8
	36.7
	36.6
	36.9
	37.4

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	UNIDO
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	Funds disbursed
	48%
	89%
	100%
	100%
	90%
	80%
	89%
	69%
	100%
	84%
	95%
	100%
	62%
	82%
	82%
	75%
	100%
	100%
	95%
	100%
	100%
	100%
	100%
	100%

	Speed until first disbursement (months)
	9.15
	9.85
	9.4
	9.34
	8.9
	9.8
	10.2
	10.6
	10.4
	10.4 
	10.3
	10.3
	10.2
	10.1
	10.0
	10.1
	10.4
	10.3
	10.0
	9.8
	9.8
	9.7
	9.6
	9.5

	Speed until project completion (months)
	33.66
	33.84
	33.7
	33.89
	31.9
	33.1
	33.0
	32.9
	32.0
	31.9 
	31.4
	32.8
	32.8
	33.7
	32.7
	33.4
	33.5
	32.7
	33.0
	34.1
	34.1
	33.9
	34.3
	34.4

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	World Bank
	2001
	2002
	2003
	2004
	2005
	2006
	2007
	2008
	2009
	2010
	2011
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	2019
	2020
	2021
	2022
	2023
	2024

	Funds disbursed
	12%
	38%
	100%
	79%
	100%
	57%
	59%
	59%
	19%
	47%
	75%
	59%
	49%
	42%
	100%
	88%
	100%
	100%
	78%
	33%
	34%
	35%
	100%
	53%

	Speed until first disbursement (months)
	11.95
	12.05
	13.7
	14.58
	13.6
	14.6
	14.3
	14.4
	14.4
	14.9 
	14.6
	15.1
	14.7
	14.0
	14.1
	14.8 
	16.8
	16.8 
	16.6
	16.9
	17.0
	17.0
	17.0
	17.0

	Speed until project completion (months)
	29.24
	28.85
	30
	30.39
	31
	31.5
	31.1
	30.7
	30.7
	30.3 
	30.1
	30.3
	30.2
	30.0
	29.8
	29.8
	29.2
	29.3 
	29.3
	29.3
	29.6
	29.6
	29.6
	28.9
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Annex III
QUALITATIVE ASSESSMENT OF THE IMPLEMENTING AGENCIES BY THE NATIONAL OZONE UNITS FOR 2024

	Category
	Sub-category
	Questions
	Values
	Australia
	France
	Germany
	UNDP
	UNEP
	UNIDO
	World Bank
	Total

	IMPACT
	General
	Has cooperation with the implementing agency substantially contributed and added value to your work or organization in managing compliance in your country?
	Highly satisfactory
	1
	1
	7
	16
	55
	28
	1
	109

	
	
	
	Satisfactory
	 
	 
	1
	10
	17
	12
	2
	42

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	2
	 
	3

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	IMPACT (Overall Rating)
	Highly satisfactory
	1
	1
	6
	13
	46
	23
	1
	91

	
	
	
	Satisfactory
	 
	 
	2
	11
	13
	9
	2
	37

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	3
	 
	4

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	In the design and implementation of the project, has the implementing agency been striving to achieve sustainable results?
	Highly satisfactory
	1
	1
	8
	15
	55
	29
	1
	110

	
	
	
	Satisfactory
	 
	 
	 
	12
	16
	11
	2
	41

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	2
	 
	2

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	ORGANIZATION 
AND COOPERATION
	General
	Did cooperation with the staff of the implementing agency take place in an atmosphere of mutual understanding?
	Highly satisfactory
	1
	1
	7
	20
	65
	32
	2
	128

	
	
	
	Satisfactory
	 
	 
	1
	9
	8
	7
	1
	26

	
	
	
	Less satisfactory
	 
	 
	 
	2
	 
	5
	 
	7

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	Did the implementing agency clearly explain its work plan and division of tasks?
	Highly satisfactory
	1
	1
	5
	14
	58
	24
	2
	105

	
	
	
	Satisfactory
	 
	 
	3
	13
	15
	18
	1
	50

	
	
	
	Less satisfactory
	 
	 
	 
	3
	 
	2
	 
	5

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	Did the implementing agency sufficiently control and monitor the delivery of consultant services?
	Highly satisfactory
	1
	1
	4
	16
	50
	29
	1
	102

	
	
	
	Satisfactory
	 
	 
	4
	11
	20
	14
	2
	51

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Did the responsible staff of the implementing agency communicate sufficiently and help to avoid misunderstanding?
	Highly satisfactory
	1
	1
	6
	17
	63
	29
	2
	119

	
	
	
	Satisfactory
	 
	 
	2
	9
	10
	9
	1
	31

	
	
	
	Less satisfactory
	 
	 
	 
	4
	 
	6
	 
	10

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	Has the use of funds been directed effectively to reach the targets and was it agreed between the national ozone unit and the implementing agency?
	Highly satisfactory
	1
	1
	6
	18
	63
	30
	2
	121

	
	
	
	Satisfactory
	 
	 
	2
	8
	9
	10
	1
	30

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	2
	 
	3

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	If there was a lead agency for a multi-agency project, did it coordinate the activities of the other implementing agencies satisfactorily?
	Highly satisfactory
	1
	 
	 
	11
	31
	16
	 
	59

	
	
	
	Satisfactory
	 
	1
	2
	5
	15
	11
	1
	35

	
	
	
	Less satisfactory
	 
	 
	 
	2
	1
	1
	 
	4

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	ORGANIZATION AND COOPERATION (Overall Rating)
	Highly satisfactory
	1
	1
	5
	14
	36
	15
	1
	73

	
	
	
	Satisfactory
	 
	 
	2
	11
	8
	9
	1
	31

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	3
	 
	3

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Was active involvement of the national ozone unit ensured in project Development?
	Highly satisfactory
	1
	1
	8
	18
	54
	33
	2
	117

	
	
	
	Satisfactory
	 
	 
	 
	10
	16
	11
	1
	38

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Was active involvement of the national ozone unit ensured in project Identification?
	Highly satisfactory
	1
	1
	8
	19
	56
	31
	2
	118

	
	
	
	Satisfactory
	 
	 
	 
	9
	14
	13
	1
	37

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Was active involvement of the national ozone unit ensured in project Implementation?
	Highly satisfactory
	1
	1
	8
	17
	56
	32
	2
	117

	
	
	
	Satisfactory
	 
	 
	 
	9
	13
	11
	1
	34

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Were the required services of the implementing agency delivered in time?
	Highly satisfactory
	1
	1
	3
	9
	56
	23
	1
	94

	
	
	
	Satisfactory
	 
	 
	5
	17
	16
	16
	2
	56

	
	
	
	Less satisfactory
	 
	 
	 
	3
	1
	5
	 
	9

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	TECHNICAL ASSISTANCE/TRAINING
	General
	Did project partners receive sufficient technical advice and/or assistance in their decision-making on technology?
	Highly satisfactory
	1
	1
	6
	13
	35
	21
	2
	79

	
	
	
	Satisfactory
	 
	 
	1
	11
	26
	17
	1
	56

	
	
	
	Less satisfactory
	 
	 
	 
	1
	1
	3
	 
	5

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Did the agency give sufficient consideration to training aspects within funding limits?
	Highly satisfactory
	1
	1
	7
	14
	51
	30
	1
	105

	
	
	
	Satisfactory
	 
	 
	1
	11
	17
	11
	2
	42

	
	
	
	Less satisfactory
	 
	 
	 
	1
	1
	3
	 
	5

	
	
	
	Unsatisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	Do you feel that you have received sufficient support in building capacities for the national implementation of the project (within the funding limitations)?
	Highly satisfactory
	1
	1
	6
	14
	47
	24
	1
	94

	
	
	
	Satisfactory
	 
	 
	2
	12
	22
	14
	2
	52

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	3
	 
	3

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Has the acquisition of services and equipment been successfully administered, contracted and its delivery monitored?
	Highly satisfactory
	1
	1
	7
	11
	29
	21
	1
	71

	
	
	
	Satisfactory
	 
	 
	1
	13
	26
	16
	2
	58

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	In case of need, was trouble‑shooting by the agency quick and in direct response to your needs?
	Highly satisfactory
	1
	1
	7
	13
	46
	28
	1
	97

	
	
	
	Satisfactory
	 
	 
	1
	12
	19
	7
	2
	41

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	2
	 
	3

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	2
	 
	3

	
	
	TECHNICAL ASSISTANCE/TRAINING (Overall Rating)
	Highly satisfactory
	1
	1
	6
	13
	37
	19
	1
	78

	
	
	
	Satisfactory
	 
	 
	1
	11
	15
	12
	2
	41

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	2
	 
	2

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Was the selection and competence of consultants provided by the agency satisfactory?
	Highly satisfactory
	1
	1
	5
	15
	45
	25
	2
	94

	
	
	
	Satisfactory
	 
	 
	2
	9
	20
	18
	1
	50

	
	
	
	Less satisfactory
	 
	 
	1
	 
	 
	 
	 
	1

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Were project partners and stakeholders encouraged by the implementing agency to participate positively in decision-making and design of activities?
	Highly satisfactory
	1
	1
	6
	16
	50
	24
	2
	100

	
	
	
	Satisfactory
	 
	 
	2
	9
	18
	16
	1
	46

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	2
	 
	2

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	Investment projects
	Has the agency been effective and met the expectations of stakeholders in providing technical advice, training and commissioning?
	Highly satisfactory
	1
	 
	3
	11
	35
	24
	1
	75

	
	
	
	Satisfactory
	 
	1
	4
	11
	15
	9
	 
	40

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Has the agency been responsive in addressing any technical difficulties that may have been encountered subsequent to the provision of non‑ODS technology?
	Highly satisfactory
	1
	1
	4
	10
	25
	19
	1
	61

	
	
	
	Satisfactory
	 
	 
	3
	12
	17
	10
	 
	42

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	1
	 
	1

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	National phase-out plans
	Has support for the distribution of equipment been adequate?
	Highly satisfactory
	1
	1
	6
	12
	33
	20
	1
	74

	
	
	
	Satisfactory
	 
	 
	2
	10
	13
	14
	1
	40

	
	
	
	Less satisfactory
	 
	 
	 
	 
	1
	 
	 
	1

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Has support to identify policy issues related to implementation been adequate?
	Highly satisfactory
	1
	1
	4
	9
	45
	24
	1
	85

	
	
	
	Satisfactory
	 
	 
	2
	9
	22
	12
	2
	47

	
	
	
	Less satisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Has technical advice on equipment specifications been adequate?
	Highly satisfactory
	1
	1
	7
	10
	31
	25
	 
	75

	
	
	
	Satisfactory
	 
	 
	1
	11
	17
	12
	2
	43

	
	
	
	Less satisfactory
	 
	 
	 
	1
	1
	 
	 
	2

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Has the technical advice or training that was provided been effective?
	Highly satisfactory
	1
	 
	5
	12
	50
	26
	1
	95

	
	
	
	Satisfactory
	 
	1
	3
	9
	14
	11
	2
	40

	
	
	
	Less satisfactory
	 
	 
	 
	1
	1
	2
	 
	4

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Were proposed implementation strategies adequate?
	Highly satisfactory
	1
	 
	5
	15
	51
	25
	2
	99

	
	
	
	Satisfactory
	 
	1
	3
	8
	13
	12
	1
	38

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	2
	 
	2

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	Regulatory assistance projects
	Were the regulations that were proposed by the agency Adapted to local circumstances?
	Highly satisfactory
	1
	 
	2
	10
	40
	20
	 
	73

	
	
	
	Satisfactory
	 
	1
	2
	4
	22
	11
	2
	42

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Were the regulations that were proposed by the agency Applicable?
	Highly satisfactory
	1
	1
	3
	10
	47
	15
	 
	77

	
	
	
	Satisfactory
	 
	 
	1
	4
	15
	16
	2
	38

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	
	Were the regulations that were proposed by the agency Enforceable?
	Highly satisfactory
	1
	1
	3
	9
	38
	17
	 
	69

	
	
	
	Satisfactory
	 
	 
	1
	5
	23
	14
	2
	45

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	 
	 
	 

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	 
	 
	1

	
	Training projects
	Was the quality of the training provided satisfactory?
	Highly satisfactory
	1
	1
	5
	14
	48
	27
	2
	98

	
	
	
	Satisfactory
	 
	 
	2
	3
	14
	8
	 
	27

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	1
	 
	1

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2

	
	
	Was the training designed so that those trained would be likely to use the skills taught?
	Highly satisfactory
	1
	1
	5
	14
	42
	25
	1
	89

	
	
	
	Satisfactory
	 
	 
	2
	3
	20
	10
	1
	36

	
	
	
	Less satisfactory
	 
	 
	 
	 
	 
	1
	 
	1

	
	
	
	Unsatisfactory
	 
	 
	 
	1
	 
	1
	 
	2
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