| NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/23 6 de diciembre de 2023 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
 PARA LA APLICACIÓN DEL
 PROTOCOLO DE MONTREAL
Nonagésima tercera reunión

Montreal, 15 – 19 de diciembre de 2023
Cuestión 8 (a) del orden del día provisional

INFORMACIÓN ACTUALIZADA SOBRE LA SITUACIÓN DE LA EJECUCIÓN DEL PLAN

ADMINISTRATIVO REFUNDIDO DEL FONDO MULTILATERAL PARA 2023-2025

- Introducción

# El presente documento consta de las secciones siguientes:

## I.	Actualización de la situación de ejecución del plan administrativo para 2023-2025

## II.	Asignación de recursos para el trienio 2021-2023

III.	Recomendación

## I.	Actualización de la situación de ejecución del plan administrativo para 2023-2025

# En su 91ª reunión, el Comité Ejecutivo refrendó el plan administrativo refundido del Fondo Multilateral para 2023-2025. En respuesta a la decisión 91/31, la Secretaría ajustó dicho plan, como se indica en el cuadro 1.

Cuadro 1. Asignación de recursos del plan administrativo del Fondo Multilateral para 2023-2025, refundido y ajustado ($EUA)*

| Descripción | 2023 | 2024 | 2025 | Total |
| --- | --- | --- | --- | --- |
| Actividades relativas a los HCFC |  |  |  |  |
| Planes de gestión de eliminación de los HCFC (PGEH) aprobados | 60 280 861 | 56 111 450 | 43 084 350 | 159 476 661 |
| Preparación de proyectos de PGEH – etapa II | 200 480 | 77 600 | 0 | 278 080 |
| Etapa II de los PGEH | 2 937 082 | 5 199 804 | 3 462 199 | 11 599 085 |
| Etapa II de los PGEH – inversión | 0 | 248 532 | 0 | 248 532 |
| Preparación de proyectos para los PGEH – etapa III | 290 100 | 92 750 | 0 | 382 850 |
| Etapa III de los PGEH | 14 794 713 | 10 344 520 | 20 526 731 | 45 665 964 |
| Preparación de proyectos para los PGEH – etapa IV | 90 000 | 0 | 0 | 90 000 |
| Etapa IV de los PGEH | 0 | 0 | 2 093 000 | 2 093 000 |
| PGEH – eficiencia energética | 3 258 494 | 2 672 980 | 3 379 420 | 9 310 894 |
| Verificación de los PGEH ** | 588 600 | 588 600 | 588 600 | 1 765 800 |
| Subtotal de actividades relativas a los HCFC | 82 440 330 | 75 336 236 | 73 134 299 | 230 910 865 |
| Actividades relativas a los HFC |  |  |  |  |
| Actividades de facilitación para la reducción de los HFC | 53 500 | 160 500 | 0 | 214 000 |
| Preparación de proyectos de los planes de aplicación de la Enmienda de Kigali para los HFC (KIP) | 3 945 431 | 2 567 011 | 144 560 | 6 657 002 |
| KIP | 27 299 967 | 21 437 607 | 245 413 | 48 982 987 |
| Preparación de proyectos de los KIP – inversión | 129 000 | 0 | 0 | 129 000 |
| KIP – inversión | 321 000 | 8 963 616 | 0 | 9 284 616 |
| Preparación de proyectos de control de emisiones del HFC-23 | 43 000 | 0 | 0 | 43 000 |
| Control de emisiones del HFC-23 | 0 | 8 000 000 | 0 | 8 000 000 |
| HFC – asistencia técnica | 0 | 678 000 | 0 | 678 000 |
| Subtotal de actividades relativas a los HFC | 31 791 898 | 41 806 734 | 389 973 | 73 988 605 |
| Proyecto piloto de eficiencia energética |  |  |  |  |
| Proyecto piloto de eficiencia energética | 20 000 000 | 0 | 0 | 20 000 000 |
| Subtotal del proyecto piloto de eficiencia energética | 20 000 000 | 0 | 0 | 20 000 000 |
| Actividades corrientes |  |  |  |  |
| Fortalecimiento institucional | 27 860 444 | 16 639 896 | 0 | 44 500 341 |
| Programa de Asistencia al Cumplimiento (PAC) | 11 445 002 | 11 788 350 | 12 142 003 | 35 375 355 |
| Unidad central | 5 969 740 | 6 011 529 | 6 053 610 | 18 034 878 |
| Secretaría/Comité Ejecutivo/supervisión y evaluación (excepto la contraparte canadiense) | 7 237 326 | 7 202 023 | 6 816 624 | 21 255 973 |
| Tesorero | 500 000 | 500 000 | 500 000 | 1 500 000 |
| Subtotal de actividades corrientes | 53 012 512 | 42 141 798 | 25 512 237 | 120 666 547 |
| Total general | 187 244 740 | 159 284 767 | 99 036 509 | 445 566 017 |
| Australia | 0 | 0 | 152 497 | 152 497 |
| Austria | 783 667 | 0 | 0 | 783 667 |
| Francia | 671 075 | 0 | 0 | 671 075 |
| Alemania | 1 349 869 | 3 705 721 | 1 028 250 | 6 083 840 |
| Japón | 67 800 | 0 | 0 | 67 800 |
| PNUD | 62 425 117 | 54 216 500 | 29 064 016 | 145 705 634 |
| PNUMA | 40 325 066 | 36 674 895 | 22 071 085 | 99 071 046 |
| ONUDI | 38 767 526 | 29 078 890 | 29 553 746 | 97 400 162 |
| Banco Mundial | 14 528 694 | 27 318 138 | 9 261 691 | 51 108 523 |
| Verificación de los PGEH ** | 588 600 | 588 600 | 588 600 | 1 765 800 |
| Proyecto piloto de eficiencia energética | 20 000 000 | 0 | 0 | 20 000 000 |
| Secretaría/Comité Ejecutivo/supervisión y evaluación (excepto la contraparte canadiense) | 7 237 326 | 7 202 023 | 6 816 624 | 21 255 973 |
| Tesorero | 500 000 | 500 000 | 500 000 | 1 500 000 |

* Incluidos los gastos de apoyo a los organismos, según proceda.

** El Comité Ejecutivo aprueba anualmente la financiación de la preparación de los informes de verificación de los PGEH para los países de bajo consumo.

I.1 Estado de ejecución del plan administrativo para 2023

3.	Los valores totales del plan administrativo para 2023 ascienden a 187 244 740 $EUA. De esta cantidad, se aprobaron 29 253 988 $EUA en la 92ª reunión. Además, en la 93ª reunión se considerarán actividades por valor de 108 304 705 $EUA; si se aprueba la financiación de todas las propuestas de proyectos presentadas según lo solicitado, quedaría disponible un saldo de 49 686 047 $EUA del plan administrativo 2023, como se indica en el cuadro 2.

Cuadro 2. Plan administrativo refundido de 2023, aprobaciones en la 92ª reunión, proyecto recomendado a la 93ª reunión, y saldo ($EUA)*

| Partidas presupuestarias | Valor total en el plan administrativo | Aprobaciones en la 92ª reunión | Actividades recomendadas a la 93ª reunión | Saldo (positivo)/negativo |
| --- | --- | --- | --- | --- |
| Organismos bilaterales | 2 872 411 | 687 988 | 1 657 265 | 527 158 |
| PNUD | 62 425 117 | 10 211 836 | 28 591 500 | 23 621 781 |
| PNUMA | 40 325 066 | 6 644 731 | 22 767 524 | 10 912 811 |
| ONUDI | 38 767 526 | 8 419 645 | 24 134 585 | 6 213 296 |
| Banco Mundial | 14 528 694 | 2 681 989 | 15 997 224 | (4 150 519) |
| Verificación de los PGEH | 588 600 | 573 900 | 0 | 14 700 |
| Proyecto piloto de eficiencia energética | 20 000 000 | 33 900 | 7 419 281 | 12 546 819 |
| Subtotal (organismos) | 179 507 414 | 29 253 988 | 100 567 379 | 49 686 047 |
| Secretaría/Comité Ejecutivo/supervisión y evaluación (excepto la contraparte canadiense) | 7 237 326 | 0 | 7 237 326 | 0 |
| Tesorero | 500 000 | 0 | 500 000 | 0 |
| Subtotal (costos corrientes) | 7 737 326 | 0 | 7 737 326 | 0 |
| Total | 187 244 740 | 29 253 988 | 108 304 705 | 49 686 047 |

* Incluidos los costos de la unidad central.

# El valor de las propuestas de proyectos recomendadas a la 93ª reunión, de 100 567 379 $EUA, es superior en 16 578 316 $EUA a su valor en el plan administrativo de 2023, e incluye 12 521 905 $EUA relacionados con propuestas de proyecto no incluidas en el plan administrativo de 2023.

# El valor de las actividades relacionadas con los HFC recomendadas a la 93ª reunión ascienda a 23 789 140 $EUA, de los cuales 3 182 574 $EUA corresponden a propuestas de proyectos no incluidos en el plan administrativo para 2023. En el Anexo I del presente documento se enumeran los proyectos relacionados con los HFC presentados por los organismos bilaterales y de ejecución a la 93ª reunión.

6.	El valor de los proyectos recomendados con arreglo a la ventana de financiación para proyectos piloto de eficiencia energética de conformidad con la decisión 91/65 asciende a 7 419 281 $EUA. Teniendo en cuenta las aprobaciones en la 92ª reunión de 33 900 $EUA y los valores recomendados a la 93ª reunión, la financiación restante disponible en esta ventana de financiación es de 12 546 819 $EUA. En el Anexo II del presente documento se enumeran los proyectos piloto presentados por los organismos bilaterales y de ejecución a la 93ª reunión de conformidad con la decisión 91/65.

7.	El valor de los proyectos recomendados con arreglo a la ventana de financiación para la preparación de inventarios nacionales de bancos de residuos de sustancias controladas de conformidad con la decisión 91/66 asciende a 3 222 500 $EUA que no están incluidos en el plan administrativo para 2023. En el Anexo III del presente documento se enumeran las actividades de preparación de proyectos presentadas por los organismos bilaterales y de ejecución a la 93ª reunión de conformidad con la decisión 91/66.

8.	Además, en relación con la decisión 91/66, el apartado c) iii) exige que los proyectos correspondientes a la ventana de financiación mencionada se sometan a la consideración del Comité Ejecutivo a partir de la 93ª reunión hasta la 97ª reunión inclusive, en el entendimiento de que se incluirán en los planes administrativos pertinentes antes de su aprobación. Durante las conversaciones mantenidas con los organismos en las reuniones de las redes, estos informaron a la Secretaría de que los países del artículo 5 necesitaban más tiempo para comprender los distintos aspectos de la gestión de sustancias controladas no deseadas y necesitaban más información de los organismos durante las reuniones de las redes antes de acordar la inclusión de estas actividades en sus respectivos planes administrativos; esto llevó más tiempo del previsto. Basándose en las aportaciones adicionales y las consultas realizadas durante los últimos meses, incluso durante la 35ª Reunión de las Partes celebrada en octubre de 2023, los países han expresado su interés en presentar proyectos con arreglo a dicha ventana de financiación. A fin de facilitar la presentación de proyectos relacionados con la preparación de inventarios de bancos de sustancias controladas usadas o no deseadas, el Comité Ejecutivo, con carácter excepcional, tal vez desee permitir que los organismos bilaterales y de ejecución presenten actividades de preparación de proyectos en el marco de la ventana de financiación establecida en virtud de la decisión 91/66 durante el año 2024, incluso en los casos en que dichas actividades no estén comprendidas en los planes administrativos.

9.	Las propuestas de proyectos por un valor de 54 097 185 $EUA que estaban incluidas en el plan administrativo para 2023 no se presentaron a la 93ª reunión. Estas propuestas se han incluido en el plan administrativo refundido del Fondo Multilateral para 2024-2026.

# I.2	Compromisos futuros

# El monto total de los compromisos futuros existentes para los acuerdos plurianuales correspondientes al período de 2023 a 2031 es de 314,16 millones $EUA, suponiendo que las solicitudes de financiación de dichos acuerdos, presentadas en la 93ª reunión, se aprueben en principio, como se indica en el cuadro 3.

Cuadro 3. Compromisos futuros (2023–2031) (miles de $EUA)

| Descripción | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Aprobados en principio | 68 086 | 53 334 | 51 015 | 42 781 | 10 187 | 5 852 | 4 733 | 8 163 | 57 | 244 207 |
| Presentados a la 93ª reunión | 27 918 | 0 | 10 122 | 14 050 | 10 623 | 24 | 5 528 | 1 683 | 0 | 69 949 |
| Total | 96 005 | 53 334 | 61 137 | 56 831 | 20 811 | 5 876 | 10 261 | 9 846 | 57 | 314 156 |

# II.	Asignación de recursos para el trienio 2021–2023

# Al 8 de noviembre de 2023, el saldo disponible en el Fondo Multilateral ascendía a 277 322 098 $EUA, con una contribución pendiente de 52 864 962 $EUA para el trienio 2021-2023, de la que no se espera recaudar 23 281 488 $EUA.  Después del 8 de noviembre de 2023, los intereses potenciales a devengar y las posibles pérdidas debidas al mecanismo de tipos de cambio fijos (FERM) se estiman en 5 849 812 $EUA y 753 989 $EUA, respectivamente. Además, los fondos devueltos para proyectos finalizados y los intereses devueltos hasta la 93ª reunión ascienden a 4 669 316 $EUA y 505 720 $EUA, respectivamente. Por consiguiente, la financiación total que podría estar disponible para nuevas asignaciones en la 93ª reunión asciende a 317 176 431 $EUA.

# Dado el valor de la financiación recomendada para los proyectos presentados a la 93ª reunión de 100 567 379 $EUA y el presupuesto de la Secretaría de 7 737 326 $EUA, el recurso disponible al final del trienio 2021-2023 sería de 208 871 726 $EUA. Además, la Quinta Reunión Extraordinaria de las Partes también tomó nota de que 246 millones $EUA en fondos restantes que se debían al Fondo Multilateral durante el trienio 2018-2020 se utilizarán después de 2023 para apoyar la aplicación del Protocolo de Montreal (decisión Ex.V/1). Por lo tanto, el total de recursos disponibles para el trienio 2024-2026 es de 454 871 726 $EUA, como se indica en el cuadro 4.

Cuadro 4. Asignación de recursos para el trienio de 2021–2023 ($EUA)

| Descripción |  | Monto ($EUA) |
| --- | --- | --- |
| Financiación disponible |  |  |
| Saldo disponible al 8 de noviembre de 2023 | (a) | 277 322 098 |
| Contribuciones pendientes para el período de 2021 a 2023 | (b) | 52 864 962 |
| Contribuciones pendientes no previstas | (c) | (23 281 488) |
| Posibles intereses devengados después del 8 de noviembre de 2023 | (d) | 5 849 812 |
| Posibles pérdidas debidas al FERM después del 8 de noviembre de 2023 | (e) | (753 989) |
| Devolución de fondos en la 93ª reunión | (f) | 4 669 316 |
| Interés devuelto a la 93ª reunión | (g) | 505 720 |
| Financiación total disponible | (h = a+b+c+d+e+f+g) | 317 176 431 |
| Gastos |  |  |
| Proyectos recomendados a la 93ª reunión | (i) | 100 567 379 |
| Secretaría/Comité Ejecutivo/Supervisión/Tesorero | (j) | 7 737 326 |
| Total de gastos | (k = i+j) | 108 304 705 |
| Recursos disponibles a finales de 2023 | (l = h-k) | 208 871 726 |
| Monto remanente para el trienio 2018–2020 que se utilizará después de 2023 | (m) | 246 000 000 |
| Total de recursos disponibles para el trienio 2024-2026 | (n= l+m) | 454 871 726 |

# III.	Recomendación

# El Comité Ejecutivo podría estimar oportuno:

## Tomar nota de:

### La actualización del estado de ejecución del plan administrativo refundido del Fondo Multilateral para 2023-2025, que figura en el documento UNEP/OzL.Pro/ExCom/93/23;

### Que el valor total de las actividades solicitadas a la 93ª reunión asciende a 100 567 379 $EUA (incluidos 23 789 140 $EUA para actividades relacionadas con los HFC, 7 419 281 $EUA para proyectos piloto de eficiencia energética y 3 222 500 $EUA para la preparación de inventarios nacionales de bancos de residuos de sustancias controladas), de los cuales 12 521 905 $EUA están asociados a propuestas de proyectos no incluidos en el plan administrativo para 2023; y

## Permitir, con carácter excepcional, que los organismos bilaterales y de ejecución presenten, durante el año 2024, proyectos para la elaboración de inventarios nacionales de bancos de residuos de sustancias controladas con arreglo a la ventana de financiación establecida en virtud de la decisión 91/66, incluso en los casos en que dichos proyectos no estén comprendidos en los planes administrativos de los organismos.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,000 | 6,500 |
| Albania | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 129,390 | 9,057 |
| Bolivia (Plurinational State of) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,500 | 5,265 |
| Bolivia (Plurinational State of) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 153,500 | 10,745 |
| Brazil | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 5,200 |
| Brazil | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 126,500 | 8,855 |
| Brazil | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 63,500 | 4,445 |
| Cambodia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,810 | 11,143 |
| Cambodia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 126,300 | 16,419 |
| Chile | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 752,607 | 52,683 |
| Chile | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,900 | 16,107 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the air-conditioning manufacturing sector | 50,000 | 3,500 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 150,000 | 10,500 |
| Congo (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 13,750 | 1,788 |
| Congo (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 67,750 | 6,098 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 145,455 | 10,182 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 14,545 | 1,018 |
| Dominican Republic (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 120,774 | 15,701 |
| Dominican Republic (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,050 | 4,505 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 320,935 | 22,465 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 44,171 | 3,092 |
| Ecuador | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 292,600 | 20,482 |
| Egypt | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 2,800 |
| Egypt | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 180,000 | 12,600 |
| Eritrea | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Eritrea | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Georgia | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 125,000 | 11,250 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 6,630 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 7,500 | 675 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 4,500 | 585 |
| Grenada | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,670 | 2,670 |
| Grenada | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 42,830 | 5,568 |
| India | UNDP | INV | KIP | Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial air-conditioning packaged and ducted air-conditioning units at Voltas Limited | 422,561 | 29,579 |
| India | UNDP | INV | KIP | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) | 423,765 | 29,664 |
| India | UNDP | INV | KIP | Demonstration/conversion from R-404A and R-407C to CO2 transcritical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing sector at Mech Air Industries | 322,452 | 22,572 |
| India | UNDP | PRP | KIP | Preparation of a demonstration project in the manufacture of compressors for mobile air-conditioning manufacturing sector | 30,000 | 2,100 |
| Jordan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 2,540,680 | 177,848 |
| Kenya | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kenya | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kyrgyzstan | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 4,590 |
| Kyrgyzstan | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 30,000 | 3,900 |
| Lebanon | UNDP | PRP | PHA | Preparation of a KIP investment project in the refrigeration manufacturing sector | 70,000 | 4,900 |
| Malawi | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 39,000 | 5,070 |
| Malawi | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,000 | 2,610 |
| Malaysia | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 3,042,912 | 213,004 |
| Mali | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 35,000 | 2,450 |
| Mali | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 135,000 | 17,550 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 79,905 | 5,593 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 12,695 | 1,574 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 283,418 | 19,839 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (foam sector plan) | 888,833 | 62,218 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 465,000 | 32,550 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 215,100 | 26,669 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 4,801,972 | 336,138 |
| Mongolia | UNIDO | PRP | KIP | Preparation of a KIP investment project in the foam sector | 80,000 | 5,600 |
| Nicaragua | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,000 | 5,200 |
| Nicaragua | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 159,000 | 14,310 |
| Niger (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I) | 15,000 | 1,950 |
| Niger (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I) | 35,000 | 850 |
| North Macedonia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 103,555 | 9,320 |
| Panama | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 331,100 | 23,177 |
| Peru | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 283,140 | 19,820 |
| Republic of Moldova (the) | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Saint Vincent and the Grenadines | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 70,000 | 9,100 |
| Saint Vincent and the Grenadines | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 30,000 | 2,100 |
| Sri Lanka | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 80,000 | 5,600 |
| Thailand | IBRD | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 220,000 | 15,400 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 496,973 | 34,788 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 46,276 | 3,239 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 106,000 | 7,420 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 10,000 | 700 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 289,220 | 20,245 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 119,265 | 8,349 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 35,533 | 4,244 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 984,000 | 68,880 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 426,163 | 50,906 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (technical assistance and policy) | 165,307 | 11,571 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bolivia (Plurinational State of) | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 96,000 | 8,640 |
| Chile | UNDP | PRP | EEF | Preparation of a pilot project for the use of R-744 (carbon dioxide) as an alternative refrigerant in heat pumps in industrial refrigeration (decision 91/65) | 30,000 | 2,100 |
| China | UNIDO | DEM | EEF | Demonstration project of replacing HFC-134a with R-744 in the field of electric vehicles (decision 91/65) | 1,371,500 | 96,005 |
| Ecuador | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 190,000 | 17,100 |
| Egypt | UNIDO | DEM | EEF | Energy efficiency pilot project in the refrigeration and air-conditioning sector (decision 91/65) | 285,000 | 19,950 |
| India | Germany | DEM | EEF | Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65) | 1,853,795 | 213,918 |
| India | UNDP | DEM | EEF | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) (technical assistance to enhance the energy efficiency of the converted equipment) (decision 91/65) | 150,000 | 13,500 |
| Kenya | Germany | PRP | EEF | Preparation for a pilot project on energy efficiency (decision 91/65) | 30,000 | 3,900 |
| Kyrgyzstan | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 206,000 | 26,780 |
| Malaysia | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in stand-alone commercial refrigeration sector (decision 91/65) | 30,000 | 2,100 |
| Mexico | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 938,620 | 65,703 |
| Nicaragua | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Nicaragua | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 66,000 | 5,940 |
| Nigeria | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 145,000 | 13,050 |
| South Africa | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 1,120,000 | 78,400 |
| Togo | Germany | PRP | EEF | Project preparation for energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Turkmenistan | UNIDO | DEM | EEF | Pilot project for maintaining and enhancing energy efficiency of replacement technologies and equipment (decision 91/65) | 142,000 | 12,780 |
| Viet Nam | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in the air-conditioning sector (decision 91/65) | 30,000 | 2,100 |
| Global | UNDP | PRP | EEF | Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago | 80,000 | 5,600 |

Annex III

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Armenia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Benin | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Bolivia (Plurinational State of) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Bolivia (Plurinational State of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Burkina Faso | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Burundi | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cameroon | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Costa Rica | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Cuba | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Dominican Republic (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Ecuador | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Egypt | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| El Salvador | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Guatemala | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Guatemala | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Honduras | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Honduras | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Jamaica | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Kenya | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Liberia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Mexico | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Montenegro | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 4,900 |
| Namibia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Nicaragua | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Nicaragua | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| North Macedonia | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 5,600 |
| Peru | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Republic of Moldova (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Seychelles | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Togo | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Trinidad and Tobago | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Turkmenistan | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Uruguay | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Venezuela (Bolivarian Republic of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Viet Nam | IBRD | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Yemen | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 13,000 |

UNEP/OzL.Pro/ExCom/93/1

Etapa II de los PGEH para Bolivia (Estado Plurinacional de) (PNUMA y ONUDI), Ecuador (ONUDI), Guatemala (PNUMA y ONUDI), Mozambique (PNUD) y Macedonia del Norte (ONUDI); etapa III de los PGEH para Viet Nam (Banco Mundial); una preparación de proyecto para la etapa III de los PGEH para Perú (PNUD); una preparación de proyecto para un proyecto de inversión del PGEH para Tailandia (Banco Mundial); un proyecto de preparación de un proyecto de demostración para la India (PNUD); cinco proyectos de preparación del KIP para proyectos de inversión para Colombia (2) (PNUD), Líbano (PNUD), Mongolia (ONUDI) y Sri Lanka (PNUD); ocho proyectos de preparación de la etapa I del KIP para Brasil (Alemania, PNUD y ONUDI), Kenya (Alemania), Malí (PNUD y PNUMA) y San Vicente y las Granadinas (PNUMA y ONUDI); tres proyectos de inversión en HFC para la India (PNUD); 12 proyectos de eficiencia energética en virtud de la decisión 89/6 para Albania (ONUDI), Benin (ONUDI), Bolivia (Estado Plurinacional de) (PNUMA y ONUDI), Ecuador (ONUDI), Granada (ONUDI), Guatemala (PNUMA y ONUDI), Lesotho (Alemania), Liberia (Alemania), Namibia (Alemania) y Seychelles (Alemania); etapa I de los KIP para Bolivia (Estado Plurinacional de) (PNUMA), Congo (PNUMA y ONUDI), República Dominicana (PNUMA y ONUDI), Kirguistán (PNUD), Nicaragua (PNUMA), Níger (PNUMA y ONUDI) y Perú (PNUD); proyecto de fortalecimiento institucional para Bolivia (Estado Plurinacional de) (PNUMA), y 37 proyectos de preparación de inventarios nacionales de bancos de residuos de sustancias controladas con arreglo a la Decisión 91/66 según el Anexo III.

Estas actividades incluyen: 104 actividades relacionadas con los HCFC para 40 países (32,37 millones $EUA), 49 actividades relacionadas con los HFC para 34 países (12,26 millones $EUA) y 28 actividades de fortalecimiento institucional (9,47 millones $EUA).

UNEP/OzL.Pro/ExCom/93/25

UNEP/OzL.Pro/ExCom/93/3

UNEP/OzL.Pro/ExCom/93/4 y UNEP/OzL.Pro/ExCom/93/95.

UNEP/OzL.Pro/ExCom/93/6 y UNEP/OzL.Pro/ExCom/93/47.