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INFORMACIÓN ACTUALIZADA SOBRE LA SITUACIÓN DE LA EJECUCIÓN DEL PLAN
ADMINISTRATIVO REFUNDIDO DEL FONDO MULTILATERAL PARA 2023-2025


Introducción

El presente documento consta de las secciones siguientes:
I.	Actualización de la situación de ejecución del plan administrativo para 2023-2025

II.	Asignación de recursos para el trienio 2021-2023

III.	Recomendación

I.	Actualización de la situación de ejecución del plan administrativo para 2023-2025

En su 91ª reunión, el Comité Ejecutivo refrendó el plan administrativo refundido del Fondo Multilateral para 2023-2025. En respuesta a la decisión 91/31, la Secretaría ajustó dicho plan, como se indica en el cuadro 1.



Cuadro 1. Asignación de recursos del plan administrativo del Fondo Multilateral para 2023‑2025, refundido y ajustado ($EUA)*
	Descripción 
	2023
	2024
	2025
	Total 

	Actividades relativas a los HCFC 

	Planes de gestión de eliminación de los HCFC (PGEH) aprobados
	60 280 861
	56 111 450
	43 084 350
	159 476 661

	Preparación de proyectos de PGEH – etapa II
	200 480
	77 600
	0
	278 080

	Etapa II de los PGEH 
	2 937 082
	5 199 804
	3 462 199
	11 599 085

	Etapa II de los PGEH – inversión
	0
	248 532
	0
	248 532

	Preparación de proyectos para los PGEH – etapa III
	290 100
	92 750
	0
	382 850

	Etapa III de los PGEH 
	14 794 713
	10 344 520
	20 526 731
	45 665 964

	Preparación de proyectos para los PGEH – etapa IV
	90 000
	0
	0
	90 000

	Etapa IV de los PGEH
	0
	0
	2 093 000
	2 093 000

	PGEH – eficiencia energética
	3 258 494
	2 672 980
	3 379 420
	9 310 894

	Verificación de los PGEH **
	588 600
	588 600
	588 600
	1 765 800

	Subtotal de actividades relativas a los HCFC 
	82 440 330
	75 336 236
	73 134 299
	230 910 865

	Actividades relativas a los HFC

	Actividades de facilitación para la reducción de los HFC
	53 500
	160 500
	0
	214 000

	Preparación de proyectos de los planes de aplicación de la Enmienda de Kigali para los HFC (KIP)
	3 945 431
	2 567 011
	144 560
	6 657 002

	KIP
	27 299 967
	21 437 607
	245 413
	48 982 987

	Preparación de proyectos de los KIP – inversión 
	129 000
	0
	0
	129 000

	KIP – inversión
	321 000
	8 963 616
	0
	9 284 616

	Preparación de proyectos de control de emisiones del HFC-23
	43 000
	0
	0
	43 000

	Control de emisiones del HFC-23
	0
	8 000 000
	0
	8 000 000

	HFC – asistencia técnica
	0
	678 000
	0
	678 000

	Subtotal de actividades relativas a los HFC
	31 791 898
	41 806 734
	389 973
	73 988 605

	Proyecto piloto de eficiencia energética 

	Proyecto piloto de eficiencia energética
	20 000 000
	0
	0
	20 000 000

	Subtotal del proyecto piloto de eficiencia energética 
	20 000 000
	0
	0
	20 000 000

	Actividades corrientes

	Fortalecimiento institucional
	27 860 444
	16 639 896
	0
	44 500 341

	Programa de Asistencia al Cumplimiento (PAC)
	11 445 002
	11 788 350
	12 142 003
	35 375 355

	Unidad central
	5 969 740
	6 011 529
	6 053 610
	18 034 878

	Secretaría/Comité Ejecutivo/supervisión y evaluación (excepto la contraparte canadiense)
	7 237 326
	7 202 023
	6 816 624
	21 255 973

	Tesorero
	500 000
	500 000
	500 000
	1 500 000

	Subtotal de actividades corrientes
	53 012 512
	42 141 798
	25 512 237
	120 666 547

	Total general
	187 244 740
	159 284 767
	99 036 509
	445 566 017

	Australia
	0
	0
	152 497
	152 497

	Austria
	783 667
	0
	0
	783 667

	Francia
	671 075
	0
	0
	671 075

	Alemania
	1 349 869
	3 705 721
	1 028 250
	6 083 840

	Japón
	67 800
	0
	0
	67 800

	PNUD
	62 425 117
	54 216 500
	29 064 016
	145 705 634

	PNUMA
	40 325 066
	36 674 895
	22 071 085
	99 071 046

	ONUDI
	38 767 526
	29 078 890
	29 553 746
	97 400 162

	Banco Mundial
	14 528 694
	27 318 138
	9 261 691
	51 108 523

	Verificación de los PGEH **
	588 600
	588 600
	588 600
	1 765 800

	Proyecto piloto de eficiencia energética
	20 000 000
	0
	0
	20 000 000

	Secretaría/Comité Ejecutivo/supervisión y evaluación (excepto la contraparte canadiense)
	7 237 326
	7 202 023
	6 816 624
	21 255 973

	Tesorero
	500 000
	500 000
	500 000
	1 500 000


* Incluidos los gastos de apoyo a los organismos, según proceda.
** El Comité Ejecutivo aprueba anualmente la financiación de la preparación de los informes de verificación de los PGEH para los países de bajo consumo.

I.1 Estado de ejecución del plan administrativo para 2023

3.	Los valores totales del plan administrativo para 2023 ascienden a 187 244 740 $EUA. De esta cantidad, se aprobaron 29 253 988 $EUA en la 92ª reunión. Además, en la 93ª reunión se considerarán actividades por valor de 108 304 705 $EUA; si se aprueba la financiación de todas las propuestas de proyectos presentadas según lo solicitado, quedaría disponible un saldo de 49 686 047 $EUA del plan administrativo 2023, como se indica en el cuadro 2.

Cuadro 2. Plan administrativo refundido de 2023, aprobaciones en la 92ª reunión, proyecto recomendado a la 93ª reunión, y saldo ($EUA)*
	Partidas presupuestarias
	Valor total en el plan administrativo
	Aprobaciones en la 92ª reunión
	Actividades recomendadas a la 93ª reunión
	Saldo (positivo)/negativo

	Organismos bilaterales 
	2 872 411
	687 988
	1 657 265
	527 158

	PNUD
	62 425 117
	10 211 836
	 28 591 500 
	23 621 781

	PNUMA
	40 325 066
	6 644 731
	 22 767 524 
	10 912 811

	ONUDI
	38 767 526
	8 419 645
	 24 134 585 
	6 213 296

	Banco Mundial
	14 528 694
	2 681 989
	15 997 224
	(4 150 519)

	Verificación de los PGEH
	588 600
	573 900
	0
	14 700

	Proyecto piloto de eficiencia energética
	20 000 000
	33 900
	7 419 281
	12 546 819

	Subtotal (organismos)
	179 507 414
	29 253 988
	100 567 379
	49 686 047

	Secretaría/Comité Ejecutivo/supervisión y evaluación (excepto la contraparte canadiense)
	7 237 326
	0
	7 237 326
	0

	Tesorero
	500 000
	0
	500 000
	0

	Subtotal (costos corrientes)
	7 737 326
	0
	7 737 326
	0

	Total
	187 244 740
	29 253 988
	108 304 705
	49 686 047


* Incluidos los costos de la unidad central.

1. El valor de las propuestas de proyectos recomendadas a la 93ª reunión, de 100 567 379 $EUA, es superior en 16 578 316 $EUA a su valor en el plan administrativo de 2023, e incluye 12 521 905 $EUA relacionados con propuestas de proyecto no incluidas en el plan administrativo de 2023[footnoteRef:2]. [2:  Etapa II de los PGEH para Bolivia (Estado Plurinacional de) (PNUMA y ONUDI), Ecuador (ONUDI), Guatemala (PNUMA y ONUDI), Mozambique (PNUD) y Macedonia del Norte (ONUDI); etapa III de los PGEH para Viet Nam (Banco Mundial); una preparación de proyecto para la etapa III de los PGEH para Perú (PNUD); una preparación de proyecto para un proyecto de inversión del PGEH para Tailandia (Banco Mundial); un proyecto de preparación de un proyecto de demostración para la India (PNUD); cinco proyectos de preparación del KIP para proyectos de inversión para Colombia (2) (PNUD), Líbano (PNUD), Mongolia (ONUDI) y Sri Lanka (PNUD); ocho proyectos de preparación de la etapa I del KIP para Brasil (Alemania, PNUD y ONUDI), Kenya (Alemania), Malí (PNUD y PNUMA) y San Vicente y las Granadinas (PNUMA y ONUDI); tres proyectos de inversión en HFC para la India (PNUD); 12 proyectos de eficiencia energética en virtud de la decisión 89/6 para Albania (ONUDI), Benin (ONUDI), Bolivia (Estado Plurinacional de) (PNUMA y ONUDI), Ecuador (ONUDI), Granada (ONUDI), Guatemala (PNUMA y ONUDI), Lesotho (Alemania), Liberia (Alemania), Namibia (Alemania) y Seychelles (Alemania); etapa I de los KIP para Bolivia (Estado Plurinacional de) (PNUMA), Congo (PNUMA y ONUDI), República Dominicana (PNUMA y ONUDI), Kirguistán (PNUD), Nicaragua (PNUMA), Níger (PNUMA y ONUDI) y Perú (PNUD); proyecto de fortalecimiento institucional para Bolivia (Estado Plurinacional de) (PNUMA), y 37 proyectos de preparación de inventarios nacionales de bancos de residuos de sustancias controladas con arreglo a la Decisión 91/66 según el Anexo III.] 

El valor de las actividades relacionadas con los HFC recomendadas a la 93ª reunión ascienda a 23 789 140 $EUA, de los cuales 3 182 574 $EUA corresponden a propuestas de proyectos no incluidos en el plan administrativo para 2023. En el Anexo I del presente documento se enumeran los proyectos relacionados con los HFC presentados por los organismos bilaterales y de ejecución a la 93ª reunión.
6.	El valor de los proyectos recomendados con arreglo a la ventana de financiación para proyectos piloto de eficiencia energética de conformidad con la decisión 91/65 asciende a 7 419 281 $EUA. Teniendo en cuenta las aprobaciones en la 92ª reunión de 33 900 $EUA y los valores recomendados a la 93ª reunión, la financiación restante disponible en esta ventana de financiación es de 12 546 819 $EUA. En el Anexo II del presente documento se enumeran los proyectos piloto presentados por los organismos bilaterales y de ejecución a la 93ª reunión de conformidad con la decisión 91/65.

7.	El valor de los proyectos recomendados con arreglo a la ventana de financiación para la preparación de inventarios nacionales de bancos de residuos de sustancias controladas de conformidad con la decisión 91/66 asciende a 3 222 500 $EUA que no están incluidos en el plan administrativo para 2023. En el Anexo III del presente documento se enumeran las actividades de preparación de proyectos presentadas por los organismos bilaterales y de ejecución a la 93ª reunión de conformidad con la decisión 91/66.

8.	Además, en relación con la decisión 91/66, el apartado c) iii) exige que los proyectos correspondientes a la ventana de financiación mencionada se sometan a la consideración del Comité Ejecutivo a partir de la 93ª reunión hasta la 97ª reunión inclusive, en el entendimiento de que se incluirán en los planes administrativos pertinentes antes de su aprobación. Durante las conversaciones mantenidas con los organismos en las reuniones de las redes, estos informaron a la Secretaría de que los países del artículo 5 necesitaban más tiempo para comprender los distintos aspectos de la gestión de sustancias controladas no deseadas y necesitaban más información de los organismos durante las reuniones de las redes antes de acordar la inclusión de estas actividades en sus respectivos planes administrativos; esto llevó más tiempo del previsto. Basándose en las aportaciones adicionales y las consultas realizadas durante los últimos meses, incluso durante la 35ª Reunión de las Partes celebrada en octubre de 2023, los países han expresado su interés en presentar proyectos con arreglo a dicha ventana de financiación. A fin de facilitar la presentación de proyectos relacionados con la preparación de inventarios de bancos de sustancias controladas usadas o no deseadas, el Comité Ejecutivo, con carácter excepcional, tal vez desee permitir que los organismos bilaterales y de ejecución presenten actividades de preparación de proyectos en el marco de la ventana de financiación establecida en virtud de la decisión 91/66 durante el año 2024, incluso en los casos en que dichas actividades no estén comprendidas en los planes administrativos.

9.	Las propuestas de proyectos por un valor de 54 097 185 $EUA[footnoteRef:3] que estaban incluidas en el plan administrativo para 2023 no se presentaron a la 93ª reunión. Estas propuestas se han incluido en el plan administrativo refundido del Fondo Multilateral para 2024-2026[footnoteRef:4]. [3:  Estas actividades incluyen: 104 actividades relacionadas con los HCFC para 40 países (32,37 millones $EUA), 49 actividades relacionadas con los HFC para 34 países (12,26 millones $EUA) y 28 actividades de fortalecimiento institucional (9,47 millones $EUA).]  [4:  UNEP/OzL.Pro/ExCom/93/25] 


I.2	Compromisos futuros
1. El monto total de los compromisos futuros existentes para los acuerdos plurianuales correspondientes al período de 2023 a 2031 es de 314,16 millones $EUA, suponiendo que las solicitudes de financiación de dichos acuerdos, presentadas en la 93ª reunión, se aprueben en principio, como se indica en el cuadro 3.
Cuadro 3. Compromisos futuros (2023–2031) (miles de $EUA)
	Descripción
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	2031
	Total

	Aprobados en principio
	68 086
	53 334
	51 015
	42 781
	10 187
	5 852
	4 733
	8 163
	57
	244 207

	Presentados a la 
93ª reunión
	27 918
	0
	10 122
	14 050
	10 623
	24
	5 528
	1 683
	0
	69 949

	Total 
	96 005
	53 334
	61 137
	56 831
	20 811
	5 876
	10 261
	9 846
	57
	314 156



II.	Asignación de recursos para el trienio 2021–2023
Al 8 de noviembre de 2023, el saldo disponible en el Fondo Multilateral ascendía a 277 322 098 $EUA, con una contribución pendiente de 52 864 962 $EUA para el trienio 2021-2023, de la que no se espera recaudar 23 281 488 $EUA[footnoteRef:5].  Después del 8 de noviembre de 2023, los intereses potenciales a devengar y las posibles pérdidas debidas al mecanismo de tipos de cambio fijos (FERM) se estiman en 5 849 812 $EUA y 753 989 $EUA, respectivamente. Además, los fondos devueltos para proyectos finalizados y los intereses devueltos hasta la 93ª reunión ascienden a 4 669 316 $EUA[footnoteRef:6] y 505 720 $EUA[footnoteRef:7], respectivamente. Por consiguiente, la financiación total que podría estar disponible para nuevas asignaciones en la 93ª reunión asciende a 317 176 431 $EUA. [5:  UNEP/OzL.Pro/ExCom/93/3]  [6:  UNEP/OzL.Pro/ExCom/93/4 y UNEP/OzL.Pro/ExCom/93/95.]  [7:  UNEP/OzL.Pro/ExCom/93/6 y UNEP/OzL.Pro/ExCom/93/47.] 

Dado el valor de la financiación recomendada para los proyectos presentados a la 93ª reunión de 100 567 379 $EUA y el presupuesto de la Secretaría de 7 737 326 $EUA, el recurso disponible al final del trienio 2021-2023 sería de 208 871 726 $EUA. Además, la Quinta Reunión Extraordinaria de las Partes también tomó nota de que 246 millones $EUA en fondos restantes que se debían al Fondo Multilateral durante el trienio 2018-2020 se utilizarán después de 2023 para apoyar la aplicación del Protocolo de Montreal (decisión Ex.V/1). Por lo tanto, el total de recursos disponibles para el trienio 2024-2026 es de 454 871 726 $EUA, como se indica en el cuadro 4.
Cuadro 4. Asignación de recursos para el trienio de 2021–2023 ($EUA)
	Descripción
	 
	Monto ($EUA)

	Financiación disponible

	Saldo disponible al 8 de noviembre de 2023
	(a)
	277 322 098

	Contribuciones pendientes para el período de 2021 a 2023
	(b)
	52 864 962

	Contribuciones pendientes no previstas
	(c)
	(23 281 488)

	Posibles intereses devengados después del 8 de noviembre de 2023
	(d)
	5 849 812

	Posibles pérdidas debidas al FERM después del 8 de noviembre de 2023
	(e)
	(753 989)

	Devolución de fondos en la 93ª reunión
	(f)
	4 669 316

	Interés devuelto a la 93ª reunión
	(g)
	505 720

	Financiación total disponible 
	(h = a+b+c+d+e+f+g)
	317 176 431

	Gastos

	Proyectos recomendados a la 93ª reunión
	(i)
	100 567 379

	Secretaría/Comité Ejecutivo/Supervisión/Tesorero
	(j)
	7 737 326

	Total de gastos
	(k = i+j)
	108 304 705

	Recursos disponibles a finales de 2023
	(l = h-k)
	208 871 726

	Monto remanente para el trienio 2018–2020 que se utilizará después de 2023
	(m)
	246 000 000

	Total de recursos disponibles para el trienio 2024-2026
	(n= l+m)
	454 871 726



III.	Recomendación

El Comité Ejecutivo podría estimar oportuno:
Tomar nota de:
La actualización del estado de ejecución del plan administrativo refundido del Fondo Multilateral para 2023-2025, que figura en el documento UNEP/OzL.Pro/ExCom/93/23;
Que el valor total de las actividades solicitadas a la 93ª reunión asciende a 100 567 379 $EUA (incluidos 23 789 140 $EUA para actividades relacionadas con los HFC, 7 419 281 $EUA para proyectos piloto de eficiencia energética y 3 222 500 $EUA para la preparación de inventarios nacionales de bancos de residuos de sustancias controladas), de los cuales 12 521 905 $EUA están asociados a propuestas de proyectos no incluidos en el plan administrativo para 2023; y
Permitir, con carácter excepcional, que los organismos bilaterales y de ejecución presenten, durante el año 2024, proyectos para la elaboración de inventarios nacionales de bancos de residuos de sustancias controladas con arreglo a la ventana de financiación establecida en virtud de la decisión 91/66, incluso en los casos en que dichos proyectos no estén comprendidos en los planes administrativos de los organismos.
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Los documentos previos al período de sesiones del Comité Ejecutivo del Fondo Multilateral para la Aplicación del Protocolo de Montreal no van en perjuicio de cualquier decisión que el Comité Ejecutivo pudiera adoptar después de la emisión de los mismos.
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Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Albania
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	50,000
	6,500

	Albania
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	129,390
	9,057

	Bolivia (Plurinational State of)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	40,500
	5,265

	Bolivia (Plurinational State of)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	153,500
	10,745

	Brazil
	Germany
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	40,000
	5,200

	Brazil
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	126,500
	8,855

	Brazil
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	63,500
	4,445

	Cambodia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	123,810
	11,143

	Cambodia
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	126,300
	16,419

	Chile
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	752,607
	52,683

	Chile
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	123,900
	16,107

	Colombia
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the air-conditioning manufacturing sector
	50,000
	3,500

	Colombia
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	150,000
	10,500

	Congo (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	13,750
	1,788

	Congo (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	67,750
	6,098

	Cuba
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	145,455
	10,182

	Cuba
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	14,545
	1,018

	Dominican Republic (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	120,774
	15,701

	Dominican Republic (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	50,050
	4,505

	Dominican Republic (the)
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	320,935
	22,465

	Dominican Republic (the)
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	44,171
	3,092

	Ecuador
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	292,600
	20,482

	Egypt
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	40,000
	2,800

	Egypt
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	180,000
	12,600

	Eritrea
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	91,000
	11,830

	Eritrea
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	39,000
	2,730

	Georgia
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Ghana
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	125,000
	11,250

	Ghana
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	51,000
	6,630

	Ghana
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	7,500
	675

	Ghana
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	4,500
	585

	Grenada
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	29,670
	2,670

	Grenada
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	42,830
	5,568

	India
	UNDP
	INV
	KIP
	Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial air-conditioning packaged and ducted air-conditioning units at Voltas Limited
	422,561
	29,579

	India
	UNDP
	INV
	KIP
	Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC‑134a to propane (R-290)
	423,765
	29,664

	India
	UNDP
	INV
	KIP
	Demonstration/conversion from R-404A and R-407C to CO2 transcritical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing sector at Mech Air Industries
	322,452
	22,572

	India
	UNDP
	PRP
	KIP
	Preparation of a demonstration project in the manufacture of compressors for mobile air-conditioning manufacturing sector
	30,000
	2,100

	Jordan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	2,540,680
	177,848

	Kenya
	Germany
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	95,000
	12,350

	Kenya
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	95,000
	12,350

	Kyrgyzstan
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	51,000
	4,590

	Kyrgyzstan
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	30,000
	3,900

	Lebanon
	UNDP
	PRP
	PHA
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	70,000
	4,900

	Malawi
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	39,000
	5,070

	Malawi
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	29,000
	2,610

	Malaysia
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	3,042,912
	213,004

	Mali
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	35,000
	2,450

	Mali
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	135,000
	17,550

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	79,905
	5,593

	Mexico
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	12,695
	1,574

	Mexico
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	283,418
	19,839

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (foam sector plan)
	888,833
	62,218

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	465,000
	32,550

	Mexico
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	215,100
	26,669

	Mexico
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	4,801,972
	336,138

	Mongolia
	UNIDO
	PRP
	KIP
	Preparation of a KIP investment project in the foam sector
	80,000
	5,600

	Nicaragua
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	40,000
	5,200

	Nicaragua
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	159,000
	14,310

	Niger (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I)
	15,000
	1,950

	Niger (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I)
	35,000
	850

	North Macedonia
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	103,555
	9,320

	Panama
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	331,100
	23,177

	Peru
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	283,140
	19,820

	Republic of Moldova (the)
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Saint Vincent and the Grenadines
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	70,000
	9,100

	Saint Vincent and the Grenadines
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	30,000
	2,100

	Sri Lanka
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	80,000
	5,600

	Thailand
	IBRD
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	220,000
	15,400

	Trinidad and Tobago
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	496,973
	34,788

	Trinidad and Tobago
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	46,276
	3,239

	Turkmenistan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	106,000
	7,420

	Turkmenistan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	10,000
	700

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector)
	289,220
	20,245

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	119,265
	8,349

	Viet Nam
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	35,533
	4,244

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	984,000
	68,880

	Viet Nam
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	426,163
	50,906

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (technical assistance and policy)
	165,307
	11,571
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Annex II

PILOT PROJECTS FOR ENERGY EFFICIENCY (DECISION 91/65) 
SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Bolivia (Plurinational State of)
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	96,000
	8,640

	Chile
	UNDP
	PRP
	EEF
	Preparation of a pilot project for the use of R-744 (carbon dioxide) as an alternative refrigerant in heat pumps in industrial refrigeration (decision 91/65)
	30,000
	2,100

	China
	UNIDO
	DEM
	EEF
	Demonstration project of replacing HFC‑134a with R-744 in the field of electric vehicles (decision 91/65)
	1,371,500
	96,005

	Ecuador
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	190,000
	17,100

	Egypt
	UNIDO
	DEM
	EEF
	Energy efficiency pilot project in the refrigeration and air-conditioning sector (decision 91/65)
	285,000
	19,950

	India
	Germany
	DEM
	EEF
	Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65)
	1,853,795
	213,918

	India
	UNDP
	DEM
	EEF
	Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC‑134a to propane (R-290) (technical assistance to enhance the energy efficiency of the converted equipment) (decision 91/65)
	150,000
	13,500

	Kenya
	Germany
	PRP
	EEF
	Preparation for a pilot project on energy efficiency (decision 91/65)
	30,000
	3,900

	Kyrgyzstan
	UNEP
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	206,000
	26,780

	Malaysia
	IBRD
	PRP
	EEF
	Preparation for a pilot project on energy efficiency in stand-alone commercial refrigeration sector (decision 91/65)
	30,000
	2,100

	Mexico
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	938,620
	65,703

	Nicaragua
	UNEP
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	30,000
	3,900

	Nicaragua
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	66,000
	5,940

	Nigeria
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	145,000
	13,050

	South Africa
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	1,120,000
	78,400

	Togo
	Germany
	PRP
	EEF
	Project preparation for energy efficiency‑related activities (decision 91/65)
	30,000
	3,900

	Turkmenistan
	UNIDO
	DEM
	EEF
	Pilot project for maintaining and enhancing energy efficiency of replacement technologies and equipment (decision 91/65)
	142,000
	12,780

	Viet Nam
	IBRD
	PRP
	EEF
	Preparation for a pilot project on energy efficiency in the air-conditioning sector (decision 91/65)
	30,000
	2,100

	Global
	UNDP
	PRP
	EEF
	Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago
	80,000
	5,600
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Annex III

PROJECT PREPARATION FOR NATIONAL INVENTORIES OF BANKS 
OF WASTE‑CONTROLLED SUBSTANCES (DECISION 91/66) 
SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Albania
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Armenia
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Benin
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Bolivia (Plurinational State of)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Bolivia (Plurinational State of)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Burkina Faso
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Burundi
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Cameroon
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Costa Rica
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Cuba
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Dominican Republic (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Ecuador
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Egypt
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	El Salvador
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Guatemala
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Guatemala
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Honduras
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Honduras
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Jamaica
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Kenya
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Liberia
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Mexico
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Montenegro
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	4,900

	Namibia
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Nicaragua
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Nicaragua
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	North Macedonia
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	5,600

	Peru
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Republic of Moldova (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Seychelles
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Togo
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Trinidad and Tobago
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Turkmenistan
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Uruguay
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Venezuela (Bolivarian Republic of)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Viet Nam
	IBRD
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Yemen
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	13,000
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