| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/94/12 13 May 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fourth Meeting

Montreal, 27-31 May 2024

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION 
OF THE 2024-2026 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND AND FINANCIAL PLANNING FOR THE TRIENNIUM 2024-2026

- Introduction

# The present document consists of the following sections:

## I.	An update on the status of the implementation of the 2024–2026 business plan

## II.	Financial planning for the triennium 2024-2026

III.	Reports on dialogues concerning qualitative performance indicators

IV.	Recommendation

## I.	Update on the status of the implementation of the 2024–2026 business plan

# At its 93rd meeting, the Executive Committee endorsed the 2024–2026 consolidated business plan of the Multilateral Fund. In response to decision 93/28, the Secretariat adjusted the consolidated 2024–2026 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2024–2026 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2024 | 2025 | 2026 | Total |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 48,499,466 | 50,384,491 | 50,158,180 | 149,042,137 |
| Approved HCFC production phase-out management plans (HPPMPs) | 23,232,000 | 0 | 0 | 23,232,000 |
| HPMP preparation - stage II | 134,400 | 44,300 | 0 | 178,700 |
| HPMP stage II | 4,970,041 | 6,870,087 | 10,870,876 | 22,711,004 |
| HPMP preparation - stage III | 522,900 | 65,400 | 0 | 588,300 |
| HPMP stage III | 15,849,471 | 10,765,760 | 23,015,282 | 49,630,513 |
| HPMP preparation - stage IV | 70,000 | 0 | 0 | 70,000 |
| HPMP stage IV | 0 | 0 | 3,691,000 | 3,691,000 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HPMP - energy efficiency | 3,726,111 | 3,305,040 | 111,200 | 7,142,351 |
| HCFC activities subtotal | 97,592,989 | 72,023,678 | 88,435,138 | 258,051,805 |
| HFC activities |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 0 | 10,127,716 | 6,590,654 | 16,718,370 |
| Approved HFC-23 emission control | 414,238 | 626,900 | 572,433 | 1,613,571 |
| HFC - enabling activities | 53,500 | 160,500 | 0 | 214,000 |
| HFC - technical assistance | 678,000 | 0 | 0 | 678,000 |
| HFC-23 | 8,000,000 | 0 | 0 | 8,000,000 |
| KIP stage I | 11,458,349 | 27,565,521 | 6,378,667 | 45,402,537 |
| KIP stage I - investment | 3,712,616 | 0 | 0 | 3,712,616 |
| KIP preparation - stage I | 2,891,415 | 1,167,771 | 211,280 | 4,270,466 |
| KIP preparation stage I - investment | 32,100 | 0 | 0 | 32,100 |
| HFC activities subtotal | 27,240,219 | 39,648,408 | 13,753,034 | 80,641,660 |
| Other activities |  |  |  |  |
| Pilot project for energy efficiency - demonstration | 1,870,000 | 1,000,000 | 0 | 2,870,000 |
| Pilot project for energy efficiency - investment | 4,789,988 | 248,600 | 0 | 5,038,588 |
| Pilot project for energy efficiency - preparation | 85,600 | 0 | 0 | 85,600 |
| ODS banks preparation | 1,232,150 | 310,300 | 0 | 1,542,450 |
| HFC activities subtotal | 7,977,738 | 1,558,900 | 0 | 9,536,638 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 22,071,008 | 1,830,362 | 21,294,756 | 45,196,125 |
| Compliance Assistance Programme (CAP) | 11,765,667 | 12,113,777 | 12,310,330 | 36,189,774 |
| Core unit | 6,611,529 | 6,653,609 | 6,095,985 | 19,361,122 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,202,023 | 6,816,624 | 6,964,604 | 20,983,251 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 48,150,226 | 27,914,372 | 47,165,675 | 123,230,273 |
| Grand total | 180,961,172 | 141,145,358 | 149,353,846 | 471,460,376 |
| By agency |  |  |  |  |
| Australia | 0 | 615,610 | 0 | 615,610 |
| Austria | 783,667 | 0 | 0 | 783,667 |
| France | 671,075 | 0 | 0 | 671,075 |
| Germany | 7,500,449 | 2,148,339 | 5,834,901 | 15,483,689 |
| UNDP | 44,305,827 | 38,729,891 | 40,741,817 | 123,777,535 |
| UNEP | 47,977,295 | 27,975,506 | 35,097,810 | 111,050,611 |
| UNIDO | 40,363,268 | 49,551,567 | 30,746,018 | 120,660,853 |
| World Bank | 31,068,968 | 14,219,221 | 28,880,096 | 74,168,285 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,202,023 | 6,816,624 | 6,964,604 | 20,983,251 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

I.1	Status of implementation of the 2024 business plan

# Table 2 sets out the submissions by agency to the 94th meeting (as at 13 May 2024), and the balance of funds from projects in the 2024 business plans.

Table 2. 2024 consolidated business plan, project recommended to the 94th meeting, and balance (US $)*

| Budget items | Total value in business plan | Activities recommended to the 94th meeting | Balance (above)/below |
| --- | --- | --- | --- |
| Bilateral agencies | 8,955,191 | 7,732,285 | 1,222,906 |
| UNDP | 44,305,827 | 17,348,354 | 26,957,473 |
| UNEP | 47,977,295 | 13,610,909 | 34,366,386 |
| UNIDO | 40,363,268 | 23,572,172 | 16,791,096 |
| World Bank | 31,068,968 | 0 | 31,068,968 |
| HPMP verification | 588,600 | 571,500 | 17,100 |
| Subtotal (agencies) | 173,259,149 | 62,835,221 | 110,423,928 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 7,202,023 | 0 | 7,202,023 |
| Treasurer | 500,000 | 0 | 500,000 |
| Subtotal (standard costs) | 7,702,023 | 0 | 7,702,023 |
| Total | 180,961,172 | 62,835,221 | 118,125,951 |

* Including core unit costs.

# The value of project proposals recommended to the 94th meeting of US $62,835,221 is US $16,475,389 above its value in the 2024 business plan and includes US $5,994,565 associated with project proposals not included in the 2024 business plan.

# The value of HFC-related activities recommended to the 94th meeting is US $4,791,958 of which US $1,160,589 is associated with project proposals not included in the 2024 business plan. Annex I to the present document lists HFC-related projects submitted by the bilateral and implementing agencies to the 94th meeting.

# The value of projects recommended under the funding window for pilot projects for energy efficiency pursuant to decision 91/65 is US $2,830,001. Taking into account approvals at the 92nd and 93rd meetings of US $3,146,488 and the values recommended to the 94th meeting, the remaining funding available under this funding window is US $14,023,511. Annex II to the present document lists the pilot projects submitted by bilateral and implementing agencies to the 94th meeting pursuant to decision 91/65.

# The value of projects recommended under the funding window for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66 is US $2,418,400 including US $1,926,700 that is not included in the 2024 business plan. Annex III to the present document lists the project preparation activities submitted by bilateral and implementing agencies to the 94th meeting pursuant to decision 91/66.

# I.2	Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2024 to 2031 is US $303.23 million, assuming that the funding requests of MYAs submitted to the 94th meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2024–2031) (US $000)

| Description | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 72,261 | 61,078 | 57,205 | 20,940 | 6,195 | 10,267 | 10,018 | 57 | 238,020 |
| Submitted to 94th meeting* | 22,929 | 0 | 11,829 | 12,852 | 11,038 | 2,169 | 4,394 | 0 | 65,212 |
| Total | 95,190 | 61,078 | 69,034 | 33,792 | 17,233 | 12,436 | 14,412 | 57 | 303,232 |

* Excluding Saudi Arabia for which the Agreement is still pending.

# II.	Financial planning for the triennium 2024-2026

# The Secretariat has prepared the financial planning for the triennium 2024-2026 taking into consideration decision XXXV/1 of the Thirty-Fifth Meeting of the Parties on the level of replenishment of the Fund, and the commitments and resource availability in the light of expected cash flow during the triennium.

Commitments and resources available during 2024–2026

# The Multilateral Fund is entering the 2024–2026 triennium with the following commitments made in the previous triennia: MYAs at a funding level of US $190.61 million, and standard activities at a funding level of US $123.23 million (such as IS, Executive Committee meetings and the Fund Secretariat’s operational costs including for monitoring and evaluation activities, Treasurer costs, UNEP’s CAP, and the core unit costs for UNDP, UNIDO and the World Bank). After taking into account previous commitments, a balance of US $651.16 million is available for new activities, as shown in table 4.

Table 4. Commitments and resources available for new activities during 2024-2026

| Description | 2024 | 2025 | 2026 | Total |
| --- | --- | --- | --- | --- |
| INCOME (A) | 321,666,667 | 321,666,667 | 321,666,667 | 965,000,000 |
| PRIOR COMMITMENTS |  |  |  |  |
| Annual tranches of approved MYAs | 72,145,704 | 61,139,107 | 57,321,267 | 190,606,078 |
| Other funding commitments |  |  |  |  |
| IS | 22,071,008 | 1,830,362 | 21,294,756 | 45,196,125 |
| UNEP’s CAP | 11,765,667 | 12,113,777 | 12,310,330 | 36,189,774 |
| Agencies core unit costs (UNDP, UNIDO, World Bank) | 6,611,529 | 6,653,609 | 6,095,985 | 19,361,122 |
| Secretariat/Executive Committee costs | 7,202,023 | 6,816,624 | 6,964,604 | 20,983,251 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Total commitments (B) | 120,295,930 | 89,053,479 | 104,486,942 | 313,836,351 |
| RESOURCES AVAILABLE FOR NEW ACTIVITIES (C=A-B) | 201,370,736 | 232,613,188 | 217,179,725 | 651,163,649 |
| New activities, 2024-2026 adjusted business plan |  |  |  |  |
| HCFC-related activities | 25,861,523 | 21,639,187 | 38,276,958 | 85,777,668 |
| HFC-related activities | 26,825,981 | 28,893,792 | 6,589,947 | 62,309,719 |
| Pilot project for energy efficiency | 6,745,588 | 1,248,600 | 0 | 7,994,188 |
| ODS banks preparation | 1,232,150 | 310,300 | 0 | 1,542,450 |
| Total new activities (D) | 60,665,242 | 52,091,879 | 44,866,904 | 157,624,025 |
| BALANCE (E=C-D) | 140,705,494 | 180,521,309 | 172,312,821 | 493,539,624 |

# Taking into account new activities in the 2024-2026 adjusted business plan of US $157.62 million, the resources available at the end of the 2024-2026 triennium is US $493.54 million.

Possible factors impacting financial planning and cash flow during the 2024-2026 triennium

# The cash flow of the Multilateral Fund for the 2024-2026 triennium is influenced by several factors, inter alia: receipt of agreed 2024-2026 pledged contributions; the potential interest to be accrued; the potential loss/gain due to the fixed-exchange rate mechanism (FERM); payment of contributions in arrears included in the carry-over; and the potential balances and interest returned from projects. The following paragraphs provide more information on these factors that could influence financial planning and cash flow of the 2024-2026 triennium.

Receipt of agreed pledged contributions

# The average rate of pledges received during the 2021-2023 triennium was 93.1 per cent. Based on this rate of pledges received, US $36.27 million of the US $525.6 million is not expected to be received during the 2024-2026 triennium.

Payment of outstanding contributions in arrears included in the carry-over

# The Parties adopted a carry-over of US $428,699,680 from the 2021-2023 triennium. This amount was based on the status of the fund balance reported at the 92nd meeting plus the projected income and expenditures accrued until 31 December 2023.

# Based on updated information at the end of 2023, the actual carry-over is US $485,797,211. The difference of US $57,097,530 between the projected and actual balance is mainly attributed to the following:

## The contributions not expected to be received increased from US $23,408,666 to US $24,948,270;

## The interest earned increased from US $10,697,124 to US $32,987,320;

## The loss to the FERM reduced from US $890,318 to US $344,268;

## The funds returned at the 93rd meeting increased from US $4,290,354 to US $4,670,024;

## The projects approved at the 93rd meeting for the four implementing agencies were reduced from US $122,704,590 to US $94,986,543;

## The Secretariat, and Monitoring and Evaluation, budget was reduced from US $7,737,326 to nil as they are already part of the allocations in the status of the Fund.

Potential interest accrued during the 2024-2026 triennium

# The total interest accrued during the 2021-2023 triennium was US $35,822,627, with an average of US $11.94 million per year. On this basis, it might expect that the interest accrued per year will be US $11.5 million during the 2024-2026 triennium.

# Gains/losses due to the fixed-exchange-rate mechanism

# The potential impact of the FERM for those countries that are qualified to use it for the 2024-2026 triennium is difficult to predict, given the fluctuations of the currency exchange against the US dollar. The document on the Status of contributions and disbursements submitted to the 94th meeting, reports that since its inception in 2000 and up to 25 April 2024, the use of the FERM has incurred a cumulative loss of US $29,868,900.

# Based on the assumption that the same Parties will continue to opt for the FERM in the 2024-2026 triennium, and assuming that the applied UN average exchange rates between 1 January 2021 to 31 December 2023 remains constant, the projected gain on exchange is US $791,205 in 2024, and US$1,432,362 in 2025 and 2026 respectively. Therefore, the total estimated FERM gain for the 2024-2026 triennium is US$3,655,929.

Potential balances returned from cancelled or completed projects

# Cash flow could be impacted by the return of balances from cancelled or completed projects. However, it is difficult to calculate the potential total funds that could be returned during the 2024-2026 triennium. The average funds returned for the 2021-2023 triennium is US $13 million per year ranging from US $7.7 million in 2023 to US $15.8 million in 2022. Bilateral and implementing agencies are strongly encouraged to return all the balances for those projects which have been operationally completed or cancelled.

Assumptions for the full allocation of the 2024-2026 budget

# The sources of uncertainty in actual cash received may have an impact on the operation of the Fund and it will be necessary to monitor the budget in the context of business planning to ensure that there are sufficient resources for planned activities. The full budget of US $965 million for the 2024-2026 triennium could be available for programming during the triennium based on the following assumptions:

## Agreed pledges would be fully paid during the triennium by June of each year in accordance with paragraph 7 of decision XI/6;

## The Parties that have paid pledged contributions in the past will continue to do so and pay the US $7,716,516 of outstanding contributions from the previous triennium;

## US $10,700,320 in interest will be accrued; and

## There will be no gains or losses due to the FERM.

Secretariat’s comments

# Based on the adjusted business plans endorsed by the Executive Committee, bilateral and implementing agencies have included a total of US $180.96 million (including US $120.3 million already committed for multi-year projects and standard activities) in the 2024 business plan; this amount is US $140.71 million below the annual budget of US $321.67 million for the triennium.

# Similarly for 2025 and 2026, the total values included in the business plans for these two years are also below the annual budget of US $321.67 million for the triennium of US $180.52 million and US $172.31 million, respectively. Therefore, there is sufficient resources available to cover all projects and activities endorsed in the 2024-2026 business plan. This would enable a 2024 budget of US $181 million, 2025 of US $392 million and 2026 of US $392 million.

# The financial planning and cash flow analysis for 2024-2026 triennium also shows that there could be a positive gain on the potential income during this triennium taking into account all the above factors and trends. However, the potential gain could be limited if arrears carried over from the 2021-2023 triennium and pledged contribution for the 2024-2026 triennium are not received on time.

# In addition, an analysis of the total values of the consolidated business plans and the actual funding levels approved over the last eight triennia, indicated that the Executive Committee approved on average 79 per cent of the funding of the projects and activities submitted by bilateral and implementing agencies. The Executive Committee may wish to urge implementing agencies to submit all projects and activities endorsed in the business plan in order to fully utilize the resources available during the for 2024-2026 triennium.

# It is noted that certain policy issues related to funding including the cost guidelines for HFC phase-down will be under discussions at the 94th meeting. The adoption of the cost funding guidelines in the manufacturing sectors and other ongoing policy discussions at the Executive Committee that would have an impact on the funding levels for different project activities may lead to additional project submissions by the agencies from 2024 onward. The decisions related to all issues at the 94th meeting could have an impact on the business plan values compared to the levels, as endorsed, for the period of 2024-2026.

## III.	Reports on dialogues concerning qualitative performance indicators

# At its 93rd meeting, the Executive Committee requested UNDP to have open and constructive discussions with the national ozone unit (NOU) of the Dominican Republic to resolve any issues raised in the evaluation of the performance of UNDP and to report to the 94th meeting on the outcome of the discussions (decision 93/8(b)).

# In line with the decision, UNDP has initiated dialogues and consultations with the Government of the Dominican Republic and reported that the meetings conducted with the authorities of the Dominican Republic helped to identify areas of improvement in the execution of the Multilateral Fund financed projects implemented by UNDP. In addition, these meetings helped to clarify roles, procedures and changes that were not clear for the NOU. The identified action points started its implementation immediately after the meeting. These meetings were conducted in an open and constructive environment, which highlighted the common goal of both NOU and UNDP of a successful implementation of the projects.

# IV.	Recommendation

# The Executive Committee may wish:

## To note:

### The update on the status of implementation of the 2024-2026 consolidated business plan of the Multilateral Fund and financial planning for the triennium 2024-2026 as contained in document UNEP/OzL.Pro/ExCom/94/12;

### That the total value of activities as requested to the 94th meeting amounts to US $62,835,221 (including US $4,791,958 for HFC-related activities, US $2,830,001 for pilot projects for energy efficiency and US $2,418,400 for the preparation of national inventories of banks of waste-controlled substances), of which US $5,994,565 is associated with project proposals not included in the 2023 business plan;

### With appreciation, the report provided by UNDP on the outcome of its discussion with the Government of the Dominican Republic on the issues raised in the assessment of its qualitative performance, in line with decision 93/8(b);

## To adopt a resource allocation of US $181 million in 2024, US $392 million in 2025, and US $392 million in 2026 with any unallocated funds to be allocated subsequently during the 2024-2026 triennium;

## To urge implementing agencies to submit all projects and activities endorsed in the business plan in order to fully utilize the resources available during the for 2024-2026 triennium; and

## To consider the availability of cash flow for the 2026 budget at the last meeting of 2025 in light of the collection of interest, unexpected return of unused balances from projects/agreements, the payment of pledges from triennia prior to the last replenishment, any losses due to non-payment of pledges expected from the last replenishment, and any losses or gains due to the fixed-exchange-rate mechanism.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 94TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Armenia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 66,000 | 8,580 |
| Armenia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 99,075 | 12,880 |
| Belize | UNDP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Belize | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Burkina Faso | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 162,500 | 21,125 |
| China | UNDP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 250,000 | 17,500 |
| El Salvador | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 180,000 | 23,400 |
| Eswatini | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 63,500 | 8,255 |
| Gambia (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,150 | 6,520 |
| Gambia (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 30,000 | 3,900 |
| Guatemala | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 51,000 | 6,630 |
| Guatemala | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 119,000 | 8,330 |
| Honduras | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 70,000 | 9,100 |
| Honduras | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 226,918 | 15,885 |
| Lao People's Democratic Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 76,000 | 9,880 |
| Lao People's Democratic Republic (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 34,000 | 4,420 |
| Liberia | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 81,500 | 10,595 |
| Montenegro | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 115,050 | 14,956 |
| Mozambique | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 86,000 | 11,180 |
| Mozambique | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 83,500 | 10,855 |
| Papua New Guinea | Germany | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Paraguay | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 235,675 | 16,497 |
| Saint Lucia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 43,000 | 5,590 |
| Saint Lucia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 27,000 | 3,510 |
| Seychelles | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 16,844 | 2,190 |
| Seychelles | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 64,836 | 8,429 |
| Sierra Leone | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 65,500 | 8,515 |
| Sierra Leone | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 21,000 | 2,730 |
| Sri Lanka | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 136,160 | 12,254 |
| Sri Lanka | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 81,999 | 10,660 |
| Tunisia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,000 | 6,500 |
| Tunisia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 1,019,779 | 71,385 |
| Tunisia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector and PMU) | 506,787 | 35,475 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 94TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Cameroon | UNIDO | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) | 120,000 | 10,800 |
| China | UNDP | PRP | EEF | Preparation for a pilot project on energy efficiency (decision 91/65) | 25,000 | 1,750 |
| El Salvador | UNDP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) | 125,000 | 11,250 |
| India | Germany | INV | EEF | Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65) | 1,730,050 | 199,638 |
| Sierra Leone | Germany | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 91/65) | 30,000 | 3,900 |
| Sri Lanka | UNDP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) | 245,700 | 22,113 |
| Tunisia | UNIDO | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) | 170,000 | 15,300 |
| Uganda | Germany | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 91/65) | 30,000 | 3,900 |
| Global | UNDP | PRP | EEF | Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago | 80,000 | 5,600 |

Annex III

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 94TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Belize | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Botswana | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cambodia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Chile | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Eritrea | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Grenada | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Guyana | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Iran (Islamic Republic of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Kyrgyzstan | UNEP | INV | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Lao People's Democratic Republic (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Lesotho | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Libya | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Malawi | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Mauritius | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Niger (the) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Nigeria | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 13,000 |
| Panama | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Paraguay | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Saint Lucia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Sierra Leone | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Somalia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Türkiye | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Zambia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Zimbabwe | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |

UNEP/OzL.Pro/ExCom/94/1

Stage II of the HPMPs for Saudi Arabia (UNEP); two project preparation for stage I of KIPs for China (UNDP) and Papua New Guinea (Germany); four energy efficiency projects under decision 89/6 for Cambodia (UNEP), Cuba (UNDP), Sri Lanka (UNDP) and Timor-Leste (UNEP); stage I of KIPs for Burkina Faso (Germany), El Salvador (UNDP), Liberia (Germany), Mozambique (UNDP and UNEP), Seychelles (Germany) and Tunisia (UNEP); and 20 project preparation for national inventories of banks of waste-controlled substances under to decision 91/66 for Afghanistan (UNIDO), Belize (UNEP), Botswana (UNIDO), Cambodia	 (UNEP), Eritrea (UNEP), Grenada (UNEP) Guyana (UNEP), Iran (Islamic Republic of) (UNIDO), Lao People's Democratic Republic (the) (UNEP), Lesotho (UNEP), Malawi (UNEP), Mauritius (Germany), the Niger (UNIDO), Nigeria (UNEP), Saint Lucia (UNEP), Sierra Leone (UNEP), Somalia (UNEP), Türkiye (UNIDO), Zambia (UNEP) and Zimbabwe (UNEP).

As at 25 April 2024, per annex I of UNEP/OzL.Pro/ExCom/94/3, Status of contributions and disbursements.

As at 25 April 2024, per annex I of UNEP/OzL.Pro/ExCom/94/3, Status of contributions and disbursements.

At the Thirty-Fifth Meeting, the Parties agreed to extend the FERM to the 2024-2026 triennium (decision  XXXV/2).

UNEP/OzL.Pro/ExCom/94/3