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	REPORT ON BALANCES AND AVAILABILITY OF RESOURCES


Introduction
This document presents a summary of financial adjustments indicated by the bilateral (BAs) and implementing agencies (IAs) as agreed by the Secretariat. It includes statistical data[footnoteRef:2] from all projects with balances that have been held for over 12 months following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to relevant decisions (referred to as “by-decision” projects in this document). The document also follows up on the Office of Internal Oversight Services (OIOS) recommendation on the financial closure of projects (decision 88/1(d)). It further indicates the level of resources available to the Executive Committee in cash as recorded in the status of contributions and disbursements document,[footnoteRef:3] as required by decision 41/92(b), and presents a recommendation. The amounts that are held by IAs and BAs for completed projects and for by-decision projects are included in Annex I and Annex II, respectively. Annex III presents the funds returned by IAs and BAs from completed, by-decision, and additional voluntary contributions projects. [2: The data presented are based on the reporting format that has been developed pursuant to decision 31/2.]  [3: UNEP/OzL.Pro/ExCom/90/3] 

Funds to be returned to the 90th meeting
The total funds to be returned by IAs amount to US $3,360,846 as shown in Table 1.
Table 1. Funds to be returned by IAs to the 90th meeting (US $)
	Agency
	Project cost
	Agency support cost
	Total cost

	UNDP
	2,156,038
	161,346
	2,317,384

	UNEP
	(17,118)
	23,719
	6,601

	UNIDO
	968,631
	68,230
	1,036,861

	Total
	3,107,551
	253,295
	3,360,846



Funds withheld by IAs and BAs
Table 2 presents information on balances of completed, by-decisions and additional voluntary contributions projects that are withheld by the IAs. Annex I provide explanations on the delays in disbursing committed amounts or not returning not-committed amount and Annex II refers to Executive Committee decisions on the delays in returning funds after one year completion of projects.
Table 2. Balances of completed, by-decision, and additional voluntary contributions projects withheld by IAs (including agency support costs)
	Year completed
	UNDP
	UNEP
	UNIDO
	Total

	
	Number
	(US $)
	Number
	(US $)
	Number
	(US $)
	Number
	(US $)

	Projects completed over two years ago

	2018
	
	
	1
	23,215
	
	
	1
	23,215

	2019
	
	
	1
	31,296
	1
	46,514
	2
	77,810

	1 Jan to 31 May  2020
	2
	31,206
	
	
	
	
	2
	31,206

	Sub-total
	2
	31,206
	2
	54,511
	1
	46,514
	5
	132,231

	Projects completed in less than two years ago

	1 June to 
31 Dec 2020
	4
	14,520
	9
	455,895
	4
	989,199
	17
	1,459,614

	Sub-total
	4
	14,520
	9
	455,895
	4
	989,199
	17
	1,459,614

	Total 
	6
	45,726
	11
	510,406
	5
	1,035,713
	22
	1,591,845

	By-decisions projects (ongoing)

	
	1
	119,016
	3
	240,643
	15
	3,473,032
	19
	3,832,691

	Grand total
	7
	164,742
	14
	751,049
	20
	4,508,745
	41
	5,424,536



Balances held by BAs

Japan withheld a balance of one project completed in 2020 amounting to US $50,059 including agency support costs.
Follow up to decision 88/1(d)

At the 88th meeting, in the context of the audit of the Multilateral Fund by the OIOS, the Executive Committee requested the Fund Secretariat, the Treasurer, the BAs and IAs to complete implementation of OIOS recommendation 5 to implement the elements of the action plan to address the delays in financial closure of projects beyond the twelve-month limit stipulated by the Executive Committee, and to include information in that regard in relevant meeting documents (decision 88/1(d)). In addressing this OIOS recommendation, on 12 November 2021, the Fund Secretariat sent an official communication to the BAs and IAs reminding them to rigorously implement all the elements of the action plan in place since the 28th meeting and to adhere to all subsequent decisions, and to financially close all projects no later than the twelve-month limit stipulated by the Executive Committee. This recommendation was also addressed by the Secretariat at the Inter-agency Coordination Meeting, held on 31 March to 1 April 2022. The Secretariat also sent to the IAs for their action a list of completed projects with balances in 2020 and prior. The Secretariat has also reminded the agencies of the need to inform the Secretariat on a continuous basis if there are any anticipated issues with the financial closure so that early action can be taken. The statistics shared with OIOS shows that UNDP has financially closed all competed projects in 2018 and 2019 and committed to close 10 projects that are multi-year agreement tranches, UNEP has achieved a 96 per cent compliance rate with the audit recommendation and committed to close additional four projects and UNIDO had closed 38 projects and committed to close nine more projects while the World Bank has no balances withheld on completed projects. Subsequently, the OIOS agreed to close the observation on delays in financial closure of projects beyond the twelve-month limit stipulated by the Executive Committee.
Availability of resources

The status of contributions and disbursements document indicates an available balance of US $424,470,206 as of 5 May 2022. The total balance returned by IAs, to the 90th meeting amounts to US $3,360,846. Therefore, the total level of resources available for approvals at the 90th meeting, is US $427,831,052. 
Secretariat’s comments
The Secretariat reminded BAs and IAs that balances of by-decisions projects and projects completed one year ago and more, should be returned to the Multilateral Fund as soon as possible. 
Considering that the total level of funding for projects and activities submitted to the 90th meeting as of 2 June 2022 is US $18,550,280, there are sufficient resources available for approvals at the 
90th meeting. 
Recommendation

The Executive Committee may wish:
(a) To note:

(i) The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/90/4;
(ii) That the net level of funds being returned at the 90th meeting by the implementing agencies was US $3,360,846, consisting of US $2,156,038, plus agency support costs of US $161,346 from UNDP; US $(17,118), plus agency support costs of US $23,719 from UNEP; and US $968,631, plus agency support costs of US $68,230 from UNIDO;
(iii) That UNDP held balances of US $31,206 including agency support costs, for two projects completed over two years previously, and US $119,016, including agency support costs, for one “by decisions of the Executive Committee” project; 
(iv) That UNEP held balances of US $54,511 including agency support costs, for two projects completed over two years and US $240,643, including agency support costs for three “by decisions of the Executive Committee” projects; and
(v) That UNIDO held balances of US $46,514 including agency support costs, for one project completed over two years and US $3,473,032, including agency support costs for 15 “by decisions of the Executive Committee” projects; 
To request:
(i) Bilateral and implementing agencies to proceed with disbursement or to cancel committed and not-committed funds that were not needed for completed projects and projects completed “by decision of the Executive Committee”, and to return the associated balances to the 91st meeting;
UNDP to proceed with disbursement or to cancel commitments for the remaining two projects completed over two years previously, and to return balances to the 91st meeting;
UNEP to proceed with disbursement or to cancel commitments for the remaining two projects completed over two years previously, and to return balances to the 91st meeting; and

UNIDO to proceed with disbursement or to cancel commitments for the remaining one project completed over two years previously.
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Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 31 December 2020 (US $)
	Funds disbursed as of 90th meeting (US $)
	Balances committed as per 90th meeting (US $)
	Balances not-committed as per 90th meeting (US $)
	Support cost on balances committed and not committed as per 90th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	COS/PHA/83/INV/59
	HCFC phase-out management plan (stage I, fifth tranche)
	Dec-20
	56,000
	47,445
	8,555
	
	642
	
	
	

	FIJ/PHA/77/INV/31
	HCFC phase-out management plan (stage I, third tranche)
	Dec-19
	59,850
	48,708
	11,142
	
	1,003
	
	
	

	FIJ/PHA/82/TAS/35
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	27,859
	2,141
	
	193
	The updated status will be reported to the 91st meeting for Fiji once the open commitment is closed /disbursed
	
	

	GUY/PHA/75/INV/28
	HCFC phase-out management plan (stage II, first tranche)
	Dec-19
	159,750
	141,936
	17,814
	
	1,247
	
	
	

	SRL/PHA/82/PRP/52
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	40,000
	38,157
	1,843
	
	129
	
	
	

	SRL/PHA/82/TAS/51
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	29,067
	933
	
	84
	The project balances are currently fully disbursed and projects financially closed. 
 

	
	

	TOTAL UNDP
	
	
	
	
	42,429
	
	3,297
	
	
	

	

	UNEP

	ASP/REF/76/DEM/59
	Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II)
	Dec-19
	375,000
	342,491
	     27,696 
	
	        3,600 
	
	
	83/37(c) and 85/18(b)

	BZE/PHA/82/PRP/36
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	5,000
	     15,000 
	
	        1,950 
	
	
	

	GAM/PHA/82/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	5,000
	     15,000 
	
	        1,950 
	
	
	

	GLO/SEV/84/TAS/350
	Compliance Assistance Programme: 2020 budget
	Dec-20
	8,899,977
	6,029,262
	   259,175 
	
	       20,734 
	
	
	

	KUW/REF/75/TAS/29
	Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling)
	Jun-18
	27,223
	6,679
	     20,544 
	
	        2,671 
	
	
	82/24(c)(ii) and 83/38(b)

	NIC/SEV/81/INS/35
	Renewal of institutional strengthening project (phase IX: 7/2018-6/2020)
	Dec-20
	85,000
	68,000
	     17,000 
	
	               - 
	
	
	

	RWA/PHA/81/PRP/29
	Preparation of a HCFC phase-out management plan (stage II)
	Nov-20
	22,000
	7,000
	     15,000 
	
	        1,950 
	
	
	

	SAU/PHA/68/TAS/18
	HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan)
	Dec-20
	43,150
	17,134
	     25,880 
	
	        3,206 
	
	
	86/16(f)(i)

	UGA/PHA/82/PRP/24
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	44
	     19,956 
	
	        2,594 
	
	
	

	ZAM/PHA/83/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	5,000
	     15,000 
	
	        1,950 
	
	
	

	ZIM/PHA/83/PRP/59
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	40,000
	5,000
	     35,000 
	
	        4,550 
	
	
	

	TOTAL UNEP
	
	
	
	
	   465,251
	
	45,155       
	
	
	

	UNIDO[footnoteRef:4] [4:  2: Financial completion initiated; 3: Financial completion to be initiated after settlement of all pending issues; 4: Project is ongoing and extension is in discussion] 


	JOR/REF/81/INV/103
	Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co.
	Jun-20
	1,637,610
	1,524,521
	113,089
	
	7,916
	4
	
	

	MOG/PHA/84/TAS/14
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	21,661
	8,339
	
	751
	2
	
	

	SAU/PHA/72/INV/21
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan)
	Dec-20
	2,693,674
	2,052,598
	641,076
	
	44,875
	2
	
	86/17(i)(i)

	SAU/REF/76/DEM/28
	Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures
	Dec-20
	1,300,000
	1,138,176
	161,824
	
	11,328
	3
	
	83/33(c), 85/17(c) and 88/27(c)

	SOA/PHA/71/INV/05
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan)
	Dec-19
	2,042,620
	1,999,149
	43,471
	
	3,043
	3
	
	

	TOTAL UNIDO
	
	
	
	
	967,799
	
	67,913
	
	
	

	
	
	
	
	
	
	
	
	
	
	

	JAPAN
	
	
	
	
	
	
	
	
	
	

	CPR/PHA/77/TAS/582
	HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component)

	Dec-20

	80,000

	35,700
	44,300
	
	5,759

	The balance is fully committed to the partner pending financial reporting. 
	The implementing partner has confirmed that they will provide the financial report by the date of ExCom 91 to enable   financially complete the project.
	

	TOTAL JAPAN
	
	
	
	
	44,300
	
	5,759
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS
	Code
	Project title
	Financial date of completion per decision
	Approved funding plus adjustments as of 31 December 2020 (US $)
	Funds disbursed as of
90th meeting (US $)
	Balances committed as per 90th  meeting (US $)
	Balances not- committed as per 90th  meeting (US $)
	Support cost on balances committed and not-committed as per 90th  meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	BRA/DES/72/DEM/305 
	Pilot demonstration project on ODS waste management and disposal 
	Dec-23 
	1,490,600 
	1,379,370

	111,230

	
	7,786

	
	
	79/18(c)(i) and 81/24(e)(ii) 

	TOTAL UNDP
	
	
	
	
	111,230
	
	7,786
	
	
	

	

	UNEP

	BAH/PHA/84/TAS/36

	HCFC phase-out management plan (stage I, third and fourth tranches) (policy, refrigeration servicing, monitoring and verification)

	91st meeting

	180,000

	70,000

	   110,000 

	
	14,300
	
	
	88/45(b)


	SAU/PHA/68/TAS/16
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring)
	87th meeting
	233,674
	182,206
	32,350
	
	4,007
	
	
	86/16(f)(i)

	SAU/PHA/77/TAS/32
	HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring)
	87th meeting
	130,400
	50,589
	71,170
	
	8,816
	
	
	86/16(f)(i)

	TOTAL UNEP
	
	
	
	
	213,520
	
	27,123
	
	
	

	UNIDO

	BHA/PHA/80/INV/25
	HCFC phase-out management plan (stage I, third tranche)
	Dec-23
	35,828
	15,823
	20,005
	
	1,800
	
	
	88/40(a)

	BRA/PHA/75/INV/311
	HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector)
	90th meeting
	1,674,275
	1,427,334
	44,841
	


	3,139
	
	
	88/61(a)(iii)

	CPR/PHA/64/INV/513
	HCFC phase-out management plan (room air-conditioner manufacturing sector plan) (stage I, first tranche)
	Dec-22
	36,430,000
	36,429,917
	83
	
	6
	
	
	84/68(d)(i) and 86/33(d)

	CPR/PHA/71/INV/536
	HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan)
	Dec-22
	8,495,000
	8,494,893
	107
	
	8
	
	
	84/68(d)(i) and 86/33(d)

	CPR/PHA/75/INV/564
	HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan)
	Dec-22
	11,250,000
	11,274,379
	(24,379)
	
	(1,706)
	
	
	84/68(d)(i) and 86/33(d)

	GLO/REF/80/DEM/344
	Global chiller replacement project (Argentina)
	Dec-21
	808,438
	121,667
	686,771
	
	51,508
	
	
	82/21(d)

	IRA/PHA/86/INV/246
	HCFC phase-out management plan (stage II, third tranche) (foam sector)
	
	524,000
	0
	148,299
	
	10,381
	
	
	

	IRQ/PHA/58/INV/09
	National phase-out plan (first tranche)
	Dec-18
	4,353,530
	3,998,281
	355,249
	
	26,644
	2
	91
	71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c)

	PHI/PHA/83/INV/104
	HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector)
	89th Meeting
	736,129
	95,414
	442,442
	
	30,971
	
	
	87/19(c)

	PHI/PHA/83/TAS/105
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	89th Meeting
	273,894
	132,310
	141,584
	
	9,911
	
	
	87/19(c)

	SAU/FOA/62/INV/13
	Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics
	89th Meeting
	1,103,578
	585,281
	518,297
	
	38,872
	
	
	86/17(i)(i)

	SAU/PHA/72/INV/20
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring)
	87th Meeting
	270,000
	235,670
	34,330
	
	2,403
	2
	91
	86/17(i)(i)

	SAU/PHA/75/INV/24
	HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan)
	87th Meeting
	1,100,000
	655,813
	444,187
	
	31,093
	2
	91
	86/17(i)(i)

	SAU/PHA/77/INV/31
	HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan)
	87th Meeting
	989,600
	576,629
	412,971
	
	28,908
	
	
	86/17(i)(i)

	SOM/PHA/77/INV/12
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	Second meeting in 2023
	141,500
	128,129
	13,371
	
	936
	
	
	88/40(a)

	TOTAL UNIDO
	
	
	
	
	3,238,159

	
	234,873
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Annex III

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

	Code
	Project title
	Project costs returned (US $)
	Agency support costs (US $)
	Total (US $)

	BHU/PHA/76/TAS/26
	HCFC phase-out management plan (third tranche)
	641
	58
	699

	BRA/SEV/75/INS/314
	Extension of institutional strengthening project (phase VIII: 12/2015-11/2017)
	5,511
	386
	5,896

	COS/PHA/81/PRP/58
	Preparation of a HCFC phase-out management plan (stage II)
	1,117
	78
	1,196

	COS/SEV/80/INS/56
	Extension of institutional strengthening project (phase XII: 1/2018-12/2019)
	5,398
	378
	5,776

	CUB/PHA/68/INV/50
	HCFC phase-out management plan ( stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector)
	1,665
	125
	1,790

	EGY/PHA/68/INV/117
	HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector)
	70,928
	5,320
	76,248

	EGY/PHA/82/INV/139
	HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector)
	118,460
	8,884
	127,344

	GHA/PHA/81/PRP/44
	Preparation of a HCFC phase-out management plan (stage II)
	230
	16
	246

	GHA/SEV/82/INS/47
	Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020)
	607
	42
	649

	IDS/PHA/71/TAS/200
	HCFC phase-out management plan (project management and coordination) (stage I, second tranche)
	159,291
	11,947
	171,238

	IDS/PHA/76/INV/208
	HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector)
	267,832
	20,087
	287,919

	IDS/SEV/80/INS/212
	Extension of institutional strengthening project (phase XI: 1/2018-12/2019)
	3,891
	272
	4,163

	IND/SEV/76/INS/467
	Extension of institutional strengthening project (phase X: 4/2016-3/2018)
	52
	4
	56

	MEX/PHA/71/INV/168
	HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers)
	314,646
	23,598
	338,244

	MEX/PHA/75/INV/178
	HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers)
	1,122,503
	84,188
	1,206,691

	MEX/REF/81/INV/187
	Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico
	5,237
	367
	5,603

	MLI/PHA/76/INV/38
	HCFC phase-out management plan (stage I, third tranche)
	14,107
	1,058
	15,165

	NEP/PHA/75/INV/35
	HCFC phase-out management plan (stage I, second tranche)
	2,684
	242
	2,926

	PAR/PHA/74/INV/34
	HCFC phase-out management plan (stage I, second tranche)
	1,858
	139
	1,997

	SRL/SEV/82/INS/53
	Extension of the institutional strengthening project (phase XII: 1/2019-12/2020)
	99
	7
	106

	URU/SEV/80/INS/70
	Extension of institutional strengthening project (phase XII: 1/2018-12/2019)
	295
	21
	316

	VEN/SEV/77/INS/135
	Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018)
	2,099
	147
	2,246

	ZIM/PHA/83/PRP/58
	Preparation of a HCFC phase-out management plan (stage II)
	8,565
	600
	9,165

	[bookmark: _Hlk5787459]Total completed projects
	
	2,107,715
	157,963
	2,265,678

	PAN/PHA/76/INV/44

	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	43,153

	3,021

	46,174

	Total “by decision” projects
	
	43,153

	3,021

	46,174

	[bookmark: _Hlk103677519]COS/SEV/80/TAS/01+

	Enabling activities for HFC phase-down

	5,170
	362
	5,532

	Total “additional voluntary contributions” projects
	
	5,170
	362
	5,532

	TOTAL UNDP
	
	2,156,038
	161,346
	2,317,384

	
	
	
	
	

	ASP/PHA/81/PRP/61
	Development of stage II of HCFC phase-out management plans for PIC countries through regional approach
	   129,990 
	     16,899 
	   146,888 

	ECU/PHA/85/TAS/73
	HCFC phase-out management plan (stage I, fifth tranche)
	    (10,000)
	     (1,300)
	    (11,300)

	ECU/PHA/86/TAS/74
	HCFC phase-out management plan (stage II, first tranche)
	    (24,000)
	     (3,120)
	    (27,120)

	ECU/SEV/83/INS/71
	Extension of institutional strengthening project (phase VII: 7/2019-6/2021)
	  (226,305)
	              - 
	  (226,305)

	ELS/PHA/65/TAS/28
	HCFC phase-out management plan (stage I, first tranche)
	       8,258 
	          290 
	       8,548 

	KUW/PHA/52/TAS/10
	Terminal phase-out management plan for Annex A Group I substances (first tranche)
	     60,820 
	       7,907 
	     68,727 

	LAO/PHA/74/TAS/27
	HCFC phase-out management plan (stage I, second tranche)
	     11,000 
	       1,430 
	     12,430 

	LAO/PHA/82/TAS/32
	Verification report on the implementation of the HCFC phase-out management plan
	       6,308 
	          820 
	       7,128 

	MOL/SEV/77/INS/36
	Extension of the institutional strengthening project (phase IX: 1/2017-12/2018)
	          708 
	              - 
	          708 

	MON/PHA/82/TAS/28
	Verification report on the implementation of the HCFC phase-out management plan
	           58 
	             8 
	           66 

	NAM/SEV/79/INS/24
	Extension of institutional strengthening project (phase IX: 7/2017-6/2019)
	     20,000 
	              - 
	     20,000 

	QAT/PHA/65/TAS/17
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	       6,045 
	          786 
	       6,831 

	Total completed projects
	
	    (17,118)

	     23,719 
	       6,601 

	TOTAL UNEP
	
	    (17,118)

	     23,719 
	       6,601 

	
	
	
	
	

	BAH/PHA/84/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	154
	11
	165

	BEN/PHA/84/PRP/39
	Preparation of a HCFC phase-out management plan (stage II)
	106
	7
	113

	BOL/PHA/86/INV/49
	HCFC phase-out management plan (stage I, fifth tranche)
	58
	5
	63

	ECU/PHA/85/INV/72
	HCFC phase-out management plan (stage I, fifth tranche)
	1,686
	127
	1,812

	EQG/PHA/82/INV/14
	HCFC phase-out management plan (stage I, third and fourth tranches)
	1,695
	153
	1,848

	ERI/PHA/84/PRP/18
	Preparation of a HCFC phase-out management plan (stage II)
	15
	1
	16

	GRN/PHA/77/INV/23
	HCFC phase-out management plan (stage I, second tranche)
	711
	64
	775

	KUW/REF/84/PRP/38
	Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector)
	78,239
	5,477
	83,715

	MDN/PHA/84/INV/42
	HCFC phase-out management plan (phase I, ninth tranche)
	38
	3
	41

	MOR/PHA/65/INV/68
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	433
	32
	465

	MOR/PHA/68/INV/69
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	615
	46
	661

	NER/PHA/82/TAS/34
	Verification report on the implementation of the HCFC phase-out management plan
	231
	21
	252

	OMA/PHA/75/INV/32
	HCFC phase-out management plan (stage II, first tranche)
	557
	39
	596

	OMA/PHA/82/INV/37
	HCFC phase-out management plan (stage II, second tranche)
	87
	6
	93

	OMA/PHA/86/INV/43
	HCFC phase-out management plan (stage II, third tranche)
	664
	46
	710

	PAK/PHA/76/TAS/95
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	5,645
	395
	6,040

	QAT/PHA/73/PRP/21
	Preparation of a HCFC phase-out management plan (stage II)
	347
	24
	372

	RWA/PHA/77/INV/27
	HCFC phase-out management plan (stage I, third tranche)
	233
	21
	254

	RWA/PHA/81/PRP/30
	Preparation of a HCFC phase-out management plan (stage II)
	808
	57
	865

	SAU/PHA/68/INV/17
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring)
	(6,628)
	(464)
	(7,092)

	SIL/PHA/76/INV/31
	HCFC phase-out management plan (stage I, third tranche)
	1,090
	98
	1,188

	SOA/PHA/67/TAS/04
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring)
	4,409
	308
	4,717

	STL/PHA/82/PRP/31
	Preparation of a HCFC phase-out management plan (stage II)
	83
	6
	89

	TUN/PHA/84/INV/78
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector)
	4,797
	336
	5,132

	TUR/SEV/80/INS/109
	Extension of institutional strengthening project (phase VIII: 12/2017-11/2019)
	5,082
	356
	5,438

	URT/PHA/76/INV/35
	HCFC phase-out management plan (stage I, second tranche)
	103
	9
	113

	YUG/PHA/84/INV/51
	HCFC phase-out management plan (stage I, fourth tranche)
	301
	23
	324

	YUG/SEV/80/INS/48
	Extension of institutional strengthening project (phase VI: 12/2017-11/2019)
	3,014
	211
	3,225

	Total completed projects
	
	104,572

	7,418
	111,990

	BRA/PHA/75/INV/311
	HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector)
	202,100
	14,147
	216,247

	EGY/PHA/82/INV/140
	HCFC phase-out management plan (stage I, third tranche) (enabling activities in the refrigeration and air-conditioning sector)
	1,987
	149
	2,136

	IRA/PHA/86/INV/246
	HCFC phase-out management plan (stage II, third tranche) (foam sector)
	375701
	26299
	402,000

	IRQ/REF/57/INV/07
	Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company
	63,547
	4,766
	68,313

	PHI/PHA/83/INV/104
	HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector)
	198,273
	13,879
	212,152

	SAU/PHA/75/INV/25
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring)
	1134
	79
	1,213

	Total “by decision” projects
	
	842,742

	59,320
	902,062

	[bookmark: _Hlk103676966]CMR/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	676
	47
	724

	GAM/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	53
	4
	57

	LEB/REF/81/INV/03+
	Conversion from HFC-134a and HFC-404A to R-600a and R-290 in domestic refrigeration at Lematic Industries
	13,984
	979
	14,963

	PRC/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	159
	11
	171

	SUD/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	344
	24
	369

	YUG/SEV/80/TAS/01+
	Enabling activities for HFC phase-down

	6,100
	427
	6,528

	Total “additional voluntary contributions” projects
	
	21,318
	1,492
	22,810

	TOTAL UNIDO
	
	968,631
	68,230
	1,036,861



image1.png




image2.png




image3.png




image4.png




