| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/90/4 3 June 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninetieth Meeting

Montreal, 20-23 June 2022

Item 4(b) of the provisional agenda

# report on balances and availability of resources

# Introduction

# This document presents a summary of financial adjustments indicated by the bilateral (BAs) and implementing agencies (IAs) as agreed by the Secretariat. It includes statistical data from all projects with balances that have been held for over 12 months following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to relevant decisions (referred to as “by-decision” projects in this document). The document also follows up on the Office of Internal Oversight Services (OIOS) recommendation on the financial closure of projects (decision 88/1(d)). It further indicates the level of resources available to the Executive Committee in cash as recorded in the status of contributions and disbursements document, as required by decision 41/92(b), and presents a recommendation. The amounts that are held by IAs and BAs for completed projects and for by-decision projects are included in Annex I and Annex II, respectively. Annex III presents the funds returned by IAs and BAs from completed, by-decision, and additional voluntary contributions projects.

Funds to be returned to the 90th meeting

# The total funds to be returned by IAs amount to US $3,360,846 as shown in Table 1.

# Table 1. Funds to be returned by IAs to the 90th meeting (US $)

| Agency | Project cost | Agency support cost | Total cost |
| --- | --- | --- | --- |
| UNDP | 2,156,038 | 161,346 | 2,317,384 |
| UNEP | (17,118) | 23,719 | 6,601 |
| UNIDO | 968,631 | 68,230 | 1,036,861 |
| Total | 3,107,551 | 253,295 | 3,360,846 |

Funds withheld by IAs and BAs

# Table 2 presents information on balances of completed, by-decisions and additional voluntary contributions projects that are withheld by the IAs. Annex I provide explanations on the delays in disbursing committed amounts or not returning not-committed amount and Annex II refers to Executive Committee decisions on the delays in returning funds after one year completion of projects.

Table 2. Balances of completed, by-decision, and additional voluntary contributions projects withheld by IAs (including agency support costs)

| Year completed | UNDP |  | UNEP |  | UNIDO |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Number | (US $) | Number | (US $) | Number | (US $) | Number | (US $) |
| Projects completed over two years ago |  |  |  |  |  |  |  |  |
| 2018 |  |  | 1 | 23,215 |  |  | 1 | 23,215 |
| 2019 |  |  | 1 | 31,296 | 1 | 46,514 | 2 | 77,810 |
| 1 Jan to 31 May 2020 | 2 | 31,206 |  |  |  |  | 2 | 31,206 |
| Sub-total | 2 | 31,206 | 2 | 54,511 | 1 | 46,514 | 5 | 132,231 |
| Projects completed in less than two years ago |  |  |  |  |  |  |  |  |
| 1 June to 31 Dec 2020 | 4 | 14,520 | 9 | 455,895 | 4 | 989,199 | 17 | 1,459,614 |
| Sub-total | 4 | 14,520 | 9 | 455,895 | 4 | 989,199 | 17 | 1,459,614 |
| Total | 6 | 45,726 | 11 | 510,406 | 5 | 1,035,713 | 22 | 1,591,845 |
| By-decisions projects (ongoing) |  |  |  |  |  |  |  |  |
|  | 1 | 119,016 | 3 | 240,643 | 15 | 3,473,032 | 19 | 3,832,691 |
| Grand total | 7 | 164,742 | 14 | 751,049 | 20 | 4,508,745 | 41 | 5,424,536 |

Balances held by BAs

# Japan withheld a balance of one project completed in 2020 amounting to US $50,059 including agency support costs.

Follow up to decision 88/1(d)

# At the 88th meeting, in the context of the audit of the Multilateral Fund by the OIOS, the Executive Committee requested the Fund Secretariat, the Treasurer, the BAs and IAs to complete implementation of OIOS recommendation 5 to implement the elements of the action plan to address the delays in financial closure of projects beyond the twelve-month limit stipulated by the Executive Committee, and to include information in that regard in relevant meeting documents (decision 88/1(d)). In addressing this OIOS recommendation, on 12 November 2021, the Fund Secretariat sent an official communication to the BAs and IAs reminding them to rigorously implement all the elements of the action plan in place since the 28th meeting and to adhere to all subsequent decisions, and to financially close all projects no later than the twelve-month limit stipulated by the Executive Committee. This recommendation was also addressed by the Secretariat at the Inter-agency Coordination Meeting, held on 31 March to 1 April 2022. The Secretariat also sent to the IAs for their action a list of completed projects with balances in 2020 and prior. The Secretariat has also reminded the agencies of the need to inform the Secretariat on a continuous basis if there are any anticipated issues with the financial closure so that early action can be taken. The statistics shared with OIOS shows that UNDP has financially closed all competed projects in 2018 and 2019 and committed to close 10 projects that are multi-year agreement tranches, UNEP has achieved a 96 per cent compliance rate with the audit recommendation and committed to close additional four projects and UNIDO had closed 38 projects and committed to close nine more projects while the World Bank has no balances withheld on completed projects. Subsequently, the OIOS agreed to close the observation on delays in financial closure of projects beyond the twelve-month limit stipulated by the Executive Committee.

Availability of resources

# The status of contributions and disbursements document indicates an available balance of US $424,470,206 as of 5 May 2022. The total balance returned by IAs, to the 90th meeting amounts to US $3,360,846. Therefore, the total level of resources available for approvals at the 90th meeting, is US $427,831,052.

Secretariat’s comments

# The Secretariat reminded BAs and IAs that balances of by-decisions projects and projects completed one year ago and more, should be returned to the Multilateral Fund as soon as possible.

# Considering that the total level of funding for projects and activities submitted to the 90th meeting as of 2 June 2022 is US $18,550,280, there are sufficient resources available for approvals at the 
90th meeting.

Recommendation

# The Executive Committee may wish:

  - To note:

- The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/90/4;

- That the net level of funds being returned at the 90th meeting by the implementing agencies was US $3,360,846, consisting of US $2,156,038, plus agency support costs of US $161,346 from UNDP; US $(17,118), plus agency support costs of US $23,719 from UNEP; and US $968,631, plus agency support costs of US $68,230 from UNIDO;

- That UNDP held balances of US $31,206 including agency support costs, for two projects completed over two years previously, and US $119,016, including agency support costs, for one “by decisions of the Executive Committee” project;

- That UNEP held balances of US $54,511 including agency support costs, for two projects completed over two years and US $240,643, including agency support costs for three “by decisions of the Executive Committee” projects; and

- That UNIDO held balances of US $46,514 including agency support costs, for one project completed over two years and US $3,473,032, including agency support costs for 15 “by decisions of the Executive Committee” projects;

## To request:

    - Bilateral and implementing agencies to proceed with disbursement or to cancel committed and not-committed funds that were not needed for completed projects and projects completed “by decision of the Executive Committee”, and to return the associated balances to the 91st meeting;

### UNDP to proceed with disbursement or to cancel commitments for the remaining two projects completed over two years previously, and to return balances to the 91st meeting;

### UNEP to proceed with disbursement or to cancel commitments for the remaining two projects completed over two years previously, and to return balances to the 91st meeting; and

### UNIDO to proceed with disbursement or to cancel commitments for the remaining one project completed over two years previously.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 90th meeting (US $) | Balances committed as per 90th meeting (US $) | Balances not-committed as per 90th meeting (US $) | Support cost on balances committed and not committed as per 90th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| COS/PHA/83/INV/59 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 56,000 | 47,445 | 8,555 |  | 642 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 48,708 | 11,142 |  | 1,003 |  |  |  |
| FIJ/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 27,859 | 2,141 |  | 193 | The updated status will be reported to the 91st meeting for Fiji once the open commitment is closed /disbursed |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 141,936 | 17,814 |  | 1,247 |  |  |  |
| SRL/PHA/82/PRP/52 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 38,157 | 1,843 |  | 129 |  |  |  |
| SRL/PHA/82/TAS/51 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 29,067 | 933 |  | 84 | The project balances are currently fully disbursed and projects financially closed. |  |  |
| TOTAL UNDP |  |  |  |  | 42,429 |  | 3,297 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Dec-19 | 375,000 | 342,491 | 27,696 |  | 3,600 |  |  | 83/37(c) and 85/18(b) |
| BZE/PHA/82/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 5,000 | 15,000 |  | 1,950 |  |  |  |
| GAM/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 5,000 | 15,000 |  | 1,950 |  |  |  |
| GLO/SEV/84/TAS/350 | Compliance Assistance Programme: 2020 budget | Dec-20 | 8,899,977 | 6,029,262 | 259,175 |  | 20,734 |  |  |  |
| KUW/REF/75/TAS/29 | Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling) | Jun-18 | 27,223 | 6,679 | 20,544 |  | 2,671 |  |  | 82/24(c)(ii) and 83/38(b) |
| NIC/SEV/81/INS/35 | Renewal of institutional strengthening project (phase IX: 7/2018-6/2020) | Dec-20 | 85,000 | 68,000 | 17,000 |  | - |  |  |  |
| RWA/PHA/81/PRP/29 | Preparation of a HCFC phase-out management plan (stage II) | Nov-20 | 22,000 | 7,000 | 15,000 |  | 1,950 |  |  |  |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Dec-20 | 43,150 | 17,134 | 25,880 |  | 3,206 |  |  | 86/16(f)(i) |
| UGA/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 44 | 19,956 |  | 2,594 |  |  |  |
| ZAM/PHA/83/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 5,000 | 15,000 |  | 1,950 |  |  |  |
| ZIM/PHA/83/PRP/59 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 5,000 | 35,000 |  | 4,550 |  |  |  |
| TOTAL UNEP |  |  |  |  | 465,251 |  | 45,155 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| JOR/REF/81/INV/103 | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co. | Jun-20 | 1,637,610 | 1,524,521 | 113,089 |  | 7,916 | 4 |  |  |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 21,661 | 8,339 |  | 751 | 2 |  |  |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-20 | 2,693,674 | 2,052,598 | 641,076 |  | 44,875 | 2 |  | 86/17(i)(i) |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | Dec-20 | 1,300,000 | 1,138,176 | 161,824 |  | 11,328 | 3 |  | 83/33(c), 85/17(c) and 88/27(c) |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 1,999,149 | 43,471 |  | 3,043 | 3 |  |  |
| TOTAL UNIDO |  |  |  |  | 967,799 |  | 67,913 |  |  |  |
| JAPAN |  |  |  |  |  |  |  |  |  |  |
| CPR/PHA/77/TAS/582 | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | Dec-20 | 80,000 | 35,700 | 44,300 |  | 5,759 | The balance is fully committed to the partner pending financial reporting. | The implementing partner has confirmed that they will provide the financial report by the date of ExCom 91 to enable financially complete the project. |  |
| TOTAL JAPAN |  |  |  |  | 44,300 |  | 5,759 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 90th meeting (US $) | Balances committed as per 90th meeting (US $) | Balances not- committed as per 90th meeting (US $) | Support cost on balances committed and not-committed as per 90th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,379,370 | 111,230 |  | 7,786 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 111,230 |  | 7,786 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| BAH/PHA/84/TAS/36 | HCFC phase-out management plan (stage I, third and fourth tranches) (policy, refrigeration servicing, monitoring and verification) | 91st meeting | 180,000 | 70,000 | 110,000 |  | 14,300 |  |  | 88/45(b) |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 182,206 | 32,350 |  | 4,007 |  |  | 86/16(f)(i) |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 50,589 | 71,170 |  | 8,816 |  |  | 86/16(f)(i) |
| TOTAL UNEP |  |  |  |  | 213,520 |  | 27,123 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| BHA/PHA/80/INV/25 | HCFC phase-out management plan (stage I, third tranche) | Dec-23 | 35,828 | 15,823 | 20,005 |  | 1,800 |  |  | 88/40(a) |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 90th meeting | 1,674,275 | 1,427,334 | 44,841 |  | 3,139 |  |  | 88/61(a)(iii) |
| CPR/PHA/64/INV/513 | HCFC phase-out management plan (room air-conditioner manufacturing sector plan) (stage I, first tranche) | Dec-22 | 36,430,000 | 36,429,917 | 83 |  | 6 |  |  | 84/68(d)(i) and 86/33(d) |
| CPR/PHA/71/INV/536 | HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan) | Dec-22 | 8,495,000 | 8,494,893 | 107 |  | 8 |  |  | 84/68(d)(i) and 86/33(d) |
| CPR/PHA/75/INV/564 | HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan) | Dec-22 | 11,250,000 | 11,274,379 | (24,379) |  | (1,706) |  |  | 84/68(d)(i) and 86/33(d) |
| GLO/REF/80/DEM/344 | Global chiller replacement project (Argentina) | Dec-21 | 808,438 | 121,667 | 686,771 |  | 51,508 |  |  | 82/21(d) |
| IRA/PHA/86/INV/246 | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  | 524,000 | 0 | 148,299 |  | 10,381 |  |  |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Dec-18 | 4,353,530 | 3,998,281 | 355,249 |  | 26,644 | 2 | 91 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 89th Meeting | 736,129 | 95,414 | 442,442 |  | 30,971 |  |  | 87/19(c) |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 89th Meeting | 273,894 | 132,310 | 141,584 |  | 9,911 |  |  | 87/19(c) |
| SAU/FOA/62/INV/13 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | 89th Meeting | 1,103,578 | 585,281 | 518,297 |  | 38,872 |  |  | 86/17(i)(i) |
| SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 87th Meeting | 270,000 | 235,670 | 34,330 |  | 2,403 | 2 | 91 | 86/17(i)(i) |
| SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | 87th Meeting | 1,100,000 | 655,813 | 444,187 |  | 31,093 | 2 | 91 | 86/17(i)(i) |
| SAU/PHA/77/INV/31 | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan) | 87th Meeting | 989,600 | 576,629 | 412,971 |  | 28,908 |  |  | 86/17(i)(i) |
| SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Second meeting in 2023 | 141,500 | 128,129 | 13,371 |  | 936 |  |  | 88/40(a) |
| TOTAL UNIDO |  |  |  |  | 3,238,159 |  | 234,873 |  |  |  |

Annex III

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | 641 | 58 | 699 |
| BRA/SEV/75/INS/314 | Extension of institutional strengthening project (phase VIII: 12/2015-11/2017) | 5,511 | 386 | 5,896 |
| COS/PHA/81/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | 1,117 | 78 | 1,196 |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | 5,398 | 378 | 5,776 |
| CUB/PHA/68/INV/50 | HCFC phase-out management plan ( stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | 1,665 | 125 | 1,790 |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | 70,928 | 5,320 | 76,248 |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | 118,460 | 8,884 | 127,344 |
| GHA/PHA/81/PRP/44 | Preparation of a HCFC phase-out management plan (stage II) | 230 | 16 | 246 |
| GHA/SEV/82/INS/47 | Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020) | 607 | 42 | 649 |
| IDS/PHA/71/TAS/200 | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | 159,291 | 11,947 | 171,238 |
| IDS/PHA/76/INV/208 | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | 267,832 | 20,087 | 287,919 |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | 3,891 | 272 | 4,163 |
| IND/SEV/76/INS/467 | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | 52 | 4 | 56 |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | 314,646 | 23,598 | 338,244 |
| MEX/PHA/75/INV/178 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers) | 1,122,503 | 84,188 | 1,206,691 |
| MEX/REF/81/INV/187 | Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico | 5,237 | 367 | 5,603 |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | 14,107 | 1,058 | 15,165 |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | 2,684 | 242 | 2,926 |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | 1,858 | 139 | 1,997 |
| SRL/SEV/82/INS/53 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | 99 | 7 | 106 |
| URU/SEV/80/INS/70 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | 295 | 21 | 316 |
| VEN/SEV/77/INS/135 | Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018) | 2,099 | 147 | 2,246 |
| ZIM/PHA/83/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | 8,565 | 600 | 9,165 |
| Total completed projects |  | 2,107,715 | 157,963 | 2,265,678 |
| PAN/PHA/76/INV/44 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 43,153 | 3,021 | 46,174 |
| Total “by decision” projects |  | 43,153 | 3,021 | 46,174 |
| COS/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 5,170 | 362 | 5,532 |
| Total “additional voluntary contributions” projects |  | 5,170 | 362 | 5,532 |
| TOTAL UNDP |  | 2,156,038 | 161,346 | 2,317,384 |
| ASP/PHA/81/PRP/61 | Development of stage II of HCFC phase-out management plans for PIC countries through regional approach | 129,990 | 16,899 | 146,888 |
| ECU/PHA/85/TAS/73 | HCFC phase-out management plan (stage I, fifth tranche) | (10,000) | (1,300) | (11,300) |
| ECU/PHA/86/TAS/74 | HCFC phase-out management plan (stage II, first tranche) | (24,000) | (3,120) | (27,120) |
| ECU/SEV/83/INS/71 | Extension of institutional strengthening project (phase VII: 7/2019-6/2021) | (226,305) | - | (226,305) |
| ELS/PHA/65/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | 8,258 | 290 | 8,548 |
| KUW/PHA/52/TAS/10 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | 60,820 | 7,907 | 68,727 |
| LAO/PHA/74/TAS/27 | HCFC phase-out management plan (stage I, second tranche) | 11,000 | 1,430 | 12,430 |
| LAO/PHA/82/TAS/32 | Verification report on the implementation of the HCFC phase-out management plan | 6,308 | 820 | 7,128 |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | 708 | - | 708 |
| MON/PHA/82/TAS/28 | Verification report on the implementation of the HCFC phase-out management plan | 58 | 8 | 66 |
| NAM/SEV/79/INS/24 | Extension of institutional strengthening project (phase IX: 7/2017-6/2019) | 20,000 | - | 20,000 |
| QAT/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 6,045 | 786 | 6,831 |
| Total completed projects |  | (17,118) | 23,719 | 6,601 |
| TOTAL UNEP |  | (17,118) | 23,719 | 6,601 |
| BAH/PHA/84/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | 154 | 11 | 165 |
| BEN/PHA/84/PRP/39 | Preparation of a HCFC phase-out management plan (stage II) | 106 | 7 | 113 |
| BOL/PHA/86/INV/49 | HCFC phase-out management plan (stage I, fifth tranche) | 58 | 5 | 63 |
| ECU/PHA/85/INV/72 | HCFC phase-out management plan (stage I, fifth tranche) | 1,686 | 127 | 1,812 |
| EQG/PHA/82/INV/14 | HCFC phase-out management plan (stage I, third and fourth tranches) | 1,695 | 153 | 1,848 |
| ERI/PHA/84/PRP/18 | Preparation of a HCFC phase-out management plan (stage II) | 15 | 1 | 16 |
| GRN/PHA/77/INV/23 | HCFC phase-out management plan (stage I, second tranche) | 711 | 64 | 775 |
| KUW/REF/84/PRP/38 | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | 78,239 | 5,477 | 83,715 |
| MDN/PHA/84/INV/42 | HCFC phase-out management plan (phase I, ninth tranche) | 38 | 3 | 41 |
| MOR/PHA/65/INV/68 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 433 | 32 | 465 |
| MOR/PHA/68/INV/69 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 615 | 46 | 661 |
| NER/PHA/82/TAS/34 | Verification report on the implementation of the HCFC phase-out management plan | 231 | 21 | 252 |
| OMA/PHA/75/INV/32 | HCFC phase-out management plan (stage II, first tranche) | 557 | 39 | 596 |
| OMA/PHA/82/INV/37 | HCFC phase-out management plan (stage II, second tranche) | 87 | 6 | 93 |
| OMA/PHA/86/INV/43 | HCFC phase-out management plan (stage II, third tranche) | 664 | 46 | 710 |
| PAK/PHA/76/TAS/95 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 5,645 | 395 | 6,040 |
| QAT/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | 347 | 24 | 372 |
| RWA/PHA/77/INV/27 | HCFC phase-out management plan (stage I, third tranche) | 233 | 21 | 254 |
| RWA/PHA/81/PRP/30 | Preparation of a HCFC phase-out management plan (stage II) | 808 | 57 | 865 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | (6,628) | (464) | (7,092) |
| SIL/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | 1,090 | 98 | 1,188 |
| SOA/PHA/67/TAS/04 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 4,409 | 308 | 4,717 |
| STL/PHA/82/PRP/31 | Preparation of a HCFC phase-out management plan (stage II) | 83 | 6 | 89 |
| TUN/PHA/84/INV/78 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 4,797 | 336 | 5,132 |
| TUR/SEV/80/INS/109 | Extension of institutional strengthening project (phase VIII: 12/2017-11/2019) | 5,082 | 356 | 5,438 |
| URT/PHA/76/INV/35 | HCFC phase-out management plan (stage I, second tranche) | 103 | 9 | 113 |
| YUG/PHA/84/INV/51 | HCFC phase-out management plan (stage I, fourth tranche) | 301 | 23 | 324 |
| YUG/SEV/80/INS/48 | Extension of institutional strengthening project (phase VI: 12/2017-11/2019) | 3,014 | 211 | 3,225 |
| Total completed projects |  | 104,572 | 7,418 | 111,990 |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 202,100 | 14,147 | 216,247 |
| EGY/PHA/82/INV/140 | HCFC phase-out management plan (stage I, third tranche) (enabling activities in the refrigeration and air-conditioning sector) | 1,987 | 149 | 2,136 |
| IRA/PHA/86/INV/246 | HCFC phase-out management plan (stage II, third tranche) (foam sector) | 375701 | 26299 | 402,000 |
| IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | 63,547 | 4,766 | 68,313 |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 198,273 | 13,879 | 212,152 |
| SAU/PHA/75/INV/25 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring) | 1134 | 79 | 1,213 |
| Total “by decision” projects |  | 842,742 | 59,320 | 902,062 |
| CMR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 676 | 47 | 724 |
| GAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 53 | 4 | 57 |
| LEB/REF/81/INV/03+ | Conversion from HFC-134a and HFC-404A to R-600a and R-290 in domestic refrigeration at Lematic Industries | 13,984 | 979 | 14,963 |
| PRC/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 159 | 11 | 171 |
| SUD/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 344 | 24 | 369 |
| YUG/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 6,100 | 427 | 6,528 |
| Total “additional voluntary contributions” projects |  | 21,318 | 1,492 | 22,810 |
| TOTAL UNIDO |  | 968,631 | 68,230 | 1,036,861 |

Document UNEP/OzL.Pro/ExCom/90/1.

The data presented are based on the reporting format that has been developed pursuant to decision 31/2.

UNEP/OzL.Pro/ExCom/90/3

2: Financial completion initiated; 3: Financial completion to be initiated after settlement of all pending issues; 4: Project is ongoing and extension is in discussion