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UNEP's WORK PROGRAMME AMENDMENTS FOR 2021*










*The present document is issued to reflect the removal of the request for preparation of the Kigali HFC implementation plan (stage I) for Liberia, which was approved at the 87th meeting. For ease of reference, changes to the document are highlighted.
COMMENTS AND RECOMMENDATION OF THE FUND SECRETARIAT
UNEP is requesting approval from the Executive Committee of US $3,455,511, plus agency support costs of US $200,930, for its 2021 work programme amendments listed in Table 1. The submission is attached to the present document.
Table 1: UNEP’s work programme amendments for 2021
	Country
	Activity/Project
	Amount requested (US $)
	Amount recommended (US $)

	SECTION A: ACTIVITIES RECOMMENDED FOR BLANKET APPROVAL

	A1: Renewal of institutional strengthening projects

	Albania
	Renewal of institutional strengthening project (phase X)
	139,776
	139,776

	Benin
	Renewal of institutional strengthening project (phase XII)
	85,000
	85,000

	Bhutan
	Renewal of institutional strengthening project (phase IX)
	85,000
	85,000

	Cameroon 
	Renewal of institutional strengthening project (phase XIII)
	178,601
	178,601

	Comoros (the)
	Renewal of institutional strengthening project (phase XII)
	85,000
	85,000

	Cook Islands
	Renewal of institutional strengthening project (phase VIII)
	85,000
	85,000

	Micronesia (Federated States of)
	Renewal of institutional strengthening project (phase VIII)
	85,000
	85,000

	Guatemala
	Renewal of institutional strengthening project (phase IX)
	159,744
	159,744

	Namibia
	Renewal of institutional strengthening project (phase XI)
	85,000
	85,000

	Paraguay
	Renewal of institutional strengthening project (phase X)
	85,000
	85,000

	Saint Vincent and the Grenadines
	Renewal of institutional strengthening project (phase VIII)
	85,000
	85,000

	Senegal
	Renewal of institutional strengthening project (phase XIV)
	194,689
	194,689

	Solomon Islands 
	Renewal of institutional strengthening project (phase IX)
	85,000
	85,000

	Sudan
	Renewal of institutional strengthening project (phase X)
	186,701
	186,701

	Timor-Leste
	Renewal of institutional strengthening project (phase VI)
	85,000
	85,000

	Vanuatu
	Renewal of institutional strengthening project (phase VIII)
	85,000
	85,000

	Subtotal for A1
	1,794,511
	1,794,511

	Agency support costs
	0
	0

	Total for A1
	1,794,511
	1,794,511

	A2: Technical assistance for enabling activities (decision 79/46)

	India
	Enabling activities for HFC phase‑down
	250,000
	250,000

	Subtotal for A2
	250,000
	250,000

	Agency support costs
	17,500
	17,500

	Total for A2
	267,500
	267,500

	A3: Technical assistance to prepare a verification report on HCFC consumption

	Botswana
	Verification report for stage II of the HPMP
	30,000
	30,000

	Djibouti
	Verification report for stage II of the HPMP
	30,000
	30,000

	Gambia (the)
	Verification report for stage II of the HPMP 
	30,000
	30,000

	Guinea-Bissau
	Verification report for stage II of the HPMP 
	30,000
	30,000

	Lao People’s Democratic Republic
	Verification report for stage II of the HPMP
	30,000
	30,000

	Mongolia
	Verification report for stage II of the HPMP
	30,000
	30,000

	Nepal
	Verification report for stage II of the HPMP
	30,000
	30,000

	Nicaragua
	Verification report for stage II of the HPMP
	30,000
	30,000

	Sao Tome and Principe
	Verification report for stage II of the HPMP
	30,000
	30,000

	Zimbabwe
	Verification report for stage II of the HPMP
	30,000
	30,000

	Subtotal for A3
	300,000
	300,000

	Agency support costs
	39,000
	39,000

	Total for A3
	339,000
	339,000

	A4: Project preparation for Kigali HFC implementation plans (KIPs)

	Cambodia a
	Preparation of a KIP (stage I)
	135,000
	135,000

	Chile b
	Preparation of a KIP (stage I)
	20,000
	20,000

	Fiji b
	Preparation of a KIP (stage I)
	35,000
	35,000

	Grenada a
	Preparation of a KIP (stage I)
	60,000
	60,000

	Lesotho c
	Preparation of a KIP (stage I)
	91,000
	91,000

	Malawi c
	Preparation of a KIP (stage I)
	119,000
	119,000

	Namibia c 
	Preparation of a KIP (stage I)
	119,000
	119,000

	Syrian Arab Republic c
	Preparation of a KIP (stage I)
	154,000
	154,000

	Rwanda c
	Preparation of a KIP (stage I)
	91,000
	91,000

	Sierra Leone c
	Preparation of a KIP (stage I)
	91,000
	91,000

	Uganda c
	Preparation of a KIP (stage I)
	70,000
	70,000

	Viet Nam d
	Preparation of a KIP (stage I)
	35,000
	35,000

	Zambia c
	Preparation of a KIP (stage I)
	91,000
	91,000

	Subtotal for A4
	1,111,000
	1,111,000

	Agency support costs
	144,430
	144,430

	Total for A4
	1,255,430
	1,255,430

	Grand total (A1, A2, A3, A4)
	3,656,441
	3,656,441


a UNDP as cooperating implementing agency 
b UNDP as lead implementing agency
c UNIDO as cooperating implementing agency
d World Bank as lead implementing agency

SECTION A: ACTIVITIES RECOMMENDED FOR BLANKET APPROVAL
A1: Renewal of institutional strengthening projects
Project description
UNEP submitted requests for the renewal of the institutional strengthening (IS) projects for the countries listed in section A1 of Table 1. The description for these projects are presented in Annex I to the present document.
Secretariat’s comments
The Secretariat reviewed the requests for the renewal of sixteen IS projects on behalf of the Governments concerned against the guidelines and relevant decisions regarding eligibility and funding levels. The requests were cross-checked against the original IS work plans for the previous phase, country programme and Article 7 data, the latest report on implementation of their HCFC phase‑out management plans (HPMPs), the agency’s progress report, and any relevant decisions of the Meeting of the Parties. It was noted that these countries have submitted their 2020 country programme data and are in compliance with the control targets under the Montreal Protocol, and their annual HCFC consumption does not exceed the annual maximum allowable consumption indicated in their HPMP Agreements with the Executive Committee. Furthermore, the requests submitted included performance indicators for the planned activities for the next phase of the IS projects, in accordance with decision 74/51(e).
The Secretariat noted the recent political situation in Sudan and discussed with UNEP implementation of projects in the country. It was agreed that UNEP would not disburse any funding approved to Sudan until UNEP has submitted a letter to the Secretariat indicating the possibility that the planned activities could be implemented in the country.
Secretariat’s recommendation
The Secretariat recommends blanket approval of the institutional strengthening renewal requests for Albania, Benin, Bhutan, Cameroon, Comoros (the), Cook Islands, Micronesia (Federated States of), Guatemala, Namibia, Paraguay, Saint Vincent and the Grenadines, Senegal, Solomon Islands, Sudan, Timor-Leste, and Vanuatu at the level of funding indicated in section A1 of Table 1 of the present document, on the understanding that UNEP would not disburse any funding approved to Sudan until UNEP has submitted a letter to the Secretariat indicating the possibility that the planned activities could be implemented in the country. The Executive Committee may wish to express to the aforementioned Governments the comments presented in Annex II to the present document.
A2: Technical assistance for enabling activities for HFC phase-down 
Background 
In line with decision 79/46,[footnoteRef:2] UNEP submitted a funding request for the implementation of enabling activities for the phase-down of HFCs in India,[footnoteRef:3] as shown in section A2 of Table 1. [2:  The Executive Committee decided inter alia to approve enabling activities on the basis that countries would be allowed the flexibility to undertake a range of activities to fulfil their initial obligations in line with the Kigali Amendment; enabling activities could consist of, but were not limited to, the following activities: facilitate and support the early ratification of the Kigali Amendment; initiating supporting institutional arrangements; the review of licensing systems; data reporting on HFCs; and demonstration of non-investment activities.]  [3:  India ratified the Kigali Amendment on 27 September 2021.] 

The enabling activities consist of: 
Development of a national strategy for the implementation of the Kigali Amendment including a study on HFC consumption and production; sectoral assessments for various applications including refrigeration and air-conditioning, foam, aerosol, servicing sector; identifying the requirements to establish the legislation and policy framework for management of HFC phase-down; and coordination among Government institutions and stakeholders on the policies and action plans required for the ratification and implementation of the Kigali Amendment; 
Review and update of the existing regulatory framework to support the import and export licensing systems for HFCs and HFC alternatives; and development of the framework for HFC data reporting and HFC licensing system in consultation with customs and relevant authorities; 
Evaluation of the practices and capacities of servicing technicians in terms of emission control and handling flammable and toxic refrigerants; assessment of the existing vocational training and qualification certificate system for the refrigeration servicing technicians; and review of alternative technology applications; and 
Outreach and awareness raising programme including development of informational materials and organization of three informative workshops for stakeholders and the public on Kigali Amendment and its implications, the HFC phase-down, and safe handling of alternatives, as well as energy efficiency and climate-friendly refrigerant options.
Secretariat’s comments 
The Secretariat reviewed the request for enabling activities and concluded that it fulfilled the requirements of decision 79/46, as noted below: 
Endorsement letter from the Government of India was submitted by UNEP; 
The project proposal included a description of the enabling activities, institutional arrangements, cost breakdown and the schedule for implementation; and 
Project implementation will be 18 months. 
The funding requested for India was consistent with decision 79/46(c) and calculated based on the country’s HCFC baseline. 
Secretariat’s recommendation 
The Secretariat recommends blanket approval for the request for enabling activities for HFC phase-down for India, at the level of funding indicated in section A2 of Table 1 above.
A3: Technical assistance to prepare a verification report on HCFC consumption
Project description
The Executive Committee requested relevant bilateral and implementing agencies to include in their respective work programme amendments for submission to the 88th meeting, funding for the preparation of verification reports on HCFC consumption for selected Article 5 countries. UNEP as the lead implementing agency is requesting funding for the verification for stage II of the HPMPs for Botswana, Djibouti, the Gambia, Guinea-Bissau, the Lao People’s Democratic Republic, Mongolia, Nepal, Nicaragua, Sao Tome and Principe and Zimbabwe.[footnoteRef:4] [4:  Decision 87/27 ] 

Secretariat’s comments
The Secretariat noted that the funding requested for these 10 countries was consistent with the funds approved for similar verifications in previous meetings. It further noted that the verification report has to be submitted at least 10 weeks prior to the applicable Executive Committee meeting where the next funding tranche for the HPMP is being sought.
Secretariat’s recommendation
The Secretariat recommends blanket approval for the preparation of verification reports for stage II of the HCFC phase-out management plans (HPMP) for Botswana, Djibouti, the Gambia, Guinea-Bissau, the Lao People’s Democratic Republic, Mongolia, Nepal, Nicaragua, Sao Tome and Principe, and Zimbabwe at the level of funding shown in section A3 of Table 1, on the understanding that the verification report should be submitted at least 10 weeks prior to the applicable Executive Committee meeting where the next funding tranche for the HPMP is being sought.
A4: Project preparation for the Kigali HFC implementation plans
Project description
UNEP submitted requests for the preparation of stage I of the KIPs for 10 Article 5 countries as lead implementing agency, and for three countries as cooperating implementing agency with UNDP as lead implementing agency for Chile and Fiji, and the World Bank for Viet Nam, as shown in section A4 of Table 1. UNDP as lead implementing agency for Chile and Fiji and as cooperating implementing agency for Cambodia and Grenada requested US $340,000, plus agency support costs of US $23,800;[footnoteRef:5] UNIDO as cooperating implementing agency for Lesotho, Malawi, Namibia, Rwanda, Sierra Leone, the Syrian Arab Republic, Uganda and Zambia requested US $354,000, plus agency support costs of US $24,780,[footnoteRef:6] and the World Bank as lead implementing agency for Viet Nam requested US $185,000, plus agency support costs of US $12,950, in their work programme amendments for 2021.  [5:  UNEP/OzL.Pro/ExCom/88/30]  [6:  UNEP/OzL.Pro/ExCom/88/32] 

Secretariat’s comments
In reviewing these requests, the Secretariat took into account the guidelines for the preparation of KIPs as contained in decision 87/50; the activities proposed for project preparation and their connection with enabling activities and other HFC-related projects in the relevant countries. The Secretariat noted that the funding requests are in line with decision 87/50, and that as lead implementing agency UNEP provided a description of the activities required for the preparation of overarching strategies for the KIPs for the 10 countries, using the format for requests for project preparation for KIPs. The submissions included estimates of imports of HFCs and HFC blends for all countries, activities for the project preparation including the development of overarching strategy; nation-wide survey with relevant stakeholders on HFC consumption, analysis of the use of HFCs and alternatives, including import and export statistics of ODS alternatives; consultation for strategy development on the introduction of Energy Efficient (EE) technologies in the market for seven countries (Malawi, Namibia, Rwanda, Sierra Leone, Syrian Arab Republic, Uganda, and Zambia); review of relevant national initiatives, policies, and regulations related to HCFC phase-out and HFC phase-down for four countries (Cambodia, Grenada, Malawi, and Namibia); and consultation meetings to finalize the overarching strategy with various stakeholders for all countries.[footnoteRef:7]  [7:  Decision 87/50] 

UNEP clarified that the project preparation for the overarching strategies for HFC phase-down for the 11 countries would draw on the activities implemented under the enabling activities, as these were the first actions associated with the phase-down of HFCs and had contributed to the ratification of the Kigali Amendment. 
Following this review, the Secretariat noted that all 13 countries for which UNEP requested funding for preparation of an HFC phase‑down management plan have ratified the Kigali Amendment;[footnoteRef:8] the countries have provided endorsement letters indicating their intention to take early action on HFC phase-down, and that the funding requested is in accordance with decision 87/50. [8:  Date of ratification (or acceptance) of the Kigali Amendment: Cambodia, 8 April 2021 A; Chile, 19 September 2017; Fiji, 16 June 2020; Grenada, 29 May 2018; Lesotho, 7 October 2019; Malawi, 21 November 2017; Namibia, 16 May 2019 A; Rwanda, 23 May 2017; Sierra Leone, 15 June 2020; the Syrian Arab Republic, 5 April 2021; Uganda, 21 June 2018; Viet Nam, 27 September 2019 A; and Zambia, 15 March 2021.] 

Secretariat’s recommendation
The Secretariat recommends blanket approval for project preparation for the Kigali HFC implementation plans for Cambodia, Chile, Fiji, Grenada, Lesotho, Malawi, Namibia, Rwanda, Sierra Leone, the Syrian Arab Republic, Uganda, Viet Nam, and Zambia at the level of funding shown in section A4 of Table 1.
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Annex I
INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:9] [9:  Data as at December 2020 are based on document UNEP/OzL.Pro/ExCom/88/12] 

Albania: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec‑01 & Nov‑02 & Jul‑05 
	151,200

	Phase II:
	Jul-06
	109,200

	Phase III:
	Apr-08
	109,200

	Phase IV:
	Jul-10
	109,200

	Phase V:
	Apr-12
	109,200

	Phase VI:
	May-14
	109,200

	Phase VII:
	May-16
	139,776

	Phase VIII:
	Nov-17
	139,776

	Phase IX:
	Dec-19
	139,776

		Total:
	1,116,528

	Amount requested for renewal (phase X) (US $):
	139,776

	Amount recommended for approval for phase X (US $): 
	139,776

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	139,776

	Date of approval of country programme:
	2003

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	6.0

	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.0

	Annex C, Group I (HCFCs)
	3.1

	Annex E (methyl bromide)
	0.0

		Total:
	3.1

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	2,752,153

	Amount disbursed (as at December 2020) (US $):
	2,279,609

	ODS to be phased out (as at July 2021) (ODP tonnes):
	72.4

	ODS phased out (as at December 2020) (ODP tonnes):
	71.8



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	716,932

	(b)
	Institutional strengthening:
	1,116,528

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	918,693

		Total:
	2,752,153

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase IX of the Institutional Strengthening (IS) project, the National Ozone Unit (NOU) of Albania implemented the revised ODS legislation. Article 7 and country programme data (including HFC consumption data) were submitted in a timely manner. The NOU coordinated activities under stages I and II of the HPMP. Several training sessions for service technicians and vocational schools were organized. Outreach materials and activities were produced and organized. Albania also celebrated World Ozone Day 2020, and participated in regional and global Montreal Protocol meetings. Of the 17 performance indicators proposed, 10 were fully achieved and 7 were partially achieved.
Plan of action
 The plan of action for the upcoming phase includes: continuing activities to adopt and implement legislation; building national capacity; monitoring and controlling the import and use of HCFCs and HFCs; facilitating access to alternative substances and technologies; continuing to train technicians in the RAC servicing sector, customs officers, and environment inspectors; supporting Albania’s compliance with Montreal Protocol obligations in partnership with public- and private-sector stakeholders; and conducting public awareness campaigns.
Benin: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-95
	50,000

	Phase II:
	Jul-99
	33,333

	Phase III:
	Mar-01
	33,333

	Phase IV:
	Jul-03
	43,333

	Phase V:
	Jul-06
	60,000

	Phase VI:
	Nov-08
	60,000

	Phase VII:
	Dec-10
	60,000

	Phase VIII:
	Dec-13
	60,000

	Phase IX:
	Nov-15
	85,000

	Phase X:
	Nov-17
	85,000

	Phase XI:
	Dec-19
	85,000

		Total:
	654,999

	Amount requested for renewal (phase XII) (US $):
	85,000

	Amount recommended for approval for phase XII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	23.8

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	13.49

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	13.49

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	2,642,926

	Amount disbursed (as at December 2020) (US $):
	2,359,295

	ODS to be phased out (as at July 2021) (ODP tonnes):
	80.0

	ODS phased out (as at December 2020) (ODP tonnes):
	75.2



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	578,027

	(b)
	Institutional strengthening:
	654,999

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,409,900

		Total:
	2,642,926

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase XI, the NOU of Benin submitted Article 7 and country programme data for 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Coordination meetings were held with the National Ozone Committee and with refrigerant importers and distributors. The NOU supervised the training of 556 RAC technicians and 203 enforcement officers. Information on the availability of HCFC alternatives, on ODS regulations and on decisions by the parties to the Montreal Protocol was disseminated to consumers and importers. Benin also celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. Of the 20 performance indicators proposed, 19 were fully achieved and one was partially achieved.
Plan of action
The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP; continuing to implement and enforce the HCFC licensing and quota system; providing information about annual quotas to importers; organizing meetings with refrigerant importers and distributors; finalizing the enabling activities project; and collecting data for timely reporting to the Ozone and Multilateral Fund Secretariats.
Bhutan: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-04 and Jul-05
	130,000

	Phase II:
	Nov-07
	60,000

	Phase III:
	Jul-09 & Jul-10
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Dec-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Jul-17
	85,000

	Phase VIII:
	May-19
	85,000

	Total:
	600,000

	Amount requested for renewal (phase IX) (US $):
	85,000

	Amount recommended for approval for phase IX (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2005

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

		Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.04

		Annex E, (methyl bromide)
	0.00

	Total:
	0.04

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,583,000

	Amount disbursed (as at December 2020) (US $):
	1,333,925

	ODS to be phased out (as at July 2021) (ODP tonnes):
	0.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.2



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	147,000

	(b)
	Institutional strengthening:
	600,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	836,000

		Total:
	1,583,000

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VIII, The NOU of Bhutan implemented and enforced the licensing and quota system for HCFC import/export and the licensing system for HFCs; provided regular training on the Montreal Protocol, the Kigali Amendment and enforcement activities to customs and other enforcement officers; implemented the Ozone Regulation to effectively monitor illegal trade of all ODS and HFCs; conducted workshops, in collaboration with UNEP, for technicians in the refrigeration and air-conditioning servicing sector in relation to the ratification of the Kigali Amendment; and coordinated the implementation of the HPMP. Of the 16 performance indicators proposed, 13 were fully achieved and three were partially achieved.
Plan of action
 The plan of action for the upcoming phase includes: focusing on continuous implementation of the HPMP and HFC phase-down; focusing on data collection and the quota system to meet HFC phase-down obligations; preparing for the monitoring of HFC consumption; preparing for additional enforcement to control HFCs; providing capacity-building for the servicing sector; and increasing the awareness of key stakeholders and market players.
Cameroon: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-93
	161,000

	Phase II:
	May-97
	107,000

	Phase III:
	Jul-99
	107,000

	Phase IV:
	Dec-03 & Dec-04
	139,532

	Phase V:
	Nov-05
	139,532

	Phase VI:
	Nov-07
	139,532

	Phase VII:
	Nov-09
	139,532

	Phase VIII:
	Nov-11
	139,532

	Phase IX:
	Dec-13
	139,532

	Phase X:
	Nov-15
	178,601

	Phase XI:
	Nov-17
	178,601

	Phase XII:
	Dec-19
	178,601

		Total:
	1,747,995

	Amount requested for renewal (phase XIII) (US $):
	178,601

	Amount recommended for approval for phase XIII (US $): 
	178,601

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	178,601

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2018

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	8.2

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	88.8

	(f)	Annex E (methyl bromide) (average 1995-1998)
	18.1

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	32.53

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	32.53

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	10,299,885

	Amount disbursed (as at December 2020) (US $):
	9,468,948

	ODS to be phased out (as at July 2021) (ODP tonnes):
	737.2

	ODS phased out (as at December 2020) (ODP tonnes):
	734.8



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	7,065,108

	(b)
	Institutional strengthening:
	1,747,995

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,486,782

		Total:
	10,299,885

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase XII, the NOU of Cameroon submitted Article 7 and country programme data for 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Coordination meetings were held with the National Ozone Committee and with the refrigeration association and importers. The Kigali amendment was ratified on 24 August 2021. The NOU also supervised the training of refrigeration and air-conditioning technicians and customs enforcement officers. Information on the availability of HCFC alternatives, on ODS regulations and on MOP decisions was disseminated to consumers and importers. Cameroon also celebrated International Ozone Day and participated in Montreal Protocol meetings. Of the 18 performance indicators proposed, 16 were fully achieved and two were partially achieved.
Plan of action
 The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP; continuing to implement the HCFC licensing and quota system, and providing information about annual quotas to importers; organizing annual stakeholder workshops to raise awareness on low-GWP HCFC alternatives; and collecting data for timely reporting to the Ozone and Multilateral Fund Secretariats.
Comoros: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-97
	27,800

	Phase II:
	Dec-00
	18,533

	Phase III:
	Apr-03
	24,093

	Phase IV:
	Apr-05
	60,000

	Phase V:
	Mar-07
	60,000

	Phase VI:
	Apr-09
	60,000

	Phase VII:
	Jul-11
	60,000

	Phase VIII:
	Jul-13
	60,000

	Phase IX:
	Nov-15
	85,000

	Phase X:
	Nov-17
	85,000

	Phase XI:
	Dec-19
	85,000

		Total:
	625,426

	Amount requested for renewal (phase XII) (US $):
	85,000

	Amount recommended for approval for phase XII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.1

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.05

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.05

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,456,426

	Amount disbursed (as at December 2020) (US $):
	1,309,130

	ODS to be phased out (as at July 2021) (ODP tonnes):
	2.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.4



Summary of activities and funds approved by the Executive Committee:

	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	75,000

	(b)
	Institutional strengthening:
	625,426

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	756,000

		Total:
	1,456,426

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase XI, Comoros submitted Article 7 and country programme data for 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Annual meetings were held with the National Ozone Committee. The NOU supervised the training of refrigeration and air-conditioning technicians, and customs enforcement officers. Information on the availability of HCFC alternatives, on ODS regulations and on MOP decisions was disseminated to consumers and importers. Comoros celebrated International Ozone Day and participated in network and Montreal Protocol meetings. Of the 19 performance indicators proposed, 17 were fully achieved, one was partially achieved and one was not achieved. 
Plan of action
The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP and the submission of stage II; continuing to implement the licensing and quota system for HCFCs and beginning to implement the HFC licensing system; organizing annual stakeholder workshops to raise awareness on low‑GWP HCFC alternatives; collecting gender-disaggregated data and taking the gender dimension into account in all activities; and collecting data for timely reporting to the Ozone and Multilateral Fund Secretariats.
Cook Islands: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-04 & Nov-06
	30,000

	Phase II:
	Nov-07 & Nov-09
	47,500

	Phase III:
	Dec-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	Dec-16
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	427,500

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2004

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.1

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.00

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.00

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	833,550

	Amount disbursed (as at December 2020) (US $):
	508,839

	ODS to be phased out (as at July 2021) (ODP tonnes):
	1.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	427,500

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	406,050

		Total:
	

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII, Cook Islands enforced the licensing system for HCFCs through monitoring of illegal trade; strengthened HFC trade controls based on recommendations from the verification of HCFC consumption; amended existing legislation; and undertook to control the import and export of HCFs as of January 2021, seeking to finalize the related regulation. The National Ozone Officer (NOO) worked in close collaboration with stakeholders to implement the Montreal Protocol and sustain compliance. Article 7 and country programme data were submitted to the Ozone and Multilateral Fund Secretariats. The NOU organized and delivered the World Ozone Day celebrations and participated in the regional network meetings. Of the 20 performance indicators proposed, 11 were fully achieved, six were partially achieved and three were not achieved.
Plan of action
 The plan of action for the upcoming phase includes: enforcing the HCFC and HCFC-based equipment ban and implementing the HFC licensing system, including the quota system; adopting and implementing individual HS codes (PACHS22) for HFCs and blends; submitting Article 7 and country programme data; engaging and coordinating with national stakeholders and the RAC association for the implementation of the HPMP; strengthening national capacity for the preparation of the HFC phase‑down; organizing World Ozone Day and developing awareness materials; and participating in meetings related to the Montreal Protocol. 
Micronesia (Federated States of): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	34,000

	Phase II:
	Jul-06 & Jul-09
	41,333

	Phase III:
	Jul-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	Dec-16
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	425,333

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.2

	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.09

	Annex E (methyl bromide)
	0.00

		Total:
	0.09

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	895,433

	Amount disbursed (as at December 2020) (US $):
	528,076

	ODS to be phased out (as at July 2021) (ODP tonnes):
	1.1

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



1.  Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	425,333

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	470,100

		Total:
	895,433

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII, Federated States of Micronesia sustained compliance through legislation, the licensing and quota system, monitoring and enforcement, capacity-building, the involvement of the RAC Association and awareness-raising activities. The ODS regulations were amended to expand their scope for controlling and monitoring HFC imports into the country and to establish the HFC licensing system, effective from February 2021. Article 7 and country programme data for 2019 and 2020 were reported to the Multilateral Fund and Ozone Secretariats. Of the 19 performance indicators proposed, 14 were fully achieved and five were partially achieved.
Plan of action
The plan of action for the upcoming phase includes: implementing the HCFC quota and licensing system and HFC licensing system, and setting up of the HFC quota system; adopting individual HS codes (PACHS22) for HFCs and blends in all States; submitting Article 7 and country programme data reports in a timely fashion; engaging the National Steering Committee and RAC Associations in the implementation of Montreal Protocol activities; coordinating with stakeholders for the implementation of the HPMP; organizing World Ozone Day celebrations and developing awareness materials; and participating in regional and international meetings. 

Guatemala: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jun-93
	172,000

	Phase II:
	May-97
	96,000

	Phase III:
	Jul-99
	96,000

	Phase IV:
	Dec-01
	96,000

	Phase V:
	Jul-04
	62,400

	Phase VI:
	Nov-07
	124,800

	Phase VII:
	Jul-10
	124,800

	Phase VIII:
	Jun-18
	159,744

		Total:
	931,744

	Amount requested for renewal (phase IX) (US $):
	159,744

	Amount recommended for approval for phase IX (US $): 
	159,744

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	159,744

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	8.3

	Annex E (methyl bromide) (average 1995-1998)
	400.7

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.0

	Annex C, Group I (HCFCs)
	4.0

	Annex E (methyl bromide)
	0.0

		Total:
	4.0

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	10,088,208

	Amount disbursed (as at December 2020) (US $):
	9,113,007

	ODS to be phased out (as at July 2021) (ODP tonnes):
	1,129.579006

	ODS phased out (as at December 2020) (ODP tonnes):
	1,117.9



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	6,882,044

	(b)
	Institutional strengthening:
	931,744

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,274,420

		Total:
	10,088,208

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase VIII, the NOO of Guatemala reported Article 7 and country programme data to the Multilateral Fund and Ozone Secretariats. The NOU coordinated HPMP activities and activities for the phase-out of methyl bromide. The NOO also coordinated ODS import/export controls with the General Direction of Customs and other enforcement authorities; conducted awareness-raising activities among ODS importers, suppliers, end-users and general public; and promoted good practices in refrigeration, technician certification and customs officer training. Guatemala also participated in meetings relating to the Montreal Protocol. Of the 29 performance indicators proposed, 25 were fully achieved, three were partially achieved and one was not achieved.
Plan of action
The plan of action for the upcoming phase includes: continuing to revise ODS legislation to fulfill the Kigali amendment requirements; strictly monitoring and controlling the imports and use of HCFCs/HFCs; and facilitating access to new alternative substances and technologies. The NOU will also promote ratification of the Kigali amendment and HFC phase-down; continue coordinating with customs for effective monitoring of international trade of controlled substances; engage stakeholders in HPMP implementation; and continue public awareness activities, as well as training of servicing technicians in the safe use of flammable refrigerants.
Namibia: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-95
	61,765

	Phase II:
	Jul-00
	41,177

	Phase III:
	Dec-03
	53,530

	Phase IV:
	Nov-05
	60,000

	Phase V:
	Nov-07
	60,000

	Phase VI:
	Nov-09
	60,000

	Phase VII:
	Apr-12
	60,000

	Phase VIII:
	Nov-14
	60,000

	Phase IX:
	Jul-17
	85,000

	Phase X:
	Dec-19
	85,000

		Total:
	626,472

	Amount requested for renewal (phase XI) (US $):
	85,000

	Amount recommended for approval for phase XI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	8.4

	Annex E, (methyl bromide) (average 1995-1998)
	0.8

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	o.74

	Annex E (methyl bromide)
	0.00

		Total:
	0.74

	Year of reported country programme implementation data:
	2020

	Summary of the project and country profile
	

	Amount approved for projects (as at July 2021) (US $):
	2,302,062

	Amount disbursed (as at December 2020) (US $):
	1,951,919

	ODS to be phased out (as at July 2021) (ODP tonnes):
	25.6

	ODS phased out (as at December 2020) (ODP tonnes):
	20.3



2. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,062,500

	(b)
	Institutional strengthening:
	626,472

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	613,090

		Total:
	2,302,062

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase X, The NOU of Namibia implemented ODS regulations through the enforcement of the licensing and quota system for HCFCs. The NOU completed the enabling activities project, embarked on an awareness programme, and conducted training for customs officers, clearing agents and refrigeration technicians and other stakeholders. The NOU assisted in amending the legislation to include control of HFC consumption in line with Kigali Amendment, which provided the opportunity to include an HFC licensing and quota system that is now operational. The NOU organized World Ozone Day and other awareness-raising activities, and conducted several training workshops and meetings using online platforms. Of the 16 performance indicators proposed, 15 were fully achieved and one was partially achieved.
Plan of action
The plan of action for the upcoming phase includes: continuing with the training programme for technicians in the refrigeration sector and customs officers/clearing agents for the enforcement of the ODS regulations; continuing the awareness-raising programme and the distribution of awareness materials to the industry and other stakeholders; continuing the timely submission of Article 7 and country programme implementation data to the Multilateral Fund and Ozone Secretariats; and attending regional and international meetings, workshops and events.
Paraguay: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Feb-97
	66,300

	Phase II:
	Dec-00
	44,200

	Phase III:
	Apr-03
	57,460

	Phase IV:
	Nov-07
	60,000

	Phase V:
	Jul-10
	60,000

	Phase VI:
	Apr-12
	60,000

	Phase VII:
	May-14
	60,000

	Phase VIII:
	Dec-16
	85,000

	Phase IX:
	Dec-18
	85,000

		Total:
	577,960

	Amount requested for renewal (phase X) (US $):
	85,000

	Amount recommended for approval for phase X(US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2021

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	18.0

	Annex E (methyl bromide)
	0.9

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	10.91

	Annex E (methyl bromide)
	0.00

		Total:
	10.91

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	4,210,637

	Amount disbursed (as at December 2020) (US $):
	3,341,267

	ODS to be phased out (as at July 2021) (ODP tonnes):
	345.1

	ODS phased out (as at December 2020) (ODP tonnes):
	340.4



3. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,588,524

	(b)
	Institutional strengthening:
	577,960

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,044,153

		Total:
	4,210,637

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Under phase IX, the NOU of Paraguay worked to achieve broad consensus on revised national ODS legislation. The NOU also submitted Article 7 and country programme implementation data in a timely manner for 2018, 2019 and 2020 to the Multilateral Fund and Ozone Secretariats. Several training sessions for service technicians and for customs officers were organized, and technical vocational schools were equipped with training equipment. The NOU produced several information and outreach materials and organized extensive World Ozone Day events in 2019 and 2020; organized the regional network meeting for Latin America in 2019 and participated in virtual network meetings. Of the 26 performance indicators proposed, 23 were fully achieved and three were partially achieved.
Plan of action
The plan of action for the upcoming tranche includes: continuing revision of ODS legislation in line with the Kigali Amendment; strictly monitoring and controlling the imports and use of HCFCs and HFCs, and facilitating access to and use of new alternative substances and technologies; continuing to coordination with customs to ensure effective surveillance of international trade; facilitating the involvement of main stakeholders; generating the mechanisms to reduce demand for equipment that works with HCFC; implementing a database of RAC technicians trained and certified in the handling of alternatives to HCFCs and HFCs; training servicing technicians in safety practices with flammable refrigerants; and continuing public awareness activities, especially with the education sector and with a gender focus, during the World Refrigeration Day, World Ozone Day celebrations and national events. 

Saint Vincent and the Grenadines: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-98
	30,300

	Phase II:
	Apr-04 & Apr-05
	43,130

	Phase III:
	Nov 06
	60,000

	Phase IV:
	Jul-09 & Dec-10
	60,000

	Phase V:
	Apr-12
	60,000

	Phase VI:
	Nov-14
	60,000

	Phase VII:
	Nov-17
	85,000

		Total:
	398,430

	Amount requested for renewal (phase VIII) (US $):
	85,000

	
Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.01

	Annex E (methyl bromide)
	0.00

		Total:
	0.01

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,348,354

	Amount disbursed (as at December 2020) (US $):
	1,063,097

	ODS to be phased out (as at July 2021) (ODP tonnes):
	2.3

	ODS phased out (as at December 2020) (ODP tonnes):
	2.2



4. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	252,115

	(b)
	Institutional strengthening:
	398,430

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	697,809

		Total:
	1,348,354

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII, the NOU of Saint Vincent and the Grenadines submitted 2020 country programme and Article 7 data despite challenges linked to the pandemic and the La Soufriere volcanic eruption. The NOU continued to promote low-GWP energy efficient technologies through information dissemination, and reviewed draft National Refrigerant Labelling Standards with support from the RAC Association and the National Steering Committee; conducted public awareness initiatives and provided training to servicing technicians in good practices and the use of alternative technologies. Of the 25 performance indicators proposed, 20 were fully achieved, five were partially achieved and five were not achieved. 
Plan of action
The plan of action for the upcoming phase includes: continuing to monitor and control the importation of refrigerants through testing and enforcement; continuing to develop national standards for the safe handling, transport and storage of refrigerants; implementing the revised regulations that include mandatory certification of technicians and the imposition of various fees including a licensing fee for all imports of non-ozone-friendly substances; and continuing public education and awareness activities. 
Senegal: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-93
	175,000

	Phase II:
	Nov-97
	117,000

	Phase III:
	Nov-99
	117,000

	Phase IV:
	Mar-02
	152,100

	Phase V:
	Dec-03
	152,100

	Phase VI:
	Nov-05
	152,100

	Phase VII:
	Nov-07
	152,100

	Phase VIII:
	Nov-09
	152,101

	Phase IX:
	Nov-11
	152,101

	Phase X:
	Dec-13
	152,101

	Phase XI:
	Nov-15
	194,689

	Phase XII:
	Nov-17
	194,689

	Phase XIII:
	Dec-19
	194,689

	Total:
	2,057,770

	Amount requested for renewal (phase XIV) (US $):
	194,689

	Amount recommended for approval for phase XIV (US $): 
	194,689

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	194,689

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	36.2

	(f)	Annex E (methyl bromide) (average 1995-1998)
	53.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	13.2

	(f)	Annex E (methyl bromide)
	0.0

	Total:
	13.2

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	4,496,195

	Amount disbursed (as at December 2020) (US $):
	3,929,827

	ODS to be phased out (as at July 2021) (ODP tonnes):
	196.3

	ODS phased out (as at December 2020) (ODP tonnes):
	148.1



5. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	747,945

	(b)
	Institutional strengthening:
	2,057,770

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,690,480

		Total:
	4,496,195

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Under phase XIII, the NOU of Senegal submitted Article 7 and country programme data to the Multilateral Fund and Ozone Secretariats. Coordination meetings were held with the National Ozone Committee and with industry association and RAC associations, and the NOU supervised the training of RAC technicians and customs and enforcement officers. Awareness activities were conducted, including the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on laws such as the control or ban of HCFC-based equipment, regulations and decisions by the Parties to the Montreal Protocol. Senegal celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. Of the 18 performance indicators proposed, 15 were fully achieved, two were partially achieved and one was not achieved. 
Plan of action
The plan of action for the upcoming phase includes: continuing information dissemination and awareness-raising; continuing implementation of the licensing and quota system for HCFCs and providing information about annual quotas to importers; beginning the technician certification programme; continuing monitoring and evaluation; organizing annual stakeholder workshops to raise awareness on low‑GWP HCFC alternatives; collecting and reporting data to the Ozone and Multilateral Fund Secretariats; and undertaking national communication on the country’s reasons for ratifying the Kigali Amendment.
Solomon Islands: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	20,250

	Phase II:
	Jul-06 & Nov-07
	36,833

	Phase III:
	Nov-09 & Apr-10
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Nov-17
	85,000

	Phase VIII:
	May-19
	85,000

		Total:
	467,083

	Amount requested for renewal (phase IX) (US $):
	85,000

	Amount recommended for approval for phase IX (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	2.0

		Annex E, (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.08

		Annex E, (methyl bromide)
	0.00

		Total:
	0.08

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	1,160,333

	Amount disbursed (as at December 2020) (US $):
	706,680

	ODS to be phased out (as at July 2021) (ODP tonnes):
	3.5

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	467,083

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	693,250

		Total:
	1,160,333

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase VIII, the NOU of the Solomon Islands helped develop an online system to enhance effectiveness in tracking and monitoring of trade of controlled substances including HFCs. The NOU submitted Article 7 and country programme data to the Ozone Secretariat and Multilateral Fund Secretariats, conducted awareness-raising activities, and engaged stakeholders, the National Steering Committee and the RAC Association. The NOU continued to follow up on the ratification of the Kigali Amendment and began drafting legislation to include the mandatory control of HFCs. The NOU participated in meetings of the Montreal Protocol. Of the 20 performance indicators proposed, 14 were fully achieved, three were partially achieved and three were not achieved.
Plan of action
The plan of action for the upcoming phase includes: enacting the Ozone Layer Protection Regulation that controls HCFCs and HFCs, as well as working to launch the electronic licensing system for both HCFCs and HFCs; continuing joint inspections with the Customs Department and Solomon Islands Refrigeration and Air-conditioning Association (SIRAC) to monitor ODS trade; coordination and supporting the National ODS Steering Committee and RAC Association in the implementation of Montreal Protocol activities; continuing to raise awareness and organize World Ozone Day; participating in relevant Montreal Protocol meetings; and supporting ratification of the Kigali Amendment.
Sudan: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	168,300

	Phase II:
	Jul-99
	112,200

	Phase III:
	Jul-01
	112,200

	Phase IV:
	Apr-04
	145,860

	Phase V:
	Jul-09
	109,395

	Phase VI:
	Dec-10
	145,860

	Phase VII:
	Apr-13
	145,860

	Phase VIII:
	Apr-13
	186,701

	Phase IX:
	Jun-18
	186,701

		Total:
	1,313,077

	Amount requested for renewal (phase X) (US $):
	186,701

	Amount recommended for approval for phase X (US $): 
	186,701

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	186,701

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan (stage I):
	2012

	Date of approval of HCFC phase-out management plan (stage II):
	2015

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	52.7

	(f)	Annex E (methyl bromide) (average 1995-1998)
	3.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	10.59

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	10.59

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	9,146,045

	Amount disbursed (as at December 2020) (US $):
	6,748,784

	ODS to be phased out (as at July 2021) (ODP tonnes):
	678.1

	ODS phased out (as at December 2020) (ODP tonnes):
	662.9



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	6,148,108

	(b)
	Institutional strengthening:
	1,313,077

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,684,860

		Total:
	9,146,045

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase IX, the NOU of Sudan made progress towards ratification of the Kigali Amendment. The NOU implemented ODS regulations through the enforcement of the HCFC licensing and quota system. Regulations have been revised to include an HFC licensing system and HFC import control, pending approval by the relevant authorities. The NOU conducted awareness-raising activities on the Montreal Protocol and Ozone Day celebrations, and trained refrigeration technicians in the safe handling of low‑GWP alternatives. The Steering Committee and the Refrigeration Association were involved in the implementation of the Montreal Protocol activities. Of the 16 performance indicators proposed, nine were fully achieved, five were partially achieved and two were not achieved. 
Plan of action
The plan of action for the upcoming phase includes: enforcing the import licensing and quota system more rigorously; conducting a training programme for technicians in the refrigeration sector; continuing to encourage ratification of the Kigali Amendment; continuing to train customs officers to support the implementation and enforcement of ODS regulations; continuing to follow-up on the approval of revised ODS regulations, which include an HFC licensing system; continuing the awareness-raising programme; continuing to submit Article 7 and country programme data to the Multilateral Fund and Ozone Secretariats; and participating in meetings, workshops and events related to the Montreal Protocol.
Timor-Leste: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-08
	40,000

	Phase II:
	Jul-10 & Jul-11
	60,000

	Phase III:
	Apr-13
	60,000

	Phase IV:
	May-16
	85,000

	Phase V:
	Dec-19
	85,000

		Total:
	330,000

	Amount requested for renewal (phase VI) (US $):
	85,000

	Amount recommended for approval for phase VI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2009

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2017

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.1

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.5

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.15

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.15

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	994,700

	Amount disbursed (as at December 2020) (US $):
	723,178

	ODS to be phased out (as at July 2021) (ODP tonnes):
	0.0

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	161,800

	(b)
	Institutional strengthening:
	330,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	502,900

		Total:
	994,700

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
During phase V, the NOU of Timor-Leste continued to enforce the licensing and quota system in accordance with the Decree-Law No. No. 36/2012; it further strengthened collaboration with the Directorate General for Customs to enforce the HCFC licensing and quota system through the National Single Window System under ASYCUDA, which integrates the risk profiling for ODS control. The NOU worked closely with the importers, customs brokers and the Directorate General for Customs to strengthen national data reconciliation and reporting procedures. Article 7 and country programme data for 2019 and 2020 were submitted to the Multilateral Fund and Ozone Secretariats. The NOO also worked closely with the Steering Committee and RAC industries; organized public awareness activities and joined meetings on the Montreal Protocol. The Government continued to work with national stakeholders on the ratification of the Kigali Amendment. Of the 18 performance indicators proposed, 15 were fully achieved and three were partially achieved.
Plan of action
The plan of action for the upcoming phase includes: strictly enforcing of HCFC licensing and quota system through the National Single Window System; implementing the HFC import and export licensing system after approval of an amendment to the existing Decree-law and the setting of HFC quota allocation criteria to be implemented from 1 January 2024; strengthening the monitoring and reporting of ODS import and export; conducting capacity-building activities for enforcement officers and refrigeration technicians; continuing to follow-up on the internal process for ratification of the Kigali Amendment; ensuring the continuity of the awareness programme and information exchange including the celebration of the World Ozone Day; and promoting international and regional cooperation on the implementation of the Montreal Protocol. 
Vanuatu: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	20,250

	Phase II:
	Apr-08 & Nov-09
	39,250

	Phase III:
	Dec-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	Dec-16
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	409,500

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2020

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.00

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.00

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	944,100

	Amount disbursed (as at December 2020) (US $):
	600,492

	ODS to be phased out (as at July 2021) (ODP tonnes):
	0.28

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



6. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	409,500

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	534,600

	
	Total:
	944,100

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII, the Government of Vanuatu strengthened its licensing and quota system by changing from an annual license to a per-shipment license. Actions were carried out to facilitate Kigali Amendment implementation, including the HFC licensing system in force since February 2020 under the new OLP Act. Vanuatu fulfilled its Article 7 and country programme data reporting obligations for 2019 and 2020. The NOO promoted and supported the implementation of the national RAC certification scheme; organized public awareness activities, organized World Ozone Day celebrations, and joined the meetings on the Montreal Protocol. Of the 18 performance indicators proposed, 15 indicators were fully achieved, two were partially achieved and one was not achieved.
Plan of action
The plan of action for the upcoming phase includes: effectively implementing the HCFC and HFC licensing system, and creating the HFC quota system; implementing individual HS codes (PACHS22) for HFCs and blends; submitting Article 7 and country programme data in a timely fashion; actively engaging national stakeholders and the RAC Association in the implementation of Montreal Protocol; organizing the World Ozone Day celebrations and developing awareness materials; and participating in regional and international meetings. Moreover, the phase will strengthen national capacity to support Vanuatu in preparing for HFC phase-down.
UNEP/OzL.Pro/ExCom/88/31/Rev.1
Annex II

UNEP/OzL.Pro/ExCom/88/31/Rev.1
Annex I

UNEP/OzL.Pro/ExCom/88/31/Rev.1
Annex I





12
13
Annex II 
DRAFT VIEWS EXPRESSED BY THE EXECUTIVE COMMITTEE ON THE RENEWAL OF INSTITUTIONAL STRENGTHENING PROJECTS SUBMITTED TO THE 88th MEETING

Albania
1. The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening (IS) project (phase IX) for Albania and noted with appreciation that the Government of Albania reported 2019 and 2020 data to the Ozone Secretariat indicating that the country is in compliance with the Montreal Protocol and country programme implementation data to the Fund Secretariat. The Committee noted that an operational ODS import/export licensing and HCFC quota system is in place, and that Albania also established an HFC licensing system. The Committee also noted with appreciation that the country has gained stakeholder support through steering committee and consultation meetings and raised the public awareness on the ozone layer protection. The Committee is therefore confident that Albania will continue implementing its HCFC phase-out management plan and institutional strengthening project in a timely and effective manner in order to prepare the country to meet and sustain the 67.5 per cent reduction in its baseline consumption of HCFCs in 2025.
Benin
The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening project for Benin (phase XI) and noted with appreciation that the Government of Benin reported 2019 and 2020 data to the Ozone Secretariat indicating that the country is in compliance with the Montreal Protocol and country programme implementation data to the Fund Secretariat. The Committee also noted that Benin has taken some significant steps to phase out its consumption of HCFCs in the current phase, in particular the implementation of ODS import controls through a licensing and quota system and the training of customs officers and refrigeration technicians. The Committee noted with appreciation that the country reached 35 per cent reduction in HCFC consumption in 2020 as per Montreal Protocol requirements. The Committee greatly appreciates the efforts of the Government of Benin to reduce HCFC consumption and is therefore hopeful that, within the next two years, Benin will continue the implementation of its IS project with outstanding success to achieve and sustain compliance with the Montreal Protocol.
Bhutan
The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening (IS) project for Bhutan (phase IX) and acknowledges with appreciation the efforts taken by the country for the development and implementation of the HFC licensing system, ratification of the Kigali Amendment and timely submission of Article 7 and country programme data reports. The Committee also notes with appreciation that the country maintains a robust licensing and quota system for HCFCs and is enforcing its import licensing system for HFCs, which enabled Bhutan to comply with its obligations during the reporting period. The Committee also notes that the HPMP is being implemented as planned, as the country reached the 35 per cent reduction target for 2020 and has successfully completed the implementation of the enabling activities project for HFC phase-down. The Committee is therefore confident that Bhutan will continue activities both at the project and policy levels to meet the future targets of the Montreal Protocol.
Cameroon
The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening project for Cameroon (phase XII) and noted with appreciation that Cameroon reported HCFC import data for 2020 under Article 7 and country programme reporting to the Ozone and Multilateral Fund Secretariats, indicating the country’s compliance with the Montreal Protocol. The Committee also noted that Cameroon has taken some significant steps to phase out its consumption of HCFCs in the current phase, in particular the implementation of ODS import controls through a licensing and quota system and the training of customs officers and refrigeration technicians. The Committee congratulated the Government of Cameroon for the ratification of the Kigali Amendment in August 2021. The Committee appreciated the efforts of the Government of Cameroon to reduce HCFC consumption and is therefore hopeful that, within the next two years, Cameroon will continue the implementation of its IS project successfully to achieve and sustain compliance with the Montreal Protocol.
Comoros
The Executive Committee reviewed the report presented with the request for the renewal of the Institutional Strengthening project for Comoros (phase XI) and noted with appreciation that Comoros reported HCFC import data for 2019 and 2020 under country programme and Article 7 reporting to the Ozone and Multilateral Fund Secretariats, indicating country’s compliance with the Montreal Protocol. The Committee also noted that Comoros has taken some significant steps to phase out its consumption of HCFCs, in particular the implementation of ODS import controls through a licensing and quota system and the training of customs officers and refrigeration technicians. The Committee noted with appreciation the establishment of the HFC licensing system in Comoros. The Committee further appreciated the efforts of the Government of Comoros to reduce HCFC consumption and is hopeful that, within the next two years, Comoros will continue the implementation of the IS project with outstanding success to achieve and sustain compliance with the Montreal Protocol.
Cook Islands
The Executive Committee reviewed the report presented with the request for the renewal of the Institutional Strengthening project for Cook Islands (phase VIII) and noted with appreciation that Cook Islands reported Article 7 and country programme data for 2019 and 2020 to the Ozone and Multilateral Fund Secretariats indicating that the country is in compliance with the Montreal Protocol phase-out requirements. The Committee acknowledged with appreciation that Cook Islands has maintained zero ODS consumption. The Committee also noted with appreciation the efforts of Cook Islands to use lessons learned from the verification of HCFC consumption to further enhance the licensing system to control HFC import and export as reflected in the legal amendment framework. The Committee is hopeful that, within the next two years, Cook Islands will continue the implementation of the IS project with outstanding success to achieve and sustain the compliance with the Montreal Protocol.
Micronesia (Federated States of)
The Executive Committee reviewed the report presented with the request for the renewal of the Institutional Strengthening project for the Federated States of Micronesia (phase VII) and noted with appreciation that the Federated States of Micronesia reported 2019 and 2020 data to the Ozone and Multilateral Fund Secretariat indicating that the country is in compliance with Montreal Protocol phase-out requirements. The Committee noted with appreciation the effective implementation of the licensing and quota system for HCFCs, the establishment of the HFC licensing system and coordination with relevant stakeholders. The Committee commended the Government of Federated States of Micronesia for achieving more than the 35 per cent HCFC consumption reduction in 2020. The Committee noted with appreciation the increased level of public awareness created to inform key stakeholders and the general public about HPMP phase‑out and Kigali Amendment obligations. The Committee is therefore hopeful that, within the next two years, the Government of Federated States of Micronesia will continue to effectively implement the new regulations to continue the implementation of the IS project with outstanding success to achieve and sustain the compliance with the Montreal Protocol.
Guatemala
The Executive Committee reviewed the report presented with the request for the Institutional Strengthening (IS) project for Guatemala (phase VIII) and noted with appreciation that the Government of Guatemala reported 2019 and 2020 data to the Ozone and Multilateral Fund Secretariats indicating that the country is in compliance with the Montreal Protocol. The Committee also noted that Guatemala has an operational ODS import/export licensing and HCFC quota system in place and has included HFCs in the licensing system. The Committee noted that Guatemala has successfully carried out public awareness and outreach activities on good refrigeration practices and the safe handling of flammable refrigerants to refrigeration technicians and end-users and has strengthened the relationship with the Refrigeration and Air Conditioning Association (ASFRIGUA). The Committee further noted that Guatemala is finalizing the enabling activities project to support the Kigali amendment ratification and has made significant progress towards ratification. The Committee is therefore confident that Guatemala will ratify the Kigali Amendment soon and will continue the implementation of the IS project with outstanding success to achieve and sustain compliance with the Montreal Protocol.
Namibia
The Executive Committee reviewed the report presented with the request for the renewal of the Institutional Strengthening (IS) project for Namibia (phase XI) and noted with appreciation that Namibia reported country programme and Article 7 data to the Fund and Ozone Secretariats on time, indicating that the country is in compliance with the Montreal Protocol and its Agreement with the Executive Committee. The Committee noted that Namibia has taken steps to address HCFC phase-out, including the implementation of a licensing and quota system for HCFCs, and the training of customs officers and refrigeration technicians. The Committee further noted with appreciation the ratification of the Kigali Amendment by the country in May 2019, with a commitment to early action on its implementation. The Committee is therefore confident that Namibia will continue its progressive reduction in HCFC consumption to achieve the 67.5 per cent target by 1 January 2025 and fulfil its other obligations under the Montreal Protocol.
Paraguay
The Executive Committee reviewed the report presented with the request for the Institutional Strengthening (IS) project for Paraguay (Phase X) and noted with appreciation that Paraguay has complied with its Article 7 data reporting and HCFC phase-out obligations under the Montreal Protocol, and that an operational ODS import/export licensing and HCFC quota system is in place and includes HFCs in the licensing system. The Committee further noted that Paraguay submitted country programme implementation data to the Secretariat in a timely manner. The Committee was pleased to note that the country has trained refrigeration technicians in good refrigeration practices and the safe handling of alternative substances, gained stakeholder’s support through the steering committee, and was committed to the formulation of norms and standards for the safe handling of alternative refrigerants. The Committee also noted that Paraguay carried out consultation meetings and raised public awareness on ozone layer protection. The Committee is therefore confident that Paraguay will continue implementing the IS project in an effective manner in order to meet the HCFC phase‑out targets by 2030 and in preparation for the HFC phase‑down.
Saint Vincent and the Grenadines
The Executive Committee reviewed the report submitted with the request for the institutional strengthening (IS) project for Saint Vincent and the Grenadines (phase VII) and noted with appreciation that the country has reported 2020 country programme implementation and Article 7 data to the Multilateral Fund and Ozone Secretariats in advance of the deadlines. The Committee acknowledged with appreciation that the Government of Saint Vincent and the Grenadines has a well-structured and operational HCFC licensing and quota system that includes the licensing of HFCs. The Committee noted with appreciation that the country has taken steps to initiate the ratification of the Kigali Amendment to the Montreal Protocol. The Committee also noted with appreciation the efforts made by the Government following the April 2021 La Soufriere Volcanic eruption. The Committee is therefore confident that the Government of Saint Vincent and the Grenadines will continue activities both at the policy and project levels to ensure that its annual HCFC consumption does not to exceed the maximum allowable consumption in the HPMP agreement with the Executive Committee, and the country will ratify the Kigali Amendment.
Senegal
The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening (IS) project for Senegal (phase XIV) and noted with appreciation that Senegal reported 2019 and 2020 data to the Ozone Secretariat indicating that the country is in compliance with the Montreal Protocol. The Committee further noted that Senegal has taken some significant steps to phase out its consumption of HCFCs in the period covered, namely the implementation of ODS import controls through a licensing and quota system and the training of customs officers and refrigeration technicians. The Committee appreciated the efforts of Senegal to reduce HCFC consumption and noted that the 35 per cent reduction in HCFC consumption was achieved in 2020 in accordance with Montreal Protocol requirements. The Committee is hopeful that, within the next two years, Senegal will continue with the implementation of its IS project with success to sustain compliance with the Montreal Protocol.
Solomon Islands
The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening (IS) project for the Solomon Islands (phase VIII) and noted with appreciation that the country is taking the necessary steps to meet the Montreal Protocol control measures related to HCFCs and HFCs. The Committee noted with appreciation that the country has reported 2019 and 2020 country programme implementation and Article 7 data to the Multilateral Fund and Ozone Secretariats. The Committee commended the Government of Solomon Islands for the development of a draft Ozone Layer Protection (OLP) bill that includes the mandatory control of HFCs and the transition to an electronic licensing and quota system. The Committee noted that Solomon Islands expedited project implementation despite challenges imposed by the Covid‑19 pandemic. The Committee also noted that the country complied with its 35 per cent reduction obligation under the Montreal Protocol in 2020. The Committee is hopeful that, in the upcoming phase of the IS project, the Government of Solomon Islands will complete the ratification of the Kigali Amendment, endorse the OLP Bill, and comply with the reporting requirements.
Sudan
The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening (IS)project for Sudan (phase X) and noted with appreciation that Sudan reported 2018, 2019 and 2020 country programme implementation and Article 7 data to the Multilateral Fund and Ozone Secretariats indicating that the country is in compliance with the Montreal Protocol. The Committee acknowledged that Sudan has an operational HCFC licensing and quota system, has carried out training of refrigeration technicians in the safe handling of low-GWP alternatives, and has conducted awareness-raising activities. The Committee acknowledged the efforts of the Government of Sudan and is therefore confident that Sudan will continue activities both at the policy and project levels to enable the country to reduce HCFC consumption and to achieve the 67.5 per cent reduction required under the Montreal Protocol by 1 January 2025. The Committee is also hopeful that the Kigali Amendment will be ratified in the next phase.
Timor-Leste
The Executive Committee reviewed the report presented with the request for the Institutional Strengthening (IS) project for Timor-Leste (phase VI) and noted with appreciation that the Government of Timor-Leste reported 2019 and 2020 data to the Ozone and Multilateral Fund Secretariats indicating that the country in compliance with the Montreal Protocol. The Committee also noted with appreciation that the country further strengthened its HCFC licensing and quota system through the National Single Window System, which enhanced the existing mechanism for effective data collection and reconciliation, as well as provided accurate data reporting. The Committee is hopeful that Timor-Leste will continue implementing its IS Project in a timely and effective manner and will soon ratify the Kigali Amendment.
Vanuatu
The Executive Committee reviewed the report presented with the request for the institutional strengthening (IS) project (phase VIII) for Vanuatu and noted with appreciation that Vanuatu reported 2019 and 2020 Article 7 and country programme data to the Ozone and Multilateral Fund Secretariats indicating that the country is in compliance with Montreal Protocol phase-out requirements. The Committee further noted and appreciated that Vanuatu has taken significant steps to sustain the phase-out of its HCFC consumption through training and capacity-building in key sectors such as law enforcement officials (including customs) and the training of RAC servicing technicians. The Committee appreciated the efforts of Vanuatu to enforce the HCFC licensing system and the ban on HCFC-based equipment, and to establish the HFC licensing system including mandatory control of HFC-based equipment. The Committee commended the Government of Vanuatu for achieving more than the 35 per cent reduction in HCFC consumption.
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