| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/4 6 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
 THE MULTILATERAL FUND FOR THE
 IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 4(b) of the provisional agenda

# report on balances and availability of resources

# Introduction

# This document presents a summary of financial adjustments indicated by the implementing agencies (IAs) and bilateral agencies (BAs), as agreed upon by the Secretariat. It includes statistical data from all projects with balances that have been held for over 12 months following project completion, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to relevant decisions (referred to as “by-decision” projects in this document) and project transfers. It also indicates the level of resources available to the Executive Committee in cash, as recorded in the Status of Contributions and Disbursements document, as required by decision 41/92(b), and presents a recommendation. The amounts held by IAs for complete and additional voluntary contributions projects are included in annex I and annex II, respectively. Annex III presents the funds returned by IAs and BAs from completed and by-decision projects.

# Funds to be returned to the 97th meeting

# The total funds to be returned by IAs and BAs amount to US $5,264,171 (i.e., US $5,197,904 by IAs and US $66,267 by BAs) from completed and by-decision projects, as shown in tables 1 and 2.

# Table 1. Funds to be returned by IAs to the 97th meeting (US $)

| Agency | Project cost | Agency support cost | Total cost |
| --- | --- | --- | --- |
| UNDP | 2,829,839 | 195,450 | 3,025,289 |
| UNEP* | 1,452,490 | 132,618 | 1,585,108 |
| UNIDO | 282,284 | 21,088 | 303,372 |
| World Bank* | 255,995 | 28,140 | 284,135 |
| Total | 4,820,608 | 377,296 | 5,197,904 |

* Includes the funds returned by UNEP, totalling US $124,300, along with agency support costs of US $16,159, and the World Bank's return of US $77,483, plus agency support costs of US $5,424.  The total amounts to be transferred to UNIDO, is outlined in table 4.

| Agency | Project cost | Agency support cost | Total |
| --- | --- | --- | --- |
| Germany | 58,643 | 7,624 | 66,267 |

Table 2. Funds to be returned by a BA to the 97th meeting (US $)

# Funds withheld by IAs

# The total funds withheld amount to US $6,994,293 by IAs, as shown in table 3.

Table 2. Balances of completed and additional voluntary contributions projects withheld by IAs (including agency support costs)

| Year completed | UNDP |  | UNIDO |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Number | US $ | Number | US $ | Number | US $ |
| Projects completed over two years ago |  |  |  |  |  |  |
| 2021 | 0 | 0 | 1 | 33,422 | 1 | 33,422 |
| 2022 | 5 | 198,729 | 3 | 84,045 | 8 | 282,774 |
| 1 Jan to 31 Oct 2023 | 5 | 106,656 | 1 | 8,485 | 6 | 115,141 |
| Sub-total | 10 | 305,385 | 5 | 125,952 | 15 | 431,337 |
| Projects completed less than two years ago |  |  |  |  |  |  |
| 1 Nov to 31 Dec 2023 | 12 | 822,651 | 8 | 1,199,261 | 20 | 2,021,912 |
| 2024 | 36 | 3,701,642 | 28 | 830,660 | 64 | 4,532,302 |
| Sub-total | 48 | 4,524,293 | 36 | 2,029,921 | 84 | 6,554,214 |
| Total | 58 | 4,829,678 | 41 | 2,155,873 | 99 | 6,985,551 |
| Additional voluntary contributions project |  |  |  |  |  |  |
|  | 1 | 8,742 |  |  | 1 | 8,742 |
| Grand total | 59 | 4,838,420 | 41 | 2,155,873 | 100 | 6,994,293 |

# Project transfer

# The Government of Armenia has requested the transfer of funds for the HCFC phase-out management plan (HPMP) (stage III, first tranche) and the Kigali HFC implementation plan (KIP) (stage I, first tranche) from UNEP to UNIDO.

# The Government of Guatemala has requested the transfer of funds for the renewal of the institutional strengthening project (phase X: 6/2024-5/2027) from UNEP to UNIDO.

# Additionally, the Government of Jordan has requested the transfer of the remaining balances of funds for the extension of the institutional strengthening project (phase XIII: 1/2019-12/2020) from the World Bank to UNIDO.

# Table 4 presents detailed information on the balances to be transferred. The Executive Committee may wish to approve these requests.

Table 4. Balances of projects for Armenia and Jordan to be transferred

| Project Title | Project No. | Return |  |  | Transfer |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | To Multilateral Fund |  |  | To Agency |  |  |
|  |  | From | Balance | PSC | To | Balance | PSC |
| Kigali HFC implementation plan (stage I, first tranche) | ARM/KIP/94/TAS/32 | UNEP | 66,000 | 8,580 | UNIDO | 66,000 | 8,580 |
| HCFC phase-out management plan (stage III, first tranche) | ARM/PHA/96/TAS/34 | UNEP | 58,300 | 7,579 | UNIDO | 58,300 | 4,081 |
| Renewal of the institutional strengthening project (phase X: 6/2024-5-2027) | GUA/SEV/94/INS/68 | UNEP | 330,670 | 0 | UNIDO | 330,670 | 23,147 |
| Extension of institutional strengthening project (phase XIII: 1/2019-12/2020) | JOR/SEV/82/INS/105 | World Bank | 77,483 | 5,424 | UNIDO | 77,483 | 5,424 |
| TOTAL |  |  | 532,453 | 21,583 |  | 532,453 | 41,232 |

Availability of resources

# The budget for the Multilateral Fund was approved at US $965 million for the 2024–2026 triennium, as decided by the Parties (decision XXXV/1). The Status of Contributions and Disbursements document indicates an available balance of US $642,928,645 as of 21 October 2025. The total balance returned by BAs and IAs to the 97th meeting amounts to US $4,974,538, excluding US $223,366 to be transferred to UNIDO. Therefore, the total level of resources available for approval at the 97th meeting is US $647,903,183.

# Secretariat’s comments

# The Secretariat reminded IAs that balances of projects completed one year ago and later, as well as by-decisions and additional voluntary contributions projects, should be returned to the Multilateral Fund as soon as possible.

# Considering that the total level of funding for projects and activities as submitted after review to the 97th meeting is US $108,014,129, there are sufficient resources available for approvals at the 97th meeting.

Recommendation

# The Executive Committee may wish:

## (a)	To note:

### The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/97/4;

### That the net level of funds being returned by the implementing agencies at the 97th meeting is US $4,974,538, consisting of US $2,829,839, plus agency support costs of US $195,450 from UNDP; US $1,328,190, plus agency support costs of US $116,459 from UNEP; US $282,284, plus agency support costs of US $21,088 from UNIDO; and US $178,512 plus agency support costs of US $22,716 from the World Bank;

### That UNDP held balances of US $305,385, including agency support costs, for 10 projects completed over two years previously; and US $8,742, including support costs for one “additional voluntary contributions project”;

### That UNIDO held balances of US $125,952, including agency support costs, for five projects completed over two years previously;

### That UNEP returns at the 97th meeting the balances for projects for Armenia in the amount of  US $124,300 plus agency support costs of US $16,159, consisting of:

### US $58,300, plus agency support costs of US $7,579 from the HCFC phase-out management plan (stage III, first tranche) (ARM/PHA/96/TAS/34);

### US $66,000, plus agency support costs of US $8,580 from the Kigali HFC implementation plan (stage I, first tranche) (ARM/KIP/94/TAS/32);

### That the World Bank returns at the 97th meeting the balance from the Extension of institutional strengthening project (phase XIII: 1/2019-12/2020) in the amount of US $77,483 plus agency support costs of US $5,424;

### That the Government of Germany returns US $66,267, including support costs for two completed projects;

## (b)	To request UNDP and UNIDO:

### To proceed with disbursement or to cancel committed funds that were not needed for completed projects and to return the associated balances at the 98th meeting;

### To proceed with disbursement or to cancel commitments for the projects completed over two years previously, and to return balances at the 98th meeting;

## (c)	To request UNDP to proceed with disbursement or return at the 98th meeting, the balances of the additional voluntary contributions project;

## (d)	To request the Treasurer:

### To offset against future UNEP approvals at the 97th meeting, a total of US $330,670 that had been allocated for the Renewal of the institutional strengthening project (phase X: 6/2024-5-2027) (GUA/SEV/94/INS/68);

### To transfer at the 97th meeting the funds returned or offset for the projects referred to in subparagraph (a)(v), (a)(vi) and (d)(i) to UNIDO for implementation, in the amount of US $532,453, plus agency support costs of US $41,232 consisting of:

### US $58,300, plus agency support costs of US $4,081, for the HCFC phase-out management plan for Armenia (stage III, first tranche) (ARM/PHA/96/TAS/34);

### US $66,000, plus agency support costs U$8,580, for the Kigali HFC implementation plan (stage I, first tranche) (ARM/KIP/94/TAS/32);

### US $330,670, plus agency support costs of US $23,147 for the Renewal of the institutional strengthening project (phase X: 6/2024-5-2027) (GUA/SEV/94/INS/68); and

### US $77,483 plus agency support costs of US $5,424 for the Extension of the institutional strengthening project (phase XIII: 1/2019-12/2020) (JOR/SEV/82/INS/105).

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2024 (US $) | Funds disbursed as of 97th meeting (US $) | Balances committed as per 97th meeting (US $) | Balances not-committed as per 97th meeting (US $) | Support cost on balances committed and not committed as per 97th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/79/INV/19 | HCFC phase-out management plan (stage II, first tranche) | Aug-22 | 450,000 | 403,483 | 46,517 |  | 3,256 |  |  |  |
| BGD/PHA/90/INV/59 | HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector) | Dec-24 | 1,967,866 | 1,678,655 | 289,211 |  | 20,245 |  |  |  |
| BZE/PHA/87/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 73,854 | 41,316 | 32,538 |  | 2,928 |  |  |  |
| COL/SEV/88/INS/115 | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) | Dec-23 | 352,768 | 340,514 | 12,254 |  | 858 |  |  |  |
| COS/KIP/87/PRP/63 | Preparation of Kigali HFC implementation plan | Dec-24 | 170,000 | 163,390 | 6,610 |  | 463 |  |  |  |
| COS/PHA/91/TAS/66 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Dec-24 | 30,000 | 26,159 | 3,841 |  | 346 |  |  |  |
| CUB/KIP/87/PRP/65 | Preparation of Kigali HFC implementation plan | Aug-24 | 170,000 | 154,279 | 15,721 |  | 1,100 |  |  |  |
| DOM/KIP/87/PRP/73 | Preparation of Kigali HFC implementation plan | Aug-24 | 190,000 | 174,370 | 15,630 |  | 1,094 |  |  |  |
| EGY/PHA/79/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | Dec-22 | 75,000 | 39,629 | 35,371 |  | 2,476 |  |  |  |
| EGY/PHA/84/INV/144 | HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector) | Dec-23 | 1,761,750 | 1,611,791 | 149,959 |  | 10,497 |  |  |  |
| ELS/PHA/87/INV/43 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 169,000 | 66,702 | 102,298 |  | 7,161 |  |  |  |
| GHA/KIP/87/PRP/51 | Preparation of Kigali HFC implementation plan | Aug-23 | 130,000 | 100,875 | 29,125 |  | 2,039 |  |  |  |
| GHA/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 459,820 | 451,580 | 8,240 |  | 577 |  |  |  |
| GRN/KIP/88/PRP/28 | Preparation of Kigali HFC implementation plan | Dec-24 | 40,000 | 14,163 | 25,837 |  | 1,809 |  |  |  |
| HAI/PHA/91/PRP/26 | Preparation of HCFC phase-out management plan (stage II) (Overarching) | Dec-24 | 30,000 | 22,767 | 7,233 |  | 506 |  |  |  |
| HAI/SEV/90/INS/25 | Extension of the institutional strengthening project (phase V: 7/2022-6/2024) | Dec-24 | 128,000 | 112,274 | 15,726 |  | 1,101 |  |  |  |
| IDS/PHA/81/INV/213 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-24 | 753,500 | 158,983 | 594,517 |  | 41,616 |  |  |  |
| IDS/PHA/87/PRP/216 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 90,000 | 85,929 | 4,071 |  | 285 |  |  |  |
| IDS/PHA/88/INV/217 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-24 | 627,086 | 0 | 627,086 |  | 43,896 |  |  |  |
| IDS/PHA/92/INV/220 | HCFC phase-out management plan (stage II, fourth tranche) | Dec-24 | 433,300 | 0 | 433,300 |  | 30,331 |  |  |  |
| IND/KIP/92/PRP/505 | Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries | Dec-24 | 30,000 | 1,501 | 28,499 |  | 1,995 |  |  |  |
| IND/PHA/86/TAS/482 | HCFC phase-out management plan (stage II, third tranche) (project management and monitoring) | Dec-24 | 800,000 | 0 | 800,000 |  | 56,000 |  |  |  |
| IRA/PHA/86/INV/243 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-24 | 576,090 | 551,597 | 24,493 |  | 1,714 |  |  |  |
| IRA/PHA/90/INV/262 | HCFC phase-out management plan (stage II, fourth tranche) (PMU) | Dec-23 | 92,000 | 69,877 | 22,123 |  | 1,549 |  |  |  |
| IRA/PHA/92/INV/264 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 93,017 | 0 | 93,017 |  | 6,511 |  |  |  |
| IRA/PHA/92/INV/265 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-23 | 145,255 | 0 | 145,255 |  | 10,168 |  |  |  |
| IRA/SEV/86/INS/249 | Extension of the institutional strengthening project (phase XIII: 4/2021-3/2023) | May-23 | 222,094 | 178,036 | 44,058 |  | 3,084 |  |  |  |
| KAM/KIP/88/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-23 | 35,000 | 24,973 | 10,027 |  | 702 |  |  |  |
| KAM/PHA/83/INV/36 | HCFC phase-out management plan (fourth tranche) | Dec-24 | 150,000 | 144,216 | 5,784 |  | 434 |  |  |  |
| LAO/KIP/87/PRP/39 | Preparation of Kigali HFC implementation plan | Dec-24 | 35,000 | 34,703 | 297 |  | 21 |  |  |  |
| LAO/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 107,000 | 88,847 | 18,153 |  | 1,634 |  |  |  |
| LEB/KIP/87/PRP/98 | Preparation of Kigali HFC implementation plan | Aug-24 | 190,000 | 186,114 | 3,886 |  | 272 |  |  |  |
| LEB/PHA/86/INV/97 | HCFC phase-out management plan (stage II, third tranche) (air-conditioning sector) | Dec-24 | 170,000 | 160,866 | 9,134 |  | 639 |  |  |  |
| LEB/SEV/86/INS/96 | Extension of the institutional strengthening project (phase XII: 4/2021-3/2023) | Dec-23 | 198,515 | 196,282 | 2,233 |  | 156 |  |  |  |
| MAL/PHA/87/PRP/189 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-24 | 90,000 | 77,729 | 12,271 |  | 859 |  |  |  |
| MAL/PHA/88/INV/193 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and management and coordination) | Dec-23 | 154,900 | 39,789 | 115,111 |  | 8,058 |  |  |  |
| MDV/KIP/87/PRP/36 | Preparation of Kigali HFC implementation plan | Dec-24 | 35,000 | 22,026 | 12,974 |  | 908 |  |  |  |
| MEX/FOA/90/PRP/198 | Preparation for HFC investment projects in the foam sector | Dec-24 | 80,000 | 76,065 | 3,935 |  | 275 |  |  |  |
| MEX/KIP/87/PRP/195 | Preparation of Kigali HFC implementation plan | Aug-23 | 85,000 | 76,433 | 8,567 |  | 600 |  |  |  |
| MEX/REF/92/INV/204 | Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima | Dec-24 | 136,500 | 112,605 | 23,895 |  | 2,151 |  |  |  |
| NEP/PHA/86/INV/41 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 90,000 | 73,239 | 16,761 |  | 1,508 |  |  |  |
| NIR/KIP/87/PRP/156 | Preparation of Kigali HFC implementation plan | Dec-24 | 137,000 | 121,589 | 15,411 |  | 1,079 |  |  |  |
| NIR/PHA/81/INV/147 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Dec-24 | 1,357,887 | 1,288,947 | 68,940 |  | 4,826 |  |  |  |
| NIR/PHA/81/TAS/148 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-22 | 1,077,113 | 1,063,456 | 13,657 |  | 956 |  |  |  |
| NIR/PHA/81/TAS/150 | HCFC phase-out management plan (stage II, first tranche) (project management and coordination) | Dec-22 | 165,000 | 90,146 | 74,854 |  | 5,240 |  |  |  |
| NIR/PHA/88/INV/163 | HCFC phase-out management plan (stage II, second tranche) (project management and coordination) | Dec-24 | 75,000 | 41,581 | 33,419 |  | 2,339 |  |  |  |
| PAK/SEV/87/INS/108 | Extension of the institutional strengthening project (phase XI: 7/2021-6/2023) | Jun-23 | 287,318 | 285,993 | 1,325 |  | 93 |  |  |  |
| PAN/KIP/87/PRP/53 | Preparation of Kigali HFC implementation plan | Jul-24 | 190,000 | 176,061 | 13,939 |  | 976 |  |  |  |
| SRL/SEV/91/INS/61 | Extension of the institutional strengthening project (phase XIV: 1/2023-12/2024) | Dec-24 | 236,796 | 234,222 | 2,574 |  | 180 |  |  |  |
| SWA/KIP/87/PRP/33 | Preparation of Kigali HFC implementation plan | Aug-23 | 30,000 | 13,397 | 16,603 |  | 1,162 |  |  |  |
| SWA/PHA/86/INV/31 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 50,000 | 49,044 | 956 |  | 86 |  |  |  |
| TLS/PHA/88/INV/24 | HCFC phase-out management plan (stage II, second tranche) | Dec-24 | 41,500 | 36,020 | 5,480 |  | 493 |  |  |  |
| TRI/KIP/87/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-24 | 190,000 | 145,057 | 44,943 |  | 3,146 |  |  |  |
| TRI/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 498,756 | 310,706 | 188,050 |  | 13,164 |  |  |  |
| URU/KIP/87/PRP/77 | Preparation of Kigali HFC implementation plan | Dec-24 | 190,000 | 80,724 | 109,276 |  | 7,649 |  |  |  |
| URU/PHA/86/INV/76 | HCFC phase-out management plan (stage III, first tranche) | Dec-24 | 350,601 | 328,657 | 21,944 |  | 1,536 |  |  |  |
| ZIM/KIP/91/PRP/66 | Preparation of a Kigali HFC implementation plan | Dec-24 | 51,000 | 21,468 | 29,532 |  | 2,067 |  |  |  |
| ZIM/PHA/86/INV/60 | HCFC phase-out management plan (stage II, first tranche) | Dec-22 | 100,000 | 84,671 | 15,329 |  | 1,073 |  |  |  |
| TOTAL UNDP |  |  |  |  | 4,511,791 |  | 317,887 |  |  |  |
| UNIDO |
| BAH/PHA/93/INV/46 | HCFC phase-out management plan (stage II, second tranche) | Dec-24 | 54,000 | 50,300 | 3,700 |  | 259 | 1 | 98 |  |
| BOL/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Aug-24 | 141,009 | 128,506 | 12,503 |  | 875 | 1 | 98 |  |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | Dec-24 | 1,472,175 | 1,470,636 | 1,539 |  | 108 | 1 | 98 |  |
| BRA/PHA/75/TAS/308 | HCFC phase-out management plan (stage II, first tranche) (project monitoring) | Dec-24 | 276,000 | 275,415 | 585 |  | 41 | 1 | 98 |  |
| BRA/PHA/82/INV/320 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector) | Dec-24 | 1,902,953 | 1,589,233 | 313,720 |  | 21,961 | 1 | 98 |  |
| BRA/PHA/88/INV/327 | HCFC phase-out management plan (stage II, fifth tranche) (commercial refrigeration and air-conditioning sector) | Dec-24 | 116,000 | 92,339 | 23,661 |  | 1,656 | 1 | 98 |  |
| CMR/KIP/88/PRP/49 | Preparation of Kigali HFC implementation plan | Dec-23 | 190,000 | 188,249 | 1,751 |  | 123 | 1 | 98 |  |
| CPR/PHA/88/INV/607 | HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan) | Dec-23 | 4,400,000 | 3,965,665 | 434,335 |  | 30,403 | 1 | 98 |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 60,409 | 59,491 |  | 5,354 | 1 | 98 |  |
| GAM/KIP/90/PRP/44 | Preparation of a Kigali HFC implementation plan | Dec-24 | 39,000 | 38,520 | 480 |  | 34 | 1 | 98 |  |
| GUA/KIP/94/PRP/69 | Preparation of a Kigali HFC implementation plan (stage I) | Dec-24 | 119,000 | 91,515 | 27,485 |  | 1,924 | 1 | 98 |  |
| HON/KIP/90/PRP/55 | Preparation of a Kigali HFC implementation plan | Dec-24 | 170,000 | 164,642 | 5,358 |  | 375 | 1 | 98 |  |
| IVC/PHA/84/PRP/47 | Preparation of a HCFC phase-out management plan (stage II) | Dec-24 | 20,000 | 16,024 | 3,976 |  | 278 | 1 | 98 |  |
| JOR/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination) | Dec-23 | 294,122 | 90,153 | 203,969 |  | 14,277 | 1 | 98 |  |
| JOR/PHA/92/PRP/115 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-24 | 35,000 | 34,988 | 12 |  | 1 | 1 | 98 |  |
| LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | Dec-23 | 943,094 | 713,112 | 229,982 |  | 16,099 | n.a. | n.a. |  |
| LIB/SEV/85/INS/44 | Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022) | Jun-23 | 174,164 | 166,234 | 7,930 |  | 555 | 1 | 98 |  |
| MEX/PHA/90/INV/200 | HCFC phase-out management plan (stage II, fourth tranche) (cleaning agent phase-out in refrigeration servicing sector and project implementation and monitoring) | Dec-24 | 1,612,350 | 1,567,895 | 44,455 |  | 3,112 | 1 | 98 |  |
| MEX/PHA/91/PRP/202 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-24 | 90,000 | 78,290 | 11,710 |  | 820 | 1 | 98 |  |
| MEX/PHA/92/INV/205 | Destruction of emissions of HFC-23 generated in the production of HCFC-22 in Quimobasicos (second tranche) | Jun-24 | 387,561 | 387,529 | 32 |  | 2 | 1 | 98 |  |
| MEX/PHA/92/INV/206 | HCFC phase-out management plan (stage II, fifth tranche) | Dec-24 | 450,600 | 284,533 | 166,067 |  | 11,625 | 1 | 98 |  |
| MOR/KIP/92/PRP/79 | Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR | Dec-24 | 30,000 | 29,564 | 436 |  | 31 | 1 | 98 |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 72,133 | 2,867 |  | 258 | 1 | 98 |  |
| NIC/PHA/86/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 100,092 | 98,549 | 1,543 |  | 108 | 1 | 98 |  |
| PAK/PHA/76/INV/94 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Dec-24 | 2,160,200 | 2,142,457 | 17,743 |  | 1,242 | 1 | 98 |  |
| PAK/PHA/83/INV/102 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | Dec-24 | 570,352 | 522,507 | 47,845 |  | 3,349 | 1 | 98 |  |
| PAK/PHA/83/TAS/100 | HCFC phase-out management plan (stage II, second tranche) (project management unit) | Dec-24 | 294,500 | 257,155 | 37,345 |  | 2,614 | 1 | 98 |  |
| PAK/PHA/90/INV/110 | HCFC phase-out management plan (stage II, fourth tranche) (domestic air-conditioner manufacturing sector) | Dec-24 | 161,340 | 159,458 | 1,882 |  | 132 | 1 | 98 |  |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | Dec-23 | 537,856 | 348,037 | 189,819 |  | 13,286 | 1 | 98 |  |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 273,894 | 235,967 | 37,927 |  | 2,655 | 1 | 98 |  |
| PRC/KIP/91/PRP/38 | Preparation of a Kigali HFC implementation plan | Dec-24 | 119,000 | 117,466 | 1,534 |  | 107 | 1 | 98 |  |
| RWA/KIP/88/PRP/38 | Preparation of Kigali HFC implementation plan | Dec-24 | 39,000 | 32,525 | 6,475 |  | 453 | 1 | 98 |  |
| SAU/REF/86/PRP/35 | Preparation of a HCFC phase-out management plan (stage II) (air-conditioning) | Dec-24 | 150,000 | 141,443 | 8,558 |  | 599 | 1 | 98 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 18,910 | 31,090 |  | 2,332 | 1 | 98 |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 4,977 | 15,023 |  | 1,052 | 1 | 98 |  |
| SIL/KIP/88/PRP/43 | Preparation of Kigali HFC implementation plan | Dec-24 | 39,000 | 39,048 | -48 |  | -3 | 1 | 98 |  |
| SIL/PHA/87/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 117,000 | 92,734 | 24,266 |  | 2,184 | 1 | 98 |  |
| SOA/PHA/91/INV/16 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring) | Dec-23 | 178,760 | 157,279 | 21,481 |  | 1,504 | 1 | 98 |  |
| SOM/PHA/88/PRP/17 | Preparation of HCFC phase-out management plan (stage II) (Overarching) | Dec-24 | 60,000 | 57,183 | 2,817 |  | 197 | 1 | 98 |  |
| TUR/KIP/90/PRP/113 | Preparation of a Kigali HFC implementation plan | Dec-24 | 120,000 | 108,742 | 11,258 |  | 788 | 1 | 98 |  |
| VEN/PHA/91/INV/137 | HCFC phase-out management plan (stage II, second tranche) (servicing sector) | Dec-24 | 261,444 | 260,972 | 472 |  | 33 | 1 | 98 |  |
| TOTAL UNIDO |  |  |  |  | 2,013,071 |  | 142,802 | 1 | 98 |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2024 (US $) | Funds disbursed as of 97th meeting (US $) | Balances committed as per 97th meeting (US $) | Balances not- committed as per 97th meeting (US $) | Support cost on balances committed and not-committed as per 97th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| FIJ/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 147,699 | 139,529 | 8,170 |  | 572 |  |  |
| TOTAL UNDP |  |  |  | 8,170 |  | 572 |  |  |

Annex III

DETAILS ON COMPLETED AND BY-DECISIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AND BILATERAL AGENCIES

| Code |  | Project title |  |  | Project costs returned (US $) | Agency support costs (US $) |  | Total (US $) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| ARG/SEV/82/INS/188 |  | Extension for institutional strengthening project (phase X: 1/2019-12/2020) |  |  |  | -8 |  | -8 |
| BRA/DES/72/DEM/305 |  | Pilot demonstration project on ODS waste management and disposal |  |  |  | -4 |  | -4 |
| BRA/PHA/82/INV/323 |  | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  |  | 530,731 | 37,151 |  | 567,882 |
| BRA/PHA/88/INV/326 |  | HCFC phase-out management plan (stage II, fifth tranche) (foam sector) |  |  | 1,194,264 | 83,598 |  | 1,277,862 |
| CHI/KIP/88/PRP/207 |  | Preparation of Kigali HFC implementation plan |  |  | 3,412 | 239 |  | 3,651 |
| CHI/PHA/81/INV/197 |  | HCFC phase-out management plan (stage II, second tranche) (foam sector) |  |  |  | -2,972 |  | -2,972 |
| CHI/PHA/85/INV/201 |  | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  |  | 42,181 | 2,952 |  | 45,133 |
| COL/KIP/87/PRP/110 |  | Preparation of Kigali HFC implementation plan |  |  | 1,988 | 139 |  | 2,127 |
| COL/PHA/84/TAS/108 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector, project management and monitoring) |  |  |  | -433 |  | -433 |
| COS/SEV/88/INS/64 |  | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) |  |  | 1,425 | 100 |  | 1,525 |
| CUB/SEV/90/INS/67 |  | Extension of institutional strengthening project (phase XII: 7/2022-6/2024) |  |  | 2,580 | 181 |  | 2,761 |
| GEO/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 7,352 | 662 |  | 8,013 |
| GHA/SEV/91/INS/54 |  | Extension of the institutional strengthening project (phase XV: 1/2023-12/2024) |  |  | 1,826 | 128 |  | 1,954 |
| IDS/SEV/90/INS/219 |  | Extension of institutional strengthening project (phase XIII: 7/2022-6/2024) |  |  | 5,812 | 407 |  | 6,219 |
| IND/PHA/86/INV/480 |  | HCFC phase-out management plan (stage II, third tranche) (polyurethane foam sector plan) |  |  | 641,013 | 44,871 |  | 685,884 |
| IND/PHA/87/PRP/487 |  | Preparation of HCFC phase-out management plan (stage III) (refrigeration sector) |  |  | 12,030 | 842 |  | 12,872 |
| JAM/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 1,586 | 143 |  | 1,729 |
| KYR/KIP/87/PRP/45 |  | Preparation of Kigali HFC implementation plan |  |  | 16,310 | 1,142 |  | 17,452 |
| KYR/PHA/90/TAS/47 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 30,000 | 2,700 |  | 32,700 |
| MAL/PHA/84/TAS/186 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 261,610 | 18,313 |  | 279,923 |
| MAL/PHA/84/TAS/187 |  | HCFC phase-out management plan (stage II, second tranche) (management and coordination) |  |  | 30,800 | 2,156 |  | 32,956 |
| MAL/SEV/88/INS/192 |  | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) |  |  | 3,218 | 225 |  | 3,443 |
| MEX/REF/90/PRP/199 |  | Preparation for replacement of HFC-134a with HC-290 refrigerant in the manufacturing of commercial refrigerators at Friocima |  |  | 1,088 | 76 |  | 1,164 |
| MOL/PHA/88/INV/45 |  | HCFC phase-out management plan (stage III, first tranche) |  |  | 18,010 | 1,261 |  | 19,271 |
| NIR/SEV/86/INS/155 |  | Extension of the institutional strengthening project (phase XI: 12/2020-11/2022) |  |  | 589 | 41 |  | 630 |
| PAR/KIP/87/PRP/42 |  | Preparation of Kigali HFC implementation plan |  |  | 2,803 | 196 |  | 2,999 |
| PER/KIP/87/PRP/59 |  | Preparation of Kigali HFC implementation plan |  |  | 4,075 | 285 |  | 4,360 |
| SRL/KIP/87/PRP/59 |  | Preparation of Kigali HFC implementation plan |  |  | 872 | 61 |  | 933 |
| TRI/SEV/88/INS/41 |  | Extension of the institutional strengthening project (phase XI: 12/2021-12/2023) |  |  | -313 | -22 |  | -335 |
| TUR/KIP/90/PRP/112 |  | Preparation of a Kigali HFC implementation plan |  |  | 12,540 | 878 |  | 13,417 |
| VEN/SEV/82/INS/136 |  | Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020) |  |  | 2,038 | 143 |  | 2,181 |
| Total completed projects |  |  |  |  | 2,829,839 | 195,450 |  | 3,025,289 |
| TOTAL UNDP |  |  |  |  | 2,829,839 | 195,450 |  | 3,025,289 |
| UNEP |  |  |  |  |  |  |  |  |
| ALB/SEV/88/INS/45 |  | Renewal of institutional strengthening project (phase X: 7/2022-6/2024) |  |  | 58 | 0 |  | 58 |
| ARM/KIP/87/PRP/27 |  | Preparation of Kigali HFC implementation plan |  |  | 1,311 | 170 |  | 1,481 |
| ARM/KIP/94/TAS/32 |  | Kigali HFC implementation plan (stage I, first tranche) |  |  | 66,000 | 5,247 |  | 71,247 |
| ARM/PHA/96/TAS/34 |  | HCFC phase-out management plan (stage III, first tranche) |  |  | 58,300 | 7,579 |  | 65,879 |
| BAH/PHA/93/TAS/45 |  | HCFC phase-out management plan (stage II, second tranche) |  |  | 1,324 | 172 |  | 1,496 |
| BEN/KIP/90/PRP/43 |  | Preparation of a Kigali HFC implementation plan |  |  | 26,111 | 3,394 |  | 29,505 |
| BHU/PHA/92/TAS/32 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 7,077 | 920 |  | 7,997 |
| BKF/PHA/84/PRP/42 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 20,000 | 2,600 |  | 22,600 |
| CHD/KIP/90/PRP/39 |  | Preparation of a Kigali HFC implementation plan |  |  | 11,590 | 1,507 |  | 13,097 |
| CHD/PHA/90/TAS/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 2,186 | 275 |  | 2,461 |
| COI/PHA/91/TAS/34 |  | Verification report on the implementation of stage I of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| DMI/PHA/62/TAS/19 |  | HCFC phase-out management plan (stage I, first tranche) |  |  | 4,450 | 579 |  | 5,029 |
| DMI/PHA/86/TAS/26 |  | Verification report on the implementation of stage I of the HCFC phase-out management plan |  |  | 875 | 114 |  | 989 |
| GBS/PHA/81/PRP/24 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 7,535 | 980 |  | 8,515 |
| GLO/SEV/93/TAS/368 |  | Compliance Assistance Programme: 2024 budget |  |  | 920,524 | 73,642 |  | 994,166 |
| GRN/KIP/88/PRP/29 |  | Preparation of Kigali HFC implementation plan |  |  | 6,429 | 836 |  | 7,265 |
| GUA/PHA/86/TAS/58 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | -3,535 | -460 |  | -3,995 |
| IND/PHA/82/TAS/476 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector plan) |  |  | 532 | 64 |  | 596 |
| IND/PHA/86/TAS/483 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector plan) |  |  | 4,989 | 604 |  | 5,593 |
| IRA/PHA/87/PRP/255 |  | Preparation of HCFC phase-out management plan (stage III) (Overarching) |  |  | 163 | 21 |  | 184 |
| IRQ/PHA/87/TAS/30 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 5,177 | 598 |  | 5,775 |
| KIR/PHA/85/TAS/16 |  | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) |  |  | 8,279 | 1,076 |  | 9,355 |
| KIR/SEV/87/INS/18 |  | Renewal of institutional strengthening project (phase VIII: 1/2022-12/2023) |  |  | 18,587 | 0 |  | 18,587 |
| LAO/KIP/87/PRP/40 |  | Preparation of Kigali HFC implementation plan |  |  | 1,058 | 138 |  | 1,196 |
| LAO/PHA/88/TAS/41 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 17,789 | 2,313 |  | 20,102 |
| LAO/SEV/91/INS/42 |  | Renewal of the institutional strengthening project (phase XI: 1/2023-12/2024) |  |  | 14 | 0 |  | 14 |
| MOL/PHA/88/TAS/46 |  | HCFC phase-out management plan (stage III, first tranche) |  |  | 5,725 | 744 |  | 6,469 |
| MON/PHA/88/TAS/34 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 1,552 | 202 |  | 1,754 |
| NEP/PHA/88/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 5,643 | 734 |  | 6,377 |
| NIC/KIP/93/TAS/55 |  | Kigali HFC implementation plan (stage I, first tranche) |  |  | 15,000 | 1,950 |  | 16,950 |
| PAK/PHA/83/TAS/101 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 390 | 51 |  | 441 |
| PAK/PHA/88/TAS/109 |  | HCFC phase-out management plan (stage II, third tranche) |  |  | 2,596 | 337 |  | 2,933 |
| PAR/PHA/87/TAS/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 25 | 3 |  | 28 |
| PAR/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 6,518 | 847 |  | 7,365 |
| PAR/SEV/88/INS/44 |  | Extension of institutional strengthening project (phase X: 12/2021-11/2023) |  |  | 3,382 | 0 |  | 3,382 |
| PER/SEV/80/INS/56 |  | Renewal of institutional strengthening project (phase V: 1/2018-12/2019) |  |  | -4,138 | 0 |  | -4,138 |
| PRC/KIP/91/PRP/37 |  | Preparation of a Kigali HFC implementation plan |  |  | 31,137 | 4,048 |  | 35,185 |
| PRC/PHA/81/PRP/33 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 20 | 3 |  | 23 |
| QAT/PHA/88/TAS/27 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 4,600 | 598 |  | 5,198 |
| RWA/PHA/91/TAS/39 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 10 | 1 |  | 11 |
| SAM/PHA/92/TAS/28 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 17,279 | 2,246 |  | 19,525 |
| SEN/KIP/87/PRP/44 |  | Preparation of Kigali HFC implementation plan |  |  | 22,395 | 2,911 |  | 25,306 |
| SEY/KIP/90/PRP/28 |  | Preparation of a Kigali HFC implementation plan |  |  | 9,800 | 1,274 |  | 11,074 |
| SOI/PHA/92/TAS/20 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 15,737 | 2,046 |  | 17,783 |
| STL/KIP/91/PRP/36 |  | Preparation of a Kigali HFC implementation plan |  |  | 31,106 | 4,044 |  | 35,150 |
| SUR/PHA/92/TAS/33 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 13,500 | 1,755 |  | 15,255 |
| SUR/SEV/77/INS/25 |  | Extension of the institutional strengthening project (phase VI: 12/2016-11/2018) |  |  | 18,773 | 0 |  | 18,773 |
| TLS/SEV/88/INS/22 |  | Extension of institutional strengthening (phase VI: 7/2022-6/2024) |  |  | 14,955 | 0 |  | 14,955 |
| TOG/KIP/90/PRP/39 |  | Preparation of a Kigali HFC implementation plan |  |  | 19,256 | 2,503 |  | 21,759 |
| TON/PHA/92/TAS/20 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 17,133 | 2,227 |  | 19,360 |
| TTR/PHA/92/TAS/20 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 12,759 | 1,659 |  | 14,418 |
| UGA/PHA/91/TAS/34 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| ZIM/KIP/91/PRP/65 |  | Preparation of a Kigali HFC implementation plan |  |  | 105 | 14 |  | 119 |
| Total completed projects |  |  |  |  | 1,452,490 | 132,618 |  | 1,585,108 |
| TOTAL UNEP |  |  |  |  | 1,452,490 | 132,618 |  | 1,585,108 |
| UNIDO |  |  |  |  |  |  |  |  |
| ALB/KIP/87/PRP/43 |  | Preparation of Kigali HFC implementation plan |  |  | 2,378 | 167 |  | 2,545 |
| BAH/PHA/88/INV/43 |  | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration foam and spray foam sector - umbrella project) |  |  | 148 | 10 |  | 158 |
| BEN/KIP/90/PRP/42 |  | Preparation of a Kigali HFC implementation plan |  |  | 1,633 | 114 |  | 1,747 |
| ECU/REF/91/INV/81 |  | Conversion of the manufacturing of domestic and commercial refrigerators from HFC-134a to isobutane (R-600a) and propane (R-290) at Induglob |  |  | 213 | 15 |  | 228 |
| EGY/PHA/84/INV/141 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector and project management unit) |  |  | 2,880 | 202 |  | 3,082 |
| EGY/PHA/88/INV/150 |  | HCFC phase-out management plan (stage II, third tranche) (enabling activities in the refrigeration and air-conditioning sector) |  |  | 1,231 | 86 |  | 1,317 |
| GAB/PHA/84/PRP/38 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 1,818 | 127 |  | 1,945 |
| GUA/PHA/91/TAS/61 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 111 | 10 |  | 121 |
| IVC/PHA/84/INV/45 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 11,628 | 814 |  | 12,442 |
| JOR/PHA/88/PRP/111 |  | Preparation of HCFC phase-out management plan (stage III) (Overarching) |  |  | 573 | 40 |  | 613 |
| LES/KIP/88/PRP/28 |  | Preparation of a Kigali HFC implementation plan |  |  | 1,291 | 90 |  | 1,381 |
| MOG/KIP/87/PRP/17 |  | Preparation of Kigali HFC implementation plan |  |  | 1,602 | 112 |  | 1,714 |
| NIR/KIP/87/PRP/158 |  | Preparation of Kigali HFC implementation plan |  |  | 3,190 | 223 |  | 3,413 |
| PAK/PHA/83/INV/99 |  | HCFC phase-out management plan (stage II, second tranche) (domestic air-conditioning sector) |  |  | 267 | 20 |  | 287 |
| SEN/KIP/87/PRP/45 |  | Preparation of Kigali HFC implementation plan |  |  | 3,879 | 272 |  | 4,151 |
| SOM/PHA/88/INV/16 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 5,506 | 385 |  | 5,891 |
| SUR/PHA/92/INV/32 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 1,064 | 96 |  | 1,160 |
| TKM/SEV/90/INS/20 |  | Extension of the institutional strengthening project (phase VI: 1/2023-12/2024) |  |  | 6 | 0 |  | 6 |
| TOG/KIP/90/PRP/38 |  | Preparation of a Kigali HFC implementation plan |  |  | 1,012 | 88 |  | 1,100 |
| TUN/KIP/88/PRP/80 |  | Preparation of Kigali HFC implementation plan |  |  | 4,694 | 329 |  | 5,023 |
| TUN/PHA/84/INV/75 |  | HCFC phase-out management plan (stage II, first tranche) (foam sector) |  |  | 879 | 61 |  | 940 |
| TUN/SEV/84/INS/77 |  | Extension of institutional strengthening project (phase IX: 1/2020-12/2021) |  |  | 455 | 31 |  | 486 |
| YUG/SEV/84/INS/53 |  | Extension of institutional strengthening project (phase VII: 12/2019-11/2021) |  |  | 10,559 | 739 |  | 11,298 |
| ZAM/PHA/86/INV/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 339 | 31 |  | 370 |
| Total completed projects |  |  |  |  | 57,356 | 4,062 |  | 61,418 |
| JOR/REF/81/INV/103 |  | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co. |  |  | 113,044 | 7,913 |  | 120,957 |
| NIC/EEF/93/DEM/56 |  | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) |  |  | 64,039 | 5,764 |  | 69,803 |
| NIC/DES/93/PRP/53 |  | Preparation of national inventory of banks of waste controlled substances and development of a national plan for management of these substances |  |  | 47,844 | 3,349 |  | 51,193 |
| Total “by-decision” projects |  |  |  |  | 224,928 | 17,026 |  | 241,954 |
| TOTAL UNIDO |  |  |  |  | 282,284 | 21,088 |  | 303,372 |
| WORLD BANK |  |  |  |  |  |  |  |  |
| GLO/SEV/93/TAS/366 |  | Core unit budget (2024) |  |  | 0 | 10,220 |  | 10,220 |
| JOR/PHA/91/INV/113 |  | HCFC phase-out management plan (stage II, third tranche) |  |  | 178,512 | 12,496 |  | 191,008 |
| JOR/SEV/82/INS/105 |  | Extension of institutional strengthening project (phase XIII: 1/2019-12/2020) |  |  | 77,483 | 5,424 |  | 82,907 |
| TOTAL WORLD BANK |  |  |  |  | 255,995 | 28,140 |  | 284,135 |
| GERMANY |  |  |  |  |  |  |  |  |
| EGY/PHA/84/INV/142 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 28,643 | 3,724 |  | 32,367 |
| KEN/EEF/93/PRP/68 |  | Preparation for a pilot project on energy efficiency (decision 91/65) |  |  | 30,000 | 3,900 |  | 33,900 |
| TOTAL GERMANY |  |  |  |  | 58,643 | 7,624 |  | 66,267 |

UNEP/OzL.Pro/ExCom/97/1

The data presented are based on the reporting format that has been developed pursuant to decision 31/2.

UNEP/OzL.Pro/ExCom/97/3

Outstanding obligations to be paid, funds will be returned with the next balance list.