| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/80/18 10 October 2017 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eightieth Meeting

Montreal, 13-17 November 2017

UNDP BUSINESS PLAN FOR 2018-2020

# This document presents the UNDP business plan for 2018-2020 and includes: the planned activities for the phase-out of ozone-depleting substances (ODS) during the 2018-2020 period; the business plan performance indicators; and recommendations for consideration by the Executive Committee. The narrative of UNDP’s business plan for 2018-2020 is attached to the present document.

Planned activities during 2018-2020

# Table 1 sets out, by year, the value of activities included in UNDP’s business plan.

Table 1: Resource allocation in the UNDP business plan for 2018-2020 as submitted (US $000s)*

|  | 2018 | 2019 | 2020 | Total (2018-2020) | Total after 2020 |
| --- | --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 50,264 | 26,339 | 38,426 | 115,028 | 53,355 |
| HCFC production - stage I | 0 | 2,000 | 2,000 | 4,000 | 10,000 |
| HPMP stage I | 0 | 0 | 107 | 107 | 107 |
| HPMP stage I - additional funding | 96 | 328 | 0 | 424 | 0 |
| HPMP PRP - stage II | 411 | 10 | 0 | 421 | 0 |
| HPMP stage II | 3,352 | 7,839 | 4,385 | 15,577 | 8,987 |
| HPMP PRP - stage III | 420 | 80 | 0 | 500 | 0 |
| HPMP stage III | 0 | 0 | 10,621 | 10,621 | 175,221 |
| Required for compliance subtotal | 54,542 | 36,596 | 55,539 | 146,678 | 247,670 |
| HFC activities |  |  |  |  |  |
| HFC - demonstration | 2,800 | 0 | 0 | 2,800 | 0 |
| HFC - enabling activities | 3,079 | 0 | 0 | 3,079 | 0 |
| HFC - investment | 600 | 5,885 | 2,140 | 8,625 | 0 |
| HFC activities subtotal | 6,479 | 5,885 | 2,140 | 14,504 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 4,305 | 2,082 | 4,304 | 10,691 | 0 |
| Core unit | 2,084 | 2,098 | 2,113 | 6,295 | 0 |
| Standard activities subtotal | 6,388 | 4,181 | 6,418 | 16,987 | 0 |
| Grand total | 67,410 | 46,662 | 64,097 | 178,169 | 247,670 |

* Including agency support cost where applicable.

# Additional information on some of the proposed activities is provided below.

HCFC production– stage I

# A total of US $14 million (including US $4 million for the period of 2018 to 2020) is included for stage I of the HCFC production phase-out management plan (HPPMP) in India that is currently not eligible.

# HPMP stage I

# UNDP included activities for Mauritania, for which stage I of the HPMP has not yet been approved, amounting to US $214,000 including US $107,000 for the period 2018 to 2020. The HPMP for Mauritania has been submitted to the 80th meeting.

# UNDP also included additional projects for stage I of HPMPs for Costa Rica, Cuba and Paraguay, amounting to US $424,297 for the period of 2018 to 2020. These requests fall under different decisions of the Executive Committee that allow these countries to submit additional projects during the implementation of stage I.

# HPMP stage II

# The total levels of funding for stage II of HPMPs in low-volume-consuming (LVC) countries to reach a 35 per cent reduction in HCFC baseline consumption amount to US $67,000 for the period after 2020, and to reach a 67.5 per cent reduction amount to US $3.2 million (including US $1.5 million for the period of 2018 to 2020).

# The funding distribution of stage II of HPMPs for non-LVC countries by sector is provided in Table 2.

Table 2: Funding distribution of stage II of HPMPs in non-LVC countries by sector (US $000)

| Sector | 2018-2020 | After 2020 | Total | Per cent of total (%) |
| --- | --- | --- | --- | --- |
| Foam | 2,000 | 0 | 2,000 | 9.4 |
| Refrigeration air-conditioning and servicing | 5,805 | 645 | 6,450 | 30.3 |
| Refrigeration manufacturing and servicing | 5,106 | 4,412 | 9,518 | 44.8 |
| Refrigeration servicing | 1,159 | 2,127 | 3,287 | 15.5 |
| Total | 14,071 | 7,185 | 21,255 | 100.0 |

HFC-related activities

# HFC activities include enabling activities (US $3.08 million in 2018 for 16 countries); technology demonstration of HFC-23 by-product conversion (US $2.8 million in 2018 for China); and investment activities (US $8.6 million in 2018 for China, the Dominican Republic, Egypt and Zimbabwe).

# One of the pre-requisites for including an HFC activity in a business plan is a letter of intention/endorsement from the government concerned. UNDP has submitted all the required letters for these activities.

Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent that has been agreed to-date.

Proposed adjustments by the Secretariat

# During the IACM, adjustments to the business plans of bilateral and implementing agencies were agreed based on relevant decisions of the Executive Committee. In reviewing the revised UNDP business plan for 2018-2020, the Secretariat noted that the following adjustments were not included:

Table 3: Adjustments to the UNDP business plan for 2018-2020 (US $000)

| Adjustment | 2018-2020 | After 2020 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the agreements | -642 | 856 |
| New HPMP activities (stages I and II) with submissions to the 80th meeting to match the proposed funding level as originally submitted | -1,456 | -279 |
| Project preparation for stages II and III of HPMPs pursuant to decision 71/42 | -290 | 290 |
| Stage II of HPMPs in LVC countries to the maximum allowable value to achieve 67.5 per cent reduction in the HCFC baseline consumption based on decision 74/50(c)(xii) | -46 | 0 |
| Institutional strengthening pursuant to decision 74/51(c) | -14 | 0 |
| HFC enabling activities as per decision 79/46(c) or submitted to the 80th meeting | -1,581 | 0 |
| Stage I of HPPMP | -4,000 | -10,000 |
| Stage II of HPMPs in non-LVC countries with the refrigeration air-conditioning sector based on a maximum cost-effectiveness of US $8.40/kg | -3,810 | -416 |
| Stage III of HPMPs in non-LVC countries with the refrigeration servicing sector based on a maximum cost-effectiveness of US $4.80/kg based on decision 74/50(c)(xiii) | -0.236 | -0.031 |
| Stage III of HPMPs in non-LVC countries with the industrial and commercial refrigeration and air-conditioning (ICR) sector based on a maximum cost-effectiveness of US $8.40/kg | 0 | -59,700 |
| Stage III of HPMP in non-LVC countries based on completion year of stage II | -10,000 | 10,000 |

# Table 4 presents the results of the Secretariat’s proposed adjustments to the UNDP business plan for 2018-2020, which are also addressed in the context of the Consolidated business plan of the Multilateral Fund for 2018-2020.

Table 4: Resource allocation in UNDP’s adjusted business plan for 2018-2020 (US $000s)*

|  | 2018 | 2019 | 2020 | Total (2018-2020) | Total after 2020 |
| --- | --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |  |
| Approved HPMPs | 50,264 | 26,339 | 37,784 | 114,386 | 54,211 |
| HCFC production - stage I | 0 | 0 | 0 | 0 | 0 |
| HPMP stage I | 0 | 0 | 173 | 173 | 299 |
| HPMP stage I - additional funding | 96 | 328 | 0 | 424 | 0 |
| HPMP PRP - stage II | 410 | 10 | 0 | 420 | 0 |
| HPMP stage II | 1,238 | 5,839 | 3,120 | 10,197 | 8,100 |
| HPMP PRP - stage III | 130 | 80 | 0 | 210 | 290 |
| HPMP stage III | 0 | 0 | 621 | 621 | 125,520 |
| Required for compliance subtotal | 52,138 | 32,596 | 41,698 | 126,433 | 188,421 |
| HFC activities |  |  |  |  |  |
| HFC - demonstration | 2,800 | 0 | 0 | 2,800 | 0 |
| HFC - enabling activities | 1,499 | 0 | 0 | 1,499 | 0 |
| HFC - investment | 600 | 5,885 | 2,140 | 8,625 | 0 |
| HFC activities subtotal | 4,899 | 5,885 | 2,140 | 12,924 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 4,305 | 2,069 | 4,304 | 10,678 | 0 |
| Core unit | 2,084 | 2,098 | 2,113 | 6,295 | 0 |
| Standard activities subtotal | 6,388 | 4,167 | 6,418 | 16,973 | 0 |
| Grand total | 63,426 | 42,648 | 50,256 | 156,330 | 188,421 |

* Including agency support cost where applicable.

Performance indicators

# UNDP submitted performance indicators pursuant to decision 71/28 in its business plan narrative. After several discussions, UNDP and the Secretariat agreed on the targets as shown in Table 5.

Table 5: Performance indicators for UNDP

| Type of indicator | Short title | Calculation | 2018 target |
| --- | --- | --- | --- |
| Planning--Approval | Tranches approved | Number of tranches approved vs. those planned* | 23 |
| Planning--Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities)** | 43 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $31,295,677 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans | 756.2 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 4 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 70% of those due |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | On time |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another cooperating or lead agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

RECOMMENDATIONS

# The Executive Committee may wish:

## To note the UNDP business plan for 2018-2020 contained in document UNEP/OzL.Pro/ExCom/80/18; and

## To approve the performance indicators for UNDP as set out in Table 5 of document UNEP/OzL.Pro/ExCom/80/18.

Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol

UNDP 2018 Business Plan Narrative

80th Meeting, 13-17 November 2017, Montreal

##### I. Introduction

The 2018-2020 UNDP Business Plan for the Multilateral Fund for the Montreal Protocol provides the Executive Committee with estimates of the funding levels needed to achieve the 2020 and 2025 control measures for HCFCs, the enabling activities required by Parties for the early ratification of the Kigali Amendment, and the stand-alone investment projects that will support the early phase-down of HFCs.  This narrative is based on an excel table that is included as Annex 1 to this report. The excel table lists all the ongoing and planned UNDP activities for which funding is expected during the period 2018 through 2020. Figures are also provided for the years 2020-2030, which are mainly related to Stage I HPMP approvals, preparation funds for Stage II, and Stage II HPMP proposals.  In addition, tentative estimates were included for Stage III HPMPs in China and India in 2020 and beyond as well.

It should also be noted that planned activities included in the 2018 column are relatively firm, while future years are indicative and are provided for planning purposes only.

In preparing this business plan, the relevant Executive Committee decisions on Business Planning, Stage I and Stage II HPMPs, HCFC investment and demonstration projects, and HFC enabling activities and stand-alone investment projects (60/44, 71/18, 71/42, 72/20, 72/40, 73/27, 74/18, 74/50, 74/51, 79/45, 79/46, and 79/47) as well as country requests have been taken into consideration.  As agreed with the Secretariat, activities which were included in UNDP’s 2017 Business Plan, but were not submitted in 2017 were reflected in the 2018 Business Plan as well.

The activities included for 2018 can be summarized as follows:

- 22 ongoing institutional strengthening activities, of which 14 will request an extension in 2018 for a combined amount of US$ 4.3 million;

- Several HCFC-related activities, some of which have resulted directly from the approval of Stage I in the previous six years.

- Two new countries (Bangladesh and Democratic Republic of the Congo) have included HCFC activities for Stage II HPMPs in 2018.

- Sixteen countries will be submitting requests for HFC enabling activities in 2018 for a total of US$ 3.1 million;

- Two countries (China and Dominican Republic) have included requests for funding for HFC stand-alone investment projects for a total of US$ 3.4 million; and

- One global request for the Core Unit support cost.

Thus the expected business planning value is US$ 67.4 million for 2018 and US$ 46.7 million for 2019 (including support costs).  This funding translates to the phase out of 768.5 ODP tonnes in 2018 and 605.6 ODP tonnes in 2019.

Figures for the Stage I HPMP-related activities in 2018 and beyond were obtained by taking the approved figures and ODP values from the agreements between the Executive Committee and the countries concerned.

Figures for the new Stage II HPMP-related activities in 2018 and beyond were based on the Stage II guidelines that were approved at the 74th meeting and were obtained using the following methodology:

- We took the sector/chemical distribution as per starting point, based on the HPMP Stage I document.

- We took the ODPs by sectors that have already been approved during Stage I and calculated the remaining eligible sector consumption by deducting the approved ODP from the original sector distribution.

- For non-LVCs, in most cases, we estimated the value of Stage II based on a calculation of up to 35% of the value of phase-out.  HCFC-141b entries were prioritized in the majority of cases.

- For LVCs that phased out 10% in Stage I, we assumed they would phase-out 35% in Stage II.

- For those LVCs that phased out 35% in Stage I, we assumed they would phase out 67.5% in Stage II.

- US dollar estimates were derived based on the cost-effectiveness figures agreed with the MLF Secretariat during the Inter-agency coordination meeting in August 2015.

- The year of the first tranche of Stage II and the duration of Stage II were determined on a country basis depending on the local context of the country.

Stage II PRP was entered one to two years before the last tranche of Stage I of the HPMP is due in most cases with the exception of a few countries.

##### II.         Resource allocation

The projects are grouped into various categories, which are described in the following summary table.

Table 1: UNDP 2018-2020 Business Plan Resource Allocations

| Category | 2018 Value (000’s) | 2019 Value (000’s) | 2020 Value (000’s) |
| --- | --- | --- | --- |
| 1a. Approved Stage I HPMP | 1,332 | 352 | 370 |
| 1b. Approved Stage II HPMP | 48,877 | 25,987 | 37,993 |
| 2a. Planned Stage I HPMP | 151 | 328 | 151 |
| 2b. Planned Stage II PRP | 398 | 10 | - |
| 2c. Planned Stage II HPMP | 3,364 | 7,839 | 4,404 |
| 2d. Planned Stage III PRP | 420 | 80 | - |
| 3. Planned Inst. Str. | 4,305 | 2,082 | 4,304 |
| 4. Core | 2,084 | 2,098 | 2,113 |
| 5a. Planned Enabling Activity | 3,079 | - | - |
| 5c. Planned investment project | 3,400 | 5,885 | 2,140 |
| 6. Production Sector | - | 2,000 | 2,000 |
| Grand Total | 67,410 | 46,662 | 64,097 |

## Chart 1: UNDP Resource Allocation for 2018 Business Plan Activities

##### III.         Geographical distribution

The UNDP Business Plan will once again cover all the regions, with approved and new activities in 48 countries, 38 of which have funding requests in 2018. The number of activities and budgets per region for 2018 is listed in Chart 1.

It should be noted that the budget amounts are in direct correlation with the amount of ODS that a country/region consumes.

Chart 2: UNDP 2018 MYA Tranches and New Activities per Region

## This graph doesn’t include the Ozone programmes in the CIS that are funded by the GEF.

##### IV.         Programme Expansion in 2018

4.1.      Background

UNDP’s 2018-2020 Business Plan has mostly been developed by taking previous years’ business plans into consideration, applying the relevant Executive Committee decisions on Business Planning, Stage I and Stage II HPMPs, investment and demonstration projects, and through communication with Article 5 countries that have expressed an interest in working with UNDP to address their compliance and other needs.

Clarifications were sought and overlaps were resolved during discussions with the MLF Secretariat and other Implementing and bilateral Agencies during and post the Inter-Agency Coordination meeting held on 5 - 7 September 2017 in Montreal.

Countries Contacted. All activities listed are either deferred from the prior year’s business plan, or have active project preparation accounts ongoing, or were included based on requests from the countries concerned.  UNDP will continue to provide technical and advisory support to all the countries assisted during Stage I, in addition to Venezuela, which UNDP wasn’t involved in Stage I for.

Coordination with other bilateral and implementing agencies. As in the past, during 2018 UNDP will continue to collaborate with both bilateral and other implementing agencies, as lead agency or cooperating agency. Collaborative arrangements in programming will continue with bilateral agencies, the Government of Italy and the Government of Japan.

4.2.   ODP Impact on the 2-year Phase-out Plan

In the next table, which is also based on Annex 1, the ODP amount listed in a given year corresponds to the US$ amount that is approved in that same year whereby the overall cost-effectiveness was applied to each individual funding tranche.

Table 2: Impact upon Project Approval (in ODP T)

| Category | ODP in 2018 | ODP in 2019 |
| --- | --- | --- |
| HCFC-141b | 172.26 | 60.19 |
| HCFC-22 | 238.95 | 291.40 |
| HCFC-22/HCFC-141b | 357.30 | 125.30 |
| HCFC-22/HFC-23 | - | 128.66 |
| Total | 768.51 | 605.55 |

*The split between the various HCFCs is often difficult to determine, especially where various agencies are active in one HPMP.  It is for those cases that the category “HCFC-22/HCFC-141b” was used.

4.4. Non-investment projects

Also included in Annex 1 are UNDP’s planned non-investment projects in 2018, with a total value of more than US$ 5.9 million, including support costs. This list excludes institutional strengthening and includes one global request under the core unit, preparation funding and HFC enabling activities.

Details on all these requests will also be included in the respective Work Programmes to be submitted throughout 2018.

Table 3: Individual Non-Investment projects (DEM/TAS) in 2018

| Agency Category | Country | Sector and Subsector | Value ($000) in 2018 |
| --- | --- | --- | --- |
| 2c. Planned Stage II PRP | Brunei Darussalam | Stage II HPMP Preparation | 10 |
| 2c. Planned Stage II PRP | Costa Rica | Stage II HPMP Preparation | 43 |
| 2c. Planned Stage II PRP | Cuba | Stage II HPMP Preparation | 60 |
| 2c. Planned Stage II PRP | El Salvador | Stage II HPMP Preparation | 30 |
| 2c. Planned Stage II PRP | Fiji | Stage II HPMP Preparation | 12 |
| 2c. Planned Stage II PRP | Georgia | Stage II HPMP Preparation | 32 |
| 2c. Planned Stage II PRP | Ghana | Stage II HPMP Preparation | 36 |
| 2c. Planned Stage II PRP | Jamaica | Stage II HPMP Preparation | 30 |
| 2c. Planned Stage II PRP | Mali | Stage II HPMP Preparation | 12 |
| 2c. Planned Stage II PRP | Nepal | Stage II HPMP Preparation | 10 |
| 2c. Planned Stage II PRP | Paraguay | Stage II HPMP Preparation (refr servicing) | 32 |
| 2c. Planned Stage II PRP | Sri Lanka | Stage II HPMP Preparation | 30 |
| 2c. Planned Stage II PRP | Swaziland | Stage II HPMP Preparation | 11 |
| 2c. Planned Stage II PRP | Trinidad and Tobago | Stage II HPMP Preparation | 64 |
| 2e. Planned Stage III PRP | Dominican Republic | Stage III HPMP Preparation | 50 |
| 2e. Planned Stage III PRP | India | Stage III HPMP Preparation (air-conditioning) | 120 |
| 2e. Planned Stage III PRP | India | Stage III HPMP Preparation (refrigeration) | 120 |
| 2e. Planned Stage III PRP | India | Stage III HPMP Preparation (overarching) | 50 |
| 2e. Planned Stage III PRP | Panama | Stage III HPMP Preparation | 40 |
| 2e. Planned Stage III PRP | Uruguay | Stage III HPMP Preparation | 40 |
| 4. Core | Global | Core Unit Support | 2,084 |
| 5a. Planned Enabling Activity | Bangladesh | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Chile | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Colombia | Enabling activities for Kigali Amendment | 273 |
| 5a. Planned enabling activity | Costa Rica | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Cuba | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | El Salvador | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | India | Enabling activities for Kigali Amendment | 273 |
| 5a. Planned enabling activity | Indonesia | Enabling activities for Kigali Amendment | 273 |
| 5a. Planned enabling activity | Iran | Enabling activities for Kigali Amendment | 273 |
| 5a. Planned enabling activity | Jamaica | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Malaysia | Enabling activities for Kigali Amendment | 273 |
| 5a. Planned enabling activity | Panama | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Paraguay | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Peru | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Trinidad and Tobago | Enabling activities for Kigali Amendment | 164 |
| 5a. Planned enabling activity | Uruguay | Enabling activities for Kigali Amendment | 82 |
| Total |  |  | 5,982 |

In addition, UNDP will prepare 14 non-investment Institutional Strengthening project extensions in 2018, as indicated in the table below. The total value of IS renewal programming in 2018 is US$ 4.3 million.  An additional 8 IS renewals (Chile, Colombia, Costa Rica, Indonesia, Malaysia, Panama, Trinidad and Tobago, Uruguay) will be submitted in 2019 and are thus not shown in the table below.

Table 4: Non-Investment Institutional Strengthening requests

| Agency Category | Country | Sector and Subsector | Value ($000) in 2018 |
| --- | --- | --- | --- |
| Planned Inst. Str. | Argentina | Institutional Strengthening | 427 |
| Planned Inst. Str. | Bangladesh | Institutional Strengthening | 178 |
| Planned Inst. Str. | Brazil | Institutional Strengthening | 481 |
| Planned Inst. Str. | China | Institutional Strengthening | 534 |
| Planned Inst. Str. | Cuba | Institutional Strengthening | 204 |
| Planned Inst. Str. | Georgia | Institutional Strengthening | 91 |
| Planned Inst. Str. | Ghana | Institutional Strengthening | 191 |
| Planned Inst. Str. | India | Institutional Strengthening | 511 |
| Planned Inst. Str. | Iran | Institutional Strengthening | 238 |
| Planned Inst. Str. | Lebanon | Institutional Strengthening | 212 |
| Planned Inst. Str. | Nigeria | Institutional Strengthening | 356 |
| Planned Inst. Str. | Pakistan | Institutional Strengthening | 307 |
| Planned Inst. Str. | Sri Lanka | Institutional Strengthening | 184 |
| Planned Inst. Str. | Venezuela | Institutional Strengthening | 391 |
| Total |  |  | 4,305 |

###### 4.5. Formulation of HPMP related activities in 2018

###### UNDP is now focused on preparing and submitting HCFC Stage II Phase-out Management Plans and has submitted such plans for 49 countries out of 50 countries. UNDP’s focus is:

###### Preparing and submitting final tranches of Stage I HPMPs.

###### Preparing and submitting subsequent tranches for already approved Stage II HPMPs (including China ICR and Solvents).  14 tranches valued at $48.9 million is expected to be submitted in 2018.

###### Developing and submitting first tranches for Stage II HPMPs.  It is expected that two countries will be submitting their Stage II HPMPs to the ExCom for its consideration in 2018.

##### V.         Activities included in the Business plan that needs special consideration

HCFC Demonstration Projects

While the preceding Section 4 of this report dealt specifically with 2017 activities only, section 5 is related to all years.

Implementation of HCFC Phase-out Management Plans (HPMPs) in developing countries involves technology and policy interventions for phasing out HCFCs, to comply with the control targets of the accelerated HCFC phase-out schedule. During Stage I of the HPMP covering the 2013 and 2015 control targets, higher ODP HCFCs and sectors (HCFC-141b and the Foams Sector) were prioritized to maximize environmental impact. It followed that larger enterprises, where cost-effective conversions could be carried out using existing and mature technologies (eg. hydrocarbons), were also prioritized.

While some companies addressed in Stage I were able to identify solutions, we are now facing the work to be done to phase out consumption in SMEs.  It has been noted during Stage I that even in the prioritized sectors/substances (HCFC-141b, Foams Sector), for enterprises with lower levels of HCFC consumption, established alternatives to HCFCs (e.g. hydrocarbons) did not always provide a sustainable solution in terms of availability, costs, performance and safety issues. Similarly, in other sectors and substances, alternatives to HCFCs are in various stages of development and market introduction and reliable data in terms of costs, availability and performance is not readily available, particularly at the country/ground level.

UNDP has significant experience in facilitating technology assessments of emerging alternatives (Methyl formate, Methyl Al, CO2, R-32, Ammonia, hydrocarbons, etc.) in various sectors and will be submitting new proposals in 2016 that are in line with the intent of ExCom Decision 72/40 and which demonstrate viable and low GWP alternatives to HCFCs using various technologies in a number of priority sectors.  Pursuant to ExCom decision 72/40, UNDP is preparing additional projects to demonstrate climate-friendly and energy-efficient alternative technologies to HCFCs, and feasibility studies on district cooling. UNDP has prepared such demonstration projects for China, Colombia, Costa Rica, Dominican Republic, Egypt, Kuwait, and Maldives.  Please see below the table for a detailed list of the countries, project titles, and budget amounts.

| Country | Project Title | MLF Grant |
| --- | --- | --- |
| China | Demonstrating ammonia semi-hermetic frequency convertible screw refrigeration compression unit in the industrial and commercial refrigeration industry | 1,026,815 |
| Colombia | HC-290 (propane) is being tested as an alternative refrigerant in commercial air-conditioning manufacturing; and validation of the use of hydrofluoro-olefins for discontinuous panels in Article 5 parties through the development of cost-effective formulations; | 500,000 |
| Costa Rica | Testing the application of an ammonia/carbon dioxide refrigeration system in replacement of HCFC-22 for the medium-sized producer and retail store of Premezclas Industriales S.A. | 524,000 |
| Dominican Republic | Feasibility study for district cooling in Punta Cana | 91,743 |
| Egypt | Demonstrating low-cost options for the conversion to non-ODS technologies in polyurethane foams at very small users; | 295,000 |
| Kuwait | Demonstrating HCFC-free low-global warming potential technology performance in air-conditioning applications; and | 293,000 |
| Maldives | Testing HCFC-free low-global warming potential alternatives in refrigeration in fisheries sector are being tested. | 141,000 |
| Grand Total |  | 2,871,558 |

Most of these projects are still in the early stages of building the project teams and initiating the procurement processes.  The most advanced project is the Feasibility study for district cooling in Punta Cana, where the study was conducted and a final report was prepared. The study showed that district cooling is a viable approach for Punta Cana, avoiding emission of ODS (future need of approximately 1000 kg can be avoided) and GHGs (8.500 ton CO2/year reduction). A seminar to present the findings and results was organized and attracted the interest of many stakeholders.

ODS Alternative Surveys

As per the decision of XXVI/9 of the Twenty-Sixth Meeting of the Parties to the Montreal Protocol on Substances that Deplete the Ozone Layer, UNDP also conducted surveys of ODS alternatives, prioritizing the Foams, Refrigeration and Air Conditioning sectors in selected developing countries representing a balance of size and regional spread in order to: establish the market penetration of current commercially available alternatives, in terms of supply chain and costs, performance and environmental impact; and identify emerging alternatives, in terms of their expected market introduction and availability, performance and projected costs.  ODS alternative surveys were approved with MLF funding for Bangladesh, Costa Rica, Cuba, Dominican Republic, El Salvador, India, Iran, Lebanon, Moldova, Panama, Paraguay and Peru.  UNDP has completed all the surveys for the countries that we are responsible for.

## The surveys show that an increase in the consumption of alternatives to HCFCs (R-404A, R-407C, R-410A, HFC-32 and R-290) is expected in the next several years, partially due to the phase-out of HCFC-22 as a result of the conversion of lines manufacturing HCFC-based equipment, as well as policies banning the manufacturing (where applicable) and/or the importation of HCFC-based equipment. As technologies in the refrigeration/air-conditioning and/or foam sectors based on HFC-32, R-290 and HFO further penetrate local markets and become more cost-effective, the consumption trend of HFCs and hydrocarbons may change.

HFC Enabling Activities and Stand-alone Investment Projects

As per ExCom decision 79/46, the Executive Committee has allowed for the submission of HFC enabling activities, which will support the early ratification of the Kigali Amendment.  The activities to be implemented will support Parties in the ratification process.  Countries can undertake a range of enabling activities to help their national ozone units to fulfill their initial obligations with regards to HFC phase-down, in line with the Kigali Amendment, including country-specific activities aimed at initiating support on institutional arrangements, the review of licensing systems, data reporting on HFC consumption and production and the national strategies.  UNDP is assisting 19 countries (Bangladesh, Chile, China, Colombia, Costa Rica, Cuba, El Salvador, Fiji, India, Indonesia, Iran Jamaica, Malaysia, Nepal, Panama, Paraguay, Peru, Trinidad and Tobago, and Uruguay) with developing HFC enabling activities and these requests will be submitted in 2018.

The Executive Committee (ExCom decision 79/45) has also allowed for the preparation of stand-alone investment projects, which will support the phase-down of HFCs.  Investment projects that will help to reduce the HFCs consumption at the enterprise level will be considered by the ExCom on a case-by-case basis.  UNDP is assisting six countries (Bangladesh, China, Colombia, Dominican Republic, Egypt, Mexico, and Zimbabwe) with preparing such projects.  Of these countries, Bangladesh and Colombia were submitted in 2017 and one project for China (Technology demonstration for HFC-23 by-product conversion), Dominican Republic and Mexico will be submitted in 2018.  The remaining projects will be submitted in 2019 and 2020.

##### VI.         Policy Issues

There are no policy issues to be highlighted.

##### VII. 2017 PERFORMANCE INDICATORS

Decision 71/28 of the Executive Committee approved the following indicators to allow for the evaluation of performance of implementing agencies, with the weightings indicated in the table below. UNDP has added a column containing the “2018 targets” for those indicators. Some of these targets can be extracted from UNDP’s 2018 business plan to be approved at the 80th ExCom meeting in November 2017. It should however be noted that this table is usually revised at that meeting, depending on the decisions that are taken. Other targets will be known once the prior year’s progress report is submitted.

| Category of performance indicator | Item | Weight | UNDP’s target for 2018 | Remarks |
| --- | --- | --- | --- | --- |
| Planning/Approval | Number of tranches approved vs. those planned* | 10 | 23 |  |
| Planning/Approval | Number of projects/activities approved vs. those planned (including project preparation activities)** | 10 | 52 | 14 IS, 16 TAS, 20 PRP, 1 DEM, 1 INV |
| Implementation | Funds disbursed (based on estimated disbursement in progress report) | 15 | 31,295,677 | As determined by the 2016 Progress Report. |
| Implementation | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans | 25 | 766.9 | ODS Phaseout associated with 23 tranches |
| Implementation | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 20 | 4 | As determined by the 2016 Progress Report. |
| Administrative | The extent to which projects are financially completed 12 months after project completion | 10 | 70% of those due | As determined by the 2016 Progress Report. |
| Administrative | Timely submission of project completion reports vs. those agreed | 5 | On time | TBD |
| Administrative | Timely submission of progress reports and business plans and responses unless otherwise agreed | 5 | On time | TBD |

* The target of an agency will be reduced if we could not submit a tranche owe to another cooperating/lead agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

Note: As per usual practice, all the above indicators will be revised during the 80th ExCom, depending on which programmes are allowed to stay in the business plan at that meeting.
ANNEX 1 – TABLES RELATED TO PERFORMANCE INDICATORS

Table 1: Performance Indicator on planned/approved tranches

| Country | Sector and Subsector |
| --- | --- |
| Bangladesh | Stage II HPMP (air conditioning and servicing) |
| Brazil | Stage II HPMP |
| Brunei Darussalam | Stage I Investment proj./Sector Plans (Servicing Sector) |
| Chile | Stage II HPMP |
| China | Stage II Investment proj./Sector Plans (ICR Sector Plan) |
| China | Stage II Investment proj./Sector Plans (Solvents Sector Plan) |
| Colombia | Stage II HPMP |
| Cuba | Stage I HPMP |
| Democratic Republic of the Congo | Stage II HPMP (servicing) |
| Dominican Republic | Stage II HPMP (servicing) |
| Egypt | Stage I HPMP |
| Fiji | Stage II HPMP Preparation |
| Georgia | Stage I HPMP |
| Ghana | Stage I HPMP |
| Guyana | Stage II HPMP (servicing) |
| India | Stage II HPMP (air conditioning, foam and refrigeration) |
| Indonesia | Stage II HPMP |
| Iran (Islamic Republic of) | Stage II HPMP (refrigeration) |
| Kyrgyzstan | Stage II HPMP (servicing) |
| Lebanon | Stage II HPMP |
| Panama | Stage II HPMP |
| Trinidad and Tobago | Stage I HPMP |
| Uruguay | Stage II HPMP (rigid foam & servicing) |

Table 2: Performance Indicator on planned/approved activities

| Country | Sector and Subsector |
| --- | --- |
| Brunei Darussalam | Stage II HPMP Preparation |
| Costa Rica | Stage II HPMP Preparation |
| Cuba | Stage II HPMP Preparation |
| El Salvador | Stage II HPMP Preparation |
| Georgia | Stage II HPMP Preparation |
| Mali | Stage II HPMP Preparation |
| Nepal | Stage II HPMP Preparation |
| Paraguay | Stage II HPMP Preparation (refr servicing) |
| Sri Lanka | Stage II HPMP Preparation |
| Swaziland | Stage II HPMP Preparation |
| Trinidad and Tobago | Stage II HPMP Preparation |
| Dominican Republic | Stage III HPMP Preparation |
| Panama | Stage III HPMP Preparation |
| Uruguay | Stage III HPMP Preparation |
| Argentina | Several Ozone unit support |
| Bangladesh | Several Ozone unit support |
| Brazil | Several Ozone unit support |
| China | Several Ozone unit support |
| Cuba | Several Ozone unit support |
| Georgia | Several Ozone unit support |
| Nigeria | Several Ozone unit support |
| Pakistan | Several Ozone unit support |
| Sri Lanka | Several Ozone unit support |
| Venezuela | Several Ozone unit support |
| Bangladesh | Enabling activities for Kigali Amendment |
| Chile | Enabling activities for Kigali Amendment |
| Colombia | Enabling activities for Kigali Amendment |
| Costa Rica | Enabling activities for Kigali Amendment |
| Cuba | Enabling activities for Kigali Amendment |
| El Salvador | Enabling activities for Kigali Amendment |
| Malaysia | Enabling activities for Kigali Amendment |
| Panama | Enabling activities for Kigali Amendment |
| Paraguay | Enabling activities for Kigali Amendment |
| Peru | Enabling activities for Kigali Amendment |
| Trinidad and Tobago | Enabling activities for Kigali Amendment |
| Uruguay | Enabling activities for Kigali Amendment |
| China | Technology demonstration for HFC-23 by-product conversion |
| Dominican Republic | Phase out of HFC-134a in commercial refrigeration |

Table 3: ODS phase-out for tranches

| Country | Sector and Subsector | ODP in 2018 |
| --- | --- | --- |
| Bangladesh | Stage II HPMP (air conditioning and servicing) | 6.80 |
| Brazil | Stage II HPMP | 105.40 |
| Brunei Darussalam | Stage I Investment proj./Sector Plans (Servicing Sector) | 0.22 |
| Chile | Stage II HPMP | 20.45 |
| China | Stage II Investment proj./Sector Plans (ICR Sector Plan) | 209.14 |
| China | Stage II Investment proj./Sector Plans (Solvents Sector Plan) | 51.59 |
| Colombia | Stage II HPMP | 29.70 |
| Cuba | Stage I HPMP | 1.10 |
| Democratic Republic of the Congo | Stage II HPMP (servicing) | 3.92 |
| Dominican Republic | Stage II HPMP (servicing) | 5.94 |
| Egypt | Stage I HPMP | 13.86 |
| Fiji | Stage II HPMP Preparation | 0.00 |
| Georgia | Stage I HPMP | 0.56 |
| Ghana | Stage I HPMP | 2.42 |
| Guyana | Stage II HPMP (servicing) | 0.16 |
| India | Stage II HPMP (air conditioning, foam and refrigeration) | 250.29 |
| Indonesia | Stage II HPMP | 7.65 |
| Iran (Islamic Republic of) | Stage II HPMP (refrigeration) | 33.77 |
| Kyrgyzstan | Stage II HPMP (servicing) | 0.76 |
| Lebanon | Stage II HPMP | 9.73 |
| Panama | Stage II HPMP | 4.86 |
| Trinidad and Tobago | Stage I HPMP | 1.77 |
| Uruguay | Stage II HPMP (rigid foam & servicing) | 6.85 |

A draft business plan for 2018-2020 of UNDP was discussed at the Inter-agency coordination meeting (IACM) held in Montreal from 5 to 7 September 2017. The business plan contained in this document has addressed the issue raised at the meeting.

UNEP/OzL.Pro/ExCom/80/44.

UNDP’s 2018 core unit cost request has been submitted to the 80th meeting (UNEP/OzL.Pro/ExCom/80/29).

As agreed at the IACM.

As agreed at the IACM.

UNEP/OzL.Pro/ExCom/80/16.

All values include agency support costs.

All values include agency support costs.

## EUR contains CIS-countries that receive MLF funding.

Tonnage in ODP and based on date of project approvals.  The figures for ODP related to ODS-waste management and destruction projects are very raw estimates. In addition it has to be clear that those figures are not phase-out as they represent ODS “use” and not “consumption”