| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/17 30 October 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 7(a)(iv) of the provisional agenda

PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2023

Introduction

# This document presents the progress report of UNEP as at 31 December 2023.

# The progress report of UNEP includes the status of implementation of projects, including 79 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2023, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2023 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2023 and cumulative since 1991

# As of 31 December 2023, the Executive Committee had approved US $445.37 million in projects for UNEP, consisting of US $411.83 million for the implementation of investment and non-investment projects, and US $33.55 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNEP as at 31 December 2023

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 882,689 |
| Destruction | 950,040 |
| Energy efficiency | 1,292,000 |
| Halon | 767,640 |
| HFC phase-down plan | 7,498,715 |
| Fumigants | 2,614,366 |
| Phase-out plan | 79,498,943 |
| Refrigeration | 13,856,016 |
| Several | 304,266,763 |
| Solvents | 198,860 |
| Sub-total | 411,826,032 |
| Agency support costs | 33,545,445 |
| Total | 445,371,477 |

# In 2023, 128 new projects and activities were approved. This level of funding is expected to result in the phase-out of 2,509 ODP tonnes of consumption of ODS and 348.2 mt (678,918 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2023.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2023. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2023

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 94 | 94 | 100 | 2,946,574 | 2,946,574 | 0 | 100 |
| Demonstration | 5 | 3 | 60 | 778,845 | 542,845 | 236,000 | 70 |
| Institutional strengthening (IS) | 1,012 | 910 | 90 | 90,204,244 | 75,085,868 | 15,118,376 | 83 |
| Investment | 5 | 3 | 60 | 634,500 | 498,112 | 136,388 | 79 |
| Project preparation | 323 | 260 | 80 | 17,006,088 | 11,695,886 | 5,310,202 | 69 |
| Technical assistance | 1,212 | 1,049 | 87 | 285,963,223 | 253,244,455 | 32,718,768 | 89 |
| Training | 196 | 196 | 100 | 14,292,557 | 14,292,557 | 0 | 100 |
| Total | 2,847 | 2,515 | 88 | 411,826,032 | 358,306,297 | 53,519,735 | 87 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNEP for 2023 and cumulative since 1991 up to 31 December 2023, is summarized as follows:

## Phase-out: In 2023, zero ODP tonnes of ODS were phased out and an additional 95.3 ODP tonnes of consumption of ODS and 340.5 mt (659,025 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 1,575 ODP tonnes of consumption of ODS had been phased out, of an expected total of 2,509 ODP tonnes of ODS from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2023, US $20.09 million was disbursed and US $24.69 million was planned for disbursement based on the 2022 progress report, representing a rate of disbursement of 81 per cent of that planned. Cumulatively, US $358.31 million had been disbursed out of the total US $411.83 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 87 per cent. In 2023, US $28.35 million was approved for implementation;

## Number of projects completed: In 2023, 116 projects were completed. Since 1991, 2,515 projects of the 2,847 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 88 per cent;

## Speed of delivery – non-investment projects: Projects that were completed in 2023 were completed on average 37 months after their approval. Since 1991, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 12 months after they had been approved;

## Project preparation: Of the 323 project preparation activities approved by the end of 2023, 260 have been completed, leaving 63 ongoing activities. In 2023, 24 project preparation activities have been completed;

## Implementation delays: A total of 332 projects were under implementation at the end of 2023, experiencing, on average, a delay of seven months. Thirty-one of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2023, 92 MYAs for HCFC phase-out management plans (HPMPs) and 14 Kigali HFC implementation plans (KIPs) were under implementation. Since 1991, 270 MYAs have been approved and 164 MYAs have been completed, representing a completion rate of 61 per cent.

# Table 3 summarizes progress made by UNEP since 1991.

## Table 3. Progress made by UNEP since 1991

| Phase out achieved |  | Disbursement (US $) | Number of projects |  | Speed of delivery for completion for non-investment projects (months) | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes |  | Approved | Completed |  |  | Approved | Completed |
| 1,575 | 0 | 358,306,297 | 2,847 | 2,515 | 37 | 7 | 270 | 164 |

*Consumption of ODS.

HFC-related projects

# As of 31 December 2023, the Executive Committee had approved 92 HFC-related projects (including two demonstration projects, 57 project preparation activities and 33 technical assistance projects) under regular contributions amounting to US $10,354,991 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Demonstration | 2 | 0 | 0 | 236,000 | 0 | 236,000 | 0 |
| Project preparation | 57 | 15 | 26 | 6,107,000 | 1,722,204 | 4,384,796 | 28 |
| Technical assistance** | 33 | 13 | 39 | 4,011,991 | 1,765,796 | 2,246,195 | 44 |
| Total | 92 | 28 | 30 | 10,354,991 | 3,488,000 | 6,866,992 | 34 |

* Excludes agency support costs.

** 348.2 mt (678,918 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2023, of the 92 projects, 15 project preparation activities and 13 technical assistance projects have been completed, leaving 64 ongoing. Fourteen of the 33 technical assistance projects are for enabling activities. Thirteen of the 14 enabling activities have been completed. Extension of the completion date was approved for the remaining enabling activity, which is expected to be completed in 2024. The remaining ongoing activities are at various stages of implementation.

# Of the total cumulative funding approved of US $10,354,991 (excluding agency support costs), US $3,488,000 had been disbursed, representing a disbursement rate of 34 per cent.

I.2	Issues identified in project implementation in 2023

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 31 projects classified as projects with implementation delays (including 27 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and four technical assistance projects). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 96th meeting.

# In addition, issues have been identified regarding tranches of MYAs for the phase-out of HCFCs; renewal of IS projects; and preparation of HPMPs. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Algeria, Bahrain, Bhutan, Burundi, Chile, China (refrigeration servicing sector), the Congo, Dominica, Ghana, Guinea-Bissau, India, Iraq, Kuwait, Nepal, the Pacific Island countries, Pakistan, Peru, Rwanda, and Uganda,  and reports on projects with specific reporting requirements associated with Maldives (additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b)) and Mauritania (HPMP), have been submitted to the 95th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Afghanistan, Botswana, Brunei Darussalam, Cabo Verde, the Democratic Republic of the Congo, Ethiopia, Guyana, Haiti, Senegal, South Sudan, and Syrian Arab Republic, tranches of which were due at the 95th meeting but were not submitted, and El Salvador, a tranche of which was submitted to the 95th meeting but subsequently withdrawn, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for cancellation, are addressed below.

# Of the 167 ongoing projects, excluding IS and project preparation, 48 projects have revised planned dates of completion since the 2022 progress report.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of IS projects had not been submitted for the last two years for eight Article 5 countries namely, Angola, Equatorial Guinea, Grenada, Namibia, Nauru, Myanmar, the Sudan, and Suriname. These projects have large remaining balances due to slow progress in implementation for various reasons including political situation. UNEP informed that it has been providing assistance to those countries and is planning to submit those renewal requests by 2025, except for the case of Myanmar, which will be subject to the political situation and the resumption of activities in the country.

# Regarding the HPMP for Haiti, UNEP informed the Secretariat that there had not been any progress for more than two years in terms of submission of the tranche request; further, no extension of the project’s completion date was approved. After consultations with UNEP, it was agreed that the request for the remaining third and fourth tranches of stage I of the HPMP would not be submitted and that the HPMP would be cancelled, noting that funds from the previous tranches had been fully disbursed.

Gender mainstreaming

# In order to help national ozone units implement the Multilateral Fund’s operational policy on gender mainstreaming, several products and initiatives were delivered under the Compliance Assistance Programme (CAP) in 2023, such as the Guidebook on Mainstreaming Gender in the Implementation of the Montreal Protocol and the International Network of Women in Cooling. They are designed to support and complement gender mainstreaming activities organized as part of CAP regional activities and national project preparation and implementation.

# In projects implemented by UNEP, gender mainstreaming activities and the use of indicators vary and depend upon the project type.  In the case of IS projects, gender-related activities and indicators are systematically included in line with the revised IS renewal format, in accordance with decision 91/63. Coordination and stakeholder consultations on gender mainstreaming issues are conducted under the IS projects. Additionally, some countries use the IS funding to engage a gender expert for a deeper gender assessment and the preparation of a gender mainstreaming roadmap.

# For tranches of HPMPs, UNEP continues to provide support and assist countries in systematically collecting and reporting on sex-disaggregated data about trainings and events. The implementation of, and reporting on, approved project activities include a gender aspect (i.e. training session exclusively for female technicians, scholarships for female technicians, technical training on flammable refrigerants for female technicians under Germany implementation, or adding gender-related sessions to workshops for importers, training of RAC technicians, among others). In the case of new stages of HPMPs, gender-related data and gender mainstreaming activities are more systematically included in their proposals. The increased variety of activities focusing on women in different groups of stakeholders is noticeable in the project documents. For new stages of KIPs, countries are conducting gender assessments as part of the KIP preparation activities. All KIP strategies include gender considerations in line with decision 92/40, which are complimentary to any gender mainstreaming activities already planned under the HPMPs.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2023, the Executive Committee had approved 79 HFC-related projects under the additional voluntary contributions amounting to US $7,515,807 (excluding agency support costs). A summary of the status of these projects is presented in table 5.

# Table 5. Status of approved HFC-related projects as of the end of 2023

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance – Enabling activities | 79 | 79 | 100 | 7,515,807 | 7,381,111 | 134,696 | 98 |

* Excludes agency support costs.

# As of the end of 2023, all 79 enabling activities approved had been completed.

# Of the total cumulative funding approved of US $7,515,807, US $7,381,111 had been disbursed, representing a disbursement rate of 98 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of UNEP as at 31 December 2023 contained in document UNEP/OzL.Pro/ExCom/95/17;

## To cancel stage I of the HCFC phase-out management plan for Haiti; and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER COUNTRY FOR 2023

# Table 1 of annex I presents the status of project implementation by country for 2023 in planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNEP for 2023

| Country | Estimated funds disbursed in 2023 (US$) | Funds disbursed in 2023 (US$) | Percentage of funds disbursed over estimation in 2023 | Percentage of planned projects completed in 2023* |
| --- | --- | --- | --- | --- |
| Afghanistan | 278,936 | 0 | 0 | 0 |
| Albania | 74,796 | 183,504 | 245 | 100 |
| Algeria | 115,315 | 0 | 0 |  |
| Angola | 126,211 | 172,032 | 136 | 0 |
| Antigua and Barbuda | 36,000 | 25,000 | 69 | 0 |
| Armenia | 40,800 | 53,190 | 130 | 0 |
| Bahamas (the) | 115,575 | 111,504 | 96 | 100 |
| Bahrain | 106,575 | 259,378 | 243 |  |
| Bangladesh | 229,535 | 128,485 | 56 | 0 |
| Barbados | 150,087 | 61,586 | 41 | 100 |
| Belize | 98,769 | 144,880 | 147 | 100 |
| Benin | 98,550 | 108,092 | 110 | 100 |
| Bhutan | 54,413 | 29,735 | 55 |  |
| Bolivia (Plurinational State of) | 68,970 | 33,227 | 48 | 0 |
| Botswana | 297,563 | 80,216 | 27 | 80 |
| Brunei Darussalam | 156,018 | 80,663 | 52 | 0 |
| Burkina Faso | 40,611 | 47,684 | 117 | 100 |
| Burundi | 51,000 | 84,795 | 166 | 100 |
| Cabo Verde | 146,300 | 2,845 | 2 |  |
| Cambodia | 137,848 | 211,784 | 154 | 100 |
| Cameroon | 107,161 | 178,601 | 167 | 100 |
| Chad | 97,100 | 149,796 | 154 |  |
| Chile | 123,368 | 121,152 | 98 | 100 |
| China | 1,539,222 | 1,653,207 | 107 | 33 |
| Colombia | 45,000 | 47,978 | 107 | 100 |
| Comoros (the) | 73,089 | 7,438 | 10 | 50 |
| Congo (the) | 53,780 | 0 | 0 | 67 |
| Cook Islands (the) | 125,123 | 37,002 | 30 | 0 |
| Cote d’Ivoire | 221,654 | 216,592 | 98 | 100 |
| Democratic Republic of the Congo (the) | 49,000 | 6,509 | 13 |  |
| Djibouti | 83,850 | 20,905 | 25 | 0 |
| Dominica | 171,814 | 105,895 | 62 | 0 |
| Dominican Republic (the) | 39,251 | 65,418 | 167 | 100 |
| Egypt | 91,000 | 104,200 | 115 |  |
| El Salvador | 51,100 | 22,664 | 44 |  |
| Equatorial Guinea | 91,404 | 0 | 0 | 33 |
| Eritrea | 50,000 | 45,000 | 90 | 100 |
| Eswatini | 114,000 | 130,000 | 114 | 100 |
| Ethiopia | 173,605 | 80,000 | 46 |  |
| Fiji | 126,277 | 88,803 | 70 | 50 |
| Gabon | 75,841 | 42,596 | 56 | 100 |
| Gambia (the) | 136,850 | 155,695 | 114 | 67 |
| Ghana | 75,399 | 171,700 | 228 | 100 |
| Grenada | 113,717 | 10,100 | 9 | 33 |
| Guatemala | 119,971 | 103,773 | 86 | 50 |
| Guinea | 81,028 | 31,395 | 39 | 100 |
| Guinea-Bissau | 73,922 | 28,398 | 38 | 33 |
| Guyana | 85,096 | 73,977 | 87 | 67 |
| Honduras | 44,438 | 24,240 | 55 | 100 |
| India | 357,568 | 67,216 | 19 | 0 |
| Iran (Islamic Republic of) | 180,560 | 141,669 | 78 | 0 |
| Iraq | 182,661 | 198,953 | 109 | 100 |
| Jamaica | 60,183 | 30,433 | 51 |  |
| Kenya | 101,446 | 101,446 | 100 |  |
| Kiribati | 181,084 | 35,091 | 19 | 50 |
| Kuwait | 349,680 | 120,432 | 34 | 100 |
| Kyrgyzstan | 87,491 | 110,948 | 127 | 100 |
| Lao People's Democratic Republic (the) | 227,628 | 172,412 | 76 | 20 |
| Lesotho | 84,350 | 105,253 | 125 | 0 |
| Liberia | 50,694 | 45,823 | 90 | 100 |
| Madagascar | 24,000 | 53,523 | 223 |  |
| Malawi | 103,312 | 219,613 | 213 | 100 |
| Maldives | 85,124 | 46,476 | 55 | 0 |
| Mali | 10,728 | 15,150 | 141 | 0 |
| Marshall Islands (the) | 129,603 | 44,553 | 34 | 0 |
| Mauritania | 55,350 | 93,000 | 168 |  |
| Mauritius | 51,000 | 85,000 | 167 | 100 |
| Mexico | 28,970 | 59,404 | 205 | 100 |
| Micronesia (Federated States of) | 145,008 | 55,471 | 38 | 0 |
| Mongolia | 146,983 | 140,545 | 96 | 33 |
| Mozambique | 109,604 | 77,083 | 70 | 100 |
| Myanmar | 127,170 | 33,256 | 26 | 0 |
| Namibia | 122,400 | 35,350 | 29 | 0 |
| Nauru | 90,270 | 2,660 | 3 | 0 |
| Nepal | 155,050 | 54,016 | 35 | 0 |
| Nicaragua | 68,983 | 103,587 | 150 | 100 |
| Niger (the) | 105,350 | 97,562 | 93 |  |
| Nigeria | 34,800 | 57,570 | 165 | 100 |
| Niue | 51,585 | 0 | 0 | 50 |
| Oman | 64,002 | 70,000 | 109 |  |
| Pakistan | 281,289 | 206,320 | 73 | 33 |
| Palau | 131,715 | 43,525 | 33 | 50 |
| Paraguay | 73,835 | 78,108 | 106 | 0 |
| Peru | 146,637 | 80,835 | 55 | 100 |
| Philippines (the) | 81,329 | 132,641 | 163 | 100 |
| Qatar | 88,697 | 50,000 | 56 |  |
| Republic of Moldova (the) | 46,526 | 64,848 | 139 | 100 |
| Rwanda | 149,100 | 150,300 | 101 | 67 |
| Saint Kitts and Nevis | 88,084 | 28,887 | 33 | 33 |
| Saint Lucia | 127,891 | 113,796 | 89 | 100 |
| Saint Vincent and the Grenadines | 158,264 | 80,484 | 51 | 33 |
| Samoa | 133,360 | 54,736 | 41 | 50 |
| Sao Tome and Principe | 114,508 | 90,828 | 79 | 67 |
| Saudi Arabia | 229,020 | 113,567 | 50 | 100 |
| Senegal | 195,895 | 104,854 | 54 | 50 |
| Serbia | 27,283 | 20,100 | 74 | 100 |
| Seychelles | 70,350 | 56,200 | 80 |  |
| Sierra Leone | 169,895 | 45,000 | 26 | 100 |
| Solomon Islands | 168,914 | 25,011 | 15 | 0 |
| Somalia | 68,850 | 95,100 | 138 | 100 |
| South Sudan | 75,675 | 127 | 0 | 100 |
| Sri Lanka | 127,349 | 42,876 | 34 | 0 |
| Sudan (the) | 112,021 | 0 | 0 | 0 |
| Suriname | 59,337 | 43,850 | 74 | 50 |
| Syrian Arab Republic | 280,206 | 11,082 | 4 | 0 |
| Timor-Leste | 66,634 | 76,260 | 114 | 100 |
| Togo | 77,150 | 78,536 | 102 |  |
| Tonga | 123,206 | 0 | 0 | 50 |
| Turkmenistan | 58,368 | 73,697 | 126 | 100 |
| Tuvalu | 75,929 | 6,304 | 8 | 50 |
| Uganda | 106,250 | 119,795 | 113 | 100 |
| United Republic of Tanzania (the) | 118,850 | 29,795 | 25 |  |
| Vanuatu | 159,361 | 61,022 | 38 | 0 |
| Viet Nam | 76,658 | 94,194 | 123 | 100 |
| Yemen | 101,999 | 169,985 | 167 | 100 |
| Zambia | 146,100 | 177,945 | 122 | 50 |
| Zimbabwe | 162,850 | 270,995 | 166 | 100 |
| Region: ASP | 410,992 | 207,152 | 50 |  |
| Global | 9,568,417 | 8,975,030 | 94 | 100 |
| Grand total | 24,688,363 | 20,088,911 | 81 | 54 |

* For projects that were planned to be completed in 2023.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER YEAR AS AT 31 DECEMBER 2023

# Table 1 of annex II presents an overview of the status of project implementation by year.  All projects and activities approved between 1991 and 2009, and in 2011 and 2013 have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 11 | 11 | 100 | 1,372,335 | 1,372,335 | 0 | 100 |
| 1992 | 15 | 15 | 100 | 1,711,000 | 1,711,000 | 0 | 100 |
| 1993 | 49 | 49 | 100 | 4,194,343 | 4,194,343 | 0 | 100 |
| 1994 | 58 | 58 | 100 | 4,231,169 | 4,231,169 | 0 | 100 |
| 1995 | 50 | 50 | 100 | 4,047,683 | 4,047,683 | 0 | 100 |
| 1996 | 47 | 47 | 100 | 3,366,039 | 3,366,039 | 0 | 100 |
| 1997 | 87 | 87 | 100 | 7,962,291 | 7,962,291 | 0 | 100 |
| 1998 | 64 | 64 | 100 | 4,669,124 | 4,669,124 | 0 | 100 |
| 1999 | 87 | 87 | 100 | 6,368,983 | 6,368,983 | 0 | 100 |
| 2000 | 85 | 85 | 100 | 6,300,398 | 6,300,398 | 0 | 100 |
| 2001 | 59 | 59 | 100 | 7,411,159 | 7,411,159 | 0 | 100 |
| 2002 | 72 | 72 | 100 | 9,469,401 | 9,469,401 | 0 | 100 |
| 2003 | 78 | 78 | 100 | 11,165,394 | 11,165,394 | 0 | 100 |
| 2004 | 99 | 99 | 100 | 12,362,652 | 12,362,652 | 0 | 100 |
| 2005 | 72 | 72 | 100 | 12,339,483 | 12,339,483 | 0 | 100 |
| 2006 | 108 | 108 | 100 | 12,731,484 | 12,731,484 | 0 | 100 |
| 2007 | 79 | 79 | 100 | 14,611,111 | 14,611,111 | 0 | 100 |
| 2008 | 132 | 132 | 100 | 17,875,070 | 17,875,070 | 0 | 100 |
| 2009 | 115 | 115 | 100 | 17,250,876 | 17,250,876 | 0 | 100 |
| 2010 | 79 | 78 | 99 | 14,361,124 | 14,314,496 | 46,629 | 100 |
| 2011 | 100 | 100 | 100 | 16,782,433 | 16,782,434 | -1 | 100 |
| 2012 | 80 | 79 | 99 | 16,137,634 | 16,086,261 | 51,373 | 100 |
| 2013 | 90 | 90 | 100 | 14,152,112 | 14,152,112 | -1 | 100 |
| 2014 | 74 | 72 | 97 | 12,339,041 | 12,304,026 | 35,015 | 100 |
| 2015 | 180 | 179 | 99 | 21,169,099 | 21,119,898 | 49,201 | 100 |
| 2016 | 95 | 94 | 99 | 19,633,315 | 19,472,744 | 160,571 | 99 |
| 2017 | 57 | 55 | 96 | 12,576,768 | 12,520,963 | 55,805 | 100 |
| 2018 | 126 | 119 | 94 | 19,587,957 | 18,975,933 | 612,024 | 97 |
| 2019 | 109 | 97 | 89 | 14,880,868 | 14,207,816 | 673,052 | 95 |
| 2020 | 134 | 102 | 76 | 15,697,493 | 11,901,436 | 3,796,057 | 76 |
| 2021 | 127 | 69 | 54 | 22,451,633 | 16,104,742 | 6,346,892 | 72 |
| 2022 | 101 | 14 | 14 | 24,266,135 | 10,908,587 | 13,357,548 | 45 |
| 2023 | 128 | 0 | 0 | 28,350,427 | 14,855 | 28,335,572 | 0 |
| Total | 2,847 | 2,515 | 88 | 411,826,032 | 358,306,297 | 53,519,735 | 87 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNEP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Antigua and Barbuda ANT/PHA/73/PRP/17 | Preparation of a HCFC phase-out management plan (stage II) | 100 | Delay in project preparation | Noting decision 77/8(j), to request UNEP to submit a status report to the 96th meeting on progress in the preparation of stage II |
| Antigua and Barbuda ANT/SEV/73/INS/16 | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | 42 | Delay in completion | To request UNEP to submit a status report to the 96th meeting on implementation progress and planned date of operational completion |
| Antigua and Barbuda ANT/SEV/93/INS/20 | Extension of institutional strengthening project (phase VI: 1/2024-12/2026) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 96th meeting on implementation progress |
| Bahamas (the) BHA/PHA/90/TAS/33 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Bangladesh BGD/PHA/81/TAS/50 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 36 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Bolivia (Plurinational State of) BOL/PHA/87/TAS/51 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Botswana BOT/PHA/86/TAS/26 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Burundi CBI/PHA/88/TAS/28 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Chile CHI/PHA/88/TAS/206 | HCFC phase-out management plan (stage III, first tranche) | 13 | Delay in project implementation | To request UNEP to submit a status report to the 96th meeting on implementation progress and funds disbursement |
| China CPR/PHA/81/TAS/595 | HCFC phase-out management plan (stage II, second tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | 93 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| China CPR/PHA/84/TAS/597 | HCFC phase-out management plan (stage II, third tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | 90 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| China CPR/PHA/91/TAS/615 | HCFC phase-out management plan (stage II, fifth tranche) (servicing sector plan and enabling programme) | 22 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Djibouti DJI/PHA/88/TAS/29 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Dominica DMI/PHA/62/TAS/19 | HCFC phase-out management plan (stage I, first tranche) | 43 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Dominica DMI/PHA/84/TAS/25 | HCFC phase-out management plan (stage I, second tranche) | 0 | 12 and 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Dominica DMI/PHA/86/TAS/26 | Verification report on the implementation of stage I of the HCFC phase-out management plan | 0 | 12 and 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Ethiopia ETH/PHA/88/TAS/33 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Grenada GRN/PHA/90/TAS/32 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Guinea-Bissau GBS/PHA/88/TAS/29 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| India IND/PHA/82/TAS/476 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector plan) | 61 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| India IND/PHA/91/TAS/502 | HCFC phase-out management plan (stage III, first tranche) (enabling activities) | 0 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/TAS/234 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 71 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Liberia LIR/PHA/90/TAS/33 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Mongolia MON/PHA/86/TAS/31 | HCFC phase-out management plan (stage II, first tranche) | 61 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Myanmar MYA/SEV/84/INS/22 | Extension of institutional strengthening project (phase V: 7/2020-6/2022) | 47 | Political situation resulting in lack of progress | To request UNEP to submit a status report to the 96th meeting on implementation progress including any change in project implementation status |
| Nepal NEP/PHA/86/TAS/43 | HCFC phase-out management plan (stage II, first tranche) | 14 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/TAS/101 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 72 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Pakistan PAK/PHA/90/TAS/114 | HCFC phase-out management plan (stage III, first tranche) (refrigeration servicing sector) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Saint Kitts and Nevis STK/PHA/74/TAS/20 | HCFC phase-out management plan (stage I, second tranche) | 0 | 12 and 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Saint Lucia STL/PHA/87/TAS/34 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Saint Vincent and the Grenadines STV/PHA/86/TAS/26 | HCFC phase-out management plan (stage I, third tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Sao Tome and Principe STP/PHA/88/TAS/33 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Sierra Leone SIL/PHA/87/TAS/41 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Sri Lanka SRL/PHA/86/TAS/56 | HCFC phase-out management plan (stage II, first tranche) | 26 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Suriname SUR/SEV/86/INS/30 | Extension of the institutional strengthening project (phase VII: 1/2021-12/2022) | 0 | Delay in implementation and administrative challenges in the national ozone unit | To request UNEP to submit a status report to the 96th meeting on implementation progress including an update on the resolution of the administrative challenges and funds disbursement |
| Suriname SUR/PHA/92/TAS/33 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | Delay in project implementation | To request UNEP to submit a status report to the 96th meeting on implementation progress, including completion of stage I, and funds disbursement |
| Suriname SUR/PHA/93/TAS/34 | HCFC phase-out management plan (stage II, first tranche) | 0 | Delay in project implementation | To request UNEP to submit a status report to the 96th meeting on implementation progress and funds disbursement |
| United Republic of Tanzania (the) URT/PHA/87/TAS/41 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |
| Vanuatu VAN/PHA/86/TAS/18 | HCFC phase-out management plan for PIC countries through regional approach (stage II, first tranche) | 11 | 12 months delays | To request UNEP to report to the 96th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/95/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 95th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 95th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2023. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

No phase-out for HFC-related projects in 2023.

No phase-out so far for HFC-related projects.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/95/39

UNEP/OzL.Pro/ExCom/95/41

UNEP/OzL.Pro/ExCom/95/43

UNEP/OzL.Pro/ExCom/95/44

UNEP/OzL.Pro/ExCom/95/46

UNEP/OzL.Pro/ExCom/95/47

UNEP/OzL.Pro/ExCom/95/49

UNEP/OzL.Pro/ExCom/95/51

UNEP/OzL.Pro/ExCom/95/54

UNEP/OzL.Pro/ExCom/95/56

UNEP/OzL.Pro/ExCom/95/58

UNEP/OzL.Pro/ExCom/95/59

UNEP/OzL.Pro/ExCom/95/62

UNEP/OzL.Pro/ExCom/95/69

UNEP/OzL.Pro/ExCom/95/71 (the Cook Islands, Kiribati, the Marshall Islands, Micronesia (Federated States of), Nauru, Niue, Palau, Samoa, Solomon Islands, Tonga, Tuvalu, and Vanuatu)

UNEP/OzL.Pro/ExCom/95/72

UNEP/OzL.Pro/ExCom/95/73

UNEP/OzL.Pro/ExCom/95/74

UNEP/OzL.Pro/ExCom/95/80

UNEP/OzL.Pro/ExCom/95/20 or UNEP/OzL.Pro/ExCom/95/21

UNEP/OzL.Pro/ExCom/95/52

UNEP/OzL.Pro/ExCom/95/24

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.