| NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/87/4 22 de junio de 2021 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
  PARA LA APLICACIÓN DEL
  PROTOCOLO DE MONTREAL
Octogésima séptima Reunión

Montreal, 28 de junio -2 de julio de 2021

# Informe sobre saldos y disponibilidad de recursos

# Introducción

- Este documento presenta una síntesis de los ajustes financieros indicados por los organismos bilaterales y de ejecución conforme a lo acordado por la Secretaría. Incluye datos estadísticos de todos los proyectos con saldos que se han retenido durante más de 12 meses después de la terminación del proyecto, de conformidad con lo requerido en las decisiones 28/7 y 56/2 c). Se ocupa de los saldos que habrán de devolverse de los proyectos de conformidad con las decisiones pertinentes (mencionados como proyectos “por decisión” en el presente documento). Indica el nivel de recursos de que dispone el Comité Ejecutivo en efectivo y pagarés, según lo registrado en el documento sobre la situación de las contribuciones y los desembolsos, como se requiere en la decisión 41/92 b), y presenta una recomendación.

- Este documento también contiene los siguientes cuatro anexos:

Anexo I	 Cantidades retenidas por los organismos de ejecución y bilaterales de proyectos terminados

Anexo II	 Cantidades retenidas por los organismos de ejecución y bilaterales de proyectos “por decisión”

Anexo III	 Cantidades retenidas por los organismos de ejecución y bilaterales para los proyectos financiados con contribuciones adicionales

Anexo IV	 Devoluciones de fondos por los organismos de ejecución y bilaterales de proyectos terminados, “por decisión” y proyectos financiados con contribuciones voluntarias adicionales

# En los anexos I, II y III se dan explicaciones sobre las demoras en el desembolso de los fondos comprometidos o la devolución de los fondos no comprometidos.

Fondos que se han de devolver a la 87ª reunión

# El total de fondos a devolver asciende a 2 315 105 $EUA (es decir, 6 747 $EUA por parte de los organismos bilaterales y 2 308 358 $EUA por parte de los organismos de ejecución) procedentes de proyectos terminados, “por decisión” y financiados con contribuciones adicionales.

Fondos que han de devolver los organismos de ejecución

# El monto total de fondos que los organismos de ejecución han de devolver asciende a 2 308 358 $EUA, como se muestra en la tabla 1.

# Tabla 1. Fondos que los organismos de ejecución han de devolver a la 87ª reunión ($EUA)

| Organismo | Costo del proyecto | Gastos de apoyo al organismo | Costo total |
| --- | --- | --- | --- |
| PNUD | 58 511 | 4 199 | 62 710 |
| PNUMA | 1 867 022 | 148 337 | 2 015 359 |
| ONUDI | 214 743 | 15 546 | 230 289 |
| Total | 2 140 276 | 168 082 | 2 308 358 |

# En la tabla 2 se presenta información sobre los saldos de proyectos terminados, “por decisión” y financiados con contribuciones voluntarias adicionales que están en poder de los organismos de ejecución.

Tabla 2. Saldos de proyectos terminados, “por decisión” y financiados con contribuciones voluntarias adicionales en poder de los organismos de ejecución (incluidos los gastos de apoyo de los organismos)

| Año de terminación | PNUD |  | PNUMA |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Número | ($EUA) | Número | ($EUA) | Número | ($EUA) | Número | ($EUA) |
| Proyectos terminados hace más de dos años |  |  |  |  |  |  |  |  |
| 2016 | 0 | 0 | 1 | 68 727 | 0 | 0 | 1 | 68 727 |
| 2017 | 0 | 0 | 3* | 8 591 | 0 | 0 | 3 | 8 591 |
| 2018 | 0 | 0 | 3 | 32 054 | 0 | 0 | 3 | 32 054 |
| 1º ene. al 31 mayo 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Subtotal | 0 | 0 | 7 | 109 372 | 0 | 0 | 7 | 109 372 |
| Proyectos terminados hace menos de dos años |  |  |  |  |  |  |  |  |
| 1 junio al 31 dic. 2019 | 15 | 4 507 300 | 7 | 444 737 | 4 | 14 134 | 26 | 4 966 171 |
| Subtotal | 15 | 4 507 300 | 7 | 444 737 | 4 | 14 134 | 26 | 4 966 171 |
| Total | 15 | 4 507 300 | 14 | 554 109 | 4 | 14 134 | 33 | 5 075 543 |
| Proyectos “por decisión” (en curso) |  |  |  |  |  |  |  |  |
|  | 1 | 160 869 | 4 | 293 788 | 0 | 0 | 5 | 454 657 |
| Contribuciones voluntarias adicionales |  |  |  |  |  |  |  |  |
|  | 0 | 0 | 1 | 10 110 | 1 | 2 132 | 2 | 12 242 |
| Gran total | 16 | 4 668 169 | 19 | 858 006 | 5 | 16 266 | 40 | 5 542 441 |

* Incluyendo un proyecto de encuesta sobre las alternativas a las SAO

Fondos que han de devolver los organismos bilaterales

# El total de fondos que deben devolver los organismos bilaterales asciende a 6 747 $EUA, que se componen de 6 247 $EUA, más los gastos de apoyo del organismo de 500 $EUA para Francia.

Disponibilidad de recursos

# El documento sobre la situación de las contribuciones y los desembolsos indica un saldo disponible de 334 427 526 $EUA al 9 de junio de 2021. El saldo total devuelto por los organismos bilaterales y de ejecución a la 87ª reunión asciende a 2 308 358 $EUA. Por lo tanto, el nivel total de recursos disponibles para las aprobaciones en la 87ª reunión asciende a 336 735 884 $EUA.

Comentarios de la Secretaría

# La Secretaría recordó a los organismos bilaterales y de ejecución que los saldos relacionados con los proyectos “por decisión” y los terminados hace un año y más deberían devolverse al Fondo Multilateral lo antes posible.

# Considerando que el nivel total de fondos para proyectos y actividades presentados a la 87ª reunión asciende a 22 042 297 $EUA, incluidos los gastos de apoyo a los organismos, los recursos disponibles son suficientes para las aprobaciones previstas en la 87ª reunión.

Recomendaciones

# Si lo juzga oportuno, el Comité Ejecutivo podrá:

  - Tomar nota de:

- El informe sobre saldos y recursos disponibles que se recoge en el documento UNEP/OzL.Pro/ExCom/87/4;

- Que el nivel neto de fondos que los organismos de ejecución devuelven a la 87ª reunión asciende a 2 308 358 $EUA, que comprenden 58 511 $EUA, más gastos de apoyo al organismo de 4 199 $EUA del PNUD; 1 867 022 $EUA, más gastos de apoyo al organismo de 148 337 $EUA del PNUMA; y 214 743 $EUA, más gastos de apoyo al organismo de 15 546 $EUA de la ONUDI;

- Que el PNUMA tenía saldos de 109 372 $EUA, que incluían los gastos de apoyo a los organismos, para siete proyectos terminados en dos años anteriores, que incluían un proyecto de encuesta sobre alternativas a las SAO con saldos de 
434 $EUA, que incluían los gastos de apoyo a los organismos, y 10 110 $EUA, que incluían los gastos de apoyo al organismo, para un proyecto financiado con contribuciones voluntarias adicionales;

- Que la ONUDI retuvo saldos de 2 132 $EUA, incluidos los gastos de apoyo al organismo, para un proyecto financiado con contribuciones voluntarias adicionales; y

- Que el nivel neto de fondos que ha de devolver el Gobierno de Francia en 
la 87a reunión es de 6 247 $EUA, más gastos de apoyo al organismo de 500 $EUA.

## Pedir:

    - Que los organismos bilaterales y de ejecución procedan al desembolso o a la cancelación de los fondos comprometidos y no comprometidos que no eran necesarios para los proyectos terminados y los proyectos terminados "por decisión del Comité Ejecutivo" y que devuelvan los saldos asociados en la 88ª reunión;

### Que el PNUMA devuelva en la 88ª reunión el saldo de un proyecto de encuesta sobre alternativas a las SAO terminado hace más de dos años, de acuerdo con la decisión 80/75 c) i), y el saldo de un proyecto terminado financiado con contribuciones voluntarias adicionales;

### Que el PNUMA proceda al desembolso o cancele los compromisos de los seis proyectos restantes terminados hace más de dos años, y que devuelva los saldos en la 88ª reunión;

### Que la ONUDI devuelva en la 88ª reunión el saldo de un proyecto terminado financiado con las contribuciones voluntarias adicionales; y

### Que el Tesorero realice el seguimiento con el Gobierno de Francia sobre la devolución en efectivo de la cantidad de 6 747 $EUA mencionada en el subpárrafo a) v).

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 87th meeting (US $) | Balances committed as per 87th meeting (US $) | Balances not-committed as per 87th meeting (US $) | Support cost on balances committed & not committed as per 87th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | Nov-19 | 57,000 | 56,359 | 641 |  | 58 |  |  |  |
| BRA/PHA/74/INV/307 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | Dec-19 | 3,000,000 | 1,979,026 | 1,020,974 |  | 76,573 |  |  | 84/32(b)(iii) and 85/5(a)(ii) |
| BRA/PHA/75/INV/315 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | Dec-19 | 1,470,700 | 437,803 | 1,032,897 |  | 77,468 |  |  | 84/32(b)(iii) and 85/5(a)(ii) |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 179,857 | 174,475 | 5,382 |  | 377 |  |  |  |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 2,000,000 | 1,857,930 | 142,070 |  | 10,655 |  |  | 82/72(a)(iv) |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 716,400 | 288,322 | 428,078 |  | 32,106 |  |  | 82/72(a)(iv) |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 35,639 | 24,211 |  | 2,179 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 111,244 | 48,506 |  | 3,396 |  |  |  |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | Dec-19 | 347,194 | 343,303 | 3,891 |  | 272 |  |  |  |
| MDV/REF/76/DEM/30 | Demonstration project for HCFC-free low-global warming potential alternatives in refrigeration in fisheries sector | Dec-19 | 141,000 | 139,472 | 1,528 |  | 138 |  |  |  |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 3,800,000 | 3,456,632 | 343,368 |  | 25,753 |  |  | 84/22(b) and (c) |
| MEX/PHA/75/INV/178 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 1,122,503 | 0 | 1,122,503 |  | 84,188 |  |  | 84/22(b) and (c) |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 92,000 | 77,893 | 14,107 |  | 1,058 |  |  |  |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 33,600 | 30,916 | 2,684 |  | 242 |  |  |  |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 131,500 | 129,642 | 1,858 |  | 139 |  |  |  |
| TOTAL UNDP |  |  |  |  | 4,192,698 |  | 314,602 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Dec-19 | 375,000 | 342,491 | 27,696 |  | 3,600 |  |  | 83/37(c) and 85/18(b) |
| BAH/PHA/68/TAS/28 | HCFC phase-out management plan (stage I, first tranche) (policy, refrigeration servicing, monitoring and verification) | Dec-18 | 120,000 | 116,882 | 3,118 |  | 405 |  |  |  |
| CHI/PHA/76/TAS/193 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | Dec-17 | 53,000 | 52,493 | 507 |  | 66 |  |  | 76/45(a)(iii) and 81/14(b)(ii) |
| GBS/PHA/71/TAS/17 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 52,000 | 29,079 | 22,921 |  | 2,980 |  |  |  |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | Dec-19 | 9,974,259 | 8,055,902 | 307,619 |  | 24,610 |  |  |  |
| GUY/PHA/75/TAS/27 | HCFC phase-out management plan (stage II, first tranche) | Oct-19 | 55,500 | 50,000 | 5,500 |  | 715 |  |  |  |
| HAI/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 40,000 | 19,591 | 20,409 |  | 2,653 |  |  |  |
| IRQ/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Dec-18 | 115,000 | 110,266 | 4,734 |  | 582 |  |  |  |
| KUW/PHA/52/TAS/10 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Jan-16 | 232,912 | 172,092 | 60,820 |  | 7,907 |  |  | 70/7(b)(ii)a. |
| KUW/REF/75/TAS/29 | Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling) | Jun-18 | 27,223 | 6,679 | 20,544 |  | 2,671 |  |  | 82/24(c)(ii) and 83/38(b) |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | Dec-19 | 88,748 | 69,423 | 19,325 |  | 0 |  |  |  |
| PAR/PHA/63/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | Jun-17 | 146,500 | 139,788 | 6,712 |  | 873 |  |  |  |
| PAR/SEV/77/INS/36 | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | Dec-19 | 85,000 | 78,292 | 6,708 |  | 0 |  |  |  |
| STL/SEV/75/TAS/24 | Survey of ODS alternatives at the national level | Dec-17 | 35,000 | 31,609 | 384 |  | 50 |  |  | 80/75(c)(i) |
| TOTAL UNEP |  |  |  |  | 506,997 |  | 47,112 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| GLO/REF/76/DEM/333 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | Jul-19 | 345,000 | 339,533 | 5,467 |  | 383 | 2 | 88th meeting | 84/24(b) |
| MLW/PHA/77/INV/40 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 60,000 | 59,885 | 115 |  | 10 | 2 | 88th meeting |  |
| SEN/PHA/65/INV/31 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 200,000 | 199,292 | 708 |  | 53 | 2 | 88th meeting |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,035,702 | 6,918 |  | 484 | 2 | 88th meeting |  |
| TOTAL UNIDO |  |  |  |  | 13,207 |  | 927 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 87th meeting (US $) | Balances committed as per 87th meeting (US $) | Balances not- committed as per 87th meeting (US $) | Support cost on balances committed and not-committed as per 87th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,340,255 | 150,345 |  | 10,524 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 150,345 |  | 10,524 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| QAT/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 87th meeting | 105,000 | 38,955 | 66,045 |  | 8,586 |  |  |  |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 165,806 | 48,750 |  | 6,039 |  |  |  |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 87th meeting | 56,726 | 4,014 | 39,000 |  | 4,832 |  |  |  |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 14,509 | 107,250 |  | 13,286 |  |  |  |
| TOTAL UNEP |  |  |  |  | 261,045 |  | 32,743 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS

| CODE | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 87th meeting (US $) | Balances committed as per 87th meeting (US $) | Balances not- committed as per 87th meeting (US $) | Support cost on balances committed and not-committed as per 87th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ZIM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down |  | 150,000 | 140,551 | 9,449 |  | 661 |  |  |  |
| TOTAL UNEP |  |  |  |  | 9,449 |  | 661 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| LEB/REF/80/PRP/01+ | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration | 85th meeting | 30,000 | 28,008 | 1,992 |  | 139 | 2 | 88th meeting | 84/2(b)(ii) |
| TOTAL UNIDO |  |  |  |  | 1,992 |  | 139 |  |  |  |

i*: 2: Financial completion initiated; 3: Financial completion to be initiated after settlement of all pending issues; 4: Project is ongoing; 5: Funds were not transferred

Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| COL/PHA/75/TAS/94 | HCFC phase-out management plan (stage II, first tranche) (technical assistance for fire protection sector) | 2 | 0 | 2 |
| COS/REF/57/PRP/41 | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | 4,883 | 366 | 5,249 |
| COS/REF/74/PRP/51 | Preparation of a demonstration project for the transition of HCFC-22-based refrigerant unit to NH3 system in cold chambers | 1 | 0 | 1 |
| GHA/SEV/76/INS/41 | Extension of the institutional strengthening project (phase XII: 1/2017-12/2018) | 3,395 | 238 | 3,633 |
| PAK/SEV/77/INS/96 | Extension of the institutional strengthening project (phase IX: 4/2017-3/2019) | 569 | 40 | 609 |
| PAN/SEV/75/INS/42 | Extension of institutional strengthening project (phase VII: 12/2015-11/2017) | 184 | 13 | 197 |
| STK/PHA/64/TAS/16 | HCFC phase-out management plan (stage I, first tranche) | 58 | 5 | 63 |
| TLS/PHA/72/PRP/11 | Preparation of a HCFC phase-out management plan (stage II) | 5,000 | 350 | 5,350 |
| TLS/PHA/80/INV/18 | HCFC phase-out management plan (stage I, third tranche) | 4,030 | 363 | 4,393 |
| TRI/PHA/64/INV/26 | HCFC phase-out management plan (foam sector) (stage I, first tranche) | -547 | -41 | -588 |
| TRI/SEV/79/INS/34 | Extension of the institutional strengthening project (phase IX: 1/2018-12/2019) | 381 | 27 | 408 |
| Total completed projects |  | 17,956 | 1,360 | 19,316 |
| DOM/REF/80/PRP/01+ | Project preparation for conversion from HFC-134a to HC-290 in the manufacture of commercial refrigerators at Farco | 18,428 | 1,290 | 19,718 |
| EGY/FOA/80/PRP/01+ | Project preparation for conversion from HFC-134a to HFO-1234ze and other liquid HFOs in the manufacture of polyurethane foam and spray foam | 12,036 | 843 | 12,879 |
| ZIM/REF/80/PRP/02+ | Project preparation for elimination of HFC-134a in the manufacture of domestic refrigerators at Capri | 10,091 | 706 | 10,797 |
| Total “additional voluntary contributions” projects |  | 40,555 | 2,839 | 43,394 |
| TOTAL UNDP |  | 58,511 | 4,199 | 62,710 |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 4,813 | 626 | 5,438 |
| BHU/SEV/79/INS/27 | Extension of institutional strengthening project (phase VII: 12/2017-11/2019) | 336 | 0 | 336 |
| CHI/PHA/73/TAS/185 | HCFC phase-out management plan (stage I, third tranche) | 248 | 32 | 280 |
| CPR/PHA/74/TAS/559 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector including enabling programme) | 5,392 | 603 | 5,995 |
| DOM/PHA/69/TAS/52 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 8,816 | 1,146 | 9,962 |
| ECU/SEV/76/INS/62 | Extension of institutional strengthening project (phase VI: 5/2016-4/2018) | 23,774 | 0 | 23,774 |
| GLO/SEV/80/TAS/341 | Compliance Assistance Programme: 2018 budget | 158,314 | 12,665 | 170,979 |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | 1,610,738 | 128,859 | 1,739,597 |
| MEX/PHA/77/TAS/184. | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 1,694 | 220 | 1,914 |
| PAN/PHA/70/TAS/35 | HCFC phase-out management plan (stage I, second tranche) | 2,017 | 262 | 2,279 |
| PAN/PHA/74/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | 1,863 | 242 | 2,105 |
| PER/PHA/68/TAS/47 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | 7,091 | 922 | 8,013 |
| PHI/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | 9,651 | 0 | 9,651 |
| Total completed projects |  | 1,834,746 | 145,578 | 1,980,324 |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 19,118 | 2,368 | 21,486 |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 136 | -987 | -851 |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 8,641 | 1,070 | 9,711 |
| Total “by decision” projects |  | 27,895 | 2,452 | 30,347 |
| GHA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 575 | 40 | 615 |
| KAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,082 | 146 | 2,228 |
| LES/SEV/80/TAS/04+ | Enabling activities for HFC phase-down | 468 | 33 | 501 |
| TON/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 1,256 | 88 | 1,344 |
| Total “additional voluntary contributions” projects |  | 4,381 | 307 | 4,688 |
| TOTAL UNEP |  | 1,867,022 | 148,337 | 2,015,359 |
| ARG/PHA/80/TAS/186 | HCFC phase-out management plan (stage II, first tranche) (monitoring and reporting of HCFC-22 production) | 1,705 | 119 | 1,824 |
| ASP/REF/76/DEM/60 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 3,550 | 249 | 3,799 |
| BDI/PHA/65/INV/29 | HCFC phase-out management plan (stage I, first tranche) | 152 | 14 | 166 |
| BEN/PHA/76/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 51 | 4 | 55 |
| ECU/PHA/82/INV/70 | HCFC phase-out management plan (stage I, fourth tranche) | 171 | 12 | 183 |
| ECU/PHA/82/PRP/68 | Preparation of a HCFC phase-out management plan (stage II) | 67 | 5 | 72 |
| EGY/REF/75/TAS/127 | Feasibility study addressing district cooling | 2,435 | 219 | 2,654 |
| GBS/PHA/77/INV/21 | HCFC phase-out management plan (stage I, third tranche) | 229 | 20 | 249 |
| GUA/PHA/81/INV/51 | HCFC phase-out management plan (stage I, fourth tranche) | 169 | 13 | 181 |
| GUA/PHA/82/PRP/55 | Preparation of a HCFC phase-out management plan (stage II) | 82 | 6 | 88 |
| MDN/PHA/79/INV/39 | HCFC phase-out management plan (phase I, seventh tranche) | 70 | 5 | 75 |
| MEX/PRO/83/PRP/192 | Project preparation for the control of HFC-23 by-product emissions in the HCFC production sector | 307. | 21 | 328 |
| MEX/SEV/79/INS/186 | Extension of institutional strengthening project (phase XIII: 7/2017-6/2019) | 328 | 22 | 350 |
| MLW/PHA/81/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | 270 | 19 | 289 |
| MOG/PHA/75/INV/11 | HCFC phase-out management plan (stage I, third tranche) | 729 | 55 | 784 |
| MOR/FOA/75/DEM/74 | Demonstration of the use of low cost pentane foaming technology for the conversion to non-ODS technologies in polyurethane foams at small- and medium-sized enterprises | 4,303 | 301 | 4,604 |
| NIR/PHA/71/INV/136 | HCFC phase-out management plan (stage I, third tranche) (refrigeration air-conditioning manufacturing and coordination) | 1,082 | 81 | 1,163 |
| QAT/SEV/79/INS/22 | Renewal of institutional strengthening project (phase IV: 8/2017-7/2019) | 29,123 | 2,038 | 31,161 |
| SAU/FOA/76/DEM/27 | Demonstration project for the phase-out of HCFCs by using HFO as foam blowing agent in the spray foam applications in high ambient temperatures | 201 | 19 | 220 |
| SUD/PHA/80/INV/42 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 150 | 10 | 160 |
| TUN/FOA/77/PRP/72 | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) | 33,747 | 2,363 | 36,110 |
| TUN/PHA/72/INV/58 | HCFC phase-out management plan (stage I, first tranche) (solvent sector plan) | 9,465 | 662 | 10,127 |
| TUR/PHA/75/INV/108 | HCFC phase-out management plan (stage I, second tranche) (technical assistance for small and medium enterprises in the foam sector) | 22,029 | 1,540 | 23,569 |
| URT/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 152 | 11 | 163 |
| YUG/PHA/82/TAS/49 | Verification report on the implementation of the HCFC phase-out management plan | 438 | 39 | 477 |
| Total completed projects |  | 111,003 | 7,848 | 118,851 |
| CPR/ARS/56/INV/473 | Sector plan for phase-out of CFCs consumption in MDI sector | 15,099 | 1,132 | 16,231 |
| QAT/PHA/65/INV/18 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 59,334 | 4,450 | 63,784 |
| QAT/PHA/65/INV/19 | HCFC phase-out management plan (stage I, first tranche) (sector conversion from HCFC-142b/HCFC-22 in the production of extruded polystyrene insulation boards to low GWP isobutene at Qatar Insulation, Orient Insulation and Al Kawthar Insulation) | 12,927 | 969 | 13,896 |
| Total “by decision” projects |  | 87,360 | 6,551 | 93,911 |
| CPR/FOA/81/PRP/05+ | Preparation for converting from HFC-134a to HFOs+CO2 with gluing technology in an extruded polystyrene foam manufacturer | 16,379 | 1,147 | 17,526 |
| MEX/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 1 | 0 | 1 |
| Total “additional voluntary contributions” projects |  | 16,380 | 1,147 | 17,527 |
| TOTAL UNIDO |  | 214,743 | 15,546 | 230,289 |
| TUN/PHA/76/INV/70 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 6,247 | 500 | 6,747 |
| TOTAL FRANCE |  | 6,247 | 500 | 6,747 |

En junio y julio de 2021 se celebrarán reuniones en línea y se llevará a cabo el proceso de aprobación entre períodos de sesiones, debido al coronavirus (COVID-19).

Los datos presentados se basan en el formato de presentación de informes que se ha elaborado en respuesta a la decisión 31/2.

UNEP/OzL.Pro/ExCom/87/3.

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5 project is ongoing; 6 Funds were not transferred.