| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/86/4 6 November 2020 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
 THE MULTILATERAL FUND FOR THE
 IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-sixth Meeting

Montreal, 2-6 November 2020

Postponed to 8-12 March 2021

# report on balances and availability of resources

# Introduction

- This document presents a summary of financial adjustments indicated by the bilateral (BAs) and implementing agencies (IAs) as agreed by the Secretariat. It includes statistical data from all projects with balances that have been held for over 12 months following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to relevant decisions (referred to as “by-decision” projects in this document). It indicates the level of resources available to the Executive Committee in cash as recorded in the Status of contributions and disbursements document, as required by decision 41/92(b), and presents a recommendation.

- This document also contains the following four annexes:

Annex I	Amounts held by IAs and BAs for completed projects

Annex II 	Amounts held by IAs and BAs for by-decision projects

Annex III 	Amounts held by IAs and BAs for the additional contributions projects

Annex IV	Fund returns by IAs and BAs from completed, on-going, by-decision, survey of ODS alternatives and additional voluntary contributions projects.

# Annexes I, II and III provide explanations on the delays in disbursing committed amounts or returning not-committed amounts.

Funds to be returned to the 86th meeting

# The total funds to be returned amount to US $2,573,517 (i.e. US $142 by BAs and US $2,573,375 by IAs) from completed, by-decision, survey of ODS alternatives and additional contributions projects.

Funds to be returned by IAs

# The total funds to be returned by IAs amount to US $2,573,375 as shown in Table 1.

# Table 1. Funds to be returned by IAs to the 86th meeting (US $)

| Agency | Project cost | Agency support cost | Total cost |
| --- | --- | --- | --- |
| UNDP | 756,229 | 55,951 | 812,180 |
| UNEP | 686,656 | 61,080 | 747,736 |
| UNIDO | 794,898 | 57,619 | 852,517 |
| World Bank | 108,881 | 52,061 | 160,942 |
| Total | 2,346,664 | 226,711 | 2,573,375 |

# Table 2 presents information on balances of completed, by-decisions and additional voluntary contributions projects that are withheld by the IAs.

Table 2. Balances of completed, by-decision, and additional voluntary contributions projects withheld by IAs (including agency support costs)

| Year completed | UNDP |  | UNEP |  | UNIDO |  | World Bank |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Number | (US $) | Number | (US $) | Number | (US $) | Number | (US $) | Number | (US $) |
| Projects completed over two years ago |  |  |  |  |  |  |  |  |  |  |
| 2017 |  |  |  |  | 1 | 38 |  |  | 1 | 38 |
| 1 Jan to 31 Oct 2018 |  |  |  |  |  |  |  |  |  |  |
| Sub-total | 0 | 0 | 0 | 0 | 1 | 38 | 0 | 0 | 1 | 38 |
| Projects completed in less than two years ago |  |  |  |  |  |  |  |  |  |  |
| 1 Nov to 31 Dec 2018 |  |  |  |  | 1 | 3,226 |  |  | 1 | 3,226 |
| 2019 | 20 | 5,154,243 |  |  | 15 | 93,862 |  |  | 35 | 5,248,105 |
| Sub-total | 20 | 5,154,243 |  |  | 16 | 97,088 |  |  | 36 | 5,251,331 |
| Total | 20 | 5,154,243 | 0 | 0 | 17 | 97,126 | 0 | 0 | 37 | 5,251,369 |
| By-decisions projects (ongoing) |  |  |  |  |  |  |  |  |  |  |
|  | 1 | 185,828 | 2 | 164,077 | 5 | 991,301 |  |  | 8 | 1,341,206 |
| Additional voluntary contributions |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | 2 | 6,637 |  |  | 2 | 6,637 |
| Grand total | 21 | 5,340,071 | 2 | 164,077 | 24 | 1,095,064 | 0 | 0 | 47 | 6,599,212 |

Funds to be returned by BAs

# The total funds to be returned by BAs amount to US $142 as shown in Table 3.

Table 3. Funds to be returned by BAs to the 86th meeting (US $)

| Agency | Project cost | Agency support cost | Total |
| --- | --- | --- | --- |
| Japan | 126 | 16 | 142 |

## Table 4 presents the balances from projects that are being held by BAs.

Table 4. Balances held by BAs (US $)

| Agency | Project cost | Agency support cost | Total |
| --- | --- | --- | --- |
| Italy | 5,000 | 350 | 5,350 |
| France | 9,964 | 1,261 | 11,225 |

Availability of resources

# The Status of contributions and disbursements document indicates an available balance of US $324,044,205 as at 30 October 2020. The total balance returned by BAs and IAs, to the 86th meeting amounts to US $2,573,517. Therefore, the total level of resources available for approvals at the 
86th meeting, amounts to US $326,617,722.

Secretariat’s comments

# The Secretariat reminded BAs and IAs that balances of by-decisions projects and projects completed one year ago and more, should be returned to the Multilateral Fund as soon as possible.

# Considering that the total level of funding for projects and activities submitted to the 86th meeting amounts to US $58,098,526 including agency support costs, there are sufficient resources available for approvals at the 86th meeting.

Recommendations

# The Executive Committee may wish:

  - To note:

- The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/86/4;

- That the net level of funds being returned at the 86th meeting by the implementing agencies was US $2,573,375, consisting of US $756,229, plus agency support costs of US $55,951 from UNDP; US $686,656, plus agency support costs of US $61,080 from UNEP; US $794,898, plus agency support costs of US $57,619 from UNIDO; and US $108,881, plus agency support cost of US $52,061 from the World Bank.

- That UNIDO held balances of US $38, including agency support costs, for one project completed over two years previously and US $6,637, including agency support costs, for two projects funded using the additional voluntary contributions;

- That the net level of funds being returned at the 86th meeting by the Government of Japan was US $126, plus agency support costs of US $16;

- That the Government of Italy held balances of US $5,350, including agency support costs, for one project funded using the additional voluntary contributions;

## To request:

    - Bilateral and implementing agencies to proceed with disbursement or to cancel committed and not-committed funds that were not needed for completed projects and for projects completed “by decision of the Executive Committee” and to return the associated balances to the 87th meeting;

(ii)	UNIDO to return to the 87th meeting the balance of two completed project funded using the additional voluntary contributions;

    - UNIDO to proceed with disbursement or to cancel commitments for one project completed over two years previously, and to return balances to the 87th meeting;

    - The Government of Italy to return to the 87th meeting the balance of one completed project funded using the additional voluntary contributions; and

    - The Treasurer to follow up with the Government of Japan, on the return, in cash, of the amount of US $142 referred to in sub-paragraph (a)(iv) above.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 86th meeting (US $) | Balances committed as per 86th meeting (US $) | Balances not-committed as per 86th meeting (US $) | Support cost on balances committed & not committed as per 86th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ARG/SEV/76/INS/175 | Extension for institutional strengthening project (phase IX: 7/2016-6/2018) | Dec-19 | 398,806 | 398,062 | 744 |  | 52 |  |  |  |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | Nov-19 | 57,000 | 56,359 | 641 |  | 58 |  |  |  |
| BRA/PHA/74/INV/307 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | Dec-19 | 3,000,000 | 1,987,516 | 1,012,484 |  | 75,936 |  |  | 84/32(b)(iii) and 85/IAP/3 |
| BRA/PHA/75/INV/315 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | Dec-19 | 1,470,700 | 437,803 | 1,032,897 |  | 77,468 |  |  | 84/32(b)(iii) and 85/IAP/3 |
| BRA/PHA/80/TAS/318 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing, regulatory actions and project monitoring) | Dec-19 | 350,000 | 315,881 | 34,119 |  | 2,388 |  |  |  |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 179,857 | 174,000 | 5,857 |  | 410 |  |  |  |
| CUB/SEV/75/INS/54 | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | Dec-19 | 190,804 | 186,537 | 4,267 |  | 299 |  |  |  |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 2,000,000 | 1,497,978 | 502,022 |  | 37,652 |  |  | 82/72(a)(iv) |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 716,400 | 84,152 | 632,248 |  | 47,419 |  |  | 82/72(a)(iv) |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 55,584 | 4,266 |  | 384 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 111,244 | 48,506 |  | 3,396 |  |  |  |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | Dec-19 | 347,194 | 338,951 | 8,243 |  | 577 |  |  |  |
| MDV/REF/76/DEM/30 | Demonstration project for HCFC-free low-global warming potential alternatives in refrigeration in fisheries sector | Dec-19 | 141,000 | 126,879 | 14,121 |  | 1,271 |  |  |  |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 3,800,000 | 3,451,582 | 348,418 |  | 26,131 |  |  | 84/22(b) and (c) |
| MEX/PHA/75/INV/178 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 1,122,503 | 0 | 1,122,503 |  | 84,188 |  |  | 84/22(b) and (c) |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 92,000 | 77,893 | 14,107 |  | 1,058 |  |  |  |
| MOL/PHA/77/INV/34 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 104,850 | 103,670 | 1,180 |  | 106 |  |  |  |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 33,600 | 30,916 | 2,684 |  | 242 |  |  |  |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 131,500 | 129,642 | 1,858 |  | 139 |  |  |  |
| TRI/SEV/79/INS/34 | Extension of the institutional strengthening project (phase IX: 1/2018-12/2019) | Dec-19 | 85,000 | 81,349 | 3,651 |  | 256 |  |  |  |
| TOTAL UNDP |  |  |  |  | 4,794,815 |  | 359,428 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| ASP/REF/76/DEM/60 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Nov-19 | 325,000 | 321,293 | 3,707 |  | 259 | 4 | 87th meeting | 83/37(c) and 85/IAP/3 |
| BDI/PHA/65/INV/29 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 80,000 | 79,848 | 152 |  | 14 | 2 | 87th meeting |  |
| EGY/REF/75/TAS/127 | Feasibility study addressing district cooling | Dec-18 | 63,521 | 60,561 | 2,960 |  | 266 | 4 | 87th meeting | 82/24(c)(ii) |
| GAB/PHA/62/INV/27 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 130,000 | 125,336 | 4,664 |  | 420 | 4 | 87th meeting |  |
| GLO/REF/76/DEM/333 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | Jul-19 | 345,000 | 344,165 | 835 |  | 58 | 4 | 87th meeting | 84/24(b) |
| MEX/SEV/79/INS/186 | Extension of institutional strengthening project (phase XIII: 7/2017-6/2019) | Jun-19 | 316,160 | 316,133 | 27 |  | 2 | 2 | 87th meeting |  |
| MLW/PHA/77/INV/40 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 60,000 | 59,885 | 115 |  | 10 | 2 | 87th meeting |  |
| MOG/PHA/75/INV/11 | HCFC phase-out management plan (stage I, third tranche) | Aug-19 | 98,500 | 97,771 | 729 |  | 55 | 2 | 87th meeting |  |
| MOR/FOA/75/DEM/74 | Demonstration of the use of low cost pentane foaming technology for the conversion to non-ODS technologies in polyurethane foams at small- and medium-sized enterprises | Sep-19 | 280,500 | 276,197 | 4,303 |  | 301 | 2 | 87th meeting | 83/32/(c) |
| NIR/PHA/71/INV/136 | HCFC phase-out management plan (stage I, third tranche) (refrigeration air-conditioning manufacturing and coordination) | Dec-17 | 645,172 | 645,137 | 35 |  | 3 | 2 | 87th meeting |  |
| SAU/FOA/76/DEM/27 | Demonstration project for the phase-out of HCFCs by using HFO as foam blowing agent in the spray foam applications in high ambient temperatures | Oct-19 | 96,250 | 96,154 | 96 |  | 9 | 2 | 87th meeting |  |
| SEN/PHA/65/INV/31 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 200,000 | 199,292 | 708 |  | 53 | 2 | 87th meeting |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,035,702 | 6,918 |  | 484 | 2 | 87th meeting |  |
| SUD/PHA/80/INV/42 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Dec-19 | 40,000 | 39,846 | 154 |  | 11 | 2 | 87th meeting |  |
| TUN/FOA/77/PRP/72 | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) | Dec-19 | 60,000 | 26,257 | 33,743 |  | 2,362 | 4 | 87th meeting |  |
| TUN/PHA/72/INV/58 | HCFC phase-out management plan (stage I, first tranche) (solvent sector plan) | Dec-19 | 231,920 | 222,455 | 9,465 |  | 662 | 2 | 87th meeting |  |
| TUR/PHA/75/INV/108 | HCFC phase-out management plan (stage I, second tranche) (technical assistance for small and medium enterprises in the foam sector) | Dec-19 | 529,450 | 507,444 | 22,006 |  | 1,540 | 2 | 87th meeting |  |
| TOTAL UNIDO |  |  |  |  | 90,617 |  | 6,509 |  |  |  |
| FRANCE | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Dec-19 | 38,000 | 28,036 | 9,964 |  | 1,261 |  |  |  |
| TOTAL FRANCE |  |  |  |  | 9,964 |  | 1,261 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 86th meeting (US $) | Balances committed as per 86th meeting (US $) | Balances not- committed as per 86th meeting (US $) | Support cost on balances committed and not-committed as per 86th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,316,929 | 173,671 |  | 12,157 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 173,671 |  | 12,157 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 86th meeting | 375,000 | 325,844 | 49,156 |  | 6,390 |  |  | 83/37(c) and 85/IAP/3 |
| QAT/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 87th meeting | 105,000 | 8,955 | 96,045 |  | 12,486 |  |  | 82/34(f) and 84/36(c) |
| TOTAL UNEP |  |  |  |  | 145,201 |  | 18,876 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| CPR/ARS/56/INV/473 | Sector plan for phase-out of CFCs consumption in MDI sector | Dec-16 | 13,500,000 | 13,484,901 | 15,099 |  | 1,132 | 2 | 87th meeting | Agreed with agency at the Coordination Meeting (Feb 2014) |
| EGY/ARS/50/INV/92 | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Jul-19 | 5,899,000 | 5,780,662 | 118,338 |  | 8,875 | 4 | 88th meeting | 79/7(c) |
| EGY/PHA/82/INV/140 | HCFC phase-out management plan (stage I, third tranche) (enabling activities in the refrigeration and air-conditioning sector) | Dec-20 | 232,575 | 157,454 | 75,121 |  | 5,634 | 4 | 89th meeting | 82/72(a)(iv) |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Dec-18 | 4,353,530 | 3,871,862 | 481,669 |  | 36,125 | 4 | 89th meeting | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | Dec-18 | 2,161,581 | 1,929,667 | 231,914 |  | 17,394 | 4 | 89th meeting | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| TOTAL UNIDO |  |  |  |  | 922,141 |  | 69,160 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS

| CODE | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 86th meeting (US $) | Balances committed as per 86th meeting (US $) | Balances not- committed as per 86th meeting (US $) | Support cost on balances committed and not-committed as per 86th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| LEB/REF/80/PRP/01+ | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration | 85th meeting | 30,000 | 28,008 | 1,992 |  | 139 |  |  |  |
| MEX/SEV/80/TAS/02+ | Enabling activities for HFC phase-down |  | 220,000 | 215,789 | 4,211 |  | 295 |  |  |  |
| TOTAL UNIDO |  |  |  |  | 6,203 |  | 434 |  |  |  |
| ITALY |  |  |  |  |  |  |  |  |  |  |
| LES/SEV/80/TAS/03+ | Enabling activities for HFC phase-down |  | 40,000 | 35,000 | 5,000 |  | 350 |  |  |  |
| TOTAL ITALY |  |  |  |  | 5,000 |  | 350 |  |  |  |

Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND ODS ALTERNATIVES SURVEY PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| BAR/PHA/80/INV/27 | HCFC phase-out management plan (stage I, second tranche) | 1,822 | 164 | 1,986 |
| BGD/PHA/75/PRP/44 | Preparation of a HCFC phase-out management plan (stage II) | 3,597 | 252 | 3,849 |
| BGD/REF/75/PRP/43 | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | 198 | 14 | 212 |
| BGD/SEV/77/INS/47 | Renewal of the institutional strengthening project (phase VIII: 1/2017-12/2018) | 4,157 | 291 | 4,448 |
| COL/FOA/76/DEM/100 | Demonstration project to validate the use of hydrofluoro-olefins for discontinuous panels in Article 5 parties through the development of cost-effective formulations | 27 | 2 | 29 |
| COL/REF/75/DEM/97 | Demonstration of HC-290 (propane) as an alternative refrigerant in commercial air-conditioning manufacturing at Industrias Thermotar ltda | 434 | 30 | 464 |
| COL/SEV/74/INS/90 | Extension of institutional strengthening project (phase X: 11/2015-10/2017) | 8 | 1 | 9 |
| CPR/PHA/75/INV/569 | HCFC phase-out management plan (stage I, third tranche) (solvent sector) | 56 | 4 | 60 |
| IDS/PHA/71/INV/199 | HCFC phase-out management plan (air conditioning sector plan) (stage I, second tranche) | 133,894 | 10,042 | 143,936 |
| IDS/PHA/72/PRP/204 | Preparation of a HCFC phase-out management plan (stage II) | 1,763 | 123 | 1,886 |
| IND/FOA/72/PRP/455 | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | 430 | 30 | 460 |
| IND/PHA/72/PRP/452 | Preparation of a HCFC phase-out management plan (stage II) | 353 | 25 | 378 |
| IND/PHA/75/INV/463 | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | 41,838 | 3,138 | 44,976 |
| IND/REF/72/PRP/453 | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | 997 | 70 | 1,067 |
| IND/REF/72/PRP/459 | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | 3,709 | 260 | 3,969 |
| IND/SEV/72/INS/457 | Extension of institutional strengthening project (phase X: 4/2014-3/2016) | 136,656 | 9,566 | 146,222 |
| IRA/PHA/72/PRP/216 | Preparation of a HCFC phase-out management plan (stage II) | 863 | 60 | 923 |
| IRA/REF/72/PRP/217 | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | 3,142 | 220 | 3,362 |
| MAL/PHA/77/INV/184 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, management and coordination) | 328 | 25 | 353 |
| NIR/PHA/72/PRP/138 | Preparation of a HCFC phase-out management plan (stage II) | 27 | 2 | 29 |
| TRI/PHA/64/INV/26 | HCFC phase-out management plan (foam sector) (stage I, first tranche) | 30,600 | 2,295 | 32,895 |
| Total completed projects |  | 364,899 | 26,613 | 391,512 |
| IDS/PHA/76/INV/208 | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | 388,912 | 29,169 | 418,081 |
| Total “by decision” projects |  | 388,912 | 29,169 | 418,081 |
| PER/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,418 | 169 | 2,537 |
| Total “additional voluntary contributions” projects |  | 2,418 | 169 | 2,587 |
| TOTAL UNDP |  | 756,229 | 55,951 | 812,180 |
| AFG/PHA/72/TAS/16 | HCFC phase-out management plan (stage I, second tranche) | 3,869 | 503 | 4,372 |
| BAH/PHA/75/TAS/29 | HCFC phase-out management plan (stage I, second tranche) (policy, refrigeration servicing, monitoring and verification) | 47 | 6 | 53 |
| BKF/SEV/79/INS/36 | Extension of the institutional strengthening project (phase XII: 7/2017-6/2019) | 73 | 0 | 73 |
| BOT/PHA/80/TAS/20 | Verification report on the implementation of the HCFC phase-out management plan | 1,169 | 152 | 1,321 |
| BRU/PHA/75/TAS/19 | Verification report on the implementation of the HCFC phase-out management plan | 2,202 | 286 | 2,488 |
| CMR/SEV/80/INS/43 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | 23 | 0 | 23 |
| COI/PHA/77/TAS/25 | HCFC phase-out management plan (stage I, third tranche) | 223 | 29 | 252 |
| COI/PHA/80/TAS/26 | Verification report on the implementation of the HCFC phase-out management plan | 3,682 | 479 | 4,161 |
| DJI/PHA/80/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 4,621 | 601 | 5,222 |
| DMI/PHA/75/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | 3 | 0 | 3 |
| GAB/PHA/79/TAS/33 | HCFC phase-out management plan (stage I, third tranche) | 117 | 15 | 132 |
| GAB/PHA/80/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 4,626 | 601 | 5,227 |
| GBS/PHA/77/TAS/20 | HCFC phase-out management plan (stage I, third tranche) | 139 | 18 | 157 |
| GBS/SEV/77/INS/22 | Extension of the institutional strengthening project (phase V: 12/2016-11/2018) | 108 | 0 | 108 |
| GLO/SEV/73/TAS/323 | Compliance Assistance Programme: 2015 budget | 259,008 | 20,721 | 279,729 |
| GLO/SEV/75/TAS/329 | Compliance Assistance Programme: 2016 budget | 134,338 | 10,747 | 145,085 |
| GLO/SEV/77/TAS/336 | Compliance Assistance Programme: 2017 budget | 27,146 | 2,172 | 29,318 |
| GLO/SEV/80/TAS/341 | Compliance Assistance Programme: 2018 budget | 107,781 | 8,622 | 116,403 |
| GUA/SEV/61/INS/41 | Renewal of the institutional strengthening project (phase VII) | 1,484 | 0 | 1,484 |
| GUI/SEV/74/INS/30 | Extension of the institutional strengthening project (phase IX: 7/2015-6/2017) | 79 | 0 | 79 |
| GUY/PHA/74/TAS/24 | HCFC phase-out management plan (stage I, second tranche) | 435 | 57 | 492 |
| GUY/PHA/77/TAS/29 | Verification report on the implementation of the HCFC phase-out management plan | 5,255 | 683 | 5,938 |
| HON/PHA/63/TAS/35 | HCFC phase-out management plan (stage I, first tranche) | 1,629 | 212 | 1,841 |
| HON/PHA/70/TAS/38 | HCFC phase-out management plan (stage I, second tranche) | 3,912 | 509 | 4,421 |
| IRQ/SEV/76/INS/25 | Extension of institutional strengthening project (phase III: 5/2016-4/2018) | 7,200 | 0 | 7,200 |
| IVC/SEV/77/INS/42 | Extension of the institutional strengthening project (phase VIII: 1/2017-12/2018) | 104 | 0 | 104 |
| JAM/PHA/70/TAS/33 | HCFC phase-out management plan (stage I, second tranche) | 2,638 | 343 | 2,981 |
| MAS/SEV/70/INS/10 | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | 2,494 | 0 | 2,494 |
| MLW/PHA/77/TAS/39 | HCFC phase-out management plan (stage I, third tranche) | 5 | 1 | 6 |
| MOL/PHA/77/TAS/35 | HCFC phase-out management plan (stage II, first tranche) | 1,642 | 213 | 1,855 |
| MOZ/PHA/73/TAS/25 | HCFC phase-out management plan (stage I, second tranche) | 139 | 18 | 157 |
| NER/SEV/80/INS/33 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | 162 | 0 | 162 |
| NIU/SEV/75/INS/11 | Extension of the institutional strengthening project (phase VI: 12/2015-11/2017) | 5,000 | 0 | 5,000 |
| PER/SEV/68/INS/45 | Renewal of institutional strengthening project (phase IV: 1/2013-12/2014) | 1,357 | 0 | 1,357 |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 13,576 | 2,686 | 16,262 |
| SOM/SEV/77/INS/11 | Extension of the institutional strengthening project (phase III: 12/2016-11/2018) | 530 | 0 | 530 |
| STL/SEV/73/INS/23 | Renewal of institutional strengthening project (phase IX: 1/2015-12/2016) | 973 | 0 | 973 |
| SWA/PHA/77/TAS/23 | HCFC phase-out management plan (stage I, third tranche) | 168 | 22 | 190 |
| SWA/PHA/80/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 1,205 | 157 | 1,362 |
| TOG/PHA/80/TAS/31 | Verification report on the implementation of the HCFC phase-out management plan | 2,810 | 365 | 3,175 |
| TUV/SEV/76/INS/13 | Extension of the institutional strengthening project (phase VI: 1/2017-12/2018) | 1,130 | 0 | 1,130 |
| Total completed projects |  | 603,102 | 50,218 | 653,320 |
| ALG/SEV/74/TAS/82 | Survey of ODS alternatives at the national level | 50,000 | 6,500 | 56,500 |
| GUY/SEV/74/TAS/26 | Survey of ODS alternatives at the national level | 5,000 | 650 | 5,650 |
| IRQ/SEV/75/TAS/24 | Survey of ODS alternatives at the national level | 7,000 | 910 | 7,910 |
| JAM/SEV/74/TAS/34 | Survey of ODS alternatives at the national level | 18,029 | 2,344 | 20,373 |
| STL/SEV/75/TAS/24 | Survey of ODS alternatives at the national level | 3,008 | 391 | 3,399 |
| TRI/SEV/74/TAS/32 | Survey of ODS alternatives at the national level | 517 | 67 | 584 |
| Total survey of ODS alternatives |  | 83,554 | 10,862 | 94,416 |
| TOTAL UNEP |  | 686,656 | 61,080 | 747,736 |
| ARG/PHA/66/INV/169 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 175 | 13 | 188 |
| ARG/PRO/82/PRP/187 | Options for proposed projects to comply with the HFC-23 by-product control obligations under the Kigali Amendment | 184 | 13 | 197 |
| ARM/SEV/76/INS/17 | Extension of institutional strengthening project (phase V: 4/2017-3/2019) | 657 | 46 | 703 |
| BAH/PHA/68/INV/27 | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-22 from the manufacturing of central air-conditioning and window air-conditioning at Awal Gulf manufacturing company) | 208 | 15 | 223 |
| BAH/PHA/68/TAS/26 | HCFC phase-out management plan (stage I, first tranche) (national HCFC reclamation) | 1,075 | 75 | 1,150 |
| BOL/PHA/75/INV/44 | HCFC phase-out management plan (stage I, third tranche) | 296 | 27 | 323 |
| CHI/PHA/76/TAS/189 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 3 | 0.5 | 4 |
| CMR/PHA/64/INV/35 | HCFC phase-out management plan (refrigeration servicing sector plan) (stage I, first tranche) | 20,332 | 1,524 | 21,856 |
| CMR/PHA/76/INV/42 | HCFC phase-out management plan (refrigeration servicing sector plan) (stage I, third tranche) | 5,775 | 433 | 6,208 |
| CMR/PHA/80/INV/44 | HCFC phase-out management plan (refrigeration servicing sector plan) (stage I, fourth tranche) | 9,136 | 685 | 9,821 |
| DRK/PHA/73/TAS/60 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 4,047 | 283 | 4,330 |
| DRK/PHA/75/TAS/63 | HCFC phase-out management plan (stage I, second tranche) (policy, refrigeration servicing and monitoring) | 18 | 1 | 19 |
| ECU/PHA/76/INV/63 | HCFC phase-out management plan (stage I, third tranche) | 136 | 11 | 147 |
| ERI/PHA/77/INV/15 | HCFC phase-out management plan (stage I, second tranche) | 262 | 24 | 286 |
| GLO/REF/76/DEM/335 | Demonstration project for the introduction of trans-critical CO2 refrigeration technology for supermarkets (Argentina and Tunisia) | 318,347 | 22,284 | 340,631 |
| IRA/PHA/68/INV/209 | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | 11,981 | 899 | 12,880 |
| IRA/PHA/74/INV/220 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | 5,800 | 435 | 6,235 |
| IRA/PHA/77/INV/230 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 1,159 | 81 | 1,240 |
| MEX/PHA/64/INV/157 | HCFC phase-out management plan (umbrella project for conversion from HCFC-141b to cyclopentane insulation foam blowing technology at three refrigeration appliances manufacturing enterprises: Fersa, Frigopanel and Metalfrio) (stage I, first tranche) | 3,615 | 271 | 3,886 |
| MEX/PHA/75/INV/177 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, technical assistance and monitoring) | 11,701 | 878 | 12,579 |
| NIR/PHA/75/TAS/144 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration air-conditioning manufacturing sector) | 6,948 | 521 | 7,469 |
| OMA/PHA/80/TAS/34 | Verification report on the implementation of the HCFC phase-out management plan | 6,195 | 558 | 6,753 |
| SAU/FOA/62/INV/11 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Line #2 in Arabian Chemical Company | 257,256 | 19,294 | 276,550 |
| STL/PHA/76/INV/26 | HCFC phase-out management plan (stage I, third tranche) | 1 | 0 | 1 |
| SUD/PHA/80/TAS/41 | Verification report on the implementation of the HCFC phase-out management plan | 457 | 41 | 498 |
| TKM/PHA/82/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 13 | 1 | 14 |
| TOG/PHA/62/INV/22 | HCFC phase-out management plan (stage I, first tranche) | 106 | 8 | 114 |
| TUN/PHA/76/INV/67 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector, project management and audit) | 767 | 54 | 821 |
| TUN/PHA/77/PRP/71 | Preparation of a HCFC phase-out management plan (stage II) | 28,010 | 1,961 | 29,971 |
| UGA/PHA/77/INV/22 | HCFC phase-out management plan (stage I, second tranche) | 102 | 9 | 111 |
| YUG/PHA/71/INV/41 | HCFC phase-out management plan (stage I, second tranche) | 154 | 12 | 166 |
| YUG/PHA/79/INV/46 | HCFC phase-out management plan (stage I, third tranche) | 1,886 | 141 | 2,027 |
| Total completed projects |  | 696,802 | 50,599 | 747,401 |
| LEB/DES/73/DEM/83 | Pilot demonstration project on ODS waste management and disposal | 7,676 | 691 | 8,367 |
| TUR/PHA/74/PRP/105 | Preparation of a HCFC phase-out management plan (stage II) | 86,149 | 6,030 | 92,179 |
| Total “by decision” projects |  | 93,825 | 6,721 | 100,546 |
| GRN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 3,509 | 246 | 3,755 |
| VIE/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 762 | 53 | 815 |
| Total “additional voluntary contributions” projects |  | 4,271 | 299 | 4,570 |
| TOTAL UNIDO |  | 794,898 | 57,619 | 852,517 |
| GLO/SEV/82/TAS/348 | Core unit budget (2019) | 0 | 43,894 | 43,894 |
| IDS/PHA/64/INV/191 | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | 31,461 | 2,360 | 33,821 |
| IDS/PHA/71/INV/202 | HCFC phase-out management plan (foam sector plan) (stage I, second tranche) | 47,231 | 3,543 | 50,774 |
| IDS/PHA/76/INV/207 | HCFC phase-out management plan (stage I, third tranche) (foam sector) | 30,189 | 2,264 | 32,453 |
| TOTAL WORLD BANK |  | 108,881 | 52,061 | 160,942 |
| SAU/FOA/62/INV/14 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | 126 | 16 | 142 |
| TOTAL JAPAN |  | 126 | 16 | 142 |

Due to coronavirus disease (COVID-19).

The data presented are based on the reporting format that has been developed pursuant to decision 31/2.

UNEP/OzL.Pro/ExCom/86/3.

Subject to decision 84/2(b)(ii) which requested UNIDO to return to the 86th meeting the balance of two completed project funded using the additional voluntary contributions.

Committed balance for one project funded using the additional voluntary contributions.

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5 project is ongoing; 6 Funds were not transferred.