| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/29 19 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1–5 December 2025

Item 9(d) of the provisional agenda

projects recommended for individual consideration

# This document provides summary information on projects and activities submitted to the 97th meeting that are recommended for individual consideration, as listed in table 1.

# Table 1. Requests recommended for individual consideration

| Projects and activities | No. of countries | No. of funding requests | Amounts recommended (US $) | Amounts in principle (US $) |
| --- | --- | --- | --- | --- |
| Stage II/III of HPMPs | 7 | 17 | 11,037,261 | 26,609,648 |
| Tranches of approved HPMPs* | 4 | 13 | 30,370,328 |  |
| Tranche of an approved HFC-23 emission control plan | 1 | 1 | 134,300 |  |
| Stage I of KIPs | 12 | 31 | 4,370,748 | 8,430,919 |
| Tranches of approved KIPs | 1 | 3 | 6,507,851 |  |
| Additional activities to maintain energy efficiency in the servicing sector (decision 89/6)** | 1 | 1 | 135,479 |  |
| Pilot projects on energy efficiency (decisions 91/65) | 11 | 12 | 3,194,281 |  |
| Global pilot project for energy efficiency (decision 91/65) | -- | 1 | 727,600 |  |
| Pilot projects on energy efficiency (decisions 94/60) | 3 | 3 | 19,887,445 |  |
| Pilot project on energy efficiency (decisions 95/87) | 1 | 1 | 1,343,118 |  |
| CAP (2026 budget)*** | -- | 1 | 12,179,124 |  |
| Core unit costs (2026)**** | -- | 3 | 6,629,064 |  |
| Total |  | 87 | 96,516,599 |  |

* Argentina, China, Senegal and South Sudan

** Submitted as part of the HPMP tranche request for Senegal

*** Document UNEP/OzL.Pro/ExCom/97/83 conisdered under agenda item 9(e)

**** Document UNEP/OzL.Pro/ExCom/97/84 considered under agenda item 9(f)

Note: Funding amounts include agency support costs.

# Tables 2 to 4 provide more information on projects and activities recommended for individual consideration, as follows: table 2 lists requests for new stages of HCFC phase-out management plans (HPMPs), tranche requests under the approved HPMP stages, and a tranche request for an HFC-23 emission control plan; table 3 presents requests for stage I of Kigali HFC implementation plans (KIPs), a KIP request submitted with a pilot project on energy efficiency, and a tranche request under an approved KIP stage; and table 4 lists requests for stand-alone pilot projects related to energy efficiency in the servicing sector submitted in line with decision 91/65 and projects submitted in line with decisions 94/60 and 95/87 on the operational framework.

Table 2: HPMP stage and tranche requests and an HFC-23 emission control plan tranche request

| Country | Stage / Tranche # | Implementing and bilateral agencies | Doc. # | Para. # | Issue | Secretariat presentation (Y/N) |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | Stage III, 1st tranche | UNDP | 97/35 | 21-46 | Imports of HCFC-141b are not part of the HCFC baseline. | Y |
| Argentina | Stage II, 4th tranche | UNIDO Italy | 97/36 | 1-45 | Request for extension of stage II to December 2027. | Y |
|  | Stage III, 1st tranche | UNIDO | 97/36/ Add.1 | -- | Flexibility to use funding for servicing to assist aerosol enterprises. Need for further understanding of leakage rates, interventions to reduce them, and available low-GWP technologies for fisheries. | Y |
|  | HFC-23 plan, 2nd and 3rd tranches | UNIDO | 97/36 | 46-74 | No specific issue to consider. | N |
| Bangladesh | Stage III, 1st tranche | UNDP UNEP | 97/37 | -- | No specific issue to consider. | N |
| Cameroon | Stage III, 1st tranche | UNIDO | 97/42 | -- | No specific issue to consider. | N |
| China: |  |  | 97/44 |  |  |  |
| ‣ Overarching | Stage II | UNDP |  | 1-29 | No specific issue to consider. | Y |
| ‣ Sector plans:* |  |  |  |  |  |  |
| • XPS foam | 8th tranche | UNIDO Germany | 97/44 | 30-49 | No specific issue to consider. | N |
| • PU foam | 6th tranche | World Bank |  | 50-76 | No specific issue to consider. | N |
| • ICR | 6th tranche | UNDP |  | 77-97 | No specific issue to consider. | N |
| • RAC | 5th tranche | UNIDO Austria Italy |  | 98-146 | Approach to estimate HFCs phased in by assisted enterprises to meet the demand of HCFC-based manufacturing capacity converted to R-290 (decision 94/34(c)). | Y |
| • Solvent | 7th tranche | UNDP |  | 147-168 | No specific issue to consider. | N |
| • Servicing | 8th tranche | UNEP Germany Japan |  | 169-191 | No specific issue to consider. | N |
| Djibouti | Stage II, 1st tranche | UNEP | 97/47 | -- | No specific issue to consider. | N |
| Egypt | Stage III, 1st tranche | UNIDO UNEP | 97/49 | 1-52 | No specific issue to consider. | N |
| Mali | Stage II, 1st tranche | UNEP UNDP | 97/58 | -- | No specific issue to consider. | N |
| Senegal | Stage II 2nd and 3rd tranches | UNEP UNIDO | 97/73 | -- | Request for extension of stage II to December 2027. | Y |
| South Sudan | Stage I, 3rd tranche | UNEP UNDP | 97/78 | -- | Request for extension of stage I to December 2026. | Y |

* XPS=extruded polystyrene; PU=polyurethane; ICR=industrial and commercial refrigeration and air-conditioning; RAC=room air-conditioning manufacturing and heat pump water heaters; servicing=refrigeration and air-conditioning servicing and the national enabling programme

Table 3: KIP stage I and tranche requests, including a KIP request with an energy-efficiency project

| Country | Type of project | Implementing and bilateral agencies | Doc. # | Para. # | Issue | Secretariat presentation (Y/N) |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | Stage I, 1st tranche | UNDP | 97/35 | 47-101 | No specific issue to consider. | N |
| Botswana | Stage I, 1st tranche | UNEP UNIDO | 97/39 | -- | No specific issue to consider. | N |
| Eritrea | Stage I, 1st tranche | UNEP UNIDO | 97/51 | -- | 2024 consumption higher than Montreal Protocol target by 17 CO2-eq tonnes. | Y |
| Ethiopia | Stage I, 1st tranche | UNEP UNIDO | 97/52 | -- | No specific issue to consider. | N |
| Fiji | Stage I, 1st tranche | UNEP/ UNDP | 97/53 | -- | No specific issue to consider. | N |
| Guinea-Bissau | Stage I, 1st tranche | UNEP UNIDO | 97/56 | 20-70 | No specific issue to consider. | N |
| Mexico | Stage I, 2nd tranche | UNIDO UNDP UNEP | 97/60 | -- | Information on the monitoring of HFC consumption provided in line with decision 93/68(c)(vi) | Y |
| Mongolia | Stage I, 1st tranche | UNEP UNIDO | 97/61 | -- | 2025 quota higher than Montreal Protocol targets. | Y |
| Oman | Stage I, 1st tranche | UNEP UNIDO | 97/67 | -- | Use of “interim” HFC baseline. | Y |
| Serbia | Stage I, 1st tranche | UNIDO UNEP | 97/74 | 19-65 | No specific issue to consider. | N |
|  | Energy efficiency (dec.91/65) | UNIDO |  | 66-94 |  | Y |
| Somalia | Stage I, 1st tranche | UNIDO UNEP | 97/76 | -- | Country is requesting change of baseline. | Y |
| South Africa | Stage I, 1st tranche | UNIDO | 97/77 | 27-89 | Request for project in the local installation and assembly sector considered on a case-by-case basis under decision 92/39. Country to request revision of HFC consumption, resulting in lower baseline. | Y |
| Tanzania (United Republic of) | Stage I, 1st tranche | UNEP UNIDO | 97/82 | -- | No specific issue to consider. | N |

Table 4: Stand-alone projects related to energy efficiency*

| Country | Implementing and bilateral agencies | Doc. # | Para. # | Project title / details |
| --- | --- | --- | --- | --- |
| Albania | UNIDO | 97/34 | -- | Introduction of leakage detection systems for RAC equipment (decision 91/65) |
| Bosnia and Herzegovina | UNIDO | 97/38 | -- | Improvement of MEPS and energy labelling in the country’s RAC sector, demonstration project to replace R-404A with R-290 plug-in units in commercial refrigeration equipment, and demonstration project on leak detection in stationary RAC systems (decision 91/65) |
| Dominican Republic | UNIDO UNEP | 97/48 | -- | Developing roadmap for MEPS introduction, and demonstration of energy efficiency technology and practices in hotels and supermarkets (decision 91/65) |
| Egypt | UNIDO | 97/49 | 53-80 | Project to convert hermetic compressors at Fresh Compressor Factory to inverter-compressor technology (decision 95/87) |
| Egypt | UNIDO | 97/49 | 81-116 | Project to enhance energy efficiency in the manufacturing of domestic refrigerators, chest freezers, and residential air conditioners (decision 94/60) |
| Georgia | UNEP | 97/54 | -- | Improvement of the framework for energy efficiency in the RAC sector through strengthening of the legal system, capacity building and promoting MEPS (decision 91/65) |
| Global | UNDP | 97/55 | -- | Pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emissions in the cold chain sectors in Colombia, Lebanon, and Trinidad and Tobago (decision 91/65) |
| Morocco | UNIDO | 97/63 | 1-29 | Pilot project to enhance energy efficiency and MEPS enforcement in the RAC sector (decision 91/65) |
| Morocco | UNIDO | 97/63 | 30-62 | Pilot project to enhance energy efficiency by supporting the manufacturing of energy-efficient domestic refrigerators and freezers (decision 94/60) |
| Panama | UNDP | 97/68 | -- | Pilot demonstration project for a CO2 transcritical cooling plant to replace an R-410A-based chiller used in cold rooms in a municipal market (decision 91/65) |
| Paraguay | UNDP | 97/69 | -- | Pilot project to improve energy-efficiency labelling schemes and introduce MEPS for residential air conditioners (decision 91/65) |
| Republic of Moldova | UNEP | 97/71 | -- | Improvement of the framework for energy efficiency in the RAC sector through strengthening of the legal system, capacity-building and promoting MEPS (decision 91/65) |
| Sierra Leone | United Kingdom | 97/75 | -- | Pilot project to demonstrate the use of R-290 as refrigerant in the commercial refrigeration sector (decision 91/65) |
| Togo | United Kingdom | 97/79 | -- | Demonstration of R-290-based air-conditioning technology and the benefits of proper refrigerant handling and management and RAC maintenance practices (decision 91/65) |
| Tunisia | UNIDO | 97/80 | 35-73 | Pilot project to enhance energy efficiency in the residential air-conditioning manufacturing sector (decision 94/60) |

*The Secretariat will make presentations for all projects included in this table.

UNEP/OzL.Pro/ExCom/97/1