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UNIDO's WORK PROGRAMME AMENDMENTS FOR 2019


COMMENTS AND RECOMMENDATION OF THE FUND SECRETARIAT
UNIDO is requesting approval from the Executive Committee of US $1,542,396, plus agency support costs of US $109,717, for its 2019 work programme amendments listed in Table 1. The submission is attached to the present document.
Table 1: UNIDO’s work programme amendments for 2019
	Country
	Activity/Project
	Amount Requested (US $)
	Amount Recommended (US $)

	SECTION A: ACTIVITIES RECOMMENDED FOR BLANKET APPROVAL

	A1: Renewal of institutional strengthening projects

	Bosnia and Herzegovina
	Renewal of institutional strengthening project (phase VII)
	122,026
	122,026

	Serbia
	Renewal of institutional strengthening project (phase VII)
	168,064
	168,064

	Tunisia
	Renewal of institutional strengthening project (phase IX)
	316,506
	316,506

	Turkey
	Renewal of institutional strengthening project (phase IX)
	332,800
	332,800

	Subtotal for A1
	939,396
	939,396

	Agency support costs (7 per cent for institutional strengthening)
	65,757
	65,757

	Total for A1
	1,005,153
	1,005,153

	A2: Technical assistance to prepare verification reports on HCFC consumption

	Guatemala
	Verification report for stage I of HCFC phase-out management plan
	30,000
	30,000

	Honduras
	Verification report for stage I of HCFC phase-out management plan
	30,000
	30,000

	Montenegro
	Verification report for stage I of HCFC phase-out management plan
	30,000
	30,000

	Subtotal for A2
	90,000
	90,000

	Agency support costs
	8,100
	8,100

	Total for A2
	98,100
	98,100

	A3: Project preparation for HCFC phase-out management plans (HPMPs)
	
	

	Armenia*
	Preparation of an HPMP (stage III)
	20,000
	20,000

	Bahamas**
	Preparation of an HPMP (stage II)
	10,000
	10,000

	Benin**
	Preparation of an HPMP (stage II)
	20,000
	20,000

	Burkina Faso**
	Preparation of an HPMP (stage II)
	20,000
	20,000

	Côte d'Ivoire**
	Preparation of an HPMP (stage II)
	20,000
	20,000

	Equatorial Guinea**
	Preparation of an HPMP (stage II)
	10,000
	10,000

	Eritrea**
	Preparation of an HPMP (stage II)
	10,000
	10,000

	Gabon**
	Preparation of an HPMP (stage II)
	20,000
	20,000

	Kuwait**
	Preparation of an HPMP (stage II)
	15,000
	15,000

	
	Preparation for HCFC phase-out investment activities (refrigeration air-conditioning)
	80,000
	80,000

	Liberia **
	Preparation of an HPMP (stage II)
	10,000
	10,000

	Madagascar**
	Preparation of an HPMP (stage II)
	20,000
	20,000

	Sierra Leone**
	Preparation of an HPMP (stage II)
	10,000
	10,000

	Subtotal for A2
	265,000
	265,000

	Agency support costs (7 per cent for project preparation)
	18,500
	18,500

	Total for A2
	283,500
	283,550

	A4: Technical assistance for enabling activities (decision 79/46)

	Algeria
	Enabling activities for HFC phase-down
	150,000
	150,000

	Subtotal for A3
	150,000
	150,000

	Agency support costs (7 per cent for technical assistance)
	10,500
	10,500

	Total for A3
	160,500
	160,500

	SECTION B: ACTIVITIES RECOMMENDED FOR INDIVIDUAL CONSIDERATION

	B1: Project preparation 

	Bahrain**
	Preparation of an HCFC phase-out management plan (stage II)
	18,000
	***

	
	Preparation for HCFC phase-out investment activities (stage II) (foam sector)
	80,000
	***

	Subtotal for B1
	98,000
	***

	Agency support costs (7 per cent for project preparation)
	6,860
	***

	Total for B1
	104,860
	***

	Grand total (A1, A2, A3, A4, B1)
	1,652,113
	1,547,253


* UNEP as cooperating implementing agency
** UNEP as lead implementing agency
***For individual consideration

SECTION A: ACTIVITIES RECOMMENDED FOR BLANKET APPROVAL
A1: Renewal of institutional strengthening projects
Project description
1. UNIDO submitted the requests for the renewal of the four institutional strengthening (IS) projects for countries listed in section A1 of Table 1. The descriptions for these projects are presented in Annex I to the present document.
Secretariat’s comments
The Secretariat reviewed the requests for the renewal of four IS projects submitted by UNIDO on behalf of the Governments concerned against the guidelines and relevant decisions regarding eligibility and funding levels. The requests were cross-checked against the original IS work plan for the previous phase, country programme and Article 7 data, the latest report on implementation of the HCFC phase‑out management plan (HPMP), the agency’s progress report, and any relevant decisions of the Meeting of the Parties. It was noted that these countries have submitted their 2018 country programme data, and are in compliance with the controlled targets under the Montreal Protocol, and their annual HCFC consumption does not exceed the annual maximum allowable consumption indicated in their respective HPMP Agreements with the Executive Committee. Furthermore, all requests submitted included performance indicators for the planned activities for the next phase of the IS projects, in accordance with decision 74/51(e).
Secretariat’s recommendations
The Secretariat recommends blanket approval of the institutional strengthening renewal requests for Bosnia and Herzegovina, Serbia, Tunisia and Turkey at the level of funding indicated in section A1 of Table 1 of the present document. The Executive Committee may wish to express to the aforementioned Governments the comments presented in Annex II to this document.
A2: Technical assistance to prepare verification reports on HCFC consumption
Project description
The Executive Committee requested relevant bilateral and implementing agencies to include in their respective work programme amendments for submission to the 84th meeting, funding for preparation for verification reports for stage I of the HPMPs for Guatemala, Honduras and Montenegro (decision 81/33) where UNIDO is the lead implementing agency.
Secretariat’s comments
The Secretariat noted that the funding requested was consistent with the funds approved for similar verifications in previous meetings. It further noted that the verification report has to be submitted at least 60 days prior to the applicable Executive Committee meeting where the next funding tranche for the HPMP is being sought.
Secretariat’s recommendations
The Secretariat recommends blanket approval for the preparation for the verification reports for stage I of the HCFC phase-out management plans for Guatemala, Honduras and Montenegro at the level of funding shown in section A2 of Table 1, on the understanding that the verification reports should be submitted at least 60 days prior to the applicable Executive Committee meeting where the next funding tranche for the HPMPs of these countries are being sought.
A3: Project preparation for HCFC phase-out management plans
Project description
UNIDO submitted a request as lead implementing agency for the preparation of stage III of the HPMP for one country, and requests for 11 countries for the preparation of stage II of the HPMPs as cooperating implementing agency with UNEP as lead implementing agency. In addition, UNIDO requested project preparation funding for investment activities in the refrigeration and air-conditioning (RAC) sector as part of stage II of the HPMP for Kuwait. These requests are shown in section A3 of Table 1.
UNIDO provided descriptions of the activities to support the request for project preparation for Armenia, and UNEP, for the other 11 countries.[footnoteRef:1] The submissions for each country included: justification for the requested project preparation funding; a progress report on the implementation of stage I and stage II of their respective HPMPs; and the list of potential activities and the corresponding budgets.  The number of enterprises and basic consumption data was also provided for the request for the investment project for Kuwait.  [1:  UNEP/OzL.Pro/ExCom/84/35.] 

UNEP as lead implementing agency for 11 countries and cooperating implementing agency for one country, has requested US $435,000, plus agency support costs, and US $10,000, plus agency support costs, respectively, in its work programme amendments for 2019.[footnoteRef:2]  [2:  Ibid.] 

Secretariat’s comments
In reviewing the 12 requests, the Secretariat took into account the guidelines for funding the preparation of stage II and stage III of the HPMPs for Article 5 countries as contained in decision 71/42; stages I and II of HPMPs as approved, and the status of implementation of the tranches as at the preparation of the present document, and decision 82/45(cc)(i).[footnoteRef:3] The Secretariat noted that the funding requested for each country is in line with decision 71/42 and that UNIDO confirmed that the remaining funding tranches for these countries will be submitted as scheduled in their Agreements with the Executive Committee.  [3:  The inclusion of stage III of HPMPs in the 2019–2021 consolidated business plan only for those countries that had had stage II of an HPMP approved to meet a reduction target by 2020;] 

UNIDO confirmed that stage II of the HPMPs for Bahamas, Benin, Burkina Faso, Côte d’Ivoire, Equatorial Guinea, Eritrea, Gabon, Liberia, Madagascar and Sierra Leone will meet the 100 per cent reduction in HCFC consumption by 2030 and that for Kuwait will meet the 67.5 per cent reduction in 2025. Stage III of the HPMP for Armenia will meet the 97.5 per cent reduction in 2030.
Secretariat’s recommendations
The Secretariat recommends blanket approval for project preparation for stage II of the HCFC phase-out management plans (HPMPs) for Bahamas, Benin, Burkina Faso, Côte d’Ivoire, Equatorial Guinea, Eritrea, Gabon, Kuwait, Liberia, Madagascar and Sierra Leone, and stage III of the for Armenia at the level of funding shown in section A3 of Table 1.
A4: Technical assistance for enabling activities 
Background
In line with decision 79/46,[footnoteRef:4] UNIDO submitted a request for funding the implementation of enabling activities in Algeria, as shown in section A4 of Table 1.  [4:  The Executive Committee decided inter alia to approve enabling activities on the basis that countries would be allowed the flexibility to undertake a range of activities to fulfil their initial obligations in line with the Kigali Amendment; enabling activities could consist of, but were not limited to, activities to: facilitate and support the early ratification of the Kigali Amendment; initiating supporting institutional arrangements; the review of licensing systems; data reporting on HFCs; and demonstration of non-investment activities.] 

1. The enabling activities consist of:
Review of the legal framework for the ratification and implementation of the initial obligations of the Kigali Amendment including assessments of current legislation and policies in place, and identifying the requirements to establish the legislation and policy framework for management of HFC phase-down;
Coordination among government institutions and stakeholders on the policies and action plans required for the ratification and implementation of the Kigali Amendment; 
Development of the regulatory framework to set up the import/export licensing systems for HFC and HFC alternatives; preparation of harmonized tariff codes for HFC for data reporting commitments, with special attention to HFC blends; review of national mechanisms used for ODS reporting to include HFCs consumption, especially for the servicing sector; and 
Awareness raising activities.
Secretariat’s comments
2. The Secretariat reviewed the request for enabling activities and concluded that it fulfilled all the requirements of decision 79/46, as noted below:
(a) Endorsement letter from the Government of Algeria indicating its intent to make best efforts to ratify the Kigali Amendment as early as possible, was submitted by UNIDO;
(b) The project proposal included a description of each of the enabling activities, institutional arrangements, cost breakdown and the schedule for implementation; and
(c) Project implementation will be 18 months.
The funding requested for Algeria was consistent with decision 79/46(c) and calculated based on the country’s HCFC baseline. 
Secretariat’s recommendation
3. The Secretariat recommends blanket approval for the request for enabling activities for HFC phase‑down for Algeria at the level of funding indicated in section A4 of Table 1 above.
SECTION B: ACTIVITIES RECOMMENDED FOR INDIVIDUAL CONSIDERATION
B1: Project preparation for HCFC phase-out management plan
Project description
UNIDO submitted a request for the preparation of stage II of the HPMP and a request for project preparation for investment projects in the foam sector for Bahrain as cooperating implementing agency, with UNEP as the lead implementing agency as shown in section B1 of Table 1. UNEP as lead implementing agency requested US $42,000, plus agency support costs in its work programme amendments for 2019.[footnoteRef:5] [5:  UNEP/OzL.Pro/ExCom/84/35] 

UNIDO provided a description of the activities to support the request for project preparation for the investment projects in the foam sector, including the number of enterprises and basic consumption data, while UNEP included details on the overarching strategy and  requested US $42,000, plus agency support costs as contained in its work programme amendments for 2019.[footnoteRef:6]   [6:  UNEP/OzL.Pro/ExCom/84/35] 

Secretariat’s comments
The Secretariat reviewed the request for project preparation for stage II of the HPMP and the request for project preparation for the investment projects in the foam sector for Bahrain based on the guidelines for funding the preparation of stage II of the HPMPs for Article 5 countries contained in decision 71/42, and the status of implementation of stage I as at the preparation of the present document. Stage II of the HPMP for Bahrain is expected to meet the 67.5 per cent reduction in 2025. It was noted that Bahrain had submitted a tranche request for the consideration of the Executive Committee at the 84th meeting.[footnoteRef:7] [7:  UNEP/OzL.Pro/ExCom/84/40] 

The Secretariat noted that the Agreement between the Government of Bahrain and the Executive Committee for stage I of its HPMP ends in 2023. Therefore, project preparation request for stage II could be submitted only two years prior to the end of the Agreement for stage I (i.e., 2021),[footnoteRef:8] in line with decision 71/42. The Government of Bahrain has submitted to the 84th meeting a tranche request associated with stage I of the HPMP, together with a request to change the completion date of stage I from 31 December 2023 to 31 December of 2020. If the Executive Committee approves the completion date of stage I of the HPMP as requested by the Government of Bahrain, the requested preparation funding for stage II submitted to the 84th meeting would be eligible.   [8:  Decision 82/45(c)(i)] 

Secretariat’s recommendation
The Executive Committee may wish to consider approving the request for project preparation for stage II of the HCFC phase-out management plan (HPMP) for Bahrain in the amount of US $18,000, plus agency support costs of US $1,260, and project preparation for investment projects in the foam sector in the amount of US $80,000, plus agency support costs of US $5,600 subject to the approval of the revision of the Agreement between the Government of Bahrain and the Executive Committee to complete stage I of the HPMP by 31 December 2020 to be discussed under agenda item 9 (f) Investment projects.
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Annex I
INSTITUTIONAL STRENGTHENING PROJECT PROPOSAL[footnoteRef:9] [9:  Data as at December 2018 are based on document UNEP/OzL.Prol/ExCom/84/20.] 

[bookmark: _GoBack]Bosnia and Herzegovina:  Renewal of institutional strengthening

	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-99
	110,000

	Phase II:
	Jul-04
	95,333

	Phase III:
	Nov-11
	95,333 

	Phase IV:
	Dec-13
	95,333

	Phase V:
	May-15
	95,333

	Phase VI:
	Nov-17
	122,026

		Total:
	613,358

	Amount requested for renewal (phase VII) (US $):
	122,026

	Amount recommended for approval for phase VII (US $): 
	122,026

	Agency support costs (US $):
	8,542

	Total cost of institutional strengthening phase VII to the Multilateral Fund (US $):
	130,568

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	1.6

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	4.7

	(f)	Annex E (methyl bromide) (average 1995-1998)
	3.5

	Latest reported ODS consumption (2018) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	2.00

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	2.00

	Year of reported country programme implementation data:
	2018

	Amount approved for projects (as at May 2019) (US $):
	4,658,617

	Amount disbursed (as at December 2018) (US $):
	4,212,462

	ODS to be phased out (as at May 2019) (ODP tonnes):
	257.6

	ODS phased out (as at December 2018) (ODP tonnes):
	315.4



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	3,340,659

	(b)
	Institutional strengthening:
	613,358

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	704,600

		Total:
	4,658,617

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
In phase VI of the institutional strengthening (IS) project, Bosnia and Herzegovina has continued the implementation of the HCFC phase-out management plan (HPMP) activities along with increased capacity building of the national ozone unit (NOU). The HCFC quota system, HFC licenses, and the ban on equipment based on HCFCs and its blends, have been approved by the Council of Ministers and implemented by the NOU in cooperation with the Indirect Taxation Authority. Bosnia and Herzegovina’s representative was a Vice-President of the Bureau of the Twenty-eighth Meeting of the Parties to the Montreal Protocol. All the 24 performance indicators of this phase have been fully achieved.
Plan of action
In phase VII, the NOU will continue building up capacity to achieve and maintain compliance with the HCFC consumption phase-out targets and supporting ongoing legislative and regulatory efforts, with a special focus on additional HCFC restrictions. Cooperation with the customs authorities to prevent illegal trade in ODS, and with the refrigeration and air-conditioning (RAC) association to train technicians, will be continued. Bosnia and Herzegovina is committed to ratifying the Kigali Amendment and has made the necessary initial steps by including the ratification into the bi‑annual work plan of the Council of Ministers and collecting opinions from relevant administrative institutions. The date of ratification will depend on the establishment of the new Parliament.
Serbia:  Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-98
	151,500

	Phase II:
	Dec-04
	131,300

	Phase III:
	Nov-09
	119,938

	Phase IV:
	Nov-11
	131,300

	Phase V:
	Dec-13
	131,300

	Phase VI:
	Nov-17
	168,064

		Total:
	833,402

	Amount requested for renewal (phase VII) (US $):
	168,064

	Amount recommended for approval for phase VII (US $): 
	168,064

	Agency support costs (US $):
	11,764

	Total cost of institutional strengthening phase VII to the Multilateral Fund (US $):
	179,828

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	8.4

	Annex E (methyl bromide) (average 1995-1998)
	8.3

	Latest reported ODS consumption (2018) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	6.61

	Annex E (methyl bromide)
	0.00

		Total:
	6.61

	Year of reported country programme implementation data:
	2018

	Amount approved for projects (as at May 2019) (US $):
	9,970,907

	Amount disbursed (as at December 2018) (US $):
	8,077,009

	ODS to be phased out (as at May 2019) (ODP tonnes):
	1,121.2

	ODS phased out (as at December 2018) (ODP tonnes):
	1,121.2



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	7,125,743

	(b)
	Institutional strengthening:
	833,402

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,011,762

		Total:
	9,970,907

	(d)
	HFC activities funded from additional voluntary contributions
	150,000


Progress report
In phase VI of the IS project, amendments to the Regulation on ODS Management, and revised conditions for issuing licenses for import and export of ODS, were adopted (March 2018), which restricted the import of HCFCs to servicing sector maintenance activities and introduced a ban on equipment containing HCFCs. The NOU has initiated, and is following up on, the procedure for the ratification of the Kigali Amendment, under the enabling activities for HFC phase-down. Public awareness activities have been organized on the occasion of the International Ozone Day. The NOU has strengthened the cooperation with the refrigeration association in the process of certification of technicians and provision of technical support on alternatives to HCFC use to other countries in the region, through organization of exhibitions, conferences and other initiatives. All the 16 performance indicators of this phase have been fully achieved.
Plan of action
In phase VII, the NOU will continue to coordinate activities to finalize the implementation of 
stage I of the HPMP in 2020 and submit stage II to the 85th meeting. The NOU will prepare early implementation of the Kigali Amendment through enabling activities for HFC phase-down. Priority will be given to liaising with stakeholders, in particular from the RAC sector, on promoting 
low-global-warming-potential (GWP) alternatives on the local market. Awareness-raising activities will also be implemented.
Tunisia:  Renewal of institutional strengthening

	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-92
	285,312

	Phase II:
	June-98
	186,700

	Phase III:
	Apr-03
	242,667

	Phase IV:
	Apr-06
	247,270

	Phase V:
	Jul-08
	247,270

	Phase VI:
	Jul-10
	247,270

	Phase VII::
	Apr 12
	247,270

	Phase VIII:
	May-15
	247,270

	
	Total:
	1,951,029

	Amount requested for renewal (phase IX) (US $):
	316,506

	Amount recommended for approval for phase IX (US $): 
	316,506

	Agency support costs (US $):
	22,155

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	338,661

	Date of approval of country programme:
	1991

	Date of approval of HCFC phase-out management plan:
	2014

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.1

	Annex C, Group I (HCFCs) (average 2009-2010)
	40.7

	Annex E (methyl bromide) (average 1995-1998)
	8.3

	Latest reported ODS consumption (2018) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	25.91

	Annex E (methyl bromide)
	0.00

		Total:
	25.91

	Year of reported country programme implementation data:
	2018

	Amount approved for projects (as at May 2019) (US $):
	13,389,657

	Amount disbursed (as at December 2018) (US $):
	10,185,179

	ODS to be phased out (as at May 2019) (ODP tonnes):
	1,397.3

	ODS phased out (as at December 2018) (ODP tonnes):
	1,566.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	8,408,446

	(b)
	Institutional strengthening:
	1,951,029

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	3,030,182

		Total:
	13,389,657

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
In phase VIII, the NOU has advanced with the implementation of the HPMP activities through strict monitoring of HCFC trade through the ODS regulatory framework and allocation of quotas; further strengthening of the cooperation with the customs authorities ensuring sustained ODS phase-out; sharing of information with industry associations; updating the membership of the National Ozone Steering Committee on Montreal Protocol matters; coordination and preparation of stage II of the HPMP; implementation of enabling activities for HFC phase-down to prepare for the ratification of the Kigali Amendment; public awareness activities, including the celebration of the International Ozone Day; country programme and Article 7 data reporting; and participation in regional network and Montreal 
Protocol-related meetings.
Plan of action
Planned activities in phase IX include: country programme and Article 7 data reporting; continued 
cross-checking of the licensing system and quota allocation against the customs records to control 
HCFC imports; implementation of stage II of the HPMP following its approval;  updating the legislation to include HFCs; establishing a certification system for RAC technicians; banning the import or manufacturing of HCFC-based equipment, including HCFC-22; continued cooperation with custom authorities and industry associations; and facilitating the ratification of the Kigali Amendment through the implementation of enabling activities for HFC phase-down. The celebration of the International Ozone Day and the participation in regional network and Montreal Protocol-related meetings are also envisaged. 
Turkey:  Renewal of institutional strengthening

	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-92
	300,000

	Phase II:
	Dec-00
	200,000

	Phase III:
	Dec-04
	260,000

	Phase IV:
	Jul-09
	195,000

	Phase V:
	Jul-11
	260,000

	Phase VI:
	Jul-13
	260,000

	Phase VII:
	May-15
	260,000

	Phase VIII:
	Nov-17
	332,800

		Total:
	2,067,800

	Amount requested for renewal  phase IX (US $):
	332,800

	Amount recommended for approval for phase IX (US $): 
	332,800

	Agency support costs (US $):
	23,296

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	356,096

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	37.4

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	551.5

	(f)	Annex E (methyl bromide) (average 1995-1998)
	479.7

	Latest reported ODS consumption (2018) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	10.57

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	10.57

	Year of reported country programme implementation data:
	2018

	Amount approved for projects (as at May 2019) (US $):
	55,116,145

	Amount disbursed (as at December 2018) (US $):
	48,245,319

	ODS to be phased out (as at May 2019) (ODP tonnes):
	4,937.0

	ODS phased out (as at December 2018) (ODP tonnes):
	5,002.1



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	47,172,947

	(b)
	Institutional strengthening:
	2,067,800

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	5,875,398

		Total:
	55,116,145

	(d)
	HFC activities funded from additional voluntary contributions
	250,000



Progress report
The capacity of the NOU has been increased by allocating additional staff from the Ministry of Environment and Urbanization, and by enhancing the functionality of the Steering Committee. Progress has been achieved in reviewing the national ODS legislation and on enabling activities for 
HFC phase-down. The Kigali Amendment is already in the parliamentary procedure with a view of its adoption. Cooperation with the refrigeration association has been enhanced through awareness-raising and pilot demonstration activities undertaken in the context of the HPMP implementation, and the 
HFC consumption trend analysis carried out annually. Prevention of illegal trade has been enhanced through improvement of a centralized electronic system. Turkey has fully achieved 11 indicators and two were partially achieved.
Plan of action
In phase IX, new ODS alternative technologies will be supported through training and 
awareness-raising activities. Monitoring of ODS trade will be strengthened, especially through the use of information-technology-based and context-dependent approaches. Data collection and reporting, communication and networking, as well as the awareness of the protection of ozone layer among stakeholders, will be strengthened. 
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Annex II 
DRAFT VIEWS EXPRESSED BY THE EXECUTIVE COMMITTEE ON RENEWAL OF INSTITUTIONAL STRENGTHENING PROJECTS SUBMITTED TO THE 84th MEETING
Bosnia and Herzegovina
1. The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening project for Bosnia and Herzegovina (phase VII), and noted with appreciation that Bosnia and Herzegovina reported 2017 and 2018 ODS consumption data under Article 7 of the Montreal Protocol to the Ozone Secretariat and country programme data to the Fund Secretariat, indicating that the country is in compliance with its Montreal Protocol obligations. The Executive Committee further noted that Bosnia and Herzegovina has taken steps, in a coordinated manner, to achieve the HCFC consumption phase-out targets and has initiated steps towards the HFC phase-down. The Executive Committee acknowledged the efforts of Bosnia and Herzegovina and is, therefore, hopeful that it will continue the timely and successful implementation of Montreal Protocol activities, including the implementation of the HPMP and institutional strengthening project activities.
Serbia
2. The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening project for Serbia (phase VII), and noted with appreciation that Serbia reported 2017 and 2018 ODS consumption data under Article 7 of the Montreal Protocol to the Ozone Secretariat and country programme data to the Fund Secretariat, indicating that the country is in compliance with its Montreal Protocol obligations. The Committee further noted that Serbia has undertaken concerted efforts towards the achievement of the HCFC consumption phase-out targets, in line with its Agreement with the Executive Committee, including through the enforcement of the ban on import of HCFC-based equipment that started in March 2018, and activities in the technical information exchange in the region. The Executive Committee acknowledged the efforts of Serbia and is, therefore, hopeful that it will continue the timely and successful implementation of Montreal Protocol activities, including the implementation of the HPMP and institutional strengthening project activities.
Tunisia
3. The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening project for Tunisia (phase IX), and noted that Tunisia reported the data under Article 7 of the Montreal Protocol to the Ozone Secretariat and country programme data to the Fund Secretariat, indicating that the country is in compliance with its Montreal Protocol obligations. The Executive Committee further noted that Tunisia has taken action to phase out HCFC consumption, including the implementation of a strict system of monitoring of trade in ODS through the national regulatory framework, and training for customs authorities. The Executive Committee acknowledged the efforts of Tunisia to implement stage I of the HPMP and noted that Tunisia has submitted stage II of the HPMP for consideration by the Executive Committee, and is, therefore, hopeful that it will continue the timely and successful implementation of the HPMP and institutional strengthening project activities. 
Turkey
4. The Executive Committee reviewed the report presented with the request for the renewal of the institutional strengthening project for Turkey (phase IX) and noted with appreciation that Turkey is in compliance with the reporting obligations under Article 7 data of the Montreal Protocol and the country programme implementation, and with the accelerated HCFC phase-out targets set in its Agreement with the Executive Committee. The Committee further noted that Turkey plays an important role in promoting alternatives to HCFCs in the refrigeration and air-conditioning sector in the Europe and Central Asia region. The Executive Committee acknowledged the efforts of Turkey and is, therefore, hopeful that it will continue the timely and successful implementation of Montreal Protocol activities, including the implementation of the HPMP and institutional strengthening project activities.
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