| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/28 10 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 8(d)(iii) of the provisional agenda

UNEP BUSINESS PLAN FOR 2024–2026

# Introduction

# This document presents UNEP business plan for 2024–2026 and includes the planned activities for the reduction of controlled substances under the Montreal Protocol during the period 2024–2026. The narrative of UNEP’s business plan for 2024–2026 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2024–2026

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2024–2026

# Table 1 sets out, by year, the value of activities included in UNEP’s business plan.

Table 1. Resource allocation in the UNEP business plan for 2024–2026 (US $)* – as submitted

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 11,170,928 | 6,571,602 | 6,431,766 | 24,174,296 | 8,344,699 |
| HPMP project preparation (PRP) – stage II | 135,600 | 28,250 | 0 | 163,850 | 0 |
| HPMP stage II | 1,526,733 | 958,403 | 4,799,204 | 7,284,340 | 8,828,158 |
| HPMP PRP – stage III | 175,150 | 22,600 | 0 | 197,750 | 0 |
| HPMP stage III | 562,300 | 154,665 | 602,799 | 1,319,764 | 868,064 |
| HPMP – energy efficiency | 2,528,940 | 2,750,420 | 271,200 | 5,550,560 | 0 |
| HCFC activities subtotal | 16,099,651 | 10,485,940 | 12,104,969 | 38,690,560 | 18,040,921 |
| HFC activities |  |  |  |  |  |
| Enabling activities for HFC phase down | 53,500 | 160,500 | 0 | 214,000 | 0 |
| Kigali HFC implementation plan (KIP) stage I – PRP | 1,818,119 | 344,650 | 150,290 | 2,313,059 | 0 |
| KIP stage I | 2,610,187 | 4,676,486 | 1,699,305 | 8,985,978 | 8,138,659 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 | 0 |
| HFC activities subtotal | 5,159,806 | 5,181,636 | 1,849,595 | 12,191,037 | 8,138,659 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment | 870,100 | 248,600 | 0 | 1,118,700 | 0 |
| National inventories of banks of waste-controlled substances – PRP | 384,200 | 0 | 0 | 384,200 | 0 |
| Other activities subtotal | 1,254,300 | 248,600 | 0 | 1,502,900 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 13,695,022 | 180,000 | 9,902,161 | 23,777,183 | 0 |
| Compliance Assistance Programme (CAP) | 11,605,710 | 11,953,882 | 12,312,498 | 35,872,090 | 0 |
| Standard activities subtotal | 25,300,732 | 12,133,882 | 22,214,659 | 59,649,273 | 0 |
| Total | 47,814,490 | 28,050,058 | 36,169,223 | 112,033,770 | 26,179,580 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

Stage II of HPMPs

# The total level of funding for stage II of HPMPs for 16 low-volume-consuming (LVC) countries to meet the 100 per cent reduction of the HCFC baseline amounts to US $3.82 million (including US $1.61 million for 2024–2026 and US $2.21 million for the period after 2026).

# The total level of funding for stage II of HPMPs for six non-LVC countries amounts to US $12.29 million (including US $5.67 million for 2024–2026 and US $6.62 million for the period after 2026).

# A total of US $163,850 is included in the business plan for project preparation for stage II of HPMPs for five countries for 2024–2026.

# Stage III of HPMPs

# A total of US $2.19 million is planned for stage III of HPMPs for six countries (Albania, Armenia, Iran (Islamic Republic of), Serbia, Timor-Leste, and Tunisia) (including US $1.32 million for 2024–2026 and US $868,064 for the period after 2026).

# A total of US $197,750 is included in the business plan for project preparation for stage III of HPMPs for seven countries for 2024–2026.

# Energy efficiency for LVC countries

# Decision 89/6 allowed bilateral and implementing agencies, when submitting existing and future stages of HPMPs for LVC countries, to include the funding associated with the need for the introduction of alternatives to HCFCs with low- or zero-global-warming potential (GWP) and for maintaining energy efficiency in the refrigeration servicing sector.

# A total of US $5.55 million is included in the business plan for energy efficiency activities for 57 LVC countries for 2024–2026.

II.2	HFC-related activities

# Enabling activities

# HFC activities include enabling activities amounting to US $214,000 in 2024–2026 for two countries (Antigua and Barbuda and the Central African Republic). Both countries have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment as early as possible, in line with decision 79/46(d)(i).

# KIP project preparation

# A total of US $2.31 million is included in the business plan for KIP project preparation activities for 22 countries in 2024–2026.

# Seventeen of the 22 countries for which KIP project preparation activities have been included have not yet ratified the Kigali Amendment but have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment in line with decision 84/46(f).

# Stage I of KIPs

# A total of US $17.12 million is included in the business plan for stage I of KIPs for 69 countries (including US $8.99 million for 2024–2026 and US $8.14 million for the period after 2026). All these countries have ratified the Kigali Amendment.

# HFC technical assistance

# UNEP has included one global HFC technical assistance project, twinning of ozone officers and national energy policymakers to support Kigali Amendment objectives, in the amount of US $678,000 in 2024. Phase I of this project was approved at the 91st meeting.

II.3	Other activities

Pilot projects for energy efficiency (decision 91/65)

# A total of US $1.12 million is included in the business plan under the funding window for pilot projects for energy efficiency (decision 91/65) for 2024–2026 for four countries (Guatemala, Honduras, Maldives, and the Republic of Moldova).

National inventories of banks of waste-controlled substances project preparation (decision 91/66)

# A total of US $384,200 is included in the business plan for the preparation of national inventories of banks of waste-controlled substances (decision 91/66) for 2024–2026 for five countries (Kyrgyzstan, Maldives, Paraguay, Peru, and Sri Lanka).

II.4	CAP

# The cost for CAP is expected to increase at an annual rate of 3 per cent as agreed by the Executive Committee. The total level of funding for CAP is US $35.87 million for 2024–2026. The CAP budget for 2024 has been submitted to the 93rd meeting.

III.	Proposed adjustments by the Secretariat

# The adjustments to the UNEP business plan for 2024–2026 were based on relevant decisions of the Executive Committee. In reviewing the revised UNEP business plan for 2024–2026, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNEP business plan for 2024–2026 (US $)* – as proposed by the Secretariat

| Adjustment | 2024–2026 | After 2026 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements including tranches of HPMPs that have been submitted to the 93rd meeting | 96,954 | 0 |
| PRP for stage II of HPMPs pursuant to decision 71/42 | (22,600) | 0 |
| Energy efficiency for LVC countries pursuant decision 89/6 or submitted to the 93rd meeting | (488,419) | 0 |
| PRP for KIPs pursuant to decision 87/50 or submitted to the 93rd meeting | (56,790) | 0 |
| Servicing sector for stage I of KIPs pursuant to decision 92/37 | (264,271) | (263,815) |
| Preparation for national inventories of banks of waste-controlled substances submitted to the 93rd meeting | (50,850) | 0 |
| IS pursuant to decision 91/63(d) | 3,184 | 0 |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNEP business plan for 2024–2026, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2024–2026.

Table 3. Resource allocation in UNEP’s adjusted business plan for 2024–2026 (US $)*

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 11,267,882 | 6,571,602 | 6,431,766 | 24,271,250 | 8,344,699 |
| HPMP PRP – stage II | 113,000 | 28,250 | 0 | 141,250 | 0 |
| HPMP stage II | 1,526,733 | 958,403 | 4,799,204 | 7,284,340 | 8,828,158 |
| HPMP PRP – stage III | 175,150 | 22,600 | 0 | 197,750 | 0 |
| HPMP stage III | 562,300 | 154,665 | 602,799 | 1,319,764 | 868,064 |
| HPMP – energy efficiency | 2,311,721 | 2,671,320 | 79,100 | 5,062,141 | 0 |
| HCFC activities subtotal | 15,956,786 | 10,406,840 | 11,912,869 | 38,276,495 | 18,040,921 |
| HFC activities |  |  |  |  |  |
| Enabling activities for HFC phase down | 53,500 | 160,500 | 0 | 214,000 | 0 |
| KIP stage I – PRP | 1,761,329 | 344,650 | 150,290 | 2,256,269 | 0 |
| KIP stage I | 2,605,880 | 4,416,522 | 1,699,305 | 8,721,707 | 7,874,844 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 | 0 |
| HFC activities subtotal | 5,098,709 | 4,921,672 | 1,849,595 | 11,869,976 | 7,874,844 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment | 870,100 | 248,600 | 0 | 1,118,700 | 0 |
| National inventories of banks of waste-controlled substances – PRP | 333,350 | 0 | 0 | 333,350 | 0 |
| Other activities subtotal | 1,203,450 | 248,600 | 0 | 1,452,050 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 13,878,207 | 180,000 | 9,722,161 | 23,780,367 | 0 |
| CAP | 11,605,710 | 11,953,882 | 12,312,498 | 35,872,090 | 0 |
| Standard activities subtotal | 25,483,917 | 12,133,882 | 22,034,659 | 59,652,457 | 0 |
| Total | 47,742,862 | 27,710,994 | 35,797,123 | 111,250,978 | 25,915,765 |

* Including agency support costs where applicable.

IV.	Performance indicators

# UNEP submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed UNEP of the targets shown in table 4.

Table 4. Performance indicators for UNEP for 2024

| Type of indicator | Short title | Calculation | 2024 target |
| --- | --- | --- | --- |
| Planning - Approval | Tranches approved | Number of tranches approved vs. those planned* | 84 |
| Planning - Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 120 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $24,723,357 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans* | 196.9 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 81 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 12 months |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | On time (5) |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency would be reduced “if it could not submit a tranche owing to another cooperating agency or lead agency” or “if the HPMP submitted for consideration by the Executive Committee was not approved as a result of factors beyond the control of the national ozone unit (NOU) and the agency”.

# Table 5 presents UNEP’s performance indicators for its CAP, which were adopted in decision 48/7(e).

Table 5. Performance indicators for UNEP’s CAP for 2024

| Performance indicator | Data | Assessment | 2024 target |
| --- | --- | --- | --- |
| Efficient follow-up to regional network/thematic meetings | List of recommendations emanating from 2021-2022 regional network/thematic meetings | Implementation rate of those meeting recommendations that are to be implemented in 2023 | 90% implementation rate |
| Effective support to NOUs in their work, particularly guidance to new NOUs | List of innovative ways/means/ products/services for supporting NOUs in their work, with specification of those destined for new NOUs | Number of innovative ways, means, products, services for supporting NOUs in their work, with specification of those destined for new NOUs | - 7 such ways, means, products, services; -All new NOUs receive capacity building support. |
| Assistance to countries in actual or potential non-compliance (as per Meeting of the Parties decisions and/or as per reported Article 7 data and trend analysis) | List of countries in actual or potential non-compliance that received CAP assistance outside the network meetings | Number of countries in actual or potential non-compliance that received CAP assistance outside the network meetings | All such countries |
| Innovations in production and delivery of global and regional information products and services | List of global and regional information products and services destined for new target audiences or that reach existing target audiences in new ways | Number of global and regional information products and services destined for new target audiences or that reach existing target audiences in new ways | 7 such products and services |
| Close cooperation between CAP regional teams and implementing and bilateral agencies working in the regions | List of joint missions/ undertakings of CAP regional staff with implementing and bilateral agencies | Number of joint missions/undertakings | 2 in each region. |

V.	Recommendation

# The Executive Committee may wish:

## To note the UNEP business plan for 2024–2026, contained in document UNEP/OzL.Pro/ExCom/93/28; and

## To approve the performance indicators for UNEP as set out in tables 4 and 5 of document UNEP/OzL.Pro/ExCom/93/28.

UNEP/OzL.Pro/ExCom/93/1

A draft business plan for 2024–2026 of UNEP was discussed at the Inter-agency coordination meeting (IACM) held in Montreal from 3 to 5 October 2023. The business plan contained in this document has addressed the issues raised at the meeting.

UNEP/OzL.Pro/ExCom/93/94

UNEP/OzL.Pro/ExCom/93/25