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PROJECT EVALUATION SHEET – MULTI-YEAR PROJECTS
Thailand  
	(I) PROJECT TITLE
	AGENCY
	MEETING APPROVED
	CONTROL MEASURE

	HCFC phase out plan (Stage I)
	World Bank
	68th 
	15% by 2018



	(II) LATEST ARTICLE 7 DATA (Annex C Group l)
	Year: 2016
	589.1 (ODP tonnes)



	(III) LATEST COUNTRY PROGRAMME SECTORAL DATA (ODP tonnes)
	Year: 2016

	Chemical
	Aerosol
	Foam
	Fire fighting
	Refrigeration
	Solvent
	Process agent
	Lab use
	Total sector consumption

	 
	Manufacturing
	Servicing
	

	HCFC-123
	
	
	
	1.1
	1.6
	
	
	
	2.7

	HCFC-124
	
	
	
	
	
	
	
	
	

	HCFC-141b
	
	133.5
	
	
	
	15.4
	
	
	148.8

	HCFC-141b in imported pre‑blended polyol
	
	12.9
	
	
	
	
	
	
	12.9

	HCFC-142b
	
	
	
	
	
	
	
	
	

	HCFC-22
	
	
	
	265.9
	169.7
	
	
	
	435.6

	HCFC-225*
	
	
	
	
	
	1.9
	
	
	1.9


*These figures include consumption for HCFC-225, HCFC-225ca and HCFC-225cb.

	(IV) CONSUMPTION DATA (ODP tonnes)

	2009 - 2010 baseline:
	927.6
	Starting point for sustained aggregate reductions:
	943.3

	CONSUMPTION ELIGIBLE FOR FUNDING (ODP tonnes)

	Already approved:
	234.73
	Remaining:
	708.57



	(V) BUSINESS PLAN
	2017
	Total

	World Bank
	ODS phase-out (ODP tonnes)
	39.21
	39.21

	
	Funding (US $)
	4,347,990
	4,347,990



	(VI) PROJECT DATA
	2012
	2013
	2014
	2015
	2016
	2017**
	2018
	Total

	Montreal Protocol consumption limits
	n/a
	927.60
	927.60
	834.84
	834.84
	834.84
	834.84
	n/a

	Maximum allowable consumption (ODP tonnes)
	n/a
	927.60
	927.60
	834.84
	834.84
	834.84
	788.46
	n/a

	Agreed funding (US$)
	World Bank*
	Project costs
	4,817,166
	9,706,154
	618,803
	3,063,542
	0
	0
	0
	18,205,665

	
	
	Support costs
	337,202
	679,431
	43,316
	214,448
	0
	0
	0
	1,274,397

	
	Japan
	Project costs
	302,965
	0
	0
	0
	0
	0
	0
	302,965

	
	
	Support costs
	39,385
	0
	0
	0
	0
	0
	0
	39,385

	Funds approved by ExCom (US$)
	Project costs
	5,120,131
	0
	0
	9,706,154
	618,803
	0
	0
	15,445,088

	
	Support costs
	376,587
	0
	0
	679,431
	43,316
	0
	0
	1,099,334

	Total funds requested for approval at this meeting (US$)
	Project costs
	0
	0
	0
	0
	0
	3,063,542
	0
	3,063,542

	
	Support costs
	0
	0
	0
	0
	0
	214,448
	0
	214,448


*The funds for the fifth (2016), sixth (2017) and seventh (2018) tranches amounting to US $1,000,000, US $753,630 and US $2,408,580, respectively, plus agency support costs will not be requested by the World Bank.
**The fourth tranche should have been submitted in 2015.
	Secretariat's recommendation:
	For individual consideration




PROJECT DESCRIPTION

On behalf of the Government of Thailand, the World Bank as the designated implementing agency, has submitted a request for funding for the fourth tranche of stage I of the HCFC phase‑out management plan (HPMP)[footnoteRef:1], at the amount of US $3,063,542, plus agency support costs of US $214,448 for the World Bank[footnoteRef:2]. The submission includes a progress report on the implementation of the third tranche, the verification report on 2016 HCFC consumption and the tranche implementation plan for 2018. [1:  The second tranche due in 2013 was approved at the 74th meeting, and the third tranche due in 2014 was approved at the 77th meeting.]  [2:  As per the communication of 18 September 2017 from the the Department of Industrial Works (DIW) to the World Bank.] 

Report on HCFC consumption

HCFC consumption

The Government of Thailand reported a consumption of 589.09 ODP tonnes of HCFC in 2016 which was 63.5 per cent below the HCFC baseline fir compliance. The 2012-2016 HCFC consumption is shown in Table 1. 
Table 1. HCFC consumption in Thailand (2012-2016 Article 7 data)
	HCFC
	2012
	2013
	2014
	2015
	2016
	Baseline

	Metric tonnes (mt)
	
	
	
	
	
	

	HCFC-22
	16,821.19
	11,988.86
	11,984.35
	10,365.31
	7,920.74
	13,028.60

	HCFC-123
	198.88
	113.47
	136.06
	142.92
	134.66
	159.75

	HCFC-124
	2.99
	4.03
	4.41
	0.12
	0
	3.41

	HCFC-141b
	2,028.98
	1,817.37
	1,830.46
	1,817.68
	1352.92
	1,865.93

	HCFC-142b
	0
	0
	0
	0
	0
	1.81

	HCFC-225*
	45.91
	37.64
	39.35
	8.67
	27.73
	54.60

	Total HCFC (mt)
	19,097.95
	13,961.37
	13,994.63
	12,334.70
	9,436.05
	15,114.10

	HCFC-141b in imported polyols
	182.23
	53.86
	92.29
	192.03
	117.03
	142.50**

	ODP tonnes
	
	
	
	
	
	

	HCFC-22
	925.17
	659.39
	659.14
	570.09
	435.64
	716.57

	HCFC-123
	3.98
	2.27
	2.72
	2.86
	2.69
	3.19

	HCFC-124
	0.07
	0.09
	0.10
	0.00
	0
	0.08

	HCFC-141b
	223.19
	199.91
	201.35
	199.94
	148.82
	205.25

	HCFC-142b
	0
	0
	0
	0
	0
	0.12

	HCFC-225*
	2.24
	1.66
	1.04
	0.61
	1.94
	2.30

	Total HCFC (ODP tonnes)
	1,154.65
	863.32
	864.35
	773.50
	589.09
	927.51

	HCFC-141b in imported polyols 
	20.05
	5.92
	10.15
	21.12
	12.87
	15.67**


*These figures include consumption for HCFC-225, HCFC-225ca and HCFC-225cb.
**Average consumption between 2007 and 2009.

In 2013, HCFC‑141b contained in imported pre-blended polyols was partially replaced by polyols blended in Thailand. In 2014, HCFC-141b in bulk and in pre-blended polyols increased due to provisions made before the control measure in 2015. Since 2014, the consumption of HCFC-22 and HCFC‑141b decreased mainly due to the implementation of phase-out projects in the air‑conditioning and foam sectors approved under stage I of the HPMP, respectively, and the implementation of a quota system to control and monitor the consumption of HCFCs. 
Country programme (CP) implementation report
The Government of Thailand reported HCFC sector consumption data under the 2016 CP implementation report which was consistent with the data reported under Article 7. 
Verification report

The verification report confirmed that the Government is implementing a licensing and quota system for HCFC imports and exports and that the total consumption of HCFCs for 2016 was 589.09 ODP tonnes. The verification concluded that Thailand has not exceeded the maximum allowable consumption level of 834.84 ODP tonnes for 2016. 
Progress report on the implementation of the third tranche of the HPMP

Legal framework
The Department of Industrial Works (DIW) established an import quota system for HCFCs in January 2013. The DIW has issued regulations to prohibit manufacturing of HCFC-22-based air‑conditioners (ACs) with a capacity of less than 50,000 BTU/hour[footnoteRef:3] for sales in domestic markets as of 1 July 2017. A ban on import of HCFC-141b (bulk and contained in pre-blended polyols) as a foam blowing agent except for spray foam applications as of 1 July 2017 was also issued. HCFC-141b contained in imported pre-blended polyols is controlled through import permits issued by the DIW. [3:  BTU: British thermal unit (equivalent to 0.293 Watt - hour).] 

After risk assessment study for ACs using HFC-32, DIW has extended the use of these ACs up to a capacity of 50,000 BTU/hour in buildings in 2017.
Manufacturing sector

Room AC manufacturing sector

Eleven enterprises consuming 1,154.75 mt (63.51 ODP tonnes) have completed their conversion in 2017. The total funds amounting to US $8,359,998 is expected to be disbursed fully to the enterprises during 2018 after completion of verification at the enterprises and administrative procedures. 
The Government has implemented the first training programme on safe use of HFC-32 in installation and servicing for 50 trainers from vocational schools. Five additional trainings will be conducted in 2017.
Technical assistance (TA) for compressor manufacturing

The enterprise Kulthorn Kriby has completed the design of HFC-32-based reciprocating compressors for equipment with refrigeration capacity of 12,000, 24,000 and 36,000 BTU/hour, and is currently developing R‑290 and CO2-based compressors. So far US $250,000 has been disbursed; it is expected that the project would be completed by December 2018.
Polyurethane (PU) foam manufacturing sector

As of September 2017, 34 foam enterprises with a total consumption of 583.44 mt (64.18 ODP tonnes) of HCFC-141b have signed sub-grant agreements for conversion for a total amount of US $5,003,611. Sixteen of these enterprises consuming 389.40 mt (42.83 ODP tonnes) have completed their conversion (i.e., seven enterprises consuming 295.67 mt (32.52 ODP tonnes) to hydrocarbon alternatives, and nine enterprises consuming 93.73 mt (10.31 ODP tonnes) to HFC-245fa).
In addition, 11 enterprises with a total consumption of 123.12 mt (13.54 ODP tonnes) of HCFC‑141b have been identified for conversion to reduced HFC-245fa or water-blown technology, at an estimated cost of US $1,145,158. Further, support would be provided for additional small foam enterprises to phase out about 90.96 mt (10 ODP tonnes) HCFC-141b in 2018 for a cost-effective and safe transition to alternatives. 
Implementation of all the foam projects under stage I of the HPMP would result in the phase-out of 797.53 mt (87.73 ODP tonnes), and would be completed by the end of December 2018. 
Technical assistance and refrigeration servicing activities

The following activities were carried out during the reporting period:
The DIW issued import quotas for five HCFCs amounting to 779.2 ODP tonnes for 2017;
The DIW and the Office of Vocational Education Commission (OVEC) signed a memorandum of understanding in August 2016 for nation-wide training for the phase-out of HCFC-22 in the AC sector, adoption of HFC‑32‑based ACs, and future training activities;
TA activities for revision of energy, safety and performance standards were initiated to support the Federation of Thai Industries, Department of Civil Works, the Town and Country Planning, the Thailand Industry Standards Institute and the Electrical and Electronic Institute. Laboratory equipment for modification of energy performance was provided to the Electrical and Electronic Institute. Activities for supporting independent training centres on safe handling, installation and servicing air-conditioning equipment, and promotion of safe use of HFC-32 ACs would be undertaken in future; 
A train-the-trainer programme for 170 trainers on safe maintenance and servicing of HFC‑32-based ACs was initiated in September 2017; these trainers would provide training to technicians on an ongoing basis; and 
Activities for developing safety procedures for using flammable substances in cooperation with OVEC, and technology transfer to micro foam enterprises with support from a systems house would be initiated in the last quarter of 2017 and completed by December 2018. 
Project implementation and monitoring unit (PMU)

Since there are two national executing agencies participating in the HPMP (Government Savings Bank (GSB) and DIW), two PMUs were established. The GSB PMU is responsible for implementing sub‑projects for which sub-grant agreements have already been signed and for developing new sub-project proposals and new sub-grant agreements; and participating in training and workshops to get an update on the Executive Committee decisions as well as the development of new technologies.
The DIW PMU is responsible for facilitating the approval of new sub-grant agreements by reviewing the sub-project eligibility, disposal plans for old and unusable equipment, and implementing the environmental management plan; undertaking other activities for facilitating and monitoring HCFC phase‑out, implementing TA activities for training institutes and non-governmental organisations and assisting DIW in annual HCFC quota allocation.
Level of fund disbursement

As of September 2017, of the US $15,445,088 approved so far, US $10,225,239 had been disbursed (US $10,004,445 for the World Bank and US $220,794 for the Government of Japan) as shown in Table 2. The balance of US $5,219,849 will be disbursed by December 2018.
Table 2. Financial report of stage I of the HPMP for Thailand (US $)
	Agency
	First tranche
	Second tranche
	Third tranche
	Total approved

	
	Approved
	Disbursed
	Approved
	Disbursed
	Approved
	Disbursed
	Approved
	Disbursed

	World Bank
	4,817,166
	2,739,602
	9,706,154
	6,777,824
	618,803
	487,019
	15,142,123
	10,004,445

	Japan
	302,965
	220,794
	0
	0
	0
	0
	302,965
	220,794

	Total
	5,120,131
	2,960,396
	9,706,154
	6,777,824
	618,803
	487,019
	15,445,088
	10,225,239

	Disbursement rate (%)
	57.8
	69.8
	78.7
	66.2



Implementation plan for the fourth tranche of the HPMP

The Government of Thailand plans to complete stage I activities by December 2018 and has the following plan to complete the remaining activities and disburse funds for respective components:
Completion of verification of conversion projects in 11 room AC manufacturing enterprises; completion of the development of R-290 and CO2-based compressors; and completion of the conversion of 45 PU foam enterprises (provision for eight additional enterprises has been included to assist any eligible enterprises that might not have been identified at no additional cost) (US $15,423,613);
Equipment support and TA to a systems house and 53 micro-foam enterprises for using HCFC-free polyols; the systems house will stop producing 47.63 mt (5.24 ODP tonnes) of HCFC-141b contained in pre‑blended polyols on completion of the project (US $213,016);
TA to about 50 small and micro foam enterprises using about 90.96 mt (10 ODP tonnes) for conversion to alternative blowing agents, through technology workshops, technical inputs on new formulations, supply of samples and demonstration and support for their adoption (US $500,000); 
Awareness on safety aspects while handling and using hydrocarbon (HC)-based foam blowing agent through three workshops and two technical workshops for PU foam users on cost‑effective and safe use of alternatives including development of one video on safe use of HC-based blowing agents and formulations, for dissemination among foam sector users (US $230,000); 
Train-the-trainer programmes for about 140 trainers on HFC-32 use through five to six workshops, technical support for safe handling, installation and maintenance of HFC‑32‑based ACs, technical support to enterprises for conversion to HFC-32, and equipment support to training institutions (US $760,060); and 
PMU for project management, monitoring and regulations enforcement support and other activities relating to project completion and closure (US $1,381,141).
With the funds approved under the fourth tranche, the remaining activities would be implemented and stage I would be completed by December 2018. Table 3 presents a summary of the disbursements as of September 2017, estimated disbursement by December 2018 and proposed revision in the budget.
Table 3. Expected disbursement for stage I of the HPMP for Thailand (US $)
	Activity
	Original approval
	Fund disbursed as of September 2017
	Estimated disbursement at end of 2018
	Revised budget proposed

	Room AC manufacturing
	8,384,521
	5,807,473
	8,359,998
	8,359,998

	Compressor
	702,630
	250,000
	702,630
	702,630

	TA for AC sector
	484,282
	220,794
	760,060
	760,060

	PU Foam
	11,494,263
	3,424,344
	7,090,985
	7,090,985

	TA for foam sector
	224,003
	42,603
	213,016
	213,016

	PMU
	1,381,141
	480,025
	1,381,141
	1,381,141

	Total
	22,670,840
	 10,225,239
	 18,507,830
	 18,507,830



SECRETARIAT’S COMMENTS AND RECOMMENDATION 

COMMENTS 

Progress report on the implementation of the third tranche of the HPMP

Legal framework

The Government of Thailand has already issued HCFC import quotas for 2017 in accordance with the Montreal Protocol control targets.
The Secretariat requested clarification on how the Government is monitoring HCFC-141b consumption in the country given that the regulations prohibit the use of HCFC-141b in all applications except for spray foam. The World Bank explained that the Government is closely monitoring imports of HCFC-141b bulk and contained in imported pre-blended polyols and enforcing penalties for sale after 1 July 2017 except for spray foam applications. In the current implementation plan, workshops and TA activities focusing on safe and cost-effective use of HCFC-free formulations will be conducted. The Government will implement the regulatory controls in cooperation with industry associations and systems houses, they would implement these. The ban on the sales of HCFC-22-based AC units by 1 January 2018 is under consideration. 
Manufacturing sector

Room AC manufacturing sector

Upon a request for additional information, the World Bank informed that the conversion of room AC manufacturing enterprises to HFC-32 was completed in June 2017; the remaining funds would be disbursed after verification activities including safety audits at the beneficiary enterprises, which is taking more time than originally expected. However, the World Bank is working closely with the Government and the enterprises to complete these activities during 2018.
With regard to regulatory barriers relating to the use of HFC-32-based AC equipment in buildings owing to safety considerations, the World Bank clarified that TA activities on safe installation and maintenance of HFC-32-based equipment up to 50,000 BTU/hour and regulations allowing their installation in high-rise buildings would facilitate market acceptance of these systems. 
PU foam manufacturing sector

The Secretariat requested a clarification on the status of implementation of HCFC-141b phase-out in the foam sector, noting that the current plan covering 34 enterprises, and the proposed plan to cover additional 11 foam enterprises and support to micro-enterprises, would account for approximately 50 per cent of the total phase-out of HCFC-141b under stage I. The World Bank explained that of the total of 131 enterprises originally proposed to be supported in stage I, only 100 enterprises would be supported. Of this, 45 enterprises have been identified and the remaining 55 are small and medium enterprises that would receive technical assistance for phasing out their HCFC consumption, in coordination with industry. The World Bank explained that the number of eligible enterprises that were willing to participate in the project was lower than the estimated number of enterprises identified during the survey. Several enterprises have converted on their own. Further, with the regulations prohibiting use of HCFC‑141b in non-spray foam applications from 1 July 2017, all enterprises using HCFC-141b in non‑spray foam applications need to convert to HCFC-141b-free alternatives; thus, the committed total phase‑out planned in stage I (166.87 ODP tonnes) would be achieved. In addition, the World Bank is working closely with the PMU to expedite conversion of the remaining enterprises and to provide support through awareness and technical assistance activities to those foam enterprises which have converted on their own, during 2017 and 2018.
TA and refrigeration servicing activities

Of the US $302,965 bilateral contribution from the Government of Japan, US $292,883 has been disbursed (US $220,794) or committed (US $72,089) for the TA activities; and the balance of US $10,082 is proposed to be allocated for promoting adoption of HFC-32-based alternatives. Upon request for clarification on the need for this component, the World Bank informed that the decision to use the balance for promoting adoption of HFC-32‑based alternatives was mainly to work, in close cooperation with the Federation of Thai Industry, with small AC manufacturers for encouraging them to adopt HFC-32 rather than other high‑global warming potential (GWP) options.
The World Bank also explained that, in line with decision 68/39(g) on reducing emission of HCFC‑22 in the servicing sector, the DIW in collaboration with the Department of Skill Labor and Vocational School Commission will continue to implement training programmes on good service practices and safe use of HFC-32-based alternatives. Further with implementation of the ban on manufacturing HCFC‑22‑based equipment for sale in domestic market, and import quota reduction, HCFC-22 emission reduction would be facilitated.
PMU expenditures

The Secretariat sought clarifications on low levels of expenditure of PMU (34.8 per cent) compared to the total budget approved. The World Bank informed that additional expenditures relating to payments for technical consultants, management fees, preparation of project completion reports, and other operating costs of the GSB PMU will be incurred by GSB until the end of 2018. An additional US $250,000 is required to support costs of technical consultants, preparation of project completion reports for those activities implemented by DIW; the balance of US $351,116 is for undertaking the review of lessons learned and experience from stage I, satisfaction surveys (interview with beneficiaries), technical visits, development and distribution of public awareness materials summarizing roles and responsibility of DIW and partner agencies contributing to the success of stage I of the HPMP. 
Revised plan of action 

The Secretariat discussed with the World Bank’s utilisation of approved funds under the project till the end of 2017 and required funding up to December 2018 including the proposed revision to the budget. The World Bank explained that the proposed revision takes into account existing commitment for projects and activities in the AC and foam sectors and additional TA activities to be undertaken for sustained phase‑out of HCFCs in these sectors and safe adoption of new technologies; further, the Government would achieve the committed phase-out with the activities planned in stage I. The World Bank also confirmed that the Government of Thailand would not request the funding amounting to US $4,162,210 relating to the remaining three tranches of stage I of the HPMP, and with the fourth tranche funding would complete implementation of stage I by December 2018; the project completion report would be submitted to the first meeting in 2019, and any remaining funds would be returned after administrative financial completion of the project. The Government of Thailand would also submit stage II of the HPMP at the 82nd meeting to address remaining eligible HCFC consumption.
Revision to the HPMP Agreement

Based on the revised plan, Appendix 2-A of the Agreement between the Government of Thailand and the Executive Committee has been updated and paragraph 16 has also been updated to indicate that the revised updated Agreement supersedes that reached at the 77th meeting, as shown in Annex I to this document. The full revised Agreement will be appended to the final report of the 80th meeting.
Conclusion 

The Secretariat noted the Government of Thailand and the World Bank progressed in several activities since 2016. The Government has completed implementation of conversion projects in the room AC manufacturing sector and is expected to disburse the remaining funds by December 2018 after necessary verification; and a range of technical assistance activities for promoting safe adoption of HFC‑32 are under implementation. The Government has implemented regulations for banning import of HCFC-141b, bulk or contained in pre-blended polyols, except spray foam applications from 1 July 2017, and the use of HCFC‑22 in the manufacturing of AC with cooling capacity lower than 50,000 BTU/hour for the domestic market from 1 January 2017. Although the PU foam sector projects have not been fully implemented as planned, the Government has presented a final plan for completing project implementation in the identified enterprises and micro-enterprises with support from a systems house; the estimated phase-out from the enterprises in the plan is 797.53 mt (87.73 ODP tonnes). The Government is also implementing TA activities to facilitate adoption of HCFC‑141b‑free alternatives in a safe and cost-effective manner; complete support to some eligible enterprises that may not have had access to assistance. With the approval of the fourth tranche of US $3,063,542, the Government would be able to complete all activities under stage I of the HPMP by December 2018 and achieve the phase-out planned. 
RECOMMENDATION 

The Executive Committee may wish to consider: 
Noting:
The progress report on the implementation of the third tranche of stage I of the HCFC phase-out management plan (HPMP) in Thailand; 
The submission of a revised plan of action for the implementation and completion of the remaining activities of stage I of the HPMP by December 2018;
That funds for the fifth, sixth and seventh tranches of stage I of the HPMP amounting to US $4,162,210 would not be requested; 
That the Fund Secretariat had updated Appendix 2-A of the Agreement between the Government of Thailand and the Executive Committee, based on the adjustments of funds for the fifth, sixth and seventh tranches, and that paragraph 16 had been updated to indicate that the revised updated Agreement superseded that reached at the 77th meeting, as contained in Annex I to the present document; 
Requesting the Government of Thailand and the World Bank to submit: progress reports on a yearly basis on the implementation of the work programme associated with the final tranche until the completion of the project, verification reports until approval of stage II, and the project completion report to the first meeting of the Executive Committee in 2019; and
Approving the fourth and final tranche of stage I of the HPMP for Thailand, and the corresponding 2018 tranche implementation plan, at the amount of US $3,063,542, plus agency support costs of US $214,448 for the World Bank.
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Annex I

TEXT TO BE INCLUDED IN THE REVISED UPDATED AGREEMENT BETWEEN THE GOVERNMENT OF THE THAILAND AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND FOR THE REDUCTION IN CONSUMPTION OF HYDROCHLOROFLUOROCARBONS
(Relevant changes are in bold font for ease of reference)

16.	This revised updated Agreement supersedes the updated Agreement reached between the Government of Thailand and the Executive Committee at the 77th meeting of the Executive Committee.

APPENDIX 2-A: THE TARGETS, AND FUNDING

	Row
	Particulars
	2012
	2013
	2014
	2015
	2016
	2017
	2018
	Total

	1.1
	Montreal Protocol reduction schedule of Annex C, Group I substances (ODP tonnes)
	n/a
	927.6
	927.6
	834.84
	834.84
	834.84
	834.84
	n/a

	1.2
	Maximum allowable total consumption of Annex C, Group I substances (ODP tonnes)
	n/a
	927.6
	927.6
	834.84
	834.84
	834.84
	788.46
	n/a

	2.1
	Lead IA (World Bank) agreed funding (US $)*
	4,817,166
	9,706,154
	618,803
	3,063,542
	0
	0
	0
	18,205,665

	2.2
	Support costs for Lead IA (US $)
	337,202
	679,431
	43,316
	214,448
	0
	0
	0
	1,274,397

	2.3
	Cooperating IA (Japan) agreed funding (US $)
	302,965
	0
	0
	0
	0
	0
	0
	302,965

	2.4
	Support costs for Cooperating IA (US $)
	39,385
	0
	0
	0
	0
	0
	0
	39,385

	3.1
	Total agreed funding (US $)
	5,120,131
	9,706,154
	618,803
	3,063,542
	0
	0
	0
	18,508,630

	3.2
	Total support costs (US $)
	376,587
	679,431
	43,316
	214,448
	0
	0
	0
	1,313,782

	3.3
	Total agreed costs (US $)
	5,496,718
	10,385,585
	662,119
	3,277,990
	0
	0
	0
	19,822,412

	4.1.1
	Total phase-out of HCFC-22 agreed to be achieved under this Agreement (ODP tonnes)
	67.86

	4.1.2
	Phase-out of HCFC-22 to be achieved in previously approved projects (ODP tonnes)
	0

	4.1.3
	Remaining eligible consumption for HCFC-22 (ODP tonnes)
	648.74

	4.2.1
	Total phase-out of HCFC-123 agreed to be achieved under this Agreement (ODP tonnes)
	0.00

	4.2.2
	Phase-out of HCFC-123 to be achieved in previously approved projects (ODP tonnes)
	0.00

	4.2.3
	Remaining eligible consumption for HCFC-123 (ODP tonnes)
	3.20

	4.3.1
	Total phase-out of HCFC-124 agreed to be achieved under this Agreement (ODP tonnes)
	0.00

	4.3.2
	Phase-out of HCFC-124 to be achieved in previously approved projects (ODP tonnes)
	0.00

	4.3.3
	Remaining eligible consumption for HCFC-124 (ODP tonnes)
	0.08

	4.4.1
	Total phase-out of HCFC-141b agreed to be achieved under this Agreement (ODP tonnes)
	151.68

	4.4.2
	Phase-out of HCFC-141b to be achieved in previously approved projects (ODP tonnes)
	0.00

	4.4.3
	Remaining eligible consumption for HCFC-141b (ODP tonnes)
	53.57

	4.5.1
	Total phase-out of HCFC-142b agreed to be achieved under this Agreement (ODP tonnes)
	0.00

	4.5.2
	Phase-out of HCFC-142b to be achieved in previously approved projects (ODP tonnes)
	0.00

	4.5.3
	Remaining eligible consumption for HCFC-142b (ODP tonnes)
	0.12

	4.6.1
	Total phase-out of HCFC-225, 225ca and 225cb agreed to be achieved under this Agreement (ODP tonnes)
	0.00

	4.6.2
	Phase-out of HCFC-225, 225ca and 225cb to be achieved in previously approved projects (ODP tonnes)
	0.00

	4.6.3
	Remaining eligible consumption for HCFC-225, 225ca and 225cb (ODP tonnes)
	2.30

	4.7.1
	Total phase-out of HCFC-141b contained in imported pre-blended polyols agreed to be achieved under this Agreement (ODP tonnes)
	15.19

	4.7.2
	Phase-out of HCFC-141b contained in imported pre-blended polyols to be achieved in previously approved projects (ODP tonnes)
	0.00

	4.7.3
	Remaining eligible consumption for HCFC-141b contained in imported pre-blended polyols (ODP tonnes)
	0.49

	*The funds for the fifth (2016), sixth (2017) and seventh (2018) tranches amounting to US $1,000,000, US $753,630 and US $2,408,580, respectively, plus agency support costs will not be requested by the World Bank.
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