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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتمــــــاع الحادي والتسعــــون 
مونتريال، من 5 إلى 9 ديسمبر/ كانون الأول 2022
البند 9 (ج) من جدول الأعمال المؤقت[footnoteRef:1]  [1:  الوثيقة UNEP/OzL.Pro/ExCom/91/1 
] 







تعديلات برنامج عمل منظمة الأمم المتحدة للتنمية الصناعية لعام 2022





تعليقات وتوصيات أمانة الصندوق
1. تطلب منظمة الأمم المتحدة للتنمية الصناعية (اليونيدو) موافقة اللجنة التنفيذية على مبلغ قدره 2,119,977 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة وقدرها 150,198 دولاراً أمريكياً لتعديلات برنامج عملها لعام 2022 المدرجة في الجدول 1. ومرفق الطلب بهذه الوثيقة.
الجدول 1: تعديلات برنامج عمل منظمة الأمم المتحدة للتنمية الصناعية لعام 2022
	البلد
	النشاط/المشروع
	المبلغ المطلوب (دولار أمريكي)
	المبلغ الموصى به (دولار أمريكي)

	القسم ألف: الأنشطة المُوصى بالموافقة الشاملة عليها

	ألف-1: تجديد مشروعات التعزيز المؤسسي

	أرمينيا
	تجديد مشروع التعزيز المؤسسي (المرحلة الثامنة) 
	153,600
	153,600

	مصر
	تجديد مشروع التعزيز المؤسسي (المرحلة الرابعة عشرة) 
	292,253
	292,253

	ليبيا
	تجديد مشروع التعزيز المؤسسي (المرحلة السابعة) 
	174,164
	174,164

	المكسيك
	تجديد مشروع التعزيز المؤسسي (المرحلة السادسة عشرة) 
	316,160
	316,160

	تركيا
	تجديد مشروع التعزيز المؤسسي (المرحلة العاشرة) 
	332,800
	332,800

	المجموع الفرعي لألف 1
	1,268,977
	1,268977

	تكاليف دعم الوكالة
	88,828
	88,828

	المجموع لألف 1
	1,357,805
	1,357805,

	ألف 2: المساعدة التقنية في إعداد تقرير تحقق عن استهلاك المواد الهيدروكلوروفلوروكربون

	بوليفيا (دولة - المتعددة القوميات)
	تقرير تحق للمرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	30,000
	30,000

	إكوادور
	تقرير تحق للمرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	30,000
	30,000

	غواتيمالا
	تقرير تحق للمرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	30,000
	30,000

	المجموع الفرعي لألف 2
	90,000
	90,000

	تكاليف دعم الوكالة
	8,100
	8,100

	المجموع لألف 2
	98,100
	98,100

	
	
	

	ألف 3: إعداد المشاريع في إطار خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية

	المكسيك
	إعداد خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة)
	90,000
	90,000

	المجموع الفرعي لألف 3
	90,000
	90,000

	تكاليف دعم الوكالة
	6,300
	6,300

	المجموع لألف 3
	96,300
	96,300

	ألف-4: إعداد مشروعات في إطار خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون

	البوسنة والهرسك
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	130,000
	130,000

	الكونغو (أ)
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	119,000
	119,000

	كوت ديفوار (ب)
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	57,000
	57,000

	غابون (ب)
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	57,000
	57,000

	غينيا بيساو (ب)
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	39,000
	39,000

	المغرب
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	190,000
	190,000

	سانت لوسيا (ب)
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	40,000
	40,000

	جمهورية تنزانيا المتحدة (ب) 
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	39,000
	39,000

	المجموع الفرعي لألف 4
	671,000
	671,000

	تكاليف دعم الوكالة
	46,970
	46,970

	 مجموع ألف 4
	717,970
	717,970

	المجموع لألف 1 وألف 2 وألف 3 وألف 4
	2,119,977
	2,119,977

	تكاليف دعم الوكالة لألف 1 وألف 2 وألف 3 وألف 4
	150,198
	150,198

	المجموع الكلي
	2,270,175
	2,270,175


(أ) برنامج الأمم المتحدة للبيئة بصفته وكالة منفذة متعاونة
(ب) برنامج الأمم المتحدة للبيئة بصفته وكالة منفذة رئيسية

القسم ألف: الأنشطة المُوصى بالموافقة الشاملة عليها
ألف-1: تجديد مشروعات التعزيز المؤسسي
وصف المشروع
1. قدّمت منظمة الأمم المتحدة للتنمية الصناعية (اليونيدو) طلبات لمشروعات تجديد التعزيز المؤسسي للبلدان المذكورة في القسم ألف 1 من الجدول 1. ويرد وصف هذه المشروعات في المرفق الأول بهذه الوثيقة.
تعليقات الأمانة
1. استعرضت الأمانة طلبات تجديد مشروعات خدمات المعلومات الخمسة التي قدمتها اليونيدو نيابة عن الحكومات المعنية في ضوء المبادئ التوجيهية والقرارات ذات الصلة المتعلقة بالأهلية ومستويات التمويل. وتم فحص الطلبات مقارنة بخطط عمل التعزيز المؤسسي الأصلية للمرحلة السابقة، وبيانات البرنامج القطري والمادة 7، وآخر تقرير عن تنفيذ خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية، والتقرير المرحلي للوكالة، وأي قرارات ذات صلة صادرة عن اجتماعات الأطراف. ولوحظ أن هذه البلدان قدمت بيانات برامجها القطرية لعام 2021 وهي تمتثل لأهداف الرقابة في بروتوكول مونتريال، وأن استهلاكها السنوي من المواد الهيدروكلوروفلوروكربونية، لا يتجاوز الحد الأقصى المسموح به للاستهلاك السنوي المذكور في اتفاقات خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية المبرمة مع اللجنة التنفيذية. علاوة على ذلك، شملت الطلبات المقدمة مؤشرات أداء للأنشطة المقررة للمرحلة التالية من مشروعات التعزيز المؤسسي، وفقاً للمقرر 74/51 (هـ).
توصية الأمانة
1. توصي الأمانة بالموافقة الشاملة على طلبات تجديد التعزيز المؤسسي لأرمينيا ومصر وليبيا والمكسيك وتركيا بمستويات التمويل المشار إليها في القسم ألف 1 من الجدول 1 من هذه الوثيقة. وقد ترغب اللجنة التنفيذية في أن توضح للحكومات المذكورة أعلاه التعليقات الواردة في المرفق الثاني بهذه الوثيقة.
ألف 2: المساعدة التقنية في إعداد تقرير تحقق عن استهلاك المواد الهيدروكلوروفلوروكربون
وصف المشروع
1. طلبت اللجنة التنفيذية من الوكالات الثنائية والمنفذة ذات الصلة أن تدرج في برنامج عملها تعديلات برنامج عملها لتقديمها إلى الاجتماع الحادي والتسعين، تمويلاً لإعداد تقارير التحقق لبلدان مختارة عاملة بالمادة 5. وتطلب اليونيدو، بصفتها الوكالة المنفذة الرئيسية، تمويلاً للتحقق في إطار المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في بوليفيا (دولة - المتعددة القوميات) وإكوادور وغواتيمالا.[footnoteRef:2]  [2:  المقرر 90/33.] 

تعليقات الأمانة
1. أشارت الأمانة إلى أن التمويل المطلوب يتوافق مع الأموال الموافق عليها لعمليات التحقق المماثلة الخاصة باجتماعات سابقة. وأشارت كذلك أنه يتعيَّن تقديم تقرير التحقق قبل 10 أيام على الأقل من اجتماع اللجنة التنفيذية ذي الصلة الذي تُطلب فيه شريحة التمويل التالية لخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية.
توصية الأمانة
1. توصي الأمانة بالموافقة الشاملة على إعداد تقارير التحقق للمرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبوليفيا (دولة - المتعددة القوميات) وإكوادور وغواتيمالا بمستويات التمويل المبينة في القسم ألف-2 من الجدول 1، على أساس أن تقارير التحقق ينبغي أن تقدم قبل 10 أسابيع على الأقل من اجتماعات اللجنة التنفيذية ذات الصلة التي يجري فيها البحث عن شرائح التمويل التالية لخطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية.
ألف 3: إعداد المشروعات في إطار خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية
وصف المشروع
1. [bookmark: _Hlk117154536]قدمت منظمة الأمم المتحدة للتنمية الصناعية (اليونيدو) طلباً لإعداد المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للمكسيك باعتبارها الوكالة المنفذة المعيّنة، كما هو مبين في القسم ألف 3 من الجدول 1.
1. وقدمت اليونيدو أوصافًا للأنشطة لدعم طلب إعداد المشروع في إطار المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، التي شملت: بياناً لأسباب التمويل المطلوب لإعداد المشروع؛ وتقريراً مرحلياً عن تنفيذ المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية؛ وقائمة بالأنشطة التي ستنفذ أثناء إعداد المشروع، والميزانيات المقابلة. 
تعليقات الأمانة
1. عند استعراض هذا الطلب، أخذت الأمانة في الاعتبار المبادئ التوجيهية لتمويل إعداد خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبلدان العاملة بالمادة 5 الواردة في المقرر 71/42، [footnoteRef:3]والتقدم المحرز في المرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية بما في ذلك حالة تنفيذ الشرائح عند إعداد الوثيقة الحالية، والمقرر 84/46(هـ).[footnoteRef:4] وأشارت الأمانة إلى أن التمويل المطلوب يتوافق مع المقرر 71/42. [3:  المبادئ التوجيهية لتمويل إعداد المرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبلدان العاملة بالمادة 5]  [4:  يُسمح بإدراج المرحلة الثالثة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية في خطة العمل فقط لتلك البلدان التي لديها المرحلة الثانية المعتمدة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية مع أهداف خفض أقل من أهداف الامتثال لعام 2025.] 

1. ولاحظت الأمانة أن الاجتماع التسعين شهد تمديد تاريخ نهاية مشروع المرحلة الثانية خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية إلى 31 ديسمبر/ كانون الأول 2024،[footnoteRef:5] وأشارت إلى أن الطلب يتماشى مع المقرر 82/45 من حيث أن طلبات المرحلة الثالثة يمكن تقديمها قبل عامين من تاريخ نهاية المرحلة الثانية من الخطة.  [5:  المقرر 90/46.] 

1. وأكدت اليونيدو أن طلب إعداد مشروع للمرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في المكسيك سيؤدي إلى الإزالة بنسبة 100 في المائة من استهلاك الهيدروكلوروفلوروكربون بحلول 1 يناير/كانون الثاني 2030.
توصية الأمانة
1. توصي الأمانة بالموافقة الشاملة على إعداد المشروع للمرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية في المكسيك، على مستوى التمويل المبين في القسم ألف 3 من الجدول 1.
ألف-4: إعداد مشروعات في إطار خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون
وصف المشروع
1. قدمت اليونيدو طلبات لإعداد المرحلة الأولى من خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون لبلدين من البلدان العاملة بالمادة 5 بوصفهما الوكالة المنفذة المعيّنة؛ ولبلد واحد يعمل بالمادة 5 باعتباره الوكالة المنفذة الرئيسية إلى جانب برنامج الأمم المتحدة للبيئة بوصفه الوكالة المنفذة المتعاونة؛ ولخمسة بلدان باعتبارها الوكالة المنفذة المتعاونة إلى جانب برنامج الأمم المتحدة للبيئة بوصفه الوكالة المنفذة الرئيسية، كما هو مبين في القسم ألف 4 من الجدول 1. وقد طلب برنامج الأمم المتحدة للبيئة، بوصفه الوكالة المنفذة الرئيسية لكوت ديفوار وغابون وغينيا - بيساو وسانت لوسيا وجمهورية تنزانيا المتحدة والوكالة المنفذة المتعاونة للكونغو، مبلغاً وقدره 589,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 76,570 دولاراً أمريكياً في تعديلات برنامج عمله لعام 2022.[footnoteRef:6]  [6:  الوثيقة UNEP/OzL.Pro/ExCom/91/33.] 

تعليقات الأمانة
1. عند استعراض هذه الطلبات، أخذت الأمانة في الاعتبار المبادئ التوجيهية لإعداد خطط تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية على النحو الوارد في المقرر 87/50؛ والأنشطة المقترحة لإعداد المشروع وعلاقتها بالأنشطة التمكينية وغيرها من المشاريع المتعلقة بالمواد الهيدروفلوروكربونية في بلدانهم. وأشارت الأمانة إلى أن اليونيدو، بصفتها الوكالة المنفذة المعيَّنة/الرئيسية، قدمت أوصافا للأنشطة اللازمة لإعداد الاستراتيجية الشاملة للمرحلة الأولى من خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون للبوسنة والهرسك والكونغو والمغرب. وشملت الطلبات بيانات عن استهلاك المواد الهيدروفلوروكربونية وخلائط الهيدروفلوروكربون لجميع البلدان. وشملت أنشطة إعداد المشاريع للبلدان الثلاثة إجراء مسح وطني وجمع بيانات عن استهلاك الهيدروفلوروكربون؛ وتحليل استخدام المواد الهيدروفلوروكربونية والبدائل؛ وتقييم القدرات والاحتياجات التدريبية في قطاع الخدمات، وتقييم قدرات الاستصلاح والتدمير؛ ووضع استراتيجية شاملة للتخفيض التدريجي للهيدروفلوروكربون؛ وإعداد التدابير الأولية‑ ذات الصلة بالهيدروفلوروكربون؛ والمشاورات مع أصحاب المصلحة والتحقق. كما تضمنت الخطط الخاصة بالبوسنة والهرسك والكونغو استعراضات للسياسات والتشريعات المتعلقة بالتخفيض التدريجي‑ للهيدروفلوروكربون؛ وتحليل بناء القدرات المطلوبة للجمارك؛ ووضع خطة للتواصل والتوعية. وأُدرجت دراسة لكفاءة الطاقة في جميع القطاعات في الأنشطة الخاصة بالكونغو والمغرب، كما أُدرجت أنشطة تعميم مراعاة المنظور الجنساني في خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون كجزء من الأنشطة الخاصة بالكونغو. 
1. وأشارت الأمانة إلى أن جميع البلدان الثلاثة التي تؤدي فيها اليونيدو دور الوكالة المنفذة المعينة أو الرئيسية قد صدقت على تعديل كيغالي؛[footnoteRef:7] وأن البلدان قدمت خطابات مصادقة تبين اعتزامها اتخاذ إجراءات مبكرة بشأن التخفيض التدريجي للهيدروفلوروكربون؛ وأن التمويل المطلوب يتوافق مع المقرر 87/50. [7:  تاريخ التصديق على تعديل كيغالي (أو قبوله): البوسنة والهرسك (26 مايو/أيار 2021) والكونغو (16 يونيه/حزيران 2022) والمغرب (22 أبريل/نيسان 2022).] 

1. [bookmark: _Hlk104444546]وقدم برنامج الأمم المتحدة للبيئة، بوصفه وكالة التنفيذ الرئيسية لكوت ديفوار وغابون وغينيا - بيساو وسانت لوسيا وجمهورية تنزانيا المتحدة، وصفاً للأنشطة المطلوبة لإعداد خطط التنفيذ المشتركة والتكاليف المقابلة لكل نشاط في تعديلات برنامج عمله؛[footnoteRef:8] كما ترد تعليقات الأمانة في ذلك التقرير. [8:  الوثيقة UNEP/OzL.Pro/ExCom/91/33.] 

توصية الأمانة
1. توصي الأمانة بالموافقة الشاملة على إعداد المشاريع لخطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون للبوسنة والهرسك والكونغو وكوت ديفوار وغابون وغينيا بيساو والمغرب وسانت لوسيا وجمهورية تنزانيا المتحدة بمستويات التمويل المبينة في القسم ألف 4 من الجدول 1.


UNEP/OzL.Pro/ExCom/91/34


UNEP/OzL.Pro/ExCom/91/34



إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها. 
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	Annex I
INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:9] [9:  Data as at December 2021 are based on document UNEP/OzL.Pro/ExCom/91/16.] 


Armenia: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Apr-09
	120,000

	Phase II:
	Dec-10
	120,000

	Phase III:
	Dec-12
	120,000

	Phase IV:
	Nov-14
	120,000

	Phase V:
	May-16
	153,600

	Phase VI:
	Dec-18
	153,600

	Phase VII:
	Dec-20
	153,600

		Total:
	940,800

	Amount requested for renewal (phase VIII) (US $):
	153,600 

	Amount recommended for approval for phase VIII (US $): 
	153,600

	Agency support costs (US $):
	10,752

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	164,352

	Date of approval of country programme:
	2009

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	7.0

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.56

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.56

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	2,413,638

	Amount disbursed (as at December 2021) (US $):
	1,815,354

	ODS to be phased out (as at June 2022) (ODP tonnes):
	3.53

	ODS phased out (as at December 2021) (ODP tonnes):
	2.20



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	692,438

	(b)
	Institutional strengthening:
	940,800

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	780,400

		Total:
	2,413,638

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase VII of the institutional strengthening (IS) project, Armenia made substantive progress in reviewing the specific national regulations aimed at controlling the import, transit, and movement of ODS in the country. In addition, Armenia improved HCFC control by taking into account the regional approach, adopting the integrated regional concept and being an active member of the region. Regular access of the National Ozone Unit (NOU) staff to senior decision-makers was assured through integration of the NOU’s Action Plan in the National Environmental Action Plan and by the legislative framework put in place. The awareness-raising programme, the latest ODS phase-out achievements, as well as the latest decisions and regulations referring to HCFC consumption in the country and the country policy are public information that was updated on a weekly basis on the dedicated webpage of the Ministry of Environment Protection ((https://www.armozone.am/en/). Of the 23 performance indicators selected for the phase, 19 were fully achieved, three were partially achieved, and one was not achieved.
Plan of action
During the upcoming phase, Armenia aims to address sustainability of the NOU by ensuring continuity of the staff. This phase of the project will assist the Government in meeting its obligations under the Montreal Protocol, with a specific focus on the future HFC phase-down including required national policies and preparation for HFC restrictions. In this context, the NOU will assist in monitoring and identification of ODS consumption and follow-up on the ongoing update of current national policies and regulations. Illegal trade will be pursued in close collaboration with Customs, as well as awareness-raising of technicians about recovery and recycling techniques and practices, with a view to use the gained experience in the HCFC phase-out programme. The NOU will continue to actively cooperate with ministries and inter-ministerial bodies as well as with advisory groups such as non-governmental organizations, refrigeration and air-conditioning associations and others.
Egypt: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jun-93
	263,450

	Phase II:
	Nov-95
	219,530

	Phase III:
	Mar-99
	175,000

	Phase IV:
	Jul-01
	175,000

	Phase V:
	Jul-03
	228,323

	Phase VI:
	Mar-07
	228,323

	Phase VII:
	Nov-08
	228,323

	Phase VIII:
	Jul-10
	228,323

	Phase IX:
	Jul-12
	228,323

	Phase X:
	May-14
	228,323

	Phase XI:
	May-16
	292,253

	Phase XII:
	Jun-18
	292,253

	Phase XIII:
	Dec-20
	292,253

		Total:
	3,079,677

	Amount requested for renewal (phase XIV) (US $):
	292,253

	Amount recommended for approval for phase XIV (US $): 
	292,253

	Agency support costs (US $):
	20,458

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	312,711

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	26.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	386.3

	(c)	Annex E (methyl bromide) (average 1995-1998)
	238.1

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	209.16

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	209.16

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	78,973,141

	Amount disbursed (as at December 2021) (US $):
	58,606,212

	ODS to be phased out (as at June 2022) (ODP tonnes):
	4,669.97

	ODS phased out (as at December 2021) (ODP tonnes):
	4,548.60



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	69,193,052

	(b)
	Institutional strengthening:
	3,079,677

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	6,700,412

		Total:
	78,973,141

	(d)
	HFC activities funded from additional voluntary contributions
	280,000



Progress report
1. During phase XIII of the IS project, the Egyptian Environmental Affairs Agency / Ozone Layer Protection Section (NOU) advanced the implementation of Montreal Protocol activities in the country and ensured the country’s compliance with its reduction targets. The focus during the phase was on: strict monitoring of HCFC trade through the national ODS regulatory framework and allocation of quotas; further strengthening cooperation with customs authorities ensuring sustained ODS phase-out; organization of training activities with customs officers on prevention of illegal trade; collaborating and sharing information with the industry associations and a large spectrum of institutions; organizing regular meetings of the National Ozone Committee; finalization of activities under stage I of the HPMP and coordination of stage II of the HPMP activities; implementation of the enabling activities project to prepare the country for ratification of the Kigali Amendment; public awareness activities, including celebration of International Ozone Day; country programme and Article 7 data reporting; and active participation in regional network and Montreal Protocol meetings. Of the 17 performance indicators selected for the phase, 15 are fully achieved and two are partially achieved.


Plan of action
1. During phase XIV, the NOU’s priority will be for Egypt to achieve its 2024 HCFC reduction target and continue with the implementation of stage II of the HPMP, including the conversion of manufacturers in the polyurethane foam and residential air-conditioning sectors that will result in significant reduction of ODS consumption. Activities planned for the phase include: country programme and Article 7 data reporting; continued monitoring of the licensing system and allocation of import quotas; continuing implementing activities under stage II of the HPMP; continuing cooperation with customs authorities and industry associations; facilitating the ratification process of the Kigali Amendment through implementation of the enabling activities project and requesting preparatory funding for developing the Kigali HFC implementation plan. Public awareness activities will include the celebration of International Ozone Day and the country plans to participate in regional network and Montreal Protocol meetings, whether online or physical, when conditions allow. The country has included 20 performance indicators for the upcoming phase, including two gender‑related indicators.
Libya: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-00
	157,000

	Phase II:
	Nov-09 & Apr-10
	136,065

	Phase III:
	Dec-13
	136,065

	Phase IV:
	May-15 & Dec-16
	155,115

	Phase V:
	Jun-18
	174,164

	Phase VI:
	Jun-20
	174,164

		Total:
	932,573

	Amount requested for renewal (phase VII) (US $):
	174,164

	Amount recommended for approval for phase VII (US $): 
	174,164

	Agency support costs (US $):
	12,191

	Total cost of institutional strengthening phase VII to the Multilateral Fund (US $):
	186,355

	Date of approval of country programme (CP):
	1999

	Date of approval of HCFC phase-out management plan:
	2015

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	118.38

	(c)	Annex E (methyl bromide) (average 1995-1998)
	94.1

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0

	(b)	Annex C, Group I (HCFCs)
	75

	(c)	Annex E (methyl bromide)
	0

		Total:
	75

	Year of reported CP implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	10,878,884

	Amount disbursed (as at December 2021) (US $):
	7,588,732

	ODS to be phased-out (as at June 2022) (ODP tonnes):
	1,604.99

	ODS phased-out (as at December 2021) (ODP tonnes):
	890.90



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	8,667,811

	(b)
	Institutional strengthening:
	932,573

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,278,500

		Total:
	10,878,884

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
1. During phase VI of the IS project, the Libyan NOU was fully staffed. Significant efforts were made, given the country’s political and security situation, to continue with the implementation of Montreal Protocol activities. Quotas for the period 2020 through 2022 were established and are monitored on regular basis. The country’s HCFC consumption was below the control limits. The NOU continued to maintain cooperation with other public institutions through regular bilateral meetings, inter-ministerial meetings and steering committees. Country programme data and Article 7 data reports for 2020 and 2021 were submitted on time. Ozone Day celebrations were organized in 2021. Libyan officials attended the online Meetings of the Parties and Open-ended Working Group meetings during the reporting period. However, due to visa issues, they could not attend the meetings organized in person. Libya has successfully achieved 10 out of the 16 planned performance indicators, while four were partially achieved and two were not achieved.
Plan of action
1. During the upcoming phase, the NOU will continue to monitor HCFC consumption to maintain compliance with the quota system and licensing system. Quotas will be issued for the years 2023 and 2024 to maintain HCFC consumption in line with the Agreement between the Executive Committee and the country and with its commitments in decision XXVII/11. Activities planned under the next phase include: country programme and Article 7 data reporting; continued monitoring the licensing system and allocation of quotas to achieve full control over the imports of all HCFCs; continued efforts to introduce a ban on importing or manufacturing HCFC-based equipment; continued cooperation with customs authorities and industry representatives; facilitating the ratification process of the Kigali Amendment; and supervising the completion of activities under stage I of the HPMP and the implementation of stage II activities. Public awareness activities will include the celebration of International Ozone Day and Libya plans to participate in regional network and Montreal Protocol meetings held during the phase. The country has included 16 performance indicators for phase VII.
Mexico: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jun-92 & Dec-94 
	350,000

	Phase II:
	Jul-95 
	95,000

	Phase III:
	Oct-96
	190,000

	Phase IV:
	Jul-98
	190,000

	Phase V:
	Jul-00 
	190,000

	Phase VI:
	Jul-02
	247,000

	Phase VII:
	Apr-05
	247,000

	Phase VIII:
	Jul-07
	247,000

	Phase IX:
	Jul-09
	185,250

	Phase X:
	Dec-10
	247,000

	Phase XI:
	Dec-12
	247,000

	Phase XII
	Nov-14
	247,000

	Phase XIII
	Jul-17
	316,160

	Phase XIV:
	Dec-18
	316,160

	Phase XV:
	Dec-20
	316,160

		Total:
	3,630,730

	Amount requested for renewal (phase XVI) (US $):
	316,160

	Amount recommended for approval for phase XVI (US $): 
	316,160

	Agency support costs (US $):
	22,131

	Total cost of institutional strengthening phase XVI to the Multilateral Fund (US $):
	338,291

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	56.4

	Annex C, Group I (HCFCs) (average 2009-2010)
	1,148.8

	Annex E (methyl bromide) (average 1995-1998)
	1,130.8

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	-90.11

	Annex E (methyl bromide)
	0.00

		Total:
	-90.11

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	131,521,310

	Amount disbursed (as at December 2021) (US $):
	118,668,152

	ODS to be phased out (as at June 2022) (ODP tonnes):
	7,179

	ODS phased out (as at December 2021) (ODP tonnes):
	7,114



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	114,514,167

	(b)
	Institutional strengthening:
	3,630,730

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	13,376,413

		Total:
	131,521,310

	(d)
	HFC activities funded from additional voluntary contributions
	1,298,123



Progress report
During phase XV of the IS project, the NOU followed up with priority to reduce Mexico’s HCFC consumption in accordance with the HPMP measures and continued implementing approved projects and application of the quota system to meet the reduction target in 2021 as per stage II of the HPMP. The HCFC quota system was improved, and the quotas and reduction targets were made public. Coordination activities continued including consultations with the national steering committee in the Head of the Office with Ministry of Foreign Affairs, industry associations, and other stakeholders. Public awareness activities also continued including the dissemination of materials for social media and the website relating to HCFC phase‑out and HFC phase-down. A training programme continued to be improved including the addition of good practices in refrigeration servicing to avoid the use of HCFC. All these activities allowed Mexico to reduce its HCFC consumption and permitted Mexico to meeting its goal of eliminating 67.5 per cent of the HCFC baseline. A roadmap to implement the Kigali Amendment was the main result of the enabling activities project. The roadmap presents the general “way forward” to implement the Kigali Amendment, based on the national diagnosis on use, consumption and sectoral distribution of HFCs. It also included an analysis of the national legal framework for the control of the consumption of substances regulated by the Montreal Protocol and its amendments. The roadmap proposed an initial general identification of the short, medium and long-term actions of four pillars of public policy on which the HFC phase-down will be supported: regulation, strategic planning, implementation, and reporting and verification. Of the 29 performance indicators selected for the phase, 21 were fully achieved, five were partially achieved and three were not achieved.
Plan of action
During the upcoming phase, the NOU will continue to keep control of HCFC consumption and implement projects and the quota system to ensure sustainability of the reduction. In addition, the NOU will work to promote the strengthening of the NOU through operational monitoring of activities, documentation and dissemination of projects; and promoting training of NOU staff in technical aspects, such as logical frameworks, the project cycle and the implementation of environmental projects supported by international funding. Work will also aim to improve the efficiency of the link between the national government and the implementing agency, as well as implementing actions to incorporate the Multilateral Fund policy on gender, including a gender analysis and gender action plan for the integration of gender sensitive actions among Multilateral Fund-supported projects. Mexico will also prepare its HFC reduction strategy during the upcoming phase.
Türkiye: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNIDO

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-92
	300,000

	Phase II:
	Dec-00
	200,000

	Phase III:
	Dec-04
	260,000

	Phase IV:
	Jul-09
	195,000

	Phase V:
	Jul-11
	260,000

	Phase VI:
	Jul-13
	260,000

	Phase VII:
	May-15
	260,000

	Phase VIII:
	Nov-17
	332,800

	Phase IX:
	Dec-19
	332,800

		Total:
	2,400,600

	Amount requested for renewal phase X (US $):
	332,800

	Amount recommended for approval for phase X (US $): 
	332,800

	Agency support costs (US $):
	23,296

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	356,096

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	37.4

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	551.5

	(c)	Annex E (methyl bromide) (average 1995-1998)
	479.7

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	3.52

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	3.52

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	57,267,795

	Amount disbursed (as at December 2021) (US $):
	49,911,747

	ODS to be phased out (as at June 2022) (ODP tonnes):
	4,963.25

	ODS phased out (as at December 2021) (ODP tonnes):
	5,002.10



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	48,771,797

	(b)
	Institutional strengthening:
	2,400,600

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	6,095,398

		Total:
	57,267,795

	(d)
	HFC activities funded from additional voluntary contributions
	250,000


Progress report
During phase IX of the IS project, the capacity of the Turkish NOU increased due to the allocation of an additional staff member by the Ministry of Environment, Urbanization and Climate Change, during a restructuring process. Progress was achieved in reviewing the ODS national legislation and through early introduction of HFC licensing, reporting and certification requirements, as a preparatory step to ensure future compliance with the HFC phase-down targets. In addition, Türkiye ratified the Kigali Amendment on 10 November 2021. The focus in the current phase was on: strict monitoring of HCFC trade through the national ODS regulatory framework and allocation of quotas; upgrading the ODS database with new modules, including the improvement of electronic systems allowing a centralized database for HFCs accessible by the NOU, customs, and trade authorities; further strengthening the cooperation with the customs authorities ensuring sustained ODS phase-out; organization of training activities with stakeholders related to the upcoming obligation following the Kigali Amendment ratification; collaboration and sharing information with the industry associations and large spectrum of institutions; organizing regular meetings of the Steering Committee; finalization of activities under stage I of the HPMP; coordination of activities for submission and approval of the preparatory funding for the Kigali HFC implementation plan; public awareness activities including celebration of International Ozone Day; country programme and Article 7 data reporting; and active participation in regional network and Montreal Protocol meetings. Of the 13 performance indicators selected for the phase, 12 were fully achieved and one was partially achieved.
Plan of action
During the upcoming phase, the NOU of Türkiye will focus on awareness-raising activities, combating illegal trade, regional cooperation and participation, and data collection and data, which were selected based on self-evaluation done by the NOU. New generation ozone- and climate-friendly alternatives to ODS and F-gases will be fully supported through training and acknowledgement meetings. Strengthened monitoring of ODS and HFC trade, especially through the use of innovative, IT-based and context-dependent approaches, is aimed at combating the illegal trade of ODS and HFCs. In addition, strengthened data collection and reporting of ODS and HFCs will be included. Improving communication and networking among stakeholders, as well as the awareness on the protection of the ozone layer will also be a focus of the upcoming phase. The NOU will work towards increased visibility at both the regional and international levels. The country has included 18 performance indicators for phase X, including two gender related indicators.
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	المرفق الثاني

مشاريع الآراء التي أعربت عنها اللجنة التنفيذية بشأن تجديد مشروعات التعزيز المؤسسي المقدمة إلى الاجتماع الحادي والتسعين 

أرمينيا
1. [bookmark: _Hlk119158666]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لأرمينيا (المرحلة الثامنة) ولاحظت مع التقدير أن حكومة أرمينيا أبلغت أمانة الصندوق ببيانات البرنامج القطري وأبلغت أمانة الأوزون ببيانات المادة 7، مما يشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال. وأشارت اللجنة كذلك إلى أن البلد استعرض لوائح المواد المستنفدة للأوزون وحسّن الرقابة على المواد الهيدروكلوروفلوروكربونية؛ وأنجز الأنشطة في إطار المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، ونسق الإعداد للمرحلة الثالثة؛ ورفع مستوى الوعي العام بشأن بروتوكول مونتريال. ولذلك، فإن اللجنة واثقة من أن حكومة أرمينيا ستواصل في العامين المقبلين تنفيذ الأنشطة لتمكين البلد من الامتثال لأهداف بروتوكول مونتريال. 
مصر
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لمصر (المرحلة الرابعة عشرة) ولاحظت مع التقدير أن حكومة مصر أبلغت أمانة الصندوق ببيانات 2020 و2021 في إطار تقارير تنفيذ البرامج القطرية وأبلغت أمانة الأوزون بموجب المادة 7، مما يشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال. وأشارت اللجنة كذلك إلى أن البلد قد اتخذ خطوات لمواصلة إزالة استهلاك الهيدروكلوروفلوروكربون بما في ذلك الرصد الصارم لتجارة الهيدروكلوروفلوروكربون من خلال الإطار التنظيمي للمواد المستنفدة للأوزون وتخصيص الحصص، وكذلك من خلال زيادة تحسين قاعدة البيانات الإلكترونية. واستمر التعاون الوثيق مع السلطات الجمركية من أجل زيادة تحسين فعالية لوائح المواد المستنفدة للأوزون وضمان تنفيذ السياسات الصادرة عن لجنة الأوزون الوطنية. وأشارت اللجنة أيضاً إلى أن مشروع الأنشطة التمكينية لمشروع التخفيض التدريجي للهيدروفلوروكربون قد اكتمل، ولذلك، تأمل أن تقوم حكومة مصر، بالإضافة إلى مواصلة تنفيذ أنشطة إزالة الهيدروكلوروفلوروكربون بنجاح، بالتصديق على تعديل كيغالي قريباً.
ليبيا
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لليبيا (المرحلة السابعة) ولاحظت مع التقدير أن حكومة ليبيا أبلغت أمانة الصندوق ببيانات البرنامج القطري لعامي 2020 و2021 وأبلغت وأمانة الأوزون بيانات المادة 7، مما يشير إلى أن البلد في حالة امتثال لخطة العمل للعودة إلى الامتثال لبروتوكول مونتريال على النحو المبين في المقرر 27/11. وأشارت اللجنة إلى أن وحدة الأوزون الوطنية مجهزة بالكامل بالموظفين، على الرغم من الوضع السياسي والأمني الحالي في البلد، وأن حصص الاستهلاك السنوية يتم تحديدها ورصدها على أساس منتظم. وأقرت اللجنة بالجهود التي تبذلها الحكومة الليبية لإكمال المرحلة الأولى من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية ومشروع الأنشطة التمكينية للتخفيض التدريجي للهيدروفلوروكربون. ولذلك تأمل اللجنة أن تواصل حكومة ليبيا تنفيذ المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للحفاظ على الاستهلاك ضمن الحدود الخاضعة للرقابة المنصوص عليها في الاتفاق المبرم مع اللجنة التنفيذية والاستمرار في الامتثال لبروتوكول مونتريال ولالتزاماتها الواردة في المقرر 27/11. 
المكسيك
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للمكسيك (المرحلة السادسة عشرة) ولاحظت مع التقدير أن حكومة المكسيك أبلغت أمانة الصندوق ببيانات البرنامج القطري وأبلغت أمانة الأوزون بيانات المادة 7، مما يشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال. وأشارت اللجنة أيضاً إلى أنه في إطار مشروع التعزيز المؤسسي، حقق البلد تقدماً في تعزيز قدرة وحدة الأوزون الوطنية على مراقبة الهيدروكلوروفلوروكربون والتحضير لتنفيذ تعديل كيغالي؛ ليصبح عضواً نشطاً في شبكة الأوزون الإقليمية لأمريكا اللاتينية؛ ودعم بلدان المنطقة من خلال نشر إنجازاتها من خلال تنظيم حلقات عمل والقيام بزيارات تقنية. وأقرت اللجنة بالجهود التي تبذلها حكومة المكسيك لتنفيذ المرحلتين الأولى والثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية، ولذلك، تأمل أن يقدم البلد الأنشطة النهائية لإزالة المواد الهيدروكلوروفلوروكربونية، في كل من قطاعي الاستهلاك والإنتاج، وأن يبدأ أنشطة للتخفيض التدريجي للهيدروفلوروكربون.
تركيا

[bookmark: _Hlk118217586]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لتركيا (المرحلة العاشرة) ولاحظت مع التقدير أن حكومة تركيا أبلغت أمانة الصندوق ببيانات 2020 و2021 بموجب تقارير تنفيذ البرنامج القطري وأبلغت وأمانة الأوزون بموجب المادة 7، مما يشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال. وأشارت اللجنة كذلك إلى أن البلد قد اتخذ خطوات لإزالة استهلاك الهيدروكلوروفلوروكربون بما في ذلك الرصد الصارم لتجارة الهيدروكلوروفلوروكربون من خلال الإطار التنظيمي للمواد المستنفدة للأوزون وتخصيص الحصص، وكذلك من خلال زيادة تحسين قاعدة البيانات الإلكترونية. وأحاطت اللجنة علماً مع التقدير بتصديق تركيا على تعديل كيغالي في 10 تشرين الثاني/نوفمبر 2021، وبالتالي فهي واثقة من أن حكومة تركيا، بالإضافة إلى مواصلة تنفيذ أنشطة إزالة المواد الهيدروكلوروفلوروكربونية، ستشرع في أنشطة التخفيض التدريجي للهيدروفلوروكربون بما في ذلك تقديم المرحلة الأولى من خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون. 
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