| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/88/25 26 October 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-eighth Meeting

Montreal, 15-19 November 2021

UNEP BUSINESS PLAN FOR 2022–2024

# This document presents the UNEP business plan for 2022–2024 and includes: the planned activities for the phase-out of controlled substances under the Montreal Protocol (controlled substances) during the 2022–2024 period; the business plan performance indicators; policy issues; and a recommendation for consideration by the Executive Committee. The narrative of UNEP’s business plan for 20221–2024 is attached to the present document.

Planned activities during the 2022–2024 period

# Table 1 sets out, by year, the value of activities included in UNEP’s business plan.

Table 1. Resource allocation in the UNEP business plan for 2022–2024 as submitted (US $000s)*

| Description | 2022 | 2023 | 2024 | Total (2022–2024) | Total after 2024 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 4,864 | 4,865 | 5,024 | 14,753 | 11,895 |
| HPMP project preparation (PRP) – stage II | 124 | 99 | 34 | 258 | 0 |
| HPMP stage II | 2,349 | 1,712 | 850 | 4,911 | 6,419 |
| HPMP stage III | 1,019 | 3,890 | 534 | 5,443 | 4,752 |
| HCFC technical assistance | 509 | 0 | 0 | 509 |  |
| HCFC activities subtotal | 8,865 | 10,566 | 6,443 | 25,873 | 23,065 |
| HFC activities |  |  |  |  |  |
| Enabling activities for HFC phase-down | 0 | 214 | 0 | 214 | 0 |
| Kigali HFC implementation plan (KIP) – PRP | 5,213 | 1,513 | 0 | 6,726 | 0 |
| HFC - technical assistance | 678 | 0 | 678 | 1,356 | 0 |
| HFC activities subtotal | 5,891 | 1,727 | 678 | 8,296 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 5,940 | 5,610 | 5,940 | 17,490 | 0 |
| Compliance Assistance Programme (CAP) | 11,428 | 11,771 | 12,124 | 35,323 | 0 |
| Standard activities subtotal | 17,368 | 17,381 | 18,064 | 52,812 | 0 |
| Total | 32,123 | 29,674 | 25,184 | 86,982 | 23,065 |

* Including agency support costs where applicable.

# Secretariat’s comments

Stage II of HPMPs

# The total levels of funding for stage II of HPMPs for low-volume-consuming (LVC) countries to meet the 67.5 per cent reduction of the HCFC baseline amount to US $1.23 million (including US $440,315 for 2022–2024), and to US $5.05 million (including US $1.83 million for 2022–2024) to meet 100 per cent reduction.

# The total levels of funding for stage II of HPMPs for non-LVC countries amount to US $5.04 million (including US $2.64 million for 2022–2024).

# Stage III of HPMPs

# A total of US $10.19 million is included in the business plan for stage III of HPMPs for seven countries (Armenia, Chile, India, Islamic Republic of Iran, Oman, Pakistan and the Republic of Moldova) (including US $5.44 million for 2022–2024).

# HCFC technical assistance regional project

# UNEP has included one HCFC technical assistance regional project for promoting low-global warming potential refrigerants for air-conditioning sectors in high ambient temperature countries (PRAHA-III), amounting to US $508,500 in 2022. This project was considered at the 86th meeting during which a few members expressed support for reinstating the project; however it was also pointed out that there was no funding window for such technical assistance projects and that the work required to address low to zero-GWP alternatives was outlined in decision XXVIII/2. Subsequently, the project was not reinstated  in the 2022-2024 business plan.

HFC-related activities

# HFC activities include enabling activities amounting to US $214,000 in 2023 for two countries (Antigua and Barbuda and the Central African Republic), one technical assistance activity amounting to US $1.36 million for 2022-2024, and KIP project preparation activities for 56 countries amounting to US $6.73 million in 2022 and 2023.

# Both countries for which enabling activities have been included, submitted the required letter from their Government indicating their intent to make best efforts to ratify the Kigali Amendment as early as possible, in line with decision 79/46(d)(i).

# Twenty-seven of the 56 countries for which KIP project preparation activities have been included have not ratified the Kigali Amendment, but have submitted the required letter from their Government indicating their intent to make best efforts to ratify the Amendment except for the Democratic Republic of the Congo.

# UNEP has included one global HFC technical assistance project, Twinning of Ozone Officers and National Energy Policymakers to support Kigali Amendment Objectives, which is not eligible for funding.

CAP

# The cost for CAP is expected to increase at an annual rate of 3 per cent as agreed by the Executive Committee. The total level of funding for CAP is US $35.32 million for 2022–2024. The CAP budget for 2022 has been submitted to the 88th meeting.

Proposed adjustments by the Secretariat

# The adjustments to the UNEP business plan for 2022–2024 were based on relevant decisions of the Executive Committee. Further adjustments may be required pending a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021–2023 triennium.

# In reviewing the revised UNEP business plan for 2022–2024, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNEP business plan for 2022–2024 (US $000)

| Adjustment | 2022–2024 | After 2024 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements, including tranches of HPMPs that are due but not submitted to the 88th meeting | 34 | 0 |
| HPMP values to reflect the draft Agreements submitted to the 88th meeting | (160) | (407) |
| Stage II of HPMPs for LVC countries to the maximum allowable value to meet the 67.5 or 100 per cent reductions in the HCFC baseline based on decision 74/50(c)(xii) | (164) | 0 |
| HCFC technical assistance | (509) | 0 |
| PRP for KIPs pursuant to decision 87/50 | (226) | 0 |
| HFC technical assistance | (1,356) | 0 |
| IS project for the Democratic People’s Republic of Korea pursuant to decision 80/34(c)(iii)b | (333) | 0 |

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNEP business plan for 2022–2024, which are also addressed in the context of the Consolidated business plan of the Multilateral Fund for 2022–2024.

Table 3. Resource allocation in UNEP’s adjusted business plan for 2022–2024 (US $000s)*

| Description | 2022 | 2023 | 2024 | Total (2022–2024) | Total after 2024 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 4,604 | 5,158 | 5,024 | 14,786 | 11,895 |
| HPMP PRP – stage II | 124 | 99 | 34 | 258 | 0 |
| HPMP stage II | 2,022 | 1,875 | 773 | 4,669 | 6,497 |
| HPMP stage III | 761 | 3,890 | 709 | 5,361 | 4,266 |
| HCFC technical assistance | 0 | 0 | 0 | 0 | 0 |
| HCFC activities subtotal | 7,512 | 11,022 | 6,540 | 25,074 | 22,658 |
| HFC activities |  |  |  |  |  |
| Enabling activities for HFC phase-down | 0 | 214 | 0 | 214 | 0 |
| KIP – PRP | 4,987 | 1,513 | 0 | 6,500 | 0 |
| HFC – technical assistance | 0 | 0 | 0 | 0 | 0 |
| HFC activities subtotal | 4,987 | 1,727 | 0 | 6,714 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 5,773 | 5,610 | 5,773 | 17,157 | 0 |
| CAP | 11,428 | 11,771 | 12,124 | 35,323 | 0 |
| Standard activities subtotal | 17,201 | 17,381 | 17,897 | 52,479 | 0 |
| Total | 29,700 | 30,130 | 24,437 | 84,268 | 22,658 |

* Including agency support cost where applicable.

Performance indicators

# UNEP submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed UNEP of the targets shown in Table 4.

Table 4. Performance indicators for UNEP for 2022

| Type of indicator | Short title | Calculation | 2022 target |
| --- | --- | --- | --- |
| Planning--Approval | Tranches approved | Number of tranches approved vs. those planned* | 54 |
| Planning--Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities)** | 99 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $21,629,928 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans* | 93.6 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 91 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 14 months |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | On time (15) |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another cooperating or lead agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

# Table 5 presents UNEP’s performance indicators for its CAP, which were adopted in decision 48/7(e).

Table 5. Performance indicators for UNEP’s CAP for 2022

| Performance Indicator | Data | Assessment | 2022 target |
| --- | --- | --- | --- |
| Efficient follow-up to regional network/ thematic meetings | List of recommendations emanating from 2018-2019 regional network/thematic meetings | Implementation rate of those meeting recommendations that are to be implemented in 2020 | 90% implementation rate |
| Effective support to National Ozone Units (NOUs) in their work, particularly guidance to new NOUs | List of innovative ways/means/ products/ services for supporting NOUs in their work, with specification of those destined for new NOUs | Number of innovative ways, means, products, services for supporting NOUs in their work, with specification of those destined for new NOUs | - 7 such ways, means, products, services; -All new NOUs receive capacity building support. |
| Assistance to countries in actual or potential noncompliance (as per MOP decisions and/or as per reported Article 7 data and trend analysis) | List of countries in actual or potential on compliance that received CAP assistance outside the network meetings | Number of countries in actual or potential non-compliance that received CAP assistance outside the network meetings | All such countries |
| Innovations in production and delivery of global and regional information products and services | List of global and regional information products and services destined for new target audiences or that reach existing target audiences in new ways | Number of global and regional information products and services destined for new target audiences or that reach existing target audiences in new ways | 7 such products and services |
| Close cooperation between CAP regional teams and Implementing and bilateral agencies working in the regions | List of joint missions/ undertakings of CAP regional staff with implementing and bilateral agencies | Number of joint missions/undertakings | Suspended during the COVID-19 pandemic due to UN and national travel restrictions |

Policy issues

# UNEP seeks guidance from the Executive Committee on the timing for submission of project preparation activities for stage III of the HPMPs. UNEP as co-operating agency for Albania, Bangladesh, Egypt and Serbia, and as lead agency for Timor-Leste, included such activities in its business plan for 2023; however, they were removed by the Secretariat based on decision 84/46(e), which allows the submission of activities related to stage III of HPMPs for countries with an approved stage II with reduction targets below the 2025 compliance targets. This issue is being addressed in the Consolidated business plan of the Multilateral Fund for 2022–2024 submitted to the 88th meeting.

RECOMMENDATION

# The Executive Committee may wish:

## To note the UNEP business plan for 2022–2024, contained in document UNEP/OzL.Pro/ExCom/88/25; and

## To approve the performance indicators for UNEP as set out in Tables 4 and 5 of document UNEP/OzL.Pro/ExCom/88/25.

Online meetings and an intersessional approval process will be held in November and December 2021 due to coronavirus disease (COVID-19).

Given the constraints imposed by the COVID-19 pandemic, the Secretariat’s comments on the initial submission of the UNEP business plan for 2022–2024 were addressed through bilateral discussions and numerous exchanges of electronic messages. All issues were satisfactorily addressed.

Inclusion of stage III of HPMPs in the business plan is allowed only for those countries with an approved stage II of HPMPs with reduction targets below the 2025 compliance targets, in line with decision 84/46(e).

UNEP/OzL.Pro/ExCom/86/100, paragraph 182

Funding for the preparation of national implementation plans to meet initial reduction obligations for the phase-down of HFCs could be provided, at the earliest, five years prior to those obligations, after a country had ratified the Kigali Amendment and on the basis of guidelines to be approved in the future (decision 79/46(b)(iii)). In addition, HFC phase-down preparation activities could be included in the business plan for countries that had not ratified the Kigali Amendment but had submitted a letter indicating their Government’s intent to make best efforts to ratify the Kigali Amendment (decision 84/46(f)). The guidelines for the preparation of KIPs were approved at the 87th meeting (decision 87/50).

UNEP/OzL.Pro/ExCom/88/34

In the absence of a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021-2023 triennium, and in light of decision XXXII/1, the indicative budget for resource allocation of the business plan for 2022–2024 was assumed at the same level of the replenishment of the 2018–2020 triennium. This issue is discussed in the consolidated 2022-2024 business plan of the Multilateral Fund (UNEP/OzL.Pro/ExCom/88/22).

UNEP/OzL.Pro/ExCom/88/22

UNEP/OzL.Pro/ExCom/88/22