| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/82/4 17 November 2018 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-second Meeting

Montreal, 3-7 December 2018

# report on balances and availability of resources

# Introduction

# This document presents a summary of financial adjustments indicated by the bilateral (BAs) and implementing agencies (IAs) as agreed by the Secretariat. It includes statistical data from all projects with balances that have been held for over 12 months following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to relevant Executive Committee’s decisions (referred to as “by-decision” projects in this document). It indicates the level of resources available to the Executive Committee in cash as recorded in the Status of contributions and disbursements document, as required by decision 41/92(b), and presents a recommendation.

# This document also contains the following three annexes:

Annex I	Amounts held by IAs and BAs for completed projects

Annex II 	Amounts held by IAs and BAs for by-decision projects

Annex III 	Amounts held by IAs for ODS alternatives survey projects

Annex IV	Fund returns by IAs and BAs from completed, by-decision and ODS alternatives survey projects

Funds to be returned to the 82nd meeting

# The total funds to be returned amount to US $3,232,996 (i.e. US $121,266 by BAs and US $3,102,557 by IAs from completed, by-decision and ODS alternatives survey projects, and US $9,173 interest by BA). Annexes I, II and III provide explanations on the delays in disbursing committed amounts or returning not-committed amounts.

Funds to be returned by IAs

- The total funds to be returned by IAs amount to US $3,102,557 as shown in Table 1 (the list of projects with funds returned is presented in Annex IV).

Table 1. Funds to be returned by IAs to the 82nd meeting (US $)

| Agency | Project | Agency Support | Total |
| --- | --- | --- | --- |
| UNDP | 109,231 | 8,619 | 117,850 |
| UNEP* | 1,248,220 | 108,993 | 1,357,213 |
| UNIDO | 1,241,267 | 90,757 | 1,332,024 |
| World Bank** | 220,000 | 75,470 | 295,470 |
| Total | 2,818,718 | 283,839 | 3,102,557 |

* Including return of balances from 2016 and 2017 Compliance Assistance Programme of US $47,101 and US $929,330, respectively, including agency support costs.

** Including 2017 return of balance from core unit budget of US $60,070.

# Table 2 presents information on balances of completed, by-decisions and ODS alternative surveys projects that are still being withheld by the IAs.

Table 2. Balances of completed, by-decision and ODS alternative surveys projects withheld by IAs (including agency support costs)

| Year completed | UNDP |  | UNEP |  | UNIDO |  | WORLD BANK |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Number | (US$) | Number | (US$) | Number | (US$) | Number | (US$) | Number | (US$ |
| Projects completed over two years ago |  |  |  |  |  |  |  |  |  |  |
| 2014 | 0 | 0 | 1 | 158,200* | 0 | 0 | 0 | 0 | 1 | 158,200 |
| 1 Jan to 31 Oct 2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sub-total | 0 | 0 | 1 | 158,200 | 0 | 0 | 0 | 0 | 1 | 158,200 |
| Projects completed in less than two years ago |  |  |  |  |  |  |  |  |  |  |
| 1 Nov to 31 Dec 2016 | 2 | 94 | 0 | 0 | 2 | 223,043 | 0 | 0 | 4 | 223,137 |
| 2017 | 7 | 17,923 | 1 | 18,556 | 4 | 114,305 | 0 | 0 | 12 | 150,784 |
| On Going | 0 | 0 | 0 | 0 | 0 |  | 1 | 463,331 | 1 | 463,331 |
| Sub-total | 9 | 18,017 | 1 | 18,556 | 6 | 337,348 | 1 | 463,331 | 17 | 837,252 |
| Total | 9 | 18,017 | 2 | 176,756 | 6 | 337,348 | 1 | 463,331 | 18 | 995,452 |
| By-decisions projects (on-going) |  |  |  |  |  |  |  |  |  |  |
|  | 3 | 1,653,070 | 0 | 0 | 3 | 816,256 | 0 | 0 | 6 | 2,469,326 |
| ODS alternatives survey |  |  |  |  |  |  |  |  |  |  |
| 2017 | 0 | 0 | 7 | 301,042 | 2 | 12,773 | 0 | 0 | 9 | 313,815 |
| Grand total | 12 | 1,671,087 | 9 | 477,798 | 11 | 1,166,377 | 1 | 463,331 | 33 | 3,778,593 |

* National ODS phase-out plan for Yemen (second tranche) (YEM/PHA/60/TAS/35).

Funds to be returned to the 82nd meeting by BAs

- The total funds to be returned by BAs amount to US $130,439 as shown in Table 3 (the list of projects with funds returned is presented in Annex IV).

Table 3. Funds to be returned by BAs to the 82nd meeting (US $)

| Agency | Project | Agency support costs | Interest | Grand Total |
| --- | --- | --- | --- | --- |
| France | 111,780 | 8,943 | 3,774 | 124,497 |
| Spain | 481 | 62 | 5,399 | 5,942 |
| Total | 112,261 | 9,005 | 9,173 | 130,439 |

- The Government of France’s return to the 82nd meeting will be either offset against future bilateral project approvals or in cash, in consultation with the Treasurer and the Secretariat.

- The Government of Spain has already returned in cash the amount of US $5,942 to the Treasurer.

- Table 4 presents the balances from completed projects that are being held by BAs.

Table 4. Balances held by BAs (US $)

| Year completed | Japan | Spain | Total |
| --- | --- | --- | --- |
| 2017 | 56 | 2,736 | 2,792 |
| Agency support costs | 7 | 356 | 363 |
| Total | 63 | 3,092 | 3,155 |

## With regard to balances held by BAs:

  - The Government of Japan has a committed balance of US $63, including agency support costs for one completed project; and

  - The Government of Spain has a committed balance of US $3,092, including agency support costs for one completed project.

Availability of resources

# The Status of contributions and disbursements document indicates an available balance amounting to US $108,841,602 as at 12 October 2018. The total net balance returned by BAs and IAs, including agency support costs and interest is US $3,232,996. The total level of resources available for approvals by the Executive Committee at the 82nd meeting, after taking into account the Fund’s balance, and the return from the Secretariat 2017 unspent budget of US $1,665,431 is US $113,740,029.

Secretariat’s comments

- During the Inter-agency Coordination Meeting, the Secretariat reminded BAs and IAs that balances associated with completed projects and by-decisions projects that are due should be returned to the Multilateral Fund no later than the 82nd meeting. BAs and IAs committed to continue with their efforts to return funds as soon as possible, and to provide an update to the 82nd meeting with a view to returning additional balances. IAs were also reminded that completed IS projects balances should be returned to the Fund.

- Considering that the total level of funding for projects and activities as submitted to the 82nd meeting amounts to US $98,717,726 including agency support costs, there are sufficient resources available for approvals at the 82nd meeting.

Recommendations

- The Executive Committee may wish:

  - To note:

    - The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/82/4;

    - That the net level of funds being returned to the 82nd meeting by the implementing agencies was US $3,102,557, consisting of US $109,231, plus agency support costs of US $8,619 from UNDP; US $1,248,220, plus agency support costs of US $108,993 from UNEP; US $1,241,267, plus agency support costs of US $90,757 from UNIDO, and US $220,000 plus agency support costs of US $75,470 from the World Bank;

### That UNEP held balances of US $158,200, including agency support costs, in not-committed balances, for one project completed over two years previously;

### That UNEP held balances of US $301,042, including agency support costs, for seven ODS alternatives survey projects;

### That UNIDO held balances of US $12,773, including agency support costs, for two ODS alternatives survey projects;

### That the net level of funds and agency support costs due to be returned by the bilateral agencies to the 82nd meeting was US $121,266, consisting of: US $120,723 from the Government of France and US $543 from the Government of Spain;

### The Governments of France’s and Spain’s return of accrued interest of US $3,774 and US $5,399, respectively, which would be considered additional income to the Fund;

### That the Government of Japan held US $63, including agency support costs, in committed balances, for one completed project;

### That the Government of Spain held US $3,092, including agency support costs, in committed balances, for one completed project.

  - To request:

    - Bilateral and implementing agencies to disburse or cancel commitments not needed for completed projects and projects completed by decision of the Executive Committee, and to return balances to the 83rd meeting;

    - UNEP and UNIDO to return the outstanding balances for ODS alternatives survey projects before the 83rd meeting, in line with decision 80/75(c)(i); and

    - The Treasurer to offset US $124,497 against the Government of France’s approvals at the 82nd meeting or to follow up with the Government of France on the return, in cash, of US $124,497 referred to in sub-paragraphs (vi) and (vii) above.

Annex I

COMMITTED AND NOT-COMMITTEED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2017 (US$) | Funds disbursed as of 82nd meeting (US$) | Balances committed as per 82nd meeting (US$) | Balances not-committed as per 82nd meeting (US$) | Support cost on balances committed & not committed as per 82nd meeting (US$) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BGD/SEV/71/INS/41 | Renewal of the institutional strengthening project (phase VII: 1/2014-12/2015) | Mar-17 | 130,000 | 128,624 | 1,376 |  | 96 |  |  |  |
| BRA/REF/47/DEM/275 | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers. | Jun-17 | 1,000,000 | 999,576 | 424 |  | 32 |  |  |  |
| CPR/REF/74/PRP/562 | Preparation of a demonstration project of ammonia semi-hermetic frequency convertible screw refrigeration system in the industrial and commercial refrigeration industry | May-17 | 24,000 | 21,970 | 2,030 |  | 142 |  |  |  |
| MOL/PHA/72/PRP/29 | Preparation of a HCFC phase-out management plan (stage II) | Mar-17 | 20,000 | 19,834 | 166 |  | 12 |  |  |  |
| NIR/SEV/73/INS/141 | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Jan-17 | 260,000 | 254,432 | 5,568 |  | 390 |  |  |  |
| PAN/PHA/72/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Dec-16 | 60,000 | 59,935 | 65 |  | 5 |  |  |  |
| TRI/SEV/73/INS/31 | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Jan-17 | 60,000 | 56,905 | 3,095 |  | 217 |  |  |  |
| URU/FOA/72/PRP/62 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Jan-17 | 68,000 | 63,911 | 4,089 |  | 286 |  |  |  |
| URU/PHA/75/INV/66 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-16 | 45,004 | 44,982 | 22 |  | 2 |  |  |  |
| TOTAL UNDP |  |  |  |  | 16,835 |  | 1,182 |  |  |  |

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2017 (US$) | Funds disbursed as of 82nd meeting (US$) | Balances committed as per 82nd meeting (US$) | Balances not-committed as per 82nd meeting (US$) | Support cost on balances committed and not- committed as per 82nd meeting (US$) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| NAU/SEV/67/INS/08 | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Aug-17 | 60,000 | 41,444 | 18,556 |  | 0 | Awaiting final expenditure report from partner. |  |  |
| YEM/PHA/60/TAS/35 | National ODS phase-out plan (second tranche) | Dec-14 | 140,000 | 0 |  | 140,000 | 18,200 |  | Amount not committed; however, according to ExCom decision, projects to be frozen until security situation is resolved. UNEP’s understanding is funds to be kept with it. ExCom to advise. |  |
| TOTAL UNEP |  |  |  |  | 18,556 | 140,000 | 18,200 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| ARG/REF/61/INV/164 | Phase-out of HCFC-22 in the room and unitary air-conditioning equipment manufacturing sector | 17-Dec | 8,112,898 | 8,075,543 | 37,355 |  | 2,802 | 2 | 83rd |  |
| EUR/DES/69/DEM/14 | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region | 17-Jul | 274,480 | 222,997 | 51,483 |  | 3,604 | 2 | 83rd |  |
| IDS/PHA/64/INV/194 | HCFC phase-out management plan (umbrella project to phase-out HCFC-141b used at Isotech Jaya Makmur, Airtekindo, Sinar Lentera Kencana and Mayer Jaya) (stage I, first tranche) | 17-Jan | 777,395 | 777,285 | 110 |  | 9 | 2 | 83rd |  |
| IRA/PHA/68/INV/209 | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | 16-Dec | 830,000 | 660,537 | 169,463 |  | 12,710 | 4 | 84th |  |
| IRA/PHA/72/INV/215 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | 16-Dec | 101,450 | 63,432 | 38,018 |  | 2,852 | 4 | 84th |  |
| TUN/FUM/73/TAS/63 | Technical assistance for the final phase-out of methyl bromide in the palm dates sector | 17-Nov | 267,657 | 249,954 | 17,703 |  | 1,239 | 2 | 83rd |  |
| TOTAL UNIDO |  |  |  |  | 314,132 |  | 23,216 |  |  |  |
| WORLD BANK |  |  |  |  |  |  |  |  |  |  |
| SAU/REF/76/DEM/29 | Demonstration project at air-conditioning manufacturers to develop window and packaged air-conditioners using low-global warming | ONG | 794,600 | 143,100 | 433,00 |  | 30,331 |  |  |  |
| TOTAL WORLD BANK |  |  |  |  | 433,000 |  | 30,331 |  |  |  |
| FRANCE |  |  |  |  |  |  |  |  |  |  |
| AFR/DES/68/TAS/41 |  | Nov-17 | 80,000 | 66,872 |  | 13,128 | 1,051 |  |  |  |
| AFR/REF/48/DEM/36 |  | Dec-17 | 360,000 | 261,348 |  | 98,652 | 7,892 |  |  |  |
| TOTAL FRANCE |  |  |  |  |  | 111,780 | 8,943 |  |  |  |
| JAPAN |  |  |  |  |  |  |  |  |  |  |
| AFR/REF/48/DEM/35 | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Dec-17 | 700,000 | 699,944 | 56 |  | 7 | 3 | 83rd |  |
| TOTAL JAPAN |  |  |  |  | 56 |  | 7 |  |  |  |
| SPAIN |  |  |  |  |  |  |  |  |  |  |
| LIB/FUM/56/INV/30 | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others (second tranche) | Dec-17 | 500,000 | 497,264 | 2,736 |  | 356 | 4 | 83rd |  |
| TOTAL SPAIN |  |  |  |  | 2,736 |  | 356 |  |  |  |

*2: Financial completion initiated; 3: Financial completion being initiated; 4 Financial completion to be initiated after settlement of all pending issues; MYA = Multiyear

Annex II

COMMITED AND NOT-COMMITED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2017 (US$) | Funds disbursed as of 82nd meeting (US$) | Balances committed as per 82nd meeting (US$) | Balances not- committed as per 82nd meeting (US$) | Support cost on balances committed and not-committed as per 82nd meeting (US$) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 273,795 | 1,216,805 |  | 85,176 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| CHI/PHA/76/INV/192 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | First meeting of 2019 | 199,299 | 184,336 | 14,963 |  | 1,122 |  |  | 76/45(a)(iii) |
| COL/DES/66/DEM/82 | Demonstration project on end of life ODS management and destruction | 82nd meeting | 1,195,000 | 883,368 | 311,632 |  | 23,372 |  |  | 79/18(c)(ii) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 1,543,399 |  | 109,671 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Dec-18 | 4,353,530 | 3,853,594 | 499,936 |  | 37,495 | 4 | 2019 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | Dec-18 | 2,161,581 | 1,918,997 | 242,584 |  | 18,190 | 4 | 2019 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| LEB/DES/73/DEM/83 | Pilot demonstration project on ODS waste management and disposal | 82nd meeting | 123,475 | 106,915 | 16,560 |  | 1,491 | 4 | 2019 | 81/24(d) and 81/24(e)(ii) |
| TOTAL UNIDO |  |  |  |  | 759,080 |  | 57,176 |  |  |  |

Annex III

COMMITED AND NOT-COMMITED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ODS ALTERNATIVES SURVEY PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2017 (US$) | Funds disbursed as of 82nd meeting (US$) | Balances committed as per 82nd meeting (US$) | Balances not- committed as per 82nd meeting (US$) | Support cost on balances committed and not-committed as per 82nd meeting (US$) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ALG/SEV/74/TAS/82 | Survey of ODS alternatives at the national level | Sep-17 | 110,000 | 50,000 |  | 60,000 | 7,800 | Awaiting final expenditure report from partner on the first payment advanced. | Possibly 83rd | 80/75(c)(ii) |
| GRN/SEV/75/TAS/20 | Survey of ODS alternatives at the national level | 82nd | 40,000 | 20,000 | 20,000 |  | 2,600 |  |  | 80/75(c)(i) |
| GUY/SEV/74/TAS/26 | Survey of ODS alternatives at the national level | 82nd | 40,000 | 15,000 | 20,000 |  | 2,600 |  |  | 80/75(c)(i) |
| IRQ/SEV/75/TAS/24 | Survey of ODS alternatives at the national level | 82nd | 110,000 | 50,520 | 52,000 |  | 6,760 |  |  | 80/75(c)(i) |
| JAM/SEV/74/TAS/34 | Survey of ODS alternatives at the national level | 82nd | 70,000 | 5,909 | 60,066 |  | 7,809 |  |  | 80/75(c)(i) |
| TLS/SEV/74/TAS/13 | Survey of ODS alternatives at the national level | 82nd | 40,000 | 21,214 | 2,838 |  | 369 |  |  | 80/75(c)(i) |
| TRI/SEV/74/TAS/32 | Survey of ODS alternatives at the national level | 82nd | 110,000 | 44,290 | 58,096 |  | 7,552 |  |  | 80/75(c)(i) |
| TOTAL UNEP |  |  |  |  | 213,000 | 60,000 | 28,042 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| LIB/SEV/75/TAS/38 | Survey of ODS alternatives at the national level | 82nd | 110,000 | 102,809 | 7,191 |  | 647 | 2 | 83rd | 80/75(c)(i) |
| OMA/SEV/74/TAS/31 | Survey of ODS alternatives at the national level | 82nd | 110,000 | 105,472 | 4,528 |  | 407 | 2 | 83rd | 80/75(c)(i) |
| TOTAL UNIDO |  |  |  |  | 11,719 |  | 1,054 |  |  |  |

Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND ODS ALTERNATIVES SURVEY PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project Title | Project costs returned (US$) | Agency support costs (US$) | Interest | Total |
| --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |
| ARM/PHA/66/INV/09 | HCFC phase-out management plan (stage I, second tranche) | 43,823 | 3,287 |  | 47,110 |
| ARM/PHA/73/PRP/12 | Preparation of a HCFC phase-out management plan (stage II) | 10 | 1 |  | 11 |
| BRA/FOA/72/PRP/301 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 25,298 | 1,771 |  | 27,069 |
| CPR/PHA/73/PRP/545 | Preparation of a HCFC phase-out management plan (stage II) (overarching strategy) | 259 | 18 |  | 277 |
| CPR/SEV/73/INS/549 | Extension of the institutional strengthening project (phase XI: 1/2015-12/2016) | 1,113 | 78 |  | 1,191 |
| CPR/SOL/73/PRP/544 | Preparation for HCFC phase-out investment activities (stage II) (solvents sector) | 2 |  |  | 2 |
| IRA/SEV/72/INS/213 | Extension of the institutional strengthening project (phase X: 1/2015-12/2016) | 67 | 5 |  | 72 |
| MOL/PHA/74/INV/31 | HCFC phase-out management plan (stage I, second tranche) | 151 | 14 |  | 165 |
| PAN/PHA/74/INV/39 | HCFC phase-out management plan (stage I, third tranche) | 1,304 | 98 |  | 1,402 |
| Total Completed Projects |  | 72,027 | 5,272 |  | 77,299 |
| BGD/SEV/75/TAS/46 | Survey of ODS alternatives at the national level | 1,520 | 137 |  | 1,657 |
| CUB/SEV/75/TAS/55 | Survey of ODS alternatives at the national level | 13 | 1 |  | 14 |
| DOM/SEV/75/TAS/59 | Survey of ODS alternatives at the national level | 1,038 | 93 |  | 1,131 |
| ELS/SEV/74/TAS/33 | Survey of ODS alternatives at the national level | 265 | 24 |  | 289 |
| IND/SEV/74/TAS/461 | Survey of ODS alternatives at the national level | 6,451 | 580 |  | 7,031 |
| IRA/SEV/74/TAS/223 | Survey of ODS alternatives at the national level | 23,002 | 2,070 |  | 25,072 |
| LEB/SEV/74/TAS/35 | Survey of ODS alternatives at the national level | 2,837 | 255 |  | 3,092 |
| MOL/SEV/75/TAS/33 | Survey of ODS alternatives at the national level | 638 | 57 |  | 695 |
| PAR/SEV/75/TAS/35 | Survey of ODS alternatives at the national level | 1,145 | 103 |  | 1,248 |
| PER/SEV/75/TAS/50 | Survey of ODS alternatives at the national level | 295 | 27 |  | 322 |
| Total ODS Projects |  | 37,204 | 3,347 |  | 40,551 |
| TOTAL UNDP |  | 109,231 | 8,619 |  | 117,850 |
| UNEP |  |  |  |  |  |
| ASP/REF/69/DEM/56 | Promoting low-global warming potential refrigerants for air-conditioning sectors in high-ambient temperature countries in West Asia | 3,642 | 473 |  | 4,115 |
| BEN/SEV/71/INS/29 | Renewal of institutional strengthening project (phase VIII: 1/2014-12/2015) | 27,000 | 0 |  | 27,000 |
| BHU/PHA/73/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | 752 | 98 |  | 850 |
| ECU/SEV/59/INS/43 | Extension of institutional strengthening project (phase V) | 16,805 | 0 |  | 16,805 |
| ERI/SEV/54/INS/06 | Institutional strengthening (phase I) | 17,992 | 0 |  | 17,992 |
| EUR/DES/69/DEM/13 | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region | 42,160 | 5,481 |  | 47,641 |
| GLO/REF/76/DEM/334 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | 50,000 | 6,500 |  | 56,500 |
| GLO/SEV/75/TAS/329 | Compliance Assistance Programme: 2016 budget | 43,612 | 3,489 |  | 47,101 |
| GLO/SEV/77/TAS/336 | Compliance Assistance Programme: 2017 budget | 860,491 | 68,839 |  | 929,330 |
| JAM/SEV/68/INS/31 | Extension of institutional strengthening project (phase VIII: 1/2013-12/2014) | 226 | 0 |  | 226 |
| KAM/PHA/61/TAS/23 | HCFC phase-out management plan (phase I, first tranche) | 779 | 101 |  | 880 |
| KAM/PHA/73/TAS/29 | Verification report on the implementation of the HCFC phase-out management plan | 397 | 52 |  | 449 |
| LAO/PHA/71/TAS/25 | Verification report on the implementation of the HCFC phase-out management plan | -1,504 | -196 |  | -1,700 |
| MDV/PHA/60/TAS/19 | HCFC phase-out management plan (first tranche) | 18,384 | 2,390 |  | 20,774 |
| MDV/PHA/73/TAS/26 | Verification report on the implementation of the HCFC phase-out management plan | 2,880 | 374 |  | 3,254 |
| NIC/PHA/73/TAS/30 | Verification report on the implementation of the HCFC phase-out management plan | 3,235 | 421 |  | 3,656 |
| TOG/SEV/73/INS/26 | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | 34 | 0 |  | 34 |
| Total Completed Projects |  | 1,086,885 | 88,022 |  | 1,174,907 |
| ANG/SEV/74/TAS/15 | Survey of ODS alternatives at the national level | 4,908 | 638 |  | 5,546 |
| BHU/SEV/74/TAS/24 | Survey of ODS alternatives at the national level | 272 | 35 |  | 307 |
| BRU/SEV/74/TAS/18 | Survey of ODS alternatives at the national level | 35,219 | 4,578 |  | 39,797 |
| CHD/SEV/74/TAS/27 | Survey of ODS alternatives at the national level | 20 | 3 |  | 23 |
| CKI/SEV/75/TAS/12 | Survey of ODS alternatives at the national level | 5,372 | 698 |  | 6,070 |
| FSM/SEV/74/TAS/11 | Survey of ODS alternatives at the national level | 7,063 | 918 |  | 7,981 |
| GUY/SEV/74/TAS/26 | Survey of ODS alternatives at the national level | 5,000 | 650 |  | 5,650 |
| IRQ/SEV/75/TAS/24 | Survey of ODS alternatives at the national level | 7,480 | 972 |  | 8,452 |
| IVC/SEV/74/TAS/40 | Survey of ODS alternatives at the national level | 30 | 4 |  | 34 |
| JAM/SEV/74/TAS/34 | Survey of ODS alternatives at the national level | 4,025 | 523 |  | 4,548 |
| KAM/SEV/74/TAS/31 | Survey of ODS alternatives at the national level | 1,178 | 153 |  | 1,331 |
| KUW/SEV/75/TAS/27 | Survey of ODS alternatives at the national level | 1,325 | 172 |  | 1,497 |
| LAO/SEV/74/TAS/29 | Survey of ODS alternatives at the national level | 2,533 | 329 |  | 2,862 |
| MAS/SEV/75/TAS/12 | Survey of ODS alternatives at the national level | 12,778 | 1,661 |  | 14,439 |
| NAU/SEV/75/TAS/11 | Survey of ODS alternatives at the national level | 17,725 | 2,304 |  | 20,029 |
| NIU/SEV/75/TAS/12 | Survey of ODS alternatives at the national level | 10,852 | 1,411 |  | 12,263 |
| SAM/SEV/75/TAS/20 | Survey of ODS alternatives at the national level | 1,701 | 221 |  | 1,922 |
| SEN/SEV/75/TAS/35 | Survey of ODS alternatives at the national level | 450 | 59 |  | 509 |
| STP/SEV/74/TAS/24 | Survey of ODS alternatives at the national level | 10,000 | 1,300 |  | 11,300 |
| TKM/SEV/74/TAS/11 | Survey of ODS alternatives at the national level | 1,781 | 231 |  | 2,012 |
| TLS/SEV/74/TAS/13 | Survey of ODS alternatives at the national level | 15,948 | 2,073 |  | 18,021 |
| TON/SEV/75/TAS/12 | Survey of ODS alternatives at the national level | 2,221 | 289 |  | 2,510 |
| TRI/SEV/74/TAS/32 | Survey of ODS alternatives at the national level | 7,613 | 990 |  | 8,603 |
| VAN/SEV/75/TAS/13 | Survey of ODS alternatives at the national level | 5,841 | 759 |  | 6,600 |
| Total ODS Projects |  | 161,335 | 20,971 |  | 182,306 |
| TOTAL UNEP |  | 1,248,220 | 108,993 |  | 1,357,213 |
| UNIDO |  |  |  |  |  |
| ALG/FOA/62/INV/75 | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Cristor | 436 | 39 |  | 475 |
| ARG/PHA/53/INV/152 | National CFC phase-out plan: 2008 work programme | 9,334 | 700 |  | 10,034 |
| ASP/REF/69/DEM/57 | Promoting low-global warming potential refrigerants for air-conditioning sectors in high-ambient temperature countries in West Asia | 6,000 | 420 |  | 6420 |
| CPR/FOA/73/PRP/546 | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | 548 | 38 |  | 586 |
| ECU/PHA/77/TAS/63 | Verification report for stage I of HCFC phase-out management plan | 322 | 29 |  | 351 |
| EGY/REF/73/PRP/119 | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | 4,439 | 311 |  | 4,750 |
| ERI/PHA/67/INV/10 | HCFC phase-out management plan (stage I, first tranche) | 179 | 16 |  | 195 |
| ETH/PHA/68/INV/22 | HCFC phase-out management plan (stage I, first tranche) | 229 | 21 |  | 250 |
| IRA/FOA/74/PRP/222 | Preparation for HCFC phase-out investment activities (stage II) (rigid polyurethane foam sector) | 2,646 | 185 |  | 2,831 |
| JOR/FOA/75/PRP/94 | Preparation for HCFC phase-out investment activities (stage II) (rigid polyurethane foam sector) | 339 | 24 |  | 363 |
| JOR/PHA/75/INV/97 | HCFC phase-out management plan (stage I, second tranche) (policy and monitoring) | 117 | 11 |  | 128 |
| NER/PHA/71/TAS/29 | Verification report for stage I of HCFC phase-out management plan | 9,871 | 888 |  | 10,759 |
| PAK/FOA/72/PRP/87 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 0 | 13 |  | 13 |
| PAK/PHA/72/PRP/85 | Preparation of a HCFC phase-out management plan (stage II) | 0 | 3 |  | 3 |
| PAK/REF/72/PRP/86 | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | 0 | 9 |  | 9 |
| SOM/PHA/67/INV/08 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 3,335 | 233 |  | 3,568 |
| SOM/PHA/67/TAS/09 | HCFC phase-out management plan (stage I, first tranche) (additional security) | 3,293 | 230 |  | 3,523 |
| TUR/DES/66/DEM/99 | Demonstration project for disposal of unwanted ODS | 477,896 | 35,842 |  | 513,738 |
| TUR/PHA/68/INV/102 | HCFC phase-out management plan (stage I, first tranche) (technical assistance for small and medium enterprises in the foam sector) | 0 | 4 |  | 4 |
| Total Completed Projects |  | 518,984 | 39,016 |  | 558,000 |
| NIR/DES/67/DEM/133 | Demonstration project for disposal of unwanted ODS | 663,279 | 46,430 |  | 709,709 |
| Total “by decision projects” |  | 663,279 | 46,430 |  | 709,709 |
| ARG/SEV/74/TAS/173 | Survey of ODS alternatives at the national level | 2,799 | 252 |  | 3,051 |
| BAH/SEV/75/TAS/31 | Survey of ODS alternatives at the national level | 663 | 60 |  | 723 |
| CMR/SEV/75/TAS/41 | Survey of ODS alternatives at the national level | 118 | 11 |  | 129 |
| MEX/SEV/74/TAS/176 | Survey of ODS alternatives at the national level | 299 | 27 |  | 326 |
| NER/SEV/74/TAS/31 | Survey of ODS alternatives at the national level | 3,288 | 296 |  | 3,584 |
| TUR/SEV/74/TAS/104 | Survey of ODS alternatives at the national level | 38,723 | 3,485 |  | 42,208 |
| URU/SEV/74/TAS/64 | Survey of ODS alternatives at the national level | 7,489 | 674 |  | 8,163 |
| VEN/SEV/74/TAS/129 | Survey of ODS alternatives at the national level | 5,625 | 506 |  | 6,131 |
| Total ODS Projects |  | 59,004 | 5,311 |  | 64,315 |
| TOTAL UNIDO |  | 1,241,267 | 90,757 |  | 1,332,024 |
| WORLD BANK |  |  |  |  |  |
| GLO/SEV/77/TAS/337 | Core unit budget (2017) |  | 60,070 |  | 60,070 |
| SAU/REF/76/DEM/29 | Demonstration project at air-conditioning manufacturers to develop window and packaged air-conditioners using low-global warming | 220,000 | 15,400 |  | 235,400 |
| TOTAL WORLD BANK |  | 220,000 | 75,470 |  | 295,470 |
| FRANCE |  |  |  |  |  |
| AFR/DES/68/TAS/41 | Strategy for disposal and destruction of ODS for five low-volume-consuming Central African countries (Burundi, Cameroon, Central African Republic, Congo and Guinea) | 13,128 | 1,051 | 197 | 14,376 |
| AFR/REF/48/DEM/36 | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | 98,652 | 7,892 | 0 | 106,544 |
| ALG/DES/72/DEM/78 | Pilot demonstration project on ODS waste management and disposal | 0 | 0 | 716 | 716 |
| MEX/DES/63/DEM/155 | Demonstration project for disposal of unwanted ODS | 0 | 0 | 2,861 | 2,861 |
| TOTAL FRANCE |  | 111,780 | 8,943 | 3,774 | 124,497 |
| SPAIN |  |  |  |  |  |
| LAC/FUM/54/TAS/40 | Technical assistance to introduce chemical alternatives in countries which have rescheduled methyl bromide phase out plan (Argentina and Uruguay) | 481 | 62 | 4,470 | 5,013 |
| MEX/FUM/66/INV/161 | National methyl bromide phase-out plan (third tranche) | 0 | 0 | 929 | 929 |
| TOTAL SPAIN |  | 481 | 62 | 5,399 | 5,942 |

The data presented are based on the reporting format that has been developed pursuant to decision 31/2.

UNEP/OzL.Pro/ExCom/82/3.

UNEP/OzL.Pro/ExCom/82/3.

Montreal, 4 to 6 September 2018.

As at 18 November 2018, and noting that HFC-related projects to be funded under pledged or additional contributions will be considered at the meeting, where relevant.