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多边基金2023-2025年综合业务计划最新执行情况 


导言

本文件包含下列部分：
第一部分：	2023-2025年业务计划的最新执行情况

第二部分：	2021-2023三年期的资源分配情况

第三部分：	建议

第一部分：2023-2025年业务计划的最新执行情况

在第九十一次会议上，执行委员会核准了多边基金2023-2025年综合业务计划。根据第91/31号决定，秘书处调整了2023-2025年综合业务计划，如表1所示。


表1.多边基金调整后的2023-2025年综合业务计划资源分配情况（美元）*
	说明
	2023年
	2024年
	2025年
	共计

	氟氯烃活动
	 
	 
	 
	 

	核准的氟氯烃淘汰管理计划
	60,280,861
	56,111,450
	43,084,350
	159,476,661

	氟氯烃淘汰管理计划项目编制 – 第二阶段
	200,480
	77,600
	0
	278,080

	氟氯烃淘汰管理计划第二阶段
	2,937,082
	5,199,804
	3,462,199
	11,599,085

	氟氯烃淘汰管理计划第二阶段 – 投资
	0
	248,532
	0
	248,532

	氟氯烃淘汰管理计划项目编制 – 第三阶段
	290,100
	92,750
	0
	382,850

	氟氯烃淘汰管理计划第三阶段
	14,794,713
	10,344,520
	20,526,731
	45,665,964

	氟氯烃淘汰管理计划项目编制 – 第四阶段
	90,000
	0
	0
	90,000

	氟氯烃淘汰管理计划第四阶段
	0
	0
	2,093,000
	2,093,000

	氟氯烃淘汰管理计划 – 能效
	3,258,494
	2,672,980
	3,379,420
	9,310,894

	氟氯烃淘汰管理计划核查**
	588,600
	588,600
	588,600
	1,765,800

	氟氯烃活动小计
	82,440,330
	75,336,236
	73,134,299
	230,910,865

	氢氟碳化物活动
	 
	 
	 
	 

	氢氟碳化物逐步减少的扶持活动
	53,500
	160,500
	0
	214,000

	基加利氢氟碳化物实施计划 – 项目编制
	3,945,431
	2,567,011
	144,560
	6,657,002

	基加利氢氟碳化物实施计划
	27,299,967
	21,437,607
	245,413
	48,982,987

	基加利氢氟碳化物实施计划项目编制 – 投资
	129,000
	0
	0
	129,000

	基加利氢氟碳化物实施计划 – 投资
	321,000
	8,963,616
	0
	9,284,616

	HFC-23排放控制项目编制
	43,000
	0
	0
	43,000

	HFC-23排放控制
	0
	8,000,000
	0
	8,000,000

	氢氟碳化物 – 技术援助
	0
	678,000
	0
	678,000

	氢氟碳化物活动小计
	31,791,898
	41,806,734
	389,973
	73,988,605

	能效试点项目
	 
	 
	 
	 

	能效试点项目
	20,000,000
	0
	0
	20,000,000

	能效试点项目小计
	20,000,000
	0
	0
	20,000,000

	标准活动
	 
	 
	 
	 

	体制强化
	27,860,444
	16,639,896
	0
	44,500,341

	履约援助方案
	11,445,002
	11,788,350
	12,142,003
	35,375,355

	核心单位
	5,969,740
	6,011,529
	6,053,610
	18,034,878

	秘书处、执行委员会以及监测和评价费用减去加拿大对应费用
	7,237,326
	7,202,023
	6,816,624
	21,255,973

	财务主任
	500,000
	500,000
	500,000
	1,500,000

	标准活动小计
	53,012,512
	42,141,798
	25,512,237
	120,666,547

	总计
	187,244,740
	159,284,767
	99,036,509
	445,566,017

	澳大利亚
	0
	0
	152,497
	152,497

	奥地利
	783,667
	0
	0
	783,667

	法国
	671,075
	0
	0
	671,075

	德国
	1,349,869
	3,705,721
	1,028,250
	6,083,840

	日本
	67,800
	0
	0
	67,800

	开发计划署
	62,425,117
	54,216,500
	29,064,016
	145,705,634

	环境规划署
	40,325,066
	36,674,895
	22,071,085
	99,071,046

	工发组织
	38,767,526
	29,078,890
	29,553,746
	97,400,162

	世界银行
	14,528,694
	27,318,138
	9,261,691
	51,108,523

	氟氯烃淘汰管理计划核查**
	588,600
	588,600
	588,600
	1,765,800

	能效试点项目
	20,000,000
	0
	0
	20,000,000

	秘书处、执行委员会以及监测和评价费用减去加拿大对应费用
	7,237,326
	7,202,023
	6,816,624
	21,255,973

	财务主任
	500,000
	500,000
	500,000
	1,500,000


* 包括适用的机构支助费用。
**低消费量国家编制氟氯烃淘汰管理计划核查报告的供资由执行委员会每年核准。

I.1	2023年业务计划执行情况

2023 年业务计划的总金额为 187,244,740 美元。其中 29,253,988 美元已在第九十二次会议上获得核准。此外，第九十三次会议将审议总额为 108,304,705 美元的活动；如表 2 所示，如果提交的所有项目提案申请的供资都获得核准，2023 年业务计划将有 49,686,047 美元的结余。
表2. 2023年综合业务计划，第九十二次会议核准的项目，向第九十三次会议建议的项目，以及结余（美元）*
	预算项目
	业务计划的资金总额
	第九十二次会议核准的项目
	向第九十三次会议建议的活动
	结余
（高于）/低于

	双边机构
	2,872,411
	687,988
	1,657,265
	527,158

	开发计划署
	62,425,117
	10,211,836
	 28,591,500 
	23,621,781

	环境规划署
	40,325,066
	6,644,731
	 22,767,524 
	10,912,811

	工发组织
	38,767,526
	8,419,645
	 24,134,585 
	6,213,296

	世界银行
	14,528,694
	2,681,989
	15,997,224
	(4,150,519)

	氟氯烃淘汰管理计划核查
	588,600
	573,900
	0
	14,700

	能效试点项目
	20,000,000
	33,900
	7,419,281
	12,546,819

	小计（机构）
	179,507,414
	29,253,988
	100,567,379
	49,686,047

	秘书处/执行委员会/监测和评价（不包括加拿大对应费用）
	7,237,326
	0
	7,237,326
	0

	财务主任
	500,000
	0
	500,000
	0

	小计（标准费用）
	7,737,326
	0
	7,737,326
	0

	共计
	187,244,740
	29,253,988
	108,304,705
	49,686,047


* 包括核心单位费用。

向第九十三次会议建议的项目提案金额为100,567,379美元，比2023年业务计划中的金额高16,578,316美元，包括与未列入2023年业务计划的项目提案有关的12,521,905美元[footnoteRef:2]。 [2: 玻利维亚多民族国（环境规划署和工发组织）、厄瓜多尔（工发组织）、危地马拉 （环境规划署和工发组织）、莫桑比克（开发计划署）和北马其顿（工发组织）氟氯烃 淘汰管理计划第二阶段；越南氟氯烃淘汰管理计划第三阶段（世界银行）；秘鲁氟氯烃 淘汰管理计划第三阶段的一个项目编制（开发计划署）；泰国氟氯烃淘汰管理计划投资项目的一个项目编制（世界银行）； 印度示范项目的一个项目编制（开发计划署）；哥伦比亚（2 个）（开发计划署）、黎巴嫩（开发计划署）、蒙古（工发组织）和斯里兰卡（开发计划署）的 5 个基加利氢氟碳化物实施计划投资项目编制；巴西（德国、开发计划署和工发组织）、肯尼亚（德国）、 马里（开发计划署和环境规划署）以及圣文森特和格林纳丁斯（环境规划署和工发组织）的 8 个基加利氢氟碳化物实施计划第一阶段项目编制； 印度的 3 个氢氟碳化物投资项目（开发计划署）；根据第 89/6 号决定，为 阿尔巴尼亚（工发组织）、贝宁（工发组织）、玻利维亚多民族国（环境规划署和工发组织）、厄瓜多尔（工发组织）、格林纳达（工发组织）、危地马拉（环境规划署和工发组织）、莱索托（德国）、利比里亚（德国）、纳米比亚（德国）和塞舌尔（德国）执行的 12 个能效项目； 玻利维亚多民族国（环境规划署）、刚果（环境规划署和工发组织）、多米尼加共和国（环境规划署和工发组织）、吉尔吉斯斯坦（开发计划署）、尼加拉瓜（环境规划署）、尼日尔（环境规划署和工发组织）和秘鲁（开发计划署）基加利氢氟碳化物实施计划第一阶段；玻利维亚多民族国（环境规划署）体制强化项目第一阶段；以及附件三根据第 91/66 号决定进行的废物管制物质库存国家清单的 37 个项目编制。 ] 

向第九十三次会议建议的氢氟碳化物相关活动金额为 23,789,140 美元，其中 3,182,574 美元与未列入 2023 年业务计划的项目提案有关。本文件附件一列出了双边和执行机构向第九十三次会议提交的氢氟碳化物相关项目。
.根据第 91/65 号决定，在能效试点项目供资窗口下建议的项目金额为 7,419,281 美元。考虑到第九十二次会议核准的 33,900 美元和向第九十三次会议建议的金额，该供资窗口下可动用的剩余资金为 12,546,819 美元。本文件附件二列出了双边和执行机构根据第 91/65 号决定向第九十三次会议提交的试点项目。
根据第 91/66 号决定在废物管制物质库存国家清单编制的供资窗口下建议的项目金额为 3,222,500 美元，未列入 2023 年业务计划。本文件附件三列出了双边和执行机构根据第 91/66 号决定向第九十三次会议提交的项目编制活动。
此外，关于第 91/66 号决定，第(c)(三)段要求，上述供资窗口下的项目将从第九十三次会议直至第九十七次会议（包括第九十七次会议）提交执行委员会审议，但前提是这些项目将在核准之前列入相关业务计划。在网络会议上与各机构讨论期间，各机构告知秘书处，第 5 条国家需要更多时间来了解无用管制物质管理的各方面内容，并需要各机构在网络会议期间提供更多信息，然后才会同意将这些活动纳入各自的业务计划；这项工作比预期花费了更多时间。在过去几个月（包括2023 年 10 月举行的缔约方第三十五次会议期间）进行了更多咨询，听取了更多意见后，各国表示有兴趣在这一供资窗口下提交项目。为了便于提交与编制废旧或无用管制物质库存清单有关的项目，谨建议执行委员会破例允许双边和执行机构在 2024 年期间，在根据第 91/66 号决定设立的供资窗口下提交项目编制活 动，即使这些活动未列入业务计划。
已列入 2023 年业务计划、金额为 54,097,185 [footnoteRef:3]美元的项目提案未提交第九十三次会议。这些提案已列入多边基金 2024-2026 年综合业务计划。[footnoteRef:4] [3:  这些活动包括：40 个国家的 104 项氟氯烃相关活动 （3,237 万美元）、34 个国家的 49 项氢氟碳化物相关活动（1,226 万美元）和 28 项体制强化活动（947 万美元）。]  [4:  UNEP/OzL.Pro/ExCom/93/25号文件] 


I.2	预先承付款项
如表3所示，假设提交给第九十三次会议的多年期协定的供资申请原则上得到核准，则2023年至2031年期间多年期协定的现有预先承付款项总额为3.1416亿美元。
表3. 预先承付款项（2023–2031年）（千美元）
	说明
	2023年
	2024年
	2025年
	2026年
	2027年
	2028年
	2029年
	2030年
	2031年
	共计

	原则上核准
	68,086
	53,334
	51,015
	42,781
	10,187
	5,852
	4,733
	8,163
	57
	244,207

	提交第九十三次会议
	27,918
	0
	10,122
	14,050
	10,623
	24
	5,528
	1,683
	0
	69,949

	共计
	96,005
	53,334
	61,137
	56,831
	20,811
	5,876
	10,261
	9,846
	57
	314,156



第二部分：2021-2023三年期的资源分配情况

截至 2023 年 11 月 8 日，多边基金的可用结余额为 277,322,098 美元，2021-2013 三年期的未缴会费为 52,864,962 美元，其中 23,281,488 美元预计无法收取。[footnoteRef:5]2023 年 11 月 8 日之后，应计利息和固定汇率机制（FERM）造成的潜在损失估计分别为 5,849,812 美元和 753,989 美元。此外，退还给第九十三次会议的已完成项目的资金和利息分别为 4,669,316 [footnoteRef:6]美元和 505,720[footnoteRef:7] 美元。因此，在第九十三次会议上可用于新拨款的资金总额为 317,176,431 美元。 [5:   UNEP/OzL.Pro/ExCom/93/3号文件]  [6:  UNEP/OzL.Pro/ExCom/93/4和UNEP/OzL.Pro/ExCom/93/95号文件]  [7:  UNEP/OzL.Pro/ExCom/93/6 和UNEP/OzL.Pro/ExCom/93/47号文件] 

鉴于提交给第九十三次会议的项目建议供资额为 100,567,379 美元，秘书处预算为 7,737,326 美元，2021-2023 三年期结束时的可用资源将为 208,871,726 美元。此外，缔约方第五次特别会议还注意到，2018-2020 三年期期间应支付给多边基金的 2.46 亿美元剩余资金将在 2023 年之后用于支持执行《蒙特利尔议定书》（第 Ex.V/1 号决定）。因此，如表 4 所示，2024-2026 三年期的可用资金总额为 454,871,726 美元。
表4. 2021-2023三年期的资源分配情况（美元）
	说明
	 
	金额（美元）

	可用资金

	截至 2023 年 11 月 8 日的可用结余
	(a)
	277,322,098

	2021至2023年的未缴会费
	(b)
	52,864,962

	预期无法收取的未缴会费
	(c)
	(23,281,488)

	2023 年 11 月 8 日之后可能的应计利息
	(d)
	5,849,812

	2023 年 11 月 8 日之后固定汇率机制造成的可能损失
	(e)
	(753,989)

	退还给第九十三次会议的资金
	(f)
	4,669,316

	退还给第九十三次会议的利息
	(g)
	505,720

	可用资金总额
	(h = a+b+c+d+e+f+g)
	317,176,431

	支出

	向第九十三次会议建议的项目
	(i)
	100,567,379

	秘书处/执行委员会/监督/财务主管
	(j)
	7,737,326

	总支出
	(k = i+j)
	108,304,705

	2023年底可用资源
	(l = h-k)
	208,871,726

	将在2023年后使用的2018–2020三年期结转金额 
	(m)
	246,000,000

	2024–2026三年期可用资源总额
	(n= l+m)
	454,871,726



第三部分：建议 

谨建议执行委员会：
注意到：
(i) UNEP/OzL.Pro/ExCom/93/23 号文件所载多边基金 2023-2025 年综合业务计  		划的最新执行情况；
(ii) 向第九十三次会议申请的活动总金额为100,567,379美元（包括用于氢氟碳			化物相关活动的 23,789,140 美元、用于能效试点项目的 7,419,281 美元和			用于编制废物管制物质库存国家清单的 3,222,500 美元），其中12,521,905			美元与未列入2023年业务计划的项目提案有关；以及
作为例外情况，允许双边和执行机构在 2024 年期间，在根据第 91/66 号决定设立的供资窗口下，提交编制废物管制物质库存国家清单的项目，即使这些项目未列入以上机构的业务计划。

UNEP/OzL.Pro/ExCom/93/23

UNEP/OzL.Pro/ExCom/93/23


执行蒙特利尔议定书多边基金执行委员会的会前文件不妨碍文件印发后执行委员会可能作出的任何决定。
2
3
Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Albania
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	50,000
	6,500

	Albania
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	129,390
	9,057

	Bolivia (Plurinational State of)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	40,500
	5,265

	Bolivia (Plurinational State of)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	153,500
	10,745

	Brazil
	Germany
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	40,000
	5,200

	Brazil
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	126,500
	8,855

	Brazil
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	63,500
	4,445

	Cambodia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	123,810
	11,143

	Cambodia
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	126,300
	16,419

	Chile
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	752,607
	52,683

	Chile
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	123,900
	16,107

	Colombia
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the air-conditioning manufacturing sector
	50,000
	3,500

	Colombia
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	150,000
	10,500

	Congo (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	13,750
	1,788

	Congo (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	67,750
	6,098

	Cuba
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	145,455
	10,182

	Cuba
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	14,545
	1,018

	Dominican Republic (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	120,774
	15,701

	Dominican Republic (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	50,050
	4,505

	Dominican Republic (the)
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	320,935
	22,465

	Dominican Republic (the)
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	44,171
	3,092

	Ecuador
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	292,600
	20,482

	Egypt
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	40,000
	2,800

	Egypt
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	180,000
	12,600

	Eritrea
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	91,000
	11,830

	Eritrea
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	39,000
	2,730

	Georgia
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Ghana
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	125,000
	11,250

	Ghana
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	51,000
	6,630

	Ghana
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	7,500
	675

	Ghana
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	4,500
	585

	Grenada
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	29,670
	2,670

	Grenada
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	42,830
	5,568

	India
	UNDP
	INV
	KIP
	Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial air-conditioning packaged and ducted air-conditioning units at Voltas Limited
	422,561
	29,579

	India
	UNDP
	INV
	KIP
	Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC‑134a to propane (R-290)
	423,765
	29,664

	India
	UNDP
	INV
	KIP
	Demonstration/conversion from R-404A and R-407C to CO2 transcritical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing sector at Mech Air Industries
	322,452
	22,572

	India
	UNDP
	PRP
	KIP
	Preparation of a demonstration project in the manufacture of compressors for mobile air-conditioning manufacturing sector
	30,000
	2,100

	Jordan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	2,540,680
	177,848

	Kenya
	Germany
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	95,000
	12,350

	Kenya
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	95,000
	12,350

	Kyrgyzstan
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	51,000
	4,590

	Kyrgyzstan
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	30,000
	3,900

	Lebanon
	UNDP
	PRP
	PHA
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	70,000
	4,900

	Malawi
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	39,000
	5,070

	Malawi
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	29,000
	2,610

	Malaysia
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	3,042,912
	213,004

	Mali
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	35,000
	2,450

	Mali
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	135,000
	17,550

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	79,905
	5,593

	Mexico
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	12,695
	1,574

	Mexico
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	283,418
	19,839

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (foam sector plan)
	888,833
	62,218

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	465,000
	32,550

	Mexico
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	215,100
	26,669

	Mexico
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	4,801,972
	336,138

	Mongolia
	UNIDO
	PRP
	KIP
	Preparation of a KIP investment project in the foam sector
	80,000
	5,600

	Nicaragua
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	40,000
	5,200

	Nicaragua
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	159,000
	14,310

	Niger (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I)
	15,000
	1,950

	Niger (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I)
	35,000
	850

	North Macedonia
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	103,555
	9,320

	Panama
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	331,100
	23,177

	Peru
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	283,140
	19,820

	Republic of Moldova (the)
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Saint Vincent and the Grenadines
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	70,000
	9,100

	Saint Vincent and the Grenadines
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	30,000
	2,100

	Sri Lanka
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	80,000
	5,600

	Thailand
	IBRD
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	220,000
	15,400

	Trinidad and Tobago
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	496,973
	34,788

	Trinidad and Tobago
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	46,276
	3,239

	Turkmenistan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	106,000
	7,420

	Turkmenistan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	10,000
	700

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector)
	289,220
	20,245

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	119,265
	8,349

	Viet Nam
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	35,533
	4,244

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	984,000
	68,880

	Viet Nam
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	426,163
	50,906

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (technical assistance and policy)
	165,307
	11,571
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Annex II

PILOT PROJECTS FOR ENERGY EFFICIENCY (DECISION 91/65) 
SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Bolivia (Plurinational State of)
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	96,000
	8,640

	Chile
	UNDP
	PRP
	EEF
	Preparation of a pilot project for the use of R-744 (carbon dioxide) as an alternative refrigerant in heat pumps in industrial refrigeration (decision 91/65)
	30,000
	2,100

	China
	UNIDO
	DEM
	EEF
	Demonstration project of replacing HFC‑134a with R-744 in the field of electric vehicles (decision 91/65)
	1,371,500
	96,005

	Ecuador
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	190,000
	17,100

	Egypt
	UNIDO
	DEM
	EEF
	Energy efficiency pilot project in the refrigeration and air-conditioning sector (decision 91/65)
	285,000
	19,950

	India
	Germany
	DEM
	EEF
	Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65)
	1,853,795
	213,918

	India
	UNDP
	DEM
	EEF
	Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC‑134a to propane (R-290) (technical assistance to enhance the energy efficiency of the converted equipment) (decision 91/65)
	150,000
	13,500

	Kenya
	Germany
	PRP
	EEF
	Preparation for a pilot project on energy efficiency (decision 91/65)
	30,000
	3,900

	Kyrgyzstan
	UNEP
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	206,000
	26,780

	Malaysia
	IBRD
	PRP
	EEF
	Preparation for a pilot project on energy efficiency in stand-alone commercial refrigeration sector (decision 91/65)
	30,000
	2,100

	Mexico
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	938,620
	65,703

	Nicaragua
	UNEP
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	30,000
	3,900

	Nicaragua
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	66,000
	5,940

	Nigeria
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	145,000
	13,050

	South Africa
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	1,120,000
	78,400

	Togo
	Germany
	PRP
	EEF
	Project preparation for energy efficiency‑related activities (decision 91/65)
	30,000
	3,900

	Turkmenistan
	UNIDO
	DEM
	EEF
	Pilot project for maintaining and enhancing energy efficiency of replacement technologies and equipment (decision 91/65)
	142,000
	12,780

	Viet Nam
	IBRD
	PRP
	EEF
	Preparation for a pilot project on energy efficiency in the air-conditioning sector (decision 91/65)
	30,000
	2,100

	Global
	UNDP
	PRP
	EEF
	Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago
	80,000
	5,600
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Annex III

PROJECT PREPARATION FOR NATIONAL INVENTORIES OF BANKS 
OF WASTE‑CONTROLLED SUBSTANCES (DECISION 91/66) 
SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Albania
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Armenia
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Benin
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Bolivia (Plurinational State of)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Bolivia (Plurinational State of)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Burkina Faso
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Burundi
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Cameroon
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Costa Rica
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Cuba
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Dominican Republic (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Ecuador
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Egypt
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	El Salvador
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Guatemala
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Guatemala
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Honduras
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Honduras
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Jamaica
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Kenya
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Liberia
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Mexico
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Montenegro
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	4,900

	Namibia
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Nicaragua
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Nicaragua
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	North Macedonia
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	5,600

	Peru
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Republic of Moldova (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Seychelles
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Togo
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Trinidad and Tobago
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Turkmenistan
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Uruguay
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Venezuela (Bolivarian Republic of)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Viet Nam
	IBRD
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Yemen
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	13,000
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