| 联 合 国 |  | EP |
| --- | --- | --- |
|  | ### 联 合 国 ### 环 境 规 划 署 | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/23 6 December 2023 CHINESE ORIGINAL: ENGLISH |

执行蒙特利尔议定书

多边基金执行委员会

第九十三次会议

2023年12月15日至19日，蒙特利尔

临时议程第8(a)项

多边基金2023-2025年综合业务计划最新执行情况

- 导言

# 本文件包含下列部分：

## 第一部分：	2023-2025年业务计划的最新执行情况

## 第二部分：	2021-2023三年期的资源分配情况

第三部分：	建议

## 第一部分：2023-2025年业务计划的最新执行情况

# 在第九十一次会议上，执行委员会核准了多边基金2023-2025年综合业务计划。根据第91/31号决定，秘书处调整了2023-2025年综合业务计划，如表1所示。

表1.多边基金调整后的2023-2025年综合业务计划资源分配情况（美元）*

| 说明 | 2023年 | 2024年 | 2025年 | 共计 |
| --- | --- | --- | --- | --- |
| 氟氯烃活动 |  |  |  |  |
| 核准的氟氯烃淘汰管理计划 | 60,280,861 | 56,111,450 | 43,084,350 | 159,476,661 |
| 氟氯烃淘汰管理计划项目编制 – 第二阶段 | 200,480 | 77,600 | 0 | 278,080 |
| 氟氯烃淘汰管理计划第二阶段 | 2,937,082 | 5,199,804 | 3,462,199 | 11,599,085 |
| 氟氯烃淘汰管理计划第二阶段 – 投资 | 0 | 248,532 | 0 | 248,532 |
| 氟氯烃淘汰管理计划项目编制 – 第三阶段 | 290,100 | 92,750 | 0 | 382,850 |
| 氟氯烃淘汰管理计划第三阶段 | 14,794,713 | 10,344,520 | 20,526,731 | 45,665,964 |
| 氟氯烃淘汰管理计划项目编制 – 第四阶段 | 90,000 | 0 | 0 | 90,000 |
| 氟氯烃淘汰管理计划第四阶段 | 0 | 0 | 2,093,000 | 2,093,000 |
| 氟氯烃淘汰管理计划 – 能效 | 3,258,494 | 2,672,980 | 3,379,420 | 9,310,894 |
| 氟氯烃淘汰管理计划核查** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| 氟氯烃活动小计 | 82,440,330 | 75,336,236 | 73,134,299 | 230,910,865 |
| 氢氟碳化物活动 |  |  |  |  |
| 氢氟碳化物逐步减少的扶持活动 | 53,500 | 160,500 | 0 | 214,000 |
| 基加利氢氟碳化物实施计划 – 项目编制 | 3,945,431 | 2,567,011 | 144,560 | 6,657,002 |
| 基加利氢氟碳化物实施计划 | 27,299,967 | 21,437,607 | 245,413 | 48,982,987 |
| 基加利氢氟碳化物实施计划项目编制 – 投资 | 129,000 | 0 | 0 | 129,000 |
| 基加利氢氟碳化物实施计划 – 投资 | 321,000 | 8,963,616 | 0 | 9,284,616 |
| HFC-23排放控制项目编制 | 43,000 | 0 | 0 | 43,000 |
| HFC-23排放控制 | 0 | 8,000,000 | 0 | 8,000,000 |
| 氢氟碳化物 – 技术援助 | 0 | 678,000 | 0 | 678,000 |
| 氢氟碳化物活动小计 | 31,791,898 | 41,806,734 | 389,973 | 73,988,605 |
| 能效试点项目 |  |  |  |  |
| 能效试点项目 | 20,000,000 | 0 | 0 | 20,000,000 |
| 能效试点项目小计 | 20,000,000 | 0 | 0 | 20,000,000 |
| 标准活动 |  |  |  |  |
| 体制强化 | 27,860,444 | 16,639,896 | 0 | 44,500,341 |
| 履约援助方案 | 11,445,002 | 11,788,350 | 12,142,003 | 35,375,355 |
| 核心单位 | 5,969,740 | 6,011,529 | 6,053,610 | 18,034,878 |
| 秘书处、执行委员会以及监测和评价费用减去加拿大对应费用 | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| 财务主任 | 500,000 | 500,000 | 500,000 | 1,500,000 |
| 标准活动小计 | 53,012,512 | 42,141,798 | 25,512,237 | 120,666,547 |
| 总计 | 187,244,740 | 159,284,767 | 99,036,509 | 445,566,017 |
| 澳大利亚 | 0 | 0 | 152,497 | 152,497 |
| 奥地利 | 783,667 | 0 | 0 | 783,667 |
| 法国 | 671,075 | 0 | 0 | 671,075 |
| 德国 | 1,349,869 | 3,705,721 | 1,028,250 | 6,083,840 |
| 日本 | 67,800 | 0 | 0 | 67,800 |
| 开发计划署 | 62,425,117 | 54,216,500 | 29,064,016 | 145,705,634 |
| 环境规划署 | 40,325,066 | 36,674,895 | 22,071,085 | 99,071,046 |
| 工发组织 | 38,767,526 | 29,078,890 | 29,553,746 | 97,400,162 |
| 世界银行 | 14,528,694 | 27,318,138 | 9,261,691 | 51,108,523 |
| 氟氯烃淘汰管理计划核查** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| 能效试点项目 | 20,000,000 | 0 | 0 | 20,000,000 |
| 秘书处、执行委员会以及监测和评价费用减去加拿大对应费用 | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| 财务主任 | 500,000 | 500,000 | 500,000 | 1,500,000 |

* 包括适用的机构支助费用。

**低消费量国家编制氟氯烃淘汰管理计划核查报告的供资由执行委员会每年核准。

I.1	2023年业务计划执行情况

# 2023 年业务计划的总金额为 187,244,740 美元。其中 29,253,988 美元已在第九十二次会议上获得核准。此外，第九十三次会议将审议总额为 108,304,705 美元的活动；如表 2 所示，如果提交的所有项目提案申请的供资都获得核准，2023 年业务计划将有 49,686,047 美元的结余。

表2. 2023年综合业务计划，第九十二次会议核准的项目，向第九十三次会议建议的项目，以及结余（美元）*

| 预算项目 | 业务计划的资金总额 | 第九十二次会议核准的项目 | 向第九十三次会议建议的活动 | 结余 （高于）/低于 |
| --- | --- | --- | --- | --- |
| 双边机构 | 2,872,411 | 687,988 | 1,657,265 | 527,158 |
| 开发计划署 | 62,425,117 | 10,211,836 | 28,591,500 | 23,621,781 |
| 环境规划署 | 40,325,066 | 6,644,731 | 22,767,524 | 10,912,811 |
| 工发组织 | 38,767,526 | 8,419,645 | 24,134,585 | 6,213,296 |
| 世界银行 | 14,528,694 | 2,681,989 | 15,997,224 | (4,150,519) |
| 氟氯烃淘汰管理计划核查 | 588,600 | 573,900 | 0 | 14,700 |
| 能效试点项目 | 20,000,000 | 33,900 | 7,419,281 | 12,546,819 |
| 小计（机构） | 179,507,414 | 29,253,988 | 100,567,379 | 49,686,047 |
| 秘书处/执行委员会/监测和评价（不包括加拿大对应费用） | 7,237,326 | 0 | 7,237,326 | 0 |
| 财务主任 | 500,000 | 0 | 500,000 | 0 |
| 小计（标准费用） | 7,737,326 | 0 | 7,737,326 | 0 |
| 共计 | 187,244,740 | 29,253,988 | 108,304,705 | 49,686,047 |

* 包括核心单位费用。

# 向第九十三次会议建议的项目提案金额为100,567,379美元，比2023年业务计划中的金额高16,578,316美元，包括与未列入2023年业务计划的项目提案有关的12,521,905美元。

# 向第九十三次会议建议的氢氟碳化物相关活动金额为 23,789,140 美元，其中 3,182,574 美元与未列入 2023 年业务计划的项目提案有关。本文件附件一列出了双边和执行机构向第九十三次会议提交的氢氟碳化物相关项目。

# .根据第 91/65 号决定，在能效试点项目供资窗口下建议的项目金额为 7,419,281 美元。考虑到第九十二次会议核准的 33,900 美元和向第九十三次会议建议的金额，该供资窗口下可动用的剩余资金为 12,546,819 美元。本文件附件二列出了双边和执行机构根据第 91/65 号决定向第九十三次会议提交的试点项目。

# 根据第 91/66 号决定在废物管制物质库存国家清单编制的供资窗口下建议的项目金额为 3,222,500 美元，未列入 2023 年业务计划。本文件附件三列出了双边和执行机构根据第 91/66 号决定向第九十三次会议提交的项目编制活动。

# 此外，关于第 91/66 号决定，第(c)(三)段要求，上述供资窗口下的项目将从第九十三次会议直至第九十七次会议（包括第九十七次会议）提交执行委员会审议，但前提是这些项目将在核准之前列入相关业务计划。在网络会议上与各机构讨论期间，各机构告知秘书处，第 5 条国家需要更多时间来了解无用管制物质管理的各方面内容，并需要各机构在网络会议期间提供更多信息，然后才会同意将这些活动纳入各自的业务计划；这项工作比预期花费了更多时间。在过去几个月（包括2023 年 10 月举行的缔约方第三十五次会议期间）进行了更多咨询，听取了更多意见后，各国表示有兴趣在这一供资窗口下提交项目。为了便于提交与编制废旧或无用管制物质库存清单有关的项目，谨建议执行委员会破例允许双边和执行机构在 2024 年期间，在根据第 91/66 号决定设立的供资窗口下提交项目编制活 动，即使这些活动未列入业务计划。

# 已列入 2023 年业务计划、金额为 54,097,185 美元的项目提案未提交第九十三次会议。这些提案已列入多边基金 2024-2026 年综合业务计划。

# I.2	预先承付款项

# 如表3所示，假设提交给第九十三次会议的多年期协定的供资申请原则上得到核准，则2023年至2031年期间多年期协定的现有预先承付款项总额为3.1416亿美元。

表3. 预先承付款项（2023–2031年）（千美元）

| 说明 | 2023年 | 2024年 | 2025年 | 2026年 | 2027年 | 2028年 | 2029年 | 2030年 | 2031年 | 共计 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 原则上核准 | 68,086 | 53,334 | 51,015 | 42,781 | 10,187 | 5,852 | 4,733 | 8,163 | 57 | 244,207 |
| 提交第九十三次会议 | 27,918 | 0 | 10,122 | 14,050 | 10,623 | 24 | 5,528 | 1,683 | 0 | 69,949 |
| 共计 | 96,005 | 53,334 | 61,137 | 56,831 | 20,811 | 5,876 | 10,261 | 9,846 | 57 | 314,156 |

# 第二部分：2021-2023三年期的资源分配情况

# 截至 2023 年 11 月 8 日，多边基金的可用结余额为 277,322,098 美元，2021-2013 三年期的未缴会费为 52,864,962 美元，其中 23,281,488 美元预计无法收取。2023 年 11 月 8 日之后，应计利息和固定汇率机制（FERM）造成的潜在损失估计分别为 5,849,812 美元和 753,989 美元。此外，退还给第九十三次会议的已完成项目的资金和利息分别为 4,669,316 美元和 505,720 美元。因此，在第九十三次会议上可用于新拨款的资金总额为 317,176,431 美元。

# 鉴于提交给第九十三次会议的项目建议供资额为 100,567,379 美元，秘书处预算为 7,737,326 美元，2021-2023 三年期结束时的可用资源将为 208,871,726 美元。此外，缔约方第五次特别会议还注意到，2018-2020 三年期期间应支付给多边基金的 2.46 亿美元剩余资金将在 2023 年之后用于支持执行《蒙特利尔议定书》（第 Ex.V/1 号决定）。因此，如表 4 所示，2024-2026 三年期的可用资金总额为 454,871,726 美元。

表4. 2021-2023三年期的资源分配情况（美元）

| 说明 |  | 金额（美元） |
| --- | --- | --- |
| 可用资金 |  |  |
| 截至 2023 年 11 月 8 日的可用结余 | (a) | 277,322,098 |
| 2021至2023年的未缴会费 | (b) | 52,864,962 |
| 预期无法收取的未缴会费 | (c) | (23,281,488) |
| 2023 年 11 月 8 日之后可能的应计利息 | (d) | 5,849,812 |
| 2023 年 11 月 8 日之后固定汇率机制造成的可能损失 | (e) | (753,989) |
| 退还给第九十三次会议的资金 | (f) | 4,669,316 |
| 退还给第九十三次会议的利息 | (g) | 505,720 |
| 可用资金总额 | (h = a+b+c+d+e+f+g) | 317,176,431 |
| 支出 |  |  |
| 向第九十三次会议建议的项目 | (i) | 100,567,379 |
| 秘书处/执行委员会/监督/财务主管 | (j) | 7,737,326 |
| 总支出 | (k = i+j) | 108,304,705 |
| 2023年底可用资源 | (l = h-k) | 208,871,726 |
| 将在2023年后使用的2018–2020三年期结转金额 | (m) | 246,000,000 |
| 2024–2026三年期可用资源总额 | (n= l+m) | 454,871,726 |

# 第三部分：建议

# 谨建议执行委员会：

## 注意到：

## UNEP/OzL.Pro/ExCom/93/23 号文件所载多边基金 2023-2025 年综合业务计  		划的最新执行情况；

## 向第九十三次会议申请的活动总金额为100,567,379美元（包括用于氢氟碳			化物相关活动的 23,789,140 美元、用于能效试点项目的 7,419,281 美元和			用于编制废物管制物质库存国家清单的 3,222,500 美元），其中12,521,905			美元与未列入2023年业务计划的项目提案有关；以及

## 作为例外情况，允许双边和执行机构在 2024 年期间，在根据第 91/66 号决定设立的供资窗口下，提交编制废物管制物质库存国家清单的项目，即使这些项目未列入以上机构的业务计划。

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,000 | 6,500 |
| Albania | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 129,390 | 9,057 |
| Bolivia (Plurinational State of) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,500 | 5,265 |
| Bolivia (Plurinational State of) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 153,500 | 10,745 |
| Brazil | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 5,200 |
| Brazil | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 126,500 | 8,855 |
| Brazil | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 63,500 | 4,445 |
| Cambodia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,810 | 11,143 |
| Cambodia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 126,300 | 16,419 |
| Chile | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 752,607 | 52,683 |
| Chile | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,900 | 16,107 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the air-conditioning manufacturing sector | 50,000 | 3,500 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 150,000 | 10,500 |
| Congo (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 13,750 | 1,788 |
| Congo (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 67,750 | 6,098 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 145,455 | 10,182 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 14,545 | 1,018 |
| Dominican Republic (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 120,774 | 15,701 |
| Dominican Republic (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,050 | 4,505 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 320,935 | 22,465 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 44,171 | 3,092 |
| Ecuador | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 292,600 | 20,482 |
| Egypt | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 2,800 |
| Egypt | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 180,000 | 12,600 |
| Eritrea | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Eritrea | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Georgia | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 125,000 | 11,250 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 6,630 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 7,500 | 675 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 4,500 | 585 |
| Grenada | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,670 | 2,670 |
| Grenada | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 42,830 | 5,568 |
| India | UNDP | INV | KIP | Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial air-conditioning packaged and ducted air-conditioning units at Voltas Limited | 422,561 | 29,579 |
| India | UNDP | INV | KIP | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) | 423,765 | 29,664 |
| India | UNDP | INV | KIP | Demonstration/conversion from R-404A and R-407C to CO2 transcritical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing sector at Mech Air Industries | 322,452 | 22,572 |
| India | UNDP | PRP | KIP | Preparation of a demonstration project in the manufacture of compressors for mobile air-conditioning manufacturing sector | 30,000 | 2,100 |
| Jordan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 2,540,680 | 177,848 |
| Kenya | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kenya | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kyrgyzstan | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 4,590 |
| Kyrgyzstan | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 30,000 | 3,900 |
| Lebanon | UNDP | PRP | PHA | Preparation of a KIP investment project in the refrigeration manufacturing sector | 70,000 | 4,900 |
| Malawi | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 39,000 | 5,070 |
| Malawi | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,000 | 2,610 |
| Malaysia | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 3,042,912 | 213,004 |
| Mali | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 35,000 | 2,450 |
| Mali | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 135,000 | 17,550 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 79,905 | 5,593 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 12,695 | 1,574 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 283,418 | 19,839 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (foam sector plan) | 888,833 | 62,218 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 465,000 | 32,550 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 215,100 | 26,669 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 4,801,972 | 336,138 |
| Mongolia | UNIDO | PRP | KIP | Preparation of a KIP investment project in the foam sector | 80,000 | 5,600 |
| Nicaragua | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,000 | 5,200 |
| Nicaragua | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 159,000 | 14,310 |
| Niger (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I) | 15,000 | 1,950 |
| Niger (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I) | 35,000 | 850 |
| North Macedonia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 103,555 | 9,320 |
| Panama | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 331,100 | 23,177 |
| Peru | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 283,140 | 19,820 |
| Republic of Moldova (the) | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Saint Vincent and the Grenadines | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 70,000 | 9,100 |
| Saint Vincent and the Grenadines | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 30,000 | 2,100 |
| Sri Lanka | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 80,000 | 5,600 |
| Thailand | IBRD | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 220,000 | 15,400 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 496,973 | 34,788 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 46,276 | 3,239 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 106,000 | 7,420 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 10,000 | 700 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 289,220 | 20,245 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 119,265 | 8,349 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 35,533 | 4,244 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 984,000 | 68,880 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 426,163 | 50,906 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (technical assistance and policy) | 165,307 | 11,571 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bolivia (Plurinational State of) | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 96,000 | 8,640 |
| Chile | UNDP | PRP | EEF | Preparation of a pilot project for the use of R-744 (carbon dioxide) as an alternative refrigerant in heat pumps in industrial refrigeration (decision 91/65) | 30,000 | 2,100 |
| China | UNIDO | DEM | EEF | Demonstration project of replacing HFC-134a with R-744 in the field of electric vehicles (decision 91/65) | 1,371,500 | 96,005 |
| Ecuador | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 190,000 | 17,100 |
| Egypt | UNIDO | DEM | EEF | Energy efficiency pilot project in the refrigeration and air-conditioning sector (decision 91/65) | 285,000 | 19,950 |
| India | Germany | DEM | EEF | Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65) | 1,853,795 | 213,918 |
| India | UNDP | DEM | EEF | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) (technical assistance to enhance the energy efficiency of the converted equipment) (decision 91/65) | 150,000 | 13,500 |
| Kenya | Germany | PRP | EEF | Preparation for a pilot project on energy efficiency (decision 91/65) | 30,000 | 3,900 |
| Kyrgyzstan | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 206,000 | 26,780 |
| Malaysia | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in stand-alone commercial refrigeration sector (decision 91/65) | 30,000 | 2,100 |
| Mexico | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 938,620 | 65,703 |
| Nicaragua | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Nicaragua | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 66,000 | 5,940 |
| Nigeria | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 145,000 | 13,050 |
| South Africa | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 1,120,000 | 78,400 |
| Togo | Germany | PRP | EEF | Project preparation for energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Turkmenistan | UNIDO | DEM | EEF | Pilot project for maintaining and enhancing energy efficiency of replacement technologies and equipment (decision 91/65) | 142,000 | 12,780 |
| Viet Nam | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in the air-conditioning sector (decision 91/65) | 30,000 | 2,100 |
| Global | UNDP | PRP | EEF | Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago | 80,000 | 5,600 |

Annex III

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Armenia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Benin | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Bolivia (Plurinational State of) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Bolivia (Plurinational State of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Burkina Faso | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Burundi | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cameroon | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Costa Rica | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Cuba | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Dominican Republic (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Ecuador | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Egypt | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| El Salvador | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Guatemala | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Guatemala | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Honduras | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Honduras | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Jamaica | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Kenya | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Liberia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Mexico | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Montenegro | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 4,900 |
| Namibia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Nicaragua | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Nicaragua | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| North Macedonia | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 5,600 |
| Peru | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Republic of Moldova (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Seychelles | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Togo | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Trinidad and Tobago | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Turkmenistan | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Uruguay | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Venezuela (Bolivarian Republic of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Viet Nam | IBRD | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Yemen | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 13,000 |

UNEP/OzL.Pro/ExCom/93/1号文件

玻利维亚多民族国（环境规划署和工发组织）、厄瓜多尔（工发组织）、危地马拉 （环境规划署和工发组织）、莫桑比克（开发计划署）和北马其顿（工发组织）氟氯烃 淘汰管理计划第二阶段；越南氟氯烃淘汰管理计划第三阶段（世界银行）；秘鲁氟氯烃 淘汰管理计划第三阶段的一个项目编制（开发计划署）；泰国氟氯烃淘汰管理计划投资项目的一个项目编制（世界银行）； 印度示范项目的一个项目编制（开发计划署）；哥伦比亚（2 个）（开发计划署）、黎巴嫩（开发计划署）、蒙古（工发组织）和斯里兰卡（开发计划署）的 5 个基加利氢氟碳化物实施计划投资项目编制；巴西（德国、开发计划署和工发组织）、肯尼亚（德国）、 马里（开发计划署和环境规划署）以及圣文森特和格林纳丁斯（环境规划署和工发组织）的 8 个基加利氢氟碳化物实施计划第一阶段项目编制； 印度的 3 个氢氟碳化物投资项目（开发计划署）；根据第 89/6 号决定，为 阿尔巴尼亚（工发组织）、贝宁（工发组织）、玻利维亚多民族国（环境规划署和工发组织）、厄瓜多尔（工发组织）、格林纳达（工发组织）、危地马拉（环境规划署和工发组织）、莱索托（德国）、利比里亚（德国）、纳米比亚（德国）和塞舌尔（德国）执行的 12 个能效项目； 玻利维亚多民族国（环境规划署）、刚果（环境规划署和工发组织）、多米尼加共和国（环境规划署和工发组织）、吉尔吉斯斯坦（开发计划署）、尼加拉瓜（环境规划署）、尼日尔（环境规划署和工发组织）和秘鲁（开发计划署）基加利氢氟碳化物实施计划第一阶段；玻利维亚多民族国（环境规划署）体制强化项目第一阶段；以及附件三根据第 91/66 号决定进行的废物管制物质库存国家清单的 37 个项目编制。

这些活动包括：40 个国家的 104 项氟氯烃相关活动 （3,237 万美元）、34 个国家的 49 项氢氟碳化物相关活动（1,226 万美元）和 28 项体制强化活动（947 万美元）。

UNEP/OzL.Pro/ExCom/93/25号文件

UNEP/OzL.Pro/ExCom/93/3号文件

UNEP/OzL.Pro/ExCom/93/4和UNEP/OzL.Pro/ExCom/93/95号文件

UNEP/OzL.Pro/ExCom/93/6 和UNEP/OzL.Pro/ExCom/93/47号文件