| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/23 6 December 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2023–2025 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# The present document consists of the following sections:

## I.	An update on the status of the implementation of the 2023–2025 business plan

## II.	Resource allocation for the 2021–2023 triennium

III.	Recommendation

## I.	Update on the status of the implementation of the 2023–2025 business plan

# At its 91st meeting, the Executive Committee endorsed the 2023–2025 consolidated business plan of the Multilateral Fund. In response to decision 91/31, the Secretariat adjusted the consolidated 2023–2025 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2023–2025 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2023 | 2024 | 2025 | Total |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 60,280,861 | 56,111,450 | 43,084,350 | 159,476,661 |
| HPMP project preparation (PRP) – stage II | 200,480 | 77,600 | 0 | 278,080 |
| HPMP stage II | 2,937,082 | 5,199,804 | 3,462,199 | 11,599,085 |
| HPMP stage II – investment | 0 | 248,532 | 0 | 248,532 |
| HPMP PRP – stage III | 290,100 | 92,750 | 0 | 382,850 |
| HPMP stage III | 14,794,713 | 10,344,520 | 20,526,731 | 45,665,964 |
| HPMP PRP – stage IV | 90,000 | 0 | 0 | 90,000 |
| HPMP stage IV | 0 | 0 | 2,093,000 | 2,093,000 |
| HPMP – energy efficiency | 3,258,494 | 2,672,980 | 3,379,420 | 9,310,894 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HCFC activities subtotal | 82,440,330 | 75,336,236 | 73,134,299 | 230,910,865 |
| HFC activities |  |  |  |  |
| Enabling activities for HFC phase-down | 53,500 | 160,500 | 0 | 214,000 |
| Kigali HFC implementation plans (KIPs) – PRP | 3,945,431 | 2,567,011 | 144,560 | 6,657,002 |
| KIPs | 27,299,967 | 21,437,607 | 245,413 | 48,982,987 |
| KIPs PRP – investment | 129,000 | 0 | 0 | 129,000 |
| KIPs – investment | 321,000 | 8,963,616 | 0 | 9,284,616 |
| HFC-23 emissions control PRP | 43,000 | 0 | 0 | 43,000 |
| HFC-23 emissions control | 0 | 8,000,000 | 0 | 8,000,000 |
| HFC – technical assistance | 0 | 678,000 | 0 | 678,000 |
| HFC activities subtotal | 31,791,898 | 41,806,734 | 389,973 | 73,988,605 |
| Pilot project for energy efficiency |  |  |  |  |
| Pilot project for energy efficiency | 20,000,000 | 0 | 0 | 20,000,000 |
| Pilot project for energy efficiency subtotal | 20,000,000 | 0 | 0 | 20,000,000 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 27,860,444 | 16,639,896 | 0 | 44,500,341 |
| Compliance Assistance Programme (CAP) | 11,445,002 | 11,788,350 | 12,142,003 | 35,375,355 |
| Core unit | 5,969,740 | 6,011,529 | 6,053,610 | 18,034,878 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 53,012,512 | 42,141,798 | 25,512,237 | 120,666,547 |
| Grand total | 187,244,740 | 159,284,767 | 99,036,509 | 445,566,017 |
| Australia | 0 | 0 | 152,497 | 152,497 |
| Austria | 783,667 | 0 | 0 | 783,667 |
| France | 671,075 | 0 | 0 | 671,075 |
| Germany | 1,349,869 | 3,705,721 | 1,028,250 | 6,083,840 |
| Japan | 67,800 | 0 | 0 | 67,800 |
| UNDP | 62,425,117 | 54,216,500 | 29,064,016 | 145,705,634 |
| UNEP | 40,325,066 | 36,674,895 | 22,071,085 | 99,071,046 |
| UNIDO | 38,767,526 | 29,078,890 | 29,553,746 | 97,400,162 |
| World Bank | 14,528,694 | 27,318,138 | 9,261,691 | 51,108,523 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Pilot project for energy efficiency | 20,000,000 | 0 | 0 | 20,000,000 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

I.1	Status of implementation of the 2023 business plan

# The total business plan values for 2023 amounts to US $187,244,740. Of this amount, US $29,253,988 has been approved at the 92nd meeting. In addition, activities amounting to US $108,304,705 would be considered at the 93rd meeting; if funding for all project proposals submitted as requested are approved, a balance of US $49,686,047 would be available from the 2023 business plan, as shown in table 2.

Table 2. 2023 consolidated business plan, approvals at the 92nd meeting, project recommended to the 93rd meeting, and balance (US $)*

| Budget items | Total value in business plan | Approvals at the 92nd meeting | Activities recommended to the 93rd meeting | Balance (above)/below |
| --- | --- | --- | --- | --- |
| Bilateral agencies | 2,872,411 | 687,988 | 1,657,265 | 527,158 |
| UNDP | 62,425,117 | 10,211,836 | 28,591,500 | 23,621,781 |
| UNEP | 40,325,066 | 6,644,731 | 22,767,524 | 10,912,811 |
| UNIDO | 38,767,526 | 8,419,645 | 24,134,585 | 6,213,296 |
| World Bank | 14,528,694 | 2,681,989 | 15,997,224 | (4,150,519) |
| HPMP verification | 588,600 | 573,900 | 0 | 14,700 |
| Pilot project for energy efficiency | 20,000,000 | 33,900 | 7,419,281 | 12,546,819 |
| Subtotal (agencies) | 179,507,414 | 29,253,988 | 100,567,379 | 49,686,047 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 7,237,326 | 0 | 7,237,326 | 0 |
| Treasurer | 500,000 | 0 | 500,000 | 0 |
| Subtotal (standard costs) | 7,737,326 | 0 | 7,737,326 | 0 |
| Total | 187,244,740 | 29,253,988 | 108,304,705 | 49,686,047 |

* Including core unit costs.

# The value of project proposals recommended to the 93rd meeting of US $100,567,379 is US $16,578,316 above its value in the 2023 business plan and includes US $12,521,905 associated with project proposals not included in the 2023 business plan.

# The value of HFC-related activities recommended to the 93rd meeting is US $23,789,140 of which US $3,182,574 is associated with project proposals not included in the 2023 business plan. Annex I to the present document lists HFC-related projects submitted by the bilateral and implementing agencies to the 93rd meeting.

# The value of projects recommended under the funding window for pilot projects for energy efficiency pursuant to decision 91/65 is US $7,419,281. Taking into account approvals at the 92nd meeting of US $33,900 and the values recommended to the 93rd meeting, the remaining funding available under this funding window is US $12,546,819. Annex II to the present document lists the pilot projects submitted by bilateral and implementing agencies to the 93rd meeting pursuant to decision 91/65.

# The value of projects recommended under the funding window for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66 is US $3,222,500 that is not included in the 2023 business plan. Annex III to the present document lists the project preparation activities submitted by bilateral and implementing agencies to the 93rd meeting pursuant to decision 91/66.

# In addition, regarding decision 91/66, paragraph (c)(iii) requires that projects under the funding window mentioned above would be submitted for the consideration of the Executive Committee as of the 93rd meeting up to and including the 97th meeting, on the understanding that they would be included in the relevant business plans before their approval. During discussions with the agencies at the network meetings, agencies informed the Secretariat that Article 5 countries needed more time to understand different aspects of management of unwanted controlled substances and needed more information from the agencies during the network meetings prior to agreeing to include these activities in their respective business plans; this took more time than expected. Based on the additional inputs and consultations held during the last few months including during the Thirty-Fifth Meeting of the Parties held in October 2023, the countries have expressed their interest in submitting projects under this funding window. In order to facilitate the submission of projects relating to the preparation of inventories of banks of used or unwanted controlled substances, the Executive Committee, on an exceptional basis, may wish to allow bilateral and implementing agencies to submit project preparation activities under the funding window established pursuant to decision 91/66 during the year 2024, even in cases where such activities are not included in the business plans.

# Project proposals with a value of US $54,097,185 that were included in the 2023 business plan, were not submitted to the 93rd meeting. These proposals have been included in the consolidated business plan of the Multilateral Fund for 2024–2026.

# I.2	Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2023 to 2031 is US $314.16 million, assuming that the funding requests of MYAs submitted to the 93rd meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2023–2031) (US $000)

| Description | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 68,086 | 53,334 | 51,015 | 42,781 | 10,187 | 5,852 | 4,733 | 8,163 | 57 | 244,207 |
| Submitted to 93rd meeting | 27,918 | 0 | 10,122 | 14,050 | 10,623 | 24 | 5,528 | 1,683 | 0 | 69,949 |
| Total | 96,005 | 53,334 | 61,137 | 56,831 | 20,811 | 5,876 | 10,261 | 9,846 | 57 | 314,156 |

# II.	Resource allocation for the 2021–2023 triennium

# As of 8 November 2023, the balance available at the Multilateral Fund amounted to US $277,322,098, with an outstanding contribution of US $52,864,962 for the 2021–2013 triennium of which US $23,281,488 is not expected to be collected. After 8 November 2023, the potential interest to be accrued and the potential loss due to the fixed-exchange rate mechanism (FERM) are estimated to US $5,849,812 and US $753,989, respectively. In addition, the funds returned for completed projects and the interest returned to the 93rd meeting amounts to US $4,669,316 and US $505,720, respectively. Accordingly, the total funding that could be available for new allocations at the 93rd meeting amounts to US $317,176,431.

# Given the value of funding recommended for projects submitted to the 93rd meeting of US $100,567,379 and the Secretariat budget of US $7,737,326, the resource available at the end of the 2021–2023 triennium would be US $208,871,726. In addition, the Fifth Extraordinary Meeting of the Parties also noted that US $246 million in remaining funds that were due to the Multilateral Fund during the triennium 2018–2020 will be used after 2023 to support the implementation of the Montreal Protocol (decision Ex.V/1). Therefore, the total resources available for the 2024–2026 triennium is US $454,871,726, as shown in table 4.

Table 4. Resource allocation for the 2021–2023 triennium (US $)

| Description |  | Amount (US $) |
| --- | --- | --- |
| Funding available |  |  |
| Balance available as of 8 November 2023 | (a) | 277,322,098 |
| Outstanding contributions for 2021 to 2023 | (b) | 52,864,962 |
| Outstanding contributions not expected | (c) | (23,281,488) |
| Potential interest accrued after 8 November 2023 | (d) | 5,849,812 |
| Potential FERM loss after 8 November 2023 | (e) | (753,989) |
| Fund returns at 93rd meeting | (f) | 4,669,316 |
| Interest returned at 93rd meeting | (g) | 505,720 |
| Total funding available | (h = a+b+c+d+e+f+g) | 317,176,431 |
| Expenditures |  |  |
| Projects recommended to the 93rd meeting | (i) | 100,567,379 |
| Secretariat/Executive Committee/Monitoring/Treasurer | (j) | 7,737,326 |
| Total expenditures | (k = i+j) | 108,304,705 |
| Resources available at the end of 2023 | (l = h-k) | 208,871,726 |
| Carry-over from the 2018–2020 triennium to be used after 2023 | (m) | 246,000,000 |
| Total resources available for the 2024–2026 triennium | (n= l+m) | 454,871,726 |

# III.	Recommendation

# The Executive Committee may wish:

## To note:

### The update on the status of implementation of the 2023–2025 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/93/23;

### That the total value of activities as requested to the 93rd meeting amounts to US $100,567,379 (including US $23,789,140 for HFC-related activities, US $7,419,281 for pilot projects for energy efficiency and US $3,222,500 for the preparation of national inventories of banks of waste-controlled substances), of which US $12,521,905 is associated with project proposals not included in the 2023 business plan; and

## To allow, on an exceptional basis, bilateral and implementing agencies to submit, during the year 2024, projects for the preparation of national inventories of banks of waste-controlled substances under the funding window established pursuant to decision 91/66, even in cases where such projects are not included in the agencies’ business plans.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,000 | 6,500 |
| Albania | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 129,390 | 9,057 |
| Bolivia (Plurinational State of) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,500 | 5,265 |
| Bolivia (Plurinational State of) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 153,500 | 10,745 |
| Brazil | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 5,200 |
| Brazil | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 126,500 | 8,855 |
| Brazil | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 63,500 | 4,445 |
| Cambodia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,810 | 11,143 |
| Cambodia | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 126,300 | 16,419 |
| Chile | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 752,607 | 52,683 |
| Chile | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 123,900 | 16,107 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the air-conditioning manufacturing sector | 50,000 | 3,500 |
| Colombia | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 150,000 | 10,500 |
| Congo (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 13,750 | 1,788 |
| Congo (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 67,750 | 6,098 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 145,455 | 10,182 |
| Cuba | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 14,545 | 1,018 |
| Dominican Republic (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 120,774 | 15,701 |
| Dominican Republic (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 50,050 | 4,505 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 320,935 | 22,465 |
| Dominican Republic (the) | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 44,171 | 3,092 |
| Ecuador | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 292,600 | 20,482 |
| Egypt | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 40,000 | 2,800 |
| Egypt | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 180,000 | 12,600 |
| Eritrea | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Eritrea | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Georgia | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 125,000 | 11,250 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 6,630 |
| Ghana | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 7,500 | 675 |
| Ghana | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 4,500 | 585 |
| Grenada | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,670 | 2,670 |
| Grenada | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 42,830 | 5,568 |
| India | UNDP | INV | KIP | Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial air-conditioning packaged and ducted air-conditioning units at Voltas Limited | 422,561 | 29,579 |
| India | UNDP | INV | KIP | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) | 423,765 | 29,664 |
| India | UNDP | INV | KIP | Demonstration/conversion from R-404A and R-407C to CO2 transcritical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing sector at Mech Air Industries | 322,452 | 22,572 |
| India | UNDP | PRP | KIP | Preparation of a demonstration project in the manufacture of compressors for mobile air-conditioning manufacturing sector | 30,000 | 2,100 |
| Jordan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 2,540,680 | 177,848 |
| Kenya | Germany | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kenya | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 95,000 | 12,350 |
| Kyrgyzstan | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 51,000 | 4,590 |
| Kyrgyzstan | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 30,000 | 3,900 |
| Lebanon | UNDP | PRP | PHA | Preparation of a KIP investment project in the refrigeration manufacturing sector | 70,000 | 4,900 |
| Malawi | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 39,000 | 5,070 |
| Malawi | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 29,000 | 2,610 |
| Malaysia | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 3,042,912 | 213,004 |
| Mali | UNDP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 35,000 | 2,450 |
| Mali | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 135,000 | 17,550 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 79,905 | 5,593 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 12,695 | 1,574 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring) | 283,418 | 19,839 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (foam sector plan) | 888,833 | 62,218 |
| Mexico | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 465,000 | 32,550 |
| Mexico | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 215,100 | 26,669 |
| Mexico | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 4,801,972 | 336,138 |
| Mongolia | UNIDO | PRP | KIP | Preparation of a KIP investment project in the foam sector | 80,000 | 5,600 |
| Nicaragua | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 40,000 | 5,200 |
| Nicaragua | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 159,000 | 14,310 |
| Niger (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I) | 15,000 | 1,950 |
| Niger (the) | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I) | 35,000 | 850 |
| North Macedonia | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 103,555 | 9,320 |
| Panama | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 331,100 | 23,177 |
| Peru | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 283,140 | 19,820 |
| Republic of Moldova (the) | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Saint Vincent and the Grenadines | UNEP | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 70,000 | 9,100 |
| Saint Vincent and the Grenadines | UNIDO | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 30,000 | 2,100 |
| Sri Lanka | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector | 80,000 | 5,600 |
| Thailand | IBRD | PRP | PHA | Preparation of a Kigali HFC implementation plan (stage I) | 220,000 | 15,400 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 496,973 | 34,788 |
| Trinidad and Tobago | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 46,276 | 3,239 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 106,000 | 7,420 |
| Turkmenistan | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 10,000 | 700 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 289,220 | 20,245 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 119,265 | 8,349 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 35,533 | 4,244 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 984,000 | 68,880 |
| Viet Nam | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 426,163 | 50,906 |
| Viet Nam | IBRD | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (technical assistance and policy) | 165,307 | 11,571 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bolivia (Plurinational State of) | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 96,000 | 8,640 |
| Chile | UNDP | PRP | EEF | Preparation of a pilot project for the use of R-744 (carbon dioxide) as an alternative refrigerant in heat pumps in industrial refrigeration (decision 91/65) | 30,000 | 2,100 |
| China | UNIDO | DEM | EEF | Demonstration project of replacing HFC-134a with R-744 in the field of electric vehicles (decision 91/65) | 1,371,500 | 96,005 |
| Ecuador | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 190,000 | 17,100 |
| Egypt | UNIDO | DEM | EEF | Energy efficiency pilot project in the refrigeration and air-conditioning sector (decision 91/65) | 285,000 | 19,950 |
| India | Germany | DEM | EEF | Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65) | 1,853,795 | 213,918 |
| India | UNDP | DEM | EEF | Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC-134a to propane (R-290) (technical assistance to enhance the energy efficiency of the converted equipment) (decision 91/65) | 150,000 | 13,500 |
| Kenya | Germany | PRP | EEF | Preparation for a pilot project on energy efficiency (decision 91/65) | 30,000 | 3,900 |
| Kyrgyzstan | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 206,000 | 26,780 |
| Malaysia | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in stand-alone commercial refrigeration sector (decision 91/65) | 30,000 | 2,100 |
| Mexico | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 938,620 | 65,703 |
| Nicaragua | UNEP | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Nicaragua | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 66,000 | 5,940 |
| Nigeria | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 145,000 | 13,050 |
| South Africa | UNIDO | DEM | EEF | Energy efficiency-related activities (decision 91/65) | 1,120,000 | 78,400 |
| Togo | Germany | PRP | EEF | Project preparation for energy efficiency-related activities (decision 91/65) | 30,000 | 3,900 |
| Turkmenistan | UNIDO | DEM | EEF | Pilot project for maintaining and enhancing energy efficiency of replacement technologies and equipment (decision 91/65) | 142,000 | 12,780 |
| Viet Nam | IBRD | PRP | EEF | Preparation for a pilot project on energy efficiency in the air-conditioning sector (decision 91/65) | 30,000 | 2,100 |
| Global | UNDP | PRP | EEF | Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago | 80,000 | 5,600 |

Annex III

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 93RD MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Armenia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Benin | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Bolivia (Plurinational State of) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Bolivia (Plurinational State of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Burkina Faso | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Burundi | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cameroon | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Costa Rica | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Cuba | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Dominican Republic (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Ecuador | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Egypt | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| El Salvador | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Guatemala | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Guatemala | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Honduras | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Honduras | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| Jamaica | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Kenya | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Liberia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Mexico | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Montenegro | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 4,900 |
| Namibia | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Nicaragua | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 35,000 | 4,550 |
| Nicaragua | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 55,000 | 3,850 |
| North Macedonia | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 5,600 |
| Peru | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Republic of Moldova (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Seychelles | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Togo | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Trinidad and Tobago | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Turkmenistan | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Uruguay | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Venezuela (Bolivarian Republic of) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Viet Nam | IBRD | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Yemen | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 13,000 |

UNEP/OzL.Pro/ExCom/93/1

Stage II of the HPMPs for Bolivia (Plurinational State of) (UNEP and UNIDO), Ecuador (UNIDO), Guatemala (UNEP and UNIDO), Mozambique (UNDP) and North Macedonia (UNIDO); stage III of the HPMPs for Viet Nam (World Bank); one project preparation for stage III of the HPMPs for Peru (UNDP); one project preparation for an HPMP investment project for Thailand (World Bank); one project preparation for a demonstration project for India (UNDP); five KIP preparation for investment projects for Colombia (2) (UNDP), Lebanon (UNDP), Mongolia (UNIDO) and Sri Lanka (UNDP); eight project preparation for stage I of KIPs for Brazil (Germany, UNDP and UNIDO), Kenya (Germany), Mali (UNDP and UNEP) and Saint Vincent and the Grenadines (UNEP and UNIDO); three HFC investment projects for India (UNDP); 12 energy efficiency projects under decision 89/6 for Albania (UNIDO), Benin (UNIDO), Bolivia (Plurinational State of) (UNEP and UNIDO), Ecuador (UNIDO), Grenada (UNIDO), Guatemala (UNEP and UNIDO), Lesotho (Germany), Liberia (Germany), Namibia (Germany) and Seychelles (Germany); stage I of KIPs for Bolivia (Plurinational State of) (UNEP), the Congo (UNEP and UNIDO), the Dominican Republic (UNEP and UNIDO), Kyrgyzstan (UNDP), Nicaragua (UNEP), the Niger (UNEP and UNIDO) and Peru (UNDP); IS project for Bolivia (Plurinational State of) (UNEP); and 37 project preparation for national inventories of banks of waste-controlled substances under to decision 91/66 as per annex III.

These activities include: 104 HCFC-related activities for 40 countries (US $32.37 million), 49 HFC-related activities for 34 countries (US $12.26 million) and 28 IS activities (US $9.47 million).

UNEP/OzL.Pro/ExCom/93/25

UNEP/OzL.Pro/ExCom/93/3

UNEP/OzL.Pro/ExCom/93/4 and UNEP/OzL.Pro/ExCom/93/95.

UNEP/OzL.Pro/ExCom/93/6 and UNEP/OzL.Pro/ExCom/93/47.