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PROGRESS REPORT OF BILATERAL COOPERATION AS AT 31 DECEMBER 2021

Introduction

The following non-Article 5 countries currently involved in bilateral cooperation activities submitted progress report[footnoteRef:2] databases: Australia, Canada, France, Germany, Italy, Japan, and Spain. Additional data from earlier progress reports for other non-Article 5 countries previously involved in bilateral cooperation,[footnoteRef:3] covering data for the projects already reported as financially completed, are included in the consolidated progress report.[footnoteRef:4] [2:  Progress reports are the only means for indicating the final closure of all funding accounts associated with projects approved by the Executive Committee for bilateral cooperation.]  [3:  Austria, Belgium, the Czech Republic, Denmark, Finland, Hungary, Israel, Poland, Portugal, the Russian Federation, Singapore, the Slovak Republic, South Africa, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland, and the United States of America.]  [4:  UNEP/OzL.Pro/ExCom/91/12] 

The progress report of the bilateral cooperation includes the implementation status of projects, including seven HFC-related projects funded under the additional voluntary contributions by 17 non‑Article 5 Parties to provide fast-start support for the implementation of the Kigali Amendment.
The Secretariat reviewed the status of implementation of each ongoing project on a country‑by‑country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2021, the potential impact of these delays on the phase‑out of controlled substances and the rate of planned disbursements. Therefore, the analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in CO2-eq tonnes.[footnoteRef:5] [5:  In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 91st meeting.] 

This document consists of the following sections:
[bookmark: _Hlk115854077]I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2021 and cumulative since 1992 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing[footnoteRef:6] project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. [6:  Ongoing projects are all projects that were under implementation as at 31 December 2021. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.] 

II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast‑start support for HFC phase-down.[footnoteRef:7] [7:  In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/91/12).] 

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2021 and cumulative since 1992

As of 31 December 2021, the Executive Committee had approved US $183.27 million in projects for the bilateral agencies, consisting of US $167.14 million for the implementation of investment and non‑investment projects and US $16.13 million for agency support costs, as shown in table 1. 
Table 1: Approved funding by sector for bilateral agencies as at 31 December 2021
	Sector
	Funding (US $)

	Aerosol
	2,051,914

	Destruction
	1,526,282

	Foam
	8,093,731

	Halon
	6,147,361

	HFC phase-down plan
	560,000

	Fumigants
	18,226,925

	Phase-out plan
	72,352,556

	Production
	10,000,000

	Refrigeration
	40,910,116

	Several
	4,759,718

	Solvents
	2,512,738

	Sub-total
	167,141,340

	Agency support costs
	16,130,410

	Total
	183,271,751



In 2021, 21 new projects and activities were approved. This level of funding is expected to result in the phase-out of 10,486 ODP tonnes and 70,104 CO2-eq tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2021.
Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2021.  Annex II presents analytical information per year since 1992.
Table 2. Status of project implementation by type as at 31 December 2021
	Type
	Number of projects*
	Funding (US $)**

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Country programme
	9
	9
	100
	340,787
	340,787
	0
	100

	Demonstration
	38
	38
	100
	9,409,431
	9,409,431
	0
	100

	Institutional strengthening (IS)
	7
	7
	100
	883,376
	883,376
	0
	100

	Investment
	253
	208
	82
	114,209,426
	103,155,914
	11,053,512
	90

	Project preparation
	131
	123
	94
	6,111,111
	5,466,111
	645,000
	89

	Technical assistance
	214
	205
	96
	27,765,793
	25,203,233
	2,562,561
	91

	Training projects
	73
	73
	100
	8,421,416
	8,421,416
	0
	100

	Total
	725
	[bookmark: _Hlk116163220]663
	91
	167,141,340
	152,880,268
	14,261,072
	91


* Excludes closed and transferred projects.
** Excludes agency support costs.

Implementation of projects and activities by the bilateral agencies for 2021 and cumulative since 1992 up to 31 December 2021 is summarized as follows and in table 3:
Phase-out:[footnoteRef:8] In 2021, 26.9 ODP tonnes of consumption of controlled substances were phased out[footnoteRef:9] and an additional 99.5 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1992, 9,213 ODP tonnes and 65,242 CO2-eq tonnes of consumption of controlled substances had been phased out, of an expected total of 10,486 ODP tonnes and 70,104 CO2-eq tonnes from projects approved (excluding cancelled and transferred projects); [8:  Phase-out of ODS is expressed in ODP tonnes and of HFCs in CO2-eq tonnes.]  [9:  No phase-out for HFC-related projects in 2021.] 

Disbursements/approvals: In 2021, US $3.44 million was disbursed and US $3.15 million was planned for disbursement based on the 2020 progress report, representing a rate of disbursement of 109 per cent of that planned. Cumulatively, US $152.88 million had been disbursed out of the total US $167.14 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 91 per cent. In 2021, US $4.71 million was approved for implementation;
Number of projects completed: In 2021, 14 projects were completed. Since 1992, 663 projects of the 725 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 91 per cent;
Speed of delivery – investment projects: Projects that were completed in 2021 were completed on average 57 months after their approval. Since 1992, the average time for completion of investment projects has been 41 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;
Speed of delivery – non-investment projects: Projects that were completed in 2021 were completed 51 months after their approval. Since 1992, the average time for completion of non-investment projects has been 44 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;
Project preparation: Of the 131 project preparation activities approved by the end of 2021, 123 have been completed, leaving eight ongoing activities. In 2021, one preparation activity was completed;
Implementation delays: A total of 62 projects were under implementation at the end of 2021, experiencing, on average, a delay of 18 months. Thirteen of these projects are classified as “projects with implementation delays”[footnoteRef:10] that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and [10:  Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61). ] 

Multi-year agreements (MYAs): In 2021, 28 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1992, 86 MYAs have been approved and 58 MYAs have been completed, representing a completion rate of 67 per cent.
Table 3 summarized progress made by the bilateral agencies since 1992. 
Table 3. Progress made by bilateral agencies since 1992 
	Phase out achieved
	Disbursement (US $)
	Number 
of projects
	Speed of delivery for completion (months)
	Average project delays (months)
	Number of MYAs

	ODP tonnes
	CO2-eq tonnes
	
	Approved
	Completed
	Investment
	Non- investment
	
	Approved
	Completed

	9,213
	65,242
	152,880,268
	725
	663
	41
	44
	18
	86
	58



HFC-related projects

As of 31 December 2021, the Executive Committee had approved 12 HFC-related projects (including three investment projects, four preparation projects and five enabling activities) under regular contributions amounting to US $1,614,988 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9. 
Table 4. HFC-related projects approved under regular contributions
	Type
	Number of projects
	Funding (US $)*

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Investment**
	3
	2
	67
	764,988
	664,988
	100,000
	87

	Project preparation
	4
	0
	0
	560,000
	0
	560,000
	0

	Technical assistance - Enabling activities
	5
	2
	40
	290,000
	290,000
	0
	100

	Total
	12
	4
	33
	1,614,988
	954,988
	660,000
	59


* Excludes agency support costs. 
** 45.5 mt (65,242 CO2-eq tonnes) of 48.9 mt (70,104 CO2-eq tonnes) of HFCs had been phased out.

As of the end of 2021, of the 12 projects approved, two investment projects and two enabling activities had been completed, leaving eight ongoing. Extension of the completion dates of the three ongoing enabling activities was approved; these activities are expected to be completed in 2022.
The four ongoing project preparation activities are for preparation of Kigali HFC implementation plans (KIPs) and are expected to be completed in 2023. The remaining ongoing investment project, approved at the 82nd meeting, with no funds disbursed, is expected to be completed in 2023. 
Of the total cumulative funding approved of US $1,614,988, US $954,988 had been disbursed, representing a disbursement rate of 59 per cent.
I.2	Issues identified in project implementation in 2021

Further to the review process, several issues were discussed with relevant bilateral agencies and satisfactorily addressed, except for issues on 13 projects classified as projects with implementation delays (including 12 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one HFC investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 92nd meeting.
In addition, an issue was identified in one MYA project. This outstanding issue is also presented in Annex III to the present document and a recommendation is proposed for consideration by the Executive Committee.
Details of progress in implementation of projects associated with the HPMPs for China (servicing sector plan)[footnoteRef:11] and India[footnoteRef:12] (both implemented by Germany) have been submitted to the 91st meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in Annex III to the present document, in particular, requests for extension of dates of completion, are addressed below. [11:  UNEP/OzL.Pro/ExCom/91/38]  [12:  UNEP/OzL.Pro/ExCom/91/42] 

Of the 54 ongoing projects, excluding project preparation, 21 projects have revised planned dates of completion since the 2020 progress report. 
In line with decision 82/11(b),[footnoteRef:13] the Government of Germany has requested the extension of the duration of two projects as shown in table 5. [13:  Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.] 

 Table 5. Projects for which an extension of the completion dates has been requested
	Country/Project code
	Project title
	Disburse-ment (%)
	Status/issues
	Original date of completion
	Date of completion requested

	Zimbabwe
ZIM/PHA/80/INV/54
	HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector)
	76
	Additional time required to complete remaining training of trainers activities, provide support to training institutes and for licensing of technicians and prepare related final project report
	Mar-2022
	Jun-2023

	Zimbabwe
ZIM/PHA/86/INV/62
	HCFC phase-out management plan (stage I, fifth tranche)
	0
	
	Jun-2022
	Jun-2023



II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

As of 31 December 2021, the Executive Committee had approved seven HFC-related projects for two bilateral agencies (Germany and Italy) under the additional voluntary contributions amounting to US $480,000 (excluding agency support costs). A summary of the status of these projects is presented in table 6. 
Table 6. Status of approved HFC-related projects as of the end of 2021
	Type
	Number of projects
	Funding (US $)*

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	Technical assistance (enabling activities)
	7
	5
	71
	480,000
	[bookmark: _Hlk116168493]441,835
	38,165
	92


* Excludes agency support costs.
As of the end of 2021, of the seven enabling activities approved, five had been completed. Extension of the completion dates of the two remaining ongoing projects for enabling activities was approved; one is expected to be completed in 2022 and the completion of the other is addressed in paragraph 22 below.
Of the total cumulative funding approved of US $480,000, US $441,835 had been disbursed, representing a disbursement rate of 92 per cent. 
Further to the review process, one project for enabling activities is classified as project with implementation delays and is included in Annex III to the present document containing the Secretariat’s recommendation requesting the submission of a report to the 92nd meeting. In line with decision 82/11(b), the Government of Germany has also requested a further extension of the duration of the aforementioned project, as shown in table 7.
Table 7. Project for which an extension of the completion date has been requested
	Country/Project code
	Project title
	Disburse-ment
(%)
	Status/issues
	Original date of completion
	Date of completion requested

	Liberia
LIR/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	89
	Due to COVID-19 restrictions, additional time needed for completing activities relating to the process of ratification of the Kigali Amendment
	Jun-2022
	Dec-2022



III.	Recommendation

The Executive Committee may wish:
To note, with appreciation, the progress reports submitted by the Governments of Australia, Canada, France, Germany, Italy, Japan and Spain contained in document UNEP/OzL.Pro/ExCom/91/13; 
To approve the extension of the completion date, to 30 June 2023, of the HCFC phase‑out management plan for Zimbabwe (stage I, fourth tranche – refrigeration servicing sector) (ZIM/PHA/80/INV/54) and fifth tranche (ZIM/PHA/86/INV/62), to allow for completion of the remaining ongoing activities as reflected in table 5 of document UNEP/OzL.Pro/ExCom/91/13;
To approve the extension of the completion date, to 31 December 2022, of the enabling activities for HFC phase-down for Liberia (LIR/SEV/80/TAS/01+), to allow for completion of the remaining ongoing activities as reflected in table 7 of document UNEP/OzL.Pro/ExCom/91/13; and
To approve the recommendations related to ongoing projects with specific issues contained in Annex III to the present document. 
UNEP/OzL.Pro/ExCom/91/13
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Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER COUNTRY FOR 2021

1. Table 1 of Annex I presents the status of project implementation by country for 2021 in achieved phased out, planned and achieved disbursements and project completion. 
[bookmark: _Hlk115855444]Table 1. Status of project implementation for 2021
	Country
	Phased out in 2021 (ODP tonnes)
	Phased out in 2021 (CO2-eq tonnes)*
	Estimated funds disbursed in 2021 (US$)
	Funds disbursed in 2021 (US$)
	Percentage of funds disbursed over estimation in 2021
	Percentage of planned projects completed in 2021**

	Argentina
	0.0
	
	10,000
	0
	0
	 

	Belize
	0.0
	
	40,000
	40,000
	100
	 

	Brazil
	18.0
	
	990,000
	472,431
	48
	 

	China
	0.0
	
	182,230
	151,097
	83
	0

	Colombia
	0.0
	
	0
	11,500
	Over
	 

	Cuba
	0.0
	
	0
	0
	 
	0

	Egypt
	0.0
	
	22,289
	3,181
	14
	 

	El Salvador
	0.0
	
	0
	0
	 
	100

	Ghana
	1.9
	
	34,183
	34,183
	100
	100

	India
	0.0
	
	685,796
	2,008,351
	293
	 

	Iran (Islamic Republic of)
	0.0
	
	215,553
	144,087
	67
	50

	Kenya
	0.0
	
	75,021
	49,733
	66
	 

	Lao People's Democratic Republic (the)
	0.0
	
	0
	0
	 
	0

	Lesotho
	0.0
	
	75,596
	70,134
	93
	100

	Liberia
	0.0
	
	46,212
	30,362
	66
	50

	Mauritius
	0.0
	
	42,231
	11,588
	27
	 

	Mexico
	7.0
	
	285,000
	138,202
	48
	0

	Mongolia
	0.0
	
	3,000
	772
	26
	 

	Namibia
	0.0
	
	33,443
	13,251
	40
	100

	Nigeria
	0.0
	
	70,000
	0
	0
	 

	Panama
	0.0
	
	0
	0
	 
	100

	Papua New Guinea
	0.0
	
	111,825
	144,379
	129
	50

	Seychelles
	0.0
	
	5,000
	1,070
	21
	 

	Tunisia
	0.0
	
	5,000
	0
	0
	100

	Viet Nam
	0.0
	
	152,984
	19,209
	13
	100

	Zimbabwe
	0.0
	
	64,397
	45,792
	71
	 

	Region: ASP
	0.0
	
	0
	53,000
	 Over
	 

	Grand total
	26.9
	0
	3,149,760
	3,442,322
	109
	57


* No phase-out in 2021 for HFC-related projects.
** For projects that were planned to be completed in 2021.
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Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER YEAR AS AT 31 DECEMBER 2021

1. Table 1 of Annex II presents an overview of the status of project implementation by year.[footnoteRef:14] All projects and activities approved between 1992 and 2012, have now been completed.  [14:  The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.] 

Table 1. Status of project implementation by year
	Year
	Number of projects*
	Funding (US $)**

	
	Approved
	Completed
	% completed
	Approved
	Disbursed
	Balance
	% disbursed

	1992
	18
	18
	100
	2,883,669
	2,883,669
	0
	100

	1993
	10
	10
	100
	1,445,586
	1,445,586
	0
	100

	1994
	30
	30
	100
	3,190,374
	3,190,374
	0
	100

	1995
	17
	17
	100
	4,654,902
	4,654,902
	0
	100

	1996
	26
	26
	100
	3,468,211
	3,468,211
	0
	100

	1997
	32
	32
	100
	4,040,251
	4,040,251
	0
	100

	1998
	39
	39
	100
	4,108,525
	4,108,525
	0
	100

	1999
	59
	59
	100
	12,131,407
	12,131,407
	0
	100

	2000
	29
	29
	100
	4,808,878
	4,808,878
	0
	100

	2001
	41
	41
	100
	7,523,213
	7,523,213
	0
	100

	2002
	61
	61
	100
	7,910,174
	7,910,174
	0
	100

	2003
	32
	32
	100
	6,810,120
	6,810,120
	0
	100

	2004
	30
	30
	100
	15,005,412
	15,005,412
	0
	100

	2005
	28
	28
	100
	18,183,034
	18,183,034
	0
	100

	2006
	25
	25
	100
	7,128,808
	7,128,808
	0
	100

	2007
	13
	13
	100
	3,138,440
	3,138,440
	0
	100

	2008
	33
	33
	100
	7,531,037
	7,531,037
	-1
	100

	2009
	21
	21
	100
	2,347,228
	2,347,228
	0
	100

	2010
	20
	20
	100
	3,278,389
	3,278,389
	-1
	100

	2011
	20
	20
	100
	6,821,798
	6,821,798
	0
	100

	2012
	11
	11
	100
	6,594,959
	6,594,959
	0
	100

	2013
	7
	6
	86
	2,276,412
	2,264,534
	11,878
	99

	2014
	14
	13
	93
	1,365,834
	1,351,141
	14,693
	99

	2015
	27
	25
	93
	4,921,949
	4,701,449
	220,500
	96

	2016
	16
	10
	63
	5,129,894
	3,328,893
	1,801,001
	65

	2017
	9
	3
	33
	2,605,614
	1,891,285
	714,329
	73

	2018
	16
	7
	44
	7,050,550
	4,239,588
	2,810,962
	60

	2019
	6
	2
	33
	1,941,319
	1,041,233
	900,086
	54

	2020
	14
	2
	14
	4,136,467
	953,486
	3,182,981
	23

	2021
	21
	0
	0
	4,708,887
	104,243
	4,604,644
	2

	Total
	725
	663
	91
	167,141,340
	152,880,268
	14,261,072
	91


* Excludes closed and transferred projects.
** Excludes agency support costs. 
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Annex III

ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR BILATERAL AGENCIES
	Country/project code
	Agency
	Project title
	Disbursement (%)
	Status/Issues
	Recommendation

	Lao People's Democratic Republic (the)
LAO/PHA/74/INV/28
	France
	HCFC phase-out management plan (stage I, second tranche)
	0
	18 months delays
	To request the Government of France to report to the 92nd meeting on this project with implementation delays

	Zimbabwe ZIM/REF/82/INV/56
	France
	Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare)
	0
	18 months delays
	To request the Government of France to report to the 92nd meeting on this project with implementation delays

	Brazil BRA/PHA/82/TAS/321
	Germany
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	42
	12 months delays
	To request the Government of Germany to report to the 92nd meeting on this project with implementation delays

	Liberia LIR/SEV/80/TAS/01+
	Germany
	Enabling activities for HFC phase-down
	89
	12 months delays
	To request the Government of Germany to report to the 92nd meeting on this project with implementation delays

	Mauritius
MAR/PHA/86/INV/30
	Germany
	HCFC phase-out management plan (stage I, fourth tranche)
	0
	Implementation of activities delayed
	To request the Government of Germany to provide a status report to the 92nd meeting on implementation progress and on disbursement level 

	Mexico MEX/PHA/77/INV/179
	Germany
	HCFC phase-out management plan (stage II, second tranche) (HC demonstration and training)
	12
	12 months delays
	To request the Government of Germany to report to the 92nd meeting on this project with implementation delays

	Papua New Guinea PNG/PHA/77/INV/15
	Germany
	HCFC phase-out management plan (third tranche)
	72
	12 months delays
	To request the Government of Germany to report to the 92nd meeting on this project with implementation delays

	Seychelles SEY/PHA/75/INV/23
	Germany
	HCFC phase-out management plan (stage I, third tranche)
	0
	18 months delays
	To request the Government of Germany to report to the 92nd meeting on this project with implementation delays

	Zimbabwe ZIM/PHA/86/INV/62
	Germany
	HCFC phase-out management plan (stage I, fifth tranche)
	0
	12 months delays
	To request the Government of Germany to report to the 92nd meeting on this project with implementation delays

	China CPR/PHA/77/INV/574
	Italy
	HCFC phase-out management plan (stage II, first tranche) (room air‑conditioner manufacturing sector plan)
	1
	12 months delays
	To request the Government of Italy to report to the 92nd meeting on this project with implementation delays

	Iran (Islamic Republic of)
IRA/PHA/77/INV/224
	Italy
	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	15
	12 months delays
	To request the Government of Italy to report to the 92nd meeting on this project with implementation delays 

	Iran (Islamic Republic of)
IRA/PHA/84/INV/237
	Italy
	HCFC phase-out management plan (stage II, second tranche) (foam sector)
	0
	12 and 18 months delays
	To request the Government of Italy to report to the 92nd meeting on this project with implementation delays

	Mexico MEX/PHA/73/INV/171
	Italy
	HCFC phase-out management plan (stage II, first tranche) (reclamation of HCFC refrigerants)
	97
	12 months delays
	To request the Government of Italy to report to the 92nd meeting on this project with implementation delays.

	Nigeria NIR/PHA/81/INV/151
	Italy
	HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector)
	0
	12 and 18 months delays
	To request the Government of Italy to report to the 92nd meeting on this project with implementation delays

	Nigeria NIR/PHA/81/TAS/149
	Italy
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	0
	12 and 18 months delays
	To request the Government of Italy to report to the 92nd meeting on this project with implementation delays


*Codes ending with “+” are from the additional contributions.
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