| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/91/13 9 November 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-first Meeting

Montreal, 5-9 December 2022

Item 7(a)(ii) of the provisional agenda

PROGRESS REPORT Of BILATERAL COOPERATION as at 31 december 2021

Introduction

# The following non-Article 5 countries currently involved in bilateral cooperation activities submitted progress report databases: Australia, Canada, France, Germany, Italy, Japan, and Spain. Additional data from earlier progress reports for other non-Article 5 countries previously involved in bilateral cooperation, covering data for the projects already reported as financially completed, are included in the consolidated progress report.

# The progress report of the bilateral cooperation includes the implementation status of projects, including seven HFC-related projects funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for the implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2021, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. Therefore, the analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2021 and cumulative since 1992 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2021 and cumulative since 1992

# As of 31 December 2021, the Executive Committee had approved US $183.27 million in projects for the bilateral agencies, consisting of US $167.14 million for the implementation of investment and non-investment projects and US $16.13 million for agency support costs, as shown in table 1.

Table 1: Approved funding by sector for bilateral agencies as at 31 December 2021

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 2,051,914 |
| Destruction | 1,526,282 |
| Foam | 8,093,731 |
| Halon | 6,147,361 |
| HFC phase-down plan | 560,000 |
| Fumigants | 18,226,925 |
| Phase-out plan | 72,352,556 |
| Production | 10,000,000 |
| Refrigeration | 40,910,116 |
| Several | 4,759,718 |
| Solvents | 2,512,738 |
| Sub-total | 167,141,340 |
| Agency support costs | 16,130,410 |
| Total | 183,271,751 |

# In 2021, 21 new projects and activities were approved. This level of funding is expected to result in the phase-out of 10,486 ODP tonnes and 70,104 CO2-eq tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2021.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2021.  Annex II presents analytical information per year since 1992.

Table 2. Status of project implementation by type as at 31 December 2021

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 9 | 9 | 100 | 340,787 | 340,787 | 0 | 100 |
| Demonstration | 38 | 38 | 100 | 9,409,431 | 9,409,431 | 0 | 100 |
| Institutional strengthening (IS) | 7 | 7 | 100 | 883,376 | 883,376 | 0 | 100 |
| Investment | 253 | 208 | 82 | 114,209,426 | 103,155,914 | 11,053,512 | 90 |
| Project preparation | 131 | 123 | 94 | 6,111,111 | 5,466,111 | 645,000 | 89 |
| Technical assistance | 214 | 205 | 96 | 27,765,793 | 25,203,233 | 2,562,561 | 91 |
| Training projects | 73 | 73 | 100 | 8,421,416 | 8,421,416 | 0 | 100 |
| Total | 725 | 663 | 91 | 167,141,340 | 152,880,268 | 14,261,072 | 91 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by the bilateral agencies for 2021 and cumulative since 1992 up to 31 December 2021 is summarized as follows and in table 3:

## Phase-out: In 2021, 26.9 ODP tonnes of consumption of controlled substances were phased out and an additional 99.5 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1992, 9,213 ODP tonnes and 65,242 CO2-eq tonnes of consumption of controlled substances had been phased out, of an expected total of 10,486 ODP tonnes and 70,104 CO2-eq tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2021, US $3.44 million was disbursed and US $3.15 million was planned for disbursement based on the 2020 progress report, representing a rate of disbursement of 109 per cent of that planned. Cumulatively, US $152.88 million had been disbursed out of the total US $167.14 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 91 per cent. In 2021, US $4.71 million was approved for implementation;

## Number of projects completed: In 2021, 14 projects were completed. Since 1992, 663 projects of the 725 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 91 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2021 were completed on average 57 months after their approval. Since 1992, the average time for completion of investment projects has been 41 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2021 were completed 51 months after their approval. Since 1992, the average time for completion of non-investment projects has been 44 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 131 project preparation activities approved by the end of 2021, 123 have been completed, leaving eight ongoing activities. In 2021, one preparation activity was completed;

## Implementation delays: A total of 62 projects were under implementation at the end of 2021, experiencing, on average, a delay of 18 months. Thirteen of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2021, 28 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1992, 86 MYAs have been approved and 58 MYAs have been completed, representing a completion rate of 67 per cent.

# Table 3 summarized progress made by the bilateral agencies since 1992.

## Table 3. Progress made by bilateral agencies since 1992

| Phase out achieved |  | Disbursement (US $) | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes |  | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 9,213 | 65,242 | 152,880,268 | 725 | 663 | 41 | 44 | 18 | 86 | 58 |

HFC-related projects

# As of 31 December 2021, the Executive Committee had approved 12 HFC-related projects (including three investment projects, four preparation projects and five enabling activities) under regular contributions amounting to US $1,614,988 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 2 | 67 | 764,988 | 664,988 | 100,000 | 87 |
| Project preparation | 4 | 0 | 0 | 560,000 | 0 | 560,000 | 0 |
| Technical assistance - Enabling activities | 5 | 2 | 40 | 290,000 | 290,000 | 0 | 100 |
| Total | 12 | 4 | 33 | 1,614,988 | 954,988 | 660,000 | 59 |

* Excludes agency support costs.

** 45.5 mt (65,242 CO2-eq tonnes) of 48.9 mt (70,104 CO2-eq tonnes) of HFCs had been phased out.

# As of the end of 2021, of the 12 projects approved, two investment projects and two enabling activities had been completed, leaving eight ongoing. Extension of the completion dates of the three ongoing enabling activities was approved; these activities are expected to be completed in 2022.

# The four ongoing project preparation activities are for preparation of Kigali HFC implementation plans (KIPs) and are expected to be completed in 2023. The remaining ongoing investment project, approved at the 82nd meeting, with no funds disbursed, is expected to be completed in 2023.

# Of the total cumulative funding approved of US $1,614,988, US $954,988 had been disbursed, representing a disbursement rate of 59 per cent.

I.2	Issues identified in project implementation in 2021

# Further to the review process, several issues were discussed with relevant bilateral agencies and satisfactorily addressed, except for issues on 13 projects classified as projects with implementation delays (including 12 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one HFC investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 92nd meeting.

# In addition, an issue was identified in one MYA project. This outstanding issue is also presented in Annex III to the present document and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for China (servicing sector plan) and India (both implemented by Germany) have been submitted to the 91st meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in Annex III to the present document, in particular, requests for extension of dates of completion, are addressed below.

# Of the 54 ongoing projects, excluding project preparation, 21 projects have revised planned dates of completion since the 2020 progress report.

# In line with decision 82/11(b), the Government of Germany has requested the extension of the duration of two projects as shown in table 5.

# Table 5. Projects for which an extension of the completion dates has been requested

| Country/Project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Zimbabwe ZIM/PHA/80/INV/54 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector) | 76 | Additional time required to complete remaining training of trainers activities, provide support to training institutes and for licensing of technicians and prepare related final project report | Mar-2022 | Jun-2023 |
| Zimbabwe ZIM/PHA/86/INV/62 | HCFC phase-out management plan (stage I, fifth tranche) | 0 |  | Jun-2022 | Jun-2023 |

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2021, the Executive Committee had approved seven HFC-related projects for two bilateral agencies (Germany and Italy) under the additional voluntary contributions amounting to US $480,000 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2021

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance (enabling activities) | 7 | 5 | 71 | 480,000 | 441,835 | 38,165 | 92 |

* Excludes agency support costs.

# As of the end of 2021, of the seven enabling activities approved, five had been completed. Extension of the completion dates of the two remaining ongoing projects for enabling activities was approved; one is expected to be completed in 2022 and the completion of the other is addressed in paragraph 22 below.

# Of the total cumulative funding approved of US $480,000, US $441,835 had been disbursed, representing a disbursement rate of 92 per cent.

# Further to the review process, one project for enabling activities is classified as project with implementation delays and is included in Annex III to the present document containing the Secretariat’s recommendation requesting the submission of a report to the 92nd meeting. In line with decision 82/11(b), the Government of Germany has also requested a further extension of the duration of the aforementioned project, as shown in table 7.

Table 7. Project for which an extension of the completion date has been requested

| Country/Project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Liberia LIR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 89 | Due to COVID-19 restrictions, additional time needed for completing activities relating to the process of ratification of the Kigali Amendment | Jun-2022 | Dec-2022 |

III.	Recommendation

# The Executive Committee may wish:

## To note, with appreciation, the progress reports submitted by the Governments of Australia, Canada, France, Germany, Italy, Japan and Spain contained in document UNEP/OzL.Pro/ExCom/91/13;

## To approve the extension of the completion date, to 30 June 2023, of the HCFC phase-out management plan for Zimbabwe (stage I, fourth tranche – refrigeration servicing sector) (ZIM/PHA/80/INV/54) and fifth tranche (ZIM/PHA/86/INV/62), to allow for completion of the remaining ongoing activities as reflected in table 5 of document UNEP/OzL.Pro/ExCom/91/13;

## To approve the extension of the completion date, to 31 December 2022, of the enabling activities for HFC phase-down for Liberia (LIR/SEV/80/TAS/01+), to allow for completion of the remaining ongoing activities as reflected in table 7 of document UNEP/OzL.Pro/ExCom/91/13; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER COUNTRY FOR 2021

# Table 1 of Annex I presents the status of project implementation by country for 2021 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation for 2021

| Country | Phased out in 2021 (ODP tonnes) | Phased out in 2021 (CO2-eq tonnes)* | Estimated funds disbursed in 2021 (US$) | Funds disbursed in 2021 (US$) | Percentage of funds disbursed over estimation in 2021 | Percentage of planned projects completed in 2021** |
| --- | --- | --- | --- | --- | --- | --- |
| Argentina | 0.0 |  | 10,000 | 0 | 0 |  |
| Belize | 0.0 |  | 40,000 | 40,000 | 100 |  |
| Brazil | 18.0 |  | 990,000 | 472,431 | 48 |  |
| China | 0.0 |  | 182,230 | 151,097 | 83 | 0 |
| Colombia | 0.0 |  | 0 | 11,500 | Over |  |
| Cuba | 0.0 |  | 0 | 0 |  | 0 |
| Egypt | 0.0 |  | 22,289 | 3,181 | 14 |  |
| El Salvador | 0.0 |  | 0 | 0 |  | 100 |
| Ghana | 1.9 |  | 34,183 | 34,183 | 100 | 100 |
| India | 0.0 |  | 685,796 | 2,008,351 | 293 |  |
| Iran (Islamic Republic of) | 0.0 |  | 215,553 | 144,087 | 67 | 50 |
| Kenya | 0.0 |  | 75,021 | 49,733 | 66 |  |
| Lao People's Democratic Republic (the) | 0.0 |  | 0 | 0 |  | 0 |
| Lesotho | 0.0 |  | 75,596 | 70,134 | 93 | 100 |
| Liberia | 0.0 |  | 46,212 | 30,362 | 66 | 50 |
| Mauritius | 0.0 |  | 42,231 | 11,588 | 27 |  |
| Mexico | 7.0 |  | 285,000 | 138,202 | 48 | 0 |
| Mongolia | 0.0 |  | 3,000 | 772 | 26 |  |
| Namibia | 0.0 |  | 33,443 | 13,251 | 40 | 100 |
| Nigeria | 0.0 |  | 70,000 | 0 | 0 |  |
| Panama | 0.0 |  | 0 | 0 |  | 100 |
| Papua New Guinea | 0.0 |  | 111,825 | 144,379 | 129 | 50 |
| Seychelles | 0.0 |  | 5,000 | 1,070 | 21 |  |
| Tunisia | 0.0 |  | 5,000 | 0 | 0 | 100 |
| Viet Nam | 0.0 |  | 152,984 | 19,209 | 13 | 100 |
| Zimbabwe | 0.0 |  | 64,397 | 45,792 | 71 |  |
| Region: ASP | 0.0 |  | 0 | 53,000 | Over |  |
| Grand total | 26.9 | 0 | 3,149,760 | 3,442,322 | 109 | 57 |

* No phase-out in 2021 for HFC-related projects.

** For projects that were planned to be completed in 2021.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER YEAR AS AT 31 DECEMBER 2021

# Table 1 of Annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1992 and 2012, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1992 | 18 | 18 | 100 | 2,883,669 | 2,883,669 | 0 | 100 |
| 1993 | 10 | 10 | 100 | 1,445,586 | 1,445,586 | 0 | 100 |
| 1994 | 30 | 30 | 100 | 3,190,374 | 3,190,374 | 0 | 100 |
| 1995 | 17 | 17 | 100 | 4,654,902 | 4,654,902 | 0 | 100 |
| 1996 | 26 | 26 | 100 | 3,468,211 | 3,468,211 | 0 | 100 |
| 1997 | 32 | 32 | 100 | 4,040,251 | 4,040,251 | 0 | 100 |
| 1998 | 39 | 39 | 100 | 4,108,525 | 4,108,525 | 0 | 100 |
| 1999 | 59 | 59 | 100 | 12,131,407 | 12,131,407 | 0 | 100 |
| 2000 | 29 | 29 | 100 | 4,808,878 | 4,808,878 | 0 | 100 |
| 2001 | 41 | 41 | 100 | 7,523,213 | 7,523,213 | 0 | 100 |
| 2002 | 61 | 61 | 100 | 7,910,174 | 7,910,174 | 0 | 100 |
| 2003 | 32 | 32 | 100 | 6,810,120 | 6,810,120 | 0 | 100 |
| 2004 | 30 | 30 | 100 | 15,005,412 | 15,005,412 | 0 | 100 |
| 2005 | 28 | 28 | 100 | 18,183,034 | 18,183,034 | 0 | 100 |
| 2006 | 25 | 25 | 100 | 7,128,808 | 7,128,808 | 0 | 100 |
| 2007 | 13 | 13 | 100 | 3,138,440 | 3,138,440 | 0 | 100 |
| 2008 | 33 | 33 | 100 | 7,531,037 | 7,531,037 | -1 | 100 |
| 2009 | 21 | 21 | 100 | 2,347,228 | 2,347,228 | 0 | 100 |
| 2010 | 20 | 20 | 100 | 3,278,389 | 3,278,389 | -1 | 100 |
| 2011 | 20 | 20 | 100 | 6,821,798 | 6,821,798 | 0 | 100 |
| 2012 | 11 | 11 | 100 | 6,594,959 | 6,594,959 | 0 | 100 |
| 2013 | 7 | 6 | 86 | 2,276,412 | 2,264,534 | 11,878 | 99 |
| 2014 | 14 | 13 | 93 | 1,365,834 | 1,351,141 | 14,693 | 99 |
| 2015 | 27 | 25 | 93 | 4,921,949 | 4,701,449 | 220,500 | 96 |
| 2016 | 16 | 10 | 63 | 5,129,894 | 3,328,893 | 1,801,001 | 65 |
| 2017 | 9 | 3 | 33 | 2,605,614 | 1,891,285 | 714,329 | 73 |
| 2018 | 16 | 7 | 44 | 7,050,550 | 4,239,588 | 2,810,962 | 60 |
| 2019 | 6 | 2 | 33 | 1,941,319 | 1,041,233 | 900,086 | 54 |
| 2020 | 14 | 2 | 14 | 4,136,467 | 953,486 | 3,182,981 | 23 |
| 2021 | 21 | 0 | 0 | 4,708,887 | 104,243 | 4,604,644 | 2 |
| Total | 725 | 663 | 91 | 167,141,340 | 152,880,268 | 14,261,072 | 91 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR BILATERAL AGENCIES

| Country/project code | Agency | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Lao People's Democratic Republic (the) LAO/PHA/74/INV/28 | France | HCFC phase-out management plan (stage I, second tranche) | 0 | 18 months delays | To request the Government of France to report to the 92nd meeting on this project with implementation delays |
| Zimbabwe ZIM/REF/82/INV/56 | France | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) | 0 | 18 months delays | To request the Government of France to report to the 92nd meeting on this project with implementation delays |
| Brazil BRA/PHA/82/TAS/321 | Germany | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 42 | 12 months delays | To request the Government of Germany to report to the 92nd meeting on this project with implementation delays |
| Liberia LIR/SEV/80/TAS/01+ | Germany | Enabling activities for HFC phase-down | 89 | 12 months delays | To request the Government of Germany to report to the 92nd meeting on this project with implementation delays |
| Mauritius MAR/PHA/86/INV/30 | Germany | HCFC phase-out management plan (stage I, fourth tranche) | 0 | Implementation of activities delayed | To request the Government of Germany to provide a status report to the 92nd meeting on implementation progress and on disbursement level |
| Mexico MEX/PHA/77/INV/179 | Germany | HCFC phase-out management plan (stage II, second tranche) (HC demonstration and training) | 12 | 12 months delays | To request the Government of Germany to report to the 92nd meeting on this project with implementation delays |
| Papua New Guinea PNG/PHA/77/INV/15 | Germany | HCFC phase-out management plan (third tranche) | 72 | 12 months delays | To request the Government of Germany to report to the 92nd meeting on this project with implementation delays |
| Seychelles SEY/PHA/75/INV/23 | Germany | HCFC phase-out management plan (stage I, third tranche) | 0 | 18 months delays | To request the Government of Germany to report to the 92nd meeting on this project with implementation delays |
| Zimbabwe ZIM/PHA/86/INV/62 | Germany | HCFC phase-out management plan (stage I, fifth tranche) | 0 | 12 months delays | To request the Government of Germany to report to the 92nd meeting on this project with implementation delays |
| China CPR/PHA/77/INV/574 | Italy | HCFC phase-out management plan (stage II, first tranche) (room air-conditioner manufacturing sector plan) | 1 | 12 months delays | To request the Government of Italy to report to the 92nd meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/77/INV/224 | Italy | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 15 | 12 months delays | To request the Government of Italy to report to the 92nd meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/INV/237 | Italy | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 0 | 12 and 18 months delays | To request the Government of Italy to report to the 92nd meeting on this project with implementation delays |
| Mexico MEX/PHA/73/INV/171 | Italy | HCFC phase-out management plan (stage II, first tranche) (reclamation of HCFC refrigerants) | 97 | 12 months delays | To request the Government of Italy to report to the 92nd meeting on this project with implementation delays. |
| Nigeria NIR/PHA/81/INV/151 | Italy | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 0 | 12 and 18 months delays | To request the Government of Italy to report to the 92nd meeting on this project with implementation delays |
| Nigeria NIR/PHA/81/TAS/149 | Italy | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 0 | 12 and 18 months delays | To request the Government of Italy to report to the 92nd meeting on this project with implementation delays |

*Codes ending with “+” are from the additional contributions.

UNEP/OzL.Pro/ExCom/91/1

# Progress reports are the only means for indicating the final closure of all funding accounts associated with projects approved by the Executive Committee for bilateral cooperation.

# Austria, Belgium, the Czech Republic, Denmark, Finland, Hungary, Israel, Poland, Portugal, the Russian Federation, Singapore, the Slovak Republic, South Africa, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland, and the United States of America.

UNEP/OzL.Pro/ExCom/91/12

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 91st meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2021. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/91/12).

Phase-out of ODS is expressed in ODP tonnes and of HFCs in CO2-eq tonnes.

No phase-out for HFC-related projects in 2021.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/91/38

UNEP/OzL.Pro/ExCom/91/42

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.