| NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/92/4 9 de mayo de 2023 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
 PARA LA APLICACIÓN DEL
 PROTOCOLO DE MONTREAL
Nonagésima segunda reunión

Montreal, 29 de mayo – 2 de junio de 2023
Cuestión 4 b) del orden del día provisional

# INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS

# Introducción

- Este documento presenta un resumen de los ajustes financieros indicados por los organismos de ejecución de conformidad con lo convenido por la Secretaría del Fondo. Incluye datos estadísticos de todos los proyectos con saldos que se han retenido durante más de 12 meses después de la terminación del proyecto, de conformidad con lo dispuesto en las decisiones 28/7 y 56/2 c). Se ocupa de los saldos que habrán de devolverse de los proyectos como seguimiento a las decisiones pertinentes (mencionados como proyectos “por decisión” en el presente documento) y transferencias de proyectos. Indica también el nivel de recursos de que dispone el Comité Ejecutivo en efectivo según lo registrado en el documento sobre la situación de las contribuciones y los desembolsos, como se requiere en la decisión 41/92 b), y presenta una recomendación. Los montos que retienen los organismos de ejecución para proyectos terminados, para proyectos “por decisión” y para proyectos financiados con contribuciones voluntarias adicionales se incluyen en el Anexo I, el Anexo II y el Anexo III, respectivamente. El Anexo IV presenta los fondos devueltos por los organismos de ejecución de proyectos terminados y de proyectos financiados con contribuciones voluntarias adicionales.

Fondos que los organismos de ejecución han de devolver a la 92ª reunión

# El monto total de los fondos que se han de devolver asciende a 2 508 725 $EUA de proyectos terminados, proyectos “por decisión” y proyectos financiados con contribuciones voluntarias adicionales, tal como figura en el cuadro 1.

# Cuadro 1. Fondos que los organismos de ejecución han de devolver a la 92ª reunión ($EUA)

| Organismo | Costos del proyecto | Gastos de apoyo al organismo | Costo total |
| --- | --- | --- | --- |
| PNUD | 334 630 | 23 485 | 358 115 |
| PNUMA | 277 372 | 17 732 | 295 104 |
| ONUDI | 1 728 863 | 123 876 | 1 852 740 |
| Banco Mundial | 2 586 | 181 | 2 767 |
| Total | 2 343 451 | 165 274 | 2 508 725 |

Fondos en poder de los organismos de ejecución

# En el cuadro 2 se presenta información sobre los saldos de los proyectos terminados, proyectos “por decisión” y proyectos financiados con contribuciones voluntarias adicionales que aún están en poder de los organismos de ejecución.

Cuadro 2. Saldos de proyectos terminados, proyectos “por decisión” y proyectos financiados con contribuciones voluntarias adicionales en poder de los organismos de ejecución (incluidos gastos de apoyo a los organismos)

| Año de terminación | PNUD |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Cantidad | ($EUA) | Cantidad | ($EUA) | Cantidad | ($EUA) |
| Proyectos terminados hace más de dos años |  |  |  |  |  |  |
| 2019 | 2 | 8 332 | 0 | 0 | 2 | 8 332 |
| 2020 | 1 | 40 434 | 0 | 0 | 1 | 40 434 |
| 1 ene. a 30 abril 2021 | 2 | 1 477 | 0 | 0 | 2 | 1 477 |
| Subtotal | 5 | 50 243 | 0 | 0 | 5 | 50 243 |
| Proyectos terminados hace menos de dos años |  |  |  |  |  |  |
| 1 mayo a 31 dic. 2021 | 24 | 727 722 | 9 | 84 953 | 33 | 812 675 |
| En curso |  |  | 1 | 120 612 | 1 | 120 612 |
| Subtotal | 24 | 727 722 | 10 | 205 565 | 34 | 933 287 |
| Total | 29 | 777 965 | 10 | 205 565 | 39 | 983 530 |
| Proyectos “por decisión” |  |  |  |  |  |  |
|  | 1 | 20 012 | 11 | 845 599 | 12 | 865 611 |
| Proyectos financiados con contribuciones voluntarias adicionales |  |  |  |  |  |  |
|  | 1 | 23 411 | 2 | 119 069 | 3 | 142 480 |
| Total general | 31 | 821 388 | 23 | 1 170 233 | 54 | 1 991 621 |

Transferencias de proyectos

# El Gobierno de la República Islámica de Irán solicitó a la Secretaría del Fondo que transfiriera al PNUD el saldo restante de los proyectos asociados con la etapa II del plan de gestión de eliminación de HCFC (PGEH) y la preparación de la etapa III del HPMP, actualmente ejecutados por el Gobierno de Alemania. El monto total que el Gobierno de Alemania devolverá al Fondo es de 866 272 $EUA, más los gastos de apoyo al organismo de 99 019 $EUA. La transferencia al PNUD de 866 272 $EUA implicaría menores gastos de apoyo al organismo, que ascienden a 60 639 $EUA.

# El Gobierno de Turkmenistán solicitó a la Secretaría del Fondo que transfiriera del PNUMA a la ONUDI el saldo restante de la preparación de proyectos del plan de ejecución relativo a los HFC conforme a la Enmienda de Kigali (KIP) por un monto de 10 000 $EUA, más gastos de apoyo al organismo de 1 300 $EUA. La transferencia a la ONUDI de 10 000 $EUA implicaría menores gastos de apoyo al organismo, que ascienden a 700 $EUA.

# El Gobierno de Jordania solicitó a la Secretaría del Fondo que transfiriera del Banco Mundial a la ONUDI el saldo restante de la preparación del proyecto de la etapa III del plan de gestión de eliminación de HCFC (general) por un monto de 35 000 $EUA, más gastos de apoyo de 2 450 $EUA.

# En el cuadro 3 figura información detallada sobre los saldos que se han de transferir. El Comité Ejecutivo podrá considerar oportuno aprobar dichas solicitudes.

Cuadro 3. Saldos de proyectos que se han de transferir

| Título del proyecto | Proyecto N.º | Devolver |  |  | Transferir |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Al Fondo Multilateral |  |  | Al organismo |  |  |
|  |  | De | Saldo | GAP | A | Saldo | GAP |
| PGEH para la República Islámica del Irán (etapa II) | IRA/PHA/84/INV/236 | Alemania | 93 017 | 10 580 | PNUD | 93 017 | 6 511 |
|  | IRA/PHA/86/INV/250 | Alemania | 145 255 | 16 521 | PNUD | 145 255 | 10 168 |
|  | IRA/PHA/90/INV/259 | Alemania | 502 500 | 57 156 | PNUD | 502 500 | 35 175 |
|  | IRA/PHA/90/INV/260 | Alemania | 95 500 | 10 862 | PNUD | 95 500 | 6 685 |
| Preparación del PGEH para la República Islámica del Irán (etapa III) | IRA/PHA/87/PRP/251 | Alemania | 5 000 | 650 | PNUD | 5 000 | 350 |
|  | IRA/PHA/87/PRP/252 | Alemania | 25 000 | 3 250 | PNUD | 25 000 | 1 750 |
| Preparación del KIP para Turkmenistán | TKM/KIP/87/PRP/87 | PNUMA | 10 000 | 1 300 | ONUDI | 10 000 | 700 |
| Preparación del PGEH para Jordania (etapa III)(general) | JOR/PHA/88/PRP/110 | Banco Mundial | 35 000 | 2 450 | ONUDI | 35 000 | 2 450 |
| Total |  |  | 911 272 | 102 769 |  | 911 272 | 63 789 |

Disponibilidad de recursos

# La situación de las contribuciones y los desembolsos indica un saldo disponible de 485 059 124 $EUA al 9 de mayo de 2023. El saldo total que los organismos de ejecución devuelven a la 92ª reunión asciende a 2 508 725 $EUA. Por lo tanto, excluyendo la cantidad de 246 millones de $EUA por concepto de saldos del trienio 2018-2020 y que se utilizará después de 2023, el nivel total de los recursos disponibles para aprobaciones en la 92ª reunión asciende a 241 567 849 $EUA.

# Observaciones de la Secretaría

# La Secretaría recordó a los organismos de ejecución que los saldos de los proyectos “por decisión”, los proyectos terminados con un año de anterioridad o más y los proyectos financiados con contribuciones voluntarias adicionales deberían devolverse al Fondo Multilateral tan pronto como fuera posible.

# Considerando que el nivel total de fondos para proyectos y actividades presentados a la 92ª reunión al 9 de mayo de 2023 asciende a 31 154 966 $EUA, los recursos disponibles son suficientes para las aprobaciones previstas para la 92ª reunión.

Recomendación

# El Comité Ejecutivo tal vez desee:

  - Tomar nota de lo siguiente:

- El informe sobre los saldos y la disponibilidad de recursos que figura en el documento UNEP/OzL.Pro/ExCom/92/4;

- Que el volumen neto de fondos que los organismos de ejecución reintegran a la 92ª reunión asciende a un total de 2 508 725 $EUA, de los cuales 334 630 $EUA, más gastos de apoyo de 23 485 $EUA que reintegra el PNUD; 277 372 $EUA, más gastos de apoyo de 17 732 $EUA que reintegra el PNUMA; 1 728 863 $EUA, más gastos de apoyo de 123 876 $EUA que reintegra la ONUDI, y 2 586 $EUA, más gastos de apoyo de 181 $EUA que reintegra el Banco Mundial;

- Que el PNUD tenía en su haber saldos de 50 243 $EUA, incluidos gastos de apoyo al organismo, por concepto de cinco proyectos terminados hace más de dos años, y de 20 012 $EUA, incluidos gastos de apoyo al organismo, por concepto de un proyecto terminado “por decisión del Comité Ejecutivo”, y de 23 411 $EUA, incluidos gastos de apoyo al organismo, por concepto de un proyecto financiado con cargo a las contribuciones voluntarias adicionales hechas por un grupo de países donantes para financiar actividades de apoyo inmediato a la reducción de los HFC;

- Que la ONUDI mantenía a su haber saldos de 119 069 $EUA, incluyendo gastos de apoyo al organismo, por concepto de dos proyectos financiado con las contribuciones voluntarias adicionales hechas por un grupo de países donantes para financiar actividades de apoyo inmediato a la reducción de los HFC;

## Solicitar:

### A los organismos de ejecución proceder al desembolso o cancelación de los fondos comprometidos y no comprometidos que ya no se precisen para proyectos terminados o para aquellos terminados “por decisión del Comité Ejecutivo”, y reintegrar los saldos respectivos a la 93ª reunión;

### Al PNUD, proceder al desembolso o cancelación de sus compromisos respecto de los restantes proyectos terminados hace más de dos años y reintegrar los saldos respectivos a la 93ª reunión;

### Al PNUD y a la ONUDI, proceder al desembolso o reintegro a la 93ª reunión de los saldos restantes por concepto de proyectos terminados financiados por contribuciones voluntarias adicionales;

### Al Gobierno de Alemania, proceder al reintegro a la 92ª reunión los saldos restantes por concepto de la etapa II del plan de gestión de eliminación de HCFC (PGEH) para la República Islámica del Irán, por la suma de 836 272 $EUA, más gastos de apoyo al organismo de 95 119 $EUA, que consiste en:

93 017 $EUA, más gastos de apoyo al organismo de 10 580 $EUA del segundo tramo (IRA/PHA/84/INV/236);

145 255 $EUA, más gastos de apoyo al organismo de 16 521 $EUA del tercer tramo (IRA/PHA/86/INV/250);

502 500 $EUA, más gastos de apoyo al organismo de 57 156 $EUA y 95 500 $EUA, más gastos de apoyo al organismo de 10 862 $EUA, del cuarto tramo (IRA/PHA/90/INV/259 e IRA/PHA/90/INV/260, respectivamente);

### Que el Tesorero transfiera, en la 92ª reunión, al PNUD los fondos devueltos por concepto de los proyectos mencionados en el apartado b) iv) anterior para su ejecución, por un monto de 836 272 $EUA, más gastos de apoyo al organismo de 58 539 $EUA, que consiste en:

- 93 017 $EUA, más gastos de apoyo al organismo de 6 511 $EUA para el segundo tramo (IRA/PHA/84/INV/236);

145 255 $EUA, más gastos de apoyo al organismo de 10 168 $EUA para el tercer tramo (IRA/PHA/86/INV/250);

502 500 $EUA, más gastos de apoyo al organismo de 35 175 $EUA, y 95 500 $EUA, más gastos de apoyo al organismo de 6 685 $EUA para el cuarto tramo (IRA/PHA/90/INV/259 e IRA/PHA/90/INV/260, respectivamente);

### Que el Gobierno de Alemania devuelva, en la 92ª reunión, el saldo por concepto de la preparación de la etapa III del plan de gestión de eliminación de HCFC para la República Islámica del Irán, por un monto de 30 000 $EUA, más gastos de apoyo al organismo de 3 900 $EUA, que consiste en:

- 5 000 $EUA, más gastos de apoyo al organismo de 650 $EUA, de la preparación de la estrategia general (IRA/PHA/87/PRP/251);

- 25 000 $EUA, más gastos de apoyo al organismo de 3 250 $EUA, de la preparación de actividades de inversión en el sector de refrigeración industrial y aire acondicionado (IRA/PHA/87/PRP/252);

### Que en la 92ª reunión el Tesorero transfiera al PNUD los fondos devueltos para los proyectos a los que se hace referencia en el apartado b) vi) anterior para su ejecución, por un monto de 30 000 $EUA, más gastos de apoyo al organismo de 2 100 $EUA, que consiste en:

- 5 000 $EUA, más gastos de apoyo al organismo de 350 $EUA para la preparación de la estrategia general (IRA/PHA/87/PRP/251);

- 25 000 $EUA, más gastos de apoyo al organismo de 1 750 $EUA para la preparación de actividades de inversión en el sector de refrigeración industrial y aire acondicionado (IRA/PHA/87/PRP/252);

### Que el PNUMA devuelva en la 92ª reunión el saldo de la preparación del plan de ejecución relativo a los HFC conforme a la Enmienda de Kigali (KIP) para Turkmenistán (TKM/KIP/87/PRP/18) por un monto de 10 000 $EUA, más gastos de apoyo al organismo de 1 300 $EUA;

### Que en la 92ª reunión el Tesorero transfiera a la ONUDI los fondos devueltos para el proyecto mencionado en el apartado b) viii) anterior para su ejecución, por un monto de 10 000 $EUA, más gastos de apoyo al organismo de 700 $EUA;

### Que el Banco Mundial devuelva en la 92ª reunión el saldo de la preparación de la etapa III del plan de gestión de eliminación de HCFC para Jordania (general) (JOR/PHA/88/PRP/110) por un monto de 35 000 $EUA, más gastos de apoyo al organismo de 2 450 $EUA;

### Que en la 92ª reunión el Tesorero transfiera a la ONUDI los fondos devueltos para el proyecto mencionado en el apartado b) x) anterior para su ejecución, por un monto de 35 000 $EUA y gastos de apoyo al organismo de 2 450 $EUA.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2021 (US $) | Funds disbursed as of 92nd meeting (US $) | Balances committed as per 92nd meeting (US $) | Balances not-committed as per 92nd meeting (US $) | Support cost on balances committed and not committed as per 92nd meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/84/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 7,391 | 22,609 |  | 2,035 |  |  |  |
| BZE/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 8,750 | 1,250 |  | 87 |  |  |  |
| CHI/SEV/83/INS/198 | Extension of the institutional strengthening project (phase XIII: 7/2019-6/2021) | Dec-21 | 238,784 | 238,615 | 169 |  | 12 |  |  |  |
| COL/PHA/81/INV/102 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Dec-21 | 1,137,247 | 594,285 | 542,962 |  | 38,007 |  |  |  |
| COL/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 11/2017-10/2019) | Jul-21 | 352,768 | 351,995 | 773 |  | 54 |  |  |  |
| COS/SEV/84/INS/62 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Dec-21 | 179,857 | 179,495 | 362 |  | 25 |  |  |  |
| CUB/PHA/82/PRP/61 | Preparation of a HCFC phase-out management plan (stage II) | Oct-21 | 60,000 | 38,281 | 21,719 |  | 1,520 |  |  |  |
| CUB/SEV/81/TAS/57 | Enabling activities for HFC phase-down | Dec-21 | 75,000 | 71,408 | 3,592 |  | 251 |  |  |  |
| DOM/PHA/83/PRP/68 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 47,408 | 12,592 |  | 881 |  |  |  |
| DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 17,143 | 12,931 | 4,212 |  | 295 |  |  |  |
| ELS/PHA/79/TAS/36 | Verification report for stage I of HCFC phase-out management plan | Jun-21 | 30,000 | 29,165 | 835 |  | 75 |  |  |  |
| ELS/SEV/81/TAS/37 | Enabling activities for HFC phase-down | Sep-21 | 100,000 | 99,478 | 523 |  | 37 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 54,065 | 5,785 |  | 521 |  |  |  |
| FIJ/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 30,000 | 26,442 | 3,558 |  | 249 |  |  |  |
| GHA/PHA/84/INV/48 | HCFC phase-out management plan (stage I, sixth tranche) | Dec-21 | 121,311 | 116,236 | 5,075 |  | 381 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 157,857 | 1,893 |  | 133 |  |  |  |
| HAI/SEV/84/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 95,000 | 90,311 | 4,689 |  | 328 |  |  |  |
| IND/SEV/84/INS/478 | Extension of institutional strengthening project (phase XII: 12/2019-11/2021) | Nov-21 | 477,734 | 476,187 | 1,547 |  | 108 |  |  |  |
| IRA/SEV/82/INS/231 | Extension of the institutional strengthening project (phase XII: 4/2019-3/2021) | Mar-21 | 222,094 | 221,620 | 474 |  | 33 |  |  |  |
| JAM/PHA/81/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Jul-21 | 40,000 | 33,501 | 6,499 |  | 455 |  |  |  |
| JAM/PHA/84/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 26,579 | 3,421 |  | 308 |  |  |  |
| JAM/PHA/85/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-21 | 58,000 | 54,898 | 3,102 |  | 233 |  |  |  |
| MAL/SEV/84/INS/188 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Dec-21 | 357,760 | 357,322 | 438 |  | 31 |  |  |  |
| MOL/PHA/86/INV/43 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 17,450 | 0 | 17,450 |  | 1,570 |  |  |  |
| PAN/PHA/83/PRP/49 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 42,695 | 17,305 |  | 1,211 |  |  |  |
| PAN/SEV/81/TAS/46 | Enabling activities for HFC phase-down | Dec-21 | 100,000 | 99,825 | 175 |  | 12 |  |  |  |
| SWA/PHA/83/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 5,609 | 4,391 |  | 307 |  |  |  |
| TRI/PHA/82/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | Jan-21 | 60,000 | 59,094 | 906 |  | 63 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 62,211 | 37,789 |  | 2,645 |  |  |  |
| TOTAL UNDP |  |  |  |  | 726,096 |  | 51,869 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| AFG/PHA/77/INV/20 | HCFC phase-out management plan (stage I, second tranche) | Sep-21 | 131,938 | 131,427 | 511 |  | 46 | 1 | 93 |  |
| CPR/PHA/71/INV/536 | HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan) | Dec-21 | 8,495,000 | 8,494,893 | 107 |  | 8 | 1 | 93 | 84/68(d)(i) and 86/33(d) |
| GAM/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 9,238 | 762 |  | 53 | 1 | 93 |  |
| IRA/PHA/86/INV/246 | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  | 524,000 | 35,578 | 112,721 |  | 7,891 | N.A. | N.A. |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Jun-21 | 4,353,530 | 4,317,013 | 36,517 |  | 2,739 | 1 | 93 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/PHA/84/INV/29 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Dec-21 | 210,000 | 177,161 | 32,839 |  | 2,463 | 1 | 93 |  |
| NIR/PHA/81/INV/146 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector and project management unit) | Dec-21 | 176,837 | 176,826 | 11 |  | 1 | 1 | 93 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 46,281 | 3,719 |  | 279 | 1 | 93 |  |
| SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Dec-21 | 1,465,361 | 1,462,556 | 2,805 |  | 210 | 1 | 93 |  |
| TOG/PHA/79/INV/30 | HCFC phase-out management plan (stage I, third tranche) | Jun-21 | 150,000 | 148,249 | 1,751 |  | 131 | 1 | 93 |  |
| TOTAL UNIDO |  |  |  |  | 191,744 |  | 13,821 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2021 (US $) | Funds disbursed as of 92nd meeting (US $) | Balances committed as per 92nd meeting (US $) | Balances not- committed as per 92nd meeting (US $) | Support cost on balances committed and not-committed as per 92nd meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,471,897 | 18,703 |  | 1,309 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 18,703 |  | 1,309 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | ONG | 1,674,275 | 1,456,105 | 16,070 |  | 1,125 | 2 | 93 |  |
| GLO/REF/80/DEM/344 | Global chiller replacement project (Argentina) | ONG | 808,438 | 770,732 | 37,706 |  | 2,828 | 2 | 93 |  |
| IVC/PHA/66/INV/36 | HCFC phase-out management plan (stage I, first tranche) | ONG | 460,000 | 459,623 | 377 |  | 28 | 2 | 93 |  |
| IVC/PHA/84/INV/45 | HCFC phase-out management plan (stage I, third tranche) | ONG | 460,000 | 449,228 | 10,772 |  | 754 | 2 | 93 |  |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | ONG | 736,129 | 236,717 | 301,139 |  | 21,079 | 2 | 93 |  |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | ONG | 273,894 | 180,332 | 93,562 |  | 6,549 | 2 | 93 |  |
| SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | ONG | 270,000 | 248,066 | 21,934 |  | 1,535 | 2 | 93 |  |
| SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | ONG | 1,100,000 | 908,061 | 191,939 |  | 13,436 | 2 | 93 |  |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | ONG | 1,300,000 | 1,188,813 | 111,187 |  | 7,783 | 1 | 93 |  |
| SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | ONG | 141,500 | 141,442 | 58 |  | 4 | 2 | 93 |  |
| SOM/PHA/88/INV/16 | HCFC phase-out management plan (stage I, third tranche) | ONG | 40,000 | 34,641 | 5,359 |  | 375 | 2 | 93 |  |
| TOTAL UNIDO |  |  |  |  | 790,103 |  | 55,496 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2021 (US $) | Funds disbursed as of 92nd meeting (US $) | Balances committed as per 92nd meeting (US $) | Balances not- committed as per 92nd meeting (US $) | Support cost on balances committed and not-committed as per 92nd meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| URU/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 100,000 | 78,121 | 21,879 |  | 1,532 |  |  |
| TOTAL UNDP |  |  |  | 21,879 |  | 1,532 |  |  |
| UNIDO |  |  |  |  |  |  |  |  |
| MEX/REF/81/INV/04+ | Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera | 1,018,123 | 925,466 | 92,657 |  | 6,486 | 1 | 93 |
| PHI/SEV/83/TAS/02+ | Enabling activities for HFC phase-down | 225,992 | 207,370 | 18,622 |  | 1,304 | 1 | 93 |
| TOTAL UNIDO |  |  |  | 111,279 |  | 7,790 |  |  |

Annex IV

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| ARM/PHA/86/INV/26 | HCFC phase-out management plan (stage II, third tranche) | 1,239 | 112 | 1,351 |
| COS/PHA/83/INV/59 | HCFC phase-out management plan (stage I, fifth tranche) | 45 | 3 | 48 |
| CUB/PHA/85/TAS/63 | HCFC phase-out management plan (stage I, fifth tranche) | 207 | 16 | 223 |
| ELS/PHA/86/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | 7,059 | 529 | 7,588 |
| KYR/PHA/85/INV/42 | HCFC phase-out management plan (stage II, third tranche) | 434 | 30 | 464 |
| PAN/PHA/85/TAS/51 | HCFC phase-out management plan (stage II, third tranche) | 33 | 2 | 36 |
| TRI/SEV/83/INS/37 | Extension of the institutional strengthening project (phase X: 1/2020-12/2021) | 491 | 34 | 525 |
| Total completed projects |  | 9,508 | 727 | 10,235 |
| IND/PHA/86/INV/479 | HCFC phase-out management plan (stage II, third tranche) (air-conditioning manufacturing sector plan) | 316,592 | 22,161 | 338,753 |
| Total “by-decisions” projects |  | 316,592 | 22,161 | 338,753 |
| COL/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 3,656 | 256 | 3,912 |
| FIJ/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,301 | 161 | 2,462 |
| PAR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 2,573 | 180 | 2,753 |
| Total “additional voluntary contributions” projects |  | 8,530 | 597 | 9,127 |
| TOTAL UNDP |  | 334,630 | 23,485 | 358,115 |
| AFG/PHA/79/TAS/21 | HCFC phase-out management plan (stage I, third tranche) | 11,374 | 1,479 | 12,853 |
| ELS/PHA/77/TAS/35 | HCFC phase-out management plan (stage I, third tranche) | 8,550 | 234 | 8,784 |
| GUA/SEV/81/INS/53 | Renewal of the institutional strengthening project (phase VIIl: 7/2018-6-2020) | 9,853 | 0 | 9,853 |
| KUW/PHA/84/PRP/39 | Preparation of a HCFC phase-out management plan (stage II) | 8,335 | 1,084 | 9,419 |
| KUW/SEV/81/TAS/33 | Enabling activities for HFC phase-down | 112,000 | 7,840 | 119,840 |
| MOL/SEV/82/INS/37 | Extension of the institutional strengthening project (phase X: 1/2019-12/2020) | 2,917 | 0 | 2,917 |
| NIC/PHA/81/TAS/36 | HCFC phase-out management plan (stage I, third tranche) | 532 | 69 | 601 |
| PAR/SEV/82/INS/38 | Extension of institutional strengthening project (phase IX: 1/2019-12/2020) | 6,740 | 0 | 6,740 |
| PHI/SEV/83/INS/106 | Extension of institutional strengthening project (phase XII: 1/2020-12/2021) | 34,093 | 0 | 34,093 |
| QAT/PHA/73/PRP/20 | Preparation of a HCFC phase-out management plan (stage II) | 9,900 | 1,287 | 11,187 |
| SAU/SEV/81/TAS/33 | Enabling activities for HFC phase-down | 56,830 | 3,978 | 60,808 |
| SEN/PHA/85/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | 851 | 111 | 962 |
| Total completed projects |  | 261,975 | 16,081 | 278,056 |
| HAI/PHA/76/TAS/21 | HCFC phase-out management plan (stage I, second tranche) | 9,556 | 1,242 | 10,798 |
| Total “by-decisions” projects |  | 9,556 | 1,242 | 10,798 |
| CHI/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 5,771 | 404 | 6,175 |
| HON/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 70 | 5 | 75 |
| Total “additional voluntary contributions” projects |  | 5,841 | 409 | 6,250 |
| TOTAL UNEP |  | 277,372 | 17,732 | 295,104 |
| BDI/PHA/81/INV/37 | HCFC phase-out management plan (stage I, third tranche) | 313 | 28 | 341 |
| CPR/PHA/64/INV/513 | HCFC phase-out management plan (room air-conditioner manufacturing sector plan) (stage I, first tranche) | 83 | 6 | 89 |
| EGY/SEV/86/INS/148 | Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022) | 253 | 18 | 271 |
| GAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 2,899 | 261 | 3,160 |
| GUA/PHA/85/TAS/59 | HCFC phase-out management plan (stage I, fifth tranche) | 21 | 2 | 23 |
| IRQ/PHA/73/PRP/19 | Preparation of a HCFC phase-out management plan (stage II) | 11,555 | 809 | 12,364 |
| JOR/SEV/82/TAS/104 | Enabling activities for HFC phase-down | 22,292 | 1,561 | 23,853 |
| LIB/SEV/81/INS/40 | Renewal of institutional strengthening project (Phase V: 7/2018-6/2020) | 1,632 | 114 | 1,746 |
| LIR/PHA/84/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | 143 | 10 | 153 |
| MAG/PHA/76/INV/28 | HCFC phase-out management plan (stage I, third tranche) | 231 | 17 | 248 |
| MOG/PHA/83/INV/13 | HCFC phase-out management plan (stage I, fourth tranche) | 2,771 | 208 | 2,979 |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 2,475 | 223 | 2,698 |
| MOG/PHA/85/INV/15 | HCFC phase-out management plan (stage I, fifth tranche) | 296 | 22 | 318 |
| OMA/PHA/86/PRP/40 | Preparation of a HCFC phase-out management plan (stage III) | 660 | 46 | 706 |
| PRC/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | 6,596 | 594 | 7,190 |
| SAU/FOA/62/INV/13 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | 518,307 | 38,873 | 557,180 |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | 613,276 | 42,929 | 656,205 |
| SAU/PHA/77/INV/31 | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan) | 412,484 | 28,874 | 441,358 |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | 6,834 | 478 | 7,312 |
| SOA/PHA/82/PRP/12 | Preparation of a HCFC phase-out management plan (stage II) | 2 | 0 | 2 |
| SUD/PHA/86/INV/46 | HCFC phase-out management plan (stage II, third tranche) | 29 | 4 | 33 |
| SUD/PHA/86/PRP/45 | Preparation of a HCFC phase-out management plan (stage III) | 259 | 18 | 277 |
| TKM/PHA/85/INV/15 | HCFC phase-out management plan (stage I, fourth tranche) | 94 | 7 | 101 |
| TOG/PHA/83/PRP/33 | Preparation of a HCFC phase-out management plan (stage II) | 245 | 17 | 262 |
| VEN/PHA/76/INV/134 | HCFC phase-out management plan (stage II, first tranche) (technical assistance in refrigeration and air-conditioning manufacturing sector) | 5,948 | 416 | 6,364 |
| Total completed projects |  | 1,609,698 | 115,535 | 1,725,233 |
| BKF/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 4,557 | 319 | 4,876 |
| CHI/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 6,950 | 3,264 | 49,897 |
| SOA/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 46,633 | 398 | 6,085 |
| SOM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 5,687 | 3,873 | 59,198 |
| TUR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 55,325 | 1 | 14 |
| URU/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 13 | 487 | 7,437 |
| Total “additional voluntary contributions” projects |  | 119,165 | 8,341 | 127,507 |
| TOTAL UNIDO |  | 1,728,863 | 123,876 | 1,852,740 |
| THA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,586 | 181 | 2,767 |
| Total “additional voluntary contributions” projects |  | 2,586 | 181 | 2,767 |
| TOTAL WORLD BANK |  | 2,586 | 181 | 2,767 |

UNEP/OzL.Pro/ExCom/92/1

Los datos presentados se basan en el formato de presentación de informes que se preparó de conformidad con la decisión 31/2.

UNEP/OzL.Pro/ExCom/92/3

Esta transferencia se trata más a fondo en los informes de situación y en los informes sobre proyectos con requisitos específicos (UNEP/OzL.Pro/ExCom/92/9).

1:  Financial closure-initiated fund not returned due to ongoing unpaid obligations. 2: Ongoing grants, balances are not due for this meeting and therefore, funds will be returned after one year after the agreement end date

1:  Financial closure-initiated fund not returned due to ongoing unpaid obligations. 2: Ongoing grants, balances are not due for this meeting and therefore, funds will be returned after one year after the agreement end date

1:  Financial closure-initiated fund not returned due to ongoing unpaid obligations.