| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/91/16 9 November 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-first Meeting

Montreal, 5-9 December 2022

Item 7(a)(v) of the provisional agenda

PROGRESS REPORT OF UNIDO as at 31 december 2021

Introduction

# This document presents the progress report of UNIDO as at 31 December 2021.

# The progress report of UNIDO includes the status of implementation of projects, including 35 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2021, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2021 and cumulative since 1993 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2021 and cumulative since 1993

# As of 31 December 2021, the Executive Committee had approved US $993.22 million in projects for UNIDO, consisting of US $876.73 million for the implementation of investment and non-investment projects, and US $116.49 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNIDO as at 31 December 2021

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 34,397,921 |
| Destruction | 3,805,540 |
| Foam | 89,067,239 |
| Halon | 1,780,369 |
| HFC phase-down plan | 2,574,000 |
| Fumigants | 78,028,741 |
| Multiple sectors | 139,440 |
| Other | 11,317,246 |
| Phase-out plan | 371,348,627 |
| Process agent | 6,337,359 |
| Production | 52,655,745 |
| Refrigeration | 182,212,578 |
| Several | 19,820,441 |
| Solvents | 23,247,443 |
| Sub-total | 876,732,689 |
| Agency support costs | 116,489,330 |
| Total | 993,222,019 |

# In 2021, 73 new projects and activities were approved. This level of funding is expected to result in the phase-out of 83,308 ODP tonnes of consumption and production and 211,531 CO2-eq tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2021.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2021. Annex II presents analytical information per year since 1993.

Table 2. Status of project implementation by type as at 31 December 2021

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 11 | 11 | 100 | 722,669 | 722,669 | 0 | 100 |
| Demonstration | 43 | 41 | 95 | 23,405,832 | 22,341,008 | 1,064,824 | 95 |
| Institutional strengthening (IS) | 95 | 78 | 82 | 15,222,493 | 13,217,569 | 2,004,924 | 87 |
| Investment | 968 | 849 | 88 | 786,209,921 | 705,697,959 | 80,511,962 | 90 |
| Project preparation | 576 | 508 | 88 | 25,680,616 | 21,883,775 | 3,796,842 | 85 |
| Technical assistance | 208 | 179 | 86 | 24,294,623 | 20,174,931 | 4,119,692 | 83 |
| Training | 23 | 23 | 100 | 1,196,535 | 1,196,535 | 0 | 100 |
| Total | 1,924 | 1,689 | 88 | 876,732,689 | 785,234,446 | 91,498,243 | 90 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNIDO for 2021 and cumulative since 1993 up to 31 December 2021, is summarized as follows:

## Phase-out: In 2021, 1,105.4 ODP tonnes of consumption of controlled substances were phased out and an additional 704.1 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1993, 64,248 ODP tonnes of consumption of controlled substances and 17,381 ODP tonnes of production of controlled substances had been phased out,  of an expected total of 83,308 ODP tonnes and 211,531 CO2-eq tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2021, US $23.92 million was disbursed and US $26.75 million was planned for disbursement based on the 2020 progress report, representing a rate of disbursement of 89 per cent of that planned. Cumulatively, US $785.23 million had been disbursed out of the total US $876.73 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 90 per cent. In 2021, US $23.09 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1993, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.42/kg and for all production sector activities (CFC and methyl bromide (MB)) was US $3.02/kg. The average cost-effectiveness of investment projects per ODP tonne was US $8.60/kg for completed projects and US $40.26/kg for ongoing projects;

## Number of projects completed: In 2021, 87 projects were completed. Since 1993, 1,689 projects of the 1,924 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 88 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2021 were completed on average 57 months after their approval. Since 1993, the average time for completion of investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2021 were completed on average 30 months after their approval. Since 1993, the average time for completion of non-investment projects has been 35 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Project preparation: Of the 576 project preparation activities approved by the end of 2021, 508 have been completed, leaving 68 ongoing activities. In 2021, 20 preparation activities have been completed;

## Implementation delays: A total of 235 projects were under implementation at the end of 2021, experiencing, on average, a delay of 21 months. Forty-six of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2021, two MYAs for the control and phase-out of HFC-23 emissions and 68 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1993, 192 MYAs have been approved and 122 MYAs have been completed, representing a completion rate of 64 per cent.

# Table 3 summarized progress made by UNIDO since 1993.

## Table 3: Progress made by UNIDO since 1993

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 81,629 | 0 | 785,234,446 | 11.42 | 3.02 | 1,924 | 1,689 | 40 | 35 | 21 | 192 | 122 |

*Consumption and production

HFC-related projects

# As of 31 December 2021, the Executive Committee had approved 33 HFC-related projects (including three investment projects, 27 preparation projects and three enabling activities) under regular contributions amounting to US $6,812,029 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 0 | 0 | 3,648,519 | 1,524,521 | 2,123,998 | 42 |
| Project preparation | 27 | 2 | 7 | 2,763,510 | 187,950 | 2,575,559 | 7 |
| Technical assistance - Enabling activities | 3 | 1 | 33 | 400,000 | 269,296 | 130,704 | 67 |
| Total | 33 | 3 | 9 | 6,812,029 | 1,981,766 | 4,830,262 | 29 |

* Excludes agency support costs.

** 118.7 mt (211,531 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2021, of the 33 projects, two preparation projects and one enabling activity have been completed, leaving 30 ongoing. Extension of the completion dates of two ongoing enabling activities was approved; these activities are expected to be completed in 2022.

# The three ongoing HFC investment projects related to the control and phase-out of HFC-23 emissions in Mexico and Argentina approved at the 86th and 87th meeting respectively, and the conversion of large commercial unitary roof top air-conditioning units in Jordan at the 81st meeting.

# Of the total cumulative funding approved of US $6,812,029 (excluding agency support costs), US $1,981,766 had been disbursed, representing a disbursement rate of 29 per cent.

I.2	Issues identified in project implementation in 2021

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 46 projects classified as projects with implementation delays (including 44 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and two investment projects). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 92nd meeting.

# In addition, issues have been identified regarding projects, tranches of MYAs, and preparation of HPMPs. These issues are also presented in Annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Albania, China (extruded polystyrene foam sector plan), the Congo, Eritrea, Mauritania, Montenegro, Morocco, Nigeria (stage III), Serbia, South Africa, Syrian Arab Republic, Togo, Turkmenistan, and Venezuela (Bolivarian Republic of), and a report on projects with specific reporting requirements associated with Senegal (HPMP), have been submitted to the 91st meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Argentina, Suriname, Tunisia and Türkiye, tranches of which were due at the 91st meeting but were not submitted, and for Iraq, the tranche of which was submitted to the 91st meeting but subsequently withdrawn during the project review process, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in Annex III to the present document, and requests for extension of dates of completion, are addressed below.

# Of the 150 ongoing projects, excluding IS and project preparation, 98 projects have revised planned dates of completion since the 2020 progress report.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of the IS project for Tunisia had not been submitted for the last two years. UNIDO indicated that sufficient balance is still available due to slow progress in implementation, and it is planning to submit the renewal request in 2023.

# In line with decision 82/11(b), UNIDO has requested the extension of the duration of four HPMPs, as shown in table 5.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/ Project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Botswana BOT/PHA/82/INV/21 | HCFC phase-out management plan (stage I, second tranche) | 0 | Additional time required for completing procurement and distribution of training equipment | Dec-22 | Jun-23 |
| Libya LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | 72 | Additional time required to complete equipment supply, installation and commissioning at Al Najah and Al Najam | Dec-22 | Dec-23 |
| Somalia SOM/PHA/88/INV/16 | HCFC phase-out management plan (stage I, third tranche) | 0 | Additional time required to recruit consultant and complete the remaining training activities | Dec-22 | Jun-23 |
| Sudan (the) SUD/PHA/75/INV/38 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 24 | Due to COVID-19 restrictions and the inability of previous supplier to fulfil contract for procurement of equipment for Target Steel and Mina, additional time required for rebidding and completing remaining procurement, installation and commissioning activities | Dec-22 | Dec-23 |

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2021, the Executive Committee had approved 35 HFC-related projects under the additional voluntary contributions, amounting to US $8,066,306 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2021

| Type | Number of projects |  |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved |  | Disbursed | Balance | % disbursed |
| Investment** | 3 | 2 | 67 | 3,912,736 |  | 2,136,277 | 1,776,459 | 55 |
| Project preparation | 4 | 4 | 100 | 101,270 |  | 101,269 | 0 | 100 |
| Technical assistance - Enabling activities | 28 | 22 | 79 | 4,052,300 |  | 3,369,771 | 682,529 | 83 |
| Total | 35 | 28 | 80 | 8,066,306 |  | 5,607,318 | 2,458,988 | 70 |

* Excludes agency support costs.

** 168.5 mt (370,517 CO2-eq tonnes) of 265.1 mt (508,586 CO2-eq tonnes) of HFCs had been phased out.

# As of the end of 2021, of the 35 projects approved, 28 projects had been completed including two investment projects, four preparation activities and 22 enabling activities, leaving seven ongoing. Extension of the completion dates of the six ongoing enabling activities was approved; these activities are expected to be completed in 2022.

# The ongoing investment project is in the refrigeration sector in Argentina; it was approved at the 81st meeting and will be completed in 2022.

# Of the total cumulative funding approved of US $8,066,306, US $5,607,318 had been disbursed representing a disbursement rate of 70 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of UNIDO as at 31 December 2021 contained in document UNEP/OzL.Pro/ExCom/91/16;

## To approve the extension of the completion dates of the HCFC phase-out management plans (HPMPs) for the countries listed below to allow for completion of the remaining ongoing activities as reflected in table 5 of document UNEP/OzL.Pro/ExCom/91/16:

### Botswana (stage I) (BOT/PHA/82/INV/21) to 30 June 2023;

### Libya (stage I) (LIB/PHA/75/INV/36) to 31 December 2023;

### Somalia (stage I) (SOM/PHA/88/INV/16) to 30 June 2023;

### The Sudan (stage II) (SUD/PHA/75/INV/38) to 31 December 2023; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER COUNTRY FOR 2021

# Table 1 of Annex I presents the status of project implementation by country for 2021 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNIDO for 2021

| Country | Phased out in 2021 (ODP tonnes) | Phased out in 2021 (CO2-eq tonnes)* | Estimated funds disbursed in 2021 (US$) | Funds disbursed in 2021 (US$) | Percentage of funds disbursed over estimation in 2021 | Percentage of planned projects completed in 2021** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 |  | 35,400 | 18,562 | 52 | 100 |
| Albania | 0.0 |  | 12,000 | 16,183 | 135 | 100 |
| Algeria | 0.0 |  | 125,001 | 131,898 | 106 |  |
| Argentina | 1.4 |  | 169,000 | 135,775 | 80 |  |
| Armenia | 0.0 |  | 47,000 | 86,698 | 184 | 100 |
| Bahamas (the) | 0.6 |  | 1,800 | 812 | 45 | 100 |
| Bahrain | 0.0 |  | 50,000 | 74,578 | 149 |  |
| Benin | 0.0 |  | 15,000 | 19,286 | 129 | 0 |
| Bolivia (Plurinational State of) | 0.0 |  | 27,000 | 82,884 | 307 | 100 |
| Bosnia and Herzegovina | 0.2 |  | 71,502 | 60,832 | 85 | 17 |
| Botswana | 0.5 |  | 72,000 | 14,121 | 20 | 33 |
| Brazil | 1.3 |  | 158,000 | 241,696 | 153 | 0 |
| Burkina Faso | 0.0 |  | 11,000 | 15,887 | 144 | 50 |
| Burundi | 0.3 |  | 73,000 | 75,623 | 104 | 100 |
| Cameroon | 0.7 |  | 100,000 | 142,884 | 143 |  |
| Chad | 0.0 |  | 10,000 | 0 | 0 | 0 |
| Chile | 1.0 |  | 150,000 | 88,501 | 59 | 100 |
| China | 965.8 |  | 18,272,500 | 14,119,249 | 77 | 100 |
| Congo (the) | 1.8 |  | 3,000 | 3,358 | 112 | 100 |
| Cote d'Ivoire | 0.4 |  | 85,000 | 38,171 | 45 | 0 |
| Democratic People’s Republic of Korea (the) | 0.0 |  | 3 | 1 | 20 |  |
| Ecuador | 0.5 |  | 115,002 | 203,912 | 177 | 100 |
| Egypt | 27.9 |  | 1,772,001 | 2,777,124 | 157 | 100 |
| Equatorial Guinea | 0.0 |  | 5,600 | 10,180 | 182 | 50 |
| Eritrea | 0.0 |  | 5,000 | 9,973 | 199 | 100 |
| Ethiopia | 0.7 |  | 30,000 | 64,303 | 214 | 100 |
| Gabon | 0.0 |  | 25,000 | 0 | 0 | 0 |
| Gambia (the) | 0.0 |  | 18,400 | 9,813 | 53 | 100 |
| Grenada | 0.0 |  | 5,000 | 4,965 | 99 | 100 |
| Guatemala | 0.2 |  | 70,001 | 40,752 | 58 | 100 |
| Guinea | 0.2 |  | 82,000 | 114,942 | 140 |  |
| Guinea-Bissau | 0.0 |  | 10,800 | 8,536 | 79 | 0 |
| Honduras | 1.5 |  | 75,800 | 75,891 | 100 | 75 |
| Iran (Islamic Republic of) | 13.2 |  | 110,000 | 35,407 | 32 |  |
| Iraq | 6.6 |  | 297,001 | 137,143 | 46 | 100 |
| Jordan | 8.7 |  | 170,001 | 412,505 | 243 | 0 |
| Kuwait | 0.0 |  | 529,000 | 201,925 | 38 | 0 |
| Liberia | 0.0 |  | 5,000 | 2,811 | 56 | 0 |
| Libya | 0.0 |  | 65,000 | 159,540 | 245 | 0 |
| Madagascar | 1.4 |  | 12,000 | 0 | 0 | 50 |
| Malawi | 0.0 |  | 10,100 | 5,653 | 56 |  |
| Mexico | 16.1 |  | 339,000 | 310,883 | 92 | 50 |
| Montenegro | 0.1 |  | 43,000 | 79,368 | 185 | 100 |
| Morocco | 0.0 |  | 155,000 | 156,460 | 101 | 50 |
| Mozambique | 0.3 |  | 17,000 | 0 | 0 | 0 |
| Myanmar | 0.0 |  | 2 | 0 | 9 | 0 |
| Nicaragua | 0.2 |  | 38,500 | 27,248 | 71 | 100 |
| Niger (the) | 0.0 |  | 38,030 | 12,408 | 33 | 0 |
| Nigeria | 0.2 |  | 125,001 | 134,402 | 108 | 50 |
| North Macedonia | 0.0 |  | 65,000 | 144,685 | 223 | 100 |
| Oman | 3.1 |  | 104,000 | 135,089 | 130 | 100 |
| Pakistan | 0.0 |  | 1,069,000 | 1,228,756 | 115 | 0 |
| Philippines (the) | 0.0 |  | 75,000 | 48,186 | 64 |  |
| Qatar | 0.0 |  | 90,202 | 50,000 | 55 | 100 |
| Rwanda | 0.0 |  | 15,701 | 5,133 | 33 | 100 |
| Saint Lucia | 0.0 |  | 2,000 | 4,460 | 223 | 100 |
| Saudi Arabia | 33.7 |  | 73,004 | 140,781 | 193 | 33 |
| Senegal | 0.0 |  | 9,002 | 575 | 6 |  |
| Serbia | 0.0 |  | 145,432 | 166,089 | 114 | 100 |
| Sierra Leone | 0.0 |  | 5,001 | 11,787 | 236 | 100 |
| Somalia | 0.0 |  | 1,000 | 5,007 | 501 | 50 |
| South Africa | 4.0 |  | 174,001 | 240,036 | 138 | 0 |
| Sudan (the) | 0.0 |  | 87,000 | 131,985 | 152 |  |
| Suriname | 0.0 |  | 2,001 | 0 | 0 | 100 |
| Syria | 12.9 |  | 176,500 | 554,442 | 314 | 67 |
| Togo | 0.0 |  | 6,000 | 4,048 | 67 | 50 |
| Tunisia | 0.0 |  | 288,001 | 416,663 | 145 | 100 |
| Türkiye | 0.0 |  | 270,000 | 114,317 | 42 | 50 |
| Turkmenistan | 0.0 |  | 60,001 | 67,763 | 113 | 100 |
| Uganda | 0.0 |  | 20,000 | 6,833 | 34 |  |
| United Republic of Tanzania (the) | 0.0 |  | 10,000 | 20,502 | 205 | 100 |
| Venezuela (Bolivarian Republic of) | 0.0 |  | 25,000 | 42,530 | 170 |  |
| Zambia | 0.0 |  | 21,000 | 3,046 | 15 | 50 |
| Global | 0.0 |  | 303,000 | 15,835 | 5 | 50 |
| Grand total | 1,105.4 | 0 | 26,753,291 | 23,921,693 | 89 | 60 |

* No phase-out in 2021 for HFC-related projects.

** For projects that were planned to be completed in 2021.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER YEAR AS AT 31 DECEMBER 2021

# Table 1 of Annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1993 and the end of 2011, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1993 | 22 | 22 | 100 | 11,815,540 | 11,815,540 | 0 | 100 |
| 1994 | 52 | 52 | 100 | 30,645,899 | 30,645,899 | 0 | 100 |
| 1995 | 59 | 59 | 100 | 25,662,092 | 25,662,092 | 0 | 100 |
| 1996 | 46 | 46 | 100 | 19,820,493 | 19,820,493 | 0 | 100 |
| 1997 | 130 | 130 | 100 | 42,083,037 | 42,083,038 | 0 | 100 |
| 1998 | 88 | 88 | 100 | 23,638,291 | 23,638,291 | 0 | 100 |
| 1999 | 123 | 123 | 100 | 34,140,324 | 34,140,324 | 0 | 100 |
| 2000 | 96 | 96 | 100 | 30,180,752 | 30,180,752 | 0 | 100 |
| 2001 | 119 | 119 | 100 | 24,700,254 | 24,700,255 | 0 | 100 |
| 2002 | 76 | 76 | 100 | 35,992,041 | 35,992,041 | 1 | 100 |
| 2003 | 49 | 49 | 100 | 29,997,305 | 29,997,305 | 0 | 100 |
| 2004 | 44 | 44 | 100 | 33,105,459 | 33,105,460 | -1 | 100 |
| 2005 | 74 | 74 | 100 | 52,035,808 | 52,035,806 | 2 | 100 |
| 2006 | 44 | 44 | 100 | 20,760,312 | 20,760,312 | 1 | 100 |
| 2007 | 42 | 42 | 100 | 24,186,740 | 24,186,740 | 0 | 100 |
| 2008 | 77 | 77 | 100 | 33,390,165 | 33,378,855 | 11,310 | 100 |
| 2009 | 70 | 70 | 100 | 15,409,470 | 14,740,112 | 669,359 | 96 |
| 2010 | 69 | 69 | 100 | 46,082,128 | 45,524,526 | 557,602 | 99 |
| 2011 | 71 | 71 | 100 | 76,542,893 | 76,542,829 | 64 | 100 |
| 2012 | 52 | 46 | 88 | 32,669,036 | 31,414,817 | 1,254,220 | 96 |
| 2013 | 37 | 36 | 97 | 31,117,693 | 31,084,555 | 33,137 | 100 |
| 2014 | 55 | 48 | 87 | 27,870,542 | 25,961,146 | 1,909,396 | 93 |
| 2015 | 84 | 71 | 85 | 37,289,761 | 24,229,431 | 13,060,330 | 65 |
| 2016 | 58 | 42 | 72 | 35,664,308 | 22,189,301 | 13,475,006 | 62 |
| 2017 | 28 | 19 | 68 | 16,426,252 | 14,000,075 | 2,426,176 | 85 |
| 2018 | 62 | 43 | 69 | 27,166,230 | 11,051,607 | 16,114,623 | 41 |
| 2019 | 66 | 18 | 27 | 19,504,383 | 5,019,087 | 14,485,296 | 26 |
| 2020 | 58 | 14 | 24 | 15,743,901 | 11,241,179 | 4,502,722 | 71 |
| 2021 | 73 | 1 | 1 | 23,091,580 | 92,581 | 22,998,999 | 0 |
| Total | 1,924 | 1,689 | 88 | 876,732,689 | 785,234,446 | 91,498,243 | 90 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNIDO

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Afghanistan AFG/PHA/85/INV/28 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | Challenging political situation | To request UNIDO to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Afghanistan AFG/PHA/85/INV/30 | HCFC phase-out management plan (stage II, first tranche) | 3 |  |  |
| Afghanistan AFG/PHA/79/INV/22 | HCFC phase-out management plan (stage I, third tranche) | 14 | 1) 12 months delays 2) Challenging political situation | 1) To request UNIDO to report to the 92nd meeting on this project with implementation delays 2) To request UNIDO to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Algeria ALG/PHA/66/INV/76 | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | 64 | 1) 12 months delays 2) Delays in implementation of conversion project and commercial production of equipment with alternative technologies in the air-conditioning manufacturer (CONDOR) | 1) To request UNIDO to report to the 92nd meeting on this project with implementation delays 2) To request UNIDO to submit a status report to the 92nd meeting on progress in implementation of activities |
| Algeria ALG/PHA/66/INV/77 | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | 62 | 1) 12 months delays 2) Delays in implementation of service sector activities and solvents component due to technical issues and project planning delays |  |
| Argentina ARG/PHA/84/TAS/191 | HCFC phase-out management plan (stage II, second tranche) (monitoring and reporting of HCFC-22 production) | 0 | 18 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Bosnia and Herzegovina BHE/PHA/72/INV/29 | HCFC phase-out management plan (stage I, second tranche) (activities in the refrigeration servicing sector including policy actions) | 94 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Bosnia and Herzegovina BHE/PHA/76/INV/33 | HCFC phase-out management plan (stage I, third tranche) (activities in the refrigeration servicing sector including policy actions) | 86 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Bosnia and Herzegovina BHE/PHA/82/INV/36 | HCFC phase-out management plan (stage I, fourth tranche) (activities in the refrigeration servicing sector including policy actions) | 5 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Botswana BOT/PHA/75/INV/18 | HCFC phase-out management plan (stage I, first tranche) | 90 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Botswana BOT/PHA/82/INV/21 | HCFC phase-out management plan (stage I, second tranche) | 0 | 18 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Brazil BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 82 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Brazil BRA/PHA/75/TAS/308 | HCFC phase-out management plan (stage II, first tranche) (project monitoring) | 99 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Brazil BRA/PHA/82/INV/320 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector) | 37 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Chile CHI/PHA/81/TAS/196 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 23 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Cameroon CMR/PHA/82/INV/45 | HCFC phase-out management plan (stage II, first tranche) | 38 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| China CPR/PHA/77/INV/576 | HCFC phase-out management plan (stage II, first tranche) (room air-conditioner manufacturing sector plan) | 30 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| China CPR/PHA/81/INV/588 | HCFC phase-out management plan (stage II, second tranche) (room air-conditioner manufacturing sector plan) | 30 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Egypt EGY/PHA/79/INV/133 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 69 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/77/INV/228 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 65 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/INV/239 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 7 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/TAS/240 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 1 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Kuwait KUW/PHA/66/INV/21 | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) | 88 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Kuwait KUW/PHA/74/INV/24 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | 2 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Kuwait KUW/PHA/74/INV/25 | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) | 91 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Kuwait KUW/PHA/83/INV/36 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector phase-out) | 0 | 18 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Mexico MEX/PHA/73/INV/174 | HCFC phase-out management plan (stage II, first tranche) (cleaning agent phase-out in refrigeration servicing sector) | 94 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Mexico MEX/PHA/81/INV/189 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 13 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Mexico MEX/PRO/86/INV/194 | Control and phase-out of HFC-23 emissions in production of HCFC-22 at Quimobasicos | 0 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Mozambique MOZ/PHA/83/INV/31 | HCFC phase-out management plan (stage I, third and fourth tranches) | 0 | 12 and 18 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Myanmar MYA/PHA/80/INV/19 | HCFC phase-out management plan (stage I, second tranche) | 90 | 1) 12 months delays. 2) Challenging political situation | 1) To request UNIDO to report to the 92nd meeting on this project with implementation delays. 2) To request UNIDO to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Myanmar MYA/PHA/83/PRP/20 | Preparation of a HCFC phase-out management plan (stage II) | 0 | Challenging political situation | To request UNIDO to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Pakistan PAK/FOA/84/INV/103 | Phase-out of HCFC-142b/HCFC-22 from the manufacturing of extruded polystyrene at Symobl Industries, Lahore | 0 | 18 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Pakistan PAK/PHA/76/INV/94 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 52 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/INV/102 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | 0 | 12 and 18 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/INV/99 | HCFC phase-out management plan (stage II, second tranche) (domestic air-conditioning sector) | 54 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/TAS/100 | HCFC phase-out management plan (stage II, second tranche) (project management unit) | 25 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Philippines (the) PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 12 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Philippines (the) PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 39 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Saudi Arabia SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 87 | 1) 12 months delays. 2) Delayed due to administrative issues related to project financial completion | 1) To request UNIDO to report to the 92nd meeting on this project with implementation delays. 2) To request UNIDO to submit a status report to the 92nd meeting on the status of resolution of administrative issues and project financial completion |
| Saudi Arabia SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | 60 |  |  |
| Saudi Arabia SAU/PHA/77/INV/31 | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan) | 58 |  |  |
| Saudi Arabia SAU/PHA/75/INV/25 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring) | 99 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Somalia SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 86 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Sudan (the) SUD/PHA/75/INV/38 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 24 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Sudan (the) SUD/PHA/86/INV/46 | HCFC phase-out management plan (stage II, third tranche) | 79 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Türkiye TUR/PHA/75/INV/107 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 52 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Türkiye TUR/PHA/84/INV/111 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring) | 1 | 12 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |
| Zambia ZAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 0 | 18 months delays | To request UNIDO to report to the 92nd meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/91/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 91st meeting.

UNIDO became an implementing agency in 1993.

Ongoing projects are all projects that were under implementation as at 31 December 2021. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/91/12).

Phase-out of ODS is expressed in ODP tonnes and of HFCs in CO2-eq tonnes.

No phase-out for HFC-related projects in 2021.

No phase-out so far for HFC-related projects.

Including 118.7 mt of HFC investment projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/91/36

UNEP/OzL.Pro/ExCom/91/38

UNEP/OzL.Pro/ExCom/91/39

UNEP/OzL.Pro/ExCom/91/41

UNEP/OzL.Pro/ExCom/91/45

UNEP/OzL.Pro/ExCom/91/46

UNEP/OzL.Pro/ExCom/91/47

UNEP/OzL.Pro/ExCom/91/49

UNEP/OzL.Pro/ExCom/91/50

UNEP/OzL.Pro/ExCom/91/51

UNEP/OzL.Pro/ExCom/91/53

UNEP/OzL.Pro/ExCom/91/54

UNEP/OzL.Pro/ExCom/91/55

UNEP/OzL.Pro/ExCom/91/56

UNEP/OzL.Pro/ExCom/91/18

UNEP/OzL.Pro/ExCom/91/21

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.