| 联 合 国 |  | EP |  |
| --- | --- | --- | --- |
|  | 联 合 国 环 境 规 划 署 |  | Distr. GENERAL UNEP/OzL.Pro/ExCom/87/11 18 June 2021 CHINESE ORIGINAL: ENGLISH |

执行蒙特利尔议定书

多边基金执行委员会

第八十七次会议

2021年6月28日至7月2日，蒙特利尔

多边基金 2021-2023 年综合业务计划最新执行情况

- 导言

# 本文件包括：

## 第一部分：2021-2023年业务计划最新执行情况

## 第二部分：2018-2020三年期资源分配

第三部分：关于质量绩效指标对话的报告

建议

附件一： 提交第八十七次会议的氢氟碳化物相关活动

## 第一部分：	2021-2023 年业务计划最新执行情况

# 执行委员会第八十六次会议核可了多边基金 2021-2023 年综合业务计划 。秘书处根据第86/45号决定调整了 2021-2023 年综合业务计划，如表 1 所示。

表 1. 调整后的多边基金 2021–2023 年综合业务计划的资源分配（美元）

| 说明 | 2021年 | 2022年 | 2023年 | 共计 |
| --- | --- | --- | --- | --- |
| 氟氯烃活动 |  |  |  |  |
| 核准的氟氯烃淘汰管理计划 | 70,475,821 | 25,976,975 | 47,114,077 | 143,566,873 |
| 氟氯烃生产 - 第二阶段 | 0 | 23,232,000 | 0 | 23,232,000 |
| 氟氯烃淘汰管理计划项目编制 - 第二阶段 | 111,700 | 104,300 | 0 | 216,000 |
| 氟氯烃淘汰管理计划第二阶段 | 15,990,112 | 4,044,477 | 12,316,504 | 32,351,093 |
| 氟氯烃淘汰管理计划项目编制 - 第三阶段 | 1,057,040 | 709,410 | 32,700 | 1,799,150 |
| 氟氯烃淘汰管理计划第三阶段 | 3,548,717 | 18,044,054 | 37,858,659 | 59,451,430 |
| 氟氯烃淘汰管理计划核查 | 588,600 | 588,600 | 588,600 | 1,765,800 |
| 氟氯烃活动小计 | 91,771,990 | 72,699,816 | 97,910,540 | 262,382,346 |
| 氢氟碳化物活动 |  |  |  |  |
| 氢氟碳化物 - 扶持活动 | 267,500 | 214,000 | 0 | 481,500 |
| 氢氟碳化物 - 投资 | 14,088,690 | 0 | 0 | 14,088,690 |
| 氢氟碳化物逐步减少计划 - 项目编制 | 9,699,078 | 3,405,003 | 111,820 | 13,215,901 |
| 氢氟碳化物逐步减少计划 | 0 | 22,918,072 | 2,616,956 | 25,535,028 |
| 氢氟碳化物活动小计 | 24,055,268 | 26,537,074 | 2,728,777 | 53,321,119 |
| 标准活动 |  |  |  |  |
| 体制强化 | 14,514,175 | 6,825,454 | 14,514,175 | 35,853,805 |
| 履约协助方案 | 11,095,078 | 11,427,930 | 11,770,768 | 34,293,775 |
| 核心单位 | 5,911,238 | 5,952,617 | 5,994,285 | 17,858,141 |
| 秘书处、执行委员会及监督和评估费用，减去加拿大对应资金 | 6,431,920 | 5,698,619 | 5,822,683 | 17,953,222 |
| 财务主任 | 500,000 | 500,000 | 500,000 | 1,500,000 |
| 标准活动小计 | 38,452,412 | 30,404,620 | 38,601,911 | 107,458,943 |
| 总计 | 154,279,670 | 129,641,510 | 139,241,228 | 423,162,408 |
| 澳大利亚 | 0 | 0 | 0 | 0 |
| 奥地利 | 391,833 | 0 | 783,667 | 1,175,500 |
| 法国 | 0 | 0 | 671,075 | 671,075 |
| 德国 | 4,776,414 | 1,749,466 | 1,045,498 | 7,571,378 |
| 意大利 | 264,840 | 0 | 0 | 264,840 |
| 日本 | 301,032 | 0 | 67,800 | 368,832 |
| 联合王国 | 169,500 | 0 | 0 | 169,500 |
| 开发署 | 34,829,052 | 44,309,669 | 60,681,076 | 139,819,796 |
| 环境署 | 30,530,888 | 21,819,781 | 25,738,174 | 78,088,843 |
| 工发组织 | 60,004,206 | 24,882,245 | 32,410,386 | 117,296,837 |
| 国际复兴开发银行 | 15,491,385 | 30,093,130 | 10,932,270 | 56,516,784 |
| 氟氯烃淘汰管理计划核查* | 588,600 | 588,600 | 588,600 | 1,765,800 |
| 秘书处、执行委员会和监督及评估费用，减去加拿大对应资金 | 6,431,920 | 5,698,619 | 5,822,683 | 17,953,222 |
| 财务主任 | 500,000 | 500,000 | 500,000 | 1,500,000 |

*  执行委员会每年核准为低消费量国家编制氟氯烃淘汰管理计划核查报告提供的资金。

2021年业务计划执行情况

# 表2开列了各机构向第八十七次会议提交的数据(截至2021年6月18日)和2021年业务计划的项目资金余额。

表2. 2019年综合业务计划、提交第八十七次会议的项目、余额(美元)*

| 预算项目 | 业务计划资金总额 | 为第八十七次会议审查/建议的活动 | 余额 (高于)/低于 |
| --- | --- | --- | --- |
| 双边机构 | 5,903,619 | 1,064,543 | 4,839,076 |
| 开发署 | 34,829,052 | 4,542,365 | 30,286,687 |
| 环境署 | 30,530,888 | 6,512,328 | 24,018,560 |
| 工发组织 | 60,004,206 | 5,609,616 | 54,394,590 |
| 世界银行 | 15,491,385 | 4,313,445 | 11,177,940 |
| 氟氯烃淘汰管理计划核查 | 588,600 | 0 | 588,600 |
| 小计(机构) | 147,347,749 | 22,042,297 | 125,305,452 |
| 秘书处/执行委员会/监督和评估 (不包括加拿大对应资金) | 6,431,920 |  | 6,431,920 |
| 财务主任 | 500,000 |  | 500,000 |
| 小计(标准费用) | 6,931,920 |  | 6,931,920 |
| 共计 | 154,279,670 | 22,042,297 | 132,237,373 |

* 包括核心单位费用。

# 为第八十七次会议审查/建议的项目提案价值为22,042,297美元，比2021年业务计划的项目提案价值低8,752,659美元，其中包括未列入2021年业务计划的项目提案费用1,003,880美元。

# 提交第八十七次会议的氢氟碳化物相关活动的价值为8,802,041美元，其中包括未列入2021年业务计划的项目提案费用642,000美元。本文件附件一列出了执行机构向第八十七次会议提交的氢氟碳化物相关项目。

# 预先承付款项

# 假设原则上核准提交第八十七次会议的多年期协定供资申请，2021年至2031年期间多年期协定现有预先承付总额为2.8338亿美元，如表3所示。

表3. 预先承付款项 (2021–2031年) (千美元)

| 说明 | 2021年 | 2022年 | 2023年 | 2024年 | 2025年 | 2026年 | 2027年 | 2028年 | 2029年 | 2030年 | 2031年 | 共计 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 已原则上核准 | 70,519 | 25,977 | 47,114 | 9,060 | 34,504 | 31,775 | 2,328 | 223 | 754 | 2,456 | 57 | 224,766 |
| 提交第87次会议 | 3,435 | 24,227 | 1,877 | 25,493 | 662 | 485 | 1,608 | 0 | 70 | 751 | 0 | 58,610 |
| 共计 | 73,954 | 50,204 | 48,991 | 34,554 | 35,166 | 32,261 | 3,936 | 223 | 824 | 3,207 | 57 | 283,376 |

# 第二部分：2018-2020三年期资源分配

# 《蒙特利尔议定书》缔约方核准2018-2020三年期 资源540,000,000美元。考虑到2018年、2019年和2020年核准的供资总额、应计利息、非第5条缔约方已缴捐款、固定汇率机制的损益以及秘书处/执行委员会/财务主任的支出，截至2021年6月9日可动用现金为334,427,526美元。

# 此外，考虑到超过核准额的现金，包括世界银行对第八十六次会议、2021-2023三年期预付款、第八十六次会议闭会期间延长核准程序(IAP-86ext)核准的项目、第八十六次会议核准项目罚款、世界银行哈龙行业计划退款和退还第八十七次会议的余额，2018-2020三年期结转额为309,705,337美元，如图4所示。

表4. 2018-2020三年期资源分配

| 说明 |  | 金额 (美元) |
| --- | --- | --- |
| 截至2021年6月9日可动用余额 | (a) | 334,427,526 |
| 世界银行超过核准额的现金，包括第86次会议 | (b) | 3,280,455 |
| 2021-2023三年期预付款 | (c) | 38,518,658 |
| IAP-86ext核准的项目 | (d) | 548,972 |
| 第86次会议核准项目罚款 | (e) | 11,463 |
| 世界银行哈龙行业计划退款 | (f) | 8,745,165 |
| 退还第87次会议的余额 | (g) | 2,308,358 |
| 余额 | (h= a+b-c-d+e+f+g) | 309,705,337 |

第三部分：关于质量绩效指标对话的报告

# 第八十六次会议请工发组织除其他外与伊拉克国家臭氧机构就评估其质量绩效进行公开和建设性讨论，并向第八十七次会议报告讨论结果(第86/8(b)号决定)。

# 因此工发组织启动了与伊拉克政府和环境署(主要执行机构)的对话和磋商，重点放在具体涉及工发组织的问题和提高其绩效的方法；监测和讨论所有进行中项目的进展情况(国家淘汰计划和氟氯烃淘汰管理计划第一阶段)；今后提交的项目。商定每月进行磋商，由环境署和工发组织共同负责安排/召开会议(两机构轮流负责召集会议)。

建议

# 谨建议执行委员会注意到：

- UNEP/OzL.Pro/ExCom/87/11号文件所载多边基金2021-2023年综合业务计划的最新执行情况；

- 提交第八十七次会议的活动总价值为22,042,297美元(包括氢氟碳化物相关活动8,802,041美元)，其中1,003,880美元属于未列入2021年业务计划的项目提案；

- 赞赏工发组织根据第86/8(b)号决定提交的与伊拉克政府就质量绩效评估过程中所提问题的讨论结果报告。

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 87TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US$) | Support costs recommended (US$) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 31,500 | 4,095 |
| Albania | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 63,500 | 4,445 |
| Argentina | UNIDO | INV | PRO | Control and phase-out of HFC-23 emissions in production of HCFC-22 at FIASA | 1,700,838 | 119,059 |
| Armenia | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Bhutan | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 10,000 | 700 |
| Bhutan | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 75,000 | 9,750 |
| Bolivia (Plurinational State of) | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 170,000 | 11,900 |
| Burkina Faso | Germany | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Colombia | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 205,000 | 14,350 |
| Costa Rica | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Cuba | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Dominican Republic (the) | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 170,000 | 11,900 |
| Ecuador | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 190,000 | 13,300 |
| Egypt | UNIDO | INV | REF | Conversion of refrigeration compressor manufacturing facility from HFC-134a-based compressors to R-600a-based compressors at Misr Compressor Manufacturing Co. (MCMC) | 1,305,536 | 91,388 |
| Eswatini | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 30,000 | 2,100 |
| Eswatini | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 100,000 | 13,000 |
| Ghana | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 105,000 | 7,350 |
| Ghana | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 45,000 | 5,850 |
| Jordan | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Kyrgyzstan | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 60,000 | 4,200 |
| Kyrgyzstan | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 25,000 | 3,250 |
| Lao People's Democratic Republic (the) | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 10,000 | 700 |
| Lao People's Democratic Republic (the) | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 75,000 | 9,750 |
| Lebanon | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Liberia | Germany | PRP | PHA | Preparation of an HFC phase-down plan | 130,000 | 16,900 |
| Malaysia | IBRD | PRP | PHA | Preparation of an HFC phase-down plan | 250,000 | 17,500 |
| Maldives | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 10,000 | 700 |
| Maldives | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 75,000 | 9,750 |
| Mauritius | Germany | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Mexico | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 90,000 | 6,300 |
| Mexico | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 35,000 | 4,550 |
| Mexico | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 125,000 | 8,750 |
| Montenegro | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 85,000 | 5,950 |
| Nicaragua | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 170,000 | 11,900 |
| Niger (the) | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Nigeria | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 25,000 | 1,750 |
| Nigeria | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 137,000 | 9,590 |
| Nigeria | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 58,000 | 7,540 |
| North Macedonia | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 85,000 | 5,950 |
| Panama | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 190,000 | 13,300 |
| Paraguay | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 170,000 | 11,900 |
| Peru | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Senegal | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 60,000 | 7,800 |
| Senegal | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 25,000 | 1,750 |
| South Africa | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 100,000 | 7,000 |
| Sri Lanka | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 135,000 | 9,450 |
| Sri Lanka | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 25,000 | 3,250 |
| Trinidad and Tobago | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Turkmenistan | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Uruguay | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |

伊朗伊斯兰共和国(德国和环境署)、印度尼西亚(开发署)和印度(环境署)氟氯烃淘汰管理计划第三阶段的项目编制；萨尔瓦多氟氯烃淘汰管理计划付款(开发署)；多民族玻利维亚国(工发组织)、哥伦比亚(开发署)、多米尼加共和国(开发署)、斯威士兰王国(开发署)和尼日利亚(工发组织)氢氟碳化物逐步减少计划项目编制。

第XXIX/1号决定。