| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/99/13 29 October 2026 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-ninth Meeting

Montreal, 7–11 December 2026

Item 7(a)(i) of the provisional agenda

CONSOLIDATED PROGRESS REPORT AS AT 31 DECEMBER 2025

Introduction

# The consolidated progress report summarizes progress and financial information provided by bilateral and implementing agencies as of 31 December 2025, in their respective progress reports submitted to the Secretariat.

# At its 96th meeting, the Executive Committee approved the revised format for progress and financial reporting, including the associated narrative reporting requirements (decision 96/54). The revised progress report database introduces changes to the titles of six existing columns and adds four new columns to improve the clarity of the data collected. In addition, nine columns have been removed to streamline reporting requirements, avoid duplication of information, and eliminate fields that are no longer relevant under current Multilateral Fund policies.

# Decision 96/54 also noted that the revised reporting format would be implemented in 2026 for the submission of the 2025 progress reports. This reporting cycle marks the first year in which progress report data and narrative have been submitted under the new format and using the new project naming convention introduced through the Knowledge Management System.

# The consolidated progress report and the progress reports of the bilateral and implementing agencies include all controlled substances under the Montreal Protocol. It presents information on HFC-related projects and activities that have been funded under the regular contributions to the Multilateral Fund and those funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Fund, the Secretariat no longer reports on these projects separately. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

Review process by the Secretariat

# The Secretariat reviewed each of the annual progress reports submitted by bilateral and implementing agencies separately. The review was based on the milestones established for investment and non-investment projects including, inter alia, signing of agreements; date of release of first disbursement; status of procurement and installation of equipment; status of services provided, including training of refrigeration technicians and customs officers; level of disbursement of approved funds; the operational and financial completion of the project; and the return of fund balances.

# During the review process, potential issues were identified, including cases where agreements had not been signed due to delays in administrative approvals, such as changes in the institutions involved in Montreal Protocol project implementation and fund management; instances where a national ozone officer was not in place; lack of financial progress reports; delays in the procurement process, predominantly due to supply chain issues, primarily affecting the availability of refrigerant identifiers; lack of availability of alternative technologies in local markets; challenges in identifying technical experts and consultants to carry out specialized activities; and security-related issues at the country and regional levels. All projects with outstanding issues either had low disbursement rates of approved funds and/or required an extension of the planned completion dates.

# The Secretariat also had several exchanges with each bilateral and implementing agency on projects and activities with outstanding issues, where several of the issues were satisfactorily resolved. For those projects and activities where the issues could not be resolved, the proposed recommendations for consideration by the Executive Committee were discussed and agreed with the relevant bilateral or implementing agencies. The projects and activities for which an extension of the completion dates has been requested, are considered in the main documents, while the lists of projects with outstanding issues are contained in annex III of each progress report of bilateral and implementing agencies. The recommendations will be considered during the discussions of each agency progress report at the 99th meeting.

# In line with decision 84/45(c), the Secretariat identified all the multi-year agreement (MYA) components with implementation delays and informed the relevant bilateral and implementing agencies. The Secretariat’s recommendations are contained in annex III of each progress report of the bilateral and implementing agencies.

# This document presents a summary of progress in implementation of projects for 2025 and cumulative since 1991 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

# The progress reports of bilateral or implementing agencies did not include any policy issue for consideration by the Executive Committee. Also, no policy issues were identified during the Secretariat’s review of the progress reports.

Progress in implementation of projects for 2025 and cumulative since 1991

# As of 31 December 2025, the Executive Committee had approved US $4.38 billion in projects for bilateral and implementing agencies, consisting of US $3.92 billion for the implementation of investment and non-investment projects, and US $463.32 million for agency support costs (excluding cancelled and transferred projects), as shown in table 1.

Table 1. Approved funding by cluster and agency as at 31 December 2025 (US $)

| Cluster | UNDP | UNEP | UNIDO | World Bank | Bilateral | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Agency programme | 596,500 | 219,020,391 | 0 | 185,000 | 242,002 | 220,043,893 |
| CFC individual | 301,302,827 | 18,859,831 | 248,861,816 | 307,224,816 | 43,812,121 | 920,061,412 |
| CFC phase-out plans | 58,120,483 | 9,549,588 | 51,560,736 | 73,523,850 | 24,891,387 | 217,646,045 |
| CFC production phase-out plans | 1,056,000 | 0 | 31,849,298 | 261,179,093 | 0 | 294,084,391 |
| Disposal | 3,086,833 | 190,040 | 3,791,983 | 400,000 | 1,526,282 | 8,995,138 |
| Emission control 1 | 0 | 0 | 3,082,494 | 0 | 0 | 3,082,494 |
| Energy efficiency | 3,771,519 | 1,617,200 | 24,739,295 | 1,430,689 | 2,976,934 | 34,535,637 |
| Government support | 70,936,154 | 100,834,251 | 23,983,246 | 10,743,662 | 1,063,376 | 207,560,689 |
| HCFC individual | 25,280,775 | 12,780,387 | 23,409,236 | 7,987,990 | 4,096,101 | 73,554,489 |
| HCFC phase-out management plan (HPMP) stage I | 164,132,892 | 27,708,270 | 218,272,599 | 99,298,659 | 19,205,445 | 528,617,865 |
| HPMP stage II | 184,185,445 | 44,754,010 | 171,535,530 | 39,651,104 | 26,649,535 | 466,775,624 |
| HPMP stage III | 33,211,908 | 4,861,825 | 26,164,893 | 3,227,127 | 7,740,496 | 75,206,249 |
| HCFC production phase-out management plan (HPPMP) stage I | 0 | 0 | 0 | 91,256,301 | 0 | 91,256,301 |
| HPPMP stage II | 0 | 0 | 0 | 66,997,213 | 0 | 66,997,213 |
| HFC individual | 16,648,883 | 26,753,474 | 26,595,198 | 2,672,594 | 3,225,403 | 75,895,552 |
| Kigali HFC implementation plan (KIP) stage I | 15,288,509 | 4,649,415 | 27,816,150 | 7,721,113 | 1,008,669 | 56,483,856 |
| Other ODS individual | 13,870,732 | 6,781,350 | 60,539,415 | 15,981,112 | 16,770,869 | 113,943,478 |
| Other ODS individual production | 0 | 0 | 0 | 951,653 | 0 | 951,653 |
| Other ODS production phase-out plans | 0 | 0 | 18,724,810 | 37,499,577 | 0 | 56,224,387 |
| Other ODS sector plans | 85,911,732 | 3,527,163 | 75,903,816 | 209,171,575 | 30,064,662 | 404,578,948 |
| Sub-total | 977,401,193 | 481,887,196 | 1,036,830,515 | 1,237,103,129 | 183,273,282 | 3,916,495,314 |
| Agency support costs | 136,799,588 | 39,580,572 | 135,531,787 | 133,373,468 | 18,033,540 | 463,318,955 |
| Total | 1,114,200,781 | 521,467,768 | 1,172,362,302 | 1,370,476,596 | 201,306,822 | 4,379,814,269 |

*Excludes cancelled and transferred projects.

# Table 2 provides a summary of project implementation since inception through the end of 2025.

# Table 2. Project summary since the inception of the Multilateral Fund

| Items | Cumulative since 1991* |
| --- | --- |
| Number of approvals | 10,375 |
| Number of projects completed | 9,255 |
| Total funds approved (excluding support costs) (US $) | 3,916,495,314 |
| Total funds disbursed (excluding support costs) (US $) | 3,589,967,400 |
| Total approved phase-out (ODP tonnes)** | 489,535.7 |
| Total actual phase-out (ODP tonnes)** | 510,811.8 |
| Total approved phase-out (mt)*** | 12,775.5 |
| Total actual phase-out (mt)*** | 2,000.0 |
| Total approved phase-out (CO2-eq tonnes)*** | 24,447,959 |
| Total actual phase-out (CO2-eq tonnes)*** | 3,423,266 |

* Excluding cancelled and transferred projects.

** Including consumption and production.

*** For HFC-related projects only (including consumption and production).

# In 2025, 291 new projects and activities were approved. This level of funding is expected to result in the phase-out of 489,536 ODP tonnes of consumption and production of ODS and 12,775 mt (24,447,959 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2025.

# Table 3 shows the status of project implementation including fund disbursement per project cluster as at 31 December 2025. Annex II presents analytical information per year since 1991.

Table 3. Status of project implementation by cluster as at 31 December 2025*

| Clusters | Number of projects |  |  | Funding (US$)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Agency programme | 269 | 264 | 98 | 220,043,893 | 206,701,121 | 13,342,772 | 94 |
| CFC individual | 3,622 | 3,622 | 100 | 920,061,412 | 920,061,417 | -5 | 100 |
| CFC phase-out plans | 429 | 429 | 100 | 217,646,045 | 217,646,045 | 1 | 100 |
| CFC production phase-out plans | 42 | 42 | 100 | 294,084,391 | 294,084,391 | 0 | 100 |
| Disposal | 34 | 34 | 100 | 8,995,138 | 8,995,139 | -1 | 100 |
| Emission control 1 | 6 | 2 | 33 | 3,082,494 | 2,690,248 | 392,246 | 87 |
| Energy efficiency | 71 | 9 | 13 | 34,535,637 | 2,206,767 | 32,328,869 | 6 |
| Government support | 1,537 | 1,397 | 91 | 207,560,689 | 178,480,868 | 29,079,821 | 86 |
| HCFC individual | 899 | 835 | 93 | 73,554,489 | 71,472,699 | 2,081,790 | 97 |
| HPMP stage I | 912 | 872 | 96 | 528,617,865 | 521,491,305 | 7,126,560 | 99 |
| HPMP stage II | 682 | 344 | 50 | 466,775,624 | 361,305,812 | 105,469,812 | 77 |
| HPMP stage III | 88 | 14 | 16 | 75,206,249 | 13,672,956 | 61,533,293 | 18 |
| HPPMP stage I | 4 | 4 | 100 | 91,256,301 | 91,256,301 | 0 | 100 |
| HPPMP stage II | 3 | 2 | 67 | 66,997,213 | 62,597,213 | 4,400,000 | 93 |
| HFC individual | 644 | 454 | 70 | 75,895,552 | 57,578,566 | 18,316,985 | 76 |
| KIP stage I | 211 | 9 | 4 | 56,483,856 | 4,290,262 | 52,193,594 | 8 |
| Other ODS individual | 589 | 589 | 100 | 113,943,478 | 113,943,470 | 8 | 100 |
| Other ODS individual production | 1 | 1 | 100 | 951,653 | 951,653 | 0 | 100 |
| Other ODS production phase-out plans | 27 | 27 | 100 | 56,224,387 | 56,224,388 | -1 | 100 |
| Other ODS sector plans | 305 | 305 | 100 | 404,578,948 | 404,316,779 | 262,169 | 100 |
| Total | 10,375 | 9,255 | 89 | 3,916,495,314 | 3,589,967,400 | 326,527,914 | 92 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

# Implementation of projects and activities by bilateral and implementing agencies for 2025 and cumulative since 1991 up to 31 December 2025 is summarized as follows:

## Phase-out: In 2025, 9,345.4 ODP tonnes of consumption and production of ODS and 286.2 mt (490,053 CO2-eq tonnes) of consumption of HFCs were phased out and an additional 922.9 ODP tonnes of consumption of ODS and 3,623.8 mt (6,730,720 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 510,812 ODP tonnes had been phased out, of an expected total of 489,536 ODP tonnes of consumption and production of ODS and 2,000 mt (3,423,266 CO2-eq tonnes) had been phased out, of an expected total of 12,775 mt (24,447,959 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects). In addition, in 2025, 50 mt (739,303 CO2-eq tonnes) of HFC-23 by-product were destroyed. Since 2022, 364.1 mt (5,388,241 CO2-eq tonnes) had been destroyed of an expected total of 1,274.3 mt (18,858,948 CO2-eq tonnes) of HFC-23 by-product from approved projects;

## Disbursements/approvals: In 2025, US $104.54 million was disbursed, and US $96.84 million was planned for disbursement based on the 2024 progress report, representing a rate of disbursement of 108 per cent of that planned. Cumulatively, US $3.59 billion had been disbursed out of the total US $3.92 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 92 per cent. In 2025, US $123.25 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $8.96/kg. The cost-effectiveness for the production sector was US $2.29/kg. The average cost-effectiveness of investment projects per ODP tonne was US $5.46/kg for completed projects and US $13.78/kg for ongoing projects;

## Number of projects completed: In 2025, 195 projects were completed. Since 1991, 9,255 projects of the 10,375 projects (excluding closed or transferred projects) financed by the Multilateral Fund have been completed, representing a completion rate of 89 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2025 were completed on average 59 months after their approval. Since 1991, the average time for completion of investment projects has been 38 months after their approval. First disbursements under these projects occurred, on average, 14 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2025 were completed on average 35 months after their approval. Since 1991, the average time for completion of non-investment projects has been 38 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 2,335 project preparation activities approved by the end of 2025, 2,108 have been completed, leaving 227 ongoing activities. In 2025, 70 project preparation activities were approved and 65 were completed;

## Implementation delays: A total of 1,120 projects were under implementation at the end of 2025, experiencing, on average, a delay of eight months. One hundred and fifty-nine of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## MYAs: In 2025, one HPPMP, 148 MYAs for HPMPs, 85 MYAs for KIPs and two MYAs for control and phase-out of HFC-23 emissions were under implementation. Since 1991, 569 MYAs have been approved and 333 MYAs have been completed, representing a completion rate of 59 per cent. Annex III summarizes the total funding approved and disbursed for HPMP activities at the country level.

# Table 4 summarizes progress made by bilateral and implementing agencies since 1991.

## Table 4. Progress made by bilateral and implementing agencies since 1991

| Phase-out achieved |  | HFC-23 by-product destroyed | Disbursement (US $) | Average CE (US$/kg) |  |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes** | CO2-eq tonnes *** |  | Consump- tion | Produc- tion | HFC-23 emissions | Approved | Completed | Invest- ment | Non- investment |  | Approved | Completed |
| 510,812 | 3,423,266 | 5,388,241 | 3,589,967,400 | 8.96 | 2.29 | 8.47 | 10,375 | 9,255 | 38 | 38 | 8 | 569 | 333 |

* Consumption and production of ODS.

** HFC-related projects.

*** HFC-23 by-product destroyed as reported in the project proposal documents.

HFC-related projects

# As of 31 December 2025, the Executive Committee had approved 855 HFC-related projects (including 15 investment projects, 332 preparation activities, 297 technical assistance projects and 211 projects related to stage I of KIPs) amounting to US $132,379,408 (excluding agency support costs) to phase out of 12,775 mt (24,447,959 CO2-eq tonnes) of consumption of HFCs. A summary of the status of these projects is presented in table 5 and the respective data has already been included in paragraphs 11 to 16.

Table 5. HFC-related projects approved*

| Clusters | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| HFC individual – investment | 15 | 14 | 93 | 19,423,266 | 15,323,516 | 4,099,750 | 79 |
| HFC individual – preparation projects | 332 | 153 | 46 | 30,310,941 | 17,116,363 | 13,194,578 | 56 |
| HFC individual – technical assistance | 297 | 287 | 97 | 26,161,345 | 25,138,688 | 1,022,658 | 96 |
| KIP stage I | 211 | 9 | 4 | 56,483,856 | 4,290,262 | 52,193,594 | 8 |
| Total | 855 | 463 | 54 | 132,379,408 | 61,868,828 | 70,510,580 | 47 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

# As of the end of 2025, of the 855 projects, 14 investment projects, 153 preparation activities, 287 technical assistance projects and nine projects related to stage I of KIPs have been completed, leaving 392 ongoing. The remaining activities are at various stages of implementation.

# Of the total cumulative funding approved of US $132,379,408 (excluding agency support costs), US $61,868,828 has been disbursed, representing a disbursement rate of 47 per cent.

# Annex IV provides information on all HFC-related projects and activities under the Multilateral Fund, irrespective of the source of funding, at the country level, indicating the status of ratification of the Kigali Amendment and the status of the HFC licensing system.

Energy-efficiency projects

# As of 31 December 2025, the Executive Committee had approved 71 energy-efficiency projects (including one demonstration project, 13 preparation activities and 39 technical assistance pilot projects under the funding window pursuant to decision 91/65; seven preparation activities and five investment projects under the funding window pursuant to decision 94/60; four preparation activities for energy-efficiency revolving-fund end-user projects pursuant to decision 95/87; one preparation activity for a conversion project pursuant to decision 87/50; and one technical assistance project for “Twinning of national ozone officers and national energy-efficiency policymakers to support Kigali Amendment”) amounting to US $34,535,637 (excluding agency support costs). A summary of the status of these projects is presented in table 6 and the respective data has already been included in paragraphs 11 to 16.

Table 6. Energy-efficiency projects approved*

| Type | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Pilot projects (decision 91/65) – demonstration | 1 | 1 | 100 | 1,853,795 | 624,891 | 1,228,904 | 34 |
| Pilot projects (decision 91/65) – project preparation | 13 | 5 | 38 | 435,000 | 225,171 | 209,829 | 52 |
| Pilot projects (decision 91/65) – technical assistance | 39 | 2 | 5 | 10,211,307 | 1,082,699 | 9,128,607 | 11 |
| Manufacturing (decision 94/60) – project preparation | 7 | 1 | 14 | 335,000 | 151,573 | 183,427 | 45 |
| Manufacturing (decision 94/60) – investment | 5 | 0 | 0 | 20,257,335 | 0 | 20,257,335 | 0 |
| Energy-efficiency revolving-fund end-user projects (decision 95/87) – project preparation | 4 | 0 | 0 | 500,000 | 103,664 | 396,336 | 21 |
| Others – project preparation | 1 | 0 | 0 | 150,000 | 18,769 | 131,231 | 13 |
| Others – technical assistance | 1 | 0 | 0 | 793,200 | 0 | 793,200 | 0 |
| Total | 71 | 9 | 13 | 34,535,637 | 2,206,767 | 32,328,869 | 6 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

# As of the end of 2025, of the 71 projects, one demonstration, five preparation and two technical assistance projects pursuant to decision 91/65 and one preparation activity pursuant to decision 94/60 have been completed, leaving 62 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $34,535,637 (excluding agency support costs), US $2,206,767 has been disbursed, representing a disbursement rate of 6 per cent.

# Annex V provides information on all energy-efficiency projects and activities under the Multilateral Fund, by funding window at the country level.

# Issues identified in project implementation in 2025

# Based on planned completion dates reported in the 2024 progress report, and the results reported in the 2025 progress reports, bilateral and implementing agencies completed 53 per cent of the projects they had planned to complete in 2025. Two hundred and sixty-nine of the 753 ongoing projects (excluding IS and project preparation) have revised their planned dates of completion since the 2024 progress report.

# Bilateral and implementing agencies achieved an overall rate of disbursement of 108 per cent in 2025. On a country/region basis, 63 countries (including regions) had a disbursement rate of over 85 per cent while 36 countries had a disbursement rate of below 50 per cent.

# In total, bilateral and implementing agencies are requested to report, at the 100th meeting, on 159 ongoing projects with implementation delays and 25 ongoing tranches of MYAs, renewal of IS projects, preparation of HPMPs, projects pursuant to decision 91/66, and enabling activities for HFC phase-down recommended for status reports.

# Secretariat comments

# The Secretariat noted that certain projects experienced delays due to operational issues. In line with decision 82/11(b), the requests for extension of their completion dates, to various dates up to 31 March 2028, are presented in the progress reports of the respective implementing and bilateral agencies and require approval by the Executive Committee. These include projects related to the HPMPs for Mauritania, Montenegro, Nigeria, the Sudan, and the Syrian Arab Republic (UNIDO), Namibia, Papua New Guinea, and Seychelles (Germany), and Viet Nam (World Bank); projects related to the KIP for Viet Nam (World Bank); five energy-efficiency projects pursuant to decision 91/65 in Mexico, Montenegro, Nigeria, and South Africa (UNIDO) and Uganda (the United Kingdom of Great Britain and Northern Ireland); and various activities related to the preparation of national inventory of banks of waste-controlled substances (decision 91/66) (all agencies).

# The agencies have continued to provide information on specific steps undertaken to address delays in the implementation of activities, including analyses of the relevant root causes and information on measures taken to avoid reoccurrence. Similar to the information reported in the 2024 progress report, the main issues identified include delays in procurement and distribution of equipment, mainly due to delays in the supply of refrigerant identifiers caused by regional conflicts; slower market uptake of low-global-warming-potential (GWP) technologies; structural changes within Governments, including changes in national ozone units (NOUs) and their financial management processes and reporting structure; the political and security situation in certain regions; challenges in identifying technical experts and consultants to conduct project studies, including for activities related to the preparation of national inventories of banks of waste controlled substances and development of national plans for the management of those substances; and delays in the submission of reports due to limited NOU capacity. The main actions taken by the agencies include defining procedures for the timely procurement of equipment through long-term agreements with qualified suppliers; for promoting the adoption of low-GWP alternative technologies, close coordination with the NOU and industry and implementation of targeted programmes, and addressing technical and operational barriers through project activities, including experience-sharing on low-GWP technology adoption; close coordination with Governments, including consultations during the network and other meetings on specific country-level issues and defining action plans to address administrative issues; expanding the number of consultants and technical experts available to conduct project studies, including for activities related to the preparation of national inventories of banks of waste controlled substances and development of national plans for the management of those substances, along with capacity-building of consultants in specific instances; and training and capacity-building of NOU staff and involving senior Government management staff on aspects related to operational progress monitoring and reporting. At its 93rd meeting, the Executive Committee approved an increase in the funding support provided to implementing agencies to strengthen their capacities to provide technical and policy assistance to Article 5 countries during the triennium 2024–2026 (decision 93/95). This increase provides support to enable more effective implementation of various activities, particularly for low-volume-consuming countries. The implementation of this increase will be reviewed at the 99th meeting in the context of the review of the administrative cost regime and core unit funding budget (decision 93/95).

Gender mainstreaming

# All implementing agencies implement the Multilateral Fund’s policy in this area. Several also apply their own institutional strategies on women’s participation and empowerment, mainstreaming guides, or internal plans, and some have specialists in this area or dedicated teams that review projects. Considerations related to women’s participation are now routinely incorporated into project design. Recent submissions of MYAs and projects related to stage I of KIPs include the mandatory section on the policy, activities and indicators that promote women’s participation and representation, and, in most cases, the collection of sex-disaggregated data.

# Common measures include targets for women’s participation in technician, trainer and customs/enforcement training; consultations with women’s associations and other stakeholders; recruitment measures that encourage women’s participation, including the recruitment of women into newly established project management units (PMUs); reporting by enterprises on female-to-male employment ratios; scholarship programmes supporting women in refrigeration and air-conditioning (RAC) and mobile air-conditioning sectors; and youth outreach activities.

# New tools are also being developed, such as a train-the-trainer manual on integrating women’s perspectives and roles, as well as reviews of good practice across project portfolios. Women’s participation in training activities and consultations has increased over time.

# Agencies report two main constraints. First, the RAC sector remains widely perceived as male-dominated. Second, resources dedicated to strengthening women’s participation across different activities are limited, particularly in low-volume-consuming countries.

Risk management

# All agencies systematically monitor implementation risks and delays and take both preventive and corrective actions. Practices include formal monitoring frameworks, including automated “red flag” checks on implementing partners for overdue reports, budget variances, ineligible expenditures, and adverse audit findings; root-cause analysis of delays, combined with preventive measures; early project readiness, through the advance preparation of work plans, terms of reference and procurement plans, and realistic clearance timelines; adaptive procurement processes such as long-term agreements with suppliers, re-tendering, bundling and local sourcing; regular follow-up with NOUs; adjustments to work plans and implementation roadmaps; deployment of in-country PMUs and missions where national capacity is limited; relationship-building across institutions to ensure continuity through political transitions; and revised schedules and prioritised activities in conflict-affected settings.

# When necessary, issues are escalated to senior government levels through management missions or country office channels, and, in exceptional cases, to the agencies’ legal offices and the Secretariat. Many delays arise from factors beyond the agencies’ control; these include changes in national policy or regulations, political transitions, conflict, and sanctions. Agencies respond by working closely with national authorities to develop and implement mitigation measures tailored to each country’s circumstances.

Recommendation

# The Executive Committee may wish to note:

## The consolidated progress report of the Multilateral Fund as at 31 December 2025, contained in document UNEP/OzL.Pro/ExCom/99/13;

## With appreciation, the efforts undertaken by bilateral and implementing agencies in reporting their 2025 activities; and

## That the bilateral and implementing agencies would report, at the 100th meeting, on 159 projects with implementation delays and 25 ongoing projects recommended for additional status reports, as contained in annex III of each individual progress report of bilateral and implementing agencies.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION

PER COUNTRY FOR 2025

# Table 1 of annex I presents the status of project implementation by country for 2025 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation for 2025

| Country | Phased out in 2025 (ODP tonnes)* | Phased out in 2025 (CO2-eq tonnes)** | Estimated funds disbursed in 2025 (US$) | Funds disbursed in 2025 (US$) | Percentage of funds disbursed over estimation in 2025 | Percentage of planned projects completed in 2025*** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan |  |  | 7 | 21,727 | 310,386 |  |
| Albania | 0.6 | 0 | 162,981 | 266,521 | 164 | 100 |
| Algeria | 11.1 | 0 | 327,239 | 713,792 | 218 | 100 |
| Angola | 5.2 | 0 | 247,480 | 153,562 | 62 | 100 |
| Antigua and Barbuda |  |  | 48,927 | 33,944 | 69 |  |
| Argentina | 11.1 | 0 | 1,185,755 | 3,398,953 | 287 | 33 |
| Armenia | 0.0 | 0 | 160,287 | 131,848 | 82 | 50 |
| Bahamas (the) |  |  | 142,400 | 82,681 | 58 |  |
| Bahrain | 11.0 | 0 | 73,044 | 189,925 | 260 | 100 |
| Bangladesh | 0.0 | 0 | 826,022 | 851,751 | 103 | 60 |
| Barbados |  |  | 135,690 | 16,502 | 12 | 0 |
| Belize | 0.0 | 0 | 238,669 | 137,139 | 57 | 100 |
| Benin |  |  | 269,459 | 142,745 | 53 | 0 |
| Bhutan | 0.0 | 0 | 145,171 | 88,037 | 61 | 50 |
| Bolivia (Plurinational State of) |  |  | 314,242 | 212,554 | 68 |  |
| Bosnia and Herzegovina | 0.6 | 0 | 147,000 | 221,016 | 150 | 100 |
| Botswana | 0.0 | 0 | 98,570 | 44,627 | 45 | 50 |
| Brazil | 24.8 | 0 | 3,421,117 | 2,303,503 | 67 | 100 |
| Brunei Darussalam | 0.9 | 0 | 148,492 | 108,739 | 73 | 100 |
| Burkina Faso | 0.0 | 0 | 225,307 | 175,536 | 78 | 0 |
| Burundi |  |  | 164,150 | 150,773 | 92 | 0 |
| Cabo Verde | 0.0 | 0 | 185,768 | 130,484 | 70 | 100 |
| Cambodia | 4.9 | 38,652 | 223,518 | 359,406 | 161 | 100 |
| Cameroon |  |  | 369,126 | 407,697 | 110 | 0 |
| Central African Republic (the) |  |  | 18,000 | 72,000 | 400 |  |
| Chad | 0.0 | 0 | 186,600 | 203,666 | 109 | 100 |
| Chile | 3.4 | 0 | 569,482 | 307,728 | 54 | 67 |
| China | 7,641.5 | 0 | 27,113,011 | 40,621,776 | 150 | 50 |
| Colombia | 0.0 | 0 | 1,288,429 | 822,127 | 64 | 100 |
| Comoros (the) |  |  | 131,003 | 3,179 | 2 |  |
| Congo (the) |  |  | 237,101 | 142,124 | 60 |  |
| Cook Islands (the) |  |  | 249,142 | 87,053 | 35 | 0 |
| Costa Rica |  |  | 388,688 | 203,863 | 52 |  |
| Côte d'Ivoire |  |  | 379,328 | 316,326 | 83 |  |
| Cuba | 0.0 | 0 | 299,307 | 315,429 | 105 | 0 |
| Democratic People's Republic of Korea (the) |  |  | 2 | 0 | 0 |  |
| Democratic Republic of the Congo (the) |  |  | 147,496 | 105,157 | 71 | 0 |
| Djibouti | 0.0 | 0 | 86,670 | 141,715 | 164 | 100 |
| Dominica |  |  | 63,645 | 35,429 | 56 |  |
| Dominican Republic (the) |  |  | 479,795 | 365,833 | 76 |  |
| Ecuador |  |  | 401,500 | 471,945 | 118 |  |
| Egypt | 25.2 | 0 | 3,740,358 | 4,003,411 | 107 | 38 |
| El Salvador | 0.0 | 0 | 267,805 | 164,855 | 62 | 100 |
| Equatorial Guinea |  |  | 79,340 | 62,400 | 79 |  |
| Eritrea | 0.0 | 0 | 123,242 | 278,952 | 226 | 50 |
| Eswatini | 0.4 | 0 | 191,475 | 261,731 | 137 |  |
| Ethiopia | 0.0 | 0 | 59,386 | 61,436 | 103 | 50 |
| Fiji | 0.0 | 0 | 239,187 | 148,096 | 62 | 40 |
| Gabon | 0.0 | 0 | 178,327 | 199,676 | 112 | 0 |
| Gambia (the) | 0.0 | 0 | 188,289 | 224,124 | 119 | 0 |
| Georgia | 0.0 | 0 | 114,375 | 190,122 | 166 | 100 |
| Ghana |  |  | 251,657 | 185,734 | 74 |  |
| Grenada | 0.1 | 0 | 259,562 | 251,344 | 97 | 100 |
| Guatemala | 0.0 | 0 | 365,920 | 200,394 | 55 | 100 |
| Guinea | 0.0 | 0 | 92,501 | 128,058 | 138 | 100 |
| Guinea-Bissau | 0.0 | 0 | 144,423 | 247,935 | 172 | 100 |
| Guyana | 0.1 | 0 | 147,930 | 53,948 | 36 | 0 |
| Haiti |  |  | 94,246 | 30,893 | 33 |  |
| Honduras | 0.0 | 0 | 286,253 | 149,676 | 52 | 100 |
| India | 29.4 | 126,039 | 6,185,450 | 5,946,303 | 96 | 58 |
| Indonesia | 0.0 | 0 | 2,010,366 | 2,394,195 | 119 | 100 |
| Iran (Islamic Republic of) | 5.2 | 0 | 1,004,540 | 674,077 | 67 | 21 |
| Iraq | 1,455.4 | 0 | 307,477 | 153,762 | 50 | 100 |
| Jamaica |  |  | 212,837 | 64,938 | 31 | 0 |
| Jordan | 0.0 | 211,513 | 437,005 | 213,511 | 49 | 50 |
| Kenya | 0.0 | 0 | 365,207 | 332,222 | 91 | 50 |
| Kiribati |  |  | 263,592 | 31,806 | 12 | 0 |
| Kuwait |  |  | 606,899 | 37,191 | 6 |  |
| Kyrgyzstan | 0.0 | 0 | 166,801 | 285,847 | 171 | 100 |
| Lao People's Democratic Republic (the) | 0.0 | 0 | 167,125 | 160,691 | 96 | 100 |
| Lebanon | 0.6 | 0 | 278,535 | 377,151 | 135 | 100 |
| Lesotho | 0.0 | 0 | 158,344 | 193,394 | 122 | 67 |
| Liberia | 0.0 | 0 | 211,616 | 158,237 | 75 | 33 |
| Libya |  |  | 150,901 | 258,036 | 171 | 0 |
| Madagascar | 3.4 | 0 | 210,825 | 275,619 | 131 | 50 |
| Malawi | 2.0 | 48,165 | 127,802 | 300,105 | 235 |  |
| Malaysia | 0.0 | 0 | 1,932,692 | 695,432 | 36 |  |
| Maldives | 0.0 | 0 | 151,571 | 106,931 | 71 | 100 |
| Mali | 0.0 | 0 | 132,920 | 264,704 | 199 | 100 |
| Marshall Islands (the) | 0.0 | 0 | 110,710 | 27,711 | 25 | 50 |
| Mauritania |  |  | 58,750 | 78,392 | 133 | 0 |
| Mauritius | 3.1 | 0 | 175,181 | 55,216 | 32 | 100 |
| Mexico | 4.0 | 0 | 1,644,768 | 2,528,784 | 154 | 67 |
| Micronesia (Federated States of) |  |  | 236,884 | 59,294 | 25 | 0 |
| Mongolia | 0.0 | 0 | 268,067 | 156,881 | 59 | 50 |
| Montenegro |  |  | 128,000 | 137,467 | 107 | 0 |
| Morocco | 0.0 | 0 | 400,335 | 401,140 | 100 |  |
| Mozambique | 0.0 | 0 | 205,456 | 169,888 | 83 | 67 |
| Myanmar |  |  | 45,000 | 0 | 0 | 0 |
| Namibia | 0.0 | 0 | 187,107 | 180,457 | 96 | 40 |
| Nauru |  |  | 151,660 | 5,766 | 4 | 0 |
| Nepal | 0.0 | 0 | 185,939 | 41,725 | 22 | 100 |
| Nicaragua | 1.4 | 28,498 | 195,435 | 104,475 | 53 |  |
| Niger (the) | 1.7 | 0 | 227,503 | 131,394 | 58 | 25 |
| Nigeria | 31.6 | 0 | 1,591,589 | 2,738,766 | 172 | 80 |
| Niue |  |  | 68,475 | 34,574 | 50 | 0 |
| North Macedonia | 0.5 | 0 | 250,000 | 282,904 | 113 | 100 |
| Oman |  |  | 168,829 | 290,966 | 172 | 0 |
| Pakistan | 8.2 | 0 | 1,161,845 | 1,229,659 | 106 | 33 |
| Palau |  |  | 218,775 | 75,250 | 34 | 0 |
| Panama | 0.0 | 0 | 396,044 | 325,491 | 82 |  |
| Papua New Guinea | 0.0 | 0 | 224,500 | 123,098 | 55 | 50 |
| Paraguay |  |  | 278,802 | 206,693 | 74 |  |
| Peru | 2.2 | 0 | 479,117 | 225,210 | 47 | 0 |
| Philippines (the) |  |  | 248,876 | 239,668 | 96 | 0 |
| Qatar |  |  | 145,079 | 98,003 | 68 |  |
| Republic of Moldova (the) | 0.0 | 0 | 125,153 | 167,991 | 134 | 50 |
| Rwanda |  |  | 95,040 | 138,681 | 146 |  |
| Saint Kitts and Nevis |  |  | 25,500 | 14,372 | 56 |  |
| Saint Lucia | 0.0 | 0 | 245,500 | 66,485 | 27 | 100 |
| Saint Vincent and the Grenadines | 0.0 | 0 | 169,754 | 54,069 | 32 | 50 |
| Samoa |  |  | 202,514 | 55,568 | 27 | 0 |
| Sao Tome and Principe |  |  | 137,086 | 10,005 | 7 |  |
| Saudi Arabia |  |  | 607,786 | 273,915 | 45 |  |
| Senegal |  |  | 261,190 | 294,371 | 113 | 0 |
| Serbia | 0.0 | 0 | 73,572 | 104,179 | 142 | 33 |
| Seychelles | 0.0 | 0 | 190,854 | 91,074 | 48 | 100 |
| Sierra Leone | 0.1 | 0 | 184,610 | 116,896 | 63 | 0 |
| Solomon Islands |  |  | 287,567 | 120,792 | 42 | 0 |
| Somalia | 0.0 | 0 | 235,451 | 275,394 | 117 |  |
| South Africa | 0.0 | 0 | 2,111,000 | 2,660,114 | 126 | 50 |
| South Sudan | 0.0 | 0 | 71,500 | 110,310 | 154 | 100 |
| Sri Lanka | 0.8 | 0 | 422,144 | 323,352 | 77 | 75 |
| Sudan (the) |  |  | 2 | 2,342 | 117,097 |  |
| Suriname | 0.0 | 0 | 164,391 | 109,357 | 67 | 100 |
| Syrian Arab Republic (the) |  |  | 395,660 | 60,569 | 15 | 0 |
| Thailand | 49.9 | 0 | 1,492,307 | 1,173,944 | 79 | 33 |
| Timor-Leste |  |  | 118,830 | 48,588 | 41 | 0 |
| Togo | 0.0 | 0 | 202,525 | 385,333 | 190 | 0 |
| Tonga |  |  | 196,734 | 115,817 | 59 | 0 |
| Trinidad and Tobago | 0.0 | 0 | 550,268 | 226,593 | 41 |  |
| Tunisia | 2.8 | 0 | 444,500 | 478,566 | 108 | 100 |
| Türkiye | 0.0 | 0 | 889,857 | 781,780 | 88 | 50 |
| Turkmenistan | 2.2 | 21,313 | 283,002 | 374,821 | 132 | 100 |
| Tuvalu |  |  | 123,680 | 78,347 | 63 | 0 |
| Uganda |  |  | 98,000 | 32,091 | 33 | 0 |
| United Republic of Tanzania (the) | 0.0 | 0 | 85,210 | 143,401 | 168 | 33 |
| Uruguay |  |  | 842,653 | 284,372 | 34 |  |
| Vanuatu |  |  | 249,372 | 78,797 | 32 | 0 |
| Venezuela (Bolivarian Republic of) |  |  | 232,487 | 295,785 | 127 | 0 |
| Viet Nam | 0.0 | 0 | 313,134 | 139,973 | 45 | 50 |
| Yemen |  |  | 137,006 | 115,022 | 84 |  |
| Zambia | 0.0 | 0 | 119,352 | 34,161 | 29 | 50 |
| Zimbabwe | 0.0 | 15,873 | 236,388 | 270,690 | 115 |  |
| Region: Asia and the Pacific |  |  | 669,569 | 142,283 | 21 | 0 |
| Global | 0.0 | 0 | 10,885,809 | 10,012,707 | 92 | 83 |
| Grand total | 9,345.4 | 490,053 | 96,836,084 | 104,537,530 | 108 | 53 |

* Including 2,210.4 ODP tonnes of consumption and 7,135 ODP tonnes of production of ODS.

** 286.2 mt (490,053 CO2-eq tonnes) in 2025 for HFC-related projects. In addition, in 2025, 50 mt (739,303 CO2-eq tonnes) of HFC-23 by-product were destroyed.

*** For projects that were planned to be completed in 2025.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION

AS AT 31 DECEMBER 2025

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2013, have now been completed.

Table 1. Status of project implementation by year*

| Year | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 68 | 68 | 100 | 7,935,719 | 7,935,719 | 0 | 100 |
| 1992 | 176 | 176 | 100 | 41,240,955 | 41,240,955 | 0 | 100 |
| 1993 | 217 | 217 | 100 | 73,198,586 | 73,198,586 | 0 | 100 |
| 1994 | 379 | 379 | 100 | 127,169,827 | 127,169,828 | -1 | 100 |
| 1995 | 355 | 355 | 100 | 109,928,036 | 109,928,037 | -1 | 100 |
| 1996 | 257 | 257 | 100 | 82,954,863 | 82,954,863 | 0 | 100 |
| 1997 | 532 | 532 | 100 | 149,550,404 | 149,550,406 | -2 | 100 |
| 1998 | 423 | 423 | 100 | 98,011,001 | 98,011,000 | 1 | 100 |
| 1999 | 547 | 547 | 100 | 151,740,800 | 151,740,801 | -1 | 100 |
| 2000 | 427 | 427 | 100 | 109,359,737 | 109,359,735 | 2 | 100 |
| 2001 | 429 | 429 | 100 | 130,098,119 | 130,098,120 | -1 | 100 |
| 2002 | 359 | 359 | 100 | 161,270,406 | 161,270,405 | 1 | 100 |
| 2003 | 247 | 247 | 100 | 157,011,471 | 157,011,471 | 0 | 100 |
| 2004 | 271 | 271 | 100 | 162,080,533 | 162,080,533 | 0 | 100 |
| 2005 | 258 | 258 | 100 | 180,181,482 | 180,181,479 | 3 | 100 |
| 2006 | 263 | 263 | 100 | 119,827,552 | 119,827,556 | -4 | 100 |
| 2007 | 214 | 214 | 100 | 120,084,049 | 120,084,047 | 2 | 100 |
| 2008 | 356 | 356 | 100 | 120,443,370 | 120,443,376 | -6 | 100 |
| 2009 | 321 | 321 | 100 | 71,273,405 | 71,011,232 | 262,173 | 100 |
| 2010 | 227 | 227 | 100 | 83,364,108 | 83,364,107 | 1 | 100 |
| 2011 | 264 | 264 | 100 | 201,702,267 | 201,836,313 | -134,046 | 100 |
| 2012 | 182 | 182 | 100 | 100,691,055 | 100,616,534 | 74,521 | 100 |
| 2013 | 184 | 184 | 100 | 125,214,438 | 125,080,397 | 134,040 | 100 |
| 2014 | 223 | 222 | 100 | 91,725,784 | 91,682,062 | 43,722 | 100 |
| 2015 | 377 | 373 | 99 | 153,970,241 | 151,666,300 | 2,303,941 | 99 |
| 2016 | 239 | 235 | 98 | 113,756,139 | 112,383,126 | 1,373,013 | 99 |
| 2017 | 202 | 198 | 98 | 74,525,568 | 73,938,385 | 587,184 | 99 |
| 2018 | 334 | 330 | 99 | 129,349,258 | 126,835,340 | 2,513,918 | 98 |
| 2019 | 226 | 212 | 94 | 47,482,693 | 43,592,627 | 3,890,065 | 92 |
| 2020 | 252 | 216 | 86 | 65,550,010 | 61,153,565 | 4,396,445 | 93 |
| 2021 | 291 | 242 | 83 | 82,404,353 | 75,607,982 | 6,796,371 | 92 |
| 2022 | 216 | 147 | 68 | 82,798,535 | 69,052,012 | 13,746,523 | 83 |
| 2023 | 356 | 101 | 28 | 112,652,731 | 53,106,160 | 59,546,571 | 47 |
| 2024 | 412 | 23 | 6 | 154,693,805 | 45,741,900 | 108,951,905 | 30 |
| 2025 | 291 | 0 | 0 | 123,254,012 | 1,212,441 | 122,041,571 | 1 |
| Total | 10,375 | 9,255 | 89 | 3,916,495,314 | 3,589,967,400 | 326,527,914 | 92 |

* Excluding closed and transferred projects.

** Excluding agency support costs.

Completed projects

# Since 1991, 9,255 projects of the 10,375 projects (excluding closed or transferred projects) financed by the Multilateral Fund were completed, representing a completion rate of 89 per cent. Tables 2 to 4 present information on completed investment, non-investment and project preparation activities.

Completed investment projects

# Table 2 presents information on investment projects that have been completed since 1991. The table presents the data in total, followed by data according to region and sector.

Table 2. Cumulative completed investment projects

| Item | Number of projects completed | Approved funding plus adjustments (US $) | Per cent of funds disbursed (%) | Consumption phased out (ODP tonnes) | Production phased out (ODP tonnes) | Consumption phased out (metric tonnes) | Consumption phased out (CO2-eq tonnes) | Average number of months from approval to first disbursement | Average number of months from approval to completion | Cost- effectiveness to the Fund (US $/kg.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | 3,183 | 2,697,833,882 | 99.7 | 281,349.9 | 211,671.0 | 1,224.1 | 1,823,366 | 14 | 38 | 5.46 |
| Region |  |  |  |  |  |  |  |  |  |  |
| Africa | 565 | 190,616,312 | 99 | 18,791.5 | 0.0 | 11.1 | 15,873 | 11 | 41 | 10.14 |
| Asia and the Pacific | 1,656 | 1,995,696,899 | 100 | 219,382.3 | 191,721.0 | 801.8 | 1,190,592 | 15 | 38 | 4.85 |
| Europe | 183 | 74,532,235 | 100 | 8,064.0 | 175.0 | 11.4 | 21,313 | 9 | 34 | 9.03 |
| Latin America and the Caribbean | 779 | 436,988,436 | 100 | 35,112.0 | 19,775.0 | 399.8 | 595,588 | 13 | 37 | 7.90 |
| Sector |  |  |  |  |  |  |  |  |  |  |
| Aerosol | 132 | 93,596,722 | 100 | 28,007.9 | 0.0 | 0.0 | 0 | 16 | 42 | 3.34 |
| Air-conditioning | 63 | 159,615,359 | 99 | 645.4 | 0.0 | 34.9 | 63,383 | 15 | 52 | 234.62 |
| Emissions | 1 | 387,561 | 100 | 0.0 | 0.0 | 0.0 | 0 | 5 | 12 | 0.00 |
| Firefighting | 50 | 72,255,166 | 100 | 42,335.1 | 41,958.0 | 0.0 | 0 | 18 | 29 | 0.86 |
| Foam | 1,179 | 748,385,688 | 100 | 82,727.5 | 0.0 | 250.0 | 257,500 | 14 | 36 | 9.02 |
| Fumigant | 123 | 99,900,005 | 100 | 8,112.5 | 0.0 | 0.0 | 0 | 9 | 49 | 12.31 |
| National ozone unit | 1 | 26,000 | 100 | 0.0 | 0.0 | 0.0 | 0 | 2 | 8 | 0.00 |
| Process agent | 32 | 120,252,626 | 100 | 19,572.5 | 52,162.0 | 0.0 | 0 | 10 | 27 | 1.68 |
| Production | 65 | 461,628,213 | 100 | 0.0 | 106,216.0 | 0.0 | 0 | 9 | 22 | 4.35 |
| Refrigeration | 609 | 518,753,164 | 100 | 41,110.3 | 0.0 | 889.7 | 1,414,020 | 15 | 40 | 12.35 |
| Servicing | 741 | 214,470,895 | 99 | 34,018.0 | 0.0 | 49.5 | 88,463 | 11 | 40 | 6.30 |
| Solvent | 176 | 191,429,266 | 100 | 23,186.3 | 11,335.0 | 0.0 | 0 | 17 | 34 | 5.55 |
| Sterilant | 3 | 1,073,855 | 100 | 60.4 | 0.0 | 0.0 | 0 | 15 | 34 | 17.78 |
| Tobacco fluffing | 8 | 16,059,360 | 100 | 1,574.0 | 0.0 | 0.0 | 0 | 12 | 20 | 10.20 |

# Overall, 99.7 per cent of the funds approved for completed investment projects have been disbursed. Since 1991, 3,183 investment projects have been completed at a total value of US $2.7 billion. The average time from approval to first disbursement for investment projects is 14 months. Investment projects have been completed, on average, 38 months after they were approved.

Completed non-investment projects

# Table 3 presents data on cumulative completed non-investment projects. Since 1991, 3,964 non-investment projects have been completed at a total value of US $774.69 million.

Table 3. Cumulative completed non-investment projects

| Item | Number of projects | Approved funding plus adjustments (US $) | Per cent of funds disbursed (%) | Average number of months from approval to first disbursement | Average number of months from approval to completion |
| --- | --- | --- | --- | --- | --- |
| Total | 3,964 | 774,690,386 | 100 | 13 | 38 |
| Region |  |  |  |  |  |
| Africa | 1,239 | 114,185,902 | 100 | 12 | 38 |
| Asia and the Pacific | 1,195 | 189,562,343 | 100 | 14 | 41 |
| Europe | 262 | 26,427,958 | 100 | 9 | 34 |
| Global | 329 | 327,700,721 | 100 | 6 | 22 |
| Latin America and the Caribbean | 939 | 116,813,461 | 100 | 14 | 42 |
| Sector |  |  |  |  |  |
| Aerosol | 30 | 2,415,057 | 100 | 12 | 39 |
| Air-conditioning | 18 | 11,566,734 | 98 | 11 | 41 |
| Compliance Assistance Programme | 23 | 175,060,139 | 100 | 1 | 16 |
| Core unit | 69 | 123,509,352 | 0 | 0 | 12 |
| Country assistance | 2 | 255,000 | 100 | 10 | 40 |
| Disposal | 17 | 8,695,687 | 100 | 11 | 65 |
| Enabling activities | 158 | 17,029,803 | 99 | 10 | 42 |
| Firefighting | 82 | 11,319,055 | 100 | 16 | 45 |
| Foam | 37 | 11,529,452 | 100 | 14 | 38 |
| Fumigant | 138 | 21,199,406 | 100 | 9 | 39 |
| National ozone unit | 1,397 | 166,901,609 | 100 | 12 | 36 |
| Pre-CAP | 171 | 22,894,564 | 100 | 4 | 20 |
| Project monitoring and coordination | 39 | 8,613,097 | 99 | 19 | 49 |
| Refrigeration | 571 | 78,823,496 | 100 | 17 | 52 |
| SERVCEE-89/6 | 5 | 459,000 | 85 | 9 | 25 |
| Servicing | 817 | 94,962,242 | 99 | 14 | 41 |
| Solvent | 40 | 4,473,562 | 100 | 14 | 28 |
| Survey | 150 | 9,171,361 | 100 | 12 | 26 |
| Technical assistance | 9 | 799,878 | 100 | 3 | 13 |
| Tobacco fluffing | 1 | 76,499 | 100 | 7 | 38 |
| Verification | 190 | 4,935,393 | 98 | 12 | 25 |

# The average time from approval to first disbursement for non-investment projects is 13 months. Non-investment projects have been completed, on average, 38 months after they were approved. This figure is influenced by the large number of projects (1,397 of 3,964) in the sector called “National ozone unit”, which had an average time from approval to completion of 36 months. Non-investment projects in the other sectors were completed between 12 and 65 months after they had been approved.

Completed project preparation activities

# Table 4 presents data on cumulative completed project preparation activities. Since 1991, 2,108 preparation activities have been completed at a total value of US $110.87 million.

Table 4. Cumulative completed project preparation activities

| Region | Number of projects | Approved funding plus adjustments (US $) | Per cent of funds disbursed (%) | Average number of months from approval to first disbursement | Average number of months from approval to completion |
| --- | --- | --- | --- | --- | --- |
| Total | 2,108 | 110,874,072 | 99 | 7 | 24 |
| Region |  |  |  |  |  |
| Africa | 590 | 23,469,432 | 97 | 9 | 27 |
| Asia and the Pacific | 762 | 50,484,453 | 99 | 7 | 24 |
| Europe | 160 | 7,622,812 | 99 | 6 | 22 |
| Global | 22 | 1,889,230 | 98 | 6 | 19 |
| Latin America and the Caribbean | 574 | 27,408,144 | 99 | 6 | 22 |
| Sector |  |  |  |  |  |
| Aerosol | 47 | 1,279,230 | 100 | 5 | 17 |
| Air-conditioning | 27 | 1,760,642 | 98 | 10 | 30 |
| Disposal | 24 | 1,265,875 | 94 | 12 | 36 |
| Emissions | 3 | 133,575 | 100 | 2 | 12 |
| Firefighting | 30 | 898,898 | 100 | 6 | 20 |
| Foam | 284 | 13,411,612 | 100 | 5 | 22 |
| Fumigant | 119 | 3,061,986 | 100 | 5 | 17 |
| Process agent | 9 | 694,384 | 100 | 8 | 19 |
| Production | 11 | 1,745,935 | 100 | 7 | 19 |
| Refrigeration | 670 | 36,636,897 | 100 | 5 | 19 |
| Servicing | 649 | 39,061,245 | 97 | 11 | 32 |
| Solvent | 60 | 2,698,033 | 100 | 6 | 26 |
| Sterilant | 1 | 5,000 | 100 | 1 | 9 |
| Technical assistance | 172 | 7,980,013 | 100 | 6 | 22 |
| Tobacco fluffing | 2 | 240,747 | 100 | 11 | 35 |

# The average time from approval to first disbursement for project preparation activities is seven months. Preparation activities have been completed, on average, 24 months after they were approved. Overall, 99 per cent of the funds approved for completed preparation activities have been disbursed.

Ongoing projects

# A total of 1,120 projects were under implementation at the end of 2025. Tables 5 to 7 present information on ongoing investment, non-investment and project preparation activities.

## Ongoing investment projects

# Table 5 presents information on the status of investment projects under implementation by region and sector.

Table 5. Cumulative ongoing investment projects

| Item | Number of projects | Approved funding plus adjustments (US $) | Funds Disbursed (US $) | Per cent of funds disbursed (%) | Number of projects disbursing | Per cent of projects disbursing (%) | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion | Overall cost-effectiveness to the Fund (US $/kg) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | 344 | 311,723,258 | 103,399,961 | 33 | 200 | 58 | 10 | 47 | 12 | 13.78 |
| Region |  |  |  |  |  |  |  |  |  |  |
| Africa | 129 | 81,680,978 | 19,181,520 | 23 | 75 | 58 | 10 | 46 | 11 | 16.20 |
| Asia and the Pacific | 105 | 165,201,042 | 67,927,842 | 41 | 58 | 55 | 10 | 50 | 16 | 13.21 |
| Europe | 28 | 10,855,176 | 4,216,777 | 39 | 17 | 61 | 7 | 48 | 15 | 11.57 |
| Latin America and the Caribbean | 82 | 53,986,062 | 12,073,822 | 22 | 50 | 61 | 10 | 42 | 8 | 13.03 |
| Sector |  |  |  |  |  |  |  |  |  |  |
| Air-conditioning | 23 | 72,248,475 | 40,536,534 | 56 | 10 | 43 | 11 | 53 | 17 | 15.76 |
| Emissions | 4 | 2,212,176 | 1,819,962 | 82 | 3 | 75 | 7 | 42 | 6 | 0.00 |
| Firefighting | 1 | 141,000 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 238.98 |
| Foam | 29 | 34,063,787 | 12,054,593 | 35 | 20 | 69 | 11 | 62 | 29 | 9.10 |
| Production | 1 | 22,000,000 | 17,600,000 | 80 | 1 | 100 | 3 | 24 | 0 | 4.69 |
| Refrigeration | 28 | 49,591,067 | 7,604,458 | 15 | 8 | 29 | 13 | 42 | 8 | 31.16 |
| Servicing | 257 | 130,943,322 | 23,758,756 | 18 | 157 | 61 | 10 | 45 | 10 | 16.44 |
| Solvent | 1 | 523,431 | 25,658 | 5 | 1 | 100 | 0 | 24 | 0 | 9.52 |

# There are currently 344 investment projects under implementation at a total value of over US $311.72 million. Around 33 per cent of the funds have already been disbursed. The overall average cost-effectiveness of ongoing investment projects is US $13.78/kg ODP to be phased out.

# The average number of months from approval to first disbursement is 10 months. The average duration of an ongoing investment project is 47 months. Typically, ongoing investment projects are completed 12 months later than originally planned, which could be considered the average delay.

Ongoing non-investment projects

# Table 6 presents information on the status of non-investment projects under implementation by region and sector.

Table 6. Cumulative ongoing non-investment projects

| Region | Number of projects | Approved funding plus adjustments (US $) | Funds disbursed (US $) | Per cent of funds disbursed (%) | Number of projects disbursing | Per cent of projects disbursing (%) | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | 549 | 126,886,069 | 34,154,561 | 27 | 270 | 49 | 14 | 41 | 5 |
| Region |  |  |  |  |  |  |  |  |  |
| Africa | 187 | 29,592,632 | 7,027,448 | 24 | 83 | 44 | 15 | 38 | 4 |
| Asia and the Pacific | 181 | 44,349,908 | 10,320,531 | 23 | 96 | 53 | 15 | 50 | 8 |
| Europe | 42 | 6,244,033 | 1,671,519 | 27 | 22 | 52 | 8 | 35 | 2 |
| Global | 6 | 23,261,500 | 9,594,013 | 41 | 1 | 17 | 0 | 17 | 2 |
| Latin America and the Caribbean | 133 | 23,437,996 | 5,541,050 | 24 | 68 | 51 | 15 | 39 | 5 |
| Sector |  |  |  |  |  |  |  |  |  |
| Compliance Assistance Programme | 2 | 22,468,300 | 9,594,013 | 43 | 1 | 50 | 0 | 18 | 6 |
| Core unit | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |
| Enabling activities | 3 | 450,000 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |
| National ozone unit | 140 | 40,659,080 | 11,866,367 | 29 | 97 | 69 | 14 | 40 | 4 |
| Project monitoring and coordination | 56 | 6,543,161 | 1,329,699 | 20 | 20 | 36 | 7 | 41 | 6 |
| Refrigeration | 1 | 500,000 | 0 | 0 | 0 | 0 | 0 | 36 | 0 |
| SERVCEE-89/6 | 70 | 6,510,000 | 613,046 | 9 | 26 | 37 | 12 | 45 | 3 |
| Servicing | 234 | 48,570,528 | 10,608,619 | 22 | 113 | 48 | 16 | 44 | 6 |
| Verification | 40 | 1,185,000 | 142,817 | 12 | 13 | 33 | 18 | 30 | 8 |

# There are currently 549 non-investment projects under implementation at a total value of US $126.89 million, with 27 per cent of the funds already disbursed.

# The average number of months from approval to first disbursement is 14 months. On average, ongoing non-investment projects are completed 41 months from the date of approval, which represents a delay of five months.

Ongoing project preparation activities

# Table 7 presents information on the status of project preparation activities under implementation by region and sector.

Table 7. Cumulative ongoing project preparation activities

| Item | Number of projects | Approved funding plus adjustments (US $) | Funds disbursed (US $) | Per cent of funds disbursed (%) | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total | 227 | 17,997,000 | 4,104,498 | 23 | 10 | 32 | 9 |
| Region |  |  |  |  |  |  |  |
| Africa | 86 | 6,790,000 | 1,720,705 | 25 | 9 | 33 | 9 |
| Asia and the Pacific | 77 | 6,219,000 | 1,021,820 | 16 | 13 | 32 | 9 |
| Europe | 16 | 1,155,000 | 308,827 | 27 | 9 | 27 | 4 |
| Global | 1 | 200,000 | 52,334 | 26 | 7 | 13 | 0 |
| Latin America and the Caribbean | 47 | 3,633,000 | 1,000,812 | 28 | 10 | 32 | 8 |
| Sector |  |  |  |  |  |  |  |
| Air-conditioning | 8 | 655,000 | 62,922 | 10 | 9 | 27 | 3 |
| Disposal | 127 | 10,420,000 | 1,390,115 | 13 | 10 | 31 | 6 |
| Foam | 1 | 80,000 | 2,828 | 4 | 7 | 26 | 13 |
| Refrigeration | 6 | 355,000 | 216,775 | 61 | 6 | 24 | 3 |
| Servicing | 85 | 6,487,000 | 2,431,857 | 37 | 11 | 35 | 13 |

# There are currently 227 project preparation activities under implementation at a total value of US $18 million, with 23 per cent of the funds already disbursed.

# The average number of months from approval to first disbursement is 10 months. On average, ongoing preparation activities are completed 32 months from the date of approval, which represents a delay of nine months.

Cancelled projects

# Table 8 presents a summary of cancelled projects.  Since 1991, 292 projects have been cancelled at a total value of US $15.14 million.

Table 8. Cancelled projects summary

| Agency | Number of projects | Approved funding plus adjustment (US $) | Funds disbursed (US $) | Balances (US $) | Consumption to be phased out per proposal (ODP tonnes) | Consumption phased out (ODP tonnes) | Consumption to be phased out per proposal (CO2-eq tonnes) | Consumption phased out (CO2-eq tonnes) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bilateral | 20 | 227,901 | 227,901 | 0 | 223.2 | 0.0 | 0 | 0 |
| UNDP | 81 | 6,895,393 | 6,895,392 | 1 | 673.1 | 0.0 | 0 | 0 |
| UNEP | 23 | 195,325 | 195,325 | 0 | 11.6 | 11.6 | 7,169 | 0 |
| UNIDO | 68 | 6,446,674 | 6,446,674 | -1 | 1,808.2 | 366.6 | 0 | 0 |
| World Bank | 100 | 1,373,519 | 1,373,519 | 0 | 656.7 | 581.1 | 0 | 0 |
| Total | 292 | 15,138,811 | 15,138,811 | 0 | 3,372.8 | 959.3 | 7,169 | 0 |

Annex III

HCFC PHASE-OUT MANAGEMENT PLANS BY COUNTRY 
AS AT 31 DECEMBER 2025

| Country | Approved phase-out (ODP tonnes) | Funds approved (US$) | Funds disbursed (US$) | Balance (US$) | Funds disbursed (%) |
| --- | --- | --- | --- | --- | --- |
| Afghanistan | 8.3 | 884,821 | 540,678 | 344,143 | 61 |
| Albania | 4.1 | 659,960 | 567,416 | 92,543 | 86 |
| Algeria | 35.5 | 3,396,304 | 1,862,734 | 1,533,570 | 55 |
| Angola | 13.4 | 1,338,415 | 746,874 | 591,541 | 56 |
| Antigua and Barbuda | 0.0 | 179,985 | 27,235 | 152,750 | 15 |
| Argentina | 245.5 | 22,669,687 | 14,456,585 | 8,213,102 | 64 |
| Armenia | 4.4 | 912,996 | 678,756 | 234,240 | 74 |
| Bahamas (the) | 3.2 | 481,754 | 356,234 | 125,520 | 74 |
| Bahrain | 50.1 | 1,644,530 | 1,644,367 | 163 | 100 |
| Bangladesh | 59.1 | 8,105,818 | 6,295,481 | 1,810,337 | 78 |
| Barbados | 2.9 | 539,178 | 289,313 | 249,865 | 54 |
| Belize | 2.0 | 689,100 | 461,275 | 227,825 | 67 |
| Benin | 16.1 | 1,070,778 | 845,385 | 225,393 | 79 |
| Bhutan | 0.3 | 569,349 | 430,341 | 139,008 | 76 |
| Bolivia (Plurinational State of) | 4.2 | 784,659 | 656,942 | 127,717 | 84 |
| Bosnia and Herzegovina | 8.2 | 1,353,692 | 1,138,079 | 215,613 | 84 |
| Botswana | 8.2 | 1,156,511 | 629,535 | 526,977 | 54 |
| Brazil | 654.6 | 51,729,108 | 43,248,451 | 8,480,657 | 84 |
| Brunei Darussalam | 2.9 | 792,772 | 402,551 | 390,221 | 51 |
| Burkina Faso | 7.2 | 1,073,630 | 762,873 | 310,757 | 71 |
| Burundi | 1.7 | 545,179 | 346,488 | 198,691 | 64 |
| Cabo Verde | 0.1 | 332,834 | 328,264 | 4,570 | 99 |
| Cambodia | 12.3 | 1,668,675 | 1,392,271 | 276,404 | 83 |
| Cameroon | 49.5 | 3,505,598 | 1,970,005 | 1,535,593 | 56 |
| Central African Republic (the) |  | 45,000 | 45,000 | 0 | 100 |
| Chad | 10.9 | 1,213,856 | 693,005 | 520,851 | 57 |
| Chile | 87.0 | 5,826,186 | 5,238,132 | 588,054 | 90 |
| China | 12,001.0 | 485,758,536 | 440,254,477 | 45,504,058 | 91 |
| Colombia | 201.2 | 12,746,254 | 12,227,186 | 519,068 | 96 |
| Comoros (the) | 0.1 | 309,653 | 159,653 | 150,000 | 52 |
| Congo (the) | 7.1 | 787,180 | 334,183 | 452,997 | 42 |
| Cook Islands (the) | 0.1 | 399,881 | 119,329 | 280,552 | 30 |
| Costa Rica | 24.2 | 2,142,204 | 1,637,886 | 504,318 | 76 |
| Côte d'Ivoire | 42.4 | 3,203,094 | 2,030,802 | 1,172,292 | 63 |
| Croatia | 6.1 | 801,942 | 801,942 | 0 | 100 |
| Cuba | 24.7 | 2,595,320 | 2,226,722 | 368,598 | 86 |
| Democratic People's Republic of Korea (the) | 19.3 | 628,132 | 281,519 | 346,613 | 45 |
| Democratic Republic of the Congo (the) | 9.4 | 832,524 | 584,668 | 247,856 | 70 |
| Djibouti | 0.5 | 403,405 | 164,405 | 239,000 | 41 |
| Dominica | 0.1 | 160,050 | 143,600 | 16,450 | 90 |
| Dominican Republic (the) | 26.6 | 4,902,859 | 4,091,062 | 811,797 | 83 |
| Ecuador | 35.7 | 3,067,511 | 2,913,065 | 154,446 | 95 |
| Egypt | 433.1 | 34,592,812 | 25,932,879 | 8,659,933 | 75 |
| El Salvador | 14.2 | 1,591,249 | 1,132,403 | 458,846 | 71 |
| Equatorial Guinea | 0.9 | 278,180 | 278,180 | 0 | 100 |
| Eritrea | 1.1 | 774,559 | 424,588 | 349,971 | 55 |
| Eswatini | 8.9 | 1,311,931 | 1,024,202 | 287,729 | 78 |
| Ethiopia | 4.5 | 797,127 | 459,398 | 337,729 | 58 |
| Fiji | 2.6 | 702,758 | 388,967 | 313,791 | 55 |
| Gabon | 20.4 | 870,641 | 651,812 | 218,829 | 75 |
| Gambia (the) | 1.0 | 686,599 | 447,534 | 239,065 | 65 |
| Georgia | 4.2 | 1,021,778 | 719,376 | 302,402 | 70 |
| Ghana | 53.7 | 2,325,355 | 1,946,853 | 378,502 | 84 |
| Grenada | 0.5 | 481,289 | 324,683 | 156,606 | 67 |
| Guatemala | 7.1 | 909,672 | 656,508 | 253,164 | 72 |
| Guinea | 4.3 | 658,941 | 548,042 | 110,899 | 83 |
| Guinea-Bissau | 2.0 | 632,349 | 321,617 | 310,732 | 51 |
| Guyana | 1.1 | 681,602 | 403,102 | 278,500 | 59 |
| Haiti | 0.9 | 364,291 | 116,291 | 248,000 | 32 |
| Honduras | 15.0 | 1,495,962 | 1,022,686 | 473,277 | 68 |
| India | 1,237.1 | 75,278,333 | 61,761,854 | 13,516,480 | 82 |
| Indonesia | 275.1 | 20,366,731 | 16,810,513 | 3,556,218 | 83 |
| Iran (Islamic Republic of) | 339.7 | 21,304,667 | 16,380,207 | 4,924,460 | 77 |
| Iraq | 22.0 | 2,046,093 | 1,286,647 | 759,446 | 63 |
| Jamaica | 11.8 | 1,036,797 | 700,634 | 336,163 | 68 |
| Jordan | 72.9 | 6,999,141 | 6,090,029 | 909,112 | 87 |
| Kenya | 14.1 | 1,973,000 | 1,492,130 | 480,870 | 76 |
| Kiribati | 0.1 | 491,821 | 119,894 | 371,927 | 24 |
| Kuwait | 322.6 | 11,637,046 | 9,786,221 | 1,850,825 | 84 |
| Kyrgyzstan | 3.2 | 799,488 | 799,488 | 0 | 100 |
| Lao People's Democratic Republic (the) | 1.5 | 683,925 | 491,153 | 192,772 | 72 |
| Lebanon | 73.6 | 7,113,759 | 6,780,103 | 333,656 | 95 |
| Lesotho | 0.5 | 711,300 | 447,587 | 263,713 | 63 |
| Liberia | 4.7 | 941,500 | 459,560 | 481,940 | 49 |
| Libya | 46.7 | 2,911,540 | 1,456,209 | 1,455,331 | 50 |
| Madagascar | 12.7 | 1,192,673 | 768,199 | 424,473 | 64 |
| Malawi | 7.3 | 983,487 | 909,601 | 73,886 | 92 |
| Malaysia | 338.8 | 20,975,702 | 15,686,709 | 5,288,993 | 75 |
| Maldives | 0.6 | 1,081,613 | 1,081,613 | 0 | 100 |
| Mali | 10.1 | 1,065,523 | 514,523 | 551,000 | 48 |
| Marshall Islands (the) | 0.2 | 316,430 | 125,848 | 190,582 | 40 |
| Mauritania | 4.5 | 607,345 | 333,933 | 273,412 | 55 |
| Mauritius | 3.1 | 902,500 | 603,492 | 299,008 | 67 |
| Mexico | 704.2 | 33,239,212 | 27,947,854 | 5,291,358 | 84 |
| Micronesia (Federated States of) | 0.1 | 562,458 | 158,656 | 403,802 | 28 |
| Mongolia | 1.1 | 835,769 | 491,858 | 343,911 | 59 |
| Montenegro | 0.8 | 1,033,593 | 733,327 | 300,266 | 71 |
| Morocco | 35.6 | 2,378,958 | 1,853,125 | 525,833 | 78 |
| Mozambique | 3.7 | 692,005 | 471,900 | 220,105 | 68 |
| Myanmar | 0.4 | 174,040 | 174,040 | 0 | 100 |
| Namibia | 8.9 | 1,020,000 | 793,807 | 226,193 | 78 |
| Nauru | 0.0 | 214,804 | 73,414 | 141,390 | 34 |
| Nepal | 1.1 | 592,854 | 313,195 | 279,659 | 53 |
| Nicaragua | 5.2 | 723,572 | 615,563 | 108,009 | 85 |
| Niger (the) | 10.8 | 910,340 | 767,632 | 142,708 | 84 |
| Nigeria | 264.1 | 15,347,246 | 13,079,980 | 2,267,266 | 85 |
| Niue | 0.0 | 180,659 | 76,174 | 104,485 | 42 |
| North Macedonia | 2.5 | 1,438,851 | 1,250,548 | 188,303 | 87 |
| Oman | 27.8 | 1,893,469 | 1,341,044 | 552,425 | 71 |
| Pakistan | 193.5 | 14,726,769 | 11,951,742 | 2,775,027 | 81 |
| Palau | 0.1 | 419,500 | 159,750 | 259,750 | 38 |
| Panama | 19.7 | 1,715,240 | 1,412,106 | 303,134 | 82 |
| Papua New Guinea | 3.4 | 1,250,000 | 1,091,404 | 158,596 | 87 |
| Paraguay | 13.5 | 1,393,132 | 950,657 | 442,475 | 68 |
| Peru | 32.8 | 1,932,034 | 1,237,403 | 694,631 | 64 |
| Philippines (the) | 91.1 | 5,965,242 | 3,319,503 | 2,645,739 | 56 |
| Qatar | 23.9 | 1,630,841 | 1,278,478 | 352,363 | 78 |
| Republic of Moldova (the) | 0.7 | 537,872 | 357,171 | 180,701 | 66 |
| Rwanda | 3.0 | 717,874 | 448,060 | 269,814 | 62 |
| Saint Kitts and Nevis | 0.3 | 164,442 | 164,442 | 0 | 100 |
| Saint Lucia | 0.8 | 713,393 | 327,009 | 386,384 | 46 |
| Saint Vincent and the Grenadines | 0.2 | 568,942 | 355,702 | 213,241 | 63 |
| Samoa | 0.2 | 532,950 | 204,734 | 328,216 | 38 |
| Sao Tome and Principe | 0.1 | 154,727 | 154,727 | 0 | 100 |
| Saudi Arabia | 551.0 | 13,111,757 | 7,326,746 | 5,785,011 | 56 |
| Senegal | 10.4 | 1,325,663 | 803,226 | 522,437 | 61 |
| Serbia | 7.9 | 1,256,665 | 1,091,002 | 165,664 | 87 |
| Seychelles | 1.4 | 700,000 | 428,063 | 271,937 | 61 |
| Sierra Leone | 1.1 | 718,530 | 502,257 | 216,273 | 70 |
| Solomon Islands | 1.8 | 710,004 | 302,384 | 407,620 | 43 |
| Somalia | 7.7 | 986,205 | 540,630 | 445,575 | 55 |
| South Africa | 302.6 | 12,157,615 | 9,409,117 | 2,748,498 | 77 |
| South Sudan | 0.6 | 210,000 | 90,500 | 119,500 | 43 |
| Sri Lanka | 16.2 | 1,548,741 | 979,859 | 568,882 | 63 |
| Sudan (the) | 49.0 | 4,330,964 | 2,715,563 | 1,615,401 | 63 |
| Suriname | 1.2 | 410,895 | 229,892 | 181,002 | 56 |
| Syrian Arab Republic | 44.7 | 4,312,296 | 1,917,853 | 2,394,443 | 44 |
| Thailand | 284.7 | 20,540,540 | 19,424,241 | 1,116,299 | 95 |
| Timor-Leste | 1.3 | 672,371 | 509,727 | 162,644 | 76 |
| Togo | 13.5 | 952,823 | 842,553 | 110,270 | 88 |
| Tonga | 0.1 | 491,659 | 195,850 | 295,809 | 40 |
| Trinidad and Tobago | 31.2 | 2,596,444 | 2,052,682 | 543,762 | 79 |
| Tunisia | 29.7 | 2,427,920 | 2,019,091 | 408,829 | 83 |
| Türkiye | 630.2 | 13,905,390 | 12,245,957 | 1,659,433 | 88 |
| Turkmenistan | 4.6 | 955,979 | 902,082 | 53,897 | 94 |
| Tuvalu | 0.1 | 246,969 | 115,137 | 131,833 | 47 |
| Uganda | 0.2 | 504,823 | 296,246 | 208,577 | 59 |
| United Republic of Tanzania (the) | 1.2 | 462,271 | 398,144 | 64,127 | 86 |
| Uruguay | 22.8 | 1,943,138 | 1,562,413 | 380,725 | 80 |
| Vanuatu | 0.3 | 613,850 | 233,453 | 380,397 | 38 |
| Venezuela (Bolivarian Republic of) | 76.1 | 3,220,110 | 3,084,286 | 135,824 | 96 |
| Viet Nam | 317.3 | 17,449,332 | 14,219,904 | 3,229,428 | 81 |
| Zambia | 3.3 | 800,953 | 473,723 | 327,230 | 59 |
| Zimbabwe | 18.1 | 1,721,318 | 1,486,292 | 235,026 | 86 |
| Region: Asia and the Pacific |  | 2,147,298 | 806,162 | 1,341,135 | 38 |
| Grand total | 20,947.9 | 1,070,599,738 | 896,470,073 | 174,129,666 | 84 |

Annex IV

AN OVERVIEW OF HFC-RELATED PROJECTS AND ACTIVITIES

# Since its 80th meeting, the Executive Committee has approved funding for the implementation of HFC investment projects and enabling activities to help national ozone units fulfil their initial obligations with regard to HFC phase-down in line with the Kigali Amendment (decision 79/46).

# As of 31 December 2025, the Executive Committee has approved 855 HFC-related projects and activities in 143 countries and two regions, consisting of 199 requests for project preparation related to HFC phase-down including Kigali HFC implementation plans (KIPs), 133 project preparation for national inventory of banks per decision 91/66, 15 investment projects, 211 projects related to stage I of KIPs, nine technical assistance projects, 127 technical assistance projects for survey of ODS alternatives at the national level and 161 enabling activities projects amounting to US $132.38 million (excluding support costs).

# Table 1 presents an overview of all HFC-related projects and activities under the Multilateral Fund, irrespective of their source of funding, at the country level, indicating the status of ratification of the Kigali Amendment and the status of the HFC licensing system.

Table 1. Overview of all HFC-related projects and activities under the Multilateral Fund

| Country | Group | Ratification of Kigali Amendment | Implem-entation of licensing system | Funds approved for (US $) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Enabling activities | Investment projects | KIP | ODS surveys | Project preparation | Preparation of national inventory of banks (91/66) | Technical assistance |
| Afghanistan | I |  |  | 136,888 |  |  | 59,742 |  | 90,000 |  |
| Albania | I | Yes | √ | 94,978 |  | 179,390 | 40,000 | 125,989 | 80,000 | 15,000 |
| Algeria | I |  |  | 144,799 |  |  | 0 |  | 90,000 |  |
| Angola | I | Yes | √ | 142,397 |  | 385,563 | 70,000 | 170,000 | 90,000 |  |
| Antigua and Barbuda | I |  |  | 50,000 |  |  | 19,116 |  | 70,000 |  |
| Argentina | I | Yes | √ | 250,000 | 7,535,648 |  | 127,201 | 294,816 | 100,000 |  |
| Armenia | I | Yes | √ | 149,639 |  | 165,075 | 70,000 | 168,689 | 90,000 |  |
| Bahamas (the) | I | Yes | √ | 95,000 |  |  | 10,000 | 130,000 | 80,000 |  |
| Bahrain | II | Yes | √ | 140,240 |  |  | 104,417 | 190,000 |  |  |
| Bangladesh | I | Yes | √ | 135,667 | 3,131,610 |  | 53,480 | 190,000 | 90,000 |  |
| Barbados | I | Yes | √ |  |  |  | 39,646 | 130,000 | 80,000 |  |
| Belize | I | Yes | √ | 89,576 |  |  | 37,626 | 130,000 | 80,000 |  |
| Benin | I | Yes | √ | 128,885 |  | 177,500 | 55,000 | 162,256 | 90,000 |  |
| Bhutan | I | Yes | √ | 49,654 |  |  | 39,728 | 100,000 | 70,000 |  |
| Bolivia (Plurinational State of) | I | Yes | √ | 150,000 |  | 194,000 | 69,934 | 165,406 | 90,000 |  |
| Bosnia and Herzegovina | I | Yes | √ | 94,920 |  | 216,000 | 40,000 | 130,000 | 80,000 |  |
| Botswana | I | Yes | √ | 96,648 |  | 95,500 | 70,000 | 170,000 | 90,000 |  |
| Brazil | I | Yes | √ |  |  |  |  | 230,000 |  |  |
| Brunei Darussalam | I | Yes | √ | 119,812 |  |  | 34,781 | 170,000 | 90,000 |  |
| Burkina Faso | I | Yes | √ | 145,443 |  | 162,500 | 55,000 | 190,000 | 90,000 |  |
| Burundi | I | Yes | √ | 100,000 |  |  | 70,000 | 170,000 | 90,000 |  |
| Cabo Verde | I | Yes | √ | 79,038 |  |  | 40,000 | 130,000 | 80,000 |  |
| Cambodia | I | Yes | √ | 147,918 |  | 250,110 | 35,000 | 159,133 | 90,000 |  |
| Cameroon | I | Yes | √ | 149,324 |  | 355,500 | 109,882 | 190,000 | 90,000 |  |
| Central African Republic (the) | I | Yes | Pending | 150,000 |  |  |  |  | 90,000 |  |
| Chad | I | Yes | √ | 130,200 |  | 216,000 | 69,980 | 158,410 | 90,000 |  |
| Chile | I | Yes | √ | 131,337 |  | 876,507 | 55,000 | 173,913 | 90,000 |  |
| China | I | Yes | √ | 244,685 | 1,274,967 |  |  | 47,687 |  |  |
| Colombia | I | Yes | √ | 246,344 |  | 2,813,811 | 65,000 | 418,012 |  |  |
| Comoros (the) | I | Yes | √ | 45,242 |  |  | 39,989 | 100,000 | 70,000 |  |
| Congo (the) | I | Yes | √ | 149,841 |  | 81,500 | 70,000 | 138,863 | 90,000 | 30,000 |
| Cook Islands (the) | I | Yes | √ | 47,711 |  | 23,250 | 34,628 |  | 24,000 |  |
| Costa Rica | I | Yes | √ | 144,830 |  | 370,968 | 70,000 | 170,000 | 90,000 |  |
| Cote d'Ivoire | I | Yes | √ | 135,605 |  |  | 109,970 | 190,000 | 90,000 |  |
| Cuba | I | Yes | √ | 146,408 |  | 160,000 | 69,987 | 170,000 | 90,000 | 30,000 |
| Democratic People's Republic of Korea (the) | I | Yes | √ |  |  |  |  |  |  |  |
| Democratic Republic of the Congo (the) | I |  |  | 132,234 |  |  | 110,000 |  | 90,000 |  |
| Djibouti | I | Yes | Pending | 22,422 |  |  | 40,000 |  |  |  |
| Dominica | I |  |  | 40,000 |  |  |  |  | 70,000 |  |
| Dominican Republic (the) | I | Yes | √ | 149,518 | 129,801 | 535,930 | 53,962 | 201,572 | 90,000 |  |
| Ecuador | I | Yes | √ | 120,725 |  | 560,272 | 109,580 | 214,127 | 90,000 |  |
| Egypt | I | Yes | √ | 246,050 |  | 10,786,475 |  | 387,964 | 100,000 |  |
| El Salvador | I | Yes | √ | 149,478 |  | 180,000 | 69,735 | 170,000 | 90,000 |  |
| Equatorial Guinea | I |  |  | 113,154 |  |  | 60,000 |  | 90,000 |  |
| Eritrea | I | Yes | √ | 92,822 |  | 89,908 | 40,000 | 130,000 | 80,000 |  |
| Eswatini | I | Yes | √ | 94,509 |  | 63,500 | 70,000 | 130,000 | 80,000 |  |
| Ethiopia | I | Yes | √ | 94,208 |  | 102,000 | 40,000 | 130,000 | 80,000 |  |
| Fiji | I | Yes | √ | 147,699 |  | 102,000 |  | 130,000 | 54,000 |  |
| Gabon | I | Yes | √ | 134,202 |  |  | 110,000 | 190,000 | 90,000 |  |
| Gambia (the) | I | Yes | √ | 94,947 |  | 80,150 | 25,000 | 120,250 | 80,000 |  |
| Georgia | I | Yes | √ | 95,000 |  | 204,500 | 40,000 | 130,000 | 80,000 |  |
| Ghana | I | Yes | √ | 149,425 |  | 188,000 | 55,000 | 189,590 | 90,000 |  |
| Grenada | I | Yes | √ | 46,491 |  | 72,500 | 40,000 | 93,571 | 70,000 |  |
| Guatemala | I | Yes | √ | 128,267 |  | 261,019 | 70,000 | 170,000 | 90,000 |  |
| Guinea | I | Yes | √ | 100,000 |  | 411,400 | 109,890 | 190,000 | 90,000 |  |
| Guinea-Bissau | I | Yes | √ | 70,803 |  | 167,500 | 40,000 | 130,000 | 80,000 |  |
| Guyana | I |  |  | 55,000 |  |  | 32,626 |  | 80,000 |  |
| Haiti | I | Yes | Pending | 90,311 |  |  |  |  |  |  |
| Honduras | I | Yes | √ | 149,931 |  | 296,918 | 70,000 | 170,000 | 90,000 |  |
| India | II | Yes | √ | 250,000 | 846,326 |  |  | 120,000 |  |  |
| Indonesia | I | Yes | √ | 246,666 |  | 3,120,409 |  | 300,000 | 100,000 |  |
| Iran (Islamic Republic of) | II |  |  | 218,403 |  |  | 106,496 |  | 100,000 |  |
| Iraq | II |  |  | 168,030 |  |  | 95,520 |  | 100,000 |  |
| Jamaica | I |  |  | 145,083 |  |  | 21,971 |  | 90,000 |  |
| Jordan | I | Yes | √ | 127,708 | 1,524,566 | 2,540,680 | 55,000 | 190,000 | 90,000 |  |
| Kenya | I | Yes | √ | 149,348 |  |  | 97,250 | 190,000 | 90,000 |  |
| Kiribati | I | Yes | √ | 32,898 |  | 15,000 | 40,000 |  | 13,000 |  |
| Kuwait | II | Yes | √ | 138,000 |  |  | 118,675 | 220,000 |  |  |
| Kyrgyzstan | I | Yes | √ | 95,000 |  | 81,000 | 20,000 | 113,690 | 80,000 | 30,000 |
| Lao People's Democratic Republic (the) | I | Yes | √ | 54,082 |  | 110,000 | 40,000 | 128,942 | 80,000 |  |
| Lebanon | I | Yes | √ | 149,979 | 1,039,874 | 1,869,792 | 100,476 | 317,134 | 90,000 |  |
| Lesotho | I | Yes | √ | 94,532 |  | 82,000 | 40,000 | 128,709 | 80,000 |  |
| Liberia | I | Yes | √ | 95,000 |  | 72,500 | 40,000 | 130,000 | 80,000 |  |
| Libya | I |  |  | 147,508 |  |  | 109,761 |  | 100,000 |  |
| Madagascar | I | Yes | Pending | 115,554 |  |  | 110,000 |  | 90,000 |  |
| Malawi | I | Yes | √ | 149,954 |  | 68,000 | 70,000 | 167,662 | 90,000 | 30,000 |
| Malaysia | I | Yes | √ | 250,000 |  | 3,042,912 |  | 330,000 | 100,000 |  |
| Maldives | I | Yes | √ | 94,801 |  |  | 20,000 | 130,000 | 80,000 |  |
| Mali | I | Yes | √ | 148,069 |  |  | 70,000 | 170,000 | 90,000 |  |
| Marshall Islands (the) | I | Yes | √ | 37,583 |  | 11,750 | 27,222 |  | 19,000 |  |
| Mauritania | I | Yes | √ | 102,338 |  |  |  |  |  |  |
| Mauritius | I | Yes | √ | 139,622 |  | 103,000 | 70,000 | 170,000 | 90,000 |  |
| Mexico | I | Yes | √ | 240,755 | 3,756,960 | 6,746,923 | 89,701 | 421,255 | 100,000 |  |
| Micronesia (Federated States of) | I | Yes | √ | 48,247 |  | 63,500 | 32,937 |  | 27,000 |  |
| Mongolia | I | Yes | √ | 92,866 |  | 81,000 | 20,000 | 210,000 | 80,000 |  |
| Montenegro | I | Yes | √ | 49,973 |  | 115,050 | 39,365 | 98,398 | 70,000 |  |
| Morocco | I | Yes | √ | 94,725 |  | 890,335 | 0 | 220,000 | 90,000 |  |
| Mozambique | I | Yes | √ | 149,330 |  | 169,500 | 67,395 | 160,300 |  | 30,000 |
| Myanmar | I |  |  | 53,623 |  |  | 22,218 |  |  |  |
| Namibia | I | Yes | √ | 147,673 |  |  | 70,000 | 170,000 | 90,000 |  |
| Nauru | I | Yes | √ | 34,339 |  | 10,500 | 22,275 |  | 13,000 |  |
| Nepal | I | Yes | √ | 48,984 |  |  | 40,000 |  | 80,000 |  |
| Nicaragua | I | Yes | √ | 150,000 |  | 159,000 | 70,000 | 168,385 | 7,156 |  |
| Niger (the) | I | Yes | √ | 148,244 |  | 279,500 | 66,712 | 170,000 | 90,000 |  |
| Nigeria | I | Yes | √ | 245,868 |  | 2,738,360 | 65,000 | 216,380 | 100,000 |  |
| Niue | I | Yes | √ | 33,863 |  | 9,250 | 29,148 |  | 13,000 |  |
| North Macedonia | I | Yes | √ | 95,000 |  | 103,555 | 39,987 | 130,000 | 80,000 | 30,000 |
| Oman | II | Yes | √ | 129,061 |  |  | 105,680 | 190,000 | 90,000 |  |
| Pakistan | II | Yes | √ | 247,420 |  |  | 130,000 | 220,000 | 100,000 |  |
| Palau | I | Yes | √ | 25,000 |  | 57,500 | 40,000 |  | 18,000 |  |
| Panama | I | Yes | √ | 149,825 |  | 331,100 | 110,000 | 190,000 | 90,000 |  |
| Papua New Guinea | I | Yes | √ | 95,000 |  |  | 40,000 | 130,000 | 80,000 |  |
| Paraguay | I | Yes | √ | 143,084 |  | 235,675 | 68,855 | 167,197 | 90,000 |  |
| Peru | I | Yes | √ | 147,582 |  | 283,140 | 105,085 | 185,925 | 90,000 |  |
| Philippines (the) | I | Yes | √ | 207,289 |  |  | 130,000 | 300,000 | 100,000 |  |
| Qatar | II |  |  | 150,000 |  |  |  |  |  |  |
| Republic of Moldova (the) | I | Yes | √ | 38,716 |  | 95,500 | 19,362 | 130,000 | 80,000 |  |
| Rwanda | I | Yes | √ | 91,190 |  | 75,900 | 40,000 | 130,000 | 80,000 |  |
| Saint Kitts and Nevis | I | Yes | √ | 50,000 |  |  |  |  | 70,000 |  |
| Saint Lucia | I | Yes | √ | 57,000 |  | 70,000 | 31,992 | 98,894 | 80,000 |  |
| Saint Vincent and the Grenadines | I | Yes | √ | 50,000 |  |  |  | 100,000 | 70,000 |  |
| Samoa | I | Yes | √ | 49,018 |  | 66,000 | 38,299 |  | 24,000 |  |
| Sao Tome and Principe | I | Yes | √ | 83,915 |  |  | 30,000 | 130,000 | 80,000 |  |
| Saudi Arabia | II | Yes | √ | 193,170 |  |  | 137,972 |  |  |  |
| Senegal | I | Yes | √ | 137,814 |  | 295,500 | 109,550 | 163,726 | 90,000 |  |
| Serbia | I | Yes | √ | 143,900 |  | 300,000 | 69,579 | 170,000 | 90,000 |  |
| Seychelles | I | Yes | √ | 95,000 |  | 81,680 | 40,000 | 120,200 | 80,000 |  |
| Sierra Leone | I | Yes | √ | 94,741 |  | 86,500 | 40,000 | 130,000 | 80,000 |  |
| Solomon Islands | I | Yes | √ | 88,655 |  | 74,125 | 40,000 |  | 24,000 |  |
| Somalia | I | Yes | √ | 144,313 |  | 194,000 |  | 170,000 | 90,000 |  |
| South Africa | I | Yes | √ | 193,367 |  | 1,720,164 |  | 220,000 | 100,000 |  |
| South Sudan | I |  |  | 94,791 |  |  |  |  |  |  |
| Sri Lanka | I | Yes | √ | 149,023 |  | 247,211 | 35,000 | 249,128 | 90,000 |  |
| Sudan (the) | I |  |  | 143,823 |  |  | 103,178 | 30,000 |  |  |
| Suriname | I |  |  | 65,650 |  |  | 38,030 |  | 80,000 |  |
| Syrian Arab Republic | I | Yes | √ | 199,235 |  |  |  | 216,790 | 100,000 |  |
| Thailand | I | Yes | √ | 247,414 | 183,514 |  | 120,000 | 250,000 | 100,000 |  |
| Timor-Leste | I |  |  | 46,669 |  |  | 21,274 |  | 70,000 |  |
| Togo | I | Yes | √ | 129,488 |  | 187,500 | 35,000 | 149,732 | 90,000 |  |
| Tonga | I | Yes | √ | 48,745 |  | 60,750 | 37,779 |  | 24,000 |  |
| Trinidad and Tobago | I | Yes | √ | 145,733 |  | 543,249 | 82,387 | 190,000 | 90,000 |  |
| Tunisia | I | Yes | √ | 149,990 |  | 1,576,566 | 110,000 | 185,306 | 90,000 |  |
| Türkiye | I | Yes | √ | 194,675 |  | 2,789,430 | 91,277 | 357,460 | 100,000 |  |
| Turkmenistan | I | Yes | √ | 148,955 |  | 257,000 | 68,597 | 168,520 | 90,000 |  |
| Tuvalu | I | Yes | √ | 25,631 |  | 12,250 | 40,000 |  | 13,000 |  |
| Uganda | I | Yes | √ | 49,763 |  |  | 38,778 | 100,000 | 70,000 |  |
| United Republic of Tanzania (the) | I | Yes | √ | 94,185 |  | 95,500 | 40,000 | 130,000 | 80,000 |  |
| Uruguay | I | Yes | √ | 148,495 |  | 176,787 | 102,511 | 190,000 | 90,000 |  |
| Vanuatu | I | Yes | √ | 46,845 |  | 31,625 | 34,159 |  | 24,000 |  |
| Venezuela (Bolivarian Republic of) | I | Yes | √ | 247,721 |  |  | 124,375 | 220,000 | 100,000 |  |
| Viet Nam | I | Yes | √ | 249,238 |  | 2,019,488 | 45,000 | 250,000 | 100,000 |  |
| Yemen | I |  |  | 250,000 |  |  |  |  | 100,000 |  |
| Zambia | I | Yes | √ | 94,254 |  |  | 40,000 | 130,000 | 80,000 |  |
| Zimbabwe | I | Yes | √ | 140,551 |  | 668,454 | 70,000 | 189,804 | 90,000 |  |
| Region: Asia and the Pacific |  |  |  |  |  | 542,500 |  | 780,000 | 640,000 |  |
| Global |  |  |  |  |  |  |  |  |  | 934,815 |
| Total |  |  |  | 17,479,803 | 19,423,266 | 56,483,856 | 7,551,727 | 19,443,785 | 10,867,156 | 1,129,815 |

Annex V

AN OVERVIEW OF ENERGY-EFFICIENCY PROJECTS AND ACTIVITIES

| Country | Funds approved (US $) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Funding windows |  |  | Others | Total |
|  | 91/65 | 94/60 | 95/87 |  |  |
| Albania | 219,000 |  |  |  | 219,000 |
| Argentina |  | 42,000 |  |  | 42,000 |
| Bolivia (Plurinational State of) | 96,000 |  |  |  | 96,000 |
| Bosnia and Herzegovina | 278,000 |  |  |  | 278,000 |
| Cameroon | 120,000 |  |  |  | 120,000 |
| Chile | 780,000 |  |  |  | 780,000 |
| China | 25,000 |  |  |  | 25,000 |
| Colombia | 506,319 |  |  |  | 506,319 |
| Costa Rica | 260,000 |  |  |  | 260,000 |
| Cuba | 360,000 |  |  |  | 360,000 |
| Dominican Republic (the) | 300,000 |  |  |  | 300,000 |
| Ecuador | 190,000 |  |  |  | 190,000 |
| Egypt | 315,000 | 17,319,530 |  |  | 17,634,530 |
| El Salvador | 125,000 |  |  |  | 125,000 |
| Georgia | 223,000 |  |  |  | 223,000 |
| Ghana | 30,000 |  |  |  | 30,000 |
| Grenada |  |  | 100,000 |  | 100,000 |
| Guatemala | 151,000 |  |  |  | 151,000 |
| Honduras | 278,068 |  |  |  | 278,068 |
| India | 2,033,795 |  |  |  | 2,033,795 |
| Indonesia |  | 35,000 |  |  | 35,000 |
| Kyrgyzstan | 206,000 |  |  |  | 206,000 |
| Lebanon | 186,000 |  |  |  | 186,000 |
| Malaysia | 530,000 | 415,689 |  |  | 945,689 |
| Mexico | 938,620 |  |  |  | 938,620 |
| Montenegro | 120,000 |  |  |  | 120,000 |
| Morocco | 266,000 | 1,234,756 |  |  | 1,500,756 |
| Nicaragua | 1,961 |  |  |  | 1,961 |
| Nigeria | 145,000 | 78,000 |  |  | 223,000 |
| North Macedonia | 271,000 |  |  |  | 271,000 |
| Panama | 342,000 |  |  |  | 342,000 |
| Paraguay | 211,500 |  |  |  | 211,500 |
| Peru | 115,000 |  |  |  | 115,000 |
| Republic of Moldova (the) | 180,000 |  |  |  | 180,000 |
| Rwanda | 30,000 |  |  |  | 30,000 |
| Serbia | 316,000 |  |  |  | 316,000 |
| Sierra Leone | 286,139 |  |  |  | 286,139 |
| South Africa | 350,000 | 30,000 |  |  | 380,000 |
| Sri Lanka | 245,700 |  |  |  | 245,700 |
| Thailand |  |  | 100,000 | 150,000 | 250,000 |
| Togo | 311,800 |  |  |  | 311,800 |
| Tunisia | 170,000 | 1,367,360 |  |  | 1,537,360 |
| Türkiye |  | 70,000 | 100,000 |  | 170,000 |
| Turkmenistan | 142,000 |  |  |  | 142,000 |
| Uganda | 465,200 |  |  |  | 465,200 |
| Uruguay | 300,000 |  |  |  | 300,000 |
| Global | 80,000 |  | 200,000 | 793,200 | 1,073,200 |
| Grand total | 12,500,102 | 20,592,335 | 500,000 | 943,200 | 34,535,637 |

UNEP/OzL.Pro/ExCom/99/1

Progress reports were submitted by the following agencies: Australia, Austria, France, Germany, Italy, Japan, Spain and the United Kingdom of Great Britain and Northern Ireland, UNDP, UNEP, UNIDO, and the World Bank (documents UNEP/OzL.Pro/ExCom/99/14 to UNEP/OzL.Pro/ExCom/99/18).

The Executive Committee requested that detailed information on a project-by-project basis be made available to Committee members, with a printout available upon request (decision 19/23). The database for the Consolidated Progress Report is provided on the 99th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

Annexes XXIX and XXX to document UNEP/OzL.Pro/ExCom/96/66

At its 77th meeting, the Executive Committee accepted, with appreciation, the additional contributions announced by 17 non-Article 5 Parties to provide fast start support for implementation of the Kigali Amendment, noting that such funding was one-time in nature and would not displace donor contributions. The contributing parties are Australia, Canada, Denmark, Finland, France, Germany, Ireland, Italy, Japan, Luxembourg, Netherlands, New Zealand, Norway, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland, and United States of America.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 99th meeting.

Excluding those that are considered in the relevant project proposal documents or under reports on projects with specific reporting requirements (UNEP/OzL.Pro/ExCom/99/19 and UNEP/OzL.Pro/ExCom/99/20).

Ongoing projects are all projects that were under implementation as at 31 December 2025. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Including 12,775 mt of HFC-related projects. Cost-effectiveness in CO2-eq is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies. The cost-effectiveness for MYAs of HPMPs is US $32.17/kg ODP, for stage I of HPPMP is US $23.93/kg ODP and for stage II of HPPMP is US $4.16/kg ODP.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61). Pursuant to decision 84/45(c), MYA components are subjected to procedure for cancellation.

UNEP/OzL.Pro/ExCom/99/87

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.

Completed projects/activities are defined in decisions 17/22 and 19/23 as projects that have been commissioned and where the ODS addressed has been phased out. A further decision (decision 28/2) extends the definition to cover situations where no further use of CFCs in the sectors covered is in evidence, where an alternative product is being produced (and/or production has begun), and where the equipment using CFCs has been destroyed/dismantled/rendered unusable with respect to ODSs. Work programme activities without an ODS phase-out are considered completed when the activity is finished (e.g., for a workshop, when it has been conducted). This definition has been applied for HCFC-related projects.

The reason that 100 per cent of funds have not been disbursed for completed projects is that it may take from six months to one year to finalise accounting records.