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Addendum

TRANCHE SUBMISSION DELAYS

This document is issued to:
· Add to the end of paragraph 10 the following sentence:

“As reported in document UNEP/OzL.Pro/ExCom/90/2, this recommendation has since then been closed by OIOS, considering it as implemented.”
· Replace in the table contained in Annex I the rows for Algeria and for total, and add a row for Argentina as follows: 

	Country
	Agency
	Tranche
	Amount (with support costs)
(US $)
	Reason for delay/withdrawal
	Recommendations

	Algeria (Stage I)
	UNIDO
	2014 and 2017
	197,898
	Government decisions/ endorsements/changes in the NOU/lack of verification report/ enterprise delays
	Noting that the mandatory verification of HCFC consumption targets has not been completed and the enterprise manufacturing air-conditioners that was supported under HPMP is using R-410A as a refrigerant in place of HFC-32, and urging the Government of Algeria to work with UNIDO  to provide a status report on the use of HFC-32 as a refrigerant in the enterprise manufacturing air‑conditioners to the 91st meeting, and to complete the verification so that the third (2014) and fourth (2017) tranches of stage I of the HPMP could be submitted to the 92nd meeting with a revised plan of action to take into account the reallocation of the 2014 and subsequent tranches. 

	Argentina 
(Stage II)
	UNIDO
	2021
	4,160,214
	COVID-19 pandemic disruption/20 per cent disbursement threshold
	Noting that the third (2021) tranche of stage II of the HPMP submitted to the 90th meeting had been withdrawn as the overall disbursement rate of the second (2019) tranche of the HPMP was below the 20 per cent threshold, and urging the Government of Argentina to work with UNIDO so that the third (2021) tranche of stage II could be submitted to the 91st meeting with a revised plan of action to take into account the reallocation of the 2021 and subsequent tranches, on the understanding that the 20 per cent disbursement threshold for funding of the previous tranche had been achieved.

	Total
	
	
	
	10,881,602
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