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UPDATE ON THE STATUS OF IMPLEMENTATION OF 
THE 2019–2021 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND


Introduction

This document consists of:
Part I:	An update on the status of the implementation of the 2019–2021 business plans

Part II:	Resource allocation for the 2018–2020 triennium

Part III: Reports on dialogues concerning qualitative performance indicators

	Recommendation.


PART I:	UPDATE ON THE STATUS OF THE IMPLEMENTATION OF THE 2019–2021 BUSINESS PLANS

At its 82nd meeting, the Executive Committee endorsed the 2019–2021 consolidated business plan of the Multilateral Fund. In response to decision 82/45(b) and (c), the Secretariat adjusted the consolidated 2019–2021 business plan, as shown in Table 1. 


Table 1. Resource allocation of the adjusted 2019–2021 consolidated business plans of the Multilateral Fund (US $)
	Item
	2019
	2020
	2021
	Total

	Required for compliance

	Approved HCFC phase-out management plans (HPMPs)
	96,379,090
	111,848,069
	85,792,031
	294,019,190

	HPMP stage I
	0
	353,978
	0
	353,978

	HPMP stage I – additional funding
	0
	645,788
	0
	645,788

	HPMP preparation (PRP) – stage II
	1,414,723
	395,650
	130,800
	1,941,173

	HPMP stage II
	1,761,439
	15,034,014
	5,046,206
	21,841,660

	HCFC production – stage II
	23,496,000
	23,496,000
	23,496,000
	70,488,000

	HPMP PRP – stage III
	246,675
	894,088
	160,500
	1,301,263

	HPMP stage III
	0
	1,299,272
	112,059
	1,411,331

	HPMP verification
	588,600
	588,600
	588,600
	1,765,800

	  Required for compliance subtotal
	123,886,528
	154,555,459
	115,326,196
	393,768,183

	HFC activities

	HFC – enabling activities
	946,950
	0
	0
	946,950

	HFC – investment 
	15,512,484
	0
	0
	15,512,484

	HFC – investment PRP
	62,100
	0
	0
	62,100

	  HFC activities subtotal
	16,521,534
	0
	0
	16,521,534

	Standard activities

	Compliance Assistance Programme (CAP)
	11,300,749
	11,639,772
	11,988,965
	34,929,486

	Core unit
	5,931,915
	5,961,294
	5,990,878
	17,884,086

	Institutional strengthening (IS)
	10,461,285
	10,886,318
	10,546,285
	31,893,889

	Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart
	6,799,233
	6,954,313
	7,114,045
	20,867,591

	Treasurer
	500,000
	500,000
	500,000
	1,500,000

	  Standard activities subtotal
	34,993,182
	35,941,697
	36,140,173
	107,075,052

	Grand total
	175,401,244
	190,497,157
	151,466,369
	517,364,769

	Indicative budget
	174,600,000
	171,000,000
	180,000,000
	525,600,000

	Difference
	801,244
	19,497,157
	-28,533,631
	-8,235,231

	Funding distribution by agency
	 
	 
	 
	 

	France
	78,769
	692,895
	0
	771,664

	Germany
	1,628,838
	2,611,677
	2,394,232
	6,634,747

	Italy
	565,000
	264,840
	0
	829,840

	Japan
	305,529
	90,400
	90,400
	486,329

	UNDP
	31,787,842
	53,743,937
	32,001,629
	117,533,408

	UNEP
	27,738,294
	28,440,307
	25,909,156
	82,087,758

	UNIDO
	59,822,423
	50,437,927
	41,319,974
	151,580,323

	World Bank
	45,586,716
	46,172,260
	41,548,333
	133,307,309

	HPMP verification*
	588,600
	588,600
	588,600
	1,765,800

	Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart
	6,799,233
	6,954,313
	7,114,045
	20,867,591

	Treasurer
	500,000
	500,000
	500,000
	1,500,000


* Funding for the preparation of HPMP verification reports for low-volume-consuming countries (LVC) is approved by the Executive Committee on an annual basis.



Status of implementation of the 2019 business plans
Table 2 sets out the submissions by agency to the 83rd meeting (as at 8 May 2019), and the balance of funds from projects in the 2019 business plans.
Table 2. 2019 consolidated business plan, submissions to the 83rd meeting, and balance (US $)*
	Budget items
	Total value in business plan
	83rd meeting submissions
	Balance (above)/below business plan levels

	Bilateral agencies
	2,578,136
	650,400
	1,927,736

	UNDP
	 31,787,842 
	 20,522,023 
	11,265,819

	UNEP
	 27,738,294 
	 7,610,531 
	20,127,763

	UNIDO
	 59,822,423 
	 14,147,945 
	45,674,478

	World Bank
	45,586,716
	25,138,537
	20,448,179

	HPMP verification
	588,600
	0
	588,600

	Sub-total (agencies)
	168,102,011
	68,069,436
	100,032,575

	Secretariat/Executive Committee/Monitoring and evaluation (excluding Canadian counterpart)
	6,799,233
	0
	6,799,233

	Treasurer
	500,000
	0
	500,000

	Sub-total (standard costs)
	7,299,233
	0
	7,299,233

	Total
	175,401,244
	[bookmark: OLE_LINK1]68,069,436
	107,331,808


* Including core unit costs.

The value of project proposals reviewed or recommended to the 83rd meeting of US $68,069,436 is US $3,034,371 below their value in the 2019 business plan, including US $717,885 associated with project proposals not included in the 2019 business plan.[footnoteRef:1]  [1:  Project preparation for stage II of the HPMPs for Syrian Arab Republic (UNEP), and for Zimbabwe (UNDP); project preparation for stage III of the HPMP for Nigeria (UNIDO); tranches of HPMP for China (2019 tranche for the servicing sector by Germany) and Mozambique (UNIDO); preparation for HFC investment projects for Indonesia (UNDP) and Lebanon (UNDP); and IS project for Cuba (UNDP). ] 

The value of HFC phase-down activities submitted to the 83rd meeting is US $1,849,684 of which US $64,200 is associated with project proposals not included in the 2019 business plan. Annex I to the present document lists HFC-related projects submitted by the implementing agencies to the 83rd meeting. 
All additional contributions by 17 non-Article 5 countries[footnoteRef:2] amounting to US $25,513,071, have been received. Since the 79th meeting, US $25,503,180 has been disbursed for HFC-related enabling activities and projects, with a balance of US $9,891. The accumulated interest accrued from the additional contributions up to 31 December 2018 amounts to US $251,138. In addition, there remains an unspent amount of US $18,003 from consultant fees approved at the 79th meeting.[footnoteRef:3] Therefore, the total amount available for programming additional HFC phase-down activities is US $279,032 for the 83rd meeting.   [2:  Australia, Canada, Denmark, Finland, France, Germany, Ireland, Italy, Japan, Luxembourg, Netherlands (the), New Zealand, Norway, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland and the United States of America.]  [3:  Consultant fees for the evaluation of cost-effective and environmentally sustainable options of HFC-23 destruction from HCFC-22 production facilities (decision 79/47(e)).] 

Table 3 presents the value for activities[footnoteRef:4] included in the 2019 consolidated business plan but not submitted to the 83rd meeting. The list of these activities is contained in Annex II to the present report. [4:  These activities include: 98 HCFC activities for 48 countries (US $65.79 million), 11 HFC activities for ten countries (US $6.56 million), 47 IS projects (US $6.96 million), core unit costs (US $5.93 million) and UNEP CAP (US $11.3 million).] 

Table 3. Activities in the 2019 consolidated business plan not yet submitted 
	Agency
	Value (US $)

	Bilateral 
	2,151,736

	UNDP
	14,246,673

	UNEP
	19,798,737

	UNIDO
	37,668,288

	World Bank
	22,090,716

	HPMP verification reports
	588,600

	Total
	[bookmark: OLE_LINK2]96,544,750



Forward commitments

The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2019 to 2031 is US $636.41 million, assuming that the funding requests of MYAs submitted to the 83rd meeting will be approved in principle, as shown in Table 4.
Table 4. Forward commitments (2019–2031) (US $000)
	Description
	2019
	2020
	2021
	2022
	2023
	2024
	2025
	2026
	2027
	2030
	2031
	Total

	Approved in principle*
	109,215
	128,389
	95,710
	78,374
	40,142
	33,458
	28,641
	26,657
	17,094
	212
	57
	557,948

	Submitted to 83rd meeting
	26,155
	26,155
	26,155
	0
	0
	0
	0
	0
	0
	0
	0
	78,465

	Total 
	135,370
	154,544
	121,865
	78,374
	40,142
	33,458
	28,641
	26,657
	17,094
	212
	57
	636,413


*Including revised HPMP agreements.

PART II: RESOURCE ALLOCATION FOR THE 2018-2020 TRIENNIUM

The resources approved by the Parties to the Montreal Protocol for the 2018–2020 triennium[footnoteRef:5] amount to US $540,000,000. Of this amount, US $144,488,023 had been allocated to activities approved in 2018, with US $395,511,977 remaining for 2019 and 2020.  [5:  Decision XXIX/1. ] 

The value of the activities reviewed or recommended to the 83rd meeting, remaining activities in the business plan and the operation of the Secretariat/Executive Committee/Monitoring and evaluation and Treasurer for the period 2019 and 2020, amounts to US $362,410,576, and is below the resources available by US $33,101,402 as shown in Table 5.
Table 5: Resource allocation for 2019 and 2020 (US$)
	Description
	2019
	2020
	Total

	Revised resource allocation (a)*
	224,511,977
	171,000,000
	395,511,977

	Project costs
	 
	 
	 

	Amounts reviewed or recommended to the 83rd meeting
	68,069,436
	 
	68,069,436

	Remaining business plans values
	96,544,750
	183,042,844
	279,587,594

	Subtotal project costs (b)
	164,614,186
	183,042,844
	347,657,030

	Recurrent costs
	 
	 
	 

	Secretariat/Executive Committee/Monitoring and Evaluation
	6,799,233
	6,954,313
	13,753,546

	Treasurer
	500,000
	500,000
	1,000,000

	Subtotal recurrent costs (c)
	7,299,233
	7,454,313
	14,753,546

	Total costs (d) = (b) + (c)
	171,913,419
	190,497,157
	362,410,576

	Balance (e) = (a) – (d)
	52,598,558
	-19,497,157
	33,101,402


 * Resources available from the 2018–2020 replenishment approved by the Parties.
PART III:	REPORTS ON DIALOGUES CONCERNING QUALITATIVE PERFORMANCE INDICATORS

At its 82nd meeting, the Executive Committee requested UNIDO to have open and constructive discussions with the national ozone units (NOUs) of Botswana, Malawi, Pakistan, Rwanda and Somalia about the areas in which their services were perceived to be less than satisfactory, and to report back at the 83rd meeting (decision 82/8(b)). 
In response to decision 82/8(b), UNIDO indicated that it has had open and constructive discussions with the relevant NOUs. Therefore, issues have been resolved in all of these countries. 
RECOMMENDATION

The Executive Committee may wish to note:
The update on the status of implementation of the 2019–2021 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/83/13; 
That US $1,849,684 in HFC phase-down activities were submitted to the 83rd meeting including US $64,200 that had not been included in the 2019–2021 business plans; and
With appreciation, the reports on dialogues with national ozone units by UNIDO with respect to the ratings in the qualitative performance assessments, as requested in decision 82/8(b).
UNEP/OzL.Pro/ExCom/83/13
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Pre-session documents of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol are without prejudice to any decision that the Executive Committee might take following issuance of the document.
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HFC PHASE-DOWN ACTIVITIES SUBMITTED TO THE 83RD MEETING
[bookmark: _GoBack]

	Country
	Agency
	Type
	Sector
	Project Title
	Amount reviewed or
recommended (US $)
	Support costs reviewed or
recommended (US $)

	Argentina
	UNIDO
	INV
	PRO
	Control and phase-out of HFC-23 emissions in production of HCFC-22 at FIASA
	1,343,677
	94,057

	Indonesia
	UNDP
	PRP
	REF
	Preparation for conversion of HFC‑134a in the manufacturing of domestic refrigerators
	30,000
	2,100

	Lebanon
	UNDP
	PRP
	REF
	Preparation for conversion of R-404A in the commercial refrigeration units for supermarkets at Leon Industries S.A.R.L.
	30,000
	2,100

	Mexico
	UNIDO
	PRP
	PRO
	Project preparation for the control of HFC‑23 by-product emissions in the HCFC production sector
	45,000
	3,150

	Pakistan
	UNDP
	PRP
	REF
	Project preparation for conversion from HFC-134a to R-600a/R-290 as refrigerant in manufacturing of deep freezers, household refrigerators and water dispenser at PAK Elektron Limited, Lahore
	30,000
	2,100

	Syrian Arab Republic*
	UNEP
	TAS
	SEV
	Enabling activities for HFC phase‑down
	250,000
	17,500

	Total
	 
	 
	 
	 
	1,728,677
	121,007


* Recommended for funding from the additional contributions by 17 non-Article 5 countries. 
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Annex II

REMAINING ACTIVITIES IN THE 2019 BUSINESS PLAN

	Country
	Agency
	Type
	Chemical
	Sector and Subsector
	Value ($000) 2019 
	ODP 2019 

	Albania
	UNEP
	INS
	SEV
	Institutional Strengthening
	139.776
	 

	Algeria
	UNEP
	TAS
	HFC
	Enabling activities
	160.500
	 

	Algeria
	UNEP
	INS
	SEV
	Institutional Strengthening
	329.472
	 

	Angola
	UNEP
	INS
	SEV
	Institutional Strengthening
	172.032
	 

	Antigua and Barbuda
	UNEP
	TAS
	HFC
	Enabling activities
	53.500
	 

	Antigua and Barbuda
	UNEP
	PHA
	HCFC
	HPMP Stage II
	32.277
	0.08

	Antigua and Barbuda
	UNIDO
	PHA
	HCFC
	HPMP Stage II - REF-Servicing
	49.521
	0.70

	Antigua and Barbuda
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Argentina
	UNIDO
	PHA
	HCFC
	HPMP - Stage II - REF-Servicing
	3,510.449
	38.01

	Bahamas (the)
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	22.600
	 

	Bahamas (the)
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	10.700
	0.00

	Bahamas (the)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Bahrain
	UNIDO
	PHA
	HCFC
	HPMP - Stage I - REF-Servicing
	1,002.211
	7.74

	Bahrain
	UNEP
	PHA
	HCFC
	HPMP Stage I
	141.250
	1.03

	Barbados
	UNEP
	TAS
	HFC
	Enabling activities
	101.650
	 

	Barbados
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	33.900
	 

	Barbados
	UNEP
	PHA
	HCFC
	HPMP Stage I
	47.460
	0.19

	Benin
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	45.200
	 

	Benin
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	21.400
	0.00

	Benin
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Bolivia (Plurinational State of)
	UNEP
	INS
	SEV
	Institutional Strengthening
	100.950
	 

	Bosnia and Herzegovina
	UNIDO
	INS
	SEV
	Institutional Strengthening
	130.568
	0.00

	Brazil
	UNIDO
	INV
	HFC
	Phase-out of HFCs and phase-in of HFO-1234ze in industrial refrigeration and A/C
	856.000
	0.0

	Burkina Faso
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	45.200
	 

	Burkina Faso
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	21.400
	0.00

	Burundi
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	22.600
	 

	Burundi
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	10.700
	0.00

	Cameroon
	UNEP
	INS
	SEV
	Institutional Strengthening
	178.601
	 

	Central African Republic (the)
	UNEP
	TAS
	HFC
	Enabling activities
	160.500
	 

	Chad
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	China
	UNDP
	INV
	HFC
	Air conditioning and production line optimization from HFC-134a to HFO‑1234yf as refrigerant in a mobile air conditioning manufacturer
	1,000.000
	0.00

	China
	UNIDO
	INV
	HFC
	Demonstration project to provide experience in ICCs and IOCs associated with the phase-down of HFCs the XPS manufacturing
	1,819.000
	0.00

	China
	IBRD
	PHA
	HCFC
	HPMP Stage II - FOA - Rigid PU foam
	11,342.000
	279.71

	China
	UNIDO
	PHA
	HCFC
	HPMP Stage II - REF-Air conditioning
	19,260.000
	207.40

	Colombia
	UNDP
	INV
	HCFC
	HPMP Stage II
	680.251
	14.89

	Colombia
	UNEP
	PHA
	HCFC
	HPMP Stage II
	56.500
	1.17

	Comoros (the)
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	33.900
	 

	Comoros (the)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Congo (the)
	UNEP
	PHA
	HCFC
	HPMP Stage I
	28.250
	0.25

	Cook Islands (the)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Costa Rica
	UNDP
	INV
	HCFC
	HPMP Stage II - REF-Servicing
	222.560
	1.83

	Costa Rica
	UNDP
	INS
	SEV
	Institutional Strengthening
	192.447
	0.00

	Cote d'Ivoire
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	45.200
	 

	Cote d'Ivoire
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	21.400
	0.00

	Cote d'Ivoire
	UNEP
	PHA
	HCFC
	HPMP Stage I
	313.891
	3.42

	Cote d'Ivoire
	UNIDO
	PHA
	HCFC
	HPMP Stage I
	492.200
	5.63

	Democratic Republic of the Congo (the)
	UNEP
	PHA
	HCFC
	HPMP Stage II
	30.451
	1.00

	Democratic Republic of the Congo (the)
	UNDP
	INV
	HCFC
	HPMP Stage II - REF-Servicing
	5.277
	0.44

	Djibouti
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	33.900
	 

	Dominica
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	33.900
	 

	Dominica
	UNEP
	PHA
	HCFC
	HPMP Stage I
	74.354
	0.03

	Egypt
	UNIDO
	PHA
	HCFC
	HPMP - Stage II - REF-Servicing
	583.150
	7.31

	Egypt
	Germany
	PHA
	HCFC
	HPMP Stage II
	234.249
	2.78

	Egypt
	UNEP
	PHA
	HCFC
	HPMP Stage II
	312.894
	3.75

	Egypt
	UNDP
	INV
	HCFC
	HPMP Stage II - HC production, XPS and foam
	1,965.323
	24.64

	Egypt
	UNIDO
	PHA
	HCFC
	HPMP Stage II - REF-Air conditioning
	224.700
	2.82

	Eritrea
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	22.391
	 

	Eritrea
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	10.898
	0.00

	Eritrea
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Ethiopia
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Gabon
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	45.200
	 

	Gabon
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	21.400
	0.00

	Ghana
	UNDP
	INV
	HCFC
	HPMP Stage I
	130.409
	2.35

	Guinea
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	45.200
	 

	Guinea
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	21.400
	0.00

	Guinea
	UNEP
	PHA
	HCFC
	HPMP Stage I
	129.950
	1.41

	Guinea
	UNIDO
	PHA
	HCFC
	HPMP Stage I
	172.000
	1.96

	Guinea
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Guyana
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Haiti
	UNEP
	TAS
	HFC
	Enabling activities
	101.650
	 

	Haiti
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	16.950
	 

	Haiti
	UNEP
	PHA
	HCFC
	HPMP Stage I
	95.916
	0.38

	Haiti
	UNEP
	INS
	SEV
	Institutional Strengthening
	128.000
	 

	Indonesia
	UNDP
	INS
	SEV
	Institutional Strengthening
	371.499
	0.00

	Iran (Islamic Republic of)
	UNIDO
	INV
	HFC
	Demonstration project on accelerating energy efficiency as a co-benefit from HFC phase down in a domestic refrigerator manufacturing company
	707.484
	0.00

	Iran (Islamic Republic of)
	Germany
	PHA
	HCFC
	HPMP Stage II
	1,025.189
	13.00

	Iran (Islamic Republic of)
	Italy
	PHA
	HCFC
	HPMP Stage II
	565.000
	7.25

	Iran (Islamic Republic of)
	UNEP
	PHA
	HCFC
	HPMP Stage II
	213.614
	2.73

	Iran (Islamic Republic of)
	UNDP
	INV
	HCFC
	HPMP Stage II - Refrigeration
	1,705.559
	22.93

	Iran (Islamic Republic of)
	UNIDO
	PHA
	HCFC
	HPMP Stage II - REF-Servicing/ FOA-Rigid PU  foam
	624.880
	8.40

	Iraq
	UNIDO
	PHA
	HCFC
	HPMP - Stage I - REF-Servicing
	225.750
	2.67

	Iraq
	UNEP
	PHA
	HCFC
	HPMP Stage I
	247.634
	2.79

	Iraq
	UNEP
	PHA
	HCFC
	HPMP Stage II
	252.012
	5.00

	Jamaica
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Jordan
	UNIDO
	PHA
	HCFC
	HPMP - Stage II - REF-Servicing
	314.711
	4.29

	Jordan
	IBRD
	PHA
	HCFC
	HPMP Stage II - FOA - Rigid PU foam
	1,084.503
	14.76

	Jordan
	UNIDO
	PHA
	HCFC
	HPMP Stage II - FOA-Rigid PU foam
	263.998
	3.59

	Kenya
	UNEP
	INS
	SEV
	Institutional Strengthening
	194.134
	 

	Kuwait
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	67.800
	 

	Kuwait
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - FOA-Rigid PU foam
	85.600
	0.00

	Kuwait
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - REF-Air Conditioning
	85.600
	0.00

	Kuwait
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	32.100
	0.00

	Liberia
	Germany
	PRP
	HCFC
	HPMP Preparation - Stage II
	33.400
	 

	Madagascar
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	45.200
	 

	Madagascar
	UNIDO
	PRP
	HCFC
	HPMP Preparation - Stage II - Refrigeration Servicing
	21.400
	0.00

	Malaysia
	UNDP
	INV
	HCFC
	HPMP Stage II - Foam, refrigeration, air conditioning
	2,648.491
	58.97

	Malaysia
	UNDP
	INS
	SEV
	Institutional Strengthening
	382.803
	0.00

	Mali
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	33.900
	 

	Marshall Islands (the)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Mauritius
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Micronesia (Federated States of)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Morocco
	UNEP
	INS
	SEV
	Institutional Strengthening
	199.680
	 

	Mozambique
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	22.600
	 

	Myanmar
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Namibia
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Nauru
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Niger (the)
	UNIDO
	PHA
	HCFC
	HPMP - Stage I - REF-Servicing
	96.750
	0.90

	Niger (the)
	UNEP
	PHA
	HCFC
	HPMP Stage I
	141.250
	1.25

	Niger (the)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	North Macedonia
	UNIDO
	PHA
	HCFC
	HPMP Stage I - REF-Servicing, FOA & INS
	80.625
	0.14

	Pakistan
	UNDP
	INV
	HFC
	Conversion of Refrigerator, Deep freezers and Water Dispenser from R 134a to R 600a
	1,500.000
	0.00

	Panama
	UNDP
	INS
	SEV
	Institutional Strengthening
	204.755
	0.00

	Peru
	UNDP
	INV
	HCFC
	HPMP Stage II
	249.738
	2.44

	Peru
	UNEP
	PHA
	HCFC
	HPMP Stage II
	47.008
	0.44

	Peru
	UNEP
	INS
	SEV
	Institutional Strengthening
	170.893
	 

	Philippines (the)
	IBRD
	PHA
	HCFC
	HPMP Stage II - REF-Air conditioning
	1,551.531
	12.97

	Qatar
	UNEP
	PHA
	HCFC
	HPMP Stage II
	76.123
	2.00

	Qatar
	UNIDO
	PHA
	HCFC
	HPMP Stage II - REF-Servicing
	143.178
	3.00

	Qatar
	UNIDO
	INS
	SEV
	Institutional Strengthening
	121.894
	0.00

	Republic of Moldova (the)
	UNDP
	TAS
	SEV
	Enabling activities
	101.650
	0.00

	Republic of Moldova (the)
	UNDP
	PRP
	HCFC
	HPMP Preparation - Stage III
	30.000
	0.00

	Republic of Moldova (the)
	UNEP
	PHA
	HCFC
	HPMP Stage II
	29.493
	0.04

	Rwanda
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Saint Kitts and Nevis
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	22.600
	 

	Saint Lucia
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Saint Vincent and the Grenadines
	UNEP
	PHA
	HCFC
	HPMP Stage I
	116.390
	0.06

	Saint Vincent and the Grenadines
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Saudi Arabia
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	33.900
	 

	Saudi Arabia
	UNIDO
	PHA
	HCFC
	HPMP Stage I - REF-Air conditioning
	909.500
	38.70

	Saudi Arabia
	UNEP
	INS
	SEV
	Institutional Strengthening
	256.000
	 

	Senegal
	UNIDO
	PHA
	HCFC
	HPMP - Stage I - REF-Servicing
	21.500
	0.23

	Senegal
	UNEP
	PHA
	HCFC
	HPMP Stage I
	90.400
	0.93

	Senegal
	UNEP
	INS
	SEV
	Institutional Strengthening
	194.689
	 

	Serbia
	UNIDO
	INS
	SEV
	Institutional Strengthening
	179.828
	0.00

	South Sudan
	UNEP
	PRP
	HCFC
	HPMP Preparation - Stage II
	22.600
	 

	South Sudan
	UNDP
	INV
	HCFC
	HPMP Stage I
	54.500
	0.14

	South Sudan
	UNEP
	PHA
	HCFC
	HPMP Stage I
	79.665
	0.19

	South Sudan
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Suriname
	UNEP
	INS
	SEV
	Institutional Strengthening
	93.866
	 

	Syrian Arab Republic
	UNIDO
	INS
	SEV
	Institutional Strengthening
	279.156
	0.00

	Timor-Leste
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Trinidad and Tobago
	UNDP
	INV
	HCFC
	HPMP Stage II - REF-Servicing
	496.418
	5.32

	Tunisia
	UNIDO
	PHA
	HCFC
	HPMP - Stage I - REF-Servicing
	116.003
	0.64

	Tunisia
	France
	PHA
	HCFC
	HPMP Stage I
	78.769
	0.41

	Tunisia
	UNEP
	PHA
	HCFC
	HPMP Stage I
	16.950
	0.09

	Tunisia
	UNEP
	PHA
	HCFC
	HPMP Stage II
	75.605
	1.50

	Tunisia
	UNIDO
	INS
	SEV
	Institutional Strengthening
	338.661
	0.00

	Turkey
	UNIDO
	PHA
	HCFC
	HPMP Stage I
	1,710.770
	52.60

	Turkey
	UNEP
	PHA
	HCFC
	HPMP Stage II
	378.017
	7.50

	Turkey
	UNIDO
	INS
	SEV
	Institutional Strengthening
	356.096
	0.00

	Uruguay
	UNDP
	INS
	SEV
	Institutional Strengthening
	206.536
	0.00

	Vanuatu
	UNEP
	INS
	SEV
	Institutional Strengthening
	85.000
	 

	Venezuela (Bolivarian Republic of)
	UNIDO
	TAS
	HCFC
	HPMP Stage II - RAC-Manufacturing
	615.250
	6.71

	Viet Nam
	Japan
	PHA
	HCFC
	HPMP Stage II
	215.129
	1.70

	Viet Nam
	IBRD
	PHA
	HCFC
	HPMP Stage II - FOA - Rigid PU foam & REF- (Air conditioning/Commercial ref/Servicing)
	6,377.682
	53.14

	Global
	IBRD
	TAS
	SEV
	Core Unit
	1,735.000
	 

	Global
	UNDP
	TAS
	SEV
	Core Unit
	2,098.458
	0.00

	Global
	UNIDO
	TAS
	SEV
	Core Unit
	2,098.457
	0.00

	Global
	UNEP
	TAS
	SEV
	Global CAP 2019 work programme
	11,300.749
	 

	Global
	ALL
	TAS
	HCFC
	HPMP Verification
	588.600
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