| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/87/4 22 June 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-seventh Meeting

Montreal, 28 June-2 July 2021

# report on balances and availability of resources

# Introduction

- This document presents a summary of financial adjustments indicated by the bilateral (BAs) and implementing agencies (IAs) as agreed by the Secretariat. It includes statistical data from all projects with balances that have been held for over 12 months following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow up to relevant decisions (referred to as “by-decision” projects in this document). It indicates the level of resources available to the Executive Committee in cash as recorded in the Status of contributions and disbursements document, as required by decision 41/92(b), and presents a recommendation.

- This document also contains the following four annexes:

Annex I	Amounts held by IAs and BAs for completed projects

Annex II 	Amounts held by IAs and BAs for by-decision projects

Annex III 	Amounts held by IAs and BAs for the additional contributions projects

Annex IV	Fund returns by IAs and BAs from completed, by-decision, and additional voluntary contributions projects

# Annexes I, II and III provide explanations on the delays in disbursing committed amounts or returning not-committed amounts.

Funds to be returned to the 87th meeting

# The total funds to be returned amount to US $2,315,105 (i.e., US $6,747 by BAs and US $2,308,358 by IAs) from completed, by-decision, and additional contributions projects.

Funds to be returned by IAs

# The total funds to be returned by IAs amount to US $2,308,358 as shown in Table 1.

# Table 1. Funds to be returned by IAs to the 87th meeting (US $)

| Agency | Project cost | Agency support cost | Total cost |
| --- | --- | --- | --- |
| UNDP | 58,511 | 4,199 | 62,710 |
| UNEP | 1,867,022 | 148,337 | 2,015,359 |
| UNIDO | 214,743 | 15,546 | 230,289 |
| Total | 2,140,276 | 168,082 | 2,308,358 |

# Table 2 presents information on balances of completed, by-decisions and additional voluntary contributions projects that are withheld by the IAs.

Table 2. Balances of completed, by-decision, and additional voluntary contributions projects withheld by IAs (including agency support costs)

| Year completed | UNDP |  | UNEP |  | UNIDO |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Number | (US $) | Number | (US $) | Number | (US $) | Number | (US $) |
| Projects completed over two years ago |  |  |  |  |  |  |  |  |
| 2016 | 0 | 0 | 1 | 68,727 | 0 | 0 | 1 | 68,727 |
| 2017 | 0 | 0 | 3* | 8,591 | 0 | 0 | 3 | 8,591 |
| 2018 | 0 | 0 | 3 | 32,054 | 0 | 0 | 3 | 32,054 |
| 1 Jan to 31 May 2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sub-total | 0 | 0 | 7 | 109,372 | 0 | 0 | 7 | 109,372 |
| Projects completed in less than two years ago |  |  |  |  |  |  |  |  |
| 1 Jun to 31 Dec 2019 | 15 | 4,507,300 | 7 | 444,737 | 4 | 14,134 | 26 | 4,966,171 |
| Sub-total | 15 | 4,507,300 | 7 | 444,737 | 4 | 14,134 | 26 | 4,966,171 |
| Total | 15 | 4,507,300 | 14 | 554,109 | 4 | 14,134 | 33 | 5,075,543 |
| By-decisions projects (ongoing) |  |  |  |  |  |  |  |  |
|  | 1 | 160,869 | 4 | 293,788 | 0 | 0 | 5 | 454,657 |
| Additional voluntary contributions |  |  |  |  |  |  |  |  |
|  | 0 | 0 | 1 | 10,110 | 1 | 2,132 | 2 | 12,242 |
| Grand total | 16 | 4,668,169 | 19 | 858,006 | 5 | 16,266 | 40 | 5,542,441 |

* Including an ODS-alternative survey project

Funds to be returned by BAs

# The total funds to be returned by BAs amount to US $6,747, consisting of US $6,247, plus agency support cost of US $500 for France.

Availability of resources

# The Status of contributions and disbursements document indicates an available balance of US $334,427,526 as at 9 June 2021. The total balance returned by BAs and IAs, to the 87th meeting amounts to US $2,308,358. Therefore, the total level of resources available for approvals at the 87th meeting, amounts to US $336,735,884.

Secretariat’s comments

# The Secretariat reminded BAs and IAs that balances of by-decisions projects and projects completed one year ago and more, should be returned to the Multilateral Fund as soon as possible.

# Considering that the total level of funding for projects and activities submitted to the 87th meeting amounts to US $22,042,297 including agency support costs, there are sufficient resources available for approvals at the 87th meeting.

Recommendations

# The Executive Committee may wish:

  - To note:

- The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/87/4;

- That the net level of funds being returned at the 87th meeting by the implementing agencies was US $2,308,358, consisting of US $58,511, plus agency support costs of US $4,199 from UNDP; US $1,867,022, plus agency support costs of US $148,337 from UNEP, and US $214,743, plus agency support costs of US $15,546 from UNIDO;

- That UNEP held balances of US $109,372, including agency support costs, for seven projects completed over two years previously which included one ODS-alternative survey project with balances of US $434, including agency support costs, and US $10,110, including agency support costs, for one project funded using the additional voluntary contributions;

- That UNIDO held balances of US $2,132, including agency support costs, for one project funded using the additional voluntary contributions; and

- That the net level of funds being returned at the 87th meeting by the Government of France was US $6,247, plus agency support costs of US $500.

## To request:

    - Bilateral and implementing agencies to proceed with disbursement or to cancel committed and not-committed funds that were not needed for completed projects and projects completed “by decision of the Executive Committee” and to return the associated balances to the 88th meeting;

### UNEP to return to the 88th meeting, the balance of one ODS-alternative survey project completed over two years previously, in line with decisions 80/75(c)(i), and the balance of one completed project funded using the additional voluntary contributions;

### UNEP to proceed with disbursement or to cancel commitments for the remaining six projects completed over two years previously, and to return balances to the 
88th meeting;

### UNIDO to return to the 88th meeting the balance of one completed project funded using the additional voluntary contributions; and

### The Treasurer to follow up with the Government of France, on the return, in cash, of the amount of US $6,747 referred to in sub-paragraph (a)(v) above.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 87th meeting (US $) | Balances committed as per 87th meeting (US $) | Balances not-committed as per 87th meeting (US $) | Support cost on balances committed & not committed as per 87th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | Nov-19 | 57,000 | 56,359 | 641 |  | 58 |  |  |  |
| BRA/PHA/74/INV/307 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | Dec-19 | 3,000,000 | 1,979,026 | 1,020,974 |  | 76,573 |  |  | 84/32(b)(iii) and 85/5(a)(ii) |
| BRA/PHA/75/INV/315 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | Dec-19 | 1,470,700 | 437,803 | 1,032,897 |  | 77,468 |  |  | 84/32(b)(iii) and 85/5(a)(ii) |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 179,857 | 174,475 | 5,382 |  | 377 |  |  |  |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 2,000,000 | 1,857,930 | 142,070 |  | 10,655 |  |  | 82/72(a)(iv) |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 716,400 | 288,322 | 428,078 |  | 32,106 |  |  | 82/72(a)(iv) |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 35,639 | 24,211 |  | 2,179 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 111,244 | 48,506 |  | 3,396 |  |  |  |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | Dec-19 | 347,194 | 343,303 | 3,891 |  | 272 |  |  |  |
| MDV/REF/76/DEM/30 | Demonstration project for HCFC-free low-global warming potential alternatives in refrigeration in fisheries sector | Dec-19 | 141,000 | 139,472 | 1,528 |  | 138 |  |  |  |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 3,800,000 | 3,456,632 | 343,368 |  | 25,753 |  |  | 84/22(b) and (c) |
| MEX/PHA/75/INV/178 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 1,122,503 | 0 | 1,122,503 |  | 84,188 |  |  | 84/22(b) and (c) |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 92,000 | 77,893 | 14,107 |  | 1,058 |  |  |  |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 33,600 | 30,916 | 2,684 |  | 242 |  |  |  |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 131,500 | 129,642 | 1,858 |  | 139 |  |  |  |
| TOTAL UNDP |  |  |  |  | 4,192,698 |  | 314,602 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Dec-19 | 375,000 | 342,491 | 27,696 |  | 3,600 |  |  | 83/37(c) and 85/18(b) |
| BAH/PHA/68/TAS/28 | HCFC phase-out management plan (stage I, first tranche) (policy, refrigeration servicing, monitoring and verification) | Dec-18 | 120,000 | 116,882 | 3,118 |  | 405 |  |  |  |
| CHI/PHA/76/TAS/193 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | Dec-17 | 53,000 | 52,493 | 507 |  | 66 |  |  | 76/45(a)(iii) and 81/14(b)(ii) |
| GBS/PHA/71/TAS/17 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 52,000 | 29,079 | 22,921 |  | 2,980 |  |  |  |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | Dec-19 | 9,974,259 | 8,055,902 | 307,619 |  | 24,610 |  |  |  |
| GUY/PHA/75/TAS/27 | HCFC phase-out management plan (stage II, first tranche) | Oct-19 | 55,500 | 50,000 | 5,500 |  | 715 |  |  |  |
| HAI/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 40,000 | 19,591 | 20,409 |  | 2,653 |  |  |  |
| IRQ/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Dec-18 | 115,000 | 110,266 | 4,734 |  | 582 |  |  |  |
| KUW/PHA/52/TAS/10 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Jan-16 | 232,912 | 172,092 | 60,820 |  | 7,907 |  |  | 70/7(b)(ii)a. |
| KUW/REF/75/TAS/29 | Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling) | Jun-18 | 27,223 | 6,679 | 20,544 |  | 2,671 |  |  | 82/24(c)(ii) and 83/38(b) |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | Dec-19 | 88,748 | 69,423 | 19,325 |  | 0 |  |  |  |
| PAR/PHA/63/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | Jun-17 | 146,500 | 139,788 | 6,712 |  | 873 |  |  |  |
| PAR/SEV/77/INS/36 | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | Dec-19 | 85,000 | 78,292 | 6,708 |  | 0 |  |  |  |
| STL/SEV/75/TAS/24 | Survey of ODS alternatives at the national level | Dec-17 | 35,000 | 31,609 | 384 |  | 50 |  |  | 80/75(c)(i) |
| TOTAL UNEP |  |  |  |  | 506,997 |  | 47,112 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| GLO/REF/76/DEM/333 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | Jul-19 | 345,000 | 339,533 | 5,467 |  | 383 | 2 | 88th meeting | 84/24(b) |
| MLW/PHA/77/INV/40 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 60,000 | 59,885 | 115 |  | 10 | 2 | 88th meeting |  |
| SEN/PHA/65/INV/31 | HCFC phase-out management plan (stage I, first tranche) | Dec-19 | 200,000 | 199,292 | 708 |  | 53 | 2 | 88th meeting |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,035,702 | 6,918 |  | 484 | 2 | 88th meeting |  |
| TOTAL UNIDO |  |  |  |  | 13,207 |  | 927 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 87th meeting (US $) | Balances committed as per 87th meeting (US $) | Balances not- committed as per 87th meeting (US $) | Support cost on balances committed and not-committed as per 87th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,340,255 | 150,345 |  | 10,524 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 150,345 |  | 10,524 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| QAT/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 87th meeting | 105,000 | 38,955 | 66,045 |  | 8,586 |  |  |  |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 165,806 | 48,750 |  | 6,039 |  |  |  |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 87th meeting | 56,726 | 4,014 | 39,000 |  | 4,832 |  |  |  |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 14,509 | 107,250 |  | 13,286 |  |  |  |
| TOTAL UNEP |  |  |  |  | 261,045 |  | 32,743 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS

| CODE | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2019 (US $) | Funds disbursed as of 87th meeting (US $) | Balances committed as per 87th meeting (US $) | Balances not- committed as per 87th meeting (US $) | Support cost on balances committed and not-committed as per 87th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ZIM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down |  | 150,000 | 140,551 | 9,449 |  | 661 |  |  |  |
| TOTAL UNEP |  |  |  |  | 9,449 |  | 661 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| LEB/REF/80/PRP/01+ | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration | 85th meeting | 30,000 | 28,008 | 1,992 |  | 139 | 2 | 88th meeting | 84/2(b)(ii) |
| TOTAL UNIDO |  |  |  |  | 1,992 |  | 139 |  |  |  |

i*: 2: Financial completion initiated; 3: Financial completion to be initiated after settlement of all pending issues; 4: Project is ongoing; 5: Funds were not transferred

Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| COL/PHA/75/TAS/94 | HCFC phase-out management plan (stage II, first tranche) (technical assistance for fire protection sector) | 2 | 0 | 2 |
| COS/REF/57/PRP/41 | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | 4,883 | 366 | 5,249 |
| COS/REF/74/PRP/51 | Preparation of a demonstration project for the transition of HCFC-22-based refrigerant unit to NH3 system in cold chambers | 1 | 0 | 1 |
| GHA/SEV/76/INS/41 | Extension of the institutional strengthening project (phase XII: 1/2017-12/2018) | 3,395 | 238 | 3,633 |
| PAK/SEV/77/INS/96 | Extension of the institutional strengthening project (phase IX: 4/2017-3/2019) | 569 | 40 | 609 |
| PAN/SEV/75/INS/42 | Extension of institutional strengthening project (phase VII: 12/2015-11/2017) | 184 | 13 | 197 |
| STK/PHA/64/TAS/16 | HCFC phase-out management plan (stage I, first tranche) | 58 | 5 | 63 |
| TLS/PHA/72/PRP/11 | Preparation of a HCFC phase-out management plan (stage II) | 5,000 | 350 | 5,350 |
| TLS/PHA/80/INV/18 | HCFC phase-out management plan (stage I, third tranche) | 4,030 | 363 | 4,393 |
| TRI/PHA/64/INV/26 | HCFC phase-out management plan (foam sector) (stage I, first tranche) | -547 | -41 | -588 |
| TRI/SEV/79/INS/34 | Extension of the institutional strengthening project (phase IX: 1/2018-12/2019) | 381 | 27 | 408 |
| Total completed projects |  | 17,956 | 1,360 | 19,316 |
| DOM/REF/80/PRP/01+ | Project preparation for conversion from HFC-134a to HC-290 in the manufacture of commercial refrigerators at Farco | 18,428 | 1,290 | 19,718 |
| EGY/FOA/80/PRP/01+ | Project preparation for conversion from HFC-134a to HFO-1234ze and other liquid HFOs in the manufacture of polyurethane foam and spray foam | 12,036 | 843 | 12,879 |
| ZIM/REF/80/PRP/02+ | Project preparation for elimination of HFC-134a in the manufacture of domestic refrigerators at Capri | 10,091 | 706 | 10,797 |
| Total “additional voluntary contributions” projects |  | 40,555 | 2,839 | 43,394 |
| TOTAL UNDP |  | 58,511 | 4,199 | 62,710 |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 4,813 | 626 | 5,438 |
| BHU/SEV/79/INS/27 | Extension of institutional strengthening project (phase VII: 12/2017-11/2019) | 336 | 0 | 336 |
| CHI/PHA/73/TAS/185 | HCFC phase-out management plan (stage I, third tranche) | 248 | 32 | 280 |
| CPR/PHA/74/TAS/559 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector including enabling programme) | 5,392 | 603 | 5,995 |
| DOM/PHA/69/TAS/52 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 8,816 | 1,146 | 9,962 |
| ECU/SEV/76/INS/62 | Extension of institutional strengthening project (phase VI: 5/2016-4/2018) | 23,774 | 0 | 23,774 |
| GLO/SEV/80/TAS/341 | Compliance Assistance Programme: 2018 budget | 158,314 | 12,665 | 170,979 |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | 1,610,738 | 128,859 | 1,739,597 |
| MEX/PHA/77/TAS/184. | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 1,694 | 220 | 1,914 |
| PAN/PHA/70/TAS/35 | HCFC phase-out management plan (stage I, second tranche) | 2,017 | 262 | 2,279 |
| PAN/PHA/74/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | 1,863 | 242 | 2,105 |
| PER/PHA/68/TAS/47 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | 7,091 | 922 | 8,013 |
| PHI/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | 9,651 | 0 | 9,651 |
| Total completed projects |  | 1,834,746 | 145,578 | 1,980,324 |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 19,118 | 2,368 | 21,486 |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 136 | -987 | -851 |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 8,641 | 1,070 | 9,711 |
| Total “by decision” projects |  | 27,895 | 2,452 | 30,347 |
| GHA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 575 | 40 | 615 |
| KAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,082 | 146 | 2,228 |
| LES/SEV/80/TAS/04+ | Enabling activities for HFC phase-down | 468 | 33 | 501 |
| TON/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 1,256 | 88 | 1,344 |
| Total “additional voluntary contributions” projects |  | 4,381 | 307 | 4,688 |
| TOTAL UNEP |  | 1,867,022 | 148,337 | 2,015,359 |
| ARG/PHA/80/TAS/186 | HCFC phase-out management plan (stage II, first tranche) (monitoring and reporting of HCFC-22 production) | 1,705 | 119 | 1,824 |
| ASP/REF/76/DEM/60 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 3,550 | 249 | 3,799 |
| BDI/PHA/65/INV/29 | HCFC phase-out management plan (stage I, first tranche) | 152 | 14 | 166 |
| BEN/PHA/76/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 51 | 4 | 55 |
| ECU/PHA/82/INV/70 | HCFC phase-out management plan (stage I, fourth tranche) | 171 | 12 | 183 |
| ECU/PHA/82/PRP/68 | Preparation of a HCFC phase-out management plan (stage II) | 67 | 5 | 72 |
| EGY/REF/75/TAS/127 | Feasibility study addressing district cooling | 2,435 | 219 | 2,654 |
| GBS/PHA/77/INV/21 | HCFC phase-out management plan (stage I, third tranche) | 229 | 20 | 249 |
| GUA/PHA/81/INV/51 | HCFC phase-out management plan (stage I, fourth tranche) | 169 | 13 | 181 |
| GUA/PHA/82/PRP/55 | Preparation of a HCFC phase-out management plan (stage II) | 82 | 6 | 88 |
| MDN/PHA/79/INV/39 | HCFC phase-out management plan (phase I, seventh tranche) | 70 | 5 | 75 |
| MEX/PRO/83/PRP/192 | Project preparation for the control of HFC-23 by-product emissions in the HCFC production sector | 307. | 21 | 328 |
| MEX/SEV/79/INS/186 | Extension of institutional strengthening project (phase XIII: 7/2017-6/2019) | 328 | 22 | 350 |
| MLW/PHA/81/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | 270 | 19 | 289 |
| MOG/PHA/75/INV/11 | HCFC phase-out management plan (stage I, third tranche) | 729 | 55 | 784 |
| MOR/FOA/75/DEM/74 | Demonstration of the use of low cost pentane foaming technology for the conversion to non-ODS technologies in polyurethane foams at small- and medium-sized enterprises | 4,303 | 301 | 4,604 |
| NIR/PHA/71/INV/136 | HCFC phase-out management plan (stage I, third tranche) (refrigeration air-conditioning manufacturing and coordination) | 1,082 | 81 | 1,163 |
| QAT/SEV/79/INS/22 | Renewal of institutional strengthening project (phase IV: 8/2017-7/2019) | 29,123 | 2,038 | 31,161 |
| SAU/FOA/76/DEM/27 | Demonstration project for the phase-out of HCFCs by using HFO as foam blowing agent in the spray foam applications in high ambient temperatures | 201 | 19 | 220 |
| SUD/PHA/80/INV/42 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 150 | 10 | 160 |
| TUN/FOA/77/PRP/72 | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) | 33,747 | 2,363 | 36,110 |
| TUN/PHA/72/INV/58 | HCFC phase-out management plan (stage I, first tranche) (solvent sector plan) | 9,465 | 662 | 10,127 |
| TUR/PHA/75/INV/108 | HCFC phase-out management plan (stage I, second tranche) (technical assistance for small and medium enterprises in the foam sector) | 22,029 | 1,540 | 23,569 |
| URT/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 152 | 11 | 163 |
| YUG/PHA/82/TAS/49 | Verification report on the implementation of the HCFC phase-out management plan | 438 | 39 | 477 |
| Total completed projects |  | 111,003 | 7,848 | 118,851 |
| CPR/ARS/56/INV/473 | Sector plan for phase-out of CFCs consumption in MDI sector | 15,099 | 1,132 | 16,231 |
| QAT/PHA/65/INV/18 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 59,334 | 4,450 | 63,784 |
| QAT/PHA/65/INV/19 | HCFC phase-out management plan (stage I, first tranche) (sector conversion from HCFC-142b/HCFC-22 in the production of extruded polystyrene insulation boards to low GWP isobutene at Qatar Insulation, Orient Insulation and Al Kawthar Insulation) | 12,927 | 969 | 13,896 |
| Total “by decision” projects |  | 87,360 | 6,551 | 93,911 |
| CPR/FOA/81/PRP/05+ | Preparation for converting from HFC-134a to HFOs+CO2 with gluing technology in an extruded polystyrene foam manufacturer | 16,379 | 1,147 | 17,526 |
| MEX/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 1 | 0 | 1 |
| Total “additional voluntary contributions” projects |  | 16,380 | 1,147 | 17,527 |
| TOTAL UNIDO |  | 214,743 | 15,546 | 230,289 |
| TUN/PHA/76/INV/70 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 6,247 | 500 | 6,747 |
| TOTAL FRANCE |  | 6,247 | 500 | 6,747 |

Online meetings and an intersessional approval process will be held in June and July 2021 due to coronavirus disease (COVID-19)

The data presented are based on the reporting format that has been developed pursuant to decision 31/2.

UNEP/OzL.Pro/ExCom/87/3.

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5 project is ongoing; 6 Funds were not transferred.