| NATIONS UNIES |  | EP |
| --- | --- | --- |
|  | Programme des Nations Unies pour l’environnement | Distr. GÉNÉRALE UNEP/OzL.Pro/ExCom/91/4 8 novembre 2022 FRANÇAIS ORIGINAL : ANGLAIS |

COMITÉ EXÉCUTIF 
  DU FONDS MULTILATÉRAL AUX FINS 
  D’APPLICATION DU PROTOCOLE DE MONTRÉAL
Quatre-vingt-onzième réunion

Montréal, 5-9 décembre 2022

Point 4 b) de l’ordre du jour provisoire

# RAPPORT SUR LES SOLDES ET LA DISPONIBILITE DES RESSOURCES

# Introduction

- Ce document présente un résumé des ajustements financiers communiqués par les agences bilatérales et d’exécution, et approuvés par le Secrétariat. Il comprend des données statistiques de tous les projets dont les soldes ont été retenus pendant plus de 12 mois après l’achèvement du projet, conformément aux décisions 28/7 and 56/2 c). Il examine les soldes à restituer provenant de projets au titre du suivi donné à des décisions les concernant (appelés projets « soumis à décision » dans le présent document). Il indique au Comité exécutif le niveau des ressources disponibles en liquidités enregistrées dans le document État des contributions et décaissements, conformément à la décision 41/92 b) et présente une recommandation. Les sommes détenues par les agences d’exécution et les agences bilatérales au titre de projets achevés, de projets soumis à décision et de projets financés à l’aide de contributions supplémentaires sont inclues dans les Annexes I, II et III respectivement. L’Annexe IV présente les fonds restitués par les agences bilatérales et d’exécution provenant de projets achevés, de projets soumis à décision, et de projets financés par des contributions volontaires supplémentaires.

Fonds devant être restitués à la 91e réunion

# Le montant total des fonds devant être restitués s’élève à 3 106 899 $US (soit 21 199 $US par les agences bilatérales et 3 085 700 $US par les agences d’exécution) pour des projets achevés et des projets financés par des contributions supplémentaires.

Fonds devant être restitués par les agences d’exécution

# Le total des fonds devant être restitués par les agences d’exécution s’élève à 3 085 700 $US, comme l’indique le tableau 1.

# Tableau 1. Fonds à restituer à la 91e réunion par les agences d’exécution ($US)

| Agence | Coût du projet | Coûts d’appui à l’agence | Coût total |
| --- | --- | --- | --- |
| PNUD | 38 438 | 2 887 | 41 325 |
| PNUE | 2 578 802 | 219 667 | 2 798 469 |
| ONUDI | 225 813 | 16 526 | 242 339 |
| Banque mondiale | 3 334 | 233 | 3 567 |
| Total | 2 846 387 | 239 313 | 3 085 700 |

Fonds devant être restitués par les agences bilatérales

# Le total des fonds devant être restitués par une agence bilatérale s’élève à 21 199 $US, se composant de 18 488 $US, plus coûts d’appui d’agence de 1 479 $US et des intérêts de 1 232 $US pour la France.

Soldes encore détenus par les agences d’exécution et les agences bilatérales

Soldes encore détenus par les agences bilatérales

# Le tableau 2 présente des informations sur les soldes encore détenus par les agences d’exécution pour des projets achevés, des projets soumis à décision et des projets financés par des contributions volontaires supplémentaires.

Tableau 2. Soldes encore détenus par les agences d’exécution (y compris coûts de soutien d’agence) pour des projets achevés, des projets soumis à décision et des projets financés par des contributions volontaires supplémentaires

| Année d’achèvement | PNUD |  | PNUE |  | ONUDI |  | Banque Mondiale |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nombre | ($US) | Nombre | ($US) | Nombre | ($US) | Nombre | ($US) | Nombre | ($US) |
| Projets achevés depuis plus de 2 ans |  |  |  |  |  |  |  |  |  |  |
| 2019 | 2 | 30 298 | 0 | 0 | 1 | 5 931 | 0 | 0 | 3 | 36 229 |
| 1 janvier au 31 octobre 2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total partiel | 2 | 30 298 | 0 | 0 | 1 | 5 931 | 0 | 0 | 3 | 36 229 |
| Projets achevés depuis moins de deux ans |  |  |  |  |  |  |  |  |  |  |
| 1 novembre au 31 déc. 2020 | 2 | 59 036 | 0 | 0 | 2 | 655 044 | 0 | 0 | 4 | 714 080 |
| 2021 | 37 | 1 790 851 | 23 | 1 193 412 | 20 | 347 820 | 0 | 0 | 80 | 3 332 083 |
| Total partiel | 39 | 1 849 887 | 23 | 1 193 412 | 22 | 1 002 864 | 0 | 0 | 84 | 4 046 163 |
| Total | 41 | 1 880 185 | 23 | 1 193 412 | 23 | 1 008 795 | 0 | 0 | 87 | 4 082 392 |
| Projets soumis à décision |  |  |  |  |  |  |  |  |  |  |
|  | 0 | 0 | 0 | 0 | 2 | 23 307 | 0 | 0 | 2 | 23 307 |
| Projets à contributions volontaires supplémentaires |  |  |  |  |  |  |  |  |  |  |
| Achevés | 4 | 43 987 | 0 | 0 | 7 | 210 806 | 1 | 334 | 12 | 255 127 |
| Total général | 45 | 1 924 172 | 23 | 1 193 412 | 32 | 1 242 908 | 1 | 334 | 101 | 4 360 826 |

Soldes encore détenus par des agences bilatérales

# Le Japon a retenu les soldes d'un projet achevé en 2021, pour un montant de 240 $US, coûts d’appui d’agence compris.

Disponibilité des ressources

# Le document État des contributions et des décaissements indique au 3 novembre 2022 un solde disponible d’un montant de 501 593 220 $US. Le solde total restitué par les agences bilatérales et d’exécution à la 91e réunion s’élève à 3 106 899 $US. De ce fait, le niveau total des ressources disponibles pour les approbations lors de cette réunion est de 504 700 119 $US.

Observations du Secrétariat

# Le Secrétariat a rappelé aux agences bilatérales et d’exécution que les soldes des projets soumis à décision, des projets achevés depuis un an ou plus et des projets financés par des contributions volontaires supplémentaires doivent être restitués dès que possible au Fonds multilatéral.

# Considérant que le montant total du financement demandé pour des projets et activités soumis à la 91e réunion s’élève à 83 048 165 $US au 3 novembre 2022, les ressources disponibles sont suffisantes pour les approbations de cette réunion.

Recommandations

# Le Comité exécutif pourrait envisager :

  - De prendre note :

- Du rapport sur les soldes et la disponibilité des ressources présenté dans le document UNEP/OzL.Pro/ExCom/91/4 ;

- Que le montant net des fonds restitués à la 91e réunion par les agences d’exécution s’élève à 3 085 700 $US, soit 38 438 $US, plus coûts d’appui d’agence de 2 887 $US par le PNUD ; 2 578 802 $US, plus coûts d’appui d’agence de 219 667 $US par le PNUE ; 225 813 $US, plus coûts d’appui d’agence de 16 526 $US par l’ONUDI ; et 3 334 $US, plus coûts d’appui d’agence de 223 $US par la Banque mondiale ;

- Que le PNUD détient un solde de 30 298 $US, coûts d’appui d’agence compris, pour deux projets achevés depuis plus de deux ans, et 43 987 $US, coûts d’agence compris, pour quatre projets financés par des contributions volontaires de la part d’un groupe de pays donateurs destinées à financer des activités à démarrage rapide pour la mise en œuvre de la réduction des émissions de HFC ;

- Que l’ONUDI détient un solde de 5 931 $US, coûts d’appui d’agence compris, pour deux projets achevés depuis plus de deux ans, 23 307 $US, coûts d’appui d’agence compris, pour deux projets achevés « par décision du Comité exécutif », et 210 806 $US, coûts d’appui d’agence compris, pour sept projets financés par des contributions volontaires de la part d’un groupe de pays donateurs destinées à financer des activités à démarrage rapide pour la mise en œuvre de la réduction des émissions de HFC ;

- Que la Banque mondiale détient un solde de 334 $US, coûts d’appui d’agence compris, pour un projet financé par des contributions volontaires de la part d’un groupe de pays donateurs destinées à financer des activités à démarrage rapide pour la mise en œuvre de la réduction des émissions de HFC ;

- Que le montant net restitué à la 91e réunion par le gouvernement de la France s’élève à 21 199 $US, comprenant 18 488 $US, plus coûts d’appui d’agence de 1 479 $US, et des intérêts courus de 1 232 $US qui seraient considérés comme un revenu supplémentaire pour le Fonds ;

## De demander :

### Aux agences bilatérales et d’exécution d’effectuer le décaissement ou d’annuler les sommes engagées et non engagées qui ne sont pas nécessaires pour les projets achevés et les projets achevés « par décision du Comité exécutif » et de retourner les soldes associés à la 92e réunion ;

### Au PNUD et à l’ONUDI de procéder au décaissement ou d’annuler ses engagements pour les projets achevés depuis plus de deux ans, et de restituer les soldes à la 92e réunion.

### Au PNUD, à l’ONUDI et à la Banque mondiale de procéder au décaissement ou de restituer à la 92e réunion les soldes des projets achevés qui ont été financés au moyen des contributions volontaires supplémentaires.

### À l’ONUDI de restituer à la 92e réunion les soldes de deux projets achevés « par décision du Comité exécutif », conformément à la décision 86/17 i) i); et

### Au Trésorier d’effectuer le suivi auprès du gouvernement de la France concernant la restitution, en liquidités, du montant de 21 199 $US dont il est question ci-dessus à l’alinéa a) vi).

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2021 (US $) | Funds disbursed as of 91st meeting (US $) | Balances committed as per 91st meeting (US $) | Balances not-committed as per 91st meeting (US $) | Support cost on balances committed and not committed as per 91st meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/84/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 7,391 | 22,609 |  | 2,035 |  |  |  |
| ARM/PHA/86/INV/26 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 21,600 | 20,361 | 1,239 |  | 112 |  |  |  |
| BZE/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 8,750 | 1,250 |  | 87 |  |  |  |
| CHI/SEV/83/INS/198 | Extension of the institutional strengthening project (phase XIII: 7/2019-6/2021) | Dec-21 | 238,784 | 238,615 | 169 |  | 12 |  |  |  |
| COL/PHA/81/INV/102 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Dec-21 | 1,137,247 | 594,529 | 542,718 |  | 37,990 |  |  |  |
| COL/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 11/2017-10/2019) | Jul-21 | 352,768 | 351,995 | 773 |  | 54 |  |  |  |
| COS/SEV/84/INS/62 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Dec-21 | 179,857 | 179,595 | 262 |  | 18 |  |  |  |
| CUB/PHA/82/PRP/61 | Preparation of a HCFC phase-out management plan (stage II) | Oct-21 | 60,000 | 33,458 | 26,542 |  | 1,858 |  |  |  |
| CUB/PHA/85/TAS/63 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-21 | 56,000 | 55,793 | 207 |  | 16 |  |  |  |
| CUB/SEV/81/TAS/57 | Enabling activities for HFC phase-down | Dec-21 | 75,000 | 71,408 | 3,592 |  | 251 |  |  |  |
| DOM/PHA/82/INV/66 | HCFC phase-out management plan (stage II, second tranche) | Dec-21 | 574,200 | 570,291 | 3,909 |  | 274 |  |  |  |
| DOM/PHA/83/PRP/68 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 47,408 | 12,592 |  | 881 |  |  |  |
| DOM/PHA/86/INV/70 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 146,558 | 0 | 146,558 |  | 10,259 |  |  |  |
| DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 17,143 | 12,931 | 4,212 |  | 295 |  |  |  |
| ELS/PHA/79/TAS/36 | Verification report for stage I of HCFC phase-out management plan | Jun-21 | 30,000 | 29,165 | 835 |  | 75 |  |  |  |
| ELS/PHA/86/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-21 | 16,000 | 0 | 16,000 |  | 1,200 |  |  |  |
| ELS/SEV/81/TAS/37 | Enabling activities for HFC phase-down | Sep-21 | 100,000 | 99,608 | 392 |  | 27 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 48,633 | 11,217 |  | 1,010 |  |  |  |
| FIJ/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 30,000 | 26,442 | 3,558 |  | 249 |  |  |  |
| GHA/PHA/84/INV/48 | HCFC phase-out management plan (stage I, sixth tranche) | Dec-21 | 121,311 | 112,739 | 8,572 |  | 643 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 142,861 | 16,889 |  | 1,182 |  |  |  |
| HAI/SEV/84/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 95,000 | 70,986 | 24,014 |  | 1,681 |  |  |  |
| IND/SEV/84/INS/478 | Extension of institutional strengthening project (phase XII: 12/2019-11/2021) | Nov-21 | 477,734 | 476,187 | 1,547 |  | 108 |  |  |  |
| IRA/PHA/84/INV/238 | HCFC phase-out management plan (stage II, second tranche) (commercial refrigeration sector) | Dec-20 | 636,320 | 619,543 | 16,777 |  | 1,174 |  |  |  |
| IRA/PHA/84/TAS/241 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project monitoring and coordination) | Dec-21 | 415,889 | 0 | 415,889 |  | 29,112 |  |  |  |
| IRA/SEV/82/INS/231 | Extension of the institutional strengthening project (phase XII: 4/2019-3/2021) | Mar-21 | 222,094 | 175,333 | 46,761 |  | 3,273 |  |  |  |
| JAM/PHA/76/INV/36 | HCFC phase-out management plan (stage I, third tranche) | Jan-21 | 183,000 | 167,895 | 15,105 |  | 1,133 |  |  |  |
| JAM/PHA/81/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Jul-21 | 40,000 | 33,501 | 6,499 |  | 455 |  |  |  |
| JAM/PHA/84/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 26,579 | 3,421 |  | 308 |  |  |  |
| JAM/PHA/85/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-21 | 58,000 | 0 | 58,000 |  | 4,350 |  |  |  |
| KYR/PHA/85/INV/42 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 55,000 | 54,566 | 434 |  | 30 |  |  |  |
| MAL/PHA/77/TAS/182 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-21 | 949,548 | 848,087 | 101,461 |  | 7,102 |  |  |  |
| MAL/SEV/84/INS/188 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Dec-21 | 357,760 | 340,441 | 17,319 |  | 1,212 |  |  |  |
| MOL/PHA/86/INV/43 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 17,450 | 0 | 17,450 |  | 1,570 |  |  |  |
| PAN/PHA/82/INV/48 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-21 | 385,800 | 312,931 | 72,869 |  | 5,101 |  |  |  |
| PAN/PHA/83/PRP/49 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 42,695 | 17,305 |  | 1,211 |  |  |  |
| PAN/PHA/85/TAS/51 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 72,754 | 0 | 72,754 |  | 5,093 |  |  |  |
| PAN/SEV/81/TAS/46 | Enabling activities for HFC phase-down | Dec-21 | 100,000 | 99,825 | 175 |  | 12 |  |  |  |
| SWA/PHA/83/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 5,513 | 4,487 |  | 314 |  |  |  |
| TRI/PHA/82/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | Jan-21 | 60,000 | 59,094 | 906 |  | 63 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 61,603 | 38,397 |  | 2,688 |  |  |  |
| TOTAL UNDP |  |  |  |  | 1,755,664 |  | 124,521 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| AFG/PHA/79/TAS/21 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 120,000 | 108,626 | 11,374 |  | 1,479 |  |  |  |
| AFG/SEV/83/INS/26 | Extension of institutional strengthening project (phase IX: 1/2020-12/2021) | Dec-21 | 192,000 | 153,881 | 38,119 |  | - |  |  |  |
| ELS/PHA/77/TAS/35 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 171,000 | 121,226 | 49,774 |  | 1,362 |  |  |  |
| ETH/PHA/81/PRP/29 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 22,000 | 7,000 | 15,000 |  | 1,950 |  |  |  |
| GAM/PHA/86/TAS/39 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-21 | 21,000 | 11,000 | 10,000 |  | 1,300 |  |  |  |
| GLO/SEV/86/TAS/356 | Compliance Assistance Programme: 2021 budget | Dec-21 | 8,229,257 | 6,162,957 | 300,301 |  | 24,024 |  |  |  |
| GRN/SEV/81/INS/24 | Extension of the institutional strengthening project (phase VI: 6/2018-5/2020) | Jun-21 | 85,000 | 68,000 | 17,000 |  | - |  |  |  |
| GUA/SEV/81/INS/53 | Renewal of the institutional strengthening project (phase VIII: 7/2018-6-2020) | Dec-21 | 159,744 | 149,891 | 9,853 |  | - |  |  |  |
| KUW/PHA/84/PRP/39 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 75,000 | 16,665 | 58,335 |  | 7,584 |  |  |  |
| KUW/SEV/81/INS/34 | Extension of institutional strengthening project (phase VII: 6/2018-5/2020) | May-21 | 134,810 | 128,010 | 6,800 |  | - |  |  |  |
| KUW/SEV/81/TAS/33 | Enabling activities for HFC phase-down | Dec-21 | 250,000 | 0 | 250,000 |  | 17,500 |  |  |  |
| MOL/SEV/82/INS/37 | Extension of the institutional strengthening project (phase X: 1/2019-12/2020) | Dec-21 | 88,748 | 85,951 | 2,797 |  | - |  |  |  |
| NIC/PHA/81/TAS/36 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 30,000 | 23,638 | 6,362 |  | 827 |  |  |  |
| PAK/PHA/76/TAS/93 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-21 | 200,000 | 184,114 | 15,886 |  | 2,063 |  |  |  |
| PAR/SEV/82/INS/38 | Extension of institutional strengthening project (phase IX: 1/2019-12/2020) | Dec-21 | 85,000 | 78,260 | 6,740 |  | - |  |  |  |
| PHI/SEV/83/INS/106 | Extension of institutional strengthening project (phase XII: 1/2020-12/2021) | Dec-21 | 231,850 | 197,757 | 34,093 |  | - |  |  |  |
| QAT/PHA/73/PRP/20 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 20,000 | 10,100 | 9,900 |  | 1,287 |  |  |  |
| QAT/SEV/82/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 50,000 | 10,000 | 40,000 |  | 2,800 |  |  |  |
| SAU/SEV/81/TAS/33 | Enabling activities for HFC phase-down | Dec-21 | 250,000 | 87,170 | 162,830 |  | 11,398 |  |  |  |
| SEN/PHA/85/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 40,000 | 29,958 | 10,042 |  | 1,306 |  |  |  |
| SEN/PHA/85/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 120,000 | 90,000 | 30,000 |  | 3,900 |  |  |  |
| SWA/PHA/83/PRP/26 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 20,000 | 5,000 | 15,000 |  | 1,950 |  |  |  |
| TON/PHA/85/TAS/16 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | Dec-21 | 12,700 | 1,660 | 11,040 |  | 1,435 |  |  |  |
| TOTAL UNEP |  |  |  |  | 1,111,248 |  | 82,164 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| AFG/PHA/77/INV/20 | HCFC phase-out management plan (stage I, second tranche) | Sep-21 | 131,938 | 131,427 | 511 |  | 46 | 2 | 92 |  |
| BDI/PHA/81/INV/37 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 80,000 | 79,816 | 184 |  | 17 | 3 | 92 |  |
| BHA/PHA/80/INV/25 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 35,828 | 35,823 | 5 |  | 0 | 3 | 92 | 88/40(a) |
| CPR/PHA/64/INV/513 | HCFC phase-out management plan (room air-conditioner manufacturing sector plan) (stage I, first tranche) | Dec-21 | 36,430,000 | 36,429,917 | 83 |  | 6 | 3 | 92 | 84/68(d)(i) and 86/33(d) |
| CPR/PHA/71/INV/536 | HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan) | Dec-21 | 8,495,000 | 8,494,893 | 107 |  | 8 | 3 | 92 | 84/68(d)(i) and 86/33(d) |
| ECU/PHA/87/TAS/78 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-21 | 10,000 | 0 | 10,000 |  | 700 | 3 | 92 |  |
| GAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 49,238 | 762 |  | 69 | 3 | 92 |  |
| GAM/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 9,238 | 762 |  | 53 | 2 | 92 |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Jun-21 | 4,353,530 | 4,317,013 | 36,517 |  | 2,739 | 2 | 92 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/PHA/73/PRP/19 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 25,000 | 24,974 | 26 |  | 2 | 3 | 92 |  |
| IRQ/PHA/84/INV/29 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Dec-21 | 210,000 | 177,161 | 32,839 |  | 2,463 | 3 | 92 |  |
| MAG/PHA/76/INV/28 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 120,000 | 119,536 | 464 |  | 35 | 3 | 92 |  |
| MOG/PHA/83/INV/13 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-21 | 30,000 | 27,377 | 2,623 |  | 197 | 3 | 92 |  |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 27,485 | 2,515 |  | 226 | 2 | 92 |  |
| MOG/PHA/85/INV/15 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-21 | 21,000 | 20,725 | 275 |  | 21 | 3 | 92 |  |
| NIR/PHA/81/INV/146 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector and project management unit) | Dec-21 | 176,837 | 176,505 | 332 |  | 30 | 3 | 92 |  |
| PRC/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 75,000 | 70,782 | 4,218 |  | 380 | 3 | 92 |  |
| SAU/FOA/62/INV/13 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | Dec-21 | 1,103,578 | 876,888 | 226,690 |  | 17,002 | 3 | 92 | 86/17(i)(i) |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-20 | 2,693,674 | 2,084,045 | 609,629 |  | 42,674 | 2 | 92 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 46,946 | 3,054 |  | 229 | 3 | 92 |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,037,077 | 5,543 |  | 388 | 2 | 92 |  |
| SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Dec-21 | 1,465,361 | 1,462,556 | 2,805 |  | 210 | 3 | 92 |  |
| TOG/PHA/79/INV/30 | HCFC phase-out management plan (stage I, third tranche) | Jun-21 | 150,000 | 148,736 | 1,264 |  | 95 | 2 | 92 |  |
| TOTAL UNIDO |  |  |  |  | 941,207 |  | 67,588 |  |  |  |
| JAPAN |  |  |  |  |  |  |  |  |  |  |
| VIE/PHA/76/TAS/71 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-21 | 43,250 | 43,038 | 212 |  | 28 |  |  |  |
| TOTAL JAPAN |  |  |  |  | 212 |  | 28 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2021 (US $) | Funds disbursed as of 91st meeting (US $) | Balances committed as per 91st meeting (US $) | Balances not- committed as per 91st meeting (US $) | Support cost on balances committed and not-committed as per 91st meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) |  | 270,000 | 258,221 | 11,779 |  | 825 |  | Financial completion initiated | 86/17(i)(i) |
| SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) |  | 1,100,000 | 1,089,997 | 10,003 |  | 700 |  | Financial completion initiated | 86/17(i)(i) |
| TOTAL UNIDO |  |  |  |  | 21,782 |  | 1,525 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2021 (US $) | Funds disbursed as of 91st meeting (US $) | Balances committed as per 91st meeting (US $) | Balances not- committed as per 91st meeting (US $) | Support cost on balances committed and not-committed as per 91st meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| COL/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 250,000 | 246,344 | 3,656 |  | 256 |  |  |
| FIJ/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 150,000 | 136,999 | 13,001 |  | 910 |  |  |
| PAR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 75,000 | 72,427 | 2,573 |  | 180 |  |  |
| URU/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 100,000 | 78,121 | 21,879 |  | 1,532 |  |  |
| TOTAL UNDP |  |  |  | 41,109 |  | 2,878 |  |  |
| UNIDO |  |  |  |  |  |  |  |  |
| BKF/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 150,000 | 144,938 | 5,062 |  | 285 | 2 | 92 |
| MEX/REF/81/INV/04+ | Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera | 1,018,123 | 925,466 | 92,657 |  | 6,486 | 3 | 92 |
| PHI/SEV/83/TAS/02+ | Enabling activities for HFC phase-down | 225,992 | 207,370 | 18,622 |  | 1,304 | 3 | 92 |
| SOA/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 240,000 | 213,017 | 26,983 |  | 1,889 | 2 | 92 |
| SOM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 150,000 | 147,945 | 2,055 |  | 144 | 3 | 92 |
| TUR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 250,000 | 198,372 | 51,628 |  | 3,614 | 3 | 92 |
| URU/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 50,000 | 49,926 | 74 |  | 5 | 3 | 92 |
| TOTAL UNIDO |  |  |  | 197,080 |  | 13,726 |  |  |

| World Bank |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| THA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 250,000 | 249,688 | 312 |  | 22 | Financial closure underway where outstanding commitments will be verified. |  |
| TOTAL WORLD BANK |  |  |  | 312 |  | 22 |  |  |

Annex IV

DETAILS ON COMPLETED, AND ADDITIONAL VOLUNTARY CONTRIBUTION PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Interest | Total (US $) |
| --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |
| CHI/PHA/76/INV/192 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | 426 | 32 |  | 458 |
| CPR/SEV/82/INS/596 | Extension of the institutional strengthening project (phase XIII: 1/2019-12/2020) | 2,430 | 170 |  | 2,600 |
| CUB/PHA/68/INV/50 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | -1,666 | -125 |  | -1,791 |
| FIJ/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 6,914 | 622 |  | 7,536 |
| GEO/PHA/84/PRP/41 | Preparation of a HCFC phase-out management plan (stage II) | 11,185 | 783 |  | 11,968 |
| GEO/SEV/81/INS/40 | Extension of the institutional strengthening project (phase X: 6/2018-5/2020) | 85 | 6 |  | 91 |
| HAI/PHA/76/INV/22 | HCFC phase-out management plan (stage I, second tranche) | 719 | 65 |  | 784 |
| MOL/PHA/84/PRP/40 | Preparation of a HCFC phase-out management plan (stage III) | 635 | 44 |  | 679 |
| SRL/PHA/82/PRP/52 | Preparation of a HCFC phase-out management plan (stage II) | 2,481 | 174 |  | 2,655 |
| SRL/PHA/82/TAS/51 | Verification report on the implementation of the HCFC phase-out management plan | 1,316 | 118 |  | 1,434 |
| SRL/PHA/85/INV/54 | HCFC phase-out management plan (stage I, fourth tranche) | 4,675 | 351 |  | 5,026 |
| Total completed projects |  | 29,200 | 2,240 |  | 31,440 |
| CPR/FOA/82/INV/06+ | Conversion from C5+HFC-245fa to C5+HFOs in a domestic refrigerator manufacturer (Hisense Kelon) | 33 | 2 |  | 35 |
| JAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 4,917 | 344 |  | 5,261 |
| LEB/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 21 | 1 |  | 22 |
| TRI/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 4,267 | 299 |  | 4,566 |
| Total “additional voluntary contributions” projects |  | 9,238 | 647 |  | 9,885 |
| TOTAL UNDP |  | 38,438 | 2,887 |  | 41,325 |
| UNEP |  |  |  |  |  |
| ALB/PHA/85/TAS/40 | HCFC phase-out management plan (stage I, fifth tranche) | 150 | 20 |  | 170 |
| ARM/PHA/83/TAS/21 | HCFC phase-out management plan (stage II, second tranche) | 1,801 | 234 |  | 2,035 |
| ARM/PHA/84/PRP/22 | Preparation of a HCFC phase-out management plan (stage III) | 82 | 11 |  | 93 |
| ASP/PHA/81/PRP/61 | Development of stage II of HCFC phase-out management plans for PIC countries through regional approach | 16,500 | 2,145 |  | 18,645 |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | 11,540 | 1,500 |  | 13,040 |
| BAH/PHA/84/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 9,175 | 1,193 |  | 10,368 |
| BAH/PHA/84/TAS/36 | HCFC phase-out management plan (stage I, third and fourth tranches) (policy, refrigeration servicing, monitoring and verification) | 10,000 | 1,300 |  | 11,300 |
| BAH/SEV/81/TAS/34 | Enabling activities for HFC phase-down | 9,760 | 683 |  | 10,443 |
| BDI/SEV/81/INS/35 | Extension of the institutional strengthening project (phase VIII: 8/2018-7/2020) | 69 |  |  | 69 |
| BHA/PHA/82/TAS/27 | Verification report on the implementation of the HCFC phase-out management plan | 9,800 | 1,274 |  | 11,074 |
| CBI/PHA/81/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | 28 | 4 |  | 32 |
| CHD/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 39 | 5 |  | 44 |
| CKI/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| CMR/SEV/84/INS/46 | Extension of institutional strengthening project (phase XII: 1/2020-12/2021) | 601 |  |  | 601 |
| COI/PHA/83/TAS/28 | HCFC phase-out management plan (stage I, fourth tranche) | 124 | 16 |  | 141 |
| COL/PHA/81/TAS/105 | HCFC phase-out management plan (stage II, second tranche) (technical assistance in policies formulation and implementation) | 7,824 | 1,017 |  | 8,842 |
| DJI/SEV/81/INS/25 | Extension of the institutional strengthening project (phase VII: 7/2018-6/2020) | 123 |  |  | 123 |
| DOM/PHA/77/TAS/61 | HCFC phase-out management plan (stage II, first tranche) | 3 |  |  | 3 |
| DOM/PHA/82/TAS/67 | HCFC phase-out management plan (stage II, second tranche) | 4,926 | 640 |  | 5,567 |
| DRC/PHA/79/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | (7,143) | (929) |  | (8,071) |
| EGY/PHA/79/TAS/131 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 72 | 9 |  | 81 |
| EQG/SEV/81/INS/12 | Renewal of the institutional strengthening project (phase III: 6/2018-5/2020) | 30 |  |  | 30 |
| FIJ/SEV/82/INS/33 | Extension of the institutional strengthening project (phase XI: 1/2019-12/2020) | 5,000 |  |  | 5,000 |
| FSM/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| GLO/SEV/86/TAS/356 | Compliance Assistance Programme: 2021 budget | 1,765,999 | 141,280 |  | 1,907,279 |
| GUA/PHA/75/TAS/50 | HCFC phase-out management plan (stage I, third tranche) | 9 | 1 |  | 10 |
| GUA/PHA/81/TAS/52 | HCFC phase-out management plan (stage I, fourth tranche) | 4,651 | 605 |  | 5,256 |
| HAI/PHA/86/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 |  | 33,900 |
| HON/PHA/81/TAS/45 | HCFC phase-out management plan (stage I, fourth tranche) | 119 | 15 |  | 134 |
| IRA/PHA/77/TAS/227 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 15,431 | 1,918 |  | 17,348 |
| IRQ/PHA/74/TAS/22 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 16,341 | 2,053 |  | 18,394 |
| IRQ/PHA/84/TAS/28 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 19,880 | 2,497 |  | 22,377 |
| IRQ/SEV/81/TAS/26 | Enabling activities for HFC phase-down | 81,970 | 5,738 |  | 87,708 |
| IVC/SEV/83/INS/43 | Extension of the institutional strengthening project (phase IX: 6/2019-5/2021) | 115 |  |  | 115 |
| KIR/PHA/84/TAS/15 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| KIR/SEV/83/INS/14 | Renewal of institutional strengthening project (phase VII: 10/2019-9/2021) | 5,000 |  |  | 5,000 |
| KUW/REF/75/TAS/29 | Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling) | 544 | 71 |  | 615 |
| MAR/SEV/82/TAS/28 | Enabling activities for HFC phase-down | 10,378 | 726 |  | 11,104 |
| MAS/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| MOL/PHA/84/PRP/39 | Preparation of a HCFC phase-out management plan (stage III) | 2,144 | 279 |  | 2,423 |
| MOL/PHA/84/TAS/38 | HCFC phase-out management plan (stage II, second tranche) | 2,703 | 351 |  | 3,054 |
| MON/PHA/82/TAS/28 | Verification report on the implementation of the HCFC phase-out management plan | (58) | (8) |  | (66) |
| MOZ/SEV/82/INS/29 | Extension of the institutional strengthening project (phase VIII: 1/2019-12/2020) | 139 |  |  | 139 |
| NAU/PHA/84/TAS/12 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| NAU/SEV/72/INS/09 | Extension of the institutional strengthening project (phase V: 8/2014-7/2016) | 19,371 |  |  | 19,371 |
| NIU/PHA/74/TAS/10 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Niue) | 5,990 | 779 |  | 6,769 |
| NIU/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| NIU/SEV/82/INS/13 | Extension of the institutional strengthening project (phase VII: 4/2019-3/2021) | 28,806 |  |  | 28,806 |
| OMA/PHA/82/TAS/38 | HCFC phase-out management plan (stage II, second tranche) | 4,950 | 644 |  | 5,594 |
| OMA/PHA/86/PRP/39 | Preparation of a HCFC phase-out management plan (stage III) | 20,000 | 2,600 |  | 22,600 |
| OMA/PHA/86/TAS/41 | HCFC phase-out management plan (stage II, third tranche) | 19,500 | 2,535 |  | 22,035 |
| OMA/SEV/81/TAS/35 | Enabling activities for HFC phase-down | 20,939 | 1,466 |  | 22,404 |
| PAR/PHA/82/PRP/39 | Preparation of a HCFC phase-out management plan (stage II) | 6,430 | 836 |  | 7,266 |
| PRC/SEV/81/INS/32 | Extension of the institutional strengthening project (phase X: 6/2018-5/2020) | 200 |  |  | 200 |
| SIL/PHA/86/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | 42 | 6 |  | 48 |
| STL/PHA/82/PRP/28 | Preparation of a HCFC phase-out management plan (stage II) | 9,900 | 1,287 |  | 11,187 |
| STL/PHA/82/TAS/30 | Verification report on the implementation of the HCFC phase-out management plan | 9,800 | 1,274 |  | 11,074 |
| STP/PHA/81/TAS/27 | HCFC phase-out management plan (stage I, fourth tranche) | 162 | 21 |  | 183 |
| STP/PHA/85/TAS/31 | HCFC phase-out management plan (stage I, fifth tranche) | 123 | 16 |  | 139 |
| STP/SEV/82/INS/30 | Extension of the institutional strengthening project (phase VI: 1/2019-12/2020) | 124 |  |  | 124 |
| TLS/PHA/86/TAS/21 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| TUV/PHA/84/TAS/15 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| TUV/SEV/82/INS/14 | Extension of the institutional strengthening project (phase VII: 4/2019-3/2021) | 5,000 |  |  | 5,000 |
| UGA/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | 5,156 | 670 |  | 5,826 |
| UGA/SEV/82/INS/26 | Extension of the Institutional strengthening project (phase III: 1/2019-12/2020) | 156 |  |  | 156 |
| URT/PHA/67/TAS/31 | HCFC phase-out management plan (stage I, first tranche) | 20,000 | 2,600 |  | 22,600 |
| VAN/PHA/84/TAS/16 | Verification report on the implementation of the HCFC phase-out management plan | 19,900 | 2,587 |  | 22,487 |
| Total completed projects |  | 2,391,619 | 206,564 |  | 2,598,184 |
| BHU/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 346 | 24 |  | 370 |
| CPR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 5,315 | 372 |  | 5,687 |
| DOM/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 482 | 34 |  | 516 |
| ECU/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 29,275 | 2,049 |  | 31,324 |
| ERI/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,178 | 152 |  | 2,330 |
| ETH/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 792 | 55 |  | 847 |
| FSM/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 1,754 | 123 |  | 1,876 |
| GUA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 21,733 | 1,521 |  | 23,254 |
| MEX/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 9,244 | 647 |  | 9,891 |
| MLW/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 46 | 3 |  | 49 |
| MOZ/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 670 | 47 |  | 717 |
| NAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,327 | 163 |  | 2,490 |
| NAU/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 23,938 | 1,676 |  | 25,614 |
| NIR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 4,132 | 289 |  | 4,421 |
| NIU/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 16,137 | 1,130 |  | 17,266 |
| RWA/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 3,810 | 267 |  | 4,077 |
| SAM/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 982 | 69 |  | 1,051 |
| SEN/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 12,186 | 853 |  | 13,039 |
| SIL/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 259 | 18 |  | 277 |
| SSD/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 209 | 15 |  | 224 |
| SWA/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 491 | 34 |  | 525 |
| TKM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 1,045 | 73 |  | 1,118 |
| TOG/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 20,512 | 1,436 |  | 21,948 |
| TUV/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 24,369 | 1,706 |  | 26,075 |
| UGA/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 237 | 17 |  | 254 |
| URT/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 815 | 57 |  | 872 |
| VAN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 3,155 | 221 |  | 3,376 |
| ZAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 746 | 52 |  | 798 |
| Total “additional voluntary contributions” projects |  | 187,183 | 13,103 |  | 200,286 |
| TOTAL UNEP |  | 2,578,802 | 219,667 |  | 2,798,469 |
| UNIDO |  |  |  |  |  |
| BOT/PHA/83/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | 278 | 19 |  | 297 |
| CHI/PHA/86/PRP/202 | Preparation of a HCFC phase-out management plan (stage III) | 476 | 33 |  | 509 |
| CPR/PRO/73/INV/552 | Sector plan for methyl bromide production sector (fourth tranche) | 6,731 | 504 |  | 7,236 |
| ECU/PHA/81/INV/65 | HCFC phase-out management plan (stage I) (foam sector plan) | 114,550 | 8,018 |  | 122,568 |
| EGY/PHA/79/INV/136 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector and project management unit) | 1,063 | 75 |  | 1,138 |
| ETH/PHA/77/INV/28 | HCFC phase-out management plan (stage I, second tranche) | 4,644 | 418 |  | 5,062 |
| ETH/PHA/81/PRP/30 | Preparation of a HCFC phase-out management plan (stage II) | 5,556 | 389 |  | 5,944 |
| IRQ/REF/73/PRP/20 | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | 27,852 | 1,950 |  | 29,802 |
| KUW/PHA/83/TAS/35 | HCFC phase-out management plan (stage I, third tranche) (extruded polystyrene foam sector phase-out) | 934 | 65 |  | 999 |
| KUW/PHA/84/PRP/40 | Preparation of a HCFC phase-out management plan (stage II) | 40 | 3 |  | 43 |
| MDN/PHA/86/INV/44 | HCFC phase-out management plan (stage I, tenth tranche) | 72 | 5 |  | 78 |
| MDN/PHA/86/TAS/43 | Verification report on implementation of stage I of the HCFC phase-out management plan | 17,341 | 1,561 |  | 18,902 |
| MEX/SEV/82/INS/191 | Extension of institutional strengthening project (phase XIV: 7/2019-6/2021) | 17,505 | 1,225 |  | 18,730 |
| MOR/PHA/83/INV/75 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 2,685 | 201 |  | 2,886 |
| NIC/PHA/86/INV/44 | HCFC phase-out management plan (stage I, fourth tranche) | 1,071 | 96 |  | 1,167 |
| OMA/SEV/82/INS/36 | Renewal of institutional strengthening support (phase VII: 12/2018-11/2020) | 1,138 | 80 |  | 1,218 |
| SIL/PHA/84/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | 1,056 | 74 |  | 1,130 |
| SUR/PHA/81/INV/27 | HCFC phase-out management plan (stage I, third tranche) | 9,633 | 867 |  | 10,500 |
| SYR/FOA/61/PRP/102 | Preparation for HCFC phase-out investment activities (foam sector) | 335 | 25 |  | 360 |
| SYR/PHA/55/PRP/97 | Preparation of a HCFC phase-out management plan | 4,057 | 305 |  | 4,362 |
| TUR/PHA/68/INV/102 | HCFC phase-out management plan (stage I, first tranche) (technical assistance for small and medium enterprises in the foam sector) |  | (4) |  | (4) |
| ZAM/PHA/83/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 6,960 | 487 |  | 7,448 |
| Total completed projects |  | 223,977 | 16,397 |  | 240,374 |
| BHE/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 80 | 6 |  | 86 |
| NER/SEV/81/TAS/01+ | Technical assistance/support | 1,756 | 123 |  | 1,879 |
| Total “additional voluntary contributions” projects |  | 1,836 | 129 |  | 1,965 |
| TOTAL UNIDO |  | 225,813 | 16,526 |  | 242,339 |
| WORLD BANK |  |  |  |  |  |
| IDS/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 3,334 | 233 |  | 3,568 |
| Total “additional voluntary contributions” projects |  | 3,334 | 233 |  | 3,568 |
| TOTAL WORLD BANK |  | 3,334 | 233 |  | 3,567 |
| FRANCE |  |  |  |  |  |
| TUN/PHA/84/INV/79 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 18,488 | 1,479 | 1,232 | 21,199 |
| Total completed projects |  | 18,488 | 1,479 | 1,232 | 21,199 |
| TOTAL FRANCE |  | 18,488 | 1,479 | 1,232 | 21,199 |

UNEP/OzL.Pro/ExCom/91/1

Les données présentées s’appuient sur le format de rapport élaboré conformément à la décision 31/2.

UNEP/OzL.Pro/ExCom/91/3

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5: Project is ongoing; 6: Funds were not transferred.

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5: Project is ongoing; 6: Funds were not transferred