| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/15 30 October 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 7(a)(ii) of the provisional agenda

PROGRESS REPORT Of BILATERAL COOPERATION as at 31 december 2023

Introduction

# The following non-Article 5 countries currently involved in bilateral cooperation activities submitted progress report databases: Australia, Canada, France, Germany, Italy, Japan, and Spain. Additional data from earlier progress reports for other non-Article 5 countries previously involved in bilateral cooperation, covering data for the projects already reported as financially completed, are included in the consolidated progress report.

# The progress report of the bilateral cooperation includes the implementation status of projects, including seven HFC-related projects funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for the implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2023, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2023 and cumulative since 1992 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2023 and cumulative since 1992

# As of 31 December 2023, the Executive Committee had approved US $189 million in projects for the bilateral agencies, consisting of US $172.27 million for the implementation of investment and non-investment projects and US $16.73 million for agency support costs, as shown in table 1.

Table 1: Approved funding by sector for bilateral agencies as at 31 December 2023

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 2,051,914 |
| Destruction | 1,866,282 |
| Energy efficiency | 843,745 |
| Foam | 8,093,731 |
| Halon | 6,147,361 |
| HFC phase-down plan | 774,000 |
| Fumigants | 18,226,925 |
| Phase-out plan | 76,082,047 |
| Production | 10,000,000 |
| Refrigeration | 40,910,116 |
| Several | 4,759,718 |
| Solvents | 2,512,738 |
| Sub-total | 172,268,576 |
| Agency support costs | 16,730,516 |
| Total | 188,999,093 |

# In 2023, 23 new projects and activities were approved. This level of funding is expected to result in the phase-out of 10,476 ODP tonnes of consumption of ODS and 48.9 mt (70,104 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2023.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2023. Annex II presents analytical information per year since 1992.

Table 2. Status of project implementation by type as at 31 December 2023

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 9 | 9 | 100 | 340,787 | 340,787 | 0 | 100 |
| Demonstration | 39 | 38 | 97 | 9,533,176 | 9,409,431 | 123,745 | 99 |
| Institutional strengthening (IS) | 7 | 7 | 100 | 883,376 | 883,376 | 0 | 100 |
| Investment | 255 | 222 | 87 | 117,633,417 | 108,024,447 | 9,608,970 | 92 |
| Project preparation | 139 | 126 | 91 | 6,695,111 | 5,665,522 | 1,029,589 | 85 |
| Technical assistance | 224 | 210 | 94 | 28,761,293 | 27,312,641 | 1,448,653 | 95 |
| Training | 73 | 73 | 100 | 8,421,416 | 8,421,416 | 0 | 100 |
| Total | 746 | 685 | 92 | 172,268,576 | 160,057,619 | 12,210,957 | 93 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by the bilateral agencies for 2023 and cumulative since 1992 up to 31 December 2023 is summarized as follows and in table 3:

## Phase-out: In 2023, 5.1 ODP tonnes of consumption of ODS were phased out and an additional 8.2 ODP tonnes of consumption of ODS were approved for phase-out. Since 1992, 9,215 ODP tonnes had been phased out, of an expected total of 10,476 ODP tonnes of consumption of ODS and 45.5 mt (65,242 CO2-eq tonnes) had been phased out, of an expected total of 48.9 mt (70,104 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2023, US $3.69 million was disbursed and US $5.24 million was planned for disbursement based on the 2022 progress report, representing a rate of disbursement of 70 per cent of that planned. Cumulatively, US $160.06 million had been disbursed out of the total US $172.27 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 93 per cent. In 2023, US $2.2 million was approved for implementation;

## Number of projects completed: In 2023, 15 projects were completed. Since 1992, 685 projects of the 746 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 92 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2023 were completed on average 59 months after their approval. Since 1992, the average time for completion of investment projects has been 42 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2023 were completed 67 months after their approval. Since 1992, the average time for completion of non-investment projects has been 44 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 139 project preparation activities approved by the end of 2023, 126 have been completed, leaving 13 ongoing activities. In 2023, three preparation activities were completed;

## Implementation delays: A total of 61 projects were under implementation at the end of 2023, experiencing, on average, a delay of 15 months. Sixteen of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2023, 25 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1992, 91 MYAs have been approved and 66 MYAs have been completed, representing a completion rate of 73 per cent.

# Table 3 summarizes progress made by the bilateral agencies since 1992.

## Table 3. Progress made by bilateral agencies since 1992

| Phase out achieved |  | Disbursement (US $) | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes |  | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 9,215 | 65,242 | 160,057,619 | 746 | 685 | 42 | 44 | 15 | 91 | 66 |

HFC-related projects

# As of 31 December 2023, the Executive Committee had approved 19 HFC-related projects (including one demonstration project, three investment projects, 10 project preparation activities and five technical assistance projects for enabling activities) under regular contributions amounting to US $2,012,733 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Demonstration | 1 | 0 | 0 | 123,745 | 0 | 123,745 | 0 |
| Investment** | 3 | 2 | 67 | 764,988 | 764,988 | 0 | 100 |
| Project preparation | 10 | 1 | 10 | 834,000 | 144,410 | 689,590 | 17 |
| Technical assistance | 5 | 5 | 100 | 290,000 | 290,000 | 0 | 100 |
| Total | 19 | 8 | 42 | 2,012,733 | 1,199,398 | 813,335 | 60 |

* Excludes agency support costs.

** 45.5 mt (65,242 CO2-eq tonnes) of 48.9 mt (70,104 CO2-eq tonnes) of HFCs had been phased out.

# As of the end of 2023, of the 19 projects approved, two investment projects, one project preparation activity and five technical assistance projects for enabling activities had been completed, leaving 11 ongoing. These activities are at various stages of implementation.

# Of the total cumulative funding approved of US $2,012,733, US $1,199,398 had been disbursed, representing a disbursement rate of 60 per cent.

I.2	Issues identified in project implementation in 2023

# Further to the review process, several issues were discussed with relevant bilateral agencies and satisfactorily addressed, except for issues on 16 projects classified as projects with implementation delays (including 14 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); one HFC investment project; and one technical assistance project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 96th meeting.

# Details of progress in implementation of projects associated with the HPMPs for China (servicing sector plan) (implemented by Germany and Japan), India (implemented by Germany), and the Pacific Island countries (implemented by Australia), and reports on projects with specific reporting requirements associated with the Kigali HFC implementation plan of Burkina Faso (implemented by Germany) and the HPMP of Viet Nam (implemented by Japan), have been submitted to the 95th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Kenya (implemented by France) and Mauritius (implemented by Germany), tranches of which were due at the 95th meeting but were not submitted, are addressed in the document on tranche submission delays.

# Of the 48 ongoing projects, excluding project preparation, 16 projects have revised planned dates of completion since the 2022 progress report.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2023, the Executive Committee had approved seven HFC-related projects for two bilateral agencies (Germany and Italy) under the additional voluntary contributions amounting to US $480,000 (excluding agency support costs). A summary of the status of these projects is presented in table 5.

# Table 5. Status of approved HFC-related projects as of the end of 2023

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance – Enabling activities | 7 | 7 | 100 | 480,000 | 479,080 | 920 | 99.8 |

* Excludes agency support costs.

# As of the end of 2023, all of the seven enabling activities approved had been completed.

# Of the total cumulative funding approved of US $480,000, US $479,080 had been disbursed, representing a disbursement rate of 99.8 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note, with appreciation, the progress reports, as at 31 December 2023, submitted by the Governments of Australia, Canada, France, Germany, Italy, Japan and Spain contained in document UNEP/OzL.Pro/ExCom/95/15; and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER COUNTRY FOR 2023

# Table 1 of annex I presents the status of project implementation by country for 2023 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation for 2023

| Country | Phased out in 2023 (ODP tonnes) | Phased out in 2023 (CO2-eq tonnes)* | Estimated funds disbursed in 2023 (US$) | Funds disbursed in 2023 (US$) | Percentage of funds disbursed over estimation in 2023 | Percentage of planned projects completed in 2023** |
| --- | --- | --- | --- | --- | --- | --- |
| Argentina | 0.0 | 0 | 40,000 | 0 | 0 |  |
| Brazil | 0.0 | 0 | 1,198,203 | 590,493 | 49 | 100 |
| Burkina Faso | 0.0 | 0 | 36,957 | 576 | 2 | 0 |
| China | 0.0 | 0 | 474,017 | 139,507 | 29 | 100 |
| Colombia | 0.0 | 0 | 60,308 | 2,498 | 4 | 50 |
| Egypt | 0.0 | 0 | 151,551 | 48,602 | 32 | 0 |
| India | 0.0 | 0 | 1,081,000 | 941,000 | 87 | 33 |
| Iran (Islamic Republic of) | 0.0 | 0 | 432,400 | 73,742 | 17 | 20 |
| Kenya | 0.0 | 0 | 131,897 | 72,630 | 55 |  |
| Lesotho | 0.0 | 0 | 51,159 | 67,963 | 133 |  |
| Liberia | 0.0 | 0 | 90,346 | 61,319 | 68 | 0 |
| Mauritius | 0.0 | 0 | 176,800 | 118,363 | 67 | 0 |
| Mexico | 3.5 | 0 | 851,616 | 961,547 | 113 | 100 |
| Mongolia | 0.0 | 0 | 3,000 | 8,112 | 270 | 0 |
| Namibia | 0.0 | 0 | 44,757 | 12,228 | 27 |  |
| Nigeria | 1.6 | 0 | 120,000 | 251,059 | 209 |  |
| Papua New Guinea | 0.0 | 0 | 16,805 | 44,276 | 263 | 100 |
| Seychelles | 0.0 | 0 | 74,555 | 38,011 | 51 | 100 |
| Viet Nam | 0.0 | 0 | 77,502 | 0 | 0 | 100 |
| Zimbabwe | 0.0 | 0 | 40,806 | 125,469 | 307 | 50 |
| Region: ASP | 0.0 | 0 | 81,497 | 131,889 | 162 | 0 |
| Grand total | 5.1 | 0 | 5,235,176 | 3,689,283 | 70 | 46 |

* No phase-out in 2023 for HFC-related projects.

** For projects that were planned to be completed in 2023.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR BILATERAL AGENCIES PER YEAR AS AT 31 DECEMBER 2023

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1992 and 2014, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1992 | 18 | 18 | 100 | 2,883,669 | 2,883,669 | 0 | 100 |
| 1993 | 10 | 10 | 100 | 1,445,586 | 1,445,586 | 0 | 100 |
| 1994 | 30 | 30 | 100 | 3,190,374 | 3,190,374 | 0 | 100 |
| 1995 | 17 | 17 | 100 | 4,654,902 | 4,654,902 | 0 | 100 |
| 1996 | 26 | 26 | 100 | 3,468,211 | 3,468,211 | 0 | 100 |
| 1997 | 32 | 32 | 100 | 4,040,251 | 4,040,251 | 0 | 100 |
| 1998 | 39 | 39 | 100 | 4,108,525 | 4,108,525 | 0 | 100 |
| 1999 | 59 | 59 | 100 | 12,131,407 | 12,131,407 | 0 | 100 |
| 2000 | 29 | 29 | 100 | 4,808,878 | 4,808,878 | 0 | 100 |
| 2001 | 41 | 41 | 100 | 7,523,213 | 7,523,213 | 0 | 100 |
| 2002 | 61 | 61 | 100 | 7,910,174 | 7,910,174 | 0 | 100 |
| 2003 | 32 | 32 | 100 | 6,810,120 | 6,810,120 | 0 | 100 |
| 2004 | 30 | 30 | 100 | 15,005,412 | 15,005,412 | 0 | 100 |
| 2005 | 28 | 28 | 100 | 18,183,034 | 18,183,034 | 0 | 100 |
| 2006 | 25 | 25 | 100 | 7,128,808 | 7,128,808 | 0 | 100 |
| 2007 | 13 | 13 | 100 | 3,138,440 | 3,138,440 | 0 | 100 |
| 2008 | 33 | 33 | 100 | 7,531,037 | 7,531,037 | -1 | 100 |
| 2009 | 21 | 21 | 100 | 2,347,228 | 2,347,228 | 0 | 100 |
| 2010 | 20 | 20 | 100 | 3,278,389 | 3,278,389 | -1 | 100 |
| 2011 | 20 | 20 | 100 | 6,821,798 | 6,821,798 | 0 | 100 |
| 2012 | 11 | 11 | 100 | 6,594,959 | 6,594,959 | 0 | 100 |
| 2013 | 7 | 7 | 100 | 2,276,412 | 2,276,412 | 0 | 100 |
| 2014 | 14 | 14 | 100 | 1,365,834 | 1,365,834 | 0 | 100 |
| 2015 | 26 | 25 | 96 | 4,881,449 | 4,742,669 | 138,780 | 97 |
| 2016 | 16 | 13 | 81 | 5,129,894 | 3,793,623 | 1,336,271 | 74 |
| 2017 | 9 | 5 | 56 | 2,605,614 | 2,276,064 | 329,550 | 87 |
| 2018 | 16 | 12 | 75 | 7,050,550 | 6,631,897 | 418,653 | 94 |
| 2019 | 5 | 3 | 60 | 1,829,814 | 1,166,105 | 663,709 | 64 |
| 2020 | 12 | 6 | 50 | 3,986,712 | 2,726,477 | 1,260,235 | 68 |
| 2021 | 19 | 4 | 21 | 4,678,887 | 1,639,925 | 3,038,962 | 35 |
| 2022 | 4 | 0 | 0 | 3,257,043 | 404,197 | 2,852,846 | 12 |
| 2023 | 23 | 1 | 4 | 2,201,953 | 30,000 | 2,171,953 | 1 |
| Total | 746 | 685 | 92 | 172,268,576 | 160,057,619 | 12,210,957 | 93 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR BILATERAL AGENCIES

| Country/Project code | Agency | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Kenya KEN/PHA/80/INV/62 | France | HCFC phase-out management plan (stage II, first tranche) | 87 | 12 months delays | To request the Government of France to report to the 96th meeting on this project with implementation delays |
| Kenya KEN/PHA/86/INV/65 | France | HCFC phase-out management plan (stage II, second tranche) | 0 | 12 and 18 months delays | To request the Government of France to report to the 96th meeting on this project with implementation delays |
| Zimbabwe ZIM/REF/82/INV/56 | France | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) | 100 | 12 months delays | Noting decision 77/8(j), to request the Government of France to report to the 96th meeting on this project with implementation delays |
| China CPR/PHA/77/INV/574 | Italy | HCFC phase-out management plan (stage II, first tranche) (room air-conditioner manufacturing sector plan) | 1 | 12 months delays | To request the Government of Italy to report to the 96th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/77/INV/224 | Italy | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 20 | 12 months delays | To request the Government of Italy to report to the 96th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/INV/237 | Italy | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 6 | 12 months delays | To request the Government of Italy to report to the 96th meeting on this project with implementation delays |
| Nigeria NIR/PHA/81/INV/151 | Italy | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 100 | 12 months delays | Noting decision 77/8(j), to request the Government of Italy to report to the 96th meeting on this project with implementation delays |
| Nigeria NIR/PHA/81/TAS/149 | Italy | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 100 | 12 months delays | Noting decision 77/8(j), to request the Government of Italy to report to the 96th meeting on this project with implementation delays |
| Brazil BRA/PHA/82/TAS/321 | Germany | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 82 | 12 months delays | To request the Government of Germany to report to the 96th meeting on this project with implementation delays |
| Egypt EGY/PHA/84/INV/142 | Germany | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 34 | 12 months delays | To request the Government of Germany to report to the 96th meeting on this project with implementation delays |
| India IND/PHA/86/INV/481 | Germany | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector plan) | 94 | 12 months delays | To request the Government of Germany to report to the 96th meeting on this project with implementation delays |
| India IND/PHA/87/INV/488 | Germany | HCFC phase-out management plan (stage II, third tranche) | 100 | 12 months delays | Noting decision 77/8(j), to request the Government of Germany to report to the 96th meeting on this project with implementation delays |
| Mauritius MAR/PHA/79/INV/27 | Germany | HCFC phase-out management plan (third tranche) | 79 | 12 months delays | To request the Government of Germany to report to the 96th meeting on this project with implementation delays |
| Mauritius MAR/PHA/86/INV/30 | Germany | HCFC phase-out management plan (stage I, fourth tranche) | 0 | 12 and 18 months delays | To request the Government of Germany to report to the 96th meeting on this project with implementation delays |
| Mauritius MAR/PHA/88/TAS/33 | Germany | Verification report on the implementation of stage I of the HCFC phase-out management plan | 0 | 12 and 18 months delays | To request the Government of Germany to report to the 96th meeting on this project with implementation delays |
| Mexico MEX/PHA/77/INV/179 | Germany | HCFC phase-out management plan (stage II, second tranche) (HC demonstration and training) | 58 | 12 months delays | To request the Government of Germany to report to the 96th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/95/1

# Progress reports are the only means for indicating the final closure of all funding accounts associated with projects approved by the Executive Committee for bilateral cooperation.

# Austria, Belgium, the Czech Republic, Denmark, Finland, Hungary, Israel, Poland, Portugal, the Russian Federation, Singapore, the Slovak Republic, South Africa, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland, and the United States of America.

UNEP/OzL.Pro/ExCom/95/14

The data has been included in the Consolidated Progress Report database, which is provided on the 95th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 95th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2023. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

No phase-out for HFC-related projects in 2023.

No approved phase-out for HFC-related projects in 2023.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/95/47

UNEP/OzL.Pro/ExCom/95/58

UNEP/OzL.Pro/ExCom/95/71 (the Cook Islands, Kiribati, the Marshall Islands, Micronesia (Federated States of), Nauru, Niue, Palau, Samoa, Solomon Islands, Tonga, Tuvalu, and Vanuatu)

UNEP/OzL.Pro/ExCom/95/20 or UNEP/OzL.Pro/ExCom/95/21

UNEP/OzL.Pro/ExCom/95/24

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.