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PROGRAMA DE TRABAJO DEL PNUD PARA EL AÑO 2023



OBSERVACIONES Y RECOMENDACIÓN DE LA SECRETARÍA DEL FONDO 
1. El PNUD solicita al Comité Ejecutivo la aprobación de la cantidad de 2 847 144 $EUA, más gastos de apoyo al organismo de 199 900 $EUA, para su programa de trabajo de 2023 que se expone en el Cuadro 1. La presentación se adjunta al presente documento. 
Cuadro 1: Programa de trabajo del PNUD para 2023
	País
	Actividad/proyecto
	Cantidad solicitada ($EUA)
	Cantidad recomendada ($EUA)

	SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL

	A1: Renovación de proyectos de fortalecimiento institucional

	Argentina
	Renovación del proyecto de fortalecimiento institucional (fase XI) 
	825 528
	825 528

	Chile
	Renovación del proyecto de fortalecimiento institucional (fase XV) 
	494 283
	494 283

	Georgia
	Renovación del proyecto de fortalecimiento institucional (fase XII) 
	180 000
	180 000

	Líbano
	Renovación del proyecto de fortalecimiento institucional (fase XIII) 
	410 926
	410 926

	Venezuela República Bolivariana de)
	Renovación del proyecto de fortalecimiento institucional (fase XV) 
	756 407
	756 407

	Subtotal para A1
	2 667 144
	2 667 144

	Gastos de apoyo del organismo
	186 700
	186 700

	Total para A1
	2 853 844
	2 853 844

	A2: Preparación de proyectos para los planes de gestión de eliminación de HCFC (PGEH)

	Líbano
	Preparación de un PGEH (fase III)
	60 000
	60 000

	Subtotal para A2
	60 000
	60 000

	Gastos de apoyo del organismo
	4 200
	4 200

	Total para A2
	64 200
	64 200

	
	
	

	A3: Preparación de proyectos para los planes de aplicación de la Enmienda de Kigali relativos a los HFC (KIP)

	India
	Preparación de un proyecto de inversión de KIP en el sector de fabricación de refrigeración para Mech Air Industries
	30 000
	30 000

	India
	Preparación de un proyecto de inversión de KIP en el sector de fabricación de refrigeración para Rockwell Industries
	30 000
	30 000

	India
	Preparación de un proyecto de inversión de KIP  en el sector de fabricación de aire acondicionado para Voltas Limited
	30 000
	30 000

	Subtotal for A3
	90 000
	90 000

	Gastos de apoyo del organismo
	6 300
	6 300

	Total para A3
	96 300
	96 300

	SECCIÓN B: ACTIVIDADES RECOMENDADAS PARA CONSIDERACIÓN INDIVIDUAL

	B1: Asistencia técnica para la elaboración de un informe de verificación del consumo de HCFC

	Fiji
	Informe de verificación de la etapa II del plan de gestión para la eliminación de los HCFC (PGEH)
	30 000
	*

	Subtotal para B1
	30 000
	*

	Gastos de apoyo del organismo
	2 700
	*

	 Total para B1
	32 700
	*

	Total para A1, A2, A3, B1
	2 847 144
	2 817 144

	Gastos de apoyo del organismo para A1, A2, A3, B1
	199 900
	197 200

	Total general
	3 047 044
	3 014 344


* Recomendado para consideración individual
[bookmark: _Hlk133330929]SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL
A1: Renovación de proyectos de fortalecimiento institucional
Descripción del proyecto 
1. El PNUD presentó sendas solicitudes para la renovación de proyectos de fortalecimiento institucional en los países que se indican en la sección A1 del Cuadro 1. Los proyectos se describen en el Anexo I al presente documento.
Observaciones de la Secretaría
1. La Secretaría analizó las solicitudes de renovación de cinco proyectos de fortalecimiento institucional en nombre de los respectivos Gobiernos a la luz de las pautas[footnoteRef:2] decisiones relevantes sobre criterios de admisibilidad y niveles de financiación. Las solicitudes se confrontaron con los planes de trabajo de fortalecimiento institucional originales de la etapa anterior, los datos del programa de país y del Artículo 7, el último informe de ejecución de los planes de gestión de eliminación de HCFC (PGEH), el informe sobre la marcha de las actividades presentado por el organismo interviniente y las correspondientes decisiones de las Reuniones de las Partes. Se tomó nota de que cinco países han presentado sus datos de programa de país para 2022 y que han dado cumplimiento a las metas de eliminación previstas en el Protocolo de Montreal y que cuatro han comunicado que su consumo anual de HCFC no excede el máximo anual permitido indicado en sus Acuerdos con el Comité Ejecutivo en el marco de los PGEH.[footnoteRef:3] Además, todas las solicitudes contenían una evaluación relativa a los indicadores de desempeño y la consecución de los objetivos previstos en el marco de los proyectos de fortalecimiento institucional de conformidad con la decisión 91/63 b).  [2:  Decisión 91/63: b) Aprobar el formato revisado para los informes finales y las solicitudes de prórroga del financiamiento de fortalecimiento institucional, y de los indicadores de desempeño correspondientes; y c) Solicitar al los países del Artículo 5, por intermedio de los organismos bilaterales y de ejecución, utilizar el formato revisado a que se refiere el subpárrafo b) anterior para toda solicitud de renovación de proyectos de fortalecimiento institucional a partir de la primera reunión del Comité Ejecutivo en 2023; ]  [3:  El consumo anual de HCFC de Argentina se examina en el documento UNEP/OzL.Pro/ExCom/92/21 que contiene la solicitud del tercer tramo de la etapa II del plan de gestión de eliminación de HCFC para Argentina.] 

Recomendación de la Secretaría
1. La Secretaría recomienda la aprobación general de las solicitudes de renovación de proyectos de fortalecimiento institucional para Argentina, Chile, Georgia, Líbano la República Bolivariana con el nivel de financiación indicado en la sección A1 del Cuadro 1 de este documento. De estimarlo necesario, el Comité Ejecutivo podrá remitir a los respectivos Gobiernos las observaciones formuladas en el Anexo II al presente documento.
A2: Preparación de proyectos para los planes de gestión de eliminación de HCFC (PGEH)
Descripción del proyecto
1. El PNUD presenta una solicitud para la preparación de la etapa III del PGEH para el Líbano en calidad de organismo de ejecución designado. Esta solicitud se muestra en la Sección 2 del Cuadro 1.
1. La presentación incluía: la justificación de la financiación solicitada para la preparación del proyecto; un informe de la marcha de las actividades sobre la ejecución de la fase II del plan de gestión de eliminación de HCFC; y la lista de actividades que se realizarán durante la preparación del proyecto y los presupuestos correspondientes. 
Observaciones de la Secretaría
1. [bookmark: _Hlk117154602]Al examinar esta solicitud, la Secretaría tuvo en cuenta las directrices para para la financiación de la preparación de la etapa II de los planes de gestión de eliminación de HCFC para los países que operan al amparo del artículo 5 que figuran en la decisión 71/42, los progresos realizados en la etapa II del plan de gestión de eliminación de HCFC, incluido el estado de ejecución de los tramos hasta la preparación del presente documento, y la decisión 84/46 e).[footnoteRef:4] La Secretaría señaló que la financiación solicitada se ajusta a la decisión 71/42 y que la solicitud se ajusta a la decisión 82/45, que permite la presentación de solicitudes de preparación de proyectos para la fase III dos años antes de la fecha de finalización de la fase II del plan de gestión de eliminación de HCFC. [4:  La inclusión de la fase III de los planes de gestión de eliminación de HCFC en el plan administrativo sólo se permite para aquellos países con una fase II aprobada de los planes de gestión de eliminación de HCFC con objetivos de reducción por debajo de los objetivos de cumplimiento para 2025.] 

1. El PNUD confirmó que la fase III del plan de gestión de eliminación de HCFC para el Líbano eliminará el 100% de los HCFC respecto del nivel básico de referencia para el 1 de enero de 2030.
Recomendaciones de la Secretaría
1. La Secretaría recomienda la aprobación general para la preparación del proyecto para la etapa III del plan de gestión de eliminación de HCFC para el Líbano al nivel de financiación indicado en la Sección A2 del Cuadro 1.

A3: A3: Preparación de proyectos para los planes de aplicación de la Enmienda de Kigali relativos a los HFC (KIP)
Descripción del proyecto
1. El PNUD presentó tres solicitudes para la preparación de la etapa I de los proyectos de inversión en el marco de los KIP, dos en el sector de fabricación de refrigeración y uno en el sector de fabricación de aire acondicionado para la India, en calidad de organismo de ejecución designado, como se indica en la Sección A3 del Cuadro. La India no ha recibido financiación para la preparación de una estrategia general para la etapa I de los KIP.
Observaciones de la Secretaría
1. Al examinar estas solicitudes, la Secretaría tuvo en cuenta las directrices para la preparación de KIP que figuran en la decisión 87/50; las actividades propuestas para la preparación de proyectos y cómo se vinculan con las actividades de apoyo y otros proyectos relativos a los HFC en el país. El PNUD proporcionó descripciones de las actividades de apoyo necesarias para la preparación de los proyectos de inversión para los KIP, utilizando el formato para solicitudes de preparación de proyectos para los KIP.
1. La Secretaría observó que:
11. La preparación del proyecto para los proyectos de inversión de los KIP en el sector de fabricación de refrigeración incluiría la conversión en dos empresas: la sustitución de R-404A y R-407C por CO2 en Mech Air Industries y la sustitución de HFC-134a por R 290 en Rockwell Industries. La preparación del proyecto para el proyecto de inversión de los KIP en el sector de fabricación de aire acondicionado incluiría la conversión en una empresa para sustituir el HFC 134a y el R-407C por R-1234ze/R1234yf en enfriadores en Voltas Limited. Las actividades de preparación del proyecto para los tres proyectos incluirían la recopilación de datos a nivel de empresa; evaluaciones de refrigerantes alternativos y de la cadena de suministro; visitas sobre el terreno para la verificación del consumo y la evaluación del equipo de referencia; diseño del proyecto, validación y revisión por pares; consulta nacional y desarrollo de la propuesta final para su presentación al Comité Ejecutivo
11. Los datos de consumo de HFC para el país y para las tres empresas no se incluyeron en la presentación. El PNUD señaló que la India es un país del grupo 2[footnoteRef:5] y que actualmente los datos de consumo de HFC para la India sólo están disponibles para 2021 y que se está trabajando para recopilar datos sectoriales de consumo de HFC en el país, que podrían presentarse una vez finalizados. En cuanto a los datos de consumo de las empresas individuales, el PNUD señaló que los datos sobre el consumo de HFC se recopilarían como parte de la preparación del proyecto propuesto.  [5:  Decisión XXVIII/2, párrafo 2] 

1. La Secretaría solicitó información sobre qué productos de estas empresas se incluirán en la conversión a alternativas de bajo PCA como parte de las solicitudes de preparación de proyectos. El PNUD aclaró que los productos pueden incluir: almacenes frigoríficos, congeladores y cámaras de maduración para Mech Air Industries; congeladores, enfriadores y refrigeradores para Rockwell Industries con dos instalaciones de fabricación; y enfriadores para Voltas Limited. 
1. La Secretaría señaló además que la India ha ratificado la Enmienda de Kigali;[footnoteRef:6] que el país ha presentado una carta de apoyo en la que manifiesta su intención de tomar medidas para la eliminación de los HFC; que la financiación solicitada se ajusta a la decisión 87/50 f) v) sobre la preparación de proyectos de inversión/planes sectoriales para la fase I de los KIP; y que el PNUD ha confirmado la presentación de la estrategia general de los KIP, que se espera tras la finalización de las evaluaciones iniciales que se están llevando a cabo actualmente en el marco de las actividades de apoyo. La Secretaría también señaló que la solicitud está en consonancia con la decisión 79/46 b) iii),[footnoteRef:7] y como país del grupo 2, las obligaciones iniciales de reducción de la India serán la congelación del consumo de HFC para 2028. [6:  27 de septiembre de 2021]  [7:  La financiación de la preparación de los planes nacionales de ejecución para cumplir las obligaciones iniciales de reducción de los HFC se podría proporcionar, como mínimo, cinco años antes de la fecha de cumplimiento de esas obligaciones, después de que un país haya ratificado la Enmienda de Kigali y sobre la base de las directrices que se hayan de aprobar en el futuro.] 

Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de la preparación de los planes de inversión del plan de aplicación de le Enmienda de Kigali relativos a los HFC en los sectores de fabricación de refrigeración y de fabricación de aire acondicionado en la India, con el nivel de financiación que figura en la Sección A3 del Cuadro 1.
SECCIÓN B: ACTIVIDADES RECOMENDADAS PARA CONSIDERACIÓN INDIVIDUAL
B1: Asistencia técnica para la elaboración de un informe de verificación del consumo de HCFC
Descripción del proyecto
1. De conformidad con la decisión 61/46 c),[footnoteRef:8] la Secretaría extrajo una muestra de 16 países que operan al amparo del Artículo 5 y que tienen un bajo volumen de consumo con el fin de verificar el cumplimiento de sus Acuerdos en el marco del PGEH. Los países seleccionados se enumeran en el Cuadro 5 del documento UNEP/OzL.Pro/ExCom/92/13 sobre la reseña de las cuestiones identificadas durante el examen de los proyectos. El PNUD, en su calidad de organismo de ejecución principal, solicita financiación para la verificación del consumo de HCFC en la etapa II del plan de gestión de eliminación de HCFC para Fiji. [8:  Se solicitó a la Secretaría que proporcionara, en la primera reunión de cada año, una lista que representara el 20% de los países con un nivel básico de consumo de HCFC de hasta 360 toneladas métricas (tm), y con un plan de gestión de la eliminación de HCFC aprobado, para aprobar su financiación a efectos de verificación del cumplimiento del acuerdo del plan de gestión de la eliminación de HCFC por parte de ese país para ese año.] 

Observaciones de la Secretaría
En consonancia con la propuesta de la Secretaría de simplificar el proceso de aprobación de financiación para la verificación del consumo de HCFC para los países de bajo consumo, tal como se describe en el documento UNEP/OzL.Pro/ExCom/92/13, la solicitud de financiación para Fiji se incluye en el presente documento.
1. La Secretaría señaló que la financiación solicitada era coherente con los fondos aprobados para verificaciones similares en reuniones anteriores y que el informe de verificación debía presentarse al menos 10 semanas antes de la reunión correspondiente del Comité Ejecutivo en la que se solicitara el siguiente tramo de financiación para el plan de gestión de eliminación de HCFC.
1. La Secretaría señaló además que la solicitud depende de la aprobación de la lista de países seleccionados para la verificación del cumplimiento que figura en el documento UNEP/OzL.Pro/ExCom/92/13.

Recomendación de la Secretaría
1. El Comité Ejecutivo podría considerar, en consonancia con el examen sobre la verificación del cumplimiento de los Acuerdos relativos a los planes de gestión de eliminación de HCFC por parte de determinados países de bajo volumen de consumo, en el punto 9 a) del orden del día, Reseña de las cuestiones identificadas durante el examen de proyectos, aprobar la preparación del informe de verificación para la etapa II del plan de gestión de eliminación de HCFC para Fiji por un monto de 30 000 $EUA, más 2 700 $EUA en concepto de gastos de apoyo al organismo, en el entendimiento de que el informe de verificación deberá presentarse al menos 10 semanas antes de la reunión correspondiente del Comité Ejecutivo en la que se solicite el siguiente tramo de financiación para el plan de gestión de eliminación de HCFC. 
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Anexo I

INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS

Argentina: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-94
	359,500

	Phase II:
	Nov-99
	239,700

	Phase III:
	Nov-02
	311,610

	Phase IV:
	Jul-05
	311,567

	Phase V:
	Nov-07
	311,567

	Phase VI:
	Nov-09
	311,568

	Phase VII:
	Nov-11
	311,567

	Phase VIII:
	Dec-13
	311,567

	Phase IX
	May-16
	398,806

	Phase X:
	Dec-18
	398,806

		Total:
	3,266,258

	Amount requested for renewal (phase XI) (US $):
	825,528

	Amount recommended for approval for phase XI (US $): 
	825,528

	Agency support costs (US $):
	57,787

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	883,315

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)  Annex B, Group III (methyl chloroform) (average 1998-2000)
	65.7

	(b)  Annex C, Group I (HCFCs) (average 2009-2010)
	400.7

	(c)  Annex E, (methyl bromide) (average 1995-1998)
	411.3

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)  Annex B, Group III (methyl chloroform)
	0.00

	(b)  Annex C, Group I (HCFCs)
	
164.23

	(c)  Annex E, (methyl bromide)
	6.70

		Total:
	138.46

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at December 2022) (US $):
	98,511,452

	Amount disbursed (as at December 2021) (US $):
	77,586,844

	ODS to be phased out (as at December 2022) (ODP tonnes):
	5,713.99

	ODS phased out (as at December 2021) (ODP tonnes):
	5,567.28



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	87,363,997

	(b)
	Institutional strengthening:
	3,266,258

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	7,881,197

		Total:
	98,511,452

	(d)
	HFC activities funded from additional voluntary contributions
	2,090,755



Progress report
During phase X, the Government of Argentina maintained the reductions in HCFC consumption and implemented enabling activities which resulted in the ratification of the Kigali Amendment in November 2019. Preparatory activities for the implementation of the Kigali Amendment included the modification of the import/export licensing system to include HFCs, preparation of a draft resolution for HFC import quotas, and a survey of legislation and standards for the safe use and handling of flammable refrigerants. Existing ODS regulations were strengthened through HCFC quotas for the years 2020 to 2023. Critical use nominations for methyl bromide were requested for 2020 to 2022 but no nominations are to be requested for future years. The Government of Argentina continued implementing stage II of the HCFC phase-out management plan (HPMP) including training of RAC technicians on flammable alternative refrigerants and initiated the technicians’ certification scheme for the safe handling of flammable refrigerants. Public awareness activities included a brochure on the Kigali Amendment and celebration of International Ozone Day. Of the seven IS objectives, five were achieved and two were partially achieved because of the delay in the submission of the fourth tranche of stage II of the HPMP due to the COVID-19 pandemic and the lack of availability and high cost of low-GWP alternatives, and as gender policy had not been included in the work plan (objective 7).
Plan of action
Under phase XI, the Government of Argentina will continue efforts to maintain the reductions in HCFC consumption through import controls and the finalization of stage II and implementation of stage III of the HPMP to comply with the HCFC control measure in 2025. In addition, the Government of Argentina will finalize the legislation for HFC quotas to be assigned from 2024 in order to comply with the first HFC control measure as at 1 January 2024, and prepare the Kigali HFC implementation plan (KIP) and other projects. The NOU will continue to coordinate activities with stakeholders, collect and submit country programme (CP) and Article 7 data, participate in regional network and Montreal Protocol meetings, and continue public awareness activities, including celebration of International Ozone Day. Gender mainstreaming will also be integrated into implementation of the next phase of the IS project.
Sustainability and risk assessment:
4.	The NOU reported that the achievement of IS objectives had been supported by timely signature of agreements and disbursement of funds. As a result of the implementation of the import and export licensing system for controlled substances, the close collaboration of the NOU with Customs, and consultations with stakeholders/manufacturers, the risk of non-compliance with the Montreal Protocol is minimal and the sustainability of ODS phase-out is ensured. Stable support from the Multilateral Fund ensures the NOU can continue its activities.
Chile: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jun-92
	213,000

	Phase II:
	Oct-96
	113,500

	Phase III:
	Jul-98
	143,500

	Phase IV:
	Dec-00
	143,500

	Phase V:
	Nov-02
	186,550

	Phase VI:
	Apr-05 and Nov-05
	186,550

	Phase VII:
	Mar-07
	186,550

	Phase VIII:
	Apr-09
	186,550

	Phase IX:
	Apr-11
	186,550

	Phase X:
	Apr-13
	186,550

	Phase XI:
	May-15
	186,550

	Phase XII:
	Jul-17
	238,784

	Phase XIII:
	May19
	238,784

	Phase XIV:
	Jul-21
	238,784

	Total:
	2,635,702

	Amount requested for renewal (phase XV) (US $):
	494,283

	Amount recommended for approval for phase XV (US $): 
	494,283

	Agency support costs (US $):
	34,600

	Total cost of institutional strengthening phase XV to the Multilateral Fund (US $):
	528,883

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	6.4

	Annex C, Group I (HCFCs) (average 2009-2010)
	87.5

	Annex E, (methyl bromide) (average 1995-1998)
	212.5

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	14.79

	Annex E, (methyl bromide)
	0.00

	Total:
	14.79

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at December 2022) (US $):
	22,253,952

	Amount disbursed (as at December 2021) (US $):
	17,154,973

	ODS to be phased out (as at December 2022) (ODP tonnes):
	1,338.3

	ODS phased out (as at December 2021) (ODP tonnes):
	1,046.7



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	12,832,861

	(b)
	Institutional strengthening:
	2,635,702

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	6,785,389

		Total:
	22,253,952

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase XIV of the IS project, the NOU of Chile was formally integrated into the Climate Change Division of the Ministry of Environment and worked in close coordination with the Climate Change Office of the Ministry. The NOU continued to successfully coordinate the implementation of the Montreal Protocol despite the challenges of the COVID-19 pandemic. Under the final tranche of stage II and first tranche of stage III the HPMP, the NOU worked in close collaboration with local authorities and stakeholders to train RAC technicians on low-GWP alternatives and good refrigeration practices. HCFC import and export controls, including those for formulated polyols, were enforced. Chile continued to prepare for implementation of the Kigali Amendment including the preparation of draft regulations for the establishment of HFC import control measures, project preparation for the KIP, and coordinated with the National Customs Service to implement the HFC licensing system and develop and HFC quota system. The NOU participated in regional network and Montreal Protocol meetings, carried out public awareness activities including through social media, and made progress on gender mainstreaming in projects and activities. Chile achieved all seven IS objectives.
Plan of action
During phase XV of the IS project, the Government of Chile will maintain the ban on CFCs and halons, and the reductions made in the consumption of HCFCs and establish the HFC import quota system. In addition, the NOU will work with public and private stakeholders to enforce control measures on the consumption of HCFCs and HFCs, implement investment projects, provide training on good refrigeration practices, and continue public awareness activities. In addition, the Government of Chile will implement stage III of the HPMP in collaboration with all stakeholders to meet the agreed targets for reductions in HCFC consumption. The Government of Chile will take steps towards the implementation of the Kigali Amendment including submission of the KIP for Chile and participate in regional network and Montreal Protocol meetings. Gender mainstreaming will be integrated into implementation of the next phase of the IS project including hiring a consultant to support the incorporation of the gender perspective in the work of the NOU and HPMP activities.
Sustainability and risk assessment 
The NOU reported that the achievement of IS objectives had been maintained by high-level government support, efficient and timely support from UNDP, and timely signature of agreements and disbursement of funds. No risks were identified for the implementation of the IS project as the Government of Chile has a solid legal and institutional framework and effective communication with the private sector vis-à-vis the commitments to reduce the consumption of controlled substances. The NOU is an integral part of the Ministry of Environment and has staff with technical knowledge which minimizes the risks associated with the introduction of new technologies.
Georgia: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-97
	70,000

	Phase II:
	Dec-00
	46,700

	Phase III:
	Apr-03
	60,667

	Phase IV:
	Apr-05
	60,667

	Phase V:
	Jul-07 
	60,667

	Phase VI:
	Apr-09
	60,667

	Phase VII:
	Apr-11
	60,667

	Phase VIII:
	Apr-13
	60,667

	Phase IX:
	May-15
	60,667

	Phase X:
	Jun-18
	85,000

	Phase XI:
	Jun-20
	85,000

		Total:
	772,036*

	Amount requested for renewal (phase XII) (US $):
	180,000

	Amount recommended for approval for phase XII (US $): 
	180,000

	Agency support costs (US $):
	12,600

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	192,600

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	5.3

	(c)	Annex E (methyl bromide) (average 1995-1998)
	13.7

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.92

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.92

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at December 2022) (US $):
	3,272,469


	Amount disbursed (as at December 2021) (US $):
	2,833,042


	ODS to be phased out (as at December 2022) (ODP tonnes):
	90.2

	ODS phased out (as at December 2021) (ODP tonnes):
	90.3


*Including funding approved for phase V at the 51st meeting

Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,242,239

	(b)
	Institutional strengthening:
	772,036

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,258,194


		Total:
	3,272,469

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase XI of the IS project, Georgia, through the national ozone unit (NOU) of the Ministry of Environmental Protection and Agriculture, successfully carried out the following activities: facilitated the adoption of legal changes including the licensing system for exempt uses of ODS and the mandatory certification of RAC technicians in line with relevant EU regulations; continued to enforce ODS control measures and monitor illegal ODS trade through training customs officers and environmental inspectors; monitored and reported ODS consumption data to the Fund and Ozone Secretariats; completed stage I of the HPMP stage I and  started implementation of stage II activities including training RAC technicians in low-GWP alternative alternatives, and building the capacity of vocational schools to incorporate ODS management issues into their curricula; cooperated with private sector representatives on low-GWP alternative demonstration projects; trained public agencies in green procurement of RAC equipment; conducted consultations with stakeholders with regard to the ratification of the Kigali Amendment; public awareness; and actively participated in regional network and Montreal Protocol meetings. Georgia achieved six of the seven IS objectives as efforts to ratify the Kigali Amendment are ongoing. 
Plan of action
Under phase XII of the IS project the Government of Georgia will update existing legislation on ODS import quotas to include all substances controlled under the Montreal Protocol including the Kigali Amendment which the country expects to ratify in 2023. The NOU will: continue to consult with key stakeholders on the regulatory implications of the ratification of the Kigali Amendment; coordinate the implementation of activities under stage II of the HPMP; improve the Electronic Refrigerant Management System (ERMS) to include refrigerants recovery, recycling, and reclamation operations; ensure timely and accurate reporting on the consumption of controlled substances; organize consultations with private sector representatives on the regulations on mandatory leak checks and ERMS; raise awareness of relevant issues, as well as celebrating International Ozone Day; further strengthen the NOU’s capacity. Gender mainstreaming will also be integrated into implementation of the next phase of the IS project including consultation with and training of stakeholders. 
Sustainability and risk assessment 
The NOU of Georgia reported that achievement of IS objectives had been underpinned by high‑level government support, efficient and timely support from UNDP, and timely signature of agreements and disbursement of funds. Risks include the low interest of stakeholders in project activities, insufficient capacity building, technical assistance and awareness raising, and also political support for IS activities. To mitigate these risks, UNDP would provide support from the management level of the UNDP country office through consultations with the NOU, the legal department of the Ministry of Environment on the legislation required to regulate all controlled substances, and further promote consultations with all relevant stakeholders to raise awareness and promote their active participation in activities. 
Lebanon: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	May-96
	179,000

	Phase II:
	Jul-00
	119,300

	Phase III:
	Jul-02
	155,090

	Phase IV:
	Dec-04
	155,090

	Phase V:
	Nov-06
	155,090

	Phase VI:
	Nov-08
	155,090

	Phase VII:
	Dec-10
	155,090

	Phase VIII:
	Dec-12
	155,090

	Phase IX:
	Nov-14
	155,090

	Phase X:
	Dec-16
	198,515

	Phase XI:
	Dec-18
	198,515

	Phase XII:
	Dec-20
	198,515

		Total:
	1,979,475

	Amount requested for renewal (phase XIII) (US $):
	410,926

	Amount recommended for approval for phase XIII (US $): 
	410,926

	Agency support costs (US $):
	28,765

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	439,691

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	73.5

	(c)	Annex E (methyl bromide) (average 1995-1998)
	236.4

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	26.09

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	26.09

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at December 2022) (US $):
	22,698,546

	Amount disbursed (as at December 2021) (US $):
	21,637,945.66


	ODS to be phased out (as at December 2022) (ODP tonnes):
	1,850.6

	ODS phased out (as at December 2021) (ODP tonnes):
	1,798.6



19. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	17,540,926

	(b)
	Institutional strengthening:
	1,979,475

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	3,178,145

		Total:
	22,698,546

	(d)
	HFC activities funded from additional voluntary contributions
	1,233,858


Progress report
During phase XII of the IS project, the NOU of Lebanon maintained compliance with the Montreal Protocol. The NOU has continued collaboration with government and non‑governmental authorities, the industrial, private and public sectors to ensure the phase-out of HCFCs and initiate activities in preparation for the HFC phase-down. The NOU worked closely with the Ministry of Environment providing policy and legislative advice which resulted in the Ministerial decision for the regulations to control HCFCs and HFCs. Activities coordinated by the NOU included: the implementation of stage II of the HPMP to convert the foam and RAC industrial sectors to non-HCFC technologies; enforcement of the regulations for controlled substances including the licensing system to monitor imports of ODS and HFCs; project preparation activities for the Kigali HFC implementation plan and an investment project to adopt low-GWP in the RAC manufacturing sector. The NOU also submitted CP and Article 7 data reports to the Fund and Ozone Secretariats, respectively; actively participated in regional network and Montreal Protocol meetings; and raised public awareness on the Montreal Protocol through seminars and celebration of International Ozone Day. The NOU encouraged all partners and stakeholders to promote the participation of females in Montreal Protocol activities including the RAC sector and a checklist for gender mainstreaming in project planning was prepared. Lebanon achieved all seven IS objectives. 
Plan of action
Under phase XIII the Government of Lebanon will continue the phase-out of HCFCs and phase‑down of HFCs through the following activities: strengthening regulations and enforcing the licensing decree to achieve further reductions of HCFC consumption and the control of HFC imports through quotas; continued monitoring of the enforcement of the regulations and legislation for controlled substances in coordination with relevant national stakeholders; continued monitoring and supervision of the implementation of stage II of the HPMP; awareness raising and capacity building in relation to the Kigali Amendment; outreach activities focussing on the refrigeration servicing sector; and, activities to promote networking and stakeholder engagement. The NOU will finalize preparation of stage I of the KIP for Lebanon for submission to the Executive Committee in 2023 or 2024; attend Montreal Protocol meetings to participate in discussions on the cost guidelines for HFC phase-down, energy efficiency and so on. Gender mainstreaming will be integrated into implementation of the next phase of the IS project including training activities in the RAC sector.
Sustainability and risk assessment
The NOU reported that efforts to meet IS objectives had been facilitated by high-level government support, efficient and timely support from UNDP, and timely signature of agreements and disbursement of funds. The NOU also stressed the importance of collaboration with stakeholders. Potential risks were the political and economic instability in the country. To mitigate the risks the NOU plans to monitor the situation and continue consultations with the relevant Government and private sector partners, as well as continuing to monitor the enforcement of regulations and legislation. 
Venezuela (Bolivarian Republic of): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-93
	329,192

	Phase II:
	Jul-95 & May‑96
	109,800

	Phase III:
	Oct-96
	219,600

	Phase IV:
	Jul-98
	219,600

	Phase V:
	Jul-00
	219,600

	Phase VI:
	Jul-02
	285,480

	Phase VII:
	Jul-04
	285,480

	Phase VIII:
	Jul-06
	285,480

	Phase IX:
	Nov-08
	285,480

	Phase X:
	Dec-10
	285,480

	Phase XI:
	Dec-12
	285,480

	Phase XII:
	Nov-14
	285,480

	Phase XIII:
	Dec-16
	365,414

	Phase XIV:
	Dec-18
	365,414

		Total:
	3,826,980

	Amount requested for renewal (phase XV) (US $):
	756,407

	Amount recommended for approval for phase XV (US $): 
	756,407

	Agency support costs (US $):
	52,948

	Total cost of institutional strengthening phase XV to the Multilateral Fund (US $):
	809,355

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	4.7

	Annex C, Group I (HCFCs) (average 2009-2010)
	207.0

	Annex E, (methyl bromide) (average 1995-1998)
	10.3

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0

	Annex C, Group I (HCFCs)
	0

	Annex E, (methyl bromide)
	0

		Total:
	0

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at December 2022) (US $):
	53,897,655

	Amount disbursed (as at December 2021) (US $):
	49,510,708

	ODS to be phased out (as at December 2022) (ODP tonnes):
	2,474.97

	ODS phased out (as at December 2021) (ODP tonnes):
	2,416.50



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	43,518,166

	(b)
	Institutional strengthening:
	3,826,980

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	6,552,509

		Total:
	53,897,655

	(d)
	HFC activities funded from additional voluntary contributions
	250,000



Progress report
During phase XIV of the IS project, the Bolivarian Republic of Venezuela faced severe economic difficulties that on one hand delayed the implementation of activities, and on the other led to a reduction of HCFC imports and the cessation of local HCFC-22 production in 2020. The country continued the application of the quota system for the import of HCFC‑141b and enforced the ban on the import of HCFC‑22 and HCFC-based equipment. Furthermore, legislation was enacted in April 2023 which will ban the production of HCFC-22, the manufacturing and new installations of all RAC equipment based on HCFC-22, and the import of HCFC-141b, both pure and contained in pre-blended polyols. The Kigali Amendment was ratified on 5 December 2022 and some measures to support future compliance with the Kigali Amendment included the approval of voluntary technical standards for handling fluorinated and flammable refrigerants and their inclusion into relevant training courses. The Government is revising regulations to incorporate the HFC phase-down schedule and HFC licensing regulations and approval is expected by early 2024. The country celebrated International Ozone Day and raised awareness of the Montreal Protocol through social media. Despite the challenges, the country achieved two of the seven IS objectives, and partially achieved five objectives because there was a delay in submitting country programme and Article 7 data, the inter‑ministerial coordination process had not been finalized, implementation of the HPMP had been delayed, and the country was not able to participate in regional meetings, and because there were no gender related activities.
Plan of action
During the upcoming phase, the Bolivarian Republic of Venezuela will continue its efforts to maintain reductions in HCFC consumption through the allocation of import quotas and issuance of licenses. The country will start to address the control of HFC by finalizing the HFC licensing and quota system, and preparation of the KIP and projects to comply with the HFC control measures. The NOU will review existing agreements on inter-governmental cooperation mechanisms and establish new agreements to facilitate the implementation of the Montreal Protocol and its Kigali Amendment, including synergies with the Ministry of Eco-socialism’s climate and energy departments. The NOU also plans to strengthen the technical capacity for the safe use of alternative refrigerants and conduct information dissemination campaigns to support the implementation of activities especially those related to the Kigali Amendment. Gender mainstreaming will also be integrated into implementation of the next phase of the IS project.
Sustainability and risk assessment
The NOU reported that efforts to meet IS objectives had been supported by high-level government support, and efficient and timely support from UNDP. The import and export licensing system substances, direct collaboration with Customs and stakeholders considerably reduce the risk of non-compliance and ensures the sustainability of ODS phase-out. During phase XIV there were changes within FONDOIN, (Fundación Fondo Venezolano de Reconversión Industrial y Tecnológica), which implements the IS project, that caused some implementation delays due the learning curve for the new management; however, this change has also reactivated the project. The main risks for the fulfilment of the project's objectives are related to the economic situation of the country, inflation, and the exchange rate of the national currency and to mitigate these risks the implementing agency will monitor and adjust project implementation procedures as necessary. The IS project staff have strong technical knowledge and experience in the use of new technologies, which minimizes the risks associated with their introduction. Furthermore, the NOU was strengthened with the recruitment of an additional staff member with a technical background in energy and climate.
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Anexo II 
CONSIDERACIONES PRELIMINARES DEL COMITÉ EJECUTIVO SOBRE LA RENOVACIÓN DE LOS PROYECTOS DE FORTALECIMIENTO INSTITUCIONAL PRESENTADOS ANTE LA 92ª REUNIÓN

Argentina 
1. El Comité Ejecutivo examinó el informe presentado junto con la solicitud relativa a la renovación del proyecto de fortalecimiento institucional para Argentina (fase XI) y observó con satisfacción que el Gobierno de Argentina había comunicado los datos de ejecución del programa de país y del Artículo 7 a las Secretarías del Fondo y del Ozono, respectivamente, indicando que el país está en situación de cumplimiento con lo dispuesto en el Protocolo de Montreal. El Comité Ejecutivo tomó nota además de que Argentina había adoptado medidas para eliminar el consumo de HCFC, incluida la aplicación de controles a la importación de HCFC mediante el sistema de concesión de licencias y cuotas, así como una estrecha colaboración con las aduanas y la capacitación de técnicos en refrigeración. El Comité Ejecutivo constató con satisfacción la ratificación por el país de la Enmienda de Kigali en noviembre de 2019 y la modificación del sistema de concesión de licencias para incluir los HFC y, por lo tanto, confía en que el Gobierno de Argentina continuará implementando las actividades de eliminación de HCFC y el proyecto de fortalecimiento institucional y presentará el plan de aplicación de la Enmienda de Kigali para los HFC de manera eficaz para lograr el cumplimiento de las medidas de control del Protocolo de Montreal.
Chile 
1. El Comité Ejecutivo examinó el informe presentado junto con la solicitud relativa al proyecto de fortalecimiento institucional para Chile (fase XV) y observó con satisfacción que el Gobierno de Chile había comunicado los datos de ejecución del programa de país y del Artículo 7 a las Secretarías del Fondo y del Ozono, respectivamente, indicando que el país está en situación de cumplimiento con lo dispuesto en el Protocolo de Montreal. El Comité Ejecutivo tomó nota además de que el Gobierno de Chile había adoptado medidas para eliminar el consumo de SAO; en particular, la aplicación de controles a las importaciones de HCFC mediante el sistema de concesión de licencias y cuotas, y la capacitación de funcionarios de aduanas y técnicos en refrigeración. El Comité Ejecutivo también señaló con satisfacción las actividades iniciadas para facilitar la aplicación de la Enmienda de Kigali. El Comité Ejecutivo constató los esfuerzos del Gobierno de Chile y, por consiguiente, espera que durante los próximos tres años el Gobierno de Chile ejecute las actividades de fortalecimiento institucional, el plan de gestión de eliminación de HCFC y el plan de aplicación de la Enmienda de Kigali relativa a los HFC a fin de mantener la eliminación del consumo de HCFC ya lograda y sentar las bases para la eliminación de los HFC.
Georgia 
1. El Comité Ejecutivo examinó el informe adjunto a la solicitud relativa a la renovación del proyecto de fortalecimiento institucional (fase XII) y observó con satisfacción que el Gobierno de Georgia había notificado a las Secretarías del Fondo y del Ozono, respectivamente, los datos de ejecución del programa de país y del Artículo 7, indicando que el país está en situación de cumplimiento con lo dispuesto en el Protocolo de Montreal. El Comité Ejecutivo constata que Georgia demostró su compromiso con la eliminación gradual del consumo de HCFC al cumplir con la medida de control de 2020 del Protocolo de Montreal, y con las reducciones graduales adicionales de las importaciones y el uso de HCFC. El Comité tomó nota además de los avances del Gobierno de Georgia hacia la ratificación de la Enmienda de Kigali. Por consiguiente, el Comité Ejecutivo confía en que Georgia logre cumplir las medidas de control para reducir su consumo de HCFC en un 67,5% para 2025 y ratifique la Enmienda de Kigali en un futuro próximo.
Líbano
1. El Comité Ejecutivo examinó el informe adjunto a la solicitud relativa a la renovación del proyecto de fortalecimiento institucional para el Líbano (etapa XIII) y tomó nota con satisfacción de que el Gobierno del Líbano había comunicado a las Secretarías del Fondo y del Ozono, respectivamente, los datos de ejecución del programa de país y del Artículo 7, indicando que el país se encuentra en situación de cumplimiento con lo dispuesto en el Protocolo de Montreal. El Comité Ejecutivo constató los esfuerzos del país por alcanzar y mantener los objetivos de reducción acelerada de HCFC acordados mediante la supervisión continua del sistema de cuotas y concesión de licencias de SAO, la ejecución de la etapa II del plan de gestión de eliminación de HCFC y las actividades de supervisión del Gobierno. El Comité Ejecutivo también toma nota con satisfacción de la medida concreta adoptada por el Gobierno para eliminar gradualmente los HFC mediante su inclusión en el sistema de concesión de licencias y, por consiguiente, confía en que en los próximos tres años el Gobierno del Líbano continúe la ejecución de su plan de gestión de eliminación de HCFC y el proyecto de fortalecimiento institucional y comience la ejecución del plan de aplicación de la Enmienda de Kigali relativo a los HFC para lograr y mantener el cumplimiento de las obligaciones contraídas en virtud del Protocolo de Montreal. 
Venezuela (República Bolivariana de)
1. El Comité Ejecutivo examinó el informe presentado junto con la solicitud relativa a la renovación del proyecto de fortalecimiento institucional para la República Bolivariana de Venezuela (fase XV) y observó con satisfacción el hecho de que el Gobierno de la República Bolivariana de Venezuela había notificado a las Secretarías del Fondo y del Ozono, respectivamente, datos sobre la ejecución del programa de país y del Artículo 7, indicando que el país estaba en situación de cumplimiento con lo dispuesto en el Protocolo de Montreal. El Comité Ejecutivo observó además que el país había adoptado medidas para eliminar el consumo de SAO, incluida la aplicación de controles a la importación de HCFC mediante el sistema de concesión de licencias y cuotas, y la capacitación de funcionarios de aduanas y técnicos en refrigeración. El Comité Ejecutivo también tomó nota con satisfacción de las actividades iniciadas para facilitar la aplicación de la Enmienda de Kigali. El Comité Ejecutivo constató el esfuerzo requerido y los desafíos enfrentados por el Gobierno de la República Bolivariana de Venezuela y, por lo tanto, confía en que en los próximos tres años el Gobierno continuará la ejecución del plan de gestión de eliminación de HCFC, la preparación del plan de aplicación de la Enmienda de Kigali relativo a los HFC y las actividades del proyecto de fortalecimiento institucional con éxito para lograr la reducción acordada del 88,8 por ciento en el consumo de HCFC para el 1º de enero de 2023 y sentar las bases para la eliminación en virtud de la Enmienda de Kigali.
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