| 联 合 国 |  | EP |
| --- | --- | --- |
|  | ### 联 合 国 环 境 规 划 署 | Distr. GENERAL UNEP/OzL.Pro/ExCom/88/4 21 October 2021 CHINESE ORIGINAL: ENGLISH |

执行蒙特利尔议定书

多边基金执行委员会

第八十八次会议

2021年11月15至19日，蒙特利尔

# 关于结余和可用资源的报告

# 导言

- 本文件概述了双边机构和执行机构提出并经秘书处同意的财务调整数。本文件根据第28/7号决定和第56/2号决定(c)段的规定，列入了所有在项目完成超过12个月后仍然持有结余的项目的统计数据。文件述及按照相关决定应退还结余的项目（在本文件中称为“特别决定”项目）。按照第41/92号决定(b)段的规定，本文件根据关于收支情况的文件中的记录列明了执行委员会可以使用的现金并提出了建议。

- 本文件还包括以下四份附件：

附件一	执行机构和双边机构持有的已完成项目的资金

附件二	执行机构和双边机构持有的特别决定项目的资金

附件三	执行机构和双边机构持有的额外捐款项目的资金

附件四	执行机构和双边机构退还的已完成项目、特别决定项目和额外自愿捐款项目的资金

# 附件一、二和三为拖延发放承付资金或退还没有承付的资金提出了解释。

应退还第八十八次会议的资金

# 已完成项目、特别决定项目和额外捐款项目应退还的资金总额为6,322,577美元（中双边机构应退还2,339美元，执行机构应退还6,320,238美元）。

执行机构应退还的资金

# 如表1所示，执行机构应退还的资金总额为6,320,238美元。

# 表1.  执行机构应退还第八十八次会议的资金（美元）

| 机构 | 项目费用 | 机构支助费用 | 费用共计 |
| --- | --- | --- | --- |
| 开发计划署 | 2,261,506 | 168,607 | 2,430,113 |
| 环境规划署 | 3,165,404 | 241,892 | 3,407,296 |
| 工发组织 | 36,947 | 2,678 | 39,625 |
| 世界银行 | 0 | 443,204 | 443,204 |
| 共计 | 5,463,857 | 856,381 | 6,320,238 |

# 表2开列了执行机构持有的已完成项目、特别决定项目和额外自愿捐款项目的结余。

# 表2. 执行机构持有的已完成项目、特别决定项目和额外自愿捐款项目的结余（包括机构支助费用）

| 完成年度 | 开发计划署 |  | 环境规划署 |  | 工发组织 |  | 共计 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 数目 | (美元) | 数目 | (美元) | 数目 | (美元) | 数目 | (美元) |
| 完成已超过2年的项目 |  |  |  |  |  |  |  |  |
| 2017 | 1 | 21,740 | 0 | 0 | 0 | 0 | 1 | 21,740 |
| 2018 | 1 | 1,787 | 0 | 0 | 0 | 0 | 1 | 1,787 |
| 2019年1月1日至10月31日 | 1 | 2,246 | 0 | 0 | 0 | 0 | 1 | 2,246 |
| 小计 | 3 | 25,773 | 0 | 0 | 0 | 0 | 3 | 25,773 |
| 完成不到两年的项目 |  |  |  |  |  |  |  |  |
| 2019年11月1日至12月31日 | 13 | 842,341 | 0 | 0 | 0 | 0 | 13 | 842,341 |
| 2020 | 20 | 3,218,499 | 2 | 18,257 | 11 | 1,235,473 | 33 | 4,472,229 |
| 小计 | 33 | 4,060,840 | 2 | 18,257 | 11 | 1,235,473 | 46 | 5,314,570 |
| 共计 | 36 | 4,086,613 | 2 | 18,257 | 11 | 1,235,473 | 49 | 5,340,343 |
| 特别决定项目（进行中） |  |  |  |  |  |  |  |  |
|  | 1 | 135,001 | 2 | 116,344 | 0 | 0 | 3 | 251,345 |
| 额外自愿捐款项目 |  |  |  |  |  |  |  |  |
|  | 3 | 22,223 | 0 | 0 | 0 | 0 | 3 | 22,223 |
| 总计 | 40 | 4,243,837 | 4 | 134,601 | 11 | 1,235,473 | 55 | 5,613,911 |

双边机构应退还的资金

# 双边机构应退还的资金总额为2,339美元，是澳大利亚应退还的2,070美元，外加机构支助费用269美元。

# 日本持有一个在2020年完成的项目的结余，包括机构支助费用在内数额为18,080美元。

可用资源

# 关于收支情况的文件表明，截至2021年10月12日有385,240,783美元的可用结余。双边机构和执行机构退还第八十八次会议的结余总额为6,322,577美元。因此，可供第八十八次会议核准使用的全部资源为391,563,360美元。

秘书处的评论

# 秘书处提醒双边机构和执行机构指出，应尽快把特别决定项目和已完成一年以上的项目的结余退还多边基金。

# 鉴于提交第八十八次会议的项目和活动所需资金共计81,490,200美元，因此有足够资源可供第八十八次会核准使用。

建议

# 谨建议执行委员会：

  - 注意到：

- UNEP/OzL.Pro/ExCom/88/4号文件所载关于结余和可用资源的报告；

- 执行机构退还给第八十八次会议的资金净额为6,320,238美元，包括开发计划署退还2,261,506美元，外加机构支助费用168,607美元；环境规划署退还3,165,404美元，外加机构支助费用241,892美元；工发组织退还36,947美元，外加机构支助费用2,678美元；世界银行退还机构支助费用443,204美元；

- 开发计划署持有三个完成已超过两年的项目的25,773美元结余，包括机构支助费用，并持有三个使用额外自愿捐款供资，举办逐步减少氢氟碳化合物扶持活动的已完成项目的22,223美元结余，包括机构支助费用；

- 环境规划署持有两个“执行委员会特别决定”完成的项目的116,344美元结余，包括机构支助费用；

- 澳大利亚政府将退还第八十八次会议的资金净额为2,070美元，外加269美元的机构支助费用；

## 要求：

- 双边机构和执行机构着手发放或取消已完成项目和“执行委员会特别决定”完成的项目所不需要的承付款和未承付资金，将相关结余退还第九十次会议；

- 开发计划署着手发放或取消三个已完成两年以上的项目承付款，将相关结余退还第九十次会议；

- 开发计划署把三个使用额外自愿捐款供资的已完成项目的结余退还第九十次会议；

- 环境规划署按照第86/16号决定(f)(一)段把两个“执行委员会特别决定”完成的项目的结余退还第九十次会议；

- 财务主任就上文(a)(五)分段所述用现金退还2,339美元一事与澳大利亚政府联系。

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2020(US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not-committed as per 88th meeting (US $) | Support cost on balances committed and not committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | Nov-19 | 57,000 | 56,359 | 641 |  | 58 |  |  |  |
| BRU/PHA/82/INV/23 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 33,000 | 26,549 | 6,451 |  | 581 |  |  |  |
| COS/PHA/81/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | Mar-20 | 40,000 | 38,883 | 1,117 |  | 78 |  |  |  |
| COS/PHA/83/INV/59 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 56,000 | 49,952 | 6,048 |  | 454 |  |  |  |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 179,857 | 174,459 | 5,398 |  | 378 |  |  |  |
| CUB/PHA/82/TAS/60 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 22,236 | 7,764 |  | 699 |  |  |  |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 2,000,000 | 1,896,153 | 103,847 |  | 7,789 |  |  |  |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Dec-19 | 716,400 | 530,037 | 186,363 |  | 13,977 |  |  |  |
| FIJ/PHA/73/INV/27 | HCFC phase-out management plan (stage I, second tranche) | Jun-17 | 37,900 | 17,955 | 19,945 |  | 1,795 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 55,584 | 4,266 |  | 384 |  |  |  |
| FIJ/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 3,718 | 26,282 |  | 2,365 |  |  |  |
| GHA/PHA/81/INV/46 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 125,000 | 105,139 | 19,861 |  | 1,490 |  |  |  |
| GHA/PHA/81/PRP/44 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 60,000 | 49,389 | 10,611 |  | 743 |  |  |  |
| GHA/SEV/82/INS/47 | Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020) | Dec-20 | 178,048 | 177,391 | 657 |  | 46 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 111,244 | 48,506 |  | 3,396 |  |  |  |
| IDS/PHA/71/TAS/200 | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | Jun-20 | 201,674 | 42,383 | 159,291 |  | 11,947 |  |  |  |
| IDS/PHA/76/INV/208 | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | Jun-20 | 512,190 | 244,358 | 267,832 |  | 20,087 |  |  |  |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | Dec-19 | 347,194 | 343,303 | 3,891 |  | 272 |  |  |  |
| IND/SEV/76/INS/467 | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | Dec-19 | 477,734 | 477,682 | 52 |  | 4 |  |  |  |
| KYR/PHA/81/INV/40 | HCFC phase-out management plan (stage II, second tranche) | Dec-20 | 175,000 | 108,104 | 66,896 |  | 4,683 |  |  |  |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Dec-19 | 3,800,000 | 3,388,171 | 411,829 |  | 30,887 |  |  |  |
| MEX/REF/81/INV/187 | Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico | Nov-20 | 2,115,012 | 2,110,680 | 4,332 |  | 303 |  |  |  |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 92,000 | 77,893 | 14,107 |  | 1,058 |  |  |  |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 33,600 | 30,916 | 2,684 |  | 242 |  |  |  |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | Dec-19 | 131,500 | 129,642 | 1,858 |  | 139 |  |  |  |
| SRL/PHA/82/PRP/52 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 29,919 | 10,081 |  | 706 |  |  |  |
| SRL/PHA/82/TAS/51 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 23,657 | 6,343 |  | 571 |  |  |  |
| SRL/SEV/82/INS/53 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | Dec-20 | 171,592 | 136,511 | 35,081 |  | 2,456 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 38,101 | 61,899 |  | 4,333 |  |  |  |
| URU/PHA/77/TAS/69 | HCFC phase-out management plan (stage II, first tranche) (implementation and monitoring) | Dec-18 | 35,800 | 34,130 | 1,670 |  | 117 |  |  |  |
| URU/SEV/80/INS/70 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Dec-19 | 193,024 | 192,729 | 295 |  | 21 |  |  |  |
| VEN/SEV/77/INS/135 | Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018) | Mar-19 | 365,414 | 363,315 | 2,099 |  | 147 |  |  |  |
| ZIM/PHA/83/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 11,435 | 8,565 |  | 600 |  |  |  |
| TOTAL UNDP |  |  |  |  | 3,807,156 |  | 279,457 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| LAO/PHA/74/TAS/27 | HCFC phase-out management plan (stage I, second tranche) | Dec-20 | 97,875 | 86,875 |  | 11,000 | 1,430 | UNEP is working on financial closure of the project. | ExCom 90 |  |
| UGA/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 14,844 |  | 5,156 | 670 | Once project is financially completed | ExCom 89 |  |
| TOTAL UNEP |  |  |  |  |  | 16,157 | 2,100 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| JOR/REF/81/INV/103 | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co. | Jun-20 | 1,637,610 | 1,524,521 | 113,089 |  | 7,917 | 3 | 90 |  |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 24,091 | 5,909 |  | 532 | 3 | 90 |  |
| NER/PHA/82/TAS/34 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 29,658 | 342 |  | 31 | 3 | 90 |  |
| PAK/PHA/76/TAS/95 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-20 | 190,000 | 180,077 | 9,923 |  | 695 | 3 | 90 |  |
| QAT/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 39,629 | 372 |  | 26 | 3 | 90 |  |
| RWA/PHA/77/INV/27 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 55,000 | 54,664 | 336 |  | 30 | 3 | 90 |  |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-20 | 2,693,674 | 2,080,492 | 613,182 |  | 42,923 | 3 | 90 | 86/17(i)(i) |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | Dec-20 | 1,300,000 | 903,494 | 396,506 |  | 27,755 | 3 | 90 | 83/33(c) and 85/17(c) |
| SIL/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-20 | 50,000 | 48,855 | 1,145 |  | 103 | 2 | 90 |  |
| SOA/PHA/67/TAS/04 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Dec-20 | 110,005 | 103,224 | 6,782 |  | 474 | 2 | 90 |  |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 2,035,702 | 6,918 |  | 484 | 3 | 90 |  |
| TOTAL UNIDO |  |  |  |  | 1,154,504 |  | 80,969 |  |  |  |
| JAPAN |  |  |  |  |  |  |  |  |  |  |
| CPR/PHA/77/TAS/582 | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | Dec-20 | 80,000 | 64,000 | 16,000 |  | 2,080 |  |  |  |
| TOTAL JAPAN |  |  |  |  | 16,000 |  | 2,080 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not- committed as per 88th meeting (US $) | Support cost on balances committed and not-committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,364,430 | 126,179 |  | 8,832 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 126,179 |  | 8,832 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 182,206 | 32,350 |  | 4,007 |  |  | 86/16(f)(i) |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 50,589 | 71,170 |  | 8,817 |  |  | 86/16(f)(i) |
| TOTAL UNEP |  |  |  |  | 103,520 |  | 12,824 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 88th meeting (US $) | Balances committed as per 88th meeting (US $) | Balances not- committed as per 88th meeting (US $) | Support cost on balances committed and not-committed as per 88th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COS/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 144,830 | 5,170 |  | 362 |  |  |
| JAM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 145,083 | 4,917 |  | 344 |  |  |
| TRI/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 150,000 | 139,318 | 10,682 |  | 748 |  |  |
| TOTAL UNDP |  |  |  | 20,769 |  | 1,454 |  |  |

Annex IV

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| ARM/PHA/84/TAS/23 | Verification report on the implementation of the HCFC phase-out management plan | 370 | 33 | 403 |
| BRA/PHA/74/INV/307 | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | 1,020,974 | 76,573 | 1,097,547 |
| BRA/PHA/75/INV/315 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | 1,032,897 | 77,468 | 1,110,365 |
| COL/PHA/75/TAS/92 | HCFC phase-out management plan (stage II, first tranche) (technical assistance in policies formulation and implementation) | 5 | 0 | 5 |
| COS/REF/76/DEM/55 | Demonstration of the application of an ammonia/carbon dioxide refrigeration system in replacement of HCFC-22 for the medium-sized producer and retail store of Premezclas Industriales S.A. | 697 | 49 | 746 |
| COS/SEV/75/INS/53 | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | 198 | 14 | 212 |
| CUB/SEV/75/INS/54 | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | 1 | 0 | 1 |
| DOM/REF/81/INV/63 | Conversion of a commercial refrigerator manufacturing line at Fábrica de Refrigeradores Comerciales, SRL (FARCO) from HFC-134a and R-404A to propane (R-290) as refrigerant | 24 | 2 | 26 |
| DRC/PHA/80/INV/45 | HCFC phase-out management plan (stage I, third tranche) | 476 | 43 | 519 |
| EGY/FOA/76/DEM/129 | Demonstration of low-cost options for the conversion to non-ODS technologies in polyurethane foams at very small users | 190,799 | 13,356 | 204,155 |
| EGY/PHA/74/PRP/126 | Preparation of a HCFC phase-out management plan (stage II) | 11,860 | 830 | 12,690 |
| ELS/PHA/77/INV/34 | HCFC phase-out management plan (stage I, third tranche) | 1,052 | 79 | 1,131 |
| IDS/PHA/71/INV/199 | HCFC phase-out management plan (air conditioning sector plan) (stage I, second tranche) | 380 | 29 | 409 |
| IDS/SEV/75/INS/206 | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | 29 | 2 | 31 |
| IND/PHA/75/INV/463 | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | 48 | 4 | 52 |
| IND/SEV/72/INS/457 | Extension of institutional strengthening project (phase X: 4/2014-3/2016) | 182 | 13 | 195 |
| MDV/PHA/69/INV/24 | HCFC phase-out management plan (second tranche) | 3 | 0 | 3 |
| NIR/PHA/75/INV/143 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector and refrigeration servicing) | 1,511 | 113 | 1624 |
| Total completed projects |  | 2,261,506 | 168,607 | 2,430,113 |
| TOTAL UNDP |  | 2,261,506 | 168,607 | 2,430,113 |
| AFG/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | 273 | 35 | 308 |
| AFG/SEV/80/INS/23 | Extension of institutional strengthening project (phase VIII: 1/2018-12/2019) | 5,754 | 0 | 5,754 |
| BEN/SEV/80/INS/35 | Renewal of institutional strengthening project (phase X: 1/2018-12/2019) | 2,663 | 0 | 2,663 |
| BKF/PHA/84/TAS/40 | Verification report on the implementation of the HCFC phase-out management plan | 710 | 92 | 802 |
| BZE/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 9,800 | 1,274 | 11,074 |
| CHI/PHA/76/TAS/193 | HCFC phase-out management plan (stage I, fourth and fifth tranches) | 507 | 66 | 573 |
| CKI/SEV/77/INS/13 | Extension of the institutional strengthening project (phase VI: 1/2017-12/2018) | 5,000 | 0 | 5,000 |
| ECU/PHA/76/TAS/64 | HCFC phase-out management plan (stage I, third tranche) | 14,590 | 1,897 | 16,487 |
| ECU/PHA/82/PRP/67 | Preparation of a HCFC phase-out management plan (stage II) | 9,900 | 1,287 | 11,187 |
| ECU/PHA/82/TAS/69 | HCFC phase-out management plan (stage I, fourth tranche) | 1,235 | 161 | 1,396 |
| ECU/PHA/85/TAS/73 | HCFC phase-out management plan (stage I, fifth tranche) | 10,000 | 1,300 | 11,300 |
| ECU/PHA/86/TAS/74 | HCFC phase-out management plan (stage II, first tranche) | 24,000 | 3,120 | 27,120 |
| ECU/SEV/83/INS/71 | Extension of institutional strengthening project (phase VII: 7/2019-6/2021) | 226,305 | 0 | 226,305 |
| ELS/PHA/65/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | 6,531 | 229 | 6,760 |
| ERI/PHA/82/TAS/17 | Verification report on the implementation of the HCFC phase-out management plan | 982 | 128 | 1,110 |
| FSM/SEV/77/INS/12 | Renewal of institutional strengthening project (phase VI: 1/2017-12/2018) | 969 | 0 | 969 |
| GAM/PHA/82/TAS/36 | Verification report on the implementation of the HCFC phase-out management plan | 1,096 | 142 | 1,238 |
| GBS/PHA/71/TAS/17 | HCFC phase-out management plan (stage I, second tranche) | 22,921 | 2,980 | 25,901 |
| GLO/SEV/82/TAS/347 | Compliance Assistance Programme: 2019 budget | 10,677 | 854 | 11,531 |
| GLO/SEV/84/TAS/350 | Compliance Assistance Programme: 2020 budget | 2,611,540 | 208,923 | 2,820,463 |
| GUA/PHA/82/PRP/54 | Preparation of a HCFC phase-out management plan (stage II) | 1,828 | 238 | 2,066 |
| HAI/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | 20,109 | 2,614 | 22,723 |
| HON/PHA/82/PRP/46 | Preparation of a HCFC phase-out management plan (stage II) | 9,706 | 1,262 | 10,968 |
| IRQ/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 4,734 | 582 | 5,316 |
| IRQ/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | 6,886 | 895 | 7,781 |
| LAO/PHA/82/TAS/32 | Verification report on the implementation of the HCFC phase-out management plan | 5,780 | 751 | 6,531 |
| MAG/PHA/82/TAS/31 | Verification report on the implementation of the HCFC phase-out management plan | 1,076 | 140 | 1,216 |
| MDV/SEV/81/INS/33 | Extension of the institutional strengthening project (phase X: 12/2018-11/2020) | 10,000 | 0 | 10,000 |
| MLW/PHA/82/TAS/44 | Verification report on the implementation of the HCFC phase-out management plan | 1,547 | 201 | 1,748 |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | 18,617 | 0 | 18,617 |
| MON/PHA/82/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| MON/PHA/82/TAS/28 | Verification report on the implementation of the HCFC phase-out management plan | 1,967 | 256 | 2,223 |
| NEP/PHA/82/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | 4,744 | 617 | 5,361 |
| NIC/PHA/74/TAS/31 | HCFC phase-out management plan (stage I, second tranche) | 3,072 | 399 | 3,471 |
| NIC/PHA/83/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| PAR/SEV/77/INS/36 | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | 4,938 | 0 | 4,938 |
| SAM/PHA/82/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | 2,519 | 327 | 2,846 |
| SOI/PHA/82/TAS/15 | Verification report on the implementation of the HCFC phase-out management plan | 7,926 | 1,030 | 8,956 |
| STV/PHA/77/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 14,738 | 1,916 | 16,654 |
| SYR/PHA/83/PRP/105 | Preparation of a HCFC phase-out management plan (stage II) | 17,375 | 2,259 | 19,634 |
| TON/PHA/82/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 5,589 | 727 | 6,316 |
| TTR/PHA/82/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 5,623 | 731 | 6,354 |
| UGA/PHA/77/TAS/21 | HCFC phase-out management plan (stage I, second tranche) | 3,500 | 455 | 3,955 |
| UGA/PHA/82/TAS/25 | Verification report on the implementation of the HCFC phase-out management plan | 380 | 49 | 429 |
| URT/PHA/82/TAS/38 | Verification report on the implementation of the HCFC phase-out management plan | 485 | 63 | 548 |
| ZAM/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 529 | 69 | 598 |
| Total completed projects |  | 3,128,821 | 239,331 | 3,368,152 |
| MON/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 2,134 | 149 | 2,283 |
| TTR/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 25,000 | 1,750 | 26,750 |
| ZIM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 9,449 | 661 | 10,110 |
| Total “additional voluntary contributions” projects |  | 36,583 | 2,561 | 39,143 |
| TOTAL UNEP |  | 3,165,404 | 241,892 | 3,407,296 |
| ARG/PHA/79/TAS/181 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 1,298 | 91 | 1,389 |
| BOL/PHA/82/PRP/47 | Preparation of a HCFC phase-out management plan (stage II) | 26 | 2 | 28 |
| EGY/ARS/50/INV/92 | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | 681 | 51 | 732 |
| EGY/SEV/81/INS/138 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | 1,253 | 88 | 1,341 |
| GAB/PHA/62/INV/27 | HCFC phase-out management plan (stage I, first tranche) | 42 | 4 | 46 |
| GLO/REF/76/DEM/333 | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | 3,212 | 225 | 3,437 |
| GUA/PHA/84/TAS/56 | Verification report on the implementation of the HCFC phase-out management plan | 3,403 | 306 | 3,709 |
| HON/PHA/84/TAS/49 | Verification report on the implementation of the HCFC phase-out management plan | 285 | 26 | 311 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 6,628 | 464 | 7,092 |
| SAU/PHA/68/INV/19 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | 215 | 15 | 230 |
| SEN/PHA/65/INV/31 | HCFC phase-out management plan (stage I, first tranche) | 521 | 39 | 560 |
| SEN/PHA/77/INV/36 | HCFC phase-out management plan (stage I, second tranche) | 1,988 | 149 | 2,137 |
| SOM/PHA/77/TAS/13 | HCFC phase-out management plan (stage I, second tranche) (additional security) | 8,172 | 572 | 8,744 |
| TKM/PHA/76/INV/12 | HCFC phase-out management plan (stage I, third tranche) | 91 | 7 | 98 |
| UGA/PHA/82/PRP/23 | Preparation of a HCFC phase-out management plan (stage II) | 26 | 2 | 28 |
| Total completed projects |  | 27,841 | 2,040 | 29,881 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 6,628 | 464 | 7,092 |
| Total “by decision” projects |  | 6,628 | 464 | 7,092 |
| ARM/SEV/80/TAS/01 | Enabling activities for HFC phase-down | 361 | 26 | 387 |
| LEB/REF/80/PRP/01 | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration | 2,106 | 147 | 2,253 |
| TUN/SEV/80/TAS/02 | Enabling activities for HFC phase-down | 10 | 1 | 11 |
| Total “additional voluntary contributions” projects |  | 2,478 | 174 | 2,652 |
| TOTAL UNIDO |  | 36,947 | 2,678 | 39,625 |
| GLO/SEV/84/TAS/351 | Core unit budget (2020) | 0 | 443,204 | 443,204 |
| TOTAL WORLD BANK |  |  | 443,204 | 443,204 |
| IDS/PHA/64/TAS/196 | HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche) | 2,070 | 269 | 2,339 |
| TOTAL AUSTRALIA |  | 2,070 | 269 | 2,339 |

由于2019冠状病毒病(Covid-19)，将于2021年11月和12月举行在线会议和闭会期间批准程序。

数据采用按第31/2号决定制定的报告格式提交。

UNEP/OzL.Pro/ExCom/88/3。

2: Financial completion initiated; 3: Financial completion being initiated; 4: Financial completion to be initiated after settlement of all pending issues; 5: Project is ongoing; 6: Funds were not transferred.