| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/18 30 October 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 7(a)(v) of the provisional agenda

PROGRESS REPORT OF UNIDO as at 31 december 2023

Introduction

# This document presents the progress report of UNIDO as at 31 December 2023.

# The progress report of UNIDO includes the status of implementation of projects, including 35 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2023, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2023 and cumulative since 1993 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2023 and cumulative since 1993

# As of 31 December 2023, the Executive Committee had approved US $1.05 billion in projects for UNIDO, consisting of US $924.6 million for the implementation of investment and non-investment projects, and US $123.19 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNIDO as at 31 December 2023

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 34,397,921 |
| Destruction | 5,005,540 |
| Energy efficiency | 2,976,620 |
| Foam | 88,536,237 |
| Halon | 1,780,369 |
| HFC phase-down plan | 14,014,915 |
| Fumigants | 78,028,741 |
| Multiple sectors | 139,440 |
| Other | 11,317,246 |
| Phase-out plan | 401,924,677 |
| Process agent | 6,337,359 |
| Production | 50,638,105 |
| Refrigeration | 182,196,588 |
| Several | 24,058,832 |
| Solvents | 23,247,443 |
| Sub-total | 924,600,031 |
| Agency support costs | 123,185,415 |
| Total | 1,047,785,446 |

# In 2023, 98 new projects and activities were approved. This level of funding is expected to result in the phase-out of 84,483 ODP tonnes of consumption and production of ODS and 1,922.8 mt (3,918,853 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2023.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2023. Annex II presents analytical information per year since 1993.

Table 2. Status of project implementation by type as at 31 December 2023

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 11 | 11 | 100 | 722,669 | 722,669 | 0 | 100 |
| Demonstration | 51 | 43 | 84 | 25,504,215 | 23,037,829 | 2,466,386 | 90 |
| Institutional strengthening (IS) | 108 | 92 | 85 | 19,483,175 | 15,695,398 | 3,787,777 | 81 |
| Investment | 1,046 | 903 | 86 | 823,152,091 | 751,973,582 | 71,178,509 | 91 |
| Project preparation | 623 | 551 | 88 | 29,172,737 | 25,396,572 | 3,776,165 | 87 |
| Technical assistance | 225 | 204 | 91 | 25,368,609 | 22,656,035 | 2,712,574 | 89 |
| Training | 23 | 23 | 100 | 1,196,535 | 1,196,535 | 0 | 100 |
| Total | 2,087 | 1,827 | 88 | 924,600,031 | 840,678,620 | 83,921,412 | 91 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNIDO for 2023 and cumulative since 1993 up to 31 December 2023, is summarized as follows:

## Phase-out: In 2023, 470.9 ODP tonnes of consumption of ODS were phased out and an additional 366.5 ODP tonnes of consumption of ODS and 1,762.8 mt (3,612,866 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1993, 65,146 ODP tonnes of consumption of ODS and 17,381 ODP tonnes of production of ODS had been phased out, of an expected total of 84,483 ODP tonnes of consumption and production of ODS from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2023, US $33.29 million was disbursed and US $27.46 million was planned for disbursement based on the 2022 progress report, representing a rate of disbursement of 121 per cent of that planned. Cumulatively, US $840.68 million had been disbursed out of the total US $924.6 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 91 per cent. In 2023, US $30.77 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1993, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.41/kg and for all production sector activities (CFC and methyl bromide (MB)) was US $2.90/kg. The average cost-effectiveness of investment projects per ODP tonne was US $8.87/kg for completed projects and US $22.44/kg for ongoing projects;

## Number of projects completed: In 2023, 69 projects were completed. Since 1993, 1,827 projects of the 2,087 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 88 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2023 were completed on average 61 months after their approval. Since 1993, the average time for completion of investment projects has been 41 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2023 were completed on average 41 months after their approval. Since 1993, the average time for completion of non-investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Project preparation: Of the 623 project preparation activities approved by the end of 2023, 551 have been completed, leaving 72 ongoing activities. In 2023, 17 preparation activities have been completed;

## Implementation delays: A total of 260 projects were under implementation at the end of 2023, experiencing, on average, a delay of 11 months. Forty-two of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2023, two MYAs for the control and phase-out of HFC-23 emissions, 70 MYAs for HCFC phase-out management plans (HPMPs) and 13 Kigali HFC implementation plans (KIPs) were under implementation. Since 1993, 224 MYAs have been approved and 139 MYAs have been completed, representing a completion rate of 62 per cent.

# Table 3 summarizes progress made by UNIDO since 1993.

## Table 3: Progress made by UNIDO since 1993

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 82,527 | 0 | 840,678,620 | 11.41 | 2.90 | 2,087 | 1,827 | 41 | 36 | 11 | 224 | 139 |

*Consumption and production

HFC-related projects

# As of 31 December 2023, the Executive Committee had approved 89 HFC-related projects (including seven demonstration projects, 24 investment projects, 55 preparation projects and three technical assistance projects for enabling activities) under regular contributions amounting to US $20,908,717 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Demonstration | 7 | 0 | 0 | 2,022,620 | 0 | 2,022,620 | 0 |
| Investment** | 24 | 0 | 0 | 13,501,380 | 3,373,712 | 10,127,668 | 25 |
| Preparation | 55 | 13 | 24 | 5,007,010 | 2,829,602 | 2,177,408 | 57 |
| Technical assistance | 3 | 3 | 100 | 377,708 | 368,074 | 9,634 | 97 |
| Total | 89 | 16 | 18 | 20,908,717 | 6,571,387 | 14,337,330 | 31 |

* Excludes agency support costs.

** 1,922.8 mt (3,918,853 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2023, of the 89 projects, 13 preparation activities and three technical assistance projects for enabling activities have been completed, leaving 73 ongoing. The 24 investment projects are at various stages of implementation and are expected to be completed in 2024, 2025 and 2026.

# Of the total cumulative funding approved of US $20,908,717 (excluding agency support costs), US $6,571,387 had been disbursed, representing a disbursement rate of 31 per cent.

I.2	Issues identified in project implementation in 2023

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 42 projects classified as projects with implementation delays (including 40 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); one technical assistance project; and one investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 96th meeting.

# In addition, issues have been identified regarding tranches of MYAs for the phase-out of HCFCs. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Algeria, Bahrain, Burundi, Chile,  China (extruded polystyrene foam sector plan), the Congo, Guinea-Bissau, Iraq, Jordan, Kuwait, Mexico, Pakistan, Rwanda, Somalia, and Uganda, and reports on projects with specific reporting requirements associated with the HPMPs for Bolivia (Plurinational State of) and Honduras, and an HFC investment project for Jordan, have been submitted to the 95th  meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to an HFC-23 emission control project for Argentina and the HPMPs for Afghanistan, Argentina, Botswana, Brunei Darussalam, Ethiopia, Senegal, and Syrian Arab Republic, tranches of which were due at the 95th meeting but were not submitted, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion, are addressed below.

# Of the 172 ongoing projects, excluding IS and project preparation, 42 projects have revised planned dates of completion since the 2022 progress report.

# In line with decision 82/11(b), UNIDO has requested the extension of the duration of one project, as shown in table 5.

Table 5. Project for which an extension of the completion date has been requested

| Country/ project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Sudan (the) SUD/PHA/75/INV/38 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 31 | Additional time required to complete equipment installation and commissioning at Mina Factory and Target Steel; delays experienced due to political situation | Dec-24 | Dec-25 |

# Gender mainstreaming

# During 2023, UNIDO has implemented the Multilateral Fund’s operational policy on gender mainstreaming in 72 countries as part of projects approved since the 85th meeting. UNIDO tries to include to the extent possible activities that would address gender equality and women’s empowerment in HPMPs or KIPs despite budgetary constraints and competing priorities in particular those faced by low-volume consuming countries.

# In many countries, the technical workforce in the refrigeration and air-conditioning (RAC) sector is predominantly male. UNIDO is actively engaged in identifying potential female technicians and engineers who could pursue careers in this sector, offering tailored training programmes. The success of these initiatives varies from country to country.

# Women were actively included in multiple training programmes aimed at enhancing skills in the RAC sector. For example, Cameroon had 128 women trained across various sessions, including specific workshops focused on the use of refrigerant reclamation equipment, service technician training, and safe handling of refrigerants. In Tunisia, 11 women were among the 124 master trainers certified, and 24 women were trained in good practices for handling refrigerants. In a regional cooperation initiative, two women from Nigeria and Cameroon were included in a training programme focused on environment-friendly technologies in the RAC sector. Ecuador organized events like “Fresh Air for All: Women Leading in Refrigeration and Climate Change” to promote women's roles in the refrigeration sector and address climate change. Various countries used the World Refrigeration Day as a platform to highlight women’s involvement in the RAC sector, with Ecuador organizing training events and Tunisia awarding a woman journalist for her contributions to environmental awareness. In Nigeria, 60 female engineering students were awarded scholarships to encourage careers in the RAC sector, with 32 already selected and awarded in a special ceremony. Women participated in study tours to gain international exposure and learn best practices in RAC, such as the visit to South Korea by a team from Nigeria that included female technicians.

# In some regions, sustained investments are imperative to bolster the number of female technicians and engineers. Adequate funding for gender mainstreaming activities, extending beyond mere participant tallies, holds the promise of yielding enduring results.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2023, the Executive Committee had approved 35 HFC-related projects under the additional voluntary contributions amounting to US $7,810,365 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2023

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 3 | 100 | 3,806,326 | 3,562,977 | 243,349 | 94 |
| Project preparation | 4 | 4 | 100 | 101,270 | 101,269 | 1 | 100 |
| Technical assistance - Enabling activities | 28 | 28 | 100 | 3,902,769 | 3,757,244 | 145,525 | 96 |
| Total | 35 | 35 | 100 | 7,810,365 | 7,421,490 | 388,875 | 95 |

* Excludes agency support costs.

** 189.4 mt (370,517 CO2-eq tonnes) of 286.0 mt (508,586 CO2-eq tonnes) of HFCs had been phased out.

# As of the end of 2023, all the 35 projects approved had been completed.

# Of the total cumulative funding approved of US $7,810,365, US $7,421,490 had been disbursed representing a disbursement rate of 95 per cent.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of UNIDO as at 31 December 2023 contained in document UNEP/OzL.Pro/ExCom/95/18;

## To approve the extension, to 31 December 2025, of the completion date of stage II of the HCFC phase-out management plan for the Sudan (first tranche (foam sector) (SUD/PHA/75/INV/38)) to allow completion of the remaining ongoing activities, as reflected in table 5 of document UNEP/OzL.Pro/ExCom/95/18; and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER COUNTRY FOR 2023

# Table 1 of annex I presents the status of project implementation by country for 2023 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNIDO for 2023

| Country | Phased out in 2023 (ODP tonnes) | Phased out in 2023 (CO2-eq tonnes)* | Estimated funds disbursed in 2023 (US$) | Funds disbursed in 2023 (US$) | Percentage of funds disbursed over estimation in 2023 | Percentage of planned projects completed in 2023** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 | 0 | 5,003 | 17,415 | 348 |  |
| Albania | 0.0 | 0 | 105,000 | 124,887 | 119 | 100 |
| Algeria | 0.0 | 0 | 50,001 | 81,725 | 163 |  |
| Argentina | 18.0 | 0 | 830,000 | 1,141,077 | 137 | 17 |
| Armenia | 0.0 | 0 | 50,983 | 114,794 | 225 | 100 |
| Bahamas (the) | 0.0 | 0 | 70,000 | 29,507 | 42 |  |
| Bahrain | 0.0 | 0 | 60,001 | 30,365 | 51 |  |
| Benin | 1.6 | 0 | 42,000 | 42,266 | 101 |  |
| Bolivia (Plurinational State of) | 0.2 | 0 | 103,000 | 108,253 | 105 | 100 |
| Bosnia and Herzegovina | 0.3 | 0 | 133,012 | 124,900 | 94 |  |
| Botswana | 1.3 | 0 | 178,532 | 104,276 | 58 | 50 |
| Brazil | 0.0 | 0 | 290,000 | 270,656 | 93 | 33 |
| Brunei Darussalam | 0.0 | 0 | 8,000 | 0 | 0 |  |
| Burkina Faso | 0.5 | 0 | 4,500 | 3,797 | 84 | 100 |
| Burundi | 0.0 | 0 | 600 | 2,414 | 402 |  |
| Cameroon | 4.0 | 0 | 225,000 | 336,122 | 149 | 100 |
| Chad | 1.0 | 0 | 40,250 | 10,766 | 27 |  |
| Chile | 1.0 | 0 | 429,000 | 563,024 | 131 | 100 |
| China | 362.0 | 0 | 14,010,002 | 14,670,065 | 105 | 100 |
| Congo (the) | 0.0 | 0 | 20,002 | 55,597 | 278 |  |
| Cote d’Ivoire | 0.0 | 0 | 238,000 | 203,371 | 85 |  |
| Democratic People’s Republic of Korea (the) | 0.0 | 0 | 3 | 0 | 6 | 0 |
| Ecuador | 0.0 | 0 | 259,000 | 360,060 | 139 | 100 |
| Egypt | 3.3 | 0 | 1,857,000 | 2,623,417 | 141 | 50 |
| Equatorial Guinea | 0.0 | 0 | 1,000 | 0 | 0 | 100 |
| Eritrea | 0.0 | 0 | 40,000 | 18,759 | 47 |  |
| Ethiopia | 0.0 | 0 | 50,000 | 21,315 | 43 |  |
| Gabon | 0.0 | 0 | 68,320 | 34,352 | 50 | 0 |
| Gambia (the) | 0.0 | 0 | 90,002 | 12,276 | 14 | 0 |
| Grenada | 0.0 | 0 | 1,000 | 18,760 | 1876 |  |
| Guatemala | 0.0 | 0 | 20,001 | 38,654 | 193 | 100 |
| Guinea | 0.0 | 0 | 25,000 | 40,205 | 161 |  |
| Guinea-Bissau | 0.0 | 0 | 18,000 | 14,121 | 78 | 100 |
| Honduras | 0.3 | 0 | 139,000 | 158,170 | 114 | 100 |
| Iran (Islamic Republic of) | 0.0 | 0 | 221,000 | 16,183 | 7 |  |
| Iraq | 0.0 | 0 | 21,002 | 210,421 | 1002 |  |
| Jordan | 5.5 | 0 | 170,678 | 197,277 | 116 | 67 |
| Kuwait | 3.0 | 0 | 1,804,000 | 1,789,195 | 99 |  |
| Lebanon | 0.0 | 0 | 5,000 | 0 | 0 | 100 |
| Lesotho | 0.0 | 0 | 15,000 | 3,649 | 24 | 0 |
| Liberia | 0.0 | 0 | 7,043 | 14,610 | 207 |  |
| Libya | 1.2 | 0 | 267,551 | 232,974 | 87 | 100 |
| Madagascar | 0.0 | 0 | 30,101 | 204 | 1 |  |
| Malawi | 0.2 | 0 | 63,000 | 88,698 | 141 | 50 |
| Mauritania | 0.0 | 0 | 60,000 | 27,810 | 46 |  |
| Mexico | 19.0 | 0 | 595,200 | 1,904,840 | 320 | 100 |
| Montenegro | 0.2 | 0 | 190,252 | 189,424 | 100 | 100 |
| Morocco | 0.0 | 0 | 179,000 | 104,637 | 58 |  |
| Mozambique | 1.2 | 0 | 62,000 | 1,716 | 3 | 100 |
| Myanmar | 0.0 | 0 | 2 | 0 | 9 | 0 |
| Namibia | 0.0 | 0 | 14,000 | 8,808 | 63 | 0 |
| Nicaragua | 0.1 | 0 | 165,000 | 198,721 | 120 | 100 |
| Niger (the) | 0.7 | 0 | 95,900 | 120,176 | 125 |  |
| Nigeria | 33.8 | 0 | 109,501 | 286,073 | 261 | 100 |
| North Macedonia | 0.4 | 0 | 140,000 | 261,616 | 187 | 100 |
| Oman | 2.4 | 0 | 98,050 | 154,134 | 157 | 100 |
| Pakistan | 2.8 | 0 | 626,002 | 1,067,373 | 171 | 100 |
| Philippines (the) | 0.0 | 0 | 250,000 | 295,494 | 118 | 100 |
| Qatar | 0.0 | 0 | 50,000 | 42,346 | 85 |  |
| Rwanda | 0.0 | 0 | 57,000 | 5,120 | 9 | 0 |
| Saint Lucia | 0.0 | 0 | 55,000 | 25,803 | 47 |  |
| Saudi Arabia | 0.0 | 0 | 12,704 | 43,372 | 341 | 100 |
| Senegal | 0.0 | 0 | 100,000 | 69,832 | 70 |  |
| Serbia | 0.5 | 0 | 94,000 | 51,329 | 55 | 50 |
| Sierra Leone | 0.0 | 0 | 55,000 | 17,759 | 32 |  |
| Somalia | 0.0 | 0 | 67,000 | 57,369 | 86 | 50 |
| South Africa | 5.1 | 0 | 386,001 | 620,767 | 161 | 80 |
| Sudan (the) | 0.0 | 0 | 60,132 | 119,149 | 198 |  |
| Suriname | 0.0 | 0 | 1,500 | 1,500 | 100 |  |
| Syria | 0.0 | 0 | 210,501 | 273,256 | 130 | 50 |
| Togo | 0.0 | 0 | 24,501 | 45,353 | 185 |  |
| Tunisia | 0.0 | 0 | 163,000 | 249,069 | 153 | 33 |
| Türkiye | 0.0 | 0 | 617,000 | 2,060,016 | 334 | 100 |
| Turkmenistan | 0.0 | 0 | 224,001 | 273,500 | 122 | 100 |
| Uganda | 0.0 | 0 | 58,000 | 51,917 | 90 | 0 |
| United Republic of Tanzania (the) | 0.0 | 0 | 55,000 | 23,315 | 42 | 0 |
| Venezuela (Bolivarian Republic of) | 1.0 | 0 | 118,001 | 290,112 | 246 | 100 |
| Zambia | 0.4 | 0 | 78,000 | 92,785 | 119 | 50 |
| Global | 0.0 | 0 | 320,000 | 302,338 | 94 | 100 |
| Grand total | 470.9 | 0 | 27,456,835 | 33,294,883 | 121 | 67 |

* No phase-out in 2023 for HFC-related projects.

** For projects that were planned to be completed in 2023.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER YEAR AS AT 31 DECEMBER 2023

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1993 and 2011 and 2013, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1993 | 22 | 22 | 100 | 11,815,540 | 11,815,540 | 0 | 100 |
| 1994 | 52 | 52 | 100 | 30,645,899 | 30,645,899 | 0 | 100 |
| 1995 | 59 | 59 | 100 | 25,662,092 | 25,662,092 | -1 | 100 |
| 1996 | 46 | 46 | 100 | 19,820,493 | 19,820,493 | 0 | 100 |
| 1997 | 130 | 130 | 100 | 42,083,037 | 42,083,038 | -1 | 100 |
| 1998 | 88 | 88 | 100 | 23,638,291 | 23,638,291 | 0 | 100 |
| 1999 | 123 | 123 | 100 | 34,140,324 | 34,140,324 | 0 | 100 |
| 2000 | 96 | 96 | 100 | 30,180,752 | 30,180,752 | 0 | 100 |
| 2001 | 119 | 119 | 100 | 24,700,254 | 24,700,255 | -1 | 100 |
| 2002 | 76 | 76 | 100 | 35,992,041 | 35,992,041 | 0 | 100 |
| 2003 | 49 | 49 | 100 | 29,997,305 | 29,997,305 | 0 | 100 |
| 2004 | 44 | 44 | 100 | 33,105,459 | 33,105,460 | -1 | 100 |
| 2005 | 74 | 74 | 100 | 52,035,808 | 52,035,806 | 2 | 100 |
| 2006 | 44 | 44 | 100 | 20,760,312 | 20,760,312 | 0 | 100 |
| 2007 | 42 | 42 | 100 | 24,186,740 | 24,186,740 | 0 | 100 |
| 2008 | 77 | 77 | 100 | 33,386,108 | 33,386,111 | -3 | 100 |
| 2009 | 70 | 70 | 100 | 15,345,924 | 15,054,995 | 290,929 | 98 |
| 2010 | 69 | 69 | 100 | 45,563,485 | 45,558,787 | 4,699 | 100 |
| 2011 | 71 | 71 | 100 | 76,542,377 | 76,542,380 | -2 | 100 |
| 2012 | 52 | 50 | 96 | 32,670,641 | 32,079,843 | 590,798 | 98 |
| 2013 | 37 | 37 | 100 | 31,110,859 | 31,086,711 | 24,148 | 100 |
| 2014 | 55 | 54 | 98 | 27,150,026 | 27,104,088 | 45,938 | 100 |
| 2015 | 83 | 78 | 94 | 36,863,403 | 34,431,334 | 2,432,069 | 93 |
| 2016 | 58 | 54 | 93 | 35,109,320 | 32,980,593 | 2,128,727 | 94 |
| 2017 | 28 | 25 | 89 | 16,415,109 | 15,491,655 | 923,454 | 94 |
| 2018 | 62 | 58 | 94 | 26,984,263 | 17,295,205 | 9,689,058 | 64 |
| 2019 | 66 | 46 | 70 | 19,184,804 | 11,847,677 | 7,337,127 | 62 |
| 2020 | 58 | 40 | 69 | 15,337,858 | 14,128,868 | 1,208,990 | 92 |
| 2021 | 73 | 29 | 40 | 23,085,475 | 10,035,376 | 13,050,099 | 43 |
| 2022 | 66 | 5 | 8 | 20,317,479 | 4,232,494 | 16,084,985 | 21 |
| 2023 | 98 | 0 | 0 | 30,768,554 | 658,155 | 30,110,399 | 2 |
| Total | 2,087 | 1,827 | 88 | 924,600,031 | 840,678,620 | 83,921,412 | 91 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNIDO

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Afghanistan AFG/PHA/79/INV/22 | HCFC phase-out management plan (stage I, third tranche) | 14 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Afghanistan AFG/PHA/85/INV/28 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | 12 and 18 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Afghanistan AFG/PHA/85/INV/30 | HCFC phase-out management plan (stage II, first tranche) | 23 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Algeria ALG/PHA/66/INV/76 | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | 64 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Algeria ALG/PHA/66/INV/77 | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | 67 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/INV/189 | HCFC phase-out management plan (stage II, second tranche) (foam sector - management and monitoring) | 93 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/INV/192 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 5 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/TAS/190 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector - management and monitoring) | 92 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/TAS/191 | HCFC phase-out management plan (stage II, second tranche) (monitoring and reporting of HCFC-22 production) | 6 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Argentina ARG/PHA/84/TAS/193 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 31 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Bosnia and Herzegovina BHE/PHA/86/TAS/38 | Verification report on implementation of stage I of the HCFC phase-out management plan | 0 | 12 and 18 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Botswana BOT/PHA/86/INV/27 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Brazil BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 98 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Brazil BRA/PHA/75/TAS/308 | HCFC phase-out management plan (stage II, first tranche) (project monitoring) | 99 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Brazil BRA/PHA/82/INV/320 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector) | 59 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Cameroon CMR/PHA/82/INV/45 | HCFC phase-out management plan (stage II, first tranche) | 70 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| China CPR/PHA/77/INV/576 | HCFC phase-out management plan (stage II, first tranche) (room air-conditioner manufacturing sector plan) | 89 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| China CPR/PHA/81/INV/588 | HCFC phase-out management plan (stage II, second tranche) (room air-conditioner manufacturing sector plan) | 50 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| China CPR/PHA/88/INV/605 | HCFC phase-out management plan (stage II, third tranche) (room air-conditioning manufacturing and heat pump water heaters sector plan) | 0 | 12 and 18 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Egypt EGY/PHA/79/INV/133 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 92 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Egypt EGY/PHA/84/INV/141 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector and project management unit) | 91 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Egypt EGY/PHA/84/INV/147 | HCFC phase-out management plan (stage II, second tranche) (residential air-conditioning manufacturing sector) | 57 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Gambia (the) GAM/PHA/86/INV/41 | HCFC phase-out management plan (stage II, first tranche) | 2 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/77/INV/228 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 65 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/INV/239 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 7 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/84/TAS/240 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 6 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/86/INV/246 | HCFC phase-out management plan (stage II, third tranche) (foam sector) | 21 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Jordan JOR/REF/81/INV/103 | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R-134a, R-407c, R-410a) to propane R-290 as refrigerant at Petra Engineering Industries Co. | 93 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Kuwait KUW/PHA/88/INV/43 | HCFC phase-out management plan (stage II, first tranche) | 11 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Liberia LIR/PHA/90/INV/32 | HCFC phase-out management plan (stage II, first tranche) | 11 | Slow progress in implementation | To request UNIDO to submit a status report to the 96th meeting on implementation progress and funds disbursement |
| Madagascar MAG/PHA/90/INV/37 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Montenegro MOG/PHA/85/INV/16 | HCFC phase-out management plan (stage II, first tranche) | 73 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Pakistan PAK/PHA/76/INV/94 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 89 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/INV/102 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | 67 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/INV/99 | HCFC phase-out management plan (stage II, second tranche) (domestic air-conditioning sector) | 95 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/TAS/100 | HCFC phase-out management plan (stage II, second tranche) (project management unit) | 70 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Pakistan PAK/PHA/90/INV/111 | HCFC phase-out management plan (stage III, first tranche) (foam sector) | 0 | 18 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Sudan (the) SUD/PHA/75/INV/38 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 36 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Suriname SUR/PHA/92/INV/32 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | Delay in project completion | To request UNIDO to submit a status report to the 96th meeting on operational completion and funds disbursement |
| Tunisia TUN/PHA/84/INV/74 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 62 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Tunisia TUN/PHA/84/INV/75 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 98 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Türkiye TUR/PHA/75/INV/107 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 96 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Türkiye TUR/PHA/84/INV/111 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring) | 62 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |
| Serbia YUG/PHA/85/INV/54 | HCFC phase-out management plan (stage II, first tranche) | 39 | 12 months delays | To request UNIDO to report to the 96th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/95/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 95th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 95th meeting.

UNIDO became an implementing agency in 1993.

Ongoing projects are all projects that were under implementation as at 31 December 2023. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

No phase-out for HFC-related projects in 2023.

No phase-out so far for HFC-related projects.

Including 1,923 mt of HFC-related projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/95/39

UNEP/OzL.Pro/ExCom/95/41

UNEP/OzL.Pro/ExCom/95/44

UNEP/OzL.Pro/ExCom/95/46

UNEP/OzL.Pro/ExCom/95/47

UNEP/OzL.Pro/ExCom/95/49

UNEP/OzL.Pro/ExCom/95/56

UNEP/OzL.Pro/ExCom/95/59

UNEP/OzL.Pro/ExCom/95/61

UNEP/OzL.Pro/ExCom/95/62

UNEP/OzL.Pro/ExCom/95/66

UNEP/OzL.Pro/ExCom/95/72

UNEP/OzL.Pro/ExCom/95/74

UNEP/OzL.Pro/ExCom/95/77

UNEP/OzL.Pro/ExCom/95/80

UNEP/OzL.Pro/ExCom/95/20 or UNEP/OzL.Pro/ExCom/95/21

UNEP/OzL.Pro/ExCom/95/24

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.