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REPORT ON BALANCES AND AVAILABILITY OF RESOURCES


Introduction

1. This document presents a summary of financial adjustments indicated by the bilateral (BAs) and implementing agencies (IAs) as agreed by the Secretariat. It includes statistical data[footnoteRef:1] from all projects with balances that have been held for over 12-month following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to relevant Executive Committee’s decisions (referred to as “by-decision” projects in this document). It indicates the level of resources available to the Executive Committee in cash and promissory notes as recorded in the status of contributions and disbursements document[footnoteRef:2], as required by decision 41/92(b), and presents a recommendation. [1: The data presented are based on the reporting format that has been developed pursuant to decision 31/2.]  [2: UNEP/OzL.Pro/ExCom/80/3.] 


2. This document also contains the following three annexes:

Annex I	Amounts held by IAs and BAs for completed projects 

Annex II 	Amounts held by IAs and BAs for by-decision projects

Annex III	Fund returns by IAs and BAs from completed and by-decision projects

Funds to be returned to the 80th meeting

3. The total funds to be returned amount to US $4,420,729 (i.e. US -$23,205 by BAs and US $4,443,934 by IAs) from completed and by-decision projects. Annexes I and II provide explanations on the delays in disbursing committed amounts or returning not-committed amounts.

Funds to be returned by IAs

4. The total funds to be returned by IAs amount to US $4,443,934 as shown in Table 1 (the list of projects with funds returned is presented in Annex III). 

Table 1. Funds to be returned by IAs to the 80th meeting (US $)
	Agency
	Project 
	Agency support 
	Total

	UNDP
	558,552
	44,491
	603,043

	UNEP*
	2,609,791
	229,320
	2,839,111

	UNIDO
	652,068
	47,948
	700,016

	World Bank**
	222,593
	79,171
	301,764

	Total
	4,043,004
	400,930
	4,443,934


* Includes return of balance against 2016 Compliance Assistance Programme budget of US $1,589,501.
** Includes return of 2016 core unit costs of US $62,476.

5. Table 2 presents information on balances of completed projects that are still being withheld by the IAs. 

Table 2. Balances of completed projects withheld by IAs (including agency support costs)
	Year completed
	UNDP
	UNEP
	UNIDO
	World Bank
	Total

	
	Number
	(US$)
	Number
	(US$)
	Number
	(US$)
	Number
	(US$)
	Number
	(US$)

	Projects completed over two years ago

	2013
	1
	6,883
	1
	27,334
	
	
	
	
	2
	34,217

	2014
	2
	248,769
	4
	350,097
	
	
	
	
	6
	598,866

	1 Jan to 
31 Oct 2015
	2
	7,335
	
	
	
	
	
	
	2
	7,335

	Sub-total
	5
	262,988
	5
	377,431
	0
	0
	0
	0
	10
	640,418

	Projects completed in less than two years ago

	1 Nov 2015 to 31 Dec 2015
	5
	47,087
	2
	15,566
	5
	302,629
	
	
	12

	365,282

	2016
	1
	167
	3
	295,219
	
	
	
	
	4
	295,386

	Sub-total
	6
	47,254
	5
	310,785
	5
	302,629
	
	
	16
	660,668

	Total 
	11
	310,242
	10
	688,216
	5
	302,629
	0
	0
	26
	1,301,086

	By-decisions projects (on-going)

	
	6
	2,281,341
	6
	231,340
	0
	0
	1
	922,822
	13
	3,435,503

	Grand total 
	17
	2,591,583
	16
	919,556
	5
	302,629
	1
	922,822
	39
	4,736,589



Funds to be returned to the 80th meeting by BAs

6. At the 68th and 69th meetings, the Government of France returned balances of completed projects amounting to US $322,799, of which US $23,205 (including agency supports costs of US $1,450) were unrecorded expenditures. The Secretariat and the Treasurer discussed this issue with the Government of France, and agreed to record the US $23,205 as expenditures in relevant projects, and that the same amount would be offset against future projects approved for the Government of France as a bilateral agency. 

7. Table 3 presents the balances from completed projects that are being held by BAs.





Table 3. Balances held by BAs (US $)
	Year completed
	Japan

	1 Nov 2015 to 31 Dec 2015
	7,782

	Agency support costs
	1,012

	Total 
	8,794

	By-decision projects 
	1,048,692

	Agency support cost
	121,684

	Total by-decision projects
	1,170,376

	Grand total
	1,179,170



8. With regard to balances held by BAs, the Government of Japan has a committed balance of US $365,464 and not-committed balance of US $813,706 for one completed and two by-decisions projects including agency support costs. 

Availability of resources

9. The status of contributions and disbursements document[footnoteRef:3] indicates an available balance amounting to US $78,880,802 as at 16 October 2017. The total net balance returned by BAs and IAs, including agency support costs is US $4,420,729. The total level of resources available for approvals by the Executive Committee at the 80th meeting, after taking into account the Fund’s balance and the total amount returned by IAs is US $83,301,531.  [3:  UNEP/OzL.Pro/ExCom80/3.] 


Secretariat’s comments

10. During the Inter-agency coordination meeting[footnoteRef:4], the Secretariat reminded BAs and IAs that balances associated with completed projects and by-decisions projects that are due should be returned to the Multilateral Fund no later than the 80th meeting. BAs and IAs committed to continue with their efforts to return funds as soon as possible, and to provide an update to the 80th meeting with a view to returning additional balances. [4:  Montreal, 5-7 September 2017.] 


11. Considering that the total level of funding for projects and activities as submitted to the 80th meeting, amounts to US $138,446,594 including agency support costs[footnoteRef:5], there are insufficient resources available for approvals at the 80th meeting. However, this information will be updated during the meeting.  [5:  As at 24 October 2017, and excluding HFC-related projects to be funded under additional contributions.] 


Recommendations

12. The Executive Committee may wish:

(a) To note:

(i) The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/80/4;

(ii) That the net level of funds being returned to the 80th meeting by the implementing agencies was US $4,443,934, consisting of US $558,552, plus agency support costs of US $44,491 from UNDP; US $2,609,791, plus agency support costs of US $229,320 from UNEP; US $652,068, plus agency support costs of US $47,948 from UNIDO; and US $222,593, plus agency support costs of US $79,171 from the World Bank;
That the net level of funds to be returned to the Government of France was 
US $21,755, plus agency support costs of US $1,450.

That UNDP held balances of US $262,988, including agency support costs, for projects completed two years previously;

(iii) [bookmark: _GoBack]That UNEP held balances of US $377,431, consisting of US $219,231 and 
US $158,200 in committed and not-committed balances, respectively, including agency support costs, for five projects completed over two years previously;

That the Government of Japan held balances of US $1,179,170, consisting of US $365,464 and US $813,706 in committed and not-committed balances, respectivly, including agency support costs, for one completed project and two projects completed “by-decision of the Executive Committee”.

(b) To request:

(i) Bilateral and implementing agencies to return, no later than the 81st meeting, the balances of all projects completed over two years previously;

(ii) Bilateral and implementing agencies to disburse or to cancel commitments 
not needed for completed projects and project completed “by-decision of the 
Executive Committee” and to return balances to the 81st meeting; 

(iii) The Government of Japan and UNEP to return to the 81st meeting not-committed balance no longer required; and

(iv) The Treasurer to offset US $23,205 against the Government of France’s contribution in cash to the Fund. 
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Pre-session documents of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol are without prejudice to any decision that the Executive Committee might take following issuance of the document.
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Annex I

COMMITTED AND NOT-COMMITTEED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 
31 December 2016 (US$)
	Funds disbursed as of 
80th meeting (US$)
	Balances committed as per 
80th meeting (US$)

	Balances 
not-committed as per 
80th  meeting (US$)
	Support cost on balances committed & not committed  as per 
80th meeting (US$)

	Why any balances could not be returned?
	When they could be returned?


	Project subject to decision

	UNDP

	ANG/PHA/65/INV/10
	HCFC phase-out management plan (stage I, first tranche)
	Dec-15
	86,222
	45,756
	40,466
	
	3,642
	MYA
	
	

	ANG/PHA/73/TAS/13
	Verification report for stage I of HCFC phase-out management plan
	Dec-15
	30,000
	29,148
	852
	
	77
	
	
	

	ARM/PHA/73/TAS/13
	Verification report for stage I of HCFC phase-out management plan
	Nov-15
	30,000
	29,909
	91
	
	8
	
	
	

	BHU/PHA/70/INV/19
	HCFC phase-out management plan (second tranche)
	Sep-15
	42,000
	41,259
	741
	
	67
	MYA
	
	

	COL/SEV/70/INS/83
	Extension of institutional strengthening project (phase IX: 11/2013-10/2015)
	Mar-16
	275,600
	275,444
	156
	
	11
	
	
	

	DOM/PHA/69/INV/53
	HCFC phase-out management plan (stage I, second tranche) (sector phase-out for the use of HCFCs in the foam manufacturing sector)
	Sep-15
	319,982
	313,910
	6,072
	
	455
	MYA
	
	

	ELS/PHA/65/INV/29
	HCFC phase-out management plan (stage I, first tranche) (phase out of HCFC-141b in imported pre-blended polyols used in the foam manufacturing sector)
	Nov-15
	439,277
	437,601
	1,676
	
	126
	MYA
	
	

	IDS/SEV/71/INS/201
	Extension of institutional strengthening project (phase IX: 1/2014-12/2015)
	Dec-15
	271,246
	271,106
	140
	
	10
	
	
	

	IRA/PHA/63/INV/204
	HCFC phase-out management plan (stage I, first tranche) (foam sector plan: one foam systems house)
	Dec-14
	0
	0
	225,500
	
	16,913
	MYA
	
	

	JAM/PHA/64/INV/28
	HCFC phase-out management plan 
(foam sector) (stage I, first tranche)
	Dec-14
	95,450
	89,537
	5,913
	
	443
	MYA
	
	

	MLI/PHA/63/INV/30
	HCFC phase-out management plan 
(stage I, first tranche)
	Dec-13
	160,000
	153,597
	6,403
	
	480
	MYA
	
	

	TOTAL UNDP
	 
	
	
	
	288,010
	
	22,232
	
	
	




	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 
31 December 2016 (US$)
	Funds disbursed as of 
80th meeting (US$)
	Balances committed as per 
80th meeting (US$)

	Balances 
not-committed as per 
80th  meeting (US$)
	Support cost on balances committed and not- committed  
as per 
80th meeting (US$)

	Why any balances could not be returned?
	When they could be returned?


	Project subject to decision

	UNEP

	BAH/PHA/59/TAS/21
	Terminal phase-out management plan (second tranche)
	Dec-14
	95,000
	33,054
	61,946
	
	8,053
	Balances transferred and committed to HPMP project (ref. decision 68/33)
	
	

	DJI/SEV/70/INS/20
	Extension of the institutional strengthening project (phase V: 7/2013-6/2015)
	
	60,000
	35,996
	24,004
	
	0
	
	
	

	GAB/PHA/62/TAS/26
	HCFC phase-out management plan (stage I, first tranche)
	Dec-15
	90,000
	85,000
	
	
	650
	
	
	

	KUW/PHA/52/TAS/10
	Terminal phase-out management plan for Annex A Group I substances (first tranche)
	Jan-16
	240,000
	17,243
	222,757
	
	28,958
	MYA
	
	

	LIR/SEV/69/INS/20
	Extension of the institutional strengthening project (phase V: 4/2013-3/2015))
	May-16
	85,213
	65,713
	19,500
	
	0
	
	
	

	PRC/SEV/71/INS/25
	Extension of the institutional strengthening project (phase VIII: 1/2014-12/2015)
	Dec-15
	60,000
	45,084
	14,916
	
	0
	
	
	

	QAT/PHA/59/TAS/14
	Terminal phase-out management plan (second tranche)
	Dec-14
	55,000
	0
	55,000
	
	7,150
	Balance was transferred and committed to HPMP as per decision 65/45 
	
	

	STP/SEV/63/INS/20
	Extension of the institutional strengthening project (phase III)
	Mar-13
	60,666
	33,332
	27,334
	
	0
	
	
	

	YEM/PHA/60/TAS/35
	National ODS phase-out plan (second tranche)
	Dec-14
	140,000
	0
	
	140,000
	18,200
	Amount not commited however according to ExCom decision (77), projects to be frozen until security situation is resovled.  UNEP understanding is funds to be kept with it. PSC erreoneously returned to ExCom 79 to be recovered
	
	

	YEM/SEV/68/INS/42
	Extension of the institutional strengthening project (phase VII: 1/2013-12/2014)
	Dec-14
	169,999
	110,251
	59,748
	
	0
	ExCom decision (77) to freeze projects until security situation is resovled.  UNEP understanding is funds to be kept with it. UNEP cannot return funds as UNEP owes country last payment which was returned from intermediary banks due to security issue in YEM. 
	
	

	TOTAL UNEP
	
	
	
	
	485,205
	140,000
	63,011
	
	
	




	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 
31 December 2016 (US$)
	Funds disbursed as of 
80th meeting (US$)
	Balances committed as per 
80th meeting (US$)

	Balances 
not-committed as per 
80th meeting (US$)
	Support cost on balances committed and not- committed 
as per 
80th meeting (US$)
	Why any balances could not be returned?
	When they could be returned?


	Project subject to decision

	UNIDO

	ARG/PHA/53/INV/152
	National CFC phase-out plan: 2008 work programme
	Dec-15
	1,167,350
	 907,654 
	259,696
	
	19,478
	MYA
	82nd meeting
	70/7(b)(ii)a


	IRA/PHA/63/INV/202
	HCFC phase-out management plan 
(stage I, first tranche)
	Dec-15
	1,300,000
	 1,290,423 
	9,577
	
	718
	MYA
	81st meeting
	

	NIR/PHA/66/INV/131
	HCFC phase-out management plan 
(stage I, second tranche) (refrigeration air-conditioning manufacturing and coordination)
	Dec-15
	550,000
	 544,196 
	5,804
	
	435
	MYA
	81st meeting
	

	SUD/FOA/62/INV/28
	Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production in the manufacturing of domestic refrigerators, commercial refrigerators and PU insulated composite panels (Modern, Amin, Coldair, Akadabi)
	Dec-15
	1,056,341
	 1,055,388 
	953
	
	71
	MYA
	81st meeting
	

	TKM/PHA/62/INV/08
	HCFC phase-out management plan 
(stage I, first tranche)
	Dec-15
	309,050
	 303,564 
	5,486
	
	411
	MYA
	81st meeting
	

	TOTAL UNIDO
	
	
	
	
	281,516
	
	21,113
	
	
	

	JAPAN

	PHI/FOA/62/INV/91
	Sector plan to phase out HCFC-141b in the foam sector
	Dec-15

	317,350

	309,568

	7,782

	
	1,012
	4

	81st meeting
	

	TOTAL JAPAN
	
	
	
	
	7,782
	
	1,012
	
	
	


*2: Financial completion initiated; 3: Financial completion being initiated; 4 Financial completion to be initiated after settlement of all pending issues; MYA = Multiyear

UNEP/OzL.Pro/ExCom/80/4
Annex I

UNEP/OzL.Pro/ExCom/80/4
		Annex I


				Annex II			
COMMITED AND NOT-COMMITED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR BY-DECISIONS PROJECTS

	Code
	Project title
	Financial date of completion per decision

	Approved funding plus adjustments as of 31 December 2016 (US$)


	Funds disbursed as of 
80th meeting (US$)
	Balances committed as per 80th meeting (US$)
	Balances not- committed as per 
80th meeting (US$)
	Support cost on balances committed and not-committed  as per 
80th meeting (US$)

	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	BRA/DES/72/DEM/305
	Pilot demonstration project on ODS waste management and disposal
	Dec-23
	1,490,600
	446,256
	1,044,344
	
	73,104
	
	
	79/18(c)(i)

	BRA/REF/47/DEM/275
	Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers
	Dec-18
	1,000,000
	977,483
	22,517
	
	1,689
	
	
	71/10(c)(i)b and 79/19(b)(ii)

	CHI/PHA/73/INV/184
	HCFC phase-out management plan (stage I, third tranche)
	First meeting of 2019
	295,744
	72,869
	222,875
	
	16,716
	MYA
	
	76/45(a)(iii)

	CHI/PHA/76/INV/192
	HCFC phase-out management plan (stage I, fourth and fifth tranches)
	First meeting of 2019
	199,299
	0
	199,299
	
	14,947
	MYA
	
	76/45(a)(iii)

	COL/DES/66/DEM/82
	Demonstration project on end of life ODS management and destruction
	Dec-20
	1,195,000
	829,380
	365,620
	
	27,421
	
	
	79/18(c)(ii)

	IND/PHA/75/INV/463
	CTC phase-out plan for the consumption and production sectors: 2009 annual programme
	First meeting of 2017
	750,093
	477,712
	272,381
	
	20,429
	MYA
	
	75/19(b)(ii)

	TOTAL UNDP
	
	
	
	
	      2,127,035 
	
	154,306
	
	
	

	
UNEP

	CHI/PHA/71/TAS/180
	HCFC phase-out management plan (stage I, second tranche)
	First meeting of 2019
	40,127
	21,275
	5,055
	13,797
	2,451
	 
	Funds to be returned at first meeting of 2019
	76/45(a)(iii)

	CHI/PHA/73/TAS/185
	HCFC phase-out management plan (stage I, third tranche)
	First meeting of 2019
	27,022
	0
	14,184
	12,838
	3,513
	 
	Funds to be returned at first meeting of 2019
	76/45(a)(iii)

	CHI/PHA/76/TAS/193
	HCFC phase-out management plan (stage I, fourth and fifth tranches)
	First meeting of 2019
	68,123
	0
	14,184
	53,939
	8,856
	 
	Funds to be returned at first meeting of 2019
	76/45(a)(iii)

	IRA/PHA/63/TAS/200
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	74th meeting
	202,000
	105,264
	65,000
	
	8,450
	Commitments of US $65,000 with 
US $55,000 advanced to the country, commitments that were erroneusly reported as balances. UNEP awaiting receipt of of expenditure reports
	 
	73/21

	IRQ/PHA/58/TAS/10
	National phase-out plan (first tranche)
	
	1,136,000
	893,130
	729
	
	95
	 
	 
	71/11(b), 73/8(c) and 75/10(b)(i) 

	IRQ/PHA/63/TAS/14
	National phase-out plan (second tranche)
	
	505,000
	14,480
	25,000
	
	3,250
	
	 
	71/11(b), 73/8(c) and 75/10(b)(i) 

	TOTAL UNEP

	
	
	
	
	124,151
	80,575
	26,614
	
	
	

	World Bank

	GLO/REF/47/DEM/268
	Global chiller replacement project (China, India, Indonesia, Malaysia and Philippines)
	Jun-19

	3,253,928

	2,172,896

	858,439

	
	64,383

	
	
	71/10(f)(iii), 75/15(b)(i) and 79/19(b)(ii)

	TOTAL WORLD BANK
	
	
	
	
	858,439
	
	64,383
	
	
	

	JAPAN

	AFR/REF/48/DEM/35
	Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan)
	Jun-16
	700,000
	464,951
	234,993
	56
	30,556
	Financial completion to be initiated after settlement of all pending issues

	81st meeting
	71/10(d)(ii), 74/2(c)(iii) and 75/11(b)(ii)

	IND/PHA/45/INV/389
	CTC phase-out plan for the consumption and production sectors: 2005 annual programme
	Dec-13
	2,500,000
	1,686,357
	
	813,643
	91,128
	Government in process of finalizing planning and implementation of revised activities

	81st meeting
	70/7(b)(ii)c

	TOTAL JAPAN
	
	
	
	
	234,993
	813,699
	121,684
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Annex III

DETAILS ON COMPLETED PROJECTS AND BY-DECISION PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

	Code
	Project Title
	Project costs returned (US$)
	Agency support costs (US$)
	Total

	UNDP

	COL/REF/47/DEM/65
	Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers
	401
	30
	431

	CUB/DES/62/DEM/46
	Pilot demonstration project on ODS waste management and disposal
	5,932
	445
	6,377

	IND/PRO/75/INV/447
	Accelerated CFC production phase-out (second tranche)
	900
	68
	968

	IND/SEV/74/TAS/461
	Survey of ODS alternatives at the national level
	173,273
	15,595
	188,868

	PAK/ARS/56/INV/71
	Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs
	378,047
	28,354
	406,401

	TOTAL UNDP
	
	558,552
	44,491
	603,043

	UNEP

	CHI/PHA/63/TAS/175
	HCFC phase-out management plan (stage I, first tranche)
	8,057
	1,047
	9,104

	ECU/SEV/59/INS/43
	Extension of institutional strengthening project (phase V)
	9,236
	0
	9,236

	GAB/PHA/62/TAS/26
	HCFC phase-out management plan (stage I, first tranche)
	5,000
	0
	5,000

	GLO/SEV/71/TAS/321
	Compliance Assistance Programme: 2014 budget
	763
	61
	824

	GLO/SEV/75/TAS/329
	Compliance Assistance Programme: 2016 budget
	1,471,760
	117,741
	1,589,501

	NER/PHA/66/TAS/27
	HCFC phase-out management plan (stage I, first tranche)
	910
	118
	1,028

	PAR/PHA/73/TAS/32
	Verification report on the implementation of the HCFC phase-out management plan
	5,223
	679
	5,902

	PHI/PHA/66/TAS/94

	National CFC phase-out plan: Final implementation plan

	223,954

	24,636

	248,590

	YEM/PHA/60/TAS/35
	National ODS phase-out plan (second tranche)
	 0
	-18,200
	-18,200

	IRA/PHA/63/TAS/200
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	-65,000
	-12,576
	-77,576

	PHI/PHA/68/TAS/95
	HCFC phase-out management plan (stage I, first tranche)
	891,795
	108,262
	1,000,057

	SUD/SEV/74/TAS/37
	Survey of ODS alternatives at the national level
	58,093
	7,552
	65,645

	TOTAL UNEP
	
	2,609,791
	229,320
	2,839,111

	UNIDO

	AFR/FUM/54/DEM/40
	Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia)
	37,453
	2,809
	40,262

	AFR/REF/48/DEM/37
	Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan)
	54,119
	4,059
	58,178

	BHA/PHA/71/INV/20
	HCFC phase-out management plan (stage I, second tranche)
	255
	23
	278

	BKF/PHA/62/INV/30
	HCFC phase-out management plan (stage I, first tranche)
	1,370
	123
	1,493

	BOL/SEV/74/TAS/41
	Survey of ODS alternatives at the national level
	66
	6
	72

	BRA/REF/72/PRP/304
	Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning manufacturing sector)
	3,828
	268
	4,096

	CPR/PRO/47/INV/436
	Sector plan for methyl bromide production sector 
(first tranche)
	5,414
	406
	5,820

	DRK/FOA/64/PRP/54
	Preparation for HCFC phase-out investment activities (polyurethane foam sector)
	3,885
	291
	4,176

	DRK/PHA/64/PRP/55
	Preparation of a HCFC phase-out management plan (additional funding)
	459
	34
	493

	ECU/SEV/74/TAS/61
	Survey of ODS alternatives at the national level
	420
	38
	458

	EGY/PHA/65/TAS/114
	HCFC phase-out management plan (stage I, first tranche) (enabling activities in the refrigeration and air-conditioning sector)
	246
	18
	264

	EGY/SEV/72/INS/118
	Extension of the institutional strengthening project (phase X: 1/2015-12/2016)
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