| EP |  | ### الأمم المتحدة |  |
| --- | --- | --- | --- |
| Distr. GENERAL UNEP/OzL.Pro/ExCom/94/19 7 May 2024 ARABIC ORIGINAL: ENGLISH | #### برنامج #### الأمم المتحدة #### للبيئة ل |  |  |

اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف

لتنفيـــذ بروتوكـول مونتريــال

الاجتمــــــاعا الرابع والتسعــــون

مونتريال، 27 - 31 مايو / أيار 2024

البندان 9(ج) و(د) من جدول الأعمال المؤقت

- برنامج عمل برنامج الأمم المتحدة للبيئة لعام 2024

- تعليقات وتوصية أمانة الصندوق

# يطلب برنامج الأمم المتحدة للبيئة (اليونيب) موافقة اللجنة التنفيذية على مبلغ 7,024,453 دولارا أمريكيا زائدا تكاليف دعم الوكالة البالغة 247,260 دولارا أمريكيا لبرنامج عملها لعام 2024 المدرج في الجدول 1. ويرفق التقديم بهذه الوثيقة.

# الجدول 1: تعديلات برنامج عمل اليونيب لعام 2024

| البلد | النشاط/ المشروع | المبلغ المطلوب (بالدولار الأمريكي) | المبلغ الموصي به (بالدولار الأمريكي) |
| --- | --- | --- | --- |
| القسم ألف: الأنشطة الموصي بالموافقة الشمولية عليها |  |  |  |
| ألف 1: تجديد مشروعات التعزيز المؤسسي |  |  |  |
| البحرين | تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية عشرة) | 180,000 | 180,000 |
| بوروندي | تجديد مشروعات التعزيز المؤسسي (المرحلة العاشرة) | 180,000 | 180,000 |
| الكاميرون | تجديد مشروعات التعزيز المؤسسي (المرحلة الرابعة عشرة) | 369,704 | 369,704 |
| تشاد | تجديد مشروعات التعزيز المؤسسي (المرحلة الحادية عشرة) | 180,000 | 180,000 |
| جزر القمر | تجديد مشروعات التعزيز المؤسسي (المرحلة الثالثة عشرة) | 180,000 | 180,000 |
| الكونغو | تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية عشرة) | 180,000 | 180,000 |
| جمهورية الكونغو الديمقراطية | تجديد مشروعات التعزيز المؤسسي (المرحلة الحادية عشرة) | 180,000 | 180,000 |
| غواتيمالا | تجديد مشروعات التعزيز المؤسسي (المرحلة العاشرة) | 330,670 | 330,670 |
| غينيا - بيساو | تجديد مشروعات التعزيز المؤسسي (المرحلة الثامنة) | 180,000 | 180,000 |
| جمهورية لاو الديمقراطية الشعبية | تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية عشرة) | 180,000 | 180,000 |
| ملديف | تجديد مشروعات التعزيز المؤسسي (المرحلة الثالثة عشرة) | 180,000 | 180,000 |
| المغرب | تجديد مشروعات التعزيز المؤسسي (المرحلة الخامسة) | 413,338 | 413,338 |
| النيجر | تجديد مشروعات التعزيز المؤسسي (المرحلة الرابعة عشرة) | 180,000 | 180,000 |
| قطر | تجديد مشروعات التعزيز المؤسسي (المرحلة السابعة) | 235,814 | 235,814 |
| سان تومي وبرينسيبي | تجديد مشروعات التعزيز المؤسسي (المرحلة الثامنة) | 180,000 | 180,000 |
| المملكة العربية السعودية | تجديد مشروعات التعزيز المؤسسي (المرحلة الرابعة) | 529,920 | 529,920 |
| السنغال | تجديد مشروعات التعزيز المؤسسي (المرحلة الخامسة عشرة) | 403,007 | 403,007 |
| جنوب السودان | تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية) | 180,000 | 180,000 |
| فانواتو | تجديد مشروعات التعزيز المؤسسي (المرحلة التاسعة) | 180,000 | 180,000 |
| المجموع الكلي للقسم ألف-1 |  | 4,622,453 | 4,622,453 |
| القسم ألف-2: إعداد المشروعات لخطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية |  |  |  |
| سانت كيتس ونيفس | إعداد خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية) | 30,000 | 30,000 |
| المجموع الفرعي للقسم ألف-2 |  | 30,000 | 30,000 |
| تكاليف دعم الوكالة |  | 3,900 | 3,900 |
| المجموع الكلي للقسم ألف-2 |  | 33,900 | 33,900 |
| القسم ألف-3: إعداد المشروعات لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية |  |  |  |
| بليز أ | الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى) | 91,000 | 91,000 |
| غواتيمالا | الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى) | 51,000 | 51,000 |
| المجموع الفرعي للقسم ألف-3 |  | 142,000 | 142,000 |
| تكاليف دعم الوكالة |  | 18,460 | 18,460 |
| المجموع الكلي للقسم ألف-3 |  | 160,460 | 160,460 |
| القسم ألف-4: إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لجمع هذه المواد ونقلها والتخلص منها |  |  |  |
| بليز | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| كمبوديا | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 90,000 | 90,000 |
| إريتريا | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| غرينادا | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 70,000 | 70,000 |
| غيانا | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| قيرغيزستان | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| جمهورية لاو الديمقراطية الشعبية | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| ليسوتو | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| ملاوي | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 90,000 | 90,000 |
| نيجيريا | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 100,000 | 100,000 |
| باراغواي | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 90,000 | 90,000 |
| سانت لوسيا | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| سيراليون | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| الصومال | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 90,000 | 90,000 |
| زامبيا | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 80,000 | 80,000 |
| زمبابوي | إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها | 90,000 | 90,000 |
| المجموع الفرعي للقسم ألف-4 |  | 1,340,000 | 1,340,000 |
| تكاليف دعم الوكالة |  | 174,200 | 174,200 |
| المجموع الكلي للقسم ألف-4 |  | 1,514,200 | 1,514,200 |
| القسم باء: الأنشطة الموصى بالنظر الفردي فيها |  |  |  |
| باء 1: تجديد مشروعات التعزيز المؤسسي |  |  |  |
| جنوب أفريقيا | طلب مشروع التعزيز المؤسسي (المرحلة الأولى) | 500,000 | * |
| المجموع الفرعي للقسم باء-1 |  | 500,000 | * |
| باء 2: المساعدة الفنية لإعداد تقرير التحقق بشأن استهلاك المواد الهيدروكلوروفلوروكربونية |  |  |  |
| جزر البهاما | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| بربادوس | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| بوركينا فاسو | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| كمبوديا | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| تشاد | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| غابون** | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| غرينادا | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| غيانا | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| مدغشقر | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| موزامبيق | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| نيكاراغوا | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| سيراليون | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| تيمور- ليشتي | تقرير التحقق للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية | 30,000 | * |
| المجموع الفرعي للقسم باء-2 |  | 390,000 | * |
| تكاليف دعم الوكالة |  | 50,700 | * |
| المجموع الكلي للقسم باء-2 |  | 440,700 | * |
| المجموع الكلي للأقسام ألف-1، وألف-2، وألف-3، وألف-4، وباء-1، وباء-2 |  | 7,024,453 | 6,134,453 |
| تكاليف دعم الوكالة للأقسام ألف-1، وألف-2، وألف-3، وألف-4، وباء-1، وباء-2 |  | 247,260 | 196,560 |
| المجموع الإجمالي |  | 7,271,713 | 6,331,013 |

أ برنامج الأمم المتحدة الإنمائي بوصفه وكالة منفذة متعاونة.

ب اليونيدو بوصفها وكالة منفذة رائدة.

* موصى بالنظر الفردي فيه.

** رهنا بالموافقة على المرحلة الثانية المقدمة في هذا الاجتماع.

الأنشطة الموصي بالموافقة الشمولية عليها

ألف-1: تجديد مشروعات التعزيز المؤسسي

وصف المشروع

# قدم اليونيب طلبات لتجديد مشروعات التعزيز المؤسسي للبلدان المدرجة في القسم ألف-1 من الجدول 1. ويرد وصف هذه المشروعات في المرفق الأول لهذه الوثيقة.

تعليقات الأمانة

# استعرضت الأمانة طلبات تجديد 19 مشروعا للتعزيز المؤسسي قدمها اليونيب نيابة عن الحكومات المعنية في ضوء المبادئ التوجيهية والقرارات ذات الصلة المتعلقة بالأهلية ومستويات التمويل. وتم فحص الطلبات مقابل خطط العمل الأصلية للمرحلة السابقة، والبرنامج القطري وبيانات المادة 7، وأحدث تقرير عن تنفيذ خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، والتقرير المرحلي للوكالة، وأي مقررات ذات صلة صادرة عن اجتماعات الأطراف. وقد لوحظ أن جميع البلدان التسعة عشر قد قدمت بياناتها الخاصة بالبرامج القطرية لعام 2022 أو لعام 2023 وهي في حالة امتثال لأهداف الرقابة بموجب بروتوكول مونتريال وأبلغت عن استهلاك سنوي للمواد الهيدروكلوروفلوروكربونية لا يتجاوز الحد الأقصى السنوي للاستهلاك المسموح به والمشار إليه في اتفاقات خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية مع اللجنة التنفيذية. وعلاوة على ذلك، تضمنت جميع الطلبات المقدمة تقييما لمؤشرات الأداء ومخاطر المشروع واستدامته وتحقيق أهداف التعزيز المؤسسي، وفقاً للمقرر 91/63 (ب).

توصية الأمانة

# توصي الأمانة العامة بالموافقة الشمولية على طلبات تجديد التعزيز المؤسسي للبحرين وبوروندي وتشاد وجزر القمر وجمهورية الكونغو الديمقراطية وجمهورية لاو الديمقراطية الشعبية وجنوب السودان والسنغال وسان تومي وبرينسيبي وغواتيمالا وغينيا - بيساو وقطر والكاميرون والكونغو وملديف والمغرب والمملكة العربية السعودية والنيجر بمستويات التمويل المبينة في القسم ألف-1 من الجدول 1 من هذه الوثيقة. وقد ترغب اللجنة التنفيذية في أن تعرب للحكومات المذكورة أعلاه عن التعليقات الواردة في المرفق الثاني لهذه الوثيقة.

ألف-2: إعداد المشروعات لخطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية

وصف المشروع

# قدم اليونيب طلبا لإعداد المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لسانت كيتس ونيفس باعتباره الوكالة المنفذة المعينة، كما هو مبين في القسم ألف-2 من
الجدول 1.

# وقدم اليونيب وصفا للأنشطة لدعم طلب إعداد المشروع للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لسانت كيتس ونيفس، والتي تضمنت: مبرر التمويل المطلوب لإعداد المشروع؛ وتقرير مرحلي عن تنفيذ المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية؛ وقائمة الأنشطة التي سيتم الاضطلاع عليها أثناء إعداد المشروع والميزانيات المقابلة باستخدام نموذج طلبات إعداد المشروع لخطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية.

تعليقات الأمانة

# عند استعراض هذا الطلب، قامت الأمانة بمراعاة المبادئ التوجيهية للتمويل الواردة في المقرر 71/42، والتقدم المحرز في المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية بما في ذلك حالة تنفيذ الشرائح حتى إعداد هذه الوثيقة؛ والمقرر 84/46(هـ). وأشارت الأمانة إلى أن التمويل المطلوب يتماشى مع المقرر 71/42. وقد تم تمديد تاريخ اتمام المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لسانت كيتس ونيفس إلى 30 يونيو/حزيران 2024 في الاجتماع الثالث والتسعين، وأشارت الأمانة إلى أن الطلب يتوافق مع المقرر 82/45 الذي يسمح بتقديم طلبات لإعداد المشروع للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية قبل عامين من تاريخ اتمام المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية.

# وأشارت الأمانة كذلك إلى أن استهلاك البلد السنوي المبلغ عنه للمواد الهيدروكلوروفلوروكربونية يمتثل لأهداف الرقابة بموجب بروتوكول مونتريال وللأهداف المحددة في الاتفاق المبرم مع اللجنة التنفيذية بشأن خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية. وأكد اليونيب أن المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لسانت كيتس ونيفيس ستتخلص تدريجيا بنسبة 100 في المائة من خط الأساس للمواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/كانون الثاني 2030.

# توصية الأمانة

# توصي الأمانة بالموافقة الشمولية على إعداد المشروع للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية في سانت كيتس ونيفس بمستوى التمويل المبين في القسم ألف-2 من الجدول 1.

ألف-3: إعداد المشروعات لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية

وصف المشروع

# قدم اليونيب طلبات لإعداد المرحلة الأولى من خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية لبلدين عاملين بالمادة 5، أولهما باعتباره الوكالة المنفذة الرائدة مع اليوئنديبي باعتبارها الوكالة المتعاونة؛ وثانيهما باعتباره الوكالة المنفذة، مع اليونيدو باعتبارها الوكالة المنفذة الرائدة. وترد هذه الطلبات في القسم ألف-3 من الجدول 1.

# وطلبت اليوئنديبي، باعتبارها الوكالة المنفذة المتعاونة لبليز مبلغ 39,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 2,730 دولارا أمريكيا، وطلب اليونيدو باعتباره الوكالة المنفذة الرائدة لغواتيمالا مبلغ 119,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 8,330 دولارا أمريكيا في برنامج عمله لعام 2024، وقدم وصفا للأنشطة المطلوبة لإعداد خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية لغواتيمالا والتكاليف المقابلة لكل نشاط؛ وترد هنا أيضا تعليقات الأمانة.

تعليقات الأمانة

# لدى استعراض هذه الطلبات، نظرت الأمانة في المبادئ التوجيهية لإعداد خطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية على النحو الوارد في المقرر 87/50؛ والأنشطة المقترحة لإعداد المشروعات وارتباطها بالأنشطة التمكينية والمشروعات الأخرى ذات الصلة بالمواد الهيدروفلوروكربونية في البلدان المعنية.

# وقام اليونيب، باعتباره الوكالة المنفذة الرائدة، بوصف الأنشطة المطلوبة لإعداد الاستراتيجية الشاملة لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية لبليز باستخدام نموذج لطلبات إعداد المشروعات لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية. وتضمنت التقديمات بيانات عن استهلاك المواد الهيدروفلوروكربونية ومزيج المواد الهيدروفلوروكربونية منذ عام 2021 وحتى عام 2023. وتضمنت أنشطة إعداد المشروع إجراء دراسة استقصائية على الصعيد الوطني وجمع بيانات عن استهلاك المواد الهيدروفلوروكربونية، وتحليل استخدام المواد الهيدروفلوروكربونية والبدائل؛ واستعراض المبادرات والسياسات واللوائح الوطنية ذات الصلة المتعلقة بالتخلص التدريجي للمواد الهيدروفلوروكربونية؛ وتقييم احتياجات التدريب والترخيص في قطاع خدمة التبريد وتكييف الهواء؛ ووضع استراتيجية شاملة للتخفيض التدريجي للمواد الهيدروفلوروكربونية؛ واجتماعات التحقق لأصحاب المصلحة؛ ووضع خطة وأنشطة للاتصالات والتوعية لتشجيع مشاركة المرأة.

# وأشارت الأمانة إلى أن بليز قد صادقت على تعديل كيغالي؛ وأنها قد قدمت خطابات تأييد تشير إلى عزمها على اتخاذ إجراءات بشأن التخفيض التدريجي للمواد الهيدروفلوروكربونية؛ وأن التمويل المطلوب يتوافق مع المقرر 87/50(ج). وأوضح اليونيب أن إعداد المشروع للاستراتيجية الشاملة لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية سوف يعتمد على الأنشطة المنفذة في إطار الأنشطة التمكينية، حيث إن هذه الإجراءات كانت هي الإجراءات الأولى المرتبطة بالتخفيض التدريجي للمواد الهيدروفلوروكربونية وساهمت في التصديق على تعديل كيغالي.

توصية الأمانة

# توصي الأمانة بالموافقة الشمولية على إعداد المشروعات للمرحلة الأولى من خطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية لبليز بمستويات التمويل المبينة في القسم ألف-3 من الجدول 1.

ألف-4: إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لجمع هذه المواد ونقلها والتخلص منها

وصف المشروع

# قدم اليونيب طلبات لإعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لستة عشر بلدا باعتباره الوكالة المنفذة المعينة، كما هو مبين في القسم ألف-4 من الجدول 1.

تعليقات الأمانة

# عند استعراض هذه الطلبات، قامت الأمانة بمراعاة معايير إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة وطنية الواردة في المقرر 91/66 والأنشطة المقترحة لإعداد المشروع وارتباطها بخطط التخلص التدريجي/ التخفيض التدريجي (أي خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية أو خطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية) في البلد. وأشارت الأمانة إلى أن كل طلب من طلبات التمويل يتماشى مع المقرر 91/66.

# وقدم اليونيب باعتباره الوكالة المنفذة المعينة وصفا للأنشطة المطلوبة لإعداد إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة وطنية لبليز، وإريتريا، وجمهورية لاو الديمقراطية الشعبية، وغرينادا، وغيانا، وقيرغيزستان، وكمبوديا، وليسوتو وباراغواي وزامبيا وزمبابوي وسيراليون والصومال وسانت لوسيا وملاوي ونيجيريا والتكاليف المقابلة لكل نشاط من الأنشطة، باستخدام نماذج التقديم ذات الصلة لمقترحات المشروعات.

# وتضمنت الأنشطة الواردة في طلبات التمويل للبلدان الستة عشر إعداد الجرد الوطني، وتقرير التحقق لأصحاب المصلحة، وخطة العمل والتقرير النهائي؛ وتقييم يعده أصحاب المصلحة المعنيون والمؤسسات والسياسات واللوائح ذات الصلة؛ والتنبؤ بكميات المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية المستخدمة أو غير المرغوب فيها والتي قد تتطلب الاسترداد أو الاستخلاص أو إعادة التدوير أو التخلص منها في المستقبل؛ وتقييم جدوى وتكاليف خيارات التخلص الحالية (إعادة التدوير، والاستخلاص، والتدمير)؛ وتقييم الجدوى الاقتصادية لإنشاء مصنع تدمير؛ واعتبارات تعميم مراعاة المنظور الجنساني. وبالإضافة إلى الأنشطة المذكورة أعلاه، شملت الأنشطة التحضيرية في 14 بلدا أيضا تحديد المختبرات والقدرة الوطنية على تحليل تركيبة المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية المستخدمة أو غير المرغوب فيها، ووضع نموذج تجاري أو تمويلي لضمان الاستدامة الطويلة الأجل لعمليات جمع المواد أو التخلص منها. وتضمنت الأنشطة التحضيرية في باراغواي أيضا إجراء ورشة عمل إقليمية لتبادل الخبرات ولوضع استراتيجيات إقليمية للإدارة السليمة بيئيا للمواد غير المرغوب فيها الخاضعة للرقابة.

توصية الأمانة

# توصي الأمانة بالموافقة الشمولية على إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لجمع هذه المواد ونقلها والتخلص منها لإريتريا وبليز وكمبوديا، وغرينادا، وغيانا، وقيرغيزستان، وجمهورية لاو الديمقراطية الشعبية، وليسوتو، وملاوي، ونيجيريا، وباراغواي، وزامبيا، وزمبابوي، وسيراليون، وسانت لوسيا، والصومال بمستوى التمويل المبين في القسم ألف-4 من الجدول 1.

القسم باء: إعداد المشروعات لخطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية

- باء-1: الأنشطة الموصى بالنظر الفردي فيها

وصف المشروع

# قدم اليونيب طلبا لمشروع التعزيز المؤسسي للبلد المدرج في القسم ألف-1 من الجدول 1. ويرد وصف هذا المشروع في المرفق الأول لهذه الوثيقة.

تعليقات الأمانة

# قررت الأطراف، في اجتماعها التاسع عشر، أن جنوب أفريقيا، باعتبارها بلدا ناميا يعمل بموجب الفقرة 1 من المادة 5 من بروتوكول مونتريال، مؤهلة للحصول على المساعدة الفنية والمالية من الصندوق المتعدد الأطراف للوفاء بالتزاماتها بالتخلص التدريجي من إنتاج واستهلاك المواد الهيدروكلوروفلوروكربونية. ومنذ الاجتماع الخامس والخمسين للجنة التنفيذية، تلقت جنوب أفريقيا دعما من الصندوق المتعدد الأطراف لتنفيذ أنشطة للتخلص التدريجي من المواد الهيدروكلوروفلوروكربونية والتخفيض التدريجي المواد الهيدروكلوروفلوروكربونية. ولم تطلب جنوب أفريقيا حتى الآن تمويلا للتعزيز المؤسسي.

# وتقر الأمانة بالتزام جنوب أفريقيا بتنفيذ بروتوكول مونتريال. وتشير الأمانة إلى أنه على الرغم من أن جنوب أفريقيا كانت قادرة على إنشاء وإدارة وحدة الأوزون الوطنية في البداية دون تمويل إضافي، فإن الوضع الاقتصادي الحالي في البلد لن يسمح له بمواصلة ذلك، مع الأخذ في الاعتبار أيضا الطلب المتزايد على العمل المتعلق بالتخفيض التدريجي للمواد الهيدروكلوروفلوروكربونية وبالمجالات الجديدة، مثل كفاءة استخدام الطاقة. وتشير الأمانة كذلك إلى أن التمويل المطلوب للتعزيز المؤسسي يتماشى مع الأنشطة المقترحة واستهلاك البلد؛ ومن شأن التمويل الإضافي أن يسمح للبلد بتخطيط وتنفيذ الأنشطة المتعلقة ببروتوكول مونتريال على نحو أفضل.

توصية الأمانة

# قد ترغب اللجنة التنفيذية في النظر في الموافقة على مشروع التعزيز المؤسسي (المرحلة الأولى) لجنوب أفريقيا بمبلغ 500,000 دولار أمريكي.

باء-2: المساعدة الفنية لإعداد تقرير التحقق بشأن استهلاك المواد الهيدروكلوروفلوروكربونية

# وتماشيا مع المقرر 61/46 (ج)، قامت الأمانة بسحب عينة من 15 بلدا منخفض الاستهلاك بموجب المادة 5 وبلدين غير منخفضَي الاستهلاك يمولان كبلدين منخفضَي الاستهلاك بغرض التحقق من امتثالهما لاتفاقات خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية الخاصة بهما. وترد البلدان المختارة في الجدول 5 من الوثيقة UNEP/OzL.Pro/ExCom/94/14 التي تقدم نظرة عامة على المسائل المحددة أثناء استعراض المشروع. وتماشيا مع المقرر 92/21 (ج)، يطلب اليونيب، باعتباره الوكالة المنفذة الرائدة، تمويلا للتحقق من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لكمبوديا، والمرحلة الثانية من خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية في جزر البهاما، وبربادوس، وبوركينا فاسو، وتشاد، وغابون، وغرينادا، وغيانا،  ومدغشقر، وموزامبيق، ونيكاراغوا، وسيراليون، وتيمور - ليشتي.

تعليقات الأمانة

# أشارت الأمانة إلى أن طلبات التمويل كانت متسقة مع الأموال المعتمدة لعمليات تحقق مماثلة في اجتماعات سابقة، وأشارت كذلك إلى أنه يجب تقديم تقارير التحقق قبل 10 أسابيع على الأقل من اجتماعات اللجنة التنفيذية ذات الصلة عندما يجري السعي للحصول على تمويل الشريحة التالية لتنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية.

توصية الأمانة

# قد ترغب اللجنة التنفيذية في النظر في الموافقة على تقديم المساعدة الفنية لإعداد تقرير التحقق الخاص بخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لكمبوديا والمرحلة الثانية من خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية في جزر البهاما، وبربادوس، وبوركينا فاسو، وتشاد، وتيمور - ليشتي، وسيراليون، وغابون، وغيانا، ومدغشقر، وموزامبيق، ونيكاراغوا، بمبلغ 30,000 دولار أمريكي لكل منها، بالإضافة إلى تكاليف دعم الوكالة البالغة 3,900 دولار أمريكي لبرنامج الأمم المتحدة للبيئة، على أساس أنه يجب تقديم تقارير التحقق على الأقل 10 أسابيع قبل اجتماعات اللجنة التنفيذية المعنية عندما يجري السعي للحصول على تمويل الشريحة التالية لتنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية.

Annex I

# institutional strengthening project proposals

Bahrain: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Oct-96 | 74,580 |
| Phase II: | Jul-00 | 49,720 |
| Phase III: | Dec-03 | 57,200 |
| Phase IV: | Nov-05 | 60,000 |
| Phase V: | Nov-07 | 60,000 |
| Phase VI: | Apr-10 | 52,500 |
| Phase VII: | Dec-12 | 60,000 |
| Phase VIII: | May-16 | 85,000 |
| Phase IX: | Jun-18 | 85,000 |
| Phase X: | Jun-20 | 85,000 |
| Phase XI: | Jun-22 | 85,000 |
| Total: |  | 754,000 |
| Amount requested for renewal (phase XII) (US $): |  | 180,000 |
| Amount recommended for approval for phase XII (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XII to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 1996 |
| Date of approval of HCFC phase-out management plan: |  | 2012 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 22.7 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 51.9 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | Not available |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 25.51 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 25.51 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | Not available |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 4,543,642 |
| Amount disbursed (as at December 2022) (US $): |  | 3,869,310 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 136.90 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 101.60 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 1,318,672 |
| (b) Institutional strengthening: | 754,000 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 2,470,969 |
| Total: | 4,543,642 |
| (d) HFC activities funded from additional voluntary contributions | 0 |

# Progress report

- Bahrain successfully implemented phase XI of its institutional strengthening (IS) project and fully achieved six performance objectives while one performance objective was partially achieved. During this phase: Article 7 and country programme data for 2021 and 2022 were reported on time and the e-licensing system was upgraded and is effectively operational for enhanced monitoring and control. Full enforcement of the updated legislation on enhancing the environmental practices in the installation and servicing of refrigeration and air-conditioning (RAC) equipment continued with a massive number of RAC technicians trained and certified. Stage II of the HCFC phase-out management plan (HPMP) implementation was initiated with the successful completion of the first tranche. Regular coordination meetings with the Gulf Cooperation Council (GCC) countries continued to coordinate implementation and enhance cooperation in preventing illegal trade. The national ozone unit (NOU) organized several awareness-raising campaigns, including extensive activities related to the observation of Ozone Day. The National Ozone Officer actively participated in the Executive Committee and Montreal Protocol meetings in 2022 and 2023.

# Plan of action

- During the next phase of the IS project, the NOU will continue to oversee the coordination and implementation of the activities planned under stage II of the HPMP and IS projects. The ratification process for the Kigali Amendment will continue and the preparation of the Kigali HFC implementation plan will be initiated. Collaboration with the GCC countries will continue, along with active engagement of stakeholders in the NOU’s activities, awareness and outreach meetings, campaigns, and celebrations of Ozone Day. The NOU will continue to actively participate in network meetings, Montreal Protocol and Executive Committee meetings.

# Sustainability and risk assessment

- The national ozone unit as part of the Supreme Council of Environment, is well integrated into the national policymaking and implementation structure. The main risk would be delayed ratification of the Kigali Amendment and the adoption of feasible alternatives for high ambient temperature conditions. UNEP’s Compliance Assistance Programme will continue to provide all required support to facilitate the process of ratifying the Kigali Amendment and thus support the country in preparing and adopting all required policies, regulations, and standards to facilitate full compliance. Support will also continue to ensure timely implementation of the ongoing HPMP so that the planned phase-out targets can be achieved and the ground for introducing new alternatives laid.

Burundi: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Nov-98 | 74,580 |
| Phase II: | Jul-02 | 57,200 |
| Phase III: | Dec-04 | 60,000 |
| Phase IV: | Nov-06 | 60,000 |
| Phase V: | Apr-09 | 60,000 |
| Phase VI: | Dec-13 | 0 |
| Phase VII: | Nov-15 | 85,000 |
| Phase VIII: | Jun-18 | 84,931 |
| Phase IX: | Jul-21 | 85,000 |
| Total: |  | 566,711 |
| Amount requested for renewal (phase X) (US $): |  | 180,000 |
| Amount recommended for approval for phase X (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase X to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 1998 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.1 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 7.2 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 207,530 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 0.77 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 0.77 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 57,963 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 2,597,637 |
| Amount disbursed (as at December 2022) (US $): |  | 2,183,772 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 59.8 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 59.5 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 538,755 |
| (b) Institutional strengthening: | 566,711 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,492,171 |
| Total: | 2,597,637 |
| (d) HFC activities funded from additional voluntary contributions | 0 |

# Progress report

- Burundi's national ozone unit (NOU) successfully implemented phase IX of the institutional strengthening (IS) project, fully achieving all seven performance indicators. The NOU gathered import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs) and submitted a comprehensive country program and Article 7 data. Annual meetings with stakeholders, including the National Ozone Committee, were conducted to ensure efficient coordination. Furthermore, Burundi ratified the Kigali Amendment on March 26, 2021. The NOU coordinated training sessions for 320 refrigeration and air-conditioning (RAC) technicians, 165 customs officers, and 50 media professionals. Ongoing efforts focused on raising awareness about HCFC alternatives, relevant legislation, and regulatory frameworks. Burundi submitted their Enabling Activities project, which was approved, and necessary steps were taken in preparing stage I of the Kigali HFC implementation plan and working closely with all stakeholders involved to ensure the Kigali Amendment's provisions are respected. Additionally, Burundi actively participated in observing Ozone Day and engaged in Protocol-related meetings. Burundi also continuously worked on improving the integration of the Multilateral Fund gender mainstreaming policy in the country’s project implementation.

# Plan of action

- Under phase X of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP and preparation of stage I of the KIP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; preparation of the KIP strategy; and continuing working on integrating gender mainstreaming into the IS activities and projects implementation.

# Sustainability and risk assessment

- The successful implementation of the IS project in Burundi relies on stable funding from the Multilateral Fund. Active participation from stakeholders, relevant associations, ministries, and agencies is crucial for developing recommendations and amendments to laws and regulations, as well as for conducting public awareness and promotional activities. The NOU is consistently guided by the National Ozone Steering Committee, which includes key line ministries, the RAC sector, and other pertinent agencies.

Cameroon: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Nov-93 | 181,930 |
| Phase II: | May-97 | 120,910 |
| Phase III: | Jul-99 | 120,910 |
| Phase IV: | Dec-03 & Dec-04 | 139,532 |
| Phase V: | Nov-05 | 139,532 |
| Phase VI: | Nov-07 | 139,532 |
| Phase VII: | Nov-09 | 139,532 |
| Phase VIII: | Nov-11 | 139,532 |
| Phase IX: | Dec-13 | 139,532 |
| Phase X: | Nov-15 | 178,601 |
| Phase XI: | Nov-17 | 178,578 |
| Phase XII: | Dec-19 | 178,000 |
| Phase XIII: | Nov-21 | 178,601 |
| Total: |  | 1,974,722 |
| Amount requested for renewal (phase XIV) (US $): |  | 369,704 |
| Amount recommended for approval for phase XIV (US $): |  | 369,704 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $): |  | 369,704 |
| Date of approval of country programme: |  | 1993 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 8.2 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 88.8 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 18.1 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 4,760,203 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) |  | 25.3 |
| (c) Annex E (methyl bromide) |  | 0.0 |
| Total: |  | 25.3 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 3,203,591 |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 12,807,177 |
| Amount disbursed (as at December 2022) (US $): |  | 10,877,226 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 981.5 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 735.8 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 8,937,997 |
| (b) Institutional strengthening: | 1,974,722 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,894,459 |
| Total: | 12,807,177 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Cameroon's national ozone unit (NOU) successfully implemented phase XIII of the institutional strengthening (IS) project, fully achieving all the seven performance indicators. The NOU gathered import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs) and submitted comprehensive country program and Article 7 data. Annual meetings with stakeholders, including the National Ozone Committee, were conducted to ensure efficient coordination. Furthermore, Cameroon ratified the Kigali Amendment on August 24, 2021. The NOU coordinated training sessions for 255 refrigeration and air-conditioning (RAC) technicians and 80 customs officers. Ongoing efforts focused on raising awareness about HCFC alternatives, relevant legislation, and regulatory frameworks. Additionally, Cameroon participated in observing Ozone Day and engaged in Protocol-related meetings.

# Plan of action

- Under phase XIV of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of the second tranche of stage II of the HPMP and the first tranche of stage I of the Kigali HFC implementation plan (KIP); coordinating the submission and implementation of the third tranche of stage II of the HPMP, stage III of the HPMP and the second tranche of stage I of the KIP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; and timely data collection and reporting to the Ozone and Fund Secretariats.

# Sustainability and risk assessment

- The successful implementation of the IS project in Cameroon relies on stable funding from the Multilateral Fund. Active participation from stakeholders, relevant associations, ministries, and agencies is crucial for developing recommendations and amendments to laws and regulations, as well as for conducting public awareness and promotional activities. The NOU is consistently guided by the National Ozone Steering Committee, which includes key line ministries, the RAC sector, and other pertinent agencies.

Chad: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Jul-98 | 67,800 |
| Phase II: | Dec-04 | 60,000 |
| Phase III: | Nov-06 | 60,000 |
| Phase IV: | Nov-08 | 60,000 |
| Phase V: | Nov-11 | 60,000 |
| Phase VI: | Dec-13 | 60,000 |
| Phase VII: | Nov-15 | 85,000 |
| Phase VIII: | Nov-17 | 85,000 |
| Phase IX: | Dec-19 | 85,000 |
| Phase X: | Dec-22 | 85,000 |
| Total: |  | 707,800 |
| Amount requested for renewal (phase XI) (US $): |  | 180,000 |
| Amount recommended for approval for phase XI (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XI to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 1998 |
| Date of approval of HCFC phase-out management plan: |  | 2010 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 16.1 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 4,154,644 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 9.91 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 9.91 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 5,374,554 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 3,392,569 |
| Amount disbursed (as at December 2022) (US $): |  | 2,755,070 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 45.6 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 37.1 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 648,638 |
| (b) Institutional strengthening: | 707,800 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 2,036,132 |
| Total: | 3,392,569 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Chad's national ozone unit (NOU) successfully implemented phase X of the institutional strengthening (IS) project, fully achieving seven out of seven performance indicators. During the phase, the NOU collected relevant import data and submitted country programme and Article 7 data as required. Annual meetings with stakeholders, including the National Ozone Committee, were held for effective coordination. The NOU oversaw training for 458 refrigeration and air-conditioning (RAC) technicians (208 women) and 405 (184 women) customs officers under the HCFC phase-out management plan (HPMP). Ongoing activities included raising awareness about HCFC alternatives, relevant laws, and regulations. Chad also observed Ozone Day and engaged in Protocol-related meetings.

Plan of action

- Under phase XI of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; and preparation and submission of the Kigali HFC implementation plan strategy.

Sustainability and risk assessment

- The IS project can be successfully implemented in Chad under conditions of stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the National Ozone Steering Committee which comprises of key line ministries, the RAC sector and other relevant agencies.

Comoros (the): Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Nov-97 | 31,414 |
| Phase II: | Dec-00 | 20,942 |
| Phase III: | Apr-03 | 24,093 |
| Phase IV: | Apr-05 | 60,000 |
| Phase V: | Mar-07 | 60,000 |
| Phase VI: | Apr-09 | 60,000 |
| Phase VII: | Jul-11 | 60,000 |
| Phase VIII: | Jul-13 | 60,000 |
| Phase IX: | Nov-15 | 85,000 |
| Phase X: | Nov-17 | 85,000 |
| Phase XI: | Dec-19 | 85,000 |
| Phase XII: | Nov-21 | 85,000 |
| Total: |  | 716,449 |
| Amount requested for renewal (phase XIII) (US $): |  | 180,000 |
| Amount recommended for approval for phase XIII (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 1997 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 0.1 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 34,958 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 0.03 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 0.03 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 19,482 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 1,751,276 |
| Amount disbursed (as at December 2022) (US $): |  | 1,558,407 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 2.6 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 0.4 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 80,965 |
| (b) Institutional strengthening: | 716,449 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 953,861 |
| Total: | 1,751,276 |
| (d) HFC activities funded from additional voluntary contributions | 50,000 |

# Progress report

- Comoros’s national ozone unit (NOU) successfully implemented phase XII of the institutional strengthening (IS) project, fully achieving five out of seven performance indicators, with two performance indicators partially achieved. The NOU collected import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs) and submitted country programme and Article 7 data as required. Annual meetings with stakeholders, including the National Ozone Committee, were conducted to ensure efficient coordination. The NOU coordinated training sessions for 12 customs officers. Ongoing efforts focus on raising awareness about HCFC alternatives, relevant legislation, and regulatory frameworks. Additionally, Comoros actively participated in observing International Ozone Day and engaged in Protocol-related meetings.

# Plan of action

- Under phase XIII of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; and preparation of the Kigali HFC implementation plan strategy.

# Sustainability and risk assessment

- The successful implementation of the IS project in Comoros relies on stable funding from the Multilateral Fund. Active participation from stakeholders, relevant associations, ministries, and agencies is crucial for developing recommendations and amendments to laws and regulations, as well as for conducting public awareness and promotional activities. The NOU is consistently guided by the National Ozone Steering Committee, which includes key line ministries, the refrigeration and air-conditioning sector, and other pertinent agencies.

Congo (the): Renewal of institutional strengthening

| Summary of the project and country profile |  |  |  |
| --- | --- | --- | --- |
| Implementing agency: |  | UNEP |  |
| Amounts previously approved for institutional strengthening (US $): |  |  |  |
| Phase I: | Jul-95 | 71,099 |
| Phase II: | Dec-00 | 47,404 |
| Phase III: | Apr-03 | 54,531 |
| Phase IV: | Apr-05 | 60,000 |
| Phase V: | Mar-07 | 60,000 |
| Phase VI: | Apr-09 | 60,000 |
| Phase VII: | Jul-11 | 60,000 |
| Phase VIII: | Dec-13 | 60,000 |
| Phase IX: | Nov-15 | 85,000 |
| Phase X: | Jun-18 | 84,800 |
| Phase XI: | Jul-21 | 85,000 |
| Total: |  | 727,834 |  |
| Amount requested for renewal (phase XII) (US $): |  | 180,000 |  |
| Amount recommended for approval for phase XII (US $): |  | 180,000 |  |
| Agency support costs (US $): |  | 0 |  |
| Total cost of institutional strengthening phase XII to the Multilateral Fund (US $): |  | 180,000 |  |
| Date of approval of country programme: |  | 1995 |  |
| Date of approval of HCFC phase-out management plan: |  | 2011 |  |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |  |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 10.14 |  |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.9 |  |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 504,649 |  |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |  |
| (b) Annex C, Group I (HCFCs) |  | 5.57 |  |
| (c) Annex E (methyl bromide) |  | 0.00 |  |
| Total: |  | 5.57 |  |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 292,240 |  |
| Year of reported country programme implementation data: |  | 2022 |  |
| Amount approved for projects (as at December 2023) (US $): |  | 2,529,770 |  |
| Amount disbursed (as at December 2022) (US $): |  | 2,184,922 |  |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 84.5 |  |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 32.1 |  |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 361,765 |
| (b) Institutional strengthening: | 727,834 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,440,171 |
| Total: | 2,529,770 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Congo's national ozone unit (NOU) successfully implemented phase XI of the institutional strengthening (IS) project, fully achieving six of seven performance indicators, with one partially achieved. The focus in the current phase was on effectively gathering import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs); submitting comprehensive country program and Article 7 data; further discussions on cooperation with the customs authority; organization of annual meetings with stakeholders, including the National Ozone Committee for better coordination; organizing training sessions for 168 refrigeration and air-conditioning (RAC) technicians and 115 customs officers focused on raising awareness on HCFC alternatives, relevant legislation, and regulatory frameworks. Congo ratified the Kigali Amendment on June 16, 2022, and its enabling activities project was approved at the 91st Executive Committee meeting. During the phase, Congo began work on preparation for implementation of its Kigali HFC implementation plan (KIP). Additionally, Congo participated in observing Ozone Day and engaged in Montreal Protocol-related meetings during the phase.

# Plan of action

- During phase XII, the NOU’s priorities will be for Congo to achieve the 67.5% HCFC reduction target by 2025 and begin implementation of the KIP. Activities planned also include: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; sustaining monitoring and evaluation efforts; continuing discussions with customs authorities and industry association; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; preparation of the KIP strategy and implementation of stage I; participation in regional network and Montreal Protocol meetings and sharing of knowledge. Gender mainstreaming will be integrated into the implementation of phase XII of the IS project.

# Sustainability and risk assessment

- The effective execution of the IS project in Congo hinges on securing consistent and constant funding provided by the Multilateral Fund. Engaging participation from stakeholders, pertinent associations, ministries, and agencies is paramount for crafting recommendations and adjustments to legislation and regulations, conducting public awareness campaigns, and promoting initiatives. The NOU consistently operates under the guidance of the National Ozone Steering Committee, comprising crucial line ministries, the RAC sector, and other relevant entities.

Democratic Republic of the Congo: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Mar-99 | 36,465 |
| Phase II: | Dec-00 | 72,930 |
| Phase III: | Jul-05 | 64,540 |
| Phase IV: | Jul-07 | 64,540 |
| Phase V: | Jul-09 | 48,405 |
| Phase VI: | Dec-10 | 64,540 |
| Phase VII: | Dec-13 | 64,540 |
| Phase VIII: | Dec-16 | 85,000 |
| Phase IX: | May-19 | 85,000 |
| Phase X: | Jul-21 | 84,800 |
| Total: |  | 670,760 |
| Amount requested for renewal (phase XI) (US $): |  | 180,000 |
| Amount recommended for approval for phase XI (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XI to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 1999 |
| Date of approval of HCFC phase-out management plan (stage I): |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 4.7 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 66.2 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 1.5 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | Not available |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) |  | 1.01 |
| (c) Annex E (methyl bromide) |  | 0.0 |
| Total: |  | 1.01 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | Not available |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 5,586,205 |
| Amount disbursed (as at December 2022) (US $): |  | 5,156,807 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 359.8 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 355.5 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 2,707,814 |
| (b) Institutional strengthening: | 670,760 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 2,207,631 |
| Total: | 5,586,205 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Democratic Republic of the Congo’s national ozone unit (NOU) successfully implemented phase X of the institutional strengthening (IS) project, fully achieving five out of seven performance indicators, with two partially achieved. The NOU collected ODS import data and submitted country programme and Article 7 data as required. Annual meetings with stakeholders, including the National Ozone Committee, were held for effective coordination. Democratic Republic of the Congo worked towards finalizing the ratification of the Kigali Amendment. The NOU oversaw training for 80 refrigeration and air-conditioning (RAC) technicians (11 women) and 33 (2 women) customs officers under the HPMP. Ongoing activities included raising awareness about HCFC alternatives, relevant laws, and regulations. During the phase, Democratic Republic of the Congo actively observed Ozone Day and engaged in Protocol-related meetings.

# Plan of action

- Under phase XI of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of the second tranche of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; establishing the licensing system for HFCs; preparation and implementation of the Kigali HFC implementation plan (KIP); sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; and timely data collection and reporting to the Ozone and Fund Secretariats.

# Sustainability and risk assessment

- The implementation of the IS project in the Democratic Republic of Congo can be successful provided there is stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries, and agencies must actively participate in developing recommendations and amendments to laws and regulations, as well as in public awareness and promotional activities. One potential risk identified by the government in achieving the project's objectives and complying with the obligations of the Montreal Protocol is the failure to meet the goals of the Kigali Amendment. This risk stems from the country's ineligibility to secure funding for the preparation and implementation of its KIP before ratifying the Kigali Amendment. Additionally, the absence of a licensing system for hydrofluorocarbons (HFCs) at the current state is also considered a potential risk. The NOU is continuously guided by the National Ozone Steering Committee, which comprises key line ministries, the RAC sector, and other relevant agencies.

Guatemala: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Jun-93 | 194,360 |
| Phase II: | May-97 | 108,480 |
| Phase III: | Jul-99 | 108,480 |
| Phase IV: | Dec-01 | 108,480 |
| Phase V: | Jul-04 | 62,400 |
| Phase VI: | Nov-07 | 124,800 |
| Phase VII: | Jul-10 | 123,316 |
| Phase VIII: | Jun-18 | 149,891 |
| Phase IX: | Nov-21 | 159,744 |
| Total: |  | 1,139,952 |
| Amount requested for renewal (phase X) (US $): |  | 330,670 |
| Amount recommended for approval for phase X (US $): |  | 330,670 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase X to the Multilateral Fund (US $): |  | 330,670 |
| Date of approval of country programme: |  | 1993 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 8.3 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 400.7 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 1,215,970 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 2.08 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 2.08 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 1,326,577 |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 10,994,432 |
| Amount disbursed (as at December 2022) (US $): |  | 10,297,773 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 1,131.4 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 1,118.5 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 7,453,217 |
| (b) Institutional strengthening: | 1,139,952 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 2,401,264 |
| Total: | 10,994,432 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Under phase IX of the institutional strengthening (IS) project, Guatemala’s national ozone unit (NOU) worked to achieve broad consensus on revised national ODS legislation. Article 7 and country programme implementation data were submitted to the Ozone and Fund Secretariats, respectively, accurately and in a timely manner. The Congress of the Republic of Guatemala ratified the Kigali Amendment on January 11, 2024. NOU staff coordinated activities under the first and second tranches of stage II of the HCFC phase-out management plan (HPMP) and worked to prepare the request for preparation of stage I Kigali HFC implementation plan (KIP) to reduce 10 per cent of the country’s HFC baseline. Several training sessions for customs officers were organized and conducted during the phase. The country encouraged the continued participation of stakeholders in the implementation of the Montreal Protocol at the national level, organized awareness-raising activities and Ozone Day celebrations, as well as active participation in regional network meetings and events.

# Plan of action

- With the continued support of the IS project, Guatemala will continue implementing import/export licensing for all controlled substances and quota system for HCFCs. The HPMP and preparation of the KIP will be implemented to meet the HCFC phase-out and HFC phase-down targets, while ensuring gender mainstreaming in implementing of those projects. In addition, the NOU will continue coordination with customs to ensure an effective surveillance of international trade of all Montreal Protocol controlled substances, to fulfill the requirements of the HPMP and the Kigali Amendment and development of national capacities to allow the efficient implementation of all its provisions. The action plan also includes a strict monitoring and control of the imports and use of HCFCs/HFCs, as well as facilitating access to and use of new alternative substances and technologies. The NOU will continue public awareness activities especially with the education sector and with a gender focus during the World Refrigeration Day and Ozone Day celebrations as well as national events.

# Sustainability and risk assessment

- The Ministry of Environment and Natural Resources (MARN in Spanish) and the NOU seek integrating the concept of sustainability aspects in all activities that make up the IS project, through the strengthening of alliances and relationships with key stakeholders, including government entities involved in implementing the regulatory framework for the management of Montreal Protocol-controlled substances, development of policies and standards that promote the introduction and sustainability of non-HCFC and low-GWP alternative refrigerants and technologies. As has been seen, a wide range of government departments and institutions have been involved in the formulation and implementation of the IS project and HPMP, and assessment tools used in national reports have been integrated to identify the environmental, economic, and social effects and benefits for the country. In addition, MARN records the results of the project following the guidelines given by the Montreal Protocol, facilitating the consultation process when necessary. Guatemala ensures the incorporation of the gender perspective in the project implementation, and in general, pursues the necessary means to guarantee sustainability and reduce the risks.

# Guinea-Bissau: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Apr-03 and Jul-04 | 90,000 |
| Phase II: | Nov-06 | 60,000 |
| Phase III: | Jul-12 | 60,000 |
| Phase IV: | Nov-14 | 60,000 |
| Phase V: | Dec-16 | 84,892 |
| Phase VI: | May-19 | 85,000 |
| Phase VII: | Jul-21 | 85,000 |
| Total: |  | 524,892 |
| Amount requested for renewal (phase VIII) (US $): |  | 180,000 |
| Amount recommended for approval for phase VIII (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 2004 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 2.83 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.00 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 722,391 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 0.77 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 0.77 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 609,742 |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 1,958,360 |
| Amount disbursed (as at December 2022) (US $): |  | 1,733,919 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 27.2 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 21.7 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 124,161 |
| (b) Institutional strengthening: | 524,892 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,309,307 |
| Total: | 1,958,360 |
| (d) HFC activities funded from additional voluntary contributions | 95,000 |

# Progress report

- Guinea-Bissau's national ozone unit (NOU) successfully implemented phase VII of the institutional strengthening (IS) project, fully achieving five performance indicators, and partially achieving two others. The NOU gathered import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs) and submitted comprehensive country program and Article 7 data as required. Annual meetings with stakeholders, including the National Ozone Committee, were conducted to ensure efficient coordination. The NOU coordinated training sessions for 125 refrigeration and air-conditioning (RAC) technicians and 80 customs officers. Ongoing efforts focused on raising awareness about HCFC alternatives, relevant legislation, and regulatory frameworks. Additionally, Guinea-Bissau actively participated in observing Ozone Day and engaged in Protocol-related meetings.

# Plan of action

- Under phase VIII of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; planned submission and implementation of stage II of the HCFC phase-out management plan and the Kigali HFC implementation plan (KIP); promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; and preparation of the KIP strategy.

# Sustainability and risk assessment

- The successful implementation of the IS project in Guinea-Bissau relies on stable funding from the Multilateral Fund and a conducive political environment. Active participation from stakeholders, relevant associations, ministries, and agencies is crucial for developing recommendations and amendments to laws and regulations, as well as for conducting public awareness and promotional activities. The NOU is consistently guided by the National Ozone Steering Committee, which includes key line ministries, the RAC sector, and other pertinent agencies, amidst the country's political risks.

Lao People’s Democratic Republic: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Jul-01 | 74,580 |
| Phase II: | Jul-04 | 57,200 |
| Phase III: | Nov-06 | 60,000 |
| Phase IV: | Nov-08 | 60,000 |
| Phase V: | Jul-10 | 60,000 |
| Phase VI: | Jul-12 | 60,000 |
| Phase VII: | May-14 | 60,000 |
| Phase VIII: | May-16 | 85,000 |
| Phase IX: | Jun-18 | 85,000 |
| Phase X: | Jun-20 | 85,000 |
| Phase XI: | Dec-22 | 120,000 |
| Total: |  | 806,780 |
| Amount requested for renewal (phase XII) (US $): |  | 180,000 |
| Amount recommended for approval for phase XII (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XII to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 2001 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 2.3 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 324,226 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 1.43 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 1.43 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 293,334 |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 2,745,261 |
| Amount disbursed (as at December 2022) (US $): |  | 2,201,057 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 32.00 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 16.30 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 635,688 |
| (b) Institutional strengthening: | 806,780 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,302,793 |
| Total: | 2,745,261 |
| (d) HFC activities funded from additional voluntary contributions | 95,000 |

# Progress report

- The implementation of the institutional strengthening (IS) project phase XI supported Lao People’s Democratic Republic to ensure compliance with its HCFC phase-out obligations during the reporting period. Lao People’s Democratic Republic continued to enforce HCFC licensing system and HFC licensing system through the Ministry of Industry and Commerce. The country submitted its 2022 country programme and Article 7 data reports to the Fund and Ozone Secretariats respectively. However, there was delay in submitting both data reports as a result of the change of the national ozone unit (NOU) to the Department of Climate Change in late 2022. The new NOU worked closely with all stakeholders to resume implementation of activities of the HCFC phase-out management plan (HPMP), such as delivering training and preparation of stage I of the Kigali HFC implementation plan (KIP), which allowed project implementation to get back on track. The NOU included gender mainstreaming in implementation of the Montreal Protocol activities during the phase. The NOU also organized public awareness raising activities and actively joined the regional and global meetings on the Montreal Protocol.

# Plan of action

- Activities planned under phase XII include: implementing the HCFC and HFC licensing and quota system; continue work with customs to assign specific Harmonized System codes for HFCs under the 2022 version; timely submission of Article 7 and country programme data; active engagement of key stakeholders and the refrigeration and air-conditioning association in the implementation of the Montreal Protocol; coordination with stakeholders for the implementation of the HPMP and KIP; organization of  Ozone Day celebrations and development of awareness materials; and participation in regional and international meetings. Gender mainstreaming will be further integrated into implementation of phase XII of the IS project.

# Sustainability and risk assessment

- The IS project can be successfully implemented in Lao People’s Democratic Republic under conditions of stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. Given the risk of delay in implementation primarily due to the government restructuring, the NOU will need to work with its senior management in strengthening the organizational structure; this would involve clarifying the roles and responsibilities of the entities involved in the IS project, ensuring smooth operations despite governmental changes. Furthermore, there is a need to develop a succession plan to ensure that knowledge and expertise are retained within the NOU and related departments, even when key personnel change.

Maldives: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Mar-94 | 46,613 |
| Phase II: | Jul-02 | 35,753 |
| Phase III: | Dec-04 | 60,000 |
| Phase IV: | Nov-06 | 60,000 |
| Phase V: | Nov-08 | 60,000 |
| Phase VI: | Jul-10 | 60,000 |
| Phase VII: | Jul-12 | 60,000 |
| Phase VIII: | May-14 | 60,000 |
| Phase IX: | Dec-16 | 85,000 |
| Phase X: | Jun-18 | 75,000 |
| Phase XI: | Jun-20 | 85,000 |
| Phase XII: | Jun-22 | 85,000 |
| Total: |  | 772,366 |
| Amount requested for renewal (phase XIII) (US $): |  | 180,000 |
| Amount recommended for approval for phase XIII (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 1993 |
| Date of approval of HCFC phase-out management plan: |  | 2010 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 4.6 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 434,219 |
| Latest reported ODS consumption (2023) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0 |
| (b) Annex C, Group I (HCFCs) |  | 0 |
| (c) Annex E (methyl bromide) |  | 0 |
| Total: |  | 0 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 317,887 |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 3,136,691 |
| Amount disbursed (as at December 2022) (US $): |  | 2,796,955 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 5.21 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 2.90 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 544,147 |
| (b) Institutional strengthening: | 772,366 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,820,179 |
| Total: | 3,136,691 |
| (d) HFC activities funded from additional voluntary contributions | 95,000 |

# Progress report

- During phase XII of the institutional strengthening (IS) project, Maldives strictly implemented the licensing and quota system for HCFCs and HFCs through the Makudi system and enforced the control measures to sustain HCFC phase-out and measures undertaken to monitor illegal trade in ODS and HFCs, and equipment containing them. The national ozone unit (NOU) submitted Article 7 and country programme data reports for 2023 in a timely manner. The NOU continued to maintain the high awareness of key stakeholders and organized several meetings and awareness-raising activities including the celebration of Ozone Day. Customs brokers and new custom officers were regularly briefed and trained on the Montreal Protocol provisions and amendments, including the Kigali Amendment. Maldives worked with UNEP for the preparation of the Kigali HFC implementation plan, and the additional activities for enhancing energy efficiency. The NOU and relevant authorities participated in all relevant Montreal Protocol meetings during the reporting period.

# Plan of action

- During the upcoming phase, the NOU will continue to monitor data and enforce the online quota and licensing system for HCFC and HFCs. The NOU will focus on the data collection of HFCs and its sectoral distribution to better design the HFC phase-down activities and fulfill HFC phase-down obligations in the upcoming years. In doing so, the NOU will closely cooperate with national stakeholders, build the capacity of customs and enforcement officers on the trade control of the substances controlled under the Montreal Protocol, support the refrigeration and air-conditioning association and its activities, collect trade data of the controlled substances from various sources and cross check them on regular basis, and submit necessary data reports to the Ozone and the Multilateral Fund Secretariats in a timely manner. The NOU will participate in all international and regional activities to be held during the phase and will organize awareness-raising activities to sensitize targeted/sector specific audiences as well as the general public on the Montreal Protocol issues.

# Sustainability and risk assessment

- The IS project can be successfully implemented in Maldives under conditions of stable funding from the Multilateral Fund. As for the IS project implemented in Maldives, stakeholders, relevant associations, and ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. There is an active advisory committee, although its composition needs to be reconfirmed following recent elections in the country.

Morocco: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | May-96 | 202,270 |
| Phase II: | Jul-04 | 155,000 |
| Phase III: | Nov-07 | 117,820 |
| Phase IV: | Nov-09 | 0 |
| Total: |  | 475,090 |
| Amount requested for renewal (phase V) (US $): |  | 413,338 |
| Amount recommended for approval for phase V (US $): |  | 413,338 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase V to the Multilateral Fund (US $): |  | 413,338 |
| Date of approval of country programme: |  | 1996 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex A, Group I (CFCs) (average 1995-1997) |  | 802.30 |
| (b) Annex A, Group II (halons) (average 1995-1997) |  | 7.00 |
| (c) Annex B, Group II (carbon tetrachloride) (average 1998-2000) |  | 1.10 |
| (d) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.10 |
| (e) Annex C, Group I (HCFCs) (average 2009-2010) |  | 51.35 |
| (f) Annex E (methyl bromide) (average 1995-1998) |  | 697.20 |
| (g) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 2,134,190 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex A, Group I (CFCs) |  | 0 |
| (b) Annex A, Group II (halons) |  | 0 |
| (c) Annex B, Group II (carbon tetrachloride) |  | 0 |
| (d) Annex B, Group III (methyl chloroform) |  | 0 |
| (e) Annex C, Group I (HCFCs) |  | 19.84 |
| (f) Annex E (methyl bromide) |  | 0 |
| Total: |  | 19.84 |
| (g) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 589,312 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 20,739,958 |
| Amount disbursed (as at December 2022) (US $): |  | 19,374,835 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 1454.7 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 1425.4 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 17,351,095 |
| (b) Institutional strengthening: | 475,090 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 2,913,772 |
| Total: | 20,739,958 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Despite its challenges, Morocco has successfully implemented all its programmes and activities under the Montreal Protocol on the protection of the ozone layer. The implementation of the institutional strengthening project was halted due to the administrative issues in processing funds at the national level. At present, all issues are resolved, and the country is ready to resume the work. During the reporting period, the national ozone unit (NOU) of Morocco implemented activities under stages I and II of the HCFC phase-out management plan (HPMP). The NOU enforced the ODS regulations through the implementation of the licensing and quota system; it further embarked on an awareness-raising programme, trained customs officers, and refrigeration technicians.

# Plan of action

- Under phase V, the Government of Morocco will continue to support activities to phase out HCFCs and promote Montreal Protocol activities. The NOU will organize steering committee meetings to support the NOU with the implementation of activities. The following actions will be undertaken during the new phase: continue to strengthen coordination within the NOU; continue to implement the licensing and quota system for HCFCs and begin the implementation of a licensing and quota system for HFCs; continue to coordinate and monitor programme activities under stage II of the HPMP and prepare and submit the first stage of the Kigali HFC implementation plan, as well as the investment project in the refrigeration manufacturing sector for MANAR; work closely with stakeholders in the refrigeration servicing sector including capacity development; and implement public awareness campaigns through virtual and print media. During the phase, the NOU will maintain its timely country programme and Article 7 data reporting and will maintain active participation in the meetings related to the Montreal Protocol and the promotion of women's participation in the refrigeration servicing sector.

# Sustainability and risk assessment

- The IS project can be successfully implemented in Morocco as the Government has expressed full support for the project. Stakeholders, relevant associations, ministries, and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the national ozone committee which comprises of key inline ministries, the refrigeration and air-conditioning sector and other relevant agencies. It is crucial that the NOU strengthens cooperation with customs in monitoring HFCs through targeted awareness for importers and customs brokers on identifying HFCs being imported with their proper HS codes.

Niger (the): Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Dec-94 | 84,524 |
| Phase II: | Nov-98 | 56,500 |
| Phase III: | Mar-01 | 56,500 |
| Phase IV: | Dec-03 | 64,827 |
| Phase V: | Nov-05 | 64,827 |
| Phase VI | Nov-07 | 64,282 |
| Phase VII: | Nov-09 | 64,828 |
| Phase VIII: | Nov-11 | 64,828 |
| Phase IX: | Dec-13 | 64,828 |
| Phase X: | Nov-15 | 85,000 |
| Phase XI: | Nov-17 | 84,838 |
| Phase XII: | Dec-19 | 85,000 |
| Phase XIII: | Jun-22 | 85,000 |
| Total: |  | 925,782 |
| Amount requested for renewal (phase XIV) (US $): |  | 180,000 |
| Amount recommended for approval for phase XIV (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 1994 |
| Date of approval of HCFC phase-out management plan: |  | 2012 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 15.98 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.00 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 1,222,358 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 7.47 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 7.47 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 813,172 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 3,532,154 |
| Amount disbursed (as at December 2022) (US $): |  | 2,720,336 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 106.5 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 40.6 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 757,886 |
| (b) Institutional strengthening: | 925,782 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,848,486 |
| Total: | 3,532,154 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Niger’s national ozone unit (NOU) successfully implemented phase XIII of the institutional strengthening (IS) project, fully achieving five out of seven performance indicators, with two partially achieved. The NOU collected import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs) and submitted comprehensive country program and Article 7 data. Annual meetings with stakeholders, including the national ozone committee, were conducted to ensure efficient coordination. The NOU coordinated training sessions for 270 refrigeration and air-conditioning (RAC) technicians and 162 customs officers. Ongoing efforts focused on raising awareness about HCFC alternatives, relevant legislation, and regulatory frameworks. Additionally, Niger participated in observing Ozone Day and engaged in Protocol-related meetings.

# Plan of action

- Under Phase XIV of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HCFC phase-out management plan and stage I of the Kigali HFC implementation plan; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; and timely data collection and reporting to the Ozone and Fund Secretariats.

Sustainability and risk assessment

- The successful implementation of the IS project in Niger relies on stable funding from the Multilateral Fund. Active participation from stakeholders, relevant associations, ministries, and agencies is crucial for developing recommendations and amendments to laws and regulations, as well as for conducting public awareness and promotional activities. The NOU is consistently guided by the National Ozone Steering Committee, which includes key line ministries, the refrigeration and RAC sector, and other pertinent agencies.

Qatar: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Mar-99 | 72,500 |
| Phase II: | Dec-03 & Jul-06 | 92,521 |
| Phase III: | Nov-09 | 94,611 |
| Phase IV: | Jul-17 | 90,733 |
| Phase V: | Jun-20 | 113,920 |
| Phase VI: | Jun-22 | 113,920 |
| Total: |  | 578,205 |
| Amount requested for renewal (phase VII) (US $): |  | 235,814 |
| Amount recommended for approval for phase VII (US $): |  | 235,814 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase VII to the Multilateral Fund (US $): |  | 235,814 |
| Date of approval of country programme: |  | 1999 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 86.9 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | Not available |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0 |
| (b) Annex C, Group I (HCFCs) |  | 56.44 |
| (c) Annex E (methyl bromide) |  | 0 |
| Total: |  | 56.44 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | Not available |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 3,855,888 |
| Amount disbursed (as at December 2022) (US $): |  | 3,103,481 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 125.2 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 122 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 1,679,028 |
| (b) Institutional strengthening: | 578,205 |
| (c) Project preparation, technical assistance, training and other non-investment projects*: | 1,598,655 |
| Total: | 3,855,888 |
| (d) HFC activities funded from additional voluntary contributions | 0 |

# * Includes US $150,000 for HFC phase-down enabling activities.

# Progress report

- Qatar’s national ozone unit (NOU) successfully implemented phase VI of the institutional strengthening (IS) project and fully achieved six performance indicators while one was partially achieved. During the phase, Qatar implemented ODS control measures and efficiently operated electronic HCFC licensing and quota system. The NOU has undertaken HCFCs data collection, processing and reporting. All required reports were submitted on time. The NOU participated in the Montreal Protocol meetings and regional network meetings. The NOU also conducted an awareness-raising campaign and information dissemination activities to facilitate full engagement of all stakeholders in order to enable a smooth implementation of the phase-out programme.

# Plan of action

- Under the upcoming phase, the NOU will continue to work with all stakeholders including academia to ensure their full engagement in implementing the Montreal Protocol funded activities. The NOU will continue the operation of the e-licensing and quota system to ensure full compliance and combat illegal trade. It will also enforce the updated licensing and quota system that includes HFCs as required under the Kigali Amendment, facilitate the ratification process of the Kigali Amendment and pursue efforts to identify feasible alternatives suitable for the high ambient temperature countries. The NOU will intensify its efforts to ensure the proper implementation of stage II of the HCFC phase-out management plan (HPMP) to achieve the upcoming phase-out targets and will continue producing public and industry awareness and preparing Montreal Protocol reports.

# Sustainability and risk assessment

- The main risk would be the delayed ratification of the Kigali Amendment and adoption of feasible alternatives for high ambient temperature conditions. UNEP’s Compliance Assistance Programme will continue to provide all required support to facilitate the process for the ratification of the Kigali Amendment and thus support the country to prepare and adopt all required policies, regulations, and standards to facilitate full compliance. Support will also continue to ensure timely implementation of the ongoing stage II of the HPMP and facilitate the approval of the third tranche under stage II in order to achieve the planned phase-out targets and lay the ground for introducing new alternatives.

Sao Tome and Principe: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Nov-02 | 30,000 |
| Phase II: | Dec-04 & Nov-06 | 100,666 |
| Phase III: | Apr-11 | 60,225 |
| Phase IV: | Dec-13 | 60,666 |
| Phase V: | May-16 | 85,000 |
| Phase VI: | Dec-18 | 84,876 |
| Phase VII: | Jul-21 | 85,000 |
| Total: |  | 506,433 |
| Amount requested for renewal (phase VIII) (US $): |  | 180,000 |
| Amount recommended for approval for phase VIII (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 2004 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 2.2 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.0 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 71,039 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 0.05 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 0.05 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 28,907 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 1,740,019 |
| Amount disbursed (as at December 2022) (US $): |  | 1,474,210 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 4.8 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 2.5 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 124,564 |
| (b) Institutional strengthening: | 506,433 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 1,109,023 |
| Total: | 1,740,019 |
| (d) HFC activities funded from additional voluntary contributions | 95,000 |

# Progress report

- Sao Tome and Principe's national ozone unit (NOU) successfully implemented phase VII of the institutional strengthening (IS) project, successfully achieving four out of seven performance indicators, with three partially achieved. The NOU collected import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs) and submitted comprehensive country program and Article 7 data. Annual meetings with stakeholders, including the National Ozone Committee, were conducted to ensure efficient coordination. The NOU organized training sessions for 14 customs agents, 15 refrigeration technicians, 19 customs tax police officers, five importing companies, and 49 stakeholders, including technicians from the General Directorate of the Environment, representatives from hospitals, and training centres, were trained on the monitoring and identification of ODS as well as on good refrigeration practices and safety related to the use of hydrocarbons. Ongoing efforts were focused on raising awareness about HCFC alternatives, relevant legislation, and regulatory frameworks. Additionally, Sao Tome and Principe participated in observing Ozone Day and engaged in Protocol-related meetings.

# Plan of action

- Under phase VIII of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HCFC phase-out management plan; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; and preparation of the Kigali HFC implementation plan strategy.

# Sustainability and risk assessment

- The successful implementation of the IS project in Sao Tome and Principe relies on stable funding from the Multilateral Fund. Active participation from stakeholders, relevant associations, ministries, and agencies is crucial for developing recommendations and amendments to laws and regulations, as well as for conducting public awareness and promotional activities. The NOU is consistently guided by the National Ozone Steering Committee, which includes key line ministries, the refrigeration and air-conditioning sector, and other pertinent agencies.

Saudi Arabia: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Nov-07 | 250,000 |
| Phase II: | Jul-12 | 200,000 |
| Phase III: | Jun-22 | 256,000 |
| Total: |  | 706,000 |
| Amount requested for renewal (phase IV) (US $): |  | 529,920 |
| Amount recommended for approval for phase IV (US $): |  | 529,920 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase IV to the Multilateral Fund (US $): |  | 529,920 |
| Date of approval of country programme: |  | 2007 |
| Date of approval of HCFC phase-out management plan: |  | 2012 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex A, Group I (CFCs) (average 1995-1997) |  | 1,798.5 |
| (b) Annex A, Group II (halons) (average 1995-1997) |  | 1,064.0 |
| (c) Annex B, Group II (carbon tetrachloride) (average 1998-2000) |  | 259.2 |
| (d) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 29.8 |
| (e) Annex C, Group I (HCFCs) (average 2009-2010) |  | 1,468.7 |
| (f) Annex E (methyl bromide) (average 1995-1998) |  | 204.1 |
| (g) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | Not available |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex A, Group I (CFCs) |  | 0 |
| (b) Annex A, Group II (halons) |  | 0 |
| (c) Annex B, Group II (carbon tetrachloride) |  | 0 |
| (d) Annex B, Group III (methyl chloroform) |  | 0 |
| (e) Annex C, Group I (HCFCs) |  | 876 |
| (f) Annex E (methyl bromide) |  | 0 |
| Total: |  | 876 |
| (g) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | Not available |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 13,753,975 |
| Amount disbursed (as at December 2022) (US $): |  | 13,230,841 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 1,158.79 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 1,060.60 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 9,279,163 |
| (b) Institutional strengthening: | 706,000 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 3,768,812 |
| Total: | 13,753,975 |
| (d) HFC activities funded from additional voluntary contributions | 0 |

# Progress report

- Saudi Arabia’s national ozone unit (NOU) successfully implemented phase III of the institutional strengthening (IS) project. During the phase, the NOU integrated the e-licensing and quota system with customs system to strengthen supervision on ODS trade, included HFCs into the system, and enhanced procedures of quota distribution by including a QR code. The NOU developed eight standard operating procedures for the issued executive regulation (ER) to implement and enforce all control measures. The NOU facilitated the completion of the remaining activities of stage I of the HCFC phase-out management plan (HPMP) to achieve smooth transition between stage I and II and started the implementation of the preparation project for stage II of the HPMP. The NOU held many workshops with governmental and private stakeholders to raise awareness and enhance compliance with the Protocol; provided training to environmental inspectors of the National Center for Environmental Compliance; and raised awareness on Montreal Protocol by publishing content on social media, distributing brochures, and participating in expositions.

Plan of action

- Saudi Arabia will continue effective coordination with all stakeholders to ensure full compliance to the Montreal Protocol and ensure their full engagement and facilitation of the ongoing Multilateral Fund-funded projects. The NOU will continue effective enhancement of the e-licensing and quota system to improve control measures and to comply with the reporting requirement. The NOU will continue to hold workshops to train customs officers in cooperation with the customs academy; industrial workshops will also be held to explore and evaluate the current challenges to adopt the HFC phase-down, as well as workshops to raise awareness of Montreal Protocol. The NOU aims for a smooth implementation and early ratification of the Kigali Amendment and smooth transition between stages I and II of the HPMP which is being submitted for consideration at the 94th meeting of the Executive Committee. The NOU will continue active participation in all regional thematic and network meetings.

# Sustainability and risk assessment

- The main risk would be the delayed ratification of the Kigali Amendment and adoption of feasible alternatives for high ambient temperature conditions. UNEP’s Compliance Assistance Programme will continue to provide all required support to facilitate the process for the ratification of the Kigali Amendment and thus support the country to prepare and adopt all required policies, regulations, and standards to facilitate full compliance. Support will also continue to ensure timely implementation of stage II of the HPMP once approved in order to achieve the planned phase-out targets and lay the ground for introducing new alternatives.

Senegal: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Nov-93 | 197,750 |
| Phase II: | Nov-97 | 132,210 |
| Phase III: | Nov-99 | 132,210 |
| Phase IV: | Mar-02 | 152,100 |
| Phase V: | Dec-03 | 152,100 |
| Phase VI: | Nov-05 | 152,100 |
| Phase VII: | Nov-07 | 152,100 |
| Phase VIII: | Nov-09 | 152,101 |
| Phase IX: | Nov-11 | 152,101 |
| Phase X: | Dec-13 | 152,101 |
| Phase XI: | Nov-15 | 194,689 |
| Phase XII: | Nov-17 | 194,689 |
| Phase XIII: | Dec-19 | 194,689 |
| Phase XIV: | Nov-21 | 194,689 |
| Total: |  | 2,305,629 |
| Amount requested for renewal (phase XV) (US $): |  | 403,007 |
| Amount recommended for approval for phase XV (US $): |  | 403,007 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase XV to the Multilateral Fund (US $): |  | 403,007 |
| Date of approval of country programme: |  | 1993 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 36.2 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 53.2 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 2,664,194 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 10.67 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 10.67 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 1,930,179 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 5,237,838 |
| Amount disbursed (as at December 2022) (US $): |  | 4,585,718 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 196.3 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 148.1 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 915,763 |
| (b) Institutional strengthening: | 2,305,629 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 2,016,447 |
| Total: | 5,237,838 |
| (d) HFC activities funded from additional voluntary contributions | 150,000 |

# Progress report

- Senegal's national ozone unit (NOU) successfully implemented phase XIV of the institutional strengthening (IS) project, fully achieving six out of seven performance indicators. The NOU collected import data on ozone-depleting substances (ODS) and hydrofluorocarbons (HFCs) and submitted comprehensive country program and Article 7 data. Annual meetings with stakeholders, including the National Ozone Committee, were conducted to ensure efficient coordination. The NOU organized training sessions for 150 refrigeration and air-conditioning (RAC) technicians and 125 customs officers. Ongoing efforts were focused on raising awareness about HCFC alternatives, relevant legislation, and regulatory frameworks. Additionally, Senegal participated in observing Ozone Day and engaged in Protocol-related meetings.

# Plan of action

- Under phase XV of the IS project, the NOU will concentrate on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HCFC phase-out management plan (HPMP); promoting and enforcing the licensing and quota system, providing importers with annual quota information; working with customs to monitor the legal trade of ODS/HFC; establishing the technician certification program; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; preparation of the Kigali HFC implementation Plan (KIP) strategy; and continuing its efforts to integrate gender mainstreaming into the implementation of the IS project.

# Sustainability and risk assessment

- The successful implementation of the IS project in Senegal relies on stable funding from the Multilateral Fund. Active participation from stakeholders, relevant associations, ministries, and agencies is crucial for developing recommendations and amendments to laws and regulations and conducting public awareness and promotional activities. The NOU consistently follows the guidance of the National Ozone Steering Committee, comprising the ministries involved, the RAC sector, and other relevant agencies.

South Africa: Request for institutional strengthening project

| Summary of the project and country profile |  |
| --- | --- |
| Implementing agency: | UNEP |
| Amount requested for phase I (US $): | 500,000 |
| Amount recommended for approval for phase I (US $): | 500,000 |
| Agency support costs (US $): | 0 |
| Total cost of institutional strengthening phase I to the Multilateral Fund (US $): | 500,000 |
| Date of approval of country programme: | n/a |
| Date of approval of HCFC phase-out management plan: | 2012 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |
| (a) Annex A, Group I (CFCs) (average 1995-1997) | 592.6 |
| (b) Annex A, Group II (halons) (average 1995-1997) | 0.0 |
| (c) Annex B, Group II (carbon tetrachloride) (average 1998-2000) | 0.0 |
| (d) Annex B, Group III (methyl chloroform) (average 1998-2000) | 0.0 |
| (e) Annex C, Group I (HCFCs) (average 2009-2010) | 369.7 |
| (f) Annex E (methyl bromide) (average 1995-1998) | 602.7 |
| (g) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) | 13,843,139 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |
| (a) Annex A, Group I (CFCs) | 0.0 |
| (b) Annex A, Group II (halons) | 0.0 |
| (c) Annex B, Group II (carbon tetrachloride) | 0.0 |
| (d) Annex B, Group III (methyl chloroform) | 0.0 |
| (e) Annex C, Group I (HCFCs) | 73.8 |
| (f) Annex E (methyl bromide) | 0.0 |
| Total: | 73.8 |
| (g) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 | 8,647,454 |
| Year of reported country programme implementation data: | 2023 |
| Amount approved for projects (as at December 2023) (US $): | 11,746,102 |
| Amount disbursed (as at December 2022) (US $): | 7,157,152 |
| ODS to be phased out (as at December 2023) (ODP tonnes): | 243.1 |
| ODS phased out (as at December 2022) (ODP tonnes): | 176.7 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 8,806,456 |
| (b) Institutional strengthening: | - |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 2,939,646 |
| Total: | 11,746,102 |
| (d) HFC activities funded from additional voluntary contributions | 240,000 |

# Plan of action

- South Africa’s national ozone unit (NOU) is located within the Department of Forestry, Fisheries and the Environment. The NOU is currently developing its Kigali HFC implementation plan and it will implement it to ensure sustained compliance with Montreal Protocol reduction targets. Under the IS project, the NOU will review and approach the key national stakeholders for formal cooperation/partnership for effective implementation of the Montreal Protocol; reorganize the National Steering Committee and coordinate stakeholder meetings; strengthen its collaboration with ITAC and customs for the effective implementation and enforcement of the quota and licensing system for import and export of the controlled substances; regular data collection and verification for timely submission of country programme and Article 7 data reports; as well as organizing various stakeholder outreach and awareness activities including celebration of the Ozone Day. South Africa also plans to host Southern African Development Community (SADC) workshops to facilitate discussions around uniform requirements and trainings of informal servicing technicians within the SADC region. The NOU will develop and distribute various types of awareness materials, such as flyers, brochures, pamphlets to be distributed at these organized events and others to the industry and other stakeholders.

# Sustainability and risk assessment

- South Africa is currently phasing out HCFC by controlling HCFC import and export using the permit and quota systems. This is achieved in collaboration with ITAC and customs officials. The Ministry of Forestry Fisheries and the Environment will continue to submit annual Article 7 and country programme data as evidence of progress in the phase-down of HFCs and phase-out of HCFCs. Awareness raising activities will be prioritized to facilitate the progressive phase-out of ODS and HFC refrigerants.

South Sudan: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Start-up: | Dec-12 | 40,000 |
| Phase I: | May-16 | 85,000 |
| Total: |  | 125,000 |
| Amount requested for renewal (phase II) (US $): |  | 180,000 |
| Amount recommended for approval for phase II (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase II to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | n/a |
| Date of approval of HCFC phase-out management plan: |  | 2016 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | - |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 4.1 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.7 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 221,410 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0.00 |
| (b) Annex C, Group I (HCFCs) |  | 1.24 |
| (c) Annex E (methyl bromide) |  | 0.00 |
| Total: |  | 1.24 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 60,060 |
| Year of reported country programme implementation data: |  | 2023 |
| Amount approved for projects (as at December 2023) (US $): |  | 472,943 |
| Amount disbursed (as at December 2022) (US $): |  | 220,479 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 0.5 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 0 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 54,500 |
| (b) Institutional strengthening: | 125,000 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 293,443 |
| Total: | 472,943 |
| (d) HFC activities funded from additional voluntary contributions | 95,000 |

# Progress report

- The implementation of the Montreal Protocol activities in South Sudan is commendable, despite the numerous challenges the country faces. During the reporting period, the national ozone unit (NOU) has satisfactorily implemented the required activities under the first phase of its institutional strengthening (IS) project. The NOU has successfully built local capacity in areas such as policy development, regulatory enforcement, and technology transfer. In particular, the NOU implemented the following activities: enforced the HCFC licensing and quota system; trained customs and enforcement officers; compiled and reported ODS consumption to the Fund and the Ozone Secretariats; and joined the rest of the world in celebrating the annual Ozone Day.

# Plan of action

- The activities planned for the second phase of the IS project for South Sudan will focus on activities aimed at promoting HCFC phase-out. Focus will also be placed on the Kigali Amendment, leading to the phase-down of HFCs. Strategic public awareness activities through stakeholders’ workshops, promotional materials, celebration of Ozone Day, will be carried out. In addition, the NOU will continue to monitor program activities under stage I of the HCFC phase-out management plan and continue the enforcement of the regulations on controlled substances under the Montreal Protocol, as well as carry out the training of relevant personnel connected with the phase-out process, among others. The Government will continue with awareness-raising programmes, training of refrigeration and air-conditioning technicians, customs officers and implementing a licensing and quota system for HCFCs to meet and sustain the 67.5 per cent reduction in 2025.

# Sustainability and assessment

- Two employees of the Government of South Sudan are tasked with the responsibility of monitoring the project and reporting on any issues that may affect the continued operation of the project. The IS project is subjected to periodic internal and external audits to ensure adequate risk avoidance and management.

# Vanuatu: Renewal of institutional strengthening

| Summary of the project and country profile |  |  |
| --- | --- | --- |
| Implementing agency: |  | UNEP |
| Amounts previously approved for institutional strengthening (US $): |  |  |
| Phase I: | Mar-02 | 20,250 |
| Phase II: | Apr-08 & Nov-09 | 39,250 |
| Phase III: | Dec-10 | 60,000 |
| Phase IV: | Jul-12 | 60,000 |
| Phase V: | May-14 | 60,000 |
| Phase VI: | Dec-16 | 85,000 |
| Phase VII: | Dec-19 | 80,000 |
| Phase VIII: | Nov-21 | 85,000 |
| Total: |  | 489,500 |
| Amount requested for renewal (phase IX) (US $): |  | 180,000 |
| Amount recommended for approval for phase IX (US $): |  | 180,000 |
| Agency support costs (US $): |  | 0 |
| Total cost of institutional strengthening phase IX to the Multilateral Fund (US $): |  | 180,000 |
| Date of approval of country programme: |  | 2002 |
| Date of approval of HCFC phase-out management plan: |  | 2011 |
| Baseline consumption of controlled substances (ODP tonnes/CO2-eq tonnes): |  |  |
| (a) Annex B, Group III (methyl chloroform) (average 1998-2000) |  | 0.0 |
| (b) Annex C, Group I (HCFCs) (average 2009-2010) |  | 0.3 |
| (c) Annex E (methyl bromide) (average 1995-1998) |  | 0.2 |
| (d) Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline) |  | 20,482 |
| Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7: |  |  |
| (a) Annex B, Group III (methyl chloroform) |  | 0 |
| (b) Annex C, Group I (HCFCs) |  | 0 |
| (c) Annex E (methyl bromide) |  | 0 |
| Total: |  | 0 |
| (d) Annex F (HFCs) (CO2-eq tonnes) as per Article 7 |  | 17,511 |
| Year of reported country programme implementation data: |  | 2022 |
| Amount approved for projects (as at December 2023) (US $): |  | 1,045,987 |
| Amount disbursed (as at December 2022) (US $): |  | 723,949 |
| ODS to be phased out (as at December 2023) (ODP tonnes): |  | 0.3 |
| ODS phased out (as at December 2022) (ODP tonnes): |  | 0.0 |

- Summary of activities and funds approved by the Executive Committee:

| Summary of activities | Funds approved (US $) |
| --- | --- |
| (a) Investment projects: | 0 |
| (b) Institutional strengthening: | 489,500 |
| (c) Project preparation, technical assistance, training and other non-investment projects: | 556,487 |
| Total: | 1,045,987 |
| (d) HFC activities funded from additional voluntary contributions | 50,000 |

# Progress report

- Phase VIII of the institutional strengthening (IS) project in Vanuatu progressed despite a setback in 2023. The NOU fully achieved six out of seven performance indicators. Vanuatu also fulfilled its data reporting obligations to the Ozone and Fund Secretariats in a timely manner and has sustained compliance with the HCFC reduction targets. The National Ozone Officer (NOO) worked in close collaboration with the Department of Customs in the implementation of the HCFC/HFC licensing system through the Vanuatu National Single Window system. In addition, Vanuatu celebrated Ozone Day and continued to disseminate information on the protection of the ozone layer and the national law. The implementation of national activities to support compliance management is ongoing with the full support of senior management and the new NOO Assistant. The key achievements during this reporting period also include the successful completion of the third tranche stage I of the HCFC phase-out management plan (HPMP).

# Plan of action

- Under phase IX activities will include: implementing the HFC licensing and quota system; amendment of the Ozone Layer Protection Act and Regulations; timely submission of Article 7 and country programme data; active engagement of key stakeholders and the refrigeration and air-conditioning (RAC) association in the implementation of the Montreal Protocol; coordination with stakeholders for the implementation of the HPMP and Kigali HFC implementation plan; organization of Ozone Day and development of awareness-raising materials; and participation in regional and international meetings. Gender mainstreaming will be integrated into implementation of the upcoming phase of the IS project.

# Sustainability and assessment

- The IS project can be successfully implemented in Vanuatu under conditions of stable funding from the Multilateral Fund. Stakeholders, relevant associations, ministries, and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the key inline ministries, the RAC sector and other relevant agencies. Although there were setbacks in the project implementation in 2023, there are no foreseen risks under phase IX.

### المرفق الثاني

- مسودة الآراء التي أعربت عنها اللجنة التنفيذية المعنية بتجديد مشروعات التعزيز المؤسسي 
المقدمة إلى الاجتماع الرابع والتسعين

- البحرين

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للبحرين (المرحلة الثانية عشرة) وأشارت مع التقدير إلى تقديم البيانات لعامي 2021 و2022 إلى أمانة الأوزون، مما يدل على الامتثال لبروتوكول مونتريال. وأقرت اللجنة أيضا بالتقدم الكبير الذي أحرزته البحرين في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع، لا سيما من خلال إنفاذ ضوابط على واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أقرت اللجنة بجهود البحرين في تقليل استهلاك الهيدروكلوروفلوروكربون، وتتوقع استمرار تنفيذ البلاد الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي، الذي يهدف إلى خفض استهلاك الهيدروكلوروفلوروكربون بنسبة 67.5 في المائة بحلول 1 يناير/كانون الثاني 2025.

- بوروندي

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لبوروندي المرحلة العاشرة) وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون مما يُثبت امتثال البلد لبروتوكول مونتريال. وأقرت اللجنة أيضا بالتقدم الكبير الذي أحرزته بوروندي في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون أثناء فترة المشروع، ولا سيما من خلال إنفاذ ضوابط على واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أقرت اللجنة بجهود بوروندي المبذولة في الحد من استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي لديها، بهدف خفض استهلاك المواد الهيدروكلوروفلوروكربونية بنسبة 67.5 في المئة بحلول 1 يناير/كانون الثاني 2025.

- الكاميرون

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للكاميرون (المرحلة الرابعة عشرة) وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون، مما يُثبت امتثال البلد لبروتوكول مونتريال. وأقرت اللجنة أيضا بالتقدم الكبير الذي أحرزته الكاميرون في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون أثناء فترة المشروع، ولا سيما من خلال تنفيذ ضوابط على واردات المواد المستنفذة للأوزون من خلال نظام التراخيص والحصص، وتدريب موظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أقرت اللجنة بجهود الكاميرون المبذولة في الحد من استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية و وتنفيذ خطة كيغالي لتنفيذ المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي لديها، بهدف خفض استهلاك المواد الهيدروكلوروفلوروكربونية بنسبة 67.5 في المئة بحلول 1 يناير/كانون الثاني 2025.

- تشاد

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لتشاد (المرحلة الحادية عشرة) وأشارت مع التقدير إلى تقديم بيانات المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية لعامي 2021 و2022 إلى أمانة صندوق والأوزون، مما يشير إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وأقرت اللجنة أيضا بالتقدم الكبير الذي أحرزته تشاد في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية خلال فترة المشروع. وعلى وجه التحديد، قامت تشاد بفرض ضوابط على واردات المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وأشارت اللجنة إلى الجهود التي تبذلها تشاد لخفض استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي، الذي يهدف إلى تحقيق تخفيض بنسبة 65 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2025، على النحو المنصوص عليه في بروتوكول مونتريال.

- جزر القمر

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لجزر القمر (المرحلة الثالثة عشرة) وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون، مشيرة إلى أن البلاد ممتثلة لبروتوكول مونتريال. وأقرت اللجنة التنفيذية  بالجهود التي تبذلها جزر القمر للتخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع، ولا سيما إنفاذ التدابير الصارمة المطبقة للتحكم في واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص، إلى جانب التدريب الشامل المقدم لموظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أحاطت اللجنة علما بمبادرات جزر القمر الرامية إلى الحد من استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية. وتأمل اللجنة أن تواصل حكومة جزر القمر تنفيذ مشروع التعزيز المؤسسي بنجاح للحفاظ على إنجازات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية والامتثال للتخفيض التدريجي للمواد الهيدروفلوروكربونية على النحو المنصوص عليه في تعديل كيغالي.

- الكونغو

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للكونغو (المرحلة الثانية عشرة) وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون، مما يشير إلى أن البلاد ممتثلة لبروتوكول مونتريال. وأقرت اللجنة أيضا بالتقدم الذي أحرزته الكونغو في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع، ولا سيما من خلال إنفاذ ضوابط على واردات المواد المستنفدة للأوزون عن طريق نظام التراخيص والحصص وتدريب موظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أشارت اللجنة إلى جهود الكونغو في الحد من استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي، بهدف خفض استهلاك المواد الهيدروكلوروفلوروكربونية بنسبة 67.5 في المائة بحلول 1 يناير/كانون الثاني 2025.

- جمهورية الكونغو الديمقراطية

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لجمهورية الكونغو الديمقراطية (المرحلة الحادية عشرة) وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. واعترفت اللجنة أيضا بالتقدم الكبير الذي أحرزته جمهورية الكونغو الديموقراطية في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع. وعلى وجه التحديد، قامت جمهورية الكونغو الديمقراطية بفرض ضوابط على واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وأشارت اللجنة إلى الجهود التي تبذلها جمهورية الكونغو الديمقراطية لخفض استهلاك المواد الهيدروكلوروفلوروكربونية وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي، الذي يهدف إلى تحقيق تخفيض بنسبة 65 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2025، على النحو المنصوص عليه في بروتوكول مونتريال.

- غواتيمالا

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لغواتيمالا (المرحلة العاشرة) وأشارت مع التقدير إلى أن البلد قد امتثل لإبلاغ البيانات والتزامات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية بموجب بروتوكول مونتريال، وأعربت عن سرورها للتصديق على تعديل كيغالي الذي جرى في يناير/كانون الثاني 2024. وأشارت اللجنة إلى أن وحدة الأوزون الوطنية قامت بتنسيق الأنشطة في إطار المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ونظمت وعقدت عدة دورات تدريبية لموظفي الجمارك. وأشارت اللجنة أيضا إلى المشاركة المستمرة لأصحاب المصلحة لدى البلد في تنفيذ بروتوكول مونتريال على المستوى الوطني، وإجراء أنشطة إذكاء الوعي والاحتفالات بيوم الأوزون، فضلا عن المشاركة النشطة في الشبكات والفعاليات الإقليمية.

- غينيا - بيساو

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لغينيا - بيساو (المرحلة الثامنة) وأشارت مع التقدير تقديم بيانات عامي 2021 و2022 إلى أمانتي الأوزون والصندوق المتعدد الأطراف، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وأقرت اللجنة أيضا بالتقدم الذي أحرزته غينيا - بيساو في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون أثناء فترة المشروع، ولا سيما من خلال إنفاذ ضوابط واردات المواد المستنفدة للأوزون عن طريق نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وأشادت اللجنة بغينيا بيساو لجهودها الرامية إلى الحد من استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتوقع استمرار نجاح البلاد في تنفيذ استراتيجياتها، بما في ذلك خططها لتحقيق خفض بنسبة 67.5 في المائة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/كانون الثاني 2025.

- جمهورية لاو الديمقراطية الشعبية

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لجمهورية لاو الديمقراطية الشعبية (المرحلة الثانية عشرة) وأشارت مع التقدير إلى أن حكومة جمهورية لاو الديمقراطية الشعبية استخدمت مشروع التعزيز المؤسسي لاستئناف التشغيل وتسريع تنفيذ المشروع لتعويض تأخر تنفيذ المشروع خلال الفترة الانتقالية. ولاحظت اللجنة أن بيانات البرنامج القطري لعام 2022 وبيانات المادة 7 تشير إلى أن البلد ممتثل لبروتوكول مونتريال والتزم بشكل مستمر بالحد الأقصى للاستهلاك المسموح به على النحو المتفق عليه مع اللجنة التنفيذية. ولاحظت اللجنة أيضا أن الحكومة واصلت تنفيذ متطلبات وضع العلامات الإلزامية على مركب الكلوروفلوروكربون المهلجن 22، وتعمل على تعزيز تدابير الإنفاذ بشأن الرقابة التجارية على المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية. وتأمل اللجنة أن تواصل حكومة جمهورية لاو الديمقراطية الشعبية تنفيذ مشروع التعزيز المؤسسي بنجاح وأن تحافظ على إنجازات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وتفي بالالتزام الأول بالتخفيض التدريجي للمواد الهيدروفلوروكربونية بموجب تعديل كيغالي.

- ملديف

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للملديف (المرحلة الثالثة عشرة) وأشارت مع التقدير إلى أن حكومة الملديف قد أبلغت بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وتأمل اللجنة أن تواصل حكومة المالديف تنفيذ مشروع التعزيز المؤسسي بنجاح وتحافظ على إنجازات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وتبدأ في التخفيض التدريجي للمواد الهيدروفلوروكربونية على النحو المنصوص عليه في تعديل كيغالي.

- المغرب

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للمغرب  (المرحلة الخامسة) وأشارت مع التقدير إلى أن حكومة المغرب قد أبلغت عن بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مشيرة إلى أن البلاد ممتثلة لبروتوكول مونتريال. ولاحظت اللجنة أن البلد يقوم بتنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وإجراء أنشطة للوصول إلى المعلومات وزيادة التوعية والمشاركة في اجتماعات الشبكات الإقليمية. وتأمل اللجنة أن تواصل حكومة المغرب تنفيذ مشروع التعزيز المؤسسي بنجاح للحفاظ على زخم التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية والوفاء بتدابير الرقابة المستقبلية لبروتوكول مونتريال وتعديل كيغالي.

- النيجر

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للنيجر (المرحلة الرابعة عشرة) وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وأشير أيضا إلى الإنجازات التي أحرزتها النيجر في جهودها للتخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع. وأشير إلى تدابير الإنفاذ التي نُفذت للتحكم في واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص، إلى جانب التدريب الشامل المقدم لموظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أقرت اللجنة بمبادرات النيجر الرامية إلى خفض استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية. وبالنظر إلى المستقبل، تتوقع اللجنة أن يواصل النيجر تنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وخطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية في المرحلة المقبلة، مع الهدف الطموح المتمثل في تحقيق تخفيض بنسبة 67.5 في المائة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/كانون الثاني 2025.

- قطر

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لقطر (المرحلة السابعة) وأشارت مع التقدير إلى أن قطر أبلغت بيانات البرنامج القطري وبيانات المادة 7 لعام 2022 إلى أمانتي الصندوق الأوزون، على التوالي، مما يشير إلى أن البلاد ممتثلة لبروتوكول مونتريال. وتتوقع اللجنة أن يتم تعزيز التنسيق الجاري مع أصحاب المصلحة والقطاعين الحكومي والخاص لضمان مشاركتهم الكاملة في تنفيذ المشاريع الجارية الممولة من بروتوكول مونتريال بما في ذلك تنفيذ المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لتحقيق هدف التخفيض لعام 2025. ولذلك، تأمل اللجنة أن تواصل قطر، خلال السنوات الثلاث المقبلة، تنفيذ خطتها لإدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وأنشطة مشروع التعزيز المؤسسي بنجاح لإعداد البلاد لمزيد من التخفيض في استهلاك المواد الهيدروكلوروفلوروكربونية بموجب بروتوكول مونتريال والبدء في الأنشطة المطلوبة بموجب تعديل كيغالي.

- سان تومي وبرينسيبي

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لسان تومي وبرينسيبي (المرحلة الثامنة وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة أيضا الجهود المبذولة للتخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع وتدابير الإنفاذ الصارمة المطبقة للتحكم في واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص، إلى جانب التدريب الشامل المقدم لموظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أقرت اللجنة بمبادرات سان تومي وبرينسيبي الرامية إلى خفض استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية. وبالنظر إلى المستقبل، تتوقع اللجنة أن تقدم سان تومي وبرينسيبي وتنفذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وخطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية في المرحلة التالية، بهدف تحقيق تخفيض بنسبة 67.5 في المائة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/كانون الثاني 2025.

- المملكة العربية السعودية

- استعرضت اللجنة التنفيذية طلب تجديد مشروع التعزيز المؤسسي للمملكة العربية السعودية (المرحلة الرابعة) وأشارت مع التقدير إلى أن المملكة العربية السعودية قد أبلغت بيانات البرامج القطرية وبيانات المادة 7 لعامي 2022 و2023 إلى أمانتي الصندوق المتعدد الأطراف والأوزون، على التوالي، مشيرة إلى أن البلاد في حالة امتثال لمتطلبات بروتوكول مونتريال. وأقرت اللجنة بالجهود التي تبذلها المملكة العربية السعودية للحد من استهلاك المواد الهيدروكلوروفلوروكربونية، ولذلك تأمل أن تواصل المملكة العربية السعودية، خلال السنوات الثلاث المقبلة، تنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وأنشطة مشروع التعزيز المؤسسي بنجاح لتحضير البلد لمزيد من التخفيض في استهلاك المواد الهيدروكلوروفلوروكربونية بموجب بروتوكول مونتريال واستكمال عملية التصديق على تعديل كيغالي.

- السنغال

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للسنغال (المرحلة الخامسة عشرة) وأشارت مع التقدير إلى تقديم بيانات عامي 2021 و2022 إلى أمانة الأوزون، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وأشارت اللجنة إلى الجهود التي تبذلها السنغال للتخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع. وأشير بصفة خاصة إلى تدابير الإنفاذ الصارمة المطبقة للتحكم في واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص، إلى جانب التدريب الشامل المقدم لموظفي الجمارك وفنيي التبريد. وعلاوة على ذلك، أقرت اللجنة بمبادرات السنغال الاستباقية الرامية إلى خفض استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية. وبالنظر إلى المستقبل، تتوقع اللجنة استمرار نجاح السنغال في تنفيذ خطتها لإدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي بهدف تحقيق تخفيض بنسبة 67.5 في المائة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/كانون الثاني 2025.

- جنوب أفريقيا

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لجنوب أفريقيا (المرحلة الأولى) ولاحظت مع التقدير أن البلد يتوفر على وحدة أوزون وطنية تشغيلية (NOU) وأنه كان يمتثل لالتزاماته بموجب بروتوكول مونتريال بما في ذلك إنفاذ نظام التراخيص والحصص للمواد الهيدروكلوروفلوروكربونية وتقديم المادة 7 وبيانات البرنامج القطري في الوقت المناسب. ولاحظت اللجنة أيضاً مع التقدير أن جنوب أفريقيا حققت التخلص التدريجي الكامل من المواد الكلوروفلوروكربونية دون دعم مالي من الصندوق المتعدد الأطراف، وأصدرت تشريعات لحظر استيراد المواد الكلوروفلوروكربونية في عام 2014. واعترفت اللجنة بالجهود التي بذلتها حكومة جنوب أفريقيا لتلبية احتياجات التزامات بروتوكول مونتريال وتنفيذ المشاريع دون وجود مشروع تعزيز مؤسسي، وهي على ثقة من أنه بالموافقة على المشروع، ستقوم الحكومة بالتنسيق مع أصحاب المصلحة الوطنيين وبناء قدراتهم، ورفع مستوى الوعي لدى مختلف أصحاب المصلحة المعنيين بقطاعات محددة، وكذلك لدى الجمهور وتنفيذ المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وتجميد استهلاك المواد الكلوروفلوروكربونية عند مستوى خط الأساس ووضع استراتيجية شاملة وخطة تنفيذ للمرحلة الأولى من خطة كيغالي لتنفيذ المواد الكلوروفلوروكربونية لتحقيق تخفيض بنسبة 10 في المائة في استهلاك المواد الكلوروفلوروكربونية من خط الأساس بحلول عام 2029.

- جنوب السودان

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لجنوب السودان (المرحلة الثانية) وأشارت مع التقدير إلى أن جنوب السودان قدمت بيانات المادة 7، مما يشير إلى أن البلاد في حالة امتثال لبروتوكول مونتريال في عام 2023. وأقرت اللجنة بأن جنوب السودان لديه نظام للتراخيص والحصص، وأن البلد قام بتدريب موظفي الجمارك وفنيي التبريد وأجرى أنشطة إذكاء الوعي وإعداد المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية. واعترفت اللجنة بالجهود التي يبذلها جنوب السودان للحد من استهلاك المواد الهيدروكلوروفلوروكربونية وتأمل أن يبدأ جنوب السودان، خلال السنوات الثلاث المقبلة، في تنفيذ المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومواصلة تنفيذ أنشطة مشروع التعزيز المؤسسي بنجاح من أجل إعداد البلد لتحقيق التخفيض المطلوب بنسبة 67.5 في المائة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/كانون الثاني 2025.

- فانواتو

- استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لفانواتو (المرحلة التاسعة) ولاحظت مع التقدير أن حكومة فانواتو، على الرغم من الانتكاسة التي حدثت في عام 2023، أبلغت عن بيانات البرنامج القطري وبيانات المادة 7 إلى أمانتي الصندوق والأوزون في الوقت المحدد، على التوالي، مما يشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة أن الحكومة تواصل التنفيذ الفعال لنظام ترخيص المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية من خلال نظام النافذة الوطنية الواحدة وتواصل الامتثال لالتزامات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية بموجب بروتوكول مونتريال والحد الأقصى للاستهلاك المسموح به على النحو المتفق عليه مع اللجنة التنفيذية ومع التزامات تعديل كيغالي. وتأمل اللجنة أن تواصل حكومة فانواتو تنفيذ مشروع التعزيز المؤسسي بنجاح للحفاظ على إنجازات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية والامتثال للتخفيض التدريجي للمواد الهيدروفلوروكربونية على النحو المنصوص عليه في تعديل كيغالي.

الوثيقة UNEP/OzL.Pro/ExCom/94/1.

يشار إليه هنا بإعداد قائمة جرد وخطة وطنية لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها.

المقرر 91/63: (ب) الموافقة على الشكل المنقح للتقارير النهائية وطلبات تمديد تمويل التعزيز المؤسسي ومؤشرات الأداء المقابلة؛ و(ج) مطالبة البلدان المدرجة في المادة 5، من خلال الوكالات الثنائية والوكالات المنفذة، باستخدام النموذج المنقح المشار إليه في الفقرة الفرعية (ب) أعلاه لجميع طلبات تجديد التعزيز المؤسسي اعتبارا من الاجتماع الأول للجنة التنفيذية في عام 2023.

يُسمح بإدراج المرحلة الثالثة من خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية في خطة العمل فقط لتلك البلدان التي لديها المرحلة الثانية المعتمدة من خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية مع أهداف خفض أقل من أهداف الامتثال لعام 2025.

المرفق الرابع عشر من الوثيقة UNEP/OzL.Pro/ExCom/93/105.

UNEP/OzL.Pro/ExCom/94/18

UNEP/OzL.Pro/ExCom/94/20

تاريخ التصديق على تعديل كيغالي: 3 أكتوبر/تشرين الأول 2023.

تلقت نيجيريا تمويلا لتنفيذ مشروع تجريبي لإدارة نفايات المواد المستنفدة للأوزون وتدميرها في الاجتماع السابع والستين (المقرر 67/24).

المقرر 14/7.

طُلب إلى الأمانة أن تقدم، في الاجتماع الأول من كل عام، قائمة تمثل 20 في المائة من البلدان التي لديها خط أساس لاستهلاك المواد الهيدروكلوروفلوروكربونية يصل إلى 360 طنا متريا، ولديها خطة معتمدة لإدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، للموافقة على تمويلها لأغراض التحقق من امتثال ذلك البلد لاتفاق خطة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لذلك العام.

بوركينا فاسو وغابون.

Data as at December 2022 are based on document UNEP/OzL.Pro/ExCom/93/17.