UNEP/OzL.Pro/ExCom/84/30
   20 November 2019

UNIDO BUSINESS PLAN FOR 2020–2022

# This document presents the UNIDO business plan for 2020–2022 and includes: the planned activities for the phase-out of controlled substances under the Montreal Protocol (controlled substances) during the 2020–2022 period; the business plan performance indicators; and a recommendation for consideration by the Executive Committee. The narrative of UNIDO’s business plan for 2020–2022 is attached to the present document.

Planned activities during 2020–2022

# Table 1 sets out, by year, the value of activities included in UNIDO’s business plan.

Table 1. Resource allocation in the UNIDO business plan for 2020–2022 as submitted (US $000s)*

|  | 2020 | 2021 | 2022 | Total (2020–2022) | Total after 2022 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 37,782 | 35,245 | 32,005 | 105,033 | 59,500 |
| HPMP stage I | 196 | 0 | 350 | 546 | 0 |
| HPMP project preparation (PRP) – stage II | 277 | 253 | 0 | 529 | 0 |
| HPMP stage II | 4,591 | 5,993 | 6,178 | 16,762 | 44,896 |
| HPMP PRP – stage III | 246 | 257 | 0 | 503 | 0 |
| HPMP stage III | 0 | 5,092 | 3,458 | 8,551 | 33,361 |
| HCFC technical assistance | 482 | 0 | 0 | 482 | 0 |
| HCFC activities subtotal | 43,574 | 46,840 | 41,992 | 132,405 | 137,758 |
| HFC activities |  |  |  |  |  |
| HFC – investment | 1,819 | 0 | 0 | 1,819 | 0 |
| HFC phase-down – PRP | 756 | 225 | 0 | 981 | 0 |
| HFC activities subtotal | 2,575 | 225 | 0 | 2,800 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 1,687 | 1,186 | 1,687 | 4,560 | 0 |
| Core unit | 2,113 | 2,128 | 2,143 | 6,384 | 0 |
| Standard activities subtotal | 3,800 | 3,314 | 3,830 | 10,944 | 0 |
| Grand total | 49,949 | 50,379 | 45,822 | 146,149 | 137,758 |

* Including agency support costs where applicable.

# Secretariat’s comments

Stage I of HPMPs

# A total of US $546,137 is included in UNIDO’s 2020–2022 business plan for Syrian Arab Republic. However, its stage I of HPMP has not yet been approved and it has not been submitted to the 84th meeting.

# Stage II of HPMPs

# The total levels of funding for stage II of HPMPs in low-volume-consuming (LVC) countries to meet the 67.5 per cent reduction of the HCFC baseline amount to US $6.86 million (including US $4.8 million for 2020–2022), and to US $43,902 in 2021 to meet a 100 per cent reduction.

# The funding distribution of stage II of HPMPs for non-LVC countries by sector is provided in Table 2.

Table 2. Funding distribution of stage II of HPMPs in non-LVC countries by sector (US $000)

| Sector | 2020–2022 | After 2022 | Total | Per cent of total (%) |
| --- | --- | --- | --- | --- |
| Rigid foam | 1,461 | 394 | 1,855 | 3.4 |
| Refrigeration air-conditioning | 276 | 0 | 276 | 0.5 |
| Refrigeration assembly | 645 | 0 | 645 | 1.2 |
| Refrigeration manufacturing | 2,609 | 27,781 | 30,390 | 55.5 |
| Refrigeration servicing | 6,926 | 14,660 | 21,586 | 39.4 |
| Total | 11,917 | 42,835 | 54,752 | 100.0 |

# Stage III of HPMPs

# A total of US $41.91 million is included in the business plan for stage III of HPMPs for six countries (Armenia, Chile, Mexico, Nigeria, the Philippines, and the Sudan) (including US $8.55 million for 2020-2022).  Inclusion of stage III of HPMPs in the business plan is allowed only for those countries that had stage II of an HPMP approved to meet a reduction target by 2020 (decision 82/45(c)(i)). Four of these countries have an approved stage II with reduction target beyond 2020 (Chile, Mexico, Nigeria and the Philippines).

HCFC technical assistance regional project

# UNIDO has included one HCFC technical assistance regional project for “promoting low-global warming potential refrigerants for air-conditioning sectors in high ambient temperature countries (PRAHA-III),” amounting to US $481,500 in 2020. No funding window for such demonstration project is available.

HFC-related activities

# HFC activities include an investment activity amounting to US $1.82 million in 2020 for one country (China) and HFC phase-down preparation activities for 13 countries amounting to US $980,660 in 2020 and 2021.

# The HFC investment project in the extruded polystyrene foam sector in China was intended to be submitted to the 84th meeting pursuant to decision 78/3(g), but the Government decided to defer the submission to a future meeting as priority was being given to the submission of stage II of its HPMP. With respect to decision 82/77(a) requiring ratification of the Kigali Amendment as a pre-requisite of approval of further HFC projects for China, the Foreign Environmental Cooperation Center/Ministry of Ecology and Environment of China plans to speed up the ratification process and consider the submission once the Amendment is ratified or the ratification process is almost completed. This project is maintained in the business plan pending decision from the Executive Committee on whether to allow submission of this project to a later meeting.

# Regarding the preparation activities, funding for the preparation of national implementation plans to meet initial reduction obligations for the phase-down of HFCs could be provided, at the earliest, five years prior to those obligations, after a country had ratified the Kigali Amendment and on the basis of guidelines to be approved in the future (decision 79/46(b)(iii)). Of the 13 countries, only Turkey has not ratified the Kigali Amendment, but has submitted the required letter from its Government indicating its intent to make best efforts to ratify the Amendment.

# Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

Proposed adjustments by the Secretariat

# During the IACM, adjustments to the business plans of bilateral and implementing agencies were agreed based on relevant decisions of the Executive Committee. In reviewing the revised UNIDO business plan for 2020–2022, the Secretariat noted that the following adjustments were not included:

Table 3. Adjustments to the UNIDO business plan for 2020–2022 (US $000)

| Adjustment | 2020–2022 | After 2022 |
| --- | --- | --- |
| HPMP values to reflect the revised Agreement submitted to the 84th meeting | 16,925 | 2,335 |
| PRP for stage II of HPMPs pursuant to decision 71/42 | (50) | 0 |
| Stage III of HPMPs pursuant to decision 82/45(c)(i) | (8,404) | (33,018) |
| HCFC technical assistance | (482) | 0 |
| PRP for HFC phase-down pursuant to decision 56/16(c) or countries that have not ratified the Kigali Amendment | (209) | 0 |

# Table 4 presents the results of the Secretariat’s proposed adjustments to the UNIDO business plan for 2020–2022, which are also addressed in the context of the Consolidated business plan of the Multilateral Fund for 2020–2022.

# Table 4. Resource allocation in UNIDO’s adjusted business plan for 2020–2022 (US $000s)*

|  | 2020 | 2021 | 2022 | Total (2020–2022) | Total after 2022 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 46,082 | 40,797 | 35,080 | 121,958 | 61,834 |
| HPMP stage I | 196 | 0 | 350 | 546 | 0 |
| HPMP PRP – stage II | 227 | 253 | 0 | 479 | 0 |
| HPMP stage II | 4,591 | 5,993 | 6,178 | 16,762 | 44,896 |
| HPMP PRP – stage III | 246 | 257 | 0 | 503 | 0 |
| HPMP stage III | 0 | 60 | 87 | 147 | 343 |
| HCFC technical assistance | 0 | 0 | 0 | 0 | 0 |
| HCFC activities subtotal | 51,342 | 47,360 | 41,694 | 140,396 | 107,074 |
| HFC activities |  |  |  |  |  |
| HFC – investment | 1,819 | 0 | 0 | 1,819 | 0 |
| HFC phase-down – PRP | 547 | 225 | 0 | 772 | 0 |
| HFC activities subtotal | 2,366 | 225 | 0 | 2,591 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 1,687 | 1,186 | 1,687 | 4,560 | 0 |
| Core unit | 2,113 | 2,128 | 2,143 | 6,384 | 0 |
| Standard activities subtotal | 3,800 | 3,314 | 3,830 | 10,944 | 0 |
| Grand total | 57,508 | 50,899 | 45,524 | 153,930 | 107,074 |

* Including agency support costs where applicable.

Performance indicators

# UNIDO submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed UNIDO of the targets shown in Table 5.

Table 5. Performance indicators for UNIDO for 2020

| Type of indicator | Short title | Calculation | 2020 target |
| --- | --- | --- | --- |
| Planning--Approval | Tranches approved | Number of tranches approved vs. those planned* | 59 |
| Planning--Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities)** | 29 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $23,582,315 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans | 796.41 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 64 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 12 months after operational completion |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | 5 |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another cooperating or lead agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

RECOMMENDATION

# The Executive Committee may wish:

## To note the UNIDO business plan for 2020–2022, contained in document UNEP/OzL.Pro/ExCom/84/30; and

## To approve the performance indicators for UNIDO as set out in Table 5 of document UNEP/OzL.Pro/ExCom/84/30.

A draft business plan for 2020–2022 of UNIDO was discussed at the Inter-agency coordination meeting (IACM) held in Montreal from 9 to 11 October 2019. The business plan contained in this document has addressed the issues raised at the meeting.

Funding was approved for the country for the phase-out of 12.9 ODP tonnes of HCFC in the refrigeration and air-conditioning sector as a stand-alone project outside its HPMP, representing 9.6 per cent of the baseline.

UNIDO’s 2020 core unit cost request has been submitted to the 84th meeting (UNEP/OzL.Pro/ExCom/84/38).

UNEP/OzL.Pro/ExCom/84/26