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UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2018–2020 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

Introduction

The Parties to the Montreal Protocol adopted a budget of US $540,000,000 for the 2018–2020 replenishment of the Multilateral Fund, on the understanding that US $34,000,000 will be provided from anticipated contributions due to the Fund and other sources from the 2015–2017 triennium, and that US $6,000,000 will be provided from interest accruing to the Fund during the 2018–2020 triennium (decision XXIX/1). 
At its 80th meeting, the Executive Committee endorsed the pro-rated business plan of the Multilateral Fund according to decision 80/34(c)(v). At the 81st meeting, the 2018–2020 pro-rated business plan was further adjusted based on the new resource allocations adopted by the Executive Committee of US $194.4 million in 2018, US $174.6 million in 2019 and US $171 million in 2020, as shown in Table 1 (decision 81/26(b)).
Table 1. Resource allocation of the pro-rated consolidated 2018–2020 business plan of the Multilateral Fund (US $)
	Item
	2018
	2019
	2020
	Total 

	Required for compliance
	 
	 
	 
	 

	Approved HCFC phase-out management plans (HPMPs)
	129,582,375
	115,880,401
	101,279,996
	346,742,772

	HCFC production – stage II
	9,091,808
	12,039,619
	8,976,124
	30,107,551

	HPMP stage I
	0
	353,978
	0
	353,978

	HPMP stage I – additional funding
	187,112
	627,148
	0
	814,260

	HPMP preparation (PRP) – stage II – low‑volume consuming (LVC) countries
	2,218,408
	518,850
	44,300
	2,781,558

	HPMP PRP – stage II - non-LVC countries
	1,072,336
	890,450
	0
	1,962,786

	HPMP stage II - LVC countries
	81,798
	268,545
	9,067,642
	9,417,984

	HPMP stage II - non-LVC countries
	5,585,329
	7,834,674
	11,325,242
	24,745,246

	HPMP verification*
	588,600
	588,600
	588,600
	1,765,800

	HCFC technical assistance
	154,380
	0
	0
	154,380

	  Required for compliance subtotal
	148,562,145
	139,002,266
	131,281,904
	418,846,316

	HFC activities
	 
	 
	 
	 

	HFC - demonstration
	3,351,981
	0
	0
	3,351,981

	HFC - enabling activities
	3,236,750
	0
	0
	3,236,750

	HFC – investment
	1,378,659
	3,937,408
	815,425
	6,131,493

	  HFC activities subtotal
	7,967,390
	3,937,408
	815,425
	12,720,224

	Standard costs
	 
	 
	 
	 

	Compliance Assistance Programme (CAP)
	10,971,601
	11,300,749
	11,639,772
	33,912,122

	Core unit
	5,902,741
	5,931,915
	5,961,294
	17,795,949

	Institutional strengthening (IS)
	13,847,453
	7,128,429
	13,847,292
	34,823,174

	Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart
	6,648,670
	6,799,233
	6,954,313
	20,402,216

	Treasurer
	500,000
	500,000
	500,000
	1,500,000

	  Standard activities subtotal
	37,870,465
	31,660,326
	38,902,670
	108,433,461

	Grand total
	194,400,000
	174,600,000
	171,000,000
	540,000,000

	Funding distribution by agency
	 
	 
	 
	 

	Canada
	565,584
	0
	0
	565,584

	France
	78,769
	0
	692,895
	771,664

	Germany
	6,490,401
	1,038,050
	1,988,661
	9,517,112

	Italy
	750,128
	0
	100,927
	851,055

	Japan
	366,097
	120,232
	90,400
	576,729

	Spain
	1,192,731
	0
	0
	1,192,731

	UNDP
	59,934,280
	34,438,004
	52,105,629
	146,477,913

	UNEP
	34,497,185
	21,231,719
	32,512,121
	88,241,025

	UNIDO
	50,594,306
	64,198,079
	43,860,902
	158,653,288

	World Bank
	32,193,248
	45,686,083
	31,605,552
	109,484,883

	HPMP verification*
	588,600
	588,600
	588,600
	1,765,800

	Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart
	6,648,670
	6,799,233
	6,954,313
	20,402,216

	Treasurer
	500,000
	500,000
	500,000
	1,500,000


* Funding for the preparation of HPMP verification reports for LVC countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2018 business plans
The total funding available for 2018 amounts to US $194,400,000. Of this amount, US $73,930,598 has been approved at the 81st meeting. Funding requests submitted to the 82nd meeting amounts to US $105,866,396. If funding requests for all project proposals submitted are approved, a balance of US $14,603,006 would be available from the 2018 business plan, as shown in Table 2. The list of project proposals submitted to the 82nd meeting is contained in Annex I to the present document.
Table 2. 2018 consolidated business plan, submissions to the 82nd meeting, and balance (US $)*
	Budget items
	Total value in business plan
	Approvals at the 81st meeting
	Submissions 82nd meeting**
	Total (81st and 82nd)
	Balance (above)/below

	Bilateral agencies
	9,443,711
	2,894,312
	5,277,018
	8,171,330
	1,272,381

	UNDP
	59,934,280
	13,521,504 
	52,180,460
	65,701,964
	(5,767,684)

	UNEP
	34,497,185
	 8,398,710 
	18,700,794
	27,099,504
	7,397,681

	UNIDO
	50,594,306
	23,462,165 
	17,402,041
	40,864,206
	9,730,100

	World Bank
	32,193,248
	25,653,907
	4,216,613
	29,870,520
	2,322,728

	HPMP verification
	588,600
	
	940,800
	940,800
	(352,200)

	Sub-total 
	187,251,330
	73,930,598
	98,717,726
	172,648,324
	14,603,006

	Secretariat/ExCom/Monitoring /Treasurer
	7,148,670
	
	7,148,670
	7,148,670
	0

	Total
	194,400,000
	73,930,598
	105,866,396
	179,796,994
	14,603,006


* Including core unit costs.
** As at 18 November 2018.

The value of project proposals submitted to the 82nd meeting of US $98,717,726 is US $5,528,155 above their value in the 2018 business plan, including US $3,329,848 associated with project proposals not included in the 2018 business plan.[footnoteRef:1] The value of HFC phase-down activities submitted to the 82nd meeting is US $4,120,570 of which US $2,959,457 is associated with project proposals not included in the 2018 business plan.  [1:  Project preparation for stage II of the HPMP for Afghanistan (UNIDO) and Belize (UNDP); HFC enabling activities for Cook Islands (UNEP), Islamic Republic of Iran (UNEP), Jordan (UNIDO), Mauritius (UNEP), Qatar (UNEP and UNIDO) and South Africa (UNIDO); HFC investment projects for China (UNDP), Egypt (UNDP) and Zimbabwe (UNDP); and IS project for Mexico (UNIDO). ] 

Project proposals with a value of US $43,602,722[footnoteRef:2] that were included in the 2018 business plan were not submitted to the 82nd meeting. These proposals have been included in the Consolidated business plan of the Multilateral Fund for 2019–2021.[footnoteRef:3] [2:  These activities include: 111 HCFC activities for 66 countries (US $33.85 million), 11 HFC-related activities for 10 countries (US $4.48 million) and 36 IS activities (US $5.27 million).]  [3:  UNEP/OzL.Pro/ExCom/82/25] 

All additional voluntary contributions by 17 non-Article 5 countries[footnoteRef:4] amounting to US $25,513,071, have been received. Since the 80th meeting, US $23,104,300 has been approved for HFC enabling activities and HFC phase-out projects, with a balance of US $2,408,771 available for programming at the 82nd meeting. [4:  Australia, Canada, Denmark, Finland, France, Germany, Ireland, Italy, Japan, Luxembourg, Netherlands (the), New Zealand, Norway, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland and the United States of America.] 

Forward commitments

[bookmark: _GoBack]The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2018 to 2031 is US $618.46 million, assuming that the funding requests of MYAs submitted to the 82nd meeting will be approved in principle, as shown in Table 3.
Table 3. Forward commitments (2018–2031) (US $000)
	Description
	2018
	2019
	2020
	2021
	2022
	2023
	2024
	2025
	2026
	2030
	2031
	Total

	Approved in principle
	108,295
	101,862
	118,246
	98,157
	58,386
	39,606
	27,960
	27,944
	32,195
	212
	57
	612,919

	Submitted to 82nd meeting
	2,159
	0
	2,265
	842
	187
	0
	0
	85
	0
	0
	0
	5,537

	Total 
	110,454
	101,862
	120,510
	98,999
	58,572
	39,606
	27,960
	28,029
	32,195
	212
	57
	618,456



RECOMMENDATION

The Executive Committee may wish to note:
The update on the status of implementation of the 2018–2020 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/82/23; and
That US $4,120,570 in HFC phase-down activities were submitted to the 82nd meeting including US $2,959,457 that had not been included in the 2018–2020 business plans. 
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PROJECT PROPOSALS SUBMITTED TO THE 82ND MEETING

	Country
	Agency
	Project title
	Funds requested (US$)
	Support costs requested (US$)
	Total (US$)

	Standard activities 

	Global
	UNEP
	Compliance Assistance Programme: 2019 budget
	9,974,259
	797,941
	10,772,200

	Global
	World Bank
	Core unit budget (2019)
	0
	1,735,000
	1,735,000

	Global
	UNDP
	Core unit budget (2019)
	0
	2,083,871
	2,083,871

	Global
	UNIDO
	Core unit budget (2019)
	0
	2,083,871
	2,083,871

	Institutional strengthening

	Argentina
	UNDP
	Extension for institutional strengthening project (phase X: 1/2019-12/2020)
	398,806
	27,916
	426,722

	Armenia
	UNIDO
	Extension of institutional strengthening project (phase VI: 4/2019-3/2021)
	153,600
	10,752
	164,352

	Barbados
	UNEP
	Renewal of institutional strengthening project (phase VII: 1/2019-12/2020)
	149,760
	0
	149,760

	Brunei Darussalam
	UNEP
	Renewal of the institutional strengthening project (phase VI: 1/2019-12/2020)
	89,600
	0
	89,600

	China
	UNDP
	Extension of the institutional strengthening project (phase XIII: 1/2019-12/2020)
	499,200
	34,944
	534,144

	Dominican Republic (the)
	UNEP
	Extension of the institutional strengthening project (phase X: 1/2019-12/2020)
	171,946
	0
	171,946

	Fiji
	UNEP
	Extension of the institutional strengthening project (phase XI: 1/2019-12/2020)
	85,000
	0
	85,000

	Ghana
	UNDP
	Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020)
	178,048
	12,463
	190,511

	Iran (Islamic Republic of)
	UNDP
	Extension of the institutional strengthening project (phase XII: 4/2019-3/2021)
	222,094
	15,547
	237,641

	Iraq
	UNEP
	Extension of institutional strengthening project (phase IV: 1/2019-12/2020)
	307,200
	0
	307,200

	Jordan
	World Bank
	Extension of institutional strengthening project (phase XIII: 1/2019-12/2020)
	188,586
	13,201
	201,787

	Lebanon
	UNDP
	Extension of the institutional strengthening project (phase XI: 4/2019-3/2021)
	198,515
	13,896
	212,411

	Lesotho
	UNEP
	Extension of the institutional strengthening project (phase IX: 1/2019-12/2020)
	85,000
	0
	85,000

	Madagascar
	UNEP
	Renewal of institutional strengthening project (phase VIII: 1/2019-12/2020)
	85,000
	0
	85,000

	Malawi
	UNEP
	Extension of institutional strengthening project (phase XI: 1/2019-12/2020)
	85,418
	0
	85,418

	Mexico
	UNIDO
	Extension of institutional strengthening project (phase XIV: 7/2019-6/2021)
	316,160
	22,131
	338,291

	Mozambique
	UNEP
	Extension of the institutional strengthening project (phase VIII: 1/2019-12/2020)
	103,424
	0
	103,424

	Nigeria
	UNDP
	Extension of the institutional strengthening project (phase X: 12/2018-11/2020)
	332,800
	23,296
	356,096

	Niue
	UNEP
	Extension of the institutional strengthening project (phase VII: 4/2019-3/2021)
	85,000
	0
	85,000

	Oman
	UNIDO
	Renewal of institutional strengthening support (phase VII: 12/2018-11/2020)
	87,638
	6,135
	93,773

	Pakistan
	UNDP
	Extension of the institutional strengthening project (phase X: 4/2019-3/2021)
	287,318
	20,112
	307,430

	Paraguay
	UNEP
	Extension of institutional strengthening project (phase VIII: 1/2019-12/2020)
	85,000
	0
	85,000

	Republic of Moldova (the)
	UNEP
	Extension of the institutional strengthening project (phase X: 1/2019-12/2020)
	88,748
	0
	88,748

	Sao Tome and Principe
	UNEP
	Extension of the institutional strengthening project (phase VI: 1/2019-12/2020)
	85,000
	0
	85,000

	Sierra Leone
	UNEP
	Extension of institutional strengthening project (phase VII: 1/2019-12/2020)
	109,824
	0
	109,824

	Sri Lanka
	UNDP
	Extension of the institutional strengthening project (phase XII: 1/2019-12/2020)
	171,592
	12,011
	183,603

	Thailand
	World Bank
	Extension of institutional strengthening project (phase IX: 1/2019-12/2020)
	443,735
	31,061
	474,796

	Togo
	UNEP
	Extension of the institutional strengthening project (phase X: 1/2019-12/2020)
	85,000
	0
	85,000

	Tuvalu
	UNEP
	Extension of the institutional strengthening project (phase VII: 4/2019-3/2021)
	85,000
	0
	85,000

	Uganda
	UNEP
	Extension of the Institutional strengthening project (phase III: 1/2019-12/2020)
	85,000
	0
	85,000

	Venezuela (Bolivarian Republic of)
	UNDP
	Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020)
	365,414
	25,579
	390,993

	Viet Nam
	UNEP
	Extension of the institutional strengthening project (phase XII: 7/2019-6/2021)
	152,289
	0
	152,289

	Verification reports for HCFC phase-out management plans (HPMPs)

	Albania
	UNIDO
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	2,700
	32,700

	Bahamas (the)
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Belize
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Cuba
	UNDP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	2,700
	32,700

	Eritrea
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Fiji
	UNDP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	2,700
	32,700

	Gambia (the)
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Grenada
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Guinea-Bissau
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Lao People’s Democratic Republic (the)
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Madagascar
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Malawi
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Mongolia
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Nepal
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Niger (the)
	UNIDO
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	2,700
	32,700

	Palau
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Saint Kitts and Nevis
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Saint Lucia
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Samoa
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Sao Tome and Principe
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Serbia
	UNIDO
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	2,700
	32,700

	Solomon Islands
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Sri Lanka
	UNDP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	2,700
	32,700

	Tonga
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Turkmenistan
	UNIDO
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	2,700
	32,700

	Uganda
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	United Republic of Tanzania (the)
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Zambia
	UNEP
	Verification report on the implementation of the HCFC phase-out management plan
	30,000
	3,900
	33,900

	Stage I of HPMPs

	Bosnia and Herzegovina
	UNIDO
	HCFC phase-out management plan (stage I, fourth tranche) (activities in the refrigeration servicing sector including policy actions)
	31,000
	2,170
	33,170

	Botswana
	UNIDO
	HCFC phase-out management plan (stage I, second tranche)
	140,000
	9,800
	149,800

	Botswana
	UNEP
	HCFC phase-out management plan (stage I, second tranche)
	90,000
	11,700
	101,700

	Brunei Darussalam
	UNDP
	HCFC phase-out management plan (stage I, third tranche)
	33,000
	2,970
	35,970

	Brunei Darussalam
	UNEP
	HCFC phase-out management plan (stage I, third tranche)
	7,000
	910
	7,910

	Chad
	UNEP
	HCFC phase-out management plan (stage I, fourth tranche)
	45,000
	5,850
	50,850

	Cuba
	UNDP
	HCFC phase-out management plan (stage I, fourth tranche)
	100,000
	7,500
	107,500

	Ecuador
	UNIDO
	HCFC phase-out management plan (stage I, fourth tranche)
	86,500
	6,487
	92,987

	Ecuador
	UNEP
	HCFC phase-out management plan (stage I, fourth tranche)
	25,000
	3,250
	28,250

	Egypt
	UNIDO
	HCFC phase-out management plan (stage I, third tranche) (enabling activities in the refrigeration and air-conditioning sector)
	232,575
	17,443
	250,018

	Egypt
	UNDP
	HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector)
	716,400
	53,730
	770,130

	Equatorial Guinea
	UNIDO
	HCFC phase-out management plan (stage I, third tranche)
	60,000
	5,400
	65,400

	Equatorial Guinea
	UNEP
	HCFC phase-out management plan (stage I, third tranche)
	45,000
	5,850
	50,850

	Gambia (the)
	UNEP
	HCFC phase-out management plan (stage I, fourth tranche)
	21,000
	2,730
	23,730

	Libya
	UNIDO
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	190,893
	13,362
	204,255

	Rwanda
	UNEP
	HCFC phase-out management plan (stage I, fourth tranche)
	30,000
	3,900
	33,900

	Saint Lucia
	UNEP
	HCFC phase-out management plan (stage I, fourth tranche)
	9,200
	1,196
	10,396

	The former Yugoslav Republic of Macedonia
	UNIDO
	HCFC phase-out management plan (phase I, eighth tranche)
	131,000
	9,825
	140,825

	Stage II of HPMPs

	Brazil
	UNIDO
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector)
	2,647,057
	185,294
	2,832,351

	Brazil
	UNDP
	HCFC phase-out management plan (stage II, third tranche) (foam sector)
	6,778,396
	474,488
	7,252,884

	Brazil
	Germany
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	2,363,637
	263,059
	2,626,696

	Brazil
	UNDP
	HCFC phase-out management plan (stage II, third tranche) (regulatory actions and project monitoring)
	390,000
	27,300
	417,300

	Cameroon
	UNIDO
	HCFC phase-out management plan (stage II, first tranche)
	517,750
	36,243
	553,993

	China
	UNIDO
	HCFC phase-out management plan (stage II, third tranche) (extruded polystyrene foam sector plan)
	8,000,000
	560,000
	8,560,000

	China
	UNDP
	HCFC phase-out management plan (stage II, third tranche) (industrial and commercial refrigeration and air-conditioning sector plan)
	12,000,000
	840,000
	12,840,000

	China
	Japan
	HCFC phase-out management plan (stage II, third tranche) (refrigeration and air-conditioning servicing sector plan and enabling component)
	80,000
	10,400
	90,400

	China
	Germany
	HCFC phase-out management plan (stage II, third tranche) (refrigeration and air-conditioning servicing sector plan and enabling component)
	300,000
	36,000
	336,000

	China
	UNEP
	HCFC phase-out management plan (stage II, third tranche) (refrigeration and air-conditioning servicing sector plan and enabling component)
	3,270,000
	361,431
	3,631,431

	China
	UNDP
	HCFC phase-out management plan (stage II, third tranche) (solvent sector plan)
	5,549,492
	388,464
	5,937,956

	Dominican Republic (the)
	UNDP
	HCFC phase-out management plan (stage II, second tranche)
	574,200
	40,194
	614,394

	Dominican Republic (the)
	UNEP
	HCFC phase-out management plan (stage II, second tranche)
	100,000
	13,000
	113,000

	India
	UNDP
	HCFC phase-out management plan (stage II, second tranche) (air-conditioning manufacturing sector plan)
	1,756,000
	122,920
	1,878,920

	India
	UNDP
	HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector plan)
	11,708,000
	819,560
	12,527,560

	India
	UNDP
	HCFC phase-out management plan (stage II, second tranche) (project management and monitoring)
	1,144,000
	80,080
	1,224,080

	India
	Germany
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector plan)
	2,000,000
	223,922
	2,223,922

	India
	UNEP
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector plan)
	300,000
	36,333
	336,333

	Oman
	UNIDO
	HCFC phase-out management plan (stage II, second tranche)
	50,000
	3,500
	53,500

	Oman
	UNEP
	HCFC phase-out management plan (stage II, second tranche)
	59,500
	7,735
	67,235

	Panama
	UNDP
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	385,800
	27,006
	412,806

	Sudan (the)
	UNIDO
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	330,441
	23,131
	353,572

	Thailand
	World Bank
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector and project management unit)
	814,470
	57,013
	871,483

	Thailand
	World Bank
	HCFC phase-out management plan (stage II, first tranche) (spary foam sector)
	685,530
	47,987
	733,517

	Uruguay
	UNDP
	HCFC phase-out management plan (stage II, second tranche) (foam sector)
	422,889
	29,602
	452,491

	Uruguay
	UNDP
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector and implementation and monitoring)
	257,000
	17,990
	274,990

	Project preparation for stage II of HPMPs

	Afghanistan
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	1,400
	21,400

	Afghanistan
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	5,200
	45,200

	Belize
	UNDP
	Preparation of a HCFC phase-out management plan (stage II)
	10,000
	700
	10,700

	Belize
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	Bolivia (Plurinational State of)
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	2,100
	32,100

	Bosnia and Herzegovina
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	2,100
	32,100

	Brunei Darussalam
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	3,900
	33,900

	Chad
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	1,400
	21,400

	Chad
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	5,200
	45,200

	Cuba
	UNDP
	Preparation of a HCFC phase-out management plan (stage II)
	60,000
	4,200
	64,200

	Ecuador
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	Ecuador
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	2,800
	42,800

	El Salvador
	UNDP
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	2,800
	42,800

	Fiji
	UNDP
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	2,100
	32,100

	Gambia (the)
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	10,000
	700
	10,700

	Gambia (the)
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	Grenada
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	3,900
	33,900

	Guatemala
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	15,000
	1,950
	16,950

	Guatemala
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	25,000
	1,750
	26,750

	Honduras
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	Honduras
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	2,800
	42,800

	Lao People’s Democratic Republic (the)
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	3,900
	33,900

	Libya
	UNIDO
	Preparation for HCFC phase-out investment activities (stage II) (foam sector)
	80,000
	5,600
	85,600

	Libya
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	70,000
	4,900
	74,900

	Mongolia
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	3,900
	33,900

	Montenegro
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	2,100
	32,100

	Nepal
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	3,900
	33,900

	Niger (the)
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	Niger (the)
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	2,800
	42,800

	Paraguay
	UNDP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	1,400
	21,400

	Paraguay
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	5,200
	45,200

	Saint Lucia
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	10,000
	700
	10,700

	Saint Lucia
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	Serbia
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	2,100
	32,100

	South Africa
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	90,000
	6,300
	96,300

	Sri Lanka
	UNDP
	Preparation of a HCFC phase-out management plan (stage II)
	40,000
	2,800
	42,800

	The former Yugoslav Republic of Macedonia
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	2,100
	32,100

	Trinidad and Tobago
	UNDP
	Preparation of a HCFC phase-out management plan (stage II)
	60,000
	4,200
	64,200

	Turkmenistan
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	30,000
	2,100
	32,100

	Uganda
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	10,000
	700
	10,700

	Uganda
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	United Republic of Tanzania (the)
	UNIDO
	Preparation of a HCFC phase-out management plan (stage II)
	10,000
	700
	10,700

	United Republic of Tanzania (the)
	UNEP
	Preparation of a HCFC phase-out management plan (stage II)
	20,000
	2,600
	22,600

	HFC - Enabling activities

	Bahamas (the)
	UNEP
	Enabling activities for HFC phase-down
	95,000
	6,650
	101,650

	Bolivia (Plurinational State of)
	UNEP
	Enabling activities for HFC phase-down
	150,000
	10,500
	160,500

	Brunei Darussalam
	UNEP
	Enabling activities for HFC phase-down
	150,000
	10,500
	160,500

	Cabo Verde
	UNEP
	Enabling activities for HFC phase-down
	95,000
	6,650
	101,650

	Cook Islands (the)
	UNEP
	Enabling activities for HFC phase-down
	50,000
	3,500
	53,500

	Iran (Islamic Republic of)
	UNEP
	Enabling activities for HFC phase-down
	95,000
	6,650
	101,650

	Iran (Islamic Republic of)
	UNDP
	Enabling activities for HFC phase-down
	155,000
	10,850
	165,850

	Jordan
	UNIDO
	Enabling activities for HFC phase-down
	150,000
	10,500
	160,500

	Mauritius
	UNEP
	Enabling activities for HFC phase-down
	150,000
	10,500
	160,500

	Qatar
	UNEP
	Enabling activities for HFC phase-down
	50,000
	3,500
	53,500

	Qatar
	UNIDO
	Enabling activities for HFC phase-down
	100,000
	7,000
	107,000

	South Africa
	UNIDO
	Enabling activities for HFC phase-down
	240,000
	16,800
	256,800

	Timor-Leste
	UNEP
	Enabling activities for HFC phase-down
	50,000
	3,500
	53,500

	HFC - Investment activities

	China
	UNDP
	Conversion from C5+HFC-245fa to C5+HFOs in a domestic refrigerator manufacturer (Hisense Kelon)
	1,275,000
	89,250
	1,364,250

	Ecuador
	UNIDO
	Conversion of domestic and commercial refrigerator manufacturing at Ecasa from the use of HFC-134a and R--404A as the refrigerants to propane (R-290) and isobutane (R-600a)
	199,480
	17,953
	217,433

	Egypt
	UNDP
	Conversion of discontinuous panel manufacturing facility from HFC-134a to HFO blowing agent at Army Factory
	224,694
	20,222
	244,916

	Thailand
	World Bank
	Conversion from HFC to propane (R-290) and isobutene (R-600a) as a refrigerant in manufacturing commercial refrigeration appliances in Pattana Intercool Co. Ltd.
	183,514
	16,516
	200,030

	Zimbabwe
	UNDP
	Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare)
	426,954
	29,887
	456,841

	Total
	 
	 
	86,348,346
	12,369,380
	98,717,726
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