| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/82/23 19 November 2018 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-second Meeting

Montreal, 3-7 December 2018

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2018–2020 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

Introduction

# The Parties to the Montreal Protocol adopted a budget of US $540,000,000 for the 2018–2020 replenishment of the Multilateral Fund, on the understanding that US $34,000,000 will be provided from anticipated contributions due to the Fund and other sources from the 2015–2017 triennium, and that US $6,000,000 will be provided from interest accruing to the Fund during the 2018–2020 triennium (decision XXIX/1).

# At its 80th meeting, the Executive Committee endorsed the pro-rated business plan of the Multilateral Fund according to decision 80/34(c)(v). At the 81st meeting, the 2018–2020 pro-rated business plan was further adjusted based on the new resource allocations adopted by the Executive Committee of US $194.4 million in 2018, US $174.6 million in 2019 and US $171 million in 2020, as shown in Table 1 (decision 81/26(b)).

Table 1. Resource allocation of the pro-rated consolidated 2018–2020 business plan of the Multilateral Fund (US $)

| Item | 2018 | 2019 | 2020 | Total |
| --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 129,582,375 | 115,880,401 | 101,279,996 | 346,742,772 |
| HCFC production – stage II | 9,091,808 | 12,039,619 | 8,976,124 | 30,107,551 |
| HPMP stage I | 0 | 353,978 | 0 | 353,978 |
| HPMP stage I – additional funding | 187,112 | 627,148 | 0 | 814,260 |
| HPMP preparation (PRP) – stage II – low-volume consuming (LVC) countries | 2,218,408 | 518,850 | 44,300 | 2,781,558 |
| HPMP PRP – stage II - non-LVC countries | 1,072,336 | 890,450 | 0 | 1,962,786 |
| HPMP stage II - LVC countries | 81,798 | 268,545 | 9,067,642 | 9,417,984 |
| HPMP stage II - non-LVC countries | 5,585,329 | 7,834,674 | 11,325,242 | 24,745,246 |
| HPMP verification* | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HCFC technical assistance | 154,380 | 0 | 0 | 154,380 |
| Required for compliance subtotal | 148,562,145 | 139,002,266 | 131,281,904 | 418,846,316 |
| HFC activities |  |  |  |  |
| HFC - demonstration | 3,351,981 | 0 | 0 | 3,351,981 |
| HFC - enabling activities | 3,236,750 | 0 | 0 | 3,236,750 |
| HFC – investment | 1,378,659 | 3,937,408 | 815,425 | 6,131,493 |
| HFC activities subtotal | 7,967,390 | 3,937,408 | 815,425 | 12,720,224 |
| Standard costs |  |  |  |  |
| Compliance Assistance Programme (CAP) | 10,971,601 | 11,300,749 | 11,639,772 | 33,912,122 |
| Core unit | 5,902,741 | 5,931,915 | 5,961,294 | 17,795,949 |
| Institutional strengthening (IS) | 13,847,453 | 7,128,429 | 13,847,292 | 34,823,174 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,648,670 | 6,799,233 | 6,954,313 | 20,402,216 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 37,870,465 | 31,660,326 | 38,902,670 | 108,433,461 |
| Grand total | 194,400,000 | 174,600,000 | 171,000,000 | 540,000,000 |
| Funding distribution by agency |  |  |  |  |
| Canada | 565,584 | 0 | 0 | 565,584 |
| France | 78,769 | 0 | 692,895 | 771,664 |
| Germany | 6,490,401 | 1,038,050 | 1,988,661 | 9,517,112 |
| Italy | 750,128 | 0 | 100,927 | 851,055 |
| Japan | 366,097 | 120,232 | 90,400 | 576,729 |
| Spain | 1,192,731 | 0 | 0 | 1,192,731 |
| UNDP | 59,934,280 | 34,438,004 | 52,105,629 | 146,477,913 |
| UNEP | 34,497,185 | 21,231,719 | 32,512,121 | 88,241,025 |
| UNIDO | 50,594,306 | 64,198,079 | 43,860,902 | 158,653,288 |
| World Bank | 32,193,248 | 45,686,083 | 31,605,552 | 109,484,883 |
| HPMP verification* | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,648,670 | 6,799,233 | 6,954,313 | 20,402,216 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Funding for the preparation of HPMP verification reports for LVC countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2018 business plans

# The total funding available for 2018 amounts to US $194,400,000. Of this amount, US $73,930,598 has been approved at the 81st meeting. Funding requests submitted to the 82nd meeting amounts to US $105,866,396. If funding requests for all project proposals submitted are approved, a balance of US $14,603,006 would be available from the 2018 business plan, as shown in Table 2. The list of project proposals submitted to the 82nd meeting is contained in Annex I to the present document.

Table 2. 2018 consolidated business plan, submissions to the 82nd meeting, and balance (US $)*

| Budget items | Total value in business plan | Approvals at the 81st meeting | Submissions 82nd meeting** | Total (81st and 82nd) | Balance (above)/below |
| --- | --- | --- | --- | --- | --- |
| Bilateral agencies | 9,443,711 | 2,894,312 | 5,277,018 | 8,171,330 | 1,272,381 |
| UNDP | 59,934,280 | 13,521,504 | 52,180,460 | 65,701,964 | (5,767,684) |
| UNEP | 34,497,185 | 8,398,710 | 18,700,794 | 27,099,504 | 7,397,681 |
| UNIDO | 50,594,306 | 23,462,165 | 17,402,041 | 40,864,206 | 9,730,100 |
| World Bank | 32,193,248 | 25,653,907 | 4,216,613 | 29,870,520 | 2,322,728 |
| HPMP verification | 588,600 |  | 940,800 | 940,800 | (352,200) |
| Sub-total | 187,251,330 | 73,930,598 | 98,717,726 | 172,648,324 | 14,603,006 |
| Secretariat/ExCom/Monitoring /Treasurer | 7,148,670 |  | 7,148,670 | 7,148,670 | 0 |
| Total | 194,400,000 | 73,930,598 | 105,866,396 | 179,796,994 | 14,603,006 |

* Including core unit costs.

** As at 18 November 2018.

# The value of project proposals submitted to the 82nd meeting of US $98,717,726 is US $5,528,155 above their value in the 2018 business plan, including US $3,329,848 associated with project proposals not included in the 2018 business plan. The value of HFC phase-down activities submitted to the 82nd meeting is US $4,120,570 of which US $2,959,457 is associated with project proposals not included in the 2018 business plan.

# Project proposals with a value of US $43,602,722 that were included in the 2018 business plan were not submitted to the 82nd meeting. These proposals have been included in the Consolidated business plan of the Multilateral Fund for 2019–2021.

# All additional voluntary contributions by 17 non-Article 5 countries amounting to US $25,513,071, have been received. Since the 80th meeting, US $23,104,300 has been approved for HFC enabling activities and HFC phase-out projects, with a balance of US $2,408,771 available for programming at the 82nd meeting.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2018 to 2031 is US $618.46 million, assuming that the funding requests of MYAs submitted to the 82nd meeting will be approved in principle, as shown in Table 3.

Table 3. Forward commitments (2018–2031) (US $000)

| Description | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 108,295 | 101,862 | 118,246 | 98,157 | 58,386 | 39,606 | 27,960 | 27,944 | 32,195 | 212 | 57 | 612,919 |
| Submitted to 82nd meeting | 2,159 | 0 | 2,265 | 842 | 187 | 0 | 0 | 85 | 0 | 0 | 0 | 5,537 |
| Total | 110,454 | 101,862 | 120,510 | 98,999 | 58,572 | 39,606 | 27,960 | 28,029 | 32,195 | 212 | 57 | 618,456 |

# RECOMMENDATION

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2018–2020 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/82/23; and

## That US $4,120,570 in HFC phase-down activities were submitted to the 82nd meeting including US $2,959,457 that had not been included in the 2018–2020 business plans.

Annex I

PROJECT PROPOSALS SUBMITTED TO THE 82ND MEETING

| Country | Agency | Project title | Funds requested (US$) | Support costs requested (US$) | Total (US$) |
| --- | --- | --- | --- | --- | --- |
| Standard activities |  |  |  |  |  |
| Global | UNEP | Compliance Assistance Programme: 2019 budget | 9,974,259 | 797,941 | 10,772,200 |
| Global | World Bank | Core unit budget (2019) | 0 | 1,735,000 | 1,735,000 |
| Global | UNDP | Core unit budget (2019) | 0 | 2,083,871 | 2,083,871 |
| Global | UNIDO | Core unit budget (2019) | 0 | 2,083,871 | 2,083,871 |
| Institutional strengthening |  |  |  |  |  |
| Argentina | UNDP | Extension for institutional strengthening project (phase X: 1/2019-12/2020) | 398,806 | 27,916 | 426,722 |
| Armenia | UNIDO | Extension of institutional strengthening project (phase VI: 4/2019-3/2021) | 153,600 | 10,752 | 164,352 |
| Barbados | UNEP | Renewal of institutional strengthening project (phase VII: 1/2019-12/2020) | 149,760 | 0 | 149,760 |
| Brunei Darussalam | UNEP | Renewal of the institutional strengthening project (phase VI: 1/2019-12/2020) | 89,600 | 0 | 89,600 |
| China | UNDP | Extension of the institutional strengthening project (phase XIII: 1/2019-12/2020) | 499,200 | 34,944 | 534,144 |
| Dominican Republic (the) | UNEP | Extension of the institutional strengthening project (phase X: 1/2019-12/2020) | 171,946 | 0 | 171,946 |
| Fiji | UNEP | Extension of the institutional strengthening project (phase XI: 1/2019-12/2020) | 85,000 | 0 | 85,000 |
| Ghana | UNDP | Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020) | 178,048 | 12,463 | 190,511 |
| Iran (Islamic Republic of) | UNDP | Extension of the institutional strengthening project (phase XII: 4/2019-3/2021) | 222,094 | 15,547 | 237,641 |
| Iraq | UNEP | Extension of institutional strengthening project (phase IV: 1/2019-12/2020) | 307,200 | 0 | 307,200 |
| Jordan | World Bank | Extension of institutional strengthening project (phase XIII: 1/2019-12/2020) | 188,586 | 13,201 | 201,787 |
| Lebanon | UNDP | Extension of the institutional strengthening project (phase XI: 4/2019-3/2021) | 198,515 | 13,896 | 212,411 |
| Lesotho | UNEP | Extension of the institutional strengthening project (phase IX: 1/2019-12/2020) | 85,000 | 0 | 85,000 |
| Madagascar | UNEP | Renewal of institutional strengthening project (phase VIII: 1/2019-12/2020) | 85,000 | 0 | 85,000 |
| Malawi | UNEP | Extension of institutional strengthening project (phase XI: 1/2019-12/2020) | 85,418 | 0 | 85,418 |
| Mexico | UNIDO | Extension of institutional strengthening project (phase XIV: 7/2019-6/2021) | 316,160 | 22,131 | 338,291 |
| Mozambique | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2019-12/2020) | 103,424 | 0 | 103,424 |
| Nigeria | UNDP | Extension of the institutional strengthening project (phase X: 12/2018-11/2020) | 332,800 | 23,296 | 356,096 |
| Niue | UNEP | Extension of the institutional strengthening project (phase VII: 4/2019-3/2021) | 85,000 | 0 | 85,000 |
| Oman | UNIDO | Renewal of institutional strengthening support (phase VII: 12/2018-11/2020) | 87,638 | 6,135 | 93,773 |
| Pakistan | UNDP | Extension of the institutional strengthening project (phase X: 4/2019-3/2021) | 287,318 | 20,112 | 307,430 |
| Paraguay | UNEP | Extension of institutional strengthening project (phase VIII: 1/2019-12/2020) | 85,000 | 0 | 85,000 |
| Republic of Moldova (the) | UNEP | Extension of the institutional strengthening project (phase X: 1/2019-12/2020) | 88,748 | 0 | 88,748 |
| Sao Tome and Principe | UNEP | Extension of the institutional strengthening project (phase VI: 1/2019-12/2020) | 85,000 | 0 | 85,000 |
| Sierra Leone | UNEP | Extension of institutional strengthening project (phase VII: 1/2019-12/2020) | 109,824 | 0 | 109,824 |
| Sri Lanka | UNDP | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | 171,592 | 12,011 | 183,603 |
| Thailand | World Bank | Extension of institutional strengthening project (phase IX: 1/2019-12/2020) | 443,735 | 31,061 | 474,796 |
| Togo | UNEP | Extension of the institutional strengthening project (phase X: 1/2019-12/2020) | 85,000 | 0 | 85,000 |
| Tuvalu | UNEP | Extension of the institutional strengthening project (phase VII: 4/2019-3/2021) | 85,000 | 0 | 85,000 |
| Uganda | UNEP | Extension of the Institutional strengthening project (phase III: 1/2019-12/2020) | 85,000 | 0 | 85,000 |
| Venezuela (Bolivarian Republic of) | UNDP | Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020) | 365,414 | 25,579 | 390,993 |
| Viet Nam | UNEP | Extension of the institutional strengthening project (phase XII: 7/2019-6/2021) | 152,289 | 0 | 152,289 |
| Verification reports for HCFC phase-out management plans (HPMPs) |  |  |  |  |  |
| Albania | UNIDO | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 2,700 | 32,700 |
| Bahamas (the) | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Belize | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Cuba | UNDP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 2,700 | 32,700 |
| Eritrea | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Fiji | UNDP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 2,700 | 32,700 |
| Gambia (the) | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Grenada | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Guinea-Bissau | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Lao People’s Democratic Republic (the) | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Madagascar | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Malawi | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Mongolia | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Nepal | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Niger (the) | UNIDO | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 2,700 | 32,700 |
| Palau | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Saint Kitts and Nevis | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Saint Lucia | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Samoa | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Sao Tome and Principe | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Serbia | UNIDO | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 2,700 | 32,700 |
| Solomon Islands | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Sri Lanka | UNDP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 2,700 | 32,700 |
| Tonga | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Turkmenistan | UNIDO | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 2,700 | 32,700 |
| Uganda | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| United Republic of Tanzania (the) | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Zambia | UNEP | Verification report on the implementation of the HCFC phase-out management plan | 30,000 | 3,900 | 33,900 |
| Stage I of HPMPs |  |  |  |  |  |
| Bosnia and Herzegovina | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (activities in the refrigeration servicing sector including policy actions) | 31,000 | 2,170 | 33,170 |
| Botswana | UNIDO | HCFC phase-out management plan (stage I, second tranche) | 140,000 | 9,800 | 149,800 |
| Botswana | UNEP | HCFC phase-out management plan (stage I, second tranche) | 90,000 | 11,700 | 101,700 |
| Brunei Darussalam | UNDP | HCFC phase-out management plan (stage I, third tranche) | 33,000 | 2,970 | 35,970 |
| Brunei Darussalam | UNEP | HCFC phase-out management plan (stage I, third tranche) | 7,000 | 910 | 7,910 |
| Chad | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | 45,000 | 5,850 | 50,850 |
| Cuba | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | 100,000 | 7,500 | 107,500 |
| Ecuador | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) | 86,500 | 6,487 | 92,987 |
| Ecuador | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | 25,000 | 3,250 | 28,250 |
| Egypt | UNIDO | HCFC phase-out management plan (stage I, third tranche) (enabling activities in the refrigeration and air-conditioning sector) | 232,575 | 17,443 | 250,018 |
| Egypt | UNDP | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | 716,400 | 53,730 | 770,130 |
| Equatorial Guinea | UNIDO | HCFC phase-out management plan (stage I, third tranche) | 60,000 | 5,400 | 65,400 |
| Equatorial Guinea | UNEP | HCFC phase-out management plan (stage I, third tranche) | 45,000 | 5,850 | 50,850 |
| Gambia (the) | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | 21,000 | 2,730 | 23,730 |
| Libya | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 190,893 | 13,362 | 204,255 |
| Rwanda | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | 30,000 | 3,900 | 33,900 |
| Saint Lucia | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | 9,200 | 1,196 | 10,396 |
| The former Yugoslav Republic of Macedonia | UNIDO | HCFC phase-out management plan (phase I, eighth tranche) | 131,000 | 9,825 | 140,825 |
| Stage II of HPMPs |  |  |  |  |  |
| Brazil | UNIDO | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector) | 2,647,057 | 185,294 | 2,832,351 |
| Brazil | UNDP | HCFC phase-out management plan (stage II, third tranche) (foam sector) | 6,778,396 | 474,488 | 7,252,884 |
| Brazil | Germany | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 2,363,637 | 263,059 | 2,626,696 |
| Brazil | UNDP | HCFC phase-out management plan (stage II, third tranche) (regulatory actions and project monitoring) | 390,000 | 27,300 | 417,300 |
| Cameroon | UNIDO | HCFC phase-out management plan (stage II, first tranche) | 517,750 | 36,243 | 553,993 |
| China | UNIDO | HCFC phase-out management plan (stage II, third tranche) (extruded polystyrene foam sector plan) | 8,000,000 | 560,000 | 8,560,000 |
| China | UNDP | HCFC phase-out management plan (stage II, third tranche) (industrial and commercial refrigeration and air-conditioning sector plan) | 12,000,000 | 840,000 | 12,840,000 |
| China | Japan | HCFC phase-out management plan (stage II, third tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | 80,000 | 10,400 | 90,400 |
| China | Germany | HCFC phase-out management plan (stage II, third tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | 300,000 | 36,000 | 336,000 |
| China | UNEP | HCFC phase-out management plan (stage II, third tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | 3,270,000 | 361,431 | 3,631,431 |
| China | UNDP | HCFC phase-out management plan (stage II, third tranche) (solvent sector plan) | 5,549,492 | 388,464 | 5,937,956 |
| Dominican Republic (the) | UNDP | HCFC phase-out management plan (stage II, second tranche) | 574,200 | 40,194 | 614,394 |
| Dominican Republic (the) | UNEP | HCFC phase-out management plan (stage II, second tranche) | 100,000 | 13,000 | 113,000 |
| India | UNDP | HCFC phase-out management plan (stage II, second tranche) (air-conditioning manufacturing sector plan) | 1,756,000 | 122,920 | 1,878,920 |
| India | UNDP | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector plan) | 11,708,000 | 819,560 | 12,527,560 |
| India | UNDP | HCFC phase-out management plan (stage II, second tranche) (project management and monitoring) | 1,144,000 | 80,080 | 1,224,080 |
| India | Germany | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector plan) | 2,000,000 | 223,922 | 2,223,922 |
| India | UNEP | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector plan) | 300,000 | 36,333 | 336,333 |
| Oman | UNIDO | HCFC phase-out management plan (stage II, second tranche) | 50,000 | 3,500 | 53,500 |
| Oman | UNEP | HCFC phase-out management plan (stage II, second tranche) | 59,500 | 7,735 | 67,235 |
| Panama | UNDP | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 385,800 | 27,006 | 412,806 |
| Sudan (the) | UNIDO | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 330,441 | 23,131 | 353,572 |
| Thailand | World Bank | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector and project management unit) | 814,470 | 57,013 | 871,483 |
| Thailand | World Bank | HCFC phase-out management plan (stage II, first tranche) (spary foam sector) | 685,530 | 47,987 | 733,517 |
| Uruguay | UNDP | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 422,889 | 29,602 | 452,491 |
| Uruguay | UNDP | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector and implementation and monitoring) | 257,000 | 17,990 | 274,990 |
| Project preparation for stage II of HPMPs |  |  |  |  |  |
| Afghanistan | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 1,400 | 21,400 |
| Afghanistan | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 5,200 | 45,200 |
| Belize | UNDP | Preparation of a HCFC phase-out management plan (stage II) | 10,000 | 700 | 10,700 |
| Belize | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| Bolivia (Plurinational State of) | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 2,100 | 32,100 |
| Bosnia and Herzegovina | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 2,100 | 32,100 |
| Brunei Darussalam | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 3,900 | 33,900 |
| Chad | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 1,400 | 21,400 |
| Chad | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 5,200 | 45,200 |
| Cuba | UNDP | Preparation of a HCFC phase-out management plan (stage II) | 60,000 | 4,200 | 64,200 |
| Ecuador | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| Ecuador | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 2,800 | 42,800 |
| El Salvador | UNDP | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 2,800 | 42,800 |
| Fiji | UNDP | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 2,100 | 32,100 |
| Gambia (the) | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 10,000 | 700 | 10,700 |
| Gambia (the) | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| Grenada | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 3,900 | 33,900 |
| Guatemala | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 15,000 | 1,950 | 16,950 |
| Guatemala | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 25,000 | 1,750 | 26,750 |
| Honduras | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| Honduras | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 2,800 | 42,800 |
| Lao People’s Democratic Republic (the) | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 3,900 | 33,900 |
| Libya | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 80,000 | 5,600 | 85,600 |
| Libya | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 70,000 | 4,900 | 74,900 |
| Mongolia | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 3,900 | 33,900 |
| Montenegro | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 2,100 | 32,100 |
| Nepal | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 3,900 | 33,900 |
| Niger (the) | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| Niger (the) | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 2,800 | 42,800 |
| Paraguay | UNDP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 1,400 | 21,400 |
| Paraguay | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 5,200 | 45,200 |
| Saint Lucia | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 10,000 | 700 | 10,700 |
| Saint Lucia | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| Serbia | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 2,100 | 32,100 |
| South Africa | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 90,000 | 6,300 | 96,300 |
| Sri Lanka | UNDP | Preparation of a HCFC phase-out management plan (stage II) | 40,000 | 2,800 | 42,800 |
| The former Yugoslav Republic of Macedonia | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 2,100 | 32,100 |
| Trinidad and Tobago | UNDP | Preparation of a HCFC phase-out management plan (stage II) | 60,000 | 4,200 | 64,200 |
| Turkmenistan | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 30,000 | 2,100 | 32,100 |
| Uganda | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 10,000 | 700 | 10,700 |
| Uganda | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| United Republic of Tanzania (the) | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | 10,000 | 700 | 10,700 |
| United Republic of Tanzania (the) | UNEP | Preparation of a HCFC phase-out management plan (stage II) | 20,000 | 2,600 | 22,600 |
| HFC - Enabling activities |  |  |  |  |  |
| Bahamas (the) | UNEP | Enabling activities for HFC phase-down | 95,000 | 6,650 | 101,650 |
| Bolivia (Plurinational State of) | UNEP | Enabling activities for HFC phase-down | 150,000 | 10,500 | 160,500 |
| Brunei Darussalam | UNEP | Enabling activities for HFC phase-down | 150,000 | 10,500 | 160,500 |
| Cabo Verde | UNEP | Enabling activities for HFC phase-down | 95,000 | 6,650 | 101,650 |
| Cook Islands (the) | UNEP | Enabling activities for HFC phase-down | 50,000 | 3,500 | 53,500 |
| Iran (Islamic Republic of) | UNEP | Enabling activities for HFC phase-down | 95,000 | 6,650 | 101,650 |
| Iran (Islamic Republic of) | UNDP | Enabling activities for HFC phase-down | 155,000 | 10,850 | 165,850 |
| Jordan | UNIDO | Enabling activities for HFC phase-down | 150,000 | 10,500 | 160,500 |
| Mauritius | UNEP | Enabling activities for HFC phase-down | 150,000 | 10,500 | 160,500 |
| Qatar | UNEP | Enabling activities for HFC phase-down | 50,000 | 3,500 | 53,500 |
| Qatar | UNIDO | Enabling activities for HFC phase-down | 100,000 | 7,000 | 107,000 |
| South Africa | UNIDO | Enabling activities for HFC phase-down | 240,000 | 16,800 | 256,800 |
| Timor-Leste | UNEP | Enabling activities for HFC phase-down | 50,000 | 3,500 | 53,500 |
| HFC - Investment activities |  |  |  |  |  |
| China | UNDP | Conversion from C5+HFC-245fa to C5+HFOs in a domestic refrigerator manufacturer (Hisense Kelon) | 1,275,000 | 89,250 | 1,364,250 |
| Ecuador | UNIDO | Conversion of domestic and commercial refrigerator manufacturing at Ecasa from the use of HFC-134a and R--404A as the refrigerants to propane (R-290) and isobutane (R-600a) | 199,480 | 17,953 | 217,433 |
| Egypt | UNDP | Conversion of discontinuous panel manufacturing facility from HFC-134a to HFO blowing agent at Army Factory | 224,694 | 20,222 | 244,916 |
| Thailand | World Bank | Conversion from HFC to propane (R-290) and isobutene (R-600a) as a refrigerant in manufacturing commercial refrigeration appliances in Pattana Intercool Co. Ltd. | 183,514 | 16,516 | 200,030 |
| Zimbabwe | UNDP | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) | 426,954 | 29,887 | 456,841 |
| Total |  |  | 86,348,346 | 12,369,380 | 98,717,726 |

Project preparation for stage II of the HPMP for Afghanistan (UNIDO) and Belize (UNDP); HFC enabling activities for Cook Islands (UNEP), Islamic Republic of Iran (UNEP), Jordan (UNIDO), Mauritius (UNEP), Qatar (UNEP and UNIDO) and South Africa (UNIDO); HFC investment projects for China (UNDP), Egypt (UNDP) and Zimbabwe (UNDP); and IS project for Mexico (UNIDO).

These activities include: 111 HCFC activities for 66 countries (US $33.85 million), 11 HFC-related activities for 10 countries (US $4.48 million) and 36 IS activities (US $5.27 million).

UNEP/OzL.Pro/ExCom/82/25

Australia, Canada, Denmark, Finland, France, Germany, Ireland, Italy, Japan, Luxembourg, Netherlands (the), New Zealand, Norway, Sweden, Switzerland, the United Kingdom of Great Britain and Northern Ireland and the United States of America.